## DOER REPORT 4_15_24
DG Interconnection Tracking and Reporting Template
Utility Timelines
Reporting Period: |  | from | 2009-01-01 | to | 2024-04-15
Date Filed: |  | 2024-04-15
Force Majeure Reporting |  |  |  | Start Date | End Date | Explanation
Enter Dates (inclusive) of Force Majeure Events with "Clock" Stoppage |  |  | Event #1 | 2012-10-26 | 2012-11-16 | Storm event |  |  |  | 16
|  |  | Event #2 | 2013-02-08 | 2013-02-13 | Storm event |  |  |  | 4 | [30 empty] | * added Complex
|  |  | Event #3 | 2013-03-06 | 2013-03-08 | Storm event |  |  |  | 3
|  |  | Event #4 | 2017-10-30 | 2017-11-03 | Storm event |  |  |  | 5
|  |  | Event #5 | 2018-03-02 | 2018-03-15 | Storm event |  |  |  | 10
|  |  | Event #6 | 2020-08-05 | 2020-08-09 | Storm event |  |  |  | 3 | [27 empty] | Heading Revised |  |  |  | Heading Revised | [10 empty] | Heading Revised
|  |  | Total Workdays (calculated) |  | 41 |  |  |  |  | 41
Application and Site Information | [6 empty] | Application Receipt |  |  |  |  | Screen Review |  |  |  |  | Supplemental Review |  |  |  |  | Standard Process Initial Review |  |  |  |  | Impact Study |  |  |  |  | Detailed Study |  |  |  |  | IA and Pre-Construction Information | [5 empty] | Construction |  |  |  |  | Witness Test |  | Authorization and Misc Information
Company Name | City/Town | Facility ID (if any) | ZIP Code | Design Capacity (kW) | Fuel Type (Solar, Wind, etc) | Circuit Name | Date Application Received | Date Application Deemed Complete | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Review of Screens Study Begun | Date Review of Screens Study Completed | Total Time Lapsed (Workdays) calculated value2 | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer2 | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage2 | Date Supplemental Review Begun | Date Supplemental Review Complete | Total Time Lapsed (Workdays) calculated value5 | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer6 | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage7 | Date Standard Process Initial Review Begun | Date Standard Process Initial Review Complete | Total Time Lapsed (Workdays) calculated value8 | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer9 | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage10 | Date Impact Study Begun | Date Impact Study Sent | Total Time Lapsed (Workdays) calculated value11 | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer12 | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage13 | Date Detailed Study Begun | Date Detailed Study Sent | Total Time Lapsed (Workdays) calculated value14 | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer15 | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage16 | Date Interconnection Agreement Sent | Date ISA & Payment Received | Estimated In-Service Date | System Modification Required | Expedited/ Standard / Complex Project | Construction Timeline Commitment (Workdays) | Date Construction Begun | Date Construction Completed | Total Time Lapsed (Workdays) calculated value17 | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer18 | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage19 | Date Witness Test Scheduled | Date Witness Test Completed | Authorization to Interconnect | STATUS | Private/Gov't | Net Metered? (Y/N)
National Grid | SOUTH EASTON | 163772 | 2375 | 250 | Natural Gas | 07_92W54 | 2009-01-20 | 2009-03-12 | [28 empty] | 2009-03-12 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | MARLBOROUGH | 163782 | 1752 | 75 | Natural Gas | 05_311W1 | 2009-01-22 | 2009-09-24 | [28 empty] | 2009-09-24 |  |  |  | EXP | [9 empty] | Connected |  | Yes
National Grid | EVERETT | 163579 | 2148 | 75 | Solar | 12_2310 | 2009-02-05 | 2009-04-17 | [28 empty] | 2009-04-17 |  |  |  | EXP | [9 empty] | Connected |  | Yes
National Grid | WORCESTER | 163581 | 1602 | 100 | Solar | 01_HT40 | 2009-02-06 | 2009-04-06 | [28 empty] | 2009-04-06 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | LYNN | 165168 | 1901 | 75 | Solar | 12_1388 | 2009-04-06 01:00 | 2009-06-11 | [28 empty] | 2009-06-11 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | TEWKSBURY | 163631 | 1876 | 95 | Solar | 14_70L1 | 2009-04-13 01:00 | 2009-06-11 | [28 empty] | 2009-06-11 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | GARDNER | 163642 | 1440 | 95 | Solar | 01_607W3 | 2009-04-22 01:00 | 2009-06-05 | [28 empty] | 2009-06-05 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | NEWBURYPORT | 163654 | 1950 | 392 | Solar | 14_36L2 | 2009-05-07 01:00 | 2009-06-11 | [28 empty] | 2009-06-11 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | NEWBURYPORT | 163655 | 1950 | 95 | Solar | 14_36L2 | 2009-05-07 01:00 | 2009-06-11 | [28 empty] | 2009-06-11 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | ATHOL | 174501 | 1331 | 230 | Hydro | 09_702W3 | 2009-05-08 01:00 | 2009-05-11 | 28 | 0 | 28 | [25 empty] | 2010-05-12 |  | 2012-10-31 |  | STD | [6 empty] | 2012-10-22 | 2012-10-22 | 2012-10-22 | Connected |  | No
National Grid | LYNN | 163662 | 1905 | 325 | Bio Gas | 12_21J27 | 2009-05-15 01:00 | 2009-11-17 | [28 empty] | 2009-11-17 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | FRANKLIN | 163663 | 2038 | 325 | Bio Gas | 05_344W2 | 2009-05-15 01:00 | 2009-11-09 | [28 empty] | 2009-11-09 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | GARDNER | 163681 | 1140 | 1620 | Landfill Gas | 01_607W1 | 2009-06-03 01:00 | 2009-12-09 | [28 empty] | 2009-12-09 |  |  |  | EXP | [9 empty] | Terminated |  | Yes
National Grid | REVERE | 163698 | 2151 | 1000 | Solar | 12_7W4 | 2009-06-12 01:00 | 2010-01-15 | [28 empty] | 2010-01-15 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | EVERETT | 163702 | 2149 | 500 | Solar | 12_10J6 | 2009-06-12 01:00 | 2010-01-15 | [28 empty] | 2010-01-15 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | HAVERHILL | 163703 | 1832 | 1000 | Solar | 14_48L2 | 2009-06-12 01:00 | 2010-01-15 | [28 empty] | 2010-01-15 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | NORTHBRIDGE | 163704 | 1588 | 1000 | Solar | 05_320W5 | 2009-06-12 01:00 | 2010-01-14 | [28 empty] | 2010-01-14 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | CHARLEMONT | 163699 | 1339 | 900 | Wind | 09_1019W1 | 2009-06-17 01:00 | 2010-11-19 | [28 empty] | 2010-11-19 |  |  |  | STD | [9 empty] | Connected |  | No
National Grid | BRIDGEWATER | 165169 | 2324 | 112 | Solar | 07_912W55 | 2009-06-18 01:00 | 2009-09-24 | [28 empty] | 2009-09-24 |  |  |  | EXP | [9 empty] | Connected |  | Yes
National Grid | NORTHAMPTON | 165170 | 1061 | 425 | Natural Gas | 09_909W1 | 2009-06-25 01:00 | 2009-01-26 | [28 empty] | 2009-01-26 |  |  |  | EXP | [9 empty] | Connected |  | Yes
National Grid | BILLERICA | 163718 | 1821 | 142 | Solar | 14_18L2 | 2009-07-14 01:00 | 2009-09-22 | [28 empty] | 2009-09-22 |  |  |  | EXP | [9 empty] | Connected |  | Yes
National Grid | SALEM | 163722 | 1970 | 326 | Solar | 12_2W2 | 2009-07-14 01:00 | 2010-01-17 | [28 empty] | 2010-01-17 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | MALDEN | 163610 | 2148 | 60 | Solar | 12_37W7 | 2009-07-16 01:00 | 2009-11-11 | [28 empty] | 2009-11-11 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | MALDEN | 163611 | 2148 | 60 | Solar | 12_37W7 | 2009-07-16 01:00 | 2009-11-11 | [28 empty] | 2009-11-11 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | SALEM | 163253 | 1970 | 68.04 | Solar | 12_2370 | 2009-07-22 01:00 | 2009-10-26 | [28 empty] | 2009-10-26 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | WORCESTER | 164348 | 1610 | 75 | Natural Gas | 01_4J324 | 2009-08-11 01:00 | 2009-11-17 | [28 empty] | 2009-11-17 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 164351 | 1609 | 75 | Natural Gas | 01_HT14 | 2009-08-11 01:00 | 2009-11-17 | [28 empty] | 2009-11-17 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 164352 | 1603 | 75 | Natural Gas | 01_HT41 | 2009-08-11 01:00 | 2009-11-17 | [28 empty] | 2009-11-17 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTFORD | 164403 | 1886 | 95 | Solar | 14_58L2 | 2009-09-10 01:00 | 2009-12-29 | [28 empty] | 2009-12-29 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | ORANGE | 164453 | 1364 | 95 | Solar | 09_702W3 | 2009-09-17 01:00 | 2009-12-23 | [28 empty] | 2009-12-23 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | ORANGE | 164454 | 1364 | 95 | Solar | 09_702W3 | 2009-09-17 01:00 | 2009-11-06 | [28 empty] | 2009-11-06 |  |  |  | EXP | [9 empty] | Connected |  | Yes
National Grid | WORCESTER | 164557 | 1604 | 86 | Solar | 01_9J310 | 2009-10-01 01:00 | 2009-12-07 | [28 empty] | 2009-12-07 |  |  |  | EXP | [9 empty] | Connected |  | Yes
National Grid | MEDFORD | 174795 | 2155 | 50 | Solar | 12_37W2 | 2009-10-02 01:00 | 2009-10-06 | 10 | 0 | 10 | [25 empty] | 2009-12-16 |  | 2012-12-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ATTLEBORO | 163398 | 2703 | 95 | Solar | 05_2J3 | 2009-10-12 01:00 | 2010-02-17 | [28 empty] | 2010-02-17 |  |  |  | EXP | [9 empty] | Connected |  | Yes
National Grid | METHUEN | 163851 | 1844 | 95 | Solar | 14_63L2 | 2009-10-12 01:00 | 2010-06-18 | [28 empty] | 2010-06-18 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | HAVERHILL | 163916 | 1830 | 60 | Natural Gas | 14_31J6 | 2009-10-27 01:00 | 2010-05-17 | [28 empty] | 2010-05-17 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | FALL RIVER | 163917 | 2720 | 82 | Solar | 05_28W41 | 2009-10-27 01:00 | 2010-02-18 | [28 empty] | 2010-02-18 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | SEEKONK | 164011 | 2771 | 100 | Solar | 05_7L1 | 2009-11-16 | 2010-02-16 | [28 empty] | 2010-02-16 |  |  |  | EXP | [9 empty] | Connected |  | Yes
National Grid | WORCESTER | 174500 | 1605 | 300 | Natural Gas | 01_27W4 | 2009-11-17 | 2009-11-24 | 16 | 0 | 16 | [25 empty] | 2010-01-25 |  | 2012-10-31 |  | EXP | [6 empty] | 2012-09-18 | 2012-09-18 | 2010-07-07 | Connected |  | Yes
National Grid | CLINTON | 164015 | 1510 | 60 | Solar | 01_216W5 | 2009-11-18 | 2010-03-02 | [28 empty] | 2010-03-02 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | SHIRLEY | 164064 | 1464 | 95 | Solar | 01_227W3 | 2009-12-02 | 2010-03-25 | [28 empty] | 2010-03-25 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | SHIRLEY | 164065 | 1464 | 95 | Solar | 01_227W3 | 2009-12-02 | 2010-03-25 | [28 empty] | 2010-03-25 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | SHIRLEY | 164066 | 1464 | 95 | Solar | 01_227W3 | 2009-12-02 | 2010-03-25 | [28 empty] | 2010-03-25 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | CHESHIRE | 164105 | 1225 | 57 | Solar | 09_1021W2 | 2009-12-07 | 2010-03-02 | [28 empty] | 2010-03-02 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | FOXBOROUGH | 165123 | 2035 | 100 | Solar | 05_349W1 | 2009-12-07 | 2010-03-24 | [28 empty] | 2010-03-24 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | FOXBOROUGH | 165124 | 2035 | 75 | Solar | 05_349W1 | 2009-12-07 | 2010-03-24 | [28 empty] | 2010-03-24 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | FOXBOROUGH | 165125 | 2035 | 100 | Solar | 05_3424W1 | 2009-12-07 | 2010-03-24 | [28 empty] | 2010-03-24 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | FOXBOROUGH | 165126 | 2035 | 75 | Solar | 05_349W1 | 2009-12-07 | 2010-03-24 | [28 empty] | 2010-03-24 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | FOXBOROUGH | 165127 | 2035 | 100 | Solar | 05_349W1 | 2009-12-07 | 2010-03-24 | [28 empty] | 2010-03-24 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | FOXBOROUGH | 165128 | 2035 | 75 | Solar | 05_3424W3 | 2009-12-07 | 2010-03-24 | [28 empty] | 2010-03-24 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | FALL RIVER | 163247 | 2720 | 75 | Solar | 05_28W40 | 2009-12-08 | 2010-01-27 | [28 empty] | 2010-01-27 | 2009-12-16 |  |  | EXP | [9 empty] | Connected |  | No
National Grid | WESTFORD | 174583 | 1886 | 1000 | Solar | 14_2387 | 2009-12-16 | 2009-12-22 | 0 | 0 | 0 | [25 empty] | 2011-08-04 | 2009-12-16 | 2012-10-31 | Yes | STD | [6 empty] | 2013-09-17 | 2013-09-17 | 2012-09-17 | Connected |  | No
National Grid | WESTFORD | 174606 | 1886 | 1000 | Solar | 14_2387 | 2009-12-16 | 2009-12-18 | 2 | 0 | 2 | [25 empty] | 2011-08-23 | 2009-12-16 | 2012-04-05 | Yes | STD | [6 empty] | 2012-08-03 | 2012-08-03 | 2012-04-05 | Connected |  | No
National Grid | WESTFORD | 174607 | 1886 | 1000 | Solar | 14_2387 | 2009-12-16 | 2009-12-22 | 0 | 0 | 0 | [25 empty] | 2011-08-23 | 2009-12-16 | 2012-04-05 | Yes | STD | [6 empty] | 2012-08-03 | 2012-08-03 | 2012-04-05 | Connected |  | No
National Grid | WESTFORD | 174608 | 1886 | 1000 | Solar | 14_2387 | 2009-12-16 | 2009-12-18 | 2 | 0 | 2 | [25 empty] | 2011-08-23 |  | 2012-04-05 | Yes | STD | [6 empty] | 2012-08-03 | 2012-08-03 | 2012-04-05 | Connected |  | No
National Grid | WEST STOCKBRIDGE | 164113 | 1266 | 60 | Solar | 09_1109W3 | 2009-12-29 | 2010-02-23 | [28 empty] | 2010-02-23 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | GREAT BARRINGTON | 164114 | 1230 | 82 | Solar | 09_1109W1 | 2009-12-29 | 2010-03-15 | [28 empty] | 2010-03-15 |  |  |  | EXP | [9 empty] | Connected |  | Yes
National Grid | BROCKTON | 164155 | 2302 | 60 | Natural Gas | 07_91W41 | 2010-01-11 | 2010-04-22 | [28 empty] | 2010-04-22 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | GARDNER | 163641 | 1440 | 3300 | Wind | 01_607W3 | 2010-01-14 | 2011-02-10 | [28 empty] | 2011-02-10 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | WORCESTER | 164163 | 1610 | 60 | Natural Gas | 01_3J373 | 2010-01-27 | 2010-04-28 | [28 empty] | 2010-04-28 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | LAWRENCE | 164165 | 1841 | 85 | Natural Gas | 14_53J3 | 2010-02-04 | 2010-04-22 | [28 empty] | 2010-04-22 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | HARVARD | 164208 | 1451 | 60 | Solar | 01_201W2 | 2010-02-17 | 2010-05-27 | [28 empty] | 2010-05-27 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | HARVARD | 164209 | 1451 | 82 | Solar | 01_201W2 | 2010-02-17 | 2010-05-27 | [28 empty] | 2010-05-27 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | ATTLEBORO | 164254 | 2703 | 300 | Solar | 05_9L3 | 2010-02-22 | 2010-06-07 | [28 empty] | 2010-06-07 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | LEOMINSTER | 164255 | 1453 | 250 | Solar | 01_219W4 | 2010-02-22 | 2010-06-07 | [28 empty] | 2010-06-07 | 2010-02-22 |  |  | EXP | [9 empty] | Connected |  | No
National Grid | SCITUATE | 174605 | 2066 | 1500 | Wind | 07_915W36 | 2010-02-22 | 2010-02-24 | 40 | 0 | 40 | [25 empty] | 2010-10-26 |  | 2012-03-29 | Yes | STD |  | 2011-10-18 | 2012-03-15 | 100 | 0 | 100 | 2012-08-03 | 2012-08-03 | 2012-03-29 | Connected |  | No
National Grid | RUTLAND | 164216 | 1543 | 300 | Bio Gas | 01_55W1 | 2010-02-23 | 2010-07-20 | [28 empty] | 2010-07-20 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | NORTH BILLERICA | 164257 | 1862 | 135 | Solar | 14_70L5 | 2010-02-23 | 2010-06-02 | [28 empty] | 2010-06-02 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | FRANKLIN | 164258 | 2038 | 400 | Solar | 05_348W6 | 2010-02-23 | 2010-07-09 | [28 empty] | 2010-07-09 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | BILLERICA | 164262 | 1821 | 75 | Solar | 14_70L6 | 2010-02-25 | 2010-06-30 | [28 empty] | 2010-06-30 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | SWANSEA | 164304 | 2777 | 82 | Solar | 05_11W81 | 2010-02-26 | 2010-05-28 | [28 empty] | 2010-05-28 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | EASTON | 164305 | 2375 | 60 | Solar | 07_92W44 | 2010-03-01 | 2010-05-12 | [28 empty] | 2010-05-12 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | MARLBOROUGH | 164306 | 1752 | 555 | Natural Gas | 05_311W6 | 2010-03-01 | 2010-06-25 | [28 empty] | 2010-06-25 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | HARVARD | 164310 | 1451 | 200 | Solar | 01_201W2 | 2010-03-12 | 2010-07-20 | [28 empty] | 2010-07-20 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | NORTH ANDOVER | 164357 | 1845 | 328 | Solar | 14_2358 | 2010-03-22 01:00 | 2011-01-24 | [28 empty] | 2011-01-24 |  |  |  | EXP | [9 empty] | Connected |  | Yes
National Grid | NORTH ANDOVER | 164358 | 1845 | 60 | Solar | 14_2326 | 2010-03-22 01:00 | 2011-01-24 | [28 empty] | 2011-01-24 | 2010-03-23 01:00 |  |  | EXP | [9 empty] | Connected |  | No
National Grid | NORTHAMPTON | 174724 | 1060 | 3500 | Natural Gas | 09_S100 | 2010-03-23 01:00 | 2010-03-30 | 38 | 0 | 38 | [25 empty] | 2012-12-12 |  | 2012-12-31 |  | STD | [6 empty] | 2013-08-28 | 2013-08-28 | 2013-12-16 | Connected |  | No
National Grid | NORTH CHELMSFORD | 164405 | 1863 | 500 | Solar | 14_73L1 | 2010-04-05 01:00 | 2010-07-07 | [28 empty] | 2010-07-07 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | HAVERHILL | 164410 | 1835 | 82 | Solar | 14_43L8 | 2010-04-12 01:00 | 2010-07-09 | [28 empty] | 2010-07-09 |  |  |  | EXP | [9 empty] | Connected |  | Yes
National Grid | WORCESTER | 164457 | 1609 | 60 | Solar | 01_23W2 | 2010-04-19 01:00 | 2010-08-31 | [28 empty] | 2010-08-31 |  |  |  | EXP | [9 empty] | Connected |  | Yes
National Grid | FALL RIVER | 164514 | 2721 | 60 | Solar | 05_115W53 | 2010-04-28 01:00 | 2010-08-23 | [28 empty] | 2010-08-23 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | ORANGE | 164515 | 1364 | 142 | Solar | 09_705W3 | 2010-05-05 01:00 | 2011-02-02 | [28 empty] | 2011-02-02 |  |  |  | EXP | [9 empty] | Connected |  | Yes
National Grid | AYER | 164517 | 1432 | 95 | Solar | 01_201W3 | 2010-05-05 01:00 | 2010-10-13 | [28 empty] | 2010-10-13 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NANTUCKET | 164518 | 2554 | 100 | Wind | 04_101L4 | 2010-05-07 01:00 | 2010-08-20 | [28 empty] | 2010-08-20 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | BEVERLY | 164561 | 1915 | 95 | Solar | 12_18L1 | 2010-05-11 01:00 | 2010-08-19 | [28 empty] | 2010-08-19 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | SHIRLEY | 164562 | 1464 | 95 | Solar | 01_227W3 | 2010-05-14 01:00 | 2010-08-23 | [28 empty] | 2010-08-23 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | LOWELL | 163813 | 1852 | 52.7 | Solar | 14_3L5 | 2010-05-19 01:00 | 2010-11-11 | [28 empty] | 2010-11-11 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | WORCESTER | 163823 | 1602 | 60 | Natural Gas | 01_HT40 | 2010-05-19 01:00 | 2010-12-16 | [28 empty] | 2010-12-16 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | LOWELL | 164570 | 1852 | 135 | Solar | 14_20L3 | 2010-05-19 01:00 | 2010-07-30 | [28 empty] | 2010-07-30 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | LOWELL | 164572 | 1854 | 100 | Solar | 14_77L1 | 2010-05-19 01:00 | 2010-08-31 | [28 empty] | 2010-08-31 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | WEBSTER | 163814 | 1570 | 250 | Solar | 01_412L6 | 2010-05-21 01:00 | 2010-07-13 | [28 empty] | 2010-07-13 |  |  |  | EXP | [9 empty] | Terminated |  | No
National Grid | WARREN | 163816 | 1083 | 95 | Solar | 09_516L3 | 2010-05-25 01:00 | 2010-09-03 | [28 empty] | 2010-09-03 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WEST WARREN | 163817 | 1092 | 95 | Solar | 09_516L3 | 2010-05-25 01:00 | 2010-07-13 | [28 empty] | 2010-07-13 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WARREN | 163818 | 1083 | 95 | Solar | 01_525L2 | 2010-05-25 01:00 | 2010-09-20 | [28 empty] | 2010-09-20 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | GARDNER | 163819 | 1440 | 79.8 | Solar | 01_607W3 | 2010-05-26 01:00 | 2010-07-07 | [28 empty] | 2010-07-07 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | ASHLEY FALLS | 163873 | 1222 | 280 | Bio Gas | 09_1108W2 | 2010-06-02 01:00 | 2011-06-20 | [28 empty] | 2011-06-20 |  |  |  | EXP | [9 empty] | Connected |  | Yes
National Grid | SHIRLEY | 163876 | 1464 | 95 | Solar | 01_227W3 | 2010-06-04 01:00 | 2010-08-23 | [28 empty] | 2010-08-23 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | TYNGSBOROUGH | 163877 | 1879 | 100 | Solar | 14_211L1 | 2010-06-04 01:00 | 2010-09-28 | [28 empty] | 2010-09-28 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | NEWBURYPORT | 163981 | 1950 | 120 | Solar | 14_60L3 | 2010-06-09 01:00 | 2010-09-21 | [28 empty] | 2010-09-21 | 2010-06-10 01:00 |  |  | EXP | [9 empty] | Connected |  | Yes
National Grid | GARDNER | 174498 | 1440 | 3300 | Wind | 01_607W4 | 2010-06-10 01:00 | 2010-06-15 | 15 | 0 | 15 | [25 empty] | 2012-12-12 |  | 2012-10-31 | Yes | STD | [6 empty] | 2013-04-12 | 2013-04-12 | 2013-04-04 | Connected |  | No
National Grid | OXFORD | 164071 | 1540 | 300 | Natural Gas | 01_412L3 | 2010-07-08 01:00 | 2010-11-26 | [28 empty] | 2010-11-26 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | MARLBOROUGH | 164068 | 1752 | 500 | Solar | 05_317W1 | 2010-07-09 01:00 | 2010-09-22 | [28 empty] | 2010-09-22 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | WESTBOROUGH | 164070 | 1581 | 266 | Solar | 05_312W3 | 2010-07-12 01:00 | 2010-11-26 | [28 empty] | 2010-11-26 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | SHIRLEY | 164079 | 1464 | 190 | Solar | 01_227W3 | 2010-07-20 01:00 | 2010-09-17 | [28 empty] | 2010-09-17 |  |  |  | EXP | [9 empty] | Connected |  | Yes
National Grid | NORTON | 174346 | 2766 | 26 | Solar | 05_8L2 | 2010-07-28 01:00 | 2010-07-28 | 28 | 0 | 28 | [25 empty] | 2012-12-12 |  | 2012-10-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MARLBOROUGH | 164166 | 1752 | 150 | Natural Gas | 05_318W5 | 2010-07-29 01:00 | 2010-12-08 | [28 empty] | 2010-12-08 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | AMESBURY | 174723 | 1913 | 35 | Solar | 14_66L1 | 2010-07-29 01:00 | 2010-07-29 | 3 | 0 | 3 | [27 empty] | 2018-06-29 |  | EXP | [6 empty] | 2017-03-13 | 2017-03-13 |  | Withdrawn |  | Yes
National Grid | EAST DOUGLAS | 174722 | 1516 | 14 | Solar | 05_320W2 | 2010-08-03 01:00 | 2010-08-26 | 0 | 0 | 0 | [25 empty] | 2010-08-03 |  | 2012-12-31 |  | EXP | [6 empty] | 2012-11-29 | 2012-11-29 | 2010-08-03 | Connected |  | Yes
National Grid | FALL RIVER | 164173 | 2720 | 100 | Solar | 05_28W42 | 2010-08-05 01:00 | 2010-09-27 | [28 empty] | 2010-09-27 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | WORCESTER | 164174 | 1605 | 120 | Solar | 01_24W4 | 2010-08-05 01:00 | 2010-09-28 | [28 empty] | 2010-09-28 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | REVERE | 174345 | 2151 | 7.5 | Natural Gas | 12_2340 | 2010-08-17 01:00 | 2010-08-24 | 10 | 0 | 10 | [10 empty] | 2010-09-08 | 2010-10-21 | 31 | 0 | 31 | [10 empty] | 2011-02-16 |  | 2016-12-31 |  | STD | [6 empty] | 2011-04-19 | 2011-04-19 |  | Withdrawn |  | Yes
National Grid | SUTTON | 164273 | 1590 | 177 | Solar | 01_304W6 | 2010-08-19 01:00 | 2010-10-27 | [28 empty] | 2010-10-27 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | TEWKSBURY | 164369 | 1876 | 95 | Solar | 14_59L1 | 2010-09-21 01:00 | 2010-12-02 | [28 empty] | 2010-12-02 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | TEWKSBURY | 164368 | 1876 | 82 | Solar | 14_59L1 | 2010-09-22 01:00 | 2010-12-02 | [28 empty] | 2010-12-02 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | LYNN | 164371 | 1902 | 142 | Solar | 12_1394 | 2010-09-27 01:00 | 2011-01-13 | [28 empty] | 2011-01-13 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | LEOMINSTER | 164421 | 1453 | 62 | Solar | 01_207W6 | 2010-10-07 01:00 | 2011-03-28 | [28 empty] | 2011-03-28 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | MARLBOROUGH | 164423 | 1752 | 123 | Solar | 05_318W5 | 2010-10-07 01:00 | 2010-12-13 | [28 empty] | 2010-12-13 | 2010-10-07 01:00 |  |  | EXP | [9 empty] | Connected |  | No
National Grid | SALISBURY | 174519 | 1952 | 1000 | Solar | 14_2377N | 2010-10-07 01:00 | 2010-10-07 | 24 | 0 | 24 | [25 empty] | 2011-06-16 | 2010-10-07 01:00 | 2012-10-31 |  | STD | [6 empty] | 2013-01-18 | 2013-01-18 | 2012-08-03 | Connected |  | No
National Grid | SALISBURY | 174520 | 1952 | 1000 | Solar | 14_2377N | 2010-10-07 01:00 | 2010-10-07 | 24 | 0 | 24 | [25 empty] | 2011-06-16 | 2010-10-07 01:00 | 2012-10-31 |  | STD | [6 empty] | 2013-01-25 | 2013-01-25 | 2012-08-03 | Connected |  | No
National Grid | SALISBURY | 174521 | 1952 | 750 | Solar | 14_2377N | 2010-10-07 01:00 | 2010-10-08 | 23 | 0 | 23 | [25 empty] | 2011-06-16 | 2010-10-07 01:00 | 2012-10-31 |  | STD | [6 empty] | 2013-01-25 | 2013-01-25 | 2012-08-03 | Connected |  | No
National Grid | SALISBURY | 174522 | 1952 | 1000 | Solar | 14_2377N | 2010-10-07 01:00 | 2010-10-08 | 23 | 0 | 23 | [25 empty] | 2011-06-16 | 2010-10-07 01:00 | 2012-10-31 |  | STD | [6 empty] | 2013-01-25 | 2013-01-25 | 2012-08-03 | Connected |  | No
National Grid | SALISBURY | 174523 | 1952 | 1000 | Solar | 14_2377N | 2010-10-07 01:00 | 2010-10-08 | 23 | 0 | 23 | [25 empty] | 2011-06-16 |  | 2012-10-31 |  | STD | [6 empty] | 2013-01-25 | 2013-01-25 | 2012-08-03 | Connected |  | No
National Grid | BRIDGEWATER | 164472 | 2325 | 95 | Solar | 07_912W73 | 2010-10-15 01:00 | 2010-12-14 | [28 empty] | 2010-12-14 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | LEOMINSTER | 164473 | 1453 | 113 | Solar | 01_207W3 | 2010-10-19 01:00 | 2011-01-25 | [28 empty] | 2011-01-25 | 2010-10-19 01:00 |  |  | EXP | [9 empty] | Connected |  | Yes
National Grid | BARRE | 174609 | 1005 | 1000 | Solar | 09_604W2 | 2010-10-19 01:00 | 2010-10-21 | 13 | 0 | 13 | [25 empty] | 2011-09-08 |  | 2012-03-02 |  | STD | [6 empty] | 2012-08-03 | 2012-08-03 | 2012-04-02 | Connected |  | Yes
National Grid | FLORENCE | 174610 | 1062 | 22 | Solar | 09_901W3 | 2010-10-19 01:00 | 2010-10-19 | 4 | 0 | 4 | [27 empty] | 2012-01-03 |  | EXP | [6 empty] | 2012-08-03 | 2012-08-03 | 2012-01-03 | Connected |  | No
National Grid | WESTBOROUGH | 174692 | 1581 | 4000 |  | 05_312W5 | 2010-10-26 01:00 | 2010-10-28 | 81 | 0 | 81 | [27 empty] | 2012-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BARRE | 174611 | 1005 | 1000 | Solar | 09_604W2 | 2010-10-28 01:00 | 2010-10-29 | 7 | 0 | 7 | [25 empty] | 2011-09-08 |  | 2012-08-08 |  | STD | [6 empty] | 2012-08-03 | 2012-08-03 | 2012-08-03 | Connected |  | No
National Grid | WORCESTER | 164527 | 1602 | 82 | Solar | 01_HT48 | 2010-11-01 01:00 | 2011-03-01 | [28 empty] | 2011-03-01 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | WORCESTER | 164529 | 1605 | 148 | Solar | 01_27W4 | 2010-11-02 01:00 | 2011-02-05 | [28 empty] | 2011-02-05 |  |  |  | EXP | [9 empty] | Connected |  | Yes
National Grid | BROCKTON | 164578 | 2301 | 95 | Solar | 07_98W44 | 2010-11-08 | 2011-02-10 | [28 empty] | 2011-02-10 | 2010-11-08 |  |  | EXP | [9 empty] | Connected |  | No
National Grid | WORCESTER | 174342 | 1604 | 7500 | Natural Gas | 01_HT25 | 2010-11-08 | 2010-11-11 | 55 | 0 | 55 | [25 empty] | 2012-12-12 | 2010-11-11 | 2012-10-31 |  | STD |  | 2011-11-10 | 2012-03-05 | 75 | 0 | 75 | 2013-01-24 | 2013-01-24 | 2013-05-07 | Connected |  | Yes
National Grid | FALL RIVER | 174516 | 2720 | 1000 | Solar | 05_28W51 | 2010-11-11 | 2010-11-11 | 38 | 0 | 38 | [10 empty] | 2011-01-11 | 2011-02-08 | 19 | 0 | 19 | [10 empty] | 2011-06-15 | 2010-11-11 | 2012-10-31 |  | STD |  | 2012-10-19 | 2012-12-26 | 30 | 0 | 30 | 2013-01-25 | 2013-01-25 | 2013-02-22 | Connected |  | No
National Grid | FALL RIVER | 174517 | 2720 | 1000 | Solar | 05_28W51 | 2010-11-11 | 2010-11-11 | 38 | 0 | 38 | [10 empty] | 2011-01-11 | 2011-02-08 | 19 | 0 | 19 | [10 empty] | 2011-06-15 | 2010-11-11 | 2012-10-31 | Yes | STD |  | 2012-12-10 | 2012-12-13 | 3 | 0 | 3 | 2013-10-18 | 2013-10-18 | 2013-02-22 | Connected |  | No
National Grid | BRIDGEWATER | 174579 | 2324 | 3000 | Solar | 07_912W55 | 2010-11-11 | 2010-11-11 | 47 | 0 | 47 | [10 empty] | 2011-01-25 | 2011-03-28 | 43 | 0 | 43 | [10 empty] | 2013-02-01 | 2010-11-12 | 2016-12-31 | Yes | STD |  | 2015-12-21 | 2016-04-25 | 84 | 0 | 84 | 2016-05-17 | 2016-05-17 | 2016-05-17 | Connected |  | No
National Grid | MILLBURY | 174487 | 1527 | 300 | Solar | 01_8W1 | 2010-11-12 | 2010-11-12 | 42 | 0 | 42 | [25 empty] | 2011-03-01 |  | 2012-10-31 | Yes | EXP |  | 2012-05-30 | 2012-07-30 | 41 | 0 | 41 | 2013-01-18 | 2013-01-18 | 2012-08-17 | Connected |  | Yes
National Grid | SHEFFIELD | 163825 | 1257 | 1750 | Solar | 09_1108W1 | 2010-11-15 | 2011-09-14 | [28 empty] | 2011-09-14 | 2010-11-16 |  |  | EXP | [9 empty] | Connected |  | No
National Grid | NORTHBRIDGE | 174612 | 1534 | 1000 | Solar | 05_320W5 | 2010-11-16 | 2010-11-16 | 22 | 0 | 22 | [25 empty] | 2011-05-27 | 2010-11-16 | 2012-02-02 | Yes | STD |  | 2011-10-14 | 2012-01-20 | 64 | 0 | 64 | 2012-08-03 | 2012-08-03 | 2012-02-02 | Connected |  | No
National Grid | NORTHBRIDGE | 174613 | 1534 | 1000 | Solar | 05_320W5 | 2010-11-16 | 2010-11-16 | 22 | 0 | 22 | [25 empty] | 2011-05-27 |  | 2012-02-28 | Yes | STD |  | 2011-10-14 | 2012-02-22 | 86 | 0 | 86 | 2012-08-03 | 2012-08-03 | 2012-02-28 | Connected |  | No
National Grid | BROCKTON | 163836 | 2302 | 357 | Solar | 07_91W41 | 2010-11-19 | 2011-04-06 | [28 empty] | 2011-04-06 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | WEST BROOKFIELD | 163990 | 1585 | 95 | Solar | 01_525L2 | 2010-11-22 | 2011-01-31 | [28 empty] | 2011-01-31 |  |  |  | EXP | [9 empty] | Connected |  | Yes
National Grid | WEST WARREN | 163991 | 1092 | 95 | Solar | 09_516L3 | 2010-11-22 | 2011-02-04 | [28 empty] | 2011-02-04 |  |  |  | EXP | [9 empty] | Connected |  | Yes
National Grid | WARREN | 163992 | 1083 | 95 | Solar | 09_516L3 | 2010-11-22 | 2011-02-04 | [28 empty] | 2011-02-04 |  |  |  | EXP | [9 empty] | Connected |  | Yes
National Grid | WESTBOROUGH | 163887 | 1581 | 190 | Solar | 05_312W2 | 2010-11-23 | 2011-02-17 | [28 empty] | 2011-02-17 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | HANOVER | 163935 | 2339 | 75 | Solar | 07_95W1 | 2010-11-29 | 2011-04-14 | [28 empty] | 2011-04-14 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | FALL RIVER | 174614 | 2720 | 2000 | Wind | 05_28W51 | 2010-11-30 | 2010-12-03 | 33 | 0 | 33 | [25 empty] | 2011-09-30 |  | 2012-04-20 |  | STD | [6 empty] | 2012-08-03 | 2012-08-03 | 2012-04-20 | Connected |  | No
National Grid | STOUGHTON | 163937 | 1473 | 86 | Solar | 07_75W7 | 2010-12-02 | 2011-01-27 | [28 empty] | 2011-01-27 |  |  |  | EXP | [9 empty] | Connected |  | Yes
National Grid | EVERETT | 174486 | 2149 | 500 | Diesel | 12_2401 | 2010-12-09 | 2010-12-09 | 38 | 0 | 38 | [10 empty] | 2011-02-04 | 2011-02-23 | 12 | 0 | 12 | [10 empty] | 2011-06-14 |  | 2012-10-31 |  | STD | [6 empty] | 2012-09-19 | 2012-09-19 | 2012-09-24 | Connected |  | Yes
National Grid | LEICESTER | 163984 | 1524 | 100 | Solar | 01_21W2 | 2010-12-14 | 2011-03-30 | [28 empty] | 2011-03-30 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | LEICESTER | 163985 | 1524 | 175 | Solar | 01_21W2 | 2010-12-14 | 2011-03-30 | [28 empty] | 2011-03-30 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | LEICESTER | 163986 | 1524 | 100 | Solar | 01_21W2 | 2010-12-14 | 2011-03-30 | [28 empty] | 2011-03-30 |  |  |  | EXP | [9 empty] | Connected |  | Yes
National Grid | STURBRIDGE | 174615 | 1518 | 585 | Solar | 01_408L2 | 2010-12-14 | 2010-12-16 | 26 | 0 | 26 | [25 empty] | 2011-03-30 |  | 2012-02-27 |  | EXP | [6 empty] | 2012-08-03 | 2012-08-03 | 2012-02-27 | Connected |  | No
National Grid | LEICESTER | 174617 | 1524 | 22.8 | Solar | 01_21W1 | 2010-12-14 | 2010-12-16 | 25 | 0 | 25 | [25 empty] | 2011-04-05 |  | 2012-02-08 |  | EXP | [6 empty] | 2012-08-03 | 2012-08-03 | 2012-02-08 | Connected |  | No
National Grid | TYNGSBOROUGH | 163988 | 1879 | 100 | Solar | 14_211L1 | 2010-12-15 | 2011-02-11 | [28 empty] | 2011-02-11 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | SALEM | 174485 | 1970 | 3 | Solar | 12_2302E | 2010-12-29 | 2011-01-03 | 12 | 0 | 12 | 2011-01-21 | 2016-12-21 | 1449 | 0 | 1449 | [20 empty] | 2011-03-01 |  | 2016-12-31 |  | EXP | [6 empty] | 2013-01-18 | 2013-01-18 |  | Withdrawn |  | Yes
National Grid | FISKDALE | 174616 | 1518 | 300 | Solar | 01_408L2 | 2010-12-29 | 2010-12-29 | 18 | 0 | 18 | [25 empty] | 2011-03-30 |  | 2012-02-29 |  | EXP | [6 empty] | 2012-08-03 | 2012-08-03 | 2012-02-29 | Connected |  | No
National Grid | LOWELL | 164086 | 1854 | 120 | Solar | 14_13L1 | 2011-01-04 | 2011-04-26 | [28 empty] | 2011-04-26 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | LOWELL | 164087 | 1854 | 60 | Solar | 14_21L2 | 2011-01-04 | 2011-04-22 | [28 empty] | 2011-04-22 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | LOWELL | 164088 | 1854 | 82 | Solar | 14_2L3 | 2011-01-04 | 2011-05-05 | [28 empty] | 2011-05-05 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | QUINCY | 164128 | 2169 | 343 | Solar | 07_3W3 | 2011-01-07 | 2011-03-08 | [28 empty] | 2011-03-08 |  |  |  | EXP | [9 empty] | Connected |  | Yes
National Grid | BRIDGEWATER | 174578 | 2324 | 2000 | Solar | 07_912W55 | 2011-01-13 | 2011-01-13 | 7 | 0 | 7 | [27 empty] | 2012-10-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HARVARD | 174686 | 1451 | 5.3 | Solar | 01_216W6 | 2011-01-24 | 2011-01-25 | 8 | 0 | 8 | 2011-02-04 | 2012-12-17 | 451 | 0 | 451 | [22 empty] | 2012-12-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTHAMPTON | 174484 | 1060 | 250 | Solar | 09_901W1 | 2011-01-25 | 2011-01-25 | 21 | 0 | 21 | 2011-02-24 | 2014-02-18 | 720 | 0 | 720 | [20 empty] | 2011-09-14 |  | 2012-07-29 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WHITINSVILLE | 164182 | 1862 | 500 | Solar | 05_320W1 | 2011-01-28 | 2011-05-10 | [28 empty] | 2011-05-10 |  |  |  | EXP | [9 empty] | Connected |  | Yes
National Grid | NORTH ANDOVER | 164183 | 1845 | 83 | Solar | 14_55L1 | 2011-01-31 | 2011-04-07 | [28 empty] | 2011-04-07 | 2011-02-01 |  |  | EXP | [9 empty] | Connected |  | No
National Grid | PALMER | 174483 | 1069 | 1000 | Solar | 09_503L4 | 2011-02-01 | 2011-02-01 | 16 | 0 | 16 | [10 empty] | 2011-02-24 | 2011-05-06 | 51 | 0 | 51 | [10 empty] | 2012-04-13 |  | 2012-10-31 | Yes | STD |  | 2013-05-31 | 2013-08-21 | 56 | 0 | 56 | 2013-08-20 | 2013-08-20 | 2013-09-13 | Connected |  | No
National Grid | WORCESTER | 164229 | 1608 | 150 | Natural Gas | 01_HT39 | 2011-02-02 | 2011-04-28 | [28 empty] | 2011-04-28 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | BRIDGEWATER | 174481 | 2324 | 24 | Solar | 07_912W21 | 2011-02-02 | 2011-02-08 | 10 | 0 | 10 | [25 empty] | 2012-12-12 | 2011-02-07 | 2012-10-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 174618 | 1603 | 200 | Solar | 01_6W1 | 2011-02-07 | 2011-02-07 | 29 | 0 | 29 | [25 empty] | 2011-05-11 |  | 2012-01-11 |  | EXP |  | 2011-08-02 | 2012-01-28 | 122 | 0 | 122 | 2012-08-03 | 2012-08-03 | 2012-01-11 | Connected |  | Yes
National Grid | BEVERLY | 164238 | 1915 | 82 | Solar | 12_12L4 | 2011-02-10 | 2011-09-14 | [28 empty] | 2011-09-14 | 2011-02-14 |  |  | EXP | [9 empty] | Connected |  | No
National Grid | SPENCER | 174577 | 1562 | 3000 | Solar | 01_552L1 | 2011-02-14 | 2011-02-14 | 14 | 0 | 14 | [10 empty] | 2011-03-07 | 2011-03-23 | 12 | 0 | 12 | [5 empty] | 2016-02-01 | 2016-02-01 | 0 | 0 | 0 | 2012-02-28 |  | 2016-12-31 | Yes | STD |  | 2016-11-29 | 2017-08-29 | 188 | 0 | 188 | 2017-03-10 | 2017-03-10 | 2017-03-10 | Connected |  | No
National Grid | SWAMPSCOTT | 164281 | 1907 | 75 | Natural Gas | 12_22W2 | 2011-02-16 | 2011-07-22 | [28 empty] | 2011-07-22 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | AVON | 174532 | 2322 | 520 | Solar | 07_75W1 | 2011-02-18 | 2011-02-18 | 71 | 0 | 71 | [10 empty] | 2011-06-01 | 2012-05-05 | 232 | 0 | 232 | [10 empty] | 2012-05-16 |  | 2012-10-31 |  | STD | [6 empty] | 2013-03-06 | 2013-03-06 | 2013-03-06 | Connected |  | No
National Grid | SWAMPSCOTT | 174619 | 1907 | 350 | Solar | 12_22W3 | 2011-02-18 | 2011-02-22 | 25 | 0 | 25 | [25 empty] | 2011-07-13 |  | 2012-02-07 |  | EXP | [6 empty] | 2012-08-03 | 2012-08-03 | 2012-02-07 | Connected |  | No
National Grid | SWAMPSCOTT | 174620 | 1907 | 60 | Solar | 12_22W3 | 2011-02-18 | 2011-02-23 | 24 | 0 | 24 | [25 empty] | 2011-05-03 |  | 2012-01-06 |  | EXP | [6 empty] | 2012-08-06 | 2012-08-06 | 2012-01-06 | Connected |  | No
National Grid | FALL RIVER | 164284 | 2720 | 60 | Solar | 05_106W44 | 2011-02-23 | 2011-08-10 | [28 empty] | 2011-08-10 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | FRANKLIN | 164290 | 2038 | 260 | Solar | 05_348W7 | 2011-03-01 | 2011-06-21 | [28 empty] | 2011-06-21 |  |  |  | EXP | [9 empty] | Connected |  | Yes
National Grid | WORCESTER | 164331 | 1605 | 82 | Solar | 01_24W4 | 2011-03-07 | 2011-06-15 | [28 empty] | 2011-06-15 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | EVERETT | 164335 | 2149 | 360 | Solar | 12_37W9 | 2011-03-08 | 2011-06-02 | [28 empty] | 2011-06-02 |  |  |  | EXP | [9 empty] | Terminated |  | No
National Grid | WESTMINSTER | 174685 | 1473 | 7.6 | Solar | 01_609W1 | 2011-03-09 | 2011-03-11 | 423 | 60 | 363 | [27 empty] | 2012-12-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | QUINCY | 164340 | 2169 | 63 | Solar | 07_1W6 | 2011-03-14 01:00 | 2011-05-27 | [28 empty] | 2011-05-27 | 2011-03-17 01:00 |  |  | EXP | [9 empty] | Connected |  | No
National Grid | HANOVER | 174195 | 2339 | 250 | Wind | 07_95W1 | 2011-03-17 01:00 | 2011-03-28 | 0 | 0 | 0 | [25 empty] | 2012-05-08 | 2011-03-28 01:00 | 2020-02-28 |  | STD |  | 2012-07-24 | 2012-10-19 | 61 | 0 | 61 | 2015-12-16 | 2015-12-16 |  | Withdrawn |  | Yes
National Grid | WINCHENDON | 174657 | 1475 | 2000 | Solar | 01_612W1 | 2011-03-28 01:00 | 2011-03-28 | 15 | 0 | 15 | [25 empty] | 2012-12-12 |  | 2012-12-31 | Yes | STD | [9 empty] | Withdrawn |  | Yes
National Grid | HANOVER | 164433 | 2339 | 100 | Solar | 07_910W51 | 2011-03-29 01:00 | 2011-05-03 | [28 empty] | 2011-05-03 | 2011-04-01 01:00 |  |  | EXP | [9 empty] | Connected |  | No
National Grid | METHUEN | 174576 | 1844 | 1000 | Solar | 14_74L1 | 2011-04-01 01:00 | 2011-04-01 | 23 | 0 | 23 | [5 empty] | 2011-06-22 | 2012-08-20 | 289 | 0 | 289 | 2011-05-04 | 2011-06-15 | 29 | 0 | 29 | 2011-06-22 | 2012-08-20 | 289 | 0 | 289 | [5 empty] | 2012-10-11 | 2011-04-04 01:00 | 2012-10-31 | Yes | STD |  | 2013-05-14 | 2013-09-16 | 85 | 0 | 85 | 2013-07-09 | 2013-07-09 | 2013-07-25 | Connected |  | No
National Grid | ATHOL | 174649 | 1331 | 1000 | Solar | 09_702W1 | 2011-04-04 01:00 | 2011-04-18 | 66 | 0 | 66 | [10 empty] | 2011-07-21 | 2011-09-08 | 34 | 0 | 34 | [10 empty] | 2012-03-28 |  | 2012-12-31 | Yes | STD |  | 2013-05-24 | 2013-10-17 | 99 | 0 | 99 | 2013-10-14 | 2013-10-14 | 2013-10-25 | Connected |  | No
National Grid | BEVERLY | 174621 | 1915 | 190 | Solar | 12_12L2 | 2011-04-06 01:00 | 2011-04-06 | 3 | 0 | 3 | [25 empty] | 2011-07-28 | 2011-04-08 01:00 | 2012-08-11 |  | EXP | [6 empty] | 2012-08-06 | 2012-08-06 | 2012-01-18 | Connected |  | Yes
National Grid | SWANSEA | 174690 | 2777 | 1000 | Solar | 05_19W73 | 2011-04-08 01:00 | 2011-04-11 | 9 | 0 | 9 | [25 empty] | 2012-06-29 | 2011-04-08 01:00 | 2012-12-31 |  | STD |  | 2012-05-30 | 2013-02-26 | 165 | 0 | 165 | 2012-12-05 | 2012-12-05 | 2012-12-05 | Connected |  | No
National Grid | SWANSEA | 174691 | 2777 | 1500 | Solar | 05_19W73 | 2011-04-08 01:00 | 2011-04-11 | 9 | 0 | 9 | [25 empty] | 2012-06-29 | 2011-04-08 01:00 | 2012-12-31 |  | STD |  | 2012-05-30 | 2013-02-26 | 165 | 0 | 165 | 2012-12-05 | 2012-12-05 | 2012-12-06 | Connected |  | No
National Grid | NEWBURYPORT | 174865 | 1950 | 30 | Solar | 14_60L1 | 2011-04-08 01:00 | 2011-04-08 | 74 | 0 | 74 | [25 empty] | 2012-05-02 |  | 2012-05-02 |  | EXP |  | 2012-02-21 | 2012-03-13 | 15 | 0 | 15 | 2012-08-09 | 2012-08-09 | 2012-05-02 | Connected |  | No
National Grid | LOWELL | 164440 | 1851 | 190 | Solar | 14_312 | 2011-04-11 01:00 | 2011-05-06 | [28 empty] | 2011-05-06 | 2011-04-11 01:00 |  |  | EXP | [9 empty] | Connected |  | No
National Grid | BARRE | 174656 | 1005 | 800 | Solar | 09_604W3 | 2011-04-11 01:00 | 2011-04-11 | 9 | 0 | 9 | [25 empty] | 2012-03-07 | 2011-04-11 01:00 | 2012-12-31 |  | STD | [6 empty] | 2012-12-03 | 2012-12-03 | 2012-12-04 | Connected |  | No
National Grid | ORANGE | 174687 | 1364 | 1000 | Solar | 09_702W3 | 2011-04-11 01:00 | 2011-04-18 | 46 | 0 | 46 | [10 empty] | 2011-06-22 | 2011-10-06 | 74 | 0 | 74 | [10 empty] | 2012-03-28 | 2011-04-11 01:00 | 2012-12-31 | Yes | STD |  | 2013-06-28 | 2013-09-10 | 50 | 0 | 50 | 2013-08-28 | 2013-08-28 | 2013-09-06 | Connected |  | No
National Grid | ORANGE | 174688 | 1364 | 2000 | Solar | 09_702W3 | 2011-04-11 01:00 | 2011-04-18 | 46 | 0 | 46 | [10 empty] | 2011-06-22 | 2011-10-06 | 74 | 0 | 74 | [10 empty] | 2012-03-28 | 2011-04-11 01:00 | 2012-12-31 | Yes | STD |  | 2013-06-28 | 2013-09-10 | 50 | 0 | 50 | 2013-08-28 | 2013-08-28 | 2013-09-06 | Connected |  | No
National Grid | BARRE | 174689 | 1005 | 800 | Solar | 09_604W3 | 2011-04-11 01:00 | 2011-04-11 | 9 | 0 | 9 | [25 empty] | 2012-03-07 | 2011-04-11 01:00 | 2012-12-31 | Yes | STD |  | 2012-07-17 | 2012-12-12 | 87 | 0 | 87 | 2012-12-03 | 2012-12-03 | 2012-12-04 | Connected |  | No
National Grid | ATHOL | 175200 | 1331 | 1000 | Solar | 09_702W1 | 2011-04-11 01:00 | 2011-08-18 | 0 | 0 | 0 | [10 empty] | 2011-07-21 | 2011-09-08 | 34 | 0 | 34 | [10 empty] | 2012-03-28 | 2011-04-11 01:00 | 2012-12-31 | Yes | STD |  | 2013-05-24 | 2013-10-17 | 99 | 0 | 99 | 2013-10-14 | 2013-10-14 | 2013-10-25 | Connected |  | No
National Grid | ATHOL | 175201 | 1331 | 1000 | Solar | 09_702W1 | 2011-04-11 01:00 | 2011-04-18 | 66 | 0 | 66 | [10 empty] | 2011-07-21 | 2011-09-08 | 34 | 0 | 34 | [10 empty] | 2012-03-28 |  | 2012-12-31 | Yes | STD | [6 empty] | 2013-10-14 | 2013-10-14 | 2013-10-25 | Connected |  | No
National Grid | BEVERLY | 174524 | 1915 | 75 | Natural Gas | 12_51L1 | 2011-04-14 01:00 | 2011-04-15 | 1 | 0 | 1 | [25 empty] | 2012-12-12 | 2011-04-14 01:00 | 2012-10-31 |  | EXP | [6 empty] | 2011-04-13 | 2011-04-13 | 2011-04-13 | Connected |  | Yes
National Grid | UXBRIDGE | 174622 | 1569 | 2000 | Solar | 05_321W2 | 2011-04-14 01:00 | 2011-04-18 | 13 | 0 | 13 | [25 empty] | 2011-12-02 |  | 2012-06-01 | Yes | STD | [6 empty] | 2012-08-06 | 2012-08-06 | 2012-06-01 | Connected |  | No
National Grid | EVERETT | 174623 | 2149 | 200 | Solar | 12_37W6 | 2011-04-14 01:00 | 2011-04-15 | 155 | 0 | 155 | [25 empty] | 2011-11-28 |  | 2012-06-29 |  | EXP | [6 empty] | 2012-08-06 | 2012-08-06 | 2012-06-29 | Connected |  | No
National Grid | PLAINVILLE | 178763 | 2762 | 142 | Solar | 05_3422W3 | 2011-04-14 01:00 | 2011-04-15 | 83 | 0 | 83 | [25 empty] | 2012-12-12 |  | 2012-10-31 |  | EXP | [6 empty] | 2014-06-03 | 2014-06-03 | 2012-09-07 | Connected |  | No
National Grid | MILFORD | 164484 | 1757 | 375 | Solar | 05_336W4 | 2011-04-15 01:00 | 2011-05-10 | [28 empty] | 2011-05-10 | 2011-04-17 01:00 |  |  | EXP | [9 empty] | Connected |  | No
National Grid | SOUTHBOROUGH | 174569 | 1772 | 1000 | Solar | 05_314W2 | 2011-04-17 01:00 | 2011-04-18 | 10 | 0 | 10 | [25 empty] | 2012-02-10 | 2011-04-19 01:00 | 2012-10-31 | Yes | STD |  | 2012-05-07 | 2012-07-23 | 52 | 0 | 52 | 2012-08-06 | 2012-08-06 | 2012-08-17 | Connected |  | No
National Grid | ADAMS | 174479 | 1220 | 1000 | Solar | 09_1021W1 | 2011-04-19 01:00 | 2011-04-20 | 14 | 0 | 14 | [25 empty] | 2012-01-23 | 2011-04-19 01:00 | 2012-10-31 | Yes | STD |  | 2013-07-26 | 2014-01-16 | 118 | 0 | 118 | 2013-12-11 | 2013-12-11 | 2013-12-13 | Connected |  | No
National Grid | WEST BRIDGEWATER | 174480 | 2379 | 1500 | Solar | 07_797W19 | 2011-04-19 01:00 | 2011-04-19 | 13 | 0 | 13 | [10 empty] | 2011-05-06 | 2011-06-20 | 30 | 0 | 30 | [10 empty] | 2012-01-23 |  | 2012-10-31 |  | STD |  | 2013-05-27 | 2013-07-27 | 42 | 0 | 42 | 2013-07-26 | 2013-07-26 | 2013-08-15 | Connected |  | Yes
National Grid | NORTHAMPTON | 164492 | 1060 | 210 | Solar | 09_901W3 | 2011-04-21 01:00 | 2011-06-13 | [28 empty] | 2011-06-13 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | NORTH DIGHTON | 175198 | 2764 | 2000 | Solar | 05_19W74 | 2011-04-26 01:00 | 2011-04-26 | 21 | 0 | 21 | [10 empty] | 2011-05-25 | 2011-06-28 | 23 | 0 | 23 | [10 empty] | 2014-07-14 |  | 2016-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | FALL RIVER | 164536 | 2720 | 95 | Solar | 05_28W50 | 2011-04-27 01:00 | 2011-06-21 | [28 empty] | 2011-06-21 |  |  |  | EXP | [9 empty] | Connected |  | Yes
National Grid | NORTH OXFORD | 174473 | 1537 | 32.4 | Solar | 01_406L1 | 2011-04-27 01:00 | 2011-04-27 | 117 | 0 | 117 | [25 empty] | 2011-12-07 |  | 2012-10-31 |  | EXP | [6 empty] | 2013-01-25 | 2013-01-25 | 2012-07-02 | Connected |  | No
National Grid | FALL RIVER | 174477 | 2720 | 203 | Solar | 05_28W50 | 2011-04-27 01:00 | 2011-04-29 | 8 | 0 | 8 | [27 empty] | 2012-10-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SAUGUS | 174478 | 1906 | 164 | Solar | 12_25W3 | 2011-04-27 01:00 | 2011-04-27 | 117 | 0 | 117 | [25 empty] | 2011-12-07 |  | 2012-10-31 |  | EXP | [6 empty] | 2013-01-25 | 2013-01-25 | 2012-06-27 | Connected |  | No
National Grid | WORCESTER | 174591 | 1606 | 39 | Solar | 01_24W2 | 2011-04-27 01:00 | 2011-04-29 | 3 | 0 | 3 | [25 empty] | 2011-11-28 |  | 2012-08-04 |  | EXP | [6 empty] | 2012-08-09 | 2012-08-09 | 2012-08-02 | Connected |  | No
National Grid | FALL RIVER | 174472 | 2720 | 250 | Solar | 05_28W42 | 2011-04-28 01:00 | 2011-04-29 | 3 | 0 | 3 | [25 empty] | 2012-12-12 | 2011-05-02 01:00 | 2012-10-31 |  | EXP | [6 empty] | 2014-06-03 | 2014-06-03 | 2011-09-28 | Connected |  | No
National Grid | LOWELL | 174624 | 1854 | 40 | Solar | 14_21L3 | 2011-05-02 01:00 | 2011-05-05 | 53 | 0 | 53 | [25 empty] | 2011-08-18 | 2011-05-02 01:00 | 2012-01-10 | Yes | EXP |  | 2011-12-12 | 2011-12-12 | 0 | 0 | 0 | 2012-08-06 | 2012-08-06 | 2012-01-10 | Connected |  | No
National Grid | LOWELL | 174625 | 1854 | 15 | Solar | 14_13J4 | 2011-05-02 01:00 | 2011-05-05 | 53 | 0 | 53 | [25 empty] | 2011-08-17 | 2011-05-02 01:00 | 2012-01-10 | Yes | EXP |  | 2011-12-01 | 2011-12-12 | 7 | 0 | 7 | 2012-08-06 | 2012-08-06 | 2012-01-10 | Connected |  | No
National Grid | LOWELL | 174626 | 1854 | 15 | Solar | 14_13J4 | 2011-05-02 01:00 | 2011-05-05 | 53 | 0 | 53 | [25 empty] | 2011-08-17 | 2011-05-02 01:00 | 2012-01-10 | Yes | EXP |  | 2011-12-01 | 2011-12-12 | 7 | 0 | 7 | 2012-08-06 | 2012-08-06 | 2012-01-10 | Connected |  | No
National Grid | LOWELL | 174627 | 1854 | 66 | Solar | 14_13J4 | 2011-05-02 01:00 | 2011-05-05 | 53 | 0 | 53 | [25 empty] | 2011-08-18 | 2011-05-02 01:00 | 2012-02-10 | Yes | EXP |  | 2011-12-01 | 2011-12-12 | 7 | 0 | 7 | 2012-08-06 | 2012-08-06 | 2012-02-10 | Connected |  | No
National Grid | LOWELL | 174628 | 1852 | 44 | Solar | 14_13J4 | 2011-05-02 01:00 | 2011-05-05 | 53 | 0 | 53 | [25 empty] | 2011-08-18 |  | 2012-01-10 | Yes | EXP |  | 2011-12-01 | 2011-12-12 | 7 | 0 | 7 | 2012-08-06 | 2012-08-06 | 2012-01-10 | Connected |  | No
National Grid | NORTHAMPTON | 164544 | 2721 | 95 | Solar | 09_909W2 | 2011-05-05 01:00 | 2011-06-30 | [28 empty] | 2011-06-30 | 2011-05-05 01:00 |  |  | EXP | [9 empty] | Connected |  | Yes
National Grid | NORTH BROOKFIELD | 175195 | 1535 | 1000 | Solar | 01_0012 | 2011-05-05 01:00 | 2011-05-05 | 6 | 0 | 6 | [10 empty] | 2011-05-13 | 2011-06-23 | 28 | 0 | 28 | [10 empty] | 2012-07-16 | 2011-05-05 01:00 | 2012-12-31 |  | STD |  | 2013-08-21 | 2013-12-12 | 77 | 0 | 77 | 2013-12-13 | 2013-12-13 | 2013-12-13 | Connected |  | No
National Grid | NORTH BROOKFIELD | 175197 | 1535 | 1000 | Solar | 01_0012 | 2011-05-05 01:00 | 2011-05-05 | 6 | 0 | 6 | [10 empty] | 2011-05-13 | 2011-06-23 | 28 | 0 | 28 | [10 empty] | 2012-07-16 | 2011-05-06 01:00 | 2012-12-31 |  | STD |  | 2013-08-21 | 2013-12-12 | 77 | 0 | 77 | 2013-12-13 | 2013-12-13 | 2013-12-13 | Connected |  | No
National Grid | NORTHBOROUGH | 174469 | 1532 | 120 | Solar | 05_313W2 | 2011-05-06 01:00 | 2011-05-09 | 16 | 0 | 16 | [25 empty] | 2011-08-29 | 2011-05-06 01:00 | 2012-10-31 | Yes | EXP |  | 2012-05-07 | 2012-07-19 | 50 | 0 | 50 | 2012-09-20 | 2012-09-20 | 2012-08-13 | Connected |  | No
National Grid | NORTHBOROUGH | 174470 | 1532 | 95 | Solar | 05_313W2 | 2011-05-06 01:00 | 2011-05-09 | 16 | 0 | 16 | [25 empty] | 2011-08-29 | 2011-05-06 01:00 | 2012-10-31 | Yes | EXP |  | 2012-05-07 | 2012-07-19 | 50 | 0 | 50 | 2012-09-20 | 2012-09-20 | 2012-08-20 | Connected |  | No
National Grid | NORTHBOROUGH | 174471 | 1532 | 285 | Solar | 05_313W2 | 2011-05-06 01:00 | 2011-05-09 | 16 | 0 | 16 | [25 empty] | 2011-08-29 | 2011-05-10 01:00 | 2012-10-31 | Yes | EXP |  | 2012-05-07 | 2012-07-19 | 50 | 0 | 50 | 2012-09-20 | 2012-09-20 | 2012-08-13 | Connected |  | No
National Grid | WARREN | 175165 | 1083 | 1000 | Solar | 09_516L2 | 2011-05-10 01:00 | 2011-05-10 | 13 | 0 | 13 | [10 empty] | 2011-05-27 | 2011-07-07 | 27 | 0 | 27 | [10 empty] | 2012-08-24 |  | 2012-12-31 | Yes | STD |  | 2013-10-07 | 2013-12-13 | 46 | 0 | 46 | 2013-12-17 | 2013-12-17 | 2013-12-27 | Connected |  | No
National Grid | FRANKLIN | 163792 | 2038 | 215 | Solar | 05_344W2 | 2011-05-16 01:00 | 2011-07-26 | [28 empty] | 2011-07-26 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | BELCHERTOWN | 163794 | 1007 | 225 | Solar | 09_509L1 | 2011-05-17 01:00 | 2011-06-22 | [28 empty] | 2011-06-22 |  |  |  | EXP | [9 empty] | Connected |  | Yes
National Grid | COHASSET | 174570 | 2025 | 900 | Wind | 07_96W41 | 2011-05-17 01:00 | 2011-05-23 | 10 | 0 | 10 | [26 empty] | 2011-05-17 01:00 | 2012-10-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LOWELL | 174629 | 1851 | 500 | Solar | 14_16L2 | 2011-05-17 01:00 | 2011-05-18 | 3 | 0 | 3 | [25 empty] | 2011-06-20 |  | 2012-01-23 | Yes | EXP |  | 2011-10-19 | 2011-11-18 | 21 | 0 | 21 | 2012-08-06 | 2012-08-06 | 2012-01-23 | Connected |  | No
National Grid | AMESBURY | 164172 | 1913 | 78 | Solar | 14_5J11 | 2011-05-20 01:00 | 2011-06-24 | [28 empty] | 2011-06-24 | 2011-05-23 01:00 |  |  | EXP | [9 empty] | Connected |  | No
National Grid | SCITUATE | 174512 | 2066 | 1500 | Solar | 07_915W36 | 2011-05-23 01:00 | 2011-05-24 | 5 | 0 | 5 | [25 empty] | 2012-12-12 | 2011-05-23 01:00 | 2012-10-31 |  | STD |  | 2013-01-02 | 2013-09-12 | 166 | 0 | 166 | 2013-09-10 | 2013-09-10 | 2013-09-23 | Connected |  | No
National Grid | SCITUATE | 174513 | 2066 | 1500 | Solar | 07_915W36 | 2011-05-23 01:00 | 2011-05-24 | 5 | 0 | 5 | [25 empty] | 2012-12-12 |  | 2012-10-31 | Yes | STD |  | 2013-01-02 | 2013-09-12 | 166 | 0 | 166 | 2013-09-10 | 2013-09-10 | 2013-09-23 | Connected |  | No
National Grid | UXBRIDGE | 175163 | 1569 | 1000 | Solar | 05_321W2 | 2011-06-02 01:00 | 2011-06-07 | 36 | 0 | 36 | [27 empty] | 2012-12-31 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | FALL RIVER | 174491 | 2721 | 82 | Solar | 05_106W45 | 2011-06-03 01:00 | 2011-06-07 | 0 | 0 | 0 | [25 empty] | 2011-07-12 |  | 2012-02-28 |  | EXP | [6 empty] | 2012-08-06 | 2012-08-06 | 2012-02-28 | Connected |  | No
National Grid | FALL RIVER | 174492 | 2721 | 120 | Solar | 05_106W45 | 2011-06-03 01:00 | 2011-06-07 | 0 | 0 | 0 | [25 empty] | 2011-07-12 |  | 2012-03-02 |  | EXP | [6 empty] | 2012-08-06 | 2012-08-06 | 2012-03-02 | Connected |  | No
National Grid | LAWRENCE | 174789 | 1843 | 60 | Solar | 14_1J2 | 2011-06-03 01:00 | 2011-06-16 | 0 | 0 | 0 | [25 empty] | 2011-10-17 | 2011-06-08 01:00 | 2012-03-12 |  | EXP | [6 empty] | 2012-08-07 | 2012-08-07 | 2012-03-12 | Connected |  | No
National Grid | ORANGE | 175046 | 1364 | 1000 | Solar | 09_702W2 | 2011-06-08 01:00 | 2011-06-10 | 7 | 0 | 7 | [25 empty] | 2012-01-06 | 2011-06-08 01:00 | 2012-08-19 | Yes | STD | [6 empty] | 2012-08-14 | 2012-08-14 | 2012-07-06 | Connected |  | No
National Grid | ORANGE | 175047 | 1364 | 1000 | Solar | 09_702W2 | 2011-06-08 01:00 | 2011-06-10 | 7 | 0 | 7 | [25 empty] | 2012-01-06 | 2011-06-08 01:00 | 2012-08-19 |  | STD | [6 empty] | 2012-08-14 | 2012-08-14 | 2012-07-06 | Connected |  | No
National Grid | ORANGE | 175048 | 1364 | 750 | Solar | 09_702W2 | 2011-06-08 01:00 | 2011-06-10 | 7 | 0 | 7 | [25 empty] | 2012-01-06 | 2011-06-09 01:00 | 2012-08-19 |  | STD | [6 empty] | 2012-08-14 | 2012-08-14 | 2012-07-06 | Connected |  | No
National Grid | MILFORD | 174788 | 1757 | 26.5 | Solar | 05_336W2 | 2011-06-09 01:00 | 2011-06-16 | 0 | 0 | 0 | [25 empty] | 2011-07-27 |  | 2012-01-23 | Yes | EXP |  | 2011-12-29 | 2012-01-18 | 12 | 0 | 12 | 2012-08-07 | 2012-08-07 | 2012-01-23 | Connected |  | No
National Grid | SAUGUS | 164000 | 1906 | 225 | Solar | 12_19W2 | 2011-06-13 01:00 | 2011-08-02 | [28 empty] | 2011-08-02 |  |  |  | EXP | [9 empty] | Connected |  | Yes
National Grid | AYER | 174493 | 1432 | 232 | Solar | 01_227W3 | 2011-06-13 01:00 | 2011-06-16 | 12 | 0 | 12 | [25 empty] | 2011-10-03 |  | 2012-03-07 |  | STD | [6 empty] | 2012-08-06 | 2012-08-06 | 2012-03-07 | Connected |  | No
National Grid | NEWBURYPORT | 174790 | 1950 | 1020 | Diesel | 14_36L2 | 2011-06-16 01:00 | 2011-06-22 | 43 | 0 | 43 | [25 empty] | 2011-12-07 |  | 2012-05-02 |  | STD | [6 empty] | 2012-08-07 | 2012-08-07 | 2012-05-02 | Connected |  | No
National Grid | WHITINSVILLE | 174791 | 1588 | 120 | Solar | 05_320W1 | 2011-06-20 01:00 | 2011-06-24 | 12 | 0 | 12 | [25 empty] | 2011-09-13 |  | 2012-03-12 |  | EXP | [6 empty] | 2012-08-07 | 2012-08-07 | 2012-03-12 | Connected |  | No
National Grid | WHITINSVILLE | 174792 | 1588 | 225 | Solar | 05_320W1 | 2011-06-20 01:00 | 2011-06-24 | 12 | 0 | 12 | [25 empty] | 2011-09-13 | 2011-06-23 01:00 | 2012-03-16 |  | EXP | [6 empty] | 2012-08-07 | 2012-08-07 | 2012-03-16 | Connected |  | No
National Grid | WARREN | 174530 | 1083 | 1000 | Solar | 09_516L3 | 2011-06-23 01:00 | 2011-06-23 | 8 | 0 | 8 | [10 empty] | 2011-07-06 | 2011-08-04 | 21 | 0 | 21 | [10 empty] | 2012-08-24 | 2011-06-23 01:00 | 2012-10-31 | Yes | STD |  | 2013-10-21 | 2013-12-30 | 47 | 0 | 47 | 2012-07-24 | 2012-07-24 | 2013-12-27 | Connected |  | No
National Grid | WARREN | 174531 | 1083 | 1000 | Solar | 09_516L3 | 2011-06-23 01:00 | 2011-06-23 | 8 | 0 | 8 | [10 empty] | 2011-07-06 | 2011-08-04 | 21 | 0 | 21 | [10 empty] | 2012-08-24 | 2011-06-27 01:00 | 2012-10-31 | Yes | STD |  | 2013-10-21 | 2013-12-30 | 47 | 0 | 47 | 2012-07-24 | 2012-07-24 | 2013-12-27 | Connected |  | No
National Grid | WARREN | 174529 | 1083 | 1000 | Solar | 09_516L3 | 2011-06-27 01:00 | 2011-06-27 | 6 | 0 | 6 | [10 empty] | 2011-07-06 | 2011-08-04 | 21 | 0 | 21 | [10 empty] | 2012-08-24 |  | 2012-10-31 | Yes | STD |  | 2013-10-21 | 2013-12-30 | 47 | 0 | 47 | 2012-07-24 | 2012-07-24 | 2013-12-27 | Connected |  | No
National Grid | SOUTHBRIDGE | 164356 | 1550 | 1600 | Landfill Gas | 01_413L4 | 2011-07-01 01:00 | 2011-12-09 | [28 empty] | 2011-12-09 | 2011-07-05 01:00 |  |  | EXP | [9 empty] | Connected |  | Yes
National Grid | CHARLTON | 174794 | 1507 | 1000 | Solar | 01_406L1 | 2011-07-05 01:00 | 2011-07-13 | 1 | 0 | 1 | [25 empty] | 2012-07-14 | 2011-07-13 01:00 | 2012-07-24 |  | STD | [6 empty] | 2012-08-07 | 2012-08-07 | 2012-07-24 | Connected |  | No
National Grid | GLOUCESTER | 174566 | 1930 | 2000 | Wind | 12_2364 | 2011-07-13 01:00 | 2011-07-18 | 8 | 0 | 8 | [25 empty] | 2012-08-01 | 2011-07-13 01:00 | 2012-08-01 | Yes | STD | [6 empty] | 2012-12-28 | 2012-12-28 | 2012-12-31 | Connected |  | No
National Grid | GLOUCESTER | 174567 | 1930 | 2000 | Wind | 12_2364 | 2011-07-13 01:00 | 2011-07-18 | 8 | 0 | 8 | [10 empty] | 2011-07-28 | 2011-09-13 | 32 | 0 | 32 | [10 empty] | 2012-08-01 | 2011-07-14 01:00 | 2012-10-31 | Yes | STD | [6 empty] | 2012-12-28 | 2012-12-28 | 2012-12-31 | Connected |  | No
National Grid | QUINCY | 174468 | 2171 | 1100 | Solar | 07_11W3 | 2011-07-14 01:00 | 2011-07-21 | 0 | 0 | 0 | [25 empty] | 2012-04-05 | 2011-07-18 01:00 | 2012-07-25 | Yes | STD |  | 2012-10-10 | 2013-03-04 | 78 | 0 | 78 | 2012-11-26 | 2012-11-26 | 2012-12-04 | Connected |  | No
National Grid | MONSON | 175162 | 1057 | 3000 | Solar | 09_503L2 | 2011-07-18 01:00 | 2011-07-21 | 14 | 0 | 14 | [10 empty] | 2011-08-10 | 2011-09-30 | 36 | 0 | 36 | [10 empty] | 2012-06-20 |  | 2012-12-31 | Yes | STD |  | 2014-01-09 | 2014-10-07 | 185 | 0 | 185 | 2014-08-25 | 2014-08-25 | 2014-08-25 | Connected |  | No
National Grid | WORCESTER | 174467 | 1604 | 250 | Natural Gas | 01_27W3 | 2011-07-20 01:00 | 2011-07-20 | 43 | 0 | 43 | 2011-09-20 | 2016-12-21 | 1281 | 0 | 1281 | [20 empty] | 2011-12-06 |  | 2016-12-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 174590 | 1844 | 1000 | Solar | 14_2376 | 2011-07-20 01:00 | 2011-07-21 | 15 | 0 | 15 | [25 empty] | 2012-12-12 |  | 2012-11-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SALEM | 174825 | 1970 | 164 | Solar | 12_49W2 | 2011-07-20 01:00 | 2011-08-05 | 3 | 0 | 3 | [25 empty] | 2011-09-30 | 2011-07-20 01:00 | 2012-04-24 |  | EXP | [6 empty] | 2012-08-07 | 2012-08-07 | 2012-04-24 | Connected |  | No
National Grid | METHUEN | 175052 | 1844 | 2000 | Solar | 14_74L1 | 2011-07-20 01:00 | 2011-07-21 | 15 | 0 | 15 | [10 empty] | 2011-08-11 | 2011-09-13 | 22 | 0 | 22 | [10 empty] | 2012-06-20 |  | 2014-06-30 |  | STD |  | 2014-04-01 | 2014-06-18 | 53 | 0 | 53 | 2014-06-25 | 2014-06-25 | 2014-06-23 | Connected |  | No
National Grid | GLOUCESTER | 175161 | 1930 | 75 | Solar | 12_51T1 | 2011-07-21 01:00 | 2011-08-05 | 3 | 0 | 3 | [27 empty] | 2012-12-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEYMOUTH | 174824 | 2190 | 1000 | Natural Gas | 07_2W2 | 2011-07-22 01:00 | 2011-07-25 | 10 | 0 | 10 | [10 empty] | 2011-08-08 | 2011-09-07 | 21 | 0 | 21 | [10 empty] | 2012-03-02 |  | 2012-04-17 |  | STD | [6 empty] | 2012-04-13 | 2012-04-13 | 2012-04-17 | Connected |  | No
National Grid | DIGHTON | 175157 | 2715 | 2000 | Solar | 05_19W73 | 2011-07-25 01:00 | 2011-07-25 | 97 | 0 | 97 | [10 empty] | 2011-12-13 | 2014-02-25 | 523 | 0 | 523 | [11 empty] | 2011-07-27 01:00 | 2012-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTBOROUGH | 175128 | 1581 | 750 | Solar | 05_312W5 | 2011-07-27 01:00 | 2011-08-05 | 13 | 0 | 13 | [10 empty] | 2011-08-24 | 2013-01-23 | 335 | 0 | 335 | [10 empty] | 2012-09-06 |  | 2012-12-31 | Yes | STD |  | 2013-03-05 | 2013-04-22 | 29 | 0 | 29 | 2013-06-12 | 2013-06-12 | 2013-07-11 | Connected |  | No
National Grid | CHELMSFORD | 174466 | 1824 | 36 | Solar | 14_73L1 | 2011-07-29 01:00 | 2012-01-30 | 0 | 0 | 0 | [25 empty] | 2012-12-12 | 2011-07-29 01:00 | 2012-10-31 |  | EXP | [6 empty] | 2012-12-04 | 2012-12-04 | 2013-01-09 | Connected |  | No
National Grid | SOUTHBRIDGE | 175013 | 1550 | 1500 | Solar | 01_413L3 | 2011-07-29 01:00 | 2011-08-05 | 35 | 0 | 35 | [10 empty] | 2011-09-26 | 2011-12-02 | 46 | 0 | 46 | [5 empty] | 2012-03-16 | 2012-04-23 | 24 | 0 | 24 | 2012-12-12 | 2011-07-29 01:00 | 2013-01-01 |  | STD | [6 empty] | 2013-04-24 | 2013-04-24 | 2013-04-24 | Connected |  | No
National Grid | SOUTHBRIDGE | 175014 | 1550 | 1500 | Solar | 01_413L3 | 2011-07-29 01:00 | 2011-08-05 | 35 | 0 | 35 | [10 empty] | 2011-09-26 | 2011-12-02 | 46 | 0 | 46 | [5 empty] | 2012-03-16 | 2012-04-23 | 24 | 0 | 24 | 2012-12-12 |  | 2013-01-01 | Yes | STD |  | 2014-03-04 | 2014-03-07 | 3 | 0 | 3 | 2013-04-24 | 2013-04-24 | 2013-04-24 | Connected |  | No
National Grid | LYNN | 175090 | 1901 | 15 | Solar | 12_1385 | 2011-07-29 01:00 | 2011-08-03 | 322 | 65 | 257 | [27 empty] | 2012-11-30 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH ADAMS | 174465 | 1247 | 200 | Solar | 09_1015W1 | 2011-08-03 01:00 | 2011-08-10 | 11 | 0 | 11 | [26 empty] | 2011-08-03 01:00 | 2012-10-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EAST BROOKFIELD | 174738 | 1515 | 6000 | Solar |  | 2011-08-03 01:00 | 2011-08-09 | 11 | 0 | 11 | [10 empty] | 2011-08-24 | 2011-10-26 | 44 | 0 | 44 | [5 empty] | 2014-04-30 | 2016-08-05 | 563 | 0 | 563 | 2013-05-29 | 2011-08-03 01:00 | 2016-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LEICESTER | 174835 | 1524 | 1000 | Solar | 01_406L1 | 2011-08-03 01:00 | 2011-08-09 | 7 | 0 | 7 | [25 empty] | 2012-03-29 | 2011-08-04 01:00 | 2012-12-31 | Yes | STD |  | 2012-07-09 | 2012-10-18 | 71 | 0 | 71 | 2012-09-27 | 2012-09-27 | 2012-10-16 | Connected |  | No
National Grid | MILLBURY | 175160 | 1527 | 3000 | Solar | 01_304W5 | 2011-08-04 01:00 | 2011-08-10 | 32 | 0 | 32 | [10 empty] | 2011-09-26 | 2012-02-24 | 102 | 0 | 102 | [10 empty] | 2013-03-14 | 2011-08-05 01:00 | 2012-12-31 | Yes | STD |  | 2013-11-13 | 2014-03-12 | 80 | 0 | 80 | 2014-02-28 | 2014-02-28 | 2014-03-06 | Connected |  | No
National Grid | BILLERICA | 174565 | 1821 | 4999 | Solar | 14_70L8 | 2011-08-05 01:00 | 2011-08-11 | 2 | 0 | 2 | [20 empty] | 2012-09-21 | 2012-09-21 | 0 | 0 | 0 | 2012-12-12 | 2011-08-05 01:00 | 2014-12-01 | Yes | STD |  | 2014-05-19 | 2014-11-12 | 121 | 0 | 121 | 2014-07-31 | 2014-07-31 | 2014-08-13 | Connected |  | No
National Grid | BILLERICA | 175159 | 1821 | 2000 | Solar | 14_70L8 | 2011-08-05 01:00 | 2011-08-11 | 2 | 0 | 2 | [20 empty] | 2012-09-21 | 2014-08-11 | 444 | 0 | 444 | 2012-12-12 | 2011-08-08 01:00 | 2012-12-31 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | SWANSEA | 174564 | 2777 | 500 | Solar | 05_19W73 | 2011-08-08 01:00 | 2011-08-08 | 7 | 0 | 7 | [25 empty] | 2012-03-16 |  | 2012-10-31 |  | STD |  | 2012-08-27 | 2013-01-18 | 83 | 0 | 83 | 2012-12-05 | 2012-12-05 | 2012-12-10 | Connected |  | No
National Grid | WORCESTER | 174464 | 1609 | 170 | Natural Gas | 01_16J3 | 2011-08-09 01:00 | 2011-08-12 | 40 | 0 | 40 | 2011-10-10 | 2011-10-10 | 0 | 0 | 0 | [20 empty] | 2011-12-07 |  | 2012-10-31 |  | EXP | [6 empty] | 2012-06-29 | 2012-06-29 | 2013-01-29 | Connected |  | Yes
National Grid | NORTH ANDOVER | 174528 | 1845 | 500 | Solar | 14_56L1 | 2011-08-09 01:00 | 2011-08-09 | 29 | 0 | 29 | 2011-09-20 | 2016-12-21 | 1281 | 0 | 1281 | [20 empty] | 2011-10-04 |  | 2016-12-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH ADAMS | 175089 | 1247 | 1000 | Solar | 09_1001W1 | 2011-08-10 01:00 | 2011-08-24 | 1 | 0 | 1 | [10 empty] | 2011-08-25 | 2011-12-19 | 78 | 0 | 78 | [10 empty] | 2014-03-18 | 2011-08-15 01:00 | 2016-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LAWRENCE | 174828 | 1840 | 100 | Solar | 14_74L4 | 2011-08-15 01:00 | 2011-08-30 | 74 | 0 | 74 | [25 empty] | 2011-12-16 |  | 2012-03-06 |  | EXP | [6 empty] | 2012-08-08 | 2012-08-08 | 2012-03-06 | Connected |  | Yes
National Grid | BRIDGEWATER | 164906 | 2324 | 96 | Solar | 07_912W73 | 2011-08-19 01:00 | 2011-11-08 | [28 empty] | 2011-11-08 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | NORTH ADAMS | 174510 | 1247 | 225 | Solar | 09_1001W1 | 2011-08-22 01:00 | 2011-08-29 | 21 | 0 | 21 | 2011-09-28 | 2011-09-28 | 0 | 0 | 0 | [20 empty] | 2011-11-21 |  | 2012-10-31 |  | EXP | [6 empty] | 2013-01-25 | 2013-01-25 | 2013-04-23 | Connected |  | Yes
National Grid | NORTH ADAMS | 174511 | 1247 | 177 | Solar | 09_1001W1 | 2011-08-22 01:00 | 2011-08-22 | 26 | 0 | 26 | 2011-09-28 | 2011-09-28 | 0 | 0 | 0 | [20 empty] | 2011-11-21 | 2011-08-22 01:00 | 2012-10-31 |  | EXP | [6 empty] | 2013-01-25 | 2013-01-25 | 2013-04-23 | Connected |  | No
National Grid | WARREN | 174563 | 1083 | 4950 | Solar | 09_516L4 | 2011-08-22 01:00 | 2011-08-25 | 30 | 0 | 30 | [10 empty] | 2011-10-07 | 2011-12-16 | 47 | 0 | 47 | [10 empty] | 2013-03-14 |  | 2014-04-01 | Yes | STD | [6 empty] | 2014-05-14 | 2014-05-14 | 2014-05-30 | Connected |  | No
National Grid | NORTH ADAMS | 174589 | 1247 | 60 | Solar | 09_1001W1 | 2011-08-22 01:00 | 2011-08-22 | 26 | 0 | 26 | 2011-09-28 | 2011-09-28 | 0 | 0 | 0 | [20 empty] | 2011-11-21 |  | 2012-08-04 |  | EXP | [6 empty] | 2013-01-25 | 2013-01-25 | 2013-04-26 | Connected |  | No
National Grid | HANOVER | 174826 | 2339 | 30 | Solar | 07_95W5 | 2011-08-22 01:00 | 2011-08-25 | 2 | 0 | 2 | [25 empty] | 2011-11-21 | 2011-08-22 01:00 | 2012-02-10 |  | EXP | [6 empty] | 2012-08-08 | 2012-08-08 | 2012-02-10 | Connected |  | No
National Grid | GRAFTON | 174827 | 1519 | 250 | Solar | 01_328W2 | 2011-08-22 01:00 | 2011-08-30 | 0 | 0 | 0 | [25 empty] | 2011-10-24 | 2011-08-22 01:00 | 2012-01-03 | Yes | EXP |  | 2011-12-14 | 2011-12-22 | 6 | 0 | 6 | 2012-08-08 | 2012-08-08 | 2012-01-03 | Connected |  | Yes
National Grid | WARREN | 175054 | 1083 | 4950 | Solar | 09_516L4 | 2011-08-22 01:00 | 2011-08-25 | 30 | 0 | 30 | [10 empty] | 2011-10-07 | 2011-12-16 | 47 | 0 | 47 | [10 empty] | 2013-03-14 | 2011-08-22 01:00 | 2012-11-30 | Yes | STD | [6 empty] | 2014-05-14 | 2014-05-14 | 2014-05-30 | Connected |  | No
National Grid | WARREN | 175083 | 1083 | 4000 | Solar | 09_516L4 | 2011-08-22 01:00 | 2011-08-25 | 30 | 0 | 30 | [10 empty] | 2011-10-07 | 2011-12-16 | 47 | 0 | 47 | [10 empty] | 2013-03-14 |  | 2012-11-30 |  | STD | [6 empty] | 2014-05-14 | 2014-05-14 | 2014-05-30 | Connected |  | No
National Grid | DIGHTON | 174604 | 2715 | 42 | Solar | 05_19W72 | 2011-08-24 01:00 | 2011-08-30 | 26 | 0 | 26 | [25 empty] | 2011-12-27 |  | 2012-03-02 |  | EXP | [6 empty] | 2012-08-08 | 2012-08-08 | 2012-06-27 | Connected |  | No
National Grid | NORTHAMPTON | 174462 | 1060 | 548 | Solar | 09_S100 | 2011-08-25 01:00 | 2011-08-25 | 14 | 0 | 14 | [10 empty] | 2011-09-15 | 2011-11-14 | 41 | 0 | 41 | [10 empty] | 2012-04-10 |  | 2014-06-30 |  | STD | [6 empty] | 2013-01-25 | 2013-01-25 | 2013-12-23 | Connected |  | No
National Grid | AUBURN | 174587 | 1501 | 22.8 | Solar | 01_26W2 | 2011-08-29 01:00 | 2011-09-16 | 11 | 0 | 11 | [25 empty] | 2011-11-14 |  | 2012-06-28 |  | EXP | [6 empty] | 2012-08-09 | 2012-08-09 | 2012-06-28 | Connected |  | No
National Grid | BROCKTON | 174588 | 2302 | 30 | Solar | 07_712J1 | 2011-08-29 01:00 | 2011-09-16 | 11 | 0 | 11 | [25 empty] | 2011-11-14 | 2011-08-29 01:00 | 2012-08-04 |  | EXP | [6 empty] | 2012-08-09 | 2012-08-09 | 2012-07-03 | Connected |  | No
National Grid | ANDOVER | 175015 | 1810 | 950 | Solar | 14_59L1 | 2011-08-29 01:00 | 2011-08-30 | 13 | 0 | 13 | [10 empty] | 2011-09-19 | 2011-11-03 | 33 | 0 | 33 | [10 empty] | 2012-12-12 | 2011-08-29 01:00 | 2012-11-30 | Yes | STD |  | 2013-04-11 | 2013-12-14 | 169 | 0 | 169 | 2013-12-13 | 2013-12-13 | 2013-12-13 | Connected |  | No
National Grid | FOXBOROUGH | 178762 | 2035 | 102.6 | Solar | 05_3422W3 | 2011-08-29 01:00 | 2011-09-12 | 181 | 0 | 181 | [25 empty] | 2013-02-07 |  | 2012-06-23 |  | EXP |  | 2012-10-11 | 2012-12-19 | 32 | 0 | 32 | 2013-02-07 | 2013-02-07 | 2013-03-12 | Connected |  | Yes
National Grid | WEYMOUTH | 174363 | 2189 | 95 | Solar | 07_12W6 | 2011-08-30 01:00 | 2011-09-12 | 10 | 0 | 10 | [25 empty] | 2012-06-25 |  | 2012-05-30 |  | EXP | [6 empty] | 2012-08-02 | 2012-08-02 | 2012-08-09 | Connected |  | No
National Grid | LYNN | 174585 | 1905 | 95 | Solar | 12_21J27 | 2011-08-30 01:00 | 2011-09-16 | 11 | 0 | 11 | [25 empty] | 2011-10-03 |  | 2012-07-10 |  | EXP | [6 empty] | 2012-08-09 | 2012-08-09 | 2012-07-10 | Connected |  | No
National Grid | NORTHBOROUGH | 174586 | 1532 | 155 | Solar | 05_313W4 | 2011-08-30 01:00 | 2011-09-12 | 25 | 0 | 25 | [25 empty] | 2011-12-01 |  | 2012-10-31 |  | EXP | [6 empty] | 2012-08-09 | 2012-08-09 | 2012-07-03 | Connected |  | No
National Grid | ORANGE | 175012 | 1364 | 3000 | Solar | 09_705W2 | 2011-08-30 01:00 | 2011-09-12 | 10 | 0 | 10 | [26 empty] | 2011-08-31 01:00 | 2012-11-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTFORD | 175011 | 1886 | 235 | Solar | 14_57L3 | 2011-08-31 01:00 | 2011-09-12 | 5 | 0 | 5 | [25 empty] | 2011-12-28 |  | 2012-11-30 |  | EXP |  | 2012-01-09 | 2012-01-09 | 0 | 0 | 0 | 2014-06-03 | 2014-06-03 | 2012-05-11 | Connected |  | No
National Grid | FALL RIVER | 164998 | 2723 | 200 | Solar | 05_106W82 | 2011-09-01 01:00 | 2011-11-07 | [28 empty] | 2011-11-07 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | FALL RIVER | 164999 | 2720 | 75 | Solar | 05_28W50 | 2011-09-01 01:00 | 2011-11-07 | [28 empty] | 2011-11-07 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | FALL RIVER | 165000 | 2724 | 135 | Solar | 05_115W55 | 2011-09-01 01:00 | 2011-11-07 | [28 empty] | 2011-11-07 | 2011-09-01 01:00 |  |  | EXP | [9 empty] | Connected |  | No
National Grid | WESTFORD | 174461 | 1886 | 34.2 | Solar | 14_57L3 | 2011-09-01 01:00 | 2011-09-19 | 0 | 0 | 0 | [25 empty] | 2012-12-12 | 2011-09-01 01:00 | 2012-10-31 |  | EXP | [6 empty] | 2013-01-10 | 2013-01-10 | 2013-01-25 | Connected |  | No
National Grid | BILLERICA | 174574 | 1821 | 999 | Solar | 14_70L8 | 2011-09-01 01:00 | 2011-09-12 | 5 | 0 | 5 | [25 empty] | 2012-12-12 |  | 2012-10-31 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | BILLERICA | 174575 | 1821 | 2000 | Solar | 14_70L8 | 2011-09-01 01:00 | 2011-09-12 | 5 | 0 | 5 | [27 empty] | 2012-08-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | EAST BRIDGEWATER | 164991 | 2333 | 1000 | Solar | 07_797W42 | 2011-09-02 01:00 | 2012-06-29 | [28 empty] | 2012-06-29 | 2011-09-02 01:00 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | EAST BRIDGEWATER | 174559 | 2333 | 2000 | Solar | 07_797W42 | 2011-09-02 01:00 | 2011-09-13 | 9 | 0 | 9 | [10 empty] | 2011-09-26 | 2011-12-09 | 51 | 0 | 51 | [10 empty] | 2012-11-09 |  | 2012-10-31 | Yes | STD |  | 2013-04-01 | 2013-05-28 | 39 | 0 | 39 | 2013-05-09 | 2013-05-09 | 2013-06-07 | Connected |  | No
National Grid | AYER | 175010 | 1432 | 1500 | Solar | 01_201W3 | 2011-09-02 01:00 | 2011-09-13 | 9 | 0 | 9 | [25 empty] | 2012-06-29 |  | 2012-11-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BARRE | 174603 | 1005 | 15 | Solar | 09_604W4 | 2011-09-07 01:00 | 2011-10-27 | 84 | 0 | 84 | [25 empty] | 2012-03-02 |  | 2012-04-19 |  | EXP | [6 empty] | 2012-08-07 | 2012-08-07 | 2012-04-19 | Connected |  | No
National Grid | WINCHENDON | 174980 | 1475 | 1000 | Solar | 01_612W3 | 2011-09-07 01:00 | 2011-09-13 | 4 | 0 | 4 | [26 empty] | 2011-09-07 01:00 | 2012-11-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WINCHENDON | 175008 | 1475 | 1900 | Solar | 01_612W3 | 2011-09-07 01:00 | 2011-09-13 | 4 | 0 | 4 | [25 empty] | 2012-12-12 |  | 2012-11-30 | Yes | STD | [6 empty] | 2014-03-06 | 2014-03-06 | 2014-03-07 | Connected |  | No
National Grid | SPENCER | 174527 | 1562 | 1000 | Solar | 01_552L1 | 2011-09-12 01:00 | 2011-09-12 | 99 | 0 | 99 | 2012-02-06 | 2014-10-28 | 655 | 0 | 655 | [21 empty] | 2011-09-13 01:00 | 2012-10-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | TEWKSBURY | 174978 | 1876 | 950 | Solar | 14_59L1 | 2011-09-13 01:00 | 2011-09-26 | 0 | 0 | 0 | [25 empty] | 2012-12-12 | 2011-09-13 01:00 | 2012-11-30 | Yes | STD |  | 2013-04-11 | 2013-12-14 | 169 | 0 | 169 | 2013-12-13 | 2013-12-13 | 2013-12-13 | Connected |  | No
National Grid | TEWKSBURY | 174979 | 1876 | 950 | Solar | 14_59L1 | 2011-09-13 01:00 | 2011-09-26 | 0 | 0 | 0 | [25 empty] | 2012-12-12 | 2011-09-16 01:00 | 2012-11-30 | Yes | STD |  | 2013-04-11 | 2013-12-14 | 169 | 0 | 169 | 2013-12-13 | 2013-12-13 | 2013-12-13 | Connected |  | No
National Grid | UXBRIDGE | 174556 | 1569 | 950 | Solar | 05_320W4 | 2011-09-16 01:00 | 2011-09-27 | 0 | 0 | 0 | [25 empty] | 2012-12-12 | 2011-09-16 01:00 | 2012-10-31 | Yes | STD |  | 2013-02-05 | 2013-10-02 | 157 | 0 | 157 | 2013-08-09 | 2013-08-09 | 2013-08-13 | Connected |  | No
National Grid | UXBRIDGE | 174557 | 1569 | 950 | Solar | 05_320W4 | 2011-09-16 01:00 | 2011-09-27 | 0 | 0 | 0 | [25 empty] | 2012-12-12 | 2011-09-16 01:00 | 2012-10-31 | Yes | STD |  | 2013-02-05 | 2013-10-02 | 157 | 0 | 157 | 2013-08-09 | 2013-08-09 | 2013-08-13 | Connected |  | No
National Grid | UXBRIDGE | 174558 | 1569 | 950 | Solar | 05_320W4 | 2011-09-16 01:00 | 2011-09-27 | 0 | 0 | 0 | [25 empty] | 2012-12-12 |  | 2012-10-31 | Yes | STD |  | 2013-02-05 | 2013-10-02 | 157 | 0 | 157 | 2013-08-09 | 2013-08-09 | 2013-08-13 | Connected |  | No
National Grid | ATHOL | 174977 | 1331 | 950 | Solar | 09_702W2 | 2011-09-16 01:00 | 2011-09-28 | 0 | 0 | 0 | [27 empty] | 2012-09-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ATHOL | 174981 | 1331 | 950 | Solar |  | 2011-09-16 01:00 | 2011-09-28 | 0 | 0 | 0 | [27 empty] | 2012-10-10 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ATHOL | 174982 | 1331 | 950 | Solar |  | 2011-09-16 01:00 | 2011-09-28 | 0 | 0 | 0 | [27 empty] | 2012-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ATHOL | 174983 | 1331 | 950 | Solar |  | 2011-09-16 01:00 | 2011-09-28 | 0 | 0 | 0 | [26 empty] | 2011-09-16 01:00 | 2012-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BARRE | 175016 | 1005 | 1500 | Solar | 09_604W3 | 2011-09-16 01:00 | 2011-09-28 | 0 | 0 | 0 | [10 empty] | 2011-09-28 | 2011-12-12 | 50 | 0 | 50 | [10 empty] | 2013-06-07 | 2011-09-20 01:00 | 2012-11-30 | Yes | STD | [6 empty] | 2014-04-11 | 2014-04-11 | 2014-04-28 | Connected |  | No
National Grid | WESTPORT | 174310 | 2790 | 12 | Solar | 56_33F4 | 2011-09-20 01:00 | 2012-01-31 | 159 | 0 | 159 | 2012-09-19 | 2012-09-19 | 0 | 0 | 0 | [20 empty] | 2012-12-12 |  | 2011-12-31 |  | EXP |  | 2014-02-03 | 2014-02-14 | 9 | 0 | 9 | 2012-04-05 | 2012-04-05 | 2014-01-31 | Connected |  | No
National Grid | WESTFORD | 174602 | 1886 | 95 | Solar | 14_58L2 | 2011-09-20 01:00 | 2011-10-04 | 4 | 0 | 4 | [25 empty] | 2011-11-23 | 2011-09-20 01:00 | 2012-01-20 |  | EXP | [6 empty] | 2012-08-09 | 2012-08-09 | 2012-01-20 | Connected |  | No
National Grid | ORANGE | 174974 | 1364 | 1500 | Solar | 09_705W2 | 2011-09-20 01:00 | 2011-09-29 | 5 | 0 | 5 | [10 empty] | 2011-10-06 | 2012-01-03 | 58 | 0 | 58 | [10 empty] | 2012-08-22 | 2011-09-20 01:00 | 2012-11-30 | Yes | STD |  | 2013-06-04 | 2013-07-25 | 35 | 0 | 35 | 2013-07-23 | 2013-07-23 | 2013-07-30 | Connected |  | Yes
National Grid | ORANGE | 174975 | 1364 | 500 | Solar | 09_705W2 | 2011-09-20 01:00 | 2011-09-29 | 5 | 0 | 5 | [10 empty] | 2011-10-06 | 2012-01-03 | 58 | 0 | 58 | [10 empty] | 2012-08-22 |  | 2012-11-30 | Yes | STD |  | 2013-06-04 | 2013-07-25 | 35 | 0 | 35 | 2013-07-23 | 2013-07-23 | 2013-07-30 | Connected |  | Yes
National Grid | ORANGE | 174976 | 1364 | 557 | Solar | 09_705W3 | 2011-09-20 01:00 | 2011-09-29 | 5 | 0 | 5 | [10 empty] | 2011-10-06 | 2012-01-03 | 58 | 0 | 58 | [10 empty] | 2012-08-22 |  | 2012-11-30 |  | STD |  | 2013-06-04 | 2013-07-25 | 35 | 0 | 35 |  |  |  | Withdrawn |  | No
National Grid | LAWRENCE | 174459 | 1840 | 250 | Solar | 14_1321 | 2011-09-21 01:00 | 2011-10-04 | 16 | 0 | 16 | [25 empty] | 2012-01-10 |  | 2012-10-31 |  | EXP | [6 empty] | 2012-09-26 | 2012-09-26 | 2012-10-02 | Connected |  | No
National Grid | MILFORD | 174601 | 1757 | 155 | Solar | 05_336W1 | 2011-09-22 01:00 | 2011-10-04 | 0 | 0 | 0 | [25 empty] | 2011-11-23 |  | 2012-04-05 |  | EXP | [6 empty] | 2012-08-09 | 2012-08-09 | 2012-04-05 | Connected |  | No
National Grid | FALL RIVER | 165087 | 2724 | 100 | Solar | 05_106W82 | 2011-09-26 01:00 | 2011-11-23 | [28 empty] | 2011-11-23 | 2011-09-26 01:00 |  |  | EXP | [9 empty] | Connected |  | Yes
National Grid | RUTLAND | 174972 | 1543 | 4999 | Solar | 01_55W3 | 2011-09-26 01:00 | 2011-10-10 | 12 | 0 | 12 | [10 empty] | 2011-10-26 | 2011-12-20 | 36 | 0 | 36 | [10 empty] | 2012-10-19 |  | 2014-06-01 |  | STD |  | 2014-03-12 | 2014-12-18 | 192 | 0 | 192 | 2014-07-09 | 2014-07-09 | 2014-07-11 | Connected |  | No
National Grid | WESTMINSTER | 174973 | 1473 | 91.2 | Solar | 01_609W1 | 2011-09-26 01:00 | 2011-09-28 | 0 | 0 | 0 | [25 empty] | 2012-12-12 |  | 2012-11-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | RUTLAND | 174987 | 1543 | 1000 | Solar |  | 2011-09-26 01:00 | 2011-10-10 | 12 | 0 | 12 | [27 empty] | 2012-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | RUTLAND | 174988 | 1543 | 1000 | Solar |  | 2011-09-26 01:00 | 2011-10-10 | 12 | 0 | 12 | [27 empty] | 2012-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | RUTLAND | 174989 | 1543 | 1000 | Solar |  | 2011-09-26 01:00 | 2011-10-10 | 12 | 0 | 12 | [27 empty] | 2012-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | RUTLAND | 175017 | 1543 | 1000 | Solar |  | 2011-09-26 01:00 | 2011-10-10 | 12 | 0 | 12 | [27 empty] | 2012-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | DRACUT | 174504 | 1826 | 33.3 | Solar | 14_21L1 | 2011-09-27 01:00 | 2011-09-27 | 87 | 0 | 87 | 2012-02-03 | 2012-02-03 | 0 | 0 | 0 | [20 empty] | 2012-03-20 |  | 2012-10-31 |  | EXP | [6 empty] | 2013-01-29 | 2013-01-29 | 2013-02-12 | Connected |  | No
National Grid | DRACUT | 174505 | 1826 | 33.3 | Solar | 14_21L1 | 2011-09-27 01:00 | 2011-09-27 | 87 | 0 | 87 | 2012-02-03 | 2012-02-03 | 0 | 0 | 0 | [20 empty] | 2012-03-20 |  | 2012-10-31 |  | EXP | [6 empty] | 2013-01-29 | 2013-01-29 | 2013-02-12 | Connected |  | No
National Grid | DRACUT | 174506 | 1826 | 33.3 | Solar | 14_21L1 | 2011-09-27 01:00 | 2011-09-27 | 87 | 0 | 87 | 2012-02-03 | 2012-02-03 | 0 | 0 | 0 | [20 empty] | 2012-03-20 |  | 2012-10-31 |  | EXP | [6 empty] | 2013-01-29 | 2013-01-29 | 2013-02-12 | Connected |  | No
National Grid | DRACUT | 174507 | 1826 | 33.3 | Solar | 14_21L1 | 2011-09-27 01:00 | 2011-09-27 | 87 | 0 | 87 | 2012-02-03 | 2012-02-03 | 0 | 0 | 0 | [20 empty] | 2012-03-20 |  | 2012-10-31 |  | EXP | [6 empty] | 2013-01-29 | 2013-01-29 | 2013-02-12 | Connected |  | No
National Grid | DRACUT | 174508 | 1826 | 33.3 | Solar | 14_21L1 | 2011-09-27 01:00 | 2011-09-27 | 87 | 0 | 87 | 2012-02-03 | 2012-02-03 | 0 | 0 | 0 | [20 empty] | 2012-03-20 |  | 2012-10-31 |  | EXP | [6 empty] | 2013-01-29 | 2013-01-29 | 2013-02-12 | Connected |  | No
National Grid | DRACUT | 174509 | 1826 | 33.3 | Solar | 14_21L1 | 2011-09-27 01:00 | 2011-09-27 | 87 | 0 | 87 | 2012-02-03 | 2012-02-03 | 0 | 0 | 0 | [20 empty] | 2012-03-20 | 2011-09-28 01:00 | 2012-10-31 |  | EXP | [6 empty] | 2013-01-29 | 2013-01-29 | 2013-02-12 | Connected |  | No
National Grid | LOWELL | 174580 | 1852 | 275 | Solar | 14_304 | 2011-09-28 01:00 | 2011-10-05 | 6 | 0 | 6 | [25 empty] | 2011-12-02 | 2011-09-29 01:00 | 2012-10-31 |  | EXP | [6 empty] | 2013-01-24 | 2013-01-24 | 2012-08-03 | Connected |  | No
National Grid | BROOKFIELD | 174944 | 1506 | 333 | Solar | 01_552L3 | 2011-09-29 01:00 | 2011-10-10 | 0 | 0 | 0 | [25 empty] | 2012-08-13 |  | 2012-11-30 | Yes | STD |  | 2013-07-29 | 2013-09-13 | 33 | 0 | 33 | 2013-09-11 | 2013-09-11 | 2013-09-11 | Connected |  | Yes
National Grid | LYNN | 174562 | 1905 | 600 | Wind | 12_2305 | 2011-09-30 01:00 | 2011-09-30 | 17 | 0 | 17 | [10 empty] | 2011-10-25 | 2011-12-09 | 30 | 0 | 30 | [10 empty] | 2013-08-19 |  | 2012-10-31 |  | STD | [6 empty] | 2014-01-07 | 2014-01-07 | 2014-01-22 | Connected |  | Yes
National Grid | RUTLAND | 174555 | 1543 | 3000 | Solar | 01_55W1 | 2011-10-02 01:00 | 2011-10-06 | 45 | 0 | 45 | [25 empty] | 2013-08-02 |  | 2012-10-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | RUTLAND | 174943 | 1543 | 3000 | Solar | 01_55W1 | 2011-10-02 01:00 | 2011-10-06 | 45 | 0 | 45 | [27 empty] | 2012-11-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BELCHERTOWN | 174526 | 1007 | 45.6 | Solar | 09_509L2 | 2011-10-03 01:00 | 2011-10-03 | 11 | 0 | 11 | 2011-10-18 | 2013-12-04 | 505 | 0 | 505 | [21 empty] | 2011-10-03 01:00 | 2012-07-30 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEOMINSTER | 174600 | 1453 | 225 | Solar | 01_219W3 | 2011-10-03 01:00 | 2011-10-12 | 0 | 0 | 0 | [25 empty] | 2011-12-05 |  | 2012-03-01 | Yes | EXP |  | 2012-02-16 | 2012-02-24 | 5 | 0 | 5 | 2012-08-09 | 2012-08-09 | 2012-03-01 | Connected |  | No
National Grid | NORTH ADAMS | 174599 | 1247 | 41 | Solar | 09_1015W1 | 2011-10-04 01:00 | 2011-10-17 | 6 | 0 | 6 | [25 empty] | 2011-12-16 |  | 2012-02-22 |  | EXP | [6 empty] | 2012-08-09 | 2012-08-09 | 2012-02-22 | Connected |  | No
National Grid | RUTLAND | 174942 | 1543 | 286 | Solar | 01_55W1 | 2011-10-05 01:00 | 2011-10-05 | 485 | 274 | 211 | [27 empty] | 2012-11-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | FRANKLIN | 174458 | 2038 | 82 | Solar | 05_344W3 | 2011-10-06 01:00 | 2011-10-19 | 4 | 0 | 4 | [25 empty] | 2012-12-12 |  | 2012-10-31 |  | EXP | [6 empty] | 2014-01-08 | 2014-01-08 | 2014-01-13 | Connected |  | No
National Grid | CHARLEMONT | 174367 | 1339 | 540 | Solar | 09_1019W1 | 2011-10-07 01:00 | 2011-11-09 | 7 | 0 | 7 | [25 empty] | 2012-05-16 | 2011-10-07 01:00 | 2012-08-31 |  | STD | [6 empty] | 2012-12-12 | 2012-12-12 | 2012-12-31 | Connected |  | No
National Grid | DOUGLAS | 174450 | 1516 | 2000 | Solar | 05_320W2 | 2011-10-07 01:00 | 2011-10-19 | 4 | 0 | 4 | [25 empty] | 2012-12-12 |  | 2012-05-01 | Yes | STD |  | 2012-10-09 | 2013-01-09 | 47 | 0 | 47 | 2012-12-28 | 2012-12-28 | 2012-12-28 | Connected |  | No
National Grid | HANCOCK | 174841 | 1237 | 3000 | Solar | 09_1003W2 | 2011-10-07 01:00 | 2011-10-07 | 44 | 0 | 44 | [10 empty] | 2011-12-13 | 2012-02-24 | 49 | 0 | 49 | [5 empty] | 2014-04-30 | 2015-02-06 | 192 | 0 | 192 |  |  | 2013-07-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NANTUCKET | 174904 | 2554 | 900 | Wind | 04_101L6 | 2011-10-07 01:00 | 2011-10-12 | 594 | 389 | 205 | [26 empty] | 2011-10-10 01:00 | 2012-11-30 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | MENDON | 174598 | 1756 | 100 | Solar | 05_321W6 | 2011-10-10 01:00 | 2011-10-10 | 0 | 0 | 0 | [25 empty] | 2011-12-06 |  | 2012-05-21 | Yes | EXP |  | 2012-03-30 | 2012-04-26 | 18 | 0 | 18 | 2012-08-09 | 2012-08-09 | 2012-05-21 | Connected |  | Yes
National Grid | THREE RIVERS | 174525 | 1080 | 582 | Solar | 09_523L1 | 2011-10-11 01:00 | 2011-11-09 | 9 | 0 | 9 | [25 empty] | 2012-08-02 |  | 2012-10-31 |  | EXP | [6 empty] | 2012-08-31 | 2012-08-31 | 2012-08-31 | Connected |  | No
National Grid | WORCESTER | 174554 | 1603 | 1333 | Solar | 01_HT22 | 2011-10-11 01:00 | 2011-11-26 | 0 | 0 | 0 | [26 empty] | 2011-10-11 01:00 | 2012-10-31 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | SPENCER | 174571 | 1562 | 2000 | Solar | 01_21W1 | 2011-10-11 01:00 | 2011-10-11 | 21 | 0 | 21 | [10 empty] | 2011-11-09 | 2011-12-20 | 26 | 0 | 26 | [10 empty] | 2012-09-23 |  | 2012-10-31 | Yes | STD |  | 2013-04-09 | 2013-06-21 | 50 | 0 | 50 | 2013-06-21 | 2013-06-21 | 2013-08-07 | Connected |  | No
National Grid | SPENCER | 174572 | 1562 | 1000 | Solar | 01_21W1 | 2011-10-11 01:00 | 2011-11-09 | 0 | 0 | 0 | [27 empty] | 2012-10-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SPENCER | 174573 | 1562 | 1000 | Solar | 01_21W1 | 2011-10-11 01:00 | 2011-11-09 | 0 | 0 | 0 | [26 empty] | 2011-10-13 01:00 | 2012-10-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SOMERSET | 174457 | 2725 | 623 | Solar | 05_11W84 | 2011-10-13 01:00 | 2011-10-13 | 19 | 0 | 19 | [10 empty] | 2011-11-09 | 2011-12-01 | 13 | 0 | 13 | [10 empty] | 2011-12-06 | 2011-10-13 01:00 | 2012-10-31 |  | STD | [6 empty] | 2013-05-30 | 2013-05-30 | 2013-06-13 | Connected |  | No
National Grid | WEST BROOKFIELD | 174597 | 1585 | 300 | Solar | 01_525L2 | 2011-10-13 01:00 | 2011-10-28 | 0 | 0 | 0 | [25 empty] | 2011-12-20 |  | 2012-03-28 |  | EXP | [6 empty] | 2012-08-09 | 2012-08-09 | 2012-03-28 | Connected |  | No
National Grid | STOUGHTON | 174938 | 2072 | 68.4 | Solar | 07_913W43 | 2011-10-13 01:00 | 2011-11-09 | 0 | 0 | 0 | 2011-11-09 | 2014-03-12 | 555 | 0 | 555 | [20 empty] | 2012-10-03 |  | 2012-11-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WHITMAN | 174940 | 2382 | 60 | Solar | 07_93W42 | 2011-10-13 01:00 | 2011-11-09 | 0 | 0 | 0 | 2011-11-09 | 2011-11-09 | 0 | 0 | 0 | [20 empty] | 2012-12-12 |  | 2012-11-30 |  | EXP | [6 empty] | 2014-12-10 | 2014-12-10 | 2014-12-16 | Connected |  | No
National Grid | WHITMAN | 174941 | 2382 | 34.2 | Solar | 07_93W42 | 2011-10-13 01:00 | 2011-11-09 | 0 | 0 | 0 | 2011-11-09 | 2011-11-09 | 0 | 0 | 0 | [20 empty] | 2012-12-04 | 2011-10-14 01:00 | 2012-11-30 |  | EXP | [6 empty] | 2013-07-01 | 2013-07-01 | 2014-12-16 | Connected |  | No
National Grid | WEST BROOKFIELD | 174181 | 1585 | 800 | Solar | 01_525L2 | 2011-10-14 01:00 | 2012-03-12 | 0 | 0 | 0 | [25 empty] | 2013-04-10 | 2011-10-17 01:00 | 2014-03-01 | Yes | STD | [6 empty] | 2015-06-03 | 2015-06-03 | 2015-06-19 | Connected |  | No
National Grid | WEST BROOKFIELD | 174180 | 1585 | 1400 | Solar | 01_525L2 | 2011-10-17 01:00 | 2012-03-12 | 0 | 0 | 0 | [25 empty] | 2014-03-14 | 2011-10-18 01:00 | 2016-12-31 |  | STD | [6 empty] | 2016-01-28 | 2016-01-28 | 2016-01-29 | Connected |  | No
National Grid | FALL RIVER | 174534 | 2720 | 950 | Solar | 05_28W51 | 2011-10-18 01:00 | 2011-11-09 | 8 | 0 | 8 | [10 empty] | 2011-11-22 | 2012-01-27 | 43 | 0 | 43 | [10 empty] | 2013-03-22 | 2011-10-18 01:00 | 2012-10-31 | Yes | STD |  | 2013-11-04 | 2014-03-18 | 89 | 0 | 89 | 2013-12-10 | 2013-12-10 | 2013-12-13 | Connected |  | No
National Grid | FALL RIVER | 174535 | 2720 | 2850 | Solar | 05_28W42 | 2011-10-18 01:00 | 2011-11-09 | 8 | 0 | 8 | [10 empty] | 2011-11-22 | 2012-01-27 | 43 | 0 | 43 | [10 empty] | 2013-04-09 |  | 2012-10-31 | Yes | STD |  | 2013-11-22 | 2013-12-19 | 18 | 0 | 18 | 2013-12-19 | 2013-12-19 | 2013-12-23 | Connected |  | No
National Grid | FALL RIVER | 174536 | 2720 | 950 | Solar | 05_28W40 | 2011-10-18 01:00 | 2011-11-09 | 8 | 0 | 8 | [27 empty] | 2012-10-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | FALL RIVER | 174537 | 2720 | 950 | Solar | 05_28W41 | 2011-10-18 01:00 | 2011-11-09 | 8 | 0 | 8 | [27 empty] | 2012-10-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | FALL RIVER | 174538 | 2720 | 950 | Solar | 05_28W41 | 2011-10-18 01:00 | 2011-11-09 | 8 | 0 | 8 | [27 empty] | 2012-10-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | FALL RIVER | 174539 | 2720 | 950 | Solar | 05_28W41 | 2011-10-18 01:00 | 2011-11-09 | 8 | 0 | 8 | [27 empty] | 2012-10-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | FALL RIVER | 174540 | 2720 | 950 | Solar | 05_28W51 | 2011-10-18 01:00 | 2011-11-09 | 8 | 0 | 8 | [27 empty] | 2012-10-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | FALL RIVER | 174541 | 2720 | 475 | Solar | 05_28W51 | 2011-10-18 01:00 | 2011-11-09 | 8 | 0 | 8 | [26 empty] | 2011-10-18 01:00 | 2012-10-31 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | BELCHERTOWN | 174560 | 1007 | 1300 | Solar | 09_509L2 | 2011-10-18 01:00 | 2011-10-18 | 36 | 0 | 36 | [10 empty] | 2011-12-10 | 2012-02-01 | 34 | 0 | 34 | [10 empty] | 2012-09-05 |  | 2012-10-31 | Yes | STD |  | 2014-06-17 | 2014-06-17 | 0 | 0 | 0 | 2014-06-17 | 2014-06-17 | 2014-07-02 | Connected |  | No
National Grid | FALL RIVER | 174581 | 2724 | 190 | Solar | 05_115W42 | 2011-10-18 01:00 | 2011-11-09 | 3 | 0 | 3 | [25 empty] | 2011-12-22 |  | 2012-10-31 |  | EXP | [6 empty] | 2012-08-07 | 2012-08-07 | 2012-07-11 | Connected |  | Yes
National Grid | FALL RIVER | 174596 | 2723 | 26 | Solar | 05_106W44 | 2011-10-18 01:00 | 2011-11-10 | 2 | 0 | 2 | 2011-11-15 | 2011-11-15 | 0 | 0 | 0 | [20 empty] | 2011-12-27 | 2011-10-18 01:00 | 2012-04-13 |  | EXP | [6 empty] | 2012-08-09 | 2012-08-09 | 2012-04-13 | Connected |  | No
National Grid | BEVERLY | 174863 | 1915 | 60 | Solar | 12_12L2 | 2011-10-18 01:00 | 2011-11-10 | 59 | 0 | 59 | [25 empty] | 2012-03-08 | 2011-10-18 01:00 | 2012-07-13 |  | EXP | [6 empty] | 2012-08-08 | 2012-08-08 | 2012-07-13 | Connected |  | No
National Grid | BEVERLY | 175049 | 1915 | 85 | Solar | 12_12L2 | 2011-10-18 01:00 | 2011-10-18 | 76 | 0 | 76 | [25 empty] | 2012-03-08 | 2011-10-18 01:00 | 2012-08-19 |  | EXP | [6 empty] | 2012-08-14 | 2012-08-14 | 2012-07-13 | Connected |  | No
National Grid | BEVERLY | 175051 | 1915 | 190 | Solar | 12_12L4 | 2011-10-18 01:00 | 2011-10-18 | 76 | 0 | 76 | 2012-02-09 | 2012-02-09 | 0 | 0 | 0 | [20 empty] | 2012-03-08 |  | 2012-11-30 |  | EXP | [6 empty] | 2013-01-29 | 2013-01-29 | 2012-08-23 | Connected |  | Yes
National Grid | SHIRLEY | 174595 | 1464 | 82 | Solar | 01_227W1 | 2011-10-19 01:00 | 2011-11-10 | 2 | 0 | 2 | [25 empty] | 2011-12-21 | 2011-10-20 01:00 | 2012-02-21 |  | EXP | [6 empty] | 2012-08-09 | 2012-08-09 | 2012-02-21 | Connected |  | Yes
National Grid | FRANKLIN | 174216 | 2038 | 500 | Solar | 05_348W6 | 2011-10-20 01:00 | 2011-11-10 | 108 | 0 | 108 | [25 empty] | 2012-04-23 | 2011-10-20 01:00 | 2012-01-15 |  | EXP |  | 2012-06-04 | 2012-06-11 | 5 | 0 | 5 | 2012-07-13 | 2012-07-13 | 2012-07-13 | Connected |  | Yes
National Grid | WORCESTER | 174418 | 1604 | 110 | Solar | 01_27W1 | 2011-10-20 01:00 | 2011-10-20 | 16 | 0 | 16 | [25 empty] | 2011-12-19 |  | 2012-05-04 |  | EXP |  | 2012-03-12 | 2012-04-12 | 22 | 0 | 22 | 2013-01-25 | 2013-01-25 | 2012-05-04 | Connected |  | Yes
National Grid | BROCKTON | 174594 | 2302 | 36.4 | Solar | 07_91W47 | 2011-10-20 01:00 | 2011-10-24 | 0 | 0 | 0 | [25 empty] | 2012-02-07 | 2011-10-23 01:00 | 2012-03-02 |  | EXP | [6 empty] | 2012-08-09 | 2012-08-09 | 2012-03-02 | Connected |  | Yes
National Grid | WORCESTER | 174185 | 1607 | 91.2 | Solar | 01_8W2 | 2011-10-23 01:00 | 2012-03-21 | 32 | 0 | 32 | [25 empty] | 2012-07-02 |  | 2012-05-01 |  | EXP |  | 2012-10-05 | 2013-01-15 | 52 | 0 | 52 | 2012-06-20 | 2012-06-20 | 2013-04-24 | Connected |  | Yes
National Grid | QUINCY | 174561 | 2169 | 150 | Solar | 07_1224 | 2011-10-24 01:00 | 2011-11-17 | 71 | 0 | 71 | [25 empty] | 2012-12-12 |  | 2012-10-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LOWELL | 174877 | 1852 | 30 | Solar | 14_75L2 | 2011-10-25 01:00 | 2011-11-18 | 69 | 0 | 69 | [25 empty] | 2012-04-02 | 2011-10-25 01:00 | 2012-12-31 |  | EXP | [6 empty] | 2012-04-16 | 2012-04-16 | 2012-04-17 | Terminated |  | No
National Grid | PALMER | 174900 | 1069 | 1000 | Solar | 09_523L2 | 2011-10-25 01:00 | 2011-11-09 | 8 | 0 | 8 | [10 empty] | 2011-11-22 | 2012-02-26 | 63 | 0 | 63 | [10 empty] | 2012-08-24 | 2011-10-25 01:00 | 2012-11-30 |  | STD | [6 empty] | 2014-03-25 | 2014-03-25 | 2014-04-25 | Connected |  | No
National Grid | PALMER | 174901 | 1069 | 1000 | Solar | 09_523L2 | 2011-10-25 01:00 | 2011-11-09 | 8 | 0 | 8 | [10 empty] | 2011-11-22 | 2012-02-26 | 63 | 0 | 63 | [10 empty] | 2012-08-24 | 2011-10-25 01:00 | 2012-11-30 |  | STD | [6 empty] | 2014-03-25 | 2014-03-25 | 2014-04-25 | Connected |  | No
National Grid | PALMER | 174902 | 1069 | 1000 | Solar | 09_523L2 | 2011-10-25 01:00 | 2011-11-09 | 8 | 0 | 8 | [10 empty] | 2011-11-22 | 2012-02-26 | 63 | 0 | 63 | [10 empty] | 2012-08-24 | 2011-10-28 01:00 | 2012-11-30 | Yes | STD |  | 2014-02-15 | 2014-03-26 | 25 | 0 | 25 | 2014-03-25 | 2014-03-25 | 2014-04-25 | Connected |  | No
National Grid | SOUTH GRAFTON | 174553 | 1560 | 1910 | Solar | 05_320W3 | 2011-10-28 01:00 | 2011-11-09 | 0 | 0 | 0 | [25 empty] | 2012-11-19 |  | 2012-10-31 |  | STD |  | 2013-05-30 | 2013-07-26 | 39 | 0 | 39 | 2013-07-17 | 2013-07-17 | 2013-09-09 | Connected |  | No
National Grid | GRANBY | 174593 | 1033 | 14 | Solar | 09_527L2 | 2011-10-28 01:00 | 2011-12-08 | 2 | 0 | 2 | [25 empty] | 2011-12-13 | 2011-10-28 01:00 | 2012-01-06 |  | EXP | [6 empty] | 2012-08-09 | 2012-08-09 | 2012-01-06 | Connected |  | No
National Grid | GLOUCESTER | 174899 | 1930 | 2500 | Wind | 12_2364 | 2011-10-28 01:00 | 2011-11-09 | 8 | 0 | 8 | [10 empty] | 2011-11-22 | 2012-02-06 | 49 | 0 | 49 | [10 empty] | 2012-12-12 |  | 2012-11-30 | Yes | STD |  | 2012-11-20 | 2012-11-26 | 3 | 0 | 3 | 2012-12-10 | 2012-12-10 | 2012-12-14 | Connected |  | No
National Grid | GREAT BARRINGTON | 174186 | 1230 | 11.61 | Solar | 09_1109W3 | 2011-10-31 01:00 | 2012-03-21 | 0 | 0 | 0 | [25 empty] | 2012-03-21 |  | 2012-05-01 |  | EXP | [6 empty] | 2012-05-17 | 2012-05-17 | 2012-07-16 | Connected |  | No
National Grid | SOUTH EASTON | 174939 | 2375 | 83.8 | Solar | 07_92W54 | 2011-10-31 01:00 | 2011-11-09 | 0 | 0 | 0 | [26 empty] | 2011-11-01 01:00 | 2012-11-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTBOROUGH | 174272 | 1581 | 1820 | Solar | 05_312W4 | 2011-11-01 01:00 | 2011-11-10 | 61 | 0 | 61 | [5 empty] | 2013-02-01 | 2013-02-01 | 0 | 0 | 0 | 2012-02-13 | 2012-04-11 | 40 | 0 | 40 | 2013-02-01 | 2013-02-01 | 0 | 0 | 0 | [5 empty] | 2013-02-28 |  | 2012-01-16 | Yes | STD |  | 2013-10-24 | 2013-12-12 | 33 | 0 | 33 | 2014-02-12 | 2014-02-12 | 2022-09-14 | Connected |  | No
National Grid | WESTBOROUGH | 174273 | 1581 | 500 | Solar | 05_312W4 | 2011-11-01 01:00 | 2012-01-11 | 63 | 0 | 63 | [5 empty] | 2012-04-12 | 2012-04-12 | 0 | 0 | 0 | [5 empty] | 2012-04-12 | 2012-04-12 | 0 | 0 | 0 | [7 empty] | 2012-01-16 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | WESTBOROUGH | 174274 | 1581 | 1000 | Solar | 05_312W4 | 2011-11-01 01:00 | 2012-01-11 | 63 | 0 | 63 | [5 empty] | 2012-04-12 | 2012-04-12 | 0 | 0 | 0 | [5 empty] | 2012-04-12 | 2012-04-12 | 0 | 0 | 0 | [6 empty] | 2011-11-03 01:00 | 2012-01-16 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HUBBARDSTON | 174549 | 1452 | 2800 | Solar | 01_602W2 | 2011-11-03 01:00 | 2011-11-28 | 16 | 0 | 16 | [10 empty] | 2011-12-20 | 2012-02-16 | 39 | 0 | 39 | [10 empty] | 2013-01-23 |  | 2014-04-01 |  | STD | [6 empty] | 2014-06-12 | 2014-06-12 | 2014-06-23 | Connected |  | No
National Grid | HUBBARDSTON | 174985 | 1452 | 1000 | Solar | 01_602W2 | 2011-11-03 01:00 | 2011-11-28 | 16 | 0 | 16 | [10 empty] | 2011-12-20 | 2012-02-16 | 39 | 0 | 39 | [10 empty] | 2013-01-23 |  | 2012-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HUBBARDSTON | 174986 | 1452 | 1000 | Solar | 01_602W2 | 2011-11-03 01:00 | 2011-11-28 | 16 | 0 | 16 | [10 empty] | 2011-12-20 | 2012-02-16 | 39 | 0 | 39 | [10 empty] | 2013-01-23 |  | 2012-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HAMILTON | 174456 | 1982 | 200 | Solar | 12_51L3 | 2011-11-04 01:00 | 2011-11-04 | 33 | 0 | 33 | 2011-12-27 | 2011-12-27 | 0 | 0 | 0 | [20 empty] | 2012-02-21 |  | 2012-10-31 |  | EXP | [6 empty] | 2013-01-28 | 2013-01-28 | 2013-02-12 | Connected |  | No
National Grid | SALISBURY | 174842 | 1952 | 2000 | Solar | 14_2396 | 2011-11-04 01:00 | 2011-11-04 | 26 | 0 | 26 | [10 empty] | 2011-12-15 | 2011-12-28 | 8 | 0 | 8 | [12 empty] | 2013-07-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SALISBURY | 174843 | 1952 | 2000 | Solar | 14_2396 | 2011-11-04 01:00 | 2011-11-04 | 26 | 0 | 26 | [10 empty] | 2011-12-15 | 2011-12-28 | 8 | 0 | 8 | [12 empty] | 2013-07-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SALISBURY | 174844 | 1952 | 2000 | Solar | 14_2396 | 2011-11-04 01:00 | 2011-11-04 | 26 | 0 | 26 | [10 empty] | 2011-12-15 | 2011-12-28 | 8 | 0 | 8 | [12 empty] | 2013-02-05 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WILLIAMSTOWN | 174286 | 1267 | 24.4 | Solar | 09_1003W1 | 2011-11-07 | 2012-01-18 | 12 | 0 | 12 | [25 empty] | 2012-04-24 |  | 2011-12-30 |  | EXP | [6 empty] | 2012-07-24 | 2012-07-24 | 2012-07-24 | Connected |  | No
National Grid | HAVERHILL | 174552 | 1835 | 420 | Landfill Gas | 14_2371 | 2011-11-07 | 2011-11-28 | 61 | 0 | 61 | [26 empty] | 2011-11-08 | 2012-10-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHARLTON | 174545 | 1507 | 2000 | Solar | 01_415L2 | 2011-11-08 | 2011-11-09 | 9 | 0 | 9 | [20 empty] | 2013-04-16 | 2013-04-16 | 0 | 0 | 0 | 2013-04-09 | 2011-11-08 | 2012-10-31 |  | STD | [6 empty] | 2014-12-30 | 2014-12-30 | 2014-12-31 | Connected |  | No
National Grid | CHARLTON | 174546 | 1507 | 2000 | Solar | 01_415L2 | 2011-11-08 | 2011-11-09 | 9 | 0 | 9 | [20 empty] | 2013-04-16 | 2013-04-16 | 0 | 0 | 0 | 2013-04-09 |  | 2012-10-31 |  | STD | [6 empty] | 2014-12-30 | 2014-12-30 | 2014-12-31 | Connected |  | No
National Grid | CHARLTON | 174548 | 1507 | 1000 | Solar | 01_415L1 | 2011-11-08 | 2011-11-09 | 9 | 0 | 9 | [20 empty] | 2014-04-30 | 2014-08-01 | 64 | 0 | 64 |  |  | 2012-10-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 174547 | 1507 | 1000 | Solar | 01_415L1 | 2011-11-09 | 2011-11-09 | 9 | 0 | 9 | [20 empty] | 2014-04-30 | 2014-08-01 | 64 | 0 | 64 |  |  | 2012-10-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ATHOL | 174984 | 1331 | 1000 | Solar | 09_702W1 | 2011-11-10 | 2011-12-27 | 623 | 51 | 572 | [27 empty] | 2012-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SALISBURY | 174182 | 1952 | 190 | Solar | 14_275L4 | 2011-11-14 | 2012-03-14 | 0 | 0 | 0 | [25 empty] | 2012-03-14 |  | 2012-03-19 |  | EXP | [6 empty] | 2012-06-26 | 2012-06-26 | 2012-07-05 | Connected |  | No
National Grid | NORWELL | 174584 | 2061 | 200 | Solar | 07_96W40 | 2011-11-14 | 2011-12-12 | 0 | 0 | 0 | [25 empty] | 2012-02-24 |  | 2012-06-01 |  | EXP | [6 empty] | 2012-05-31 | 2012-05-31 | 2012-06-01 | Connected |  | No
National Grid | FRANKLIN | 174285 | 2038 | 30 | Solar | 05_344W3 | 2011-11-15 | 2012-01-18 | 64 | 0 | 64 | [25 empty] | 2012-04-20 |  | 2012-01-23 |  | EXP | [6 empty] | 2012-07-05 | 2012-07-05 | 2012-07-24 | Connected |  | No
National Grid | SALISBURY | 174265 | 1952 | 19.89 | Solar | 14_275L4 | 2011-11-16 | 2012-01-09 | 10 | 0 | 10 | [25 empty] | 2012-03-14 |  | 2012-01-14 |  | EXP | [6 empty] | 2012-06-26 | 2012-06-26 | 2012-07-16 | Connected |  | No
National Grid | WINCHENDON | 174542 | 1475 | 2000 | Solar | 01_612W3 | 2011-11-16 | 2011-12-20 | 0 | 0 | 0 | [27 empty] | 2012-10-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WINCHENDON | 174543 | 1475 | 2000 | Solar | 01_612W3 | 2011-11-16 | 2011-12-20 | 0 | 0 | 0 | [27 empty] | 2012-10-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WINCHENDON | 174544 | 1475 | 2000 | Solar | 01_612W3 | 2011-11-16 | 2011-12-20 | 0 | 0 | 0 | [26 empty] | 2011-11-16 | 2012-10-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | GRAFTON | 174551 | 1519 | 1500 | Solar | 01_304W2 | 2011-11-16 | 2011-11-16 | 39 | 0 | 39 | [10 empty] | 2012-01-17 | 2012-02-27 | 28 | 0 | 28 | [10 empty] | 2012-08-30 |  | 2012-10-31 | Yes | STD |  | 2013-08-08 | 2013-10-18 | 49 | 0 | 49 | 2013-09-24 | 2013-09-24 | 2013-10-11 | Connected |  | No
National Grid | WEYMOUTH | 174592 | 2189 | 15 | Solar | 07_9W2 | 2011-11-16 | 2012-01-09 | 0 | 0 | 0 | [25 empty] | 2012-01-10 | 2011-11-18 | 2012-01-31 |  | EXP | [6 empty] | 2012-08-08 | 2012-08-08 | 2012-02-10 | Connected |  | No
National Grid | LEICESTER | 174428 | 1524 | 4883 | Solar | 01_21W2 | 2011-11-18 | 2011-11-22 | 0 | 0 | 0 | [20 empty] | 2014-03-18 | 2014-03-18 | 0 | 0 | 0 | 2012-03-14 |  | 2014-06-01 |  | STD | [6 empty] | 2015-01-23 | 2015-01-23 | 2015-01-29 | Connected |  | No
National Grid | LEICESTER | 174429 | 1524 | 2000 | Solar |  | 2011-11-18 | 2012-06-28 | 0 | 0 | 0 | [25 empty] | 2013-03-14 |  | 2012-10-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LEICESTER | 174430 | 1524 | 3000 | Solar | 01_21W2 | 2011-11-18 | 2011-11-22 | 1 | 0 | 1 | [27 empty] | 2012-10-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LEICESTER | 174948 | 1524 | 1000 | Solar | 01_406L1 | 2011-11-18 | 2011-11-18 | 51 | 0 | 51 | [10 empty] | 2012-02-06 | 2012-03-12 | 24 | 0 | 24 | [12 empty] | 2012-10-03 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LEICESTER | 174949 | 1524 | 2000 | Solar | 01_6W1 | 2011-11-18 | 2011-11-18 | 51 | 0 | 51 | [10 empty] | 2012-02-06 | 2012-03-12 | 24 | 0 | 24 | [12 empty] | 2012-10-03 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LEICESTER | 174950 | 1524 | 1000 | Solar | 01_6W1 | 2011-11-18 | 2011-11-18 | 51 | 0 | 51 | [10 empty] | 2012-02-06 | 2012-03-12 | 24 | 0 | 24 | [11 empty] | 2011-11-21 | 2012-10-03 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTBOROUGH | 174427 | 1581 | 600 | Solar | 05_312W1 | 2011-11-21 | 2012-01-11 | 8 | 0 | 8 | [25 empty] | 2012-07-25 |  | 2012-10-31 |  | STD |  | 2012-08-21 | 2012-10-11 | 35 | 0 | 35 | 2012-10-09 | 2012-10-09 | 2012-10-15 | Connected |  | No
National Grid | HANCOCK | 174215 | 1237 | 75 | Natural Gas | 09_1018K1 | 2011-11-22 | 2012-02-14 | 0 | 0 | 0 | [25 empty] | 2012-12-12 |  | 2012-04-01 |  | EXP | [6 empty] | 2012-10-02 | 2012-10-02 | 2013-12-03 | Connected |  | No
National Grid | UXBRIDGE | 174300 | 1569 | 1000 | Solar |  | 2011-11-22 | 2012-01-27 | 18 | 0 | 18 | [20 empty] | 2014-04-30 | 2014-05-16 | 12 | 0 | 12 | 2014-05-16 |  | 2012-07-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | UXBRIDGE | 174301 | 1569 | 1000 | Solar |  | 2011-11-22 | 2012-01-27 | 18 | 0 | 18 | [27 empty] | 2012-07-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | UXBRIDGE | 174302 | 1569 | 1000 | Solar |  | 2011-11-22 | 2012-01-27 | 18 | 0 | 18 | [26 empty] | 2011-11-23 | 2012-07-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH BROOKFIELD | 174422 | 1535 | 3000 | Solar | 01_525L1 | 2011-11-23 | 2011-11-23 | 33 | 0 | 33 | [25 empty] | 2012-12-04 |  | 2012-10-31 | Yes | STD |  | 2014-02-13 | 2014-06-13 | 82 | 0 | 82 | 2014-06-16 | 2014-06-16 | 2014-06-16 | Connected |  | No
National Grid | NORTH BROOKFIELD | 174424 | 1535 | 1000 | Solar | 01_525L1 | 2011-11-23 | 2011-12-01 | 29 | 0 | 29 | [27 empty] | 2012-10-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH BROOKFIELD | 174425 | 1535 | 1000 | Solar | 01_525L1 | 2011-11-23 | 2011-12-01 | 29 | 0 | 29 | [27 empty] | 2012-10-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MENDON | 174455 | 1756 | 150 | Solar | 05_335W1 | 2011-11-28 | 2012-01-09 | 4 | 0 | 4 | [25 empty] | 2012-02-27 | 2011-12-01 | 2012-04-01 |  | EXP | [6 empty] | 2012-09-24 | 2012-09-24 | 2012-08-31 | Connected |  | No
National Grid | MARLBOROUGH | 174829 | 1752 | 270 | Solar | 05_310W4 | 2011-12-01 | 2011-12-13 | 21 | 0 | 21 | [25 empty] | 2012-01-13 |  | 2012-07-09 | Yes | EXP |  | 2012-06-20 | 2012-06-28 | 6 | 0 | 6 | 2012-08-08 | 2012-08-08 | 2012-07-09 | Connected |  | No
National Grid | LANCASTER | 174229 | 1523 | 26 | Solar | 01_225W1 | 2011-12-08 | 2012-02-21 | 17 | 0 | 17 | [25 empty] | 2012-03-15 |  | 2011-12-30 |  | EXP | [6 empty] | 2012-04-24 | 2012-04-24 | 2012-04-24 | Connected |  | No
National Grid | PALMER | 174289 | 1069 | 950 | Solar | 09_523L4 | 2011-12-08 | 2011-12-09 | 40 | 0 | 40 | 2012-02-08 | 2014-02-25 | 485 | 0 | 485 | [22 empty] | 2013-03-01 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | PALMER | 174288 | 1069 | 950 | Solar | 09_523L4 | 2011-12-09 | 2011-12-09 | 40 | 0 | 40 | 2012-02-08 | 2014-05-16 | 541 | 0 | 541 | [22 empty] | 2013-03-01 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | PALMER | 174290 | 1069 | 950 | Solar | 09_523L4 | 2011-12-09 | 2011-12-09 | 40 | 0 | 40 | 2012-02-08 | 2014-02-25 | 485 | 0 | 485 | [22 empty] | 2013-03-01 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | PALMER | 174291 | 1069 | 950 | Solar | 09_523L4 | 2011-12-09 | 2011-12-09 | 40 | 0 | 40 | 2012-02-08 | 2014-02-21 | 483 | 0 | 483 | [22 empty] | 2013-03-01 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | PALMER | 174292 | 1069 | 950 | Solar | 09_523L4 | 2011-12-09 | 2011-12-09 | 40 | 0 | 40 | 2012-02-08 | 2014-02-25 | 485 | 163 | 322 | [21 empty] | 2011-12-09 | 2013-03-01 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 174308 | 1844 | 190 | Solar | 14_74L3 | 2011-12-09 | 2012-01-30 | 25 | 0 | 25 | [25 empty] | 2012-03-13 | 2011-12-13 | 2012-02-01 |  | EXP |  | 2012-05-08 | 2012-05-09 | 1 | 0 | 1 | 2012-05-11 | 2012-05-11 | 2012-05-23 | Connected |  | No
National Grid | LAWRENCE | 174279 | 1840 | 491 | Solar | 14_74L4 | 2011-12-13 | 2012-01-13 | 62 | 0 | 62 | [25 empty] | 2012-05-02 |  | 2012-03-01 | Yes | EXP |  | 2012-06-06 | 2012-07-16 | 26 | 0 | 26 | 2012-06-26 | 2012-06-26 | 2012-07-02 | Connected |  | No
National Grid | MALDEN | 174340 | 2148 | 50 | Solar | 12_5C5 | 2011-12-13 | 2012-02-13 | 23 | 0 | 23 | [25 empty] | 2012-03-19 |  | 2012-03-30 |  | EXP | [6 empty] | 2012-06-05 | 2012-06-05 | 2012-07-18 | Connected |  | No
National Grid | LEOMINSTER | 174277 | 1453 | 25.6 | Solar | 01_207W4 | 2011-12-14 | 2012-01-12 | 13 | 0 | 13 | [5 empty] | 2012-03-13 | 2012-03-14 | 1 | 0 | 1 | [5 empty] | 2012-03-13 | 2012-03-14 | 1 | 0 | 1 | [5 empty] | 2012-03-14 |  | 2012-04-14 |  | EXP | [6 empty] | 2012-04-02 | 2012-04-02 | 2012-04-24 | Connected |  | No
National Grid | UXBRIDGE | 174416 | 1569 | 750 | Solar |  | 2011-12-14 | 2012-01-10 | 4 | 0 | 4 | [26 empty] | 2011-12-14 | 2012-07-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WRENTHAM | 178747 | 2093 | 500 | Solar | 05_3422W4 | 2011-12-14 | 2012-01-17 | 62 | 0 | 62 | [25 empty] | 2012-09-18 |  | 2012-06-08 | Yes | STD |  | 2013-01-16 | 2013-02-24 | 22 | 0 | 22 | 2013-02-22 | 2013-02-22 | 2013-03-05 | Connected |  | No
National Grid | WRENTHAM | 178755 | 2093 | 500 | Solar | 05_3422W4 | 2011-12-14 | 2012-01-17 | 61 | 0 | 61 | [27 empty] | 2012-01-22 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HAVERHILL | 174294 | 1832 | 300 | Solar | 14_48L1 | 2011-12-15 | 2012-01-23 | 17 | 0 | 17 | [25 empty] | 2012-02-27 | 2011-12-16 | 2012-01-28 |  | EXP | [6 empty] | 2012-06-01 | 2012-06-01 | 2012-06-04 | Connected |  | No
National Grid | NORTH ADAMS | 174295 | 1247 | 2250 | Solar | 09_1015W1 | 2011-12-16 | 2011-12-16 | 45 | 0 | 45 | [10 empty] | 2012-02-23 | 2012-04-25 | 42 | 0 | 42 | [10 empty] | 2014-06-27 |  | 2013-08-30 | Yes | STD |  | 2015-03-24 | 2015-08-12 | 97 | 0 | 97 | 2015-07-16 | 2015-07-16 | 2015-07-16 | Connected |  | No
National Grid | SUTTON | 174283 | 1590 | 2000 | Solar | 05_320W5 | 2011-12-17 | 2012-01-18 | 102 | 0 | 102 | [20 empty] | 2014-04-30 | 2014-09-08 | 89 | 0 | 89 |  |  | 2012-08-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SUTTON | 174284 | 1590 | 2000 | Solar | 05_320W5 | 2011-12-17 | 2012-01-18 | 102 | 0 | 102 | [27 empty] | 2012-08-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SUTTON | 178805 | 1590 | 1212.2 | Solar | 05_320W5 | 2011-12-17 | 2012-01-18 | 102 | 0 | 102 | [27 empty] | 2012-08-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SWANSEA | 174269 | 2777 | 300 | Solar | 05_11W81 | 2011-12-19 | 2011-12-19 | 30 | 0 | 30 | 2012-02-02 | 2014-02-20 | 486 | 0 | 486 | 2013-01-29 | 2013-01-29 | 0 | 0 | 0 | [5 empty] | 2013-01-29 | 2013-01-29 | 0 | 0 | 0 | [5 empty] | 2012-04-18 |  | 2012-06-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHARLTON | 174214 | 1507 | 1000 | Solar | 01_406L1 | 2011-12-20 | 2012-02-14 | 27 | 0 | 27 | [27 empty] | 2012-09-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LAWRENCE | 174275 | 1841 | 380 | Solar | 14_1321 | 2011-12-20 | 2012-01-11 | 34 | 0 | 34 | [25 empty] | 2012-05-02 |  | 2012-04-01 |  | EXP | [6 empty] | 2012-06-15 | 2012-06-15 | 2012-07-06 | Connected |  | No
National Grid | DRACUT | 174326 | 1826 | 1000 | Solar | 14_75L3 | 2011-12-20 | 2012-02-06 | 29 | 0 | 29 | [20 empty] | 2014-04-30 | 2014-09-04 | 87 | 0 | 87 |  |  | 2012-09-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | DRACUT | 174327 | 1826 | 1500 | Solar | 14_75L3 | 2011-12-20 | 2012-02-06 | 29 | 0 | 29 | [26 empty] | 2011-12-20 | 2012-09-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | OXFORD | 174328 | 1540 | 2750 | Solar | 01_406L4 | 2011-12-20 | 2012-02-06 | 32 | 0 | 32 | [25 empty] | 2012-11-28 | 2011-12-20 | 2014-06-21 | Yes | STD |  | 2014-03-10 | 2014-05-15 | 46 | 0 | 46 | 2014-06-24 | 2014-06-24 | 2014-07-02 | Connected |  | No
National Grid | OXFORD | 174329 | 1540 | 1750 | Solar | 01_406L4 | 2011-12-20 | 2012-02-06 | 32 | 0 | 32 | [25 empty] | 2012-11-28 |  | 2012-09-01 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | MARLBOROUGH | 174312 | 1752 | 333 | Solar | 05_317W2 | 2011-12-21 | 2012-02-01 | 26 | 0 | 26 | [20 empty] | 2012-03-26 | 2012-03-26 | 0 | 0 | 0 | 2012-04-02 | 2011-12-22 | 2012-06-08 |  | EXP | [6 empty] | 2012-09-12 | 2012-09-12 | 2012-09-17 | Connected |  | No
National Grid | FRANKLIN | 174298 | 2038 | 2000 | Solar | 05_2284 | 2011-12-22 | 2012-01-24 | 21 | 0 | 21 | [25 empty] | 2013-01-23 | 2011-12-22 | 2012-03-01 | Yes | STD |  | 2014-01-07 | 2014-03-25 | 52 | 0 | 52 | 2013-12-26 | 2013-12-26 | 2013-12-26 | Connected |  | No
National Grid | FRANKLIN | 178759 | 2038 | 3000 | Solar | 05_3422W1 | 2011-12-22 | 2012-01-24 | 21 | 0 | 21 | [25 empty] | 2012-11-06 |  | 2012-03-01 | Yes | STD |  | 2013-07-02 | 2013-10-04 | 66 | 0 | 66 | 2013-09-19 | 2013-09-19 | 2013-11-18 | Connected |  | No
National Grid | FRANKLIN | 178760 | 2038 | 300 | Solar | 05_3422W1 | 2011-12-22 | 2012-01-24 | 21 | 0 | 21 | [26 empty] | 2011-12-23 | 2012-03-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 174297 | 1844 | 1800 | Solar | 14_63L2 | 2011-12-23 | 2011-12-23 | 40 | 0 | 40 | [10 empty] | 2012-02-23 | 2012-04-25 | 42 | 0 | 42 | [10 empty] | 2012-12-24 |  | 2012-09-01 |  | STD |  | 2013-10-21 | 2014-01-02 | 49 | 0 | 49 | 2013-12-31 | 2013-12-31 | 2014-02-07 | Connected |  | No
National Grid | WESTMINSTER | 174268 | 1473 | 300 | Solar | 01_609W1 | 2011-12-26 | 2012-01-10 | 53 | 0 | 53 | [27 empty] | 2012-05-16 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 174271 | 1604 | 517 | Solar | 01_10J383 | 2011-12-26 | 2012-01-10 | 15 | 0 | 15 | [5 empty] | 2012-04-12 | 2012-06-22 | 48 | 0 | 48 | [5 empty] | 2012-04-12 | 2012-06-22 | 48 | 0 | 48 | [7 empty] | 2012-05-16 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BRADFORD | 174270 | 1835 | 229.68 | Solar | 14_43L8 | 2011-12-27 | 2012-12-27 | 0 | 0 | 0 | 2012-02-03 | 2012-02-03 | 0 | 0 | 0 | [20 empty] | 2012-05-01 | 2011-12-27 | 2012-05-01 |  | EXP | [6 empty] | 2013-01-29 | 2013-01-29 | 2013-06-26 | Connected |  | No
National Grid | HUBBARDSTON | 174293 | 1452 | 2000 | Solar | 01_602W2 | 2011-12-27 | 2012-01-19 | 18 | 0 | 18 | [25 empty] | 2012-12-06 | 2011-12-27 | 2012-10-01 | Yes | STD |  | 2014-01-24 | 2014-02-10 | 11 | 0 | 11 | 2013-11-08 | 2013-11-08 | 2013-12-09 | Connected |  | No
National Grid | PALMER | 178756 | 1069 | 2550 | Solar | 09_503L1 | 2011-12-27 | 2012-12-27 | 0 | 0 | 0 | [10 empty] | 2012-02-17 | 2012-05-16 | 60 | 0 | 60 | [10 empty] | 2014-09-03 |  | 2016-04-30 | Yes | STD |  | 2016-10-13 | 2017-03-20 | 106 | 0 | 106 | 2017-07-13 | 2017-07-13 | 2017-03-31 | Connected |  | No
National Grid | PALMER | 178757 | 1069 | 1000 | Solar | 09_503L1 | 2011-12-27 | 2012-12-27 | 0 | 0 | 0 | [27 empty] | 2012-11-01 |  | STD |  | 2016-10-13 | 2017-03-20 | 106 | 0 | 106 |  |  |  | Withdrawn |  | No
National Grid | PALMER | 178758 | 1069 | 1000 | Solar | 09_503L1 | 2011-12-27 | 2012-12-27 | 0 | 0 | 0 | [27 empty] | 2012-11-01 |  | STD |  | 2016-10-13 | 2017-03-20 | 106 | 0 | 106 |  |  |  | Withdrawn |  | No
National Grid | WEYMOUTH | 174264 | 2189 | 16.83 | Solar | 07_12W2 | 2011-12-28 | 2012-01-06 | 8 | 0 | 8 | 2012-01-19 | 2012-01-19 | 0 | 0 | 0 | [20 empty] | 2012-03-02 |  | 2012-04-01 |  | EXP | [6 empty] | 2012-03-30 | 2012-03-30 | 2012-04-12 | Connected |  | No
National Grid | SOMERSET | 174266 | 2725 | 26 | Solar | 05_11W84 | 2011-12-28 | 2012-01-09 | 10 | 0 | 10 | [25 empty] | 2012-04-12 |  | 2012-02-25 |  | EXP | [6 empty] | 2012-05-08 | 2012-05-08 | 2012-05-16 | Connected |  | No
National Grid | WESTFORD | 174303 | 1886 | 500 | Solar | 14_2387 | 2011-12-29 | 2012-01-27 | 19 | 0 | 19 | [27 empty] | 2012-06-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTFORD | 174304 | 1886 | 500 | Solar | 14_73L2 | 2011-12-29 | 2012-01-27 | 19 | 0 | 19 | [26 empty] | 2011-12-30 | 2012-02-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | FRANKLIN | 174278 | 2038 | 1725 | Solar | 05_344W3 | 2011-12-30 | 2011-12-30 | 25 | 0 | 25 | 2012-02-07 | 2012-02-07 | 0 | 0 | 0 | [20 empty] | 2013-01-03 | 2011-12-30 | 2012-07-02 | Yes | EXP |  | 2013-04-19 | 2013-06-14 | 39 | 0 | 39 | 2013-07-01 | 2013-07-01 | 2013-07-03 | Connected |  | No
National Grid | LAWRENCE | 174280 | 1843 | 600 | Solar | 14_8T2 | 2011-12-30 | 2012-01-13 | 62 | 0 | 62 | [25 empty] | 2012-12-12 |  | 2012-06-01 | Yes | EXP |  | 2012-11-16 | 2013-02-26 | 62 | 0 | 62 | 2012-12-17 | 2012-12-17 | 2012-12-31 | Connected |  | No
National Grid | ORANGE | 174309 | 1364 | 1800 | Solar | 09_705W2 | 2011-12-30 | 2012-01-30 | 28 | 0 | 28 | [26 empty] | 2011-12-31 | 2012-06-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 174281 | 1844 | 55 | Solar | 14_43L4 | 2011-12-31 | 2012-01-17 | 2 | 0 | 2 | [5 empty] | 2012-03-07 | 2012-02-02 | 0 | 0 | 0 | [5 empty] | 2012-03-07 | 2012-02-02 | 0 | 0 | 0 | [5 empty] | 2012-04-18 |  | 2012-01-24 |  | EXP |  | 2012-05-14 | 2012-05-18 | 4 | 0 | 4 | 2012-06-15 | 2012-06-15 | 2012-07-03 | Connected |  | No
National Grid | TYNGSBORO | 174305 | 1879 | 475 | Solar | 14_211L1 | 2012-01-01 | 2012-01-30 | 19 | 0 | 19 | [25 empty] | 2012-06-08 | 2012-01-01 | 2012-05-16 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | TYNGSBORO | 175350 | 1879 | 491 | Solar | 14_211L1 | 2012-01-01 | 2012-01-30 | 19 | 0 | 19 | [25 empty] | 2014-09-05 |  | 2014-12-31 | Yes | EXP |  | 2015-05-04 | 2015-05-22 | 14 | 0 | 14 | 2014-09-17 | 2014-09-17 | 2015-05-27 | Connected |  | No
National Grid | MELROSE | 174267 | 2176 | 75 | Solar | 12_16W6 | 2012-01-03 | 2012-01-10 | 10 | 0 | 10 | [25 empty] | 2012-03-15 | 2012-01-03 | 2012-04-02 |  | EXP | [6 empty] | 2012-06-26 | 2012-06-26 | 2012-07-05 | Connected |  | No
National Grid | CHARLTON | 178771 | 1507 | 1980 | Solar | 01_415L1 | 2012-01-03 | 2012-01-04 | 5 | 0 | 5 | [10 empty] | 2012-01-11 | 2013-09-25 | 402 | 0 | 402 | [10 empty] | 2014-05-21 |  | 2016-12-31 |  | STD |  | 2016-03-08 | 2016-09-02 | 123 | 0 | 123 | 2016-09-01 | 2016-09-01 | 2016-10-07 | Connected |  | No
National Grid | WRENTHAM | 178761 | 2093 | 625 | Natural Gas | 05_3422W4 | 2012-01-05 | 2012-02-13 | 43 | 0 | 43 | [25 empty] | 2012-09-18 | 2012-01-06 | 2012-02-18 |  | STD | [6 empty] | 2012-12-18 | 2012-12-18 | 2012-12-19 | Connected |  | Yes
National Grid | HOPEDALE | 174306 | 1747 | 95 | Solar | 05_335W9 | 2012-01-06 | 2012-01-30 | 22 | 0 | 22 | [25 empty] | 2012-04-27 |  | 2012-05-07 | Yes | EXP |  | 2012-06-06 | 2012-06-18 | 8 | 0 | 8 | 2012-07-16 | 2012-07-16 | 2012-07-24 | Connected |  | No
National Grid | PALMER | 174317 | 1069 | 1000 | Solar |  | 2012-01-07 | 2012-01-17 | 39 | 0 | 39 | [10 empty] | 2012-03-13 | 2012-05-30 | 55 | 0 | 55 | [12 empty] | 2012-02-07 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTMINSTER | 174307 | 1473 | 500 | Solar | 01_602W3 | 2012-01-10 | 2012-01-10 | 23 | 0 | 23 | 2012-02-13 | 2012-02-13 | 0 | 0 | 0 | [20 empty] | 2012-07-09 |  | 2012-07-01 |  | EXP | [6 empty] | 2012-12-05 | 2012-12-05 | 2012-12-06 | Connected |  | No
National Grid | WESTBOROUGH | 174313 | 1581 | 95 | Solar | 05_314W3 | 2012-01-11 | 2012-02-01 | 27 | 0 | 27 | [25 empty] | 2012-04-19 | 2012-01-12 | 2012-05-01 |  | EXP | [6 empty] | 2012-08-27 | 2012-08-27 | 2012-09-10 | Connected |  | No
National Grid | ROCKLAND | 174311 | 2370 | 2000 | Solar | 07_93W40 | 2012-01-12 | 2012-01-12 | 13 | 0 | 13 | [10 empty] | 2012-02-01 | 2012-05-03 | 63 | 0 | 63 | [10 empty] | 2012-10-11 |  | 2012-10-01 | Yes | STD |  | 2013-09-13 | 2013-12-28 | 72 | 0 | 72 | 2013-12-27 | 2013-12-27 | 2013-12-27 | Connected |  | No
National Grid | CHARLTON | 174211 | 1508 | 1000 | Solar | 01_415L1 | 2012-01-13 | 2012-02-14 | 27 | 0 | 27 | [27 empty] | 2012-10-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 174212 | 1508 | 1000 | Solar | 01_415L1 | 2012-01-13 | 2012-02-14 | 27 | 0 | 27 | [27 empty] | 2012-10-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 174213 | 1508 | 1000 | Solar | 01_415L1 | 2012-01-13 | 2012-02-14 | 27 | 0 | 27 | [27 empty] | 2012-10-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HUBBARDSTON | 174322 | 1452 | 1125 | Solar | 01_609W1 | 2012-01-13 | 2012-02-03 | 26 | 0 | 26 | [10 empty] | 2012-03-13 | 2012-05-23 | 49 | 0 | 49 | [12 empty] | 2012-02-08 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HUBBARDSTON | 174323 | 1452 | 1000 | Solar | 09_604W4 | 2012-01-13 | 2012-02-03 | 26 | 0 | 26 | [26 empty] | 2012-01-13 | 2012-02-08 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BARRE | 174324 | 1005 | 2000 | Solar | 09_604W1 | 2012-01-13 | 2012-02-06 | 26 | 0 | 26 | [25 empty] | 2013-06-07 |  | 2012-12-31 | Yes | STD | [6 empty] | 2014-05-28 | 2014-05-28 | 2014-05-29 | Connected |  | No
National Grid | CHARLTON | 174735 | 1508 | 1000 | Solar | 01_415L1 | 2012-01-13 | 2013-01-04 | 0 | 0 | 0 | [10 empty] | 2012-03-26 | 2012-06-13 | 55 | 0 | 55 | [12 empty] | 2013-05-15 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 174736 | 1508 | 1000 | Solar | 01_415L1 | 2012-01-13 | 2013-01-04 | 0 | 0 | 0 | [10 empty] | 2012-03-26 | 2012-06-13 | 55 | 0 | 55 | [12 empty] | 2013-05-15 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 174737 | 1508 | 1000 | Solar | 01_415L1 | 2012-01-13 | 2013-01-04 | 0 | 0 | 0 | [10 empty] | 2012-03-26 | 2012-06-13 | 55 | 0 | 55 | [12 empty] | 2013-05-15 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | FRANKLIN | 174314 | 2038 | 20.5 | Solar | 05_341W2 | 2012-01-16 | 2012-02-02 | 39 | 0 | 39 | [26 empty] | 2012-01-17 | 2012-03-15 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BRIMFIELD | 174315 | 1010 | 25 | Solar | 01_408L2 | 2012-01-17 | 2012-02-02 | 28 | 0 | 28 | [25 empty] | 2012-04-27 |  | 2012-03-30 |  | EXP |  | 2012-04-26 | 2012-07-27 | 63 | 0 | 63 | 2012-08-03 | 2012-08-03 | 2012-08-10 | Connected |  | No
National Grid | PALMER | 174316 | 1069 | 2000 | Solar |  | 2012-01-17 | 2012-01-17 | 39 | 0 | 39 | [10 empty] | 2012-03-13 | 2012-05-30 | 53 | 0 | 53 | [12 empty] | 2012-09-25 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | PALMER | 174318 | 1069 | 1000 | Solar |  | 2012-01-17 | 2012-01-17 | 39 | 0 | 39 | [10 empty] | 2012-03-13 | 2012-05-30 | 53 | 0 | 53 | [12 empty] | 2012-09-25 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | PALMER | 174319 | 1069 | 5000 | Solar |  | 2012-01-17 | 2012-01-17 | 39 | 0 | 39 | [10 empty] | 2012-03-13 | 2012-05-30 | 53 | 0 | 53 | [12 empty] | 2012-09-25 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | PALMER | 174320 | 1069 | 1000 | Solar |  | 2012-01-17 | 2012-01-17 | 39 | 0 | 39 | [10 empty] | 2012-03-13 | 2012-05-30 | 53 | 0 | 53 | [12 empty] | 2012-09-25 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LEICESTER | 174330 | 1524 | 14.28 | Solar | 01_21W2 | 2012-01-17 | 2012-02-07 | 31 | 0 | 31 | [25 empty] | 2012-04-06 |  | 2012-02-20 |  | EXP | [6 empty] | 2012-04-30 | 2012-04-30 | 2012-07-18 | Connected |  | No
National Grid | SOUTHBRIDGE | 174325 | 1550 | 2000 | Solar | 01_413L4 | 2012-01-18 | 2012-02-06 | 29 | 0 | 29 | [20 empty] | 2014-04-30 | 2014-06-19 | 34 | 0 | 34 |  | 2012-01-18 | 2012-06-30 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | EAST LONGMEADOW | 174331 | 1028 | 1500 | Solar | 09_508L2 | 2012-01-18 | 2012-02-08 | 224 | 0 | 224 | [10 empty] | 2013-01-25 | 2013-03-29 | 36 | 0 | 36 | [5 empty] | 2016-11-28 | 2016-11-28 | 0 | 0 | 0 | 2014-10-15 | 2012-01-18 | 2016-12-31 |  | STD |  | 2016-10-18 | 2017-01-27 | 68 | 0 | 68 |  |  | 2017-05-01 | Connected |  | No
National Grid | NORTHBOROUGH | 174332 | 1532 | 300 | Solar | 05_312W2 | 2012-01-18 | 2012-02-08 | 30 | 0 | 30 | [25 empty] | 2012-08-29 |  | 2012-07-01 | Yes | EXP |  | 2012-09-25 | 2012-11-29 | 29 | 0 | 29 | 2013-01-22 | 2013-01-22 | 2013-02-06 | Connected |  | No
National Grid | FRANKLIN | 174333 | 2038 | 231 | Solar | 05_348W7 | 2012-01-24 | 2012-02-08 | 30 | 0 | 30 | [25 empty] | 2012-05-17 |  | 2012-02-13 |  | EXP | [6 empty] | 2012-08-03 | 2012-08-03 | 2012-09-28 | Connected |  | No
National Grid | SWANSEA | 174334 | 2777 | 185.6 | Solar | 05_11W85 | 2012-01-24 | 2012-02-10 | 28 | 0 | 28 | [25 empty] | 2012-12-12 |  | 2012-02-15 |  | EXP | [6 empty] | 2012-11-21 | 2012-11-21 | 2012-12-13 | Connected |  | No
National Grid | SPENCER | 174335 | 1562 | 2000 | Solar | 01_21W1 | 2012-01-25 | 2012-01-25 | 40 | 0 | 40 | [10 empty] | 2012-03-23 | 2012-05-16 | 37 | 0 | 37 | [12 empty] | 2012-12-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SUTTON | 174336 | 1590 | 42 | Solar | 05_320W5 | 2012-01-26 | 2012-02-10 | 28 | 0 | 28 | [25 empty] | 2012-04-13 |  | 2012-03-09 |  | EXP | [6 empty] | 2012-04-27 | 2012-04-27 | 2012-05-04 | Connected |  | No
National Grid | SWANSEA | 174337 | 2777 | 499 | Solar | 05_11W85 | 2012-01-27 | 2012-02-10 | 29 | 0 | 29 | [25 empty] | 2013-01-24 |  | 2012-04-14 |  | STD | [6 empty] | 2015-01-29 | 2015-01-29 | 2015-02-18 | Connected |  | No
National Grid | SWANSEA | 174338 | 2777 | 260 | Solar | 05_11W85 | 2012-01-27 | 2012-02-10 | 29 | 0 | 29 | [20 empty] | 2014-04-30 | 2014-04-30 | 0 | 0 | 0 | 2013-03-01 | 2012-01-30 | 2012-02-15 |  | STD | [6 empty] | 2015-02-03 | 2015-02-03 | 2015-05-08 | Connected |  | No
National Grid | STOUGHTON | 174339 | 2072 | 1725 | Solar | 07_94W42 | 2012-01-30 | 2012-01-30 | 37 | 0 | 37 | [10 empty] | 2012-03-23 | 2012-05-05 | 30 | 0 | 30 | [10 empty] | 2013-04-08 |  | 2016-12-31 |  | STD |  | 2015-08-20 | 2016-03-31 | 151 | 0 | 151 | 2016-04-05 | 2016-04-05 | 2016-04-05 | Connected |  | No
National Grid | METHUEN | 174341 | 1844 | 225 | Solar | 14_75L6 | 2012-01-30 | 2012-02-13 | 28 | 0 | 28 | [27 empty] | 2012-06-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RUTLAND | 174218 | 1543 | 11.38 | Solar | 01_55W1 | 2012-01-31 | 2012-02-17 | 25 | 0 | 25 | [25 empty] | 2012-04-13 | 2012-01-31 | 2012-03-01 |  | EXP | [6 empty] | 2012-07-23 | 2012-07-23 | 2012-08-07 | Connected |  | No
National Grid | LANCASTER | 174230 | 1523 | 2500 | Solar | 01_227W3 | 2012-01-31 | 2012-02-21 | 24 | 0 | 24 | [25 empty] | 2013-01-22 | 2012-01-31 | 2014-06-30 | Yes | STD |  | 2014-01-13 | 2014-07-18 | 127 | 0 | 127 | 2014-01-09 | 2014-01-09 | 2014-01-09 | Connected |  | No
National Grid | LANCASTER | 174231 | 1523 | 2000 | Solar | 01_227W1 | 2012-01-31 | 2012-02-21 | 24 | 0 | 24 | [25 empty] | 2013-01-22 |  | 2014-06-30 | Yes | STD |  | 2014-01-13 | 2014-07-18 | 127 | 0 | 127 | 2014-06-19 | 2014-06-19 | 2014-06-19 | Connected |  | No
National Grid | LANCASTER | 174232 | 1523 | 2000 | Solar | 01_227W3 | 2012-01-31 | 2012-02-21 | 24 | 0 | 24 | [25 empty] | 2013-01-22 |  | 2012-11-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SOUTH EASTON | 174210 | 2375 | 100 | Solar | 07_98W48 | 2012-02-01 | 2012-02-13 | 28 | 0 | 28 | [25 empty] | 2012-12-12 |  | 2012-02-18 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTH ADAMS | 174233 | 1247 | 1000 | Solar | 09_1001W1 | 2012-02-01 | 2012-02-02 | 36 | 0 | 36 | [10 empty] | 2012-03-27 | 2012-05-10 | 31 | 0 | 31 | [12 empty] | 2013-08-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LAWRENCE | 174234 | 1843 | 500 | Solar | 14_8L3 | 2012-02-02 | 2012-02-22 | 24 | 0 | 24 | [10 empty] | 2012-03-28 | 2012-09-24 | 123 | 0 | 123 | [12 empty] | 2012-06-01 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 174235 | 1843 | 725 | Solar | 14_8L3 | 2012-02-02 | 2012-02-22 | 24 | 0 | 24 | [10 empty] | 2012-03-28 | 2012-09-24 | 123 | 0 | 123 | [12 empty] | 2012-06-01 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | STOUGHTON | 174221 | 2072 | 500 | Solar |  | 2012-02-07 | 2012-02-21 | 51 | 0 | 51 | [27 empty] | 2012-07-01 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | EVERETT | 174222 | 2149 | 500 |  | 12_10J6 | 2012-02-07 | 2012-02-21 | 19 | 0 | 19 | [27 empty] | 2012-06-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LENOX | 174201 | 1240 | 1000 | Solar | 09_1103W2 | 2012-02-09 | 2012-03-05 | 20 | 0 | 20 | [27 empty] | 2012-08-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HALIFAX | 174219 | 2338 | 2000 | Solar | 07_912W75 | 2012-02-09 | 2012-02-17 | 25 | 0 | 25 | [27 empty] | 2012-02-22 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HALIFAX | 174220 | 2338 | 500 | Solar | 07_912W75 | 2012-02-09 | 2012-02-20 | 24 | 0 | 24 | [27 empty] | 2012-07-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | EVERETT | 174223 | 2149 | 500 |  | 12_10J6 | 2012-02-09 | 2012-02-21 | 35 | 0 | 35 | [27 empty] | 2012-02-26 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ORANGE | 174224 | 1364 | 6000 | Solar | 09_705W2 | 2012-02-09 | 2012-02-21 | 37 | 0 | 37 | [27 empty] | 2012-10-09 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ORANGE | 174225 | 1364 | 1000 | Solar | 09_705W2 | 2012-02-09 | 2012-02-21 | 37 | 0 | 37 | [27 empty] | 2012-10-09 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ORANGE | 174226 | 1364 | 1000 | Solar | 09_705W2 | 2012-02-09 | 2012-02-21 | 37 | 0 | 37 | [27 empty] | 2012-10-09 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ORANGE | 174227 | 1364 | 1000 | Solar | 09_705W2 | 2012-02-09 | 2012-02-21 | 37 | 0 | 37 | [27 empty] | 2012-10-09 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ORANGE | 174228 | 1364 | 1000 | Solar | 09_705W2 | 2012-02-09 | 2012-02-21 | 37 | 0 | 37 | [26 empty] | 2012-02-09 | 2012-10-09 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HALIFAX | 175062 | 2338 | 2500 | Solar | 07_912W75 | 2012-02-09 | 2012-02-17 | 25 | 0 | 25 | [20 empty] | 2014-04-30 | 2014-04-30 | 0 | 0 | 0 | 2014-04-11 |  | 2013-03-15 | Yes | STD |  | 2015-06-03 | 2015-10-31 | 104 | 0 | 104 | 2012-10-22 | 2012-10-22 | 2015-08-11 | Connected |  | No
National Grid | BRIDGEWATER | 174236 | 2324 | 110 | Solar | 07_912W21 | 2012-02-10 | 2012-02-24 | 23 | 0 | 23 | 2012-03-29 | 2012-03-29 | 0 | 0 | 0 | [20 empty] | 2012-12-12 |  | 2012-04-05 |  | EXP | [6 empty] | 2012-11-28 | 2012-11-28 | 2012-12-18 | Connected |  | No
National Grid | FRANKLIN | 174237 | 2038 | 15.69 | Solar | 05_344W5 | 2012-02-13 | 2012-02-24 | 21 | 0 | 21 | [25 empty] | 2012-05-03 | 2012-02-15 | 2012-03-11 |  | EXP | [6 empty] | 2012-06-07 | 2012-06-07 | 2012-06-19 | Connected |  | Yes
National Grid | PALMER | 174238 | 1069 | 2000 | Solar | 09_514L1 | 2012-02-15 | 2012-02-15 | 29 | 0 | 29 | [10 empty] | 2012-03-29 | 2012-05-14 | 31 | 0 | 31 | [10 empty] | 2012-12-12 |  | 2012-04-01 | Yes | STD |  | 2013-12-19 | 2014-01-24 | 23 | 0 | 23 | 2013-12-24 | 2013-12-24 | 2013-12-27 | Connected |  | No
National Grid | NORTH OXFORD | 174250 | 1537 | 95 | Solar | 01_406L4 | 2012-02-15 | 2012-02-29 | 22 | 0 | 22 | [25 empty] | 2012-05-21 |  | 2012-06-01 |  | EXP | [6 empty] | 2012-06-18 | 2012-06-18 | 2012-06-29 | Connected |  | No
National Grid | FOXBOROUGH | 178749 | 2035 | 75 | Solar | 05_3424W1 | 2012-02-15 | 2012-02-28 | 22 | 0 | 22 | [25 empty] | 2012-12-12 | 2012-02-15 | 2012-07-01 |  | EXP | [6 empty] | 2012-12-19 | 2012-12-19 | 2012-12-19 | Connected |  | No
National Grid | FOXBOROUGH | 178750 | 2035 | 495 | Solar | 05_3424W1 | 2012-02-15 | 2012-02-28 | 22 | 0 | 22 | 2012-03-30 | 2012-03-30 | 0 | 0 | 0 | [20 empty] | 2012-06-29 | 2012-02-15 | 2012-07-01 |  | EXP | [6 empty] | 2012-12-19 | 2012-12-19 | 2012-12-19 | Connected |  | No
National Grid | FOXBOROUGH | 178751 | 2035 | 125 | Solar | 05_3424W1 | 2012-02-15 | 2012-02-28 | 22 | 0 | 22 | 2012-03-30 | 2012-03-30 | 0 | 0 | 0 | [20 empty] | 2012-06-29 | 2012-02-15 | 2012-07-01 |  | EXP | [6 empty] | 2012-12-13 | 2012-12-13 | 2012-12-19 | Connected |  | No
National Grid | FOXBOROUGH | 178752 | 2035 | 45 | Solar | 05_349W1 | 2012-02-15 | 2012-02-28 | 22 | 0 | 22 | [25 empty] | 2012-03-30 | 2012-02-15 | 2012-07-01 |  | EXP | [6 empty] | 2012-12-17 | 2012-12-17 | 2012-12-28 | Connected |  | No
National Grid | FOXBOROUGH | 178753 | 2035 | 62 | Solar | 05_349W1 | 2012-02-15 | 2012-02-28 | 22 | 0 | 22 | [10 empty] | 2012-03-30 | 2012-07-05 | 65 | 0 | 65 | [10 empty] | 2012-07-05 | 2012-02-15 | 2012-07-01 |  | STD | [6 empty] | 2012-08-08 | 2012-08-08 | 2012-12-20 | Connected |  | No
National Grid | FOXBOROUGH | 178754 | 2035 | 45 | Solar | 05_349W1 | 2012-02-15 | 2012-02-28 | 22 | 0 | 22 | [25 empty] | 2012-08-08 |  | 2012-07-01 |  | EXP |  | 2012-09-25 | 2012-09-12 | 0 | 0 | 0 | 2012-08-08 | 2012-08-08 | 2012-12-28 | Connected |  | No
National Grid | SEEKONK | 174239 | 2771 | 500 | Solar | 05_9L5 | 2012-02-17 | 2012-02-24 | 23 | 0 | 23 | [27 empty] | 2012-06-01 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WARE | 174242 | 1082 | 2500 | Solar |  | 2012-02-21 | 2012-02-27 | 0 | 0 | 0 | [27 empty] | 2012-12-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WARE | 174243 | 1082 | 2000 | Solar | 09_523L4 | 2012-02-21 | 2012-02-27 | 22 | 0 | 22 | [10 empty] | 2012-03-29 | 2012-05-24 | 39 | 0 | 39 | [12 empty] | 2014-07-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTHBOROUGH | 174244 | 1532 | 10.32 | Solar | 05_313W3 | 2012-02-22 | 2012-02-27 | 22 | 0 | 22 | [25 empty] | 2012-05-01 |  | 2012-05-15 |  | EXP | [6 empty] | 2012-06-18 | 2012-06-18 | 2012-07-26 | Connected |  | No
National Grid | SPENCER | 174246 | 1562 | 1000 | Solar | 01_552L1 | 2012-02-23 | 2012-02-28 | 21 | 0 | 21 | [10 empty] | 2012-03-29 | 2012-10-01 | 127 | 0 | 127 | [12 empty] | 2012-11-06 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SPENCER | 174247 | 1562 | 1000 | Solar |  | 2012-02-23 | 2012-02-28 | 1 | 0 | 1 | [27 empty] | 2012-11-06 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SPENCER | 174248 | 1562 | 1000 | Solar | 01_552L1 | 2012-02-23 | 2012-02-28 | 21 | 0 | 21 | [10 empty] | 2012-03-29 | 2012-10-01 | 127 | 0 | 127 | [12 empty] | 2012-11-06 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | FRANKLIN | 174249 | 2038 | 250 | Solar | 05_348W6 | 2012-02-23 | 2012-02-29 | 22 | 0 | 22 | 2012-04-02 | 2012-04-02 | 0 | 0 | 0 | 2012-10-29 | 2012-11-05 | 0 | 0 | 0 | [5 empty] | 2012-10-29 | 2012-11-05 | 0 | 0 | 0 | 2012-11-05 | 2012-11-05 | 0 | 0 | 0 | 2012-11-05 |  | 2012-06-01 |  | EXP | [6 empty] | 2012-12-13 | 2012-12-13 | 2012-12-17 | Connected |  | No
National Grid | NEW SALEM | 174251 | 1355 | 18 | Solar | 09_705W2 | 2012-02-24 | 2012-02-29 | 22 | 0 | 22 | [25 empty] | 2012-05-21 |  | 2012-06-01 |  | EXP | [6 empty] | 2012-05-21 | 2012-05-21 | 2012-10-19 | Connected |  | No
National Grid | HUBBARDSTON | 174209 | 1452 | 500 | Solar | 09_604W4 | 2012-02-27 | 2012-03-07 | 18 | 0 | 18 | [27 empty] | 2012-10-01 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | GLOUCESTER | 174252 | 1930 | 450 | Solar | 12_2327 | 2012-02-27 | 2012-03-01 | 27 | 0 | 27 | 2012-04-10 | 2012-04-10 | 0 | 0 | 0 | [20 empty] | 2012-12-13 |  | 2012-06-15 |  | EXP | [6 empty] | 2012-12-31 | 2012-12-31 | 2012-12-31 | Connected |  | No
National Grid | WORCESTER | 174253 | 1602 | 1095 | Solar | 01_23W3 | 2012-02-27 | 2012-02-27 | 25 | 0 | 25 | [10 empty] | 2012-04-03 | 2012-05-21 | 33 | 0 | 33 | [11 empty] | 2012-02-27 | 2012-12-01 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | FALL RIVER | 174254 | 2720 | 95 | Solar | 05_106W46 | 2012-02-27 | 2012-03-01 | 21 | 0 | 21 | [25 empty] | 2012-12-12 |  | 2012-06-01 |  | EXP |  | 2012-12-04 | 2012-12-17 | 9 | 0 | 9 | 2012-08-14 | 2012-08-14 | 2013-05-03 | Connected |  | No
National Grid | NORWELL | 174255 | 2061 | 50 | Solar | 07_96W40 | 2012-02-28 | 2012-03-01 | 23 | 0 | 23 | [25 empty] | 2012-12-12 |  | 2012-07-01 |  | EXP | [6 empty] | 2013-07-03 | 2013-07-03 | 2013-07-24 | Connected |  | No
National Grid | NORWELL | 174256 | 2061 | 135 | Solar | 07_96W40 | 2012-02-28 | 2012-03-01 | 23 | 0 | 23 | [27 empty] | 2012-07-01 |  | EXP | [6 empty] | 2012-09-13 | 2012-09-13 |  | Withdrawn |  | No
National Grid | HARVARD | 174259 | 1451 | 217 | Solar | 01_201W2 | 2012-02-28 | 2012-03-02 | 20 | 0 | 20 | [27 empty] | 2012-06-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORWELL | 174839 | 2061 | 260 | Solar | 07_96W40 | 2012-02-28 | 2012-03-31 | 2 | 0 | 2 | 2012-04-04 | 2012-04-04 | 0 | 0 | 0 | [20 empty] | 2012-09-13 |  | 2012-09-11 |  | EXP | [6 empty] | 2012-09-13 | 2012-09-13 | 2013-08-06 | Connected |  | No
National Grid | NORWELL | 175057 | 2061 | 135 | Solar | 07_96W40 | 2012-02-28 | 2012-03-01 | 23 | 0 | 23 | [25 empty] | 2012-10-17 |  | 2012-11-23 |  | EXP | [6 empty] | 2012-10-18 | 2012-10-18 | 2013-08-15 | Connected |  | No
National Grid | LENOX | 174202 | 1240 | 1000 | Solar |  | 2012-02-29 | 2012-03-05 | 20 | 0 | 20 | [27 empty] | 2012-08-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LENOX | 174203 | 1240 | 1000 | Solar | 09_1103W2 | 2012-02-29 | 2012-03-05 | 20 | 0 | 20 | [27 empty] | 2012-08-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LENOX | 174204 | 1240 | 750 | Solar | 09_1103W2 | 2012-02-29 | 2012-03-05 | 20 | 0 | 20 | [26 empty] | 2012-02-29 | 2012-08-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BOLTON | 174205 | 1740 | 4950 | Solar | 01_225W1 | 2012-02-29 | 2012-02-29 | 23 | 0 | 23 | [10 empty] | 2012-04-03 | 2012-05-22 | 34 | 0 | 34 | [10 empty] | 2012-11-29 |  | 2013-01-01 | Yes | STD |  | 2013-10-11 | 2013-12-03 | 34 | 0 | 34 | 2013-12-12 | 2013-12-12 | 2013-12-12 | Connected |  | No
National Grid | BOLTON | 174206 | 1740 | 2450 | Solar | 01_216W4 | 2012-02-29 | 2012-02-29 | 23 | 0 | 23 | [10 empty] | 2012-04-03 | 2012-05-22 | 34 | 0 | 34 | [10 empty] | 2012-11-29 |  | 2013-01-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BOLTON | 174207 | 1740 | 500 | Solar | 01_225W1 | 2012-02-29 | 2012-03-06 | 19 | 0 | 19 | [27 empty] | 2013-01-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BOLTON | 174208 | 1740 | 450 | Solar | 01_225W1 | 2012-02-29 | 2012-03-06 | 19 | 0 | 19 | [27 empty] | 2013-01-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BELCHERTOWN | 174257 | 1007 | 20 | Solar | 09_509L2 | 2012-02-29 | 2012-03-02 | 30 | 0 | 30 | [25 empty] | 2012-05-21 |  | 2012-05-14 |  | EXP | [6 empty] | 2012-05-21 | 2012-05-21 | 2012-10-22 | Connected |  | No
National Grid | LEOMINSTER | 174258 | 1453 | 111 | Solar | 01_207W3 | 2012-02-29 | 2012-03-02 | 20 | 0 | 20 | [25 empty] | 2012-12-12 |  | 2012-08-06 |  | EXP | [6 empty] | 2012-08-16 | 2012-08-16 | 2013-03-02 | Connected |  | No
National Grid | OXFORD | 174261 | 1540 | 94.25 | Solar | 01_406L4 | 2012-02-29 | 2012-03-05 | 30 | 0 | 30 | [25 empty] | 2012-10-01 |  | 2012-06-01 |  | EXP | [6 empty] | 2012-10-19 | 2012-10-19 | 2012-11-26 | Connected |  | No
National Grid | LENOX | 174262 | 1240 | 1250 | Solar | 09_1103W2 | 2012-02-29 | 2012-03-05 | 20 | 0 | 20 | [25 empty] | 2013-03-28 |  | 2012-08-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BELCHERTOWN | 174260 | 1007 | 34.2 | Solar | 09_509L2 | 2012-03-02 | 2012-03-05 | 19 | 0 | 19 | [25 empty] | 2012-05-31 |  | 2012-06-01 |  | EXP | [6 empty] | 2012-05-31 | 2012-05-31 | 2012-07-26 | Connected |  | No
National Grid | PETERSHAM | 174175 | 1366 | 500 | Solar | 09_604W1 | 2012-03-04 | 2012-03-07 | 21 | 0 | 21 | [27 empty] | 2012-08-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | PETERSHAM | 174176 | 1366 | 500 | Solar | 09_604W1 | 2012-03-04 | 2012-03-07 | 21 | 0 | 21 | [27 empty] | 2012-08-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SWANSEA | 174178 | 2777 | 20 | Solar | 05_11W83 | 2012-03-05 | 2012-03-08 | 25 | 0 | 25 | [25 empty] | 2012-06-05 |  | 2012-05-16 |  | EXP | [6 empty] | 2012-06-05 | 2012-06-05 | 2012-08-02 | Connected |  | No
National Grid | WESTMINSTER | 174177 | 1473 | 11.4 | Solar | 01_602W2 | 2012-03-06 | 2012-03-08 | 30 | 0 | 30 | [25 empty] | 2012-06-04 |  | 2012-06-04 |  | EXP | [6 empty] | 2012-06-04 | 2012-06-04 | 2012-07-16 | Connected |  | No
National Grid | NORTHBOROUGH | 174179 | 1532 | 54 | Solar | 05_313W3 | 2012-03-06 | 2012-03-09 | 21 | 0 | 21 | [25 empty] | 2012-06-08 | 2012-03-12 01:00 | 2012-08-01 |  | EXP | [6 empty] | 2012-06-08 | 2012-06-08 | 2012-10-02 | Connected |  | No
National Grid | LANCASTER | 174187 | 1523 | 500 | Solar | 01_227W1 | 2012-03-12 01:00 | 2012-03-21 | 11 | 0 | 11 | 2012-04-05 | 2012-04-05 | 0 | 0 | 0 | [20 empty] | 2013-01-24 | 2012-03-13 01:00 | 2012-06-01 | Yes | EXP |  | 2013-07-15 | 2013-09-27 | 53 | 0 | 53 | 2013-09-26 | 2013-09-26 | 2013-09-27 | Connected |  | No
National Grid | DOUGLAS | 174183 | 1516 | 3000 | Solar | 05_320W4 | 2012-03-13 01:00 | 2012-03-13 | 3 | 0 | 3 | [10 empty] | 2012-03-19 | 2012-05-24 | 47 | 0 | 47 | [10 empty] | 2013-01-11 |  | 2012-08-01 | Yes | STD |  | 2013-07-03 | 2013-09-27 | 60 | 0 | 60 | 2013-10-04 | 2013-10-04 | 2013-10-04 | Connected |  | No
National Grid | DOUGLAS | 174184 | 1516 | 1000 | Solar | 05_321W4 | 2012-03-13 01:00 | 2012-03-19 | 1 | 0 | 1 | [27 empty] | 2012-08-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTHAMPTON | 174170 | 1060 | 50 | Natural Gas | 09_901W1 | 2012-03-14 01:00 | 2012-03-19 | 126 | 0 | 126 | 2012-09-18 | 2014-04-04 | 360 | 0 | 360 | [20 empty] | 2013-02-20 |  | 2012-11-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SEEKONK | 174188 | 2771 | 2000 | Solar | 05_7L5 | 2012-03-14 01:00 | 2012-03-21 | 11 | 0 | 11 | [27 empty] | 2012-11-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SOUTHBRIDGE | 174118 | 1550 | 1725 | Solar | 01_413L2 | 2012-03-15 01:00 | 2012-03-19 | 16 | 0 | 16 | [27 empty] | 2012-08-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ORANGE | 174190 | 1364 | 1000 | Solar | 09_705W2 | 2012-03-15 01:00 | 2012-03-22 | 16 | 0 | 16 | [27 empty] | 2012-07-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | PETERSHAM | 174191 | 1366 | 1750 | Solar | 09_604W1 | 2012-03-15 01:00 | 2012-03-22 | 11 | 0 | 11 | [27 empty] | 2012-08-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 174193 | 1507 | 14.19 | Solar | 01_415L2 | 2012-03-16 01:00 | 2012-03-22 | 13 | 0 | 13 | [25 empty] | 2012-06-11 |  | 2012-04-19 |  | EXP | [6 empty] | 2012-06-11 | 2012-06-11 | 2012-08-03 | Connected |  | No
National Grid | NORTHBOROUGH | 174194 | 1532 | 22.5 | Solar | 05_313W3 | 2012-03-19 01:00 | 2012-03-23 | 21 | 0 | 21 | [25 empty] | 2012-06-14 |  | 2012-06-04 |  | EXP | [6 empty] | 2012-06-12 | 2012-06-12 | 2012-07-25 | Connected |  | No
National Grid | FOXBOROUGH | 178748 | 2035 | 30 | Solar | 05_3432W2 | 2012-03-19 01:00 | 2012-03-22 | 13 | 0 | 13 | [25 empty] | 2012-08-10 |  | 2012-06-01 |  | EXP | [6 empty] | 2012-06-11 | 2012-06-11 | 2012-08-27 | Connected |  | No
National Grid | WEST BRIDGEWATER | 174196 | 2379 | 1500 | Solar | 07_797W19 | 2012-03-20 01:00 | 2012-03-22 | 15 | 0 | 15 | [25 empty] | 2013-02-20 | 2012-03-20 01:00 | 2012-11-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH EASTON | 174197 | 2356 | 2000 | Solar | 07_98W46 | 2012-03-20 01:00 | 2012-03-28 | 13 | 0 | 13 | [10 empty] | 2012-04-16 | 2012-09-04 | 96 | 0 | 96 | [10 empty] | 2013-07-17 |  | 2014-06-01 | Yes | STD |  | 2014-06-05 | 2014-07-11 | 24 | 0 | 24 | 2014-07-25 | 2014-07-25 | 2014-07-31 | Connected |  | No
National Grid | GRANBY | 174198 | 1033 | 3300 | Solar | 09_527L1 | 2012-03-20 01:00 | 2012-03-22 | 18 | 0 | 18 | [27 empty] | 2012-10-15 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WEST BRIDGEWATER | 174898 | 2379 | 1800 | Solar | 07_797W19 | 2012-03-20 01:00 | 2012-03-22 | 15 | 0 | 15 | [10 empty] | 2012-04-12 | 2012-07-18 | 65 | 0 | 65 | [10 empty] | 2013-02-20 |  | 2012-12-03 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | CHESHIRE | 174199 | 1225 | 450 | Solar | 09_1021W1 | 2012-03-22 01:00 | 2012-03-22 | 17 | 0 | 17 | 2012-04-16 | 2012-04-16 | 0 | 0 | 0 | [20 empty] | 2012-08-03 |  | 2012-09-30 |  | EXP | [6 empty] | 2012-12-14 | 2012-12-14 | 2012-12-26 | Connected |  | No
National Grid | PALMER | 174109 | 1069 | 1000 | Solar |  | 2012-03-27 01:00 | 2012-03-27 | 14 | 0 | 14 | [10 empty] | 2012-04-16 | 2012-05-31 | 31 | 0 | 31 | [12 empty] | 2012-10-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | PALMER | 174110 | 1069 | 2000 | Solar |  | 2012-03-27 01:00 | 2012-03-27 | 14 | 0 | 14 | [10 empty] | 2012-04-16 | 2012-05-31 | 31 | 0 | 31 | [11 empty] | 2012-03-27 01:00 | 2012-10-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTBOROUGH | 174200 | 1581 | 260 | Solar | 05_312W1 | 2012-03-27 01:00 | 2012-03-27 | 14 | 0 | 14 | [25 empty] | 2012-12-12 |  | 2012-10-01 |  | EXP |  | 2013-02-06 | 2013-03-04 | 13 | 0 | 13 | 2013-03-21 | 2013-03-21 | 2013-04-01 | Connected |  | Yes
National Grid | EAST LONGMEADOW | 174111 | 1028 | 695 | Solar | 09_522L4 | 2012-03-28 01:00 | 2012-03-28 | 36 | 0 | 36 | [10 empty] | 2012-05-18 | 2012-07-02 | 29 | 0 | 29 | [12 empty] | 2012-09-10 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | EAST LONGMEADOW | 174112 | 1028 | 695 | Solar | 09_522L4 | 2012-03-28 01:00 | 2012-03-28 | 36 | 0 | 36 | [10 empty] | 2012-05-18 | 2012-07-02 | 29 | 0 | 29 | [12 empty] | 2012-09-10 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HAVERHILL | 174120 | 1830 | 2000 | Solar | 14_43L7 | 2012-03-29 01:00 | 2012-04-05 | 9 | 0 | 9 | [27 empty] | 2013-03-29 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HAVERHILL | 174121 | 1830 | 2000 | Solar | 14_43L7 | 2012-03-29 01:00 | 2012-04-05 | 9 | 0 | 9 | [27 empty] | 2013-03-29 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ORANGE | 174113 | 1364 | 13.54 | Solar | 09_705W2 | 2012-03-30 01:00 | 2012-04-02 | 10 | 0 | 10 | [25 empty] | 2012-07-27 | 2012-03-30 01:00 | 2012-05-28 |  | EXP | [6 empty] | 2012-07-27 | 2012-07-27 | 2012-11-29 | Connected |  | No
National Grid | SOUTH EASTON | 174114 | 2375 | 1500 | Solar | 07_92W54 | 2012-03-30 01:00 | 2012-04-02 | 10 | 0 | 10 | [10 empty] | 2012-04-17 | 2012-06-25 | 47 | 0 | 47 | [10 empty] | 2012-12-05 |  | 2012-10-31 | Yes | STD |  | 2013-07-31 | 2013-09-27 | 41 | 0 | 41 | 2013-09-25 | 2013-09-25 | 2013-10-24 | Connected |  | Yes
National Grid | WESTMINSTER | 174115 | 1473 | 2000 | Solar | 01_609W2 | 2012-03-30 01:00 | 2012-04-03 | 12 | 0 | 12 | [27 empty] | 2012-11-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LANCASTER | 174116 | 1523 | 2000 | Solar | 01_225W1 | 2012-03-30 01:00 | 2012-04-03 | 12 | 0 | 12 | [27 empty] | 2012-11-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SOUTH HAMILTON | 174122 | 1982 | 250 | Solar | 12_51T2 | 2012-04-04 01:00 | 2012-04-06 | 9 | 0 | 9 | [27 empty] | 2012-07-15 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOUTH HAMILTON | 174123 | 1982 | 128.25 | Solar | 12_51T2 | 2012-04-04 01:00 | 2012-04-06 | 9 | 0 | 9 | [27 empty] | 2012-07-15 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 174124 | 1604 | 1000 |  | 01_18J394 | 2012-04-05 01:00 | 2012-04-11 | 6 | 0 | 6 | [26 empty] | 2012-04-05 15:18 | 2012-08-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HAVERHILL | 174119 | 1830 | 4968 | Solar | 14_2356 | 2012-04-05 15:18 | 2012-04-05 | 9 | 0 | 9 | [25 empty] | 2014-05-12 | 2012-04-06 01:00 | 2017-12-29 |  | STD |  | 2017-02-15 | 2017-08-21 | 129 | 0 | 129 | 2017-12-19 | 2017-12-19 | 2017-04-03 | Connected |  | No
National Grid | LANCASTER | 174125 | 1523 | 3000 | Solar | 01_225W3 | 2012-04-06 01:00 | 2012-04-10 | 8 | 0 | 8 | [10 empty] | 2012-04-23 | 2012-06-22 | 42 | 0 | 42 | [10 empty] | 2013-01-04 |  | 2012-12-01 | Yes | STD |  | 2013-10-22 | 2014-02-22 | 83 | 0 | 83 | 2013-11-29 | 2013-11-29 | 2013-11-30 | Connected |  | No
National Grid | LANCASTER | 174136 | 1523 | 1000 | Solar | 01_225W3 | 2012-04-06 01:00 | 2012-04-10 | 8 | 0 | 8 | [27 empty] | 2012-12-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORWELL | 174137 | 2061 | 20.5 | Solar | 07_96W43 | 2012-04-06 01:00 | 2012-04-06 | 10 | 0 | 10 | [25 empty] | 2012-08-02 |  | 2012-06-04 |  | EXP | [6 empty] | 2013-01-04 | 2013-01-04 | 2013-01-11 | Connected |  | No
National Grid | AMESBURY | 174139 | 1913 | 22.8 | Solar | 14_5J11 | 2012-04-10 01:00 | 2012-04-12 | 6 | 0 | 6 | [25 empty] | 2012-07-31 | 2012-04-10 01:00 | 2012-06-01 |  | EXP | [6 empty] | 2012-08-06 | 2012-08-06 | 2012-11-19 | Connected |  | No
National Grid | ATTLEBORO | 174145 | 2703 | 9.99 | Solar | 05_9L4 | 2012-04-10 01:00 | 2012-04-12 | 13 | 0 | 13 | 2012-05-02 | 2012-05-02 | 0 | 0 | 0 | [20 empty] | 2012-12-18 | 2012-04-10 01:00 | 2012-06-01 |  | EXP |  | 2013-01-21 | 2013-02-25 | 19 | 0 | 19 | 2013-03-04 | 2013-03-04 | 2013-03-15 | Connected |  | No
National Grid | ATTLEBORO | 174146 | 2703 | 9.99 | Solar | 05_9L4 | 2012-04-10 01:00 | 2012-04-12 | 14 | 0 | 14 | 2012-05-03 | 2012-05-03 | 0 | 0 | 0 | [20 empty] | 2012-12-18 | 2012-04-10 01:00 | 2012-06-01 |  | EXP |  | 2013-01-21 | 2013-02-25 | 19 | 0 | 19 | 2013-03-04 | 2013-03-04 | 2013-03-15 | Connected |  | No
National Grid | ATTLEBORO | 174147 | 2703 | 9.99 | Solar | 05_9L4 | 2012-04-10 01:00 | 2012-04-12 | 14 | 0 | 14 | 2012-05-03 | 2012-05-03 | 0 | 0 | 0 | [20 empty] | 2012-12-18 |  | 2012-06-01 |  | EXP |  | 2013-01-21 | 2013-02-25 | 19 | 0 | 19 | 2013-03-04 | 2013-03-04 | 2013-03-15 | Connected |  | No
National Grid | BILLERICA | 174140 | 1821 | 82.3 | Solar | 14_92L6 | 2012-04-11 01:00 | 2012-04-13 | 9 | 0 | 9 | [25 empty] | 2012-08-06 | 2012-04-13 01:00 | 2012-07-06 |  | EXP | [6 empty] | 2012-08-06 | 2012-08-06 | 2012-12-27 | Connected |  | No
National Grid | ORANGE | 174141 | 1364 | 52.8 | Solar | 09_702W3 | 2012-04-13 01:00 | 2012-04-17 | 8 | 0 | 8 | 2012-04-27 | 2012-04-27 | 0 | 0 | 0 | [20 empty] | 2012-12-12 | 2012-04-16 01:00 | 2012-06-01 |  | EXP | [6 empty] | 2013-04-29 | 2013-04-29 | 2013-04-29 | Connected |  | No
National Grid | PALMER | 174158 | 1069 | 3800 | Solar | 09_0504 | 2012-04-16 01:00 | 2012-04-19 | 14 | 0 | 14 | [10 empty] | 2012-05-09 | 2012-06-26 | 32 | 0 | 32 | [5 empty] | 2013-08-17 | 2013-10-15 | 39 | 0 | 39 | 2013-08-09 |  | 2016-12-31 |  | STD | [6 empty] | 2016-02-23 | 2016-02-23 | 2016-02-23 | Connected |  | No
National Grid | PALMER | 174159 | 1069 | 3000 | Solar | 09_0504 | 2012-04-16 01:00 | 2012-04-19 | 14 | 0 | 14 | [10 empty] | 2012-05-09 | 2012-06-26 | 32 | 0 | 32 | [12 empty] | 2012-12-15 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | PALMER | 174160 | 1069 | 2000 | Solar | 09_0504 | 2012-04-16 01:00 | 2012-04-19 | 14 | 0 | 14 | [10 empty] | 2012-05-09 | 2012-06-26 | 32 | 0 | 32 | [12 empty] | 2012-12-15 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BILLERICA | 174142 | 1821 | 2000 | Solar | 14_70L8 | 2012-04-17 01:00 | 2012-04-19 | 0 | 0 | 0 | [25 empty] | 2012-08-06 |  | 2012-12-03 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BILLERICA | 174143 | 1821 | 2000 | Solar | 14_70L8 | 2012-04-17 01:00 | 2012-04-19 | 0 | 0 | 0 | [25 empty] | 2012-08-06 |  | 2012-12-03 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BILLERICA | 174144 | 1821 | 999 | Solar | 14_2389 | 2012-04-17 01:00 | 2012-04-19 | 0 | 0 | 0 | [25 empty] | 2012-08-06 | 2012-04-18 01:00 | 2012-12-03 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HARVARD | 174148 | 1451 | 30 | Solar | 01_201W2 | 2012-04-18 01:00 | 2012-04-23 | 9 | 0 | 9 | [25 empty] | 2012-12-12 | 2012-04-20 01:00 | 2012-08-01 |  | EXP |  | 2013-01-10 | 2013-02-27 | 28 | 0 | 28 | 2013-02-20 | 2013-02-20 | 2013-03-11 | Connected |  | No
National Grid | GILBERTVILLE | 174161 | 1031 | 1825.6 | Solar | 09_501L2 | 2012-04-20 01:00 | 2012-04-24 | 11 | 0 | 11 | [10 empty] | 2012-05-09 | 2012-06-25 | 31 | 0 | 31 | [5 empty] | 2013-09-10 | 2013-10-22 | 29 | 0 | 29 | 2013-12-31 |  | 2014-12-31 | Yes | STD |  | 2015-06-29 | 2015-07-29 | 21 | 0 | 21 | 2015-07-29 | 2015-07-29 | 2015-07-31 | Connected |  | No
National Grid | LANCASTER | 174154 | 1523 | 1000 | Solar | 01_225W2 | 2012-04-23 01:00 | 2012-04-25 | 9 | 0 | 9 | [10 empty] | 2012-05-08 | 2012-06-22 | 31 | 0 | 31 | [12 empty] | 2012-12-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH ANDOVER | 174155 | 1845 | 1000 | Solar | 14_56L3 | 2012-04-23 01:00 | 2012-04-25 | 3 | 0 | 3 | [27 empty] | 2012-11-28 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH ANDOVER | 174156 | 1845 | 1000 | Solar | 14_56L3 | 2012-04-23 01:00 | 2012-04-25 | 3 | 0 | 3 | [26 empty] | 2012-04-23 01:00 | 2012-05-05 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | GILBERTVILLE | 174162 | 1031 | 972.8 | Solar | 09_501L2 | 2012-04-23 01:00 | 2012-04-24 | 11 | 0 | 11 | [10 empty] | 2012-05-09 | 2012-06-25 | 31 | 0 | 31 | [5 empty] | 2013-09-10 | 2013-10-22 | 29 | 0 | 29 | 2013-12-31 |  | 2014-12-31 | Yes | STD |  | 2015-06-29 | 2015-07-29 | 21 | 0 | 21 | 2015-07-29 | 2015-07-29 | 2015-07-31 | Connected |  | No
National Grid | BELCHERTOWN | 174163 | 1007 | 11.39 | Solar | 09_527L1 | 2012-04-23 01:00 | 2012-04-25 | 9 | 0 | 9 | [25 empty] | 2012-08-13 |  | 2012-06-22 |  | EXP | [6 empty] | 2012-08-13 | 2012-08-13 | 2013-01-14 | Connected |  | No
National Grid | WESTBOROUGH | 174164 | 1581 | 10.75 | Solar | 05_312W4 | 2012-04-23 01:00 | 2012-04-25 | 9 | 0 | 9 | [25 empty] | 2012-08-23 |  | 2012-06-01 |  | EXP | [6 empty] | 2012-08-23 | 2012-08-23 | 2012-12-21 | Connected |  | No
National Grid | NORTH ANDOVER | 174171 | 1845 | 1000 | Solar | 14_56L3 | 2012-04-23 01:00 | 2012-04-25 | 8 | 0 | 8 | [10 empty] | 2012-05-07 | 2012-07-11 | 44 | 0 | 44 | [12 empty] | 2012-05-12 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH ANDOVER | 174172 | 1845 | 1000 | Solar | 14_56L3 | 2012-04-23 01:00 | 2012-04-25 | 8 | 0 | 8 | [10 empty] | 2012-05-07 | 2012-07-11 | 44 | 0 | 44 | [12 empty] | 2012-05-12 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 174157 | 1610 | 2016 | Natural Gas | 01_HT41 | 2012-04-24 01:00 | 2012-04-27 | 8 | 0 | 8 | [10 empty] | 2012-05-09 | 2012-05-13 | 3 | 0 | 3 | [10 empty] | 2012-12-10 |  | 2016-12-31 |  | STD | [8 empty] | 2017-07-14 | Connected |  | No
National Grid | LOWELL | 174165 | 1854 | 566 | Solar | 14_77L3 | 2012-04-24 01:00 | 2012-04-24 | 13 | 0 | 13 | 2012-05-11 | 2012-05-11 | 0 | 0 | 0 | [20 empty] | 2012-11-19 |  | 2012-07-31 |  | EXP | [6 empty] | 2013-03-25 | 2013-03-25 | 2013-05-21 | Connected |  | No
National Grid | WESTBOROUGH | 174127 | 1581 | 13.97 | Solar | 05_312W4 | 2012-04-26 01:00 | 2012-05-01 | 9 | 0 | 9 | 2012-05-14 | 2012-05-14 | 0 | 0 | 0 | [20 empty] | 2012-10-04 |  | 2012-06-29 |  | EXP | [6 empty] | 2012-08-29 | 2012-08-29 | 2012-10-10 | Connected |  | No
National Grid | WORCESTER | 174126 | 1603 | 135 | Solar | 01_6W2 | 2012-04-27 01:00 | 2012-05-01 | 8 | 0 | 8 | [25 empty] | 2013-03-29 |  | 2012-08-09 |  | EXP | [6 empty] | 2013-03-29 | 2013-03-29 | 2014-01-06 | Connected |  | Yes
National Grid | WORCESTER | 174173 | 1602 | 75 | Solar | 01_HT59 | 2012-04-27 01:00 | 2012-05-01 | 8 | 0 | 8 | [25 empty] | 2012-12-12 |  | 2012-05-15 |  | EXP | [6 empty] | 2013-02-06 | 2013-02-06 | 2013-03-02 | Connected |  | No
National Grid | WORCESTER | 174174 | 1602 | 135 | Solar | 01_HT59 | 2012-04-27 01:00 | 2012-05-01 | 8 | 0 | 8 | [25 empty] | 2012-12-12 |  | 2012-08-20 |  | EXP | [6 empty] | 2015-06-12 | 2015-06-12 | 2013-03-02 | Connected |  | No
National Grid | BEVERLY | 174128 | 1915 | 224 | Solar | 12_12L4 | 2012-04-30 01:00 | 2012-05-02 | 11 | 0 | 11 | 2012-05-17 | 2012-05-17 | 0 | 0 | 0 | [20 empty] | 2012-08-20 |  | 2012-09-28 |  | EXP | [6 empty] | 2013-01-30 | 2013-01-30 | 2013-01-08 | Connected |  | No
National Grid | BEVERLY | 174129 | 1915 | 224 | Solar | 12_12L4 | 2012-04-30 01:00 | 2012-05-02 | 11 | 0 | 11 | 2012-05-17 | 2012-05-17 | 0 | 0 | 0 | [20 empty] | 2012-08-20 |  | 2012-09-28 |  | EXP | [6 empty] | 2013-01-30 | 2013-01-30 | 2013-01-08 | Connected |  | No
National Grid | STURBRIDGE | 174130 | 1566 | 2000 | Solar | 01_413L7 | 2012-05-01 01:00 | 2012-05-04 | 8 | 0 | 8 | [10 empty] | 2012-05-16 | 2012-08-16 | 63 | 0 | 63 | [12 empty] | 2012-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SAUGUS | 174131 | 1906 | 252 | Solar | 12_19W2 | 2012-05-03 01:00 | 2012-05-07 | 9 | 0 | 9 | 2012-05-18 | 2012-05-18 | 0 | 0 | 0 | [20 empty] | 2012-12-12 |  | 2012-10-29 |  | EXP | [6 empty] | 2013-06-20 | 2013-06-20 | 2013-06-28 | Connected |  | No
National Grid | LEOMINSTER | 174132 | 1453 | 300 | Solar | 01_227W1 | 2012-05-03 01:00 | 2012-05-07 | 9 | 0 | 9 | [27 empty] | 2012-10-29 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GRAFTON | 174133 | 1519 | 24.94 | Solar | 01_304W1 | 2012-05-03 01:00 | 2012-05-07 | 17 | 0 | 17 | 2012-05-31 | 2012-05-31 | 0 | 0 | 0 | [20 empty] | 2012-10-03 |  | 2012-08-10 |  | EXP | [6 empty] | 2013-12-26 | 2013-12-26 | 2013-12-26 | Connected |  | No
National Grid | ATTLEBORO | 174134 | 2703 | 36 | Solar | 05_9L2 | 2012-05-04 01:00 | 2012-05-08 | 9 | 0 | 9 | 2012-05-21 | 2012-05-21 | 0 | 0 | 0 | [20 empty] | 2012-08-31 |  | 2012-05-19 |  | EXP | [6 empty] | 2012-08-31 | 2012-08-31 | 2012-10-24 | Connected |  | No
National Grid | WEST STOCKBRIDGE | 174135 | 1266 | 12 | Solar | 09_1109W3 | 2012-05-08 01:00 | 2012-05-10 | 7 | 0 | 7 | 2012-05-21 | 2012-05-21 | 0 | 0 | 0 | [20 empty] | 2012-10-22 |  | 2012-07-10 |  | EXP | [6 empty] | 2012-08-29 | 2012-08-29 | 2012-11-20 | Connected |  | No
National Grid | LOWELL | 174350 | 1852 | 675 | Solar | 14_2381 | 2012-05-08 01:00 | 2012-05-10 | 8 | 0 | 8 | [10 empty] | 2012-05-22 | 2012-07-03 | 28 | 0 | 28 | [12 empty] | 2012-08-01 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | NORTHAMPTON | 174352 | 1060 | 17 | Solar | 09_901W1 | 2012-05-09 01:00 | 2012-05-11 | 7 | 0 | 7 | 2012-05-22 | 2012-05-22 | 0 | 0 | 0 | [20 empty] | 2012-09-13 |  | 2012-07-31 |  | EXP | [6 empty] | 2012-08-30 | 2012-08-30 | 2012-10-11 | Connected |  | No
National Grid | SUTTON | 174356 | 1590 | 143 | Natural Gas | 01_304W6 | 2012-05-11 01:00 | 2012-05-15 | 154 | 0 | 154 | [27 empty] | 2012-08-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SEEKONK | 174357 | 2771 | 12 | Solar | 05_7L1 | 2012-05-15 01:00 | 2012-05-17 | 7 | 0 | 7 | 2012-05-29 | 2012-05-29 | 0 | 0 | 0 | [20 empty] | 2012-09-05 |  | 2012-07-27 |  | EXP | [6 empty] | 2012-09-06 | 2012-09-06 | 2012-11-29 | Connected |  | No
National Grid | CLINTON | 174358 | 1510 | 10.53 | Solar | 01_216W3 | 2012-05-16 01:00 | 2012-05-18 | 7 | 0 | 7 | 2012-05-30 | 2012-05-30 | 0 | 0 | 0 | [20 empty] | 2012-12-12 | 2012-05-17 01:00 | 2012-07-31 |  | EXP | [6 empty] | 2012-09-06 | 2012-09-06 | 2013-05-30 | Connected |  | No
National Grid | RUTLAND | 174354 | 1543 | 2000 | Solar | 01_55W1 | 2012-05-17 01:00 | 2012-05-18 | 7 | 0 | 7 | [10 empty] | 2012-05-30 | 2012-08-16 | 54 | 0 | 54 | [5 empty] | 2014-03-28 | 2014-03-28 | 0 | 0 | 0 | 2013-09-12 |  | 2012-12-31 |  | STD | [6 empty] | 2016-03-22 | 2016-03-22 | 2015-11-03 | Connected |  | No
National Grid | RUTLAND | 174355 | 1543 | 1000 | Solar | 01_55W1 | 2012-05-17 01:00 | 2012-05-18 | 7 | 0 | 7 | [10 empty] | 2012-05-30 | 2012-08-16 | 54 | 0 | 54 | [12 empty] | 2012-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 174362 | 1507 | 17 | Solar | 01_415L1 | 2012-05-17 01:00 | 2012-05-21 | 6 | 0 | 6 | 2012-05-30 | 2012-05-30 | 0 | 0 | 0 | [20 empty] | 2012-12-12 | 2012-05-21 01:00 | 2012-07-31 |  | EXP | [6 empty] | 2012-09-07 | 2012-09-07 | 2013-04-01 | Connected |  | No
National Grid | NORTH ANDOVER | 174365 | 1845 | 7.5 | Solar | 14_56L2 | 2012-05-21 01:00 | 2012-05-23 | 8 | 0 | 8 | 2012-06-05 | 2012-06-05 | 0 | 0 | 0 | [20 empty] | 2012-11-15 |  | 2012-08-01 |  | EXP |  | 2012-10-04 | 2012-11-19 | 15 | 0 | 15 | 2012-11-15 | 2012-11-15 | 2012-11-15 | Connected |  | No
National Grid | ANDOVER | 174366 | 1810 | 45.6 | Solar | 14_3J40 | 2012-05-21 01:00 | 2012-05-24 | 6 | 0 | 6 | [25 empty] | 2012-08-03 |  | 2012-08-01 |  | EXP | [6 empty] | 2012-10-01 | 2012-10-01 | 2012-10-19 | Connected |  | No
National Grid | FRANKLIN | 174372 | 2038 | 250 | Solar | 05_348W5 | 2012-05-23 01:00 | 2012-05-25 | 7 | 0 | 7 | 2012-06-06 | 2012-06-06 | 0 | 0 | 0 | [20 empty] | 2012-12-12 | 2012-05-29 01:00 | 2012-11-01 |  | EXP | [6 empty] | 2012-12-13 | 2012-12-13 | 2012-12-20 | Connected |  | No
National Grid | TEWKSBURY | 174373 | 1876 | 260 | Solar | 14_2385 | 2012-05-29 01:00 | 2012-06-01 | 11 | 0 | 11 | 2012-06-18 | 2012-06-18 | 0 | 0 | 0 | 2012-12-17 | 2013-01-30 | 29 | 0 | 29 | [5 empty] | 2012-12-17 | 2013-01-30 | 29 | 0 | 29 | [5 empty] | 2013-01-30 | 2012-05-29 01:00 | 2014-10-31 | Yes | EXP |  | 2014-07-28 | 2016-08-19 | 513 | 0 | 513 | 2015-05-14 | 2015-05-14 | 2014-12-03 | Connected |  | No
National Grid | CLINTON | 174374 | 1510 | 1000 | Solar | 01_216W3 | 2012-05-29 01:00 | 2012-06-01 | 6 | 0 | 6 | [10 empty] | 2012-06-11 | 2012-08-17 | 47 | 0 | 47 | [5 empty] | 2013-09-24 | 2013-09-24 | 0 | 0 | 0 | 2013-03-14 | 2012-05-29 01:00 | 2018-03-02 | Yes | STD |  | 2017-11-30 | 2018-02-21 | 55 | 0 | 55 | 2018-03-01 | 2018-03-01 | 2018-03-01 | Connected |  | No
National Grid | WESTMINSTER | 174375 | 1473 | 600 | Solar | 01_610W3 | 2012-05-29 01:00 | 2012-06-01 | 11 | 0 | 11 | 2012-06-18 | 2012-06-18 | 0 | 0 | 0 | [20 empty] | 2013-03-14 | 2012-05-29 01:00 | 2016-12-31 | Yes | EXP |  | 2015-10-01 | 2015-10-09 | 6 | 0 | 6 | 2012-06-03 | 2012-06-03 | 2015-12-24 | Connected |  | No
National Grid | CLINTON | 174376 | 1510 | 1954 | Solar | 01_216W5 | 2012-05-29 01:00 | 2012-06-01 | 6 | 0 | 6 | [10 empty] | 2012-06-11 | 2012-08-17 | 47 | 0 | 47 | [5 empty] | 2014-03-26 | 2014-03-26 | 0 | 0 | 0 | 2013-03-14 |  | 2017-08-31 | Yes | STD |  | 2017-11-02 | 2017-08-10 | 0 | 0 | 0 | 2017-06-27 | 2017-06-27 | 2017-09-29 | Connected |  | No
National Grid | CLINTON | 174377 | 1510 | 1000 | Solar | 01_216W5 | 2012-05-29 01:00 | 2012-06-01 | 6 | 0 | 6 | [10 empty] | 2012-06-11 | 2012-08-17 | 47 | 0 | 47 | [12 empty] | 2013-01-15 |  | STD |  | 2017-11-02 | 2017-08-10 | 0 | 0 | 0 |  |  |  | Withdrawn |  | No
National Grid | NEW BRAINTREE | 174379 | 1531 | 3000 | Solar | 09_604W3 | 2012-05-29 01:00 | 2012-06-01 | 6 | 0 | 6 | [10 empty] | 2012-06-11 | 2012-09-18 | 68 | 0 | 68 | [10 empty] | 2015-03-06 |  | 2013-02-13 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NEW BRAINTREE | 174380 | 1531 | 1000 | Solar | 09_604W3 | 2012-05-29 01:00 | 2012-06-01 | 6 | 0 | 6 | [10 empty] | 2012-06-11 | 2012-09-18 | 68 | 0 | 68 | [12 empty] | 2013-02-15 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NEW BRAINTREE | 174381 | 1531 | 1000 | Solar | 09_604W3 | 2012-05-29 01:00 | 2012-06-01 | 6 | 0 | 6 | [10 empty] | 2012-06-11 | 2012-09-18 | 68 | 0 | 68 | [12 empty] | 2013-02-15 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HUBBARDSTON | 174382 | 1452 | 2.58 | Solar | 01_602W2 | 2012-05-30 01:00 | 2012-06-04 | 7 | 0 | 7 | 2012-06-13 | 2012-06-13 | 0 | 0 | 0 | [20 empty] | 2012-09-10 |  | 2012-08-15 |  | EXP | [6 empty] | 2012-09-10 | 2012-09-10 | 2013-01-22 | Connected |  | No
National Grid | RUTLAND | 174384 | 1543 | 4 | Solar | 01_55W1 | 2012-05-31 01:00 | 2012-06-04 | 7 | 0 | 7 | 2012-06-13 | 2012-06-13 | 0 | 0 | 0 | [20 empty] | 2012-09-24 | 2012-05-31 01:00 | 2012-08-31 |  | EXP | [6 empty] | 2012-09-06 | 2012-09-06 | 2012-09-24 | Connected |  | No
National Grid | SPENCER | 174385 | 1562 | 2650 | Solar | 01_55K11 | 2012-05-31 01:00 | 2012-06-01 | 36 | 0 | 36 | [10 empty] | 2012-07-25 | 2012-10-03 | 49 | 0 | 49 | [5 empty] | 2015-02-18 | 2016-06-29 | 338 | 0 | 338 | 2014-12-23 |  | 2016-02-03 |  | STD | [8 empty] | 2016-11-28 | Connected |  | No
National Grid | WILBRAHAM | 174386 | 1095 | 14 | Solar | 09_507L1 | 2012-06-01 01:00 | 2012-06-05 | 28 | 0 | 28 | 2012-07-17 | 2012-07-17 | 0 | 0 | 0 | [20 empty] | 2012-12-12 |  | 2012-09-28 |  | EXP | [6 empty] | 2012-09-14 | 2012-09-14 | 2013-02-22 | Connected |  | No
National Grid | STURBRIDGE | 174387 | 1566 | 2000 | Solar | 01_415L3 | 2012-06-01 01:00 | 2012-06-05 | 7 | 0 | 7 | [10 empty] | 2012-06-14 | 2012-08-20 | 45 | 0 | 45 | [12 empty] | 2012-12-15 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WILBRAHAM | 174389 | 1095 | 17.2 | Solar | 09_507L1 | 2012-06-06 01:00 | 2012-06-08 | 6 | 0 | 6 | 2012-06-18 | 2012-06-18 | 0 | 0 | 0 | [20 empty] | 2012-12-12 | 2012-06-07 01:00 | 2012-08-31 |  | EXP | [6 empty] | 2012-09-07 | 2012-09-07 | 2013-01-04 | Connected |  | No
National Grid | MENDON | 174392 | 1756 | 95 | Solar | 05_321W6 | 2012-06-07 01:00 | 2012-06-11 | 7 | 0 | 7 | 2012-06-21 | 2012-06-21 | 0 | 0 | 0 | 2012-10-17 | 2012-10-17 | 0 | 0 | 0 | [5 empty] | 2012-10-17 | 2012-10-17 | 0 | 0 | 0 | [5 empty] | 2012-12-12 |  | 2012-09-28 |  | EXP | [6 empty] | 2013-03-07 | 2013-03-07 | 2013-03-26 | Connected |  | No
National Grid | ABINGTON | 174390 | 2351 | 230 | Solar | 07_60J1 | 2012-06-08 01:00 | 2012-06-11 | 5 | 0 | 5 | 2012-06-19 | 2014-01-16 | 370 | 0 | 370 | 2014-01-15 | 2014-01-15 | 0 | 0 | 0 | [5 empty] | 2014-01-15 | 2014-01-15 | 0 | 0 | 0 | [6 empty] | 2012-06-14 01:00 | 2012-10-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GARDNER | 174396 | 1440 | 2000 | Solar | 01_607W1 | 2012-06-14 01:00 | 2012-06-18 | 5 | 0 | 5 | [10 empty] | 2012-06-26 | 2012-09-24 | 62 | 0 | 62 | [10 empty] | 2013-05-17 |  | 2014-02-11 | Yes | STD |  | 2013-11-27 | 2014-04-25 | 100 | 0 | 100 | 2014-05-06 | 2014-05-06 | 2014-05-23 | Connected |  | No
National Grid | GARDNER | 174397 | 1440 | 1000 | Solar | 01_607W1 | 2012-06-14 01:00 | 2012-06-18 | 5 | 0 | 5 | [27 empty] | 2013-08-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | GARDNER | 174398 | 1440 | 1000 | Solar | 01_607W1 | 2012-06-14 01:00 | 2012-06-18 | 5 | 0 | 5 | [10 empty] | 2012-06-26 | 2012-09-26 | 64 | 0 | 64 | [12 empty] | 2013-08-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | QUINCY | 174402 | 2169 | 116.2 | Solar | 07_3W3 | 2012-06-14 01:00 | 2012-06-18 | 6 | 0 | 6 | [25 empty] | 2012-10-16 |  | 2012-09-28 |  | EXP | [6 empty] | 2012-08-07 | 2012-08-07 | 2012-11-16 | Connected |  | No
National Grid | NORWELL | 174399 | 2061 | 13 | Solar | 07_96W44 | 2012-06-15 01:00 | 2012-06-18 | 5 | 0 | 5 | 2012-06-26 | 2012-06-26 | 0 | 0 | 0 | [20 empty] | 2012-10-29 | 2012-06-19 01:00 | 2012-08-31 |  | EXP | [6 empty] | 2012-10-02 | 2012-10-02 | 2012-11-29 | Connected |  | No
National Grid | WEST BRIDGEWATER | 174410 | 2379 | 1750 | Solar | 07_98W44 | 2012-06-19 01:00 | 2012-06-21 | 6 | 0 | 6 | [10 empty] | 2012-06-29 | 2012-10-04 | 67 | 0 | 67 | [10 empty] | 2013-02-21 |  | 2012-11-01 |  | STD |  | 2013-01-11 | 2013-04-16 | 56 | 0 | 56 | 2013-11-20 | 2013-11-20 | 2013-12-06 | Connected |  | Yes
National Grid | WEBSTER | 174409 | 1570 | 11.18 | Solar | 01_412L1 | 2012-06-20 01:00 | 2012-06-22 | 5 | 0 | 5 | 2012-06-29 | 2012-06-29 | 0 | 0 | 0 | [20 empty] | 2012-12-12 |  | 2012-09-17 |  | EXP | [6 empty] | 2012-09-19 | 2012-09-19 | 2013-01-03 | Connected |  | No
National Grid | WORCESTER | 174417 | 1602 | 142 | Solar | 01_6W2 | 2012-06-21 01:00 | 2012-06-25 | 6 | 0 | 6 | 2012-07-03 | 2013-10-08 | 293 | 0 | 293 | [20 empty] | 2012-12-12 |  | 2012-09-10 |  | EXP | [6 empty] | 2012-09-25 | 2012-09-25 |  | Withdrawn |  | No
National Grid | WENHAM | 174411 | 1984 | 14 | Solar | 12_51T2 | 2012-06-22 01:00 | 2012-06-22 | 10 | 0 | 10 | 2012-07-09 | 2012-07-09 | 0 | 0 | 0 | [20 empty] | 2012-12-11 |  | 2012-09-06 |  | EXP | [6 empty] | 2012-09-28 | 2012-09-28 | 2012-12-11 | Connected |  | No
National Grid | ORANGE | 174414 | 1364 | 500 | Solar | 09_705W3 | 2012-06-22 01:00 | 2012-06-26 | 6 | 0 | 6 | 2012-07-05 | 2014-02-03 | 370 | 0 | 370 | 2013-09-27 | 2013-10-08 | 7 | 0 | 7 | [5 empty] | 2013-09-27 | 2013-10-08 | 7 | 0 | 7 | [5 empty] | 2013-11-05 |  | 2013-12-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | ATTLEBORO | 174419 | 2703 | 1791 | Solar |  | 2012-06-24 01:00 | 2012-06-27 | 8 | 0 | 8 | [10 empty] | 2012-07-10 | 2012-08-21 | 30 | 0 | 30 | [5 empty] | 2014-04-30 | 2014-09-08 | 89 | 0 | 89 |  |  | 2013-04-20 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MEDFORD | 174415 | 2155 | 833 | Solar | 12_37W2 | 2012-06-25 01:00 | 2012-06-27 | 5 | 0 | 5 | [10 empty] | 2012-07-05 | 2012-10-05 | 65 | 0 | 65 | [11 empty] | 2012-06-27 01:00 | 2013-07-05 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | CHARLTON | 174420 | 1507 | 950 | Solar | 01_406L3 | 2012-06-27 01:00 | 2012-06-28 | 6 | 0 | 6 | [10 empty] | 2012-07-09 | 2012-10-02 | 60 | 0 | 60 | [10 empty] | 2013-03-14 | 2012-06-27 01:00 | 2012-10-30 |  | STD |  | 2013-08-21 | 2014-01-17 | 101 | 0 | 101 | 2013-11-12 | 2013-11-12 | 2013-12-09 | Connected |  | No
National Grid | CHARLTON | 174421 | 1507 | 950 | Solar | 01_406L3 | 2012-06-27 01:00 | 2012-06-28 | 6 | 0 | 6 | [10 empty] | 2012-07-09 | 2012-10-02 | 60 | 0 | 60 | [10 empty] | 2013-03-14 | 2012-06-27 01:00 | 2012-10-30 | Yes | STD |  | 2013-08-21 | 2014-01-17 | 101 | 0 | 101 | 2013-11-12 | 2013-11-12 | 2013-12-09 | Connected |  | No
National Grid | RUTLAND | 174431 | 1543 | 4680 | Solar | 01_55W1 | 2012-06-27 01:00 | 2012-06-29 | 6 | 0 | 6 | [10 empty] | 2012-07-10 | 2012-10-09 | 63 | 0 | 63 | [10 empty] | 2015-02-18 |  | 2017-10-12 | Yes | STD |  | 2017-03-15 | 2017-08-18 | 109 | 0 | 109 | 2017-08-23 | 2017-08-23 | 2017-09-29 | Connected |  | No
National Grid | RUTLAND | 174432 | 1543 | 2000 | Solar | 01_55W1 | 2012-06-27 01:00 | 2012-06-29 | 6 | 0 | 6 | [10 empty] | 2012-07-10 | 2012-10-09 | 63 | 0 | 63 | [12 empty] | 2013-05-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | RUTLAND | 174433 | 1543 | 2000 | Solar | 01_55W1 | 2012-06-27 01:00 | 2012-06-29 | 6 | 0 | 6 | [10 empty] | 2012-07-10 | 2012-10-09 | 63 | 0 | 63 | [12 empty] | 2013-05-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | FALL RIVER | 174436 | 2720 | 75 | Solar | 05_28W42 | 2012-06-27 01:00 | 2012-07-02 | 7 | 0 | 7 | 2012-07-12 | 2012-07-12 | 0 | 0 | 0 | [20 empty] | 2012-12-12 | 2012-06-28 01:00 | 2012-10-22 |  | EXP | [6 empty] | 2012-09-28 | 2012-09-28 | 2012-12-14 | Connected |  | No
National Grid | GRANBY | 174435 | 1033 | 13.8 | Solar | 09_527L1 | 2012-06-28 01:00 | 2012-07-02 | 6 | 0 | 6 | 2012-07-11 | 2012-07-11 | 0 | 0 | 0 | [20 empty] | 2012-11-19 |  | 2012-10-26 |  | EXP |  | 2012-07-23 | 2012-10-18 | 61 | 0 | 61 | 2012-10-02 | 2012-10-02 | 2012-11-28 | Connected |  | No
National Grid | ATTLEBORO | 174441 | 2703 | 1875 | Solar | 05_2J3 | 2012-06-28 01:00 | 2012-06-29 | 7 | 0 | 7 | [10 empty] | 2012-07-11 | 2012-08-21 | 29 | 0 | 29 | [12 empty] | 2012-11-15 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | REHOBOTH | 174437 | 2769 | 1000 | Solar | 05_8L4 | 2012-06-29 01:00 | 2012-07-02 | 8 | 0 | 8 | [10 empty] | 2012-07-13 | 2012-08-22 | 28 | 0 | 28 | [12 empty] | 2013-10-12 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | REHOBOTH | 174438 | 2769 | 1000 | Solar | 05_7L4 | 2012-06-29 01:00 | 2012-07-02 | 8 | 0 | 8 | [10 empty] | 2012-07-13 | 2012-08-22 | 28 | 0 | 28 | [12 empty] | 2013-10-12 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | REHOBOTH | 174439 | 2769 | 1000 | Solar | 05_7L4 | 2012-06-29 01:00 | 2012-07-02 | 8 | 0 | 8 | [10 empty] | 2012-07-13 | 2012-08-22 | 28 | 0 | 28 | [12 empty] | 2013-10-12 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BARRE | 174442 | 1005 | 1000 | Solar | 09_604W2 | 2012-07-03 01:00 | 2012-07-03 | 9 | 0 | 9 | [10 empty] | 2012-07-17 | 2012-08-22 | 26 | 0 | 26 | [12 empty] | 2012-11-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MARLBOROUGH | 174443 | 1752 | 30 | Solar | 05_310W5 | 2012-07-06 01:00 | 2012-07-09 | 8 | 0 | 8 | 2012-07-19 | 2012-07-19 | 0 | 0 | 0 | [20 empty] | 2012-12-12 |  | 2012-11-30 |  | EXP | [6 empty] | 2012-10-04 | 2012-10-04 | 2013-01-09 | Connected |  | No
National Grid | WEYMOUTH | 174444 | 2188 | 45 | Solar | 07_12W1 | 2012-07-09 01:00 | 2012-07-11 | 6 | 0 | 6 | 2012-07-19 | 2012-07-19 | 0 | 0 | 0 | [20 empty] | 2012-12-12 | 2012-07-09 01:00 | 2012-11-30 |  | EXP | [6 empty] | 2012-09-28 | 2012-09-28 | 2013-03-06 | Connected |  | No
National Grid | EAST DOUGLAS | 174445 | 1516 | 60 | Solar | 05_320W2 | 2012-07-09 01:00 | 2012-07-11 | 6 | 0 | 6 | 2012-07-19 | 2012-07-19 | 0 | 0 | 0 | 2013-02-11 | 2013-02-11 | 0 | 0 | 0 | [5 empty] | 2013-02-11 | 2013-02-11 | 0 | 0 | 0 | [5 empty] | 2013-02-11 |  | 2012-11-30 | Yes | EXP |  | 2013-06-18 | 2013-07-31 | 30 | 0 | 30 | 2013-02-11 | 2013-02-11 | 2013-08-12 | Connected |  | No
National Grid | MILFORD | 174446 | 1757 | 82 | Solar | 05_336W1 | 2012-07-10 01:00 | 2012-07-12 | 6 | 0 | 6 | 2012-07-20 | 2012-07-20 | 0 | 0 | 0 | [20 empty] | 2012-12-12 |  | 2012-11-30 |  | EXP | [6 empty] | 2012-10-03 | 2012-10-03 | 2012-12-31 | Connected |  | No
National Grid | BRIMFIELD | 174447 | 1010 | 1000 | Solar | 09_503L4 | 2012-07-11 01:00 | 2012-07-12 | 8 | 0 | 8 | [10 empty] | 2012-07-24 | 2012-10-16 | 58 | 0 | 58 | [12 empty] | 2013-04-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BRIMFIELD | 174448 | 1010 | 1000 | Solar | 09_503L4 | 2012-07-11 01:00 | 2012-07-12 | 8 | 0 | 8 | [10 empty] | 2012-07-24 | 2012-10-16 | 58 | 0 | 58 | [12 empty] | 2013-04-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BRIMFIELD | 174449 | 1010 | 1000 | Solar | 09_503L4 | 2012-07-11 01:00 | 2012-07-12 | 8 | 0 | 8 | [10 empty] | 2012-07-24 | 2012-10-16 | 58 | 0 | 58 | [12 empty] | 2013-04-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BEVERLY | 174453 | 1915 | 75 | Diesel | 12_12J7 | 2012-07-12 01:00 | 2012-07-16 | 6 | 0 | 6 | 2012-07-24 | 2012-07-24 | 0 | 0 | 0 | [20 empty] | 2012-12-12 |  | 2012-10-31 |  | EXP | [6 empty] | 2012-12-24 | 2012-12-24 | 2013-03-29 | Connected |  | No
National Grid | SWANSEA | 174454 | 2777 | 3260 | Solar | 05_11W85 | 2012-07-13 01:00 | 2012-07-17 | 7 | 0 | 7 | [27 empty] | 2013-02-28 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SALISBURY | 174475 | 1952 | 2000 | Solar | 14_275L4 | 2012-07-18 01:00 | 2012-07-20 | 4 | 0 | 4 | [10 empty] | 2012-07-26 | 2012-10-17 | 57 | 0 | 57 | [12 empty] | 2013-10-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SALISBURY | 174476 | 1952 | 500 | Solar | 14_275L4 | 2012-07-18 01:00 | 2012-07-20 | 4 | 0 | 4 | [27 empty] | 2013-10-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HAMPDEN | 174514 | 1036 | 2000 | Solar | 09_524L1 | 2012-07-20 01:00 | 2012-07-24 | 2 | 0 | 2 | [10 empty] | 2012-07-26 | 2012-08-23 | 20 | 0 | 20 | [12 empty] | 2013-06-28 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HAMPDEN | 174515 | 1036 | 1000 | Solar | 09_524L1 | 2012-07-20 01:00 | 2012-07-24 | 2 | 0 | 2 | [10 empty] | 2012-07-26 | 2012-08-23 | 20 | 0 | 20 | [11 empty] | 2012-07-24 01:00 | 2013-06-28 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HANCOCK | 174343 | 1237 | 2000 | Solar | 09_1018K1 | 2012-07-24 01:00 | 2012-07-24 | 9 | 0 | 9 | [10 empty] | 2012-08-06 | 2012-10-17 | 50 | 0 | 50 | [10 empty] | 2014-03-28 | 2012-07-24 01:00 | 2016-12-31 | Yes | STD |  | 2015-09-18 | 2015-12-17 | 61 | 0 | 61 | 2015-12-14 | 2015-12-14 | 2015-12-14 | Connected |  | No
National Grid | MILFORD | 174349 | 1757 | 60 | Solar | 05_336W1 | 2012-07-24 01:00 | 2012-07-24 | 9 | 0 | 9 | 2012-08-06 | 2012-08-06 | 0 | 0 | 0 | [20 empty] | 2012-12-12 | 2012-07-25 01:00 | 2012-11-30 |  | EXP |  | 2013-02-05 | 2013-04-11 | 38 | 0 | 38 | 2013-04-22 | 2013-04-22 | 2013-04-23 | Connected |  | No
National Grid | WEST BROOKFIELD | 174550 | 1585 | 39 | Solar | 01_525L2 | 2012-07-25 01:00 | 2012-07-26 | 7 | 0 | 7 | 2012-08-06 | 2012-08-06 | 0 | 0 | 0 | [20 empty] | 2012-12-12 |  | 2012-10-31 | Yes | EXP |  | 2013-03-29 | 2013-03-29 | 0 | 0 | 0 | 2013-03-29 | 2013-03-29 | 2013-04-16 | Connected |  | No
National Grid | NORTHBOROUGH | 174489 | 1532 | 2000 | Solar | 05_313W3 | 2012-07-26 01:00 | 2012-07-27 | 8 | 0 | 8 | [10 empty] | 2012-08-08 | 2012-10-09 | 42 | 0 | 42 | [12 empty] | 2013-07-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTHBOROUGH | 174490 | 1532 | 1000 | Solar | 05_313W3 | 2012-07-26 01:00 | 2012-07-27 | 8 | 0 | 8 | [10 empty] | 2012-08-08 | 2012-10-09 | 42 | 0 | 42 | [12 empty] | 2013-07-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HOLLAND | 174494 | 1521 | 2000 | Solar | 09_516L1 | 2012-07-27 01:00 | 2012-07-27 | 9 | 0 | 9 | [10 empty] | 2012-08-09 | 2013-01-16 | 93 | 0 | 93 | [12 empty] | 2013-07-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HOLLAND | 174495 | 1521 | 1000 | Solar | 09_516L1 | 2012-07-27 01:00 | 2012-07-27 | 9 | 0 | 9 | [10 empty] | 2012-08-09 | 2013-01-16 | 93 | 0 | 93 | [11 empty] | 2012-07-27 01:00 | 2013-07-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BRIMFIELD | 174496 | 1010 | 3000 | Solar | 09_516L1 | 2012-07-27 01:00 | 2012-07-27 | 9 | 0 | 9 | [10 empty] | 2012-08-09 | 2012-10-18 | 48 | 0 | 48 | [10 empty] | 2013-05-20 |  | 2013-07-01 |  | STD | [6 empty] | 2014-06-19 | 2014-06-19 | 2014-06-19 | Connected |  | No
National Grid | BRIMFIELD | 174497 | 1010 | 1000 | Solar | 09_516L1 | 2012-07-27 01:00 | 2012-07-27 | 9 | 0 | 9 | [10 empty] | 2012-08-09 | 2012-10-18 | 48 | 0 | 48 | [12 empty] | 2013-07-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | FOXBOROUGH | 178766 | 2035 | 375 | Solar | 05_3424W1 | 2012-07-27 01:00 | 2012-07-27 | 242 | 233 | 9 | [26 empty] | 2012-07-30 01:00 | 2012-12-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BEVERLY | 174823 | 1915 | 2000 | Solar | 12_2365 | 2012-07-30 01:00 | 2012-08-01 | 6 | 0 | 6 | [10 empty] | 2012-08-09 | 2012-10-19 | 49 | 0 | 49 | [10 empty] | 2013-04-30 |  | 2014-04-01 |  | STD | [6 empty] | 2014-05-01 | 2014-05-01 | 2014-05-08 | Connected |  | No
National Grid | PLAINVILLE | 178767 | 2762 | 225 | Solar | 05_3451W3 | 2012-07-31 01:00 | 2012-08-02 | 8 | 2 | 6 | 2012-08-14 | 2012-08-14 | 0 | 0 | 0 | [20 empty] | 2012-12-12 |  | 2012-11-30 |  | EXP | [6 empty] | 2012-12-18 | 2012-12-18 | 2012-12-31 | Connected |  | No
National Grid | SHIRLEY | 174830 | 1464 | 500 | Solar | 01_201W1 | 2012-08-01 01:00 | 2012-08-03 | 7 | 0 | 7 | [10 empty] | 2012-08-14 | 2012-10-09 | 38 | 0 | 38 | [12 empty] | 2012-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SHIRLEY | 174831 | 1464 | 2500 | Solar | 01_201W1 | 2012-08-01 01:00 | 2012-08-03 | 7 | 0 | 7 | [10 empty] | 2012-08-14 | 2012-11-24 | 55 | 0 | 55 | [12 empty] | 2013-07-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SHIRLEY | 174859 | 1464 | 500 | Solar | 01_201W1 | 2012-08-01 01:00 | 2012-08-03 | 7 | 0 | 7 | [10 empty] | 2012-08-14 | 2012-11-24 | 55 | 0 | 55 | [11 empty] | 2012-08-02 01:00 | 2013-07-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LOWELL | 174864 | 1851 | 1333 | Solar | 14_2L4 | 2012-08-02 01:00 | 2012-08-03 | 7 | 0 | 7 | [10 empty] | 2012-08-14 | 2012-10-24 | 49 | 0 | 49 | [10 empty] | 2013-05-10 | 2012-08-02 01:00 | 2012-12-31 | Yes | STD |  | 2013-10-25 | 2013-12-27 | 42 | 0 | 42 | 2013-12-26 | 2013-12-26 | 2013-12-27 | Connected |  | No
National Grid | REHOBOTH | 174866 | 2769 | 2000 | Solar | 05_8L4 | 2012-08-02 01:00 | 2012-08-06 | 6 | 0 | 6 | [10 empty] | 2012-08-14 | 2012-10-15 | 42 | 0 | 42 | [10 empty] | 2013-05-20 | 2012-08-03 01:00 | 2013-07-01 | Yes | STD |  | 2013-10-17 | 2013-12-19 | 43 | 0 | 43 | 2013-12-16 | 2013-12-16 | 2013-12-23 | Connected |  | No
National Grid | BRIDGEWATER | 174861 | 2324 | 3000 | Solar | 07_797W1 | 2012-08-03 01:00 | 2012-08-06 | 11 | 9 | 2 | [10 empty] | 2012-08-21 | 2012-11-24 | 50 | 0 | 50 | [10 empty] | 2013-06-27 |  | 2014-06-01 |  | STD | [6 empty] | 2012-08-07 | 2012-08-07 | 2015-08-11 | Connected |  | No
National Grid | BRIDGEWATER | 174862 | 2324 | 1000 | Solar | 07_797W1 | 2012-08-03 01:00 | 2012-08-06 | 11 | 9 | 2 | [10 empty] | 2012-08-21 | 2012-11-24 | 50 | 0 | 50 | [10 empty] | 2013-06-27 |  | 2012-12-31 |  | STD | [8 empty] | 2015-08-11 | Withdrawn |  | No
National Grid | PEPPERELL | 174867 | 1463 | 11 | Solar | 01_226L2 | 2012-08-06 01:00 | 2012-08-08 | 6 | 0 | 6 | 2012-08-16 | 2012-08-16 | 0 | 0 | 0 | [20 empty] | 2012-12-12 |  | 2012-11-30 |  | EXP | [6 empty] | 2012-12-21 | 2012-12-21 | 2013-02-14 | Connected |  | No
National Grid | HOLBROOK | 174896 | 2343 | 13 | Solar | 07_911W77 | 2012-08-06 01:00 | 2012-08-08 | 6 | 0 | 6 | 2012-08-16 | 2013-04-17 | 142 | 0 | 142 | [22 empty] | 2012-11-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTHAMPTON | 174897 | 1060 | 32.46 | Solar | 09_905W1 | 2012-08-07 01:00 | 2012-08-09 | 6 | 0 | 6 | 2012-08-17 | 2012-08-17 | 0 | 0 | 0 | [20 empty] | 2012-12-12 |  | 2012-11-30 |  | EXP | [6 empty] | 2013-03-15 | 2013-03-15 | 2013-04-03 | Connected |  | No
National Grid | DOUGLAS | 174903 | 1516 | 1000 | Solar | 05_320W2 | 2012-08-10 01:00 | 2012-08-10 | 244 | 241 | 3 | [27 empty] | 2012-12-31 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | TYNGSBORO | 175050 | 1879 | 37.8 | Solar | 14_211L1 | 2012-08-10 01:00 | 2012-08-13 | 5 | 0 | 5 | 2012-08-20 | 2012-08-20 | 0 | 0 | 0 | [20 empty] | 2012-12-12 |  | 2012-11-15 |  | EXP | [6 empty] | 2013-12-09 | 2013-12-09 | 2013-12-09 | Connected |  | No
National Grid | FALL RIVER | 175053 | 2721 | 80.25 | Solar | 05_115W44 | 2012-08-13 01:00 | 2012-08-14 | 8 | 3 | 5 | 2012-08-24 | 2013-11-06 | 276 | 0 | 276 | [22 empty] | 2012-11-30 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | REVERE | 175084 | 2151 | 144.3 | Solar | 12_7W4 | 2012-08-14 01:00 | 2012-08-15 | 5 | 0 | 5 | 2012-08-22 | 2012-08-22 | 0 | 0 | 0 | [20 empty] | 2013-02-11 |  | 2012-11-15 |  | EXP | [6 empty] | 2013-02-11 | 2013-02-11 | 2014-08-08 | Connected |  | No
National Grid | SHUTESBURY | 175085 | 1072 | 12.2 | Solar | 09_704W1 | 2012-08-14 01:00 | 2012-08-15 | 5 | 0 | 5 | 2012-08-22 | 2012-08-22 | 0 | 0 | 0 | [20 empty] | 2012-12-12 |  | 2012-11-30 |  | EXP | [6 empty] | 2012-10-24 | 2012-10-24 | 2012-12-28 | Connected |  | No
National Grid | BRIMFIELD | 175086 | 1010 | 2000 | Solar | 09_503L4 | 2012-08-14 01:00 | 2012-08-15 | 6 | 0 | 6 | [10 empty] | 2012-08-23 | 2012-11-24 | 48 | 0 | 48 | [12 empty] | 2013-07-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BRIMFIELD | 175087 | 1010 | 1000 | Solar | 09_503L4 | 2012-08-14 01:00 | 2012-08-15 | 6 | 0 | 6 | [10 empty] | 2012-08-23 | 2012-11-24 | 48 | 0 | 48 | [12 empty] | 2013-07-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BRIMFIELD | 175088 | 1010 | 1000 | Solar | 09_503L4 | 2012-08-14 01:00 | 2012-08-15 | 6 | 0 | 6 | [10 empty] | 2012-08-23 | 2012-11-24 | 48 | 0 | 48 | [11 empty] | 2012-08-16 01:00 | 2013-07-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ESSEX | 175123 | 1929 | 18 | Solar | 12_51T2 | 2012-08-16 01:00 | 2012-08-17 | 5 | 0 | 5 | 2012-08-24 | 2012-08-24 | 0 | 0 | 0 | [20 empty] | 2012-12-12 |  | 2012-11-30 |  | EXP | [6 empty] | 2013-04-02 | 2013-04-02 | 2013-04-02 | Connected |  | No
National Grid | FOXBOROUGH | 178772 | 2035 | 300 | Solar | 05_3422W3 | 2012-08-16 01:00 | 2012-08-17 | 5 | 1 | 4 | 2012-08-24 | 2012-08-24 | 0 | 0 | 0 | [20 empty] | 2012-10-19 |  | 2012-11-27 |  | EXP | [6 empty] | 2013-01-03 | 2013-01-03 | 2013-01-17 | Connected |  | No
National Grid | SHUTESBURY | 175121 | 1072 | 3000 | Solar | 09_704W1 | 2012-08-17 01:00 | 2012-08-20 | 7 | 0 | 7 | [10 empty] | 2012-08-29 | 2012-12-03 | 49 | 0 | 49 | [12 empty] | 2013-06-03 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SHUTESBURY | 175122 | 1072 | 3000 | Solar | 09_704W1 | 2012-08-17 01:00 | 2012-08-20 | 7 | 0 | 7 | [10 empty] | 2012-08-29 | 2012-11-26 | 44 | 0 | 44 | [11 empty] | 2012-08-20 01:00 | 2013-06-03 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SWANSEA | 175126 | 2777 | 1656 | Solar | 05_11W84 | 2012-08-20 01:00 | 2012-08-21 | 7 | 0 | 7 | [10 empty] | 2012-08-30 | 2012-12-24 | 63 | 0 | 63 | [10 empty] | 2013-09-13 |  | 2017-09-08 |  | STD |  | 2017-03-14 | 2017-08-29 | 117 | 0 | 117 | 2017-08-29 | 2017-08-29 | 2017-08-31 | Connected |  | No
National Grid | SWANSEA | 175127 | 2777 | 1760 | Solar | 05_11W84 | 2012-08-20 01:00 | 2012-08-21 | 7 | 0 | 7 | [10 empty] | 2012-08-30 | 2012-12-24 | 63 | 0 | 63 | [12 empty] | 2013-02-28 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | PEMBROKE | 175158 | 2359 | 95 | Solar | 07_70J1 | 2012-08-20 01:00 | 2012-08-21 | 7 | 0 | 7 | 2012-08-30 | 2012-08-30 | 0 | 0 | 0 | [20 empty] | 2012-12-13 |  | 2012-11-01 |  | EXP | [6 empty] | 2013-04-02 | 2013-04-02 | 2013-06-18 | Connected |  | No
National Grid | MARLBOROUGH | 174650 | 1752 | 110 | Solar | 05_313W4 | 2012-08-21 01:00 | 2012-08-22 | 7 | 0 | 7 | 2012-08-31 | 2012-08-31 | 0 | 0 | 0 | [20 empty] | 2013-04-08 |  | 2012-12-14 |  | EXP | [6 empty] | 2013-10-29 | 2013-10-29 | 2013-10-29 | Connected |  | Yes
National Grid | MARLBOROUGH | 174651 | 1752 | 125 | Solar | 05_313W4 | 2012-08-21 01:00 | 2012-08-22 | 7 | 0 | 7 | 2012-08-31 | 2012-08-31 | 0 | 0 | 0 | [20 empty] | 2013-04-08 |  | 2012-12-14 |  | EXP | [6 empty] | 2013-10-29 | 2013-10-29 | 2013-10-29 | Connected |  | No
National Grid | WARE | 174652 | 1082 | 260 | Solar | 09_523L4 | 2012-08-21 01:00 | 2012-08-22 | 8 | 0 | 8 | 2012-09-04 | 2012-09-04 | 0 | 0 | 0 | [20 empty] | 2012-12-11 |  | 2012-11-01 |  | EXP | [6 empty] | 2012-12-28 | 2012-12-28 | 2012-12-28 | Connected |  | No
National Grid | HALIFAX | 174653 | 2338 | 225 | Solar | 07_912W75 | 2012-08-21 01:00 | 2012-08-22 | 8 | 0 | 8 | 2012-09-04 | 2012-09-04 | 0 | 0 | 0 | [20 empty] | 2012-12-11 |  | 2012-11-01 |  | EXP | [6 empty] | 2012-12-28 | 2012-12-28 | 2012-12-28 | Connected |  | Yes
National Grid | ABINGTON | 174654 | 2351 | 266 | Solar | 07_93W42 | 2012-08-21 01:00 | 2012-08-22 | 8 | 0 | 8 | 2012-09-04 | 2012-09-04 | 0 | 0 | 0 | [20 empty] | 2012-12-11 |  | 2012-11-01 |  | EXP | [6 empty] | 2012-12-28 | 2012-12-28 | 2012-12-28 | Connected |  | Yes
National Grid | NORTHBRIDGE | 174655 | 1534 | 375 | Solar | 05_320W5 | 2012-08-21 01:00 | 2012-08-22 | 8 | 0 | 8 | 2012-09-04 | 2012-09-04 | 0 | 0 | 0 | [20 empty] | 2012-12-13 |  | 2012-11-01 |  | EXP | [6 empty] | 2012-12-28 | 2012-12-28 | 2012-12-28 | Connected |  | Yes
National Grid | TEWKSBURY | 174727 | 1876 | 260 | Solar | 14_20L3 | 2012-08-21 01:00 | 2012-08-23 | 7 | 0 | 7 | 2012-09-04 | 2012-09-04 | 0 | 0 | 0 | [20 empty] | 2012-12-11 |  | 2012-11-01 |  | EXP | [6 empty] | 2012-12-28 | 2012-12-28 | 2012-12-28 | Connected |  | No
National Grid | MARLBOROUGH | 175196 | 1752 | 100 | Solar | 05_310W4 | 2012-08-21 01:00 | 2012-08-22 | 7 | 0 | 7 | 2012-08-31 | 2012-08-31 | 0 | 0 | 0 | [20 empty] | 2013-04-08 |  | 2012-12-14 |  | EXP | [6 empty] | 2013-10-29 | 2013-10-29 | 2013-10-29 | Connected |  | No
National Grid | MARLBOROUGH | 175199 | 1752 | 125 | Solar | 05_313W4 | 2012-08-21 01:00 | 2012-08-22 | 7 | 0 | 7 | 2012-08-31 | 2012-08-31 | 0 | 0 | 0 | [20 empty] | 2013-04-08 |  | 2012-12-14 |  | EXP | [6 empty] | 2013-10-29 | 2013-10-29 | 2013-10-29 | Connected |  | Yes
National Grid | MARLBOROUGH | 175202 | 1752 | 110 | Solar | 05_310W4 | 2012-08-21 01:00 | 2012-08-22 | 7 | 0 | 7 | 2012-08-31 | 2012-08-31 | 0 | 0 | 0 | [20 empty] | 2013-04-08 |  | 2012-12-14 |  | EXP | [6 empty] | 2013-10-29 | 2013-10-29 | 2013-10-29 | Connected |  | Yes
National Grid | MARLBOROUGH | 174730 | 1752 | 100 | Solar | 05_313W4 | 2012-08-22 01:00 | 2012-08-23 | 7 | 0 | 7 | 2012-09-04 | 2012-09-04 | 0 | 0 | 0 | [20 empty] | 2013-04-08 |  | 2012-12-14 |  | EXP | [6 empty] | 2013-12-12 | 2013-12-12 | 2013-12-13 | Connected |  | No
National Grid | WORCESTER | 174763 | 1606 | 60 | Solar | 01_24W2 | 2012-08-23 01:00 | 2012-08-24 | 8 | 0 | 8 | 2012-09-06 | 2012-09-06 | 0 | 0 | 0 | [20 empty] | 2012-12-12 | 2012-08-23 01:00 | 2012-12-07 |  | EXP | [6 empty] | 2012-12-17 | 2012-12-17 | 2012-12-31 | Connected |  | No
National Grid | STOUGHTON | 174764 | 2072 | 332 | Solar | 07_94W42 | 2012-08-23 01:00 | 2012-08-24 | 11 | 3 | 8 | 2012-09-11 | 2012-09-11 | 0 | 0 | 0 | [20 empty] | 2013-01-28 |  | 2012-11-30 |  | EXP |  | 2013-02-28 | 2013-05-13 | 47 | 0 | 47 | 2013-05-28 | 2013-05-28 | 2013-05-30 | Connected |  | No
National Grid | WESTFORD | 174767 | 1886 | 100 | Solar | 14_58L3 | 2012-08-24 01:00 | 2012-08-24 | 8 | 0 | 8 | 2012-09-06 | 2012-09-06 | 0 | 0 | 0 | [20 empty] | 2013-05-02 |  | 2012-12-14 |  | EXP | [6 empty] | 2013-12-10 | 2013-12-10 | 2013-12-10 | Connected |  | No
National Grid | WESTFORD | 174768 | 1886 | 75 | Solar | 14_58L3 | 2012-08-24 01:00 | 2012-08-24 | 8 | 0 | 8 | 2012-09-06 | 2012-09-06 | 0 | 0 | 0 | [20 empty] | 2013-05-02 |  | 2012-12-14 |  | EXP | [6 empty] | 2013-12-10 | 2013-12-10 | 2013-12-10 | Connected |  | No
National Grid | MARLBOROUGH | 174769 | 1752 | 110 | Solar | 05_313W4 | 2012-08-27 01:00 | 2012-08-29 | 10 | 4 | 6 | 2012-09-13 | 2012-09-13 | 0 | 0 | 0 | [20 empty] | 2013-04-08 |  | 2012-12-14 |  | EXP | [6 empty] | 2013-12-10 | 2013-12-10 | 2013-12-13 | Connected |  | No
National Grid | WESTFORD | 174796 | 1886 | 13 | Solar | 14_58L3 | 2012-08-28 01:00 | 2012-08-30 | 6 | 0 | 6 | 2012-09-10 | 2012-09-10 | 0 | 0 | 0 | [20 empty] | 2012-12-01 | 2012-08-28 01:00 | 2012-11-30 |  | EXP | [6 empty] | 2013-02-07 | 2013-02-07 | 2013-02-21 | Connected |  | No
National Grid | AVON | 174838 | 2322 | 75 | Solar | 07_75W5 | 2012-08-28 01:00 | 2012-08-30 | 6 | 0 | 6 | 2012-09-10 | 2012-09-10 | 0 | 0 | 0 | [20 empty] | 2012-12-17 |  | 2012-12-27 |  | EXP |  | 2013-04-10 | 2013-04-22 | 7 | 0 | 7 | 2013-04-23 | 2013-04-23 | 2013-06-03 | Connected |  | Yes
National Grid | WORCESTER | 174797 | 1605 | 100 | Solar | 01_24W4 | 2012-08-29 01:00 | 2012-08-30 | 6 | 0 | 6 | 2012-09-10 | 2014-07-21 | 438 | 119 | 319 | [22 empty] | 2012-12-07 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEOMINSTER | 174798 | 1453 | 400 | Solar | 01_225W4 | 2012-08-29 01:00 | 2012-08-30 | 6 | 0 | 6 | 2012-09-10 | 2012-10-18 | 27 | 0 | 27 | [22 empty] | 2013-06-03 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SHUTESBURY | 174799 | 1072 | 15 | Solar | 09_704W1 | 2012-08-29 01:00 | 2012-08-30 | 6 | 0 | 6 | 2012-09-10 | 2012-09-10 | 0 | 0 | 0 | [20 empty] | 2012-12-03 |  | 2012-11-16 |  | EXP | [6 empty] | 2012-12-03 | 2012-12-03 | 2013-01-15 | Connected |  | No
National Grid | QUINCY | 174802 | 2169 | 155 | Solar | 07_1224 | 2012-08-29 01:00 | 2012-08-31 | 6 | 0 | 6 | 2012-09-11 | 2012-09-11 | 0 | 0 | 0 | [20 empty] | 2013-01-15 | 2012-08-30 01:00 | 2012-12-17 |  | EXP | [6 empty] | 2013-01-15 | 2013-01-15 | 2013-04-09 | Connected |  | No
National Grid | HARVARD | 174832 | 1451 | 260 | Solar | 01_201W2 | 2012-08-30 01:00 | 2012-08-31 | 6 | 0 | 6 | 2012-09-11 | 2012-09-11 | 0 | 0 | 0 | [20 empty] | 2013-07-29 |  | 2014-06-27 | Yes | EXP |  | 2014-05-28 | 2014-07-21 | 36 | 0 | 36 | 2014-06-13 | 2014-06-13 | 2014-06-26 | Connected |  | No
National Grid | HARVARD | 174833 | 1451 | 210 | Solar | 01_201W2 | 2012-08-30 01:00 | 2012-08-31 | 6 | 0 | 6 | [27 empty] | 2012-11-12 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SOUTHBOROUGH | 174836 | 1772 | 1450 | Solar | 05_310W6 | 2012-08-31 01:00 | 2012-08-31 | 7 | 0 | 7 | [10 empty] | 2012-09-12 | 2012-11-27 | 36 | 0 | 36 | [12 empty] | 2013-02-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTBOROUGH | 174837 | 1581 | 30 | Solar | 05_312W3 | 2012-09-04 01:00 | 2012-09-05 | 6 | 0 | 6 | 2012-09-13 | 2014-07-17 | 433 | 0 | 433 | [20 empty] | 2012-12-04 |  | 2012-12-28 |  | EXP | [6 empty] | 2012-12-04 | 2012-12-04 |  | Withdrawn |  | Yes
National Grid | QUINCY | 174868 | 2169 | 420 | Solar | 07_1W4 | 2012-09-06 01:00 | 2012-09-07 | 7 | 0 | 7 | 2012-09-18 | 2014-03-24 | 351 | 0 | 351 | [20 empty] | 2013-01-28 |  | 2012-12-11 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SWANSEA | 174873 | 2777 | 2000 | Solar | 05_11W81 | 2012-09-10 01:00 | 2012-09-11 | 7 | 0 | 7 | [10 empty] | 2012-09-20 | 2012-11-27 | 30 | 0 | 30 | [11 empty] | 2012-09-10 01:00 | 2012-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | STURBRIDGE | 174874 | 1566 | 1000 | Solar | 01_415L3 | 2012-09-10 01:00 | 2012-09-11 | 7 | 0 | 7 | [10 empty] | 2012-09-20 | 2012-09-26 | 4 | 0 | 4 | [10 empty] | 2013-08-12 |  | 2016-06-13 |  | STD | [6 empty] | 2017-10-19 | 2017-10-19 | 2017-10-19 | Connected |  | No
National Grid | SWANSEA | 174875 | 2777 | 3000 | Solar | 05_11W84 | 2012-09-11 01:00 | 2012-09-12 | 10 | 3 | 7 | [10 empty] | 2012-09-26 | 2012-12-24 | 45 | 0 | 45 | [12 empty] | 2014-03-14 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WEYMOUTH | 174876 | 2189 | 95 | Solar | 07_12W3 | 2012-09-11 01:00 | 2012-09-12 | 7 | 7 | 0 | 2012-09-21 | 2012-09-21 | 0 | 0 | 0 | [20 empty] | 2012-12-20 |  | 2012-12-17 |  | EXP | [6 empty] | 2012-12-20 | 2012-12-20 | 2013-02-08 | Connected |  | No
National Grid | SUTTON | 174906 | 1590 | 15 | Solar | 01_304W5 | 2012-09-14 01:00 | 2012-09-17 | 7 | 4 | 3 | 2012-09-26 | 2012-09-26 | 0 | 0 | 0 | [20 empty] | 2012-12-12 | 2012-09-14 01:00 | 2012-11-15 |  | EXP | [6 empty] | 2013-02-08 | 2013-02-08 | 2013-03-02 | Connected |  | No
National Grid | STURBRIDGE | 174907 | 1566 | 1000 | Solar | 01_415L3 | 2012-09-14 01:00 | 2012-09-17 | 3 | 0 | 3 | [10 empty] | 2012-09-20 | 2012-09-26 | 4 | 0 | 4 | [10 empty] | 2013-08-12 |  | 2016-06-13 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | LEOMINSTER | 174908 | 1453 | 499 | Solar | 01_225W3 | 2012-09-14 01:00 | 2012-09-17 | 22 | 21 | 1 | [26 empty] | 2012-09-14 01:00 | 2013-06-03 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | STURBRIDGE | 178084 | 1566 | 1000 | Solar | 01_415L3 | 2012-09-14 01:00 | 2012-09-17 | 3 | 0 | 3 | [10 empty] | 2012-09-20 | 2012-09-26 | 4 | 0 | 4 | [10 empty] | 2013-08-12 |  | 2018-05-14 | Yes | STD |  | 2015-04-13 | 2017-08-29 | 593 | 0 | 593 | 2017-10-19 | 2017-10-19 | 2017-10-19 | Connected |  | No
National Grid | HOLLAND | 174909 | 1521 | 3000 | Solar | 09_516L1 | 2012-09-17 01:00 | 2012-09-18 | 7 | 0 | 7 | [10 empty] | 2012-09-27 | 2013-01-29 | 67 | 0 | 67 | [12 empty] | 2013-07-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HEATH | 174910 | 1346 | 2000 | Solar | 09_1019W1 | 2012-09-17 01:00 | 2012-09-18 | 7 | 0 | 7 | [10 empty] | 2012-09-27 | 2012-12-03 | 29 | 0 | 29 | [12 empty] | 2013-07-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NEW SALEM | 174911 | 1355 | 3000 | Solar | 09_604W1 | 2012-09-17 01:00 | 2012-09-18 | 7 | 0 | 7 | [26 empty] | 2012-09-18 01:00 | 2013-07-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | REHOBOTH | 174912 | 2769 | 1000 | Solar | 05_7L5 | 2012-09-18 01:00 | 2012-09-19 | 7 | 0 | 7 | [10 empty] | 2012-09-28 | 2012-12-26 | 44 | 0 | 44 | [10 empty] | 2013-12-31 |  | 2014-06-30 | Yes | STD |  | 2014-05-05 | 2014-07-17 | 50 | 0 | 50 | 2014-07-02 | 2014-07-02 | 2014-07-15 | Connected |  | No
National Grid | WRENTHAM | 178769 | 2093 | 12 | Solar | 05_3422W1 | 2012-09-18 01:00 | 2012-09-19 | 7 | 0 | 7 | 2012-09-28 | 2012-09-28 | 0 | 0 | 0 | [20 empty] | 2013-01-14 |  | 2012-11-20 |  | EXP | [6 empty] | 2013-01-14 | 2013-01-14 | 2013-04-01 | Connected |  | No
National Grid | BLACKSTONE | 174913 | 1504 | 11 | Solar | 05_321W9 | 2012-09-19 01:00 | 2012-09-20 | 7 | 0 | 7 | 2012-10-01 | 2012-10-01 | 0 | 0 | 0 | [20 empty] | 2013-01-16 |  | 2012-11-20 |  | EXP | [6 empty] | 2013-03-20 | 2013-03-20 | 2013-04-04 | Connected |  | No
National Grid | LEEDS | 174914 | 1053 | 21 | Solar | 09_909W3 | 2012-09-19 01:00 | 2012-09-20 | 7 | 0 | 7 | 2012-10-01 | 2012-10-23 | 15 | 0 | 15 | [21 empty] | 2012-09-19 01:00 | 2012-12-14 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LEEDS | 175023 | 1053 | 21 | Solar | 09_909W3 | 2012-09-19 01:00 | 2012-09-20 | 7 | 0 | 7 | 2012-10-01 | 2012-10-01 | 0 | 0 | 0 | [20 empty] | 2012-10-10 |  | 2012-12-14 | Yes | EXP | [6 empty] | 2012-10-12 | 2012-10-12 | 2013-03-21 | Connected |  | No
National Grid | GRAFTON | 174945 | 1519 | 45 | Solar | 01_304W1 | 2012-09-21 01:00 | 2012-09-21 | 9 | 0 | 9 | 2012-10-04 | 2012-10-04 | 0 | 0 | 0 | 2013-03-28 | 2013-04-30 | 22 | 0 | 22 | [5 empty] | 2013-03-28 | 2013-04-30 | 22 | 0 | 22 | [5 empty] | 2013-05-06 |  | 2013-02-01 |  | EXP | [6 empty] | 2013-05-23 | 2013-05-23 | 2013-10-30 | Connected |  | No
National Grid | MILLBURY | 174946 | 1527 | 142 | Solar | 01_8W2 | 2012-09-24 01:00 | 2012-09-25 | 7 | 0 | 7 | 2012-10-04 | 2012-10-04 | 0 | 0 | 0 | [20 empty] | 2013-01-15 |  | 2012-12-03 |  | EXP | [6 empty] | 2013-01-15 | 2013-01-15 | 2013-02-08 | Connected |  | No
National Grid | LENOX | 174951 | 1240 | 18.06 | Solar | 09_1103W2 | 2012-09-27 01:00 | 2012-09-28 | 7 | 1 | 6 | 2012-10-10 | 2012-10-10 | 0 | 0 | 0 | [20 empty] | 2013-01-16 | 2012-09-28 01:00 | 2012-11-30 |  | EXP | [6 empty] | 2013-03-25 | 2013-03-25 | 2013-04-22 | Connected |  | No
National Grid | NORTHAMPTON | 174953 | 1060 | 250 | Solar | 09_901W1 | 2012-09-28 01:00 | 2012-10-01 | 6 | 0 | 6 | 2012-10-10 | 2012-10-10 | 0 | 0 | 0 | 2013-02-08 | 2013-03-14 | 16 | 0 | 16 | [5 empty] | 2013-02-08 | 2013-03-14 | 16 | 0 | 16 | [5 empty] | 2013-03-19 |  | 2012-12-31 | Yes | EXP | [6 empty] | 2013-08-15 | 2013-08-15 | 2013-09-06 | Connected |  | No
National Grid | WRENTHAM | 178770 | 2093 | 10 | Solar | 05_3422W1 | 2012-10-02 01:00 | 2012-10-03 | 6 | 0 | 6 | 2012-10-12 | 2012-12-27 | 36 | 0 | 36 | [22 empty] | 2012-12-05 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LEOMINSTER | 175018 | 1453 | 500 | Solar | 01_225W3 | 2012-10-08 01:00 | 2012-10-09 | 7 | 0 | 7 | 2012-10-18 | 2014-01-16 | 286 | 223 | 63 | [22 empty] | 2013-06-03 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | GARDNER | 175019 | 1440 | 350 | Solar | 01_602W2 | 2012-10-08 01:00 | 2012-10-09 | 7 | 0 | 7 | 2012-10-18 | 2016-08-05 | 919 | 0 | 919 | [20 empty] | 2013-05-13 |  | 2016-12-31 |  | EXP | [8 empty] | 2013-09-10 | Connected |  | No
National Grid | GARDNER | 175020 | 1440 | 150 | Solar | 01_602W2 | 2012-10-08 01:00 | 2012-10-09 | 7 | 0 | 7 | 2012-10-18 | 2014-04-09 | 342 | 0 | 342 | [20 empty] | 2013-05-13 | 2012-10-08 01:00 | 2013-06-03 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | HAMPDEN | 175021 | 1036 | 3500 | Solar | 09_139L1 | 2012-10-08 01:00 | 2012-10-09 | 8 | 0 | 8 | [10 empty] | 2012-10-19 | 2012-12-03 | 14 | 0 | 14 | [10 empty] | 2014-01-20 |  | 2013-06-03 | Yes | STD | [6 empty] | 2015-07-24 | 2015-07-24 | 2015-07-31 | Connected |  | No
National Grid | HAMPDEN | 175022 | 1036 | 2000 | Solar | 09_524L1 | 2012-10-08 01:00 | 2012-10-09 | 8 | 0 | 8 | [10 empty] | 2012-10-19 | 2012-11-24 | 9 | 0 | 9 | [12 empty] | 2013-06-03 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WILLIAMSTOWN | 175055 | 1267 | 2000 | Wind | 09_1003W2 | 2012-10-10 01:00 | 2012-10-11 | 8 | 0 | 8 | [27 empty] | 2014-11-03 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LEOMINSTER | 174890 | 1453 | 300 | Solar | 01_225W4 | 2012-10-12 01:00 | 2012-10-15 | 7 | 0 | 7 | 2012-10-24 | 2016-08-08 | 916 | 0 | 916 | [20 empty] | 2013-03-04 |  | 2013-10-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEOMINSTER | 175026 | 1453 | 400 | Solar | 01_225W4 | 2012-10-12 01:00 | 2012-10-15 | 7 | 0 | 7 | 2012-10-24 | 2015-09-29 | 704 | 0 | 704 | [20 empty] | 2013-03-04 |  | 2013-06-03 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | OAKHAM | 175058 | 1068 | 2000 | Solar | 09_604W2 | 2012-10-17 01:00 | 2012-10-19 | 16 | 11 | 5 | [10 empty] | 2012-12-05 | 2013-02-04 | 40 | 0 | 40 | [12 empty] | 2013-07-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | GREAT BARRINGTON | 175059 | 1230 | 18.7 | Solar | 09_1109W3 | 2012-10-18 01:00 | 2012-10-19 | 5 | 0 | 5 | 2012-11-06 | 2012-11-06 | 0 | 0 | 0 | [20 empty] | 2013-02-15 | 2012-10-18 01:00 | 2012-12-17 |  | EXP | [6 empty] | 2014-03-27 | 2014-03-27 | 2013-05-01 | Connected |  | No
National Grid | LENOX | 175060 | 1240 | 112.23 | Solar | 09_1103W1 | 2012-10-18 01:00 | 2012-10-19 | 5 | 0 | 5 | 2012-11-06 | 2012-11-06 | 0 | 0 | 0 | [20 empty] | 2013-02-15 |  | 2012-12-17 | Yes | EXP |  | 2013-08-08 | 2013-08-15 | 5 | 0 | 5 | 2013-04-02 | 2013-04-02 | 2013-05-01 | Connected |  | No
National Grid | LENOX | 175061 | 1240 | 48.37 | Solar | 09_1103W1 | 2012-10-19 01:00 | 2012-10-19 | 5 | 0 | 5 | 2012-11-06 | 2014-04-03 | 332 | 0 | 332 | [20 empty] | 2013-02-15 |  | 2012-12-17 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | REVERE | 175063 | 2151 | 2880 | Solar | 12_2307 | 2012-10-23 01:00 | 2012-10-24 | 2 | 0 | 2 | [10 empty] | 2012-11-06 | 2012-12-27 | 26 | 0 | 26 | [10 empty] | 2014-03-13 | 2012-10-23 01:00 | 2013-07-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WARE | 175064 | 1082 | 4016 | Solar | 09_501L4 | 2012-10-23 01:00 | 2012-10-24 | 13 | 11 | 2 | [10 empty] | 2012-12-05 | 2013-02-05 | 41 | 0 | 41 | [5 empty] | 2014-04-23 | 2014-06-11 | 34 | 0 | 34 | 2014-06-11 |  | 2016-07-01 | Yes | STD |  | 2016-09-09 | 2017-06-20 | 193 | 0 | 193 | 2017-06-28 | 2017-06-28 | 2017-06-28 | Connected |  | No
National Grid | EAST BRIDGEWATER | 175092 | 2333 | 12 | Solar | 07_797W42 | 2012-10-23 01:00 | 2012-10-24 | 2 | 0 | 2 | 2012-11-06 | 2012-11-06 | 0 | 0 | 0 | [20 empty] | 2013-01-18 |  | 2013-01-15 |  | EXP | [6 empty] | 2014-02-03 | 2014-02-03 | 2014-02-10 | Connected |  | No
National Grid | NEWBURYPORT | 175095 | 1950 | 12 | Solar | 14_36L1 | 2012-10-23 01:00 | 2012-10-24 | 2 | 0 | 2 | 2012-11-19 | 2012-11-19 | 0 | 0 | 0 | [20 empty] | 2013-01-25 |  | 2013-01-31 |  | EXP | [6 empty] | 2013-01-25 | 2013-01-25 | 2013-03-14 | Connected |  | No
National Grid | STURBRIDGE | 175101 | 1566 | 2000 | Solar | 01_413L2 | 2012-10-25 01:00 | 2012-10-29 | 1 | 1 | 0 | [10 empty] | 2012-11-20 | 2012-12-31 | 27 | 0 | 27 | [12 empty] | 2013-06-13 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SOUTHBRIDGE | 175096 | 1550 | 500 | Solar | 01_413L3 | 2012-10-26 01:00 | 2012-10-29 | 0 | 0 | 0 | 2012-11-19 | 2013-09-24 | 203 | 0 | 203 | [22 empty] | 2013-06-03 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SOUTHBRIDGE | 175097 | 1550 | 1000 | Solar | 01_413L6 | 2012-10-26 01:00 | 2012-10-29 | 0 | 0 | 0 | [10 empty] | 2012-11-19 | 2012-12-28 | 27 | 0 | 27 | [12 empty] | 2013-06-03 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SOUTHBRIDGE | 175098 | 1550 | 2000 | Solar | 01_413L6 | 2012-10-26 01:00 | 2012-10-29 | 0 | 0 | 0 | [10 empty] | 2012-11-19 | 2012-12-28 | 27 | 0 | 27 | [12 empty] | 2013-06-03 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ALFORD | 175099 | 1230 | 16.5 | Solar | 09_1109W3 | 2012-10-29 01:00 | 2012-11-02 | 0 | 0 | 0 | 2012-11-19 | 2012-11-19 | 0 | 0 | 0 | [20 empty] | 2013-02-15 | 2012-10-30 01:00 | 2013-01-31 |  | EXP | [6 empty] | 2013-04-29 | 2013-04-29 | 2013-04-03 | Connected |  | No
National Grid | UXBRIDGE | 175129 | 1569 | 3000 | Solar | 05_321W9 | 2012-10-30 01:00 | 2012-11-02 | 1 | 0 | 1 | [10 empty] | 2012-11-20 | 2013-01-02 | 28 | 0 | 28 | [10 empty] | 2013-07-03 | 2012-11-02 01:00 | 2014-12-31 | Yes | STD |  | 2014-06-05 | 2015-04-15 | 213 | 0 | 213 | 2015-04-10 | 2015-04-10 | 2015-04-16 | Connected |  | No
National Grid | GARDNER | 175102 | 1440 | 1000 | Solar | 01_602W2 | 2012-11-02 01:00 | 2012-11-05 | 1 | 0 | 1 | [10 empty] | 2012-11-20 | 2013-01-14 | 36 | 0 | 36 | [10 empty] | 2013-05-17 |  | 2014-04-01 |  | STD |  | 2014-03-21 | 2014-04-29 | 26 | 0 | 26 | 2014-06-13 | 2014-06-13 | 2014-06-13 | Connected |  | No
National Grid | NORTH ANDOVER | 175130 | 1845 | 12 | Solar | 14_56L2 | 2012-11-02 01:00 | 2012-11-05 | 1 | 0 | 1 | 2012-11-20 | 2012-11-20 | 0 | 0 | 0 | [20 empty] | 2013-02-19 |  | 2013-02-15 |  | EXP | [6 empty] | 2013-02-19 | 2013-02-19 | 2013-05-07 | Connected |  | No
National Grid | SPENCER | 175131 | 1562 | 4000 | Solar |  | 2012-11-04 01:00 | 2012-11-05 | 4 | 4 | 0 | [10 empty] | 2012-11-26 | 2013-01-04 | 27 | 0 | 27 | [10 empty] | 2013-08-23 |  | 2016-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 175132 | 1608 | 75 | Solar | 01_HT50 | 2012-11-06 | 2012-11-07 | 7 | 7 | 0 | 2012-11-29 | 2012-11-29 | 0 | 0 | 0 | [20 empty] | 2013-02-06 |  | 2013-01-31 |  | EXP |  | 2013-03-14 | 2013-04-24 | 27 | 0 | 27 | 2014-02-20 | 2014-02-20 | 2014-04-02 | Connected |  | No
National Grid | CHARLTON | 175133 | 1507 | 500 | Solar | 01_406L1 | 2012-11-08 | 2012-11-12 | 4 | 0 | 4 | 2012-11-26 | 2014-09-08 | 435 | 0 | 435 | [22 empty] | 2013-10-16 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LAWRENCE | 174705 | 1840 | 250 | Solar | 14_6J5 | 2012-11-11 | 2012-11-13 | 5 | 0 | 5 | 2012-11-27 | 2013-09-16 | 192 | 0 | 192 | 2013-07-12 | 2013-09-16 | 45 | 0 | 45 | [5 empty] | 2013-07-12 | 2013-09-16 | 45 | 0 | 45 | [5 empty] | 2013-07-12 | 2012-11-11 | 2013-08-15 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 174787 | 1840 | 100 | Solar | 14_2J4 | 2012-11-11 | 2012-11-13 | 5 | 0 | 5 | 2012-11-27 | 2012-11-27 | 0 | 0 | 0 | [20 empty] | 2013-07-12 | 2012-11-11 | 2013-08-11 | Yes | EXP |  | 2014-03-07 | 2014-12-08 | 187 | 0 | 187 | 2014-04-23 | 2014-04-23 | 2014-04-24 | Connected |  | No
National Grid | LAWRENCE | 175134 | 1840 | 100 | Solar | 14_6J5 | 2012-11-11 | 2012-11-13 | 5 | 5 | 0 | 2012-11-27 | 2012-11-27 | 0 | 0 | 0 | [20 empty] | 2013-07-19 |  | 2013-01-31 | Yes | EXP |  | 2014-02-06 | 2014-04-14 | 45 | 0 | 45 | 2013-08-05 | 2013-08-05 | 2014-04-24 | Connected |  | No
National Grid | LAWRENCE | 175135 | 1840 | 150 | Solar | 14_2J4 | 2012-11-11 | 2012-11-13 | 5 | 5 | 0 | [27 empty] | 2013-01-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 175136 | 1840 | 100 | Solar | 14_6J5 | 2012-11-11 | 2012-11-13 | 5 | 5 | 0 | [27 empty] | 2013-01-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WRENTHAM | 175137 | 2093 | 5000 | Solar | 05_2284 | 2012-11-12 | 2012-11-13 | 5 | 0 | 5 | [10 empty] | 2012-11-27 | 2013-01-04 | 26 | 0 | 26 | [12 empty] | 2013-11-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HAMPDEN | 175138 | 1036 | 1000 | Solar | 09_524L1 | 2012-11-12 | 2012-11-13 | 14 | 9 | 5 | [10 empty] | 2012-12-10 | 2013-01-16 | 25 | 0 | 25 | [12 empty] | 2013-06-03 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MENDON | 175167 | 1756 | 15 | Solar | 05_321W6 | 2012-11-13 | 2012-11-14 | 6 | 0 | 6 | 2012-11-28 | 2013-01-22 | 36 | 0 | 36 | [22 empty] | 2013-02-04 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BEVERLY | 175168 | 1915 | 60 | Solar | 12_51L1 | 2012-11-14 | 2012-11-16 | 15 | 9 | 6 | 2012-12-11 | 2012-12-11 | 0 | 0 | 0 | [20 empty] | 2013-03-13 |  | 2013-01-31 |  | EXP | [6 empty] | 2013-06-25 | 2013-06-25 | 2013-08-21 | Connected |  | No
National Grid | SUTTON | 175169 | 1590 | 20 | Solar | 01_304W5 | 2012-11-14 | 2012-11-16 | 7 | 1 | 6 | 2012-11-29 | 2012-11-29 | 0 | 0 | 0 | [20 empty] | 2013-02-13 |  | 2013-01-31 |  | EXP | [6 empty] | 2013-02-13 | 2013-02-13 | 2013-04-12 | Connected |  | No
National Grid | REHOBOTH | 175170 | 2769 | 1500 | Solar | 05_7L5 | 2012-11-15 | 2012-11-19 | 8 | 0 | 8 | [10 empty] | 2012-11-30 | 2013-01-07 | 24 | 0 | 24 | [11 empty] | 2012-11-16 | 2013-08-22 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | HAVERHILL | 174888 | 1830 | 630 | Solar | 14_47L1 | 2012-11-16 | 2012-11-20 | 10 | 0 | 10 | [10 empty] | 2012-12-05 | 2013-03-05 | 56 | 0 | 56 | [10 empty] | 2013-09-09 | 2012-11-16 | 2014-06-30 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | HAVERHILL | 175171 | 1830 | 800 | Solar | 14_47L1 | 2012-11-16 | 2012-11-20 | 10 | 0 | 10 | [10 empty] | 2012-12-05 | 2013-03-05 | 56 | 0 | 56 | [10 empty] | 2013-08-12 | 2012-11-16 | 2016-12-31 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | MARLBOROUGH | 175172 | 1752 | 85 | Solar | 05_311W1 | 2012-11-16 | 2012-11-20 | 10 | 0 | 10 | 2012-12-05 | 2012-12-05 | 0 | 0 | 0 | [20 empty] | 2013-02-21 |  | 2013-04-01 | Yes | EXP | [6 empty] | 2013-02-21 | 2013-02-21 | 2013-07-12 | Connected |  | No
National Grid | WILLIAMSBURG | 175173 | 1096 | 19 | Solar | 09_909W3 | 2012-11-20 | 2012-11-26 | 7 | 0 | 7 | 2012-12-05 | 2012-12-05 | 0 | 0 | 0 | [20 empty] | 2013-02-12 |  | 2013-02-28 |  | EXP | [6 empty] | 2013-02-12 | 2013-02-12 | 2013-07-24 | Connected |  | No
National Grid | WESTBOROUGH | 175072 | 1581 | 95 | Solar | 05_312W2 | 2012-11-21 | 2012-11-26 | 9 | 0 | 9 | 2012-12-07 | 2012-12-07 | 0 | 0 | 0 | [20 empty] | 2013-03-14 |  | 2013-05-31 |  | EXP | [6 empty] | 2013-03-21 | 2013-03-21 | 2013-04-16 | Connected |  | No
National Grid | WESTBOROUGH | 175174 | 1581 | 95 | Solar | 05_312W2 | 2012-11-21 | 2012-11-26 | 9 | 0 | 9 | 2012-12-07 | 2013-04-08 | 74 | 3 | 71 | [20 empty] | 2013-03-14 |  | 2013-02-28 |  | EXP | [6 empty] | 2013-03-21 | 2013-03-21 |  | Withdrawn |  | Yes
National Grid | MEDFORD | 175175 | 2155 | 200 | Solar | 12_11J3 | 2012-11-27 | 2012-11-28 | 8 | 0 | 8 | 2012-12-10 | 2012-12-10 | 0 | 0 | 0 | [20 empty] | 2013-02-22 |  | 2013-02-28 |  | EXP | [6 empty] | 2013-06-18 | 2013-06-18 | 2013-10-09 | Connected |  | No
National Grid | NEWBURY | 175203 | 1951 | 3000 | Solar | 14_60L1 | 2012-11-30 | 2012-12-03 | 9 | 0 | 9 | [10 empty] | 2012-12-14 | 2013-01-14 | 19 | 0 | 19 | [12 empty] | 2013-09-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MILFORD | 174659 | 1757 | 250 | Solar | 05_336W4 | 2012-12-03 | 2012-12-05 | 12 | 4 | 8 | 2012-12-21 | 2014-04-03 | 309 | 0 | 309 | [20 empty] | 2013-03-14 | 2012-12-04 | 2013-05-01 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | GRAFTON | 175206 | 1519 | 3000 | Solar | 01_304W1 | 2012-12-04 | 2012-12-06 | 7 | 0 | 7 | [10 empty] | 2012-12-17 | 2013-01-15 | 19 | 0 | 19 | [5 empty] | 2013-01-15 | 2013-01-15 | 0 | 0 | 0 | 2013-08-09 |  | 2014-12-31 | Yes | STD |  | 2014-08-11 | 2016-03-29 | 404 | 0 | 404 | 2015-03-15 | 2015-03-15 | 2015-03-16 | Connected |  | No
National Grid | DRACUT | 175207 | 1826 | 12 | Solar | 14_75L3 | 2012-12-04 | 2012-12-06 | 7 | 0 | 7 | 2012-12-17 | 2013-11-06 | 214 | 0 | 214 | [20 empty] | 2013-02-15 |  | 2013-03-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SUTTON | 175211 | 1590 | 12.255 | Solar | 01_304W2 | 2012-12-04 | 2012-12-06 | 11 | 8 | 3 | 2012-12-21 | 2012-12-21 | 0 | 0 | 0 | [20 empty] | 2013-03-08 |  | 2013-02-28 |  | EXP | [6 empty] | 2013-03-08 | 2013-03-08 | 2013-04-22 | Connected |  | No
National Grid | MEDFORD | 175209 | 2155 | 12 | Solar | 12_17J6 | 2012-12-05 | 2012-12-07 | 10 | 5 | 5 | 2012-12-21 | 2012-12-21 | 0 | 0 | 0 | [20 empty] | 2013-02-15 | 2012-12-05 | 2013-02-28 |  | EXP | [6 empty] | 2013-02-15 | 2013-02-15 | 2013-03-14 | Connected |  | No
National Grid | ATTLEBORO | 175210 | 2703 | 285 | Solar | 05_9L5 | 2012-12-05 | 2012-12-07 | 6 | 0 | 6 | 2012-12-17 | 2012-12-17 | 0 | 0 | 0 | [20 empty] | 2013-02-14 |  | 2013-05-15 | Yes | EXP |  | 2013-06-07 | 2013-07-31 | 36 | 0 | 36 | 2013-02-15 | 2013-02-15 | 2013-09-23 | Connected |  | No
National Grid | WESTBOROUGH | 175204 | 1581 | 1800 | Solar | 05_312W2 | 2012-12-06 | 2012-12-07 | 8 | 0 | 8 | [10 empty] | 2012-12-19 | 2013-03-21 | 54 | 0 | 54 | [11 empty] | 2012-12-07 | 2013-06-03 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WEBSTER | 175205 | 1570 | 1380 | Solar | 01_412L1 | 2012-12-07 | 2012-12-07 | 8 | 0 | 8 | [10 empty] | 2012-12-19 | 2013-01-15 | 17 | 0 | 17 | [10 empty] | 2014-06-27 |  | 2016-01-20 | Yes | STD |  | 2015-07-30 | 2016-12-20 | 346 | 0 | 346 | 2016-12-29 | 2016-12-29 | 2016-12-29 | Connected |  | No
National Grid | WORCESTER | 175212 | 1604 | 1200 | Natural Gas | 01_10J383 | 2012-12-07 | 2012-12-10 | 12 | 7 | 5 | [10 empty] | 2012-12-27 | 2013-02-20 | 32 | 0 | 32 | [10 empty] | 2013-10-24 |  | 2013-08-30 |  | STD | [6 empty] | 2013-10-24 | 2013-10-24 | 2013-10-24 | Terminated |  | No
National Grid | SUTTON | 174658 | 1590 | 150 | Natural Gas | 01_304W6 | 2012-12-10 | 2012-12-11 | 20 | 14 | 6 | 2013-01-10 | 2013-01-10 | 0 | 0 | 0 | [20 empty] | 2013-03-18 |  | 2014-10-15 |  | EXP | [6 empty] | 2015-06-15 | 2015-06-15 | 2015-06-30 | Connected |  | No
National Grid | BRIMFIELD | 174660 | 1010 | 3000 | Solar |  | 2012-12-11 | 2012-12-11 | 8 | 0 | 8 | [10 empty] | 2012-12-21 | 2013-01-29 | 24 | 0 | 24 | [11 empty] | 2012-12-11 | 2013-07-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WENDELL | 174661 | 1379 | 1000 | Solar | 09_705W1 | 2012-12-11 | 2012-12-14 | 7 | 0 | 7 | [10 empty] | 2012-12-26 | 2013-03-20 | 49 | 0 | 49 | [5 empty] | 2015-02-06 | 2018-05-10 | 176 | 0 | 176 | 2015-02-06 |  | 2018-12-31 | Yes | STD |  | 2018-11-15 | 2018-12-17 | 32 | 0 | 32 |  |  | 2018-12-28 | Connected |  | No
National Grid | BELCHERTOWN | 174662 | 1007 | 11.18 | Solar | 09_509L2 | 2012-12-12 | 2012-12-14 | 7 | 0 | 7 | 2012-12-26 | 2012-12-26 | 0 | 0 | 0 | [20 empty] | 2013-03-08 | 2012-12-12 | 2013-03-01 |  | EXP | [6 empty] | 2013-03-25 | 2013-03-25 | 2013-04-22 | Connected |  | No
National Grid | BEVERLY | 174664 | 1915 | 110 | Solar | 12_12L6 | 2012-12-12 | 2012-12-14 | 8 | 0 | 8 | 2012-12-27 | 2012-12-27 | 0 | 0 | 0 | [20 empty] | 2013-03-06 | 2012-12-12 | 2013-04-30 | Yes | EXP | [6 empty] | 2013-08-07 | 2013-08-07 | 2013-08-15 | Connected |  | Yes
National Grid | BEVERLY | 174665 | 1915 | 230 | Solar | 12_12L6 | 2012-12-12 | 2012-12-14 | 8 | 0 | 8 | 2012-12-27 | 2012-12-27 | 0 | 0 | 0 | [20 empty] | 2013-03-06 | 2012-12-13 | 2013-04-30 | Yes | EXP | [6 empty] | 2013-08-07 | 2013-08-07 | 2013-08-15 | Connected |  | No
National Grid | BEVERLY | 174663 | 1915 | 50 | Solar | 12_12L4 | 2012-12-13 | 2012-12-14 | 8 | 0 | 8 | 2012-12-27 | 2012-12-27 | 0 | 0 | 0 | 2013-03-12 | 2013-03-12 | 0 | 0 | 0 | [5 empty] | 2013-03-12 | 2013-03-12 | 0 | 0 | 0 | [5 empty] | 2013-03-06 |  | 2013-04-30 | Yes | EXP | [6 empty] | 2013-08-07 | 2013-08-07 | 2013-08-28 | Connected |  | Yes
National Grid | MILLBURY | 174666 | 1527 | 19.99 | Solar | 01_304W5 | 2012-12-18 | 2012-12-19 | 8 | 0 | 8 | 2013-01-02 | 2013-01-02 | 0 | 0 | 0 | [20 empty] | 2013-03-18 | 2012-12-21 | 2013-03-08 |  | EXP | [6 empty] | 2013-05-22 | 2013-05-22 | 2013-06-11 | Connected |  | No
National Grid | NORTON | 174694 | 2766 | 500 | Solar | 07_92W79 | 2012-12-21 | 2012-12-21 | 9 | 0 | 9 | [10 empty] | 2013-01-07 | 2013-03-20 | 42 | 0 | 42 | [5 empty] | 2014-01-15 | 2014-04-03 | 53 | 0 | 53 | 2013-12-31 |  | 2016-12-31 | Yes | STD | [6 empty] | 2012-12-25 | 2012-12-25 | 2016-02-23 | Connected |  | No
National Grid | NORTON | 174695 | 2766 | 900 | Solar | 07_92W79 | 2012-12-21 | 2012-12-21 | 9 | 0 | 9 | [10 empty] | 2013-01-07 | 2013-03-20 | 42 | 0 | 42 | [10 empty] | 2015-05-07 | 2012-12-21 | 2015-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTON | 175004 | 2766 | 500 | Solar | 07_92W79 | 2012-12-21 | 2012-12-21 | 9 | 0 | 9 | [10 empty] | 2013-01-07 | 2013-03-20 | 42 | 0 | 42 | [5 empty] | 2014-01-15 | 2014-04-03 | 53 | 0 | 53 | 2013-12-31 | 2012-12-21 | 2016-12-31 | Yes | STD | [8 empty] | 2016-02-23 | Connected |  | No
National Grid | NORTON | 175005 | 2766 | 750 | Solar | 07_92W79 | 2012-12-21 | 2012-12-21 | 9 | 0 | 9 | [10 empty] | 2013-01-07 | 2013-03-20 | 42 | 0 | 42 | [5 empty] | 2014-01-15 | 2014-04-03 | 53 | 0 | 53 | 2013-12-31 | 2012-12-21 | 2016-12-31 | Yes | STD | [6 empty] | 2013-09-18 | 2013-09-18 | 2016-02-23 | Connected |  | No
National Grid | NORTON | 175006 | 2766 | 750 | Solar | 07_92W79 | 2012-12-21 | 2012-12-21 | 9 | 0 | 9 | [10 empty] | 2013-01-07 | 2013-03-20 | 42 | 0 | 42 | [5 empty] | 2014-01-15 | 2014-04-03 | 53 | 0 | 53 | 2013-12-31 |  | 2016-12-31 | Yes | STD | [6 empty] | 2013-09-18 | 2013-09-18 | 2016-02-23 | Connected |  | No
National Grid | NORTON | 175514 | 2766 | 500 | Solar | 07_92W79 | 2012-12-21 | 2012-12-21 | 9 | 0 | 9 | [10 empty] | 2013-01-07 | 2013-03-20 | 42 | 0 | 42 | [11 empty] | 2012-12-26 | 2014-11-28 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WILLIAMSBURG | 174696 | 1096 | 2266 | Solar | 09_909W3 | 2012-12-26 | 2012-12-27 | 8 | 0 | 8 | [10 empty] | 2013-01-09 | 2013-03-20 | 40 | 0 | 40 | [5 empty] | 2014-10-06 | 2014-10-06 | 0 | 0 | 0 | 2013-08-22 | 2012-12-31 | 2016-12-31 | Yes | STD |  | 2014-11-26 | 2016-02-12 | 300 | 0 | 300 | 2016-02-26 | 2016-02-26 | 2016-02-26 | Connected |  | No
National Grid | LEOMINSTER | 174697 | 1453 | 2000 | Solar | 01_219W2 | 2012-12-31 | 2013-01-02 | 6 | 0 | 6 | [10 empty] | 2013-01-10 | 2013-03-20 | 39 | 0 | 39 | [10 empty] | 2014-04-08 |  | 2014-01-31 | Yes | STD |  | 2014-12-26 | 2015-04-14 | 73 | 0 | 73 | 2015-04-09 | 2015-04-09 | 2015-04-09 | Connected |  | No
National Grid | BRIMFIELD | 174698 | 1010 | 2000 | Solar | 09_503L4 | 2013-01-01 | 2013-01-03 | 7 | 0 | 7 | [27 empty] | 2013-07-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | AMESBURY | 174700 | 1913 | 595 | Solar | 14_275L2 | 2013-01-03 | 2013-01-04 | 7 | 0 | 7 | 2013-01-15 | 2014-05-29 | 332 | 0 | 332 | [20 empty] | 2013-05-02 |  | 2013-05-31 |  | EXP | [6 empty] | 2013-05-02 | 2013-05-02 |  | Withdrawn |  | No
National Grid | WESTMINSTER | 174702 | 1473 | 13.5 | Solar | 01_609W2 | 2013-01-03 | 2013-01-04 | 16 | 9 | 7 | 2013-01-29 | 2013-01-29 | 0 | 0 | 0 | [20 empty] | 2013-05-23 |  | 2013-03-29 |  | EXP | [6 empty] | 2013-06-05 | 2013-06-05 | 2013-08-15 | Connected |  | No
National Grid | SEEKONK | 174699 | 2771 | 60 | Natural Gas | 05_7L3 | 2013-01-04 | 2013-01-07 | 13 | 13 | 0 | [27 empty] | 2013-06-28 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MILLBURY | 174701 | 1527 | 11.5 | Solar | 01_304W5 | 2013-01-04 | 2013-01-07 | 8 | 0 | 8 | 2013-01-17 | 2013-01-17 | 0 | 0 | 0 | [20 empty] | 2013-03-08 | 2013-01-04 | 2013-04-30 |  | EXP | [6 empty] | 2013-06-03 | 2013-06-03 | 2013-06-06 | Connected |  | No
National Grid | SALISBURY | 174732 | 1952 | 32.9 | Solar | 14_7L2 | 2013-01-04 | 2013-01-07 | 8 | 0 | 8 | 2013-01-17 | 2013-01-17 | 0 | 0 | 0 | [20 empty] | 2013-03-18 |  | 2013-03-29 | Yes | EXP | [6 empty] | 2013-04-17 | 2013-04-17 | 2013-08-15 | Connected |  | Yes
National Grid | FRANKLIN | 174733 | 2038 | 13.97 | Solar | 05_344W1 | 2013-01-08 | 2013-01-09 | 7 | 0 | 7 | 2013-01-18 | 2013-01-18 | 0 | 0 | 0 | [20 empty] | 2013-03-25 |  | 2013-03-29 |  | EXP | [6 empty] | 2013-10-07 | 2013-10-07 | 2013-12-03 | Connected |  | No
National Grid | UXBRIDGE | 174734 | 1569 | 13.115 | Solar | 05_320W4 | 2013-01-08 | 2013-01-09 | 7 | 0 | 7 | 2013-01-18 | 2013-01-18 | 0 | 0 | 0 | [20 empty] | 2013-03-11 |  | 2013-03-29 |  | EXP | [6 empty] | 2013-05-31 | 2013-05-31 | 2013-06-11 | Connected |  | No
National Grid | MENDON | 174770 | 1756 | 12.9 | Solar | 05_321W6 | 2013-01-14 | 2013-01-15 | 5 | 0 | 5 | 2013-01-23 | 2013-01-23 | 0 | 0 | 0 | [20 empty] | 2013-03-15 |  | 2013-04-30 |  | EXP | [6 empty] | 2013-05-17 | 2013-05-17 | 2013-06-03 | Connected |  | No
National Grid | MILLBURY | 174739 | 1527 | 300 | Solar | 01_8W2 | 2013-01-15 | 2013-01-16 | 6 | 0 | 6 | 2013-01-25 | 2013-01-25 | 0 | 0 | 0 | [20 empty] | 2013-03-21 |  | 2013-06-28 |  | EXP | [6 empty] | 2013-03-26 | 2013-03-26 | 2013-08-20 | Connected |  | No
National Grid | TYNGSBORO | 174740 | 1879 | 5500 | Solar | 14_211L2 | 2013-01-15 | 2013-01-16 | 6 | 0 | 6 | [10 empty] | 2013-01-25 | 2013-04-04 | 40 | 0 | 40 | [12 empty] | 2013-10-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | GOSHEN | 174741 | 1032 | 3000 | Solar | 09_909W3 | 2013-01-16 | 2013-01-17 | 37 | 31 | 6 | [27 empty] | 2013-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | UPTON | 174772 | 1568 | 60 | Solar | 05_335W3 | 2013-01-17 | 2013-01-18 | 9 | 7 | 2 | 2013-02-01 | 2013-02-01 | 0 | 0 | 0 | [20 empty] | 2013-04-16 |  | 2013-04-15 |  | EXP | [6 empty] | 2013-07-29 | 2013-07-29 | 2013-08-16 | Connected |  | No
National Grid | RUTLAND | 174773 | 1543 | 57.5 | Solar | 01_55W1 | 2013-01-17 | 2013-01-18 | 10 | 8 | 2 | 2013-02-04 | 2013-02-04 | 0 | 0 | 0 | [20 empty] | 2013-04-30 |  | 2013-05-01 |  | EXP | [6 empty] | 2013-05-02 | 2013-05-02 | 2013-10-04 | Connected |  | No
National Grid | BRIMFIELD | 174777 | 1010 | 3000 | Solar |  | 2013-01-21 | 2013-01-22 | 9 | 1 | 8 | [10 empty] | 2013-02-04 | 2014-09-08 | 388 | 0 | 388 | [12 empty] | 2013-11-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HOUSATONIC | 174778 | 1236 | 3000 | Solar | 09_1109W2 | 2013-01-21 | 2013-01-22 | 9 | 1 | 8 | [10 empty] | 2013-02-04 | 2013-04-03 | 33 | 0 | 33 | [12 empty] | 2013-11-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HOUSATONIC | 174779 | 1236 | 1000 | Solar | 09_1109W2 | 2013-01-21 | 2013-01-22 | 12 | 4 | 8 | [10 empty] | 2013-02-07 | 2013-04-03 | 30 | 0 | 30 | [12 empty] | 2013-11-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SEEKONK | 174774 | 2771 | 60 | Natural Gas | 05_7L3 | 2013-01-22 | 2013-01-22 | 16 | 13 | 3 | 2013-02-20 | 2014-09-04 | 379 | 0 | 379 | [20 empty] | 2013-03-26 |  | 2013-06-28 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SEEKONK | 174775 | 2771 | 60 | Natural Gas | 05_7L3 | 2013-01-22 | 2013-01-22 | 16 | 13 | 3 | 2013-02-20 | 2014-09-04 | 379 | 0 | 379 | [20 empty] | 2013-03-26 |  | 2013-06-28 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NEWBURY | 174776 | 1951 | 3000 | Solar | 14_60L4 | 2013-01-22 | 2013-01-23 | 5 | 0 | 5 | [10 empty] | 2013-01-30 | 2013-05-21 | 69 | 0 | 69 | [12 empty] | 2013-10-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HOLBROOK | 174807 | 2343 | 20 | Solar | 07_2W1 | 2013-01-22 | 2013-01-23 | 7 | 0 | 7 | 2013-02-01 | 2013-02-01 | 0 | 0 | 0 | [20 empty] | 2013-03-25 |  | 2013-04-30 |  | EXP | [6 empty] | 2013-03-25 | 2013-03-25 | 2013-04-29 | Connected |  | No
National Grid | MEDFORD | 174805 | 2155 | 300 | Solar | 12_11J3 | 2013-01-23 | 2013-01-24 | 6 | 0 | 6 | 2013-02-01 | 2014-07-08 | 346 | 0 | 346 | [20 empty] | 2013-04-02 |  | 2013-06-28 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | AMESBURY | 174806 | 1913 | 300 | Solar | 14_275L2 | 2013-01-23 | 2013-01-24 | 7 | 0 | 7 | 2013-02-04 | 2013-02-04 | 0 | 0 | 0 | [20 empty] | 2013-03-28 |  | 2013-06-28 |  | EXP | [6 empty] | 2013-03-28 | 2013-03-28 | 2013-08-22 | Connected |  | No
National Grid | GRANBY | 174808 | 1033 | 16 | Solar | 09_527L1 | 2013-01-24 | 2013-01-25 | 6 | 0 | 6 | 2013-02-04 | 2013-02-04 | 0 | 0 | 0 | [20 empty] | 2013-03-15 |  | 2013-04-30 |  | EXP | [6 empty] | 2013-04-10 | 2013-04-10 | 2013-05-02 | Connected |  | No
National Grid | WORCESTER | 174809 | 1604 | 145 | Solar | 01_10J323 | 2013-01-24 | 2013-01-25 | 7 | 0 | 7 | 2013-02-05 | 2013-02-05 | 0 | 0 | 0 | [20 empty] | 2013-04-12 |  | 2013-05-15 |  | EXP |  | 2013-05-22 | 2013-07-17 | 37 | 0 | 37 | 2013-07-29 | 2013-07-29 | 2013-08-20 | Connected |  | Yes
National Grid | HANOVER | 174810 | 2339 | 250 | Solar | 07_95W2 | 2013-01-24 | 2013-01-25 | 10 | 4 | 6 | 2013-02-14 | 2014-10-03 | 403 | 0 | 403 | [20 empty] | 2013-03-26 | 2013-01-29 | 2013-05-31 |  | EXP | [6 empty] | 2013-03-26 | 2013-03-26 |  | Withdrawn |  | Yes
National Grid | NORTH GRAFTON | 174845 | 1536 | 2000 | Solar | 01_328W3 | 2013-01-29 | 2013-01-31 | 5 | 0 | 5 | [10 empty] | 2013-02-07 | 2013-04-01 | 28 | 0 | 28 | [10 empty] | 2013-12-09 |  | 2017-08-01 |  | STD | [6 empty] | 2017-07-12 | 2017-07-12 | 2017-07-31 | Connected |  | No
National Grid | BELCHERTOWN | 174846 | 1007 | 11.83 | Solar | 09_509L1 | 2013-01-30 | 2013-01-31 | 7 | 0 | 7 | 2013-02-15 | 2013-02-15 | 0 | 0 | 0 | [20 empty] | 2013-04-18 |  | 2013-04-30 |  | EXP | [6 empty] | 2013-05-21 | 2013-05-21 | 2013-05-24 | Connected |  | No
National Grid | SHEFFIELD | 174847 | 1257 | 30 | Solar | 09_1109W2 | 2013-02-04 | 2013-02-05 | 5 | 0 | 5 | 2013-02-19 | 2013-02-19 | 0 | 0 | 0 | [20 empty] | 2013-03-18 |  | 2013-04-30 |  | EXP | [6 empty] | 2013-05-16 | 2013-05-16 | 2013-06-10 | Connected |  | No
National Grid | MENDON | 174848 | 1756 | 20 | Solar | 05_335W1 | 2013-02-05 | 2013-02-06 | 4 | 0 | 4 | 2013-02-19 | 2013-02-19 | 0 | 0 | 0 | [20 empty] | 2013-04-08 |  | 2013-04-30 |  | EXP | [6 empty] | 2013-04-08 | 2013-04-08 | 2013-07-02 | Connected |  | No
National Grid | LANCASTER | 174878 | 1523 | 1800 | Solar | 01_225W1 | 2013-02-06 | 2013-02-07 | 210 | 207 | 3 | [27 empty] | 2013-10-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTMINSTER | 174879 | 1473 | 1800 | Solar | 01_609W2 | 2013-02-06 | 2013-02-07 | 210 | 207 | 3 | [26 empty] | 2013-02-14 | 2013-10-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTBOROUGH | 174880 | 1581 | 250.8 | Solar | 05_314W4 | 2013-02-14 | 2013-02-15 | 7 | 2 | 5 | 2013-02-27 | 2013-02-27 | 0 | 0 | 0 | [20 empty] | 2013-10-08 |  | 2013-10-01 |  | EXP |  | 2013-11-19 | 2014-03-15 | 79 | 0 | 79 | 2014-11-20 | 2014-11-20 | 2014-12-02 | Connected |  | No
National Grid | NORTHBOROUGH | 174916 | 1532 | 760 | Solar | 05_313W3 | 2013-02-14 | 2013-02-19 | 7 | 0 | 7 | [10 empty] | 2013-02-28 | 2013-04-09 | 24 | 0 | 24 | [10 empty] | 2013-10-18 |  | 2014-06-30 |  | STD | [6 empty] | 2014-12-30 | 2014-12-30 | 2014-12-31 | Connected |  | No
National Grid | BLACKSTONE | 174884 | 1504 | 11 | Solar | 05_321W6 | 2013-02-15 | 2013-02-21 | 5 | 0 | 5 | 2013-02-28 | 2013-02-28 | 0 | 0 | 0 | [20 empty] | 2013-03-28 |  | 2013-05-31 |  | EXP | [6 empty] | 2013-04-29 | 2013-04-29 | 2013-05-22 | Connected |  | No
National Grid | WRENTHAM | 178768 | 2093 | 11 | Solar | 05_3422W1 | 2013-02-15 | 2013-02-21 | 5 | 0 | 5 | 2013-02-28 | 2013-04-17 | 34 | 0 | 34 | [20 empty] | 2013-04-17 |  | 2016-12-31 |  | EXP | [6 empty] | 2013-04-17 | 2013-04-17 | 2014-01-01 | Connected |  | No
National Grid | FALL RIVER | 174885 | 2721 | 40 | Solar | 05_106W43 | 2013-02-16 | 2013-02-19 | 7 | 0 | 7 | 2013-02-28 | 2014-04-04 | 269 | 0 | 269 | [20 empty] | 2013-04-02 |  | 2013-05-31 |  | EXP | [6 empty] | 2013-04-02 | 2013-04-02 |  | Withdrawn |  | No
National Grid | WESTBOROUGH | 174886 | 1581 | 1500 | Solar | 05_312W5 | 2013-02-21 | 2013-02-25 | 6 | 0 | 6 | [10 empty] | 2013-03-05 | 2013-04-05 | 19 | 0 | 19 | [10 empty] | 2013-08-12 |  | 2013-08-30 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | FRANKLIN | 174915 | 2038 | 12.9 | Solar | 05_344W4 | 2013-02-21 | 2013-02-25 | 6 | 0 | 6 | 2013-03-05 | 2014-07-08 | 329 | 0 | 329 | [20 empty] | 2013-04-09 |  | 2013-05-31 |  | EXP | [6 empty] | 2013-04-09 | 2013-04-09 |  | Withdrawn |  | Yes
National Grid | SAUGUS | 174925 | 1906 | 1000 | Solar | 12_25W1 | 2013-02-25 | 2013-02-27 | 5 | 0 | 5 | [10 empty] | 2013-03-07 | 2013-04-09 | 20 | 0 | 20 | [12 empty] | 2013-10-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | OXFORD | 174918 | 1540 | 13.12 | Solar | 01_406L3 | 2013-02-26 | 2013-02-27 | 7 | 2 | 5 | 2013-03-13 | 2013-03-13 | 0 | 0 | 0 | [20 empty] | 2013-03-22 |  | 2013-05-31 |  | EXP | [6 empty] | 2013-09-04 | 2013-09-04 | 2013-11-20 | Connected |  | No
National Grid | GOSHEN | 174919 | 1032 | 3000 | Solar | 09_909W3 | 2013-02-26 | 2013-02-27 | 5 | 0 | 5 | [10 empty] | 2013-03-07 | 2013-04-08 | 19 | 0 | 19 | [12 empty] | 2013-11-29 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORWELL | 174920 | 2061 | 2000 | Solar | 07_96W40 | 2013-02-26 | 2013-02-27 | 5 | 0 | 5 | [10 empty] | 2013-03-07 | 2013-04-08 | 19 | 0 | 19 | [12 empty] | 2013-11-29 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LEICESTER | 174924 | 1524 | 75 | Solar | 01_6W2 | 2013-02-26 | 2013-02-27 | 5 | 1 | 4 | 2013-03-11 | 2013-03-11 | 0 | 0 | 0 | [20 empty] | 2013-05-22 | 2013-02-27 | 2013-07-31 |  | EXP | [6 empty] | 2013-07-03 | 2013-07-03 | 2013-07-19 | Connected |  | No
National Grid | HOPEDALE | 174954 | 1747 | 164 | Solar | 05_335W1 | 2013-02-27 | 2013-02-28 | 4 | 0 | 4 | 2013-03-11 | 2013-03-11 | 0 | 0 | 0 | [20 empty] | 2013-03-22 |  | 2016-01-15 | Yes | EXP |  | 2015-11-04 | 2015-11-09 | 3 | 0 | 3 | 2013-07-30 | 2013-07-30 | 2015-12-29 | Connected |  | Yes
National Grid | MELROSE | 174956 | 2176 | 260 | Solar | 12_2335 | 2013-02-28 | 2013-03-01 | 3 | 0 | 3 | 2013-03-11 | 2013-03-11 | 0 | 0 | 0 | [20 empty] | 2013-06-07 |  | 2013-07-31 |  | EXP | [6 empty] | 2013-12-19 | 2013-12-19 | 2013-12-19 | Connected |  | Yes
National Grid | SCITUATE | 174958 | 2066 | 85 | Solar | 07_915W37 | 2013-02-28 | 2013-03-01 | 3 | 0 | 3 | 2013-03-11 | 2013-03-11 | 0 | 0 | 0 | [20 empty] | 2013-06-03 | 2013-03-01 | 2013-07-31 |  | EXP | [6 empty] | 2013-12-12 | 2013-12-12 | 2013-12-27 | Connected |  | No
National Grid | BERLIN | 174855 | 1503 | 750 | Solar | 05_318W3 | 2013-03-01 | 2013-03-05 | 4 | 0 | 4 | [10 empty] | 2013-03-14 | 2013-04-18 | 23 | 0 | 23 | [10 empty] | 2013-10-18 | 2013-03-01 | 2014-06-30 |  | STD | [6 empty] | 2014-12-30 | 2014-12-30 | 2014-12-30 | Connected |  | No
National Grid | BERLIN | 174856 | 1503 | 750 | Solar | 05_318W3 | 2013-03-01 | 2013-03-05 | 4 | 0 | 4 | [10 empty] | 2013-03-14 | 2013-04-18 | 23 | 0 | 23 | [10 empty] | 2013-10-18 | 2013-03-01 | 2014-06-30 |  | STD | [6 empty] | 2014-12-30 | 2014-12-30 | 2014-12-30 | Connected |  | No
National Grid | BERLIN | 174857 | 1503 | 750 | Solar | 05_318W3 | 2013-03-01 | 2013-03-05 | 4 | 0 | 4 | [10 empty] | 2013-03-14 | 2013-04-18 | 23 | 0 | 23 | [10 empty] | 2013-10-18 | 2013-03-01 | 2014-06-30 |  | STD | [6 empty] | 2014-12-30 | 2014-12-30 | 2014-12-30 | Connected |  | No
National Grid | REHOBOTH | 174957 | 2769 | 3334 | Solar | 05_2248 | 2013-03-01 | 2013-03-04 | 5 | 0 | 5 | [10 empty] | 2013-03-14 | 2013-03-21 | 4 | 0 | 4 | [10 empty] | 2013-10-18 | 2013-03-01 | 2014-06-30 |  | STD | [6 empty] | 2015-07-16 | 2015-07-16 | 2015-07-21 | Connected |  | No
National Grid | BERLIN | 174960 | 1503 | 750 | Solar | 05_318W3 | 2013-03-01 | 2013-03-05 | 4 | 0 | 4 | [10 empty] | 2013-03-14 | 2013-04-18 | 23 | 0 | 23 | [10 empty] | 2013-10-18 | 2013-03-04 | 2014-06-30 |  | STD | [6 empty] | 2014-12-30 | 2014-12-30 | 2014-12-30 | Connected |  | No
National Grid | WEST BRIDGEWATER | 174959 | 2379 | 300 | Solar | 07_912W21 | 2013-03-04 | 2013-03-04 | 5 | 0 | 5 | 2013-03-14 | 2013-03-14 | 0 | 0 | 0 | [20 empty] | 2013-04-15 | 2013-03-05 | 2013-11-29 | Yes | EXP |  | 2013-11-19 | 2013-12-02 | 8 | 0 | 8 | 2013-11-05 | 2013-11-05 | 2013-12-12 | Connected |  | No
National Grid | DRACUT | 174961 | 1826 | 60 | Solar | 14_75L3 | 2013-03-05 | 2013-03-06 | 4 | 0 | 4 | 2013-03-15 | 2013-03-15 | 0 | 0 | 0 | [20 empty] | 2013-09-30 |  | 2013-06-14 | Yes | EXP |  | 2014-01-30 | 2014-03-11 | 27 | 0 | 27 | 2014-04-24 | 2014-04-24 | 2014-04-24 | Connected |  | No
National Grid | REVERE | 174990 | 2151 | 75 | Diesel | 12_7W1 | 2013-03-06 | 2013-03-07 | 5 | 0 | 5 | 2013-03-18 | 2013-03-18 | 0 | 0 | 0 | [20 empty] | 2013-04-19 |  | 2013-06-28 |  | EXP | [6 empty] | 2013-09-13 | 2013-09-13 | 2013-09-17 | Connected |  | Yes
National Grid | SUTTON | 174996 | 1590 | 1250 | Solar | 01_304W6 | 2013-03-08 | 2013-03-11 | 5 | 0 | 5 | [10 empty] | 2013-03-19 | 2013-04-30 | 29 | 0 | 29 | [12 empty] | 2013-08-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LEICESTER | 174992 | 1524 | 13.11 | Solar | 01_23W3 | 2013-03-11 01:00 | 2013-03-12 | 5 | 0 | 5 | 2013-03-20 | 2013-03-20 | 0 | 0 | 0 | [20 empty] | 2013-04-03 |  | 2013-07-05 |  | EXP | [6 empty] | 2013-04-03 | 2013-04-03 | 2013-05-24 | Connected |  | No
National Grid | WESTBOROUGH | 174993 | 1581 | 100 | Solar | 05_312W1 | 2013-03-11 01:00 | 2013-03-12 | 4 | 0 | 4 | 2013-03-19 | 2017-02-27 | 978 | 0 | 978 | [20 empty] | 2013-04-30 |  | 2016-12-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BOXFORD | 174994 | 1921 | 13 | Solar | 14_55L1 | 2013-03-13 01:00 | 2013-03-14 | 6 | 0 | 6 | 2013-03-25 | 2013-03-25 | 0 | 0 | 0 | [20 empty] | 2013-04-11 | 2013-03-20 01:00 | 2013-06-28 |  | EXP | [6 empty] | 2013-04-15 | 2013-04-15 | 2013-06-05 | Connected |  | No
National Grid | GRAFTON | 175027 | 1519 | 1000 | Solar | 01_328W1 | 2013-03-20 01:00 | 2013-03-21 | 6 | 0 | 6 | [10 empty] | 2013-03-29 | 2013-05-15 | 32 | 0 | 32 | [10 empty] | 2014-03-19 |  | 2016-02-16 | Yes | STD |  | 2016-06-24 | 2017-01-06 | 133 | 0 | 133 |  |  | 2017-02-10 | Connected |  | No
National Grid | BEVERLY | 175028 | 1915 | 800 | Solar | 12_51T1 | 2013-03-20 01:00 | 2013-03-21 | 6 | 0 | 6 | [10 empty] | 2013-03-29 | 2013-05-15 | 32 | 0 | 32 | [10 empty] | 2013-05-15 |  | 2014-06-30 |  | STD | [6 empty] | 2013-12-27 | 2013-12-27 | 2013-12-30 | Connected |  | No
National Grid | AMESBURY | 175029 | 1913 | 300 | Solar | 14_2377N | 2013-03-21 01:00 | 2013-03-25 | 6 | 0 | 6 | 2013-04-02 | 2013-04-02 | 0 | 0 | 0 | 2013-06-11 | 2013-06-11 | 0 | 0 | 0 | [5 empty] | 2013-06-11 | 2013-06-11 | 0 | 0 | 0 | [5 empty] | 2013-06-12 |  | 2013-08-30 |  | EXP | [6 empty] | 2013-08-23 | 2013-08-23 | 2013-09-19 | Connected |  | No
National Grid | AMESBURY | 175030 | 1913 | 50 | Solar | 14_2377N | 2013-03-21 01:00 | 2013-03-25 | 6 | 0 | 6 | [27 empty] | 2013-08-30 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEICESTER | 175031 | 1524 | 1000 | Solar | 01_406L1 | 2013-03-21 01:00 | 2013-03-25 | 6 | 0 | 6 | [10 empty] | 2013-04-02 | 2013-05-07 | 24 | 0 | 24 | [11 empty] | 2013-03-22 01:00 | 2013-08-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BRIMFIELD | 175032 | 1010 | 2000 | Solar | 09_516L1 | 2013-03-22 01:00 | 2013-03-25 | 7 | 0 | 7 | [10 empty] | 2013-04-03 | 2013-05-14 | 28 | 0 | 28 | [10 empty] | 2013-08-23 |  | 2014-07-01 |  | STD | [6 empty] | 2014-06-19 | 2014-06-19 | 2014-06-19 | Connected |  | No
National Grid | FALL RIVER | 175033 | 2720 | 900 | Wind | 05_28W40 | 2013-03-25 01:00 | 2013-03-26 | 7 | 0 | 7 | [10 empty] | 2013-04-04 | 2013-06-14 | 49 | 0 | 49 | [12 empty] | 2014-04-14 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | WARE | 175065 | 1082 | 936 | Solar | 09_501L4 | 2013-03-28 01:00 | 2013-03-29 | 7 | 0 | 7 | [10 empty] | 2013-04-09 | 2013-06-14 | 46 | 0 | 46 | [5 empty] | 2014-04-23 | 2014-06-11 | 34 | 0 | 34 | 2014-06-11 | 2013-03-28 01:00 | 2016-07-01 |  | STD | [6 empty] | 2017-07-12 | 2017-07-12 | 2017-08-04 | Connected |  | No
National Grid | OXFORD | 175066 | 1540 | 1500 | Solar | 01_406L3 | 2013-03-28 01:00 | 2013-03-29 | 7 | 0 | 7 | [10 empty] | 2013-04-09 | 2013-06-24 | 51 | 0 | 51 | [10 empty] | 2014-01-20 | 2013-03-28 01:00 | 2018-05-11 | Yes | STD | [6 empty] | 2018-04-16 | 2018-04-16 | 2018-05-10 | Connected |  | No
National Grid | HUBBARDSTON | 175067 | 1452 | 675 | Solar | 01_602W2 | 2013-03-28 01:00 | 2013-03-29 | 19 | 12 | 7 | [10 empty] | 2013-04-26 | 2013-06-03 | 25 | 0 | 25 | [10 empty] | 2013-11-01 |  | 2014-02-03 | Yes | STD |  | 2014-10-09 | 2014-12-10 | 41 | 0 | 41 | 2014-12-23 | 2014-12-23 | 2014-12-23 | Connected |  | No
National Grid | BELCHERTOWN | 175068 | 1007 | 21.2 | Solar | 09_509L1 | 2013-04-01 01:00 | 2013-04-02 | 7 | 0 | 7 | 2013-04-11 | 2013-04-11 | 0 | 0 | 0 | [20 empty] | 2013-04-19 | 2013-04-03 01:00 | 2013-04-08 |  | EXP | [6 empty] | 2013-06-17 | 2013-06-17 | 2013-06-26 | Connected |  | No
National Grid | FRANKLIN | 175069 | 2038 | 1050 | Solar | 05_344W3 | 2013-04-03 01:00 | 2013-04-04 | 7 | 0 | 7 | [10 empty] | 2013-04-15 | 2013-06-24 | 47 | 0 | 47 | [10 empty] | 2014-04-03 |  | 2014-06-30 |  | STD |  | 2014-09-22 | 2015-03-30 | 127 | 0 | 127 | 2015-05-11 | 2015-05-11 | 2015-05-22 | Connected |  | No
National Grid | REVERE | 175070 | 2151 | 200 | Solar | 12_2340 | 2013-04-04 01:00 | 2013-04-05 | 6 | 0 | 6 | 2013-04-16 | 2014-05-27 | 276 | 0 | 276 | [22 empty] | 2013-10-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BOXFORD | 175071 | 1921 | 11.61 | Solar | 14_56L3 | 2013-04-08 01:00 | 2013-04-09 | 5 | 0 | 5 | 2013-04-17 | 2013-04-17 | 0 | 0 | 0 | [20 empty] | 2013-05-07 |  | 2013-07-31 |  | EXP | [6 empty] | 2013-05-07 | 2013-05-07 | 2013-07-29 | Connected |  | No
National Grid | SWANSEA | 175105 | 2777 | 400 | Solar | 05_11W84 | 2013-04-08 01:00 | 2013-04-10 | 7 | 2 | 5 | 2013-04-22 | 2014-10-02 | 361 | 0 | 361 | [22 empty] | 2013-12-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MENDON | 174635 | 1756 | 9.67 | Solar | 05_321W6 | 2013-04-12 01:00 | 2013-04-15 | 5 | 0 | 5 | 2013-04-23 | 2013-04-23 | 0 | 0 | 0 | [20 empty] | 2013-05-28 |  | 2013-07-01 |  | EXP | [6 empty] | 2013-05-28 | 2013-05-28 | 2013-06-17 | Connected |  | No
National Grid | MENDON | 175073 | 1756 | 9.67 | Solar | 05_321W6 | 2013-04-12 01:00 | 2013-04-15 | 5 | 0 | 5 | [27 empty] | 2013-07-01 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SEEKONK | 174852 | 2771 | 5000 | Solar | 05_2248 | 2013-04-16 01:00 | 2013-04-17 | 7 | 0 | 7 | [10 empty] | 2013-04-26 | 2013-07-16 | 54 | 0 | 54 | [10 empty] | 2016-03-28 | 2013-04-16 01:00 | 2019-09-23 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SEEKONK | 174853 | 2771 | 990 | Solar | 05_2248 | 2013-04-16 01:00 | 2013-04-17 | 7 | 0 | 7 | [10 empty] | 2013-04-26 | 2013-07-16 | 54 | 0 | 54 | [10 empty] | 2016-03-28 | 2013-04-16 01:00 | 2020-08-19 | Yes | STD |  | 2020-04-14 | 2020-04-13 | 0 | 0 | 0 | 2020-05-15 | 2020-05-15 | 2020-08-19 | Connected |  | No
National Grid | SEEKONK | 175104 | 2771 | 3960 | Solar | 05_2248 | 2013-04-16 01:00 | 2013-04-17 | 7 | 0 | 7 | [10 empty] | 2013-04-26 | 2013-07-16 | 54 | 0 | 54 | [10 empty] | 2016-03-28 |  | 2020-08-19 | Yes | STD |  | 2020-04-14 | 2020-04-13 | 0 | 0 | 0 | 2020-05-15 | 2020-05-15 | 2020-08-19 | Connected |  | No
National Grid | MEDFORD | 175106 | 2155 | 20 | Solar | 12_9C4 | 2013-04-18 01:00 | 2013-04-22 | 6 | 0 | 6 | 2013-04-30 | 2013-04-30 | 0 | 0 | 0 | [20 empty] | 2013-06-20 | 2013-04-22 01:00 | 2013-06-21 |  | EXP | [6 empty] | 2013-10-28 | 2013-10-28 | 2013-11-12 | Connected |  | No
National Grid | FALL RIVER | 175108 | 2720 | 1500 | Solar | 05_28W51 | 2013-04-22 01:00 | 2013-04-23 | 6 | 0 | 6 | [10 empty] | 2013-05-01 | 2013-06-05 | 24 | 0 | 24 | [10 empty] | 2013-11-14 | 2013-04-22 01:00 | 2013-09-02 | Yes | STD |  | 2014-10-03 | 2014-12-08 | 43 | 0 | 43 | 2013-04-22 | 2013-04-22 | 2014-12-18 | Connected |  | No
National Grid | NEWBURY | 175109 | 1951 | 1992 | Solar | 14_60L1 | 2013-04-22 01:00 | 2013-04-23 | 7 | 0 | 7 | [10 empty] | 2013-05-02 | 2013-06-24 | 35 | 0 | 35 | [10 empty] | 2014-06-02 |  | 2016-12-31 | Yes | STD |  | 2017-01-03 | 2017-04-18 | 72 | 0 | 72 |  |  | 2017-05-04 | Connected |  | No
National Grid | LENOX | 175110 | 1240 | 1000 | Solar | 09_1103W1 | 2013-04-22 01:00 | 2013-04-23 | 8 | 2 | 6 | [10 empty] | 2013-05-03 | 2013-06-13 | 28 | 0 | 28 | [12 empty] | 2013-10-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | RUTLAND | 175139 | 1543 | 300 | Bio Gas | 01_55W1 | 2013-04-23 01:00 | 2013-04-24 | 6 | 0 | 6 | 2013-05-02 | 2013-05-02 | 0 | 0 | 0 | [20 empty] | 2013-11-27 |  | 2013-08-30 |  | EXP | [6 empty] | 2013-12-10 | 2013-12-10 | 2014-04-16 | Connected |  | No
National Grid | ADAMS | 175140 | 1220 | 1500 | Solar | 09_1021W1 | 2013-04-23 01:00 | 2013-04-24 | 6 | 0 | 6 | [10 empty] | 2013-05-02 | 2013-06-14 | 30 | 0 | 30 | [12 empty] | 2014-01-10 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MILFORD | 175145 | 1757 | 85 | Solar | 05_336W1 | 2013-04-25 01:00 | 2013-04-26 | 6 | 0 | 6 | 2013-05-06 | 2013-05-06 | 0 | 0 | 0 | [20 empty] | 2013-06-18 |  | 2013-07-01 |  | EXP | [6 empty] | 2013-09-13 | 2013-09-13 | 2013-09-20 | Connected |  | No
National Grid | HAMPDEN | 175146 | 1036 | 3500 | Solar | 09_524L1 | 2013-04-29 01:00 | 2013-04-30 | 8 | 1 | 7 | [10 empty] | 2013-05-10 | 2014-08-11 | 310 | 0 | 310 | [12 empty] | 2014-08-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BRIMFIELD | 175177 | 1010 | 2000 | Solar |  | 2013-04-29 01:00 | 2013-04-30 | 21 | 14 | 7 | [10 empty] | 2013-05-30 | 2013-07-12 | 29 | 0 | 29 | [11 empty] | 2013-04-29 01:00 | 2014-05-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 178773 | 1507 | 1980 | Solar | 01_552L1 | 2013-04-29 01:00 | 2013-04-30 | 31 | 25 | 6 | [10 empty] | 2013-06-13 | 2013-07-22 | 25 | 17 | 8 | [5 empty] | 2014-04-30 | 2014-04-30 | 0 | 0 | 0 | 2014-05-21 |  | 2016-12-31 | Yes | STD |  | 2016-06-24 | 2016-09-27 | 65 | 0 | 65 | 2016-10-26 | 2016-10-26 | 2016-10-28 | Connected |  | No
National Grid | WORCESTER | 175176 | 1607 | 18 | Solar | 01_8W2 | 2013-04-30 01:00 | 2013-05-01 | 7 | 1 | 6 | 2013-05-10 | 2013-05-10 | 0 | 0 | 0 | [20 empty] | 2013-07-12 |  | 2013-07-31 |  | EXP | [6 empty] | 2013-09-13 | 2013-09-13 | 2013-09-25 | Connected |  | No
National Grid | MARLBOROUGH | 175178 | 1752 | 1073.6 | Solar | 05_311W6 | 2013-05-03 01:00 | 2013-05-06 | 7 | 0 | 7 | [10 empty] | 2013-05-15 | 2013-07-02 | 32 | 0 | 32 | [5 empty] | 2014-04-30 | 2014-04-30 | 0 | 0 | 0 | 2014-03-03 |  | 2016-12-31 |  | STD | [6 empty] | 2015-12-18 | 2015-12-18 | 2015-12-21 | Connected |  | No
National Grid | WEST STOCKBRIDGE | 175179 | 1266 | 20 | Solar | 09_1109W3 | 2013-05-03 01:00 | 2013-05-06 | 7 | 0 | 7 | 2013-05-15 | 2013-05-15 | 0 | 0 | 0 | [20 empty] | 2013-07-01 | 2013-05-06 01:00 | 2013-05-11 |  | EXP | [6 empty] | 2013-07-22 | 2013-07-22 | 2013-07-25 | Connected |  | No
National Grid | DIGHTON | 175180 | 2715 | 3130 | Solar | 05_19W72 | 2013-05-06 01:00 | 2013-05-07 | 8 | 0 | 8 | [10 empty] | 2013-05-17 | 2013-06-24 | 24 | 0 | 24 | [10 empty] | 2014-10-21 |  | 2017-07-07 | Yes | STD |  | 2017-03-17 | 2017-06-30 | 73 | 0 | 73 | 2017-06-29 | 2017-06-29 | 2017-07-13 | Connected |  | No
National Grid | FALL RIVER | 175183 | 2720 | 60 | Natural Gas | 05_106W81 | 2013-05-06 01:00 | 2013-05-07 | 8 | 0 | 8 | 2013-05-17 | 2013-05-17 | 0 | 0 | 0 | [20 empty] | 2013-08-08 |  | 2013-09-30 |  | EXP | [6 empty] | 2013-12-12 | 2013-12-12 | 2013-12-31 | Connected |  | No
National Grid | ROWE | 175181 | 1367 | 5000 | Solar | 09_1019W1 | 2013-05-09 01:00 | 2013-05-09 | 8 | 0 | 8 | [10 empty] | 2013-05-21 | 2013-06-24 | 22 | 0 | 22 | [12 empty] | 2014-06-02 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ANDOVER | 175182 | 1810 | 490 | Solar | 14_54L3 | 2013-05-09 01:00 | 2013-05-10 | 7 | 0 | 7 | 2013-05-21 | 2015-01-29 | 419 | 4 | 415 | [20 empty] | 2013-07-03 |  | 2013-12-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | ERVING | 175185 | 1344 | 650 | Natural Gas | 09_705W1 | 2013-05-10 01:00 | 2013-05-13 | 8 | 0 | 8 | [10 empty] | 2013-05-23 | 2013-07-09 | 30 | 0 | 30 | [10 empty] | 2013-12-09 |  | 2019-06-30 |  | STD | [8 empty] | 2019-05-17 | Connected |  | No
National Grid | SPENCER | 174632 | 1562 | 1500 | Solar | 01_552L1 | 2013-05-13 01:00 | 2013-05-15 | 218 | 212 | 6 | [27 empty] | 2014-01-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HANCOCK | 174636 | 1237 | 4500 | Solar | 09_1003W2 | 2013-05-13 01:00 | 2013-05-14 | 219 | 211 | 8 | [27 empty] | 2013-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | GARDNER | 174639 | 1440 | 60 | Solar | 01_607W2 | 2013-05-23 01:00 | 2013-05-24 | 7 | 0 | 7 | 2013-06-05 | 2017-12-15 | 1121 | 0 | 1121 | [20 empty] | 2013-06-19 |  | 2020-10-14 |  | EXP | [6 empty] | 2015-03-03 | 2015-03-03 | 2020-10-14 | Connected |  | No
National Grid | FRANKLIN | 174668 | 2038 | 55.2 | Solar | 05_348W5 | 2013-06-03 01:00 | 2013-06-04 | 7 | 0 | 7 | 2013-06-13 | 2013-06-13 | 0 | 0 | 0 | [20 empty] | 2013-07-01 |  | 2013-09-02 |  | EXP | [6 empty] | 2013-08-23 | 2013-08-23 | 2013-08-30 | Connected |  | No
National Grid | STOUGHTON | 174674 | 2072 | 170 | Solar | 07_913W69 | 2013-06-03 01:00 | 2013-06-04 | 9 | 2 | 7 | 2013-06-17 | 2013-06-17 | 0 | 0 | 0 | [20 empty] | 2013-07-22 |  | 2014-05-30 |  | EXP | [6 empty] | 2013-07-30 | 2013-07-30 | 2014-06-02 | Connected |  | No
National Grid | WILLIAMSTOWN | 174675 | 1267 | 500 | Solar | 09_1003W1 | 2013-06-03 01:00 | 2013-06-04 | 7 | 0 | 7 | [26 empty] | 2013-06-03 01:00 | 2013-12-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WILLIAMSTOWN | 174785 | 1267 | 500 | Solar | 09_1003W1 | 2013-06-03 01:00 | 2013-06-04 | 7 | 0 | 7 | 2013-06-13 | 2014-05-27 | 235 | 41 | 194 | [20 empty] | 2013-11-01 | 2013-06-05 01:00 | 2013-12-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NEWBURY | 174669 | 1952 | 1980 | Solar | 14_2405 | 2013-06-05 01:00 | 2013-06-06 | 7 | 0 | 7 | [10 empty] | 2013-06-17 | 2013-07-15 | 18 | 0 | 18 | [10 empty] | 2014-06-02 |  | 2023-12-21 | Yes | STD |  | 2023-10-11 | 2023-12-06 | 57 | 0 | 57 |  |  | 2023-12-29 | Connected |  | No
National Grid | WRENTHAM | 178764 | 2093 | 499 | Solar | 05_3424W3 | 2013-06-05 01:00 | 2013-06-06 | 7 | 0 | 7 | 2013-06-17 | 2017-10-17 | 1077 | 0 | 1077 | 2014-07-08 | 2017-10-17 | 816 | 0 | 816 | [5 empty] | 2014-07-08 | 2017-10-17 | 816 | 0 | 816 | [5 empty] | 2014-07-22 |  | 2018-09-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LEEDS | 174670 | 1053 | 200 | Natural Gas | 09_909W4 | 2013-06-06 01:00 | 2013-06-07 | 23 | 22 | 1 | 2013-07-12 | 2013-07-12 | 0 | 0 | 0 | [20 empty] | 2013-07-31 |  | 2013-11-29 |  | EXP | [6 empty] | 2015-11-24 | 2015-11-24 | 2015-11-24 | Connected |  | No
National Grid | NORTON | 174672 | 2766 | 1000 | Solar | 05_4L2 | 2013-06-07 01:00 | 2013-06-10 | 6 | 0 | 6 | [10 empty] | 2013-06-19 | 2013-09-03 | 52 | 0 | 52 | [12 empty] | 2014-06-02 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTON | 174673 | 2766 | 1000 | Solar | 05_4L2 | 2013-06-07 01:00 | 2013-06-10 | 6 | 0 | 6 | [10 empty] | 2013-06-19 | 2013-09-03 | 52 | 0 | 52 | [11 empty] | 2013-06-10 01:00 | 2014-06-02 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | OXFORD | 174703 | 1540 | 492 | Solar | 01_406L2 | 2013-06-10 01:00 | 2013-06-11 | 6 | 0 | 6 | [10 empty] | 2013-06-20 | 2013-07-22 | 21 | 0 | 21 | [10 empty] | 2014-12-18 |  | 2016-07-29 |  | STD | [8 empty] | 2016-11-23 | Connected |  | No
National Grid | NORTON | 174706 | 2766 | 1500 | Solar | 05_8L2 | 2013-06-10 01:00 | 2013-06-11 | 12 | 6 | 6 | [10 empty] | 2013-06-28 | 2013-09-03 | 45 | 0 | 45 | [12 empty] | 2014-05-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SOUTH EASTON | 174704 | 2375 | 75 | Solar | 07_92W44 | 2013-06-14 01:00 | 2013-06-17 | 6 | 0 | 6 | 2013-06-26 | 2013-06-26 | 0 | 0 | 0 | [20 empty] | 2013-07-09 |  | 2013-08-16 |  | EXP | [6 empty] | 2013-12-06 | 2013-12-06 | 2013-12-12 | Connected |  | No
National Grid | GARDNER | 174707 | 1440 | 60 | Natural Gas | 01_607W1 | 2013-06-17 01:00 | 2013-06-18 | 13 | 5 | 8 | 2013-07-08 | 2013-07-23 | 11 | 0 | 11 | [20 empty] | 2013-07-23 |  | 2017-12-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SWANSEA | 174708 | 2777 | 500 | Solar | 05_11W85 | 2013-06-17 01:00 | 2013-06-18 | 46 | 38 | 8 | [27 empty] | 2013-11-29 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FALL RIVER | 174711 | 2723 | 485 | Solar | 05_115W43 | 2013-06-21 01:00 | 2013-06-24 | 6 | 0 | 6 | 2013-07-02 | 2013-07-02 | 0 | 0 | 0 | [20 empty] | 2013-07-11 |  | 2013-11-01 |  | EXP | [6 empty] | 2013-12-31 | 2013-12-31 | 2013-12-31 | Connected |  | No
National Grid | WHITINSVILLE | 174712 | 1588 | 19.35 | Solar | 05_320W3 | 2013-06-23 01:00 | 2013-06-24 | 7 | 0 | 7 | 2013-07-03 | 2013-07-03 | 0 | 0 | 0 | [20 empty] | 2013-07-12 |  | 2013-12-02 |  | EXP | [6 empty] | 2013-08-29 | 2013-08-29 | 2013-11-12 | Connected |  | No
National Grid | ADAMS | 174742 | 1220 | 75 | Solar | 09_1021W2 | 2013-06-24 01:00 | 2013-06-25 | 6 | 0 | 6 | 2013-07-03 | 2014-04-30 | 204 | 0 | 204 | [20 empty] | 2013-07-23 | 2013-07-01 01:00 | 2013-11-29 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BELLINGHAM | 174743 | 2019 | 3108 | Solar | 05_344W4 | 2013-07-01 01:00 | 2013-07-02 | 6 | 0 | 6 | [10 empty] | 2013-07-11 | 2013-08-02 | 16 | 0 | 16 | [10 empty] | 2014-03-18 | 2013-07-02 01:00 | 2016-03-15 |  | STD |  | 2015-11-02 | 2017-01-03 | 289 | 0 | 289 | 2016-12-21 | 2016-12-21 | 2016-12-23 | Connected |  | No
National Grid | FALL RIVER | 174744 | 2720 | 2000 | Solar | 05_28W40 | 2013-07-02 01:00 | 2013-07-03 | 6 | 0 | 6 | [10 empty] | 2013-07-12 | 2013-08-09 | 20 | 0 | 20 | [10 empty] | 2014-04-03 | 2013-07-08 01:00 | 2014-06-30 | Yes | STD |  | 2015-03-10 | 2015-04-02 | 16 | 0 | 16 | 2015-04-30 | 2015-04-30 | 2015-05-07 | Connected |  | No
National Grid | SOUTHBOROUGH | 174781 | 1772 | 480 | Solar | 05_310W3 | 2013-07-08 01:00 | 2013-07-09 | 8 | 0 | 8 | 2013-07-19 | 2013-07-19 | 0 | 0 | 0 | 2013-11-05 | 2014-01-23 | 52 | 0 | 52 | [5 empty] | 2013-11-05 | 2014-01-23 | 52 | 0 | 52 | [5 empty] | 2014-02-11 |  | 2017-12-20 | Yes | EXP |  | 2017-09-22 | 2017-10-16 | 15 | 0 | 15 | 2017-09-18 | 2017-09-18 | 2017-12-01 | Connected |  | No
National Grid | CHELMSFORD | 174746 | 1824 | 225 | Solar | 14_73L1 | 2013-07-09 01:00 | 2013-07-10 | 19 | 11 | 8 | 2013-08-06 | 2015-11-18 | 567 | 3 | 564 | [20 empty] | 2013-08-19 |  | 2014-09-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHELMSFORD | 174747 | 1824 | 225 | Solar | 14_24L2 | 2013-07-09 01:00 | 2013-07-10 | 19 | 11 | 8 | 2013-08-06 | 2015-03-30 | 407 | 1 | 406 | [20 empty] | 2013-08-19 |  | 2014-08-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHELMSFORD | 174748 | 1824 | 75 | Solar | 14_16L1 | 2013-07-09 01:00 | 2013-07-10 | 19 | 11 | 8 | 2013-08-06 | 2015-11-18 | 567 | 3 | 564 | [20 empty] | 2013-08-16 |  | 2014-09-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHELMSFORD | 174749 | 1824 | 295 | Solar | 14_73L1 | 2013-07-09 01:00 | 2013-07-10 | 18 | 10 | 8 | 2013-08-05 | 2015-11-18 | 568 | 16 | 552 | [20 empty] | 2013-09-03 | 2013-07-09 01:00 | 2014-09-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHELMSFORD | 174750 | 1824 | 225 | Solar | 14_73L1 | 2013-07-09 01:00 | 2013-07-10 | 18 | 10 | 8 | 2013-08-05 | 2015-11-18 | 568 | 2 | 566 | [20 empty] | 2013-09-04 |  | 2014-09-30 |  | EXP |  | 2014-07-23 | 2015-11-18 | 329 | 0 | 329 |  |  |  | Withdrawn |  | No
National Grid | CHELMSFORD | 174751 | 1824 | 150 | Solar | 14_24L3 | 2013-07-09 01:00 | 2013-07-10 | 18 | 10 | 8 | 2013-08-05 | 2015-11-18 | 568 | 39 | 529 | [20 empty] | 2013-10-31 |  | 2014-09-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | CHELMSFORD | 174780 | 1824 | 100 | Solar | 14_16L4 | 2013-07-09 01:00 | 2013-07-10 | 19 | 11 | 8 | 2013-08-06 | 2015-12-11 | 583 | 7 | 576 | [20 empty] | 2013-08-27 |  | 2016-12-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BEVERLY | 174782 | 1915 | 7.31 | Solar | 12_12L2 | 2013-07-11 01:00 | 2013-07-12 | 7 | 0 | 7 | 2013-07-23 | 2013-07-23 | 0 | 0 | 0 | [20 empty] | 2013-07-26 | 2013-07-17 01:00 | 2013-10-31 |  | EXP | [6 empty] | 2013-11-04 | 2013-11-04 | 2013-11-04 | Connected |  | No
National Grid | BROCKTON | 174784 | 2301 | 180 | Solar | 07_91W48 | 2013-07-17 01:00 | 2013-07-18 | 5 | 0 | 5 | 2013-07-25 | 2013-07-25 | 0 | 0 | 0 | [20 empty] | 2013-08-09 |  | 2014-07-30 | Yes | EXP |  | 2014-04-23 | 2014-06-26 | 44 | 0 | 44 | 2014-07-17 | 2014-07-17 | 2014-07-23 | Connected |  | No
National Grid | NORTH BROOKFIELD | 174818 | 1535 | 749 | Solar | 09_604W2 | 2013-07-29 01:00 | 2013-07-30 | 8 | 0 | 8 | [10 empty] | 2013-08-09 | 2013-11-18 | 68 | 0 | 68 | [12 empty] | 2013-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LEOMINSTER | 178765 | 1453 | 495 | Solar | 01_219W5 | 2013-07-29 01:00 | 2013-07-29 | 8 | 0 | 8 | [10 empty] | 2013-08-08 | 2014-03-03 | 139 | 0 | 139 | [10 empty] | 2014-03-13 |  | 2014-01-31 |  | STD | [6 empty] | 2014-07-14 | 2014-07-14 | 2014-07-24 | Connected |  | No
National Grid | CHARLTON | 174814 | 1507 | 60 | Solar | 01_413L4 | 2013-07-30 01:00 | 2013-07-31 | 6 | 0 | 6 | 2013-08-08 | 2013-08-08 | 0 | 0 | 0 | [20 empty] | 2013-09-12 |  | 2014-01-31 |  | EXP | [6 empty] | 2013-12-11 | 2013-12-11 | 2013-12-11 | Connected |  | No
National Grid | BOLTON | 174815 | 1740 | 995 | Solar | 01_216W6 | 2013-07-31 01:00 | 2013-08-01 | 7 | 0 | 7 | 2013-08-12 | 2013-08-12 | 0 | 0 | 0 | 2014-01-14 | 2014-03-05 | 34 | 0 | 34 | [5 empty] | 2014-01-14 | 2014-03-05 | 34 | 0 | 34 | [5 empty] | 2014-03-14 | 2013-07-31 01:00 | 2013-12-31 |  | EXP | [6 empty] | 2014-12-24 | 2014-12-24 | 2014-12-30 | Connected |  | No
National Grid | HAVERHILL | 174816 | 1832 | 3000 | Solar | 14_48L1 | 2013-07-31 01:00 | 2013-08-01 | 8 | 0 | 8 | [10 empty] | 2013-08-13 | 2013-09-24 | 29 | 0 | 29 | [10 empty] | 2014-06-16 | 2013-08-02 01:00 | 2017-09-15 |  | STD | [6 empty] | 2017-09-15 | 2017-09-15 | 2017-09-27 | Connected |  | No
National Grid | EAST BRIDGEWATER | 174821 | 2333 | 180 | Solar | 07_797W29 | 2013-08-02 01:00 | 2013-08-05 | 7 | 0 | 7 | 2013-08-14 | 2013-08-14 | 0 | 0 | 0 | [20 empty] | 2013-08-26 |  | 2014-11-01 |  | EXP | [6 empty] | 2015-02-13 | 2015-02-13 | 2015-02-13 | Connected |  | Yes
National Grid | SALISBURY | 174822 | 1952 | 30 | Solar | 14_7L4 | 2013-08-02 01:00 | 2013-08-05 | 7 | 1 | 6 | 2013-08-14 | 2014-04-02 | 156 | 3 | 153 | [20 empty] | 2013-09-06 | 2013-08-05 01:00 | 2013-11-29 |  | EXP | [6 empty] | 2013-12-06 | 2013-12-06 |  | Withdrawn |  | No
National Grid | ASHLEY FALLS | 174850 | 1222 | 999 | Solar | 09_1108W2 | 2013-08-05 01:00 | 2013-08-05 | 8 | 0 | 8 | [10 empty] | 2013-08-15 | 2013-10-04 | 35 | 0 | 35 | [10 empty] | 2014-04-23 |  | 2014-06-30 | Yes | STD |  | 2015-03-10 | 2015-04-02 | 16 | 0 | 16 | 2015-05-01 | 2015-05-01 | 2015-04-28 | Connected |  | No
National Grid | CHELMSFORD | 174786 | 1824 | 300 | Solar | 14_16L4 | 2013-08-06 01:00 | 2013-08-06 | 1 | 0 | 1 | 2013-08-07 | 2015-11-18 | 566 | 5 | 561 | [20 empty] | 2013-08-27 | 2013-08-06 01:00 | 2014-09-14 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GREAT BARRINGTON | 174851 | 1230 | 499 | Solar | 09_1109W2 | 2013-08-06 01:00 | 2013-08-08 | 8 | 2 | 6 | [10 empty] | 2013-08-20 | 2014-09-29 | 275 | 0 | 275 | [10 empty] | 2015-02-06 |  | 2016-02-05 | Yes | STD |  | 2016-09-02 | 2016-12-05 | 62 | 0 | 62 | 2016-11-07 | 2016-11-07 | 2016-11-14 | Connected |  | No
National Grid | HALIFAX | 174858 | 2338 | 10 | Solar | 07_797W24 | 2013-08-08 01:00 | 2013-08-09 | 6 | 0 | 6 | 2013-08-19 | 2013-08-19 | 0 | 0 | 0 | [20 empty] | 2013-08-30 |  | 2016-12-31 |  | EXP | [6 empty] | 2015-03-16 | 2015-03-16 | 2017-02-09 | Connected |  | Yes
National Grid | ANDOVER | 174889 | 1810 | 20 | Solar | 14_59L1 | 2013-08-13 01:00 | 2013-08-14 | 7 | 0 | 7 | 2013-08-23 | 2013-08-23 | 0 | 0 | 0 | [20 empty] | 2013-09-16 |  | 2013-09-25 |  | EXP | [6 empty] | 2013-12-09 | 2013-12-09 | 2014-02-10 | Connected |  | No
National Grid | BILLERICA | 174891 | 1821 | 990 | Solar | 14_92L4 | 2013-08-14 01:00 | 2013-08-15 | 6 | 0 | 6 | [5 empty] | 2013-10-22 | 2013-11-22 | 22 | 0 | 22 | 2013-08-23 | 2013-10-01 | 26 | 0 | 26 | 2013-10-22 | 2013-11-22 | 22 | 0 | 22 | [5 empty] | 2013-12-02 | 2013-08-20 01:00 | 2013-12-31 |  | STD | [6 empty] | 2013-12-28 | 2013-12-28 | 2013-12-31 | Connected |  | No
National Grid | ASHLEY FALLS | 174893 | 1222 | 280 | Bio Gas | 09_1108W2 | 2013-08-20 01:00 | 2013-08-21 | 5 | 0 | 5 | [10 empty] | 2013-08-28 | 2013-09-24 | 18 | 0 | 18 | [10 empty] | 2015-04-22 |  | 2018-09-10 | Yes | STD |  | 2017-09-25 | 2018-03-30 | 111 | 0 | 111 |  |  | 2018-09-05 | Connected |  | Yes
National Grid | NORTHBOROUGH | 174894 | 1532 | 666 | Solar | 05_318W3 | 2013-08-20 01:00 | 2013-08-21 | 52 | 43 | 9 | [10 empty] | 2013-11-05 | 2014-09-16 | 213 | 0 | 213 | [12 empty] | 2014-09-30 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | WEST STOCKBRIDGE | 174895 | 1266 | 3000 | Solar | 09_1109W3 | 2013-08-20 01:00 | 2013-08-21 | 6 | 0 | 6 | [10 empty] | 2013-08-29 | 2013-10-01 | 22 | 0 | 22 | [12 empty] | 2014-03-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | STOCKBRIDGE | 174926 | 1262 | 1000 | Solar | 09_1102W1 | 2013-08-21 01:00 | 2013-08-22 | 6 | 0 | 6 | [10 empty] | 2013-08-30 | 2014-02-03 | 104 | 94 | 10 | [12 empty] | 2014-10-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | STOCKBRIDGE | 174927 | 1262 | 3000 | Solar | 09_1102W1 | 2013-08-21 01:00 | 2013-08-22 | 6 | 0 | 6 | [10 empty] | 2013-08-30 | 2014-02-03 | 104 | 94 | 10 | [12 empty] | 2014-10-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WEST STOCKBRIDGE | 174928 | 1266 | 400 | Solar | 09_1102W1 | 2013-08-21 01:00 | 2013-08-22 | 6 | 0 | 6 | 2013-08-30 | 2014-05-29 | 183 | 94 | 89 | [21 empty] | 2013-08-22 01:00 | 2014-10-31 |  | EXP |  | 2017-06-20 | 2017-10-02 | 72 | 0 | 72 |  |  |  | Withdrawn |  | No
National Grid | AVON | 174929 | 2322 | 990 | Solar | 07_75W5 | 2013-08-22 01:00 | 2013-08-23 | 6 | 0 | 6 | 2013-09-03 | 2013-09-03 | 0 | 0 | 0 | [20 empty] | 2014-01-28 |  | 2014-01-31 | Yes | EXP |  | 2014-11-05 | 2014-12-18 | 29 | 0 | 29 | 2014-12-16 | 2014-12-16 | 2014-12-30 | Connected |  | No
National Grid | SWANSEA | 174930 | 2777 | 50 | Solar | 05_11W81 | 2013-08-26 01:00 | 2013-08-28 | 11 | 4 | 7 | 2013-09-13 | 2013-09-13 | 0 | 0 | 0 | [20 empty] | 2013-09-26 |  | 2013-12-31 |  | EXP | [6 empty] | 2013-12-06 | 2013-12-06 | 2013-12-12 | Connected |  | No
National Grid | PEMBROKE | 174931 | 2359 | 180 | Solar | 07_910W52 | 2013-08-26 01:00 | 2013-08-28 | 8 | 1 | 7 | 2013-09-10 | 2016-08-12 | 725 | 398 | 327 | [20 empty] | 2015-07-21 | 2013-08-29 01:00 | 2016-02-18 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SAUGUS | 174932 | 1906 | 278.4 | Solar | 12_25W2 | 2013-08-29 01:00 | 2013-08-30 | 7 | 0 | 7 | 2013-09-11 | 2013-09-11 | 0 | 0 | 0 | [20 empty] | 2013-10-18 | 2013-08-29 01:00 | 2014-10-31 |  | EXP |  | 2014-12-19 | 2015-02-12 | 36 | 0 | 36 | 2015-04-01 | 2015-04-01 | 2015-04-06 | Connected |  | No
National Grid | MARLBOROUGH | 174933 | 1752 | 371.2 | Solar | 05_318W1 | 2013-08-29 01:00 | 2013-08-30 | 7 | 0 | 7 | 2013-09-11 | 2013-09-11 | 0 | 0 | 0 | [20 empty] | 2014-01-13 |  | 2014-10-30 |  | EXP |  | 2015-04-02 | 2015-04-10 | 6 | 0 | 6 | 2015-05-22 | 2015-05-22 | 2015-05-22 | Connected |  | No
National Grid | WORCESTER | 174963 | 1610 | 60 | Solar | 01_4J336 | 2013-08-30 01:00 | 2013-09-03 | 7 | 0 | 7 | 2013-09-12 | 2013-09-12 | 0 | 0 | 0 | [20 empty] | 2013-11-04 |  | 2013-11-29 |  | EXP | [6 empty] | 2014-02-28 | 2014-02-28 | 2014-02-28 | Connected |  | No
National Grid | WORCESTER | 174964 | 1606 | 81 | Solar | 01_24W4 | 2013-08-30 01:00 | 2013-09-03 | 7 | 0 | 7 | 2013-09-12 | 2013-09-12 | 0 | 0 | 0 | [20 empty] | 2013-09-24 |  | 2013-11-29 |  | EXP | [6 empty] | 2013-12-11 | 2013-12-11 | 2013-12-11 | Connected |  | No
National Grid | WORCESTER | 174965 | 1610 | 130 | Solar | 01_4J324 | 2013-08-30 01:00 | 2013-09-03 | 7 | 0 | 7 | 2013-09-12 | 2013-09-12 | 0 | 0 | 0 | [20 empty] | 2013-09-27 |  | 2013-11-29 |  | EXP | [6 empty] | 2014-02-20 | 2014-02-20 | 2014-02-20 | Connected |  | No
National Grid | WORCESTER | 174966 | 1610 | 154 | Solar | 01_6J319 | 2013-09-03 01:00 | 2013-09-04 | 9 | 0 | 9 | 2013-09-17 | 2015-02-20 | 353 | 3 | 350 | [20 empty] | 2013-10-02 |  | 2014-08-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | AYER | 174968 | 1432 | 27 | Solar | 01_201W3 | 2013-09-06 01:00 | 2013-09-09 | 7 | 0 | 7 | 2013-09-18 | 2013-09-18 | 0 | 0 | 0 | [20 empty] | 2013-10-22 |  | 2013-11-29 |  | EXP | [6 empty] | 2013-11-27 | 2013-11-27 | 2013-12-27 | Connected |  | No
National Grid | HAMILTON | 174970 | 1982 | 85 | Solar | 12_51L3 | 2013-09-10 01:00 | 2013-09-11 | 7 | 0 | 7 | 2013-09-20 | 2013-09-20 | 0 | 0 | 0 | [20 empty] | 2013-12-12 | 2013-09-10 01:00 | 2013-12-31 |  | EXP | [6 empty] | 2014-03-07 | 2014-03-07 | 2014-04-04 | Connected |  | No
National Grid | HOUSATONIC | 174971 | 1236 | 2500 | Solar | 09_1109W1 | 2013-09-10 01:00 | 2013-09-11 | 87 | 80 | 7 | [10 empty] | 2014-01-17 | 2014-02-07 | 14 | 0 | 14 | [10 empty] | 2014-06-27 |  | 2016-12-31 | Yes | STD |  | 2016-04-12 | 2016-04-11 | 0 | 0 | 0 | 2016-05-06 | 2016-05-06 | 2016-05-06 | Connected |  | No
National Grid | FALL RIVER | 175001 | 2720 | 60 | Solar | 05_106W46 | 2013-09-11 01:00 | 2013-09-12 | 10 | 3 | 7 | 2013-09-26 | 2013-09-26 | 0 | 0 | 0 | [20 empty] | 2016-09-01 |  | 2016-09-26 |  | EXP | [6 empty] | 2016-09-15 | 2016-09-15 | 2016-09-26 | Connected |  | No
National Grid | SALISBURY | 175002 | 1952 | 150 | Solar | 14_7L4 | 2013-09-12 01:00 | 2013-09-13 | 6 | 0 | 6 | 2013-09-23 | 2013-09-23 | 0 | 0 | 0 | [20 empty] | 2013-10-24 |  | 2013-11-29 |  | EXP | [6 empty] | 2014-02-28 | 2014-02-28 | 2014-03-07 | Connected |  | No
National Grid | HANOVER | 175036 | 2339 | 85 | Solar | 07_95W1 | 2013-09-13 01:00 | 2013-09-16 | 8 | 0 | 8 | 2013-09-26 | 2013-09-26 | 0 | 0 | 0 | [20 empty] | 2013-11-12 |  | 2014-10-31 |  | EXP | [6 empty] | 2014-12-01 | 2014-12-01 | 2014-12-19 | Connected |  | No
National Grid | HARDWICK | 175003 | 1037 | 4000 | Solar | 09_604W3 | 2013-09-16 01:00 | 2013-09-17 | 7 | 0 | 7 | [10 empty] | 2013-09-26 | 2013-10-25 | 20 | 0 | 20 | [10 empty] | 2014-10-16 | 2013-09-18 01:00 | 2014-08-29 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | GRAFTON | 175007 | 1519 | 2700 | Solar | 01_304W1 | 2013-09-18 01:00 | 2013-09-19 | 9 | 1 | 8 | [10 empty] | 2013-10-02 | 2013-10-23 | 14 | 1 | 13 | [10 empty] | 2014-05-05 |  | 2016-05-14 | Yes | STD |  | 2016-03-18 | 2016-12-20 | 189 | 0 | 189 |  |  | 2016-10-28 | Connected |  | No
National Grid | MALDEN | 175037 | 2148 | 300 | Solar | 12_16J6 | 2013-09-20 01:00 | 2013-09-23 | 12 | 5 | 7 | 2013-10-09 | 2013-10-09 | 0 | 0 | 0 | [20 empty] | 2013-10-28 |  | 2013-12-31 |  | EXP | [6 empty] | 2013-12-23 | 2013-12-23 | 2013-12-27 | Connected |  | No
National Grid | MARLBOROUGH | 175038 | 1752 | 100 | Solar | 05_317W2 | 2013-09-22 01:00 | 2013-09-23 | 7 | 0 | 7 | 2013-10-02 | 2013-10-02 | 0 | 0 | 0 | [20 empty] | 2013-11-01 |  | 2013-12-31 |  | EXP | [6 empty] | 2013-11-08 | 2013-11-08 | 2014-01-08 | Connected |  | No
National Grid | WORCESTER | 175045 | 1603 | 246.5 | Solar | 01_6W2 | 2013-09-23 01:00 | 2013-09-24 | 6 | 0 | 6 | 2013-10-02 | 2015-02-10 | 335 | 0 | 335 | [20 empty] | 2014-03-24 |  | 2015-09-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 175074 | 1604 | 100 | Solar | 01_27W1 | 2013-09-23 01:00 | 2013-09-24 | 6 | 0 | 6 | 2013-10-02 | 2013-10-02 | 0 | 0 | 0 | [20 empty] | 2013-11-12 |  | 2016-12-05 |  | EXP | [6 empty] | 2016-10-20 | 2016-10-20 | 2016-12-06 | Connected |  | No
National Grid | WORCESTER | 175075 | 1604 | 75 | Solar | 01_27W1 | 2013-09-23 01:00 | 2013-09-24 | 6 | 0 | 6 | 2013-10-02 | 2013-10-02 | 0 | 0 | 0 | [20 empty] | 2013-10-15 |  | 2016-11-10 |  | EXP | [6 empty] | 2016-10-20 | 2016-10-20 | 2016-12-15 | Connected |  | No
National Grid | WORCESTER | 175076 | 1602 | 100 | Solar | 01_1J363 | 2013-09-23 01:00 | 2013-09-24 | 6 | 0 | 6 | 2013-10-02 | 2013-10-02 | 0 | 0 | 0 | [20 empty] | 2013-10-25 | 2013-09-24 01:00 | 2016-02-01 |  | EXP | [6 empty] | 2016-02-29 | 2016-02-29 | 2016-04-05 | Connected |  | No
National Grid | WORCESTER | 175077 | 1609 | 35 | Solar | 01_11J331 | 2013-09-24 01:00 | 2013-09-26 | 4 | 0 | 4 | 2013-10-02 | 2017-01-23 | 818 | 0 | 818 | [20 empty] | 2013-11-13 |  | 2016-07-31 | Yes | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 175078 | 1605 | 200 | Solar | 01_HT39 | 2013-09-24 01:00 | 2013-09-26 | 4 | 0 | 4 | 2013-10-02 | 2013-10-02 | 0 | 0 | 0 | [20 empty] | 2013-10-21 |  | 2016-12-05 |  | EXP | [6 empty] | 2016-10-20 | 2016-10-20 | 2016-12-05 | Connected |  | No
National Grid | LAWRENCE | 175079 | 1841 | 300 | Solar | 14_8L2 | 2013-09-30 01:00 | 2013-10-01 | 7 | 0 | 7 | 2013-10-10 | 2013-10-10 | 0 | 0 | 0 | [20 empty] | 2013-12-20 | 2013-10-01 01:00 | 2013-12-31 |  | EXP | [6 empty] | 2014-03-17 | 2014-03-17 | 2014-05-27 | Connected |  | No
National Grid | OXFORD | 175080 | 1540 | 1000 | Natural Gas | 01_412L3 | 2013-10-01 01:00 | 2013-10-02 | 6 | 0 | 6 | [10 empty] | 2013-10-10 | 2013-12-11 | 41 | 0 | 41 | [10 empty] | 2015-03-08 |  | 2016-12-31 | Yes | STD |  | 2016-06-17 | 2016-09-01 | 52 | 0 | 52 | 2013-10-02 | 2013-10-02 | 2016-06-14 | Connected |  | No
National Grid | EVERETT | 175081 | 2149 | 30 | Solar | 12_37W6 | 2013-10-01 01:00 | 2013-10-02 | 6 | 0 | 6 | 2013-10-10 | 2013-10-10 | 0 | 0 | 0 | [20 empty] | 2013-10-22 |  | 2013-12-31 |  | EXP | [6 empty] | 2013-12-23 | 2013-12-23 | 2013-12-27 | Connected |  | No
National Grid | ATTLEBORO | 175082 | 2703 | 75 | Solar | 05_2248 | 2013-10-08 01:00 | 2013-10-09 | 3 | 0 | 3 | 2013-10-15 | 2013-10-15 | 0 | 0 | 0 | [20 empty] | 2013-11-18 |  | 2013-12-31 |  | EXP | [6 empty] | 2014-01-08 | 2014-01-08 | 2014-03-20 | Connected |  | No
National Grid | LYNN | 175112 | 1901 | 100 | Solar | 12_1393 | 2013-10-09 01:00 | 2013-10-10 | 8 | 2 | 6 | 2013-10-23 | 2013-10-23 | 0 | 0 | 0 | [20 empty] | 2013-11-20 | 2013-10-10 01:00 | 2014-09-01 |  | EXP | [6 empty] | 2014-02-28 | 2014-02-28 | 2014-07-25 | Connected |  | No
National Grid | WILBRAHAM | 175114 | 1095 | 750 | Solar | 09_523L1 | 2013-10-10 01:00 | 2013-10-11 | 6 | 0 | 6 | [5 empty] | 2014-01-11 | 2014-04-21 | 67 | 0 | 67 | 2013-10-22 | 2013-12-05 | 30 | 0 | 30 | 2014-01-11 | 2014-04-21 | 67 | 0 | 67 | [5 empty] | 2014-05-15 |  | 2016-06-01 |  | STD |  | 2016-04-22 | 2016-08-19 | 82 | 0 | 82 | 2016-08-22 | 2016-08-22 | 2016-08-22 | Connected |  | No
National Grid | BEVERLY | 175113 | 1915 | 19.99 | Solar | 12_51L3 | 2013-10-15 01:00 | 2013-10-16 | 7 | 0 | 7 | 2013-10-25 | 2013-10-25 | 0 | 0 | 0 | [20 empty] | 2013-12-03 |  | 2013-12-31 |  | EXP | [6 empty] | 2014-02-12 | 2014-02-12 | 2014-02-24 | Connected |  | No
National Grid | SEEKONK | 175115 | 2771 | 100 | Solar | 05_7L3 | 2013-10-16 01:00 | 2013-10-17 | 6 | 0 | 6 | 2013-10-25 | 2013-10-25 | 0 | 0 | 0 | [20 empty] | 2013-11-08 |  | 2013-12-02 |  | EXP | [6 empty] | 2013-11-14 | 2013-11-14 | 2013-12-31 | Connected |  | Yes
National Grid | SWANSEA | 175116 | 2777 | 25 | Solar | 05_11W81 | 2013-10-16 01:00 | 2013-10-17 | 6 | 0 | 6 | 2013-10-25 | 2013-10-25 | 0 | 0 | 0 | [20 empty] | 2013-11-06 |  | 2014-09-01 |  | EXP | [6 empty] | 2014-05-27 | 2014-05-27 | 2014-07-03 | Connected |  | No
National Grid | NORTH EASTON | 175117 | 2356 | 84 | Solar | 07_92W44 | 2013-10-18 01:00 | 2013-10-21 | 5 | 0 | 5 | 2013-10-28 | 2013-10-28 | 0 | 0 | 0 | [20 empty] | 2013-11-04 |  | 2013-12-31 |  | EXP | [6 empty] | 2014-02-11 | 2014-02-11 | 2014-02-25 | Connected |  | No
National Grid | NORTH EASTON | 175118 | 2356 | 50 | Solar | 07_98W46 | 2013-10-18 01:00 | 2013-10-21 | 5 | 0 | 5 | 2013-10-28 | 2013-10-28 | 0 | 0 | 0 | [20 empty] | 2013-11-19 | 2013-10-18 01:00 | 2013-12-31 |  | EXP | [6 empty] | 2014-01-27 | 2014-01-27 | 2014-02-06 | Connected |  | No
National Grid | BILLERICA | 175120 | 1862 | 2850 | Solar | 14_2385 | 2013-10-18 01:00 | 2013-10-21 | 4 | 0 | 4 | [10 empty] | 2013-10-25 | 2013-12-11 | 31 | 0 | 31 | [10 empty] | 2015-01-06 |  | 2016-12-31 | Yes | STD |  | 2016-06-23 | 2017-04-07 | 197 | 0 | 197 | 2016-12-21 | 2016-12-21 | 2016-12-28 | Connected |  | No
National Grid | WORCESTER | 175149 | 1610 | 50 | Solar | 01_4J324 | 2013-10-21 01:00 | 2013-10-22 | 8 | 0 | 8 | 2013-11-01 | 2014-01-06 | 41 | 0 | 41 | [20 empty] | 2014-01-17 |  | 2017-01-06 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BEVERLY | 175147 | 1915 | 34.2 | Solar | 12_12J7 | 2013-10-24 01:00 | 2013-10-25 | 8 | 1 | 7 | 2013-11-06 | 2013-11-06 | 0 | 0 | 0 | [20 empty] | 2013-11-08 |  | 2013-12-31 |  | EXP | [6 empty] | 2014-02-28 | 2014-02-28 | 2014-03-24 | Connected |  | No
National Grid | SOUTH ATTLEBORO | 175148 | 2703 | 50 | Solar | 05_9L5 | 2013-10-25 01:00 | 2013-10-25 | 6 | 0 | 6 | 2013-11-04 | 2013-11-04 | 0 | 0 | 0 | [20 empty] | 2013-11-13 | 2013-10-30 01:00 | 2013-12-31 |  | EXP | [6 empty] | 2014-01-24 | 2014-01-24 | 2014-01-24 | Connected |  | No
National Grid | BEVERLY | 175151 | 1915 | 224 | Solar | 12_51L1 | 2013-10-30 01:00 | 2013-10-31 | 5 | 0 | 5 | 2013-11-07 | 2013-11-07 | 0 | 0 | 0 | [20 empty] | 2013-12-11 |  | 2014-05-30 |  | EXP |  | 2014-08-04 | 2014-08-04 | 0 | 0 | 0 | 2014-08-06 | 2014-08-06 | 2014-08-07 | Connected |  | No
National Grid | GARDNER | 175152 | 1440 | 750 | Solar | 01_607W3 | 2013-11-01 01:00 | 2013-11-04 | 11 | 11 | 0 | [5 empty] | 2014-01-02 |  | 1053 | 203 | 850 | 2013-11-20 | 2014-01-02 | 28 | 28 | 0 | 2014-01-02 |  | 1053 | 203 | 850 | [5 empty] | 2015-09-11 |  |  |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | NORTHAMPTON | 175153 | 1060 | 40 | Solar | 09_901W3 | 2013-11-05 | 2013-11-06 | 5 | 0 | 5 | 2013-11-14 | 2013-11-14 | 0 | 0 | 0 | [20 empty] | 2013-12-02 |  | 2013-12-31 |  | EXP | [6 empty] | 2013-12-09 | 2013-12-09 | 2014-02-28 | Connected |  | No
National Grid | RUTLAND | 175154 | 1543 | 50 | Solar | 01_55W1 | 2013-11-05 | 2013-11-05 | 5 | 0 | 5 | 2013-11-13 | 2016-08-12 | 681 | 0 | 681 | [20 empty] | 2014-02-25 |  | 2016-12-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LENOX | 175155 | 1240 | 16.34 | Solar | 09_1103W1 | 2013-11-11 | 2013-11-12 | 13 | 6 | 7 | 2013-12-02 | 2014-07-01 | 143 | 0 | 143 | [20 empty] | 2013-12-03 |  | 2013-12-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MEDFORD | 175156 | 2155 | 82.8 | Solar | 12_2344 | 2013-11-12 | 2013-11-13 | 6 | 0 | 6 | 2013-11-21 | 2013-11-21 | 0 | 0 | 0 | [20 empty] | 2013-12-03 |  | 2013-12-31 |  | EXP | [6 empty] | 2014-04-24 | 2014-04-24 | 2014-04-24 | Connected |  | No
National Grid | BEVERLY | 175187 | 1915 | 60 | Natural Gas | 12_51L3 | 2013-11-14 | 2013-11-15 | 6 | 0 | 6 | 2013-11-25 | 2013-11-25 | 0 | 0 | 0 | [20 empty] | 2013-12-10 |  | 2014-02-17 |  | EXP | [6 empty] | 2014-05-01 | 2014-05-01 | 2014-05-27 | Connected |  | No
National Grid | CHELMSFORD | 175186 | 1824 | 335 | Solar | 14_24L1 | 2013-11-18 | 2013-11-19 | 1 | 0 | 1 | 2013-11-20 | 2015-11-18 | 494 | 0 | 494 | [20 empty] | 2013-11-26 |  | 2014-04-30 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SALEM | 175188 | 1970 | 18 | Solar | 12_49W2 | 2013-11-19 | 2013-11-20 | 4 | 0 | 4 | 2013-11-26 | 2013-11-26 | 0 | 0 | 0 | [20 empty] | 2013-12-12 |  | 2014-01-31 |  | EXP | [6 empty] | 2013-12-17 | 2013-12-17 | 2014-08-01 | Connected |  | No
National Grid | ABINGTON | 175189 | 2351 | 60 | Solar | 07_911W77 | 2013-11-19 | 2013-11-20 | 4 | 0 | 4 | 2013-11-26 | 2013-11-26 | 0 | 0 | 0 | [20 empty] | 2014-03-05 |  | 2014-01-31 |  | EXP | [6 empty] | 2014-09-24 | 2014-09-24 | 2014-12-11 | Connected |  | No
National Grid | ABINGTON | 175190 | 2351 | 60 | Solar | 07_911W77 | 2013-11-19 | 2013-11-20 | 4 | 0 | 4 | 2013-11-26 | 2013-11-26 | 0 | 0 | 0 | [20 empty] | 2014-03-05 |  | 2014-01-31 |  | EXP | [6 empty] | 2014-09-24 | 2014-09-24 | 2014-12-11 | Connected |  | No
National Grid | WORCESTER | 175192 | 1605 | 150 | Natural Gas | 01_HT61 | 2013-11-21 | 2013-11-25 | 6 | 0 | 6 | 2013-12-04 | 2013-12-04 | 0 | 0 | 0 | [20 empty] | 2013-12-30 |  | 2014-03-31 |  | EXP | [6 empty] | 2014-06-02 | 2014-06-02 | 2014-06-02 | Connected |  | Yes
National Grid | LAWRENCE | 175191 | 1843 | 45 | Solar | 14_8L3 | 2013-11-22 | 2013-11-25 | 6 | 0 | 6 | 2013-12-04 | 2013-12-04 | 0 | 0 | 0 | [20 empty] | 2013-12-12 | 2013-12-03 | 2014-01-31 |  | EXP | [6 empty] | 2014-03-26 | 2014-03-26 | 2014-04-25 | Connected |  | No
National Grid | TYNGSBORO | 174640 | 1879 | 1720 | Solar | 01_210L1 | 2013-12-03 | 2013-12-04 | 5 | 0 | 5 | [10 empty] | 2013-12-11 | 2014-01-03 | 15 | 0 | 15 | [10 empty] | 2015-09-11 | 2013-12-03 | 2016-12-31 | Yes | STD |  | 2016-11-30 | 2017-01-09 | 26 | 0 | 26 | 2016-12-29 | 2016-12-29 | 2016-12-29 | Connected |  | No
National Grid | BRIDGEWATER | 175193 | 2324 | 1000 | Solar | 07_912W55 | 2013-12-03 | 2013-12-04 | 5 | 0 | 5 | [5 empty] | 2014-01-14 | 2015-09-09 | 410 | 59 | 351 | 2013-12-11 | 2013-12-23 | 8 | 0 | 8 | 2014-01-14 | 2015-09-09 | 410 | 59 | 351 | [5 empty] | 2014-08-25 | 2013-12-03 | 2014-09-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BRIDGEWATER | 175194 | 2324 | 800 | Solar | 07_912W55 | 2013-12-03 | 2013-12-04 | 5 | 0 | 5 | [10 empty] | 2013-12-11 | 2013-12-23 | 8 | 0 | 8 | [10 empty] | 2014-08-25 | 2013-12-04 | 2020-04-30 | Yes | STD |  | 2019-11-16 | 2020-03-12 | 116 | 0 | 116 | 2020-03-25 | 2020-03-25 | 2020-04-09 | Connected |  | No
National Grid | WORCESTER | 174641 | 1605 | 82.8 | Solar | 01_27W4 | 2013-12-04 | 2013-12-04 | 5 | 0 | 5 | 2013-12-11 | 2017-09-25 | 941 | 6 | 935 | [20 empty] | 2013-12-27 |  | 2016-12-31 | Yes | EXP | [9 empty] | Withdrawn |  | No
National Grid | RUTLAND | 174642 | 1543 | 21 | Solar | 01_55W1 | 2013-12-06 | 2013-12-09 | 8 | 0 | 8 | 2013-12-19 | 2013-12-19 | 0 | 0 | 0 | [20 empty] | 2013-12-19 |  | 2014-01-31 |  | EXP | [6 empty] | 2014-01-21 | 2014-01-21 | 2015-01-30 | Connected |  | No
National Grid | AYER | 174643 | 1432 | 90 | Solar | 01_201W2 | 2013-12-11 | 2013-12-12 | 4 | 0 | 4 | 2013-12-18 | 2013-12-18 | 0 | 0 | 0 | [20 empty] | 2014-01-07 |  | 2014-01-31 |  | EXP | [6 empty] | 2014-01-08 | 2014-01-08 | 2014-04-07 | Connected |  | Yes
National Grid | ANDOVER | 174644 | 1810 | 18 | Solar | 14_3J40 | 2013-12-17 | 2013-12-19 | 5 | 0 | 5 | 2013-12-27 | 2013-12-27 | 0 | 0 | 0 | [20 empty] | 2014-01-02 | 2013-12-17 | 2014-02-28 |  | EXP | [6 empty] | 2014-01-13 | 2014-01-13 | 2014-04-25 | Connected |  | No
National Grid | SOMERSET | 174646 | 2726 | 3000 | Solar | 05_11W84 | 2013-12-17 | 2013-12-18 | 22 | 16 | 6 | [10 empty] | 2014-01-22 | 2014-02-07 | 12 | 0 | 12 | [12 empty] | 2014-06-30 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | SOMERSET | 174647 | 2726 | 3000 | Solar | 05_11W84 | 2013-12-17 | 2013-12-18 | 22 | 16 | 6 | [10 empty] | 2014-01-22 | 2014-02-07 | 12 | 0 | 12 | [11 empty] | 2013-12-20 | 2014-06-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MANCHAUG | 174645 | 1526 | 44.4 | Solar | 05_320W5 | 2013-12-20 | 2013-12-23 | 6 | 0 | 6 | 2014-01-02 | 2014-01-02 | 0 | 0 | 0 | [20 empty] | 2014-01-27 | 2013-12-24 | 2014-02-28 |  | EXP |  | 2014-06-09 | 2014-06-09 | 0 | 0 | 0 | 2014-07-15 | 2014-07-15 | 2014-07-16 | Connected |  | No
National Grid | DIGHTON | 174648 | 2715 | 499 | Solar | 05_19W74 | 2013-12-24 | 2013-12-26 | 6 | 0 | 6 | 2014-01-06 | 2014-01-06 | 0 | 0 | 0 | [20 empty] | 2014-01-28 |  | 2016-04-08 |  | EXP |  | 2016-01-28 | 2016-03-25 | 39 | 0 | 39 | 2016-01-25 | 2016-01-25 | 2016-04-14 | Connected |  | No
National Grid | GRANBY | 174676 | 1033 | 3000 | Solar | 09_527L1 | 2013-12-30 | 2014-01-02 | 6 | 0 | 6 | [10 empty] | 2014-01-10 | 2014-01-28 | 11 | 0 | 11 | [10 empty] | 2014-09-05 |  | 2016-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SAUGUS | 174678 | 1906 | 22.8 | Solar | 12_19W1 | 2013-12-30 | 2014-01-02 | 286 | 284 | 2 | [27 empty] | 2014-05-30 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BEVERLY | 174679 | 1915 | 45 | Solar | 12_51T1 | 2014-01-06 | 2014-01-07 | 5 | 0 | 5 | 2014-01-14 | 2014-01-14 | 0 | 0 | 0 | [20 empty] | 2014-01-21 | 2014-01-06 | 2014-03-31 |  | EXP | [6 empty] | 2014-02-21 | 2014-02-21 | 2014-04-25 | Connected |  | No
National Grid | OAKHAM | 174680 | 1068 | 19.99 | Solar | 09_604W2 | 2014-01-06 | 2014-01-07 | 5 | 0 | 5 | 2014-01-14 | 2014-01-14 | 0 | 0 | 0 | [20 empty] | 2014-02-07 | 2014-01-08 | 2014-03-31 |  | EXP |  | 2015-01-22 | 2014-04-08 | 0 | 0 | 0 | 2014-06-12 | 2014-06-12 | 2014-07-08 | Connected |  | No
National Grid | HUBBARDSTON | 174681 | 1452 | 30 | Solar | 01_602W2 | 2014-01-08 | 2014-01-09 | 2 | 0 | 2 | 2014-01-13 | 2014-01-13 | 0 | 0 | 0 | [20 empty] | 2014-01-29 |  | 2014-06-20 | Yes | EXP | [6 empty] | 2014-01-29 | 2014-01-29 | 2014-06-24 | Connected |  | No
National Grid | WOLLASTON | 174682 | 2170 | 40 | Solar | 07_1W6 | 2014-01-09 | 2014-01-10 | 5 | 0 | 5 | 2014-01-17 | 2014-01-17 | 0 | 0 | 0 | [20 empty] | 2014-01-22 |  | 2014-03-31 |  | EXP | [6 empty] | 2014-04-22 | 2014-04-22 | 2014-04-25 | Connected |  | No
National Grid | WOLLASTON | 174683 | 2170 | 30 | Solar | 07_1W6 | 2014-01-09 | 2014-01-10 | 5 | 0 | 5 | 2014-01-17 | 2014-01-17 | 0 | 0 | 0 | [20 empty] | 2014-01-24 |  | 2014-03-31 |  | EXP | [6 empty] | 2014-04-11 | 2014-04-11 | 2014-04-11 | Connected |  | No
National Grid | WOLLASTON | 174684 | 2170 | 50 | Solar | 07_1W8 | 2014-01-09 | 2014-01-10 | 5 | 0 | 5 | 2014-01-17 | 2014-01-17 | 0 | 0 | 0 | [20 empty] | 2014-01-24 |  | 2014-03-31 |  | EXP | [6 empty] | 2014-04-07 | 2014-04-07 | 2014-04-24 | Connected |  | No
National Grid | WOLLASTON | 174713 | 2170 | 85 | Solar | 07_1W8 | 2014-01-09 | 2014-01-10 | 5 | 0 | 5 | 2014-01-17 | 2014-01-17 | 0 | 0 | 0 | [20 empty] | 2014-02-27 | 2014-01-09 | 2014-03-31 |  | EXP | [6 empty] | 2014-04-07 | 2014-04-07 | 2014-04-24 | Connected |  | No
National Grid | RUTLAND | 174714 | 1543 | 70 | Solar | 01_55W1 | 2014-01-09 | 2014-01-10 | 5 | 0 | 5 | 2014-01-17 | 2014-01-17 | 0 | 0 | 0 | [20 empty] | 2014-01-22 |  | 2014-08-29 |  | EXP | [6 empty] | 2014-07-28 | 2014-07-28 | 2015-08-06 | Connected |  | No
National Grid | HOUSATONIC | 174715 | 1236 | 2000 | Solar | 09_1109W3 | 2014-01-13 | 2014-01-14 | 7 | 0 | 7 | [10 empty] | 2014-01-24 | 2014-02-10 | 11 | 0 | 11 | [11 empty] | 2014-01-13 | 2014-08-29 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WEST WARREN | 174716 | 1092 | 1000 | Solar | 09_516L3 | 2014-01-13 | 2014-01-14 | 7 | 0 | 7 | [10 empty] | 2014-01-24 | 2014-02-12 | 13 | 0 | 13 | [10 empty] | 2014-06-27 |  | 2015-12-30 |  | STD | [6 empty] | 2014-01-13 | 2014-01-13 | 2015-12-31 | Connected |  | No
National Grid | CHARLTON | 174717 | 1507 | 52.8 | Solar | 01_413L4 | 2014-01-13 | 2014-01-15 | 6 | 0 | 6 | 2014-01-24 | 2014-01-24 | 0 | 0 | 0 | [20 empty] | 2014-01-30 | 2014-01-14 | 2014-03-31 |  | EXP | [6 empty] | 2014-03-10 | 2014-03-10 | 2015-07-21 | Connected |  | No
National Grid | WEST WARREN | 174718 | 1092 | 1000 | Solar | 09_516L3 | 2014-01-14 | 2014-01-15 | 6 | 0 | 6 | [10 empty] | 2014-01-24 | 2014-02-12 | 13 | 0 | 13 | [10 empty] | 2014-06-27 |  | 2016-02-24 |  | STD | [6 empty] | 2014-01-14 | 2014-01-14 | 2015-12-31 | Connected |  | No
National Grid | STOUGHTON | 174720 | 2072 | 500 | Solar | 07_94W44 | 2014-01-14 | 2014-01-15 | 6 | 0 | 6 | 2014-01-24 | 2014-03-28 | 43 | 7 | 36 | [22 empty] | 2014-12-01 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SHEFFIELD | 174719 | 1257 | 364 | Solar | 09_1108W2 | 2014-01-15 | 2014-01-16 | 4 | 0 | 4 | [27 empty] | 2014-03-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WHITMAN | 174721 | 2382 | 15.8 | Solar | 07_93W43 | 2014-01-15 | 2014-01-16 | 6 | 0 | 6 | 2014-01-27 | 2014-01-27 | 0 | 0 | 0 | [20 empty] | 2014-01-29 |  | 2014-03-31 |  | EXP | [6 empty] | 2014-02-26 | 2014-02-26 | 2014-03-26 | Connected |  | No
National Grid | WILLIAMSTOWN | 174752 | 1267 | 19.99 | Solar | 09_1001W1 | 2014-01-22 | 2014-01-23 | 7 | 0 | 7 | 2014-02-03 | 2014-02-03 | 0 | 0 | 0 | [20 empty] | 2014-04-14 |  | 2014-08-15 |  | EXP | [6 empty] | 2014-04-15 | 2014-04-15 | 2014-08-01 | Connected |  | No
National Grid | FRANKLIN | 174754 | 2038 | 56 | Solar | 05_344W6 | 2014-01-28 | 2014-01-29 | 7 | 0 | 7 | 2014-02-07 | 2014-02-07 | 0 | 0 | 0 | [20 empty] | 2014-02-18 |  | 2014-04-30 |  | EXP | [6 empty] | 2014-12-08 | 2014-12-08 | 2015-01-09 | Connected |  | No
National Grid | WINCHENDON | 174753 | 1475 | 24.73 | Solar | 01_612W1 | 2014-01-31 | 2014-02-03 | 6 | 0 | 6 | 2014-02-11 | 2014-02-11 | 0 | 0 | 0 | [20 empty] | 2014-04-24 |  | 2014-04-30 |  | EXP | [6 empty] | 2014-07-10 | 2014-07-10 | 2014-08-26 | Connected |  | No
National Grid | WEBSTER | 174756 | 1570 | 1000 | Solar | 01_412L2 | 2014-02-03 | 2014-02-03 | 7 | 0 | 7 | [10 empty] | 2014-02-12 | 2014-02-26 | 9 | 0 | 9 | [10 empty] | 2014-10-03 |  | 2016-08-14 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ANDOVER | 174755 | 1810 | 495 | Solar | 14_8T1 | 2014-02-05 | 2014-02-06 | 5 | 0 | 5 | 2014-02-13 | 2014-02-13 | 0 | 0 | 0 | 2014-11-04 | 2014-11-04 | 0 | 0 | 0 | [5 empty] | 2014-11-04 | 2014-11-04 | 0 | 0 | 0 | [5 empty] | 2014-03-11 | 2014-02-06 | 2014-06-30 |  | EXP | [6 empty] | 2014-09-22 | 2014-09-22 | 2014-10-02 | Connected |  | No
National Grid | DUDLEY | 174757 | 1571 | 448 | Solar | 01_412L4 | 2014-02-06 | 2014-02-07 | 19 | 14 | 5 | [10 empty] | 2014-03-07 | 2014-03-18 | 6 | 0 | 6 | [10 empty] | 2015-01-09 | 2014-02-06 | 2017-04-30 | Yes | STD |  | 2016-12-16 | 2017-06-06 | 116 | 0 | 116 | 2017-07-14 | 2017-07-14 | 2017-04-18 | Connected |  | No
National Grid | DUDLEY | 174758 | 1571 | 497.6 | Solar | 01_412L4 | 2014-02-06 | 2014-02-07 | 19 | 14 | 5 | [10 empty] | 2014-03-07 | 2014-03-18 | 6 | 0 | 6 | [10 empty] | 2015-01-09 | 2014-02-06 | 2017-08-31 | Yes | STD |  | 2016-12-16 | 2017-06-06 | 116 | 0 | 116 | 2017-07-14 | 2017-07-14 | 2017-08-11 | Connected |  | No
National Grid | DUDLEY | 174759 | 1571 | 497.6 | Solar | 01_412L4 | 2014-02-06 | 2014-02-07 | 19 | 14 | 5 | [10 empty] | 2014-03-07 | 2014-03-18 | 6 | 0 | 6 | [10 empty] | 2015-01-09 | 2014-02-06 | 2017-06-30 | Yes | STD |  | 2016-12-16 | 2017-06-06 | 116 | 0 | 116 | 2017-07-14 | 2017-07-14 | 2017-06-28 | Connected |  | No
National Grid | DUDLEY | 174760 | 1571 | 497.6 | Solar | 01_412L4 | 2014-02-06 | 2014-02-07 | 19 | 14 | 5 | [10 empty] | 2014-03-07 | 2014-03-18 | 6 | 0 | 6 | [10 empty] | 2015-01-09 |  | 2017-04-28 | Yes | STD |  | 2016-12-16 | 2017-06-06 | 116 | 0 | 116 | 2017-07-14 | 2017-07-14 | 2017-04-18 | Connected |  | No
National Grid | NORTHAMPTON | 175368 | 1060 | 34.2 | Solar | 09_909W2 | 2014-02-06 | 2014-02-07 | 5 | 0 | 5 | 2014-02-14 | 2014-02-14 | 0 | 0 | 0 | [20 empty] | 2014-02-21 | 2014-02-10 | 2014-05-30 |  | EXP | [6 empty] | 2014-02-25 | 2014-02-25 | 2014-06-17 | Connected |  | No
National Grid | NORTON | 175369 | 2766 | 648 | Solar | 05_8L2 | 2014-02-10 | 2014-02-11 | 5 | 0 | 5 | 2014-02-19 | 2014-02-19 | 0 | 0 | 0 | 2014-04-09 | 2014-05-27 | 32 | 8 | 24 | [5 empty] | 2014-04-09 | 2014-05-27 | 32 | 8 | 24 | [5 empty] | 2014-05-28 |  | 2014-10-14 | Yes | EXP |  | 2014-10-28 | 2014-11-08 | 9 | 0 | 9 | 2014-12-23 | 2014-12-23 | 2014-12-29 | Connected |  | No
National Grid | WILLIAMSTOWN | 175370 | 1267 | 41.92 | Solar | 09_1001W1 | 2014-02-14 | 2014-02-18 | 9 | 4 | 5 | 2014-03-03 | 2014-03-03 | 0 | 0 | 0 | [20 empty] | 2014-03-12 | 2014-02-14 | 2014-09-30 |  | EXP | [6 empty] | 2014-08-01 | 2014-08-01 | 2014-09-19 | Connected |  | No
National Grid | RUTLAND | 175371 | 1543 | 46.08 | Solar | 01_55W1 | 2014-02-14 | 2014-02-18 | 5 | 0 | 5 | 2014-02-25 | 2014-02-25 | 0 | 0 | 0 | [20 empty] | 2014-07-03 | 2014-02-14 | 2014-08-29 |  | EXP |  | 2015-01-06 | 2015-01-06 | 0 | 0 | 0 | 2015-03-02 | 2015-03-02 | 2015-03-05 | Connected |  | No
National Grid | ANDOVER | 175373 | 1810 | 494 | Solar | 14_8T1 | 2014-02-14 | 2014-02-18 | 7 | 1 | 6 | 2014-02-27 | 2014-02-27 | 0 | 0 | 0 | 2014-03-25 | 2014-04-21 | 19 | 0 | 19 | [5 empty] | 2014-03-25 | 2014-04-21 | 19 | 0 | 19 | [5 empty] | 2014-07-29 |  | 2016-12-31 | Yes | EXP |  | 2015-08-13 | 2015-12-23 | 90 | 0 | 90 | 2015-02-19 | 2015-02-19 | 2015-12-21 | Connected |  | No
National Grid | SALEM | 175372 | 1970 | 820 | Natural Gas | 12_2W2 | 2014-02-19 | 2014-02-20 | 6 | 0 | 6 | [10 empty] | 2014-02-28 | 2014-03-21 | 14 | 0 | 14 | [10 empty] | 2014-10-09 | 2014-02-25 | 2014-07-31 |  | STD | [6 empty] | 2015-11-03 | 2015-11-03 | 2015-11-03 | Connected |  | No
National Grid | BELCHERTOWN | 175374 | 1007 | 1000 | Solar | 09_509L1 | 2014-02-25 | 2014-02-26 | 11 | 4 | 7 | [10 empty] | 2014-03-13 | 2014-04-01 | 12 | 0 | 12 | [10 empty] | 2014-07-29 |  | 2016-12-31 | Yes | STD |  | 2016-01-15 | 2016-05-25 | 89 | 0 | 89 | 2017-12-19 | 2017-12-19 | 2016-05-26 | Connected |  | No
National Grid | WILBRAHAM | 175375 | 1095 | 3000 | Solar | 09_507L2 | 2014-02-26 | 2014-02-27 | 6 | 0 | 6 | [10 empty] | 2014-03-07 | 2014-03-17 | 6 | 0 | 6 | [12 empty] | 2014-10-31 |  | STD |  | 2016-10-13 | 2016-12-02 | 34 | 0 | 34 |  |  |  | Withdrawn |  | No
National Grid | MONROE | 175376 | 1350 | 5000 | Solar | 09_1009W1 | 2014-03-03 | 2014-03-04 | 7 | 0 | 7 | [10 empty] | 2014-03-13 | 2014-04-03 | 14 | 0 | 14 | [11 empty] | 2014-03-03 | 2014-09-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MENDON | 175405 | 1756 | 1000 | Solar | 05_332W1 | 2014-03-03 | 2014-03-04 | 7 | 0 | 7 | [10 empty] | 2014-03-13 | 2014-04-08 | 17 | 0 | 17 | [10 empty] | 2015-08-25 | 2014-03-03 | 2017-07-15 | Yes | STD |  | 2017-02-27 | 2017-08-03 | 110 | 0 | 110 | 2017-11-21 | 2017-11-21 | 2017-11-21 | Connected |  | No
National Grid | OXFORD | 175408 | 1540 | 2000 | Solar | 01_406L2 | 2014-03-03 | 2014-03-04 | 7 | 0 | 7 | [10 empty] | 2014-03-13 | 2014-04-07 | 16 | 0 | 16 | [10 empty] | 2015-04-01 | 2014-03-03 | 2016-09-14 | Yes | STD |  | 2016-06-27 | 2016-12-20 | 121 | 0 | 121 |  |  | 2016-11-23 | Connected |  | No
National Grid | OXFORD | 175410 | 1540 | 1992 | Solar | 01_406L2 | 2014-03-03 | 2014-03-04 | 7 | 0 | 7 | [10 empty] | 2014-03-13 | 2014-04-07 | 16 | 0 | 16 | [10 empty] | 2015-04-01 | 2014-03-03 | 2016-09-14 |  | STD | [8 empty] | 2016-12-01 | Connected |  | No
National Grid | OXFORD | 175411 | 1540 | 1992 | Solar | 01_406L2 | 2014-03-03 | 2014-03-04 | 7 | 0 | 7 | [10 empty] | 2014-03-13 | 2014-04-07 | 16 | 0 | 16 | [10 empty] | 2015-04-01 | 2014-03-03 | 2016-09-14 |  | STD | [8 empty] | 2016-11-23 | Connected |  | No
National Grid | OXFORD | 175412 | 1540 | 2000 | Solar | 01_406L2 | 2014-03-03 | 2014-03-04 | 7 | 0 | 7 | [10 empty] | 2014-03-13 | 2014-04-07 | 16 | 0 | 16 | [10 empty] | 2015-04-01 | 2014-03-03 | 2016-09-14 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | MENDON | 175441 | 1756 | 1000 | Solar | 05_332W1 | 2014-03-03 | 2014-03-04 | 7 | 0 | 7 | [10 empty] | 2014-03-13 | 2014-04-08 | 17 | 0 | 17 | [10 empty] | 2015-08-25 |  | 2017-07-15 | Yes | STD |  | 2017-02-27 | 2017-08-03 | 110 | 0 | 110 | 2017-11-21 | 2017-11-21 | 2017-11-21 | Connected |  | No
National Grid | MILFORD | 175407 | 1757 | 170 | Solar | 05_336W1 | 2014-03-04 | 2014-03-05 | 6 | 0 | 6 | 2014-03-13 | 2014-03-13 | 0 | 0 | 0 | [20 empty] | 2014-04-01 | 2014-03-04 | 2014-09-30 |  | EXP | [6 empty] | 2014-05-13 | 2014-05-13 | 2014-10-21 | Connected |  | No
National Grid | OXFORD | 175409 | 1540 | 996 | Solar | 01_406L2 | 2014-03-04 | 2014-03-04 | 7 | 0 | 7 | [10 empty] | 2014-03-13 | 2014-04-07 | 16 | 0 | 16 | [10 empty] | 2015-04-01 | 2014-03-10 01:00 | 2016-09-14 | Yes | STD |  | 2016-06-27 | 2016-12-20 | 121 | 0 | 121 |  |  | 2016-11-23 | Connected |  | No
National Grid | WESTMINSTER | 175446 | 1473 | 450 | Solar | 01_610W3 | 2014-03-10 01:00 | 2014-03-11 | 4 | 0 | 4 | [10 empty] | 2014-03-18 | 2014-04-09 | 16 | 0 | 16 | [10 empty] | 2014-12-11 |  | 2016-06-09 | Yes | STD |  | 2016-06-20 | 2016-09-08 | 56 | 0 | 56 |  |  | 2016-09-27 | Connected |  | No
National Grid | MENDON | 175447 | 1756 | 5000 | Solar | 05_335W1 | 2014-03-12 01:00 | 2014-03-13 | 6 | 0 | 6 | [10 empty] | 2014-03-24 | 2014-04-11 | 14 | 0 | 14 | [12 empty] | 2014-09-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MONROE | 175448 | 1350 | 5000 | Solar | 09_1009W1 | 2014-03-12 01:00 | 2014-03-13 | 6 | 0 | 6 | [10 empty] | 2014-03-24 | 2014-04-03 | 8 | 0 | 8 | [11 empty] | 2014-03-12 01:00 | 2015-04-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WARREN | 175449 | 1083 | 990 | Solar | 09_516L3 | 2014-03-12 01:00 | 2014-03-13 | 6 | 0 | 6 | [10 empty] | 2014-03-24 | 2014-04-21 | 20 | 0 | 20 | [10 empty] | 2015-04-01 | 2014-03-12 01:00 | 2016-02-09 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | MENDON | 175477 | 1756 | 1000 | Solar | 05_332W1 | 2014-03-12 01:00 | 2014-03-13 | 6 | 0 | 6 | [10 empty] | 2014-03-24 | 2014-04-08 | 11 | 0 | 11 | [10 empty] | 2015-08-25 |  | 2017-07-31 | Yes | STD |  | 2017-02-27 | 2017-08-03 | 110 | 0 | 110 | 2017-11-21 | 2017-11-21 | 2017-11-21 | Connected |  | No
National Grid | SOUTHBOROUGH | 175478 | 1772 | 250 | Solar | 05_310W6 | 2014-03-13 01:00 | 2014-03-14 | 5 | 0 | 5 | [26 empty] | 2014-03-13 01:00 | 2014-06-30 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | REVERE | 175479 | 2151 | 240.8 | Solar | 12_16W4 | 2014-03-13 01:00 | 2014-03-14 | 10 | 5 | 5 | 2014-03-31 | 2014-03-31 | 0 | 0 | 0 | [20 empty] | 2014-04-23 |  | 2014-08-29 |  | EXP |  | 2014-08-26 | 2014-08-26 | 0 | 0 | 0 | 2014-12-12 | 2014-12-12 | 2015-01-02 | Connected |  | No
National Grid | BILLERICA | 175483 | 1862 | 4999 | Solar | 14_70L1 | 2014-03-14 01:00 | 2014-03-17 | 7 | 0 | 7 | [10 empty] | 2014-03-27 | 2014-05-14 | 33 | 0 | 33 | [12 empty] | 2015-02-27 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MALDEN | 175484 | 2148 | 75 | Natural Gas | 12_37W4 | 2014-03-18 01:00 | 2014-03-19 | 8 | 2 | 6 | 2014-03-31 | 2014-03-31 | 0 | 0 | 0 | [20 empty] | 2014-04-11 | 2014-03-21 01:00 | 2014-09-30 |  | EXP | [6 empty] | 2014-10-15 | 2014-10-15 | 2014-10-28 | Connected |  | Yes
National Grid | BILLERICA | 175480 | 1862 | 4999 | Solar | 14_70L1 | 2014-03-21 01:00 | 2014-03-24 | 10 | 4 | 6 | [10 empty] | 2014-04-07 | 2014-05-14 | 26 | 0 | 26 | [12 empty] | 2015-03-31 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 175482 | 1605 | 47.3 | Solar | 01_12J376 | 2014-03-21 01:00 | 2014-03-25 | 5 | 1 | 4 | 2014-04-01 | 2014-04-01 | 0 | 0 | 0 | [20 empty] | 2014-04-09 |  | 2014-05-30 |  | EXP | [6 empty] | 2014-04-14 | 2014-04-14 | 2014-07-11 | Connected |  | No
National Grid | AVON | 175513 | 2322 | 250 | Solar | 07_75W1 | 2014-03-26 01:00 | 2014-03-27 | 6 | 0 | 6 | 2014-04-04 | 2014-04-04 | 0 | 0 | 0 | [20 empty] | 2014-05-02 |  | 2014-07-31 |  | EXP | [6 empty] | 2014-06-12 | 2014-06-12 | 2015-03-13 | Connected |  | No
National Grid | WEST BRIDGEWATER | 175515 | 2379 | 250 | Solar | 07_98W44 | 2014-03-28 01:00 | 2014-03-31 | 6 | 0 | 6 | 2014-04-08 | 2016-06-23 | 548 | 3 | 545 | [20 empty] | 2014-04-24 | 2014-04-01 01:00 | 2016-12-31 |  | EXP | [6 empty] | 2015-06-29 | 2015-06-29 |  | Withdrawn |  | Yes
National Grid | NORTON | 175517 | 2766 | 495 | Solar | 05_8L2 | 2014-04-01 01:00 | 2014-04-02 | 7 | 0 | 7 | [10 empty] | 2014-04-11 | 2014-07-11 | 61 | 32 | 29 | [10 empty] | 2016-03-17 | 2014-04-01 01:00 | 2017-12-29 | Yes | STD |  | 2017-03-28 | 2017-12-18 | 177 | 0 | 177 | 2017-12-28 | 2017-12-28 | 2017-12-28 | Connected |  | No
National Grid | NORTON | 175518 | 2766 | 495 | Solar | 05_8L2 | 2014-04-01 01:00 | 2014-04-02 | 7 | 0 | 7 | [10 empty] | 2014-04-11 | 2014-07-11 | 61 | 32 | 29 | [10 empty] | 2016-03-17 | 2014-04-02 01:00 | 2017-12-29 | Yes | STD |  | 2017-03-28 | 2017-12-18 | 177 | 0 | 177 | 2017-12-28 | 2017-12-28 | 2017-12-28 | Connected |  | No
National Grid | FOXBOROUGH | 178776 | 2035 | 255 | Solar | 05_3424W1 | 2014-04-02 01:00 | 2014-04-04 | 5 | 0 | 5 | 2014-04-11 | 2014-04-11 | 0 | 0 | 0 | [20 empty] | 2014-04-24 |  | 2014-06-30 | Yes | EXP | [6 empty] | 2015-08-13 | 2015-08-13 | 2015-08-13 | Connected |  | No
National Grid | HAVERHILL | 175551 | 1832 | 196 | Solar | 14_48L1 | 2014-04-07 01:00 | 2014-04-08 | 8 | 0 | 8 | 2014-04-18 | 2014-04-18 | 0 | 0 | 0 | [20 empty] | 2014-05-13 | 2014-04-08 01:00 | 2014-10-01 |  | EXP | [6 empty] | 2014-06-18 | 2014-06-18 | 2015-05-27 | Connected |  | No
National Grid | SUTTON | 175519 | 1590 | 1950 | Solar | 05_320W5 | 2014-04-08 01:00 | 2014-04-09 | 5 | 0 | 5 | [10 empty] | 2014-04-16 | 2014-04-28 | 7 | 0 | 7 | [10 empty] | 2015-01-09 | 2014-04-09 01:00 | 2016-12-31 |  | STD | [6 empty] | 2016-11-30 | 2016-11-30 | 2016-11-30 | Connected |  | No
National Grid | REVERE | 175520 | 2151 | 266 | Solar | 12_35J3 | 2014-04-09 01:00 | 2014-04-10 | 10 | 4 | 6 | 2014-04-25 | 2016-10-05 | 608 | 2 | 606 | [20 empty] | 2014-05-06 |  | 2016-02-04 | Yes | EXP | [9 empty] | Withdrawn |  | No
National Grid | GREAT BARRINGTON | 175548 | 1230 | 33.48 | Solar | 09_1109W1 | 2014-04-10 01:00 | 2014-04-11 | 6 | 0 | 6 | 2014-04-22 | 2014-04-22 | 0 | 0 | 0 | [20 empty] | 2014-05-05 |  | 2014-07-31 |  | EXP | [6 empty] | 2014-06-17 | 2014-06-17 | 2014-07-16 | Connected |  | No
National Grid | WILLIAMSTOWN | 175549 | 1267 | 16.125 | Solar | 09_1003W2 | 2014-04-11 01:00 | 2014-04-14 | 5 | 0 | 5 | 2014-04-22 | 2014-04-22 | 0 | 0 | 0 | [20 empty] | 2014-05-21 |  | 2014-09-30 |  | EXP | [6 empty] | 2014-07-30 | 2014-07-30 | 2014-09-08 | Connected |  | No
National Grid | TOPSFIELD | 175550 | 1983 | 33.3 | Solar | 12_26L1 | 2014-04-11 01:00 | 2014-04-14 | 6 | 0 | 6 | 2014-04-23 | 2014-04-23 | 0 | 0 | 0 | [20 empty] | 2014-05-13 | 2014-04-15 01:00 | 2014-08-29 |  | EXP | [6 empty] | 2014-06-17 | 2014-06-17 | 2014-09-02 | Connected |  | Yes
National Grid | MENDON | 175553 | 1756 | 1000 | Solar | 05_332W1 | 2014-04-15 01:00 | 2014-04-16 | 6 | 0 | 6 | [10 empty] | 2014-04-25 | 2014-05-15 | 14 | 3 | 11 | [10 empty] | 2015-01-12 |  | 2017-08-10 |  | STD |  | 2016-12-01 | 2017-07-14 | 154 | 0 | 154 | 2017-07-19 | 2017-07-19 | 2017-07-21 | Connected |  | No
National Grid | WILLIAMSTOWN | 175552 | 1267 | 2000 | Solar | 09_1003W1 | 2014-04-16 01:00 | 2014-04-17 | 5 | 0 | 5 | [10 empty] | 2014-04-25 | 2014-05-16 | 15 | 0 | 15 | [12 empty] | 2015-02-27 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ATTLEBORO | 175554 | 2703 | 750 | Solar | 05_9L5 | 2014-04-16 01:00 | 2014-04-17 | 5 | 0 | 5 | [5 empty] | 2014-06-17 | 2014-07-31 | 30 | 0 | 30 | 2014-04-25 | 2014-05-22 | 19 | 0 | 19 | 2014-06-17 | 2014-07-31 | 30 | 0 | 30 | [5 empty] | 2014-10-27 |  | 2014-12-31 |  | STD | [6 empty] | 2015-03-27 | 2015-03-27 | 2015-04-03 | Connected |  | No
National Grid | UXBRIDGE | 175583 | 1569 | 15.265 | Solar | 05_321W2 | 2014-04-16 01:00 | 2014-04-17 | 6 | 0 | 6 | 2014-04-28 | 2014-04-28 | 0 | 0 | 0 | [20 empty] | 2014-05-20 |  | 2014-08-29 |  | EXP | [6 empty] | 2014-05-20 | 2014-05-20 | 2014-08-15 | Connected |  | No
National Grid | RANDOLPH | 175584 | 2368 | 17 | Solar | 07_97W2 | 2014-04-18 01:00 | 2014-04-21 | 6 | 0 | 6 | 2014-04-30 | 2014-04-30 | 0 | 0 | 0 | [20 empty] | 2014-05-01 | 2014-04-18 01:00 | 2014-06-30 |  | EXP | [6 empty] | 2014-06-23 | 2014-06-23 | 2014-07-10 | Connected |  | No
National Grid | UPTON | 175586 | 1568 | 20 | Solar | 05_335W3 | 2014-04-18 01:00 | 2014-04-21 | 6 | 0 | 6 | 2014-04-30 | 2014-04-30 | 0 | 0 | 0 | [20 empty] | 2014-05-16 |  | 2014-06-30 |  | EXP | [6 empty] | 2014-05-29 | 2014-05-29 | 2014-07-14 | Connected |  | No
National Grid | GRANBY | 175588 | 1033 | 2000 | Solar | 09_527L1 | 2014-04-21 01:00 | 2014-04-22 | 7 | 0 | 7 | [10 empty] | 2014-05-01 | 2014-05-29 | 19 | 0 | 19 | [10 empty] | 2015-01-09 | 2014-04-22 01:00 | 2016-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WILBRAHAM | 175590 | 1095 | 496 | Solar | 09_507L2 | 2014-04-22 01:00 | 2014-04-23 | 9 | 4 | 5 | 2014-05-06 | 2014-05-06 | 0 | 0 | 0 | 2014-08-06 | 2014-08-06 | 0 | 0 | 0 | [5 empty] | 2014-08-06 | 2014-08-06 | 0 | 0 | 0 | [5 empty] | 2014-08-06 | 2014-04-23 01:00 | 2016-06-30 | Yes | EXP |  | 2016-10-13 | 2016-12-02 | 34 | 0 | 34 | 2016-12-08 | 2016-12-08 | 2016-12-08 | Connected |  | No
National Grid | REHOBOTH | 175591 | 2769 | 1670 | Solar | 05_7L5 | 2014-04-23 01:00 | 2014-04-25 | 6 | 0 | 6 | [10 empty] | 2014-05-05 | 2014-06-02 | 19 | 0 | 19 | [10 empty] | 2014-12-05 | 2014-04-24 01:00 | 2016-12-31 | Yes | STD |  | 2015-10-19 | 2016-02-18 | 82 | 0 | 82 | 2015-12-21 | 2015-12-21 | 2015-12-24 | Connected |  | No
National Grid | MILFORD | 175585 | 1757 | 170 | Solar | 05_336W1 | 2014-04-24 01:00 | 2014-04-25 | 3 | 0 | 3 | 2014-04-30 | 2014-04-30 | 0 | 0 | 0 | [20 empty] | 2014-05-13 | 2014-04-24 01:00 | 2014-10-31 | Yes | EXP | [6 empty] | 2014-05-13 | 2014-05-13 | 2015-02-17 | Connected |  | No
National Grid | SUTTON | 175617 | 1590 | 114 | Solar | 01_304W6 | 2014-04-24 01:00 | 2014-04-25 | 6 | 0 | 6 | 2014-05-05 | 2014-05-05 | 0 | 0 | 0 | [20 empty] | 2014-06-04 | 2014-04-28 01:00 | 2014-09-30 | Yes | EXP |  | 2014-10-15 | 2014-12-17 | 43 | 0 | 43 | 2014-07-21 | 2014-07-21 | 2014-12-19 | Connected |  | No
National Grid | WEST BRIDGEWATER | 175587 | 2379 | 496 | Solar | 07_98W44 | 2014-04-28 01:00 | 2014-04-30 | 2 | 0 | 2 | [10 empty] | 2014-05-02 | 2014-05-27 | 16 | 0 | 16 | [10 empty] | 2015-10-09 |  | 2018-09-13 | Yes | STD |  | 2018-02-16 | 2018-08-28 | 193 | 0 | 193 |  |  | 2018-09-07 | Connected |  | No
National Grid | WILLIAMSTOWN | 175618 | 1267 | 18 | Solar | 09_1003W1 | 2014-04-30 01:00 | 2014-05-01 | 6 | 0 | 6 | 2014-05-09 | 2014-05-09 | 0 | 0 | 0 | [20 empty] | 2014-06-03 |  | 2014-08-15 |  | EXP | [6 empty] | 2014-06-03 | 2014-06-03 | 2014-07-23 | Connected |  | No
National Grid | TYNGSBORO | 175619 | 1879 | 2000 | Hydro | 14_2399 | 2014-04-30 01:00 | 2014-05-01 | 2 | 0 | 2 | [10 empty] | 2014-05-05 | 2014-08-12 | 68 | 0 | 68 | [11 empty] | 2014-05-05 01:00 | 2016-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | DIGHTON | 175622 | 2715 | 996 | Solar | 05_19W73 | 2014-05-05 01:00 | 2014-05-06 | 7 | 0 | 7 | [10 empty] | 2014-05-15 | 2014-06-02 | 11 | 0 | 11 | [10 empty] | 2015-06-05 | 2014-05-05 01:00 | 2016-12-31 | Yes | STD |  | 2016-12-01 | 2016-12-30 | 20 | 0 | 20 | 2016-12-30 | 2016-12-30 | 2016-12-30 | Connected |  | No
National Grid | ATTLEBORO | 175623 | 2703 | 996 | Solar | 05_8L3 | 2014-05-05 01:00 | 2014-05-06 | 7 | 0 | 7 | 2014-05-15 | 2014-05-15 | 0 | 0 | 0 | 2014-07-30 | 2014-09-03 | 24 | 0 | 24 | [5 empty] | 2014-07-30 | 2014-09-03 | 24 | 0 | 24 | [5 empty] | 2015-01-28 | 2014-05-05 01:00 | 2016-12-31 | Yes | EXP |  | 2015-09-17 | 2015-12-18 | 63 | 0 | 63 | 2015-12-21 | 2015-12-21 | 2015-12-21 | Connected |  | No
National Grid | MILLBURY | 175624 | 1527 | 684 | Solar | 01_26W2 | 2014-05-05 01:00 | 2014-05-06 | 7 | 0 | 7 | 2014-05-15 | 2014-05-15 | 0 | 0 | 0 | 2014-07-30 | 2014-08-29 | 22 | 4 | 18 | [5 empty] | 2014-07-30 | 2014-08-29 | 22 | 4 | 18 | [5 empty] | 2014-10-02 | 2014-05-05 01:00 | 2015-12-31 | Yes | EXP |  | 2015-08-25 | 2015-11-23 | 61 | 0 | 61 | 2015-11-18 | 2015-11-18 | 2015-12-16 | Connected |  | No
National Grid | GRAFTON | 175625 | 1519 | 672 | Solar | 01_304W1 | 2014-05-05 01:00 | 2014-05-06 | 7 | 4 | 3 | [5 empty] | 2014-06-13 | 2014-06-13 | 0 | 0 | 0 | 2014-05-15 | 2014-09-12 | 82 | 12 | 70 | 2014-06-13 | 2014-06-13 | 0 | 0 | 0 | [5 empty] | 2015-10-09 | 2014-05-05 01:00 | 2016-12-01 | Yes | STD |  | 2016-04-19 | 2016-12-21 | 169 | 0 | 169 | 2016-12-09 | 2016-12-09 | 2016-12-21 | Connected |  | No
National Grid | CHARLTON | 175653 | 1507 | 684 | Solar | 01_406L3 | 2014-05-05 01:00 | 2014-05-06 | 7 | 4 | 3 | [10 empty] | 2014-05-15 | 2014-09-04 | 76 | 20 | 56 | [10 empty] | 2015-03-20 |  | 2015-12-30 | Yes | STD |  | 2015-10-22 | 2015-12-22 | 41 | 0 | 41 | 2015-12-11 | 2015-12-11 | 2015-12-30 | Connected |  | No
National Grid | CHARLTON | 175654 | 1507 | 480 | Solar | 01_413L4 | 2014-05-05 01:00 | 2014-05-06 | 7 | 0 | 7 | 2014-05-15 | 2014-07-23 | 46 | 8 | 38 | [20 empty] | 2014-06-25 | 2014-05-09 01:00 | 2014-10-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | ATTLEBORO | 175655 | 2703 | 684 | Solar | 05_9L2 | 2014-05-09 01:00 | 2014-05-12 | 8 | 0 | 8 | 2014-05-22 | 2014-05-22 | 0 | 0 | 0 | 2014-07-30 | 2014-08-29 | 22 | 0 | 22 | [5 empty] | 2014-07-30 | 2014-08-29 | 22 | 0 | 22 | [5 empty] | 2015-01-28 |  | 2016-12-31 | Yes | EXP |  | 2016-05-04 | 2016-08-23 | 76 | 0 | 76 | 2016-08-31 | 2016-08-31 | 2016-08-31 | Connected |  | No
National Grid | GLOUCESTER | 175656 | 1930 | 17.6 | Solar | 12_51T1 | 2014-05-13 01:00 | 2014-05-14 | 6 | 0 | 6 | 2014-05-22 | 2014-05-22 | 0 | 0 | 0 | [20 empty] | 2014-06-23 | 2014-05-13 01:00 | 2014-09-30 |  | EXP | [6 empty] | 2014-07-22 | 2014-07-22 | 2014-09-02 | Connected |  | No
National Grid | ATTLEBORO | 175657 | 2703 | 60 | Solar | 05_9L2 | 2014-05-13 01:00 | 2014-05-14 | 7 | 0 | 7 | 2014-05-23 | 2014-05-23 | 0 | 0 | 0 | [20 empty] | 2014-06-16 | 2014-05-19 01:00 | 2014-09-30 | Yes | EXP |  | 2014-11-05 | 2014-11-20 | 10 | 0 | 10 | 2014-12-12 | 2014-12-12 | 2014-12-16 | Connected |  | No
National Grid | MENDON | 175658 | 1756 | 386 | Solar | 05_332W1 | 2014-05-19 01:00 | 2014-05-20 | 6 | 0 | 6 | 2014-05-29 | 2014-05-29 | 0 | 0 | 0 | [20 empty] | 2014-07-24 | 2014-05-22 01:00 | 2015-08-14 | Yes | EXP | [6 empty] | 2014-08-12 | 2014-08-12 | 2016-12-14 | Connected |  | No
National Grid | ATHOL | 175659 | 1331 | 600 | Solar | 09_702W3 | 2014-05-22 01:00 | 2014-05-23 | 6 | 2 | 4 | [10 empty] | 2014-06-03 | 2014-07-08 | 23 | 0 | 23 | [10 empty] | 2015-03-13 |  | 2016-11-28 | Yes | STD |  | 2016-01-22 | 2016-01-22 | 0 | 0 | 0 | 2016-12-06 | 2016-12-06 | 2016-12-29 | Connected |  | No
National Grid | HALIFAX | 175660 | 2338 | 480 | Solar | 07_912W75 | 2014-05-22 01:00 | 2014-05-23 | 6 | 0 | 6 | 2014-06-03 | 2014-11-18 | 115 | 0 | 115 | 2014-06-27 | 2014-11-18 | 98 | 0 | 98 | [5 empty] | 2014-06-27 | 2014-11-18 | 98 | 0 | 98 | [6 empty] | 2014-05-22 01:00 | 2015-02-16 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTH BROOKFIELD | 175688 | 1535 | 480 | Solar | 09_604W3 | 2014-05-22 01:00 | 2014-05-23 | 6 | 0 | 6 | 2014-06-03 | 2014-06-03 | 0 | 0 | 0 | 2014-07-30 | 2014-08-29 | 22 | 0 | 22 | [5 empty] | 2014-07-30 | 2014-08-29 | 22 | 0 | 22 | [5 empty] | 2014-10-06 |  | 2015-11-13 | Yes | EXP |  | 2015-10-06 | 2015-10-21 | 10 | 0 | 10 | 2015-11-05 | 2015-11-05 | 2015-11-16 | Connected |  | No
National Grid | WENDELL | 175689 | 1379 | 480 | Solar | 09_705W1 | 2014-05-22 01:00 | 2014-05-23 | 6 | 0 | 6 | 2014-06-03 | 2014-08-12 | 48 | 0 | 48 | [22 empty] | 2015-02-27 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WENDELL | 175764 | 1379 | 480 | Solar | 09_705W1 | 2014-05-22 01:00 | 2014-05-23 | 6 | 0 | 6 | 2014-06-03 | 2014-08-12 | 48 | 0 | 48 | [22 empty] | 2015-02-27 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | PEMBROKE | 175661 | 2359 | 70 | Solar | 07_910W51 | 2014-05-23 01:00 | 2014-05-27 | 5 | 2 | 3 | 2014-06-03 | 2014-06-03 | 0 | 0 | 0 | [20 empty] | 2014-06-23 |  | 2014-08-29 |  | EXP | [6 empty] | 2014-07-02 | 2014-07-02 | 2014-11-19 | Connected |  | No
National Grid | WORCESTER | 175690 | 1607 | 225 | Solar | 01_8W1 | 2014-05-23 01:00 | 2014-05-27 | 6 | 0 | 6 | 2014-06-04 | 2014-06-04 | 0 | 0 | 0 | [20 empty] | 2014-06-27 |  | 2014-08-29 |  | EXP | [6 empty] | 2014-07-02 | 2014-07-02 | 2014-10-29 | Connected |  | No
National Grid | SOUTH EASTON | 175692 | 2375 | 15.8 | Solar | 07_92W79 | 2014-05-23 01:00 | 2014-05-27 | 5 | 0 | 5 | 2014-06-03 | 2014-06-03 | 0 | 0 | 0 | [20 empty] | 2014-07-02 |  | 2014-08-29 |  | EXP | [6 empty] | 2014-07-02 | 2014-07-02 | 2015-09-25 | Connected |  | No
National Grid | WESTFORD | 175693 | 1886 | 18 | Solar | 14_57L3 | 2014-05-23 01:00 | 2014-05-27 | 5 | 0 | 5 | 2014-06-03 | 2014-06-03 | 0 | 0 | 0 | [20 empty] | 2014-07-02 | 2014-05-27 01:00 | 2014-08-29 |  | EXP | [6 empty] | 2014-07-02 | 2014-07-02 | 2014-10-13 | Connected |  | No
National Grid | FALL RIVER | 175725 | 2720 | 500 | Solar | 05_28W51 | 2014-05-27 01:00 | 2014-05-28 | 5 | 0 | 5 | [10 empty] | 2014-06-04 | 2014-07-10 | 24 | 0 | 24 | [12 empty] | 2014-11-28 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | STOUGHTON | 175691 | 2072 | 880 | Solar | 07_94W44 | 2014-05-28 01:00 | 2014-05-29 | 5 | 0 | 5 | [10 empty] | 2014-06-05 | 2014-07-08 | 21 | 0 | 21 | [10 empty] | 2015-02-19 | 2014-05-28 01:00 | 2016-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WEST STOCKBRIDGE | 175694 | 1266 | 500 | Solar | 09_1102W1 | 2014-05-28 01:00 | 2014-05-29 | 6 | 0 | 6 | [10 empty] | 2014-06-06 | 2014-08-21 | 52 | 28 | 24 | [10 empty] | 2015-06-24 |  | 2017-11-30 | Yes | STD |  | 2017-06-20 | 2017-10-02 | 72 | 0 | 72 | 2017-10-11 | 2017-10-11 | 2017-10-11 | Connected |  | No
National Grid | STOCKBRIDGE | 175696 | 1262 | 500 | Solar | 09_1102W1 | 2014-05-28 01:00 | 2014-05-29 | 6 | 0 | 6 | [10 empty] | 2014-06-06 | 2014-08-21 | 52 | 28 | 24 | [10 empty] | 2015-06-24 |  | 2016-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | STOCKBRIDGE | 175724 | 1262 | 500 | Solar | 09_1102W1 | 2014-05-28 01:00 | 2014-05-29 | 6 | 0 | 6 | [10 empty] | 2014-06-06 | 2014-08-21 | 52 | 28 | 24 | [10 empty] | 2015-06-24 |  | 2016-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SHEFFIELD | 175761 | 1257 | 364 | Solar |  | 2014-05-29 01:00 | 2014-05-30 | 57 | 51 | 6 | [26 empty] | 2014-05-30 01:00 | 2014-11-28 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | FRANKLIN | 175726 | 2038 | 140 | Solar | 05_341W2 | 2014-05-30 01:00 | 2014-06-02 | 14 | 9 | 5 | 2014-06-23 | 2014-06-23 | 0 | 0 | 0 | [20 empty] | 2014-07-22 |  | 2014-10-15 | Yes | EXP |  | 2014-10-16 | 2014-12-04 | 33 | 0 | 33 | 2014-07-16 | 2014-07-16 | 2014-12-30 | Connected |  | No
National Grid | GRAFTON | 175727 | 1519 | 1000 | Solar | 01_304W2 | 2014-06-02 01:00 | 2014-06-03 | 19 | 13 | 6 | [27 empty] | 2014-12-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | GRAFTON | 175728 | 1519 | 1000 | Solar | 01_304W2 | 2014-06-02 01:00 | 2014-06-03 | 19 | 13 | 6 | [27 empty] | 2014-12-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH QUINCY | 175732 | 2171 | 1161 | Solar | 07_11W4 | 2014-06-02 01:00 | 2014-06-03 | 6 | 0 | 6 | [10 empty] | 2014-06-11 | 2014-07-28 | 31 | 15 | 16 | [11 empty] | 2014-06-03 01:00 | 2014-12-31 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | OXFORD | 175729 | 1540 | 996 | Solar | 01_406L1 | 2014-06-03 01:00 | 2014-06-04 | 5 | 0 | 5 | [10 empty] | 2014-06-11 | 2014-07-10 | 19 | 0 | 19 | [10 empty] | 2014-11-24 | 2014-06-03 01:00 | 2016-04-23 | Yes | STD |  | 2015-10-20 | 2016-04-27 | 128 | 0 | 128 | 2014-06-05 | 2014-06-05 | 2016-05-12 | Connected |  | No
National Grid | WESTMINSTER | 175730 | 1473 | 1000 | Solar | 01_610W3 | 2014-06-03 01:00 | 2014-06-04 | 6 | 0 | 6 | [10 empty] | 2014-06-12 | 2014-06-27 | 10 | 4 | 6 | [5 empty] | 2016-03-18 | 2016-03-15 | 0 | 0 | 0 | 2016-08-15 | 2014-06-03 01:00 | 2018-10-15 | Yes | STD | [6 empty] | 2018-09-07 | 2018-09-07 | 2018-10-05 | Connected |  | No
National Grid | WESTMINSTER | 175731 | 1473 | 499 | Solar | 01_610W3 | 2014-06-03 01:00 | 2014-06-04 | 6 | 0 | 6 | [10 empty] | 2014-06-12 | 2014-06-27 | 10 | 4 | 6 | [5 empty] | 2016-03-18 | 2016-03-15 | 0 | 0 | 0 | 2016-08-15 |  | 2018-10-15 | Yes | STD | [6 empty] | 2018-09-07 | 2018-09-07 | 2018-10-05 | Connected |  | No
National Grid | WORCESTER | 175762 | 1609 | 17 | Solar | 01_16J2 | 2014-06-05 01:00 | 2014-06-06 | 6 | 0 | 6 | 2014-06-16 | 2014-06-16 | 0 | 0 | 0 | [20 empty] | 2014-07-11 |  | 2014-08-29 |  | EXP | [6 empty] | 2014-07-11 | 2014-07-11 | 2014-10-09 | Connected |  | No
National Grid | SWANSEA | 175763 | 2777 | 684 | Solar | 05_19W73 | 2014-06-05 01:00 | 2014-06-06 | 6 | 0 | 6 | [10 empty] | 2014-06-16 | 2014-09-04 | 55 | 0 | 55 | [12 empty] | 2014-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | RANDOLPH | 175765 | 2368 | 16.01 | Solar | 07_97W2 | 2014-06-06 01:00 | 2014-06-09 | 5 | 2 | 3 | 2014-06-16 | 2014-06-16 | 0 | 0 | 0 | [20 empty] | 2014-07-11 |  | 2014-08-29 |  | EXP | [6 empty] | 2014-07-11 | 2014-07-11 | 2014-08-15 | Connected |  | No
National Grid | SOUTH EASTON | 175768 | 2375 | 1000 | Solar | 07_92W54 | 2014-06-06 01:00 | 2014-06-09 | 11 | 6 | 5 | [10 empty] | 2014-06-25 | 2014-10-03 | 70 | 68 | 2 | [12 empty] | 2014-11-28 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | NORTHBOROUGH | 175231 | 1532 | 504 | Solar | 05_312W3 | 2014-06-10 01:00 | 2014-06-11 | 7 | 3 | 4 | 2014-06-23 | 2014-09-23 | 64 | 0 | 64 | [21 empty] | 2014-06-10 01:00 | 2014-10-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOUTHBRIDGE | 175235 | 1550 | 480 | Solar | 01_413L4 | 2014-06-10 01:00 | 2014-06-11 | 6 | 0 | 6 | [10 empty] | 2014-06-20 | 2014-07-16 | 17 | 0 | 17 | [5 empty] | 2014-12-25 | 2015-03-11 | 50 | 0 | 50 | 2015-03-12 | 2014-06-10 01:00 | 2016-12-31 |  | STD |  | 2016-01-18 | 2016-04-01 | 51 | 0 | 51 | 2016-03-31 | 2016-03-31 | 2016-04-01 | Connected |  | No
National Grid | SOUTHBRIDGE | 175236 | 1550 | 480 | Solar | 01_413L4 | 2014-06-10 01:00 | 2014-06-11 | 6 | 0 | 6 | [10 empty] | 2014-06-20 | 2014-07-16 | 17 | 0 | 17 | [5 empty] | 2014-12-25 | 2015-03-11 | 50 | 0 | 50 | 2015-03-12 | 2014-06-10 01:00 | 2016-12-31 |  | STD |  | 2016-01-28 | 2016-04-01 | 44 | 0 | 44 | 2016-03-31 | 2016-03-31 | 2016-04-01 | Connected |  | No
National Grid | SOUTHBRIDGE | 175237 | 1550 | 480 | Solar | 01_413L4 | 2014-06-10 01:00 | 2014-06-11 | 6 | 0 | 6 | [10 empty] | 2014-06-20 | 2014-07-16 | 17 | 0 | 17 | [5 empty] | 2014-12-25 | 2014-12-25 | 0 | 0 | 0 | 2015-03-12 | 2014-06-10 01:00 | 2016-12-31 |  | STD |  | 2016-01-28 | 2016-04-01 | 44 | 0 | 44 | 2016-03-31 | 2016-03-31 | 2016-04-01 | Connected |  | No
National Grid | SOUTHBRIDGE | 175264 | 1550 | 480 | Solar | 01_413L4 | 2014-06-10 01:00 | 2014-06-11 | 6 | 0 | 6 | [10 empty] | 2014-06-20 | 2014-07-16 | 17 | 0 | 17 | [5 empty] | 2014-12-25 | 2014-12-25 | 0 | 0 | 0 | 2015-03-12 |  | 2016-12-31 |  | STD |  | 2016-03-29 | 2016-04-01 | 3 | 0 | 3 | 2016-03-31 | 2016-03-31 | 2016-04-01 | Connected |  | No
National Grid | WESTPORT | 175769 | 2790 | 4800 | Solar | 05_115W52 | 2014-06-10 01:00 | 2014-06-11 | 7 | 4 | 3 | [10 empty] | 2014-06-23 | 2014-07-21 | 19 | 0 | 19 | [10 empty] | 2015-04-27 | 2014-06-10 01:00 | 2016-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | FOXBOROUGH | 178774 | 2035 | 2000 | Solar | 05_3432W2 | 2014-06-10 01:00 | 2014-06-11 | 7 | 4 | 3 | [10 empty] | 2014-06-23 | 2014-07-21 | 19 | 0 | 19 | [10 empty] | 2015-02-06 | 2014-06-10 01:00 | 2017-10-15 |  | STD |  | 2017-08-16 | 2017-10-04 | 34 | 0 | 34 | 2017-10-11 | 2017-10-11 | 2017-10-11 | Connected |  | No
National Grid | FOXBOROUGH | 178781 | 2035 | 1200 | Solar | 05_3432W2 | 2014-06-10 01:00 | 2014-06-11 | 18 | 15 | 3 | [10 empty] | 2014-07-09 | 2014-07-21 | 8 | 0 | 8 | [10 empty] | 2015-02-06 |  | 2017-07-31 |  | STD |  | 2015-10-22 | 2017-07-14 | 429 | 0 | 429 | 2017-07-19 | 2017-07-19 | 2017-07-25 | Connected |  | No
National Grid | RANDOLPH | 175767 | 2368 | 5000 | Solar | 07_97W2 | 2014-06-12 01:00 | 2014-06-13 | 4 | 0 | 4 | [10 empty] | 2014-06-20 | 2014-07-17 | 18 | 0 | 18 | [12 empty] | 2015-02-27 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | DUDLEY | 175265 | 1571 | 15.8 | Solar | 01_412L4 | 2014-06-16 01:00 | 2014-06-18 | 6 | 0 | 6 | 2014-06-26 | 2014-09-02 | 46 | 0 | 46 | [20 empty] | 2014-07-22 |  | 2014-09-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 175270 | 1605 | 336 | Solar | 01_27W4 | 2014-06-16 01:00 | 2014-06-17 | 7 | 0 | 7 | 2014-06-27 | 2017-04-04 | 687 | 32 | 655 | [20 empty] | 2014-09-12 | 2014-06-17 01:00 | 2014-11-28 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BARRE | 175232 | 1005 | 480 | Solar | 09_604W1 | 2014-06-17 01:00 | 2014-06-17 | 2 | 0 | 2 | [10 empty] | 2014-06-20 | 2014-07-22 | 21 | 0 | 21 | [10 empty] | 2014-12-22 | 2014-06-17 01:00 | 2016-12-31 | Yes | STD |  | 2015-09-03 | 2015-12-02 | 60 | 0 | 60 | 2015-11-30 | 2015-11-30 | 2015-12-30 | Connected |  | No
National Grid | BARRE | 175233 | 1005 | 480 | Solar | 09_604W1 | 2014-06-17 01:00 | 2014-06-17 | 2 | 0 | 2 | [10 empty] | 2014-06-20 | 2014-07-22 | 21 | 0 | 21 | [10 empty] | 2014-12-22 | 2014-06-17 01:00 | 2016-12-31 | Yes | STD |  | 2015-09-03 | 2015-12-02 | 60 | 0 | 60 | 2015-11-30 | 2015-11-30 | 2015-12-22 | Connected |  | No
National Grid | BARRE | 175234 | 1005 | 480 | Solar | 09_604W1 | 2014-06-17 01:00 | 2014-06-17 | 2 | 0 | 2 | [10 empty] | 2014-06-20 | 2014-07-22 | 21 | 0 | 21 | [10 empty] | 2014-12-22 |  | 2016-12-31 | Yes | STD |  | 2015-09-03 | 2015-12-02 | 60 | 0 | 60 | 2015-11-30 | 2015-11-30 | 2015-12-22 | Connected |  | No
National Grid | BELCHERTOWN | 175266 | 1007 | 480 | Solar | 09_509L1 | 2014-06-18 01:00 | 2014-06-19 | 6 | 0 | 6 | 2014-06-27 | 2014-11-18 | 98 | 0 | 98 | [22 empty] | 2014-11-28 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SWANSEA | 175268 | 2777 | 130 | Solar | 05_11W85 | 2014-06-20 01:00 | 2014-06-23 | 9 | 7 | 2 | 2014-07-07 | 2014-07-07 | 0 | 0 | 0 | [20 empty] | 2014-08-04 | 2014-06-23 01:00 | 2014-10-31 |  | EXP | [6 empty] | 2014-12-08 | 2014-12-08 | 2014-12-22 | Connected |  | No
National Grid | RUTLAND | 175272 | 1543 | 997.6 | Solar | 01_55W1 | 2014-06-23 01:00 | 2014-06-24 | 7 | 5 | 2 | [10 empty] | 2014-07-03 | 2014-08-06 | 23 | 0 | 23 | [10 empty] | 2015-02-18 |  | 2016-06-01 | Yes | STD |  | 2016-11-29 | 2017-01-16 | 32 | 0 | 32 | 2017-01-13 | 2017-01-13 | 2017-01-13 | Connected |  | No
National Grid | REHOBOTH | 175303 | 2769 | 4800 | Solar | 05_7L5 | 2014-06-24 01:00 | 2014-06-25 | 5 | 0 | 5 | [10 empty] | 2014-07-02 | 2014-08-04 | 22 | 0 | 22 | [11 empty] | 2014-06-25 01:00 | 2015-01-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NEW BRAINTREE | 175304 | 1531 | 499 | Solar | 09_604W3 | 2014-06-25 01:00 | 2014-06-26 | 6 | 0 | 6 | 2014-07-07 | 2014-07-07 | 0 | 0 | 0 | [20 empty] | 2014-08-15 |  | 2016-11-18 | Yes | EXP |  | 2016-12-02 | 2017-03-29 | 79 | 0 | 79 | 2017-04-12 | 2017-04-12 | 2017-04-12 | Connected |  | No
National Grid | EAST BRIDGEWATER | 175305 | 2333 | 16 | Solar | 07_797W24 | 2014-06-25 01:00 | 2014-06-26 | 19 | 13 | 6 | 2014-07-24 | 2014-07-24 | 0 | 0 | 0 | [20 empty] | 2014-08-14 |  | 2014-09-30 |  | EXP | [6 empty] | 2014-09-03 | 2014-09-03 | 2014-11-14 | Connected |  | No
National Grid | LYNN | 175306 | 1905 | 232 | Solar | 12_21J29 | 2014-06-25 01:00 | 2014-06-26 | 6 | 0 | 6 | 2014-07-07 | 2014-07-07 | 0 | 0 | 0 | [20 empty] | 2014-07-28 |  | 2014-10-31 |  | EXP | [6 empty] | 2014-07-28 | 2014-07-28 | 2014-12-31 | Connected |  | No
National Grid | HANOVER | 175381 | 2339 | 1000 | Solar | 07_95W2 | 2014-06-26 01:00 | 2014-06-27 | 69 | 69 | 0 | 2014-10-06 | 2015-10-20 | 257 | 0 | 257 | [20 empty] | 2014-12-09 |  | 2015-02-27 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | QUINCY | 175309 | 2169 | 135 | Solar | 07_3W3 | 2014-06-27 01:00 | 2014-06-30 | 6 | 1 | 5 | 2014-07-09 | 2014-07-09 | 0 | 0 | 0 | [20 empty] | 2014-08-08 |  | 2014-12-31 |  | EXP | [6 empty] | 2014-08-08 | 2014-08-08 | 2016-03-31 | Connected |  | No
National Grid | QUINCY | 175310 | 2169 | 129 | Solar | 07_1W3 | 2014-06-27 01:00 | 2014-06-30 | 6 | 1 | 5 | 2014-07-09 | 2014-07-09 | 0 | 0 | 0 | [20 empty] | 2014-08-05 | 2014-06-27 01:00 | 2014-11-28 |  | EXP | [6 empty] | 2015-01-23 | 2015-01-23 | 2015-01-29 | Connected |  | No
National Grid | SALEM | 175311 | 1970 | 1560 | Natural Gas | 12_2349 | 2014-06-27 01:00 | 2014-06-30 | 4 | 0 | 4 | [10 empty] | 2014-07-07 | 2014-08-08 | 24 | 0 | 24 | [10 empty] | 2015-06-12 | 2014-06-27 01:00 | 2019-11-22 | Yes | STD |  | 2019-08-06 | 2019-08-05 | 0 | 0 | 0 |  |  | 2019-11-22 | Connected |  | No
National Grid | WEST BROOKFIELD | 175312 | 1585 | 1414 | Solar | 01_525L2 | 2014-06-27 01:00 | 2014-06-30 | 6 | 4 | 2 | [10 empty] | 2014-07-09 | 2014-08-07 | 21 | 0 | 21 | [5 empty] | 2016-08-11 | 2016-08-11 | 0 | 0 | 0 | 2015-03-23 | 2014-06-27 01:00 | 2016-02-18 |  | STD |  | 2016-03-31 | 2016-06-08 | 47 | 0 | 47 | 2016-08-23 | 2016-08-23 | 2016-08-23 | Connected |  | No
National Grid | HOUSATONIC | 175341 | 1236 | 2000 | Solar | 09_1109W3 | 2014-06-27 01:00 | 2014-06-27 | 5 | 0 | 5 | [10 empty] | 2014-07-07 | 2014-07-09 | 2 | 0 | 2 | [10 empty] | 2014-07-29 | 2014-06-30 01:00 | 2016-12-31 | Yes | STD |  | 2016-01-04 | 2016-05-05 | 84 | 0 | 84 | 2016-05-06 | 2016-05-06 | 2016-05-06 | Connected |  | No
National Grid | NORTH CHELMSFORD | 175307 | 1863 | 910 | Solar | 14_2L1 | 2014-06-30 01:00 | 2014-06-30 | 3 | 0 | 3 | [10 empty] | 2014-07-03 | 2014-08-06 | 23 | 0 | 23 | [10 empty] | 2016-01-28 |  | 2021-08-03 | Yes | STD |  | 2019-05-21 | 2021-07-21 | 406 | 4 | 402 |  |  | 2021-08-03 | Connected |  | No
National Grid | QUINCY | 175342 | 2169 | 144 | Solar | 07_1W2 | 2014-07-02 01:00 | 2014-07-03 | 3 | 0 | 3 | 2014-07-09 | 2014-07-09 | 0 | 0 | 0 | [20 empty] | 2014-08-07 |  | 2014-11-28 |  | EXP | [6 empty] | 2014-08-07 | 2014-08-07 | 2015-03-16 | Connected |  | No
National Grid | WOLLASTON | 175343 | 2170 | 42 | Solar | 07_1W6 | 2014-07-02 01:00 | 2014-07-03 | 3 | 0 | 3 | 2014-07-09 | 2014-07-09 | 0 | 0 | 0 | [20 empty] | 2014-08-05 |  | 2014-11-28 |  | EXP | [6 empty] | 2015-01-21 | 2015-01-21 | 2015-01-30 | Connected |  | No
National Grid | QUINCY | 175344 | 2169 | 60 | Solar | 07_3W1 | 2014-07-02 01:00 | 2014-07-03 | 3 | 0 | 3 | 2014-07-09 | 2014-07-09 | 0 | 0 | 0 | [20 empty] | 2014-08-05 |  | 2014-11-28 |  | EXP | [6 empty] | 2015-01-21 | 2015-01-21 | 2015-01-29 | Connected |  | No
National Grid | UXBRIDGE | 175346 | 1569 | 265 | Solar | 05_321W4 | 2014-07-03 01:00 | 2014-07-07 | 3 | 0 | 3 | 2014-07-10 | 2014-07-10 | 0 | 0 | 0 | [20 empty] | 2014-07-22 |  | 2014-11-28 |  | EXP | [6 empty] | 2014-07-22 | 2014-07-22 | 2016-03-02 | Connected |  | No
National Grid | UXBRIDGE | 175347 | 1569 | 42 | Solar | 05_321W4 | 2014-07-03 01:00 | 2014-07-07 | 3 | 0 | 3 | 2014-07-10 | 2014-07-10 | 0 | 0 | 0 | [20 empty] | 2014-08-05 |  | 2016-12-31 |  | EXP | [6 empty] | 2014-09-18 | 2014-09-18 | 2016-01-22 | Connected |  | No
National Grid | LYNN | 175379 | 1902 | 75 | Natural Gas | 12_1393 | 2014-07-08 01:00 | 2014-07-09 | 6 | 6 | 0 | 2014-07-17 | 2014-07-17 | 0 | 0 | 0 | [20 empty] | 2014-08-22 |  | 2014-11-28 |  | EXP | [6 empty] | 2014-12-30 | 2014-12-30 | 2015-01-05 | Connected |  | Yes
National Grid | NORTH ADAMS | 175348 | 1247 | 139.2 | Solar | 09_1021W2 | 2014-07-09 01:00 | 2014-07-09 | 1 | 0 | 1 | 2014-07-10 | 2014-07-10 | 0 | 0 | 0 | [20 empty] | 2014-07-29 |  | 2014-10-31 |  | EXP | [6 empty] | 2014-07-29 | 2014-07-29 | 2014-12-22 | Connected |  | No
National Grid | ORANGE | 175349 | 1364 | 69.6 | Solar | 09_705W3 | 2014-07-09 01:00 | 2014-07-09 | 1 | 0 | 1 | 2014-07-10 | 2014-07-10 | 0 | 0 | 0 | [20 empty] | 2014-07-28 |  | 2014-11-28 |  | EXP | [6 empty] | 2014-07-28 | 2014-07-28 | 2016-12-16 | Connected |  | Yes
National Grid | NORTHBOROUGH | 175377 | 1532 | 368 | Solar | 05_312W2 | 2014-07-09 01:00 | 2014-07-09 | 1 | 0 | 1 | 2014-07-10 | 2014-07-10 | 0 | 0 | 0 | [20 empty] | 2014-07-29 |  | 2014-11-28 |  | EXP | [6 empty] | 2014-12-15 | 2014-12-15 | 2014-12-31 | Connected |  | No
National Grid | GARDNER | 175378 | 1440 | 278.4 | Solar | 01_602W2 | 2014-07-09 01:00 | 2014-07-09 | 1 | 0 | 1 | 2014-07-10 | 2014-07-10 | 0 | 0 | 0 | [20 empty] | 2014-07-30 | 2014-07-09 01:00 | 2014-11-28 |  | EXP | [6 empty] | 2014-10-16 | 2014-10-16 | 2014-12-31 | Connected |  | No
National Grid | PALMER | 175380 | 1069 | 499 | Solar | 09_503L1 | 2014-07-09 01:00 | 2014-07-10 | 5 | 0 | 5 | [10 empty] | 2014-07-17 | 2014-08-14 | 20 | 0 | 20 | [10 empty] | 2015-03-12 |  | 2016-01-15 | Yes | STD |  | 2016-08-03 | 2016-10-11 | 47 | 0 | 47 | 2017-03-17 | 2017-03-17 | 2016-10-17 | Connected |  | No
National Grid | DRACUT | 175382 | 1826 | 18 | Solar | 14_78L9 | 2014-07-09 01:00 | 2014-07-10 | 5 | 0 | 5 | 2014-07-17 | 2014-07-17 | 0 | 0 | 0 | [20 empty] | 2014-08-12 |  | 2014-09-30 |  | EXP | [6 empty] | 2014-09-12 | 2014-09-12 | 2014-10-31 | Connected |  | No
National Grid | RANDOLPH | 175383 | 2368 | 17 | Solar | 07_5W3 | 2014-07-09 01:00 | 2014-07-10 | 5 | 0 | 5 | 2014-07-17 | 2014-08-11 | 17 | 0 | 17 | [22 empty] | 2014-09-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTH ANDOVER | 175384 | 1845 | 52 | Solar | 14_43L7 | 2014-07-09 01:00 | 2014-07-10 | 5 | 0 | 5 | 2014-07-17 | 2014-07-17 | 0 | 0 | 0 | [20 empty] | 2014-07-31 |  | 2014-11-28 |  | EXP | [6 empty] | 2014-08-07 | 2014-08-07 | 2015-01-15 | Connected |  | No
National Grid | BROCKTON | 175385 | 2301 | 92 | Solar | 07_911W25 | 2014-07-09 01:00 | 2014-07-10 | 5 | 0 | 5 | 2014-07-17 | 2014-07-17 | 0 | 0 | 0 | [20 empty] | 2014-07-31 | 2014-07-09 01:00 | 2014-11-28 |  | EXP | [6 empty] | 2014-08-07 | 2014-08-07 | 2015-03-17 | Connected |  | Yes
National Grid | NORTH BILLERICA | 175414 | 1862 | 76 | Solar | 14_70L4 | 2014-07-09 01:00 | 2014-07-10 | 5 | 0 | 5 | 2014-07-17 | 2014-07-17 | 0 | 0 | 0 | [20 empty] | 2014-08-04 |  | 2014-11-28 | Yes | EXP |  | 2015-03-27 | 2015-05-11 | 30 | 0 | 30 | 2014-08-07 | 2014-08-07 | 2015-07-20 | Connected |  | No
National Grid | WOLLASTON | 175415 | 2170 | 52 | Solar | 07_1W8 | 2014-07-09 01:00 | 2014-07-10 | 5 | 0 | 5 | 2014-07-17 | 2014-07-17 | 0 | 0 | 0 | [20 empty] | 2014-07-31 | 2014-07-09 01:00 | 2014-11-28 |  | EXP | [6 empty] | 2014-08-11 | 2014-08-11 | 2015-01-08 | Connected |  | No
National Grid | AMESBURY | 175416 | 1913 | 4500 | Solar | 14_275L4 | 2014-07-09 01:00 | 2014-07-10 | 5 | 0 | 5 | [10 empty] | 2014-07-17 | 2014-08-14 | 20 | 18 | 2 | [10 empty] | 2015-03-17 |  | 2016-12-31 | Yes | STD |  | 2016-08-30 | 2017-01-30 | 102 | 0 | 102 | 2016-12-14 | 2016-12-14 | 2016-12-22 | Connected |  | No
National Grid | HUBBARDSTON | 175417 | 1452 | 16 | Solar | 01_602W2 | 2014-07-10 01:00 | 2014-07-11 | 7 | 0 | 7 | 2014-07-22 | 2014-07-22 | 0 | 0 | 0 | [20 empty] | 2014-07-24 |  | 2014-09-30 |  | EXP | [6 empty] | 2014-08-12 | 2014-08-12 | 2014-10-14 | Connected |  | No
National Grid | LEOMINSTER | 175419 | 1453 | 30 | Solar | 01_219W4 | 2014-07-11 01:00 | 2014-07-14 | 6 | 0 | 6 | 2014-07-22 | 2014-07-22 | 0 | 0 | 0 | [20 empty] | 2014-07-28 |  | 2014-11-28 |  | EXP | [6 empty] | 2014-07-29 | 2014-07-29 | 2014-12-18 | Connected |  | No
National Grid | QUINCY | 175421 | 2169 | 96 | Solar | 07_1W5 | 2014-07-14 01:00 | 2014-07-15 | 6 | 3 | 3 | 2014-07-23 | 2014-07-23 | 0 | 0 | 0 | [20 empty] | 2014-08-15 |  | 2014-10-31 |  | EXP | [6 empty] | 2014-09-16 | 2014-09-16 | 2016-03-18 | Connected |  | No
National Grid | NORTH QUINCY | 175422 | 2171 | 225 | Solar | 07_11W3 | 2014-07-14 01:00 | 2014-07-23 | 0 | 0 | 0 | 2014-07-23 | 2014-07-23 | 0 | 0 | 0 | [20 empty] | 2014-08-25 |  | 2014-10-31 |  | EXP | [6 empty] | 2014-10-01 | 2014-10-01 | 2015-03-13 | Connected |  | No
National Grid | QUINCY | 175423 | 2170 | 195 | Solar | 07_1W6 | 2014-07-14 01:00 | 2014-07-15 | 6 | 2 | 4 | 2014-07-23 | 2014-07-23 | 0 | 0 | 0 | [20 empty] | 2014-08-18 | 2014-07-14 01:00 | 2014-10-31 |  | EXP | [6 empty] | 2014-08-29 | 2014-08-29 | 2015-01-30 | Connected |  | No
National Grid | PALMER | 175486 | 1069 | 4880 | Solar | 09_523L4 | 2014-07-14 01:00 | 2014-07-15 | 7 | 0 | 7 | [10 empty] | 2014-07-24 | 2014-08-19 | 18 | 0 | 18 | [5 empty] | 2015-01-27 | 2015-03-04 | 25 | 0 | 25 | 2015-03-12 |  | 2016-06-01 |  | STD | [6 empty] | 2015-12-21 | 2015-12-21 | 2015-12-22 | Connected |  | No
National Grid | NORTH QUINCY | 175450 | 2171 | 45 | Solar | 07_11W1 | 2014-07-15 01:00 | 2014-07-16 | 5 | 2 | 3 | 2014-07-23 | 2014-07-23 | 0 | 0 | 0 | [20 empty] | 2014-08-25 |  | 2014-10-31 |  | EXP | [6 empty] | 2014-10-01 | 2014-10-01 | 2015-06-25 | Connected |  | No
National Grid | QUINCY | 175453 | 2169 | 120 | Solar | 07_1W2 | 2014-07-15 01:00 | 2014-07-17 | 5 | 0 | 5 | 2014-07-24 | 2014-07-24 | 0 | 0 | 0 | [20 empty] | 2014-08-25 | 2014-07-16 01:00 | 2014-10-31 |  | EXP | [6 empty] | 2014-10-01 | 2014-10-01 | 2015-11-23 | Connected |  | No
National Grid | SHIRLEY | 175452 | 1464 | 2000 | Solar | 01_201W1 | 2014-07-16 01:00 | 2014-07-17 | 4 | 2 | 2 | [10 empty] | 2014-07-23 | 2014-08-20 | 20 | 0 | 20 | [10 empty] | 2014-12-18 | 2014-07-16 01:00 | 2016-02-01 | Yes | STD |  | 2016-04-20 | 2016-08-10 | 77 | 0 | 77 | 2016-08-12 | 2016-08-12 | 2016-08-12 | Connected |  | No
National Grid | SHIRLEY | 175454 | 1464 | 1500 | Solar | 01_227W1 | 2014-07-16 01:00 | 2014-07-17 | 4 | 0 | 4 | [10 empty] | 2014-07-23 | 2014-08-20 | 20 | 0 | 20 | [10 empty] | 2014-12-18 |  | 2016-06-01 | Yes | STD |  | 2017-02-03 | 2017-03-03 | 19 | 0 | 19 | 2017-05-15 | 2017-05-15 | 2017-05-15 | Connected |  | No
National Grid | WORCESTER | 175455 | 1606 | 252 | Solar | 01_14J368 | 2014-07-17 01:00 | 2014-07-21 | 3 | 0 | 3 | 2014-07-24 | 2014-07-24 | 0 | 0 | 0 | [20 empty] | 2014-10-06 |  | 2014-11-28 |  | EXP | [6 empty] | 2014-12-15 | 2014-12-15 | 2016-03-23 | Connected |  | No
National Grid | WORCESTER | 175456 | 1605 | 87 | Solar | 01_24W2 | 2014-07-17 01:00 | 2014-07-21 | 3 | 0 | 3 | 2014-07-24 | 2014-07-24 | 0 | 0 | 0 | [20 empty] | 2014-10-06 |  | 2014-11-28 |  | EXP | [6 empty] | 2014-10-06 | 2014-10-06 | 2016-03-25 | Connected |  | No
National Grid | WORCESTER | 175457 | 1606 | 56 | Solar | 01_24W3 | 2014-07-17 01:00 | 2014-07-21 | 3 | 0 | 3 | 2014-07-24 | 2014-07-24 | 0 | 0 | 0 | [20 empty] | 2014-10-24 |  | 2014-11-28 |  | EXP | [6 empty] | 2014-12-15 | 2014-12-15 | 2016-01-21 | Connected |  | No
National Grid | LOWELL | 175458 | 1852 | 60 | Natural Gas | 14_21L3 | 2014-07-17 01:00 | 2014-07-21 | 3 | 0 | 3 | 2014-07-24 | 2014-07-24 | 0 | 0 | 0 | [20 empty] | 2014-08-22 |  | 2014-10-31 |  | EXP | [6 empty] | 2014-11-04 | 2014-11-04 | 2014-11-10 | Connected |  | No
National Grid | NORTHAMPTON | 175420 | 1060 | 200 | Solar | 09_905W1 | 2014-07-18 01:00 | 2014-07-18 | 570 | 570 | 0 | 2016-11-01 | 2017-06-14 | 153 | 152 | 1 | [21 empty] | 2014-07-21 01:00 | 2017-07-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BARRE | 175451 | 1005 | 480 | Solar | 09_604W1 | 2014-07-21 01:00 | 2014-07-22 | 1 | 0 | 1 | [10 empty] | 2014-07-23 | 2014-08-01 | 7 | 0 | 7 | [10 empty] | 2014-12-22 |  | 2016-12-31 |  | STD | [6 empty] | 2015-11-30 | 2015-11-30 | 2015-12-22 | Connected |  | No
National Grid | MANCHESTER | 175487 | 1944 | 495 | Solar | 12_51T1 | 2014-07-22 01:00 | 2014-07-24 | 7 | 7 | 0 | 2014-08-04 | 2016-10-26 | 554 | 2 | 552 | [20 empty] | 2014-08-28 |  | 2016-01-20 |  | EXP | [6 empty] | 2014-09-15 | 2014-09-15 |  | Withdrawn |  | Yes
National Grid | HAVERHILL | 175488 | 1830 | 100 | Solar | 14_31J1 | 2014-07-23 01:00 | 2014-07-24 | 7 | 7 | 0 | 2014-08-04 | 2014-08-04 | 0 | 0 | 0 | [20 empty] | 2014-09-11 |  | 2014-10-31 |  | EXP | [6 empty] | 2014-12-08 | 2014-12-08 | 2015-04-09 | Connected |  | No
National Grid | MARLBOROUGH | 175489 | 1752 | 16.8 | Solar | 05_317W7 | 2014-07-23 01:00 | 2014-07-24 | 7 | 7 | 0 | 2014-08-04 | 2014-08-04 | 0 | 0 | 0 | [20 empty] | 2014-09-08 |  | 2014-10-31 |  | EXP | [6 empty] | 2014-09-08 | 2014-09-08 | 2015-12-11 | Connected |  | Yes
National Grid | EAST BROOKFIELD | 175494 | 1515 | 480 | Solar | 01_525L2 | 2014-07-23 01:00 | 2014-07-25 | 7 | 0 | 7 | 2014-08-05 | 2014-11-18 | 72 | 0 | 72 | [22 empty] | 2014-12-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTH ADAMS | 175490 | 1247 | 480 | Solar | 09_1015W1 | 2014-07-25 01:00 | 2014-07-28 | 7 | 0 | 7 | 2014-08-06 | 2014-11-18 | 71 | 0 | 71 | [22 empty] | 2015-04-01 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTH ADAMS | 175491 | 1247 | 480 | Solar | 09_1021W2 | 2014-07-25 01:00 | 2014-07-28 | 7 | 0 | 7 | 2014-08-06 | 2014-12-15 | 89 | 0 | 89 | 2014-10-01 | 2014-12-11 | 48 | 0 | 48 | [5 empty] | 2014-10-01 | 2014-12-11 | 48 | 0 | 48 | [6 empty] | 2014-07-25 01:00 | 2015-04-01 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | ANDOVER | 175492 | 1810 | 1800 | Solar | 14_59L5 | 2014-07-25 01:00 | 2014-07-28 | 7 | 0 | 7 | [10 empty] | 2014-08-06 | 2014-09-03 | 19 | 0 | 19 | [10 empty] | 2015-03-13 | 2014-07-25 01:00 | 2016-03-01 | Yes | STD |  | 2015-10-28 | 2017-07-13 | 424 | 0 | 424 | 2017-05-24 | 2017-05-24 | 2017-06-26 | Connected |  | No
National Grid | UXBRIDGE | 175493 | 1569 | 1000 | Solar | 05_321W2 | 2014-07-25 01:00 | 2014-07-28 | 9 | 4 | 5 | [10 empty] | 2014-08-08 | 2014-09-05 | 19 | 0 | 19 | [10 empty] | 2015-05-11 | 2014-07-25 01:00 | 2017-06-30 |  | STD |  | 2016-03-03 | 2017-03-13 | 254 | 0 | 254 | 2017-05-17 | 2017-05-17 | 2017-07-18 | Connected |  | No
National Grid | WESTMINSTER | 175521 | 1473 | 499 | Solar | 01_609W1 | 2014-07-25 01:00 | 2014-07-28 | 7 | 0 | 7 | [10 empty] | 2014-08-06 | 2014-09-04 | 20 | 0 | 20 | [10 empty] | 2015-07-31 | 2014-07-25 01:00 | 2018-03-31 |  | STD |  | 2017-05-09 | 2018-03-19 | 198 | 0 | 198 | 2017-12-05 | 2017-12-05 | 2018-03-19 | Connected |  | No
National Grid | WESTMINSTER | 175522 | 1473 | 499 | Solar | 01_609W1 | 2014-07-25 01:00 | 2014-07-28 | 7 | 0 | 7 | [10 empty] | 2014-08-06 | 2014-09-04 | 20 | 0 | 20 | [10 empty] | 2015-07-31 | 2014-07-25 01:00 | 2018-03-31 |  | STD |  | 2017-05-09 | 2018-03-19 | 198 | 0 | 198 | 2018-02-13 | 2018-02-13 | 2018-03-19 | Connected |  | No
National Grid | WESTMINSTER | 175523 | 1473 | 499 | Solar | 01_609W1 | 2014-07-25 01:00 | 2014-07-28 | 7 | 0 | 7 | [10 empty] | 2014-08-06 | 2014-09-04 | 20 | 0 | 20 | [10 empty] | 2015-07-31 |  | 2018-03-31 |  | STD |  | 2017-05-09 | 2018-03-19 | 198 | 0 | 198 | 2018-02-13 | 2018-02-13 | 2018-03-19 | Connected |  | No
National Grid | NORTH ADAMS | 175528 | 1247 | 480 | Solar | 09_1015W1 | 2014-07-25 01:00 | 2014-07-28 | 7 | 0 | 7 | [10 empty] | 2014-08-06 | 2014-08-29 | 17 | 0 | 17 | [11 empty] | 2014-07-28 01:00 | 2015-04-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SALISBURY | 175524 | 1952 | 500 | Solar | 14_7L4 | 2014-07-28 01:00 | 2014-07-29 | 7 | 0 | 7 | 2014-08-07 | 2014-08-07 | 0 | 0 | 0 | 2014-09-24 | 2014-11-06 | 30 | 0 | 30 | [5 empty] | 2014-09-24 | 2014-11-06 | 30 | 0 | 30 | [5 empty] | 2015-02-06 |  | 2016-12-31 | Yes | EXP |  | 2017-05-30 | 2017-06-24 | 19 | 0 | 19 | 2017-08-01 | 2017-08-01 | 2017-08-04 | Connected |  | No
National Grid | STOCKBRIDGE | 175525 | 1262 | 336 | Solar | 09_1102W1 | 2014-07-28 01:00 | 2014-07-29 | 7 | 2 | 5 | [10 empty] | 2014-08-07 | 2014-08-21 | 10 | 0 | 10 | [10 empty] | 2015-06-24 | 2014-07-29 01:00 | 2016-12-31 |  | STD | [6 empty] | 2015-06-24 | 2015-06-24 |  | Withdrawn |  | No
National Grid | BOXFORD | 175526 | 1921 | 750 | Solar | 14_56L3 | 2014-07-29 01:00 | 2014-07-30 | 6 | 0 | 6 | [5 empty] | 2014-10-21 | 2014-12-01 | 27 | 1 | 26 | 2014-08-07 | 2014-09-05 | 20 | 0 | 20 | 2014-10-21 | 2014-12-01 | 27 | 1 | 26 | [5 empty] | 2015-04-03 | 2014-07-29 01:00 | 2017-09-08 | Yes | STD |  | 2017-02-24 | 2017-09-12 | 138 | 0 | 138 | 2017-08-18 | 2017-08-18 | 2017-09-15 | Connected |  | No
National Grid | NORTON | 175527 | 2766 | 1600 | Solar | 05_4L1 | 2014-07-29 01:00 | 2014-07-30 | 6 | 0 | 6 | [10 empty] | 2014-08-07 | 2014-09-05 | 20 | 0 | 20 | [10 empty] | 2015-03-27 | 2014-07-30 01:00 | 2016-05-01 | Yes | STD |  | 2016-10-13 | 2017-02-28 | 92 | 0 | 92 | 2016-12-29 | 2016-12-29 | 2016-12-29 | Connected |  | No
National Grid | AYER | 175557 | 1432 | 996 | Solar | 01_201W1 | 2014-07-30 01:00 | 2014-07-31 | 6 | 1 | 5 | [5 empty] | 2014-10-01 | 2014-10-13 | 8 | 0 | 8 | 2014-08-08 | 2014-09-10 | 22 | 1 | 21 | 2014-10-01 | 2014-10-13 | 8 | 0 | 8 | [5 empty] | 2015-08-25 |  | 2016-12-10 | Yes | STD |  | 2016-07-07 | 2016-12-20 | 114 | 0 | 114 | 2016-12-07 | 2016-12-07 | 2016-12-21 | Connected |  | No
National Grid | CHARLTON | 175558 | 1507 | 480 | Solar | 01_413L4 | 2014-07-30 01:00 | 2014-07-31 | 7 | 0 | 7 | 2014-08-11 | 2014-12-10 | 83 | 0 | 83 | [22 empty] | 2015-08-03 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 175559 | 1507 | 480 | Solar | 01_413L4 | 2014-07-30 01:00 | 2014-07-31 | 7 | 0 | 7 | 2014-08-11 | 2014-12-10 | 83 | 0 | 83 | [21 empty] | 2014-07-31 01:00 | 2015-06-01 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | FRANKLIN | 175213 | 2038 | 266 | Solar | 05_348W7 | 2014-07-31 01:00 | 2014-08-01 | 7 | 0 | 7 | 2014-08-12 | 2014-08-12 | 0 | 0 | 0 | [20 empty] | 2014-08-19 |  | 2015-01-30 | Yes | EXP | [6 empty] | 2014-12-05 | 2014-12-05 | 2014-12-15 | Connected |  | No
National Grid | ABINGTON | 175560 | 2351 | 996 | Solar | 07_93W42 | 2014-07-31 01:00 | 2014-08-01 | 7 | 0 | 7 | 2014-08-12 | 2015-01-15 | 106 | 0 | 106 | [22 empty] | 2015-06-01 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | ABINGTON | 175561 | 2351 | 996 | Solar | 07_93W42 | 2014-07-31 01:00 | 2014-08-01 | 7 | 0 | 7 | [10 empty] | 2014-08-12 | 2014-09-09 | 19 | 0 | 19 | [12 empty] | 2015-06-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BILLERICA | 175562 | 1821 | 12 | Solar | 14_70L8 | 2014-07-31 01:00 | 2014-08-01 | 7 | 0 | 7 | 2014-08-12 | 2014-08-12 | 0 | 0 | 0 | [20 empty] | 2014-09-02 | 2014-07-31 01:00 | 2014-10-31 |  | EXP | [6 empty] | 2015-02-17 | 2015-02-17 | 2015-05-19 | Connected |  | No
National Grid | RANDOLPH | 175563 | 2368 | 14.8 | Solar | 07_97W2 | 2014-07-31 01:00 | 2014-08-01 | 7 | 0 | 7 | 2014-08-12 | 2014-08-12 | 0 | 0 | 0 | [20 empty] | 2014-09-02 |  | 2014-10-31 | Yes | EXP |  | 2015-10-07 | 2015-10-13 | 3 | 0 | 3 | 2015-10-26 | 2015-10-26 | 2015-10-26 | Connected |  | No
National Grid | UXBRIDGE | 175564 | 1569 | 16 | Solar | 05_320W4 | 2014-07-31 01:00 | 2014-08-01 | 7 | 0 | 7 | 2014-08-12 | 2014-08-12 | 0 | 0 | 0 | [20 empty] | 2014-08-18 |  | 2014-10-31 |  | EXP | [6 empty] | 2014-09-04 | 2014-09-04 | 2015-02-23 | Connected |  | No
National Grid | FRANKLIN | 175592 | 2038 | 266 | Solar | 05_348W7 | 2014-07-31 01:00 | 2014-08-01 | 7 | 0 | 7 | 2014-08-12 | 2014-11-06 | 60 | 0 | 60 | [20 empty] | 2014-08-19 |  | 2014-10-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH QUINCY | 175593 | 2171 | 132 | Solar | 07_4J2 | 2014-07-31 01:00 | 2014-08-01 | 7 | 0 | 7 | 2014-08-12 | 2014-08-12 | 0 | 0 | 0 | [20 empty] | 2014-08-29 |  | 2014-11-28 |  | EXP | [6 empty] | 2015-03-16 | 2015-03-16 | 2015-03-16 | Connected |  | No
National Grid | NORTH QUINCY | 175594 | 2171 | 63 | Solar | 07_1W8 | 2014-07-31 01:00 | 2014-08-01 | 7 | 0 | 7 | 2014-08-12 | 2014-08-12 | 0 | 0 | 0 | [20 empty] | 2014-08-29 | 2014-08-01 01:00 | 2014-10-31 |  | EXP | [6 empty] | 2016-03-14 | 2016-03-14 | 2016-03-14 | Connected |  | No
National Grid | STURBRIDGE | 175595 | 1566 | 996 | Solar | 01_413L2 | 2014-08-01 01:00 | 2014-08-04 | 6 | 0 | 6 | [10 empty] | 2014-08-12 | 2014-09-09 | 19 | 0 | 19 | [10 empty] | 2015-04-27 |  | 2016-04-01 | Yes | STD |  | 2016-05-24 | 2016-06-28 | 23 | 0 | 23 | 2016-06-27 | 2016-06-27 | 2016-06-30 | Connected |  | No
National Grid | STURBRIDGE | 175596 | 1566 | 480 | Solar | 01_413L2 | 2014-08-01 01:00 | 2014-08-04 | 6 | 0 | 6 | 2014-08-12 | 2014-10-02 | 36 | 0 | 36 | [21 empty] | 2014-08-01 01:00 | 2015-06-15 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 175597 | 2301 | 998 | Solar | 07_94W41 | 2014-08-01 01:00 | 2014-08-04 | 6 | 0 | 6 | [10 empty] | 2014-08-12 | 2014-08-29 | 13 | 0 | 13 | [10 empty] | 2015-03-30 |  | 2016-01-20 | Yes | STD |  | 2016-09-14 | 2017-01-17 | 83 | 0 | 83 | 2017-04-05 | 2017-04-05 | 2017-04-05 | Connected |  | No
National Grid | CHARLTON | 175598 | 1507 | 772.8 | Solar | 01_406L1 | 2014-08-01 01:00 | 2014-08-04 | 15 | 10 | 5 | [10 empty] | 2014-08-25 | 2014-09-22 | 19 | 0 | 19 | [10 empty] | 2014-12-23 |  | 2016-12-31 |  | STD | [6 empty] | 2016-06-20 | 2016-06-20 | 2016-07-20 | Connected |  | No
National Grid | QUINCY | 175599 | 2169 | 72 | Solar | 07_1W8 | 2014-08-01 01:00 | 2014-08-04 | 6 | 0 | 6 | 2014-08-12 | 2017-02-06 | 616 | 0 | 616 | [20 empty] | 2014-08-29 | 2014-08-04 01:00 | 2014-11-28 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHARLTON | 175600 | 1507 | 1000 | Solar | 01_413L4 | 2014-08-04 01:00 | 2014-08-05 | 8 | 0 | 8 | [10 empty] | 2014-08-15 | 2014-09-15 | 20 | 0 | 20 | [10 empty] | 2015-11-23 | 2014-08-05 01:00 | 2018-07-30 | Yes | STD |  | 2016-11-28 | 2017-03-28 | 82 | 0 | 82 |  |  | 2018-07-20 | Connected |  | No
National Grid | WARREN | 175626 | 1083 | 990 | Solar | 09_516L3 | 2014-08-05 01:00 | 2014-08-07 | 6 | 0 | 6 | [10 empty] | 2014-08-15 | 2014-09-15 | 20 | 0 | 20 | [5 empty] | 2016-10-18 | 2016-12-14 | 39 | 0 | 39 | 2015-04-01 |  | 2017-05-03 | Yes | STD |  | 2016-10-18 | 2017-05-02 | 133 | 0 | 133 | 2017-04-21 | 2017-04-21 | 2017-05-03 | Connected |  | Yes
National Grid | NORTH BROOKFIELD | 175629 | 1535 | 120 | Solar | 01_525L1 | 2014-08-06 01:00 | 2014-08-07 | 7 | 0 | 7 | 2014-08-18 | 2014-08-18 | 0 | 0 | 0 | [20 empty] | 2014-09-17 |  | 2015-01-30 |  | EXP | [6 empty] | 2014-09-17 | 2014-09-17 | 2015-02-20 | Connected |  | No
National Grid | QUINCY | 175633 | 2169 | 120 | Solar | 07_1W6 | 2014-08-06 01:00 | 2014-08-07 | 36 | 31 | 5 | 2014-09-29 | 2014-09-29 | 0 | 0 | 0 | [20 empty] | 2014-10-08 | 2014-08-07 01:00 | 2014-12-31 |  | EXP | [6 empty] | 2015-01-20 | 2015-01-20 | 2015-01-29 | Connected |  | No
National Grid | SHIRLEY | 175662 | 1464 | 996 | Solar | 01_227W3 | 2014-08-07 01:00 | 2014-08-08 | 8 | 4 | 4 | [10 empty] | 2014-08-20 | 2014-09-19 | 21 | 0 | 21 | [10 empty] | 2015-04-20 | 2014-08-08 01:00 | 2016-06-15 | Yes | STD |  | 2015-11-03 | 2016-01-30 | 59 | 0 | 59 | 2015-12-31 | 2015-12-31 | 2015-12-31 | Connected |  | No
National Grid | OXFORD | 175665 | 1540 | 996 | Solar | 01_406L2 | 2014-08-08 01:00 | 2014-08-11 | 5 | 0 | 5 | [10 empty] | 2014-08-18 | 2014-08-18 | 0 | 0 | 0 | [10 empty] | 2014-12-18 | 2014-08-08 01:00 | 2016-07-29 |  | STD | [8 empty] | 2016-11-23 | Connected |  | No
National Grid | OXFORD | 175666 | 1540 | 996 | Solar | 01_406L2 | 2014-08-08 01:00 | 2014-08-11 | 5 | 0 | 5 | [10 empty] | 2014-08-18 | 2014-08-18 | 0 | 0 | 0 | [10 empty] | 2014-12-18 | 2014-08-08 01:00 | 2016-07-29 |  | STD | [8 empty] | 2016-11-23 | Connected |  | No
National Grid | OXFORD | 175667 | 1540 | 470 | Solar | 01_406L2 | 2014-08-08 01:00 | 2014-08-11 | 5 | 0 | 5 | [10 empty] | 2014-08-18 | 2014-08-18 | 0 | 0 | 0 | [10 empty] | 2014-12-18 |  | 2016-07-29 |  | STD | [8 empty] | 2016-11-23 | Connected |  | No
National Grid | PLAINVILLE | 178780 | 2762 | 19.995 | Solar | 05_3451W3 | 2014-08-08 01:00 | 2014-08-11 | 7 | 1 | 6 | 2014-08-20 | 2014-08-20 | 0 | 0 | 0 | [20 empty] | 2014-09-04 |  | 2014-11-28 |  | EXP | [6 empty] | 2014-09-04 | 2014-09-04 | 2014-11-06 | Connected |  | No
National Grid | BRIMFIELD | 175628 | 1010 | 1000 | Solar | 01_408L2 | 2014-08-11 01:00 | 2014-08-12 | 37 | 36 | 1 | [10 empty] | 2014-10-03 | 2014-10-29 | 17 | 0 | 17 | [11 empty] | 2014-08-11 01:00 | 2015-05-29 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | STURBRIDGE | 175664 | 1566 | 996 | Solar | 01_413L2 | 2014-08-11 01:00 | 2014-08-12 | 6 | 0 | 6 | [10 empty] | 2014-08-20 | 2014-09-09 | 13 | 0 | 13 | [10 empty] | 2015-04-27 | 2014-08-11 01:00 | 2016-03-15 | Yes | STD |  | 2016-05-24 | 2016-06-28 | 23 | 0 | 23 | 2016-06-27 | 2016-06-27 | 2016-06-30 | Connected |  | No
National Grid | HOPEDALE | 175733 | 1747 | 1000 | Solar | 05_335W1 | 2014-08-11 01:00 | 2014-08-12 | 7 | 0 | 7 | [10 empty] | 2014-08-21 | 2014-09-09 | 12 | 0 | 12 | [10 empty] | 2015-02-18 | 2014-08-11 01:00 | 2017-07-31 | Yes | STD |  | 2017-05-17 | 2017-07-27 | 49 | 0 | 49 | 2017-08-04 | 2017-08-04 | 2017-08-08 | Connected |  | No
National Grid | NEW SALEM | 175734 | 1355 | 576 | Solar | 09_702W3 | 2014-08-11 01:00 | 2014-08-12 | 7 | 0 | 7 | [10 empty] | 2014-08-21 | 2014-09-19 | 20 | 0 | 20 | [10 empty] | 2015-04-21 |  | 2018-01-31 | Yes | STD | [6 empty] | 2018-04-04 | 2018-04-04 | 2018-05-31 | Connected |  | No
National Grid | BRIMFIELD | 175735 | 1010 | 500 | Solar | 01_408L2 | 2014-08-11 01:00 | 2014-08-12 | 7 | 0 | 7 | [10 empty] | 2014-08-21 | 2014-09-19 | 20 | 0 | 20 | [10 empty] | 2015-04-21 |  | 2016-05-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MONSON | 175737 | 1057 | 5350 | Solar | 09_0504 | 2014-08-11 01:00 | 2014-08-12 | 8 | 0 | 8 | [10 empty] | 2014-08-22 | 2014-09-23 | 21 | 0 | 21 | [10 empty] | 2015-04-01 | 2014-08-11 01:00 | 2016-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MONSON | 175738 | 1057 | 4280 | Solar | 09_503L2 | 2014-08-11 01:00 | 2014-08-12 | 8 | 0 | 8 | [10 empty] | 2014-08-22 | 2014-09-23 | 21 | 0 | 21 | [10 empty] | 2015-04-01 | 2014-08-12 01:00 | 2017-12-31 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | SPENCER | 175669 | 1562 | 1000 | Solar | 01_55K11 | 2014-08-12 01:00 | 2014-08-13 | 5 | 0 | 5 | [10 empty] | 2014-08-20 | 2014-08-26 | 4 | 0 | 4 | [5 empty] | 2015-02-24 | 2016-06-24 | 331 | 0 | 331 | 2016-06-24 | 2014-08-12 01:00 | 2016-01-28 |  | STD | [8 empty] | 2016-11-28 | Connected |  | No
National Grid | SPENCER | 175697 | 1562 | 2000 | Solar | 01_55K11 | 2014-08-12 01:00 | 2014-08-13 | 5 | 0 | 5 | [10 empty] | 2014-08-20 | 2014-08-26 | 4 | 0 | 4 | [5 empty] | 2015-02-24 | 2016-06-24 | 331 | 0 | 331 | 2016-06-24 | 2014-08-12 01:00 | 2016-01-28 |  | STD | [8 empty] | 2016-11-28 | Connected |  | No
National Grid | SPENCER | 175698 | 1562 | 393 | Solar | 01_55K11 | 2014-08-12 01:00 | 2014-08-13 | 5 | 0 | 5 | [10 empty] | 2014-08-20 | 2014-08-26 | 4 | 0 | 4 | [5 empty] | 2015-02-24 | 2016-06-24 | 331 | 0 | 331 | 2016-06-24 | 2014-08-12 01:00 | 2016-01-28 |  | STD | [8 empty] | 2016-12-12 | Connected |  | No
National Grid | SPENCER | 175699 | 1562 | 629 | Solar | 01_55K11 | 2014-08-12 01:00 | 2014-08-13 | 5 | 0 | 5 | [10 empty] | 2014-08-20 | 2014-08-26 | 4 | 0 | 4 | [5 empty] | 2015-02-24 | 2016-06-24 | 331 | 0 | 331 | 2016-06-24 | 2014-08-12 01:00 | 2016-01-28 |  | STD | [8 empty] | 2016-12-12 | Connected |  | No
National Grid | SPENCER | 175700 | 1562 | 860 | Solar | 01_55K11 | 2014-08-12 01:00 | 2014-08-13 | 5 | 0 | 5 | [10 empty] | 2014-08-20 | 2014-08-26 | 4 | 0 | 4 | [5 empty] | 2015-02-24 | 2016-06-24 | 331 | 0 | 331 | 2016-06-24 | 2014-08-12 01:00 | 2016-02-03 |  | STD | [8 empty] | 2016-11-28 | Connected |  | No
National Grid | SPENCER | 175701 | 1562 | 2000 | Solar | 01_55K11 | 2014-08-12 01:00 | 2014-08-13 | 5 | 0 | 5 | [10 empty] | 2014-08-20 | 2014-08-26 | 4 | 0 | 4 | [5 empty] | 2015-02-24 | 2016-06-24 | 331 | 0 | 331 | 2016-06-24 | 2014-08-12 01:00 | 2016-01-28 |  | STD | [8 empty] | 2016-11-28 | Connected |  | No
National Grid | SPENCER | 175702 | 1562 | 2000 | Solar | 01_55K11 | 2014-08-12 01:00 | 2014-08-13 | 5 | 0 | 5 | [10 empty] | 2014-08-20 | 2014-08-26 | 4 | 0 | 4 | [5 empty] | 2015-02-24 | 2016-06-24 | 331 | 0 | 331 | 2016-06-24 | 2014-08-12 01:00 | 2016-01-28 |  | STD | [8 empty] | 2016-11-28 | Connected |  | No
National Grid | SPENCER | 175703 | 1562 | 1400 | Solar | 01_55K11 | 2014-08-12 01:00 | 2014-08-13 | 5 | 0 | 5 | [10 empty] | 2014-08-20 | 2014-08-26 | 4 | 0 | 4 | [5 empty] | 2015-02-24 | 2016-06-24 | 331 | 0 | 331 | 2016-06-24 | 2014-08-12 01:00 | 2016-01-28 |  | STD | [8 empty] | 2016-11-28 | Connected |  | No
National Grid | SPENCER | 175704 | 1562 | 1750 | Solar | 01_55K11 | 2014-08-12 01:00 | 2014-08-13 | 5 | 0 | 5 | [10 empty] | 2014-08-20 | 2014-08-26 | 4 | 0 | 4 | [5 empty] | 2015-02-24 | 2016-06-24 | 331 | 0 | 331 | 2016-06-24 | 2014-08-14 01:00 | 2016-01-28 |  | STD | [6 empty] | 2016-11-28 | 2016-11-28 | 2016-11-28 | Connected |  | No
National Grid | LEOMINSTER | 175736 | 1453 | 27 | Solar | 01_225W4 | 2014-08-14 01:00 | 2014-08-15 | 7 | 0 | 7 | 2014-08-26 | 2014-08-26 | 0 | 0 | 0 | [20 empty] | 2014-10-01 |  | 2014-11-28 | Yes | EXP |  | 2014-12-10 | 2014-12-23 | 9 | 0 | 9 | 2014-10-06 | 2014-10-06 | 2015-01-12 | Connected |  | No
National Grid | MILLBURY | 175739 | 1527 | 100 | Solar | 01_328W2 | 2014-08-14 01:00 | 2014-08-15 | 7 | 1 | 6 | 2014-08-26 | 2015-02-18 | 118 | 32 | 86 | [20 empty] | 2015-01-14 |  | 2014-12-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | OXFORD | 175721 | 1540 | 100 | Solar | 01_406L4 | 2014-08-15 01:00 | 2014-08-18 | 6 | 0 | 6 | 2014-08-26 | 2014-08-26 | 0 | 0 | 0 | [20 empty] | 2014-10-06 |  | 2015-01-03 |  | EXP | [6 empty] | 2014-12-26 | 2014-12-26 | 2015-01-20 | Connected |  | Yes
National Grid | OXFORD | 175770 | 1540 | 100 | Solar | 01_406L4 | 2014-08-15 01:00 | 2014-08-18 | 6 | 0 | 6 | 2014-08-26 | 2015-01-15 | 96 | 0 | 96 | [20 empty] | 2014-10-06 |  | 2014-12-31 |  | EXP | [6 empty] | 2014-12-26 | 2014-12-26 |  | Withdrawn |  | Yes
National Grid | SCITUATE | 175771 | 2066 | 196 | Solar | 07_915W37 | 2014-08-15 01:00 | 2014-08-18 | 6 | 1 | 5 | 2014-08-26 | 2014-08-26 | 0 | 0 | 0 | [20 empty] | 2014-09-16 |  | 2014-12-31 |  | EXP | [6 empty] | 2014-12-19 | 2014-12-19 | 2014-12-19 | Connected |  | No
National Grid | HUBBARDSTON | 175772 | 1452 | 480 | Solar | 01_609W1 | 2014-08-15 01:00 | 2014-08-18 | 6 | 0 | 6 | 2014-08-26 | 2014-11-18 | 57 | 0 | 57 | [22 empty] | 2015-01-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | HUBBARDSTON | 175773 | 1452 | 480 | Solar | 01_609W1 | 2014-08-15 01:00 | 2014-08-18 | 6 | 0 | 6 | 2014-08-26 | 2014-11-18 | 57 | 0 | 57 | [21 empty] | 2014-08-15 01:00 | 2015-01-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | PEPPERELL | 175774 | 1463 | 990 | Solar | 01_226L1 | 2014-08-15 01:00 | 2014-08-18 | 6 | 0 | 6 | [10 empty] | 2014-08-26 | 2014-09-25 | 21 | 0 | 21 | [5 empty] | 2015-10-08 | 2015-10-28 | 13 | 13 | 0 | 2015-12-11 |  | 2016-07-30 | Yes | STD |  | 2016-04-06 | 2016-07-28 | 77 | 0 | 77 | 2016-07-21 | 2016-07-21 | 2016-07-28 | Connected |  | No
National Grid | TYNGSBORO | 175775 | 1879 | 60 | Solar | 14_211L1 | 2014-08-15 01:00 | 2014-08-18 | 7 | 0 | 7 | 2014-08-27 | 2014-08-27 | 0 | 0 | 0 | [20 empty] | 2014-09-19 | 2014-08-20 01:00 | 2014-11-28 |  | EXP | [6 empty] | 2014-09-19 | 2014-09-19 | 2014-11-24 | Connected |  | No
National Grid | BARRE | 175238 | 1005 | 480 | Solar | 09_604W3 | 2014-08-20 01:00 | 2014-08-21 | 7 | 0 | 7 | 2014-09-02 | 2014-09-02 | 0 | 0 | 0 | 2014-10-21 | 2014-11-24 | 23 | 0 | 23 | [5 empty] | 2014-10-21 | 2014-11-24 | 23 | 0 | 23 | [5 empty] | 2014-12-24 |  | 2015-11-15 | Yes | EXP |  | 2015-09-08 | 2015-11-12 | 45 | 0 | 45 | 2015-11-06 | 2015-11-06 | 2015-11-16 | Connected |  | No
National Grid | FALL RIVER | 175777 | 2720 | 85 | Solar | 05_106W45 | 2014-08-20 01:00 | 2014-08-21 | 7 | 3 | 4 | 2014-09-02 | 2014-09-02 | 0 | 0 | 0 | [20 empty] | 2014-09-10 | 2014-08-20 01:00 | 2014-12-31 |  | EXP | [6 empty] | 2014-09-15 | 2014-09-15 | 2014-12-04 | Connected |  | No
National Grid | WESTMINSTER | 175778 | 1473 | 480 | Solar | 01_602W3 | 2014-08-20 01:00 | 2014-08-21 | 7 | 0 | 7 | 2014-09-02 | 2014-09-02 | 0 | 0 | 0 | 2014-10-21 | 2014-11-26 | 25 | 0 | 25 | [5 empty] | 2014-10-21 | 2014-11-26 | 25 | 0 | 25 | [5 empty] | 2014-12-31 |  | 2015-09-01 | Yes | EXP |  | 2015-09-18 | 2015-11-03 | 31 | 0 | 31 | 2015-10-23 | 2015-10-23 | 2015-11-16 | Connected |  | No
National Grid | ANDOVER | 175240 | 1810 | 15.2 | Solar | 14_59L1 | 2014-08-21 01:00 | 2014-08-22 | 7 | 0 | 7 | 2014-09-03 | 2014-09-03 | 0 | 0 | 0 | [20 empty] | 2014-09-18 |  | 2014-11-28 |  | EXP | [6 empty] | 2014-09-18 | 2014-09-18 | 2014-12-08 | Connected |  | No
National Grid | UXBRIDGE | 175241 | 1569 | 20 | Solar | 05_321W2 | 2014-08-22 01:00 | 2014-08-25 | 5 | 0 | 5 | 2014-09-02 | 2014-09-02 | 0 | 0 | 0 | [20 empty] | 2014-09-18 |  | 2014-11-28 |  | EXP | [6 empty] | 2014-09-18 | 2014-09-18 | 2015-04-24 | Connected |  | No
National Grid | STOUGHTON | 175242 | 2072 | 75 | Solar | 07_94W44 | 2014-08-25 01:00 | 2014-08-26 | 5 | 0 | 5 | 2014-09-03 | 2014-09-03 | 0 | 0 | 0 | [20 empty] | 2014-09-18 | 2014-08-25 01:00 | 2014-12-31 |  | EXP | [6 empty] | 2014-09-18 | 2014-09-18 | 2014-11-17 | Connected |  | No
National Grid | CHARLTON | 175243 | 1507 | 17 | Solar | 01_415L2 | 2014-08-25 01:00 | 2014-08-26 | 7 | 0 | 7 | 2014-09-05 | 2014-09-05 | 0 | 0 | 0 | [20 empty] | 2014-10-01 | 2014-08-27 01:00 | 2014-12-10 | Yes | EXP |  | 2015-01-14 | 2015-01-06 | 0 | 0 | 0 | 2015-01-13 | 2015-01-13 | 2015-03-06 | Connected |  | No
National Grid | LEICESTER | 175244 | 1524 | 684 | Solar | 01_21W2 | 2014-08-27 01:00 | 2014-08-28 | 7 | 0 | 7 | [10 empty] | 2014-09-09 | 2014-10-06 | 19 | 0 | 19 | [10 empty] | 2015-05-05 |  | 2016-06-30 |  | STD |  | 2016-02-19 | 2016-06-28 | 88 | 0 | 88 | 2016-06-22 | 2016-06-22 | 2016-06-29 | Connected |  | No
National Grid | WRENTHAM | 178775 | 2093 | 170 | Solar | 05_3424W1 | 2014-08-27 01:00 | 2014-08-28 | 7 | 0 | 7 | 2014-09-09 | 2014-09-09 | 0 | 0 | 0 | [20 empty] | 2014-10-02 | 2014-08-28 01:00 | 2014-11-28 |  | EXP | [6 empty] | 2015-01-02 | 2015-01-02 | 2016-02-22 | Connected |  | Yes
National Grid | DUDLEY | 175245 | 1571 | 1000 | Solar | 01_413L3 | 2014-08-28 01:00 | 2014-08-29 | 6 | 6 | 0 | [10 empty] | 2014-09-09 | 2014-10-07 | 21 | 21 | 0 | [5 empty] | 2017-01-20 | 2017-02-17 | 20 | 0 | 20 | 2017-07-11 |  | 2018-07-31 | Yes | STD |  | 2017-12-27 | 2018-05-08 | 132 | 0 | 132 | 2018-06-11 | 2018-06-11 | 2018-07-18 | Connected |  | No
National Grid | SAUGUS | 175273 | 1906 | 42.57 | Solar | 12_19W2 | 2014-08-28 01:00 | 2014-08-29 | 6 | 5 | 1 | 2014-09-09 | 2014-09-09 | 0 | 0 | 0 | [20 empty] | 2014-09-18 |  | 2014-11-28 |  | EXP | [6 empty] | 2014-09-18 | 2014-09-18 | 2015-05-29 | Connected |  | No
National Grid | MARLBOROUGH | 175274 | 1752 | 42.57 | Solar | 05_310W5 | 2014-08-28 01:00 | 2014-08-29 | 6 | 0 | 6 | 2014-09-09 | 2014-09-09 | 0 | 0 | 0 | [20 empty] | 2014-09-18 |  | 2014-11-28 |  | EXP | [6 empty] | 2014-09-18 | 2014-09-18 | 2015-04-30 | Connected |  | No
National Grid | BROCKTON | 175275 | 2302 | 42.57 | Solar | 07_91W47 | 2014-08-28 01:00 | 2014-08-29 | 6 | 0 | 6 | 2014-09-09 | 2014-09-09 | 0 | 0 | 0 | [20 empty] | 2014-09-19 |  | 2014-11-28 |  | EXP | [6 empty] | 2014-09-19 | 2014-09-19 | 2015-04-30 | Connected |  | No
National Grid | HOLBROOK | 175276 | 2343 | 42.57 | Solar | 07_2W1 | 2014-08-28 01:00 | 2014-08-29 | 6 | 0 | 6 | 2014-09-09 | 2014-09-09 | 0 | 0 | 0 | [20 empty] | 2014-09-23 |  | 2014-11-28 |  | EXP | [6 empty] | 2014-09-22 | 2014-09-22 | 2015-05-05 | Connected |  | No
National Grid | WEYMOUTH | 175277 | 2188 | 42.57 | Solar | 07_12W2 | 2014-08-28 01:00 | 2014-08-29 | 6 | 0 | 6 | 2014-09-09 | 2014-09-09 | 0 | 0 | 0 | [20 empty] | 2014-09-19 |  | 2014-11-28 |  | EXP | [6 empty] | 2014-09-22 | 2014-09-22 | 2015-05-01 | Connected |  | No
National Grid | EAST LONGMEADOW | 175278 | 1028 | 30.42 | Solar | 09_508L5 | 2014-08-28 01:00 | 2014-08-29 | 6 | 0 | 6 | 2014-09-09 | 2014-09-09 | 0 | 0 | 0 | [20 empty] | 2014-09-22 |  | 2014-11-28 |  | EXP | [6 empty] | 2014-09-22 | 2014-09-22 | 2015-04-30 | Connected |  | No
National Grid | WEYMOUTH | 175279 | 2190 | 42.57 | Solar | 07_2W2 | 2014-08-28 01:00 | 2014-08-29 | 6 | 0 | 6 | 2014-09-09 | 2014-09-09 | 0 | 0 | 0 | [20 empty] | 2014-09-22 |  | 2014-11-28 |  | EXP | [6 empty] | 2014-09-22 | 2014-09-22 | 2015-05-01 | Connected |  | No
National Grid | WHITMAN | 175280 | 2382 | 42.57 | Solar | 07_797W29 | 2014-08-28 01:00 | 2014-08-29 | 6 | 0 | 6 | 2014-09-09 | 2014-09-09 | 0 | 0 | 0 | [20 empty] | 2014-09-22 |  | 2014-11-28 |  | EXP | [6 empty] | 2014-09-22 | 2014-09-22 | 2015-05-04 | Connected |  | No
National Grid | SOUTHBOROUGH | 175281 | 1772 | 42.57 | Solar | 05_310W6 | 2014-08-28 01:00 | 2014-08-29 | 6 | 0 | 6 | 2014-09-09 | 2014-09-09 | 0 | 0 | 0 | [20 empty] | 2014-09-22 |  | 2014-11-28 |  | EXP | [6 empty] | 2014-09-22 | 2014-09-22 | 2015-04-30 | Connected |  | No
National Grid | WORCESTER | 175282 | 1605 | 42.57 | Solar | 01_15J392 | 2014-08-28 01:00 | 2014-08-29 | 6 | 0 | 6 | 2014-09-09 | 2014-09-09 | 0 | 0 | 0 | [20 empty] | 2014-09-22 |  | 2014-11-28 |  | EXP | [6 empty] | 2014-09-22 | 2014-09-22 | 2015-05-05 | Connected |  | No
National Grid | WORCESTER | 175283 | 1604 | 42.57 | Solar | 01_9J337 | 2014-08-28 01:00 | 2014-08-29 | 6 | 0 | 6 | 2014-09-09 | 2014-09-09 | 0 | 0 | 0 | [20 empty] | 2014-09-22 |  | 2014-11-28 |  | EXP | [6 empty] | 2014-09-22 | 2014-09-22 | 2015-05-04 | Connected |  | No
National Grid | LANCASTER | 175313 | 1523 | 587.2 | Solar | 01_227W1 | 2014-08-28 01:00 | 2014-08-29 | 7 | 0 | 7 | [10 empty] | 2014-09-10 | 2014-10-09 | 21 | 0 | 21 | [12 empty] | 2015-01-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LANCASTER | 175314 | 1523 | 594.4 | Solar | 01_227W1 | 2014-08-28 01:00 | 2014-08-29 | 7 | 0 | 7 | [10 empty] | 2014-09-10 | 2014-10-09 | 21 | 0 | 21 | [11 empty] | 2014-08-29 01:00 | 2015-01-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SHEFFIELD | 175315 | 1257 | 499 | Solar | 09_1109W2 | 2014-08-29 01:00 | 2014-09-02 | 6 | 0 | 6 | 2014-09-10 | 2014-09-10 | 0 | 0 | 0 | [20 empty] | 2014-10-22 |  | 2016-06-01 | Yes | EXP |  | 2016-06-14 | 2016-10-19 | 87 | 0 | 87 | 2016-07-06 | 2016-07-06 | 2016-10-26 | Connected |  | No
National Grid | BEVERLY | 175316 | 1915 | 6.45 | Solar | 12_12L2 | 2014-08-29 01:00 | 2014-09-02 | 6 | 0 | 6 | 2014-09-10 | 2014-09-10 | 0 | 0 | 0 | [20 empty] | 2014-10-07 |  | 2014-11-28 |  | EXP | [6 empty] | 2014-10-07 | 2014-10-07 | 2015-04-27 | Connected |  | No
National Grid | ABINGTON | 175317 | 2351 | 417.6 | Solar | 07_93W41 | 2014-08-29 01:00 | 2014-09-02 | 6 | 0 | 6 | 2014-09-10 | 2014-09-10 | 0 | 0 | 0 | [20 empty] | 2014-11-05 |  | 2014-12-31 |  | EXP | [6 empty] | 2014-12-24 | 2014-12-24 | 2014-12-31 | Connected |  | Yes
National Grid | HANOVER | 175318 | 2339 | 440.8 | Solar | 07_95W1 | 2014-08-29 01:00 | 2014-09-02 | 6 | 0 | 6 | 2014-09-10 | 2014-09-10 | 0 | 0 | 0 | [20 empty] | 2014-11-05 |  | 2014-12-31 |  | EXP | [6 empty] | 2015-01-05 | 2015-01-05 | 2014-12-31 | Connected |  | No
National Grid | MARLBOROUGH | 175319 | 1752 | 440.8 | Solar | 05_311W5 | 2014-08-29 01:00 | 2014-09-02 | 6 | 2 | 4 | 2014-09-10 | 2014-09-10 | 0 | 0 | 0 | [20 empty] | 2014-11-05 |  | 2014-12-31 |  | EXP | [6 empty] | 2014-12-23 | 2014-12-23 | 2014-12-31 | Connected |  | No
National Grid | REVERE | 175320 | 2151 | 417.6 | Solar | 12_7W4 | 2014-08-29 01:00 | 2014-09-02 | 6 | 0 | 6 | 2014-09-10 | 2014-09-10 | 0 | 0 | 0 | [20 empty] | 2014-11-05 |  | 2014-12-31 |  | EXP | [6 empty] | 2014-12-23 | 2014-12-23 | 2014-12-31 | Connected |  | No
National Grid | SOUTH EASTON | 175321 | 2375 | 440.8 | Solar | 07_92W79 | 2014-08-29 01:00 | 2014-09-02 | 6 | 0 | 6 | 2014-09-10 | 2015-11-24 | 299 | 0 | 299 | [22 empty] | 2014-12-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MILFORD | 175322 | 1757 | 301.6 | Solar | 05_336W4 | 2014-08-29 01:00 | 2014-09-02 | 6 | 0 | 6 | 2014-09-10 | 2014-09-10 | 0 | 0 | 0 | [20 empty] | 2014-11-05 |  | 2014-12-31 |  | EXP | [6 empty] | 2014-12-23 | 2014-12-23 | 2014-12-31 | Connected |  | No
National Grid | STOUGHTON | 175351 | 2072 | 440.8 | Solar | 07_913W17 | 2014-08-29 01:00 | 2014-09-02 | 6 | 0 | 6 | 2014-09-10 | 2014-09-10 | 0 | 0 | 0 | [20 empty] | 2014-11-05 |  | 2014-12-31 |  | EXP | [6 empty] | 2014-12-23 | 2014-12-23 | 2014-12-31 | Connected |  | Yes
National Grid | BRIDGEWATER | 175352 | 2324 | 499 | Solar | 07_912W73 | 2014-08-29 01:00 | 2014-09-02 | 6 | 0 | 6 | [26 empty] | 2014-08-29 01:00 | 2015-11-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | ADAMS | 175353 | 1220 | 996.8 | Solar | 09_1021W1 | 2014-08-29 01:00 | 2014-09-02 | 6 | 0 | 6 | [10 empty] | 2014-09-10 | 2014-10-09 | 21 | 0 | 21 | [10 empty] | 2015-03-12 |  | 2014-12-31 | Yes | STD |  | 2015-08-25 | 2015-11-23 | 61 | 0 | 61 | 2015-11-25 | 2015-11-25 | 2015-11-25 | Connected |  | No
National Grid | ATTLEBORO | 175284 | 2703 | 30.96 | Solar | 05_8L3 | 2014-09-02 01:00 | 2014-09-03 | 4 | 0 | 4 | 2014-09-09 | 2014-09-09 | 0 | 0 | 0 | [20 empty] | 2014-09-22 |  | 2014-11-28 |  | EXP | [6 empty] | 2014-09-22 | 2014-09-22 | 2015-08-20 | Connected |  | No
National Grid | HARVARD | 175355 | 1451 | 200 | Solar | 01_201W2 | 2014-09-05 01:00 | 2014-09-08 | 7 | 0 | 7 | 2014-09-17 | 2014-09-17 | 0 | 0 | 0 | [20 empty] | 2014-10-22 |  | 2014-12-31 |  | EXP | [6 empty] | 2014-12-17 | 2014-12-17 | 2014-12-18 | Connected |  | No
National Grid | MARLBOROUGH | 175356 | 1752 | 1200 | Bio Gas | 05_317W1 | 2014-09-05 01:00 | 2014-09-08 | 9 | 4 | 5 | [10 empty] | 2014-09-19 | 2014-10-20 | 20 | 0 | 20 | [10 empty] | 2014-12-24 |  | 2016-12-31 |  | STD | [6 empty] | 2015-12-22 | 2015-12-22 | 2015-12-22 | Connected |  | No
National Grid | TEWKSBURY | 175357 | 1876 | 30 | Solar | 14_59L5 | 2014-09-08 01:00 | 2014-09-09 | 17 | 14 | 3 | 2014-10-02 | 2014-10-02 | 0 | 0 | 0 | [20 empty] | 2014-10-06 | 2014-09-09 01:00 | 2015-01-30 |  | EXP | [6 empty] | 2014-10-06 | 2014-10-06 | 2015-08-20 | Connected |  | No
National Grid | WORCESTER | 175354 | 1602 | 2100 | Solar | 01_8W1 | 2014-09-09 01:00 | 2014-09-10 | 8 | 0 | 8 | [10 empty] | 2014-09-22 | 2014-10-17 | 18 | 0 | 18 | [10 empty] | 2015-06-01 |  | 2016-12-31 | Yes | STD |  | 2016-12-28 | 2017-09-09 | 176 | 0 | 176 | 2017-05-17 | 2017-05-17 | 2017-05-17 | Connected |  | No
National Grid | MELROSE | 175387 | 2176 | 90 | Solar | 12_25W5 | 2014-09-10 01:00 | 2014-09-11 | 7 | 0 | 7 | 2014-09-22 | 2014-09-22 | 0 | 0 | 0 | [20 empty] | 2014-10-08 |  | 2014-12-15 |  | EXP | [6 empty] | 2014-12-30 | 2014-12-30 | 2015-01-15 | Connected |  | No
National Grid | BOXFORD | 175388 | 1921 | 15.2 | Solar | 14_56L3 | 2014-09-10 01:00 | 2014-09-11 | 7 | 0 | 7 | 2014-09-22 | 2014-09-22 | 0 | 0 | 0 | [20 empty] | 2014-10-08 |  | 2014-12-01 |  | EXP | [6 empty] | 2014-10-08 | 2014-10-08 | 2014-12-26 | Connected |  | No
National Grid | NEWBURYPORT | 175389 | 1950 | 100 | Solar | 14_60L4 | 2014-09-11 01:00 | 2014-09-12 | 7 | 0 | 7 | 2014-09-23 | 2014-09-23 | 0 | 0 | 0 | [20 empty] | 2014-10-09 | 2014-09-11 01:00 | 2014-12-19 |  | EXP | [6 empty] | 2015-02-05 | 2015-02-05 | 2015-02-18 | Connected |  | No
National Grid | UXBRIDGE | 175390 | 1569 | 728 | Solar | 05_321W2 | 2014-09-11 01:00 | 2014-09-12 | 7 | 6 | 1 | [10 empty] | 2014-09-23 | 2014-10-20 | 18 | 0 | 18 | [10 empty] | 2015-03-23 |  | 2016-01-26 |  | STD | [6 empty] | 2016-07-19 | 2016-07-19 | 2016-06-17 | Connected |  | No
National Grid | LENOX | 175358 | 1240 | 19 | Solar | 09_1103W1 | 2014-09-12 01:00 | 2014-09-15 | 5 | 0 | 5 | 2014-09-22 | 2014-09-22 | 0 | 0 | 0 | [20 empty] | 2014-09-23 |  | 2014-11-28 |  | EXP | [6 empty] | 2014-09-23 | 2014-09-23 | 2014-11-13 | Connected |  | No
National Grid | AVON | 175391 | 2322 | 266 | Solar | 07_75W5 | 2014-09-12 10:09 | 2014-09-15 | 6 | 0 | 6 | 2014-09-23 | 2014-09-23 | 0 | 0 | 0 | 2015-02-27 | 2015-04-01 | 22 | 0 | 22 | [5 empty] | 2015-02-27 | 2015-04-01 | 22 | 0 | 22 | [5 empty] | 2015-04-14 |  | 2016-12-31 |  | EXP | [6 empty] | 2015-06-16 | 2015-06-16 | 2017-03-07 | Connected |  | No
National Grid | SWANSEA | 175392 | 2777 | 19.13 | Solar | 05_11W84 | 2014-09-15 01:00 | 2014-09-16 | 13 | 5 | 8 | 2014-10-03 | 2014-10-03 | 0 | 0 | 0 | [20 empty] | 2014-10-10 |  | 2014-11-28 |  | EXP | [6 empty] | 2015-06-16 | 2015-06-16 | 2015-11-20 | Connected |  | No
National Grid | ATTLEBORO | 175394 | 2703 | 131 | Solar | 05_9L2 | 2014-09-16 01:00 | 2014-09-17 | 7 | 0 | 7 | 2014-09-26 | 2014-09-26 | 0 | 0 | 0 | [20 empty] | 2014-10-10 |  | 2014-12-31 |  | EXP | [6 empty] | 2015-01-15 | 2015-01-15 | 2015-02-05 | Connected |  | No
National Grid | OXFORD | 175395 | 1540 | 10 | Solar | 01_406L4 | 2014-09-16 01:00 | 2014-09-17 | 7 | 0 | 7 | 2014-09-26 | 2014-10-16 | 13 | 0 | 13 | [21 empty] | 2014-09-18 01:00 | 2014-11-28 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | GRANBY | 175424 | 1033 | 499 | Solar | 09_527L1 | 2014-09-18 01:00 | 2014-09-19 | 6 | 0 | 6 | [10 empty] | 2014-09-28 | 2014-10-24 | 18 | 0 | 18 | [10 empty] | 2015-09-29 | 2014-09-18 01:00 | 2017-02-14 |  | STD | [6 empty] | 2016-12-27 | 2016-12-27 | 2016-12-27 | Connected |  | No
National Grid | GRANBY | 175425 | 1033 | 499 | Solar | 09_527L1 | 2014-09-18 01:00 | 2014-09-19 | 6 | 0 | 6 | [10 empty] | 2014-09-28 | 2014-10-24 | 18 | 0 | 18 | [10 empty] | 2015-09-29 |  | 2016-03-15 |  | STD | [6 empty] | 2016-12-27 | 2016-12-27 | 2016-12-27 | Connected |  | No
National Grid | GRANBY | 175426 | 1033 | 280 | Solar | 09_527L1 | 2014-09-18 01:00 | 2014-09-19 | 6 | 0 | 6 | [10 empty] | 2014-09-28 | 2014-10-24 | 18 | 0 | 18 | [12 empty] | 2014-09-29 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | GRANBY | 175427 | 1033 | 392 | Solar | 09_527L1 | 2014-09-18 01:00 | 2014-09-19 | 6 | 0 | 6 | [10 empty] | 2014-09-28 | 2014-10-24 | 18 | 0 | 18 | [11 empty] | 2014-09-18 01:00 | 2015-04-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | GRANBY | 175428 | 1033 | 499 | Solar | 09_527L1 | 2014-09-18 01:00 | 2014-09-19 | 6 | 0 | 6 | [10 empty] | 2014-09-28 | 2014-10-24 | 18 | 0 | 18 | [10 empty] | 2015-09-29 | 2014-09-18 01:00 | 2017-02-14 |  | STD | [6 empty] | 2016-12-27 | 2016-12-27 | 2016-12-27 | Connected |  | No
National Grid | GRANBY | 175429 | 1033 | 499 | Solar | 09_527L1 | 2014-09-18 01:00 | 2014-09-19 | 6 | 0 | 6 | [10 empty] | 2014-09-29 | 2014-10-24 | 18 | 0 | 18 | [10 empty] | 2015-09-29 | 2014-09-18 01:00 | 2016-03-15 |  | STD | [6 empty] | 2016-12-27 | 2016-12-27 | 2016-12-27 | Connected |  | No
National Grid | LUDLOW | 175430 | 1056 | 499 | Solar | 09_527L1 | 2014-09-18 01:00 | 2014-09-19 | 6 | 0 | 6 | [10 empty] | 2014-09-28 | 2014-10-24 | 18 | 0 | 18 | [10 empty] | 2015-09-29 | 2014-09-18 01:00 | 2017-02-14 | Yes | STD | [6 empty] | 2016-12-27 | 2016-12-27 | 2016-12-27 | Connected |  | No
National Grid | WEST NEWBURY | 175431 | 1985 | 354 | Solar | 14_47L2 | 2014-09-18 01:00 | 2014-09-19 | 6 | 0 | 6 | 2014-09-29 | 2014-09-29 | 0 | 0 | 0 | [20 empty] | 2014-11-05 |  | 2015-06-01 | Yes | EXP |  | 2015-10-07 | 2015-11-23 | 31 | 0 | 31 | 2014-11-05 | 2014-11-05 | 2015-11-23 | Connected |  | No
National Grid | GRAFTON | 175459 | 1519 | 499 | Solar | 01_304W6 | 2014-09-19 01:00 | 2014-09-22 | 7 | 0 | 7 | 2014-10-01 | 2015-01-15 | 71 | 0 | 71 | [21 empty] | 2014-09-19 01:00 | 2015-01-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WILLIAMSTOWN | 175460 | 1267 | 414 | Solar | 09_1003W1 | 2014-09-19 01:00 | 2014-09-22 | 7 | 0 | 7 | 2014-10-01 | 2014-10-01 | 0 | 0 | 0 | [20 empty] | 2014-11-07 | 2014-09-19 01:00 | 2015-01-30 | Yes | EXP |  | 2015-04-02 | 2015-05-19 | 32 | 0 | 32 | 2015-06-09 | 2015-06-09 | 2015-06-09 | Connected |  | No
National Grid | UXBRIDGE | 175462 | 1569 | 950 | Solar | 05_321W2 | 2014-09-19 01:00 | 2014-09-22 | 7 | 0 | 7 | [10 empty] | 2014-10-01 | 2014-10-20 | 12 | 0 | 12 | [10 empty] | 2015-03-23 | 2014-09-19 01:00 | 2016-02-10 | Yes | STD |  | 2015-10-01 | 2016-06-23 | 179 | 0 | 179 | 2016-07-19 | 2016-07-19 | 2016-06-17 | Connected |  | No
National Grid | UXBRIDGE | 175463 | 1569 | 450 | Solar | 05_321W2 | 2014-09-19 01:00 | 2014-09-22 | 7 | 0 | 7 | [10 empty] | 2014-10-01 | 2014-10-20 | 12 | 0 | 12 | [10 empty] | 2015-03-23 | 2014-09-22 01:00 | 2016-12-31 | Yes | STD |  | 2015-10-01 | 2016-06-23 | 179 | 0 | 179 | 2016-07-19 | 2016-07-19 | 2016-06-17 | Connected |  | No
National Grid | BEVERLY | 175464 | 1915 | 881.6 | Solar | 12_18J3 | 2014-09-22 01:00 | 2014-09-23 | 6 | 0 | 6 | [10 empty] | 2014-10-01 | 2014-10-29 | 19 | 0 | 19 | [10 empty] | 2015-03-10 |  | 2016-01-01 | Yes | STD |  | 2015-11-04 | 2016-05-19 | 133 | 0 | 133 | 2016-05-06 | 2016-05-06 | 2016-05-06 | Connected |  | No
National Grid | PEPPERELL | 175461 | 1463 | 499 | Solar | 01_226L1 | 2014-09-23 01:00 | 2014-09-24 | 32 | 27 | 5 | [10 empty] | 2014-11-10 | 2014-12-04 | 16 | 0 | 16 | [12 empty] | 2015-07-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 175465 | 2302 | 490 | Solar | 07_91W46 | 2014-09-24 01:00 | 2014-09-25 | 7 | 0 | 7 | 2014-10-06 | 2014-10-06 | 0 | 0 | 0 | [20 empty] | 2014-10-29 |  | 2015-01-30 |  | EXP | [6 empty] | 2016-02-17 | 2016-02-17 | 2016-02-17 | Connected |  | No
National Grid | TYNGSBORO | 175466 | 1879 | 150 | Solar | 01_210L1 | 2014-09-24 01:00 | 2014-09-25 | 7 | 0 | 7 | 2014-10-06 | 2014-10-06 | 0 | 0 | 0 | [20 empty] | 2014-10-17 |  | 2015-01-30 |  | EXP | [6 empty] | 2015-01-30 | 2015-01-30 | 2015-02-25 | Connected |  | Yes
National Grid | FRANKLIN | 175467 | 2038 | 7.6 | Solar | 05_341W1 | 2014-09-24 01:00 | 2014-09-25 | 7 | 0 | 7 | 2014-10-06 | 2014-10-16 | 7 | 0 | 7 | [21 empty] | 2014-09-25 01:00 | 2014-12-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | TYNGSBORO | 175496 | 1879 | 68.4 | Solar | 14_211L1 | 2014-09-25 01:00 | 2014-09-26 | 6 | 0 | 6 | 2014-10-06 | 2014-10-06 | 0 | 0 | 0 | [20 empty] | 2014-11-10 |  | 2014-12-31 | Yes | EXP |  | 2015-01-23 | 2015-02-19 | 18 | 0 | 18 | 2015-02-26 | 2015-02-26 | 2015-04-16 | Connected |  | No
National Grid | BROCKTON | 175497 | 2301 | 1889 | Solar | 07_98W49 | 2014-09-26 01:00 | 2014-09-29 | 8 | 0 | 8 | [10 empty] | 2014-10-09 | 2014-10-31 | 15 | 0 | 15 | [12 empty] | 2015-10-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 175498 | 2301 | 990 | Solar | 07_91W48 | 2014-09-26 01:00 | 2014-09-29 | 8 | 0 | 8 | [10 empty] | 2014-10-09 | 2014-10-31 | 15 | 0 | 15 | [11 empty] | 2014-09-26 01:00 | 2015-10-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ANDOVER | 175499 | 1810 | 29.455 | Solar | 14_59L6 | 2014-09-26 01:00 | 2014-09-29 | 6 | 0 | 6 | 2014-10-07 | 2014-10-07 | 0 | 0 | 0 | [20 empty] | 2015-03-31 | 2014-09-29 01:00 | 2016-12-31 |  | EXP |  | 2015-10-22 | 2016-02-01 | 67 | 0 | 67 | 2016-05-17 | 2016-05-17 | 2016-06-02 | Connected |  | No
National Grid | UXBRIDGE | 175502 | 1569 | 1000 | Solar | 05_321W2 | 2014-09-29 01:00 | 2014-09-29 | 8 | 0 | 8 | [10 empty] | 2014-10-09 | 2014-10-31 | 15 | 0 | 15 | [10 empty] | 2015-03-23 | 2014-09-29 01:00 | 2016-01-21 | Yes | STD |  | 2016-06-09 | 2016-09-14 | 66 | 0 | 66 | 2016-12-22 | 2016-12-22 | 2016-12-22 | Connected |  | No
National Grid | CHARLTON | 175530 | 1507 | 499 | Solar | 01_415L1 | 2014-09-29 01:00 | 2014-09-29 | 8 | 3 | 5 | [10 empty] | 2014-10-09 | 2014-11-05 | 18 | 0 | 18 | [10 empty] | 2015-11-06 |  | 2016-05-01 | Yes | STD | [6 empty] | 2018-01-02 | 2018-01-02 | 2018-01-02 | Connected |  | No
National Grid | CHARLTON | 175531 | 1507 | 499 | Solar | 01_415L1 | 2014-09-29 01:00 | 2014-09-30 | 11 | 6 | 5 | [10 empty] | 2014-10-16 | 2014-11-14 | 20 | 0 | 20 | [10 empty] | 2015-11-06 | 2014-09-29 01:00 | 2016-05-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 175532 | 1507 | 499 | Solar | 01_415L1 | 2014-09-29 01:00 | 2014-09-30 | 11 | 6 | 5 | [10 empty] | 2014-10-16 | 2014-11-14 | 20 | 0 | 20 | [10 empty] | 2015-11-06 |  | 2016-05-01 | Yes | STD | [6 empty] | 2018-01-02 | 2018-01-02 | 2018-01-02 | Connected |  | No
National Grid | CHARLTON | 175533 | 1507 | 499 | Solar | 01_415L1 | 2014-09-29 01:00 | 2014-09-30 | 11 | 6 | 5 | [10 empty] | 2014-10-16 | 2014-11-14 | 20 | 0 | 20 | [10 empty] | 2015-11-06 | 2014-10-01 01:00 | 2016-05-01 |  | STD | [6 empty] | 2018-01-02 | 2018-01-02 | 2018-01-02 | Connected |  | No
National Grid | FRANKLIN | 175503 | 2038 | 490 | Solar | 05_348W7 | 2014-10-01 01:00 | 2014-10-02 | 3 | 0 | 3 | 2014-10-07 | 2014-10-07 | 0 | 0 | 0 | [20 empty] | 2014-11-10 |  | 2015-01-30 |  | EXP |  | 2015-03-10 | 2015-03-17 | 5 | 0 | 5 | 2015-02-06 | 2015-02-06 | 2015-03-19 | Connected |  | No
National Grid | NORTON | 175536 | 2766 | 1500 | Solar | 05_8L2 | 2014-10-02 01:00 | 2014-10-03 | 6 | 0 | 6 | [10 empty] | 2014-10-14 | 2014-11-06 | 17 | 0 | 17 | [12 empty] | 2016-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 175538 | 1507 | 499 | Solar | 01_415L1 | 2014-10-06 01:00 | 2014-10-07 | 6 | 4 | 2 | [10 empty] | 2014-10-16 | 2014-11-14 | 20 | 0 | 20 | [12 empty] | 2015-03-27 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SPENCER | 175566 | 1562 | 997.6 | Solar | 01_552L1 | 2014-10-06 01:00 | 2014-10-07 | 6 | 2 | 4 | [10 empty] | 2014-10-16 | 2014-11-14 | 20 | 1 | 19 | [10 empty] | 2015-06-12 |  | 2016-09-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HAYDENVILLE | 175567 | 1039 | 5.5 | Solar | 09_909W3 | 2014-10-08 01:00 | 2014-10-09 | 6 | 0 | 6 | 2014-10-20 | 2014-10-23 | 3 | 0 | 3 | [21 empty] | 2014-10-09 01:00 | 2015-02-02 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MILLBURY | 175537 | 1527 | 499 | Solar | 01_328W1 | 2014-10-09 01:00 | 2014-10-10 | 1 | 1 | 0 | 2014-10-14 | 2014-10-14 | 0 | 0 | 0 | [20 empty] | 2015-01-14 |  | 2016-01-15 | Yes | EXP |  | 2017-04-08 | 2017-04-13 | 3 | 0 | 3 | 2015-03-27 | 2015-03-27 | 2017-08-23 | Connected |  | No
National Grid | HOLBROOK | 175568 | 2343 | 10 | Solar | 07_911W77 | 2014-10-09 01:00 | 2014-10-10 | 6 | 0 | 6 | 2014-10-21 | 2014-10-21 | 0 | 0 | 0 | [20 empty] | 2015-01-07 | 2014-10-10 01:00 | 2015-02-09 |  | EXP | [6 empty] | 2015-02-04 | 2015-02-04 | 2016-07-27 | Connected |  | No
National Grid | HARVARD | 175571 | 1451 | 6 | Solar | 01_216W6 | 2014-10-10 01:00 | 2014-10-14 | 10 | 7 | 3 | 2014-10-28 | 2014-10-28 | 0 | 0 | 0 | [20 empty] | 2014-11-20 |  | 2015-04-22 |  | EXP |  | 2015-03-11 | 2015-03-16 | 3 | 0 | 3 | 2015-03-12 | 2015-03-12 | 2015-06-01 | Connected |  | No
National Grid | FLORIDA | 175572 | 1247 | 480 | Solar | 09_1015W1 | 2014-10-13 01:00 | 2014-10-15 | 6 | 0 | 6 | [10 empty] | 2014-10-23 | 2014-11-20 | 19 | 0 | 19 | [11 empty] | 2014-10-15 01:00 | 2016-09-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 175573 | 2302 | 3720 | Solar | 07_91W41 | 2014-10-15 01:00 | 2014-10-16 | 5 | 0 | 5 | [10 empty] | 2014-10-23 | 2014-11-12 | 13 | 0 | 13 | [10 empty] | 2015-06-10 |  | 2017-09-30 | Yes | STD |  | 2017-06-16 | 2017-08-08 | 36 | 0 | 36 | 2017-08-09 | 2017-08-09 | 2017-08-24 | Connected |  | No
National Grid | NORTHBOROUGH | 175601 | 1532 | 460 | Solar | 05_312W3 | 2014-10-15 01:00 | 2014-10-16 | 5 | 0 | 5 | 2014-10-23 | 2014-10-23 | 0 | 0 | 0 | 2015-01-27 | 2015-03-06 | 27 | 0 | 27 | [5 empty] | 2015-01-27 | 2015-03-06 | 27 | 0 | 27 | [5 empty] | 2015-03-20 | 2014-10-15 01:00 | 2015-01-31 |  | EXP | [6 empty] | 2015-03-27 | 2015-03-27 | 2016-02-04 | Connected |  | No
National Grid | SUTTON | 175603 | 1590 | 990 | Solar | 01_304W6 | 2014-10-15 01:00 | 2014-10-16 | 5 | 0 | 5 | [10 empty] | 2014-10-23 | 2014-11-19 | 18 | 0 | 18 | [10 empty] | 2015-05-12 |  | 2016-12-31 | Yes | STD |  | 2017-07-12 | 2017-07-12 | 0 | 0 | 0 | 2017-08-15 | 2017-08-15 | 2017-08-15 | Connected |  | No
National Grid | HANOVER | 175605 | 2339 | 17.6 | Solar | 07_95W2 | 2014-10-16 01:00 | 2014-10-17 | 8 | 5 | 3 | 2014-10-29 | 2014-10-29 | 0 | 0 | 0 | [20 empty] | 2014-11-10 | 2014-10-17 01:00 | 2014-12-31 |  | EXP | [6 empty] | 2015-01-30 | 2015-01-30 | 2015-02-24 | Connected |  | No
National Grid | ERVING | 175602 | 1344 | 5600 | Natural Gas | 09_705W1 | 2014-10-17 01:00 | 2014-10-20 | 2 | 0 | 2 | [10 empty] | 2014-10-22 | 2014-11-06 | 11 | 0 | 11 | [10 empty] | 2015-02-05 | 2014-10-17 01:00 | 2016-12-31 |  | STD |  | 2015-06-09 | 2015-11-17 | 110 | 0 | 110 | 2015-11-11 | 2015-11-11 | 2015-11-30 | Connected |  | No
National Grid | CHARLEMONT | 175607 | 1339 | 18 | Solar | 09_1019W1 | 2014-10-17 01:00 | 2014-10-20 | 6 | 0 | 6 | 2014-10-28 | 2014-10-28 | 0 | 0 | 0 | [20 empty] | 2014-12-12 |  | 2014-12-31 | Yes | EXP |  | 2015-01-02 | 2015-02-12 | 28 | 0 | 28 | 2015-02-17 | 2015-02-17 | 2015-03-05 | Connected |  | No
National Grid | BELLINGHAM | 175608 | 2019 | 998 | Solar | 05_344W4 | 2014-10-17 01:00 | 2014-10-20 | 6 | 0 | 6 | [10 empty] | 2014-10-28 | 2014-11-25 | 19 | 0 | 19 | [11 empty] | 2014-10-17 01:00 | 2015-03-27 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | REHOBOTH | 175609 | 2769 | 812 | Solar | 05_7L4 | 2014-10-17 01:00 | 2014-10-20 | 6 | 0 | 6 | [10 empty] | 2014-10-28 | 2014-11-24 | 18 | 0 | 18 | [10 empty] | 2015-04-16 |  | 2016-03-15 |  | STD |  | 2016-08-12 | 2016-12-20 | 88 | 0 | 88 | 2016-12-28 | 2016-12-28 | 2016-12-28 | Connected |  | No
National Grid | WESTFORD | 175635 | 1886 | 998 | Solar | 14_73L2 | 2014-10-17 01:00 | 2014-10-20 | 6 | 0 | 6 | [10 empty] | 2014-10-28 | 2014-11-05 | 6 | 0 | 6 | [12 empty] | 2015-03-27 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | GLOUCESTER | 175636 | 1930 | 45 | Solar | 12_51T3 | 2014-10-19 01:00 | 2014-10-21 | 6 | 2 | 4 | 2014-10-29 | 2014-10-29 | 0 | 0 | 0 | [20 empty] | 2014-11-05 |  | 2014-12-31 |  | EXP | [6 empty] | 2015-01-15 | 2015-01-15 | 2015-02-13 | Connected |  | No
National Grid | WORCESTER | 175640 | 1603 | 354 | Solar | 01_6W2 | 2014-10-20 01:00 | 2014-10-21 | 8 | 4 | 4 | 2014-10-31 | 2014-10-31 | 0 | 0 | 0 | [20 empty] | 2015-03-23 |  | 2016-09-01 |  | EXP | [6 empty] | 2014-10-23 | 2014-10-23 | 2016-06-16 | Connected |  | Yes
National Grid | ATTLEBORO | 175606 | 2703 | 644 | Solar | 05_9L4 | 2014-10-21 01:00 | 2014-10-22 | 4 | 0 | 4 | [10 empty] | 2014-10-28 | 2014-11-25 | 19 | 0 | 19 | [12 empty] | 2015-04-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | RUTLAND | 175638 | 1543 | 15.8 | Solar | 01_55W1 | 2014-10-21 01:00 | 2014-10-22 | 5 | 0 | 5 | 2014-10-29 | 2014-10-29 | 0 | 0 | 0 | [20 empty] | 2014-11-03 |  | 2015-02-06 |  | EXP | [6 empty] | 2015-01-28 | 2015-01-28 | 2016-05-27 | Connected |  | No
National Grid | MARLBOROUGH | 175639 | 1752 | 16 | Solar | 05_310W5 | 2014-10-21 01:00 | 2014-10-22 | 5 | 0 | 5 | 2014-10-29 | 2014-10-29 | 0 | 0 | 0 | [20 empty] | 2014-11-06 | 2014-10-21 01:00 | 2015-02-06 |  | EXP | [6 empty] | 2016-08-11 | 2016-08-11 | 2016-08-16 | Connected |  | No
National Grid | LEICESTER | 175641 | 1524 | 16 | Solar | 01_21W2 | 2014-10-21 01:00 | 2014-10-22 | 5 | 0 | 5 | 2014-10-29 | 2014-10-29 | 0 | 0 | 0 | [20 empty] | 2014-11-24 |  | 2016-12-31 |  | EXP | [6 empty] | 2015-08-05 | 2015-08-05 | 2016-10-20 | Connected |  | No
National Grid | GLOUCESTER | 175642 | 1930 | 17 | Solar | 12_24J10 | 2014-10-21 01:00 | 2014-10-22 | 5 | 0 | 5 | 2014-10-29 | 2014-10-29 | 0 | 0 | 0 | [20 empty] | 2014-11-10 |  | 2015-02-06 |  | EXP | [6 empty] | 2016-06-09 | 2016-06-09 | 2016-06-14 | Connected |  | No
National Grid | NORTH EASTON | 175643 | 2356 | 18 | Solar | 07_92W78 | 2014-10-21 01:00 | 2014-10-22 | 5 | 0 | 5 | 2014-10-29 | 2014-10-29 | 0 | 0 | 0 | [20 empty] | 2014-11-10 | 2014-10-21 01:00 | 2015-02-06 |  | EXP | [6 empty] | 2015-02-26 | 2015-02-26 | 2015-09-24 | Connected |  | No
National Grid | DRACUT | 175670 | 1826 | 7.6 | Solar | 14_78L9 | 2014-10-21 01:00 | 2014-10-22 | 6 | 0 | 6 | 2014-10-30 | 2014-10-30 | 0 | 0 | 0 | [20 empty] | 2014-11-26 |  | 2016-12-31 | Yes | EXP |  | 2016-06-24 | 2016-06-24 | 0 | 0 | 0 | 2015-02-26 | 2015-02-26 | 2016-08-17 | Connected |  | No
National Grid | SHIRLEY | 175671 | 1464 | 1008 | Solar | 01_227W3 | 2014-10-21 01:00 | 2014-10-22 | 5 | 0 | 5 | [10 empty] | 2014-10-29 | 2014-11-19 | 14 | 0 | 14 | [12 empty] | 2015-04-15 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HANOVER | 175672 | 2339 | 816 | Solar | 07_95W2 | 2014-10-21 01:00 | 2014-10-22 | 6 | 0 | 6 | [10 empty] | 2014-10-30 | 2014-11-26 | 18 | 0 | 18 | [12 empty] | 2015-04-15 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | FALL RIVER | 175675 | 2720 | 500 | Solar | 05_28W51 | 2014-10-21 01:00 | 2014-10-22 | 7 | 0 | 7 | [10 empty] | 2014-10-31 | 2014-11-26 | 17 | 0 | 17 | [10 empty] | 2015-04-27 |  |  |  | STD | [6 empty] | 2018-01-26 | 2018-01-26 |  | Withdrawn |  | No
National Grid | NANTUCKET | 175673 | 2554 | 3024 | Solar | 04_101L7 | 2014-10-22 01:00 | 2014-10-23 | 3 | 0 | 3 | [27 empty] | 2015-09-02 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NANTUCKET | 175674 | 2554 | 499 | Solar | 04_101L7 | 2014-10-22 01:00 | 2014-10-23 | 6 | 0 | 6 | 2014-10-31 | 2014-11-06 | 4 | 0 | 4 | [22 empty] | 2015-09-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NANTUCKET | 175677 | 2554 | 499 | Solar | 04_101L7 | 2014-10-22 01:00 | 2014-10-23 | 6 | 0 | 6 | [27 empty] | 2015-09-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 175678 | 1507 | 1000 | Solar | 01_415L1 | 2014-10-22 01:00 | 2014-10-23 | 6 | 0 | 6 | [10 empty] | 2014-10-31 | 2014-12-01 | 19 | 0 | 19 | [12 empty] | 2015-03-27 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ABINGTON | 175705 | 2351 | 996 | Solar | 07_93W42 | 2014-10-22 01:00 | 2014-10-23 | 6 | 0 | 6 | [10 empty] | 2014-10-31 | 2014-11-26 | 17 | 0 | 17 | [10 empty] | 2015-04-21 |  | 2016-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 175706 | 1507 | 1000 | Solar | 01_415L1 | 2014-10-22 01:00 | 2014-10-23 | 6 | 0 | 6 | [10 empty] | 2014-10-31 | 2014-12-01 | 19 | 0 | 19 | [12 empty] | 2015-03-27 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ABINGTON | 175707 | 2351 | 996 | Solar | 07_93W42 | 2014-10-22 01:00 | 2014-10-23 | 6 | 0 | 6 | [10 empty] | 2014-10-31 | 2014-11-26 | 17 | 0 | 17 | [10 empty] | 2015-04-21 | 2014-10-23 01:00 | 2016-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTON | 175637 | 2766 | 1000 | Solar | 05_4L1 | 2014-10-23 01:00 | 2014-10-24 | 6 | 0 | 6 | [10 empty] | 2014-11-03 | 2014-12-03 | 20 | 0 | 20 | [10 empty] | 2015-03-26 | 2014-10-23 01:00 | 2016-12-31 | Yes | STD |  | 2016-04-25 | 2017-04-11 | 240 | 0 | 240 | 2017-04-28 | 2017-04-28 | 2017-04-28 | Connected |  | No
National Grid | WEST GROTON | 175712 | 1472 | 5600 | Natural Gas | 01_201W4 | 2014-10-23 01:00 | 2014-10-24 | 4 | 0 | 4 | [10 empty] | 2014-10-30 | 2014-11-14 | 10 | 0 | 10 | [10 empty] | 2015-04-27 |  | 2016-12-31 | Yes | STD |  | 2015-07-09 | 2015-08-13 | 25 | 0 | 25 | 2015-12-02 | 2015-12-02 | 2015-12-09 | Connected |  | No
National Grid | BELLINGHAM | 175708 | 2019 | 18 | Solar | 05_335W1 | 2014-10-24 01:00 | 2014-10-27 | 5 | 3 | 2 | 2014-11-03 | 2014-11-03 | 0 | 0 | 0 | [20 empty] | 2014-11-12 | 2014-10-25 01:00 | 2015-02-24 |  | EXP | [6 empty] | 2015-01-21 | 2015-01-21 | 2015-08-28 | Connected |  | No
National Grid | CLARKSBURG | 175710 | 1247 | 499 | Solar | 09_1015W2 | 2014-10-25 01:00 | 2014-10-27 | 6 | 1 | 5 | 2014-11-04 | 2014-11-04 | 0 | 0 | 0 | 2015-01-14 | 2015-02-24 | 27 | 0 | 27 | [5 empty] | 2015-01-14 | 2015-02-24 | 27 | 0 | 27 | [5 empty] | 2015-02-24 | 2014-10-25 01:00 | 2016-01-19 | Yes | EXP |  | 2016-07-19 | 2016-10-20 | 65 | 0 | 65 |  |  | 2016-11-14 | Connected |  | No
National Grid | CHESHIRE | 175711 | 1225 | 499 | Solar | 09_1021W2 | 2014-10-25 01:00 | 2014-10-27 | 10 | 8 | 2 | 2014-11-10 | 2014-11-10 | 0 | 0 | 0 | 2014-12-24 | 2015-02-24 | 40 | 0 | 40 | [5 empty] | 2014-12-24 | 2015-02-24 | 40 | 0 | 40 | [5 empty] | 2015-02-24 | 2014-10-27 01:00 | 2016-12-31 | Yes | EXP |  | 2016-10-11 | 2016-11-28 | 32 | 0 | 32 |  |  | 2016-11-14 | Connected |  | No
National Grid | SHEFFIELD | 175709 | 1257 | 250 | Solar | 09_1109W2 | 2014-10-27 01:00 | 2014-10-27 | 7 | 1 | 6 | 2014-11-05 | 2014-11-05 | 0 | 0 | 0 | 2015-01-03 | 2015-02-24 | 34 | 0 | 34 | [5 empty] | 2015-01-03 | 2015-02-24 | 34 | 0 | 34 | [5 empty] | 2015-02-24 |  | 2016-06-01 | Yes | EXP |  | 2016-06-14 | 2016-10-19 | 87 | 0 | 87 |  |  | 2016-10-26 | Connected |  | No
National Grid | MILLBURY | 175713 | 1527 | 5 | Solar | 01_304W1 | 2014-10-27 01:00 | 2014-10-28 | 6 | 1 | 5 | 2014-11-05 | 2014-11-05 | 0 | 0 | 0 | [20 empty] | 2014-11-25 |  | 2015-01-28 |  | EXP | [6 empty] | 2015-02-20 | 2015-02-20 | 2015-08-07 | Connected |  | No
National Grid | NANTUCKET | 175676 | 2554 | 1596 | Solar | 04_101L7 | 2014-10-28 01:00 | 2014-10-29 | 2 | 1 | 1 | [10 empty] | 2014-10-31 | 2014-12-12 | 28 | 9 | 19 | [12 empty] | 2015-09-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 175743 | 2301 | 684 | Solar | 07_91W49 | 2014-10-28 01:00 | 2014-10-30 | 4 | 4 | 0 | [10 empty] | 2014-11-05 | 2014-12-05 | 20 | 0 | 20 | [12 empty] | 2015-03-18 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | PALMER | 175744 | 1069 | 496.8 | Solar | 09_514L1 | 2014-10-28 01:00 | 2014-11-05 | 0 | 0 | 0 | [5 empty] | 2014-12-20 | 2015-01-14 | 15 | 3 | 12 | 2014-11-05 | 2014-12-05 | 20 | 0 | 20 | 2014-12-20 | 2015-01-14 | 15 | 3 | 12 | [5 empty] | 2015-06-05 |  | 2016-02-15 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SUTTON | 175745 | 1590 | 496.8 | Solar | 01_304W6 | 2014-10-28 01:00 | 2014-10-29 | 5 | 0 | 5 | 2014-11-05 | 2015-06-17 | 151 | 16 | 135 | [20 empty] | 2015-04-27 |  | 2015-03-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BLACKSTONE | 175746 | 1504 | 20 | Solar | 05_108W60 | 2014-10-29 01:00 | 2014-11-03 | 5 | 3 | 2 | 2014-11-10 | 2014-11-10 | 0 | 0 | 0 | [20 empty] | 2014-11-12 | 2014-10-30 01:00 | 2015-01-15 |  | EXP | [6 empty] | 2015-01-30 | 2015-01-30 | 2015-03-03 | Connected |  | No
National Grid | DUDLEY | 175747 | 1571 | 1000 | Solar | 01_412L4 | 2014-10-30 01:00 | 2014-11-03 | 5 | 1 | 4 | [10 empty] | 2014-11-10 | 2014-12-08 | 18 | 0 | 18 | [10 empty] | 2015-09-25 |  | 2017-09-01 | Yes | STD |  | 2017-06-05 | 2017-08-16 | 51 | 0 | 51 | 2017-08-21 | 2017-08-21 | 2017-09-14 | Connected |  | No
National Grid | DUDLEY | 175748 | 1571 | 16 | Solar | 01_412L2 | 2014-10-30 01:00 | 2014-10-31 | 6 | 4 | 2 | 2014-11-10 | 2015-11-16 | 251 | 0 | 251 | [20 empty] | 2014-11-12 |  | 2014-12-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTHAMPTON | 175749 | 1060 | 11.8 | Solar | 09_901W3 | 2014-10-30 01:00 | 2014-10-31 | 6 | 0 | 6 | 2014-11-10 | 2015-01-07 | 38 | 0 | 38 | [22 empty] | 2015-03-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SOUTH HAMILTON | 175750 | 1982 | 17.2 | Solar | 12_51T2 | 2014-10-31 01:00 | 2014-11-03 | 6 | 5 | 1 | 2014-11-12 | 2014-11-12 | 0 | 0 | 0 | [20 empty] | 2014-11-13 | 2014-10-31 01:00 | 2015-03-31 |  | EXP | [6 empty] | 2015-01-12 | 2015-01-12 | 2015-09-17 | Connected |  | No
National Grid | REVERE | 175751 | 2151 | 21.07 | Solar | 12_35J2 | 2014-10-31 01:00 | 2014-11-03 | 6 | 5 | 1 | 2014-11-12 | 2014-11-12 | 0 | 0 | 0 | [20 empty] | 2014-12-05 |  | 2016-12-31 | Yes | EXP |  | 2016-04-29 | 2016-04-30 | 1 | 0 | 1 | 2015-01-28 | 2015-01-28 | 2016-05-20 | Connected |  | No
National Grid | BARRE | 175752 | 1005 | 480 | Solar | 09_604W4 | 2014-10-31 01:00 | 2014-11-03 | 5 | 1 | 4 | [10 empty] | 2014-11-10 | 2014-12-08 | 18 | 0 | 18 | [11 empty] | 2014-11-03 | 2016-11-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BARRE | 175214 | 1005 | 960 | Solar | 09_604W4 | 2014-11-03 | 2014-11-04 | 8 | 5 | 3 | [10 empty] | 2014-11-17 | 2014-12-08 | 14 | 0 | 14 | [5 empty] | 2017-03-18 | 2017-02-14 | 0 | 0 | 0 | 2017-05-09 | 2014-11-03 | 2018-09-27 | Yes | STD | [8 empty] | 2018-09-17 | Connected |  | No
National Grid | HARDWICK | 175215 | 1037 | 480 | Solar | 09_501L2 | 2014-11-03 | 2014-11-04 | 8 | 5 | 3 | [10 empty] | 2014-11-17 | 2014-12-18 | 22 | 0 | 22 | [5 empty] | 2016-05-10 | 2016-06-27 | 32 | 0 | 32 | 2015-12-21 | 2014-11-03 | 2017-03-31 | Yes | STD |  | 2016-10-28 | 2017-03-23 | 98 | 0 | 98 | 2017-03-27 | 2017-03-27 | 2017-04-03 | Connected |  | No
National Grid | HARDWICK | 175216 | 1037 | 480 | Solar | 09_501L2 | 2014-11-03 | 2014-11-04 | 8 | 5 | 3 | [10 empty] | 2014-11-17 | 2014-12-18 | 22 | 0 | 22 | [5 empty] | 2016-05-10 | 2016-06-27 | 32 | 0 | 32 | 2015-12-21 |  | 2017-03-31 | Yes | STD |  | 2016-10-10 | 2017-03-23 | 111 | 0 | 111 | 2017-03-27 | 2017-03-27 | 2017-04-03 | Connected |  | No
National Grid | BARRE | 175217 | 1005 | 480 | Solar | 09_604W4 | 2014-11-03 | 2014-11-04 | 8 | 5 | 3 | 2014-11-17 | 2015-05-29 | 131 | 0 | 131 | [22 empty] | 2015-03-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NEW BRAINTREE | 175218 | 1531 | 750 | Solar | 09_604W3 | 2014-11-03 | 2014-11-04 | 12 | 10 | 2 | [10 empty] | 2014-11-21 | 2014-12-19 | 19 | 0 | 19 | [12 empty] | 2016-09-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH BROOKFIELD | 175219 | 1535 | 18 | Solar | 01_525L1 | 2014-11-03 | 2014-11-04 | 6 | 2 | 4 | 2014-11-13 | 2014-11-13 | 0 | 0 | 0 | [20 empty] | 2014-11-14 |  | 2015-06-01 |  | EXP | [6 empty] | 2015-02-18 | 2015-02-18 | 2015-09-30 | Connected |  | No
National Grid | SPENCER | 175220 | 1562 | 17.5 | Solar | 01_21W1 | 2014-11-03 | 2014-11-04 | 6 | 1 | 5 | 2014-11-13 | 2014-11-13 | 0 | 0 | 0 | [20 empty] | 2014-11-14 |  | 2015-01-30 |  | EXP | [6 empty] | 2015-02-26 | 2015-02-26 | 2016-03-08 | Connected |  | No
National Grid | BRIDGEWATER | 175221 | 2324 | 19 | Solar | 07_797W1 | 2014-11-03 | 2014-11-04 | 7 | 4 | 3 | 2014-11-14 | 2014-11-14 | 0 | 0 | 0 | [20 empty] | 2014-11-19 |  | 2015-01-30 |  | EXP | [6 empty] | 2015-08-05 | 2015-08-05 | 2016-05-10 | Connected |  | No
National Grid | OXFORD | 175246 | 1540 | 800 | Solar | 01_406L3 | 2014-11-04 | 2014-11-05 | 19 | 17 | 2 | [10 empty] | 2014-12-04 | 2015-01-05 | 20 | 0 | 20 | [12 empty] | 2015-08-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SWANSEA | 175247 | 2777 | 999 | Solar | 05_11W84 | 2014-11-04 | 2014-11-05 | 21 | 19 | 2 | [10 empty] | 2014-12-08 | 2015-01-05 | 18 | 0 | 18 | [11 empty] | 2014-11-04 | 2015-08-01 |  | STD |  | 2017-03-14 | 2017-08-29 | 117 | 0 | 117 |  |  |  | Withdrawn |  | No
National Grid | DUDLEY | 175248 | 1571 | 1000 | Solar | 01_413L3 | 2014-11-04 | 2014-11-05 | 20 | 20 | 0 | [10 empty] | 2014-12-04 | 2015-01-05 | 21 | 21 | 0 | [5 empty] | 2017-01-20 | 2017-02-17 | 20 | 0 | 20 | 2017-07-11 | 2014-11-04 | 2018-07-31 | Yes | STD |  | 2017-12-27 | 2018-05-08 | 132 | 0 | 132 |  |  | 2018-07-26 | Connected |  | No
National Grid | DUDLEY | 175249 | 1571 | 1000 | Solar | 01_413L3 | 2014-11-04 | 2014-11-05 | 20 | 20 | 0 | [10 empty] | 2014-12-04 | 2015-01-05 | 21 | 21 | 0 | [5 empty] | 2017-01-20 | 2017-02-17 | 20 | 0 | 20 | 2017-07-11 |  | 2018-07-31 | Yes | STD |  | 2017-12-27 | 2018-05-08 | 132 | 0 | 132 | 2018-06-12 | 2018-06-12 | 2018-07-26 | Connected |  | No
National Grid | SUTTON | 175250 | 1590 | 24.94 | Solar | 01_304W6 | 2014-11-05 | 2014-11-06 | 6 | 3 | 3 | 2014-11-17 | 2014-11-17 | 0 | 0 | 0 | [20 empty] | 2014-11-19 |  | 2015-01-30 |  | EXP | [6 empty] | 2015-11-19 | 2015-11-19 | 2015-11-19 | Connected |  | No
National Grid | MILLBURY | 175251 | 1527 | 17.2 | Solar | 01_304W3 | 2014-11-05 | 2014-11-06 | 6 | 3 | 3 | 2014-11-17 | 2014-11-17 | 0 | 0 | 0 | [20 empty] | 2014-11-20 |  | 2015-01-30 |  | EXP | [6 empty] | 2015-02-03 | 2015-02-03 | 2016-04-19 | Connected |  | No
National Grid | FALL RIVER | 175252 | 2723 | 20.64 | Solar | 05_106W44 | 2014-11-05 | 2014-11-06 | 6 | 3 | 3 | 2014-11-17 | 2017-09-25 | 710 | 0 | 710 | [20 empty] | 2014-11-20 |  | 2017-12-01 |  | EXP | [6 empty] | 2015-01-28 | 2015-01-28 |  | Withdrawn |  | Yes
National Grid | SAUGUS | 175253 | 1906 | 8.82 | Solar | 12_25W1 | 2014-11-05 | 2014-11-06 | 5 | 0 | 5 | 2014-11-14 | 2014-11-14 | 0 | 0 | 0 | [20 empty] | 2014-11-19 |  | 2015-01-30 |  | EXP | [6 empty] | 2015-01-21 | 2015-01-21 | 2015-09-04 | Connected |  | No
National Grid | MILLBURY | 175254 | 1527 | 6.88 | Solar | 01_304W3 | 2014-11-05 | 2014-11-06 | 5 | 0 | 5 | 2014-11-14 | 2015-06-22 | 147 | 0 | 147 | [20 empty] | 2014-12-08 | 2014-11-05 | 2015-01-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | CHELMSFORD | 175285 | 1824 | 30 | Solar | 14_58L2 | 2014-11-05 | 2014-11-06 | 5 | 1 | 4 | 2014-11-14 | 2015-06-22 | 147 | 4 | 143 | [20 empty] | 2014-12-11 | 2014-11-05 | 2015-01-30 | Yes | EXP | [6 empty] | 2015-02-17 | 2015-02-17 | 2015-03-06 | Connected |  | No
National Grid | CHELMSFORD | 176030 | 1824 | 30 | Solar | 14_58L2 | 2014-11-05 | 2014-11-06 | 3 | 0 | 3 | 2014-11-12 | 2014-11-12 | 0 | 0 | 0 | [20 empty] | 2014-12-11 |  | 2015-09-30 | Yes | EXP | [6 empty] | 2015-02-17 | 2015-02-17 | 2015-03-06 | Connected |  | No
National Grid | OXFORD | 175286 | 1540 | 19.78 | Solar | 01_406L4 | 2014-11-06 | 2014-11-07 | 5 | 3 | 2 | 2014-11-17 | 2014-11-17 | 0 | 0 | 0 | [20 empty] | 2014-11-20 |  | 2015-01-30 |  | EXP | [6 empty] | 2015-01-28 | 2015-01-28 | 2016-04-27 | Connected |  | No
National Grid | LEOMINSTER | 175288 | 1453 | 225 | Solar | 01_219W4 | 2014-11-06 | 2014-11-07 | 5 | 0 | 5 | 2014-11-17 | 2014-11-17 | 0 | 0 | 0 | [20 empty] | 2014-12-04 | 2014-11-06 | 2015-04-01 |  | EXP | [6 empty] | 2014-12-19 | 2014-12-19 | 2015-10-22 | Connected |  | No
National Grid | NORTH EASTON | 175289 | 2356 | 370 | Solar | 07_92W43 | 2014-11-06 | 2014-11-07 | 5 | 1 | 4 | 2014-11-17 | 2014-11-17 | 0 | 0 | 0 | [20 empty] | 2014-12-19 | 2014-11-06 | 2016-12-31 | Yes | EXP |  | 2016-09-29 | 2016-11-21 | 35 | 0 | 35 | 2017-02-07 | 2017-02-07 | 2017-02-16 | Connected |  | No
National Grid | NORTH EASTON | 175290 | 2356 | 189 | Solar | 07_92W43 | 2014-11-06 | 2014-11-07 | 5 | 1 | 4 | 2014-11-17 | 2014-11-17 | 0 | 0 | 0 | [20 empty] | 2014-12-19 |  | 2016-12-31 | Yes | EXP |  | 2016-09-29 | 2016-10-31 | 21 | 0 | 21 | 2015-02-05 | 2015-02-05 | 2017-02-23 | Connected |  | No
National Grid | FALL RIVER | 175291 | 2721 | 36 | Solar | 05_115W44 | 2014-11-06 | 2014-11-07 | 5 | 2 | 3 | 2014-11-17 | 2014-11-17 | 0 | 0 | 0 | [20 empty] | 2014-11-20 |  | 2015-02-27 |  | EXP | [6 empty] | 2015-02-27 | 2015-02-27 | 2015-04-16 | Connected |  | No
National Grid | FALL RIVER | 175292 | 2721 | 20 | Solar | 05_106W42 | 2014-11-07 | 2014-11-10 | 6 | 2 | 4 | 2014-11-19 | 2014-11-19 | 0 | 0 | 0 | [20 empty] | 2014-12-09 |  | 2015-02-27 |  | EXP | [6 empty] | 2015-02-27 | 2015-02-27 | 2015-04-17 | Connected |  | No
National Grid | FALL RIVER | 175293 | 2721 | 20 | Solar | 05_106W42 | 2014-11-07 | 2014-11-10 | 6 | 2 | 4 | 2014-11-19 | 2014-11-19 | 0 | 0 | 0 | [20 empty] | 2014-11-26 |  | 2015-02-27 |  | EXP | [6 empty] | 2015-04-16 | 2015-04-16 | 2015-04-16 | Connected |  | No
National Grid | CHARLTON | 175323 | 1507 | 630 | Solar | 01_415L2 | 2014-11-07 | 2014-11-10 | 6 | 2 | 4 | [10 empty] | 2014-11-19 | 2014-12-19 | 21 | 0 | 21 | [12 empty] | 2015-07-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SOUTHBRIDGE | 175324 | 1550 | 256.2 | Solar | 01_413L1 | 2014-11-07 | 2014-11-10 | 6 | 0 | 6 | 2014-11-19 | 2014-11-19 | 0 | 0 | 0 | [20 empty] | 2014-12-16 | 2014-11-10 | 2015-03-31 |  | EXP | [6 empty] | 2015-10-20 | 2015-10-20 | 2015-10-21 | Connected |  | No
National Grid | NORWELL | 175327 | 2061 | 419 | Solar | 07_95W5 | 2014-11-10 | 2014-11-11 | 5 | 2 | 3 | 2014-11-19 | 2014-11-19 | 0 | 0 | 0 | [20 empty] | 2015-01-14 |  | 2016-04-15 | Yes | EXP |  | 2017-01-30 | 2017-03-22 | 36 | 0 | 36 | 2015-02-04 | 2015-02-04 | 2017-03-30 | Connected |  | No
National Grid | STURBRIDGE | 175328 | 1566 | 540 | Solar | 01_415L3 | 2014-11-10 | 2014-11-12 | 5 | 2 | 3 | [10 empty] | 2014-11-19 | 2014-12-17 | 19 | 0 | 19 | [12 empty] | 2015-04-15 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SEEKONK | 175329 | 2771 | 16 | Solar | 05_7L1 | 2014-11-11 | 2014-11-12 | 2 | 1 | 1 | [26 empty] | 2014-11-11 | 2015-01-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | OXFORD | 175330 | 1540 | 996 | Solar | 01_406L2 | 2014-11-11 | 2014-11-12 | 5 | 1 | 4 | [10 empty] | 2014-11-19 | 2014-12-01 | 7 | 0 | 7 | [10 empty] | 2015-04-01 | 2014-11-11 | 2016-09-14 |  | STD | [8 empty] | 2016-11-23 | Connected |  | No
National Grid | OXFORD | 175331 | 1540 | 3000 | Solar | 01_406L4 | 2014-11-11 | 2014-11-12 | 5 | 1 | 4 | [10 empty] | 2014-11-19 | 2014-12-01 | 7 | 0 | 7 | [10 empty] | 2015-04-01 |  | 2016-09-14 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | SEEKONK | 175359 | 2771 | 16 | Solar | 05_7L1 | 2014-11-11 | 2014-11-12 | 5 | 0 | 5 | 2014-11-19 | 2014-11-19 | 0 | 0 | 0 | [20 empty] | 2014-11-21 |  | 2015-01-30 |  | EXP | [6 empty] | 2015-01-21 | 2015-01-21 | 2016-06-17 | Connected |  | No
National Grid | FALL RIVER | 175360 | 2724 | 20 | Solar | 05_115W55 | 2014-11-12 | 2014-11-13 | 2 | 0 | 2 | [27 empty] | 2015-01-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BILLERICA | 175361 | 1821 | 8 | Solar | 14_92L2 | 2014-11-13 | 2014-11-14 | 5 | 0 | 5 | 2014-11-21 | 2015-11-24 | 249 | 0 | 249 | [20 empty] | 2014-11-21 |  | 2015-01-11 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 175364 | 2301 | 20 | Solar | 07_911W13 | 2014-11-13 | 2014-11-14 | 5 | 1 | 4 | 2014-11-21 | 2014-11-21 | 0 | 0 | 0 | [20 empty] | 2014-12-09 |  | 2015-01-31 |  | EXP | [6 empty] | 2015-04-24 | 2015-04-24 | 2015-06-26 | Connected |  | No
National Grid | MILLBURY | 175362 | 1527 | 336 | Solar | 01_304W3 | 2014-11-14 | 2014-11-17 | 4 | 1 | 3 | 2014-11-21 | 2015-05-22 | 123 | 0 | 123 | [20 empty] | 2015-01-14 |  | 2015-03-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 175363 | 2302 | 5 | Solar | 07_712J1 | 2014-11-14 | 2014-11-17 | 4 | 0 | 4 | 2014-11-21 | 2016-09-02 | 442 | 0 | 442 | [20 empty] | 2014-11-25 |  | 2015-01-31 |  | EXP | [6 empty] | 2015-02-19 | 2015-02-19 |  | Withdrawn |  | No
National Grid | AYER | 175365 | 1432 | 79.2 | Solar | 01_201W2 | 2014-11-17 | 2014-11-18 | 4 | 0 | 4 | 2014-11-24 | 2014-11-24 | 0 | 0 | 0 | [20 empty] | 2014-12-01 |  | 2015-04-30 |  | EXP | [6 empty] | 2015-01-28 | 2015-01-28 | 2015-12-09 | Connected |  | No
National Grid | BROCKTON | 175366 | 2302 | 984 | Solar | 07_911W77 | 2014-11-17 | 2014-11-18 | 5 | 3 | 2 | [10 empty] | 2014-11-25 | 2014-12-23 | 19 | 0 | 19 | [11 empty] | 2014-11-17 | 2016-03-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HUBBARDSTON | 175367 | 1452 | 960 | Solar | 01_602W2 | 2014-11-17 | 2014-11-18 | 5 | 3 | 2 | [10 empty] | 2014-11-25 | 2014-12-24 | 20 | 0 | 20 | [5 empty] | 2016-05-13 | 2016-09-19 | 87 | 0 | 87 | 2017-01-17 |  | 2017-03-31 | Yes | STD |  | 2017-03-29 | 2017-03-27 | 0 | 0 | 0 | 2017-04-21 | 2017-04-21 | 2017-05-05 | Connected |  | No
National Grid | SOUTHBRIDGE | 175396 | 1550 | 480 | Solar | 01_413L4 | 2014-11-17 | 2014-11-18 | 5 | 4 | 1 | [10 empty] | 2014-11-25 | 2014-12-24 | 20 | 0 | 20 | [12 empty] | 2015-03-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 175397 | 2302 | 475.2 | Solar | 07_712J1 | 2014-11-17 | 2014-11-18 | 4 | 0 | 4 | 2014-11-24 | 2015-11-16 | 242 | 4 | 238 | 2015-07-31 | 2015-11-16 | 73 | 0 | 73 | [5 empty] | 2015-07-31 | 2015-11-16 | 73 | 0 | 73 | [7 empty] | 2016-02-15 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | DIGHTON | 175398 | 2715 | 475 | Solar | 05_19W72 | 2014-11-17 | 2014-11-18 | 4 | 0 | 4 | [10 empty] | 2014-11-24 | 2014-12-29 | 23 | 4 | 19 | [10 empty] | 2015-07-30 |  | 2016-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | QUINCY | 175399 | 2169 | 1850 | Natural Gas | 07_1202 | 2014-11-17 | 2014-11-18 | 4 | 3 | 1 | [10 empty] | 2014-11-24 | 2014-12-23 | 20 | 0 | 20 | [10 empty] | 2015-08-24 |  | 2016-12-31 |  | STD | [6 empty] | 2015-12-14 | 2015-12-14 | 2015-12-14 | Connected |  | Yes
National Grid | AMESBURY | 175401 | 1913 | 17 | Solar | 14_5J14 | 2014-11-19 | 2014-11-21 | 15 | 15 | 0 | 2014-12-15 | 2015-01-05 | 13 | 0 | 13 | [22 empty] | 2015-01-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | AMESBURY | 175681 | 1913 | 17 | Solar | 14_5J14 | 2014-11-19 | 2014-11-21 | 15 | 0 | 15 | 2014-12-15 | 2014-12-15 | 0 | 0 | 0 | [20 empty] | 2015-01-07 | 2014-11-21 | 2015-01-31 |  | EXP | [6 empty] | 2015-02-20 | 2015-02-20 | 2015-10-29 | Connected |  | No
National Grid | PALMER | 175402 | 1069 | 1080 | Solar | 09_503L4 | 2014-11-21 | 2014-11-24 | 5 | 1 | 4 | [10 empty] | 2014-12-02 | 2014-12-19 | 13 | 0 | 13 | [10 empty] | 2015-07-30 | 2014-11-21 | 2016-05-01 | Yes | STD |  | 2017-01-10 | 2017-02-17 | 27 | 0 | 27 |  |  | 2017-03-10 | Connected |  | No
National Grid | HUBBARDSTON | 175403 | 1452 | 960 | Solar | 01_602W2 | 2014-11-21 | 2014-11-24 | 8 | 7 | 1 | [10 empty] | 2014-12-05 | 2015-01-06 | 20 | 0 | 20 | [5 empty] | 2016-05-13 | 2016-09-19 | 87 | 0 | 87 | 2017-01-17 |  | 2017-04-10 | Yes | STD |  | 2017-02-10 | 2017-09-05 | 142 | 0 | 142 | 2017-04-21 | 2017-04-21 | 2017-05-05 | Connected |  | No
National Grid | HALIFAX | 175432 | 2338 | 1000 | Solar | 07_912W75 | 2014-11-24 | 2014-11-25 | 5 | 3 | 2 | [10 empty] | 2014-12-03 | 2014-12-24 | 15 | 0 | 15 | [10 empty] | 2015-08-07 |  | 2016-08-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | REHOBOTH | 175433 | 2769 | 1000 | Solar | 05_7L4 | 2014-11-24 | 2014-11-25 | 5 | 3 | 2 | [10 empty] | 2014-12-03 | 2014-12-18 | 11 | 0 | 11 | [12 empty] | 2015-07-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | FLORIDA | 175434 | 1247 | 984 | Solar | 09_1015W1 | 2014-11-24 | 2014-11-25 | 6 | 6 | 0 | [10 empty] | 2014-12-04 | 2015-01-05 | 20 | 0 | 20 | [12 empty] | 2015-03-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTHBRIDGE | 175435 | 1534 | 28 | Solar | 05_320W3 | 2014-11-24 | 2014-11-25 | 5 | 3 | 2 | 2014-12-03 | 2014-12-03 | 0 | 0 | 0 | [20 empty] | 2014-12-03 |  | 2015-03-31 |  | EXP | [6 empty] | 2015-01-16 | 2015-01-16 | 2015-06-23 | Connected |  | No
National Grid | WORCESTER | 175436 | 1608 | 150 | Natural Gas | 01_HT61 | 2014-11-24 | 2014-11-25 | 5 | 3 | 2 | 2014-12-03 | 2014-12-03 | 0 | 0 | 0 | 2015-09-10 | 2016-03-16 | 127 | 114 | 13 | [5 empty] | 2015-09-10 | 2016-03-16 | 127 | 114 | 13 | [5 empty] | 2016-03-23 |  | 2016-12-31 |  | EXP | [6 empty] | 2016-04-26 | 2016-04-26 | 2016-05-05 | Connected |  | No
National Grid | REHOBOTH | 175437 | 2769 | 1000 | Solar | 05_7L4 | 2014-11-24 | 2014-11-25 | 5 | 3 | 2 | [10 empty] | 2014-12-03 | 2014-12-18 | 11 | 0 | 11 | [10 empty] | 2015-08-14 | 2014-11-24 | 2016-08-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | REHOBOTH | 175438 | 2769 | 1000 | Solar | 05_7L4 | 2014-11-24 | 2014-11-25 | 5 | 3 | 2 | [10 empty] | 2014-12-03 | 2014-12-18 | 11 | 0 | 11 | [10 empty] | 2015-08-14 |  | 2025-11-10 |  | STD |  | 2021-10-20 |  | 909 | 852 | 57 |  |  |  | Construction |  | No
National Grid | CHARLTON | 175439 | 1507 | 1000 | Solar | 01_406L1 | 2014-11-24 | 2014-11-25 | 5 | 2 | 3 | [10 empty] | 2014-12-03 | 2015-01-02 | 20 | 0 | 20 | [10 empty] | 2015-07-16 |  | 2016-08-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | CHARLEMONT | 175440 | 1339 | 499 | Solar | 09_1007G1 | 2014-11-24 | 2014-11-25 | 6 | 5 | 1 | [10 empty] | 2014-12-04 | 2015-01-05 | 20 | 0 | 20 | [12 empty] | 2015-05-15 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WEST BROOKFIELD | 175404 | 1585 | 0 |  |  | 2014-11-25 | 2014-11-24 | 5 | 0 | 5 | [26 empty] | 2014-11-25 | 2014-12-17 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BEVERLY | 175468 | 1915 | 4.73 | Solar | 12_51L3 | 2014-11-25 | 2014-11-26 | 5 | 0 | 5 | 2014-12-04 | 2014-12-04 | 0 | 0 | 0 | [20 empty] | 2015-02-18 |  | 2015-04-30 | Yes | EXP |  | 2015-05-08 | 2015-05-08 | 0 | 0 | 0 | 2015-03-09 | 2015-03-09 | 2015-11-23 | Connected |  | No
National Grid | WEST BROOKFIELD | 175469 | 1585 | 2250 | Solar | 01_525L2 | 2014-11-25 | 2014-11-26 | 6 | 3 | 3 | [10 empty] | 2014-12-05 | 2015-01-06 | 20 | 0 | 20 | [12 empty] | 2015-07-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WEBSTER | 175472 | 1570 | 762 | Solar | 01_412L2 | 2014-11-26 | 2014-12-02 | 28 | 28 | 0 | [10 empty] | 2015-01-13 | 2015-02-04 | 15 | 0 | 15 | [10 empty] | 2015-11-23 | 2014-11-26 | 2016-03-16 |  | STD |  | 2017-08-11 | 2017-09-09 | 20 | 0 | 20 |  |  |  | Withdrawn |  | No
National Grid | WEBSTER | 177152 | 1570 | 762 | Solar | 01_412L2 | 2014-11-26 | 2014-12-02 | 28 | 0 | 28 | [10 empty] | 2015-01-13 | 2015-02-04 | 15 | 0 | 15 | [10 empty] | 2015-11-26 |  | 2017-12-31 | Yes | STD |  | 2017-08-11 | 2017-09-09 | 20 | 0 | 20 | 2017-12-01 | 2017-12-01 | 2017-12-19 | Connected |  | No
National Grid | RUTLAND | 175471 | 1543 | 4.75 | Solar | 01_55W1 | 2014-12-01 | 2014-12-02 | 6 | 5 | 1 | [10 empty] | 2014-12-10 | 2015-01-02 | 15 | 0 | 15 | [10 empty] | 2015-01-02 | 2014-12-02 | 2015-04-30 |  | STD | [6 empty] | 2015-06-03 | 2015-06-03 | 2015-06-10 | Connected |  | No
National Grid | SOUTHBRIDGE | 175473 | 1550 | 480 | Solar | 01_413L4 | 2014-12-02 | 2014-12-04 | 10 | 8 | 2 | [10 empty] | 2014-12-18 | 2015-01-09 | 14 | 0 | 14 | [5 empty] | 2015-08-11 | 2015-10-05 | 38 | 1 | 37 | 2016-02-05 |  | 2017-12-31 |  | STD |  | 2017-05-04 | 2017-12-12 | 147 | 0 | 147 | 2017-12-13 | 2017-12-13 | 2017-12-31 | Connected |  | No
National Grid | HARDWICK | 175475 | 1037 | 1000 | Solar | 09_501L2 | 2014-12-04 | 2014-12-05 | 5 | 3 | 2 | [10 empty] | 2014-12-12 | 2015-01-12 | 19 | 0 | 19 | [10 empty] | 2015-06-18 |  | 2017-03-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HARDWICK | 175476 | 1037 | 1000 | Solar | 09_501L2 | 2014-12-04 | 2014-12-05 | 5 | 3 | 2 | [10 empty] | 2014-12-12 | 2015-01-12 | 19 | 0 | 19 | [10 empty] | 2015-06-18 |  | 2017-03-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 175504 | 1507 | 1000 | Solar | 01_406L3 | 2014-12-04 | 2014-12-05 | 5 | 3 | 2 | [10 empty] | 2014-12-12 | 2015-01-13 | 20 | 0 | 20 | [10 empty] | 2015-07-30 |  | 2016-10-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 175505 | 1507 | 1000 | Solar | 01_406L3 | 2014-12-04 | 2014-12-05 | 5 | 3 | 2 | [10 empty] | 2014-12-12 | 2015-01-13 | 20 | 0 | 20 | [10 empty] | 2015-07-30 |  | 2016-10-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SHEFFIELD | 175506 | 1257 | 1000 | Solar | 09_1109W1 | 2014-12-04 | 2014-12-05 | 5 | 3 | 2 | [10 empty] | 2014-12-12 | 2015-01-30 | 32 | 0 | 32 | [10 empty] | 2015-06-19 |  | 2016-10-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SHEFFIELD | 175507 | 1257 | 1000 | Solar | 09_1109W1 | 2014-12-04 | 2014-12-05 | 5 | 3 | 2 | [10 empty] | 2014-12-12 | 2015-01-30 | 32 | 0 | 32 | [10 empty] | 2015-06-19 |  | 2016-10-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SHEFFIELD | 175508 | 1257 | 630 | Solar | 09_1109W1 | 2014-12-04 | 2014-12-05 | 5 | 2 | 3 | [10 empty] | 2014-12-12 | 2015-01-30 | 32 | 0 | 32 | [12 empty] | 2015-08-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | OXFORD | 175509 | 1540 | 1000 | Solar | 01_406L3 | 2014-12-04 | 2014-12-05 | 5 | 2 | 3 | [10 empty] | 2014-12-12 | 2015-01-13 | 20 | 0 | 20 | [10 empty] | 2015-07-30 |  | 2016-10-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | OXFORD | 175510 | 1540 | 1000 | Solar | 01_406L3 | 2014-12-04 | 2014-12-05 | 5 | 2 | 3 | [10 empty] | 2014-12-12 | 2015-01-13 | 20 | 0 | 20 | [10 empty] | 2015-07-30 |  | 2016-10-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTHAMPTON | 175539 | 1062 | 1000 | Solar | 09_901W3 | 2014-12-04 | 2014-12-05 | 4 | 1 | 3 | [10 empty] | 2014-12-11 | 2015-01-09 | 19 | 0 | 19 | [12 empty] | 2015-04-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | OXFORD | 175540 | 1540 | 1000 | Solar | 01_406L3 | 2014-12-04 | 2014-12-05 | 5 | 2 | 3 | [10 empty] | 2014-12-12 | 2015-01-13 | 20 | 0 | 20 | [10 empty] | 2015-07-30 | 2014-12-05 | 2016-10-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SOUTHBRIDGE | 175474 | 1550 | 984 | Solar | 01_413L4 | 2014-12-05 | 2014-12-05 | 5 | 5 | 0 | [10 empty] | 2014-12-12 | 2015-01-09 | 18 | 18 | 0 | [5 empty] | 2015-08-11 | 2015-10-05 | 39 | 39 | 0 | 2016-02-05 | 2014-12-05 | 2017-12-31 |  | STD |  | 2017-05-04 | 2017-12-12 | 147 | 0 | 147 | 2017-12-13 | 2017-12-13 | 2017-12-31 | Connected |  | No
National Grid | WEBSTER | 175511 | 1570 | 140 | Solar | 01_412L1 | 2014-12-05 | 2014-12-08 | 4 | 4 | 0 | 2014-12-12 | 2014-12-12 | 0 | 0 | 0 | [20 empty] | 2015-02-25 |  | 2015-04-30 | Yes | EXP |  | 2015-06-01 | 2015-07-08 | 25 | 0 | 25 | 2015-02-25 | 2015-02-25 | 2015-08-21 | Connected |  | No
National Grid | WEBSTER | 175512 | 1570 | 75 | Solar | 01_412L1 | 2014-12-05 | 2014-12-08 | 4 | 1 | 3 | 2014-12-12 | 2014-12-12 | 0 | 0 | 0 | [20 empty] | 2014-12-12 | 2014-12-05 | 2015-04-30 |  | EXP | [6 empty] | 2015-02-04 | 2015-02-04 | 2015-07-10 | Connected |  | No
National Grid | BARRE | 175541 | 1005 | 380 | Solar | 09_604W4 | 2014-12-05 | 2014-12-08 | 4 | 0 | 4 | [10 empty] | 2014-12-12 | 2015-01-13 | 20 | 0 | 20 | [5 empty] | 2016-05-09 | 2016-05-09 | 0 | 0 | 0 | 2015-12-22 | 2014-12-05 | 2018-03-31 |  | STD |  | 2018-01-03 | 2018-02-20 | 32 | 0 | 32 | 2018-02-21 | 2018-02-21 | 2018-03-06 | Connected |  | No
National Grid | BARRE | 175542 | 1005 | 540 | Solar | 09_604W4 | 2014-12-05 | 2014-12-08 | 4 | 0 | 4 | [10 empty] | 2014-12-12 | 2015-01-13 | 20 | 0 | 20 | [10 empty] | 2015-12-22 |  | 2018-03-31 |  | STD |  | 2018-01-03 | 2018-02-20 | 32 | 0 | 32 | 2018-02-21 | 2018-02-21 | 2018-03-06 | Connected |  | No
National Grid | BARRE | 175543 | 1005 | 557 | Solar | 09_604W4 | 2014-12-05 | 2014-12-08 | 4 | 0 | 4 | [10 empty] | 2014-12-12 | 2015-01-13 | 20 | 0 | 20 | [11 empty] | 2014-12-05 | 2015-10-31 |  | STD |  | 2018-01-03 | 2018-02-20 | 32 | 0 | 32 |  |  |  | Withdrawn |  | No
National Grid | BARRE | 175544 | 1005 | 1000 | Solar | 09_604W4 | 2014-12-05 | 2014-12-08 | 4 | 0 | 4 | [10 empty] | 2014-12-12 | 2015-01-13 | 20 | 0 | 20 | [10 empty] | 2015-12-22 | 2014-12-05 | 2018-03-31 |  | STD |  | 2018-01-03 | 2018-02-20 | 32 | 0 | 32 | 2018-02-21 | 2018-02-21 | 2018-03-06 | Connected |  | No
National Grid | WILLIAMSBURG | 175545 | 1096 | 990 | Solar | 09_909W3 | 2014-12-05 | 2014-12-08 | 4 | 0 | 4 | [10 empty] | 2014-12-12 | 2015-01-13 | 20 | 0 | 20 | [5 empty] | 2016-10-19 | 2016-10-19 | 0 | 0 | 0 | 2015-06-10 | 2014-12-05 | 2016-12-31 |  | STD | [6 empty] | 2017-07-06 | 2017-07-06 | 2017-07-06 | Connected |  | No
National Grid | GOSHEN | 175546 | 1032 | 852 | Solar | 09_909W3 | 2014-12-05 | 2014-12-08 | 4 | 0 | 4 | [10 empty] | 2014-12-12 | 2015-01-13 | 20 | 0 | 20 | [5 empty] | 2016-10-19 | 2016-10-19 | 0 | 0 | 0 | 2015-06-10 | 2014-12-05 | 2016-12-31 |  | STD | [6 empty] | 2017-07-06 | 2017-07-06 | 2017-07-06 | Connected |  | No
National Grid | HOPEDALE | 175574 | 1747 | 490 | Solar | 05_335W3 | 2014-12-05 | 2014-12-08 | 4 | 1 | 3 | 2014-12-12 | 2014-12-12 | 0 | 0 | 0 | [20 empty] | 2015-02-25 |  | 2015-07-31 | Yes | EXP |  | 2015-08-24 | 2015-11-16 | 57 | 0 | 57 | 2015-05-07 | 2015-05-07 | 2015-11-20 | Connected |  | No
National Grid | LANCASTER | 175575 | 1523 | 22.8 | Solar | 01_225W1 | 2014-12-09 | 2014-12-10 | 4 | 3 | 1 | 2014-12-16 | 2014-12-16 | 0 | 0 | 0 | [20 empty] | 2014-12-31 |  | 2015-02-28 |  | EXP | [6 empty] | 2015-04-09 | 2015-04-09 | 2015-09-25 | Connected |  | No
National Grid | SUTTON | 175576 | 1590 | 20 | Solar | 01_304W2 | 2014-12-09 | 2014-12-10 | 4 | 2 | 2 | 2014-12-16 | 2015-11-09 | 223 | 0 | 223 | [20 empty] | 2014-12-16 |  | 2015-02-28 |  | EXP | [6 empty] | 2015-01-28 | 2015-01-28 |  | Withdrawn |  | No
National Grid | WILBRAHAM | 175577 | 1095 | 15.2 | Solar | 09_507L2 | 2014-12-09 | 2014-12-10 | 4 | 2 | 2 | 2014-12-16 | 2014-12-16 | 0 | 0 | 0 | [20 empty] | 2014-12-16 |  | 2015-02-28 |  | EXP | [6 empty] | 2015-02-20 | 2015-02-20 | 2015-09-30 | Connected |  | No
National Grid | CHARLTON | 175578 | 1507 | 30 | Solar | 01_415L2 | 2014-12-09 | 2014-12-10 | 16 | 14 | 2 | [27 empty] | 2015-03-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FOXBOROUGH | 178777 | 2035 | 17.6 | Solar | 05_3424W5 | 2014-12-09 | 2014-12-10 | 4 | 2 | 2 | 2014-12-16 | 2016-08-10 | 409 | 0 | 409 | [20 empty] | 2014-12-16 |  | 2015-02-28 |  | EXP | [6 empty] | 2015-02-20 | 2015-02-20 |  | Withdrawn |  | Yes
National Grid | LANCASTER | 175579 | 1523 | 150 | Solar | 01_227W1 | 2014-12-10 | 2014-12-11 | 27 | 6 | 21 | 2015-01-22 | 2015-01-22 | 0 | 0 | 0 | [20 empty] | 2015-02-03 |  | 2015-02-28 |  | EXP | [6 empty] | 2015-02-03 | 2015-02-03 | 2015-04-22 | Connected |  | No
National Grid | BARRE | 175580 | 1005 | 984 | Solar | 09_604W1 | 2014-12-10 | 2014-12-11 | 12 | 10 | 2 | [10 empty] | 2014-12-30 | 2015-01-23 | 16 | 0 | 16 | [12 empty] | 2016-11-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | UPTON | 175581 | 1568 | 13.6 | Solar | 05_320W1 | 2014-12-12 | 2014-12-15 | 38 | 38 | 0 | 2015-02-10 | 2015-02-10 | 0 | 0 | 0 | [20 empty] | 2015-02-11 |  | 2015-04-30 |  | EXP | [6 empty] | 2016-02-05 | 2016-02-05 | 2016-02-05 | Connected |  | No
National Grid | DUDLEY | 175582 | 1571 | 19 | Solar | 01_412L4 | 2014-12-14 | 2014-12-15 | 6 | 4 | 2 | 2014-12-23 | 2014-12-23 | 0 | 0 | 0 | [20 empty] | 2015-01-06 |  | 2015-02-28 |  | EXP | [6 empty] | 2016-01-07 | 2016-01-07 | 2016-01-07 | Connected |  | No
National Grid | BARRE | 175610 | 1005 | 480 | Solar | 09_604W1 | 2014-12-15 | 2014-12-16 | 5 | 3 | 2 | [10 empty] | 2014-12-23 | 2015-01-23 | 20 | 0 | 20 | [11 empty] | 2014-12-16 | 2016-11-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH ANDOVER | 175611 | 1845 | 3384 | Solar | 14_43L7 | 2014-12-16 | 2014-12-17 | 4 | 1 | 3 | [10 empty] | 2014-12-23 | 2015-12-02 | 233 | 232 | 1 | [5 empty] | 2015-12-07 | 2015-12-07 | 0 | 0 | 0 | 2016-05-01 |  | 2023-04-01 | Yes | STD |  | 2016-12-16 | 2016-12-16 | 0 | 0 | 0 | 2017-04-11 | 2017-04-11 | 2023-04-03 | Connected |  | No
National Grid | NORTH ANDOVER | 175612 | 1845 | 2000 | Solar | 14_2358 | 2014-12-16 | 2014-12-17 | 4 | 0 | 4 | [10 empty] | 2014-12-23 | 2015-01-23 | 20 | 0 | 20 | [12 empty] | 2015-12-01 |  | STD |  | 2016-12-16 | 2017-08-31 | 177 | 0 | 177 |  |  |  | Withdrawn |  | No
National Grid | SOMERSET | 175613 | 2726 | 258 | Solar | 05_19W72 | 2014-12-16 | 2014-12-17 | 25 | 25 | 0 | [26 empty] | 2014-12-16 | 2015-04-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SOMERSET | 175614 | 2726 | 240 | Solar | 05_11W82 | 2014-12-16 | 2014-12-17 | 4 | 2 | 2 | 2014-12-23 | 2014-12-23 | 0 | 0 | 0 | [20 empty] | 2015-01-23 |  | 2015-04-30 |  | EXP | [6 empty] | 2016-04-06 | 2016-04-06 | 2016-04-06 | Connected |  | No
National Grid | STOUGHTON | 175615 | 2072 | 27.3 | Solar | 07_913W47 | 2014-12-16 | 2014-12-17 | 4 | 3 | 1 | 2014-12-23 | 2014-12-23 | 0 | 0 | 0 | [20 empty] | 2015-01-05 | 2014-12-16 | 2015-04-15 |  | EXP | [6 empty] | 2015-02-19 | 2015-02-19 | 2015-07-02 | Connected |  | No
National Grid | HALIFAX | 175616 | 2338 | 23.4 | Solar | 07_797W24 | 2014-12-16 | 2014-12-17 | 8 | 7 | 1 | 2014-12-30 | 2014-12-30 | 0 | 0 | 0 | [20 empty] | 2015-01-21 |  | 2016-12-31 | Yes | EXP |  | 2015-11-02 | 2015-11-10 | 6 | 0 | 6 | 2015-01-22 | 2015-01-22 | 2016-06-17 | Connected |  | Yes
National Grid | BELCHERTOWN | 175644 | 1007 | 3.23 | Solar | 09_527L1 | 2014-12-16 | 2014-12-17 | 8 | 7 | 1 | 2014-12-30 | 2014-12-30 | 0 | 0 | 0 | [20 empty] | 2015-01-21 |  | 2016-12-31 |  | EXP | [6 empty] | 2015-07-20 | 2015-07-20 | 2016-01-08 | Connected |  | No
National Grid | SALEM | 175645 | 1970 | 5.16 | Solar | 12_29W4 | 2014-12-16 | 2014-12-17 | 8 | 6 | 2 | 2014-12-30 | 2014-12-30 | 0 | 0 | 0 | [20 empty] | 2015-01-22 |  | 2015-02-16 |  | EXP | [6 empty] | 2015-06-11 | 2015-06-11 | 2015-10-21 | Connected |  | No
National Grid | SALEM | 175646 | 1970 | 5.16 | Solar | 12_29W4 | 2014-12-16 | 2014-12-17 | 8 | 6 | 2 | 2014-12-30 | 2014-12-30 | 0 | 0 | 0 | [20 empty] | 2015-01-22 |  | 2015-02-16 |  | EXP | [6 empty] | 2015-02-20 | 2015-02-20 | 2015-10-21 | Connected |  | No
National Grid | BEVERLY | 175647 | 1915 | 3.66 | Solar | 12_12L2 | 2014-12-16 | 2014-12-17 | 8 | 6 | 2 | 2014-12-30 | 2014-12-30 | 0 | 0 | 0 | [20 empty] | 2015-01-06 |  | 2015-02-16 |  | EXP | [6 empty] | 2015-03-27 | 2015-03-27 | 2015-09-29 | Connected |  | No
National Grid | BILLERICA | 175648 | 1821 | 4.73 | Solar | 14_92L1 | 2014-12-16 | 2014-12-17 | 8 | 6 | 2 | 2014-12-30 | 2014-12-30 | 0 | 0 | 0 | [20 empty] | 2015-01-06 |  | 2015-02-16 |  | EXP | [6 empty] | 2015-02-19 | 2015-02-19 | 2015-12-10 | Connected |  | No
National Grid | LYNN | 175649 | 1902 | 5.38 | Solar | 12_1384 | 2014-12-16 | 2014-12-17 | 8 | 6 | 2 | 2014-12-30 | 2015-02-06 | 26 | 0 | 26 | [22 empty] | 2015-02-16 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH ANDOVER | 178778 | 1845 | 2000 | Solar | 14_2358 | 2014-12-16 | 2014-12-17 | 4 | 0 | 4 | [10 empty] | 2014-12-23 | 2015-01-23 | 20 | 0 | 20 | [10 empty] | 2015-09-30 |  | 2016-12-31 |  | STD |  | 2016-12-16 | 2018-01-26 | 271 | 0 | 271 |  |  |  | Withdrawn |  | No
National Grid | NORTH ANDOVER | 178779 | 1845 | 2000 | Solar | 14_2358 | 2014-12-16 | 2014-12-17 | 4 | 0 | 4 | [10 empty] | 2014-12-23 | 2015-01-23 | 20 | 0 | 20 | [10 empty] | 2015-09-30 | 2014-12-17 | 2016-12-31 |  | STD |  | 2016-12-16 | 2018-02-14 | 284 | 0 | 284 |  |  |  | Withdrawn |  | No
National Grid | CHARLTON | 175650 | 1507 | 18 | Solar | 01_406L1 | 2014-12-17 | 2014-12-18 | 5 | 1 | 4 | 2014-12-26 | 2014-12-26 | 0 | 0 | 0 | [20 empty] | 2015-01-21 | 2014-12-17 | 2016-12-31 | Yes | EXP | [6 empty] | 2016-08-30 | 2016-08-30 | 2016-08-30 | Connected |  | No
National Grid | CHARLTON | 175651 | 1507 | 1000 | Solar | 01_415L1 | 2014-12-17 | 2014-12-18 | 7 | 5 | 2 | [25 empty] | 2016-01-29 | 2014-12-17 | 2018-05-29 | Yes | STD | [8 empty] | 2018-07-02 | Connected |  | No
National Grid | CHARLTON | 175652 | 1507 | 499 | Solar | 01_415L1 | 2014-12-17 | 2014-12-18 | 7 | 5 | 2 | [25 empty] | 2016-01-29 |  | 2018-05-25 | Yes | STD | [8 empty] | 2018-07-02 | Connected |  | No
National Grid | WORCESTER | 175679 | 1606 | 30 | Solar | 01_24W3 | 2014-12-18 | 2014-12-19 | 6 | 1 | 5 | 2014-12-30 | 2014-12-30 | 0 | 0 | 0 | [20 empty] | 2015-01-08 | 2014-12-19 | 2015-02-28 |  | EXP | [6 empty] | 2015-04-06 | 2015-04-06 | 2015-06-01 | Connected |  | No
National Grid | MILLBURY | 175680 | 1527 | 97.5 | Solar | 01_304W5 | 2014-12-19 | 2014-12-22 | 5 | 0 | 5 | 2014-12-30 | 2014-12-30 | 0 | 0 | 0 | [20 empty] | 2015-01-12 | 2014-12-23 | 2016-12-31 | Yes | EXP |  | 2015-12-10 | 2016-01-19 | 25 | 0 | 25 | 2015-04-01 | 2015-04-01 | 2016-04-08 | Connected |  | No
National Grid | BILLERICA | 175685 | 1862 | 4999 | Solar | 14_2385 | 2014-12-23 | 2014-12-26 | 16 | 15 | 1 | [10 empty] | 2015-01-21 | 2015-01-21 | 0 | 0 | 0 | [10 empty] | 2015-07-30 |  | 2017-05-31 | Yes | STD |  | 2017-01-16 | 2017-07-27 | 133 | 0 | 133 | 2017-06-05 | 2017-06-05 | 2017-06-07 | Connected |  | No
National Grid | OXFORD | 175686 | 1540 | 17 | Solar | 01_406L4 | 2014-12-23 | 2014-12-24 | 8 | 5 | 3 | 2015-01-07 | 2015-01-07 | 0 | 0 | 0 | [20 empty] | 2015-01-30 | 2014-12-23 | 2015-04-30 |  | EXP | [6 empty] | 2015-02-20 | 2015-02-20 | 2015-11-12 | Connected |  | No
National Grid | CHARLTON | 175687 | 1507 | 1000 | Solar | 01_415L1 | 2014-12-23 | 2014-12-24 | 5 | 0 | 5 | [25 empty] | 2016-01-29 | 2014-12-24 | 2018-05-25 | Yes | STD | [8 empty] | 2018-07-02 | Connected |  | No
National Grid | LAWRENCE | 175682 | 1841 | 115.2 | Solar | 14_6J2 | 2014-12-24 | 2014-12-26 | 4 | 0 | 4 | 2015-01-02 | 2015-01-02 | 0 | 0 | 0 | [20 empty] | 2015-02-03 | 2014-12-24 | 2016-01-19 | Yes | EXP |  | 2015-11-12 | 2016-09-01 | 200 | 0 | 200 | 2015-02-04 | 2015-02-04 | 2015-12-22 | Connected |  | No
National Grid | WORCESTER | 175683 | 1604 | 75.6 | Solar | 01_HT26 | 2014-12-24 | 2014-12-26 | 4 | 1 | 3 | 2015-01-02 | 2015-01-02 | 0 | 0 | 0 | [20 empty] | 2015-02-04 | 2014-12-24 | 2015-05-31 |  | EXP | [6 empty] | 2015-02-04 | 2015-02-04 | 2015-10-28 | Connected |  | Yes
National Grid | WORCESTER | 175684 | 1609 | 75.6 | Solar | 01_9J327 | 2014-12-24 | 2014-12-26 | 4 | 1 | 3 | 2015-01-02 | 2015-06-02 | 102 | 3 | 99 | [22 empty] | 2015-05-31 | Yes | EXP | [9 empty] | Withdrawn |  | No
National Grid | NEWBURYPORT | 175714 | 1950 | 64 | Solar | 14_36L2 | 2014-12-24 | 2014-12-24 | 7 | 4 | 3 | 2015-01-06 | 2015-02-17 | 28 | 0 | 28 | [20 empty] | 2015-02-17 |  | 2016-12-31 |  | EXP | [6 empty] | 2015-02-17 | 2015-02-17 |  | Withdrawn |  | No
National Grid | OXFORD | 175716 | 1540 | 1000 | Solar | 01_406L3 | 2014-12-26 | 2014-12-29 | 11 | 9 | 2 | [10 empty] | 2015-01-14 | 2015-02-13 | 21 | 0 | 21 | [10 empty] | 2015-10-05 |  | 2016-08-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | DIGHTON | 175717 | 2715 | 1000 | Solar | 05_19W74 | 2014-12-26 | 2014-12-29 | 17 | 15 | 2 | [26 empty] | 2014-12-29 | 2015-08-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | CHELMSFORD | 175222 | 1824 | 225 | Solar | 14_73L1 | 2014-12-29 | 2014-12-29 | 1 | 0 | 1 | 2014-12-30 | 2014-12-30 | 0 | 0 | 0 | [20 empty] | 2015-03-14 | 2014-12-29 | 2015-06-30 |  | EXP |  | 2015-03-11 | 2015-04-06 | 17 | 0 | 17 | 2015-05-13 | 2015-05-13 | 2015-06-01 | Connected |  | No
National Grid | LOWELL | 175719 | 1852 | 120.9 | Solar | 14_3L5 | 2014-12-29 | 2014-12-30 | 8 | 6 | 2 | 2015-01-12 | 2015-01-12 | 0 | 0 | 0 | [20 empty] | 2015-02-03 | 2014-12-29 | 2015-05-31 |  | EXP | [6 empty] | 2015-02-04 | 2015-02-04 | 2015-11-25 | Connected |  | No
National Grid | CHELMSFORD | 175753 | 1824 | 300 | Solar | 14_16L4 | 2014-12-29 | 2014-12-29 | 1 | 0 | 1 | 2014-12-30 | 2014-12-30 | 0 | 0 | 0 | [20 empty] | 2015-03-04 | 2014-12-29 | 2015-06-30 |  | EXP |  | 2015-03-10 | 2015-06-26 | 74 | 0 | 74 | 2015-05-22 | 2015-05-22 | 2015-05-22 | Connected |  | No
National Grid | CHELMSFORD | 175754 | 1824 | 100 | Solar | 14_16L4 | 2014-12-29 | 2014-12-29 | 1 | 0 | 1 | 2014-12-30 | 2014-12-30 | 0 | 0 | 0 | [20 empty] | 2015-03-14 | 2014-12-29 | 2015-06-30 |  | EXP |  | 2015-03-06 | 2015-05-06 | 41 | 0 | 41 | 2015-06-01 | 2015-06-01 | 2015-06-01 | Connected |  | No
National Grid | CHELMSFORD | 175755 | 1824 | 325 | Solar | 14_24L1 | 2014-12-29 | 2014-12-29 | 1 | 0 | 1 | 2014-12-30 | 2014-12-30 | 0 | 0 | 0 | [20 empty] | 2015-03-14 | 2014-12-29 | 2015-06-30 |  | EXP |  | 2015-03-10 | 2015-04-24 | 31 | 0 | 31 | 2015-05-22 | 2015-05-22 | 2015-05-26 | Connected |  | No
National Grid | CHELMSFORD | 175756 | 1824 | 225 | Solar | 14_73L1 | 2014-12-29 | 2014-12-29 | 1 | 0 | 1 | 2014-12-30 | 2014-12-30 | 0 | 0 | 0 | [20 empty] | 2015-03-14 | 2014-12-29 | 2015-06-30 |  | EXP |  | 2015-03-10 | 2015-04-24 | 31 | 0 | 31 | 2015-06-02 | 2015-06-02 | 2015-07-13 | Connected |  | No
National Grid | CHELMSFORD | 175757 | 1824 | 295 | Solar | 14_73L1 | 2014-12-29 | 2014-12-29 | 1 | 0 | 1 | 2014-12-30 | 2014-12-30 | 0 | 0 | 0 | [20 empty] | 2015-03-09 | 2014-12-29 | 2015-06-30 |  | EXP |  | 2015-03-10 | 2015-04-28 | 33 | 0 | 33 | 2015-05-22 | 2015-05-22 | 2015-05-22 | Connected |  | No
National Grid | CHELMSFORD | 175758 | 1824 | 150 | Solar | 14_24L3 | 2014-12-29 | 2014-12-29 | 1 | 0 | 1 | 2014-12-30 | 2014-12-30 | 0 | 0 | 0 | [20 empty] | 2015-03-09 | 2014-12-29 | 2015-06-30 |  | EXP |  | 2015-03-06 | 2015-05-06 | 41 | 0 | 41 | 2015-06-01 | 2015-06-01 | 2015-06-01 | Connected |  | No
National Grid | CHELMSFORD | 175759 | 1824 | 225 | Solar | 14_24L2 | 2014-12-29 | 2014-12-29 | 1 | 0 | 1 | 2014-12-30 | 2014-12-30 | 0 | 0 | 0 | [20 empty] | 2015-03-14 | 2014-12-29 | 2015-06-30 |  | EXP |  | 2015-03-11 | 2015-04-24 | 30 | 0 | 30 | 2015-05-26 | 2015-05-26 | 2015-05-26 | Connected |  | No
National Grid | CHELMSFORD | 175760 | 1824 | 75 | Solar | 14_16L1 | 2014-12-29 | 2014-12-29 | 1 | 0 | 1 | 2014-12-30 | 2014-12-30 | 0 | 0 | 0 | [20 empty] | 2015-03-09 |  | 2015-06-30 |  | EXP |  | 2015-03-06 | 2015-04-28 | 35 | 0 | 35 | 2015-06-02 | 2015-06-02 | 2015-06-02 | Connected |  | No
National Grid | SPENCER | 175715 | 1562 | 1500 | Solar | 01_552L1 | 2014-12-30 | 2014-12-30 | 15 | 14 | 1 | [10 empty] | 2015-01-22 | 2015-02-24 | 22 | 0 | 22 | [12 empty] | 2015-06-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ATTLEBORO | 175718 | 2703 | 475 | Solar | 05_9L4 | 2014-12-30 | 2014-12-30 | 6 | 1 | 5 | 2015-01-08 | 2015-08-03 | 140 | 0 | 140 | 2015-03-03 | 2015-08-03 | 104 | 0 | 104 | [5 empty] | 2015-03-03 | 2015-08-03 | 104 | 0 | 104 | [7 empty] | 2015-08-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | RUTLAND | 175720 | 1543 | 499 | Solar | 01_55W1 | 2014-12-31 | 2015-01-02 | 9 | 9 | 0 | [10 empty] | 2015-01-15 | 2015-02-12 | 19 | 4 | 15 | [12 empty] | 2015-06-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MILFORD | 175722 | 1757 | 16 | Solar | 05_335W3 | 2014-12-31 | 2015-01-02 | 13 | 11 | 2 | 2015-01-22 | 2015-01-22 | 0 | 0 | 0 | [20 empty] | 2015-02-03 |  | 2015-05-31 |  | EXP | [6 empty] | 2015-06-09 | 2015-06-09 | 2016-03-01 | Connected |  | No
National Grid | PEPPERELL | 175223 | 1463 | 5 | Solar | 01_226L1 | 2015-01-05 | 2015-01-06 | 28 | 25 | 3 | 2015-02-17 | 2015-02-17 | 0 | 0 | 0 | [20 empty] | 2015-02-17 |  | 2015-05-31 |  | EXP | [6 empty] | 2015-05-11 | 2015-05-11 | 2016-02-11 | Connected |  | No
National Grid | WILLIAMSTOWN | 175723 | 1267 | 1187 | Natural Gas | 09_1003W1 | 2015-01-05 | 2015-01-05 | 12 | 10 | 2 | [10 empty] | 2015-01-22 | 2015-02-04 | 9 | 0 | 9 | [10 empty] | 2015-12-03 |  | 2016-12-31 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | WEST NEWBURY | 175224 | 1985 | 19 | Solar | 14_47L2 | 2015-01-06 | 2015-01-07 | 43 | 40 | 3 | 2015-03-11 | 2016-08-05 | 349 | 0 | 349 | [20 empty] | 2015-03-12 |  | 2015-05-01 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LYNN | 175225 | 1904 | 11.25 | Solar | 12_24W1 | 2015-01-06 | 2015-01-07 | 10 | 7 | 3 | 2015-01-22 | 2015-01-22 | 0 | 0 | 0 | [20 empty] | 2015-02-04 |  | 2015-05-31 |  | EXP | [6 empty] | 2015-02-20 | 2015-02-20 | 2015-07-06 | Connected |  | No
National Grid | WESTFORD | 175226 | 1886 | 12 | Solar | 14_57L3 | 2015-01-06 | 2015-01-07 | 8 | 4 | 4 | 2015-01-17 | 2015-01-17 | 0 | 0 | 0 | [20 empty] | 2015-02-02 | 2015-01-06 | 2015-05-31 |  | EXP | [6 empty] | 2015-10-01 | 2015-10-01 | 2016-06-06 | Connected |  | No
National Grid | LYNN | 175227 | 1904 | 7.6 | Solar | 12_29W4 | 2015-01-06 | 2015-01-07 | 4 | 0 | 4 | 2015-01-13 | 2015-01-13 | 0 | 0 | 0 | [20 empty] | 2015-02-13 |  | 2016-12-31 | Yes | EXP |  | 2015-11-16 | 2015-12-29 | 29 | 0 | 29 | 2015-04-16 | 2015-04-16 | 2016-06-14 | Connected |  | No
National Grid | EAST BRIDGEWATER | 175228 | 2333 | 17.6 | Solar | 07_797W23 | 2015-01-06 | 2015-01-06 | 9 | 4 | 5 | 2015-01-17 | 2015-01-17 | 0 | 0 | 0 | [20 empty] | 2015-02-02 |  | 2015-05-31 |  | EXP | [6 empty] | 2015-10-06 | 2015-10-06 | 2016-06-17 | Connected |  | No
National Grid | SWANSEA | 175229 | 2777 | 483 | Solar | 05_11W84 | 2015-01-07 | 2015-01-08 | 14 | 12 | 2 | [10 empty] | 2015-01-29 | 2015-02-27 | 20 | 0 | 20 | [10 empty] | 2015-07-06 |  | 2015-05-31 |  | STD | [6 empty] | 2015-07-06 | 2015-07-06 | 2016-02-01 | Connected |  | No
National Grid | SEEKONK | 175230 | 2771 | 230 | Solar | 05_7L3 | 2015-01-07 | 2015-01-08 | 7 | 5 | 2 | 2015-01-19 | 2015-01-19 | 0 | 0 | 0 | [20 empty] | 2015-02-12 |  | 2015-05-31 |  | EXP | [6 empty] | 2015-03-09 | 2015-03-09 | 2015-07-29 | Connected |  | No
National Grid | WARREN | 175255 | 1083 | 480 | Solar | 09_516L2 | 2015-01-07 | 2015-01-08 | 10 | 8 | 2 | 2015-01-23 | 2016-12-06 | 464 | 0 | 464 | [20 empty] | 2015-03-19 |  | 2016-12-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTBOROUGH | 175259 | 1581 | 138 | Solar | 05_312W2 | 2015-01-07 | 2015-01-08 | 4 | 0 | 4 | 2015-01-14 | 2015-01-14 | 0 | 0 | 0 | 2015-03-11 | 2015-06-23 | 70 | 30 | 40 | [5 empty] | 2015-03-11 | 2015-06-23 | 70 | 30 | 40 | [5 empty] | 2015-11-02 |  | 2016-12-31 |  | EXP | [6 empty] | 2015-11-02 | 2015-11-02 | 2017-06-21 | Connected |  | No
National Grid | WORCESTER | 175256 | 1606 | 56 | Solar | 01_24W3 | 2015-01-08 | 2015-01-09 | 4 | 2 | 2 | 2015-01-15 | 2015-01-15 | 0 | 0 | 0 | [20 empty] | 2015-02-02 |  | 2015-05-31 |  | EXP | [6 empty] | 2015-03-27 | 2015-03-27 | 2015-09-17 | Connected |  | No
National Grid | PLAINVILLE | 175257 | 2762 | 414 | Solar | 05_3337W1 | 2015-01-08 | 2015-01-09 | 9 | 8 | 1 | 2015-01-23 | 2015-01-23 | 0 | 0 | 0 | [20 empty] | 2015-02-20 |  | 2015-06-30 |  | EXP | [6 empty] | 2015-03-09 | 2015-03-09 | 2015-07-29 | Connected |  | No
National Grid | GARDNER | 175258 | 1440 | 42 | Solar | 01_607W1 | 2015-01-08 | 2015-01-09 | 4 | 2 | 2 | 2015-01-15 | 2016-09-30 | 425 | 0 | 425 | [20 empty] | 2015-02-02 |  | 2015-05-31 |  | EXP | [6 empty] | 2015-03-27 | 2015-03-27 |  | Withdrawn |  | No
National Grid | BROCKTON | 175260 | 2302 | 8 | Solar | 07_911W56 | 2015-01-09 | 2015-01-12 | 13 | 11 | 2 | 2015-01-30 | 2015-01-30 | 0 | 0 | 0 | [20 empty] | 2015-02-11 |  | 2015-05-31 |  | EXP | [6 empty] | 2015-03-05 | 2015-03-05 | 2015-06-01 | Connected |  | No
National Grid | EAST BRIDGEWATER | 175261 | 2333 | 22.8 | Solar | 07_797W24 | 2015-01-09 | 2015-01-12 | 5 | 2 | 3 | 2015-01-19 | 2015-01-19 | 0 | 0 | 0 | [20 empty] | 2015-03-03 |  | 2015-05-31 |  | EXP | [6 empty] | 2015-03-03 | 2015-03-03 | 2015-08-28 | Connected |  | No
National Grid | LEOMINSTER | 176051 | 1453 | 184 | Solar | 01_227W1 | 2015-01-12 | 2015-01-13 | 11 | 0 | 11 | 2015-01-29 | 2015-01-29 | 0 | 0 | 0 | [20 empty] | 2015-02-13 |  | 2015-07-31 |  | EXP | [6 empty] | 2015-02-17 | 2015-02-17 | 2016-02-04 | Connected |  | No
National Grid | ADAMS | 175262 | 1220 | 1000 | Solar | 09_1021W2 | 2015-01-13 | 2015-01-14 | 4 | 0 | 4 | [10 empty] | 2015-01-21 | 2015-02-20 | 21 | 0 | 21 | [12 empty] | 2015-07-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LEICESTER | 175263 | 1524 | 1000 | Solar | 01_21W1 | 2015-01-13 | 2015-01-14 | 4 | 0 | 4 | [10 empty] | 2015-01-21 | 2015-02-20 | 21 | 0 | 21 | [12 empty] | 2015-07-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | RUTLAND | 175294 | 1543 | 6 | Solar | 01_55W1 | 2015-01-13 | 2015-01-14 | 28 | 27 | 1 | 2015-02-25 | 2015-02-25 | 0 | 0 | 0 | [20 empty] | 2015-02-25 | 2015-01-14 | 2015-05-31 |  | EXP | [6 empty] | 2015-04-28 | 2015-04-28 | 2015-11-12 | Connected |  | No
National Grid | EAST BRIDGEWATER | 175295 | 2333 | 21.2 | Solar | 07_797W23 | 2015-01-14 | 2015-01-15 | 4 | 1 | 3 | 2015-01-22 | 2015-01-22 | 0 | 0 | 0 | [20 empty] | 2015-02-17 |  | 2016-12-31 | Yes | EXP |  | 2016-11-04 | 2016-11-15 | 6 | 0 | 6 | 2017-01-12 | 2017-01-12 | 2017-01-24 | Connected |  | No
National Grid | RUTLAND | 175296 | 1543 | 19.25 | Solar | 01_55W1 | 2015-01-14 | 2015-01-15 | 4 | 2 | 2 | 2015-01-22 | 2015-01-22 | 0 | 0 | 0 | [20 empty] | 2015-02-03 | 2015-01-15 | 2015-05-31 |  | EXP | [6 empty] | 2015-03-27 | 2015-03-27 | 2015-06-10 | Connected |  | No
National Grid | HAMPDEN | 175297 | 1036 | 499 | Solar | 09_139L3 | 2015-01-15 | 2015-01-16 | 4 | 0 | 4 | 2015-01-23 | 2015-01-23 | 0 | 0 | 0 | [20 empty] | 2015-03-03 |  | 2016-03-10 | Yes | EXP |  | 2015-11-04 | 2015-12-23 | 33 | 0 | 33 | 2016-01-25 | 2016-01-25 | 2016-01-25 | Connected |  | No
National Grid | LYNN | 175298 | 1904 | 5 | Solar | 12_29W4 | 2015-01-15 | 2015-01-17 | 43 | 43 | 0 | 2015-03-24 | 2015-03-24 | 0 | 0 | 0 | [20 empty] | 2015-03-27 |  | 2015-05-31 |  | EXP | [6 empty] | 2016-01-08 | 2016-01-08 | 2016-01-08 | Connected |  | No
National Grid | MARLBOROUGH | 175299 | 1752 | 300 | Solar | 05_311W4 | 2015-01-15 | 2015-01-19 | 3 | 1 | 2 | 2015-01-23 | 2015-01-23 | 0 | 0 | 0 | [20 empty] | 2015-02-03 | 2015-01-16 | 2015-05-31 |  | EXP | [6 empty] | 2015-02-03 | 2015-02-03 | 2015-09-18 | Connected |  | No
National Grid | LEICESTER | 175340 | 1524 | 1000 | Solar | 01_406L1 | 2015-01-16 | 2015-01-16 | 24 | 21 | 3 | [10 empty] | 2015-02-23 | 2015-04-21 | 39 | 0 | 39 | [5 empty] | 2015-09-30 | 2015-10-29 | 20 | 0 | 20 | 2015-10-29 | 2015-01-17 | 2018-03-31 |  | STD | [6 empty] | 2017-07-24 | 2017-07-24 | 2018-03-26 | Connected |  | No
National Grid | WESTMINSTER | 175300 | 1473 | 4875 | Solar | 01_602W2 | 2015-01-17 | 2015-01-19 | 29 | 29 | 0 | [10 empty] | 2015-03-03 | 2015-04-02 | 21 | 0 | 21 | [10 empty] | 2016-11-01 |  | 2021-06-07 | Yes | STD |  | 2020-10-28 | 2021-03-26 | 149 | 0 | 149 |  |  | 2021-06-04 | Connected |  | No
National Grid | WESTMINSTER | 175301 | 1473 | 1000 | Solar | 01_602W2 | 2015-01-17 | 2015-01-19 | 29 | 29 | 0 | [10 empty] | 2015-03-03 | 2015-04-02 | 21 | 0 | 21 | [10 empty] | 2016-11-01 | 2015-01-17 | 2019-10-16 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTMINSTER | 175302 | 1473 | 1000 | Solar | 01_602W2 | 2015-01-17 | 2015-01-19 | 29 | 29 | 0 | [10 empty] | 2015-03-03 | 2015-04-02 | 21 | 0 | 21 | [10 empty] | 2016-11-01 | 2015-01-17 | 2019-10-16 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTMINSTER | 175332 | 1473 | 1000 | Solar | 01_602W2 | 2015-01-17 | 2015-01-19 | 29 | 29 | 0 | [10 empty] | 2015-03-03 | 2015-04-02 | 21 | 0 | 21 | [10 empty] | 2016-11-01 |  | 2019-10-16 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTMINSTER | 175333 | 1473 | 1000 | Solar | 01_602W2 | 2015-01-17 | 2015-01-19 | 29 | 29 | 0 | [10 empty] | 2015-03-03 | 2015-04-02 | 21 | 0 | 21 | [10 empty] | 2016-11-01 |  | 2019-10-16 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LEICESTER | 175334 | 1524 | 800 | Solar | 01_21W2 | 2015-01-17 | 2015-01-20 | 40 | 40 | 0 | [10 empty] | 2015-03-19 | 2015-04-13 | 17 | 0 | 17 | [12 empty] | 2016-11-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LEICESTER | 175335 | 1524 | 800 | Solar | 01_21W2 | 2015-01-17 | 2015-01-20 | 40 | 40 | 0 | [10 empty] | 2015-03-19 | 2015-04-13 | 17 | 0 | 17 | [12 empty] | 2015-07-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LEICESTER | 175336 | 1524 | 1000 | Solar | 01_21W2 | 2015-01-17 | 2015-01-20 | 38 | 38 | 0 | [10 empty] | 2015-03-16 | 2015-04-13 | 19 | 0 | 19 | [5 empty] | 2016-04-07 | 2016-12-22 | 177 | 0 | 177 |  |  | 2016-11-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LEOMINSTER | 175337 | 1453 | 100 | Solar | 01_207W3 | 2015-01-19 | 2015-01-20 | 4 | 1 | 3 | 2015-01-26 | 2015-01-26 | 0 | 0 | 0 | [20 empty] | 2015-02-12 |  | 2015-06-30 |  | EXP | [6 empty] | 2015-02-12 | 2015-02-12 | 2015-06-11 | Connected |  | No
National Grid | PLAINVILLE | 175338 | 2762 | 615 | Solar | 05_3337W1 | 2015-01-20 | 2015-01-20 | 6 | 0 | 6 | [5 empty] | 2015-03-13 | 2015-05-12 | 40 | 40 | 0 | 2015-01-28 | 2015-02-25 | 19 | 0 | 19 | 2015-03-13 | 2015-05-12 | 40 | 40 | 0 | [5 empty] | 2015-08-05 | 2015-01-20 | 2015-09-01 |  | STD | [6 empty] | 2015-09-17 | 2015-09-17 | 2015-09-21 | Connected |  | No
National Grid | RUTLAND | 175339 | 1543 | 222 | Solar | 01_55W1 | 2015-01-20 | 2015-01-21 | 5 | 1 | 4 | 2015-01-28 | 2017-05-31 | 581 | 0 | 581 | 2015-03-27 | 2015-04-28 | 21 | 0 | 21 | [5 empty] | 2015-03-27 | 2015-04-28 | 21 | 0 | 21 | [5 empty] | 2015-05-05 |  | 2016-12-31 | Yes | EXP | [9 empty] | Withdrawn |  | No
National Grid | DOUGLAS | 175936 | 1516 | 22.8 | Solar | 05_320W2 | 2015-01-20 | 2015-01-21 | 5 | 1 | 4 | 2015-01-28 | 2015-01-28 | 0 | 0 | 0 | [20 empty] | 2015-02-20 |  | 2015-06-30 |  | EXP | [6 empty] | 2015-03-11 | 2015-03-11 | 2015-09-28 | Connected |  | No
National Grid | GLOUCESTER | 175937 | 1930 | 750 | Solar | 12_51T2 | 2015-01-20 | 2015-01-21 | 5 | 0 | 5 | [10 empty] | 2015-01-28 | 2015-02-25 | 19 | 0 | 19 | [12 empty] | 2015-08-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SOMERSET | 175974 | 2726 | 258 | Solar | 05_19W72 | 2015-01-20 | 2015-01-23 | 3 | 0 | 3 | 2015-01-28 | 2016-06-20 | 345 | 0 | 345 | 2015-03-11 | 2015-04-08 | 19 | 0 | 19 | [5 empty] | 2015-03-11 | 2015-04-08 | 19 | 0 | 19 | [5 empty] | 2015-04-17 | 2015-01-20 | 2016-12-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SOMERSET | 177262 | 2726 | 270 | Solar | 05_19W72 | 2015-01-20 | 2015-01-23 | 3 | 0 | 3 | 2015-01-28 | 2015-01-28 | 0 | 0 | 0 | 2015-03-11 | 2015-04-08 | 19 | 0 | 19 | [5 empty] | 2015-03-11 | 2015-04-08 | 19 | 0 | 19 | [5 empty] | 2015-04-17 |  | 2017-08-28 | Yes | EXP |  | 2016-05-13 | 2016-06-20 | 24 | 0 | 24 | 2016-11-02 | 2016-11-02 | 2016-11-07 | Connected |  | No
National Grid | BILLERICA | 175938 | 1821 | 16 | Solar | 14_92L6 | 2015-01-21 | 2015-01-22 | 5 | 1 | 4 | 2015-01-29 | 2015-01-29 | 0 | 0 | 0 | [20 empty] | 2015-02-04 |  | 2015-05-31 |  | EXP | [6 empty] | 2016-05-04 | 2016-05-04 | 2016-06-15 | Connected |  | No
National Grid | BLACKSTONE | 175939 | 1504 | 7.6 | Solar | 05_321W9 | 2015-01-21 | 2015-01-22 | 23 | 22 | 1 | 2015-02-25 | 2015-02-25 | 0 | 0 | 0 | [20 empty] | 2015-03-09 |  | 2015-05-31 |  | EXP | [6 empty] | 2015-03-13 | 2015-03-13 | 2015-12-07 | Connected |  | No
National Grid | HALIFAX | 175940 | 2338 | 19 | Solar | 07_797W24 | 2015-01-21 | 2015-01-22 | 5 | 1 | 4 | 2015-01-29 | 2017-04-26 | 556 | 0 | 556 | [20 empty] | 2015-02-04 |  | 2015-05-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BELLINGHAM | 175941 | 2019 | 15.2 | Solar | 05_344W4 | 2015-01-21 | 2015-01-22 | 5 | 1 | 4 | 2015-01-29 | 2015-01-29 | 0 | 0 | 0 | [20 empty] | 2015-02-04 |  | 2015-05-31 |  | EXP | [6 empty] | 2015-11-19 | 2015-11-19 | 2015-11-19 | Connected |  | No
National Grid | HANSON | 175942 | 2341 | 22.6 | Solar | 07_93W43 | 2015-01-21 | 2015-01-22 | 5 | 1 | 4 | 2015-01-29 | 2015-01-29 | 0 | 0 | 0 | [20 empty] | 2015-02-04 | 2015-01-21 | 2015-05-31 |  | EXP | [6 empty] | 2016-06-01 | 2016-06-01 | 2016-06-01 | Connected |  | No
National Grid | LEICESTER | 175943 | 1524 | 1000 | Solar | 01_21W1 | 2015-01-21 | 2015-01-22 | 5 | 1 | 4 | [10 empty] | 2015-01-29 | 2015-02-26 | 19 | 0 | 19 | [10 empty] | 2015-08-21 |  | 2018-09-28 | Yes | STD |  | 2018-04-09 | 2018-08-27 | 130 | 0 | 130 |  |  | 2018-09-06 | Connected |  | No
National Grid | CHESHIRE | 175944 | 1225 | 1000 | Solar | 09_1021W2 | 2015-01-21 | 2015-01-22 | 5 | 1 | 4 | [10 empty] | 2015-01-29 | 2015-02-27 | 20 | 0 | 20 | [12 empty] | 2015-07-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | AUBURN | 175945 | 1501 | 1000 | Solar | 01_406L2 | 2015-01-21 | 2015-01-22 | 5 | 1 | 4 | [10 empty] | 2015-01-29 | 2015-02-27 | 20 | 0 | 20 | [11 empty] | 2015-01-22 | 2015-07-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ORANGE | 175976 | 1364 | 920 | Solar | 09_705W3 | 2015-01-22 | 2015-01-23 | 9 | 8 | 1 | [10 empty] | 2015-02-05 | 2015-03-16 | 26 | 0 | 26 | [10 empty] | 2015-08-04 | 2015-01-22 | 2016-12-31 | Yes | STD |  | 2017-03-16 | 2017-05-23 | 47 | 0 | 47 | 2017-05-30 | 2017-05-30 | 2017-05-30 | Connected |  | No
National Grid | PHILLIPSTON | 175979 | 1331 | 990 | Solar | 09_702W1 | 2015-01-22 | 2015-01-23 | 7 | 2 | 5 | [10 empty] | 2015-02-03 | 2015-03-05 | 21 | 0 | 21 | [5 empty] | 2016-06-24 | 2016-08-01 | 25 | 0 | 25 | 2016-06-24 |  | 2015-06-30 | Yes | STD |  | 2016-12-20 | 2017-05-02 | 90 | 0 | 90 | 2017-07-06 | 2017-07-06 | 2017-07-06 | Connected |  | No
National Grid | SUTTON | 175978 | 1590 | 95 | Solar | 01_304W6 | 2015-01-23 | 2015-01-26 | 24 | 22 | 2 | 2015-03-02 | 2015-03-02 | 0 | 0 | 0 | [20 empty] | 2015-04-07 |  | 2015-06-30 |  | EXP | [6 empty] | 2015-04-08 | 2015-04-08 | 2015-06-11 | Connected |  | No
National Grid | WORCESTER | 175980 | 1604 | 42 | Solar | 01_9J315 | 2015-01-23 | 2015-01-26 | 6 | 0 | 6 | 2015-02-03 | 2015-02-03 | 0 | 0 | 0 | [20 empty] | 2015-02-23 |  | 2015-06-30 |  | EXP | [6 empty] | 2015-08-20 | 2015-08-20 | 2015-08-21 | Connected |  | No
National Grid | WORCESTER | 175981 | 1602 | 28 | Solar | 01_6W2 | 2015-01-23 | 2015-01-26 | 6 | 0 | 6 | 2015-02-03 | 2015-02-03 | 0 | 0 | 0 | [20 empty] | 2015-02-09 | 2015-01-23 | 2015-06-30 |  | EXP | [6 empty] | 2015-06-23 | 2015-06-23 | 2015-07-07 | Connected |  | No
National Grid | GRAFTON | 175982 | 1519 | 990 | Solar | 01_304W1 | 2015-01-23 | 2015-01-26 | 6 | 0 | 6 | [10 empty] | 2015-02-03 | 2015-03-05 | 21 | 0 | 21 | [5 empty] | 2015-09-16 | 2015-10-02 | 12 | 0 | 12 | 2015-12-08 | 2015-01-23 | 2015-06-30 | Yes | STD |  | 2017-09-21 | 2017-11-27 | 39 | 0 | 39 | 2018-01-02 | 2018-01-02 | 2018-01-02 | Connected |  | No
National Grid | BELLINGHAM | 176011 | 2019 | 11 | Solar | 05_344W4 | 2015-01-23 | 2015-01-26 | 6 | 2 | 4 | 2015-02-03 | 2015-02-03 | 0 | 0 | 0 | [20 empty] | 2015-02-23 |  | 2016-07-19 | Yes | EXP |  | 2015-11-05 | 2015-11-16 | 6 | 0 | 6 | 2016-03-28 | 2016-03-28 | 2016-03-28 | Connected |  | No
National Grid | ROCKLAND | 176012 | 2370 | 6 | Solar | 07_95W4 | 2015-01-23 | 2015-01-26 | 6 | 2 | 4 | 2015-02-03 | 2015-02-03 | 0 | 0 | 0 | [20 empty] | 2015-02-06 |  | 2015-06-30 |  | EXP | [6 empty] | 2015-03-27 | 2015-03-27 | 2015-09-24 | Connected |  | No
National Grid | WORCESTER | 176013 | 1606 | 17.6 | Solar | 01_24W3 | 2015-01-23 | 2015-01-26 | 8 | 6 | 2 | 2015-02-05 | 2015-10-20 | 175 | 0 | 175 | [20 empty] | 2015-02-24 |  | 2015-06-30 |  | EXP | [6 empty] | 2015-02-24 | 2015-02-24 |  | Withdrawn |  | No
National Grid | GARDNER | 176014 | 1440 | 1000 | Solar | 01_601W1 | 2015-01-23 | 2015-01-26 | 25 | 23 | 2 | [10 empty] | 2015-03-03 | 2015-04-03 | 22 | 0 | 22 | [12 empty] | 2015-07-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | GARDNER | 176015 | 1440 | 1000 | Solar | 01_601W1 | 2015-01-23 | 2015-01-26 | 25 | 23 | 2 | [10 empty] | 2015-03-03 | 2015-04-03 | 22 | 0 | 22 | [12 empty] | 2015-07-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | GARDNER | 176016 | 1440 | 1000 | Solar | 01_601W1 | 2015-01-23 | 2015-01-23 | 26 | 23 | 3 | [10 empty] | 2015-03-03 | 2015-04-03 | 22 | 0 | 22 | [12 empty] | 2015-07-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | PLAINVILLE | 178783 | 2762 | 1000 | Solar | 05_3422W3 | 2015-01-23 | 2015-01-26 | 25 | 23 | 2 | [10 empty] | 2015-03-03 | 2015-03-31 | 19 | 0 | 19 | [12 empty] | 2015-07-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | PLAINVILLE | 178784 | 2762 | 1000 | Solar | 05_3422W3 | 2015-01-23 | 2015-01-26 | 25 | 23 | 2 | [10 empty] | 2015-03-03 | 2015-03-31 | 19 | 0 | 19 | [12 empty] | 2015-07-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | GRAFTON | 176017 | 1519 | 21.4 | Solar | 01_304W1 | 2015-01-26 | 2015-01-28 | 4 | 0 | 4 | 2015-02-03 | 2015-02-03 | 0 | 0 | 0 | [20 empty] | 2015-02-06 |  | 2015-05-31 |  | EXP | [6 empty] | 2015-02-20 | 2015-02-20 | 2015-12-11 | Connected |  | No
National Grid | SALISBURY | 176047 | 1952 | 42 | Solar | 14_7L4 | 2015-01-26 | 2015-01-28 | 4 | 0 | 4 | 2015-02-03 | 2015-02-03 | 0 | 0 | 0 | [20 empty] | 2015-02-06 |  | 2015-06-30 |  | EXP | [6 empty] | 2015-02-20 | 2015-02-20 | 2015-03-31 | Connected |  | No
National Grid | TEWKSBURY | 176048 | 1876 | 300 | Solar | 14_59L5 | 2015-01-26 | 2015-01-28 | 4 | 0 | 4 | 2015-02-03 | 2015-02-13 | 8 | 0 | 8 | [21 empty] | 2015-01-26 | 2015-06-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BRIMFIELD | 176049 | 1010 | 1000 | Solar | 09_516L1 | 2015-01-26 | 2015-01-28 | 4 | 1 | 3 | [10 empty] | 2015-02-03 | 2015-03-04 | 20 | 0 | 20 | [12 empty] | 2015-07-31 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | MILFORD | 176052 | 1757 | 4.5 | Solar | 05_335W5 | 2015-01-29 | 2015-01-30 | 4 | 4 | 0 | 2015-02-05 | 2015-02-05 | 0 | 0 | 0 | [20 empty] | 2015-02-24 |  | 2015-06-30 |  | EXP | [6 empty] | 2015-02-24 | 2015-02-24 | 2015-09-25 | Connected |  | No
National Grid | RUTLAND | 176053 | 1543 | 22.58 | Solar | 01_55W1 | 2015-01-29 | 2015-01-30 | 5 | 4 | 1 | 2015-02-06 | 2015-02-06 | 0 | 0 | 0 | [20 empty] | 2015-02-09 | 2015-01-29 | 2015-06-30 |  | EXP | [6 empty] | 2015-03-10 | 2015-03-10 | 2015-06-10 | Connected |  | No
National Grid | STURBRIDGE | 176124 | 1566 | 540 | Solar | 01_415L3 | 2015-01-29 | 2015-01-30 | 5 | 0 | 5 | [10 empty] | 2015-02-06 | 2015-03-09 | 20 | 0 | 20 | [12 empty] | 2015-07-31 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | MELROSE | 176158 | 2176 | 15.2 | Solar | 12_25W4 | 2015-01-29 | 2015-01-30 | 9 | 3 | 6 | [27 empty] | 2015-06-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LYNN | 176054 | 1902 | 3 | Solar | 12_21J28 | 2015-01-30 | 2015-02-03 | 18 | 18 | 0 | 2015-03-02 | 2015-04-16 | 32 | 0 | 32 | [20 empty] | 2015-04-16 |  | 2015-06-30 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEBSTER | 176055 | 1570 | 15.48 | Solar | 01_412L2 | 2015-01-30 | 2015-02-03 | 11 | 11 | 0 | 2015-02-19 | 2015-02-19 | 0 | 0 | 0 | [20 empty] | 2015-02-20 |  | 2015-06-30 |  | EXP | [6 empty] | 2015-03-27 | 2015-03-27 | 2015-11-19 | Connected |  | No
National Grid | BELLINGHAM | 176082 | 2019 | 50 | Solar | 05_344W4 | 2015-01-30 | 2015-02-03 | 15 | 15 | 0 | 2015-02-25 | 2015-02-25 | 0 | 0 | 0 | [20 empty] | 2015-02-27 | 2015-01-30 | 2015-06-27 |  | EXP | [6 empty] | 2015-04-01 | 2015-04-01 | 2016-05-10 | Connected |  | No
National Grid | EAST LONGMEADOW | 176083 | 1028 | 560 | Solar | 09_508L4 | 2015-01-30 | 2015-02-03 | 3 | 2 | 1 | 2015-02-06 | 2015-02-06 | 0 | 0 | 0 | 2017-03-13 | 2015-05-05 | 0 | 0 | 0 | [5 empty] | 2017-03-13 | 2015-05-05 | 0 | 0 | 0 | [5 empty] | 2015-05-12 |  | 2016-12-30 | Yes | EXP |  | 2016-10-19 | 2016-11-28 | 26 | 0 | 26 | 2017-05-01 | 2017-05-01 | 2017-05-16 | Connected |  | No
National Grid | SALISBURY | 176087 | 1952 | 990 | Solar | 14_2396N | 2015-01-30 | 2015-02-03 | 3 | 1 | 2 | [10 empty] | 2015-02-06 | 2015-03-09 | 20 | 0 | 20 | [5 empty] | 2015-10-09 | 2015-11-04 | 17 | 17 | 0 | 2016-01-12 |  | 2015-08-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SALISBURY | 176088 | 1952 | 990 | Solar | 14_2396N | 2015-01-30 | 2015-02-03 | 3 | 1 | 2 | [10 empty] | 2015-02-06 | 2015-03-09 | 20 | 0 | 20 | [5 empty] | 2015-10-09 | 2015-11-04 | 17 | 17 | 0 | 2016-01-12 |  | 2015-08-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SALISBURY | 176089 | 1952 | 990 | Solar | 14_2396N | 2015-01-30 | 2015-02-03 | 3 | 1 | 2 | [10 empty] | 2015-02-06 | 2015-03-09 | 20 | 0 | 20 | [5 empty] | 2015-10-09 | 2015-11-04 | 17 | 17 | 0 | 2016-01-12 |  | 2015-08-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SALISBURY | 176121 | 1952 | 990 | Solar | 14_2396N | 2015-01-30 | 2015-02-03 | 3 | 1 | 2 | [10 empty] | 2015-02-06 | 2015-03-09 | 20 | 0 | 20 | [5 empty] | 2015-10-09 | 2015-11-04 | 17 | 17 | 0 | 2016-01-12 |  | 2015-08-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SALISBURY | 176122 | 1952 | 990 | Solar | 14_2396N | 2015-01-30 | 2015-02-03 | 3 | 1 | 2 | [10 empty] | 2015-02-06 | 2015-03-09 | 20 | 0 | 20 | [5 empty] | 2015-10-09 | 2015-11-04 | 17 | 17 | 0 | 2015-04-15 | 2015-02-02 | 2015-08-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 176086 | 1605 | 5 | Solar | 01_24W2 | 2015-02-02 | 2015-02-03 | 5 | 1 | 4 | 2015-02-10 | 2015-02-10 | 0 | 0 | 0 | [20 empty] | 2015-02-25 | 2015-02-02 | 2016-12-31 | Yes | EXP |  | 2016-03-11 | 2016-03-31 | 13 | 0 | 13 | 2016-08-08 | 2016-08-08 | 2016-08-08 | Connected |  | No
National Grid | RANDOLPH | 176090 | 2368 | 7.6 | Solar | 07_97W2 | 2015-02-02 | 2015-02-03 | 5 | 1 | 4 | 2015-02-10 | 2015-02-10 | 0 | 0 | 0 | [20 empty] | 2015-02-25 | 2015-02-02 | 2015-06-30 | Yes | EXP |  | 2015-11-04 | 2015-11-04 | 0 | 0 | 0 | 2015-04-20 | 2015-04-20 | 2015-11-09 | Connected |  | No
National Grid | NORTH ADAMS | 176120 | 1247 | 990 | Solar | 09_1021W2 | 2015-02-02 | 2015-02-03 | 5 | 1 | 4 | [10 empty] | 2015-02-10 | 2015-03-10 | 19 | 0 | 19 | [10 empty] | 2015-08-18 | 2015-02-02 | 2016-12-31 | Yes | STD |  | 2017-03-24 | 2017-06-30 | 68 | 0 | 68 | 2017-07-20 | 2017-07-20 | 2017-07-20 | Connected |  | No
National Grid | NORTH ADAMS | 176123 | 1247 | 990 | Solar | 09_1021W2 | 2015-02-02 | 2015-02-03 | 5 | 1 | 4 | [10 empty] | 2015-02-10 | 2015-03-10 | 19 | 0 | 19 | [10 empty] | 2015-08-18 |  | 2016-12-31 | Yes | STD |  | 2017-03-24 | 2017-06-30 | 68 | 0 | 68 | 2017-07-20 | 2017-07-20 | 2017-07-20 | Connected |  | No
National Grid | SOUTH EASTON | 176155 | 2375 | 490 | Solar | 07_92W54 | 2015-02-02 | 2015-02-03 | 11 | 7 | 4 | [10 empty] | 2015-02-19 | 2015-03-27 | 25 | 6 | 19 | [12 empty] | 2015-07-31 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | WEST BRIDGEWATER | 176125 | 2379 | 1660 | Solar | 07_98W44 | 2015-02-03 | 2015-02-04 | 4 | 0 | 4 | [10 empty] | 2015-02-10 | 2015-03-10 | 19 | 0 | 19 | [5 empty] | 2015-09-10 | 2016-07-06 | 202 | 191 | 11 | 2016-07-06 |  | 2015-07-31 |  | STD |  | 2016-12-07 | 2017-06-19 | 132 | 0 | 132 |  |  |  | Withdrawn |  | No
National Grid | GRAFTON | 176126 | 1519 | 15 | Solar | 01_328W3 | 2015-02-03 | 2015-02-04 | 5 | 2 | 3 | 2015-02-11 | 2015-02-11 | 0 | 0 | 0 | [20 empty] | 2015-02-12 | 2015-02-03 | 2015-07-31 |  | EXP | [6 empty] | 2015-03-27 | 2015-03-27 | 2015-06-03 | Connected |  | No
National Grid | WEST BRIDGEWATER | 176127 | 2379 | 1656 | Solar | 07_98W44 | 2015-02-03 | 2015-02-04 | 4 | 0 | 4 | [10 empty] | 2015-02-10 | 2015-03-10 | 19 | 0 | 19 | [5 empty] | 2015-09-10 | 2016-07-06 | 202 | 191 | 11 | 2016-07-06 | 2015-02-03 | 2015-07-31 | Yes | STD |  | 2016-12-07 | 2017-06-19 | 132 | 0 | 132 | 2017-07-06 | 2017-07-06 | 2017-07-06 | Connected |  | No
National Grid | BEVERLY | 176156 | 1915 | 21.4 | Solar | 12_51T1 | 2015-02-03 | 2015-02-04 | 6 | 3 | 3 | 2015-02-12 | 2015-02-12 | 0 | 0 | 0 | [20 empty] | 2015-03-02 |  | 2016-07-19 | Yes | EXP |  | 2016-05-18 | 2017-10-17 | 353 | 0 | 353 | 2016-04-06 | 2016-04-06 | 2016-04-06 | Connected |  | No
National Grid | DIGHTON | 176085 | 2715 | 499 | Solar | 05_19W73 | 2015-02-04 | 2015-02-04 | 5 | 1 | 4 | [5 empty] | 2015-03-19 | 2017-02-14 | 474 | 0 | 474 | 2015-02-11 | 2015-03-18 | 23 | 0 | 23 | 2015-03-19 | 2017-02-14 | 474 | 0 | 474 | [7 empty] | 2015-07-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | AYER | 176157 | 1434 | 230 | Solar | 01_201W2 | 2015-02-04 | 2015-02-06 | 3 | 1 | 2 | 2015-02-11 | 2015-02-11 | 0 | 0 | 0 | [20 empty] | 2015-03-03 |  | 2015-07-31 |  | EXP | [6 empty] | 2015-07-23 | 2015-07-23 | 2015-08-06 | Connected |  | No
National Grid | NORTH ADAMS | 176159 | 1247 | 250 | Solar | 09_1021W1 | 2015-02-04 | 2015-02-06 | 3 | 1 | 2 | 2015-02-11 | 2015-02-11 | 0 | 0 | 0 | [20 empty] | 2015-03-17 |  | 2015-07-31 |  | EXP | [6 empty] | 2015-08-03 | 2015-08-03 | 2015-08-07 | Connected |  | No
National Grid | ABINGTON | 176194 | 2351 | 990 | Solar | 07_93W41 | 2015-02-04 | 2015-02-06 | 4 | 0 | 4 | [10 empty] | 2015-02-12 | 2015-03-12 | 19 | 0 | 19 | [12 empty] | 2015-08-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ABINGTON | 176195 | 2351 | 800 | Solar | 07_93W41 | 2015-02-04 | 2015-02-06 | 4 | 0 | 4 | [10 empty] | 2015-02-12 | 2015-03-12 | 19 | 0 | 19 | [12 empty] | 2015-08-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BEVERLY | 176160 | 1915 | 17.4 | Solar | 12_51T2 | 2015-02-05 | 2015-02-06 | 4 | 1 | 3 | 2015-02-12 | 2015-02-12 | 0 | 0 | 0 | [20 empty] | 2015-02-13 |  | 2015-06-30 |  | EXP | [6 empty] | 2015-03-06 | 2015-03-06 | 2015-09-25 | Connected |  | No
National Grid | LEOMINSTER | 176161 | 1453 | 11 | Solar | 01_207W2 | 2015-02-05 | 2015-02-06 | 4 | 1 | 3 | 2015-02-12 | 2015-02-12 | 0 | 0 | 0 | [20 empty] | 2015-02-27 | 2015-02-06 | 2016-06-24 |  | EXP | [6 empty] | 2015-02-27 | 2015-02-27 | 2016-03-18 | Connected |  | No
National Grid | RUTLAND | 176162 | 1543 | 1000 | Solar | 01_55W3 | 2015-02-06 | 2015-02-09 | 4 | 1 | 3 | [10 empty] | 2015-02-13 | 2015-03-16 | 20 | 0 | 20 | [10 empty] | 2015-12-16 | 2015-02-06 | 2017-09-24 | Yes | STD |  | 2017-08-11 | 2017-09-15 | 24 | 0 | 24 | 2017-09-08 | 2017-09-08 | 2017-09-29 | Connected |  | No
National Grid | CLARKSBURG | 176163 | 1247 | 990 | Solar | 09_1015W2 | 2015-02-06 | 2015-02-09 | 4 | 0 | 4 | [10 empty] | 2015-02-13 | 2015-03-12 | 18 | 0 | 18 | [10 empty] | 2015-07-21 | 2015-02-06 | 2016-12-31 | Yes | STD |  | 2017-02-21 | 2017-07-03 | 92 | 0 | 92 | 2017-07-20 | 2017-07-20 | 2017-07-20 | Connected |  | No
National Grid | UXBRIDGE | 176164 | 1569 | 990 | Solar | 05_321W6 | 2015-02-06 | 2015-02-09 | 4 | 0 | 4 | [10 empty] | 2015-02-13 | 2015-03-16 | 20 | 0 | 20 | [10 empty] | 2015-07-20 |  | 2016-12-31 | Yes | STD |  | 2017-01-12 | 2017-06-15 | 106 | 0 | 106 | 2017-06-05 | 2017-06-05 | 2017-07-06 | Connected |  | No
National Grid | GLOUCESTER | 176196 | 1930 | 950 | Solar | 12_51T1 | 2015-02-06 | 2015-05-14 | 0 | 0 | 0 | [10 empty] | 2015-05-14 | 2015-05-14 | 0 | 0 | 0 | [12 empty] | 2015-08-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | GLOUCESTER | 176197 | 1930 | 900 | Solar | 12_51T1 | 2015-02-06 | 2015-02-09 | 4 | 0 | 4 | [10 empty] | 2015-02-13 | 2015-03-16 | 20 | 0 | 20 | [12 empty] | 2015-08-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LEOMINSTER | 176193 | 1453 | 260 | Solar | 01_225W3 | 2015-02-09 | 2015-02-10 | 4 | 0 | 4 | 2015-02-17 | 2015-02-17 | 0 | 0 | 0 | [20 empty] | 2015-02-25 |  | 2015-07-31 |  | EXP | [6 empty] | 2015-10-07 | 2015-10-07 | 2015-10-07 | Connected |  | No
National Grid | ADAMS | 176199 | 1220 | 1000 | Solar | 09_1021W2 | 2015-02-11 | 2015-02-12 | 4 | 2 | 2 | [10 empty] | 2015-02-19 | 2015-03-19 | 19 | 0 | 19 | [12 empty] | 2015-07-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | DUDLEY | 176200 | 1571 | 17.6 | Solar | 01_412L4 | 2015-02-11 | 2015-02-12 | 4 | 2 | 2 | 2015-02-19 | 2015-02-19 | 0 | 0 | 0 | [20 empty] | 2015-03-04 | 2015-02-11 | 2016-12-31 |  | EXP | [6 empty] | 2015-03-04 | 2015-03-04 | 2015-12-11 | Connected |  | No
National Grid | CHARLTON | 176201 | 1507 | 2000 | Solar | 01_415L2 | 2015-02-11 | 2015-02-12 | 4 | 1 | 3 | [10 empty] | 2015-02-19 | 2015-03-19 | 19 | 0 | 19 | [5 empty] | 2016-08-12 | 2016-08-12 | 0 | 0 | 0 | 2015-12-11 |  | 2018-02-08 | Yes | STD |  | 2018-03-20 | 2018-03-20 | 0 | 0 | 0 | 2017-12-13 | 2017-12-13 | 2017-12-31 | Connected |  | No
National Grid | DUNSTABLE | 176229 | 1827 | 17.6 | Solar | 01_210L1 | 2015-02-11 | 2015-02-12 | 4 | 2 | 2 | 2015-02-19 | 2015-02-19 | 0 | 0 | 0 | [20 empty] | 2015-02-20 |  | 2015-06-30 |  | EXP | [6 empty] | 2015-10-01 | 2015-10-01 | 2016-04-12 | Connected |  | No
National Grid | WINCHENDON | 176230 | 1475 | 500 | Solar | 01_612W1 | 2015-02-11 | 2015-02-12 | 6 | 2 | 4 | [5 empty] | 2015-04-09 | 2015-07-24 | 72 | 0 | 72 | 2015-02-23 | 2015-03-24 | 20 | 0 | 20 | 2015-04-09 | 2015-07-24 | 72 | 0 | 72 | [7 empty] | 2015-08-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | DUNSTABLE | 176231 | 1827 | 24 | Solar | 01_210L1 | 2015-02-13 | 2015-02-17 | 4 | 0 | 4 | 2015-02-23 | 2015-02-23 | 0 | 0 | 0 | [20 empty] | 2015-02-24 |  | 2015-06-30 |  | EXP | [6 empty] | 2015-03-10 | 2015-03-10 | 2015-08-19 | Connected |  | No
National Grid | WORCESTER | 176232 | 1602 | 60 | Natural Gas | 01_HT40 | 2015-02-13 | 2015-02-13 | 10 | 7 | 3 | 2015-03-02 | 2015-03-02 | 0 | 0 | 0 | [20 empty] | 2015-03-04 | 2015-02-14 | 2015-07-31 |  | EXP | [6 empty] | 2016-02-19 | 2016-02-19 | 2016-02-18 | Connected |  | Yes
National Grid | MILLBURY | 176233 | 1527 | 100 | Solar | 01_328W2 | 2015-02-14 | 2015-02-17 | 4 | 0 | 4 | 2015-02-23 | 2015-02-23 | 0 | 0 | 0 | [20 empty] | 2015-03-10 |  | 2016-12-31 | Yes | EXP |  | 2015-11-05 | 2016-03-04 | 80 | 0 | 80 | 2016-04-04 | 2016-04-04 | 2016-04-04 | Connected |  | No
National Grid | PALMER | 176198 | 1069 | 144 | Solar | 09_0504 | 2015-02-16 | 2015-02-16 | 4 | 0 | 4 | 2015-02-23 | 2015-12-21 | 206 | 29 | 177 | [20 empty] | 2015-04-22 | 2015-02-17 | 2015-06-30 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MEDFORD | 176235 | 2155 | 4000 | Natural Gas | 12_64J4 | 2015-02-17 | 2015-02-17 | 5 | 0 | 5 | [10 empty] | 2015-02-24 | 2015-03-25 | 20 | 0 | 20 | [10 empty] | 2016-10-21 |  | 2017-06-15 |  | STD |  | 2017-09-25 | 2017-09-25 | 0 | 0 | 0 | 2017-09-29 | 2017-09-29 | 2017-09-29 | Connected |  | No
National Grid | ROCKPORT | 176236 | 1966 | 15 | Solar | 12_40J2 | 2015-02-17 | 2015-02-18 | 5 | 0 | 5 | 2015-02-25 | 2015-02-25 | 0 | 0 | 0 | [20 empty] | 2015-02-26 |  | 2015-06-30 |  | EXP | [6 empty] | 2015-04-01 | 2015-04-01 | 2015-07-02 | Connected |  | No
National Grid | ORANGE | 176237 | 1364 | 1000 | Solar | 09_705W3 | 2015-02-17 | 2015-02-18 | 9 | 5 | 4 | [10 empty] | 2015-03-03 | 2015-04-01 | 20 | 0 | 20 | [12 empty] | 2015-11-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ORANGE | 176267 | 1364 | 1000 | Solar | 09_705W3 | 2015-02-17 | 2015-02-18 | 9 | 5 | 4 | [10 empty] | 2015-03-03 | 2015-04-01 | 20 | 0 | 20 | [12 empty] | 2015-11-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ATTLEBORO | 176268 | 2703 | 17.6 | Solar | 05_2J1 | 2015-02-18 | 2015-02-19 | 4 | 1 | 3 | 2015-02-25 | 2017-02-01 | 480 | 0 | 480 | [20 empty] | 2015-02-27 |  | 2015-07-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 176269 | 1844 | 17.6 | Solar | 14_74L4 | 2015-02-18 | 2015-02-19 | 4 | 1 | 3 | 2015-02-25 | 2015-02-25 | 0 | 0 | 0 | [20 empty] | 2015-02-27 |  | 2015-07-13 |  | EXP | [6 empty] | 2015-10-01 | 2015-10-01 | 2016-07-25 | Connected |  | No
National Grid | GLOUCESTER | 176270 | 1930 | 17.42 | Solar | 12_51T3 | 2015-02-18 | 2015-02-19 | 4 | 0 | 4 | 2015-02-25 | 2015-02-25 | 0 | 0 | 0 | [20 empty] | 2015-02-27 | 2015-02-19 | 2015-07-31 |  | EXP | [6 empty] | 2015-03-27 | 2015-03-27 | 2015-06-30 | Connected |  | No
National Grid | WEST BRIDGEWATER | 176272 | 2379 | 3084 | Solar | 07_92W54 | 2015-02-19 | 2015-02-19 | 7 | 0 | 7 | [10 empty] | 2015-03-02 | 2015-03-30 | 19 | 0 | 19 | [10 empty] | 2015-10-12 | 2015-02-19 | 2017-12-14 | Yes | STD |  | 2017-05-24 | 2018-02-20 | 179 | 0 | 179 | 2017-11-20 | 2017-11-20 | 2017-12-14 | Connected |  | No
National Grid | WINCHENDON | 176273 | 1475 | 984 | Solar | 01_612W1 | 2015-02-19 | 2015-02-19 | 7 | 0 | 7 | [10 empty] | 2015-03-02 | 2015-03-31 | 20 | 0 | 20 | [10 empty] | 2016-07-21 | 2015-02-19 | 2019-12-31 | Yes | STD |  | 2019-06-08 | 2019-06-07 | 0 | 0 | 0 | 2019-10-09 | 2019-10-09 | 2019-12-27 | Connected |  | No
National Grid | WINCHENDON | 176274 | 1475 | 984 | Solar | 01_612W1 | 2015-02-19 | 2015-02-19 | 7 | 0 | 7 | [10 empty] | 2015-03-02 | 2015-03-31 | 20 | 0 | 20 | [10 empty] | 2016-07-21 |  | 2019-12-31 | Yes | STD |  | 2019-06-08 | 2019-06-07 | 0 | 0 | 0 | 2019-10-15 | 2019-10-15 | 2019-12-27 | Connected |  | No
National Grid | SPENCER | 176305 | 1562 | 16.5 | Solar | 01_552L1 | 2015-02-20 | 2015-02-23 | 10 | 5 | 5 | 2015-03-07 | 2015-03-07 | 0 | 0 | 0 | [20 empty] | 2015-03-09 |  | 2015-07-31 |  | EXP | [6 empty] | 2015-07-20 | 2015-07-20 | 2015-07-29 | Connected |  | No
National Grid | HUBBARDSTON | 176306 | 1452 | 15.2 | Solar | 09_604W4 | 2015-02-20 | 2015-02-23 | 7 | 0 | 7 | 2015-03-04 | 2015-03-04 | 0 | 0 | 0 | [20 empty] | 2015-03-05 |  | 2015-07-31 |  | EXP | [6 empty] | 2017-05-12 | 2017-05-12 | 2017-05-12 | Connected |  | No
National Grid | BROCKTON | 176307 | 2301 | 252 | Solar | 07_94W41 | 2015-02-20 | 2015-02-23 | 11 | 5 | 6 | 2015-03-10 | 2015-03-10 | 0 | 0 | 0 | [20 empty] | 2015-03-24 | 2015-02-20 | 2015-09-30 |  | EXP | [6 empty] | 2015-05-27 | 2015-05-27 | 2015-07-21 | Connected |  | No
National Grid | BRIDGEWATER | 176308 | 2324 | 1000 | Solar | 07_912W55 | 2015-02-20 | 2015-02-23 | 9 | 3 | 6 | [10 empty] | 2015-03-06 | 2015-04-03 | 19 | 0 | 19 | [11 empty] | 2015-02-20 | 2015-12-31 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | BRIDGEWATER | 176309 | 2324 | 2000 | Solar | 07_912W55 | 2015-02-20 | 2015-02-23 | 9 | 3 | 6 | [10 empty] | 2015-03-06 | 2015-04-03 | 19 | 0 | 19 | [12 empty] | 2015-12-31 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | ATTLEBORO | 176342 | 2703 | 2000 | Solar | 05_8L3 | 2015-02-20 | 2015-02-23 | 7 | 0 | 7 | [10 empty] | 2015-03-04 | 2015-03-30 | 17 | 0 | 17 | [12 empty] | 2015-09-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ATTLEBORO | 176343 | 2703 | 1000 | Solar | 05_8L3 | 2015-02-20 | 2015-02-23 | 7 | 0 | 7 | [10 empty] | 2015-03-04 | 2015-03-30 | 17 | 0 | 17 | [12 empty] | 2015-09-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ROCKLAND | 176310 | 2370 | 10 | Solar | 07_95W4 | 2015-02-23 | 2015-02-24 | 6 | 0 | 6 | 2015-03-04 | 2015-03-04 | 0 | 0 | 0 | [20 empty] | 2015-03-05 |  | 2015-07-31 |  | EXP | [6 empty] | 2016-09-01 | 2016-09-01 | 2016-09-07 | Connected |  | No
National Grid | BILLERICA | 176311 | 1821 | 5 | Solar | 14_70L8 | 2015-02-25 | 2015-02-26 | 8 | 5 | 3 | 2015-03-10 | 2015-03-10 | 0 | 0 | 0 | [20 empty] | 2015-03-27 |  | 2015-07-31 |  | EXP | [6 empty] | 2015-06-11 | 2015-06-11 | 2015-10-02 | Connected |  | No
National Grid | EAST BRIDGEWATER | 176312 | 2333 | 5.16 | Solar | 07_797W42 | 2015-02-25 | 2015-02-26 | 9 | 6 | 3 | 2015-03-11 | 2016-12-15 | 439 | 0 | 439 | [20 empty] | 2015-03-17 | 2015-02-25 | 2016-12-31 |  | EXP | [6 empty] | 2015-03-17 | 2015-03-17 |  | Withdrawn |  | Yes
National Grid | AUBURN | 176341 | 1501 | 8.6 | Solar | 01_26W1 | 2015-02-25 | 2015-02-26 | 9 | 6 | 3 | 2015-03-11 | 2015-03-11 | 0 | 0 | 0 | [20 empty] | 2015-03-17 |  | 2016-12-31 | Yes | EXP |  | 2016-02-18 | 2016-03-14 | 17 | 0 | 17 | 2015-03-17 | 2015-03-17 | 2016-05-05 | Connected |  | No
National Grid | WORCESTER | 176344 | 1604 | 8.39 | Solar | 01_10J383 | 2015-02-25 | 2015-02-26 | 9 | 5 | 4 | 2015-03-11 | 2015-03-11 | 0 | 0 | 0 | [20 empty] | 2015-03-12 | 2015-02-25 | 2015-07-31 |  | EXP | [6 empty] | 2015-03-12 | 2015-03-12 | 2016-01-13 | Connected |  | No
National Grid | BEVERLY | 176345 | 1915 | 6.67 | Solar | 12_51L1 | 2015-02-25 | 2015-02-26 | 9 | 5 | 4 | 2015-03-11 | 2015-03-11 | 0 | 0 | 0 | [20 empty] | 2015-03-17 | 2015-02-25 | 2016-12-31 | Yes | EXP |  | 2016-02-11 | 2016-04-30 | 54 | 0 | 54 | 2015-03-17 | 2015-03-17 | 2016-10-12 | Connected |  | No
National Grid | OAKHAM | 176349 | 1068 | 2000 | Solar | 09_604W2 | 2015-02-25 | 2015-02-26 | 7 | 1 | 6 | [10 empty] | 2015-03-09 | 2015-04-06 | 19 | 0 | 19 | [5 empty] | 2016-12-22 | 2017-02-17 | 38 | 11 | 27 | 2017-03-30 |  | 2021-04-21 | Yes | STD |  | 2020-01-11 | 2021-02-12 | 397 | 180 | 217 |  |  | 2021-04-20 | Connected |  | No
National Grid | NORTH EASTON | 176348 | 2356 | 225 | Solar | 07_98W46 | 2015-02-26 | 2015-03-02 | 5 | 0 | 5 | 2015-03-09 | 2015-03-09 | 0 | 0 | 0 | [20 empty] | 2015-03-30 |  | 2015-09-30 |  | EXP | [6 empty] | 2016-04-01 | 2016-04-01 | 2016-04-01 | Connected |  | No
National Grid | EAST BROOKFIELD | 175797 | 1515 | 990 | Solar | 01_552L3 | 2015-02-27 | 2015-03-02 | 5 | 0 | 5 | [5 empty] | 2015-09-22 | 2015-10-20 | 19 | 0 | 19 | 2015-03-09 | 2015-04-06 | 19 | 0 | 19 | 2015-09-22 | 2015-10-20 | 19 | 0 | 19 | [7 empty] | 2015-09-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MILLVILLE | 175798 | 1529 | 990 | Solar | 05_321W9 | 2015-02-27 | 2015-03-02 | 6 | 0 | 6 | [10 empty] | 2015-03-10 | 2015-04-08 | 20 | 0 | 20 | [12 empty] | 2015-09-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | DOUGLAS | 175799 | 1516 | 16 | Solar | 01_412L1 | 2015-02-27 | 2015-03-02 | 6 | 1 | 5 | 2015-03-10 | 2015-03-10 | 0 | 0 | 0 | [20 empty] | 2015-03-12 |  | 2015-07-31 |  | EXP | [6 empty] | 2015-03-27 | 2015-03-27 | 2015-12-23 | Connected |  | No
National Grid | REHOBOTH | 175800 | 2769 | 990 | Solar | 05_9L5 | 2015-02-27 | 2015-03-02 | 6 | 0 | 6 | [10 empty] | 2015-03-10 | 2015-04-08 | 20 | 0 | 20 | [11 empty] | 2015-02-27 | 2015-09-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BOLTON | 175801 | 1740 | 1980 | Solar | 01_225W1 | 2015-02-27 | 2015-03-03 | 5 | 0 | 5 | [10 empty] | 2015-03-10 | 2015-04-07 | 19 | 0 | 19 | [10 empty] | 2015-08-25 |  | 2016-12-31 | Yes | STD |  | 2016-11-14 | 2017-01-06 | 36 | 0 | 36 | 2016-12-22 | 2016-12-22 | 2016-12-27 | Connected |  | No
National Grid | FALL RIVER | 175803 | 2720 | 990 | Solar | 05_28W50 | 2015-02-27 | 2015-03-02 | 5 | 0 | 5 | [10 empty] | 2015-03-09 | 2015-04-06 | 19 | 0 | 19 | [12 empty] | 2015-09-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MILLBURY | 175804 | 1527 | 990 | Solar | 01_304W4 | 2015-02-27 | 2015-03-02 | 5 | 0 | 5 | [10 empty] | 2015-03-09 | 2015-04-06 | 19 | 0 | 19 | [12 empty] | 2015-09-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HUBBARDSTON | 175834 | 1452 | 990 | Solar | 01_609W1 | 2015-02-27 | 2015-03-02 | 6 | 0 | 6 | [10 empty] | 2015-03-10 | 2015-04-08 | 20 | 0 | 20 | [12 empty] | 2015-09-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HUBBARDSTON | 175836 | 1452 | 990 | Solar | 01_609W1 | 2015-02-27 | 2015-03-02 | 6 | 0 | 6 | [10 empty] | 2015-03-10 | 2015-04-08 | 20 | 0 | 20 | [12 empty] | 2015-09-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MILLBURY | 176166 | 1527 | 990 | Solar | 01_304W4 | 2015-02-27 | 2015-04-20 | 0 | 0 | 0 | [10 empty] | 2015-03-09 | 2015-04-06 | 19 | 0 | 19 | [12 empty] | 2015-09-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MALDEN | 176347 | 2148 | 140 | Solar | 12_16W5 | 2015-02-27 | 2015-03-02 | 5 | 0 | 5 | 2015-03-09 | 2015-03-09 | 0 | 0 | 0 | [20 empty] | 2015-03-23 | 2015-02-27 | 2015-09-30 |  | EXP | [6 empty] | 2015-03-25 | 2015-03-25 | 2015-11-18 | Connected |  | No
National Grid | BOLTON | 178357 | 1740 | 1980 | Solar | 01_225W1 | 2015-02-27 | 2015-03-03 | 5 | 0 | 5 | [10 empty] | 2015-03-10 | 2015-04-07 | 19 | 0 | 19 | [10 empty] | 2015-08-25 |  | 2019-03-06 | Yes | STD |  | 2016-11-14 | 2017-01-06 | 36 | 0 | 36 | 2016-12-23 | 2016-12-23 | 2016-12-27 | Connected |  | No
National Grid | MILFORD | 175805 | 1757 | 54 | Solar | 05_335W3 | 2015-03-02 | 2015-03-03 | 26 | 22 | 4 | 2015-04-09 | 2015-04-09 | 0 | 0 | 0 | [20 empty] | 2015-04-13 | 2015-03-03 | 2015-08-31 |  | EXP | [6 empty] | 2015-04-24 | 2015-04-24 | 2015-08-12 | Connected |  | No
National Grid | PALMER | 175802 | 1069 | 4400 | Solar | 09_523L4 | 2015-03-03 | 2015-03-04 | 4 | 1 | 3 | [10 empty] | 2015-03-10 | 2015-04-08 | 20 | 0 | 20 | [10 empty] | 2015-10-12 |  | 2016-12-31 | Yes | STD |  | 2016-09-02 | 2017-02-23 | 116 | 0 | 116 |  |  | 2016-12-30 | Connected |  | No
National Grid | CHELMSFORD | 175833 | 1824 | 16.34 | Solar | 14_24L2 | 2015-03-03 | 2015-03-04 | 8 | 5 | 3 | 2015-03-16 | 2015-03-16 | 0 | 0 | 0 | [20 empty] | 2015-03-16 |  | 2015-07-14 |  | EXP | [6 empty] | 2015-03-27 | 2015-03-27 | 2015-06-15 | Connected |  | No
National Grid | WILLIAMSTOWN | 175835 | 1267 | 28 | Solar | 09_1003W2 | 2015-03-03 | 2015-03-04 | 4 | 0 | 4 | 2015-03-10 | 2015-03-10 | 0 | 0 | 0 | [20 empty] | 2015-04-07 |  | 2015-07-15 |  | EXP | [6 empty] | 2015-04-24 | 2015-04-24 | 2016-10-04 | Connected |  | No
National Grid | DIGHTON | 175837 | 2715 | 15.2 | Solar | 05_19W74 | 2015-03-04 | 2015-03-05 | 5 | 1 | 4 | 2015-03-12 | 2015-07-28 | 93 | 0 | 93 | [20 empty] | 2015-03-13 | 2015-03-04 | 2015-07-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MONSON | 175838 | 1057 | 2000 | Solar | 09_503L2 | 2015-03-04 | 2015-03-05 | 4 | 0 | 4 | [10 empty] | 2015-03-11 | 2015-04-09 | 20 | 0 | 20 | [10 empty] | 2015-10-13 |  | 2017-08-14 | Yes | STD |  | 2017-03-08 | 2017-07-21 | 94 | 0 | 94 | 2017-08-18 | 2017-08-18 | 2017-08-18 | Connected |  | No
National Grid | REHOBOTH | 175839 | 2769 | 17.4 | Solar | 05_8L4 | 2015-03-04 | 2015-03-05 | 5 | 1 | 4 | 2015-03-12 | 2016-08-10 | 351 | 0 | 351 | [20 empty] | 2015-03-13 |  | 2015-07-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ANDOVER | 175840 | 1810 | 16 | Solar | 14_62L2 | 2015-03-04 | 2015-03-05 | 10 | 6 | 4 | 2015-03-20 | 2016-08-10 | 346 | 0 | 346 | [20 empty] | 2015-03-26 | 2015-03-06 | 2015-07-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BEVERLY | 175841 | 1915 | 100 | Solar | 12_51L1 | 2015-03-06 | 2015-03-09 | 5 | 0 | 5 | 2015-03-16 |  | 756 | 0 | 756 | [20 empty] | 2015-05-28 |  | 2018-06-29 |  | EXP |  | 2016-07-28 |  | 416 | 0 | 416 | 2015-07-20 | 2015-07-20 |  | Withdrawn |  | No
National Grid | BEVERLY | 175842 | 1915 | 100 | Solar | 12_51L1 | 2015-03-06 | 2015-03-09 | 3 | 0 | 3 | [26 empty] | 2015-03-06 | 2015-10-12 |  | EXP |  | 2016-07-28 | 2015-03-12 | 0 | 0 | 0 |  |  |  | Withdrawn |  | No
National Grid | LEICESTER | 175875 | 1524 | 2000 | Solar | 01_406L1 | 2015-03-06 | 2015-03-09 | 6 | 2 | 4 | [10 empty] | 2015-03-17 | 2015-04-16 | 21 | 0 | 21 | [5 empty] | 2016-01-22 | 2016-05-17 | 79 | 0 | 79 | 2016-05-17 | 2015-03-06 | 2017-12-31 | Yes | STD |  | 2018-03-02 | 2018-03-02 | 0 | 0 | 0 | 2017-12-31 | 2017-12-31 | 2017-12-31 | Connected |  | No
National Grid | LEICESTER | 175877 | 1524 | 2000 | Solar | 01_406L1 | 2015-03-06 | 2015-03-09 | 6 | 2 | 4 | [10 empty] | 2015-03-17 | 2015-04-16 | 21 | 0 | 21 | [5 empty] | 2016-01-22 | 2016-05-17 | 79 | 0 | 79 | 2016-05-17 | 2015-03-06 | 2017-12-31 | Yes | STD |  | 2018-03-02 | 2018-03-02 | 0 | 0 | 0 | 2017-12-31 | 2017-12-31 | 2017-12-31 | Connected |  | No
National Grid | LEICESTER | 175878 | 1524 | 1000 | Solar | 01_406L1 | 2015-03-06 | 2015-03-09 | 6 | 2 | 4 | [10 empty] | 2015-03-17 | 2015-04-16 | 21 | 0 | 21 | [5 empty] | 2016-01-22 | 2016-05-17 | 79 | 0 | 79 | 2016-05-17 |  | 2017-12-31 | Yes | STD |  | 2018-03-02 | 2018-03-02 | 0 | 0 | 0 | 2017-12-31 | 2017-12-31 | 2017-12-31 | Connected |  | No
National Grid | SWANSEA | 175880 | 2777 | 450 | Solar | 05_11W84 | 2015-03-06 | 2015-03-09 | 5 | 0 | 5 | 2015-03-16 | 2015-08-11 | 101 | 6 | 95 | [22 empty] | 2015-09-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 175873 | 1844 | 16 | Solar | 14_63L1 | 2015-03-09 01:00 | 2015-03-10 | 11 | 9 | 2 | 2015-03-26 | 2015-03-26 | 0 | 0 | 0 | [20 empty] | 2015-03-27 |  | 2015-08-10 |  | EXP | [6 empty] | 2015-07-21 | 2015-07-21 | 2015-12-09 | Connected |  | No
National Grid | SOUTHBRIDGE | 175874 | 1550 | 25 | Solar | 01_413L3 | 2015-03-09 01:00 | 2015-03-10 | 4 | 0 | 4 | 2015-03-16 | 2016-09-27 | 382 | 0 | 382 | [20 empty] | 2015-03-17 |  | 2016-12-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BEVERLY | 175876 | 1915 | 50 | Solar | 12_12L4 | 2015-03-09 01:00 | 2015-03-10 | 4 | 0 | 4 | 2015-03-16 | 2015-03-16 | 0 | 0 | 0 | [20 empty] | 2015-03-17 |  | 2015-08-13 |  | EXP | [6 empty] | 2015-05-13 | 2015-05-13 | 2015-07-07 | Connected |  | No
National Grid | AVON | 175879 | 2322 | 446.4 | Solar | 07_75W5 | 2015-03-09 01:00 | 2015-03-10 | 4 | 0 | 4 | 2015-03-16 | 2015-03-16 | 0 | 0 | 0 | [20 empty] | 2015-04-01 |  | 2015-09-30 |  | EXP | [6 empty] | 2015-04-06 | 2015-04-06 | 2017-03-30 | Connected |  | No
National Grid | BEVERLY | 175881 | 1915 | 40 | Solar | 12_12J6 | 2015-03-09 01:00 | 2015-03-13 | 1 | 0 | 1 | 2015-03-16 | 2015-03-16 | 0 | 0 | 0 | [20 empty] | 2015-03-18 |  | 2015-08-17 |  | EXP | [6 empty] | 2015-04-01 | 2015-04-01 | 2015-07-02 | Connected |  | No
National Grid | WILLIAMSTOWN | 175910 | 1267 | 130 | Solar | 09_1003W1 | 2015-03-09 01:00 | 2015-03-10 | 5 | 0 | 5 | 2015-03-18 | 2015-03-18 | 0 | 0 | 0 | [20 empty] | 2015-04-07 |  | 2015-07-31 |  | EXP | [6 empty] | 2015-07-30 | 2015-07-30 | 2015-07-30 | Connected |  | No
National Grid | FLORENCE | 175909 | 1062 | 20 | Solar | 09_909W4 | 2015-03-10 01:00 | 2015-03-11 | 4 | 0 | 4 | 2015-03-18 | 2015-03-18 | 0 | 0 | 0 | [20 empty] | 2015-03-19 |  | 2015-07-31 |  | EXP | [6 empty] | 2015-03-27 | 2015-03-27 | 2015-07-23 | Connected |  | No
National Grid | GLOUCESTER | 175911 | 1930 | 20 | Solar | 12_51T1 | 2015-03-11 01:00 | 2015-03-12 | 11 | 8 | 3 | 2015-03-30 | 2015-03-30 | 0 | 0 | 0 | [20 empty] | 2015-03-31 | 2015-03-11 01:00 | 2015-07-31 |  | EXP | [6 empty] | 2015-04-27 | 2015-04-27 | 2015-07-10 | Connected |  | No
National Grid | NORTHBRIDGE | 175913 | 1534 | 500 | Natural Gas | 05_321W10 | 2015-03-11 01:00 | 2015-03-12 | 3 | 0 | 3 | [10 empty] | 2015-03-17 | 2015-04-15 | 20 | 1 | 19 | [10 empty] | 2017-03-17 | 2015-03-11 01:00 | 2018-06-01 | Yes | STD |  | 2017-07-12 | 2017-07-28 | 12 | 0 | 12 | 2018-01-26 | 2018-01-26 | 2018-04-27 | Connected |  | No
National Grid | DIGHTON | 175915 | 2715 | 2000 | Solar | 05_19W73 | 2015-03-11 01:00 | 2015-03-12 | 9 | 6 | 3 | [10 empty] | 2015-03-26 | 2015-04-22 | 18 | 0 | 18 | [10 empty] | 2016-03-29 | 2015-03-12 01:00 | 2017-12-31 | Yes | STD |  | 2017-09-19 | 2017-12-14 | 54 | 0 | 54 | 2017-12-15 | 2017-12-15 | 2017-12-19 | Connected |  | No
National Grid | STURBRIDGE | 175914 | 1566 | 1500 | Solar | 01_408L1 | 2015-03-12 01:00 | 2015-03-13 | 2 | 0 | 2 | [10 empty] | 2015-03-18 | 2015-05-12 | 38 | 0 | 38 | [5 empty] | 2016-07-12 | 2016-10-06 | 61 | 0 | 61 | 2016-10-11 |  | 2017-10-31 | Yes | STD |  | 2017-06-22 | 2018-02-28 | 165 | 0 | 165 | 2017-10-18 | 2017-10-18 | 2017-11-29 | Connected |  | No
National Grid | PALMER | 175916 | 1069 | 252 | Solar | 09_503L1 | 2015-03-12 01:00 | 2015-03-13 | 8 | 6 | 2 | 2015-03-26 | 2015-03-26 | 0 | 0 | 0 | [20 empty] | 2015-03-31 |  | 2015-08-12 |  | EXP | [6 empty] | 2015-04-10 | 2015-04-10 | 2015-11-19 | Connected |  | No
National Grid | HAVERHILL | 175917 | 1830 | 1000 | Solar | 14_76L1 | 2015-03-12 01:00 | 2015-03-13 | 3 | 0 | 3 | [10 empty] | 2015-03-19 | 2015-04-16 | 20 | 0 | 20 | [10 empty] | 2015-09-29 |  | 2016-12-14 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BARRE | 175951 | 1005 | 990 | Solar | 09_604W3 | 2015-03-12 01:00 | 2015-03-13 | 8 | 3 | 5 | [10 empty] | 2015-03-26 | 2015-04-24 | 20 | 0 | 20 | [12 empty] | 2015-09-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BARRE | 175954 | 1005 | 990 | Solar | 09_604W3 | 2015-03-12 01:00 | 2015-03-20 | 4 | 3 | 1 | [10 empty] | 2015-03-26 | 2015-04-24 | 20 | 0 | 20 | [12 empty] | 2015-09-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTHBRIDGE | 175949 | 1534 | 15.2 | Solar | 05_320W1 | 2015-03-13 01:00 | 2015-03-16 | 7 | 4 | 3 | 2015-03-26 | 2017-02-13 | 468 | 0 | 468 | [20 empty] | 2015-03-27 |  | 2015-07-31 |  | EXP | [6 empty] | 2015-04-14 | 2015-04-14 |  | Withdrawn |  | No
National Grid | UXBRIDGE | 175948 | 1569 | 630 | Solar | 05_321W4 | 2015-03-16 01:00 | 2015-03-17 | 2 | 0 | 2 | [10 empty] | 2015-03-20 | 2015-04-17 | 20 | 0 | 20 | [11 empty] | 2015-03-16 01:00 | 2015-09-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH EASTON | 175950 | 2356 | 2166 | Solar | 07_98W46 | 2015-03-16 01:00 | 2015-03-17 | 6 | 4 | 2 | [10 empty] | 2015-03-26 | 2015-04-27 | 21 | 0 | 21 | [10 empty] | 2016-02-03 |  | 2017-08-31 | Yes | STD |  | 2017-03-06 | 2017-08-15 | 113 | 0 | 113 | 2017-08-16 | 2017-08-16 | 2017-09-06 | Connected |  | No
National Grid | MARLBOROUGH | 175946 | 1752 | 2.4 | Solar | 05_311W3 | 2015-03-17 01:00 | 2015-03-18 | 3 | 2 | 1 | 2015-03-23 | 2015-03-23 | 0 | 0 | 0 | [20 empty] | 2015-03-26 |  | 2015-07-17 |  | EXP | [6 empty] | 2016-09-22 | 2016-09-22 | 2017-05-05 | Connected |  | No
National Grid | WESTBOROUGH | 175947 | 1582 | 336 | Solar | 05_314W5 | 2015-03-17 01:00 | 2015-03-18 | 2 | 1 | 1 | 2015-03-20 | 2016-11-10 | 410 | 13 | 397 | [20 empty] | 2015-05-08 |  | 2015-08-17 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FRANKLIN | 175989 | 2038 | 15 | Solar | 05_344W5 | 2015-03-18 01:00 | 2015-03-19 | 4 | 0 | 4 | 2015-03-25 | 2015-03-25 | 0 | 0 | 0 | [20 empty] | 2015-03-26 |  | 2015-07-20 |  | EXP | [6 empty] | 2015-04-15 | 2015-04-15 | 2016-03-18 | Connected |  | No
National Grid | MARLBOROUGH | 175990 | 1752 | 12 | Solar | 05_311W4 | 2015-03-18 01:00 | 2015-03-19 | 4 | 0 | 4 | 2015-03-25 | 2015-03-25 | 0 | 0 | 0 | [20 empty] | 2015-04-10 |  | 2016-12-31 |  | EXP | [6 empty] | 2015-04-10 | 2015-04-10 | 2016-10-05 | Connected |  | No
National Grid | EAST BRIDGEWATER | 175952 | 2333 | 17.6 | Solar | 07_797W24 | 2015-03-19 01:00 | 2015-03-20 | 10 | 9 | 1 | 2015-04-03 | 2017-02-01 | 454 | 0 | 454 | [20 empty] | 2015-04-06 |  | 2015-07-17 |  | EXP | [6 empty] | 2015-04-24 | 2015-04-24 |  | Withdrawn |  | No
National Grid | NORTH GRAFTON | 175953 | 1536 | 20.21 | Solar | 01_328W2 | 2015-03-19 01:00 | 2015-03-20 | 3 | 0 | 3 | 2015-03-25 | 2015-06-10 | 53 | 0 | 53 | [20 empty] | 2015-04-09 | 2015-03-20 01:00 | 2015-07-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | AUBURN | 175983 | 1501 | 4875 | Solar | 01_26W1 | 2015-03-20 01:00 | 2015-03-23 | 5 | 4 | 1 | [10 empty] | 2015-03-30 | 2015-04-27 | 19 | 0 | 19 | [10 empty] | 2016-11-15 |  | 2022-05-25 | Yes | STD | [8 empty] | 2022-05-17 | Connected |  | No
National Grid | AUBURN | 175984 | 1540 | 1000 | Solar | 01_26W1 | 2015-03-20 01:00 | 2015-03-23 | 5 | 4 | 1 | [10 empty] | 2015-03-30 | 2015-04-27 | 19 | 0 | 19 | [10 empty] | 2016-11-15 |  | 2015-09-21 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | AUBURN | 175985 | 1501 | 1000 | Solar | 01_26W1 | 2015-03-20 01:00 | 2015-03-23 | 5 | 4 | 1 | [10 empty] | 2015-03-30 | 2015-04-27 | 19 | 0 | 19 | [10 empty] | 2016-11-15 |  | 2015-09-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | AUBURN | 175986 | 1501 | 1000 | Solar | 01_26W1 | 2015-03-20 01:00 | 2015-03-20 | 6 | 4 | 2 | [10 empty] | 2015-03-30 | 2015-04-27 | 19 | 0 | 19 | [10 empty] | 2016-11-15 |  | 2015-09-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | AUBURN | 175987 | 1501 | 1000 | Solar | 01_26W1 | 2015-03-20 01:00 | 2015-03-23 | 5 | 4 | 1 | [10 empty] | 2015-03-30 | 2015-04-27 | 19 | 0 | 19 | [10 empty] | 2016-11-15 |  | 2015-09-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 176018 | 1507 | 7.6 | Solar | 01_415L1 | 2015-03-20 01:00 | 2015-03-23 | 2 | 1 | 1 | 2015-03-25 | 2016-08-10 | 343 | 0 | 343 | [20 empty] | 2015-03-27 |  | 2015-07-20 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SHUTESBURY | 176019 | 1072 | 4500 | Solar | 09_704W1 | 2015-03-20 01:00 | 2015-03-23 | 17 | 14 | 3 | [10 empty] | 2015-04-15 | 2015-05-13 | 19 | 0 | 19 | [10 empty] | 2016-02-24 | 2015-03-23 01:00 | 2019-04-01 |  | STD |  | 2018-08-04 | 2018-10-18 | 75 | 0 | 75 |  |  | 2019-03-27 | Connected |  | No
National Grid | BEVERLY | 175991 | 1915 | 100 | Solar | 12_51L1 | 2015-03-23 01:00 | 2015-03-24 | 2 | 0 | 2 | 2015-03-26 |  | 749 | 0 | 749 | [20 empty] | 2015-05-28 |  | 2018-05-31 | Yes | EXP | [6 empty] | 2015-07-20 | 2015-07-20 |  | Withdrawn |  | No
National Grid | MILFORD | 176021 | 1757 | 820 | Natural Gas | 05_335W4 | 2015-03-23 01:00 | 2015-03-24 | 2 | 0 | 2 | [10 empty] | 2015-03-26 | 2015-05-20 | 38 | 0 | 38 | [10 empty] | 2015-10-20 |  | 2016-12-31 |  | STD | [6 empty] | 2015-12-23 | 2015-12-23 | 2015-12-23 | Connected |  | No
National Grid | MILFORD | 176865 | 1757 | 820 | Natural Gas | 05_335W4 | 2015-03-23 01:00 | 2015-03-24 | 2 | 0 | 2 | [10 empty] | 2015-03-26 | 2015-05-20 | 38 | 0 | 38 | [10 empty] | 2015-10-20 |  | 2016-01-27 |  | STD | [6 empty] | 2015-12-23 | 2015-12-23 | 2015-12-23 | Connected |  | No
National Grid | BILLERICA | 176022 | 1821 | 3 | Solar | 14_92L2 | 2015-03-25 01:00 | 2015-03-26 | 6 | 0 | 6 | 2015-04-03 | 2017-02-15 | 464 | 0 | 464 | [20 empty] | 2015-04-06 |  | 2015-08-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HARDWICK | 176023 | 1037 | 180 | Solar | 09_501L2 | 2015-03-25 01:00 | 2015-03-26 | 7 | 4 | 3 | 2015-04-06 | 2015-04-06 | 0 | 0 | 0 | [20 empty] | 2015-04-06 |  | 2015-08-31 |  | EXP | [6 empty] | 2017-07-10 | 2017-07-10 | 2017-07-31 | Connected |  | No
National Grid | SWANSEA | 176025 | 2777 | 980 | Solar | 05_19W73 | 2015-03-27 01:00 | 2015-03-30 | 4 | 0 | 4 | [10 empty] | 2015-04-03 | 2015-05-04 | 20 | 0 | 20 | [12 empty] | 2015-09-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HAVERHILL | 176056 | 1832 | 980 | Solar | 14_74L1 | 2015-03-27 01:00 | 2015-03-30 | 4 | 1 | 3 | [10 empty] | 2015-04-03 | 2015-05-04 | 20 | 0 | 20 | [11 empty] | 2015-03-27 01:00 | 2015-09-01 |  | STD |  | 2017-08-22 | 2018-01-31 | 104 | 0 | 104 |  |  |  | Withdrawn |  | No
National Grid | HAVERHILL | 176057 | 1832 | 996 | Solar | 14_74L1 | 2015-03-27 01:00 | 2015-03-30 | 4 | 0 | 4 | [10 empty] | 2015-04-03 | 2015-05-04 | 20 | 0 | 20 | [10 empty] | 2015-12-11 | 2015-03-27 01:00 | 2015-08-01 | Yes | STD |  | 2017-08-22 | 2018-01-31 | 104 | 0 | 104 | 2017-11-16 | 2017-11-16 | 2017-11-16 | Connected |  | No
National Grid | SWANSEA | 176058 | 2777 | 996 | Solar | 05_11W84 | 2015-03-27 01:00 | 2015-03-30 | 4 | 0 | 4 | [10 empty] | 2015-04-03 | 2015-04-29 | 17 | 0 | 17 | [5 empty] | 2016-03-10 | 2016-03-10 | 0 | 0 | 0 | 2016-02-24 |  | 2017-10-15 | Yes | STD |  | 2017-09-11 | 2017-10-24 | 30 | 0 | 30 | 2017-10-12 | 2017-10-12 | 2017-10-17 | Connected |  | No
National Grid | SWANSEA | 176059 | 2777 | 980 | Solar | 05_11W84 | 2015-03-27 01:00 | 2015-03-30 | 4 | 0 | 4 | [10 empty] | 2015-04-03 | 2015-04-29 | 17 | 0 | 17 | [11 empty] | 2015-03-27 01:00 | 2015-08-07 |  | STD |  | 2017-09-11 | 2017-10-24 | 30 | 0 | 30 |  |  |  | Withdrawn |  | No
National Grid | NORTH ADAMS | 176060 | 1247 | 499 | Solar | 09_1021W2 | 2015-03-27 01:00 | 2015-03-30 | 4 | 0 | 4 | [10 empty] | 2015-04-03 | 2015-05-05 | 21 | 0 | 21 | [5 empty] | 2016-07-12 | 2016-10-19 | 69 | 14 | 55 | 2016-11-22 | 2015-03-27 01:00 | 2017-05-01 | Yes | STD |  | 2017-06-19 | 2017-06-09 | 0 | 0 | 0 | 2017-08-11 | 2017-08-11 | 2017-08-24 | Connected |  | No
National Grid | TYNGSBORO | 176061 | 1879 | 900 | Solar | 01_210L1 | 2015-03-27 01:00 | 2015-03-30 | 6 | 1 | 5 | [10 empty] | 2015-04-07 | 2015-05-05 | 19 | 0 | 19 | [10 empty] | 2016-01-11 | 2015-03-30 01:00 | 2015-08-08 | Yes | STD |  | 2016-11-30 | 2017-01-09 | 26 | 0 | 26 | 2016-12-29 | 2016-12-29 | 2016-12-29 | Connected |  | No
National Grid | WESTBOROUGH | 176026 | 1581 | 266 | Solar | 05_312W2 | 2015-03-30 01:00 | 2015-03-31 | 7 | 3 | 4 | 2015-04-09 | 2015-05-12 | 22 | 0 | 22 | [22 empty] | 2015-08-25 | Yes | EXP |  | 2016-03-29 | 2016-06-02 | 45 | 0 | 45 |  |  |  | Withdrawn |  | No
National Grid | WESTBOROUGH | 176027 | 1581 | 475 | Solar | 05_312W2 | 2015-03-30 01:00 | 2015-03-31 | 6 | 2 | 4 | [27 empty] | 2015-08-25 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTBOROUGH | 176093 | 1581 | 475 | Solar | 05_312W2 | 2015-03-30 01:00 | 2015-03-31 | 8 | 0 | 8 | 2015-04-10 | 2015-05-12 | 21 | 0 | 21 | [22 empty] | 2015-08-25 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | REHOBOTH | 176062 | 2769 | 28.8 | Solar | 05_7L4 | 2015-03-31 01:00 | 2015-04-01 | 4 | 1 | 3 | 2015-04-07 | 2015-04-07 | 0 | 0 | 0 | [20 empty] | 2015-04-08 |  | 2015-07-31 |  | EXP | [6 empty] | 2015-09-23 | 2015-09-23 | 2015-09-28 | Connected |  | No
National Grid | NORTHAMPTON | 176063 | 1060 | 45 | Solar | 09_909W2 | 2015-04-01 01:00 | 2015-04-02 | 5 | 0 | 5 | 2015-04-09 | 2015-04-09 | 0 | 0 | 0 | [20 empty] | 2015-04-13 |  | 2015-04-12 |  | EXP | [6 empty] | 2015-04-24 | 2015-04-24 | 2015-10-09 | Connected |  | No
National Grid | BEVERLY | 176091 | 1915 | 266 | Solar | 12_51L2 | 2015-04-01 01:00 | 2015-04-02 | 6 | 0 | 6 | 2015-04-10 | 2015-05-12 | 21 | 0 | 21 | [22 empty] | 2015-10-25 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BEVERLY | 176064 | 1915 | 135 | Solar | 12_51L2 | 2015-04-02 01:00 | 2015-04-02 | 6 | 0 | 6 | 2015-04-10 | 2015-05-12 | 21 | 0 | 21 | [22 empty] | 2015-10-25 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MILFORD | 176094 | 1757 | 84 | Solar | 05_335W5 | 2015-04-02 01:00 | 2015-04-09 | 2 | 0 | 2 | 2015-04-13 | 2015-12-10 | 165 | 0 | 165 | [20 empty] | 2015-04-13 | 2015-04-03 01:00 | 2015-08-07 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BRIDGEWATER | 176095 | 2324 | 750 | Wind | 07_912W55 | 2015-04-03 01:00 | 2015-04-06 | 5 | 0 | 5 | [10 empty] | 2015-04-13 | 2015-05-11 | 19 | 0 | 19 | [5 empty] | 2015-07-30 | 2016-01-15 | 115 | 0 | 115 | 2016-03-31 |  | 2020-10-30 |  | STD |  | 2016-12-14 | 2018-05-17 | 519 | 0 | 519 | 2018-04-05 | 2018-04-05 | 2020-09-29 | Connected |  | No
National Grid | WESTBOROUGH | 176096 | 1581 | 300 | Solar | 05_312W4 | 2015-04-03 01:00 | 2015-04-06 | 5 | 0 | 5 | 2015-04-13 | 2015-04-20 | 5 | 0 | 5 | [20 empty] | 2015-04-20 |  | 2018-02-07 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MILLBURY | 176092 | 1527 | 980 | Solar | 01_304W4 | 2015-04-06 01:00 | 2015-04-07 | 2 | 0 | 2 | [10 empty] | 2015-04-09 | 2015-04-20 | 7 | 0 | 7 | [11 empty] | 2015-04-06 01:00 | 2015-09-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SAUGUS | 176097 | 1906 | 1296 | Solar | 12_25W1 | 2015-04-06 01:00 | 2015-04-07 | 4 | 0 | 4 | [10 empty] | 2015-04-13 | 2015-05-11 | 19 | 0 | 19 | [10 empty] | 2016-04-06 |  | 2017-09-29 |  | STD | [6 empty] | 2017-09-07 | 2017-09-07 | 2017-09-08 | Connected |  | No
National Grid | HOLBROOK | 176098 | 2343 | 16.77 | Solar | 07_2W1 | 2015-04-07 01:00 | 2015-04-08 | 4 | 1 | 3 | 2015-04-14 | 2015-04-14 | 0 | 0 | 0 | [20 empty] | 2015-04-14 |  | 2015-08-10 |  | EXP | [6 empty] | 2015-04-27 | 2015-04-27 | 2016-07-25 | Connected |  | No
National Grid | FLORENCE | 176099 | 1062 | 300 | Solar | 09_909W4 | 2015-04-10 01:00 | 2015-04-13 | 3 | 3 | 0 | 2015-04-16 | 2016-07-27 | 317 | 0 | 317 | [20 empty] | 2015-04-21 | 2015-04-13 01:00 | 2015-09-11 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH ADAMS | 176100 | 1247 | 996 | Solar | 09_1015W1 | 2015-04-13 01:00 | 2015-04-13 | 1 | 0 | 1 | [10 empty] | 2015-04-14 | 2015-05-12 | 19 | 0 | 19 | [10 empty] | 2017-05-08 |  | 2017-11-01 | Yes | STD |  | 2017-06-13 | 2017-10-06 | 81 | 0 | 81 | 2017-09-26 | 2017-09-26 | 2017-10-10 | Connected |  | No
National Grid | RUTLAND | 176129 | 1543 | 4.3 | Solar | 01_55W1 | 2015-04-13 01:00 | 2015-04-13 | 3 | 2 | 1 | 2015-04-16 | 2015-04-16 | 0 | 0 | 0 | [20 empty] | 2015-04-16 |  | 2015-08-31 |  | EXP | [6 empty] | 2015-04-27 | 2015-04-27 | 2015-08-26 | Connected |  | No
National Grid | QUINCY | 176128 | 2169 | 225 | Natural Gas | 07_3W4 | 2015-04-14 01:00 | 2015-04-14 | 0 | 0 | 0 | 2015-04-14 | 2015-04-14 | 0 | 0 | 0 | [20 empty] | 2015-04-16 |  | 2015-09-01 |  | EXP | [6 empty] | 2015-08-14 | 2015-08-14 | 2015-08-25 | Connected |  | Yes
National Grid | SAUGUS | 176130 | 1906 | 7.1 | Solar | 12_23W1 | 2015-04-14 01:00 | 2015-04-14 | 1 | 0 | 1 | 2015-04-15 | 2015-04-15 | 0 | 0 | 0 | [20 empty] | 2015-04-17 |  | 2015-08-31 |  | EXP | [6 empty] | 2015-07-02 | 2015-07-02 | 2015-07-06 | Connected |  | No
National Grid | WESTMINSTER | 176131 | 1473 | 19 | Solar | 01_610W3 | 2015-04-14 01:00 | 2015-04-15 | 1 | 1 | 0 | 2015-04-16 | 2017-02-01 | 445 | 0 | 445 | [20 empty] | 2015-04-17 |  | 2015-08-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LANCASTER | 176132 | 1523 | 495 | Solar | 01_225W1 | 2015-04-14 01:00 | 2015-04-15 | 4 | 4 | 0 | 2015-04-22 | 2015-12-21 | 166 | 0 | 166 | [21 empty] | 2015-04-15 01:00 | 2015-09-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTHBRIDGE | 176133 | 1534 | 10 | Solar | 05_320W1 | 2015-04-15 01:00 | 2015-04-16 | 1 | 1 | 0 | 2015-04-17 | 2015-04-17 | 0 | 0 | 0 | [20 empty] | 2015-04-27 |  | 2016-12-31 |  | EXP |  | 2016-02-19 | 2016-02-29 | 6 | 0 | 6 | 2015-04-27 | 2015-04-27 | 2016-08-08 | Connected |  | No
National Grid | BRIDGEWATER | 176134 | 2324 | 1000 | Solar | 07_797W42 | 2015-04-16 01:00 | 2015-04-16 | 1 | 1 | 0 | [10 empty] | 2015-04-17 | 2015-05-18 | 20 | 0 | 20 | [11 empty] | 2015-04-16 01:00 | 2015-09-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BEVERLY | 176135 | 1915 | 3520 | Solar | 12_51L1 | 2015-04-16 01:00 | 2015-04-17 | 2 | 2 | 0 | [10 empty] | 2015-04-22 | 2015-05-20 | 20 | 0 | 20 | [5 empty] | 2017-09-06 | 2018-07-27 | 224 | 0 | 224 | 2016-08-04 | 2015-04-17 01:00 | 2020-12-31 | Yes | STD |  | 2020-05-22 | 2020-10-26 | 158 | 5 | 153 |  |  | 2020-12-23 | Connected |  | No
National Grid | WESTBOROUGH | 176165 | 1581 | 850 | Solar | 05_312W4 | 2015-04-17 01:00 | 2015-04-17 | 2 | 2 | 0 | [10 empty] | 2015-04-22 | 2015-05-07 | 11 | 0 | 11 | [5 empty] | 2015-12-22 | 2016-05-11 | 95 | 0 | 95 | 2016-06-03 | 2015-04-17 01:00 | 2017-03-17 | Yes | STD |  | 2016-10-13 | 2017-04-07 | 120 | 0 | 120 | 2017-04-26 | 2017-04-26 | 2017-04-26 | Connected |  | No
National Grid | SWANSEA | 176169 | 2777 | 476 | Solar | 05_11W81 | 2015-04-17 01:00 | 2015-04-20 | 1 | 1 | 0 | 2015-04-22 | 2015-04-22 | 0 | 0 | 0 | [20 empty] | 2015-05-29 |  | 2016-12-31 | Yes | EXP |  | 2016-08-30 | 2016-12-12 | 70 | 0 | 70 | 2015-05-29 | 2015-05-29 | 2016-12-13 | Connected |  | No
National Grid | BEVERLY | 176167 | 1915 | 150 | Solar | 12_51T1 | 2015-04-20 01:00 | 2015-04-20 | 0 | 0 | 0 | 2015-04-20 | 2015-04-20 | 0 | 0 | 0 | [20 empty] | 2015-04-22 |  | 2015-09-30 |  | EXP | [6 empty] | 2015-06-19 | 2015-06-19 | 2015-11-06 | Connected |  | No
National Grid | GLOUCESTER | 176170 | 1930 | 2.75 | Solar | 12_51T1 | 2015-04-22 01:00 | 2015-04-23 | 1 | 1 | 0 | 2015-04-24 | 2015-04-24 | 0 | 0 | 0 | [20 empty] | 2015-05-11 |  | 2015-09-30 |  | EXP | [6 empty] | 2015-06-01 | 2015-06-01 | 2015-09-24 | Connected |  | No
National Grid | MILFORD | 176171 | 1757 | 6 | Solar | 05_335W5 | 2015-04-23 01:00 | 2015-04-23 | 3 | 2 | 1 | 2015-04-28 | 2015-04-28 | 0 | 0 | 0 | [20 empty] | 2015-04-29 |  | 2015-08-31 |  | EXP | [6 empty] | 2015-06-17 | 2015-06-17 | 2015-10-26 | Connected |  | No
National Grid | BERLIN | 176172 | 1503 | 2000 | Solar |  | 2015-04-23 01:00 | 2015-04-24 | 2 | 2 | 0 | [10 empty] | 2015-04-28 | 2015-05-27 | 20 | 0 | 20 | [11 empty] | 2015-04-23 01:00 | 2015-10-23 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | FALL RIVER | 176173 | 2720 | 972 | Solar | 05_28W41 | 2015-04-23 01:00 | 2015-04-24 | 3 | 3 | 0 | [10 empty] | 2015-04-29 | 2015-05-26 | 18 | 0 | 18 | [5 empty] | 2015-11-18 | 2015-12-21 | 22 | 0 | 22 | 2016-01-22 |  | 2015-09-30 | Yes | STD |  | 2016-07-12 | 2016-10-17 | 67 | 0 | 67 | 2016-10-21 | 2016-10-21 | 2016-10-28 | Connected |  | No
National Grid | SHEFFIELD | 176202 | 1257 | 150 | Solar | 09_1109W2 | 2015-04-24 01:00 | 2015-04-27 | 0 | 0 | 0 | 2015-04-27 | 2016-04-13 | 240 | 0 | 240 | [20 empty] | 2015-06-09 | 2015-04-24 01:00 | 2016-12-31 |  | EXP | [6 empty] | 2015-07-10 | 2015-07-10 |  | Withdrawn |  | No
National Grid | SPENCER | 176203 | 1562 | 3.8 | Solar | 01_21W1 | 2015-04-24 01:00 | 2015-04-27 | 2 | 2 | 0 | 2015-04-29 | 2015-04-29 | 0 | 0 | 0 | [20 empty] | 2015-05-14 | 2015-04-24 01:00 | 2016-12-31 | Yes | EXP |  | 2016-06-17 | 2016-06-15 | 0 | 0 | 0 | 2016-05-26 | 2016-05-26 | 2016-05-26 | Connected |  | No
National Grid | WORCESTER | 176204 | 1605 | 13.6 | Solar | 01_24W2 | 2015-04-24 01:00 | 2015-04-27 | 2 | 2 | 0 | 2015-04-29 | 2015-04-29 | 0 | 0 | 0 | [20 empty] | 2015-05-13 |  | 2016-12-31 | Yes | EXP |  | 2016-10-14 | 2016-10-26 | 8 | 0 | 8 | 2015-05-13 | 2015-05-13 | 2016-11-15 | Connected |  | No
National Grid | GILBERTVILLE | 176205 | 1031 | 495 | Solar | 09_501L2 | 2015-04-24 01:00 | 2015-04-27 | 6 | 6 | 0 | 2015-05-05 | 2016-05-02 | 246 | 0 | 246 | [22 empty] | 2015-09-01 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTHBOROUGH | 176206 | 1532 | 15.6 | Solar | 05_313W4 | 2015-04-24 01:00 | 2015-04-27 | 6 | 6 | 0 | 2015-05-05 | 2015-05-05 | 0 | 0 | 0 | [20 empty] | 2015-05-12 | 2015-04-24 01:00 | 2015-08-31 |  | EXP | [6 empty] | 2016-03-23 | 2016-03-23 | 2016-03-23 | Connected |  | No
National Grid | LYNN | 176207 | 1904 | 11.4 | Solar | 12_29W1 | 2015-04-24 01:00 | 2015-04-28 | 2 | 2 | 0 | 2015-04-30 | 2015-04-30 | 0 | 0 | 0 | [20 empty] | 2015-05-14 |  | 2016-12-31 | Yes | EXP |  | 2016-08-29 | 2016-09-30 | 23 | 0 | 23 | 2016-09-12 | 2016-09-12 | 2016-09-12 | Connected |  | No
National Grid | DUDLEY | 176210 | 1571 | 5 | Solar | 01_412L5 | 2015-04-27 01:00 | 2015-04-29 | 0 | 0 | 0 | 2015-04-29 | 2015-04-29 | 0 | 0 | 0 | [20 empty] | 2015-04-30 | 2015-04-27 01:00 | 2015-09-30 |  | EXP | [6 empty] | 2016-03-22 | 2016-03-22 | 2016-03-29 | Connected |  | No
National Grid | SHIRLEY | 176238 | 1464 | 1000 | Solar | 01_201W1 | 2015-04-27 01:00 | 2015-05-04 | 2 | 0 | 2 | [10 empty] | 2015-05-06 | 2015-06-04 | 20 | 0 | 20 | [5 empty] | 2016-08-26 | 2016-06-24 | 0 | 0 | 0 | 2016-08-04 | 2015-04-27 01:00 | 2018-07-31 |  | STD |  | 2017-11-28 | 2018-05-30 | 183 | 0 | 183 | 2018-01-25 | 2018-01-25 | 2018-06-29 | Connected |  | No
National Grid | SHIRLEY | 176239 | 1464 | 1000 | Solar | 01_201W1 | 2015-04-27 01:00 | 2015-05-04 | 2 | 2 | 0 | [10 empty] | 2015-05-06 | 2015-06-04 | 20 | 0 | 20 | [5 empty] | 2016-03-15 | 2016-06-24 | 69 | 0 | 69 | 2016-08-04 |  | 2018-07-31 |  | STD |  | 2017-11-28 | 2018-05-30 | 183 | 0 | 183 | 2018-01-09 | 2018-01-09 | 2018-06-29 | Connected |  | No
National Grid | FOXBOROUGH | 178786 | 2035 | 19.4 | Solar | 05_3422W3 | 2015-04-27 01:00 | 2015-04-29 | 0 | 0 | 0 | 2015-04-29 | 2015-04-29 | 0 | 0 | 0 | [20 empty] | 2015-04-30 | 2015-04-28 01:00 | 2015-09-30 |  | EXP | [6 empty] | 2015-08-04 | 2015-08-04 | 2016-07-01 | Connected |  | No
National Grid | UPTON | 176240 | 1568 | 1000 | Solar | 05_335W3 | 2015-04-28 01:00 | 2015-05-04 | 0 | 0 | 0 | [10 empty] | 2015-05-04 | 2015-05-29 | 18 | 0 | 18 | [10 empty] | 2015-10-27 | 2015-04-28 01:00 | 2017-08-31 | Yes | STD |  | 2017-05-10 | 2017-08-22 | 72 | 0 | 72 | 2017-09-05 | 2017-09-05 | 2017-09-05 | Connected |  | No
National Grid | UPTON | 176241 | 1568 | 1000 | Solar | 05_335W3 | 2015-04-28 01:00 | 2015-05-04 | 0 | 0 | 0 | [10 empty] | 2015-05-04 | 2015-05-29 | 18 | 0 | 18 | [10 empty] | 2015-10-27 | 2015-04-29 01:00 | 2017-08-31 | Yes | STD |  | 2017-05-10 | 2017-08-22 | 72 | 0 | 72 | 2017-09-05 | 2017-09-05 | 2017-09-05 | Connected |  | No
National Grid | CHARLTON | 176242 | 1507 | 2000 | Solar | 01_415L2 | 2015-04-29 01:00 | 2015-05-04 | 0 | 0 | 0 | [10 empty] | 2015-05-04 | 2015-06-01 | 19 | 0 | 19 | [5 empty] | 2016-08-11 | 2016-07-11 | 0 | 0 | 0 | 2016-07-11 |  | 2018-04-01 | Yes | STD |  | 2017-07-31 | 2018-02-08 | 126 | 0 | 126 | 2018-03-15 | 2018-03-15 | 2018-03-15 | Connected |  | No
National Grid | CHARLTON | 176243 | 1507 | 275 | Solar | 01_415L2 | 2015-04-29 01:00 | 2015-05-04 | 0 | 0 | 0 | [10 empty] | 2015-05-04 | 2015-06-01 | 19 | 0 | 19 | [5 empty] | 2016-08-19 | 2016-07-11 | 0 | 0 | 0 | 2016-07-11 |  | 2015-10-30 |  | STD |  | 2017-07-31 | 2018-02-08 | 126 | 0 | 126 |  |  |  | Withdrawn |  | No
National Grid | WORCESTER | 176244 | 1604 | 96 | Solar | 01_27W5 | 2015-04-30 01:00 | 2015-05-04 | 1 | 1 | 0 | 2015-05-05 | 2015-05-05 | 0 | 0 | 0 | [20 empty] | 2015-05-12 |  | 2015-10-30 |  | EXP | [6 empty] | 2015-06-01 | 2015-06-01 | 2016-12-02 | Connected |  | No
National Grid | EAST BRIDGEWATER | 176245 | 2333 | 5100 | Solar | 07_91W41 | 2015-04-30 01:00 | 2015-05-06 | 0 | 0 | 0 | [10 empty] | 2015-05-06 | 2015-05-08 | 2 | 0 | 2 | [12 empty] | 2015-10-30 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | BILLERICA | 176246 | 1821 | 17.2 | Solar | 14_70L6 | 2015-04-30 01:00 | 2015-05-06 | 5 | 5 | 0 | 2015-05-13 | 2015-05-13 | 0 | 0 | 0 | [20 empty] | 2015-05-14 |  | 2015-10-30 |  | EXP | [6 empty] | 2015-12-10 | 2015-12-10 | 2015-12-10 | Connected |  | No
National Grid | RANDOLPH | 176247 | 2368 | 3780 | Solar | 07_97W2 | 2015-05-01 01:00 | 2015-05-06 | 2 | 2 | 0 | [26 empty] | 2015-05-01 01:00 | 2015-10-30 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 176275 | 2302 | 10 | Solar | 07_712J1 | 2015-05-01 01:00 | 2015-08-22 | 70 | 70 | 0 | 2015-08-18 | 2015-08-25 | 5 | 0 | 5 | [20 empty] | 2015-09-09 |  | 2019-02-02 | Yes | EXP |  | 2016-11-10 | 2016-11-22 | 7 | 0 | 7 |  |  | 2019-01-31 | Connected |  | Yes
National Grid | LYNN | 176276 | 1905 | 79 | Solar | 12_29W3 | 2015-05-04 01:00 | 2015-05-07 | 0 | 0 | 0 | 2015-05-07 | 2016-09-30 | 349 | 0 | 349 | [20 empty] | 2015-05-12 |  | 2015-10-30 |  | EXP | [6 empty] | 2015-06-09 | 2015-06-09 |  | Withdrawn |  | No
National Grid | DUNSTABLE | 176277 | 1827 | 20 | Solar | 01_210L1 | 2015-05-05 01:00 | 2015-05-07 | 50 | 50 | 0 | [26 empty] | 2015-05-05 01:00 | 2015-10-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | HANOVER | 176278 | 2339 | 98 | Solar | 07_910W51 | 2015-05-05 01:00 | 2015-05-07 | 1 | 1 | 0 | 2015-05-08 | 2017-01-13 | 418 | 0 | 418 | [20 empty] | 2015-05-13 |  | 2015-10-30 | Yes | EXP | [9 empty] | Withdrawn |  | No
National Grid | WARE | 176279 | 1082 | 75 | Solar | 09_501L1 | 2015-05-06 01:00 | 2015-05-07 | 1 | 1 | 0 | 2015-05-08 | 2015-05-08 | 0 | 0 | 0 | [20 empty] | 2015-06-03 | 2015-05-06 01:00 | 2015-10-30 |  | EXP | [6 empty] | 2015-06-10 | 2015-06-10 | 2016-11-23 | Connected |  | No
National Grid | NEWBURYPORT | 176280 | 1950 | 42 | Solar | 14_60L3 | 2015-05-06 01:00 | 2015-05-07 | 0 | 0 | 0 | 2015-05-07 | 2015-05-07 | 0 | 0 | 0 | [20 empty] | 2015-05-22 |  | 2015-10-30 | Yes | EXP |  | 2016-03-14 | 2016-03-14 | 0 | 0 | 0 | 2015-06-09 | 2015-06-09 | 2016-05-13 | Connected |  | No
National Grid | AUBURN | 176281 | 1501 | 16.32 | Solar | 01_6W1 | 2015-05-06 01:00 | 2015-05-08 | 3 | 3 | 0 | 2015-05-13 | 2015-05-13 | 0 | 0 | 0 | [20 empty] | 2015-05-14 |  | 2015-10-30 |  | EXP | [6 empty] | 2016-05-09 | 2016-05-09 | 2016-05-12 | Connected |  | No
National Grid | MILLBURY | 176282 | 1527 | 19 | Solar | 01_304W4 | 2015-05-06 01:00 | 2015-05-08 | 3 | 3 | 0 | 2015-05-13 | 2015-05-13 | 0 | 0 | 0 | [20 empty] | 2015-05-14 |  | 2015-10-30 |  | EXP | [6 empty] | 2015-12-07 | 2015-12-07 | 2015-12-07 | Connected |  | No
National Grid | BARRE | 175975 | 1005 | 990 | Solar | 09_604W4 | 2015-05-07 01:00 | 2015-05-08 | 0 | 0 | 0 | [10 empty] | 2015-05-08 | 2015-05-08 | 0 | 0 | 0 | [11 empty] | 2015-05-07 01:00 | 2015-06-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BARRE | 175977 | 1005 | 760 | Solar | 09_604W4 | 2015-05-07 01:00 | 2015-05-08 | 0 | 0 | 0 | [10 empty] | 2015-05-08 | 2015-05-08 | 0 | 0 | 0 | [5 empty] | 2016-05-31 | 2016-08-11 | 50 | 0 | 50 | 2015-12-09 |  | 2016-06-30 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | GLOUCESTER | 176284 | 1930 | 126 | Solar | 12_51T1 | 2015-05-07 01:00 | 2015-05-11 | 14 | 14 | 0 | 2015-06-01 | 2015-06-01 | 0 | 0 | 0 | [20 empty] | 2015-08-31 |  | 2016-12-31 |  | EXP | [6 empty] | 2016-02-12 | 2016-02-12 | 2017-03-13 | Connected |  | No
National Grid | HUBBARDSTON | 176313 | 1452 | 96 | Solar | 01_609W1 | 2015-05-07 01:00 | 2015-05-11 | 0 | 0 | 0 | 2015-05-11 | 2015-05-11 | 0 | 0 | 0 | [20 empty] | 2015-05-13 | 2015-05-08 01:00 | 2015-10-30 |  | EXP | [6 empty] | 2015-06-09 | 2015-06-09 | 2016-05-10 | Connected |  | No
National Grid | EAST BRIDGEWATER | 176315 | 2333 | 2610 | Solar | 07_91W41 | 2015-05-08 01:00 | 2015-05-12 | 0 | 0 | 0 | [10 empty] | 2015-05-12 | 2015-06-04 | 16 | 0 | 16 | [10 empty] | 2015-12-24 | 2015-05-08 01:00 | 2017-10-10 | Yes | STD |  | 2017-05-05 | 2017-11-08 | 124 | 0 | 124 | 2017-11-08 | 2017-11-08 | 2017-11-15 | Connected |  | No
National Grid | RANDOLPH | 176316 | 2368 | 3780 | Solar | 07_97W2 | 2015-05-08 01:00 | 2015-05-12 | 0 | 0 | 0 | [10 empty] | 2015-05-12 | 2015-06-09 | 19 | 0 | 19 | [10 empty] | 2016-02-01 | 2015-05-08 01:00 | 2017-11-09 | Yes | STD |  | 2017-06-28 | 2017-10-24 | 81 | 0 | 81 | 2017-10-25 | 2017-10-25 | 2017-11-07 | Connected |  | No
National Grid | PLAINVILLE | 176317 | 2762 | 4890 | Solar | 05_2286 | 2015-05-08 01:00 | 2015-05-12 | 0 | 0 | 0 | [10 empty] | 2015-05-12 | 2015-06-09 | 19 | 0 | 19 | [10 empty] | 2015-12-24 | 2015-05-11 01:00 | 2017-07-07 | Yes | STD |  | 2017-06-21 | 2017-08-02 | 29 | 0 | 29 | 2017-08-24 | 2017-08-24 | 2017-08-25 | Connected |  | No
National Grid | CLINTON | 176314 | 1510 | 183 | Solar | 01_216W2 | 2015-05-11 01:00 | 2015-05-11 | 4 | 4 | 0 | 2015-05-15 | 2015-05-15 | 0 | 0 | 0 | [20 empty] | 2015-06-19 |  | 2016-12-31 | Yes | EXP |  | 2016-06-21 | 2016-07-27 | 25 | 0 | 25 | 2015-12-11 | 2015-12-11 | 2016-08-04 | Connected |  | No
National Grid | CLARKSBURG | 176318 | 1247 | 497 | Solar | 09_1015W2 | 2015-05-11 01:00 | 2015-05-12 | 0 | 0 | 0 | 2015-05-12 | 2015-06-09 | 19 | 0 | 19 | [22 empty] | 2015-10-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SHIRLEY | 176319 | 1464 | 904.8 | Solar | 01_201W1 | 2015-05-11 01:00 | 2015-05-13 | 2 | 2 | 0 | [10 empty] | 2015-05-15 | 2015-06-15 | 20 | 0 | 20 | [5 empty] | 2016-10-28 | 2016-10-28 | 0 | 0 | 0 |  |  | 2015-10-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SHIRLEY | 176320 | 1464 | 997.6 | Solar | 01_201W1 | 2015-05-11 01:00 | 2015-05-13 | 2 | 2 | 0 | [10 empty] | 2015-05-15 | 2015-06-15 | 20 | 0 | 20 | [5 empty] | 2016-10-28 | 2016-10-28 | 0 | 0 | 0 |  | 2015-05-13 01:00 | 2015-10-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ATTLEBORO | 176321 | 2703 | 140 | Solar | 05_9L4 | 2015-05-13 01:00 | 2015-05-14 | 2 | 2 | 0 | 2015-05-18 | 2015-05-18 | 0 | 0 | 0 | [20 empty] | 2015-09-10 | 2015-05-13 01:00 | 2016-12-31 | Yes | EXP |  | 2016-03-28 | 2016-05-16 | 34 | 0 | 34 | 2016-07-11 | 2016-07-11 | 2016-07-14 | Connected |  | No
National Grid | ATTLEBORO | 176350 | 2703 | 40 | Solar | 05_8L1 | 2015-05-13 01:00 | 2015-05-14 | 2 | 2 | 0 | 2015-05-18 | 2015-05-18 | 0 | 0 | 0 | [20 empty] | 2015-08-05 | 2015-05-13 01:00 | 2016-12-31 | Yes | EXP |  | 2015-11-05 | 2016-02-03 | 59 | 0 | 59 | 2016-02-04 | 2016-02-04 | 2016-02-16 | Connected |  | No
National Grid | MILLBURY | 176351 | 1527 | 7 | Solar | 01_304W5 | 2015-05-13 01:00 | 2015-05-14 | 2 | 2 | 0 | 2015-05-18 | 2015-05-18 | 0 | 0 | 0 | [20 empty] | 2015-06-05 |  | 2016-12-31 | Yes | EXP |  | 2016-03-17 | 2016-03-25 | 5 | 0 | 5 | 2016-05-10 | 2016-05-10 | 2016-05-12 | Connected |  | No
National Grid | BELCHERTOWN | 176352 | 1007 | 499 | Solar | 09_509L2 | 2015-05-13 01:00 | 2015-05-14 | 38 | 38 | 0 | 2015-07-10 | 2016-11-29 | 345 | 0 | 345 | [22 empty] | 2015-10-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTPORT | 176354 | 2790 | 38 | Solar | 05_115W45 | 2015-05-14 01:00 | 2015-05-18 | 0 | 0 | 0 | 2015-05-18 | 2016-12-06 | 386 | 0 | 386 | [21 empty] | 2015-05-14 01:00 | 2015-10-30 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BELLINGHAM | 176355 | 2019 | 6 | Solar | 05_108W60 | 2015-05-14 01:00 | 2015-05-18 | 0 | 0 | 0 | 2015-05-18 | 2015-05-18 | 0 | 0 | 0 | [20 empty] | 2015-06-02 |  | 2016-12-31 | Yes | EXP |  | 2015-11-19 | 2015-12-15 | 17 | 0 | 17 | 2016-03-22 | 2016-03-22 | 2016-03-28 | Connected |  | No
National Grid | RUTLAND | 176356 | 1543 | 5 | Solar | 01_55W1 | 2015-05-14 01:00 | 2015-05-19 | 0 | 0 | 0 | [25 empty] | 2015-05-20 |  | 2015-10-30 |  | EXP | [6 empty] | 2015-07-30 | 2015-07-30 | 2015-10-01 | Connected |  | No
National Grid | WORCESTER | 176357 | 1602 | 10 | Solar | 01_23W3 | 2015-05-14 01:00 | 2015-05-19 | 0 | 0 | 0 | 2015-05-19 | 2015-05-19 | 0 | 0 | 0 | [20 empty] | 2015-05-20 | 2015-05-15 01:00 | 2015-10-30 |  | EXP | [6 empty] | 2015-07-23 | 2015-07-23 | 2015-11-24 | Connected |  | No
National Grid | WEST NEWBURY | 175806 | 1985 | 27.6 | Solar | 14_47L1 | 2015-05-15 01:00 | 2015-05-21 | 0 | 0 | 0 | 2015-05-21 | 2015-05-21 | 0 | 0 | 0 | [20 empty] | 2015-06-04 |  | 2016-12-31 | Yes | EXP |  | 2016-05-10 | 2016-05-13 | 3 | 0 | 3 | 2015-07-20 | 2015-07-20 | 2016-07-15 | Connected |  | No
National Grid | SUTTON | 175807 | 1590 | 27.95 | Solar | 01_304W6 | 2015-05-15 01:00 | 2015-05-21 | 0 | 0 | 0 | 2015-05-21 | 2015-05-21 | 0 | 0 | 0 | [20 empty] | 2015-05-22 | 2015-05-15 10:11 | 2015-10-30 |  | EXP | [6 empty] | 2015-06-09 | 2015-06-09 | 2016-01-22 | Connected |  | No
National Grid | CHARLTON | 176353 | 1507 | 2500 | Solar | 01_413L4 | 2015-05-15 10:11 | 2015-05-15 | 0 | 0 | 0 | [10 empty] | 2015-05-15 | 2015-06-12 | 19 | 0 | 19 | [5 empty] | 2015-11-25 | 2015-12-23 | 19 | 0 | 19 | 2015-12-23 |  | 2015-10-30 |  | STD | [6 empty] | 2017-10-03 | 2017-10-03 | 2017-10-03 | Connected |  | No
National Grid | OXFORD | 175808 | 1540 | 100 | Solar | 01_406L1 | 2015-05-18 01:00 | 2015-05-21 | 5 | 5 | 0 | 2015-05-29 | 2015-05-29 | 0 | 0 | 0 | [20 empty] | 2015-07-10 | 2015-05-18 01:00 | 2016-12-31 |  | EXP | [6 empty] | 2016-10-19 | 2016-10-19 | 2016-09-16 | Connected |  | No
National Grid | WESTBOROUGH | 175809 | 1581 | 741 | Solar | 05_312W2 | 2015-05-18 01:00 | 2015-05-21 | 0 | 0 | 0 | 2015-05-21 | 2015-05-21 | 0 | 0 | 0 | 2015-07-11 | 2015-10-06 | 60 | 28 | 32 | [5 empty] | 2015-07-11 | 2015-10-06 | 60 | 28 | 32 | [5 empty] | 2015-10-30 |  | 2016-12-31 | Yes | EXP |  | 2016-03-29 | 2016-06-02 | 45 | 0 | 45 | 2016-11-30 | 2016-11-30 | 2016-06-28 | Connected |  | No
National Grid | SOMERSET | 175810 | 2725 | 5 | Solar | 05_11W84 | 2015-05-18 01:00 | 2015-05-21 | 0 | 0 | 0 | 2015-05-21 | 2015-06-25 | 23 | 0 | 23 | [20 empty] | 2015-06-09 |  | 2015-10-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SHIRLEY | 175811 | 1464 | 15.2 | Solar | 01_227W3 | 2015-05-18 01:00 | 2015-05-21 | 3 | 3 | 0 | 2015-05-27 | 2015-06-12 | 12 | 0 | 12 | [20 empty] | 2015-06-12 |  | 2018-01-05 |  | EXP | [6 empty] | 2015-06-22 | 2015-06-22 |  | Withdrawn |  | Yes
National Grid | DRACUT | 175812 | 1826 | 17.63 | Solar | 14_75L3 | 2015-05-18 01:00 | 2015-05-21 | 3 | 3 | 0 | 2015-05-27 | 2015-05-27 | 0 | 0 | 0 | [20 empty] | 2015-06-01 |  | 2015-10-30 |  | EXP | [6 empty] | 2015-07-13 | 2015-07-13 | 2015-11-20 | Connected |  | No
National Grid | SEEKONK | 175813 | 2771 | 40 | Solar | 05_7L5 | 2015-05-18 01:00 | 2015-05-21 | 3 | 3 | 0 | 2015-05-27 | 2015-05-27 | 0 | 0 | 0 | [20 empty] | 2015-06-08 |  | 2015-10-30 |  | EXP | [6 empty] | 2015-06-24 | 2015-06-24 | 2015-11-23 | Connected |  | No
National Grid | NORTHAMPTON | 175814 | 1060 | 7.6 | Solar | 09_901W3 | 2015-05-18 01:00 | 2015-05-21 | 4 | 4 | 0 | 2015-05-28 | 2015-05-28 | 0 | 0 | 0 | [20 empty] | 2015-06-18 |  | 2015-10-30 |  | EXP | [6 empty] | 2015-09-10 | 2015-09-10 | 2015-09-10 | Connected |  | No
National Grid | LOWELL | 176358 | 1851 | 30 | Solar | 14_2L4 | 2015-05-18 01:00 | 2015-05-19 | 0 | 0 | 0 | 2015-05-19 | 2015-08-05 | 53 | 0 | 53 | [21 empty] | 2015-05-19 01:00 | 2015-10-30 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTON | 175843 | 2766 | 998 | Solar | 05_4L1 | 2015-05-19 01:00 | 2015-05-21 | 1 | 1 | 0 | [10 empty] | 2015-05-22 | 2015-06-23 | 20 | 0 | 20 | [5 empty] | 2015-05-20 |  | 711 | 116 | 595 | 2016-04-28 |  | 2015-10-30 | Yes | STD | [6 empty] | 2016-04-29 | 2016-04-29 |  | Withdrawn |  | No
National Grid | MILFORD | 175844 | 1757 | 17.6 | Solar | 05_336W3 | 2015-05-19 01:00 | 2015-05-22 | 0 | 0 | 0 | 2015-05-22 | 2015-05-22 | 0 | 0 | 0 | [20 empty] | 2015-05-28 |  | 2015-10-30 |  | EXP | [6 empty] | 2015-07-20 | 2015-07-20 | 2016-03-28 | Connected |  | No
National Grid | BEVERLY | 175845 | 1915 | 401 | Solar | 12_51L1 | 2015-05-19 01:00 | 2015-05-22 | 0 | 0 | 0 | 2015-05-22 | 2016-11-10 | 366 | 0 | 366 | [22 empty] | 2015-10-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WARE | 175847 | 1082 | 70 | Solar | 09_501L1 | 2015-05-19 01:00 | 2015-05-25 | 0 | 0 | 0 | 2015-05-25 | 2015-05-25 | 0 | 0 | 0 | [20 empty] | 2015-07-01 |  | 2015-10-30 |  | EXP | [6 empty] | 2015-07-01 | 2015-07-01 | 2015-12-15 | Connected |  | No
National Grid | WARE | 175848 | 1082 | 224 | Solar | 09_501L1 | 2015-05-19 01:00 | 2015-05-25 | 0 | 0 | 0 | 2015-05-25 | 2015-05-25 | 0 | 0 | 0 | [20 empty] | 2015-07-01 |  | 2015-10-30 |  | EXP | [6 empty] | 2015-07-01 | 2015-07-01 | 2015-12-15 | Connected |  | No
National Grid | MILLBURY | 175849 | 1527 | 1000 | Solar | 01_26W2 | 2015-05-20 01:00 | 2015-05-25 | 11 | 11 | 0 | [10 empty] | 2015-06-10 | 2015-07-08 | 18 | 0 | 18 | [5 empty] | 2017-02-10 | 2016-06-30 | 0 | 0 | 0 | 2016-08-03 |  | 2017-09-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MARLBOROUGH | 175850 | 1752 | 300 | Solar | 05_310W4 | 2015-05-20 01:00 | 2015-05-25 | 2 | 2 | 0 | 2015-05-28 | 2015-05-28 | 0 | 0 | 0 | 2015-07-30 | 2015-09-03 | 25 | 6 | 19 | [5 empty] | 2015-07-30 | 2015-09-03 | 25 | 6 | 19 | [5 empty] | 2015-09-22 |  | 2016-12-31 |  | EXP | [6 empty] | 2016-05-18 | 2016-05-18 | 2017-01-09 | Connected |  | No
National Grid | SWANSEA | 175851 | 2777 | 17.6 | Solar | 05_11W84 | 2015-05-20 01:00 | 2015-05-25 | 4 | 4 | 0 | [27 empty] | 2015-10-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | HANOVER | 175884 | 2339 | 15.2 | Solar | 07_910W51 | 2015-05-20 01:00 | 2015-05-26 | 1 | 1 | 0 | 2015-05-27 | 2015-07-08 | 28 | 0 | 28 | [20 empty] | 2015-06-18 | 2015-05-20 01:00 | 2015-10-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MILLBURY | 177735 | 1527 | 1000 | Solar | 01_26W2 | 2015-05-20 01:00 | 2015-05-25 | 11 | 0 | 11 | [10 empty] | 2015-06-10 | 2015-07-08 | 18 | 0 | 18 | [5 empty] | 2016-05-12 | 2016-06-30 | 33 | 0 | 33 | 2016-08-03 |  | 2018-09-21 | Yes | STD | [8 empty] | 2018-09-10 | Connected |  | No
National Grid | BEVERLY | 175852 | 1915 | 1104 | Solar | 12_12L4 | 2015-05-21 01:00 | 2015-05-25 | 16 | 16 | 0 | [10 empty] | 2015-06-18 | 2015-07-16 | 19 | 0 | 19 | [10 empty] | 2016-01-15 | 2015-05-21 01:00 | 2015-10-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LEOMINSTER | 175882 | 1453 | 984 | Solar | 01_207W6 | 2015-05-21 01:00 | 2015-05-25 | 1 | 1 | 0 | [10 empty] | 2015-05-27 | 2015-06-25 | 20 | 0 | 20 | [10 empty] | 2016-07-01 |  | 2017-10-31 | Yes | STD |  | 2017-09-14 | 2018-01-05 | 71 | 0 | 71 | 2017-12-28 | 2017-12-28 | 2018-01-04 | Connected |  | No
National Grid | ANDOVER | 175885 | 1810 | 6.75 | Solar | 14_54L3 | 2015-05-21 01:00 | 2015-05-26 | 0 | 0 | 0 | 2015-05-26 | 2015-05-26 | 0 | 0 | 0 | [20 empty] | 2015-06-01 | 2015-05-22 01:00 | 2015-10-30 |  | EXP | [6 empty] | 2015-08-26 | 2015-08-26 | 2015-09-01 | Connected |  | No
National Grid | SEEKONK | 175883 | 2771 | 150 | Solar | 05_9L5 | 2015-05-22 01:00 | 2015-05-25 | 5 | 5 | 0 | [10 empty] | 2015-06-02 | 2015-06-30 | 19 | 0 | 19 | [10 empty] | 2015-12-01 |  | 2016-10-30 | Yes | STD |  | 2016-08-11 | 2016-10-19 | 47 | 0 | 47 | 2016-10-31 | 2016-10-31 | 2016-11-08 | Connected |  | No
National Grid | NORTH BILLERICA | 175886 | 1862 | 3.8 | Solar | 14_70L5 | 2015-05-26 01:00 | 2015-05-28 | 0 | 0 | 0 | 2015-05-28 | 2015-05-28 | 0 | 0 | 0 | [20 empty] | 2015-06-30 |  | 2015-10-30 |  | EXP | [6 empty] | 2015-11-16 | 2015-11-16 | 2015-11-19 | Connected |  | No
National Grid | RUTLAND | 175887 | 1543 | 7.6 | Solar | 01_55W1 | 2015-05-26 01:00 | 2015-05-28 | 0 | 0 | 0 | 2015-05-28 | 2015-05-28 | 0 | 0 | 0 | [20 empty] | 2015-06-30 |  | 2015-10-30 |  | EXP | [6 empty] | 2015-09-22 | 2015-09-22 | 2015-10-02 | Connected |  | No
National Grid | MALDEN | 175889 | 2148 | 56 | Solar | 12_16J4 | 2015-05-27 01:00 | 2015-05-28 | 1 | 1 | 0 | 2015-05-29 | 2015-05-29 | 0 | 0 | 0 | [20 empty] | 2015-06-23 |  | 2015-10-30 |  | EXP | [6 empty] | 2015-06-30 | 2015-06-30 | 2016-01-25 | Connected |  | No
National Grid | ABINGTON | 175890 | 2351 | 56 | Solar | 07_99W32 | 2015-05-27 01:00 | 2015-05-28 | 1 | 1 | 0 | 2015-05-29 | 2015-05-29 | 0 | 0 | 0 | [20 empty] | 2015-06-08 |  | 2015-10-30 |  | EXP | [6 empty] | 2015-06-09 | 2015-06-09 | 2015-12-15 | Connected |  | No
National Grid | NORTH ADAMS | 175918 | 1247 | 197 | Natural Gas | 09_1015W1 | 2015-05-28 01:00 | 2015-05-29 | 201 | 201 | 0 | 2016-03-22 | 2016-06-01 | 80 | 30 | 50 | [20 empty] | 2016-06-01 |  | 2019-09-30 |  | EXP | [6 empty] | 2018-02-15 | 2018-02-15 | 2019-11-21 | Connected |  | No
National Grid | BEVERLY | 175920 | 1915 | 9.8 | Solar | 12_51L1 | 2015-05-28 01:00 | 2015-05-29 | 6 | 6 | 0 | [26 empty] | 2015-05-29 01:00 | 2015-10-30 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BELCHERTOWN | 175922 | 1007 | 2000 | Solar | 09_523L2 | 2015-05-29 01:00 | 2015-06-01 | 0 | 0 | 0 | [10 empty] | 2015-06-01 | 2015-06-29 | 19 | 0 | 19 | [5 empty] | 2016-02-23 | 2016-04-04 | 28 | 0 | 28 | 2016-04-04 | 2015-05-29 01:00 | 2018-03-31 | Yes | STD |  | 2017-09-26 | 2018-02-05 | 83 | 0 | 83 | 2018-02-13 | 2018-02-13 | 2018-03-30 | Connected |  | No
National Grid | BELCHERTOWN | 175923 | 1007 | 2000 | Solar | 09_523L2 | 2015-05-29 01:00 | 2015-06-01 | 0 | 0 | 0 | [10 empty] | 2015-06-01 | 2015-06-29 | 19 | 0 | 19 | [5 empty] | 2016-02-23 | 2016-04-04 | 28 | 0 | 28 | 2016-04-04 | 2015-05-29 01:00 | 2018-03-31 | Yes | STD |  | 2017-09-26 | 2018-02-05 | 83 | 0 | 83 | 2018-03-30 | 2018-03-30 | 2018-03-30 | Connected |  | No
National Grid | SHIRLEY | 175924 | 1464 | 997.6 | Solar | 01_227W3 | 2015-05-29 01:00 | 2015-06-01 | 1 | 1 | 0 | [10 empty] | 2015-06-02 | 2015-07-01 | 20 | 0 | 20 | [10 empty] | 2016-01-27 | 2015-05-29 01:00 | 2015-11-30 |  | STD | [6 empty] | 2017-08-01 | 2017-08-01 | 2017-08-01 | Connected |  | No
National Grid | AYER | 175925 | 1432 | 750 | Solar | 01_201W1 | 2015-05-29 01:00 | 2015-06-01 | 1 | 1 | 0 | [10 empty] | 2015-06-02 | 2015-07-01 | 20 | 0 | 20 | [5 empty] | 2016-09-30 | 2016-06-15 | 0 | 0 | 0 | 2018-12-05 |  | 2022-12-31 | Yes | STD |  | 2022-04-16 | 2022-06-18 | 64 | 0 | 64 |  |  | 2022-12-29 | Connected |  | No
National Grid | SWANSEA | 175926 | 2777 | 16 | Solar | 05_19W73 | 2015-06-01 01:00 | 2015-06-02 | 11 | 11 | 0 | 2015-06-17 | 2015-10-19 | 84 | 0 | 84 | [20 empty] | 2015-07-06 |  | 2016-06-30 |  | EXP | [6 empty] | 2015-07-06 | 2015-07-06 |  | Withdrawn |  | No
National Grid | REHOBOTH | 175955 | 2769 | 59.4 | Solar | 05_7L5 | 2015-06-02 01:00 | 2015-06-02 | 0 | 0 | 0 | 2015-06-02 | 2015-06-02 | 0 | 0 | 0 | [20 empty] | 2015-06-08 |  | 2016-06-30 |  | EXP | [6 empty] | 2015-06-15 | 2015-06-15 | 2016-03-18 | Connected |  | Yes
National Grid | SEEKONK | 175956 | 2771 | 239.8 | Solar | 05_7L5 | 2015-06-02 01:00 | 2015-06-02 | 0 | 0 | 0 | 2015-06-02 | 2015-06-02 | 0 | 0 | 0 | 2015-07-18 | 2015-08-14 | 19 | 0 | 19 | [5 empty] | 2015-07-18 | 2015-08-14 | 19 | 0 | 19 | [5 empty] | 2015-09-11 | 2015-06-02 01:00 | 2016-06-30 |  | EXP | [6 empty] | 2016-07-27 | 2016-07-27 | 2016-08-04 | Connected |  | No
National Grid | ATTLEBORO | 175957 | 2703 | 997 | Solar | 05_9L2 | 2015-06-02 01:00 | 2015-06-03 | 4 | 4 | 0 | [10 empty] | 2015-06-09 | 2015-07-08 | 19 | 0 | 19 | [10 empty] | 2015-12-04 |  | 2016-06-30 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | AYER | 175958 | 1432 | 989 | Solar |  | 2015-06-03 01:00 | 2015-06-04 | 1 | 1 | 0 | [26 empty] | 2015-06-03 01:00 | 2015-06-09 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | AYER | 175959 | 1432 | 989 | Solar | 01_201W4 | 2015-06-03 01:00 | 2015-06-04 | 8 | 8 | 0 | [10 empty] | 2015-06-16 | 2015-07-01 | 10 | 0 | 10 | [5 empty] | 2016-03-15 | 2016-06-15 | 63 | 18 | 45 | 2017-05-22 | 2015-06-04 01:00 | 2016-06-30 |  | STD | [6 empty] | 2017-10-26 | 2017-10-26 | 2017-10-26 | Connected |  | No
National Grid | LAWRENCE | 175960 | 1843 | 227 | Solar | 14_61L2 | 2015-06-04 01:00 | 2015-06-04 | 2 | 2 | 0 | 2015-06-08 | 2017-02-13 | 418 | 0 | 418 | [20 empty] | 2015-08-04 | 2015-06-04 01:00 | 2016-06-30 | Yes | EXP | [9 empty] | Withdrawn |  | No
National Grid | LENOX | 175961 | 1240 | 606 | Solar | 09_1103W2 | 2015-06-04 01:00 | 2015-06-05 | 0 | 0 | 0 | [10 empty] | 2015-06-05 | 2015-07-07 | 20 | 0 | 20 | [10 empty] | 2016-08-02 |  | 2017-12-07 | Yes | STD |  | 2017-06-07 | 2017-11-30 | 116 | 0 | 116 | 2017-11-20 | 2017-11-20 | 2017-12-07 | Connected |  | No
National Grid | SOUTHBOROUGH | 175964 | 1772 | 9.25 | Solar | 05_310W5 | 2015-06-05 01:00 | 2015-06-08 | 1 | 1 | 0 | 2015-06-09 | 2015-06-09 | 0 | 0 | 0 | [20 empty] | 2015-06-30 | 2015-06-05 01:00 | 2016-06-30 |  | EXP | [6 empty] | 2015-07-02 | 2015-07-02 | 2015-08-12 | Connected |  | No
National Grid | BELLINGHAM | 175992 | 2019 | 198 | Solar | 05_335W1 | 2015-06-05 01:00 | 2015-06-08 | 2 | 2 | 0 | 2015-06-10 | 2015-06-10 | 0 | 0 | 0 | [20 empty] | 2015-08-05 |  | 2016-06-13 | Yes | EXP |  | 2015-10-27 | 2015-12-14 | 32 | 0 | 32 | 2015-12-23 | 2015-12-23 | 2016-01-13 | Connected |  | No
National Grid | BELCHERTOWN | 175993 | 1007 | 4.95 | Solar | 09_527L1 | 2015-06-10 01:00 | 2015-06-11 | 6 | 6 | 0 | 2015-06-22 | 2015-06-22 | 0 | 0 | 0 | [20 empty] | 2015-07-16 |  | 2016-06-16 |  | EXP | [6 empty] | 2016-04-13 | 2016-04-13 | 2016-04-19 | Connected |  | No
National Grid | BILLERICA | 175994 | 1821 | 16.35 | Solar | 14_70L6 | 2015-06-10 01:00 | 2015-06-11 | 6 | 6 | 0 | 2015-06-22 | 2015-06-22 | 0 | 0 | 0 | [20 empty] | 2015-07-01 |  | 2016-06-16 |  | EXP | [6 empty] | 2016-10-06 | 2016-10-06 | 2016-10-06 | Connected |  | No
National Grid | PALMER | 175995 | 1069 | 16.98 | Solar | 09_514L1 | 2015-06-10 01:00 | 2015-06-11 | 6 | 6 | 0 | 2015-06-22 | 2015-06-22 | 0 | 0 | 0 | [20 empty] | 2015-07-01 |  | 2016-06-16 |  | EXP | [6 empty] | 2015-08-04 | 2015-08-04 | 2016-01-12 | Connected |  | No
National Grid | CHARLTON | 175996 | 1507 | 18.75 | Solar | 01_413L3 | 2015-06-11 01:00 | 2015-06-12 | 6 | 6 | 0 | 2015-06-23 | 2015-06-23 | 0 | 0 | 0 | [20 empty] | 2015-07-01 |  | 2016-06-17 |  | EXP | [6 empty] | 2015-11-06 | 2015-11-06 | 2015-11-06 | Connected |  | No
National Grid | GRANBY | 175997 | 1033 | 10 | Solar | 09_527L1 | 2015-06-11 01:00 | 2015-06-12 | 2 | 2 | 0 | 2015-06-16 | 2015-06-16 | 0 | 0 | 0 | [20 empty] | 2015-07-06 |  | 2016-06-17 |  | EXP | [6 empty] | 2015-07-06 | 2015-07-06 | 2016-01-12 | Connected |  | No
National Grid | SWANSEA | 176000 | 2777 | 10 | Solar | 05_11W83 | 2015-06-11 01:00 | 2015-06-16 | 0 | 0 | 0 | 2015-06-16 | 2015-06-16 | 0 | 0 | 0 | [20 empty] | 2015-07-17 |  | 2016-06-21 |  | EXP | [6 empty] | 2016-03-24 | 2016-03-24 | 2016-03-28 | Connected |  | No
National Grid | ANDOVER | 176001 | 1810 | 20 | Solar | 14_50L1 | 2015-06-15 01:00 | 2015-06-16 | 16 | 16 | 0 | 2015-07-10 | 2015-07-10 | 0 | 0 | 0 | [20 empty] | 2015-07-13 |  | 2016-06-21 |  | EXP | [6 empty] | 2015-09-23 | 2015-09-23 | 2015-09-29 | Connected |  | No
National Grid | GLOUCESTER | 176028 | 1930 | 30.25 | Solar | 12_51T3 | 2015-06-16 01:00 | 2015-06-16 | 4 | 4 | 0 | 2015-06-23 | 2015-06-23 | 0 | 0 | 0 | [20 empty] | 2015-07-01 |  | 2016-06-21 |  | EXP | [6 empty] | 2016-12-20 | 2016-12-20 | 2016-12-20 | Connected |  | No
National Grid | MARLBOROUGH | 176029 | 1752 | 23.75 | Solar | 05_317W8 | 2015-06-16 01:00 | 2015-06-17 | 22 | 22 | 0 | 2015-07-21 | 2015-07-21 | 0 | 0 | 0 | [20 empty] | 2015-07-28 |  | 2016-06-22 |  | EXP | [6 empty] | 2015-12-10 | 2015-12-10 | 2015-12-10 | Connected |  | No
National Grid | FALL RIVER | 176031 | 2724 | 450 | Solar | 05_115W42 | 2015-06-18 01:00 | 2015-06-19 | 34 | 34 | 0 | 2015-08-07 | 2016-11-02 | 308 | 0 | 308 | [20 empty] | 2015-09-28 |  | 2017-01-30 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GREAT BARRINGTON | 176065 | 1230 | 499 | Solar | 09_1109W3 | 2015-06-18 01:00 | 2015-06-22 | 1 | 1 | 0 | [10 empty] | 2015-06-23 | 2015-07-21 | 19 | 0 | 19 | [10 empty] | 2016-07-08 |  | 2016-06-27 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | GREAT BARRINGTON | 176066 | 1230 | 499 | Solar | 09_1109W3 | 2015-06-18 01:00 | 2015-06-22 | 1 | 1 | 0 | [10 empty] | 2015-06-23 | 2015-07-21 | 19 | 0 | 19 | [10 empty] | 2016-07-08 | 2015-06-19 01:00 | 2016-06-27 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | THORNDIKE | 176032 | 1079 | 499 | Solar | 09_523L4 | 2015-06-19 01:00 | 2015-06-19 | 9 | 9 | 0 | [10 empty] | 2015-07-02 | 2015-07-30 | 19 | 0 | 19 | [12 empty] | 2016-06-24 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | LEOMINSTER | 176033 | 1453 | 6.45 | Solar | 01_219W5 | 2015-06-19 01:00 | 2015-06-19 | 2 | 2 | 0 | 2015-06-23 | 2015-06-23 | 0 | 0 | 0 | [20 empty] | 2015-07-16 |  | 2016-06-24 |  | EXP | [6 empty] | 2016-04-07 | 2016-04-07 | 2016-04-13 | Connected |  | No
National Grid | WHITINSVILLE | 176067 | 1588 | 10 | Solar | 05_320W5 | 2015-06-19 01:00 | 2015-06-22 | 6 | 6 | 0 | 2015-06-30 | 2015-06-30 | 0 | 0 | 0 | [20 empty] | 2015-07-07 | 2015-06-19 01:00 | 2016-06-27 |  | EXP | [6 empty] | 2016-05-04 | 2016-05-04 | 2016-05-10 | Connected |  | No
National Grid | LEOMINSTER | 176068 | 1453 | 7.6 | Solar | 01_225W4 | 2015-06-19 01:00 | 2015-06-22 | 6 | 6 | 0 | 2015-06-30 | 2015-06-30 | 0 | 0 | 0 | [20 empty] | 2015-07-17 |  | 2016-06-27 | Yes | EXP |  | 2016-03-14 | 2016-03-23 | 6 | 0 | 6 | 2015-11-13 | 2015-11-13 | 2016-04-27 | Connected |  | No
National Grid | MILLBURY | 176069 | 1527 | 6 | Solar | 01_304W3 | 2015-06-19 01:00 | 2015-06-22 | 6 | 6 | 0 | 2015-06-30 | 2015-06-30 | 0 | 0 | 0 | [20 empty] | 2015-07-02 |  | 2016-06-27 |  | EXP | [6 empty] | 2015-08-04 | 2015-08-04 | 2016-07-29 | Connected |  | No
National Grid | MILFORD | 176070 | 1757 | 3.8 | Solar | 05_336W3 | 2015-06-19 01:00 | 2015-06-22 | 6 | 6 | 0 | 2015-06-30 | 2015-06-30 | 0 | 0 | 0 | [20 empty] | 2015-07-02 |  | 2016-06-27 |  | EXP | [6 empty] | 2015-08-04 | 2015-08-04 | 2016-03-22 | Connected |  | No
National Grid | NORTH BROOKFIELD | 176071 | 1535 | 10 | Solar | 09_604W2 | 2015-06-19 01:00 | 2015-06-23 | 12 | 12 | 0 | 2015-07-10 | 2015-07-10 | 0 | 0 | 0 | [20 empty] | 2015-07-28 |  | 2016-06-28 |  | EXP | [6 empty] | 2015-07-28 | 2015-07-28 | 2016-06-30 | Connected |  | No
National Grid | BELCHERTOWN | 176072 | 1007 | 11.4 | Solar | 09_523L2 | 2015-06-19 01:00 | 2015-06-23 | 5 | 5 | 0 | 2015-06-30 | 2015-12-21 | 119 | 0 | 119 | [22 empty] | 2016-06-28 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MILLBURY | 176101 | 1527 | 7.6 | Solar | 01_304W3 | 2015-06-19 01:00 | 2015-06-23 | 5 | 5 | 0 | 2015-06-30 | 2015-06-30 | 0 | 0 | 0 | [20 empty] | 2015-07-01 |  | 2016-06-28 |  | EXP | [6 empty] | 2015-08-04 | 2015-08-04 | 2016-04-19 | Connected |  | No
National Grid | MILLBURY | 176102 | 1527 | 6.45 | Solar | 01_304W1 | 2015-06-19 01:00 | 2015-06-23 | 5 | 5 | 0 | 2015-06-30 | 2015-06-30 | 0 | 0 | 0 | [20 empty] | 2015-07-01 |  | 2016-06-28 |  | EXP | [6 empty] | 2015-08-04 | 2015-08-04 | 2015-11-13 | Connected |  | No
National Grid | PEPPERELL | 176103 | 1463 | 6 | Solar | 01_226L1 | 2015-06-19 01:00 | 2015-06-23 | 5 | 5 | 0 | 2015-06-30 | 2015-06-30 | 0 | 0 | 0 | [20 empty] | 2015-07-01 |  | 2016-06-28 |  | EXP | [6 empty] | 2015-08-05 | 2015-08-05 | 2015-12-01 | Connected |  | No
National Grid | GARDNER | 176104 | 1440 | 10 | Solar | 01_607W5 | 2015-06-19 01:00 | 2015-06-23 | 5 | 5 | 0 | 2015-06-30 | 2015-06-30 | 0 | 0 | 0 | [20 empty] | 2015-07-30 |  | 2016-06-28 |  | EXP | [6 empty] | 2015-07-30 | 2015-07-30 | 2016-03-01 | Connected |  | No
National Grid | NORTHBOROUGH | 176105 | 1532 | 20 | Solar | 05_313W3 | 2015-06-24 01:00 | 2015-06-25 | 3 | 3 | 0 | 2015-06-30 | 2015-06-30 | 0 | 0 | 0 | [20 empty] | 2015-07-01 |  | 2016-06-30 |  | EXP | [6 empty] | 2015-11-03 | 2015-11-03 | 2015-11-04 | Connected |  | No
National Grid | LENOX | 176106 | 1240 | 30 | Solar | 09_1103W1 | 2015-06-25 01:00 | 2015-06-25 | 8 | 8 | 0 | 2015-07-08 | 2015-07-08 | 0 | 0 | 0 | [20 empty] | 2015-07-22 |  | 2016-06-30 |  | EXP | [6 empty] | 2015-07-22 | 2015-07-22 | 2016-03-08 | Connected |  | No
National Grid | MARLBOROUGH | 176107 | 1752 | 250 | Natural Gas | 05_310W5 | 2015-06-25 01:00 | 2015-06-25 | 3 | 3 | 0 | 2015-06-30 | 2015-06-30 | 0 | 0 | 0 | [20 empty] | 2015-08-06 | 2015-06-26 01:00 | 2016-06-30 |  | EXP | [6 empty] | 2015-12-18 | 2015-12-18 | 2015-12-18 | Connected |  | No
National Grid | BROCKTON | 176108 | 2302 | 476 | Solar | 07_91W47 | 2015-06-26 01:00 | 2015-06-26 | 2 | 2 | 0 | 2015-06-30 | 2017-04-24 | 451 | 0 | 451 | [20 empty] | 2015-08-06 |  | 2016-07-01 | Yes | EXP | [6 empty] | 2015-08-06 | 2015-08-06 |  | Withdrawn |  | No
National Grid | NEWBURY | 176109 | 1951 | 47.1 | Solar | 14_60L2 | 2015-06-26 01:00 | 2015-06-26 | 2 | 2 | 0 | 2015-06-30 | 2015-06-30 | 0 | 0 | 0 | [20 empty] | 2015-07-22 | 2015-06-26 01:00 | 2016-07-01 |  | EXP | [6 empty] | 2015-07-22 | 2015-07-22 | 2015-11-03 | Connected |  | No
National Grid | WILLIAMSTOWN | 176138 | 1267 | 1500 | Solar | 09_1003W1 | 2015-06-26 01:00 | 2015-06-30 | 1 | 0 | 1 | [10 empty] | 2015-07-01 | 2015-07-29 | 19 | 0 | 19 | [10 empty] | 2016-04-06 |  | 2017-10-18 | Yes | STD | [6 empty] | 2017-10-20 | 2017-10-20 | 2017-11-17 | Connected |  | No
National Grid | OXFORD | 176139 | 1540 | 8.39 | Solar | 01_406L3 | 2015-06-26 01:00 | 2015-07-01 | 0 | 0 | 0 | 2015-07-01 | 2015-07-01 | 0 | 0 | 0 | [20 empty] | 2015-07-17 |  | 2016-07-06 |  | EXP | [6 empty] | 2015-08-03 | 2015-08-03 | 2016-01-28 | Connected |  | No
National Grid | MILLBURY | 176140 | 1527 | 6.88 | Solar | 01_304W3 | 2015-06-26 01:00 | 2015-07-01 | 0 | 0 | 0 | 2015-07-01 | 2015-07-01 | 0 | 0 | 0 | [20 empty] | 2015-07-17 | 2015-06-26 01:00 | 2016-07-06 |  | EXP | [6 empty] | 2016-04-27 | 2016-04-27 | 2016-06-22 | Connected |  | No
National Grid | NORTH GRAFTON | 176141 | 1536 | 11.4 | Solar | 01_328W2 | 2015-06-26 01:00 | 2015-07-01 | 0 | 0 | 0 | 2015-07-01 | 2015-07-01 | 0 | 0 | 0 | [20 empty] | 2015-07-17 |  | 2016-07-06 | Yes | EXP |  | 2016-06-07 | 2016-06-23 | 11 | 0 | 11 | 2016-05-11 | 2016-05-11 | 2016-07-01 | Connected |  | No
National Grid | SALEM | 176142 | 1970 | 7.75 | Solar | 12_29W4 | 2015-06-29 01:00 | 2015-07-01 | 6 | 6 | 0 | 2015-07-10 | 2017-02-15 | 398 | 0 | 398 | [20 empty] | 2015-07-27 | 2015-06-29 01:00 | 2016-07-06 |  | EXP | [6 empty] | 2015-07-27 | 2015-07-27 |  | Withdrawn |  | Yes
National Grid | EAST BROOKFIELD | 176143 | 1515 | 76 | Solar | 01_552L3 | 2015-06-29 01:00 | 2015-07-01 | 1 | 1 | 0 | 2015-07-02 | 2015-07-02 | 0 | 0 | 0 | [20 empty] | 2015-07-22 | 2015-06-29 01:00 | 2016-07-06 | Yes | EXP |  | 2015-11-12 | 2015-11-30 | 11 | 0 | 11 | 2015-07-22 | 2015-07-22 | 2016-01-15 | Connected |  | No
National Grid | LEICESTER | 176144 | 1524 | 17.6 | Solar | 01_21W2 | 2015-06-29 01:00 | 2015-07-01 | 6 | 6 | 0 | 2015-07-10 | 2015-07-10 | 0 | 0 | 0 | [20 empty] | 2015-07-28 |  | 2016-07-06 | Yes | EXP |  | 2017-02-08 | 2017-02-22 | 9 | 0 | 9 | 2015-07-28 | 2015-07-28 | 2017-03-20 | Connected |  | No
National Grid | EAST BROOKFIELD | 176145 | 1515 | 100 | Solar | 01_552L3 | 2015-06-30 01:00 | 2015-07-01 | 2 | 2 | 0 | 2015-07-03 | 2015-07-03 | 0 | 0 | 0 | [20 empty] | 2015-07-09 |  | 2016-07-06 |  | EXP | [6 empty] | 2015-08-05 | 2015-08-05 | 2016-02-18 | Connected |  | No
National Grid | AYER | 176175 | 1432 | 35 | Solar | 01_201W3 | 2015-07-02 01:00 | 2015-07-02 | 4 | 4 | 0 | 2015-07-09 | 2015-07-09 | 0 | 0 | 0 | [20 empty] | 2015-07-13 | 2015-07-02 01:00 | 2016-07-07 |  | EXP | [6 empty] | 2015-08-05 | 2015-08-05 | 2015-12-21 | Connected |  | No
National Grid | SOUTHBRIDGE | 176176 | 1550 | 1000 | Solar | 01_413L1 | 2015-07-02 01:00 | 2015-07-06 | 2 | 2 | 0 | [10 empty] | 2015-07-08 | 2015-08-03 | 18 | 0 | 18 | [10 empty] | 2015-12-23 |  | 2016-07-11 | Yes | STD |  | 2017-08-04 | 2017-09-20 | 32 | 0 | 32 | 2017-10-16 | 2017-10-16 | 2015-10-13 | Connected |  | No
National Grid | LEICESTER | 176182 | 1524 | 499 | Solar | 01_21W2 | 2015-07-02 01:00 | 2015-07-06 | 2 | 2 | 0 | [10 empty] | 2015-07-08 | 2015-08-05 | 20 | 0 | 20 | [12 empty] | 2016-07-11 |  | STD |  | 2018-01-03 | 2018-04-02 | 50 | 0 | 50 |  |  |  | Withdrawn |  | No
National Grid | LEICESTER | 176183 | 1524 | 517 | Solar | 01_21W2 | 2015-07-02 01:00 | 2015-07-06 | 2 | 2 | 0 | [10 empty] | 2015-07-08 | 2015-08-05 | 20 | 0 | 20 | [12 empty] | 2016-07-11 |  | STD |  | 2018-01-03 | 2018-04-02 | 50 | 0 | 50 |  |  |  | Withdrawn |  | No
National Grid | LEICESTER | 176211 | 1524 | 499 | Solar | 01_21W2 | 2015-07-02 01:00 | 2015-07-06 | 2 | 2 | 0 | [10 empty] | 2015-07-08 | 2015-08-05 | 20 | 0 | 20 | [5 empty] | 2016-08-09 | 2017-01-19 | 110 | 0 | 110 |  |  | 2016-07-11 |  | STD |  | 2018-01-03 | 2018-04-02 | 50 | 0 | 50 |  |  |  | Withdrawn |  | No
National Grid | LEICESTER | 176213 | 1524 | 499 | Solar | 01_21W2 | 2015-07-02 01:00 | 2015-07-06 | 2 | 2 | 0 | [10 empty] | 2015-07-08 | 2015-08-05 | 20 | 0 | 20 | [12 empty] | 2016-07-11 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LEICESTER | 176214 | 1524 | 499 | Solar | 01_21W2 | 2015-07-02 01:00 | 2015-07-06 | 2 | 2 | 0 | [10 empty] | 2015-07-08 | 2015-08-05 | 20 | 0 | 20 | [11 empty] | 2015-07-02 01:00 | 2015-07-11 |  | STD |  | 2018-01-03 | 2018-04-02 | 50 | 0 | 50 |  |  |  | Withdrawn |  | No
National Grid | SPENCER | 176215 | 1562 | 1000 | Solar | 01_21W1 | 2015-07-02 01:00 | 2015-07-07 | 1 | 1 | 0 | [10 empty] | 2015-07-08 | 2015-08-03 | 18 | 0 | 18 | [10 empty] | 2016-02-17 | 2015-07-02 01:00 | 2017-10-07 | Yes | STD |  | 2017-10-11 | 2017-12-21 | 44 | 0 | 44 | 2018-01-02 | 2018-01-02 | 2018-01-02 | Connected |  | No
National Grid | SPENCER | 176216 | 1562 | 1000 | Solar | 01_21W1 | 2015-07-02 01:00 | 2015-07-07 | 1 | 1 | 0 | [10 empty] | 2015-07-08 | 2015-08-03 | 18 | 0 | 18 | [10 empty] | 2016-02-17 | 2015-07-06 01:00 | 2017-10-07 | Yes | STD |  | 2017-10-11 | 2017-12-21 | 44 | 0 | 44 | 2018-01-02 | 2018-01-02 | 2018-01-02 | Connected |  | No
National Grid | LEICESTER | 176181 | 1524 | 2886 | Solar | 05_01_21W2 | 2015-07-06 01:00 | 2015-07-06 | 2 | 2 | 0 | [10 empty] | 2015-07-08 | 2015-08-05 | 20 | 0 | 20 | [5 empty] | 2016-08-09 | 2016-10-06 | 41 | 0 | 41 | 2017-03-10 |  | 2018-07-11 | Yes | STD |  | 2018-01-03 | 2018-04-02 | 50 | 0 | 50 | 2018-03-30 | 2018-03-30 | 2018-04-05 | Connected |  | No
National Grid | GREAT BARRINGTON | 176217 | 1230 | 162.4 | Solar | 09_1109W1 | 2015-07-07 01:00 | 2015-07-07 | 0 | 0 | 0 | 2015-07-07 | 2017-02-02 | 392 | 0 | 392 | [20 empty] | 2015-07-22 | 2015-07-07 01:00 | 2016-07-12 |  | EXP | [6 empty] | 2015-07-22 | 2015-07-22 |  | Withdrawn |  | Yes
National Grid | SPENCER | 176250 | 1562 | 499 | Solar | 01_552L1 | 2015-07-07 01:00 | 2015-07-08 | 0 | 0 | 0 | [10 empty] | 2015-07-08 | 2015-08-05 | 20 | 0 | 20 | [10 empty] | 2016-02-14 | 2015-07-07 01:00 | 2017-10-26 |  | STD | [6 empty] | 2017-12-14 | 2017-12-14 | 2017-12-27 | Connected |  | No
National Grid | SPENCER | 176251 | 1562 | 499 | Solar | 01_552L1 | 2015-07-07 01:00 | 2015-07-08 | 0 | 0 | 0 | [10 empty] | 2015-07-08 | 2015-08-05 | 20 | 0 | 20 | [10 empty] | 2016-02-14 | 2015-07-08 01:00 | 2017-10-26 |  | STD | [6 empty] | 2017-12-14 | 2017-12-14 | 2017-12-27 | Connected |  | No
National Grid | WORCESTER | 176249 | 1610 | 140 | Solar | 01_HT15 | 2015-07-08 01:00 | 2015-07-08 | 2 | 2 | 0 | 2015-07-10 | 2015-07-10 | 0 | 0 | 0 | [20 empty] | 2015-08-05 | 2015-07-09 01:00 | 2016-07-13 |  | EXP |  | 2015-12-10 | 2016-03-17 | 66 | 0 | 66 | 2016-08-15 | 2016-08-15 | 2016-08-15 | Connected |  | No
National Grid | WINCHENDON | 176256 | 1475 | 2000 | Solar | 01_612W1 | 2015-07-09 01:00 | 2015-07-10 | 18 | 18 | 0 | [10 empty] | 2015-08-05 | 2015-08-26 | 15 | 0 | 15 | [5 empty] | 2016-07-01 | 2016-07-20 | 12 | 0 | 12 | 2016-07-06 | 2015-07-09 01:00 | 2018-08-31 | Yes | STD |  | 2018-04-30 | 2018-06-05 | 36 | 0 | 36 |  |  | 2018-08-10 | Connected |  | No
National Grid | LEICESTER | 176285 | 1524 | 1000 | Solar | 01_21W2 | 2015-07-09 01:00 | 2015-07-10 | 0 | 0 | 0 | [10 empty] | 2015-07-10 | 2015-08-07 | 20 | 0 | 20 | [5 empty] | 2017-05-05 | 2016-10-06 | 0 | 0 | 0 | 2016-10-06 |  | 2016-07-15 |  | STD |  | 2017-08-07 | 2017-10-27 | 57 | 0 | 57 | 2017-11-08 | 2017-11-08 | 2017-11-08 | Connected |  | No
National Grid | WORCESTER | 176286 | 1602 | 130 | Solar | 01_HT14 | 2015-07-10 01:00 | 2015-07-10 | 209 | 209 | 0 | [27 empty] | 2016-07-15 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEST BROOKFIELD | 176288 | 1585 | 17.4 | Solar | 01_525L2 | 2015-07-10 01:00 | 2015-07-13 | 1 | 1 | 0 | 2015-07-14 | 2017-02-13 | 394 | 0 | 394 | [20 empty] | 2015-07-15 | 2015-07-10 01:00 | 2016-07-18 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORWELL | 176289 | 2061 | 18.4 | Solar | 07_96W43 | 2015-07-10 01:00 | 2015-07-13 | 11 | 11 | 0 | 2015-07-28 | 2015-07-28 | 0 | 0 | 0 | [20 empty] | 2015-08-06 | 2015-07-10 01:00 | 2016-07-18 |  | EXP |  | 2015-01-20 | 2015-09-03 | 156 | 11 | 145 | 2016-08-15 | 2016-08-15 | 2016-08-15 | Connected |  | No
National Grid | RUTLAND | 176290 | 1543 | 22.8 | Solar | 01_55W1 | 2015-07-10 01:00 | 2015-07-13 | 1 | 1 | 0 | 2015-07-14 | 2015-07-14 | 0 | 0 | 0 | [20 empty] | 2015-07-30 |  | 2016-07-18 |  | EXP | [6 empty] | 2015-07-30 | 2015-07-30 | 2017-01-19 | Connected |  | Yes
National Grid | WARREN | 176291 | 1083 | 21.4 | Solar | 09_516L2 | 2015-07-10 01:00 | 2015-07-13 | 1 | 1 | 0 | 2015-07-14 | 2016-09-28 | 302 | 0 | 302 | [20 empty] | 2015-07-30 |  | 2016-07-18 |  | EXP | [6 empty] | 2015-07-30 | 2015-07-30 |  | Withdrawn |  | Yes
National Grid | NORTHBRIDGE | 176293 | 1534 | 7.6 | Solar | 05_320W1 | 2015-07-10 01:00 | 2015-07-13 | 15 | 15 | 0 | 2015-08-03 | 2015-08-04 | 1 | 0 | 1 | [22 empty] | 2016-07-18 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BARRE | 176322 | 1005 | 15.2 | Solar | 09_604W3 | 2015-07-14 01:00 | 2015-07-15 | 8 | 8 | 0 | 2015-07-27 | 2016-10-27 | 313 | 0 | 313 | [20 empty] | 2015-07-27 |  | 2016-07-20 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MALDEN | 176325 | 2148 | 495 | Solar | 12_37W7 | 2015-07-14 01:00 | 2015-07-16 | 3 | 3 | 0 | [26 empty] | 2015-07-15 01:00 | 2016-07-21 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 176323 | 1507 | 30 | Solar | 01_415L1 | 2015-07-15 01:00 | 2015-07-15 | 3 | 3 | 0 | 2015-07-20 | 2017-02-13 | 390 | 0 | 390 | [20 empty] | 2015-08-07 |  | 2017-07-20 | Yes | EXP |  | 2017-04-05 | 2017-04-21 | 11 | 0 | 11 | 2015-07-31 | 2015-07-31 |  | Withdrawn |  | No
National Grid | AVON | 176324 | 2322 | 50 | Solar | 07_75W5 | 2015-07-16 01:00 | 2015-07-16 | 3 | 3 | 0 | 2015-07-21 | 2015-07-21 | 0 | 0 | 0 | [20 empty] | 2015-07-28 | 2015-07-17 01:00 | 2016-07-21 |  | EXP | [6 empty] | 2016-02-24 | 2016-02-24 | 2016-02-24 | Connected |  | No
National Grid | NORTH ANDOVER | 176326 | 1845 | 3200 | Natural Gas | 14_2326 | 2015-07-17 01:00 | 2015-07-17 | 2 | 2 | 0 | [10 empty] | 2015-07-21 | 2015-08-18 | 21 | 21 | 0 | [10 empty] | 2016-05-03 |  | 2019-08-20 | Yes | STD |  | 2017-05-31 | 2017-10-30 | 105 | 0 | 105 |  |  | 2019-08-16 | Connected |  | No
National Grid | LEOMINSTER | 176327 | 1453 | 2800 | Solar | 01_225W2 | 2015-07-17 01:00 | 2015-07-20 | 1 | 1 | 0 | [10 empty] | 2015-07-21 | 2015-08-18 | 20 | 0 | 20 | [10 empty] | 2015-11-23 | 2015-07-17 01:00 | 2016-07-01 |  | STD | [8 empty] | 2016-12-19 | Withdrawn |  | No
National Grid | LEOMINSTER | 177388 | 1453 | 2800 | Solar | 01_225W2 | 2015-07-17 01:00 | 2015-07-21 | 0 | 0 | 0 | [10 empty] | 2015-07-21 | 2015-08-18 | 20 | 0 | 20 | [10 empty] | 2015-11-23 | 2015-07-20 01:00 | 2018-07-20 | Yes | STD |  | 2017-08-28 | 2018-06-18 | 145 | 0 | 145 |  |  | 2017-07-20 | Connected |  | No
National Grid | SOMERSET | 176328 | 2725 | 3.8 | Solar | 05_11W84 | 2015-07-20 01:00 | 2015-07-21 | 4 | 4 | 0 | 2015-07-27 | 2015-07-27 | 0 | 0 | 0 | [20 empty] | 2015-07-28 |  | 2016-07-26 |  | EXP | [6 empty] | 2016-05-03 | 2016-05-03 | 2016-05-03 | Connected |  | No
National Grid | LYNN | 176329 | 1902 | 3.8 | Solar | 12_1384 | 2015-07-20 01:00 | 2015-07-21 | 4 | 4 | 0 | 2015-07-27 | 2016-05-12 | 198 | 88 | 110 | [20 empty] | 2016-02-08 | 2015-07-21 01:00 | 2016-07-26 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NEW BRAINTREE | 175779 | 1531 | 40 | Solar | 09_604W3 | 2015-07-21 01:00 | 2015-07-22 | 3 | 3 | 0 | 2015-07-27 | 2015-07-27 | 0 | 0 | 0 | [20 empty] | 2015-08-13 |  | 2017-08-27 | Yes | EXP |  | 2017-04-27 | 2017-05-11 | 10 | 0 | 10 | 2015-08-13 | 2015-08-13 | 2017-06-19 | Connected |  | No
National Grid | PHILLIPSTON | 176330 | 1331 | 16 | Solar | 09_702W1 | 2015-07-21 01:00 | 2015-07-22 | 3 | 3 | 0 | 2015-07-27 | 2015-07-27 | 0 | 0 | 0 | [20 empty] | 2015-07-28 |  | 2016-07-27 |  | EXP | [6 empty] | 2016-06-22 | 2016-06-22 | 2016-06-22 | Connected |  | No
National Grid | CHARLTON | 176331 | 1507 | 40 | Solar | 01_415L2 | 2015-07-21 01:00 | 2015-07-22 | 3 | 3 | 0 | 2015-07-27 | 2017-02-16 | 388 | 0 | 388 | [20 empty] | 2015-08-07 | 2015-07-22 01:00 | 2016-07-27 |  | EXP | [6 empty] | 2015-08-07 | 2015-08-07 |  | Withdrawn |  | Yes
National Grid | WESTBOROUGH | 175780 | 1581 | 866 | Solar | 05_312W4 | 2015-07-22 01:00 | 2015-07-22 | 10 | 10 | 0 | [10 empty] | 2015-08-05 | 2015-08-28 | 17 | 0 | 17 | [5 empty] | 2016-01-05 | 2016-05-17 | 91 | 10 | 81 | 2016-06-03 |  | 2016-07-27 | Yes | STD |  | 2016-11-09 | 2017-01-25 | 50 | 0 | 50 | 2017-01-26 | 2017-01-26 | 2017-02-01 | Connected |  | No
National Grid | WILLIAMSBURG | 175781 | 1096 | 16 | Solar | 09_909W3 | 2015-07-22 01:00 | 2015-07-22 | 4 | 4 | 0 | 2015-07-28 | 2015-07-28 | 0 | 0 | 0 | [20 empty] | 2015-08-13 |  | 2016-03-18 |  | EXP | [6 empty] | 2016-03-11 | 2016-03-11 | 2016-03-23 | Connected |  | No
National Grid | WEST NEWBURY | 175784 | 1985 | 14 | Solar | 14_47L2 | 2015-07-24 01:00 | 2015-09-11 | 0 | 0 | 0 | 2015-09-25 | 2015-09-25 | 0 | 0 | 0 | [20 empty] | 2015-12-01 |  | 2016-08-01 |  | EXP | [6 empty] | 2017-12-19 | 2017-12-19 | 2017-09-25 | Connected |  | No
National Grid | MILL RIVER | 176190 | 1244 | 496 | Solar | 09_1109W1 | 2015-07-24 01:00 | 2015-09-03 | 0 | 0 | 0 | 2015-09-03 | 2017-02-15 | 359 | 0 | 359 | [22 empty] | 2016-09-08 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WEST WARREN | 176191 | 1092 | 496 | Solar | 09_516L3 | 2015-07-24 01:00 | 2015-09-03 | 0 | 0 | 0 | 2015-09-03 | 2016-08-12 | 233 | 0 | 233 | [22 empty] | 2016-09-08 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WALES | 176192 | 1081 | 496 | Solar | 09_516L1 | 2015-07-24 01:00 | 2015-09-03 | 0 | 0 | 0 | [10 empty] | 2015-09-03 | 2015-10-14 | 27 | 0 | 27 | [12 empty] | 2016-09-08 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MILFORD | 175785 | 1757 | 42 | Solar | 05_336W1 | 2015-07-27 01:00 | 2015-07-27 | 0 | 0 | 0 | 2015-07-27 | 2015-07-27 | 0 | 0 | 0 | [20 empty] | 2015-07-30 |  | 2016-08-01 |  | EXP | [6 empty] | 2016-02-18 | 2016-02-18 | 2016-02-19 | Connected |  | No
National Grid | FRANKLIN | 175786 | 2038 | 42 | Solar | 05_344W6 | 2015-07-27 01:00 | 2015-07-27 | 0 | 0 | 0 | 2015-07-27 | 2015-07-27 | 0 | 0 | 0 | [20 empty] | 2015-07-29 | 2015-07-27 01:00 | 2016-08-01 |  | EXP | [6 empty] | 2016-02-02 | 2016-02-02 | 2016-02-12 | Connected |  | No
National Grid | CLARKSBURG | 175787 | 1247 | 995 | Solar | 09_1015W2 | 2015-07-27 01:00 | 2015-07-27 | 19 | 19 | 0 | [10 empty] | 2015-08-21 | 2015-09-21 | 20 | 0 | 20 | [5 empty] | 2016-02-25 | 2016-05-27 | 64 | 19 | 45 | 2016-09-09 |  | 2017-10-04 | Yes | STD | [6 empty] | 2018-01-02 | 2018-01-02 | 2018-01-02 | Connected |  | No
National Grid | OXFORD | 175815 | 1540 | 360 | Solar | 01_406L2 | 2015-07-27 01:00 | 2015-07-28 | 2 | 2 | 0 | 2015-07-30 | 2018-02-09 | 625 | 0 | 625 | [20 empty] | 2015-07-31 |  | 2018-08-24 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | AVON | 175816 | 2322 | 360 | Solar | 07_75W3 | 2015-07-27 01:00 | 2015-07-28 | 2 | 2 | 0 | 2015-07-30 | 2017-10-19 | 554 | 0 | 554 | [20 empty] | 2015-07-31 |  | 2017-09-06 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FALL RIVER | 175817 | 2724 | 150 | Solar | 05_115W42 | 2015-07-28 01:00 | 2015-07-29 | 2 | 2 | 0 | 2015-07-31 | 2015-07-31 | 0 | 0 | 0 | [20 empty] | 2015-08-04 | 2015-07-30 01:00 | 2016-08-03 |  | EXP | [6 empty] | 2016-09-07 | 2016-09-07 | 2016-09-07 | Connected |  | No
National Grid | WESTPORT | 175819 | 2790 | 2000 | Solar | 05_115W52 | 2015-07-30 01:00 | 2015-07-30 | 9 | 9 | 0 | [10 empty] | 2015-08-12 | 2015-09-09 | 19 | 0 | 19 | [10 empty] | 2016-08-16 | 2015-07-31 01:00 | 2017-07-15 | Yes | STD |  | 2017-03-01 | 2017-06-23 | 80 | 0 | 80 | 2017-06-27 | 2017-06-27 | 2017-07-31 | Connected |  | No
National Grid | DUNSTABLE | 175821 | 1827 | 5 | Solar | 01_210L1 | 2015-07-31 01:00 | 2015-08-03 | 2 | 2 | 0 | 2015-08-05 | 2015-08-05 | 0 | 0 | 0 | [20 empty] | 2015-08-18 |  | 2016-08-08 | Yes | EXP | [6 empty] | 2015-08-18 | 2015-08-18 | 2016-06-17 | Connected |  | No
National Grid | NEW SALEM | 175857 | 1355 | 30.1 | Solar | 09_705W2 | 2015-07-31 01:00 | 2015-08-04 | 0 | 0 | 0 | 2015-08-04 | 2016-07-15 | 235 | 0 | 235 | [20 empty] | 2015-08-06 | 2015-07-31 01:00 | 2016-08-09 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NEW SALEM | 175858 | 1355 | 30 | Solar | 09_705W2 | 2015-07-31 01:00 | 2015-08-04 | 0 | 0 | 0 | 2015-08-04 | 2015-08-04 | 0 | 0 | 0 | [20 empty] | 2015-08-18 |  | 2016-08-09 | Yes | EXP |  | 2016-09-01 | 2016-09-14 | 8 | 0 | 8 | 2015-08-18 | 2015-08-18 | 2016-10-12 | Connected |  | No
National Grid | CHELMSFORD | 175896 | 1824 | 476 | Solar | 14_58L2 | 2015-07-31 01:00 | 2015-08-05 | 1 | 1 | 0 | [10 empty] | 2015-08-06 | 2015-09-03 | 20 | 0 | 20 | [12 empty] | 2016-08-10 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | CHELMSFORD | 175897 | 1824 | 1988 | Solar | 14_58L2 | 2015-07-31 01:00 | 2015-08-05 | 1 | 1 | 0 | [10 empty] | 2015-08-06 | 2015-09-03 | 20 | 0 | 20 | [12 empty] | 2016-08-10 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | CHELMSFORD | 175898 | 1824 | 476 | Solar | 14_58L2 | 2015-07-31 01:00 | 2015-08-05 | 1 | 1 | 0 | [10 empty] | 2015-08-06 | 2015-09-03 | 20 | 0 | 20 | [12 empty] | 2016-08-10 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | TEWKSBURY | 175822 | 1876 | 120 | Solar | 14_59L5 | 2015-08-03 01:00 | 2015-08-03 | 10 | 10 | 0 | 2015-08-17 | 2015-08-17 | 0 | 0 | 0 | [20 empty] | 2015-10-22 |  | 2016-02-15 |  | EXP | [6 empty] | 2016-02-11 | 2016-02-11 | 2016-02-17 | Connected |  | No
National Grid | NANTUCKET | 175824 | 2554 | 25 | Solar | 04_101L8 | 2015-08-03 01:00 | 2015-08-03 | 1 | 1 | 0 | [27 empty] | 2016-08-09 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NANTUCKET | 175853 | 2554 | 25 | Solar | 04_101L8 | 2015-08-03 01:00 | 2015-08-03 | 1 | 1 | 0 | [27 empty] | 2016-08-08 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | PEMBROKE | 175854 | 2359 | 10 | Solar | 07_910W25 | 2015-08-03 01:00 | 2015-08-04 | 3 | 3 | 0 | 2015-08-07 | 2015-08-07 | 0 | 0 | 0 | [20 empty] | 2015-08-21 |  | 2016-08-09 |  | EXP | [6 empty] | 2015-08-21 | 2015-08-21 | 2015-12-18 | Connected |  | No
National Grid | SOMERSET | 175855 | 2726 | 10 | Solar | 05_19W72 | 2015-08-03 01:00 | 2015-08-04 | 4 | 4 | 0 | 2015-08-10 | 2015-08-10 | 0 | 0 | 0 | [20 empty] | 2015-09-01 |  | 2016-08-09 |  | EXP | [6 empty] | 2015-08-21 | 2015-08-21 | 2016-02-18 | Connected |  | No
National Grid | NANTUCKET | 175856 | 2554 | 25 | Solar | 04_101L8 | 2015-08-04 01:00 | 2015-08-04 | 1 | 1 | 0 | 2015-08-05 | 2015-08-05 | 0 | 0 | 0 | [20 empty] | 2015-08-06 |  | 2016-08-09 |  | EXP | [6 empty] | 2015-10-01 | 2015-10-01 | 2016-03-25 | Connected |  | No
National Grid | SUTTON | 175861 | 1590 | 100 | Solar | 01_304W6 | 2015-08-04 01:00 | 2015-08-05 | 3 | 3 | 0 | 2015-08-10 | 2015-08-10 | 0 | 0 | 0 | [20 empty] | 2015-08-19 |  | 2016-08-10 |  | EXP | [6 empty] | 2015-08-19 | 2015-08-19 | 2015-12-18 | Connected |  | No
National Grid | UPTON | 175862 | 1568 | 5 | Solar | 05_320W1 | 2015-08-04 01:00 | 2015-08-05 | 3 | 3 | 0 | 2015-08-10 | 2015-08-10 | 0 | 0 | 0 | [20 empty] | 2015-08-21 |  | 2016-08-10 |  | EXP | [6 empty] | 2015-08-21 | 2015-08-21 | 2016-05-05 | Connected |  | No
National Grid | WESTMINSTER | 175891 | 1473 | 5 | Solar | 01_610W3 | 2015-08-04 01:00 | 2015-08-05 | 3 | 3 | 0 | 2015-08-10 | 2017-02-17 | 379 | 0 | 379 | [20 empty] | 2015-08-10 | 2015-08-04 01:00 | 2016-08-10 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEOMINSTER | 175892 | 1453 | 5 | Solar | 01_219W4 | 2015-08-04 01:00 | 2015-08-05 | 3 | 3 | 0 | 2015-08-10 | 2015-08-10 | 0 | 0 | 0 | [20 empty] | 2015-08-19 |  | 2016-08-10 |  | EXP |  | 2016-05-24 | 2016-06-22 | 19 | 0 | 19 | 2015-08-19 | 2015-08-19 | 2016-08-29 | Connected |  | No
National Grid | SOMERSET | 175893 | 2726 | 7.6 | Solar | 05_19W72 | 2015-08-04 01:00 | 2015-08-05 | 3 | 3 | 0 | 2015-08-10 | 2015-08-10 | 0 | 0 | 0 | [20 empty] | 2015-08-31 |  | 2016-08-10 |  | EXP | [6 empty] | 2015-08-31 | 2015-08-31 | 2016-01-28 | Connected |  | No
National Grid | FRANKLIN | 175894 | 2038 | 6 | Solar | 05_341W1 | 2015-08-04 01:00 | 2015-08-05 | 3 | 3 | 0 | 2015-08-10 | 2015-08-10 | 0 | 0 | 0 | [20 empty] | 2015-08-21 | 2015-08-04 01:00 | 2016-08-10 |  | EXP | [6 empty] | 2015-08-21 | 2015-08-21 | 2015-12-03 | Connected |  | No
National Grid | DUDLEY | 175895 | 1571 | 7.6 | Solar | 01_412L4 | 2015-08-04 01:00 | 2015-08-05 | 3 | 3 | 0 | 2015-08-10 | 2015-08-10 | 0 | 0 | 0 | [20 empty] | 2015-08-18 |  | 2016-08-10 | Yes | EXP |  | 2016-09-13 | 2016-09-23 | 8 | 0 | 8 | 2015-08-18 | 2015-08-18 | 2016-09-28 | Connected |  | No
National Grid | WORCESTER | 175928 | 1602 | 99 | Solar | 01_2J328 | 2015-08-05 01:00 | 2015-08-06 | 2 | 2 | 0 | 2015-08-10 | 2017-04-14 | 418 | 0 | 418 | [20 empty] | 2015-08-12 |  | 2016-08-11 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SCITUATE | 175929 | 2066 | 20 | Solar | 07_915W35 | 2015-08-05 01:00 | 2015-08-06 | 3 | 3 | 0 | 2015-08-11 | 2015-08-11 | 0 | 0 | 0 | [20 empty] | 2015-08-11 |  | 2016-08-11 |  | EXP | [6 empty] | 2015-10-20 | 2015-10-20 | 2015-11-04 | Connected |  | No
National Grid | REVERE | 175930 | 2151 | 10 | Solar | 12_16W4 | 2015-08-06 01:00 | 2015-08-10 | 2 | 2 | 0 | 2015-08-12 | 2015-08-12 | 0 | 0 | 0 | [20 empty] | 2015-08-21 |  | 2016-08-15 |  | EXP | [6 empty] | 2015-08-21 | 2015-08-21 | 2016-08-02 | Connected |  | No
National Grid | OXFORD | 175931 | 1540 | 10.75 | Solar | 01_406L3 | 2015-08-06 01:00 | 2015-08-10 | 2 | 2 | 0 | 2015-08-12 | 2015-08-12 | 0 | 0 | 0 | [20 empty] | 2015-08-12 | 2015-08-06 01:00 | 2016-08-15 |  | EXP | [6 empty] | 2016-02-03 | 2016-02-03 | 2018-01-03 | Connected |  | No
National Grid | DRACUT | 175932 | 1826 | 4.3 | Solar | 14_75L2 | 2015-08-06 01:00 | 2015-08-10 | 2 | 2 | 0 | 2015-08-12 | 2015-08-12 | 0 | 0 | 0 | [20 empty] | 2015-09-01 |  | 2016-08-15 | Yes | EXP |  | 2016-04-25 | 2016-05-17 | 16 | 0 | 16 | 2016-06-20 | 2016-06-20 | 2016-06-22 | Connected |  | No
National Grid | METHUEN | 175933 | 1844 | 7.6 | Solar | 14_74L4 | 2015-08-06 01:00 | 2015-08-10 | 2 | 2 | 0 | 2015-08-12 | 2017-01-27 | 362 | 0 | 362 | [20 empty] | 2015-08-21 |  | 2016-08-15 |  | EXP | [6 empty] | 2015-08-21 | 2015-08-21 |  | Withdrawn |  | Yes
National Grid | SWANSEA | 175934 | 2777 | 8.6 | Solar | 05_11W81 | 2015-08-06 01:00 | 2015-08-10 | 2 | 2 | 0 | 2015-08-12 | 2015-08-12 | 0 | 0 | 0 | [20 empty] | 2015-09-01 |  | 2016-08-15 |  | EXP | [6 empty] | 2016-03-14 | 2016-03-14 | 2016-03-16 | Connected |  | No
National Grid | LEOMINSTER | 175935 | 1453 | 10 | Solar | 01_219W2 | 2015-08-06 01:00 | 2015-08-06 | 4 | 2 | 2 | 2015-08-12 | 2015-10-20 | 47 | 0 | 47 | [20 empty] | 2015-08-21 |  | 2016-08-15 |  | EXP | [6 empty] | 2015-08-21 | 2015-08-21 |  | Withdrawn |  | No
National Grid | WILBRAHAM | 175965 | 1095 | 8.39 | Solar | 09_507L2 | 2015-08-06 01:00 | 2015-08-10 | 2 | 2 | 0 | 2015-08-12 | 2015-08-12 | 0 | 0 | 0 | [20 empty] | 2015-09-08 |  | 2016-08-15 |  | EXP | [6 empty] | 2016-04-12 | 2016-04-12 | 2016-04-14 | Connected |  | No
National Grid | SPENCER | 175966 | 1562 | 18 | Solar | 01_552L1 | 2015-08-06 01:00 | 2015-08-10 | 4 | 4 | 0 | 2015-08-14 | 2016-06-29 | 216 | 0 | 216 | [20 empty] | 2015-09-10 |  | 2016-08-15 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SAUGUS | 175967 | 1906 | 11.4 | Solar | 12_23W2 | 2015-08-06 01:00 | 2015-08-12 | 0 | 0 | 0 | 2015-08-12 | 2015-08-12 | 0 | 0 | 0 | [20 empty] | 2015-09-08 |  | 2016-08-17 |  | EXP | [6 empty] | 2016-04-06 | 2016-04-06 | 2016-04-26 | Connected |  | No
National Grid | LYNN | 175968 | 1904 | 6 | Solar | 12_24W1 | 2015-08-06 01:00 | 2015-08-12 | 0 | 0 | 0 | 2015-08-12 | 2015-10-23 | 50 | 0 | 50 | [20 empty] | 2015-08-24 |  | 2016-08-17 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LEOMINSTER | 176439 | 1453 | 10 | Solar | 01_219W2 | 2015-08-06 01:00 | 2015-08-06 | 4 | 0 | 4 | 2015-08-12 | 2015-08-12 | 0 | 0 | 0 | [20 empty] | 2015-08-21 |  | 2016-08-15 |  | EXP | [6 empty] | 2016-03-17 | 2016-03-17 | 2016-07-19 | Connected |  | No
National Grid | DUDLEY | 175969 | 1571 | 19.75 | Solar | 01_412L4 | 2015-08-07 01:00 | 2015-08-12 | 0 | 0 | 0 | 2015-08-12 | 2015-08-12 | 0 | 0 | 0 | [20 empty] | 2015-08-24 |  | 2016-08-17 |  | EXP | [6 empty] | 2016-09-15 | 2016-09-15 | 2016-09-15 | Connected |  | No
National Grid | BROCKTON | 175973 | 2302 | 250 | Solar | 07_911W56 | 2015-08-10 01:00 | 2015-08-13 | 3 | 3 | 0 | 2015-08-18 | 2015-08-18 | 0 | 0 | 0 | [20 empty] | 2015-09-14 | 2015-08-11 01:00 | 2016-08-18 |  | EXP | [6 empty] | 2015-10-06 | 2015-10-06 | 2015-12-11 | Connected |  | No
National Grid | MILFORD | 175970 | 1757 | 56 | Solar | 05_336W1 | 2015-08-11 01:00 | 2015-08-12 | 0 | 0 | 0 | 2015-08-12 | 2015-08-12 | 0 | 0 | 0 | [20 empty] | 2015-08-25 | 2015-08-11 01:00 | 2015-08-17 | Yes | EXP |  | 2015-12-16 | 2016-03-11 | 58 | 0 | 58 | 2016-02-09 | 2016-02-09 | 2016-03-28 | Connected |  | No
National Grid | SALEM | 176002 | 1970 | 8.17 | Solar | 12_2W1 | 2015-08-11 01:00 | 2015-08-14 | 0 | 0 | 0 | 2015-08-14 | 2015-08-14 | 0 | 0 | 0 | [20 empty] | 2015-09-08 | 2015-08-11 01:00 | 2016-08-19 | Yes | EXP |  | 2016-08-19 | 2016-09-21 | 22 | 0 | 22 | 2016-05-10 | 2016-05-10 | 2016-10-28 | Connected |  | No
National Grid | SALEM | 176003 | 1970 | 9.46 | Solar | 12_2W2 | 2015-08-11 01:00 | 2015-08-14 | 0 | 0 | 0 | 2015-08-14 | 2015-08-24 | 6 | 0 | 6 | [20 empty] | 2015-09-08 |  | 2018-07-27 | Yes | EXP |  | 2017-11-07 | 2018-05-03 | 177 | 0 | 177 |  |  | 2018-07-25 | Connected |  | No
National Grid | METHUEN | 176004 | 1844 | 7.6 | Solar | 14_74L2 | 2015-08-11 01:00 | 2015-08-14 | 0 | 0 | 0 | 2015-08-14 | 2015-08-14 | 0 | 0 | 0 | [20 empty] | 2015-08-24 |  | 2016-08-19 |  | EXP | [6 empty] | 2017-01-25 | 2017-01-25 | 2017-01-25 | Connected |  | No
National Grid | DRACUT | 176005 | 1826 | 10.32 | Solar | 14_75L2 | 2015-08-11 01:00 | 2015-08-14 | 0 | 0 | 0 | 2015-08-14 | 2015-08-14 | 0 | 0 | 0 | [20 empty] | 2015-09-08 |  | 2016-08-19 |  | EXP | [6 empty] | 2016-04-06 | 2016-04-06 | 2016-04-08 | Connected |  | No
National Grid | TEWKSBURY | 176006 | 1876 | 7.6 | Solar | 14_70L1 | 2015-08-11 01:00 | 2015-08-14 | 0 | 0 | 0 | 2015-08-14 | 2017-02-17 | 375 | 0 | 375 | [20 empty] | 2015-08-25 |  | 2016-08-19 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTBOROUGH | 176007 | 1581 | 857.1 | Solar | 05_312W5 | 2015-08-12 01:00 | 2015-08-18 | 2 | 2 | 0 | 2015-08-20 | 2015-10-20 | 42 | 15 | 27 | [21 empty] | 2015-08-13 01:00 | 2017-11-30 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTHAMPTON | 175972 | 1060 | 176 | Solar | 09_901W1 | 2015-08-13 01:00 | 2015-08-13 | 0 | 0 | 0 | 2015-08-13 | 2015-08-13 | 0 | 0 | 0 | [20 empty] | 2015-09-11 |  | 2016-08-18 |  | EXP |  | 2016-06-03 | 2016-12-08 | 128 | 0 | 128 | 2016-12-14 | 2016-12-14 | 2016-12-20 | Connected |  | No
National Grid | LEOMINSTER | 176008 | 1453 | 6 | Solar | 01_219W5 | 2015-08-13 01:00 | 2015-08-14 | 2 | 2 | 0 | 2015-08-18 | 2015-08-24 | 4 | 0 | 4 | [21 empty] | 2015-08-13 01:00 | 2016-08-19 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | RUTLAND | 176009 | 1543 | 2230 | Solar | 01_55W1 | 2015-08-13 01:00 | 2015-08-14 | 2 | 2 | 0 | [10 empty] | 2015-08-18 | 2015-09-16 | 20 | 0 | 20 | [10 empty] | 2017-05-26 |  | 2019-09-19 | Yes | STD |  | 2018-11-09 | 2019-01-31 | 83 | 0 | 83 | 2019-06-07 | 2019-06-07 | 2019-08-28 | Connected |  | No
National Grid | LOWELL | 176010 | 1851 | 64.8 | Solar | 14_2L4 | 2015-08-13 01:00 | 2015-08-14 | 0 | 0 | 0 | 2015-08-14 | 2015-08-14 | 0 | 0 | 0 | [20 empty] | 2015-08-31 |  | 2016-08-19 |  | EXP | [6 empty] | 2016-05-13 | 2016-05-13 | 2016-05-18 | Connected |  | No
National Grid | MELROSE | 176038 | 2176 | 10 | Solar | 12_25W5 | 2015-08-13 01:00 | 2015-08-14 | 2 | 2 | 0 | 2015-08-18 | 2015-08-18 | 0 | 0 | 0 | [20 empty] | 2015-08-25 |  | 2016-08-19 |  | EXP | [6 empty] | 2016-06-22 | 2016-06-22 | 2016-08-05 | Connected |  | No
National Grid | REVERE | 176039 | 2151 | 2.58 | Solar | 12_7W2 | 2015-08-13 01:00 | 2015-08-14 | 2 | 2 | 0 | 2015-08-18 | 2015-08-18 | 0 | 0 | 0 | [20 empty] | 2015-09-09 |  | 2016-08-19 |  | EXP | [6 empty] | 2016-05-12 | 2016-05-12 | 2016-06-27 | Connected |  | No
National Grid | NORTON | 176040 | 2766 | 10 | Solar | 05_8L4 | 2015-08-13 01:00 | 2015-08-14 | 16 | 16 | 0 | [27 empty] | 2016-08-19 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTH BILLERICA | 176041 | 1862 | 11.4 | Solar | 14_70L1 | 2015-08-14 01:00 | 2015-08-17 | 1 | 1 | 0 | 2015-08-18 | 2015-08-18 | 0 | 0 | 0 | [20 empty] | 2015-09-09 |  | 2016-08-22 |  | EXP | [6 empty] | 2016-03-11 | 2016-03-11 | 2016-03-17 | Connected |  | No
National Grid | WORCESTER | 176042 | 1606 | 476 | Solar | 01_24W2 | 2015-08-14 01:00 | 2015-08-17 | 1 | 1 | 0 | 2015-08-18 | 2015-08-18 | 0 | 0 | 0 | [20 empty] | 2015-09-16 | 2015-08-14 01:00 | 2016-08-22 |  | EXP | [6 empty] | 2015-10-06 | 2015-10-06 | 2016-06-09 | Connected |  | Yes
National Grid | WESTMINSTER | 176043 | 1473 | 1000 | Solar | 01_602W2 | 2015-08-14 01:00 | 2015-08-18 | 0 | 0 | 0 | [10 empty] | 2015-08-18 | 2015-09-15 | 19 | 0 | 19 | [10 empty] | 2016-10-17 |  | 2020-02-24 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTMINSTER | 176044 | 1473 | 630 | Solar | 01_602W2 | 2015-08-14 01:00 | 2015-08-18 | 0 | 0 | 0 | [10 empty] | 2015-08-18 | 2015-09-15 | 19 | 0 | 19 | [12 empty] | 2016-08-23 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTON | 176046 | 2766 | 480 | Solar | 05_4L1 | 2015-08-18 01:00 | 2015-08-18 | 2 | 2 | 0 | 2015-08-20 | 2016-09-19 | 268 | 0 | 268 | [21 empty] | 2015-08-18 01:00 | 2016-08-23 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SHIRLEY | 176075 | 1464 | 920 | Solar | 01_201W1 | 2015-08-18 01:00 | 2015-08-20 | 7 | 7 | 0 | 2015-08-31 | 2015-08-31 | 0 | 0 | 0 | 2015-11-06 | 2015-12-02 | 16 | 0 | 16 | [5 empty] | 2015-11-06 | 2015-12-02 | 16 | 0 | 16 | [5 empty] | 2016-03-23 | 2015-08-18 01:00 | 2016-08-25 |  | EXP | [6 empty] | 2017-03-08 | 2017-03-08 | 2017-03-08 | Connected |  | No
National Grid | LAWRENCE | 176220 | 1843 | 349 | Solar | 14_2326 | 2015-08-18 01:00 | 2015-09-04 | 0 | 0 | 0 | 2015-09-04 | 2015-10-13 | 185 | 160 | 25 | [20 empty] | 2016-08-05 |  | 2018-10-03 | Yes | EXP | [8 empty] | 2018-10-29 | Connected |  | No
National Grid | LAWRENCE | 176221 | 1843 | 122 | Solar | 14_2326 | 2015-08-18 01:00 | 2015-09-04 | 0 | 0 | 0 | 2015-09-04 | 2015-09-04 | 0 | 0 | 0 | [20 empty] | 2015-10-05 | 2015-08-18 01:00 | 2016-09-09 |  | EXP | [6 empty] | 2017-10-04 | 2017-10-04 | 2017-10-04 | Connected |  | No
National Grid | LAWRENCE | 176222 | 1843 | 158 | Solar | 14_2326 | 2015-08-18 01:00 | 2015-09-04 | 0 | 0 | 0 | 2015-09-04 | 2017-12-11 | 558 | 59 | 499 | [20 empty] | 2015-10-05 | 2015-08-18 01:00 | 2016-09-09 | Yes | EXP | [9 empty] | Withdrawn |  | No
National Grid | LAWRENCE | 176223 | 1843 | 232 | Solar | 14_2326 | 2015-08-18 01:00 | 2015-09-04 | 0 | 0 | 0 | 2015-09-04 | 2015-09-04 | 0 | 0 | 0 | [20 empty] | 2015-10-05 | 2015-08-18 01:00 | 2016-09-09 |  | EXP | [6 empty] | 2017-09-06 | 2017-09-06 | 2017-09-06 | Connected |  | No
National Grid | LAWRENCE | 178092 | 1843 | 122 | Solar | 14_2326 | 2015-08-18 01:00 | 2015-09-04 | 0 | 0 | 0 | 2015-09-04 | 2015-10-05 | 20 | 0 | 20 | [20 empty] | 2015-10-05 | 2015-08-18 01:00 | 2018-10-17 | Yes | EXP | [8 empty] | 2017-10-04 | Connected |  | No
National Grid | LAWRENCE | 178093 | 1843 | 232 | Solar | 14_2326 | 2015-08-18 01:00 | 2015-09-04 | 0 | 0 | 0 | 2015-09-04 | 2015-10-05 | 20 | 0 | 20 | [20 empty] | 2015-10-05 |  | 2018-07-15 | Yes | EXP | [8 empty] | 2018-06-11 | Connected |  | No
National Grid | PLAINVILLE | 178785 | 2762 | 480 | Solar | 05_3422W1 | 2015-08-18 01:00 | 2015-08-18 | 2 | 2 | 0 | 2015-08-20 | 2016-09-19 | 268 | 0 | 268 | [21 empty] | 2015-08-19 01:00 | 2016-08-23 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 176074 | 2302 | 7.6 | Solar | 07_712J1 | 2015-08-19 01:00 | 2015-08-19 | 3 | 3 | 0 | 2015-08-24 | 2015-08-24 | 0 | 0 | 0 | [20 empty] | 2015-09-09 |  | 2016-08-24 | Yes | EXP |  | 2016-01-11 | 2016-02-19 | 27 | 0 | 27 | 2016-05-16 | 2016-05-16 | 2016-05-20 | Connected |  | No
National Grid | LEOMINSTER | 176076 | 1453 | 10 | Solar | 01_219W2 | 2015-08-20 01:00 | 2015-08-20 | 0 | 0 | 0 | 2015-08-20 | 2015-10-19 | 40 | 0 | 40 | [20 empty] | 2015-09-10 |  | 2016-08-25 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | GRANBY | 176077 | 1033 | 998 | Solar | 09_527L1 | 2015-08-20 01:00 | 2015-08-20 | 7 | 7 | 0 | [10 empty] | 2015-08-31 | 2015-09-29 | 20 | 0 | 20 | [5 empty] | 2015-10-30 |  | 599 | 0 | 599 |  |  | 2016-04-15 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH ANDOVER | 176081 | 1845 | 27 | Solar | 14_7J3 | 2015-08-20 01:00 | 2015-08-21 | 9 | 9 | 0 | [27 empty] | 2016-08-26 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTH ANDOVER | 176110 | 1845 | 27 | Solar | 14_7J3 | 2015-08-20 01:00 | 2015-08-21 | 9 | 9 | 0 | [27 empty] | 2016-08-26 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | GARDNER | 176116 | 1440 | 7.6 | Solar | 01_607W1 | 2015-08-20 01:00 | 2015-08-24 | 0 | 0 | 0 | 2015-08-24 | 2015-08-24 | 0 | 0 | 0 | [20 empty] | 2015-09-10 |  | 2016-08-29 |  | EXP | [6 empty] | 2016-03-16 | 2016-03-16 | 2016-03-18 | Connected |  | No
National Grid | HALIFAX | 176117 | 2338 | 10 | Solar | 07_912W75 | 2015-08-20 01:00 | 2015-08-24 | 0 | 0 | 0 | 2015-08-24 | 2015-08-24 | 0 | 0 | 0 | [20 empty] | 2015-09-10 | 2015-08-21 01:00 | 2016-08-29 |  | EXP | [6 empty] | 2016-03-22 | 2016-03-22 | 2016-03-28 | Connected |  | Yes
National Grid | WESTFORD | 176080 | 1886 | 323 | Solar | 14_57L1 | 2015-08-21 01:00 | 2015-08-21 | 0 | 0 | 0 | 2015-08-21 | 2016-11-15 | 306 | 14 | 292 | 2015-11-05 | 2016-09-23 | 219 | 14 | 205 | [5 empty] | 2015-11-05 | 2016-09-23 | 219 | 14 | 205 | [5 empty] | 2016-02-09 |  | 2017-04-15 | Yes | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RUTLAND | 176118 | 1543 | 6 | Solar | 01_55W1 | 2015-08-21 01:00 | 2015-08-25 | 13 | 13 | 0 | 2015-09-14 | 2015-09-14 | 0 | 0 | 0 | [20 empty] | 2015-09-17 | 2015-08-21 01:00 | 2016-08-30 |  | EXP | [6 empty] | 2016-04-14 | 2016-04-14 | 2016-04-25 | Connected |  | No
National Grid | WESTFORD | 177190 | 1886 | 323 | Solar | 14_58L2 | 2015-08-21 01:00 | 2015-08-21 | 4 | 0 | 4 | 2015-08-27 | 2015-08-27 | 0 | 0 | 0 | 2015-11-05 | 2016-01-06 | 40 | 12 | 28 | [5 empty] | 2015-11-05 | 2016-01-06 | 40 | 12 | 28 | [5 empty] | 2016-02-09 |  | 2017-08-01 | Yes | EXP |  | 2017-06-15 | 2017-09-06 | 57 | 0 | 57 | 2017-08-30 | 2017-08-30 | 2017-09-07 | Connected |  | No
National Grid | HAVERHILL | 176146 | 1830 | 1700 | Solar | 14_65L3 | 2015-08-24 01:00 | 2015-08-25 | 4 | 4 | 0 | [10 empty] | 2015-08-31 | 2015-09-29 | 20 | 0 | 20 | [5 empty] | 2016-05-27 |  | 457 | 21 | 436 | 2016-05-12 | 2015-08-24 01:00 | 2016-08-12 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | PEMBROKE | 176147 | 2359 | 2400 | Solar | 07_910W25 | 2015-08-24 01:00 | 2015-08-25 | 4 | 4 | 0 | [10 empty] | 2015-08-31 | 2015-09-28 | 19 | 0 | 19 | [5 empty] | 2016-03-23 | 2016-03-23 | 0 | 0 | 0 | 2016-05-11 |  | 2017-12-18 | Yes | STD |  | 2017-08-03 | 2017-12-18 | 88 | 0 | 88 | 2017-12-05 | 2017-12-05 | 2017-12-18 | Connected |  | No
National Grid | CHARLTON | 176149 | 1507 | 6 | Solar | 01_406L1 | 2015-08-25 01:00 | 2015-08-31 | 0 | 0 | 0 | 2015-08-31 | 2018-02-14 | 606 | 0 | 606 | [20 empty] | 2015-09-10 | 2015-08-26 01:00 | 2016-09-05 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEST STOCKBRIDGE | 176151 | 1266 | 2000 | Solar | 09_1109W3 | 2015-08-26 01:00 | 2015-08-31 | 1 | 1 | 0 | [10 empty] | 2015-09-01 | 2015-10-06 | 24 | 0 | 24 | [10 empty] | 2016-02-01 |  | 2017-11-02 | Yes | STD |  | 2017-06-20 | 2017-10-31 | 91 | 0 | 91 | 2017-11-08 | 2017-11-08 | 2017-11-08 | Connected |  | No
National Grid | BILLERICA | 176148 | 1821 | 172 | Solar | 14_92L2 | 2015-08-27 01:00 | 2015-08-31 | 0 | 0 | 0 | 2015-08-31 | 2015-08-31 | 0 | 0 | 0 | [20 empty] | 2015-09-01 |  | 2016-09-05 |  | EXP | [6 empty] | 2016-02-02 | 2016-02-02 | 2016-05-05 | Connected |  | No
National Grid | STOUGHTON | 176150 | 2072 | 100 | Solar | 07_913W69 | 2015-08-28 01:00 | 2015-08-31 | 0 | 0 | 0 | 2015-08-31 | 2015-08-31 | 0 | 0 | 0 | [20 empty] | 2015-09-01 |  | 2016-09-05 |  | EXP | [6 empty] | 2016-02-04 | 2016-02-04 | 2016-03-09 | Connected |  | No
National Grid | FALL RIVER | 176154 | 2720 | 56 | Solar | 05_106W43 | 2015-08-28 01:00 | 2015-08-31 | 3 | 3 | 0 | 2015-09-03 | 2015-09-03 | 0 | 0 | 0 | [20 empty] | 2015-09-11 | 2015-08-28 01:00 | 2016-09-05 |  | EXP | [6 empty] | 2016-03-23 | 2016-03-23 | 2016-03-23 | Connected |  | No
National Grid | SOMERSET | 176184 | 2726 | 1143 | Solar | 05_11W82 | 2015-08-28 01:00 | 2015-09-01 | 2 | 2 | 0 | [10 empty] | 2015-09-03 | 2015-12-17 | 71 | 37 | 34 | [10 empty] | 2016-04-21 | 2015-08-28 01:00 | 2016-09-06 | Yes | STD |  | 2016-08-11 | 2016-11-07 | 60 | 0 | 60 | 2017-06-27 | 2017-06-27 | 2017-05-17 | Connected |  | No
National Grid | GLOUCESTER | 176185 | 1930 | 112 | Solar | 12_51T1 | 2015-08-28 01:00 | 2015-09-01 | 3 | 3 | 0 | 2015-09-04 | 2015-09-04 | 0 | 0 | 0 | [20 empty] | 2015-09-10 |  | 2016-09-06 | Yes | EXP |  | 2016-12-19 | 2017-02-24 | 45 | 0 | 45 | 2017-04-20 | 2017-04-20 | 2017-04-14 | Connected |  | No
National Grid | GLOUCESTER | 176186 | 1930 | 112 | Solar | 12_51T1 | 2015-08-28 01:00 | 2015-09-01 | 3 | 3 | 0 | 2015-09-04 | 2015-09-04 | 0 | 0 | 0 | [20 empty] | 2015-09-16 |  | 2016-09-06 |  | EXP | [6 empty] | 2017-04-11 | 2017-04-11 | 2017-04-11 | Connected |  | No
National Grid | EVERETT | 176188 | 2149 | 500 |  | 12_10J6 | 2015-09-01 01:00 | 2015-09-03 | 0 | 0 | 0 | [10 empty] | 2015-09-03 | 2015-09-29 | 17 | 0 | 17 | [11 empty] | 2015-09-01 01:00 | 2016-09-08 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 176189 | 1604 | 500 | Battery Add-On | 01_8W1 | 2015-09-01 01:00 | 2015-09-03 | 0 | 0 | 0 | [10 empty] | 2015-09-03 | 2015-10-06 | 22 | 0 | 22 | [5 empty] | 2016-03-10 | 2016-03-10 | 0 | 0 | 0 | 2016-05-02 |  | 2016-09-08 |  | STD |  | 2017-04-19 | 2017-06-08 | 35 | 0 | 35 | 2017-08-01 | 2017-08-01 | 2017-08-29 | Terminated |  | No
National Grid | GRAFTON | 176224 | 1519 | 7.6 | Solar | 01_304W2 | 2015-09-01 01:00 | 2015-09-07 | 1 | 1 | 0 | 2015-09-09 | 2017-02-17 | 358 | 0 | 358 | [20 empty] | 2015-09-09 | 2015-09-01 01:00 | 2016-09-12 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BILLERICA | 176225 | 1821 | 7.6 | Solar | 14_92L6 | 2015-09-01 01:00 | 2015-09-07 | 1 | 1 | 0 | 2015-09-09 | 2015-09-09 | 0 | 0 | 0 | [20 empty] | 2015-09-23 |  | 2016-09-12 | Yes | EXP |  | 2016-05-06 | 2016-09-02 | 82 | 0 | 82 | 2015-09-23 | 2015-09-23 | 2016-09-13 | Connected |  | No
National Grid | TEWKSBURY | 176226 | 1876 | 10 | Solar | 14_70L1 | 2015-09-01 01:00 | 2015-09-07 | 1 | 1 | 0 | 2015-09-09 | 2017-02-17 | 358 | 0 | 358 | [20 empty] | 2015-09-09 | 2015-09-01 01:00 | 2016-09-12 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTPORT | 176227 | 2790 | 10 | Solar | 05_115W45 | 2015-09-01 01:00 | 2015-09-07 | 1 | 1 | 0 | 2015-09-09 | 2015-09-09 | 0 | 0 | 0 | [20 empty] | 2015-09-23 | 2015-09-02 01:00 | 2016-09-12 | Yes | EXP |  | 2016-01-21 | 2016-01-28 | 5 | 0 | 5 | 2015-09-23 | 2015-09-23 | 2016-05-05 | Connected |  | No
National Grid | MILLBURY | 176228 | 1527 | 6 | Solar | 01_304W4 | 2015-09-02 01:00 | 2015-09-07 | 1 | 1 | 0 | 2015-09-09 | 2015-09-09 | 0 | 0 | 0 | [20 empty] | 2015-09-23 | 2015-09-03 01:00 | 2016-09-12 | Yes | EXP |  | 2016-07-29 | 2016-08-06 | 6 | 0 | 6 | 2015-09-23 | 2015-09-23 | 2016-08-23 | Connected |  | No
National Grid | LEOMINSTER | 176257 | 1453 | 252 | Solar | 01_219W2 | 2015-09-03 01:00 | 2015-09-07 | 0 | 0 | 0 | 2015-09-07 | 2015-09-07 | 0 | 0 | 0 | [20 empty] | 2015-09-24 |  | 2016-09-12 | Yes | EXP |  | 2016-06-22 | 2016-08-30 | 48 | 0 | 48 | 2015-09-24 | 2015-09-24 | 2016-10-07 | Connected |  | No
National Grid | BRIDGEWATER | 176258 | 2324 | 10 | Solar | 07_912W55 | 2015-09-03 01:00 | 2015-09-07 | 3 | 3 | 0 | 2015-09-11 | 2015-09-11 | 0 | 0 | 0 | [20 empty] | 2015-09-11 |  | 2016-09-12 |  | EXP | [6 empty] | 2015-12-10 | 2015-12-10 | 2015-12-10 | Connected |  | No
National Grid | MILFORD | 176259 | 1757 | 18.06 | Solar | 05_335W5 | 2015-09-04 01:00 | 2015-09-07 | 4 | 4 | 0 | 2015-09-14 | 2015-09-14 | 0 | 0 | 0 | [20 empty] | 2015-09-16 |  | 2016-09-12 |  | EXP | [6 empty] | 2015-12-23 | 2015-12-23 | 2015-12-23 | Connected |  | No
National Grid | LEOMINSTER | 176260 | 1453 | 10 | Solar | 01_225W4 | 2015-09-04 01:00 | 2015-09-07 | 3 | 3 | 0 | 2015-09-11 | 2015-09-11 | 0 | 0 | 0 | [20 empty] | 2015-09-25 |  | 2016-09-12 |  | EXP | [6 empty] | 2015-09-25 | 2015-09-25 | 2016-03-17 | Connected |  | No
National Grid | MARLBOROUGH | 176261 | 1752 | 6 | Solar | 05_310W5 | 2015-09-04 01:00 | 2015-09-07 | 3 | 3 | 0 | 2015-09-11 | 2015-09-11 | 0 | 0 | 0 | [20 empty] | 2015-09-25 |  | 2016-09-12 |  | EXP | [6 empty] | 2015-09-25 | 2015-09-25 | 2016-02-12 | Connected |  | No
National Grid | RUTLAND | 176262 | 1543 | 10 | Solar | 01_55W1 | 2015-09-04 01:00 | 2015-09-08 | 3 | 3 | 0 | 2015-09-11 | 2015-09-11 | 0 | 0 | 0 | [20 empty] | 2015-09-11 |  | 2016-09-13 |  | EXP | [6 empty] | 2016-03-23 | 2016-03-23 | 2016-03-23 | Connected |  | No
National Grid | RUTLAND | 176264 | 1543 | 380 | Landfill Gas | 01_55W1 | 2015-09-04 01:00 | 2015-09-09 | 3 | 3 | 0 | [10 empty] | 2015-09-14 | 2015-10-13 | 20 | 0 | 20 | [12 empty] | 2016-09-14 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HARDWICK | 176263 | 1037 | 20 | Solar | 09_501L2 | 2015-09-08 01:00 | 2015-09-08 | 4 | 4 | 0 | 2015-09-14 | 2017-01-25 | 338 | 0 | 338 | [20 empty] | 2015-10-01 |  | 2016-09-13 |  | EXP | [6 empty] | 2016-04-11 | 2016-04-11 |  | Withdrawn |  | Yes
National Grid | HOPEDALE | 176265 | 1747 | 200 | Solar | 05_335W9 | 2015-09-09 01:00 | 2015-09-09 | 3 | 3 | 0 | 2015-09-14 | 2015-09-14 | 0 | 0 | 0 | [20 empty] | 2015-09-18 |  | 2016-09-14 |  | EXP | [6 empty] | 2016-03-22 | 2016-03-22 | 2016-04-08 | Connected |  | No
National Grid | NEW SALEM | 176294 | 1364 | 2000 | Solar | 09_702W3 | 2015-09-09 01:00 | 2015-09-10 | 1 | 1 | 0 | [10 empty] | 2015-09-11 | 2015-10-19 | 25 | 0 | 25 | [12 empty] | 2016-09-15 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WARE | 176295 | 1082 | 1000 | Solar | 09_501L1 | 2015-09-09 01:00 | 2015-09-11 | 2 | 2 | 0 | [10 empty] | 2015-09-15 | 2015-10-20 | 24 | 0 | 24 | [11 empty] | 2015-09-11 01:00 | 2016-09-16 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | TYNGSBORO | 176299 | 1879 | 300 | Solar | 01_210L1 | 2015-09-11 01:00 | 2015-09-14 | 0 | 0 | 0 | 2015-09-14 | 2015-09-14 | 0 | 0 | 0 | [20 empty] | 2015-11-25 |  | 2016-09-19 |  | EXP | [6 empty] | 2015-11-25 | 2015-11-25 | 2016-05-02 | Connected |  | No
National Grid | SOUTHBRIDGE | 176301 | 1550 | 1126 | Natural Gas | 01_413L6 | 2015-09-11 01:00 | 2015-09-15 | 1 | 1 | 0 | [10 empty] | 2015-09-16 | 2015-10-30 | 31 | 0 | 31 | [10 empty] | 2017-08-30 |  | 2018-07-01 |  | STD | [6 empty] | 2018-03-23 | 2018-03-23 | 2018-08-27 | Connected |  | No
National Grid | NORTH DIGHTON | 176302 | 2764 | 490 | Solar | 05_19W74 | 2015-09-15 01:00 | 2015-09-15 | 0 | 0 | 0 | 2015-09-15 | 2016-09-07 | 243 | 0 | 243 | [21 empty] | 2015-09-15 01:00 | 2016-09-20 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | REVERE | 176303 | 2151 | 4.3 | Solar | 12_16W8 | 2015-09-15 01:00 | 2015-09-16 | 4 | 4 | 0 | 2015-09-22 | 2015-09-22 | 0 | 0 | 0 | [20 empty] | 2015-10-09 |  | 2016-09-21 | Yes | EXP |  | 2016-09-01 | 2016-08-31 | 0 | 0 | 0 | 2016-09-12 | 2016-09-12 | 2016-09-12 | Connected |  | No
National Grid | GRANBY | 176332 | 1033 | 7.6 | Solar | 09_527L1 | 2015-09-15 01:00 | 2015-09-16 | 4 | 4 | 0 | 2015-09-22 | 2017-02-13 | 345 | 0 | 345 | [20 empty] | 2015-10-09 | 2015-09-15 01:00 | 2016-09-21 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BLACKSTONE | 176333 | 1504 | 6 | Solar | 05_108W60 | 2015-09-15 01:00 | 2015-09-16 | 4 | 4 | 0 | 2015-09-22 | 2015-09-22 | 0 | 0 | 0 | [20 empty] | 2015-10-09 |  | 2016-09-21 | Yes | EXP |  | 2016-10-18 | 2016-10-27 | 7 | 0 | 7 | 2016-12-13 | 2016-12-13 | 2016-12-16 | Connected |  | No
National Grid | WORCESTER | 176334 | 1603 | 6.67 | Solar | 01_6W2 | 2015-09-15 01:00 | 2015-09-16 | 4 | 4 | 0 | 2015-09-22 | 2017-02-17 | 349 | 0 | 349 | [20 empty] | 2015-09-25 |  | 2016-09-21 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH BROOKFIELD | 175791 | 1535 | 1000 | Solar | 01_525L2 | 2015-09-16 01:00 | 2015-09-18 | 26 | 26 | 0 | [10 empty] | 2015-10-27 | 2015-11-23 | 18 | 0 | 18 | [10 empty] | 2016-04-28 | 2015-09-16 01:00 | 2016-09-23 |  | STD |  | 2017-08-22 | 2017-11-14 | 52 | 0 | 52 | 2017-11-17 | 2017-11-17 | 2017-11-17 | Connected |  | No
National Grid | NORTH BROOKFIELD | 175792 | 1535 | 1000 | Solar | 01_525L2 | 2015-09-16 01:00 | 2015-09-18 | 26 | 26 | 0 | [10 empty] | 2015-10-27 | 2015-11-23 | 18 | 0 | 18 | [10 empty] | 2016-04-28 |  | 2016-09-23 | Yes | STD |  | 2017-08-22 | 2017-11-14 | 52 | 0 | 52 | 2017-11-17 | 2017-11-17 | 2017-11-17 | Connected |  | No
National Grid | SOUTHBRIDGE | 175793 | 1550 | 760 | Solar | 01_413L3 | 2015-09-16 01:00 | 2015-09-21 | 0 | 0 | 0 | [10 empty] | 2015-09-21 | 2015-10-19 | 19 | 0 | 19 | [12 empty] | 2016-09-26 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SOUTHBRIDGE | 175794 | 1550 | 1000 | Solar | 01_413L3 | 2015-09-16 01:00 | 2015-09-21 | 0 | 0 | 0 | [10 empty] | 2015-09-21 | 2015-10-19 | 19 | 0 | 19 | [11 empty] | 2015-09-16 01:00 | 2016-09-26 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MENDON | 175795 | 1756 | 1100 | Solar | 05_335W1 | 2015-09-16 01:00 | 2015-09-21 | 1 | 1 | 0 | [10 empty] | 2015-09-22 | 2015-10-20 | 19 | 0 | 19 | [10 empty] | 2016-08-04 | 2015-09-16 01:00 | 2018-06-30 | Yes | STD |  | 2017-06-05 | 2017-12-14 | 128 | 0 | 128 |  |  |  | Withdrawn |  | No
National Grid | MENDON | 175796 | 1756 | 743 | Solar | 05_335W1 | 2015-09-16 01:00 | 2015-09-21 | 1 | 1 | 0 | [10 empty] | 2015-09-22 | 2015-10-20 | 19 | 0 | 19 | [10 empty] | 2016-08-04 | 2015-09-16 01:00 | 2017-12-22 | Yes | STD |  | 2017-06-05 | 2017-12-14 | 128 | 0 | 128 | 2017-12-20 | 2017-12-20 | 2017-12-22 | Connected |  | No
National Grid | MENDON | 175825 | 1756 | 1860 | Solar | 05_335W1 | 2015-09-16 01:00 | 2015-09-21 | 1 | 1 | 0 | [10 empty] | 2015-09-22 | 2015-10-20 | 19 | 0 | 19 | [10 empty] | 2016-08-04 |  | 2017-12-22 | Yes | STD |  | 2017-06-05 | 2017-12-14 | 128 | 0 | 128 | 2017-12-20 | 2017-12-20 | 2017-12-22 | Connected |  | No
National Grid | WHITMAN | 176335 | 2382 | 70 | Solar | 07_93W43 | 2015-09-16 01:00 | 2015-09-16 | 1 | 1 | 0 | 2015-09-17 | 2015-09-17 | 0 | 0 | 0 | [20 empty] | 2015-10-02 | 2015-09-16 01:00 | 2016-09-21 |  | EXP | [6 empty] | 2016-08-26 | 2016-08-26 | 2016-08-26 | Connected |  | Yes
National Grid | PHILLIPSTON | 176337 | 1331 | 972 | Solar | 09_702W1 | 2015-09-16 01:00 | 2015-09-17 | 3 | 3 | 0 | [10 empty] | 2015-09-22 | 2015-10-20 | 19 | 0 | 19 | [5 empty] | 2016-01-27 | 2016-04-04 | 46 | 0 | 46 | 2016-09-20 | 2015-09-17 01:00 | 2016-09-22 |  | STD | [6 empty] | 2017-10-23 | 2017-10-23 | 2017-10-23 | Connected |  | No
National Grid | GLOUCESTER | 175788 | 1930 | 200 | Solar | 12_51T3 | 2015-09-17 01:00 | 2015-09-18 | 0 | 0 | 0 | 2015-09-18 | 2015-09-18 | 0 | 0 | 0 | [20 empty] | 2015-09-23 |  | 2016-09-23 | Yes | EXP | [6 empty] | 2016-04-15 | 2016-04-15 | 2016-05-03 | Connected |  | No
National Grid | FRANKLIN | 175789 | 2038 | 46 | Solar | 05_344W3 | 2015-09-17 01:00 | 2015-09-18 | 0 | 0 | 0 | 2015-09-18 | 2017-03-09 | 364 | 48 | 316 | 2015-11-03 | 2015-12-02 | 19 | 1 | 18 | [5 empty] | 2015-11-03 | 2015-12-02 | 19 | 1 | 18 | [5 empty] | 2016-02-24 | 2015-09-17 01:00 | 2017-03-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ABINGTON | 176336 | 2351 | 996 | Solar | 07_93W42 | 2015-09-17 01:00 | 2015-09-17 | 1 | 1 | 0 | [10 empty] | 2015-09-17 | 2015-10-15 | 20 | 20 | 0 | [10 empty] | 2016-03-30 |  | 2016-09-22 |  | STD |  | 2016-09-19 | 2016-12-19 | 62 | 0 | 62 | 2016-12-30 | 2016-12-30 | 2016-12-30 | Connected |  | No
National Grid | WORCESTER | 176338 | 1607 | 308 | Solar | 01_8J364 | 2015-09-17 01:00 | 2015-09-17 | 3 | 3 | 0 | 2015-09-22 | 2015-09-22 | 0 | 0 | 0 | [20 empty] | 2015-10-29 |  | 2016-09-22 |  | EXP | [6 empty] | 2016-02-08 | 2016-02-08 | 2016-02-12 | Connected |  | No
National Grid | REVERE | 176339 | 2151 | 3.8 | Solar | 12_7W2 | 2015-09-17 01:00 | 2015-09-17 | 5 | 5 | 0 | 2015-09-24 | 2017-01-25 | 330 | 0 | 330 | [20 empty] | 2015-10-12 |  | 2016-09-22 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | TEWKSBURY | 176340 | 1876 | 268 | Solar | 14_20L2 | 2015-09-17 01:00 | 2015-09-17 | 3 | 3 | 0 | 2015-09-22 | 2015-09-22 | 0 | 0 | 0 | [20 empty] | 2015-11-04 |  | 2016-09-22 |  | EXP | [6 empty] | 2015-11-12 | 2015-11-12 | 2016-01-27 | Connected |  | No
National Grid | ORANGE | 175790 | 1364 | 112 | Solar | 09_702W3 | 2015-09-18 01:00 | 2015-09-18 | 2 | 2 | 0 | 2015-09-22 | 2015-09-22 | 0 | 0 | 0 | [20 empty] | 2015-09-29 | 2015-09-18 01:00 | 2016-09-23 |  | EXP | [6 empty] | 2016-03-22 | 2016-03-22 | 2016-04-15 | Connected |  | No
National Grid | BILLERICA | 175826 | 1821 | 7.6 | Solar | 14_18L3 | 2015-09-18 01:00 | 2015-09-21 | 3 | 3 | 0 | 2015-09-24 | 2015-09-24 | 0 | 0 | 0 | [20 empty] | 2015-10-12 |  | 2016-09-26 | Yes | EXP |  | 2016-04-04 | 2016-05-13 | 28 | 0 | 28 | 2016-05-04 | 2016-05-04 | 2016-06-17 | Connected |  | No
National Grid | SOMERSET | 175827 | 2726 | 7.6 | Solar | 05_19W74 | 2015-09-18 01:00 | 2015-09-22 | 2 | 2 | 0 | 2015-09-24 | 2015-09-24 | 0 | 0 | 0 | [20 empty] | 2015-09-28 |  | 2016-09-27 |  | EXP | [6 empty] | 2016-03-24 | 2016-03-24 | 2016-03-24 | Connected |  | No
National Grid | RUTLAND | 175828 | 1543 | 10 | Solar | 01_55W1 | 2015-09-18 01:00 | 2015-09-22 | 2 | 2 | 0 | 2015-09-24 | 2015-09-24 | 0 | 0 | 0 | [20 empty] | 2015-09-25 |  | 2016-09-27 |  | EXP | [6 empty] | 2016-04-04 | 2016-04-04 | 2016-04-08 | Connected |  | No
National Grid | GARDNER | 175829 | 1440 | 7.6 | Solar | 01_607W1 | 2015-09-18 01:00 | 2015-09-22 | 2 | 2 | 0 | 2015-09-24 | 2015-09-24 | 0 | 0 | 0 | [20 empty] | 2015-10-09 |  | 2016-09-27 |  | EXP | [6 empty] | 2016-05-12 | 2016-05-12 | 2016-05-16 | Connected |  | No
National Grid | WESTMINSTER | 175830 | 1473 | 6 | Solar | 01_607W4 | 2015-09-18 01:00 | 2015-09-22 | 2 | 2 | 0 | 2015-09-24 | 2015-09-24 | 0 | 0 | 0 | [20 empty] | 2015-10-23 |  | 2016-09-27 |  | EXP | [6 empty] | 2015-10-23 | 2015-10-23 | 2016-05-12 | Connected |  | No
National Grid | WORCESTER | 175904 | 1606 | 10 | Solar | 01_24W3 | 2015-09-18 01:00 | 2015-10-01 | 0 | 0 | 0 | 2015-10-01 | 2015-10-01 | 0 | 0 | 0 | [20 empty] | 2015-10-13 |  | 2016-10-06 |  | EXP | [6 empty] | 2015-10-13 | 2015-10-13 | 2016-01-26 | Connected |  | No
National Grid | UXBRIDGE | 175831 | 1569 | 135 | Solar | 05_321W5 | 2015-09-21 01:00 | 2015-09-23 | 2 | 2 | 0 | 2015-09-25 | 2015-10-08 | 623 | 0 | 623 | [20 empty] | 2015-10-08 |  | 2018-06-29 |  | EXP | [6 empty] | 2016-02-12 | 2016-02-12 | 2018-08-29 | Connected |  | Yes
National Grid | SOMERSET | 175863 | 2726 | 7.6 | Solar | 05_18J5 | 2015-09-21 01:00 | 2015-09-23 | 2 | 2 | 0 | 2015-09-25 | 2015-09-25 | 0 | 0 | 0 | [20 empty] | 2015-10-23 |  | 2016-09-28 |  | EXP | [6 empty] | 2015-10-23 | 2015-10-23 | 2016-04-29 | Connected |  | No
National Grid | UXBRIDGE | 175864 | 1569 | 10 | Solar | 05_321W4 | 2015-09-22 01:00 | 2015-09-23 | 3 | 3 | 0 | 2015-09-28 | 2015-09-28 | 0 | 0 | 0 | [20 empty] | 2015-09-30 |  | 2016-09-28 |  | EXP | [6 empty] | 2015-09-22 | 2015-09-22 | 2016-03-14 | Connected |  | No
National Grid | ORANGE | 175865 | 1364 | 1000 | Solar | 09_702W3 | 2015-09-22 01:00 | 2015-09-23 | 19 | 19 | 0 | [10 empty] | 2015-10-21 | 2015-11-02 | 8 | 0 | 8 | [12 empty] | 2016-09-28 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | FOXBOROUGH | 178782 | 2035 | 2700 | Solar | 05_3432W2 | 2015-09-22 01:00 | 2015-09-22 | 1 | 1 | 0 | [10 empty] | 2015-09-23 | 2015-11-13 | 35 | 14 | 21 | [12 empty] | 2016-09-27 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | DRACUT | 175869 | 1826 | 22.8 | Solar | 14_78L1 | 2015-09-25 01:00 | 2015-09-28 | 3 | 3 | 0 | 2015-10-01 | 2015-10-01 | 0 | 0 | 0 | [20 empty] | 2015-10-02 |  | 2016-10-03 |  | EXP | [6 empty] | 2015-12-07 | 2015-12-07 | 2015-12-07 | Connected |  | No
National Grid | GLOUCESTER | 175870 | 1930 | 25 | Solar | 12_52L1 | 2015-09-25 01:00 | 2015-09-28 | 1 | 1 | 0 | 2015-09-29 | 2015-09-29 | 0 | 0 | 0 | [20 empty] | 2015-10-14 |  | 2016-10-03 |  | EXP | [6 empty] | 2016-01-29 | 2016-01-29 | 2016-02-03 | Connected |  | No
National Grid | PEPPERELL | 175871 | 1463 | 7.6 | Solar | 01_226L1 | 2015-09-25 01:00 | 2015-09-29 | 2 | 2 | 0 | 2015-10-01 | 2015-10-01 | 0 | 0 | 0 | [20 empty] | 2015-10-02 |  | 2016-10-04 |  | EXP | [6 empty] | 2015-12-02 | 2015-12-02 | 2015-12-02 | Connected |  | No
National Grid | WEBSTER | 175872 | 1570 | 56 | Solar | 01_412L4 | 2015-09-28 01:00 | 2015-09-29 | 3 | 3 | 0 | 2015-10-02 | 2015-10-02 | 0 | 0 | 0 | [20 empty] | 2015-10-08 |  | 2016-10-04 |  | EXP | [6 empty] | 2016-02-24 | 2016-02-24 | 2016-02-24 | Connected |  | No
National Grid | MILLBURY | 175902 | 1527 | 308 | Solar | 01_304W6 | 2015-09-28 01:00 | 2015-09-29 | 3 | 3 | 0 | 2015-10-02 | 2016-10-12 | 254 | 0 | 254 | 2016-01-04 | 2016-02-23 | 34 | 0 | 34 | [5 empty] | 2016-01-04 | 2016-02-23 | 34 | 0 | 34 | [6 empty] | 2015-09-28 01:00 | 2016-10-04 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SPENCER | 175903 | 1562 | 224 | Solar | 01_21W1 | 2015-09-28 01:00 | 2015-09-30 | 0 | 0 | 0 | 2015-09-30 | 2015-09-30 | 0 | 0 | 0 | [20 empty] | 2015-11-10 |  | 2016-10-05 |  | EXP |  | 2015-12-23 | 2015-12-28 | 2 | 0 | 2 | 2016-02-17 | 2016-02-17 | 2016-03-24 | Connected |  | No
National Grid | LOWELL | 175900 | 1851 | 100 | Solar | 14_16L3 | 2015-09-29 01:00 | 2015-09-29 | 0 | 0 | 0 | 2015-09-29 | 2015-09-29 | 0 | 0 | 0 | [20 empty] | 2015-10-01 |  | 2016-10-04 |  | EXP | [6 empty] | 2016-03-09 | 2016-03-09 | 2016-03-11 | Connected |  | No
National Grid | LOWELL | 175901 | 1851 | 224 | Solar | 14_2L3 | 2015-09-29 01:00 | 2015-09-29 | 0 | 0 | 0 | 2015-09-29 | 2015-09-29 | 0 | 0 | 0 | [20 empty] | 2015-10-01 |  | 2016-10-04 |  | EXP | [6 empty] | 2016-03-09 | 2016-03-09 | 2016-03-18 | Connected |  | No
National Grid | BELCHERTOWN | 175908 | 1007 | 374 | Solar | 09_527L1 | 2015-09-30 01:00 | 2015-10-05 | 8 | 8 | 0 | 2015-10-16 | 2015-10-16 | 0 | 0 | 0 | 2016-01-06 | 2016-04-08 | 64 | 0 | 64 | [5 empty] | 2016-01-06 | 2016-04-08 | 64 | 0 | 64 | [5 empty] | 2018-02-09 | 2015-10-01 01:00 | 2018-12-14 |  | EXP | [6 empty] | 2018-02-09 | 2018-02-09 | 2018-02-09 | Connected |  | No
National Grid | WESTMINSTER | 175905 | 1473 | 5.94 | Solar | 01_607W4 | 2015-10-01 01:00 | 2015-10-01 | 4 | 4 | 0 | 2015-10-07 | 2015-10-07 | 0 | 0 | 0 | [20 empty] | 2015-10-22 |  | 2016-10-06 | Yes | EXP |  | 2016-04-21 | 2016-04-21 | 0 | 0 | 0 | 2015-10-22 | 2015-10-22 | 2016-06-17 | Connected |  | No
National Grid | SOUTH GRAFTON | 176514 | 1560 | 10 | Solar | 01_304W2 | 2015-10-01 01:00 | 2015-10-05 | 1 | 1 | 0 | 2015-10-06 | 2015-10-06 | 0 | 0 | 0 | [20 empty] | 2015-10-07 | 2015-10-01 01:00 | 2016-10-10 |  | EXP | [6 empty] | 2016-04-20 | 2016-04-20 | 2016-04-27 | Connected |  | No
National Grid | BELCHERTOWN | 176515 | 1007 | 5 | Solar | 09_523L2 | 2015-10-01 01:00 | 2015-10-05 | 1 | 1 | 0 | 2015-10-06 | 2015-10-06 | 0 | 0 | 0 | [20 empty] | 2015-10-23 |  | 2016-10-10 |  | EXP |  | 2016-08-12 | 2016-09-13 | 21 | 0 | 21 | 2015-10-23 | 2015-10-23 | 2016-10-11 | Connected |  | No
National Grid | AYER | 176517 | 1432 | 80 | Solar | 01_201W2 | 2015-10-01 01:00 | 2015-10-06 | 0 | 0 | 0 | 2015-10-06 | 2015-10-06 | 0 | 0 | 0 | [20 empty] | 2015-10-08 | 2015-10-01 01:00 | 2016-10-11 |  | EXP | [6 empty] | 2015-12-29 | 2015-12-29 | 2015-12-29 | Connected |  | No
National Grid | NORTH EGREMONT | 176518 | 1252 | 1980 | Solar | 09_1109W3 | 2015-10-01 01:00 | 2015-10-06 | 0 | 0 | 0 | [10 empty] | 2015-10-06 | 2015-11-03 | 19 | 0 | 19 | [10 empty] | 2016-04-11 | 2015-10-01 01:00 | 2016-10-11 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | GREAT BARRINGTON | 176519 | 1230 | 1920 | Solar | 09_1109W3 | 2015-10-01 01:00 | 2015-10-06 | 0 | 0 | 0 | [10 empty] | 2015-10-06 | 2015-11-03 | 19 | 0 | 19 | [10 empty] | 2016-04-11 |  | 2018-08-31 | Yes | STD |  | 2016-08-09 | 2017-01-19 | 164 | 0 | 164 |  |  | 2018-08-06 | Connected |  | No
National Grid | LANCASTER | 176516 | 1523 | 10 | Solar | 01_216W4 | 2015-10-02 01:00 | 2015-10-05 | 0 | 0 | 0 | 2015-10-05 | 2015-10-05 | 0 | 0 | 0 | [20 empty] | 2015-10-07 |  | 2016-10-10 |  | EXP | [6 empty] | 2015-12-29 | 2015-12-29 | 2016-01-12 | Connected |  | No
National Grid | NORTH QUINCY | 176520 | 2171 | 768 | Solar | 07_1104 | 2015-10-05 01:00 | 2015-10-06 | 0 | 0 | 0 | [5 empty] | 2016-01-08 | 2016-02-10 | 22 | 4 | 18 | 2015-10-06 | 2015-11-04 | 20 | 0 | 20 | 2016-01-08 | 2016-02-10 | 22 | 4 | 18 | [5 empty] | 2017-10-05 | 2015-10-05 01:00 | 2017-12-01 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | STOUGHTON | 176521 | 2072 | 112 | Solar | 07_75W7 | 2015-10-05 01:00 | 2015-10-07 | 2 | 2 | 0 | 2015-10-09 | 2015-10-09 | 0 | 0 | 0 | [20 empty] | 2015-11-12 |  | 2016-10-12 | Yes | EXP |  | 2016-03-14 | 2016-04-30 | 33 | 0 | 33 | 2016-05-09 | 2016-05-09 | 2016-05-20 | Connected |  | No
National Grid | EAST LONGMEADOW | 176522 | 1028 | 250 | Solar | 09_508L4 | 2015-10-05 01:00 | 2015-10-07 | 4 | 4 | 0 | 2015-10-14 | 2015-10-14 | 0 | 0 | 0 | [20 empty] | 2015-11-10 |  | 2016-10-12 |  | EXP | [6 empty] | 2016-01-04 | 2016-01-04 | 2016-01-20 | Connected |  | No
National Grid | MILLBURY | 176551 | 1527 | 7.6 | Solar | 01_304W3 | 2015-10-05 01:00 | 2015-10-08 | 1 | 1 | 0 | 2015-10-09 | 2015-10-09 | 0 | 0 | 0 | [20 empty] | 2015-10-15 | 2015-10-05 01:00 | 2016-10-13 |  | EXP | [6 empty] | 2016-08-23 | 2016-08-23 | 2016-08-23 | Connected |  | No
National Grid | WORCESTER | 176552 | 1605 | 7.6 | Solar | 01_24W2 | 2015-10-05 01:00 | 2015-10-08 | 1 | 1 | 0 | 2015-10-09 | 2015-10-09 | 0 | 0 | 0 | [20 empty] | 2015-11-02 |  | 2016-10-13 | Yes | EXP |  | 2016-08-03 | 2016-08-31 | 20 | 0 | 20 | 2016-09-21 | 2016-09-21 | 2016-09-21 | Connected |  | No
National Grid | AYER | 176553 | 1432 | 6 | Solar | 01_201W2 | 2015-10-05 01:00 | 2015-10-08 | 1 | 1 | 0 | 2015-10-09 | 2015-10-09 | 0 | 0 | 0 | [20 empty] | 2015-10-19 |  | 2016-10-13 |  | EXP | [6 empty] | 2016-04-12 | 2016-04-12 | 2016-06-03 | Connected |  | No
National Grid | PALMER | 176554 | 1069 | 7.6 | Solar | 09_503L4 | 2015-10-05 01:00 | 2015-10-08 | 1 | 1 | 0 | 2015-10-09 | 2015-10-09 | 0 | 0 | 0 | [20 empty] | 2015-10-26 |  | 2016-10-13 |  | EXP | [6 empty] | 2016-05-09 | 2016-05-09 | 2016-05-12 | Connected |  | No
National Grid | GRAFTON | 176555 | 1519 | 10 | Solar | 01_304W1 | 2015-10-05 01:00 | 2015-10-08 | 1 | 1 | 0 | 2015-10-09 | 2017-02-17 | 336 | 0 | 336 | [20 empty] | 2015-10-15 |  | 2016-10-13 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MILFORD | 176556 | 1757 | 11.4 | Solar | 05_336W3 | 2015-10-07 01:00 | 2015-10-08 | 1 | 1 | 0 | 2015-10-09 | 2015-10-09 | 0 | 0 | 0 | [20 empty] | 2015-10-23 |  | 2016-10-13 |  | EXP | [6 empty] | 2016-03-11 | 2016-03-11 | 2016-03-17 | Connected |  | No
National Grid | LEOMINSTER | 176557 | 1453 | 6 | Solar | 01_207W6 | 2015-10-07 01:00 | 2015-10-08 | 1 | 1 | 0 | 2015-10-09 | 2015-10-09 | 0 | 0 | 0 | [20 empty] | 2015-10-23 |  | 2016-10-13 |  | EXP | [6 empty] | 2016-03-31 | 2016-03-31 | 2016-04-06 | Connected |  | No
National Grid | AVON | 176559 | 2322 | 2052 | Solar | 07_97W5 | 2015-10-08 01:00 | 2015-10-09 | 0 | 0 | 0 | [10 empty] | 2015-10-09 | 2015-11-06 | 19 | 0 | 19 | [5 empty] | 2016-02-03 | 2017-08-09 | 378 | 89 | 289 | 2016-08-25 |  | 2016-10-14 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | PEPPERELL | 176589 | 1463 | 19.75 | Solar | 01_226L2 | 2015-10-08 01:00 | 2015-10-09 | 0 | 0 | 0 | 2015-10-09 | 2015-10-09 | 0 | 0 | 0 | [20 empty] | 2015-10-19 |  | 2016-10-14 |  | EXP | [6 empty] | 2015-12-24 | 2015-12-24 | 2015-12-24 | Connected |  | No
National Grid | BRIMFIELD | 176591 | 1010 | 496 | Solar | 09_503L4 | 2015-10-08 01:00 | 2015-10-09 | 2 | 2 | 0 | [5 empty] | 2015-12-02 | 2016-03-01 | 60 | 7 | 53 | 2015-10-14 | 2015-11-10 | 19 | 0 | 19 | 2015-12-02 | 2016-03-01 | 60 | 7 | 53 | [6 empty] | 2015-10-08 01:00 | 2016-10-14 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | DUDLEY | 176592 | 1571 | 10 | Solar | 01_412L4 | 2015-10-08 01:00 | 2015-10-09 | 1 | 1 | 0 | 2015-10-13 | 2015-10-13 | 0 | 0 | 0 | [20 empty] | 2015-11-02 | 2015-10-09 01:00 | 2016-10-14 | Yes | EXP |  | 2016-08-31 | 2016-10-28 | 40 | 0 | 40 | 2015-11-02 | 2015-11-02 | 2016-11-02 | Connected |  | No
National Grid | CHARLTON | 176593 | 1507 | 496 | Solar | 01_406L1 | 2015-10-09 01:00 | 2015-10-09 | 1 | 1 | 0 | [10 empty] | 2015-10-12 | 2018-06-04 | 20 | 0 | 20 | [5 empty] | 2016-07-15 | 2018-06-04 | 44 | 5 | 39 | 2017-02-21 | 2015-10-15 01:00 | 2020-01-31 | Yes | STD |  | 2019-03-14 | 2019-12-02 | 263 | 81 | 182 |  |  | 2020-01-14 | Connected |  | No
National Grid | NORTH ANDOVER | 176627 | 1845 | 1000 | Solar | 14_56L3 | 2015-10-15 01:00 | 2015-10-15 | 6 | 6 | 0 | [10 empty] | 2015-10-23 | 2015-11-24 | 21 | 0 | 21 | [10 empty] | 2017-04-26 |  | 2019-03-22 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | HOLBROOK | 176628 | 2343 | 10 | Solar | 07_97W3 | 2015-10-15 01:00 | 2015-10-15 | 4 | 4 | 0 | 2015-10-21 | 2015-10-21 | 0 | 0 | 0 | [20 empty] | 2015-11-10 |  | 2016-10-20 |  | EXP | [6 empty] | 2016-05-04 | 2016-05-04 | 2016-08-18 | Connected |  | No
National Grid | RUTLAND | 176629 | 1543 | 6 | Solar | 01_55W1 | 2015-10-15 01:00 | 2015-10-16 | 3 | 3 | 0 | 2015-10-21 | 2015-10-21 | 0 | 0 | 0 | [20 empty] | 2015-10-26 |  | 2016-10-21 |  | EXP | [6 empty] | 2016-04-12 | 2016-04-12 | 2016-04-29 | Connected |  | No
National Grid | LOWELL | 176630 | 1854 | 10 | Solar | 14_77L1 | 2015-10-15 01:00 | 2015-10-16 | 3 | 3 | 0 | 2015-10-21 | 2015-10-21 | 0 | 0 | 0 | [20 empty] | 2015-11-10 |  | 2016-10-21 |  | EXP | [6 empty] | 2016-08-19 | 2016-08-19 | 2016-08-19 | Connected |  | No
National Grid | MARLBOROUGH | 176631 | 1752 | 75 | Solar | 05_317W1 | 2015-10-16 01:00 | 2015-10-20 | 3 | 3 | 0 | 2015-10-23 | 2016-01-20 | 58 | 0 | 58 | [22 empty] | 2016-10-25 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | STOCKBRIDGE | 176632 | 1262 | 527 | Solar | 09_1102W1 | 2015-10-16 01:00 | 2015-10-20 | 0 | 0 | 0 | [10 empty] | 2015-10-20 | 2015-11-13 | 17 | 0 | 17 | [12 empty] | 2016-10-25 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | FLORENCE | 176633 | 1062 | 528 | Solar | 09_909W4 | 2015-10-16 01:00 | 2015-10-20 | 0 | 0 | 0 | [10 empty] | 2015-10-20 | 2015-11-13 | 17 | 0 | 17 | [12 empty] | 2016-10-25 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | EAST LONGMEADOW | 176634 | 1028 | 527 | Solar | 09_139L1 | 2015-10-16 01:00 | 2015-10-20 | 0 | 0 | 0 | [10 empty] | 2015-10-20 | 2015-11-13 | 17 | 0 | 17 | [12 empty] | 2016-10-25 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 176665 | 1844 | 17.25 | Solar | 14_74L4 | 2015-10-19 01:00 | 2015-10-21 | 7 | 7 | 0 | 2015-10-30 | 2015-10-30 | 0 | 0 | 0 | [20 empty] | 2015-10-30 |  | 2016-10-26 |  | EXP | [6 empty] | 2016-08-09 | 2016-08-09 | 2016-08-09 | Connected |  | No
National Grid | BROCKTON | 176666 | 2302 | 15.48 | Solar | 07_911W56 | 2015-10-19 01:00 | 2015-10-21 | 2 | 2 | 0 | 2015-10-23 | 2015-10-23 | 0 | 0 | 0 | [20 empty] | 2015-10-26 | 2015-10-20 01:00 | 2016-10-26 |  | EXP | [6 empty] | 2016-07-27 | 2016-07-27 | 2016-08-01 | Connected |  | No
National Grid | WEBSTER | 176663 | 1570 | 1000 | Solar | 01_412L6 | 2015-10-20 01:00 | 2015-10-20 | 3 | 3 | 0 | [10 empty] | 2015-10-23 | 2015-11-24 | 21 | 0 | 21 | [10 empty] | 2017-06-19 |  | 2021-06-10 | Yes | STD |  | 2020-10-03 | 2021-02-26 | 146 | 0 | 146 |  |  | 2021-06-08 | Connected |  | No
National Grid | WEBSTER | 176664 | 1570 | 660 | Solar | 01_412L6 | 2015-10-20 01:00 | 2015-10-20 | 3 | 3 | 0 | [10 empty] | 2015-10-23 | 2015-11-24 | 21 | 0 | 21 | [10 empty] | 2017-06-19 |  | 2016-10-25 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MALDEN | 176667 | 2148 | 268.8 | Solar | 12_16J4 | 2015-10-20 01:00 | 2015-10-21 | 2 | 2 | 0 | 2015-10-23 | 2017-02-27 | 332 | 26 | 306 | [20 empty] | 2016-01-26 |  | 2016-10-26 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTH BROOKFIELD | 176669 | 1535 | 499 | Solar | 01_525L2 | 2015-10-20 01:00 | 2015-10-21 | 4 | 4 | 0 | [10 empty] | 2015-10-27 | 2015-11-23 | 18 | 0 | 18 | [10 empty] | 2016-04-28 |  | 2016-10-26 |  | STD |  | 2017-08-22 | 2017-11-14 | 52 | 0 | 52 |  |  |  | Withdrawn |  | No
National Grid | SHEFFIELD | 176670 | 1257 | 875 | Solar | 09_1108W1 | 2015-10-22 01:00 | 2015-10-22 | 6 | 6 | 0 | [10 empty] | 2015-10-30 | 2015-11-23 | 15 | 0 | 15 | [5 empty] | 2017-04-27 | 2017-09-18 | 99 | 0 | 99 |  |  | 2016-10-27 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BRIDGEWATER | 176671 | 2324 | 499 | Solar | 07_797W1 | 2015-10-22 01:00 | 2015-10-23 | 2 | 2 | 0 | 2015-10-27 | 2016-05-03 | 127 | 0 | 127 | [21 empty] | 2015-10-23 01:00 | 2016-10-28 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | GREAT BARRINGTON | 176672 | 1230 | 1000 | Solar | 09_1109W3 | 2015-10-23 01:00 | 2015-10-26 | 4 | 4 | 0 | [10 empty] | 2015-10-30 | 2015-11-30 | 19 | 0 | 19 | [10 empty] | 2016-04-11 |  | 2017-11-16 | Yes | STD |  | 2017-02-21 | 2017-10-31 | 174 | 0 | 174 | 2017-11-08 | 2017-11-08 | 2017-11-08 | Connected |  | No
National Grid | DIGHTON | 176701 | 2715 | 12 | Solar | 05_19W72 | 2015-10-26 01:00 | 2015-10-26 | 9 | 9 | 0 | 2015-11-06 | 2015-11-06 | 0 | 0 | 0 | [20 empty] | 2015-11-09 | 2015-10-27 01:00 | 2016-10-31 |  | EXP | [6 empty] | 2016-03-14 | 2016-03-14 | 2016-03-17 | Connected |  | No
National Grid | WORCESTER | 176705 | 1605 | 6 | Solar | 01_27W4 | 2015-10-27 01:00 | 2015-10-28 | 2 | 2 | 0 | 2015-10-30 | 2017-04-26 | 368 | 0 | 368 | [20 empty] | 2015-11-10 | 2015-10-27 01:00 | 2016-11-02 | Yes | EXP |  | 2016-05-19 | 2016-06-01 | 8 | 0 | 8 |  |  |  | Withdrawn |  | Yes
National Grid | LOWELL | 176706 | 1854 | 6.8 | Solar | 14_21L3 | 2015-10-27 01:00 | 2015-10-28 | 2 | 2 | 0 | 2015-10-30 | 2015-10-30 | 0 | 0 | 0 | [20 empty] | 2015-11-17 |  | 2016-11-02 | Yes | EXP |  | 2016-05-11 | 2016-05-26 | 11 | 0 | 11 | 2015-11-17 | 2015-11-17 | 2016-10-25 | Connected |  | No
National Grid | LOWELL | 176707 | 1852 | 3.8 | Solar | 14_70L3 | 2015-10-27 01:00 | 2015-10-28 | 2 | 2 | 0 | 2015-10-30 | 2015-10-30 | 0 | 0 | 0 | [20 empty] | 2015-11-05 | 2015-10-27 01:00 | 2016-11-02 |  | EXP | [6 empty] | 2016-04-27 | 2016-04-27 | 2016-07-26 | Connected |  | No
National Grid | SAUGUS | 176708 | 1906 | 10 | Solar | 12_25W1 | 2015-10-27 01:00 | 2015-10-29 | 1 | 1 | 0 | 2015-10-30 | 2015-10-30 | 0 | 0 | 0 | [20 empty] | 2015-11-25 | 2015-10-28 01:00 | 2016-11-03 | Yes | EXP |  | 2016-09-21 | 2016-10-11 | 13 | 0 | 13 | 2015-11-25 | 2015-11-25 | 2016-10-26 | Connected |  | No
National Grid | HAMPDEN | 176704 | 1036 | 499 | Solar | 09_139L3 | 2015-10-28 01:00 | 2015-10-28 | 0 | 0 | 0 | 2015-10-28 | 2015-10-28 | 0 | 0 | 0 | [20 empty] | 2015-12-24 |  | 2016-11-02 | Yes | EXP |  | 2016-12-30 | 2017-02-14 | 30 | 0 | 30 | 2017-03-21 | 2017-03-21 | 2017-03-30 | Connected |  | No
National Grid | DRACUT | 176709 | 1826 | 3.8 | Solar | 14_78L9 | 2015-10-28 01:00 | 2015-10-29 | 3 | 3 | 0 | 2015-11-03 | 2017-04-26 | 366 | 0 | 366 | [20 empty] | 2015-11-24 |  | 2016-11-03 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTMINSTER | 176737 | 1473 | 496 | Solar | 01_609W2 | 2015-10-29 01:00 | 2015-10-29 | 3 | 3 | 0 | [10 empty] | 2015-11-03 | 2015-12-04 | 21 | 0 | 21 | [10 empty] | 2016-08-04 |  | 2016-11-03 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LEOMINSTER | 176738 | 1453 | 900 | Solar | 01_219W2 | 2015-10-29 01:00 | 2015-10-30 | 0 | 0 | 0 | [10 empty] | 2015-10-30 | 2015-12-01 | 20 | 0 | 20 | [12 empty] | 2016-11-04 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | UPTON | 176739 | 1568 | 3 | Solar | 05_320W1 | 2015-10-29 01:00 | 2015-11-02 | 2 | 2 | 0 | 2015-11-04 | 2016-12-14 | 275 | 0 | 275 | [20 empty] | 2015-11-17 |  | 2016-11-07 |  | EXP | [6 empty] | 2015-11-17 | 2015-11-17 |  | Withdrawn |  | No
National Grid | LOWELL | 176741 | 1851 | 150 | Solar | 14_2L3 | 2015-10-30 01:00 | 2015-11-02 | 4 | 4 | 0 | 2015-11-06 | 2017-07-24 | 424 | 56 | 368 | [20 empty] | 2016-02-03 | 2015-10-30 01:00 | 2017-09-07 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LOWELL | 176838 | 1851 | 150 | Solar | 14_2L3 | 2015-10-30 01:00 | 2015-11-02 | 4 | 0 | 4 | 2015-11-06 | 2017-02-10 | 312 | 56 | 256 | [20 empty] | 2016-02-03 |  | 2016-11-07 | Yes | EXP | [9 empty] | Withdrawn |  | No
National Grid | LOWELL | 178013 | 1851 | 150 | Solar | 14_2L3 | 2015-10-30 01:00 | 2015-11-02 | 4 | 0 | 4 | 2015-11-06 | 2015-11-06 | 0 | 0 | 0 | [20 empty] | 2016-02-03 |  | 2018-07-04 |  | EXP | [6 empty] | 2017-07-18 | 2017-07-18 | 2017-07-16 | Connected |  | No
National Grid | HUBBARDSTON | 176743 | 1452 | 2200 | Solar | 01_609W1 | 2015-11-02 | 2015-11-03 | 1 | 1 | 0 | [10 empty] | 2015-11-04 | 2015-12-04 | 20 | 0 | 20 | [12 empty] | 2016-11-08 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HUBBARDSTON | 176744 | 1452 | 2000 | Solar | 01_609W1 | 2015-11-02 | 2015-11-03 | 1 | 1 | 0 | [10 empty] | 2015-11-04 | 2015-12-04 | 20 | 0 | 20 | [12 empty] | 2016-11-08 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTBOROUGH | 176745 | 1581 | 50.4 | Solar | 05_312W4 | 2015-11-02 | 2015-11-03 | 3 | 3 | 0 | 2015-11-06 | 2015-11-06 | 0 | 0 | 0 | [20 empty] | 2015-11-12 | 2015-11-02 | 2016-11-08 |  | EXP | [6 empty] | 2017-01-04 | 2017-01-04 | 2017-01-06 | Connected |  | No
National Grid | GARDNER | 176746 | 1440 | 10 | Solar | 01_607W5 | 2015-11-02 | 2015-11-03 | 3 | 3 | 0 | 2015-11-06 | 2015-11-06 | 0 | 0 | 0 | [20 empty] | 2015-11-25 |  | 2016-11-08 | Yes | EXP |  | 2016-06-06 | 2016-06-21 | 10 | 0 | 10 | 2015-11-25 | 2015-11-25 | 2016-09-28 | Connected |  | No
National Grid | ATHOL | 176742 | 1331 | 1100 | Solar | 09_702W2 | 2015-11-03 | 2015-11-03 | 0 | 0 | 0 | [10 empty] | 2015-11-03 | 2015-12-04 | 21 | 0 | 21 | [12 empty] | 2016-11-08 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 176774 | 2302 | 6 | Solar | 07_911W56 | 2015-11-03 | 2015-11-04 | 0 | 0 | 0 | 2015-11-04 | 2015-11-04 | 0 | 0 | 0 | [20 empty] | 2015-11-05 |  | 2016-11-09 |  | EXP | [6 empty] | 2016-05-06 | 2016-05-06 | 2016-05-12 | Connected |  | No
National Grid | AMESBURY | 176775 | 1913 | 2800 | Solar | 14_275L4 | 2015-11-03 | 2015-11-04 | 53 | 53 | 0 | [10 empty] | 2016-01-25 | 2016-02-04 | 8 | 0 | 8 | [11 empty] | 2015-11-04 | 2016-11-09 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | CHELMSFORD | 176776 | 1824 | 390 | Solar | 14_2L1 | 2015-11-04 | 2015-11-04 | 0 | 0 | 0 | 2015-11-04 | 2015-12-05 | 0 | 0 | 0 | 2016-02-15 | 2016-02-24 | 0 | 0 | 0 | [5 empty] | 2016-02-15 | 2016-02-24 | 0 | 0 | 0 | [5 empty] | 2016-02-24 |  | 2019-06-14 |  | EXP |  | 2017-07-11 | 2017-08-23 | 0 | 0 | 0 |  |  | 2019-06-12 | Connected |  | No
National Grid | LYNN | 176777 | 1904 | 8.5 | Solar | 12_24W1 | 2015-11-04 | 2015-11-04 | 3 | 3 | 0 | 2015-11-09 | 2015-11-09 | 0 | 0 | 0 | [20 empty] | 2015-11-10 |  | 2016-11-09 |  | EXP | [6 empty] | 2016-02-16 | 2016-02-16 | 2017-01-10 | Connected |  | No
National Grid | MARLBOROUGH | 176778 | 1752 | 576 | Solar | 05_310W3 | 2015-11-04 | 2015-11-04 | 2 | 2 | 0 | [10 empty] | 2015-11-06 | 2015-12-09 | 21 | 0 | 21 | [12 empty] | 2016-11-09 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 176779 | 1606 | 7.6 | Solar | 01_24W3 | 2015-11-04 | 2015-11-05 | 0 | 0 | 0 | [27 empty] | 2016-11-10 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 176780 | 1606 | 7.6 | Solar | 01_24W3 | 2015-11-04 | 2015-11-05 | 2 | 2 | 0 | 2015-11-09 | 2015-11-09 | 0 | 0 | 0 | [20 empty] | 2015-11-25 |  | 2016-11-10 |  | EXP | [6 empty] | 2015-11-25 | 2015-11-25 | 2016-05-25 | Connected |  | No
National Grid | ATHOL | 176781 | 1331 | 2000 | Solar | 09_702W2 | 2015-11-05 | 2015-11-05 | 2 | 2 | 0 | [10 empty] | 2015-11-09 | 2015-12-04 | 17 | 0 | 17 | [12 empty] | 2016-11-10 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BARRE | 176782 | 1005 | 2000 | Solar | 09_604W1 | 2015-11-05 | 2015-11-05 | 3 | 3 | 0 | [10 empty] | 2015-11-10 | 2015-12-10 | 20 | 0 | 20 | [12 empty] | 2016-11-10 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH BROOKFIELD | 176783 | 1535 | 2000 | Solar | 09_604W3 | 2015-11-05 | 2015-11-05 | 3 | 3 | 0 | [10 empty] | 2015-11-10 | 2015-12-09 | 19 | 0 | 19 | [12 empty] | 2016-11-10 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH BROOKFIELD | 176811 | 1535 | 2000 | Solar | 01_525L2 | 2015-11-05 | 2015-11-05 | 2 | 2 | 0 | [10 empty] | 2015-11-09 | 2015-12-08 | 19 | 0 | 19 | [12 empty] | 2016-11-10 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BARRE | 176812 | 1005 | 1000 | Solar | 09_604W3 | 2015-11-05 | 2015-11-05 | 3 | 3 | 0 | [10 empty] | 2015-11-10 | 2015-12-10 | 20 | 0 | 20 | [12 empty] | 2016-11-10 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTMINSTER | 176813 | 1473 | 2000 | Solar | 01_602W3 | 2015-11-05 | 2015-11-05 | 2 | 2 | 0 | [10 empty] | 2015-11-09 | 2015-12-07 | 18 | 0 | 18 | [11 empty] | 2015-11-05 | 2016-11-10 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HALIFAX | 176814 | 2338 | 6.75 | Solar | 07_912W75 | 2015-11-05 | 2015-11-05 | 15 | 15 | 0 | 2015-11-30 | 2017-12-14 | 504 | 1 | 503 | [20 empty] | 2015-12-15 |  | 2016-11-10 |  | EXP | [6 empty] | 2015-12-15 | 2015-12-15 |  | Withdrawn |  | Yes
National Grid | WESTMINSTER | 176815 | 1473 | 2200 | Solar | 01_602W3 | 2015-11-05 | 2015-11-06 | 2 | 2 | 0 | [10 empty] | 2015-11-10 | 2015-12-28 | 31 | 0 | 31 | [12 empty] | 2016-11-11 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTMINSTER | 176816 | 1473 | 2200 | Solar | 01_602W3 | 2015-11-05 | 2015-11-06 | 2 | 2 | 0 | [10 empty] | 2015-11-10 | 2015-12-28 | 31 | 0 | 31 | [12 empty] | 2016-11-11 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTON | 176818 | 2766 | 10 | Solar | 05_4L2 | 2015-11-05 | 2015-11-06 | 13 | 13 | 0 | 2015-11-27 | 2015-11-27 | 0 | 0 | 0 | [20 empty] | 2015-11-30 |  | 2016-11-11 |  | EXP | [6 empty] | 2016-05-11 | 2016-05-11 | 2016-05-16 | Connected |  | No
National Grid | PALMER | 176817 | 1069 | 990 | Solar | 09_503L4 | 2015-11-06 | 2015-11-06 | 0 | 0 | 0 | [10 empty] | 2015-11-06 | 2015-12-08 | 20 | 0 | 20 | [11 empty] | 2015-11-06 | 2016-11-11 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | UPTON | 176819 | 1568 | 299.7 | Solar | 05_335W3 | 2015-11-06 | 2015-11-09 | 0 | 0 | 0 | 2015-11-09 | 2015-11-09 | 0 | 0 | 0 | 2016-02-23 | 2016-03-25 | 22 | 1 | 21 | [5 empty] | 2016-02-23 | 2016-03-25 | 22 | 1 | 21 | [5 empty] | 2016-05-17 |  | 2017-04-06 | Yes | EXP |  | 2016-10-06 | 2017-04-05 | 122 | 0 | 122 | 2017-03-21 | 2017-03-21 | 2017-05-03 | Connected |  | No
National Grid | WESTMINSTER | 176848 | 1473 | 480 | Solar | 01_602W3 | 2015-11-09 | 2015-11-09 | 1 | 1 | 0 | 2015-11-10 | 2016-03-29 | 93 | 0 | 93 | [22 empty] | 2016-11-14 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SOUTH EASTON | 176849 | 2375 | 996 | Solar | 07_92W79 | 2015-11-09 | 2015-11-10 | 2 | 2 | 0 | [10 empty] | 2015-11-13 | 2015-12-14 | 20 | 0 | 20 | [12 empty] | 2016-11-15 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MONSON | 176850 | 1057 | 972 | Solar | 09_503L2 | 2015-11-09 | 2015-11-10 | 0 | 0 | 0 | [10 empty] | 2015-11-10 | 2015-12-11 | 21 | 0 | 21 | [11 empty] | 2015-11-11 | 2019-02-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WEBSTER | 176851 | 1570 | 45.6 | Solar | 01_412L2 | 2015-11-11 | 2015-11-13 | 3 | 3 | 0 | 2015-11-18 | 2015-11-18 | 0 | 0 | 0 | [20 empty] | 2015-12-04 |  | 2016-11-18 | Yes | EXP |  | 2016-05-11 | 2016-07-13 | 42 | 0 | 42 | 2015-12-04 | 2015-12-04 | 2016-08-23 | Connected |  | No
National Grid | WESTBOROUGH | 176852 | 1581 | 60.42 | Solar | 05_312W5 | 2015-11-11 | 2015-11-13 | 1 | 1 | 0 | 2015-11-16 | 2016-12-13 | 267 | 0 | 267 | [20 empty] | 2015-11-17 |  | 2016-11-18 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HAVERHILL | 176413 | 1835 | 92.4 | Solar | 14_43L8 | 2015-11-12 | 2015-11-13 | 5 | 0 | 5 | 2015-11-20 | 2015-11-20 | 0 | 0 | 0 | [20 empty] | 2015-11-20 |  | 2016-11-18 |  | EXP | [6 empty] | 2016-03-03 | 2016-03-03 | 2016-03-03 | Connected |  | No
National Grid | REHOBOTH | 176853 | 2769 | 1000 | Solar | 05_7L5 | 2015-11-12 | 2015-11-13 | 1 | 1 | 0 | [10 empty] | 2015-11-16 | 2015-12-16 | 21 | 0 | 21 | [11 empty] | 2015-11-12 | 2016-11-18 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HAVERHILL | 176854 | 1835 | 92.4 | Solar | 14_43L8 | 2015-11-12 | 2015-11-13 | 5 | 5 | 0 | 2015-11-20 | 2015-12-03 | 8 | 0 | 8 | [20 empty] | 2015-11-20 |  | 2016-11-18 | Yes | EXP | [9 empty] | Withdrawn |  | No
National Grid | SEEKONK | 176855 | 2771 | 10 | Solar | 05_7L1 | 2015-11-12 | 2015-11-13 | 3 | 3 | 0 | 2015-11-18 | 2015-11-18 | 0 | 0 | 0 | [20 empty] | 2015-11-23 |  | 2016-11-18 |  | EXP | [6 empty] | 2016-05-18 | 2016-05-18 | 2016-05-27 | Connected |  | No
National Grid | WORCESTER | 176856 | 1605 | 9 | Solar | 01_24W2 | 2015-11-12 | 2015-11-13 | 3 | 3 | 0 | 2015-11-18 | 2015-11-18 | 0 | 0 | 0 | [20 empty] | 2015-11-18 | 2015-11-12 | 2016-11-18 |  | EXP | [6 empty] | 2016-05-06 | 2016-05-06 | 2016-05-17 | Connected |  | No
National Grid | CHARLTON | 176885 | 1507 | 11.4 | Solar | 01_406L1 | 2015-11-12 | 2015-11-13 | 89 | 89 | 0 | 2016-03-25 | 2016-03-25 | 0 | 0 | 0 | [20 empty] | 2016-04-12 |  | 2016-11-18 | Yes | EXP |  | 2016-11-09 | 2016-11-16 | 4 | 0 | 4 | 2017-02-07 | 2017-02-07 | 2017-02-07 | Connected |  | No
National Grid | BARRE | 176886 | 1005 | 17.25 | Solar | 09_604W1 | 2015-11-12 | 2015-11-13 | 3 | 3 | 0 | 2015-11-18 | 2017-01-13 | 286 | 0 | 286 | [20 empty] | 2015-11-18 |  | 2016-11-18 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEOMINSTER | 176887 | 1453 | 10 | Solar | 01_225W4 | 2015-11-12 | 2015-11-13 | 3 | 3 | 0 | 2015-11-18 | 2016-08-19 | 187 | 0 | 187 | [20 empty] | 2015-12-04 |  | 2016-11-18 |  | EXP | [6 empty] | 2015-12-04 | 2015-12-04 |  | Withdrawn |  | No
National Grid | BROCKTON | 176888 | 2302 | 11.55 | Solar | 07_91W40 | 2015-11-12 | 2015-11-13 | 3 | 3 | 0 | 2015-11-18 | 2016-11-22 | 251 | 0 | 251 | [20 empty] | 2015-12-04 |  | 2016-11-18 |  | EXP | [6 empty] | 2015-12-04 | 2015-12-04 |  | Withdrawn |  | Yes
National Grid | CLINTON | 176889 | 1510 | 6.45 | Solar | 01_216W3 | 2015-11-12 | 2015-11-13 | 3 | 3 | 0 | 2015-11-18 | 2015-11-18 | 0 | 0 | 0 | [20 empty] | 2015-11-19 | 2015-11-12 | 2016-11-18 |  | EXP | [6 empty] | 2016-07-26 | 2016-07-26 | 2016-07-26 | Connected |  | No
National Grid | FALL RIVER | 176921 | 2720 | 996 | Solar | 05_115W52 | 2015-11-12 | 2015-11-19 | 2 | 2 | 0 | [10 empty] | 2015-11-23 | 2015-12-14 | 14 | 0 | 14 | [10 empty] | 2016-07-26 | 2015-11-12 | 2017-12-30 | Yes | STD |  | 2017-04-14 | 2017-12-27 | 170 | 0 | 170 | 2017-12-29 | 2017-12-29 | 2017-12-30 | Connected |  | No
National Grid | FALL RIVER | 176922 | 2720 | 996 | Solar | 05_115W52 | 2015-11-12 | 2015-11-19 | 2 | 2 | 0 | [10 empty] | 2015-11-23 | 2015-12-14 | 14 | 0 | 14 | [10 empty] | 2016-07-26 |  | 2017-12-30 |  | STD |  | 2017-04-14 | 2017-12-27 | 170 | 0 | 170 | 2017-12-29 | 2017-12-29 | 2017-12-30 | Connected |  | No
National Grid | MARLBOROUGH | 176890 | 1752 | 54 | Solar | 05_310W6 | 2015-11-13 | 2015-11-16 | 24 | 24 | 0 | 2015-12-21 | 2015-12-21 | 0 | 0 | 0 | [20 empty] | 2016-01-05 |  | 2016-11-21 |  | EXP | [6 empty] | 2017-01-03 | 2017-01-03 | 2017-01-03 | Connected |  | No
National Grid | PALMER | 176892 | 1069 | 2000 | Solar | 09_503L1 | 2015-11-16 | 2015-11-16 | 2 | 2 | 0 | [10 empty] | 2015-11-18 | 2015-12-21 | 22 | 0 | 22 | [11 empty] | 2015-11-16 | 2016-11-21 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WINCHENDON | 176920 | 1475 | 3100 | Solar | 01_612W1 | 2015-11-16 | 2015-11-17 | 5 | 5 | 0 | [10 empty] | 2015-11-24 | 2015-12-28 | 22 | 0 | 22 | [5 empty] | 2017-04-12 | 2018-05-15 | 275 | 0 | 275 | 2016-08-25 |  | 2018-10-22 | Yes | STD |  | 2018-05-02 | 2018-07-05 | 64 | 0 | 64 |  |  | 2018-09-25 | Connected |  | No
National Grid | BELCHERTOWN | 176923 | 1007 | 10.32 | Solar | 09_523L2 | 2015-11-18 | 2015-11-19 | 3 | 3 | 0 | 2015-11-24 | 2016-03-01 | 65 | 0 | 65 | [20 empty] | 2015-12-14 |  | 2016-11-24 |  | EXP | [6 empty] | 2015-12-14 | 2015-12-14 |  | Withdrawn |  | No
National Grid | NORTHBOROUGH | 176924 | 1532 | 28 | Solar | 05_313W1 | 2015-11-19 | 2015-11-19 | 3 | 3 | 0 | 2015-11-24 | 2015-11-24 | 0 | 0 | 0 | [20 empty] | 2015-11-30 |  | 2016-11-24 |  | EXP | [6 empty] | 2016-05-26 | 2016-05-26 | 2016-07-06 | Connected |  | Yes
National Grid | BLACKSTONE | 176377 | 1504 | 792 | Solar | 05_321W6 | 2015-11-20 | 2015-11-23 | 1 | 1 | 0 | [10 empty] | 2015-11-24 | 2015-12-14 | 13 | 1 | 12 | [12 empty] | 2016-11-28 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MILLBURY | 176378 | 1527 | 16 | Solar | 01_304W5 | 2015-11-20 | 2015-11-23 | 1 | 1 | 0 | 2015-11-24 | 2015-11-24 | 0 | 0 | 0 | [20 empty] | 2015-12-01 | 2015-11-20 | 2016-11-28 |  | EXP | [6 empty] | 2016-03-02 | 2016-03-02 | 2016-03-09 | Connected |  | No
National Grid | LEOMINSTER | 176925 | 1453 | 500 | Solar | 01_219W5 | 2015-11-20 | 2015-11-20 | 11 | 11 | 0 | [10 empty] | 2015-12-08 | 2016-01-06 | 19 | 0 | 19 | [5 empty] | 2016-08-02 | 2016-08-02 | 0 | 0 | 0 | 2016-08-02 |  | 2018-04-27 | Yes | STD |  | 2017-10-23 | 2018-03-02 | 83 | 0 | 83 | 2018-04-11 | 2018-04-11 | 2018-04-27 | Connected |  | No
National Grid | LOWELL | 176926 | 1854 | 10 | Solar | 14_21L3 | 2015-11-20 | 2015-11-20 | 2 | 2 | 0 | 2015-11-24 | 2015-11-24 | 0 | 0 | 0 | [20 empty] | 2015-12-14 |  | 2016-11-25 |  | EXP | [6 empty] | 2015-12-14 | 2015-12-14 | 2016-09-14 | Connected |  | No
National Grid | TEWKSBURY | 176927 | 1876 | 7.6 | Solar | 14_59L3 | 2015-11-20 | 2015-11-20 | 2 | 2 | 0 | 2015-11-24 | 2015-11-24 | 0 | 0 | 0 | [20 empty] | 2015-11-30 |  | 2016-11-25 |  | EXP | [6 empty] | 2016-05-19 | 2016-05-19 | 2016-05-23 | Connected |  | No
National Grid | WESTBOROUGH | 176928 | 1581 | 32.4 | Solar | 05_314W4 | 2015-11-20 | 2015-11-20 | 16 | 16 | 0 | 2015-12-15 | 2015-12-15 | 0 | 0 | 0 | [20 empty] | 2015-12-15 |  | 2016-11-25 |  | EXP | [6 empty] | 2017-01-03 | 2017-01-03 | 2017-01-11 | Connected |  | No
National Grid | LYNN | 176380 | 1905 | 1520 | Solar | 12_7J901 | 2015-11-23 | 2015-11-24 | 1 | 1 | 0 | [10 empty] | 2015-11-25 | 2015-12-18 | 16 | 0 | 16 | [10 empty] | 2016-03-23 | 2015-11-24 | 2016-11-29 |  | STD | [6 empty] | 2016-12-06 | 2016-12-06 | 2016-12-12 | Connected |  | Yes
National Grid | GREAT BARRINGTON | 176379 | 1230 | 275 | Solar | 09_1109W2 | 2015-11-24 | 2015-11-24 | 0 | 0 | 0 | 2015-11-24 | 2015-11-24 | 0 | 0 | 0 | 2016-03-28 | 2016-05-10 | 30 | 0 | 30 | [5 empty] | 2016-03-28 | 2016-05-10 | 30 | 0 | 30 | [5 empty] | 2016-05-24 |  | 2017-12-29 | Yes | EXP |  | 2017-02-22 | 2017-09-08 | 138 | 0 | 138 | 2017-11-17 | 2017-11-17 | 2017-11-16 | Connected |  | No
National Grid | FOXBOROUGH | 178787 | 2035 | 325 | Solar | 05_3424W5 | 2015-11-24 | 2015-11-24 | 2 | 2 | 0 | [10 empty] | 2015-11-27 | 2015-12-17 | 14 | 0 | 14 | [12 empty] | 2016-11-29 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | WEST BRIDGEWATER | 176382 | 2379 | 496 | Solar | 07_98W44 | 2015-11-25 | 2015-11-25 | 3 | 3 | 0 | 2015-12-01 | 2016-11-29 | 247 | 0 | 247 | [22 empty] | 2016-11-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | RUTLAND | 176383 | 1543 | 28 | Solar | 01_55W1 | 2015-11-25 | 2015-11-25 | 8 | 8 | 0 | 2015-12-08 | 2018-01-04 | 511 | 72 | 439 | [20 empty] | 2016-04-05 |  | 2018-06-29 |  | EXP | [8 empty] | 2018-08-30 | Connected |  | No
National Grid | BILLERICA | 176414 | 1821 | 480 | Solar | 14_18L1 | 2015-11-30 | 2015-12-03 | 0 | 0 | 0 | 2015-12-03 | 2015-12-03 | 25 | 25 | 0 | [20 empty] | 2016-05-03 |  | 2018-06-28 |  | EXP | [8 empty] | 2018-06-22 | Connected |  | No
National Grid | MARLBOROUGH | 176385 | 1752 | 480 | Solar | 05_313W2 | 2015-12-01 | 2015-12-02 | 6 | 6 | 0 | [10 empty] | 2015-12-10 | 2015-12-18 | 6 | 0 | 6 | [10 empty] | 2016-09-09 |  | 2017-08-01 |  | STD | [6 empty] | 2017-06-21 | 2017-06-21 | 2017-07-06 | Connected |  | No
National Grid | BELLINGHAM | 176417 | 2019 | 10 | Solar | 05_108W60 | 2015-12-02 | 2015-12-03 | 3 | 3 | 0 | 2015-12-08 | 2015-12-08 | 0 | 0 | 0 | [20 empty] | 2015-12-15 |  | 2016-12-08 |  | EXP | [6 empty] | 2015-12-15 | 2015-12-15 | 2016-06-06 | Connected |  | No
National Grid | ROCKLAND | 176418 | 2370 | 86.4 | Solar | 07_64J1 | 2015-12-03 | 2015-12-03 | 3 | 3 | 0 | 2015-12-08 | 2015-12-08 | 0 | 0 | 0 | [20 empty] | 2015-12-09 |  | 2016-12-08 |  | EXP | [6 empty] | 2017-01-03 | 2017-01-03 | 2017-01-03 | Connected |  | No
National Grid | OXFORD | 176419 | 1540 | 1250 | Solar | 01_406L4 | 2015-12-07 | 2015-12-08 | 0 | 0 | 0 | [10 empty] | 2015-12-08 | 2016-01-07 | 20 | 0 | 20 | [12 empty] | 2016-12-13 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LOWELL | 176420 | 1854 | 6 | Solar | 14_21L3 | 2015-12-07 | 2015-12-08 | 2 | 2 | 0 | 2015-12-10 | 2015-12-10 | 0 | 0 | 0 | [20 empty] | 2015-12-14 |  | 2016-12-13 |  | EXP | [6 empty] | 2016-05-10 | 2016-05-10 | 2016-06-02 | Connected |  | No
National Grid | NORTH ANDOVER | 176421 | 1845 | 25 | Solar | 14_7J3 | 2015-12-08 | 2015-12-08 | 0 | 0 | 0 | 2015-12-08 | 2015-12-08 | 0 | 0 | 0 | [20 empty] | 2015-12-11 |  | 2016-12-13 |  | EXP | [6 empty] | 2016-02-29 | 2016-02-29 | 2016-03-28 | Connected |  | No
National Grid | NORTH ANDOVER | 176450 | 1845 | 27 | Solar | 14_7J3 | 2015-12-08 | 2015-12-08 | 0 | 0 | 0 | 2015-12-08 | 2015-12-08 | 0 | 0 | 0 | [20 empty] | 2015-12-11 |  | 2016-12-13 |  | EXP | [6 empty] | 2016-03-28 | 2016-03-28 | 2016-03-01 | Connected |  | No
National Grid | AMESBURY | 176451 | 1913 | 52.8 | Solar | 14_5J11 | 2015-12-08 | 2015-12-08 | 7 | 7 | 0 | 2015-12-17 | 2016-06-15 | 122 | 0 | 122 | [21 empty] | 2015-12-08 | 2016-12-13 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WALES | 176453 | 1081 | 2000 | Solar | 09_516L1 | 2015-12-08 | 2015-12-08 | 2 | 2 | 0 | [10 empty] | 2015-12-10 | 2016-01-12 | 21 | 0 | 21 | [10 empty] | 2017-05-05 |  | 2020-08-14 | Yes | STD |  | 2019-06-08 | 2019-12-20 | 195 | 0 | 195 |  |  | 2020-08-26 | Connected |  | No
National Grid | FALL RIVER | 176454 | 2720 | 3 | Solar | 05_28W51 | 2015-12-08 | 2015-12-09 | 4 | 4 | 0 | 2015-12-15 | 2015-12-15 | 0 | 0 | 0 | [20 empty] | 2015-12-15 | 2015-12-08 | 2016-12-14 |  | EXP | [6 empty] | 2016-09-09 | 2016-09-09 | 2016-09-13 | Connected |  | No
National Grid | REHOBOTH | 176455 | 2769 | 7.6 | Solar | 05_8L4 | 2015-12-08 | 2015-12-09 | 4 | 4 | 0 | 2015-12-15 | 2015-12-15 | 0 | 0 | 0 | [20 empty] | 2015-12-24 |  | 2016-12-14 | Yes | EXP |  | 2016-10-05 | 2016-10-11 | 3 | 0 | 3 | 2016-11-01 | 2016-11-01 | 2016-11-08 | Connected |  | No
National Grid | CHELMSFORD | 176456 | 1824 | 7.6 | Solar | 14_24L1 | 2015-12-08 | 2015-12-09 | 4 | 4 | 0 | 2015-12-15 | 2015-12-15 | 0 | 0 | 0 | [20 empty] | 2016-01-07 |  | 2016-12-14 |  | EXP | [6 empty] | 2016-06-10 | 2016-06-10 | 2016-06-16 | Connected |  | No
National Grid | MONSON | 176457 | 1057 | 7.6 | Solar | 09_503L2 | 2015-12-08 | 2015-12-09 | 4 | 4 | 0 | 2015-12-15 | 2015-12-15 | 0 | 0 | 0 | [20 empty] | 2015-12-24 |  | 2016-12-14 |  | EXP | [6 empty] | 2016-06-10 | 2016-06-10 | 2016-06-21 | Connected |  | No
National Grid | OXFORD | 176458 | 1540 | 6 | Solar | 01_406L4 | 2015-12-08 | 2015-12-09 | 4 | 4 | 0 | 2015-12-15 | 2015-12-15 | 0 | 0 | 0 | [20 empty] | 2015-12-24 |  | 2016-12-14 |  | EXP | [6 empty] | 2016-05-09 | 2016-05-09 | 2016-05-10 | Connected |  | No
National Grid | OXFORD | 176487 | 1540 | 3000 | Natural Gas | 01_412L3 | 2015-12-08 | 2015-12-09 | 1 | 1 | 0 | [10 empty] | 2015-12-10 | 2016-01-11 | 20 | 0 | 20 | [5 empty] | 2016-05-23 | 2016-06-23 | 21 | 0 | 21 | 2016-11-07 | 2015-12-08 | 2019-01-31 |  | STD | [8 empty] | 2019-01-19 | Connected |  | Yes
National Grid | OXFORD | 176490 | 1540 | 4000.002 | Solar | 01_406L4 | 2015-12-08 | 2015-12-10 | 0 | 0 | 0 | [10 empty] | 2015-12-10 | 2016-01-05 | 16 | 0 | 16 | [10 empty] | 2017-05-01 |  | 2020-02-14 | Yes | STD |  | 2019-10-16 | 2020-01-14 | 90 | 0 | 90 |  |  | 2020-02-13 | Connected |  | No
National Grid | OXFORD | 176491 | 1540 | 2000 | Solar | 01_406L4 | 2015-12-08 | 2015-12-10 | 0 | 0 | 0 | [10 empty] | 2015-12-10 | 2016-01-05 | 16 | 0 | 16 | [10 empty] | 2017-05-01 |  | 2016-12-15 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LYNN | 176486 | 1902 | 5 | Solar | 12_1384 | 2015-12-09 | 2015-12-09 | 4 | 4 | 0 | 2015-12-15 | 2016-01-21 | 24 | 0 | 24 | [22 empty] | 2016-12-14 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | EAST LONGMEADOW | 176488 | 1028 | 7.6 | Solar | 09_139L5 | 2015-12-09 | 2015-12-09 | 4 | 4 | 0 | 2015-12-15 | 2015-12-15 | 0 | 0 | 0 | [20 empty] | 2015-12-16 |  | 2016-12-14 |  | EXP | [6 empty] | 2016-08-11 | 2016-08-11 | 2016-08-11 | Connected |  | No
National Grid | SOUTH GRAFTON | 176489 | 1560 | 7.6 | Solar | 01_304W2 | 2015-12-09 | 2015-12-09 | 4 | 4 | 0 | 2015-12-15 | 2015-12-15 | 0 | 0 | 0 | [20 empty] | 2015-12-16 |  | 2016-12-14 |  | EXP | [6 empty] | 2016-09-01 | 2016-09-01 | 2016-09-01 | Connected |  | No
National Grid | ORANGE | 176492 | 1364 | 80 | Solar | 09_705W3 | 2015-12-09 | 2015-12-10 | 5 | 5 | 0 | 2015-12-17 | 2015-12-17 | 0 | 0 | 0 | [20 empty] | 2016-01-19 |  | 2016-12-15 |  | EXP | [6 empty] | 2016-12-13 | 2016-12-13 | 2016-12-29 | Connected |  | No
National Grid | HOPEDALE | 176493 | 1747 | 9.75 | Solar | 05_335W9 | 2015-12-10 | 2015-12-10 | 20 | 20 | 0 | 2016-01-11 | 2016-01-11 | 0 | 0 | 0 | [20 empty] | 2016-01-19 |  | 2016-12-15 |  | EXP | [6 empty] | 2016-03-08 | 2016-03-08 | 2016-03-08 | Connected |  | No
National Grid | WESTBOROUGH | 176494 | 1581 | 15.25 | Solar | 05_312W4 | 2015-12-10 | 2015-12-10 | 29 | 29 | 0 | 2016-01-25 | 2016-01-25 | 0 | 0 | 0 | [20 empty] | 2016-02-05 |  | 2016-12-15 |  | EXP | [6 empty] | 2016-02-18 | 2016-02-18 | 2016-02-24 | Connected |  | No
National Grid | LOWELL | 176495 | 1854 | 6 | Solar | 14_21L3 | 2015-12-11 | 2015-12-11 | 2 | 2 | 0 | 2015-12-15 | 2015-12-15 | 0 | 0 | 0 | [20 empty] | 2015-12-16 |  | 2016-12-16 |  | EXP | [6 empty] | 2016-05-10 | 2016-05-10 | 2016-06-22 | Connected |  | No
National Grid | WILLIAMSTOWN | 176523 | 1267 | 80.5 | Solar | 09_1003W1 | 2015-12-11 | 2015-12-11 | 4 | 4 | 0 | 2015-12-17 | 2015-12-17 | 0 | 0 | 0 | [20 empty] | 2016-01-25 |  | 2016-12-16 |  | EXP | [6 empty] | 2016-08-19 | 2016-08-19 | 2016-08-24 | Connected |  | No
National Grid | MENDON | 176527 | 1756 | 10 | Solar | 05_332W1 | 2015-12-14 | 2015-12-15 | 2 | 2 | 0 | 2015-12-17 | 2015-12-17 | 0 | 0 | 0 | [20 empty] | 2016-01-04 |  | 2016-12-20 |  | EXP | [6 empty] | 2016-04-25 | 2016-04-25 | 2016-04-27 | Connected |  | No
National Grid | MILLVILLE | 176528 | 1529 | 10 | Solar | 05_321W2 | 2015-12-15 | 2015-12-15 | 16 | 16 | 0 | 2016-01-08 | 2016-01-08 | 0 | 0 | 0 | [20 empty] | 2016-01-19 |  | 2016-12-20 |  | EXP | [6 empty] | 2016-01-20 | 2016-01-20 | 2016-03-07 | Connected |  | No
National Grid | HOPEDALE | 176529 | 1747 | 7.6 | Solar | 05_332W1 | 2015-12-16 | 2015-12-17 | 3 | 3 | 0 | 2015-12-22 | 2015-12-22 | 0 | 0 | 0 | [20 empty] | 2016-01-04 |  | 2016-12-22 |  | EXP | [6 empty] | 2016-08-29 | 2016-08-29 | 2016-08-29 | Connected |  | No
National Grid | GLOUCESTER | 176530 | 1930 | 108 | Solar | 12_51T3 | 2015-12-16 | 2015-12-17 | 0 | 0 | 0 | 2015-12-17 | 2015-12-17 | 0 | 0 | 0 | [20 empty] | 2016-01-04 |  | 2016-12-22 |  | EXP | [6 empty] | 2016-08-19 | 2016-08-19 | 2016-08-19 | Connected |  | Yes
National Grid | OXFORD | 176531 | 1540 | 252 | Solar | 01_406L4 | 2015-12-17 | 2015-12-17 | 27 | 27 | 0 | 2016-01-28 | 2016-11-03 | 192 | 0 | 192 | [21 empty] | 2015-12-17 | 2016-12-22 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEYMOUTH | 176532 | 2189 | 428 | Solar | 07_12W3 | 2015-12-17 | 2015-12-18 | 0 | 0 | 0 | 2015-12-18 | 2015-12-18 | 0 | 0 | 0 | [20 empty] | 2016-01-04 | 2015-12-17 | 2016-12-23 | Yes | EXP |  | 2016-06-08 | 2017-04-24 | 217 | 0 | 217 | 2017-05-12 | 2017-05-12 | 2017-05-12 | Connected |  | No
National Grid | WARE | 176560 | 1082 | 972 | Solar | 09_501L2 | 2015-12-17 | 2015-12-17 | 1 | 0 | 1 | [10 empty] | 2015-12-18 | 2016-01-15 | 18 | 0 | 18 | [5 empty] | 2016-10-18 | 2016-10-25 | 5 | 0 | 5 | 2019-02-04 | 2015-12-18 | 2020-10-09 | Yes | STD |  | 2020-02-28 | 2020-04-01 | 33 | 0 | 33 |  |  | 2020-10-08 | Connected |  | No
National Grid | WARE | 176561 | 1082 | 250 | Solar | 09_501L2 | 2015-12-18 | 2015-12-22 | 1 | 0 | 1 | [10 empty] | 2015-12-22 | 2016-01-22 | 19 | 0 | 19 | [5 empty] | 2016-08-02 | 2016-10-25 | 59 | 0 | 59 | 2019-01-15 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SOMERSET | 176564 | 2726 | 42 | Solar | 05_18J5 | 2015-12-22 | 2015-12-22 | 22 | 22 | 0 | 2016-01-26 | 2016-01-26 | 0 | 0 | 0 | [20 empty] | 2016-01-27 | 2015-12-23 | 2016-12-27 |  | EXP | [6 empty] | 2016-02-04 | 2016-02-04 | 2016-06-16 | Connected |  | No
National Grid | GARDNER | 176568 | 1440 | 7.6 | Solar | 01_607W4 | 2015-12-23 | 2015-12-24 | 20 | 20 | 0 | 2016-01-26 | 2016-01-26 | 0 | 0 | 0 | [20 empty] | 2016-02-23 |  | 2016-12-29 | Yes | EXP |  | 2016-07-18 | 2016-08-16 | 21 | 0 | 21 | 2016-09-01 | 2016-09-01 | 2016-09-01 | Connected |  | No
National Grid | WINCHENDON | 176569 | 1475 | 7.6 | Solar | 01_612W3 | 2015-12-24 | 2015-12-24 | 4 | 4 | 0 | 2015-12-31 | 2015-12-31 | 0 | 0 | 0 | [20 empty] | 2016-01-04 |  | 2016-12-29 |  | EXP | [6 empty] | 2016-05-26 | 2016-05-26 | 2016-09-12 | Connected |  | No
National Grid | LEOMINSTER | 176599 | 1453 | 75 | Solar | 01_207W3 | 2015-12-29 | 2015-12-30 | 0 | 0 | 0 | 2015-12-30 | 2015-12-30 | 0 | 0 | 0 | [20 empty] | 2016-01-14 | 2015-12-29 | 2017-01-04 |  | EXP | [6 empty] | 2016-11-15 | 2016-11-15 | 2016-11-15 | Connected |  | No
National Grid | CHARLTON | 176600 | 1507 | 1000 | Solar | 01_415L2 | 2015-12-29 | 2015-12-30 | 3 | 3 | 0 | [10 empty] | 2016-01-05 | 2016-01-12 | 5 | 0 | 5 | [5 empty] | 2016-03-29 | 2016-07-05 | 66 | 17 | 49 | 2016-07-19 | 2015-12-29 | 2017-01-04 |  | STD | [6 empty] | 2017-12-08 | 2017-12-08 | 2017-12-08 | Connected |  | No
National Grid | MONSON | 176601 | 1057 | 2000 | Solar | 09_503L2 | 2015-12-29 | 2015-12-30 | 3 | 3 | 0 | [10 empty] | 2016-01-05 | 2016-01-15 | 8 | 0 | 8 | [5 empty] | 2016-06-24 | 2016-09-27 | 65 | 12 | 53 | 2016-09-30 | 2015-12-29 | 2019-02-28 | Yes | STD |  | 2018-09-19 | 2018-11-09 | 51 | 0 | 51 |  |  | 2019-02-28 | Connected |  | No
National Grid | UXBRIDGE | 176607 | 1569 | 1000 | Solar | 05_321W2 | 2015-12-29 | 2016-01-04 | 1 | 1 | 0 | [10 empty] | 2016-01-05 | 2016-01-12 | 5 | 1 | 4 | [5 empty] | 2016-05-06 | 2016-07-19 | 49 | 0 | 49 | 2016-07-19 | 2015-12-29 | 2017-10-20 | Yes | STD |  | 2017-07-20 | 2018-01-11 | 114 | 0 | 114 | 2017-12-20 | 2017-12-20 | 2017-12-22 | Connected |  | No
National Grid | UXBRIDGE | 176636 | 1569 | 2000 | Solar | 05_321W2 | 2015-12-29 | 2016-01-04 | 1 | 1 | 0 | [10 empty] | 2016-01-05 | 2016-01-12 | 5 | 1 | 4 | [5 empty] | 2016-05-06 | 2016-07-19 | 49 | 0 | 49 | 2016-07-19 | 2015-12-29 | 2017-10-20 | Yes | STD |  | 2017-07-20 | 2018-01-11 | 114 | 0 | 114 | 2017-12-20 | 2017-12-20 | 2017-12-22 | Connected |  | No
National Grid | SOUTHBRIDGE | 176637 | 1550 | 1000 | Solar | 01_413L3 | 2015-12-29 | 2016-01-04 | 1 | 1 | 0 | [10 empty] | 2016-01-05 | 2016-01-14 | 7 | 0 | 7 | [10 empty] | 2016-05-09 | 2015-12-29 | 2017-01-09 | Yes | STD |  | 2017-09-11 | 2017-11-07 | 35 | 0 | 35 | 2017-11-08 | 2017-11-08 | 2017-11-08 | Connected |  | No
National Grid | SOUTHBRIDGE | 176638 | 1550 | 1000 | Solar | 01_413L3 | 2015-12-29 | 2016-01-04 | 1 | 1 | 0 | [10 empty] | 2016-01-05 | 2016-01-14 | 7 | 0 | 7 | [10 empty] | 2016-05-09 | 2015-12-29 | 2017-01-09 | Yes | STD |  | 2017-09-11 | 2017-11-07 | 35 | 0 | 35 | 2018-01-02 | 2018-01-02 | 2018-01-02 | Connected |  | No
National Grid | SOUTHBRIDGE | 176639 | 1550 | 1000 | Solar | 01_413L3 | 2015-12-29 | 2016-01-04 | 1 | 1 | 0 | [10 empty] | 2016-01-05 | 2016-01-14 | 7 | 0 | 7 | [10 empty] | 2016-05-09 |  | 2017-01-09 | Yes | STD |  | 2017-09-11 | 2017-11-07 | 35 | 0 | 35 | 2017-11-08 | 2017-11-08 | 2017-11-08 | Connected |  | No
National Grid | LYNN | 176604 | 1905 | 4.25 | Solar | 12_29W3 | 2015-12-30 | 2015-12-30 | 3 | 3 | 0 | 2016-01-05 | 2017-02-06 | 270 | 0 | 270 | [20 empty] | 2016-01-22 | 2015-12-30 | 2017-01-04 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GARDNER | 176605 | 1440 | 10 | Solar | 01_607W1 | 2015-12-30 | 2016-04-06 | 0 | 0 | 0 | 2016-04-20 | 2016-04-20 | 0 | 0 | 0 | [20 empty] | 2016-05-04 |  | 2017-01-05 | Yes | EXP |  | 2016-10-04 | 2016-10-11 | 4 | 0 | 4 | 2017-03-21 | 2017-03-21 | 2017-03-21 | Connected |  | No
National Grid | NEWBURYPORT | 176642 | 1950 | 375 | Solar | 14_2405 | 2015-12-31 | 2016-01-04 | 1 | 1 | 0 | 2016-01-05 | 2016-01-05 | 0 | 0 | 0 | [20 empty] | 2016-02-05 |  | 2017-01-09 |  | EXP | [6 empty] | 2016-12-30 | 2016-12-30 | 2016-12-30 | Connected |  | No
National Grid | QUINCY | 176643 | 2171 | 528 | Solar | 07_11W3 | 2015-12-31 | 2016-01-04 | 12 | 12 | 0 | [10 empty] | 2016-01-21 | 2016-02-04 | 10 | 0 | 10 | [12 empty] | 2018-03-15 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | ATHOL | 176673 | 1331 | 7.6 | Solar | 09_702W1 | 2016-01-04 | 2016-01-04 | 59 | 59 | 0 | 2016-03-30 | 2016-03-30 | 0 | 0 | 0 | [20 empty] | 2016-04-12 |  | 2017-01-09 |  | EXP | [6 empty] | 2016-10-28 | 2016-10-28 | 2016-10-28 | Connected |  | No
National Grid | LEOMINSTER | 176674 | 1453 | 100 | Solar | 01_225W3 | 2016-01-04 | 2016-01-05 | 0 | 0 | 0 | 2016-01-05 | 2016-01-05 | 0 | 0 | 0 | [20 empty] | 2016-01-22 |  | 2017-01-10 |  | EXP | [6 empty] | 2017-01-06 | 2017-01-06 | 2017-01-04 | Connected |  | No
National Grid | CHELMSFORD | 176675 | 1824 | 10 | Solar | 14_24L1 | 2016-01-04 | 2016-01-05 | 1 | 1 | 0 | 2016-01-06 | 2016-04-06 | 62 | 0 | 62 | [20 empty] | 2016-01-29 | 2016-01-04 | 2017-01-10 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 176676 | 2301 | 5 | Solar | 07_98W46 | 2016-01-04 | 2016-01-05 | 1 | 1 | 0 | 2016-01-06 | 2016-01-06 | 0 | 0 | 0 | [20 empty] | 2016-01-29 |  | 2017-01-10 |  | EXP |  | 2017-04-23 | 2017-05-05 | 9 | 0 | 9 | 2017-05-08 | 2017-05-08 | 2017-05-10 | Connected |  | No
National Grid | MARLBOROUGH | 176678 | 1752 | 6 | Solar | 05_311W3 | 2016-01-04 | 2016-01-06 | 0 | 0 | 0 | 2016-01-06 | 2016-01-06 | 0 | 0 | 0 | [20 empty] | 2016-01-29 |  | 2017-01-11 |  | EXP | [6 empty] | 2016-07-26 | 2016-07-26 | 2016-08-23 | Connected |  | No
National Grid | BROCKTON | 176679 | 2302 | 10 | Solar | 07_911W56 | 2016-01-04 | 2016-01-06 | 0 | 0 | 0 | 2016-01-06 | 2016-01-06 | 0 | 0 | 0 | [20 empty] | 2016-01-29 |  | 2017-01-11 |  | EXP | [6 empty] | 2016-07-25 | 2016-07-25 | 2016-07-26 | Connected |  | No
National Grid | METHUEN | 176680 | 1844 | 6 | Solar | 14_74L3 | 2016-01-04 | 2016-01-06 | 0 | 0 | 0 | 2016-01-06 | 2016-01-06 | 0 | 0 | 0 | [20 empty] | 2016-01-15 |  | 2017-01-11 |  | EXP | [6 empty] | 2016-04-18 | 2016-04-18 | 2016-05-24 | Connected |  | No
National Grid | NORTHBRIDGE | 176681 | 1534 | 7.74 | Solar | 05_320W3 | 2016-01-04 | 2016-01-06 | 2 | 2 | 0 | 2016-01-08 | 2016-01-08 | 0 | 0 | 0 | [20 empty] | 2016-01-19 | 2016-01-05 | 2017-01-11 |  | EXP | [6 empty] | 2016-03-11 | 2016-03-11 | 2016-03-17 | Connected |  | No
National Grid | CHARLTON | 176677 | 1507 | 112 | Solar | 01_415L3 | 2016-01-05 | 2016-01-06 | 0 | 0 | 0 | 2016-01-06 | 2016-01-06 | 0 | 0 | 0 | 2016-06-28 | 2016-09-15 | 55 | 34 | 21 | [5 empty] | 2016-06-28 | 2016-09-15 | 55 | 34 | 21 | [5 empty] | 2016-10-31 |  | 2018-01-11 | Yes | EXP |  | 2017-07-26 | 2017-07-28 | 2 | 0 | 2 | 2017-11-21 | 2017-11-21 | 2017-11-21 | Connected |  | No
National Grid | LENOX | 176710 | 1240 | 38.4 | Solar | 09_1103W2 | 2016-01-06 | 2016-01-07 | 3 | 3 | 0 | 2016-01-12 | 2016-01-12 | 0 | 0 | 0 | [20 empty] | 2016-01-15 |  | 2017-01-12 |  | EXP | [6 empty] | 2016-08-25 | 2016-08-25 | 2016-09-14 | Connected |  | No
National Grid | METHUEN | 176711 | 1844 | 6 | Solar | 14_63L1 | 2016-01-07 | 2016-01-08 | 10 | 10 | 0 | 2016-01-25 | 2016-01-25 | 0 | 0 | 0 | [20 empty] | 2016-02-09 |  | 2017-01-13 |  | EXP | [6 empty] | 2016-05-04 | 2016-05-04 | 2016-05-09 | Connected |  | No
National Grid | SAUGUS | 176712 | 1906 | 8.75 | Solar | 12_25W1 | 2016-01-07 | 2016-01-08 | 3 | 3 | 0 | 2016-01-13 | 2016-01-13 | 0 | 0 | 0 | [20 empty] | 2016-01-19 |  | 2017-01-13 |  | EXP | [6 empty] | 2016-02-22 | 2016-02-22 | 2016-02-25 | Connected |  | No
National Grid | LEOMINSTER | 176714 | 1453 | 15.2 | Solar | 01_227W1 | 2016-01-08 | 2016-01-08 | 3 | 3 | 0 | 2016-01-13 | 2016-01-13 | 0 | 0 | 0 | [20 empty] | 2016-01-15 |  | 2017-01-13 |  | EXP | [6 empty] | 2016-10-12 | 2016-10-12 | 2016-10-19 | Connected |  | No
National Grid | OAKHAM | 176715 | 1068 | 16.4 | Solar | 09_604W2 | 2016-01-08 | 2016-01-08 | 3 | 3 | 0 | 2016-01-13 | 2017-02-13 | 269 | 0 | 269 | [20 empty] | 2016-01-15 |  | 2017-01-27 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHELMSFORD | 176716 | 1824 | 10 | Solar | 14_16L1 | 2016-01-11 | 2016-01-12 | 1 | 1 | 0 | 2016-01-13 | 2016-01-13 | 0 | 0 | 0 | [20 empty] | 2016-01-29 |  | 2017-01-17 |  | EXP | [6 empty] | 2016-03-07 | 2016-03-07 | 2016-08-11 | Connected |  | No
National Grid | LOWELL | 176717 | 1854 | 5 | Solar | 14_77L1 | 2016-01-11 | 2016-01-12 | 3 | 3 | 0 | 2016-01-15 | 2016-01-15 | 0 | 0 | 0 | [20 empty] | 2016-02-02 | 2016-01-11 | 2017-01-17 |  | EXP | [6 empty] | 2016-08-01 | 2016-08-01 | 2016-08-02 | Connected |  | No
National Grid | BROCKTON | 176718 | 2301 | 259.2 | Solar | 14_48L2 | 2016-01-11 | 2016-01-12 | 2 | 2 | 0 | [10 empty] | 2016-01-14 | 2016-01-27 | 8 | 0 | 8 | [10 empty] | 2016-07-28 |  | 2017-12-05 | Yes | STD |  | 2017-10-12 | 2017-11-06 | 12 | 0 | 12 | 2017-11-02 | 2017-11-02 | 2017-12-05 | Connected |  | No
National Grid | LEOMINSTER | 176747 | 1453 | 3 | Solar | 01_219W2 | 2016-01-11 | 2016-01-12 | 3 | 3 | 0 | 2016-01-15 | 2017-02-23 | 274 | 0 | 274 | [20 empty] | 2016-02-02 |  | 2017-04-02 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SWANSEA | 176748 | 2777 | 5 | Solar | 05_11W81 | 2016-01-11 | 2016-01-12 | 3 | 3 | 0 | 2016-01-15 | 2016-01-15 | 0 | 0 | 0 | [20 empty] | 2016-02-02 | 2016-01-11 | 2017-01-17 |  | EXP | [6 empty] | 2016-08-29 | 2016-08-29 | 2016-09-01 | Connected |  | No
National Grid | LAWRENCE | 176749 | 1843 | 6.45 | Solar | 14_61L2 | 2016-01-11 | 2016-01-12 | 5 | 5 | 0 | 2016-01-20 | 2016-01-20 | 0 | 0 | 0 | [20 empty] | 2016-02-09 |  | 2017-01-17 | Yes | EXP |  | 2016-07-07 | 2016-08-01 | 17 | 0 | 17 | 2016-10-21 | 2016-10-21 | 2016-10-25 | Connected |  | No
National Grid | SPENCER | 176750 | 1562 | 11.4 | Solar | 01_552L1 | 2016-01-12 | 2016-01-12 | 9 | 9 | 0 | 2016-01-26 | 2017-02-17 | 265 | 0 | 265 | [20 empty] | 2016-02-23 |  | 2017-01-17 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | OXFORD | 176751 | 1540 | 6 | Solar | 01_406L3 | 2016-01-12 | 2016-01-12 | 9 | 9 | 0 | 2016-01-26 | 2017-02-13 | 261 | 0 | 261 | [20 empty] | 2016-02-04 | 2016-01-12 | 2017-01-27 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SAUGUS | 176752 | 1906 | 34.2 | Solar | 12_25W1 | 2016-01-12 | 2016-01-13 | 8 | 8 | 0 | 2016-01-26 | 2016-01-26 | 0 | 0 | 0 | [20 empty] | 2016-02-09 |  | 2017-01-18 | Yes | EXP |  | 2016-05-27 | 2016-06-03 | 4 | 0 | 4 | 2016-08-19 | 2016-08-19 | 2016-08-19 | Connected |  | No
National Grid | BELLINGHAM | 176753 | 2019 | 7.6 | Solar | 05_344W4 | 2016-01-12 | 2016-01-13 | 8 | 8 | 0 | 2016-01-26 | 2016-01-26 | 0 | 0 | 0 | [20 empty] | 2016-02-04 |  | 2017-01-18 |  | EXP | [6 empty] | 2016-03-16 | 2016-03-16 | 2016-06-30 | Connected |  | No
National Grid | WINCHENDON | 176754 | 1477 | 10 | Solar | 01_612W3 | 2016-01-12 | 2016-01-13 | 4 | 4 | 0 | 2016-01-20 | 2016-01-20 | 0 | 0 | 0 | [20 empty] | 2016-01-21 |  | 2017-01-18 |  | EXP | [6 empty] | 2016-01-27 | 2016-01-27 | 2016-05-27 | Connected |  | No
National Grid | SOMERSET | 176755 | 2725 | 300 | Solar | 05_11W84 | 2016-01-13 | 2016-01-13 | 3 | 3 | 0 | 2016-01-19 | 2016-10-05 | 179 | 0 | 179 | [22 empty] | 2017-01-18 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MALDEN | 176784 | 2148 | 432 | Solar | 12_16W5 | 2016-01-13 | 2016-01-13 | 9 | 9 | 0 | 2016-01-27 | 2016-01-27 | 0 | 0 | 0 | [20 empty] | 2016-10-25 | 2016-01-13 | 2017-07-01 |  | EXP | [6 empty] | 2017-01-12 | 2017-01-12 | 2017-06-30 | Connected |  | No
National Grid | WESTBOROUGH | 176785 | 1581 | 726 | Solar | 05_312W2 | 2016-01-13 | 2016-01-14 | 2 | 2 | 0 | [10 empty] | 2016-01-19 | 2016-01-27 | 6 | 0 | 6 | [10 empty] | 2016-05-18 |  | 2017-01-19 |  | STD | [6 empty] | 2016-12-22 | 2016-12-22 | 2016-12-22 | Connected |  | No
National Grid | SOUTH GRAFTON | 176786 | 1560 | 312.5 | Solar | 05_320W3 | 2016-01-14 | 2016-01-15 | 0 | 0 | 0 | 2016-01-15 | 2016-12-15 | 228 | 0 | 228 | [22 empty] | 2017-01-20 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | REVERE | 176787 | 2151 | 6 | Solar | 12_16W8 | 2016-01-14 | 2016-01-15 | 6 | 6 | 0 | 2016-01-26 | 2017-02-22 | 267 | 0 | 267 | [20 empty] | 2016-02-23 | 2016-01-14 | 2017-01-20 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | REVERE | 176788 | 2151 | 11.4 | Solar | 12_7W2 | 2016-01-14 | 2016-01-15 | 6 | 6 | 0 | 2016-01-26 | 2016-01-26 | 0 | 0 | 0 | [20 empty] | 2016-02-23 |  | 2017-10-31 | Yes | EXP |  | 2017-09-18 | 2017-11-14 | 34 | 0 | 34 | 2017-04-28 | 2017-04-28 | 2017-11-16 | Connected |  | No
National Grid | GLOUCESTER | 176789 | 1930 | 7.6 | Solar | 12_28L2 | 2016-01-14 | 2016-01-15 | 0 | 0 | 0 | [26 empty] | 2016-01-14 | 2017-01-20 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BELCHERTOWN | 176790 | 1007 | 7.6 | Solar | 09_509L1 | 2016-01-14 | 2016-01-15 | 6 | 6 | 0 | 2016-01-26 | 2016-01-26 | 0 | 0 | 0 | [20 empty] | 2016-02-23 |  | 2017-01-20 | Yes | EXP |  | 2016-12-15 | 2017-01-10 | 16 | 0 | 16 | 2017-04-12 | 2017-04-12 | 2017-04-14 | Connected |  | No
National Grid | GLOUCESTER | 176791 | 1930 | 7.6 | Solar | 12_28L2 | 2016-01-14 | 2016-01-15 | 6 | 6 | 0 | 2016-01-26 | 2016-01-26 | 0 | 0 | 0 | [20 empty] | 2016-02-04 |  | 2017-01-20 |  | EXP | [6 empty] | 2016-03-16 | 2016-03-16 | 2016-08-02 | Connected |  | No
National Grid | BELLINGHAM | 176820 | 2019 | 6 | Solar | 05_344W4 | 2016-01-14 | 2016-01-15 | 6 | 6 | 0 | 2016-01-26 | 2016-01-26 | 0 | 0 | 0 | [20 empty] | 2016-02-04 |  | 2017-01-20 |  | EXP | [6 empty] | 2016-03-16 | 2016-03-16 | 2016-12-16 | Connected |  | No
National Grid | SOMERSET | 176821 | 2726 | 6 | Solar | 05_18J7 | 2016-01-14 | 2016-01-15 | 2 | 2 | 0 | 2016-01-20 | 2016-01-20 | 0 | 0 | 0 | [20 empty] | 2016-02-09 |  | 2017-01-20 |  | EXP | [6 empty] | 2016-06-01 | 2016-06-01 | 2016-06-06 | Connected |  | No
National Grid | EAST BRIDGEWATER | 176822 | 2333 | 10 | Solar | 07_797W23 | 2016-01-14 | 2016-01-15 | 6 | 6 | 0 | 2016-01-26 | 2016-01-26 | 0 | 0 | 0 | [20 empty] | 2016-02-09 |  | 2017-01-20 |  | EXP | [6 empty] | 2016-05-04 | 2016-05-04 | 2016-11-21 | Connected |  | Yes
National Grid | METHUEN | 176823 | 1844 | 6 | Solar | 14_74L3 | 2016-01-14 | 2016-01-15 | 6 | 6 | 0 | 2016-01-26 | 2016-01-26 | 0 | 0 | 0 | [20 empty] | 2016-02-05 | 2016-01-15 | 2017-01-20 |  | EXP | [6 empty] | 2016-03-16 | 2016-03-16 | 2016-08-25 | Connected |  | No
National Grid | BROCKTON | 176824 | 2301 | 7.6 | Solar | 07_911W25 | 2016-01-15 | 2016-01-15 | 0 | 0 | 0 | 2016-01-15 | 2016-01-15 | 0 | 0 | 0 | [20 empty] | 2016-02-09 |  | 2017-01-20 |  | EXP |  | 2016-08-12 | 2016-09-02 | 15 | 0 | 15 | 2016-10-06 | 2016-10-06 | 2016-10-11 | Connected |  | No
National Grid | SEEKONK | 176825 | 2771 | 9 | Solar | 05_7L1 | 2016-01-15 | 2016-01-15 | 1 | 1 | 0 | 2016-01-19 | 2016-01-19 | 0 | 0 | 0 | [20 empty] | 2016-01-22 | 2016-01-18 | 2017-01-20 |  | EXP | [6 empty] | 2016-04-12 | 2016-04-12 | 2016-04-12 | Connected |  | No
National Grid | QUINCY | 176826 | 2169 | 54 | Solar | 07_1W1 | 2016-01-18 | 2016-01-19 | 2 | 2 | 0 | 2016-01-21 | 2016-01-21 | 0 | 0 | 0 | [20 empty] | 2016-02-12 |  | 2017-01-24 |  | EXP | [6 empty] | 2016-10-12 | 2016-10-12 | 2016-10-25 | Connected |  | No
National Grid | AUBURN | 176827 | 1501 | 10 | Solar | 01_26W3 | 2016-01-18 | 2016-01-19 | 5 | 5 | 0 | 2016-01-26 | 2017-02-13 | 261 | 0 | 261 | [20 empty] | 2016-03-16 |  | 2017-01-30 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MILFORD | 176828 | 1757 | 7.6 | Solar | 05_336W3 | 2016-01-18 | 2016-01-19 | 5 | 5 | 0 | 2016-01-26 | 2016-01-26 | 0 | 0 | 0 | [20 empty] | 2016-02-09 |  | 2017-01-24 |  | EXP | [6 empty] | 2016-10-10 | 2016-10-10 | 2016-10-13 | Connected |  | No
National Grid | MARLBOROUGH | 176857 | 1752 | 75 | Solar | 05_317W1 | 2016-01-19 | 2016-01-19 | 0 | 0 | 0 | 2016-01-19 | 2016-09-16 | 166 | 0 | 166 | [22 empty] | 2017-01-24 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | FRANKLIN | 176858 | 2038 | 10 | Solar | 05_344W1 | 2016-01-19 | 2016-01-19 | 3 | 3 | 0 | 2016-01-22 | 2017-01-13 | 243 | 0 | 243 | [20 empty] | 2016-01-28 |  | 2017-01-24 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BILLERICA | 176859 | 1821 | 30 | Hydrogen | 14_18L3 | 2016-01-20 | 2016-01-20 | 1 | 1 | 0 | 2016-01-21 | 2016-02-19 | 25 | 0 | 25 | [20 empty] | 2016-02-23 |  | 2020-11-16 |  | EXP | [8 empty] | 2020-12-18 | Connected |  | No
National Grid | SOMERSET | 176860 | 2726 | 7.6 | Solar | 05_18J7 | 2016-01-20 | 2016-01-20 | 3 | 3 | 0 | 2016-01-25 | 2016-01-25 | 0 | 0 | 0 | [20 empty] | 2016-02-23 |  | 2017-01-25 |  | EXP | [6 empty] | 2016-07-13 | 2016-07-13 | 2016-07-18 | Connected |  | No
National Grid | NANTUCKET | 176861 | 2554 | 27 | Solar | 04_101L4 | 2016-01-20 | 2016-01-21 | 1 | 1 | 0 | 2016-01-22 | 2016-01-22 | 0 | 0 | 0 | [20 empty] | 2016-02-04 |  | 2017-01-26 |  | EXP | [6 empty] | 2016-05-18 | 2016-05-18 | 2016-06-13 | Connected |  | No
National Grid | NORTHBOROUGH | 176862 | 1532 | 10 | Solar | 05_313W4 | 2016-01-21 | 2016-01-21 | 3 | 3 | 0 | 2016-01-26 | 2016-01-26 | 0 | 0 | 0 | [20 empty] | 2016-02-05 |  | 2017-01-26 |  | EXP | [6 empty] | 2016-03-16 | 2016-03-16 | 2016-07-19 | Connected |  | No
National Grid | FALL RIVER | 176863 | 2721 | 40.25 | Solar | 05_106W43 | 2016-01-21 | 2016-01-21 | 4 | 4 | 0 | 2016-01-27 | 2016-01-27 | 0 | 0 | 0 | [20 empty] | 2016-02-05 |  | 2017-01-26 |  | EXP | [6 empty] | 2016-10-18 | 2016-10-18 | 2016-10-24 | Connected |  | No
National Grid | LYNN | 176864 | 1901 | 26.75 | Solar | 12_1385 | 2016-01-21 | 2016-01-21 | 4 | 4 | 0 | 2016-01-27 | 2016-03-15 | 33 | 0 | 33 | [22 empty] | 2017-01-26 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTBOROUGH | 176866 | 1582 | 1232 | Solar | 05_314W5 | 2016-01-22 | 2016-01-22 | 2 | 2 | 0 | [10 empty] | 2016-01-26 | 2016-02-17 | 15 | 0 | 15 | [11 empty] | 2016-01-22 | 2017-01-27 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | WESTPORT | 176894 | 2790 | 4000.002 | Solar | 05_115W52 | 2016-01-22 | 2016-01-25 | 4 | 4 | 0 | [10 empty] | 2016-01-29 | 2016-03-18 | 33 | 0 | 33 | [10 empty] | 2016-08-16 | 2016-01-22 | 2018-12-05 | Yes | STD |  | 2018-05-05 | 2018-10-03 | 151 | 0 | 151 |  |  | 2018-11-30 | Connected |  | No
National Grid | WESTPORT | 176895 | 2790 | 1500 | Solar | 05_115W52 | 2016-01-22 | 2016-01-25 | 4 | 4 | 0 | [10 empty] | 2016-01-29 | 2016-03-18 | 33 | 0 | 33 | [10 empty] | 2016-08-16 | 2016-01-22 | 2018-12-06 | Yes | STD | [8 empty] | 2018-12-03 | Connected |  | No
National Grid | WESTPORT | 176902 | 2790 | 750 | Solar | 05_115W52 | 2016-01-22 | 2016-01-28 | 1 | 1 | 0 | [10 empty] | 2016-01-29 | 2016-03-18 | 33 | 0 | 33 | [10 empty] | 2016-08-16 |  | 2018-12-05 | Yes | STD | [8 empty] | 2018-11-14 | Connected |  | No
National Grid | DIGHTON | 176896 | 2715 | 2000 | Solar | 05_19W72 | 2016-01-25 | 2016-01-25 | 0 | 0 | 0 | [10 empty] | 2016-01-25 | 2016-02-19 | 18 | 0 | 18 | [5 empty] | 2017-03-23 |  | 254 | 0 | 254 | 2016-09-29 |  | 2017-01-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | DIGHTON | 176897 | 2715 | 2000 | Solar | 05_19W72 | 2016-01-25 | 2016-01-25 | 0 | 0 | 0 | [10 empty] | 2016-01-25 | 2016-02-19 | 18 | 0 | 18 | [5 empty] | 2017-04-04 | 2017-04-17 | 9 | 0 | 9 | 2016-09-29 |  | 2017-01-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ATHOL | 176898 | 1331 | 10 | Solar | 09_702W1 | 2016-01-25 | 2016-01-26 | 1 | 1 | 0 | 2016-01-27 | 2017-02-01 | 252 | 0 | 252 | [20 empty] | 2016-03-16 |  | 2017-01-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MARLBOROUGH | 158029 | 1752 | 7.6 | Solar | 05_311W5 | 2016-01-26 | 2016-01-26 | 2 | 0 | 2 | [27 empty] | 2017-02-01 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WEBSTER | 176899 | 1570 | 23.4 | Solar | 01_412L2 | 2016-01-26 | 2016-01-26 | 3 | 3 | 0 | 2016-01-29 | 2016-01-29 | 0 | 0 | 0 | [20 empty] | 2016-02-01 |  | 2017-01-31 |  | EXP | [6 empty] | 2016-09-16 | 2016-09-16 | 2016-09-16 | Connected |  | No
National Grid | WESTMINSTER | 176901 | 1473 | 6 | Solar | 01_602W2 | 2016-01-27 | 2016-01-27 | 6 | 6 | 0 | [25 empty] | 2016-02-17 | 2016-01-27 | 2017-02-01 |  | EXP | [6 empty] | 2016-02-19 | 2016-02-19 | 2016-04-11 | Connected |  | No
National Grid | LEOMINSTER | 176930 | 1453 | 360 | Solar | 01_207W3 | 2016-01-27 | 2016-01-28 | 2 | 2 | 0 | 2016-02-01 | 2016-02-01 | 0 | 0 | 0 | [20 empty] | 2016-04-29 |  | 2017-04-14 | Yes | EXP |  | 2016-12-08 | 2017-03-21 | 69 | 0 | 69 | 2017-04-07 | 2017-04-07 | 2017-04-12 | Connected |  | No
National Grid | DUDLEY | 176931 | 1571 | 22.8 | Solar | 01_412L4 | 2016-01-28 | 2016-01-28 | 0 | 0 | 0 | 2016-01-28 | 2016-01-28 | 0 | 0 | 0 | [20 empty] | 2016-02-05 | 2016-01-28 | 2017-04-02 |  | EXP | [6 empty] | 2016-11-07 | 2016-11-07 | 2016-11-17 | Connected |  | No
National Grid | BRIDGEWATER | 176932 | 2324 | 960 | Solar | 07_912W73 | 2016-01-28 | 2016-01-28 | 12 | 12 | 0 | [10 empty] | 2016-02-16 | 2016-03-15 | 20 | 0 | 20 | [10 empty] | 2017-08-14 |  | 2025-02-14 | Yes | STD |  | 2020-11-10 | 2020-11-09 | 0 | 0 | 0 |  |  | 2024-03-05 | Connected |  | No
National Grid | WESTBOROUGH | 176933 | 1581 | 72 | Solar | 05_314W4 | 2016-01-28 | 2016-01-28 | 4 | 4 | 0 | 2016-02-03 | 2016-02-03 | 0 | 0 | 0 | [20 empty] | 2016-02-23 |  | 2017-02-02 |  | EXP | [6 empty] | 2016-11-07 | 2016-11-07 | 2016-08-12 | Connected |  | No
National Grid | HOLBROOK | 176934 | 2343 | 180 | Solar | 07_10W1 | 2016-01-28 | 2016-01-28 | 4 | 4 | 0 | 2016-02-03 | 2016-02-03 | 0 | 0 | 0 | [20 empty] | 2016-02-23 |  | 2017-02-02 |  | EXP | [6 empty] | 2016-11-29 | 2016-11-29 | 2016-12-05 | Connected |  | No
National Grid | ATTLEBORO | 176386 | 2703 | 10 | Solar | 05_9L1 | 2016-01-29 | 2016-02-01 | 6 | 6 | 0 | 2016-02-09 | 2016-02-09 | 0 | 0 | 0 | [20 empty] | 2016-02-16 |  | 2017-02-06 |  | EXP | [6 empty] | 2016-11-22 | 2016-11-22 | 2016-11-28 | Connected |  | No
National Grid | MILLBURY | 176387 | 1527 | 11.4 | Solar | 01_304W3 | 2016-01-29 | 2016-02-01 | 6 | 6 | 0 | 2016-02-09 | 2017-02-27 | 260 | 0 | 260 | [20 empty] | 2016-03-08 |  | 2017-02-06 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEYMOUTH | 176388 | 2190 | 3.8 | Solar | 07_8W1 | 2016-01-29 | 2016-02-01 | 3 | 3 | 0 | 2016-02-04 | 2016-02-04 | 0 | 0 | 0 | [20 empty] | 2016-02-23 |  | 2017-02-06 |  | EXP | [6 empty] | 2016-12-01 | 2016-12-01 | 2016-12-05 | Connected |  | No
National Grid | LYNN | 176389 | 1902 | 6 | Solar | 12_1384 | 2016-01-29 | 2016-02-01 | 6 | 6 | 0 | 2016-02-09 | 2016-03-08 | 19 | 0 | 19 | [22 empty] | 2017-02-06 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BEVERLY | 176390 | 1915 | 7.6 | Solar | 12_12L2 | 2016-01-29 | 2016-02-01 | 6 | 6 | 0 | 2016-02-09 | 2017-02-13 | 251 | 0 | 251 | [20 empty] | 2016-03-08 | 2016-01-29 | 2017-02-06 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LYNN | 176935 | 1904 | 6 | Solar | 12_24W2 | 2016-01-29 | 2016-02-01 | 6 | 6 | 0 | 2016-02-09 | 2016-02-09 | 0 | 0 | 0 | [20 empty] | 2016-03-07 |  | 2017-02-06 | Yes | EXP | [6 empty] | 2016-09-19 | 2016-09-19 | 2016-09-19 | Connected |  | No
National Grid | METHUEN | 176936 | 1844 | 7.6 | Solar | 14_74L3 | 2016-01-29 | 2016-02-01 | 6 | 6 | 0 | 2016-02-09 | 2016-02-09 | 0 | 0 | 0 | [20 empty] | 2016-03-07 |  | 2017-02-06 |  | EXP | [6 empty] | 2016-08-04 | 2016-08-04 | 2016-08-08 | Connected |  | No
National Grid | DRACUT | 176937 | 1826 | 6 | Solar | 14_21L1 | 2016-01-29 | 2016-02-01 | 6 | 6 | 0 | 2016-02-09 | 2016-02-09 | 0 | 0 | 0 | [20 empty] | 2016-02-10 |  | 2017-02-06 |  | EXP | [6 empty] | 2016-03-16 | 2016-03-16 | 2016-06-10 | Connected |  | No
National Grid | SHIRLEY | 176391 | 1464 | 168 | Solar | 01_227W3 | 2016-02-01 | 2016-02-03 | 0 | 0 | 0 | 2016-02-03 | 2017-01-23 | 240 | 0 | 240 | [20 empty] | 2016-03-02 |  | 2017-02-08 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | AMESBURY | 176392 | 1913 | 300 | Solar | 14_275L2 | 2016-02-02 | 2016-02-03 | 1 | 1 | 0 | 2016-02-04 | 2016-02-04 | 0 | 0 | 0 | 2016-03-16 | 2016-03-16 | 0 | 0 | 0 | [5 empty] | 2016-03-16 | 2016-03-16 | 0 | 0 | 0 | [5 empty] | 2016-03-16 |  | 2016-09-15 |  | EXP | [6 empty] | 2016-09-29 | 2016-09-29 | 2016-09-30 | Connected |  | No
National Grid | ANDOVER | 176393 | 1810 | 56 | Solar | 14_50L3 | 2016-02-02 | 2016-02-03 | 4 | 4 | 0 | 2016-02-09 | 2016-02-09 | 0 | 0 | 0 | [20 empty] | 2016-02-10 |  | 2017-09-08 |  | EXP | [6 empty] | 2016-02-16 | 2016-02-16 | 2017-06-23 | Connected |  | No
National Grid | BEVERLY | 176394 | 1915 | 10 | Solar | 12_51L1 | 2016-02-02 | 2016-02-03 | 4 | 4 | 0 | 2016-02-09 | 2016-03-11 | 22 | 0 | 22 | [20 empty] | 2016-03-03 |  | 2017-02-08 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | TYNGSBORO | 176422 | 1879 | 2000 | Solar | 14_211L1 | 2016-02-02 | 2016-02-04 | 3 | 3 | 0 | [10 empty] | 2016-02-09 | 2016-03-08 | 19 | 0 | 19 | [11 empty] | 2016-02-02 | 2017-02-09 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BRIDGEWATER | 176423 | 2324 | 4990 | Solar | 07_912W55 | 2016-02-02 | 2016-02-04 | 3 | 3 | 0 | [10 empty] | 2016-02-09 | 2016-02-29 | 13 | 0 | 13 | [10 empty] | 2017-05-30 | 2016-02-02 | 2022-02-25 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | BRIDGEWATER | 176424 | 2324 | 1980 | Solar | 07_912W55 | 2016-02-02 | 2016-02-04 | 3 | 3 | 0 | [10 empty] | 2016-02-09 | 2016-02-29 | 13 | 0 | 13 | [10 empty] | 2017-05-30 | 2016-02-02 | 2019-06-27 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | BRIDGEWATER | 176425 | 2324 | 1980 | Solar | 07_912W55 | 2016-02-02 | 2016-02-04 | 3 | 3 | 0 | [10 empty] | 2016-02-09 | 2016-02-29 | 13 | 0 | 13 | [10 empty] | 2017-05-30 | 2016-02-03 | 2019-06-27 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | BRIDGEWATER | 176426 | 2324 | 6.45 | Solar | 07_912W75 | 2016-02-03 | 2016-02-04 | 5 | 5 | 0 | 2016-02-11 | 2016-02-11 | 0 | 0 | 0 | [20 empty] | 2016-03-08 | 2016-02-03 | 2017-02-09 | Yes | EXP |  | 2016-10-04 | 2016-10-12 | 5 | 0 | 5 | 2016-10-19 | 2016-10-19 | 2016-10-25 | Connected |  | No
National Grid | FALL RIVER | 176427 | 2724 | 10 | Solar | 05_115W42 | 2016-02-03 | 2016-02-04 | 3 | 3 | 0 | 2016-02-09 | 2016-02-09 | 0 | 0 | 0 | [20 empty] | 2016-03-07 |  | 2018-01-08 | Yes | EXP |  | 2017-08-11 | 2017-09-06 | 17 | 0 | 17 | 2017-09-27 | 2017-09-27 | 2017-09-29 | Connected |  | No
National Grid | SPENCER | 176428 | 1562 | 10 | Solar | 01_552L1 | 2016-02-03 | 2016-02-04 | 3 | 3 | 0 | 2016-02-09 | 2017-01-17 | 232 | 0 | 232 | [20 empty] | 2016-03-07 |  | 2017-02-09 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WINCHENDON | 176430 | 1475 | 2000 | Solar | 01_612W1 | 2016-02-04 | 2016-02-04 | 1 | 1 | 0 | [10 empty] | 2016-02-05 | 2016-03-07 | 20 | 0 | 20 | [12 empty] | 2017-02-09 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | COHASSET | 176459 | 2025 | 10 | Solar | 07_18J1 | 2016-02-04 | 2016-02-05 | 0 | 0 | 0 | 2016-02-05 | 2016-02-05 | 0 | 0 | 0 | [20 empty] | 2016-02-08 |  | 2017-02-10 |  | EXP | [6 empty] | 2016-05-13 | 2016-05-13 | 2016-05-16 | Connected |  | No
National Grid | MALDEN | 176460 | 2148 | 56 | Solar | 12_16W3 | 2016-02-04 | 2016-02-08 | 1 | 1 | 0 | 2016-02-09 | 2016-02-09 | 0 | 0 | 0 | [20 empty] | 2016-02-10 |  | 2017-02-13 |  | EXP | [6 empty] | 2016-11-22 | 2016-11-22 | 2016-11-22 | Connected |  | No
National Grid | CHARLEMONT | 176461 | 1339 | 7.6 | Solar | 09_1007G1 | 2016-02-04 | 2016-02-08 | 3 | 3 | 0 | 2016-02-11 | 2016-02-11 | 0 | 0 | 0 | [20 empty] | 2016-02-17 |  | 2017-02-13 |  | EXP | [6 empty] | 2016-08-24 | 2016-08-24 | 2016-08-24 | Connected |  | No
National Grid | GRAFTON | 176462 | 1519 | 10 | Solar | 05_320W3 | 2016-02-04 | 2016-02-08 | 3 | 3 | 0 | 2016-02-11 | 2016-02-11 | 0 | 0 | 0 | [20 empty] | 2016-02-17 |  | 2017-02-13 |  | EXP | [6 empty] | 2016-05-16 | 2016-05-16 | 2016-05-18 | Connected |  | No
National Grid | SOUTH GRAFTON | 176463 | 1560 | 7.6 | Solar | 01_304W2 | 2016-02-04 | 2016-02-08 | 3 | 3 | 0 | 2016-02-11 | 2016-02-11 | 0 | 0 | 0 | [20 empty] | 2016-02-17 |  | 2017-02-13 |  | EXP | [6 empty] | 2016-05-09 | 2016-05-09 | 2016-05-12 | Connected |  | No
National Grid | MILLBURY | 176464 | 1527 | 4.3 | Solar | 01_304W4 | 2016-02-05 | 2016-02-08 | 4 | 4 | 0 | 2016-02-12 | 2017-01-25 | 235 | 0 | 235 | [20 empty] | 2016-03-08 |  | 2017-02-13 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LANCASTER | 176465 | 1523 | 99.9 | Solar | 01_225W1 | 2016-02-05 | 2016-02-08 | 0 | 0 | 0 | 2016-02-08 | 2016-02-08 | 0 | 0 | 0 | [20 empty] | 2016-02-09 |  | 2017-02-13 |  | EXP | [6 empty] | 2016-11-18 | 2016-11-18 | 2016-11-18 | Connected |  | No
National Grid | METHUEN | 176466 | 1844 | 408 | Solar | 14_5J41 | 2016-02-05 | 2016-02-08 | 3 | 3 | 0 | 2016-02-11 | 2016-12-15 | 210 | 0 | 210 | [22 empty] | 2017-02-13 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WHITINSVILLE | 176467 | 1588 | 27 | Solar | 05_320W1 | 2016-02-05 | 2016-02-08 | 3 | 3 | 0 | 2016-02-11 | 2016-02-11 | 0 | 0 | 0 | [20 empty] | 2016-02-12 |  | 2017-02-13 |  | EXP | [6 empty] | 2016-11-18 | 2016-11-18 | 2016-12-05 | Connected |  | No
National Grid | HAVERHILL | 176496 | 1832 | 17.6 | Solar | 14_43L6 | 2016-02-05 | 2016-02-08 | 8 | 8 | 0 | 2016-02-19 | 2016-02-19 | 0 | 0 | 0 | [20 empty] | 2016-03-01 | 2016-02-07 | 2017-02-13 |  | EXP | [6 empty] | 2016-09-20 | 2016-09-20 | 2016-09-20 | Connected |  | No
National Grid | HAVERHILL | 176497 | 1832 | 34.2 | Solar | 14_43L6 | 2016-02-07 | 2016-02-08 | 5 | 5 | 0 | 2016-02-16 | 2016-02-16 | 0 | 0 | 0 | [20 empty] | 2016-03-02 |  | 2017-02-13 | Yes | EXP |  | 2016-06-28 | 2016-07-05 | 4 | 0 | 4 | 2016-04-11 | 2016-04-11 | 2016-08-11 | Connected |  | No
National Grid | ANDOVER | 176499 | 1810 | 98 | Solar | 14_50L3 | 2016-02-08 | 2016-02-10 | 5 | 5 | 0 | 2016-02-18 | 2016-02-26 | 6 | 0 | 6 | [20 empty] | 2016-02-26 |  | 2018-04-30 |  | EXP | [6 empty] | 2018-03-23 | 2018-03-23 | 2018-04-29 | Connected |  | No
National Grid | NORTH BILLERICA | 176502 | 1862 | 499.5 | Solar | 14_2385 | 2016-02-08 | 2016-02-10 | 3 | 3 | 0 | 2016-02-16 | 2018-02-14 | 493 | 0 | 493 | [22 empty] | 2017-02-15 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MANCHESTER | 176498 | 1944 | 22.8 | Solar | 12_28L2 | 2016-02-09 | 2016-02-10 | 1 | 1 | 0 | 2016-02-11 | 2016-02-11 | 0 | 0 | 0 | [20 empty] | 2016-02-12 |  | 2017-02-15 |  | EXP | [6 empty] | 2016-02-19 | 2016-02-19 | 2016-10-24 | Connected |  | No
National Grid | NORTON | 176500 | 2766 | 952 | Solar | 05_4L1 | 2016-02-09 | 2016-02-10 | 1 | 1 | 0 | [10 empty] | 2016-02-11 | 2016-03-09 | 18 | 0 | 18 | [5 empty] | 2016-08-04 | 2016-08-04 | 1 | 1 | 0 | 2016-09-22 |  | 2017-03-30 |  | STD | [6 empty] | 2017-03-27 | 2017-03-27 | 2017-03-29 | Connected |  | No
National Grid | BELCHERTOWN | 176501 | 1007 | 10 | Solar | 09_523L2 | 2016-02-09 | 2016-02-10 | 18 | 18 | 0 | 2016-03-08 | 2016-03-08 | 0 | 0 | 0 | [20 empty] | 2016-04-25 |  | 2017-02-15 |  | EXP | [6 empty] | 2016-04-25 | 2016-04-25 | 2016-09-28 | Connected |  | No
National Grid | LYNN | 176503 | 1905 | 64.8 | Solar | 12_21J32 | 2016-02-09 | 2016-02-10 | 2 | 2 | 0 | 2016-02-12 | 2016-02-12 | 0 | 0 | 0 | [20 empty] | 2016-02-17 |  | 2017-02-15 |  | EXP | [6 empty] | 2016-10-13 | 2016-10-13 | 2016-10-19 | Connected |  | No
National Grid | LOWELL | 176504 | 1854 | 150 | Solar | 14_2L3 | 2016-02-09 | 2016-02-10 | 7 | 7 | 0 | 2016-02-22 | 2016-02-22 | 0 | 0 | 0 | [20 empty] | 2016-02-26 |  | 2017-02-15 |  | EXP | [6 empty] | 2016-12-07 | 2016-12-07 | 2016-11-23 | Connected |  | No
National Grid | MARLBOROUGH | 176533 | 1752 | 7.6 | Solar | 05_311W5 | 2016-02-09 | 2016-02-10 | 3 | 3 | 0 | 2016-02-16 | 2016-02-16 | 0 | 0 | 0 | [20 empty] | 2016-03-08 | 2016-02-09 | 2017-02-15 |  | EXP | [6 empty] | 2016-07-08 | 2016-07-08 | 2016-07-12 | Connected |  | No
National Grid | MILFORD | 176534 | 1757 | 6 | Solar | 05_335W5 | 2016-02-09 | 2016-02-10 | 3 | 3 | 0 | 2016-02-16 | 2016-02-16 | 0 | 0 | 0 | [20 empty] | 2016-03-08 |  | 2017-02-15 | Yes | EXP |  | 2016-05-11 | 2016-05-13 | 2 | 0 | 2 | 2017-05-01 | 2017-05-01 | 2017-05-05 | Connected |  | No
National Grid | NORTH DIGHTON | 176535 | 2764 | 6 | Solar | 05_19W74 | 2016-02-09 | 2016-02-10 | 3 | 3 | 0 | 2016-02-16 | 2016-02-16 | 0 | 0 | 0 | [20 empty] | 2016-02-17 | 2016-02-09 | 2017-02-15 |  | EXP | [6 empty] | 2016-06-16 | 2016-06-16 | 2016-06-23 | Connected |  | No
National Grid | BRIDGEWATER | 176536 | 2324 | 10 | Solar | 07_912W55 | 2016-02-09 | 2016-02-10 | 3 | 3 | 0 | 2016-02-16 | 2016-02-16 | 0 | 0 | 0 | [20 empty] | 2016-03-08 | 2016-02-10 | 2017-12-15 | Yes | EXP |  | 2017-02-06 | 2017-02-15 | 7 | 0 | 7 | 2017-08-24 | 2017-08-24 | 2017-08-29 | Connected |  | Yes
National Grid | DIGHTON | 176537 | 2715 | 10 | Solar | 05_19W73 | 2016-02-10 | 2016-02-11 | 15 | 15 | 0 | 2016-03-04 | 2016-03-04 | 0 | 0 | 0 | [20 empty] | 2016-04-01 |  | 2017-02-16 | Yes | EXP |  | 2016-08-16 | 2016-08-30 | 10 | 0 | 10 | 2016-10-24 | 2016-10-24 | 2016-10-26 | Connected |  | No
National Grid | HAVERHILL | 176538 | 1832 | 34.2 | Solar | 14_43L6 | 2016-02-10 | 2016-02-11 | 5 | 5 | 0 | 2016-02-19 | 2017-11-22 | 434 | 0 | 434 | [20 empty] | 2016-03-02 |  | 2017-11-20 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HAVERHILL | 176539 | 1830 | 46.8 | Solar | 14_32J5 | 2016-02-10 | 2016-02-11 | 5 | 5 | 0 | 2016-02-19 | 2016-02-19 | 0 | 0 | 0 | [20 empty] | 2016-02-24 |  | 2017-09-16 |  | EXP | [6 empty] | 2017-03-23 | 2017-03-23 | 2017-03-23 | Connected |  | No
National Grid | HAVERHILL | 176540 | 1830 | 1250 | Solar | 14_47L1 | 2016-02-10 | 2016-02-11 | 2 | 2 | 0 | [10 empty] | 2016-02-16 | 2016-03-16 | 21 | 0 | 21 | [10 empty] | 2016-11-04 | 2016-02-10 | 2017-02-16 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SPENCER | 176541 | 1562 | 900 | Solar | 01_552L1 | 2016-02-10 | 2016-02-11 | 2 | 2 | 0 | [10 empty] | 2016-02-16 | 2016-03-08 | 15 | 0 | 15 | [10 empty] | 2016-11-04 |  | 2022-02-11 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | STOUGHTON | 176571 | 2072 | 300 | Solar | 07_913W69 | 2016-02-10 | 2016-02-11 | 1 | 1 | 0 | 2016-02-12 | 2016-11-02 | 180 | 0 | 180 | [22 empty] | 2017-02-16 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BEVERLY | 176572 | 1915 | 68 | Solar | 12_12L2 | 2016-02-11 | 2016-02-11 | 3 | 3 | 0 | 2016-02-17 | 2016-10-10 | 162 | 0 | 162 | [20 empty] | 2016-02-17 |  | 2017-02-16 |  | EXP | [6 empty] | 2016-09-29 | 2016-09-29 |  | Withdrawn |  | No
National Grid | HAVERHILL | 176573 | 1832 | 1462 | Solar | 14_48L4 | 2016-02-11 | 2016-02-12 | 2 | 2 | 0 | [27 empty] | 2017-02-17 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | ROCKLAND | 176574 | 2370 | 57.6 | Solar | 07_96W40 | 2016-02-11 | 2016-02-12 | 1 | 1 | 0 | 2016-02-16 | 2016-02-16 | 0 | 0 | 0 | [20 empty] | 2016-02-17 |  | 2017-02-17 |  | EXP | [6 empty] | 2016-11-29 | 2016-11-29 | 2016-12-01 | Connected |  | No
National Grid | SEEKONK | 176575 | 2771 | 6 | Solar | 05_7L1 | 2016-02-11 | 2016-02-12 | 0 | 0 | 0 | [26 empty] | 2016-02-11 | 2017-02-17 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SEEKONK | 176576 | 2771 | 6 | Solar | 05_7L1 | 2016-02-11 | 2016-02-12 | 9 | 9 | 0 | 2016-02-26 | 2016-02-26 | 0 | 0 | 0 | [20 empty] | 2016-03-31 |  | 2017-02-17 | Yes | EXP |  | 2016-08-11 | 2016-08-23 | 8 | 0 | 8 | 2016-10-28 | 2016-10-28 | 2016-11-03 | Connected |  | No
National Grid | HAVERHILL | 176616 | 1832 | 1335.6 | Solar | 14_48L4 | 2016-02-11 | 2016-02-17 | 3 | 3 | 0 | [10 empty] | 2016-02-22 | 2016-03-22 | 20 | 0 | 20 | [10 empty] | 2016-09-14 |  | 2017-02-22 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BEVERLY | 177522 | 1915 | 24 | Solar | 12_12L2 | 2016-02-11 | 2016-02-11 | 3 | 0 | 3 | 2016-02-17 | 2016-02-17 | 0 | 0 | 0 | [20 empty] | 2016-02-17 |  | 2017-10-04 |  | EXP | [6 empty] | 2016-09-29 | 2016-09-29 | 2016-10-05 | Connected |  | No
National Grid | BELCHERTOWN | 176577 | 1007 | 23 | Solar | 09_509L2 | 2016-02-12 | 2016-02-12 | 5 | 5 | 0 | 2016-02-22 | 2016-02-22 | 0 | 0 | 0 | [20 empty] | 2016-03-31 |  | 2017-02-17 |  | EXP | [6 empty] | 2016-03-31 | 2016-03-31 | 2016-10-06 | Connected |  | No
National Grid | NORTHAMPTON | 176579 | 1062 | 0 |  |  | 2016-02-12 | 2016-02-12 | 1 | 1 | 0 | [27 empty] | 2016-02-17 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTHAMPTON | 176608 | 1062 | 0 |  |  | 2016-02-12 | 2016-02-12 | 1 | 1 | 0 | [27 empty] | 2016-02-17 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | RUTLAND | 176609 | 1543 | 616 | Solar | 01_55W1 | 2016-02-12 | 2016-02-15 | 4 | 4 | 0 | [10 empty] | 2016-02-22 | 2016-03-22 | 20 | 0 | 20 | [11 empty] | 2016-02-12 | 2017-02-20 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | NORTHAMPTON | 176610 | 1062 | 2355 | Solar | 09_909W4 | 2016-02-12 | 2016-02-15 | 0 | 0 | 0 | [10 empty] | 2016-02-15 | 2016-03-11 | 18 | 0 | 18 | [10 empty] | 2016-09-07 |  | 2017-10-31 | Yes | STD |  | 2017-08-23 | 2017-10-12 | 34 | 0 | 34 | 2017-10-26 | 2017-10-26 | 2017-11-09 | Connected |  | No
National Grid | NORTHAMPTON | 176611 | 1062 | 488 | Solar | 09_909W4 | 2016-02-12 | 2016-02-15 | 0 | 0 | 0 | [10 empty] | 2016-02-15 | 2016-03-11 | 18 | 0 | 18 | [12 empty] | 2017-02-20 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ATTLEBORO | 176612 | 2703 | 250 | Solar | 05_9L1 | 2016-02-12 | 2016-02-15 | 10 | 10 | 0 | 2016-03-01 | 2016-03-01 | 0 | 0 | 0 | 2016-08-24 | 2016-09-21 | 19 | 1 | 18 | [5 empty] | 2016-08-24 | 2016-09-21 | 19 | 1 | 18 | [5 empty] | 2016-11-14 |  | 2017-05-12 |  | EXP | [6 empty] | 2017-05-02 | 2017-05-02 | 2017-05-12 | Connected |  | No
National Grid | SWAMPSCOTT | 176613 | 1907 | 32.4 | Solar | 12_22W1 | 2016-02-12 | 2016-02-15 | 3 | 3 | 0 | 2016-02-18 | 2016-02-18 | 0 | 0 | 0 | [20 empty] | 2016-04-29 |  | 2017-08-20 |  | EXP | [6 empty] | 2017-08-07 | 2017-08-07 | 2017-08-07 | Connected |  | No
National Grid | NORTH CHELMSFORD | 176615 | 1863 | 55 | Solar | 14_73L2 | 2016-02-15 | 2016-02-16 | 48 | 48 | 0 | 2016-04-26 | 2016-04-26 | 0 | 0 | 0 | [20 empty] | 2016-05-13 |  | 2017-02-21 |  | EXP | [6 empty] | 2016-09-14 | 2016-09-14 | 2016-09-26 | Connected |  | No
National Grid | WESTFORD | 176617 | 1886 | 200 | Solar | 14_57L1 | 2016-02-17 | 2016-02-17 | 3 | 3 | 0 | 2016-02-22 | 2016-02-22 | 0 | 0 | 0 | [20 empty] | 2016-03-25 | 2016-02-17 | 2017-02-22 |  | EXP | [6 empty] | 2016-05-31 | 2016-05-31 | 2016-05-31 | Connected |  | Yes
National Grid | SOMERSET | 176645 | 2726 | 5 | Solar | 05_19W72 | 2016-02-17 | 2016-02-17 | 3 | 3 | 0 | 2016-02-22 | 2016-02-22 | 0 | 0 | 0 | [20 empty] | 2016-03-21 |  | 2017-02-22 | Yes | EXP |  | 2016-06-01 | 2016-06-10 | 7 | 0 | 7 | 2016-03-21 | 2016-03-21 | 2017-01-03 | Connected |  | No
National Grid | HOLBROOK | 176646 | 2343 | 1988 | Solar | 07_97W3 | 2016-02-17 | 2016-02-18 | 0 | 0 | 0 | [10 empty] | 2016-02-18 | 2016-03-08 | 13 | 0 | 13 | [12 empty] | 2017-02-23 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HOLBROOK | 176647 | 2343 | 1260 | Solar | 07_97W3 | 2016-02-17 | 2016-02-18 | 0 | 0 | 0 | [10 empty] | 2016-02-18 | 2016-03-08 | 13 | 0 | 13 | [11 empty] | 2016-02-17 | 2017-02-23 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SOMERSET | 176648 | 2726 | 7.6 | Solar | 05_19W72 | 2016-02-17 | 2016-02-18 | 2 | 2 | 0 | 2016-02-22 | 2016-02-22 | 0 | 0 | 0 | [20 empty] | 2016-03-21 |  | 2017-02-23 | Yes | EXP |  | 2016-07-18 | 2016-07-26 | 6 | 0 | 6 | 2016-03-21 | 2016-03-21 | 2016-10-13 | Connected |  | No
National Grid | SOMERSET | 176649 | 2726 | 6 | Solar | 05_19W74 | 2016-02-17 | 2016-02-18 | 2 | 2 | 0 | 2016-02-22 | 2016-02-22 | 0 | 0 | 0 | [20 empty] | 2016-02-24 | 2016-02-17 | 2017-02-23 |  | EXP | [6 empty] | 2016-04-12 | 2016-04-12 | 2016-06-06 | Connected |  | No
National Grid | BROCKTON | 176650 | 2302 | 3 | Solar | 07_69J1 | 2016-02-17 | 2016-02-18 | 2 | 2 | 0 | 2016-02-22 | 2016-02-22 | 0 | 0 | 0 | [20 empty] | 2016-03-29 |  | 2017-02-23 | Yes | EXP |  | 2016-08-04 | 2016-08-30 | 18 | 0 | 18 | 2016-12-28 | 2016-12-28 | 2017-01-03 | Connected |  | No
National Grid | NORTH ANDOVER | 176651 | 1845 | 524 | Solar | 14_71L3 | 2016-02-17 | 2016-02-18 | 1 | 1 | 0 | [10 empty] | 2016-02-19 | 2016-03-08 | 12 | 0 | 12 | [11 empty] | 2016-02-17 | 2017-02-23 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | RANDOLPH | 176652 | 2368 | 6 | Solar | 07_97W3 | 2016-02-17 | 2016-02-18 | 2 | 2 | 0 | 2016-02-22 | 2016-02-25 | 3 | 0 | 3 | [20 empty] | 2016-03-31 |  | 2019-09-26 | Yes | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GRANBY | 176653 | 1033 | 10 | Solar | 09_527L1 | 2016-02-17 | 2016-02-18 | 3 | 3 | 0 | 2016-02-23 | 2017-02-01 | 234 | 0 | 234 | [20 empty] | 2016-03-28 |  | 2017-02-23 |  | EXP | [6 empty] | 2016-03-28 | 2016-03-28 |  | Withdrawn |  | No
National Grid | MILLBURY | 176683 | 1527 | 4.73 | Solar | 01_304W1 | 2016-02-18 | 2016-02-18 | 35 | 35 | 0 | 2016-04-08 | 2016-06-30 | 56 | 0 | 56 | [20 empty] | 2016-04-13 | 2016-02-18 | 2017-02-23 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOMERSET | 176684 | 2726 | 6 | Solar | 05_19W72 | 2016-02-18 | 2016-02-19 | 1 | 1 | 0 | 2016-02-22 | 2016-02-22 | 0 | 0 | 0 | [20 empty] | 2016-03-21 |  | 2017-02-24 | Yes | EXP |  | 2016-07-18 | 2016-08-05 | 14 | 0 | 14 | 2016-12-29 | 2016-12-29 | 2017-01-04 | Connected |  | No
National Grid | SAUGUS | 176687 | 1906 | 6 | Solar | 12_23W2 | 2016-02-18 | 2016-02-19 | 2 | 2 | 0 | 2016-02-23 | 2016-02-23 | 0 | 0 | 0 | [20 empty] | 2016-02-29 |  | 2017-02-24 |  | EXP | [6 empty] | 2016-08-25 | 2016-08-25 | 2016-08-25 | Connected |  | No
National Grid | CHARLTON | 176688 | 1507 | 6 | Solar | 01_406L1 | 2016-02-18 | 2016-02-19 | 2 | 2 | 0 | 2016-02-23 | 2016-02-23 | 0 | 0 | 0 | [20 empty] | 2016-02-25 |  | 2017-02-24 |  | EXP | [6 empty] | 2016-12-01 | 2016-12-01 | 2016-12-01 | Connected |  | No
National Grid | GLOUCESTER | 176689 | 1930 | 10 | Solar | 12_24J10 | 2016-02-19 | 2016-02-19 | 2 | 2 | 0 | 2016-02-23 | 2016-02-23 | 0 | 0 | 0 | [20 empty] | 2016-02-25 | 2016-02-19 | 2017-02-24 |  | EXP | [6 empty] | 2016-08-16 | 2016-08-16 | 2016-08-16 | Connected |  | No
National Grid | BROOKFIELD | 176690 | 1506 | 496 | Solar | 01_552L3 | 2016-02-19 | 2016-02-22 | 0 | 0 | 0 | [10 empty] | 2016-02-22 | 2016-03-16 | 17 | 0 | 17 | [10 empty] | 2016-09-28 | 2016-02-19 | 2018-12-28 | Yes | STD |  | 2018-12-19 | 2018-12-18 | 0 | 0 | 0 |  |  | 2018-12-13 | Connected |  | No
National Grid | BROOKFIELD | 176719 | 1506 | 496 | Solar | 01_552L3 | 2016-02-19 | 2016-02-22 | 0 | 0 | 0 | [10 empty] | 2016-02-22 | 2016-03-16 | 17 | 0 | 17 | [10 empty] | 2016-09-28 |  | 2018-12-28 | Yes | STD |  | 2018-12-19 | 2018-12-18 | 0 | 0 | 0 |  |  | 2018-12-24 | Connected |  | No
National Grid | WEYMOUTH | 176721 | 2190 | 10 | Solar | 07_12W3 | 2016-02-22 | 2016-02-23 | 73 | 73 | 0 | 2016-06-08 | 2016-06-08 | 0 | 0 | 0 | [20 empty] | 2016-06-14 |  | 2017-02-28 |  | EXP | [6 empty] | 2016-11-17 | 2016-11-17 | 2016-11-17 | Connected |  | No
National Grid | SAUGUS | 176722 | 1906 | 7.6 | Solar | 12_23W2 | 2016-02-22 | 2016-02-23 | 0 | 0 | 0 | 2016-02-23 | 2016-02-23 | 0 | 0 | 0 | [20 empty] | 2016-02-29 |  | 2017-02-28 |  | EXP | [6 empty] | 2016-08-17 | 2016-08-17 | 2016-08-19 | Connected |  | No
National Grid | WEYMOUTH | 176723 | 2188 | 10 | Solar | 07_12W2 | 2016-02-22 | 2016-02-23 | 4 | 4 | 0 | 2016-02-29 | 2016-02-29 | 0 | 0 | 0 | [20 empty] | 2016-03-03 | 2016-02-23 | 2017-02-28 |  | EXP | [6 empty] | 2016-06-14 | 2016-06-14 | 2016-06-15 | Connected |  | No
National Grid | STOCKBRIDGE | 176724 | 1262 | 668 | Solar | 09_1102W1 | 2016-02-23 | 2016-02-23 | 10 | 10 | 0 | [10 empty] | 2016-03-08 | 2016-04-05 | 19 | 9 | 10 | [5 empty] | 2016-09-20 | 2017-01-12 | 77 | 0 | 77 | 2017-11-03 |  | 2017-10-31 | Yes | STD |  | 2018-01-05 | 2018-02-09 | 24 | 0 | 24 | 2018-02-12 | 2018-02-12 | 2018-02-16 | Connected |  | No
National Grid | REHOBOTH | 176725 | 2769 | 500 | Solar | 05_3J2 | 2016-02-23 | 2016-02-23 | 0 | 0 | 0 | [10 empty] | 2016-02-23 | 2016-03-29 | 24 | 6 | 18 | [12 empty] | 2018-02-28 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTFORD | 176726 | 1886 | 179 | Solar | 14_58L2 | 2016-02-23 | 2016-02-23 | 0 | 0 | 0 | [10 empty] | 2016-02-23 | 2016-03-22 | 19 | 0 | 19 | [10 empty] | 2016-08-02 | 2016-02-23 | 2017-02-28 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH CHELMSFORD | 176727 | 1863 | 10 | Solar | 14_73L1 | 2016-02-23 | 2016-02-23 | 3 | 3 | 0 | 2016-02-26 | 2016-02-26 | 0 | 0 | 0 | [20 empty] | 2016-04-04 |  | 2017-08-28 | Yes | EXP |  | 2017-07-11 | 2017-07-31 | 14 | 0 | 14 | 2017-08-23 | 2017-08-23 | 2017-08-23 | Connected |  | No
National Grid | CHELMSFORD | 176756 | 1824 | 20.86 | Solar | 14_58L2 | 2016-02-23 | 2016-02-25 | 1 | 1 | 0 | 2016-02-26 | 2016-02-26 | 0 | 0 | 0 | [20 empty] | 2016-02-29 |  | 2017-03-01 |  | EXP | [6 empty] | 2016-11-01 | 2016-11-01 | 2016-11-01 | Connected |  | No
National Grid | REVERE | 176757 | 2151 | 17.6 | Solar | 12_16W7 | 2016-02-24 | 2016-02-25 | 1 | 1 | 0 | 2016-02-26 | 2016-02-26 | 0 | 0 | 0 | [20 empty] | 2016-03-01 |  | 2017-03-01 |  | EXP | [6 empty] | 2016-08-08 | 2016-08-08 | 2016-08-08 | Connected |  | No
National Grid | SOUTH GRAFTON | 176758 | 1560 | 6 | Solar | 05_320W3 | 2016-02-24 | 2016-02-25 | 2 | 2 | 0 | [10 empty] | 2016-02-29 | 2016-03-02 | 2 | 0 | 2 | [10 empty] | 2016-03-02 | 2016-02-24 | 2017-03-01 |  | STD | [6 empty] | 2016-05-13 | 2016-05-13 | 2016-05-18 | Connected |  | No
National Grid | HOLBROOK | 176759 | 2343 | 5 | Solar | 07_2W1 | 2016-02-24 | 2016-02-25 | 2 | 2 | 0 | 2016-02-29 | 2016-02-29 | 0 | 0 | 0 | [20 empty] | 2016-04-08 | 2016-02-24 | 2017-03-01 |  | EXP |  | 2017-01-11 | 2017-01-17 | 3 | 0 | 3 | 2016-04-08 | 2016-04-08 | 2017-01-30 | Connected |  | No
National Grid | PEPPERELL | 176760 | 1463 | 10 | Solar | 01_226L2 | 2016-02-24 | 2016-02-25 | 1 | 1 | 0 | 2016-02-26 | 2016-02-26 | 0 | 0 | 0 | [20 empty] | 2016-04-04 |  | 2017-03-01 | Yes | EXP |  | 2016-07-06 | 2016-08-27 | 38 | 0 | 38 | 2016-04-04 | 2016-04-04 | 2016-11-04 | Connected |  | No
National Grid | BILLERICA | 176761 | 1821 | 7.6 | Solar | 14_92L2 | 2016-02-24 | 2016-02-25 | 2 | 2 | 0 | 2016-02-29 | 2016-02-29 | 0 | 0 | 0 | [20 empty] | 2016-03-02 |  | 2017-03-01 |  | EXP | [6 empty] | 2016-08-29 | 2016-08-29 | 2016-08-29 | Connected |  | No
National Grid | ROCKLAND | 176762 | 2370 | 5 | Solar | 07_95W4 | 2016-02-24 | 2016-02-25 | 2 | 2 | 0 | 2016-02-29 | 2016-02-29 | 0 | 0 | 0 | [20 empty] | 2016-03-02 |  | 2017-03-01 |  | EXP | [6 empty] | 2016-07-27 | 2016-07-27 | 2016-08-01 | Connected |  | No
National Grid | LYNN | 176763 | 1905 | 6 | Solar | 12_29W1 | 2016-02-24 | 2016-02-25 | 1 | 1 | 0 | 2016-02-26 | 2017-02-27 | 248 | 0 | 248 | [20 empty] | 2016-04-28 | 2016-02-24 | 2017-05-01 |  | EXP | [6 empty] | 2016-04-28 | 2016-04-28 |  | Withdrawn |  | Yes
National Grid | WEBSTER | 176764 | 1570 | 6 | Solar | 01_412L2 | 2016-02-24 | 2016-02-25 | 5 | 5 | 0 | 2016-03-03 | 2016-03-03 | 0 | 0 | 0 | [20 empty] | 2016-04-04 |  | 2017-03-01 | Yes | EXP |  | 2016-08-04 | 2016-08-23 | 13 | 0 | 13 | 2016-04-04 | 2016-04-04 | 2016-09-15 | Connected |  | No
National Grid | WEST BRIDGEWATER | 176793 | 2379 | 11.4 | Solar | 07_797W19 | 2016-02-24 | 2016-02-25 | 5 | 5 | 0 | 2016-03-03 | 2017-02-16 | 238 | 0 | 238 | [20 empty] | 2016-04-18 | 2016-02-24 | 2017-03-01 |  | EXP | [6 empty] | 2016-04-18 | 2016-04-18 |  | Withdrawn |  | Yes
National Grid | BELLINGHAM | 176794 | 2019 | 7.6 | Solar | 05_108W60 | 2016-02-24 | 2016-02-25 | 2 | 2 | 0 | 2016-02-29 | 2016-02-29 | 0 | 0 | 0 | [20 empty] | 2016-04-06 | 2016-02-25 | 2017-03-01 | Yes | EXP |  | 2016-06-28 | 2016-09-15 | 55 | 0 | 55 | 2016-04-06 | 2016-04-06 | 2016-11-18 | Connected |  | No
National Grid | LEOMINSTER | 176795 | 1453 | 10 | Solar | 01_207W6 | 2016-02-25 | 2016-02-25 | 2 | 2 | 0 | 2016-02-29 | 2016-02-29 | 0 | 0 | 0 | [20 empty] | 2016-04-07 | 2016-02-25 | 2017-03-01 | Yes | EXP |  | 2016-07-18 | 2016-08-01 | 10 | 0 | 10 | 2016-04-07 | 2016-04-07 | 2016-08-03 | Connected |  | No
National Grid | FALL RIVER | 176796 | 2723 | 216 | Solar | 05_115W52 | 2016-02-25 | 2016-02-26 | 1 | 1 | 0 | 2016-02-29 | 2016-02-29 | 0 | 0 | 0 | [20 empty] | 2016-11-02 | 2016-02-25 | 2017-03-02 | Yes | EXP |  | 2017-01-05 | 2017-01-30 | 16 | 0 | 16 | 2017-05-05 | 2017-05-05 | 2017-05-08 | Connected |  | No
National Grid | TYNGSBORO | 176797 | 1879 | 6 | Solar | 01_210L1 | 2016-02-25 | 2016-02-26 | 1 | 1 | 0 | 2016-02-29 | 2017-05-01 | 291 | 0 | 291 | [20 empty] | 2016-04-04 | 2016-02-25 | 2017-05-31 | Yes | EXP |  | 2017-03-16 | 2017-05-08 | 36 | 0 | 36 | 2016-04-04 | 2016-04-04 |  | Withdrawn |  | No
National Grid | BROCKTON | 176798 | 2302 | 10 | Solar | 07_911W56 | 2016-02-25 | 2016-02-26 | 1 | 1 | 0 | 2016-02-29 | 2016-02-29 | 0 | 0 | 0 | [20 empty] | 2016-04-07 |  | 2017-03-02 | Yes | EXP |  | 2016-07-26 | 2016-08-05 | 8 | 0 | 8 | 2016-04-07 | 2016-04-07 | 2017-02-08 | Connected |  | No
National Grid | STOUGHTON | 176799 | 2072 | 11.4 | Solar | 07_913W17 | 2016-02-25 | 2016-02-26 | 4 | 4 | 0 | 2016-03-03 | 2016-03-03 | 0 | 0 | 0 | [20 empty] | 2016-03-04 |  | 2017-03-02 |  | EXP | [6 empty] | 2016-11-03 | 2016-11-03 | 2016-11-07 | Connected |  | No
National Grid | ORANGE | 176800 | 1364 | 288 | Solar | 09_702W3 | 2016-02-25 | 2016-02-29 | 3 | 3 | 0 | 2016-03-03 | 2016-03-03 | 0 | 0 | 0 | 2016-07-01 | 2016-08-03 | 22 | 1 | 21 | [5 empty] | 2016-07-01 | 2016-08-03 | 22 | 1 | 21 | [5 empty] | 2017-03-13 |  | 2018-06-29 |  | EXP | [6 empty] | 2017-12-07 | 2017-12-07 | 2017-12-07 | Connected |  | No
National Grid | BELLINGHAM | 176831 | 2019 | 6 | Solar | 05_108W60 | 2016-02-25 | 2016-02-29 | 3 | 3 | 0 | 2016-03-03 | 2016-03-03 | 0 | 0 | 0 | [20 empty] | 2016-04-12 | 2016-02-25 | 2017-03-05 |  | EXP | [6 empty] | 2016-04-12 | 2016-04-12 | 2017-02-22 | Connected |  | No
National Grid | TYNGSBORO | 177964 | 1879 | 6 | Solar | 01_210L1 | 2016-02-25 | 2016-02-25 | 0 | 0 | 0 | 2016-02-29 | 2016-02-29 | 0 | 0 | 0 | [20 empty] | 2016-04-04 |  | 2018-04-26 | Yes | EXP |  | 2017-03-16 | 2017-05-08 | 36 | 0 | 36 | 2017-04-21 | 2017-04-21 | 2017-06-20 | Connected |  | No
National Grid | WHITINSVILLE | 176832 | 1588 | 10 | Solar | 05_320W3 | 2016-02-26 | 2016-02-29 | 6 | 6 | 0 | 2016-03-08 | 2016-03-08 | 0 | 0 | 0 | [20 empty] | 2016-03-15 |  | 2017-03-05 |  | EXP | [6 empty] | 2016-06-01 | 2016-06-01 | 2016-06-17 | Connected |  | No
National Grid | MARLBOROUGH | 176833 | 1752 | 10 | Solar | 05_311W6 | 2016-02-28 | 2016-02-29 | 3 | 3 | 0 | 2016-03-03 | 2016-03-03 | 0 | 0 | 0 | [20 empty] | 2016-03-04 |  | 2017-03-05 |  | EXP | [6 empty] | 2016-07-19 | 2016-07-19 | 2016-07-19 | Connected |  | No
National Grid | SOUTHBOROUGH | 176834 | 1772 | 650 | Solar | 05_310W6 | 2016-02-29 | 2016-02-29 | 7 | 7 | 0 | [10 empty] | 2016-03-08 | 2016-05-10 | 43 | 43 | 0 | [10 empty] | 2017-02-17 |  | 2017-12-08 |  | STD | [6 empty] | 2017-12-07 | 2017-12-07 | 2017-12-14 | Connected |  | No
National Grid | SOMERSET | 176835 | 2726 | 3.8 | Solar | 05_19W72 | 2016-02-29 | 2016-03-01 | 2 | 2 | 0 | 2016-03-03 | 2016-03-03 | 0 | 0 | 0 | [20 empty] | 2016-04-12 |  | 2017-03-06 |  | EXP | [6 empty] | 2016-04-12 | 2016-04-12 | 2016-08-09 | Connected |  | No
National Grid | NORTHBOROUGH | 176836 | 1532 | 3.75 | Solar | 05_314W4 | 2016-02-29 | 2016-03-01 | 5 | 5 | 0 | 2016-03-08 | 2016-03-08 | 0 | 0 | 0 | [20 empty] | 2016-03-15 |  | 2017-03-06 |  | EXP | [6 empty] | 2016-05-10 | 2016-05-10 | 2016-05-12 | Connected |  | No
National Grid | BELCHERTOWN | 176837 | 1007 | 10 | Solar | 09_523L2 | 2016-02-29 | 2016-03-01 | 2 | 2 | 0 | 2016-03-03 | 2016-03-03 | 0 | 0 | 0 | [20 empty] | 2016-04-12 |  | 2017-03-06 |  | EXP | [6 empty] | 2016-04-12 | 2016-04-12 | 2016-07-18 | Connected |  | No
National Grid | NANTUCKET | 176867 | 2554 | 21.75 | Solar | 04_101L8 | 2016-03-01 | 2016-03-01 | 2 | 2 | 0 | 2016-03-03 | 2016-03-03 | 0 | 0 | 0 | [20 empty] | 2016-03-07 |  | 2017-03-06 |  | EXP | [6 empty] | 2016-05-23 | 2016-05-23 | 2016-08-08 | Connected |  | No
National Grid | ORANGE | 176868 | 1364 | 499 | Solar | 09_702W3 | 2016-03-01 | 2016-03-02 | 1 | 1 | 0 | [10 empty] | 2016-03-03 | 2016-05-12 | 48 | 33 | 15 | [12 empty] | 2017-03-07 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | MALDEN | 176869 | 2148 | 10 | Solar | 12_5C3 | 2016-03-01 | 2016-03-02 | 1 | 1 | 0 | 2016-03-03 | 2016-05-25 | 57 | 0 | 57 | [20 empty] | 2016-04-18 | 2016-03-01 | 2017-03-07 |  | EXP | [6 empty] | 2016-04-18 | 2016-04-18 |  | Withdrawn |  | Yes
National Grid | DRACUT | 176870 | 1826 | 7.6 | Solar | 14_75L5 | 2016-03-01 | 2016-03-02 | 1 | 1 | 0 | 2016-03-03 | 2016-03-03 | 0 | 0 | 0 | [20 empty] | 2016-04-18 | 2016-03-01 | 2017-03-07 | Yes | EXP |  | 2016-09-30 | 2016-10-18 | 11 | 0 | 11 | 2016-04-18 | 2016-04-18 | 2016-10-17 | Connected |  | No
National Grid | LEOMINSTER | 176871 | 1453 | 6 | Solar | 01_225W3 | 2016-03-01 | 2016-03-02 | 2 | 2 | 0 | 2016-03-04 | 2016-03-04 | 0 | 0 | 0 | [20 empty] | 2016-04-22 |  | 2017-03-07 | Yes | EXP |  | 2016-07-07 | 2016-07-27 | 14 | 0 | 14 | 2017-01-19 | 2017-01-19 | 2017-01-19 | Connected |  | No
National Grid | RUTLAND | 176872 | 1543 | 10 | Solar | 01_55W1 | 2016-03-01 | 2016-03-02 | 2 | 2 | 0 | 2016-03-04 | 2016-03-04 | 0 | 0 | 0 | [20 empty] | 2016-03-07 |  | 2017-03-07 |  | EXP | [6 empty] | 2016-08-02 | 2016-08-02 | 2016-08-08 | Connected |  | No
National Grid | WEYMOUTH | 176874 | 2188 | 10 | Solar | 07_12W2 | 2016-03-02 | 2016-03-02 | 4 | 4 | 0 | 2016-03-08 | 2017-01-13 | 212 | 0 | 212 | [20 empty] | 2016-03-14 | 2016-03-02 | 2017-03-07 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOMERSET | 176875 | 2726 | 7.6 | Solar | 05_11W82 | 2016-03-02 | 2016-03-02 | 30 | 30 | 0 | 2016-04-14 | 2016-04-14 | 0 | 0 | 0 | [20 empty] | 2016-04-26 |  | 2017-03-07 | Yes | EXP |  | 2016-09-06 | 2016-09-21 | 11 | 0 | 11 | 2016-11-04 | 2016-11-04 | 2016-11-09 | Connected |  | No
National Grid | SEEKONK | 176903 | 2771 | 4.73 | Solar | 05_6J1 | 2016-03-03 | 2016-03-03 | 18 | 18 | 0 | 2016-03-30 | 2016-03-30 | 0 | 0 | 0 | [20 empty] | 2016-04-06 |  | 2017-03-08 |  | EXP | [6 empty] | 2016-11-30 | 2016-11-30 | 2016-12-02 | Connected |  | No
National Grid | EAST LONGMEADOW | 176904 | 1028 | 468 | Solar | 09_522L2 | 2016-03-03 | 2016-03-04 | 2 | 2 | 0 | [10 empty] | 2016-03-08 | 2016-03-24 | 11 | 0 | 11 | [10 empty] | 2016-07-18 |  | 2016-12-28 |  | STD | [6 empty] | 2016-08-01 | 2016-08-01 | 2017-01-05 | Connected |  | No
National Grid | FOXBOROUGH | 178789 | 2035 | 1775 | Solar | 05_3431W2 | 2016-03-04 | 2016-03-04 | 1 | 1 | 0 | [10 empty] | 2016-03-07 | 2016-04-21 | 31 | 17 | 14 | [11 empty] | 2016-03-07 | 2017-03-09 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | SOMERSET | 176359 | 2726 | 5 | Solar | 05_18J5 | 2016-03-07 | 2016-03-08 | 2 | 2 | 0 | 2016-03-10 | 2016-03-10 | 0 | 0 | 0 | [20 empty] | 2016-04-22 |  | 2017-03-13 | Yes | EXP |  | 2016-07-27 | 2016-08-15 | 13 | 0 | 13 | 2016-04-22 | 2016-04-22 | 2016-10-19 | Connected |  | No
National Grid | LEOMINSTER | 176908 | 1453 | 231 | Solar | 01_219W5 | 2016-03-07 | 2016-03-07 | 4 | 4 | 0 | 2016-03-11 | 2017-12-01 | 425 | 14 | 411 | [20 empty] | 2016-04-27 |  | 2017-03-12 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | DIGHTON | 176362 | 2715 | 10 | Solar | 05_19W73 | 2016-03-08 | 2016-03-10 | 1 | 1 | 0 | 2016-03-11 | 2016-03-11 | 0 | 0 | 0 | [20 empty] | 2016-03-14 | 2016-03-08 | 2017-03-15 |  | EXP | [6 empty] | 2016-07-15 | 2016-07-15 | 2016-07-15 | Connected |  | No
National Grid | AUBURN | 176363 | 1501 | 7.6 | Solar | 01_406L2 | 2016-03-08 | 2016-03-10 | 3 | 3 | 0 | 2016-03-15 | 2016-03-15 | 0 | 0 | 0 | [20 empty] | 2016-03-30 |  | 2018-01-15 | Yes | EXP |  | 2017-05-19 | 2017-06-02 | 9 | 0 | 9 | 2017-08-11 | 2017-08-11 | 2017-08-11 | Connected |  | No
National Grid | MONSON | 176364 | 1057 | 10 | Solar | 09_507L1 | 2016-03-08 | 2016-03-10 | 3 | 3 | 0 | 2016-03-15 | 2017-02-16 | 230 | 0 | 230 | [20 empty] | 2016-03-30 |  | 2017-03-15 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BLACKSTONE | 176365 | 1504 | 3.8 | Solar | 05_108W60 | 2016-03-08 | 2016-03-10 | 3 | 3 | 0 | 2016-03-15 | 2017-02-13 | 227 | 0 | 227 | [20 empty] | 2016-03-31 | 2016-03-08 | 2017-03-15 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BRIDGEWATER | 176910 | 2324 | 499 | Solar | 07_797W1 | 2016-03-08 | 2016-03-09 | 0 | 0 | 0 | [10 empty] | 2016-03-09 | 2016-03-18 | 6 | 0 | 6 | [10 empty] | 2016-07-05 | 2016-03-09 | 2017-12-15 | Yes | STD |  | 2016-11-10 | 2017-08-09 | 185 | 0 | 185 | 2016-12-21 | 2016-12-21 | 2017-12-08 | Connected |  | No
National Grid | COHASSET | 176361 | 2025 | 420 | Solar | 07_96W41 | 2016-03-09 | 2016-03-10 | 0 | 0 | 0 | 2016-03-10 | 2016-03-10 | 0 | 0 | 0 | 2016-04-18 | 2016-06-17 | 42 | 12 | 30 | [5 empty] | 2016-04-18 | 2016-06-17 | 42 | 12 | 30 | [5 empty] | 2016-07-06 |  | 2017-09-08 |  | EXP |  | 2017-06-22 | 2017-08-10 | 34 | 0 | 34 | 2017-08-29 | 2017-08-29 | 2017-08-29 | Connected |  | No
National Grid | SOUTH GRAFTON | 176366 | 1560 | 10 | Solar | 01_304W2 | 2016-03-09 | 2016-03-10 | 3 | 3 | 0 | 2016-03-15 | 2016-03-15 | 0 | 0 | 0 | [20 empty] | 2016-03-16 |  | 2017-03-15 |  | EXP | [6 empty] | 2016-08-29 | 2016-08-29 | 2016-08-29 | Connected |  | No
National Grid | HOLLAND | 176367 | 1521 | 10 | Solar | 09_516L1 | 2016-03-10 | 2016-03-10 | 2 | 2 | 0 | 2016-03-14 | 2016-03-14 | 0 | 0 | 0 | [20 empty] | 2016-04-26 | 2016-03-10 | 2017-03-15 |  | EXP | [6 empty] | 2016-04-26 | 2016-04-26 | 2016-11-14 | Connected |  | No
National Grid | DUNSTABLE | 176396 | 1827 | 10 | Solar | 01_210L1 | 2016-03-10 | 2016-03-10 | 5 | 5 | 0 | 2016-03-17 | 2016-03-17 | 0 | 0 | 0 | [20 empty] | 2016-04-01 | 2016-03-10 | 2017-03-15 | Yes | EXP |  | 2016-09-23 | 2016-11-08 | 31 | 0 | 31 | 2016-06-30 | 2016-06-30 | 2016-07-11 | Connected |  | No
National Grid | WORCESTER | 176397 | 1605 | 2649 | Natural Gas | 01_HT61 | 2016-03-10 | 2016-03-11 | 3 | 3 | 0 | [10 empty] | 2016-03-16 | 2016-06-13 | 60 | 44 | 16 | [5 empty] | 2016-10-04 | 2016-12-13 | 47 | 13 | 34 | 2017-01-25 |  | 2019-01-31 | Yes | STD |  | 2018-01-03 | 2018-07-26 | 204 | 0 | 204 | 2018-01-25 | 2018-01-25 | 2019-01-10 | Connected |  | No
National Grid | WESTMINSTER | 176398 | 1473 | 10 | Solar | 01_602W2 | 2016-03-10 | 2016-03-11 | 1 | 1 | 0 | 2016-03-14 | 2016-03-14 | 0 | 0 | 0 | [20 empty] | 2016-03-15 | 2016-03-10 | 2017-03-16 |  | EXP | [6 empty] | 2016-04-28 | 2016-04-28 | 2016-06-13 | Connected |  | No
National Grid | GARDNER | 176399 | 1440 | 7.6 | Solar | 01_607W4 | 2016-03-10 | 2016-03-14 | 0 | 0 | 0 | 2016-03-14 | 2016-03-14 | 0 | 0 | 0 | [20 empty] | 2016-04-25 |  | 2017-03-19 | Yes | EXP |  | 2016-07-18 | 2016-08-11 | 18 | 0 | 18 | 2016-04-25 | 2016-04-25 | 2016-09-08 | Connected |  | No
National Grid | SUTTON | 176400 | 1590 | 7.6 | Solar | 01_304W2 | 2016-03-11 | 2016-03-14 | 3 | 3 | 0 | 2016-03-18 | 2016-03-18 | 0 | 0 | 0 | [20 empty] | 2016-04-04 |  | 2017-03-19 |  | EXP | [6 empty] | 2016-09-01 | 2016-09-01 | 2016-09-01 | Connected |  | No
National Grid | BELLINGHAM | 176401 | 2019 | 3.8 | Solar | 05_344W4 | 2016-03-11 | 2016-03-14 | 3 | 3 | 0 | 2016-03-17 | 2017-02-16 | 228 | 0 | 228 | [20 empty] | 2016-04-04 |  | 2017-03-19 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WILBRAHAM | 176402 | 1095 | 6 | Solar | 09_507L2 | 2016-03-11 | 2016-03-14 | 3 | 3 | 0 | 2016-03-17 | 2017-02-13 | 225 | 0 | 225 | [20 empty] | 2016-04-01 |  | 2017-03-19 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MILLBURY | 176403 | 1527 | 3.8 | Solar | 01_304W5 | 2016-03-11 | 2016-03-14 | 3 | 3 | 0 | 2016-03-17 | 2017-02-27 | 234 | 0 | 234 | [20 empty] | 2016-04-01 |  | 2017-03-19 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | UPTON | 176431 | 1568 | 6 | Solar | 05_320W1 | 2016-03-11 | 2016-03-14 | 3 | 3 | 0 | 2016-03-17 | 2016-03-17 | 0 | 0 | 0 | [20 empty] | 2016-04-04 | 2016-03-14 01:00 | 2017-03-19 |  | EXP | [6 empty] | 2016-10-28 | 2016-10-28 | 2016-11-01 | Connected |  | No
National Grid | LEOMINSTER | 176432 | 1453 | 1965 | Natural Gas | 01_219W6 | 2016-03-14 01:00 | 2016-03-14 | 13 | 13 | 0 | [10 empty] | 2016-04-01 | 2016-06-23 | 56 | 38 | 18 | [10 empty] | 2017-03-20 | 2016-03-16 01:00 | 2019-06-30 | Yes | STD |  | 2017-10-11 | 2018-04-04 | 103 | 0 | 103 | 2018-01-05 | 2018-01-05 | 2018-08-08 | Connected |  | No
National Grid | BLACKSTONE | 176436 | 1504 | 6 | Solar | 05_321W9 | 2016-03-16 01:00 | 2016-03-16 | 6 | 6 | 0 | 2016-03-25 | 2016-03-25 | 0 | 0 | 0 | [20 empty] | 2016-04-12 | 2016-03-16 01:00 | 2017-03-21 |  | EXP |  | 2016-04-19 | 2016-05-31 | 29 | 0 | 29 | 2016-10-28 | 2016-10-28 | 2016-11-01 | Connected |  | No
National Grid | BROCKTON | 176437 | 2302 | 10 | Solar | 07_712J1 | 2016-03-16 01:00 | 2016-03-16 | 3 | 3 | 0 | 2016-03-22 | 2016-03-22 | 0 | 0 | 0 | [20 empty] | 2016-04-12 |  | 2017-03-21 | Yes | EXP |  | 2016-12-14 | 2017-01-05 | 14 | 0 | 14 | 2017-01-19 | 2017-01-19 | 2017-01-23 | Connected |  | No
National Grid | SAUGUS | 176438 | 1906 | 10 | Solar | 12_25W1 | 2016-03-16 01:00 | 2016-03-17 | 2 | 2 | 0 | 2016-03-22 | 2016-03-22 | 0 | 0 | 0 | [20 empty] | 2016-04-04 | 2016-03-17 01:00 | 2017-03-22 |  | EXP | [6 empty] | 2016-07-29 | 2016-07-29 | 2016-07-29 | Connected |  | No
National Grid | STOUGHTON | 176468 | 2072 | 6 | Solar | 07_913W67 | 2016-03-17 01:00 | 2016-03-18 | 2 | 2 | 0 | 2016-03-22 | 2016-03-22 | 0 | 0 | 0 | [20 empty] | 2016-04-12 | 2016-03-17 01:00 | 2017-03-23 |  | EXP |  | 2017-01-25 | 2017-02-11 | 13 | 0 | 13 | 2017-03-15 | 2017-03-15 | 2017-03-17 | Connected |  | No
National Grid | BILLERICA | 176469 | 1821 | 10 | Solar | 14_92L6 | 2016-03-17 01:00 | 2016-03-18 | 2 | 2 | 0 | 2016-03-22 | 2016-03-22 | 0 | 0 | 0 | [20 empty] | 2016-04-12 |  | 2017-03-23 | Yes | EXP |  | 2016-06-21 | 2016-07-29 | 27 | 0 | 27 | 2016-09-20 | 2016-09-20 | 2016-09-23 | Connected |  | No
National Grid | METHUEN | 176470 | 1844 | 252 | Solar | 14_74L3 | 2016-03-20 01:00 | 2016-03-21 | 13 | 13 | 0 | 2016-04-07 | 2017-10-19 | 383 | 0 | 383 | [20 empty] | 2016-04-29 | 2016-03-20 01:00 | 2017-12-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEOMINSTER | 176471 | 1453 | 7.6 | Solar | 01_207W6 | 2016-03-20 01:00 | 2016-03-21 | 3 | 3 | 0 | 2016-03-24 | 2016-03-24 | 0 | 0 | 0 | [20 empty] | 2016-04-12 |  | 2017-03-26 |  | EXP |  | 2016-11-08 | 2016-11-29 | 13 | 0 | 13 | 2017-01-19 | 2017-01-19 | 2017-01-19 | Connected |  | No
National Grid | WARE | 176472 | 1082 | 375 | Hydro | 09_501L1 | 2016-03-21 01:00 | 2016-03-22 | 5 | 5 | 0 | [10 empty] | 2016-03-29 | 2016-05-13 | 32 | 13 | 19 | [12 empty] | 2017-03-27 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | FALL RIVER | 176473 | 2721 | 72 | Solar | 05_115W44 | 2016-03-22 01:00 | 2016-03-23 | 3 | 3 | 0 | 2016-03-28 | 2016-03-28 | 0 | 0 | 0 | [20 empty] | 2016-05-10 |  | 2016-09-30 |  | EXP | [6 empty] | 2016-09-21 | 2016-09-21 | 2016-10-04 | Connected |  | No
National Grid | NORTH CHELMSFORD | 176474 | 1863 | 21.8 | Solar | 14_2L3 | 2016-03-23 01:00 | 2016-03-24 | 3 | 3 | 0 | 2016-03-29 | 2016-03-29 | 0 | 0 | 0 | [20 empty] | 2016-04-29 |  | 2017-03-29 |  | EXP | [6 empty] | 2016-08-29 | 2016-08-29 | 2016-08-29 | Connected |  | No
National Grid | HAVERHILL | 176476 | 1830 | 100 | Solar | 14_31J5 | 2016-03-24 01:00 | 2016-03-25 | 9 | 9 | 0 | 2016-04-07 | 2018-03-13 | 468 | 17 | 451 | [20 empty] | 2016-05-17 | 2016-03-24 01:00 | 2018-05-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTMINSTER | 176505 | 1473 | 540 | Solar | 01_609W1 | 2016-03-24 01:00 | 2016-03-25 | 2 | 2 | 0 | [10 empty] | 2016-03-29 | 2016-05-26 | 41 | 37 | 4 | [10 empty] | 2016-12-15 | 2016-03-24 01:00 | 2018-12-31 | Yes | STD |  | 2018-12-12 | 2019-01-02 | 21 | 0 | 21 |  |  | 2018-12-31 | Connected |  | No
National Grid | GARDNER | 176507 | 1440 | 6 | Solar | 01_607W1 | 2016-03-24 01:00 | 2016-03-25 | 36 | 36 | 0 | 2016-05-17 | 2016-05-17 | 0 | 0 | 0 | [20 empty] | 2016-06-06 |  | 2017-03-30 | Yes | EXP |  | 2016-07-28 | 2016-09-23 | 40 | 0 | 40 | 2016-11-08 | 2016-11-08 | 2016-11-10 | Connected |  | No
National Grid | NORTH GRAFTON | 176508 | 1536 | 5 | Solar | 01_304W1 | 2016-03-24 01:00 | 2016-03-25 | 3 | 3 | 0 | 2016-03-30 | 2016-03-30 | 0 | 0 | 0 | [20 empty] | 2016-04-06 |  | 2017-03-30 |  | EXP | [6 empty] | 2016-10-05 | 2016-10-05 | 2016-10-11 | Connected |  | No
National Grid | TEWKSBURY | 176509 | 1876 | 5.5 | Solar | 14_70L8 | 2016-03-28 01:00 | 2016-03-29 | 3 | 3 | 0 | 2016-04-01 | 2017-01-17 | 196 | 0 | 196 | [20 empty] | 2016-04-20 |  | 2017-04-03 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CLINTON | 176510 | 1510 | 10 | Solar | 01_216W4 | 2016-03-28 01:00 | 2016-03-29 | 3 | 3 | 0 | 2016-04-01 | 2016-04-01 | 0 | 0 | 0 | [20 empty] | 2016-04-06 |  | 2017-04-03 |  | EXP | [6 empty] | 2016-08-11 | 2016-08-11 | 2016-08-11 | Connected |  | No
National Grid | RUTLAND | 176511 | 1543 | 10 | Solar | 01_55W1 | 2016-03-28 01:00 | 2016-03-29 | 3 | 3 | 0 | 2016-04-01 | 2016-04-01 | 0 | 0 | 0 | [20 empty] | 2016-04-06 | 2016-03-29 01:00 | 2017-04-03 |  | EXP | [6 empty] | 2016-08-31 | 2016-08-31 | 2016-08-31 | Connected |  | No
National Grid | LAWRENCE | 176512 | 1843 | 7.6 | Solar | 14_61L3 | 2016-03-29 01:00 | 2016-03-30 | 2 | 2 | 0 | 2016-04-01 | 2016-04-01 | 0 | 0 | 0 | [20 empty] | 2016-04-19 |  | 2017-08-04 | Yes | EXP |  | 2016-08-26 | 2017-01-11 | 92 | 0 | 92 | 2017-05-31 | 2017-05-31 | 2017-05-31 | Connected |  | No
National Grid | HAVERHILL | 176513 | 1830 | 99.9 | Solar | 14_31J6 | 2016-03-30 01:00 | 2016-04-01 | 4 | 4 | 0 | 2016-04-07 | 2018-02-14 | 457 | 77 | 380 | [20 empty] | 2016-08-16 |  | 2017-12-06 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | TEWKSBURY | 176542 | 1876 | 10 | Solar | 14_59L3 | 2016-03-30 01:00 | 2016-04-01 | 2 | 2 | 0 | 2016-04-05 | 2016-09-30 | 123 | 0 | 123 | [20 empty] | 2016-04-19 |  | 2017-04-06 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BRADFORD | 176543 | 1835 | 476 | Solar | 14_43L3 | 2016-03-30 01:00 | 2016-04-01 | 4 | 4 | 0 | 2016-04-07 | 2018-02-14 | 457 | 0 | 457 | [20 empty] | 2016-05-03 |  | 2017-10-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | EAST BRIDGEWATER | 176544 | 2333 | 10 | Solar | 07_797W42 | 2016-03-31 01:00 | 2016-04-01 | 2 | 2 | 0 | 2016-04-05 | 2016-04-05 | 0 | 0 | 0 | [20 empty] | 2016-04-06 |  | 2017-04-06 |  | EXP | [6 empty] | 2016-09-29 | 2016-09-29 | 2016-10-03 | Connected |  | No
National Grid | AUBURN | 176545 | 1501 | 10 | Solar | 01_406L2 | 2016-03-31 01:00 | 2016-04-01 | 2 | 2 | 0 | 2016-04-05 | 2017-02-06 | 208 | 0 | 208 | [20 empty] | 2016-04-19 | 2016-04-03 01:00 | 2017-04-06 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 176546 | 1607 | 1992 | Solar | 01_8W2 | 2016-04-03 01:00 | 2016-04-04 | 0 | 0 | 0 | [10 empty] | 2016-04-04 | 2016-05-09 | 24 | 5 | 19 | [10 empty] | 2016-08-29 | 2016-04-05 01:00 | 2018-11-14 | Yes | STD | [8 empty] | 2018-11-14 | Connected |  | No
National Grid | EAST BRIDGEWATER | 176549 | 2333 | 9.6 | Solar | 07_797W23 | 2016-04-05 01:00 | 2016-04-05 | 1 | 1 | 0 | 2016-04-06 | 2016-04-06 | 0 | 0 | 0 | [20 empty] | 2016-04-19 | 2016-04-05 01:00 | 2017-04-10 | Yes | EXP |  | 2016-11-10 | 2016-11-21 | 6 | 0 | 6 | 2016-11-28 | 2016-11-28 | 2016-11-30 | Connected |  | No
National Grid | NORTH BILLERICA | 176550 | 1862 | 10 | Solar | 14_70L1 | 2016-04-05 01:00 | 2016-04-06 | 1 | 1 | 0 | 2016-04-07 | 2016-04-07 | 0 | 0 | 0 | [20 empty] | 2016-04-19 | 2016-04-05 01:00 | 2017-04-11 | Yes | EXP |  | 2016-09-06 | 2016-09-14 | 6 | 0 | 6 | 2016-12-07 | 2016-12-07 | 2016-12-07 | Connected |  | No
National Grid | RANDOLPH | 176580 | 2368 | 3.8 | Solar | 07_97W2 | 2016-04-05 01:00 | 2016-04-06 | 1 | 1 | 0 | 2016-04-07 | 2016-04-07 | 0 | 0 | 0 | [20 empty] | 2016-04-26 |  | 2017-04-11 |  | EXP |  | 2016-09-15 | 2016-10-18 | 22 | 0 | 22 | 2016-08-11 | 2016-08-11 | 2016-12-02 | Connected |  | No
National Grid | SWANSEA | 176583 | 2777 | 7.6 | Solar | 05_11W81 | 2016-04-07 01:00 | 2016-04-07 | 4 | 4 | 0 | 2016-04-13 | 2017-02-01 | 199 | 0 | 199 | [20 empty] | 2016-04-26 | 2016-04-07 01:00 | 2017-04-12 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHARLTON | 176584 | 1507 | 9.5 | Solar | 01_415L2 | 2016-04-07 01:00 | 2016-04-08 | 31 | 31 | 0 | 2016-05-24 | 2016-05-24 | 0 | 0 | 0 | [20 empty] | 2016-06-06 | 2016-04-08 01:00 | 2017-04-13 | Yes | EXP |  | 2016-11-30 | 2016-12-08 | 6 | 0 | 6 | 2017-05-10 | 2017-05-10 | 2017-05-15 | Connected |  | No
National Grid | WORCESTER | 176587 | 1604 | 6 | Solar | 01_10J383 | 2016-04-08 01:00 | 2016-04-11 | 2 | 2 | 0 | 2016-04-13 | 2016-04-13 | 0 | 0 | 0 | [20 empty] | 2016-04-26 | 2016-04-11 01:00 | 2017-04-16 | Yes | EXP |  | 2016-09-14 | 2016-10-03 | 13 | 0 | 13 | 2016-10-19 | 2016-10-19 | 2016-10-19 | Connected |  | No
National Grid | BROCKTON | 176588 | 2302 | 3 | Solar | 07_911W56 | 2016-04-11 01:00 | 2016-04-11 | 2 | 2 | 0 | 2016-04-13 | 2016-04-13 | 0 | 0 | 0 | [20 empty] | 2016-04-26 | 2016-04-11 01:00 | 2017-04-16 |  | EXP | [6 empty] | 2016-09-23 | 2016-09-23 | 2016-09-28 | Connected |  | No
National Grid | MILLBURY | 176619 | 1527 | 10 | Solar | 01_304W4 | 2016-04-11 01:00 | 2016-04-12 | 2 | 2 | 0 | 2016-04-14 | 2016-04-14 | 0 | 0 | 0 | [20 empty] | 2016-04-26 |  | 2017-10-17 | Yes | EXP |  | 2017-06-30 | 2017-06-28 | 0 | 0 | 0 | 2017-07-14 | 2017-07-14 | 2017-07-14 | Connected |  | No
National Grid | HANOVER | 176618 | 2339 | 1000 | Solar | 07_95W2 | 2016-04-12 01:00 | 2016-04-12 | 0 | 0 | 0 | [10 empty] | 2016-04-12 | 2016-05-20 | 27 | 15 | 12 | [11 empty] | 2016-04-12 01:00 | 2017-04-17 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 176620 | 2301 | 10 | Solar | 07_91W49 | 2016-04-12 01:00 | 2016-04-13 | 1 | 1 | 0 | 2016-04-14 | 2016-04-14 | 0 | 0 | 0 | [20 empty] | 2016-04-26 | 2016-04-12 01:00 | 2017-04-18 | Yes | EXP |  | 2016-07-18 | 2016-07-25 | 5 | 0 | 5 | 2017-01-23 | 2017-01-23 | 2017-03-09 | Connected |  | No
National Grid | CHELMSFORD | 176621 | 1824 | 7.6 | Solar | 14_24L1 | 2016-04-12 01:00 | 2016-04-13 | 1 | 1 | 0 | 2016-04-14 | 2016-04-14 | 0 | 0 | 0 | [20 empty] | 2016-04-26 | 2016-04-12 01:00 | 2017-04-18 | Yes | EXP |  | 2016-08-16 | 2016-08-31 | 11 | 0 | 11 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Connected |  | No
National Grid | REHOBOTH | 176622 | 2769 | 10 | Solar | 05_7L4 | 2016-04-12 01:00 | 2016-04-13 | 1 | 1 | 0 | 2016-04-14 | 2016-04-14 | 0 | 0 | 0 | [20 empty] | 2016-04-26 |  | 2017-04-18 | Yes | EXP |  | 2016-08-11 | 2016-09-06 | 17 | 0 | 17 | 2016-11-10 | 2016-11-10 | 2016-11-14 | Connected |  | No
National Grid | BILLERICA | 176623 | 1821 | 3 | Solar | 14_18L2 | 2016-04-14 01:00 | 2016-04-14 | 2 | 2 | 0 | 2016-04-19 | 2016-11-15 | 144 | 0 | 144 | [20 empty] | 2016-04-26 |  | 2017-04-19 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SALEM | 176624 | 1970 | 6 | Solar | 12_2W1 | 2016-04-15 01:00 | 2016-04-19 | 1 | 1 | 0 | 2016-04-20 | 2017-02-06 | 198 | 0 | 198 | [20 empty] | 2016-05-04 |  | 2017-04-24 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | REHOBOTH | 176625 | 2769 | 10 | Solar | 05_8L4 | 2016-04-15 01:00 | 2016-04-19 | 1 | 1 | 0 | 2016-04-20 | 2016-04-20 | 0 | 0 | 0 | [20 empty] | 2016-04-27 | 2016-04-15 01:00 | 2017-04-24 |  | EXP | [6 empty] | 2016-10-18 | 2016-10-18 | 2016-10-21 | Connected |  | No
National Grid | SALEM | 176626 | 1970 | 7.6 | Solar | 12_29W4 | 2016-04-15 01:00 | 2016-04-19 | 1 | 1 | 0 | 2016-04-20 | 2016-04-20 | 0 | 0 | 0 | [20 empty] | 2016-07-20 |  | 2017-10-30 | Yes | EXP |  | 2017-04-26 | 2017-08-02 | 68 | 0 | 68 | 2017-04-20 | 2017-04-20 | 2017-08-18 | Connected |  | No
National Grid | DRACUT | 176654 | 1826 | 7.6 | Solar | 14_78L9 | 2016-04-15 01:00 | 2016-04-19 | 1 | 1 | 0 | 2016-04-20 | 2017-02-06 | 198 | 0 | 198 | [20 empty] | 2016-05-03 | 2016-04-18 01:00 | 2017-04-24 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | DIGHTON | 176655 | 2715 | 4.25 | Solar | 05_19W73 | 2016-04-18 01:00 | 2016-04-19 | 2 | 2 | 0 | 2016-04-21 | 2016-04-21 | 0 | 0 | 0 | [20 empty] | 2016-05-04 |  | 2017-04-24 | Yes | EXP |  | 2017-05-11 | 2017-05-31 | 13 | 0 | 13 | 2017-06-02 | 2017-06-02 | 2017-06-06 | Connected |  | No
National Grid | LEOMINSTER | 176657 | 1453 | 3.8 | Solar | 01_207W6 | 2016-04-19 01:00 | 2016-04-21 | 13 | 13 | 0 | 2016-05-10 | 2017-02-06 | 184 | 0 | 184 | [20 empty] | 2016-05-25 |  | 2017-04-26 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEBSTER | 176658 | 1570 | 6 | Solar | 01_412L2 | 2016-04-19 01:00 | 2016-04-21 | 13 | 13 | 0 | 2016-05-10 | 2017-02-06 | 184 | 0 | 184 | [20 empty] | 2016-05-26 | 2016-04-20 01:00 | 2017-04-26 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEOMINSTER | 176656 | 1453 | 10 | Solar | 01_207W6 | 2016-04-20 01:00 | 2016-04-20 | 1 | 1 | 0 | 2016-04-21 | 2016-04-21 | 0 | 0 | 0 | [20 empty] | 2016-05-03 |  | 2017-04-25 | Yes | EXP |  | 2016-08-30 | 2016-09-09 | 7 | 0 | 7 | 2016-12-02 | 2016-12-02 | 2016-12-02 | Connected |  | No
National Grid | SOUTHBRIDGE | 176659 | 1550 | 936 | Solar | 01_413L4 | 2016-04-20 01:00 | 2016-04-21 | 0 | 0 | 0 | [27 empty] | 2017-04-26 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SOUTHBRIDGE | 176660 | 1550 | 1440 | Solar | 01_413L2 | 2016-04-20 01:00 | 2016-04-21 | 0 | 0 | 0 | [27 empty] | 2017-04-26 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SOUTHBRIDGE | 176661 | 1550 | 720 | Solar | 01_413L4 | 2016-04-20 01:00 | 2016-04-21 | 0 | 0 | 0 | [10 empty] | 2016-04-21 | 2016-06-02 | 29 | 19 | 10 | [12 empty] | 2017-04-26 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SOUTHBRIDGE | 176691 | 1550 | 936 | Solar | 01_413L4 | 2016-04-20 01:00 | 2016-04-21 | 0 | 0 | 0 | [27 empty] | 2017-04-26 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SOUTHBRIDGE | 176692 | 1550 | 1872 | Solar | 01_413L4 | 2016-04-20 01:00 | 2016-04-21 | 0 | 0 | 0 | [27 empty] | 2017-04-26 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SOUTHBRIDGE | 176693 | 1550 | 1872 | Solar | 01_413L4 | 2016-04-20 01:00 | 2016-04-21 | 0 | 0 | 0 | [27 empty] | 2017-04-26 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BELLINGHAM | 176694 | 2019 | 750 | Solar | 05_335W1 | 2016-04-20 01:00 | 2016-04-21 | 3 | 3 | 0 | [10 empty] | 2016-04-26 | 2016-06-09 | 31 | 20 | 11 | [10 empty] | 2017-01-04 |  | 2018-04-26 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HOLBROOK | 176695 | 2343 | 10 | Solar | 07_10W1 | 2016-04-20 01:00 | 2016-04-25 | 0 | 0 | 0 | 2016-04-25 | 2016-04-25 | 0 | 0 | 0 | [20 empty] | 2016-05-02 | 2016-04-20 01:00 | 2017-04-30 |  | EXP | [6 empty] | 2016-08-25 | 2016-08-25 | 2016-08-29 | Connected |  | No
National Grid | SOUTHBRIDGE | 176731 | 1550 | 999 | Solar | 01_413L4 | 2016-04-20 01:00 | 2016-04-26 | 0 | 0 | 0 | [10 empty] | 2016-04-26 | 2016-06-02 | 26 | 15 | 11 | [10 empty] | 2017-11-13 | 2016-04-20 01:00 | 2020-12-31 | Yes | STD |  | 2020-08-22 | 2020-12-03 | 103 | 0 | 103 | 2020-12-14 | 2020-12-14 | 2020-12-30 | Connected |  | No
National Grid | SOUTHBRIDGE | 176732 | 1550 | 936 | Solar | 01_413L4 | 2016-04-20 01:00 | 2016-04-26 | 1 | 0 | 1 | [10 empty] | 2016-04-27 | 2016-06-02 | 25 | 15 | 10 | [10 empty] | 2019-04-02 |  | 2020-12-31 | Yes | STD |  | 2020-08-22 | 2020-11-25 | 95 | 0 | 95 | 2020-12-03 | 2020-12-03 | 2020-12-31 | Connected |  | No
National Grid | SOUTHBRIDGE | 176766 | 1550 | 1872 | Solar | 01_413L4 | 2016-04-20 01:00 | 2016-04-27 | 0 | 0 | 0 | [10 empty] | 2016-04-27 | 2016-06-02 | 25 | 15 | 10 | [11 empty] | 2016-04-20 01:00 | 2017-05-02 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SOUTHBRIDGE | 176767 | 1550 | 936 | Solar | 01_413L4 | 2016-04-20 01:00 | 2016-04-27 | 0 | 0 | 0 | [10 empty] | 2016-04-27 | 2016-06-02 | 25 | 15 | 10 | [10 empty] | 2019-01-15 |  | 2020-12-18 | Yes | STD |  | 2020-07-08 | 2020-10-14 | 99 | 5 | 94 |  |  | 2020-12-16 | Connected |  | No
National Grid | SOUTHBRIDGE | 176768 | 1550 | 1872 | Solar | 01_413L3 | 2016-04-20 01:00 | 2016-04-27 | 0 | 0 | 0 | [10 empty] | 2016-04-27 | 2016-05-31 | 23 | 15 | 8 | [12 empty] | 2019-01-07 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 176696 | 1605 | 10 | Solar | 01_24W2 | 2016-04-21 01:00 | 2016-04-25 | 3 | 3 | 0 | 2016-04-28 | 2016-07-08 | 48 | 0 | 48 | [21 empty] | 2016-04-21 01:00 | 2017-04-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | UXBRIDGE | 176697 | 1569 | 1872 | Solar | 05_321W6 | 2016-04-21 01:00 | 2016-04-26 | 0 | 0 | 0 | [10 empty] | 2016-04-26 | 2016-06-08 | 30 | 22 | 8 | [5 empty] | 2018-03-29 | 2017-05-19 | 0 | 0 | 0 | 2017-05-03 |  | 2018-09-21 | Yes | STD |  | 2018-04-12 | 2018-08-10 | 110 | 0 | 110 |  |  | 2018-09-19 | Connected |  | No
National Grid | WINCHENDON | 176699 | 1475 | 288 | Solar | 01_612W1 | 2016-04-22 01:00 | 2016-04-26 | 0 | 0 | 0 | [10 empty] | 2016-04-26 | 2016-05-27 | 23 | 16 | 7 | [12 empty] | 2017-05-01 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | WINCHENDON | 176700 | 1475 | 1980 | Solar | 01_612W1 | 2016-04-22 01:00 | 2016-04-26 | 0 | 0 | 0 | [10 empty] | 2016-04-26 | 2016-06-03 | 27 | 21 | 6 | [11 empty] | 2016-04-25 01:00 | 2017-05-01 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | RUTLAND | 176698 | 1543 | 380 | Bio Gas | 01_55W1 | 2016-04-25 01:00 | 2016-04-25 | 15 | 15 | 0 | [10 empty] | 2016-05-16 | 2016-07-06 | 34 | 13 | 21 | [10 empty] | 2016-12-07 | 2016-04-25 01:00 | 2022-07-05 | Yes | STD |  | 2019-03-09 | 2019-09-26 | 202 | 107 | 95 |  |  | 2022-03-16 | Connected |  | No
National Grid | DUNSTABLE | 176728 | 1827 | 40 | Solar | 01_210L1 | 2016-04-25 01:00 | 2016-04-26 | 3 | 3 | 0 | 2016-04-29 | 2016-04-29 | 0 | 0 | 0 | [20 empty] | 2016-05-05 |  | 2017-05-01 | Yes | EXP |  | 2016-07-19 | 2016-09-12 | 38 | 0 | 38 | 2017-01-05 | 2017-01-05 | 2017-01-05 | Connected |  | No
National Grid | MEDFORD | 176729 | 2155 | 150 | Solar | 12_37W4 | 2016-04-25 01:00 | 2016-04-26 | 1 | 1 | 0 | 2016-04-27 | 2017-06-09 | 279 | 9 | 270 | [20 empty] | 2016-06-06 | 2016-04-25 01:00 | 2017-05-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 176730 | 1606 | 6 | Solar | 01_24W3 | 2016-04-25 01:00 | 2016-04-26 | 2 | 2 | 0 | 2016-04-28 | 2016-04-28 | 0 | 0 | 0 | [20 empty] | 2016-05-11 |  | 2017-05-01 |  | EXP | [6 empty] | 2017-01-12 | 2017-01-12 | 2017-01-12 | Connected |  | No
National Grid | WILLIAMSTOWN | 176733 | 1267 | 160 | Solar | 09_1003W1 | 2016-04-26 01:00 | 2016-04-27 | 2 | 2 | 0 | 2016-04-29 | 2016-04-29 | 0 | 0 | 0 | [20 empty] | 2016-05-26 |  | 2017-05-02 |  | EXP | [6 empty] | 2017-04-26 | 2017-04-26 | 2017-04-26 | Connected |  | No
National Grid | MILFORD | 176734 | 1757 | 206 | Solar | 05_336W4 | 2016-04-26 01:00 | 2016-04-27 | 9 | 9 | 0 | [27 empty] | 2017-05-02 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | FALL RIVER | 176805 | 2721 | 225 | Solar | 05_115W43 | 2016-04-27 01:00 | 2016-04-27 | 19 | 19 | 0 | 2016-05-24 | 2016-05-24 | 0 | 0 | 0 | [20 empty] | 2016-08-19 |  | 2017-03-15 |  | EXP | [6 empty] | 2017-08-22 | 2017-08-22 | 2017-08-24 | Connected |  | No
National Grid | BELLINGHAM | 176806 | 2019 | 6 | Solar | 05_344W4 | 2016-04-27 01:00 | 2016-04-28 | 8 | 8 | 0 | 2016-05-10 | 2017-01-26 | 177 | 0 | 177 | [20 empty] | 2016-05-17 |  | 2017-05-03 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BELLINGHAM | 176807 | 2019 | 6 | Solar | 05_344W4 | 2016-04-27 01:00 | 2016-04-28 | 8 | 8 | 0 | 2016-05-10 | 2016-05-10 | 0 | 0 | 0 | [20 empty] | 2016-05-17 |  | 2017-05-03 |  | EXP | [6 empty] | 2016-09-16 | 2016-09-16 | 2016-11-22 | Connected |  | No
National Grid | SHIRLEY | 176808 | 1464 | 13.6 | Solar | 01_227W3 | 2016-04-27 01:00 | 2016-04-28 | 8 | 8 | 0 | 2016-05-10 | 2017-02-06 | 184 | 0 | 184 | [20 empty] | 2016-05-26 |  | 2017-05-03 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | UPTON | 176809 | 1568 | 11.4 | Solar | 05_335W3 | 2016-04-27 01:00 | 2016-04-28 | 8 | 8 | 0 | 2016-05-10 | 2017-02-06 | 184 | 0 | 184 | [20 empty] | 2016-05-26 |  | 2017-05-03 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GLOUCESTER | 176810 | 1930 | 22.8 | Solar | 12_51T1 | 2016-04-27 01:00 | 2016-04-28 | 1 | 1 | 0 | 2016-04-29 | 2016-04-29 | 0 | 0 | 0 | [20 empty] | 2016-05-03 |  | 2017-05-03 |  | EXP | [6 empty] | 2016-05-25 | 2016-05-25 | 2016-09-15 | Connected |  | No
National Grid | ANDOVER | 176839 | 1810 | 50 | Solar | 14_8T1 | 2016-04-29 01:00 | 2016-04-29 | 3 | 3 | 0 | 2016-05-04 | 2016-05-04 | 0 | 0 | 0 | [20 empty] | 2016-05-05 | 2016-05-02 01:00 | 2017-05-04 |  | EXP | [6 empty] | 2016-10-13 | 2016-10-13 | 2016-11-03 | Connected |  | No
National Grid | UPTON | 176840 | 1568 | 7 | Solar | 05_320W1 | 2016-05-02 01:00 | 2016-05-02 | 5 | 5 | 0 | 2016-05-09 | 2016-05-09 | 0 | 0 | 0 | [20 empty] | 2016-05-25 | 2016-05-02 01:00 | 2017-05-07 | Yes | EXP |  | 2016-08-01 | 2016-10-19 | 55 | 0 | 55 | 2016-10-26 | 2016-10-26 | 2016-10-26 | Connected |  | No
National Grid | METHUEN | 176841 | 1844 | 10 | Solar | 14_63L1 | 2016-05-02 01:00 | 2016-05-02 | 3 | 3 | 0 | 2016-05-05 | 2018-03-13 | 449 | 0 | 449 | [20 empty] | 2016-05-12 |  | 2018-07-31 | Yes | EXP |  | 2017-07-11 | 2017-07-28 | 13 | 0 | 13 |  |  |  | Withdrawn |  | Yes
National Grid | FRANKLIN | 176842 | 2038 | 10 | Solar | 05_344W4 | 2016-05-02 01:00 | 2016-05-02 | 34 | 34 | 0 | 2016-06-21 | 2016-06-21 | 0 | 0 | 0 | [20 empty] | 2016-06-29 | 2016-05-02 01:00 | 2017-05-07 |  | EXP | [6 empty] | 2017-01-17 | 2017-01-17 | 2017-01-20 | Connected |  | No
National Grid | WORCESTER | 176843 | 1602 | 6 | Solar | 01_6W2 | 2016-05-02 01:00 | 2016-05-03 | 2 | 2 | 0 | 2016-05-05 | 2016-05-05 | 0 | 0 | 0 | [20 empty] | 2016-05-12 |  | 2018-01-08 | Yes | EXP |  | 2016-10-31 | 2016-10-25 | 0 | 0 | 0 | 2017-05-31 | 2017-05-31 | 2017-05-31 | Connected |  | No
National Grid | FRANKLIN | 176844 | 2038 | 9 | Solar | 05_344W5 | 2016-05-02 01:00 | 2016-05-03 | 3 | 3 | 0 | 2016-05-06 | 2016-05-06 | 0 | 0 | 0 | [20 empty] | 2016-05-17 |  | 2017-05-08 |  | EXP | [6 empty] | 2016-08-23 | 2016-08-23 | 2016-08-29 | Connected |  | No
National Grid | OXFORD | 176845 | 1540 | 15 | Solar | 01_406L3 | 2016-05-02 01:00 | 2016-05-03 | 3 | 3 | 0 | 2016-05-06 | 2016-06-27 | 34 | 0 | 34 | [20 empty] | 2016-05-25 | 2016-05-03 01:00 | 2017-05-08 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | CHARLEMONT | 176846 | 1339 | 25 | Solar | 09_1019W1 | 2016-05-03 01:00 | 2016-05-03 | 5 | 5 | 0 | 2016-05-10 | 2016-05-10 | 0 | 0 | 0 | [20 empty] | 2016-06-14 |  | 2017-05-08 | Yes | EXP |  | 2016-10-27 | 2016-11-08 | 8 | 0 | 8 | 2016-11-14 | 2016-11-14 | 2016-11-16 | Connected |  | No
National Grid | CHARLEMONT | 176876 | 1339 | 15 | Solar | 09_1019W1 | 2016-05-03 01:00 | 2016-05-04 | 4 | 4 | 0 | 2016-05-10 | 2016-06-13 | 23 | 0 | 23 | [22 empty] | 2017-05-09 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | GRAFTON | 176877 | 1519 | 995 | Solar | 01_304W2 | 2016-05-04 01:00 | 2016-05-04 | 7 | 7 | 0 | [10 empty] | 2016-05-13 | 2016-06-20 | 24 | 11 | 13 | [10 empty] | 2016-10-21 |  | 2018-09-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | STOUGHTON | 176878 | 2072 | 28.8 | Solar | 07_913W43 | 2016-05-04 01:00 | 2016-05-04 | 2 | 2 | 0 | 2016-05-06 | 2016-05-06 | 0 | 0 | 0 | [20 empty] | 2016-05-18 | 2016-05-04 01:00 | 2017-05-09 |  | EXP | [6 empty] | 2017-01-09 | 2017-01-09 | 2017-01-09 | Connected |  | No
National Grid | HUBBARDSTON | 176879 | 1452 | 266.4 | Solar | 01_602W2 | 2016-05-04 01:00 | 2016-05-05 | 1 | 1 | 0 | [10 empty] | 2016-05-06 | 2016-06-28 | 35 | 14 | 21 | [10 empty] | 2016-12-21 | 2016-05-04 01:00 | 2017-12-29 | Yes | STD |  | 2017-05-01 | 2017-10-04 | 109 | 0 | 109 | 2018-01-11 | 2018-01-11 | 2017-12-11 | Connected |  | No
National Grid | SALEM | 176880 | 1970 | 10 | Solar | 12_29W4 | 2016-05-04 01:00 | 2016-05-05 | 3 | 3 | 0 | 2016-05-10 | 2016-05-10 | 0 | 0 | 0 | [20 empty] | 2016-05-26 |  | 2017-05-10 | Yes | EXP |  | 2017-03-22 | 2017-04-10 | 13 | 0 | 13 | 2017-04-20 | 2017-04-20 | 2017-04-25 | Connected |  | No
National Grid | MILFORD | 176881 | 1757 | 3.8 | Solar | 05_336W3 | 2016-05-04 01:00 | 2016-05-05 | 3 | 3 | 0 | 2016-05-10 | 2017-01-20 | 173 | 0 | 173 | [20 empty] | 2016-05-26 |  | 2017-05-10 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 176882 | 1602 | 7.53 | Solar | 01_23W3 | 2016-05-04 01:00 | 2016-05-05 | 3 | 3 | 0 | 2016-05-10 | 2016-05-10 | 0 | 0 | 0 | [20 empty] | 2016-05-19 |  | 2017-05-10 |  | EXP | [6 empty] | 2016-10-27 | 2016-10-27 | 2016-10-27 | Connected |  | No
National Grid | BELLINGHAM | 176883 | 2019 | 10 | Solar | 05_344W4 | 2016-05-04 01:00 | 2016-05-05 | 3 | 3 | 0 | 2016-05-10 | 2016-05-10 | 0 | 0 | 0 | [20 empty] | 2016-05-17 |  | 2017-05-10 |  | EXP | [6 empty] | 2016-09-08 | 2016-09-08 | 2016-09-14 | Connected |  | No
National Grid | METHUEN | 176884 | 1844 | 7.6 | Solar | 14_74L3 | 2016-05-04 01:00 | 2016-05-05 | 3 | 3 | 0 | 2016-05-10 | 2017-02-06 | 184 | 0 | 184 | [20 empty] | 2016-05-27 |  | 2017-05-10 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 176912 | 1844 | 10 | Solar | 14_63L2 | 2016-05-04 01:00 | 2016-05-05 | 3 | 3 | 0 | 2016-05-10 | 2017-05-16 | 253 | 0 | 253 | [20 empty] | 2016-05-27 |  | 2017-05-10 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 176913 | 1844 | 7.6 | Solar | 14_74L1 | 2016-05-04 01:00 | 2016-05-05 | 3 | 3 | 0 | 2016-05-10 | 2017-02-06 | 184 | 0 | 184 | [20 empty] | 2016-05-27 | 2016-05-04 01:00 | 2017-05-10 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RANDOLPH | 176914 | 2368 | 11.4 | Solar | 07_97W2 | 2016-05-04 01:00 | 2016-05-05 | 3 | 3 | 0 | 2016-05-10 | 2016-05-10 | 0 | 0 | 0 | [20 empty] | 2016-05-27 | 2016-05-04 01:00 | 2017-05-10 | Yes | EXP |  | 2016-11-07 | 2016-11-26 | 13 | 0 | 13 | 2016-12-05 | 2016-12-05 | 2016-12-05 | Connected |  | No
National Grid | REVERE | 176915 | 2151 | 14.19 | Solar | 12_16W4 | 2016-05-04 01:00 | 2016-05-05 | 3 | 3 | 0 | 2016-05-10 | 2016-05-10 | 0 | 0 | 0 | [20 empty] | 2016-05-27 |  | 2017-05-10 | Yes | EXP | [6 empty] | 2016-12-06 | 2016-12-06 | 2016-11-15 | Connected |  | No
National Grid | BELCHERTOWN | 176916 | 1007 | 3.8 | Solar | 09_509L1 | 2016-05-04 01:00 | 2016-05-05 | 3 | 3 | 0 | 2016-05-10 | 2016-05-10 | 0 | 0 | 0 | [20 empty] | 2016-05-19 |  | 2017-05-10 |  | EXP | [6 empty] | 2016-11-02 | 2016-11-02 | 2016-11-02 | Connected |  | No
National Grid | GRAFTON | 176917 | 1519 | 10 | Solar | 05_320W3 | 2016-05-05 01:00 | 2016-05-06 | 1 | 1 | 0 | 2016-05-09 | 2016-05-09 | 0 | 0 | 0 | [20 empty] | 2016-05-24 |  | 2017-05-11 |  | EXP | [6 empty] | 2016-08-29 | 2016-08-29 | 2016-08-29 | Connected |  | No
National Grid | WILLIAMSTOWN | 176918 | 1267 | 316 | Solar | 09_1003W2 | 2016-05-05 01:00 | 2016-05-06 | 3 | 3 | 0 | 2016-05-10 |  | 470 | 470 | 0 | 2016-06-24 | 2016-07-28 | 24 | 24 | 0 | [5 empty] | 2016-06-24 | 2016-07-28 | 24 | 24 | 0 | [7 empty] | 2018-06-11 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FALL RIVER | 176919 | 2724 | 6 | Solar | 05_115W42 | 2016-05-05 01:00 | 2016-05-06 | 4 | 4 | 0 | 2016-05-12 | 2016-07-05 | 35 | 0 | 35 | [20 empty] | 2016-06-06 |  | 2017-05-11 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WARE | 176368 | 1082 | 499 | Solar | 09_501L1 | 2016-05-06 01:00 | 2016-05-06 | 0 | 0 | 0 | [10 empty] | 2016-05-06 | 2016-06-07 | 21 | 1 | 20 | [12 empty] | 2017-05-11 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NANTUCKET | 176375 | 2554 | 284 | Solar | 04_101L4 | 2016-05-06 01:00 | 2016-05-09 | 1 | 1 | 0 | 2016-05-10 | 2016-05-10 | 0 | 0 | 0 | [20 empty] | 2016-07-13 |  | 2017-05-14 |  | EXP | [6 empty] | 2016-09-15 | 2016-09-15 | 2016-12-29 | Connected |  | No
National Grid | NORTH ANDOVER | 176444 | 1845 | 108 | Solar | 14_2326 | 2016-05-06 01:00 | 2016-05-16 | 0 | 0 | 0 | 2016-05-16 | 2018-02-21 | 435 | 0 | 435 | 2016-06-16 | 2016-08-10 | 37 | 0 | 37 | [5 empty] | 2016-06-16 | 2016-08-10 | 37 | 0 | 37 | [5 empty] | 2016-08-25 |  | 2018-02-28 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HAVERHILL | 176406 | 1832 | 720 | Solar | 14_48L4 | 2016-05-09 01:00 | 2016-05-11 | 0 | 0 | 0 | [10 empty] | 2016-05-11 | 2016-07-13 | 42 | 32 | 10 | [11 empty] | 2016-05-09 01:00 | 2017-05-16 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | NORTON | 176408 | 2766 | 8.25 | Solar | 05_8L3 | 2016-05-09 01:00 | 2016-05-11 | 3 | 3 | 0 | 2016-05-16 | 2016-05-16 | 0 | 0 | 0 | [20 empty] | 2016-06-06 |  | 2017-05-16 | Yes | EXP |  | 2016-08-04 | 2016-08-20 | 12 | 0 | 12 | 2016-10-11 | 2016-10-11 | 2016-10-11 | Connected |  | No
National Grid | ATTLEBORO | 176410 | 2703 | 10 | Solar | 05_9L1 | 2016-05-09 01:00 | 2016-05-11 | 1 | 1 | 0 | 2016-05-12 | 2017-02-06 | 182 | 0 | 182 | [20 empty] | 2016-06-06 |  | 2017-05-16 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GARDNER | 176405 | 1440 | 1500 | Wind | 01_607W4 | 2016-05-10 01:00 | 2016-05-11 | 0 | 0 | 0 | [10 empty] | 2016-05-11 | 2016-07-06 | 37 | 13 | 24 | [11 empty] | 2016-05-10 01:00 | 2017-05-16 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NEW BRAINTREE | 176411 | 1531 | 34.2 | Solar | 09_604W3 | 2016-05-10 01:00 | 2016-05-11 | 2 | 2 | 0 | 2016-05-13 | 2016-05-13 | 0 | 0 | 0 | [20 empty] | 2016-06-06 |  | 2017-05-16 | Yes | EXP |  | 2017-02-27 | 2017-03-22 | 17 | 0 | 17 | 2017-03-23 | 2017-03-23 | 2017-03-29 | Connected |  | No
National Grid | AYER | 176412 | 1432 | 949.2 | Solar | 01_201W2 | 2016-05-10 01:00 | 2016-05-11 | 15 | 15 | 0 | [10 empty] | 2016-06-01 | 2016-06-15 | 10 | 9 | 1 | [12 empty] | 2017-05-16 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MILFORD | 176441 | 1757 | 206 | Solar | 05_336W4 | 2016-05-10 01:00 | 2016-05-12 | 1 | 1 | 0 | 2016-05-13 | 2016-08-03 | 55 | 0 | 55 | [21 empty] | 2016-05-10 01:00 | 2017-05-17 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MILFORD | 177077 | 1757 | 206 | Solar | 05_336W4 | 2016-05-10 01:00 | 2016-05-12 | 1 | 0 | 1 | 2016-05-13 | 2016-05-13 | 0 | 0 | 0 | [20 empty] | 2016-08-15 | 2016-05-10 01:00 | 2016-12-30 | Yes | EXP |  | 2016-11-10 | 2016-12-28 | 31 | 0 | 31 | 2016-12-28 | 2016-12-28 | 2017-01-10 | Connected |  | No
National Grid | FOXBOROUGH | 178788 | 2035 | 32.8 | Solar | 05_3431W1 | 2016-05-10 01:00 | 2016-05-11 | 0 | 0 | 0 | 2016-05-11 | 2016-05-11 | 0 | 0 | 0 | [20 empty] | 2016-05-31 | 2016-05-11 01:00 | 2017-05-16 | Yes | EXP |  | 2016-12-05 | 2017-01-05 | 21 | 0 | 21 | 2017-02-14 | 2017-02-14 | 2017-02-14 | Connected |  | No
National Grid | ADAMS | 176442 | 1220 | 10 | Solar | 09_1021W1 | 2016-05-11 01:00 | 2016-05-12 | 2 | 2 | 0 | 2016-05-16 | 2016-05-16 | 0 | 0 | 0 | [20 empty] | 2016-06-06 |  | 2017-05-17 | Yes | EXP |  | 2016-09-21 | 2016-10-07 | 12 | 0 | 12 | 2016-11-07 | 2016-11-07 | 2016-11-10 | Connected |  | No
National Grid | AVON | 176443 | 2322 | 360 | Solar | 07_75W5 | 2016-05-15 01:00 | 2016-05-16 | 21 | 21 | 0 | 2016-06-15 | 2016-11-03 | 97 | 0 | 97 | [22 empty] | 2017-05-21 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH ANDOVER | 176445 | 1845 | 140 | Solar | 14_2326 | 2016-05-16 01:00 | 2016-05-16 | 0 | 0 | 0 | 2016-05-16 | 2016-05-16 | 0 | 0 | 0 | 2016-08-19 | 2016-08-10 | 0 | 0 | 0 | [5 empty] | 2016-08-19 | 2016-08-10 | 0 | 0 | 0 | [5 empty] | 2016-08-25 |  | 2017-09-21 |  | EXP | [6 empty] | 2017-07-19 | 2017-07-19 | 2017-07-19 | Connected |  | No
National Grid | MILLBURY | 176446 | 1527 | 72 | Solar | 01_304W4 | 2016-05-17 01:00 | 2016-05-17 | 20 | 20 | 0 | 2016-06-15 | 2016-06-15 | 0 | 0 | 0 | [20 empty] | 2016-06-24 |  | 2017-05-22 |  | EXP | [6 empty] | 2016-10-03 | 2016-10-03 | 2016-10-03 | Connected |  | No
National Grid | NORTH ANDOVER | 176448 | 1845 | 140 | Solar | 14_2326 | 2016-05-17 01:00 | 2016-05-18 | 0 | 0 | 0 | 2016-05-18 | 2016-05-18 | 0 | 0 | 0 | 2016-06-16 | 2016-08-10 | 37 | 0 | 37 | [5 empty] | 2016-06-16 | 2016-08-10 | 37 | 0 | 37 | [5 empty] | 2016-08-25 |  | 2017-05-23 |  | EXP | [6 empty] | 2017-05-23 | 2017-05-23 | 2017-05-23 | Connected |  | No
National Grid | GRANBY | 176449 | 1033 | 17.4 | Solar | 09_527L1 | 2016-05-18 01:00 | 2016-05-18 | 0 | 0 | 0 | 2016-05-18 | 2016-05-18 | 0 | 0 | 0 | [20 empty] | 2016-06-13 |  | 2017-05-23 |  | EXP | [6 empty] | 2016-07-13 | 2016-07-13 | 2016-07-13 | Connected |  | No
National Grid | TEWKSBURY | 176478 | 1876 | 133.2 | Solar | 14_59L5 | 2016-05-18 01:00 | 2016-05-25 | 0 | 0 | 0 | 2016-05-25 | 2018-02-21 | 428 | 0 | 428 | [20 empty] | 2016-06-21 |  | 2018-02-28 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOMERSET | 176479 | 2726 | 288 | Solar | 05_19W72 | 2016-05-19 01:00 | 2016-05-25 | 20 | 20 | 0 | 2016-06-24 | 2016-06-24 | 0 | 0 | 0 | 2016-08-16 | 2016-09-16 | 22 | 7 | 15 | [5 empty] | 2016-08-16 | 2016-09-16 | 22 | 7 | 15 | [5 empty] | 2017-03-03 |  | 2017-07-15 |  | EXP | [6 empty] | 2017-06-28 | 2017-06-28 | 2017-08-03 | Connected |  | No
National Grid | MARLBOROUGH | 176480 | 1752 | 75 | Solar | 05_317W1 | 2016-05-19 01:00 | 2016-05-25 | 0 | 0 | 0 | 2016-05-25 | 2016-06-16 | 35 | 18 | 17 | [20 empty] | 2016-08-05 | 2016-05-20 01:00 | 2019-05-31 |  | EXP | [8 empty] | 2019-07-02 | Connected |  | No
National Grid | STURBRIDGE | 176481 | 1566 | 57.6 | Solar | 01_415L3 | 2016-05-20 01:00 | 2016-05-25 | 0 | 0 | 0 | 2016-05-25 | 2016-05-25 | 0 | 0 | 0 | [20 empty] | 2016-06-08 | 2016-05-20 01:00 | 2017-05-30 | Yes | EXP |  | 2017-05-01 | 2017-05-09 | 6 | 0 | 6 | 2017-06-21 | 2017-06-21 | 2017-06-28 | Connected |  | No
National Grid | FALL RIVER | 176482 | 2720 | 144 | Solar | 05_106W81 | 2016-05-20 01:00 | 2016-05-25 | 1 | 1 | 0 | 2016-05-26 | 2016-05-26 | 0 | 0 | 0 | [20 empty] | 2016-06-27 | 2016-05-23 01:00 | 2017-05-30 | Yes | EXP |  | 2016-10-10 | 2016-11-04 | 18 | 0 | 18 | 2016-12-06 | 2016-12-06 | 2016-12-08 | Connected |  | No
National Grid | LAWRENCE | 176483 | 1841 | 6 | Solar | 14_8L2 | 2016-05-23 01:00 | 2016-05-25 | 0 | 0 | 0 | 2016-05-25 | 2016-05-25 | 0 | 0 | 0 | [20 empty] | 2016-06-06 |  | 2017-05-30 | Yes | EXP |  | 2016-11-28 | 2016-12-14 | 12 | 0 | 12 | 2017-04-20 | 2017-04-20 | 2017-04-26 | Connected |  | No
National Grid | WORCESTER | 176484 | 1603 | 7.6 | Solar | 01_6W1 | 2016-05-23 01:00 | 2016-05-25 | 1 | 1 | 0 | 2016-05-26 | 2016-09-27 | 84 | 0 | 84 | [20 empty] | 2016-06-08 | 2016-05-23 01:00 | 2017-05-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SOMERSET | 176485 | 2726 | 6 | Solar | 05_19W72 | 2016-05-23 01:00 | 2016-05-25 | 1 | 1 | 0 | 2016-05-26 | 2016-05-26 | 0 | 0 | 0 | [20 empty] | 2016-06-06 | 2016-05-24 01:00 | 2017-05-30 | Yes | EXP |  | 2016-10-03 | 2016-10-13 | 7 | 0 | 7 | 2017-02-16 | 2017-02-16 | 2017-02-16 | Connected |  | No
National Grid | ATTLEBORO | 177097 | 2703 | 5 | Solar | 05_9L6 | 2016-05-24 01:00 | 2016-05-25 | 2 | 2 | 0 | 2016-05-27 | 2016-05-27 | 0 | 0 | 0 | [20 empty] | 2016-06-06 |  | 2017-05-30 | Yes | EXP |  | 2016-11-03 | 2016-11-14 | 6 | 0 | 6 | 2017-01-05 | 2017-01-05 | 2017-01-05 | Connected |  | No
National Grid | FALL RIVER | 177098 | 2720 | 3 | Solar | 05_28W51 | 2016-05-24 01:00 | 2016-05-25 | 2 | 2 | 0 | 2016-05-27 | 2016-07-26 | 39 | 0 | 39 | [21 empty] | 2016-05-24 01:00 | 2017-05-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTON | 177099 | 2766 | 10 | Solar | 05_8L4 | 2016-05-24 01:00 | 2016-05-25 | 2 | 2 | 0 | 2016-05-27 | 2016-05-27 | 0 | 0 | 0 | [20 empty] | 2016-06-06 |  | 2017-05-30 | Yes | EXP |  | 2016-08-24 | 2016-09-06 | 8 | 0 | 8 | 2016-12-29 | 2016-12-29 | 2016-12-29 | Connected |  | No
National Grid | NORWELL | 177100 | 2061 | 20 | Solar | 07_96W43 | 2016-05-26 01:00 | 2016-05-26 | 3 | 3 | 0 | 2016-06-01 | 2016-06-01 | 0 | 0 | 0 | [20 empty] | 2016-06-13 | 2016-05-26 01:00 | 2017-05-31 |  | EXP | [6 empty] | 2016-09-02 | 2016-09-02 | 2016-09-02 | Connected |  | No
National Grid | EVERETT | 177102 | 2149 | 1332 | Solar | 12_2401 | 2016-05-26 01:00 | 2016-05-27 | 0 | 0 | 0 | [10 empty] | 2016-05-27 | 2016-07-07 | 26 | 9 | 17 | [10 empty] | 2016-12-01 | 2016-05-27 01:00 | 2017-09-29 | Yes | STD |  | 2017-09-22 | 2018-02-14 | 92 | 0 | 92 | 2017-09-18 | 2017-09-18 | 2017-09-22 | Connected |  | No
National Grid | BILLERICA | 177103 | 1821 | 288 | Solar | 14_92L1 | 2016-05-27 01:00 | 2016-05-31 | 3 | 3 | 0 | 2016-06-03 | 2016-06-03 | 0 | 0 | 0 | [20 empty] | 2016-08-19 | 2016-05-27 01:00 | 2017-07-05 | Yes | EXP | [6 empty] | 2017-05-30 | 2017-05-30 | 2017-05-30 | Connected |  | No
National Grid | BILLERICA | 177104 | 1821 | 288 | Solar | 14_92L1 | 2016-05-27 01:00 | 2016-05-31 | 3 | 3 | 0 | 2016-06-03 | 2016-06-03 | 0 | 0 | 0 | [20 empty] | 2016-09-01 |  | 2017-07-05 | Yes | EXP | [6 empty] | 2017-05-30 | 2017-05-30 | 2017-05-30 | Connected |  | No
National Grid | WILBRAHAM | 177105 | 1095 | 225 | Solar | 09_507L3 | 2016-05-27 01:00 | 2016-05-31 | 3 | 3 | 0 | 2016-06-03 | 2018-01-14 | 397 | 0 | 397 | [20 empty] | 2016-06-24 |  | 2017-06-05 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 177106 | 1606 | 120 | Solar | 01_12J391 | 2016-05-27 01:00 | 2016-05-31 | 3 | 3 | 0 | 2016-06-03 | 2016-06-03 | 0 | 0 | 0 | [20 empty] | 2016-06-30 |  | 2017-06-05 |  | EXP | [6 empty] | 2016-12-06 | 2016-12-06 | 2016-12-06 | Connected |  | No
National Grid | AMESBURY | 177136 | 1913 | 7.6 | Solar | 14_275L2 | 2016-05-27 01:00 | 2016-05-31 | 1 | 1 | 0 | 2016-06-01 | 2016-06-01 | 0 | 0 | 0 | [20 empty] | 2016-06-08 | 2016-05-27 01:00 | 2017-06-05 |  | EXP | [6 empty] | 2016-09-23 | 2016-09-23 | 2016-09-28 | Connected |  | No
National Grid | LEOMINSTER | 177137 | 1453 | 7.6 | Solar | 01_207W6 | 2016-05-27 01:00 | 2016-05-31 | 1 | 1 | 0 | 2016-06-01 | 2016-06-01 | 0 | 0 | 0 | [20 empty] | 2016-06-14 |  | 2017-06-05 | Yes | EXP |  | 2016-11-01 | 2016-11-14 | 8 | 0 | 8 | 2016-12-07 | 2016-12-07 | 2016-12-12 | Connected |  | No
National Grid | METHUEN | 177138 | 1844 | 6 | Solar | 14_63L2 | 2016-05-27 01:00 | 2016-06-01 | 0 | 0 | 0 | 2016-06-01 | 2016-06-01 | 0 | 0 | 0 | [20 empty] | 2016-06-02 |  | 2017-06-06 |  | EXP | [6 empty] | 2016-09-28 | 2016-09-28 | 2016-10-04 | Connected |  | No
National Grid | BROCKTON | 177139 | 2301 | 7.6 | Solar | 07_98W10 | 2016-05-27 01:00 | 2016-06-01 | 0 | 0 | 0 | 2016-06-01 | 2016-07-26 | 37 | 0 | 37 | [20 empty] | 2016-06-14 |  | 2017-06-06 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | REVERE | 177140 | 2151 | 6 | Solar | 12_16W4 | 2016-05-27 01:00 | 2016-06-01 | 9 | 9 | 0 | 2016-06-14 | 2017-01-26 | 153 | 0 | 153 | [20 empty] | 2016-06-14 |  | 2017-06-06 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | REVERE | 177141 | 2151 | 10 | Solar | 12_7W2 | 2016-05-27 01:00 | 2016-06-01 | 0 | 0 | 0 | 2016-06-01 | 2017-01-26 | 162 | 0 | 162 | [20 empty] | 2016-06-20 | 2016-05-27 01:00 | 2017-06-06 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTPORT | 177142 | 2790 | 6 | Solar | 05_115W45 | 2016-05-27 01:00 | 2016-06-01 | 0 | 0 | 0 | 2016-06-01 | 2016-06-01 | 0 | 0 | 0 | [20 empty] | 2016-06-21 | 2016-05-27 01:00 | 2017-06-06 | Yes | EXP |  | 2016-09-01 | 2016-09-12 | 6 | 0 | 6 | 2016-12-01 | 2016-12-01 | 2016-12-01 | Connected |  | No
National Grid | SAUGUS | 177143 | 1906 | 6 | Solar | 12_23W2 | 2016-05-27 01:00 | 2016-06-01 | 0 | 0 | 0 | 2016-06-01 | 2016-06-01 | 0 | 0 | 0 | [20 empty] | 2016-06-20 |  | 2017-08-01 | Yes | EXP |  | 2017-05-31 | 2017-06-14 | 10 | 0 | 10 | 2017-06-29 | 2017-06-29 | 2017-07-10 | Connected |  | No
National Grid | TEWKSBURY | 177144 | 1876 | 10 | Solar | 14_59L3 | 2016-05-29 01:00 | 2016-06-01 | 2 | 2 | 0 | 2016-06-03 | 2017-02-01 | 164 | 0 | 164 | [20 empty] | 2016-06-20 | 2016-05-29 01:00 | 2017-06-06 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MILFORD | 177172 | 1757 | 10 | Solar | 05_335W3 | 2016-05-29 01:00 | 2016-06-01 | 2 | 2 | 0 | 2016-06-03 | 2016-06-03 | 0 | 0 | 0 | [20 empty] | 2016-06-20 |  | 2017-06-06 | Yes | EXP |  | 2016-09-13 | 2016-09-23 | 8 | 0 | 8 | 2016-11-03 | 2016-11-03 | 2016-11-03 | Connected |  | No
National Grid | RUTLAND | 177173 | 1543 | 5.59 | Solar | 01_55W1 | 2016-05-31 01:00 | 2016-06-01 | 17 | 17 | 0 | 2016-06-27 | 2016-06-27 | 0 | 0 | 0 | [20 empty] | 2016-06-30 | 2016-05-31 01:00 | 2017-06-06 |  | EXP | [6 empty] | 2016-12-20 | 2016-12-20 | 2016-12-20 | Connected |  | No
National Grid | MILFORD | 177174 | 1757 | 10 | Solar | 05_336W3 | 2016-05-31 01:00 | 2016-06-01 | 1 | 1 | 0 | 2016-06-02 | 2016-06-02 | 0 | 0 | 0 | [20 empty] | 2016-06-20 | 2016-06-01 01:00 | 2017-06-06 | Yes | EXP |  | 2016-11-03 | 2016-12-07 | 22 | 0 | 22 | 2017-07-17 | 2017-07-17 | 2017-07-19 | Connected |  | No
National Grid | CHARLTON | 177175 | 1507 | 22.8 | Solar | 01_415L1 | 2016-06-01 01:00 | 2016-06-01 | 0 | 0 | 0 | 2016-06-01 | 2016-06-01 | 0 | 0 | 0 | [20 empty] | 2016-06-01 | 2016-06-01 01:00 | 2017-06-06 | Yes | EXP |  | 2017-04-05 | 2017-04-21 | 11 | 0 | 11 | 2016-06-01 | 2016-06-01 | 2017-05-15 | Connected |  | No
National Grid | MILFORD | 177176 | 1757 | 20.2 | Solar | 05_335W5 | 2016-06-01 01:00 | 2016-06-01 | 2 | 2 | 0 | 2016-06-03 | 2016-06-03 | 0 | 0 | 0 | [20 empty] | 2016-07-06 |  | 2017-06-06 | Yes | EXP |  | 2016-10-11 | 2016-10-11 | 0 | 0 | 0 | 2016-10-21 | 2016-10-21 | 2016-10-25 | Connected |  | No
National Grid | WINCHENDON | 177177 | 1475 | 144 | Solar | 01_612W1 | 2016-06-02 01:00 | 2016-06-03 | 5 | 5 | 0 | 2016-06-10 | 2016-06-10 | 0 | 0 | 0 | [20 empty] | 2016-07-14 |  | 2017-06-08 |  | EXP | [6 empty] | 2016-11-16 | 2016-11-16 | 2016-11-16 | Connected |  | No
National Grid | BROCKTON | 177178 | 2302 | 3.8 | Solar | 07_712J1 | 2016-06-05 01:00 | 2016-06-07 | 8 | 8 | 0 | 2016-06-20 | 2017-02-01 | 154 | 0 | 154 | [20 empty] | 2016-06-28 |  | 2017-06-12 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SOUTH GRAFTON | 177179 | 1560 | 9 | Solar | 05_320W3 | 2016-06-06 01:00 | 2016-06-07 | 1 | 1 | 0 | 2016-06-08 | 2016-06-08 | 0 | 0 | 0 | [20 empty] | 2016-06-14 |  | 2017-06-12 |  | EXP | [6 empty] | 2016-11-22 | 2016-11-22 | 2016-11-28 | Connected |  | No
National Grid | OAKHAM | 177180 | 1068 | 12.75 | Solar | 09_604W2 | 2016-06-06 01:00 | 2016-06-07 | 3 | 3 | 0 | 2016-06-10 | 2016-06-10 | 0 | 0 | 0 | [20 empty] | 2016-06-20 | 2016-06-06 01:00 | 2017-06-12 |  | EXP | [6 empty] | 2016-10-04 | 2016-10-04 | 2016-10-06 | Connected |  | No
National Grid | BEVERLY | 177208 | 1915 | 7 | Solar | 12_12L2 | 2016-06-06 01:00 | 2016-06-07 | 3 | 3 | 0 | 2016-06-10 | 2016-06-10 | 0 | 0 | 0 | [20 empty] | 2016-06-20 |  | 2017-06-12 | Yes | EXP |  | 2016-08-22 | 2016-10-07 | 33 | 0 | 33 | 2016-11-02 | 2016-11-02 | 2016-11-07 | Connected |  | No
National Grid | SWANSEA | 177209 | 2777 | 10 | Solar | 05_11W84 | 2016-06-06 01:00 | 2016-06-07 | 1 | 1 | 0 | 2016-06-08 | 2017-04-12 | 210 | 0 | 210 | [20 empty] | 2016-06-20 |  | 2017-06-12 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH ADAMS | 177210 | 1247 | 480 | Solar | 09_1021W1 | 2016-06-07 01:00 | 2016-06-08 | 3 | 3 | 0 | [10 empty] | 2016-06-13 | 2016-07-12 | 19 | 0 | 19 | [11 empty] | 2016-06-07 01:00 | 2017-06-13 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HALIFAX | 177212 | 2338 | 1000 | Solar | 07_912W75 | 2016-06-07 01:00 | 2016-06-08 | 0 | 0 | 0 | [10 empty] | 2016-06-08 | 2016-07-26 | 32 | 14 | 18 | [10 empty] | 2017-02-16 |  | 2019-04-05 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 177213 | 1507 | 1000 | Solar | 01_406L1 | 2016-06-08 01:00 | 2016-06-09 | 0 | 0 | 0 | [10 empty] | 2016-06-09 | 2016-07-26 | 31 | 14 | 17 | [12 empty] | 2017-06-14 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WINCHENDON | 177215 | 1475 | 60 | Solar | 01_612W1 | 2016-06-10 01:00 | 2016-06-13 | 7 | 7 | 0 | 2016-06-23 | 2016-06-23 | 0 | 0 | 0 | [20 empty] | 2016-07-12 |  | 2017-06-18 |  | EXP | [6 empty] | 2016-11-15 | 2016-11-15 | 2016-11-15 | Connected |  | No
National Grid | BILLERICA | 177216 | 1821 | 75 | Solar | 14_92L2 | 2016-06-10 01:00 | 2016-06-13 | 4 | 4 | 0 | 2016-06-17 | 2017-01-18 | 144 | 0 | 144 | [20 empty] | 2016-06-27 | 2016-06-13 01:00 | 2017-06-18 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 177246 | 1843 | 1139 | Solar | 14_8T2 | 2016-06-13 01:00 | 2016-06-14 | 62 | 62 | 0 | [10 empty] | 2016-09-13 | 2016-10-18 | 24 | 21 | 3 | [10 empty] | 2017-03-07 |  | 2018-08-06 | Yes | STD |  | 2018-02-23 | 2018-08-03 | 126 | 0 | 126 | 2018-06-26 | 2018-06-26 | 2018-08-06 | Connected |  | No
National Grid | BROCKTON | 177250 | 2302 | 10 | Solar | 07_911W56 | 2016-06-14 01:00 | 2016-06-15 | 2 | 2 | 0 | 2016-06-17 | 2017-01-26 | 150 | 0 | 150 | [20 empty] | 2016-06-27 |  | 2017-06-20 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 177251 | 1844 | 6 | Solar | 14_75L6 | 2016-06-14 01:00 | 2016-06-15 | 2 | 2 | 0 | 2016-06-17 | 2017-06-07 | 241 | 0 | 241 | [20 empty] | 2016-06-27 |  | 2017-06-20 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 177252 | 1844 | 6 | Solar | 14_63L1 | 2016-06-14 01:00 | 2016-06-15 | 2 | 2 | 0 | 2016-06-17 | 2017-02-06 | 157 | 0 | 157 | [20 empty] | 2016-06-27 | 2016-06-14 01:00 | 2017-06-20 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LYNN | 177253 | 1904 | 3.8 | Solar | 12_29W1 | 2016-06-14 01:00 | 2016-06-15 | 2 | 2 | 0 | 2016-06-17 | 2016-06-17 | 0 | 0 | 0 | [20 empty] | 2016-06-27 |  | 2017-06-20 | Yes | EXP | [6 empty] | 2016-10-26 | 2016-10-26 | 2016-10-26 | Connected |  | No
National Grid | GRANBY | 177254 | 1033 | 6 | Solar | 09_527L1 | 2016-06-14 01:00 | 2016-06-15 | 2 | 2 | 0 | 2016-06-20 | 2016-06-20 | 0 | 0 | 0 | [20 empty] | 2016-06-28 |  | 2017-06-20 |  | EXP | [6 empty] | 2016-10-27 | 2016-10-27 | 2016-10-27 | Connected |  | No
National Grid | LYNN | 177282 | 1904 | 10 | Solar | 12_24W1 | 2016-06-14 01:00 | 2016-06-15 | 1 | 1 | 0 | 2016-06-16 | 2016-06-16 | 0 | 0 | 0 | [20 empty] | 2016-06-27 | 2016-06-15 01:00 | 2017-06-20 |  | EXP | [6 empty] | 2016-11-16 | 2016-11-16 | 2016-11-16 | Connected |  | No
National Grid | EAST LONGMEADOW | 177284 | 1028 | 73.3 | Solar | 09_508L1 | 2016-06-15 01:00 | 2016-06-16 | 7 | 7 | 0 | 2016-06-28 | 2016-06-28 | 0 | 0 | 0 | [20 empty] | 2016-08-04 | 2016-06-16 01:00 | 2017-06-21 |  | EXP |  | 2017-02-07 | 2017-03-06 | 18 | 0 | 18 | 2017-03-23 | 2017-03-23 | 2017-03-27 | Connected |  | No
National Grid | BEVERLY | 177285 | 1915 | 10 | Solar | 12_51L3 | 2016-06-16 01:00 | 2016-06-16 | 1 | 1 | 0 | 2016-06-20 | 2016-06-20 | 0 | 0 | 0 | [20 empty] | 2016-06-28 |  | 2017-06-21 | Yes | EXP |  | 2016-11-10 | 2017-01-05 | 36 | 0 | 36 | 2017-01-09 | 2017-01-09 | 2017-01-09 | Connected |  | No
National Grid | NORWELL | 177286 | 2061 | 7.6 | Solar | 07_96W43 | 2016-06-16 01:00 | 2016-06-16 | 0 | 0 | 0 | 2016-06-16 | 2016-06-16 | 0 | 0 | 0 | [20 empty] | 2016-09-06 |  | 2017-06-21 |  | EXP | [6 empty] | 2017-03-16 | 2017-03-16 | 2017-03-21 | Connected |  | No
National Grid | SOUTH EASTON | 177287 | 2375 | 240 | Solar | 07_98W48 | 2016-06-16 01:00 | 2016-06-17 | 0 | 0 | 0 | [10 empty] | 2016-06-17 | 2016-07-21 | 22 | 7 | 15 | [10 empty] | 2016-11-09 |  | 2017-02-22 |  | STD | [6 empty] | 2016-12-15 | 2016-12-15 | 2017-03-06 | Connected |  | No
National Grid | BARRE | 177323 | 1005 | 7.6 | Solar | 09_604W3 | 2016-06-16 01:00 | 2016-06-21 | 0 | 0 | 0 | 2016-06-21 | 2016-06-21 | 0 | 0 | 0 | [20 empty] | 2016-06-28 |  | 2017-06-26 |  | EXP | [6 empty] | 2016-10-06 | 2016-10-06 | 2016-10-06 | Connected |  | No
National Grid | DIGHTON | 177288 | 2715 | 233.1 | Solar | 05_19W74 | 2016-06-17 01:00 | 2016-06-20 | 0 | 0 | 0 | [5 empty] | 2016-08-16 | 2016-09-15 | 21 | 4 | 17 | 2016-06-20 | 2016-07-15 | 18 | 5 | 13 | 2016-08-16 | 2016-09-15 | 21 | 4 | 17 | [6 empty] | 2016-06-17 01:00 | 2017-06-25 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | WESTMINSTER | 177289 | 1473 | 174 | Hydro | 01_609W1 | 2016-06-17 01:00 | 2016-06-20 | 11 | 11 | 0 | [10 empty] | 2016-07-06 | 2016-09-06 | 43 | 25 | 18 | [10 empty] | 2016-08-29 | 2016-06-17 01:00 | 2020-09-25 | Yes | STD | [8 empty] | 2020-09-28 | Connected |  | No
National Grid | REHOBOTH | 177290 | 2769 | 10 | Solar | 05_7L4 | 2016-06-17 01:00 | 2016-06-20 | 1 | 1 | 0 | 2016-06-21 | 2016-06-21 | 0 | 0 | 0 | [20 empty] | 2016-06-29 |  | 2017-06-25 | Yes | EXP |  | 2016-09-28 | 2016-10-05 | 5 | 0 | 5 | 2017-02-27 | 2017-02-27 | 2017-03-01 | Connected |  | No
National Grid | RANDOLPH | 177321 | 2368 | 7.6 | Solar | 07_97W5 | 2016-06-17 01:00 | 2016-06-20 | 1 | 1 | 0 | 2016-06-21 | 2017-01-26 | 149 | 0 | 149 | [20 empty] | 2016-06-28 |  | 2017-06-25 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 177322 | 1844 | 7.6 | Solar | 14_74L5 | 2016-06-17 01:00 | 2016-06-20 | 1 | 1 | 0 | 2016-06-21 | 2016-06-21 | 0 | 0 | 0 | [20 empty] | 2016-06-27 |  | 2017-06-25 |  | EXP | [6 empty] | 2016-11-03 | 2016-11-03 | 2016-11-07 | Connected |  | No
National Grid | METHUEN | 177324 | 1844 | 10 | Solar | 14_74L6 | 2016-06-17 01:00 | 2016-06-21 | 0 | 0 | 0 | 2016-06-21 | 2017-02-06 | 156 | 0 | 156 | [20 empty] | 2016-06-29 |  | 2017-06-26 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | TEWKSBURY | 177325 | 1876 | 6 | Solar | 14_59L3 | 2016-06-17 01:00 | 2016-06-21 | 1 | 1 | 0 | 2016-06-22 | 2016-10-05 | 73 | 0 | 73 | [20 empty] | 2016-07-07 |  | 2017-06-26 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WEYMOUTH | 177326 | 2188 | 828 | Solar | 07_99W32 | 2016-06-20 01:00 | 2016-06-21 | 3 | 3 | 0 | [10 empty] | 2016-06-24 | 2016-08-03 | 27 | 12 | 15 | [12 empty] | 2018-09-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | RANDOLPH | 177328 | 2368 | 15.2 | Solar | 07_97W3 | 2016-06-20 01:00 | 2016-06-21 | 2 | 2 | 0 | 2016-06-23 | 2016-06-23 | 0 | 0 | 0 | [20 empty] | 2016-06-28 | 2016-06-21 01:00 | 2017-06-26 |  | EXP | [6 empty] | 2016-10-12 | 2016-10-12 | 2016-10-17 | Connected |  | No
National Grid | METHUEN | 177329 | 1844 | 120 | Solar | 14_5J44 | 2016-06-21 01:00 | 2016-06-23 | 2 | 2 | 0 | 2016-06-27 | 2016-06-27 | 0 | 0 | 0 | [20 empty] | 2016-08-12 | 2016-06-21 01:00 | 2017-06-28 | Yes | EXP |  | 2017-02-15 | 2017-02-28 | 8 | 0 | 8 | 2017-04-19 | 2017-04-19 | 2017-04-19 | Connected |  | No
National Grid | WESTBOROUGH | 177359 | 1581 | 10.5 | Solar | 05_313W2 | 2016-06-21 01:00 | 2016-06-23 | 3 | 3 | 0 | 2016-06-28 | 2016-06-28 | 0 | 0 | 0 | [20 empty] | 2016-07-19 |  | 2017-06-28 | Yes | EXP |  | 2016-11-01 | 2016-12-07 | 24 | 0 | 24 | 2017-01-17 | 2017-01-17 | 2017-01-23 | Connected |  | No
National Grid | MELROSE | 177360 | 2176 | 43.2 | Solar | 12_4C3 | 2016-06-21 01:00 | 2016-06-23 | 0 | 0 | 0 | 2016-06-23 | 2016-06-23 | 0 | 0 | 0 | [20 empty] | 2016-06-28 |  | 2017-06-28 |  | EXP | [6 empty] | 2017-05-23 | 2017-05-23 | 2017-05-23 | Connected |  | No
National Grid | SALEM | 177361 | 1970 | 75 | Natural Gas | 12_49W2 | 2016-06-22 01:00 | 2016-06-23 | 18 | 18 | 0 | 2016-07-20 | 2016-07-20 | 0 | 0 | 0 | [20 empty] | 2016-09-12 |  | 2017-06-28 |  | EXP | [6 empty] | 2016-11-17 | 2016-11-17 | 2016-12-07 | Connected |  | No
National Grid | HAVERHILL | 177362 | 1830 | 150 | Solar | 14_48L3 | 2016-06-23 01:00 | 2016-06-23 | 0 | 0 | 0 | 2016-06-23 | 2016-06-23 | 0 | 0 | 0 | [20 empty] | 2016-07-15 |  | 2017-06-28 |  | EXP | [6 empty] | 2017-03-08 | 2017-03-08 | 2017-03-08 | Connected |  | No
National Grid | CHARLTON | 177363 | 1507 | 6.67 | Solar | 01_415L2 | 2016-06-23 01:00 | 2016-06-27 | 7 | 7 | 0 | 2016-07-07 | 2017-02-06 | 145 | 0 | 145 | [20 empty] | 2016-07-19 |  | 2017-07-02 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MARLBOROUGH | 177517 | 1752 | 75 | Solar | 05_317W1 | 2016-06-23 01:00 | 2016-06-23 | 5 | 0 | 5 | 2016-06-30 | 2016-09-16 | 54 | 0 | 54 | [22 empty] | 2016-10-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HOPEDALE | 177364 | 1747 | 50 | Solar | 05_335W4 | 2016-06-24 01:00 | 2016-06-27 | 1 | 1 | 0 | 2016-06-28 | 2016-06-28 | 0 | 0 | 0 | [20 empty] | 2016-07-07 | 2016-06-24 01:00 | 2017-07-02 |  | EXP | [6 empty] | 2017-01-20 | 2017-01-20 | 2017-01-24 | Connected |  | No
National Grid | MEDFORD | 177365 | 2155 | 390 | Solar | 12_37W2 | 2016-06-24 01:00 | 2016-06-27 | 0 | 0 | 0 | 2016-06-27 | 2016-06-27 | 0 | 0 | 0 | [20 empty] | 2016-09-15 |  | 2017-07-02 | Yes | EXP |  | 2016-12-12 | 2017-01-28 | 32 | 0 | 32 | 2017-03-10 | 2017-03-10 | 2017-03-09 | Connected |  | No
National Grid | SOUTH EASTON | 177366 | 2375 | 20 | Solar | 07_92W44 | 2016-06-28 01:00 | 2016-06-28 | 0 | 0 | 0 | 2016-06-28 | 2016-06-28 | 0 | 0 | 0 | [20 empty] | 2016-07-08 |  | 2017-07-03 |  | EXP | [6 empty] | 2016-11-02 | 2016-11-02 | 2016-11-02 | Connected |  | No
National Grid | WEBSTER | 177367 | 1570 | 528 | Solar | 01_412L5 | 2016-06-28 01:00 | 2016-06-28 | 0 | 0 | 0 | [10 empty] | 2016-06-28 | 2016-08-23 | 39 | 21 | 18 | [12 empty] | 2017-07-03 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | SALISBURY | 177398 | 1952 | 57.6 | Solar | 14_7L2 | 2016-06-28 01:00 | 2016-06-29 | 7 | 7 | 0 | 2016-07-11 | 2016-07-11 | 0 | 0 | 0 | [20 empty] | 2016-07-25 | 2016-06-28 01:00 | 2017-07-05 |  | EXP | [6 empty] | 2016-09-22 | 2016-09-22 | 2016-09-22 | Connected |  | Yes
National Grid | HAVERHILL | 177399 | 1830 | 75 | Solar | 14_48L3 | 2016-06-28 01:00 | 2016-06-29 | 0 | 0 | 0 | 2016-06-29 | 2016-06-29 | 0 | 0 | 0 | [20 empty] | 2016-08-29 |  | 2017-07-05 |  | EXP |  | 2016-08-03 | 2016-09-21 | 34 | 0 | 34 | 2017-03-08 | 2017-03-08 | 2017-03-08 | Connected |  | No
National Grid | BROCKTON | 177400 | 2301 | 480 | Solar | 07_911W25 | 2016-06-29 01:00 | 2016-06-30 | 0 | 0 | 0 | 2016-06-30 | 2016-06-30 | 0 | 0 | 0 | [20 empty] | 2016-08-24 |  | 2017-07-05 |  | EXP | [6 empty] | 2017-05-30 | 2017-05-30 | 2017-06-01 | Connected |  | No
National Grid | LOWELL | 177401 | 1854 | 3.44 | Solar | 14_77L3 | 2016-06-29 01:00 | 2016-06-30 | 3 | 3 | 0 | 2016-07-06 | 2016-09-22 | 55 | 0 | 55 | [21 empty] | 2016-06-29 01:00 | 2017-07-05 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | FALL RIVER | 177402 | 2721 | 10 | Solar | 05_115W52 | 2016-06-29 01:00 | 2016-06-30 | 3 | 3 | 0 | 2016-07-06 | 2016-07-06 | 0 | 0 | 0 | [20 empty] | 2016-07-18 |  | 2017-07-05 | Yes | EXP |  | 2017-05-23 | 2017-06-23 | 22 | 0 | 22 | 2017-07-17 | 2017-07-17 | 2017-07-19 | Connected |  | No
National Grid | OXFORD | 177404 | 1540 | 6 | Solar | 01_406L4 | 2016-06-29 01:00 | 2016-06-30 | 3 | 3 | 0 | 2016-07-06 | 2017-02-06 | 146 | 0 | 146 | [20 empty] | 2016-07-18 |  | 2017-07-05 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LOWELL | 177405 | 1854 | 7.6 | Solar | 14_77L3 | 2016-06-29 01:00 | 2016-06-30 | 3 | 3 | 0 | 2016-07-06 | 2017-02-06 | 146 | 0 | 146 | [20 empty] | 2016-07-19 |  | 2017-07-05 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTPORT | 177406 | 2790 | 7.6 | Solar | 05_115W45 | 2016-06-29 01:00 | 2016-06-30 | 3 | 3 | 0 | 2016-07-06 | 2017-01-26 | 139 | 0 | 139 | [20 empty] | 2016-07-19 | 2016-06-29 01:00 | 2017-07-05 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MILFORD | 177435 | 1757 | 366.3 | Solar | 05_335W5 | 2016-06-29 01:00 | 2016-06-30 | 3 | 3 | 0 | [10 empty] | 2016-07-06 | 2016-07-15 | 7 | 0 | 7 | [10 empty] | 2016-11-15 |  | 2017-07-05 |  | STD |  | 2017-03-08 | 2017-06-30 | 80 | 0 | 80 | 2017-08-16 | 2017-08-16 | 2017-08-16 | Connected |  | No
National Grid | HAVERHILL | 177403 | 1830 | 10 | Solar | 14_76L3 | 2016-06-30 01:00 | 2016-06-30 | 3 | 3 | 0 | 2016-07-06 | 2016-10-12 | 68 | 0 | 68 | [21 empty] | 2016-06-30 01:00 | 2017-07-05 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NEW BRAINTREE | 177436 | 1531 | 10 | Solar | 09_604W3 | 2016-06-30 01:00 | 2016-07-01 | 2 | 2 | 0 | 2016-07-06 | 2016-07-06 | 0 | 0 | 0 | [20 empty] | 2016-07-18 | 2016-06-30 01:00 | 2017-07-06 | Yes | EXP |  | 2016-10-12 | 2016-10-12 | 0 | 0 | 0 | 2016-11-21 | 2016-11-21 | 2016-11-21 | Connected |  | No
National Grid | WORCESTER | 177437 | 1604 | 8.6 | Solar | 01_10J383 | 2016-06-30 01:00 | 2016-07-01 | 2 | 2 | 0 | 2016-07-06 | 2016-07-06 | 0 | 0 | 0 | [20 empty] | 2016-07-18 | 2016-07-01 01:00 | 2017-07-06 | Yes | EXP |  | 2016-11-10 | 2016-12-02 | 14 | 0 | 14 | 2016-12-20 | 2016-12-20 | 2016-12-20 | Connected |  | No
National Grid | SOUTHBRIDGE | 177438 | 1550 | 260 | Solar | 01_413L7 | 2016-07-01 01:00 | 2016-07-01 | 2 | 2 | 0 | 2016-07-06 | 2016-07-06 | 0 | 0 | 0 | [20 empty] | 2016-09-19 | 2016-07-06 01:00 | 2017-10-06 | Yes | EXP |  | 2017-07-17 | 2017-09-27 | 51 | 0 | 51 | 2017-09-29 | 2017-09-29 | 2017-09-29 | Connected |  | No
National Grid | MEDFORD | 177474 | 2155 | 7.5 | Solar | 12_11J13 | 2016-07-06 01:00 | 2016-07-07 | 26 | 26 | 0 | 2016-08-12 | 2016-08-12 | 0 | 0 | 0 | [20 empty] | 2016-08-18 |  | 2017-07-12 | Yes | EXP | [6 empty] | 2017-01-27 | 2017-01-27 | 2017-01-27 | Connected |  | No
National Grid | MILFORD | 177475 | 1757 | 225 | Solar | 05_335W3 | 2016-07-06 01:00 | 2016-07-07 | 0 | 0 | 0 | 2016-07-07 | 2016-07-07 | 0 | 0 | 0 | 2016-09-06 | 2016-10-04 | 20 | 1 | 19 | [5 empty] | 2016-09-06 | 2016-10-04 | 20 | 1 | 19 | [5 empty] | 2016-10-28 | 2016-07-06 01:00 | 2017-02-05 |  | EXP | [6 empty] | 2017-02-03 | 2017-02-03 | 2017-02-22 | Connected |  | No
National Grid | DRACUT | 177476 | 1826 | 10 | Solar | 14_78L9 | 2016-07-06 01:00 | 2016-07-07 | 1 | 1 | 0 | 2016-07-08 | 2016-07-08 | 0 | 0 | 0 | [20 empty] | 2016-07-19 | 2016-07-06 01:00 | 2017-12-12 | Yes | EXP |  | 2017-05-16 | 2017-06-05 | 13 | 0 | 13 | 2017-07-28 | 2017-07-28 | 2017-07-28 | Connected |  | No
National Grid | NORTH OXFORD | 177477 | 1537 | 20 | Solar | 01_406L1 | 2016-07-06 01:00 | 2016-07-08 | 1 | 1 | 0 | 2016-07-11 | 2016-07-11 | 0 | 0 | 0 | [20 empty] | 2016-07-29 |  | 2017-08-31 | Yes | EXP |  | 2017-06-03 | 2017-08-25 | 58 | 0 | 58 | 2017-08-23 | 2017-08-23 | 2017-08-22 | Connected |  | No
National Grid | HAVERHILL | 177479 | 1832 | 75.6 | Solar | 14_43L3 | 2016-07-06 01:00 | 2016-07-08 | 35 | 35 | 0 | 2016-08-26 | 2017-08-18 | 244 | 55 | 189 | [20 empty] | 2016-12-01 |  | 2017-08-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MARLBOROUGH | 177480 | 1752 | 952 | Solar | 05_310W4 | 2016-07-07 01:00 | 2016-07-08 | 0 | 0 | 0 | [10 empty] | 2016-07-08 | 2016-09-19 | 50 | 29 | 21 | [12 empty] | 2017-07-13 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 177481 | 1607 | 150 | Solar | 01_8J389 | 2016-07-08 01:00 | 2016-07-11 | 0 | 0 | 0 | 2016-07-11 | 2016-07-11 | 0 | 0 | 0 | [20 empty] | 2016-08-08 |  | 2017-07-16 |  | EXP | [6 empty] | 2017-03-20 | 2017-03-20 | 2017-03-20 | Connected |  | No
National Grid | CHARLTON | 177508 | 1507 | 99.9 | Solar | 01_406L1 | 2016-07-08 01:00 | 2016-07-11 | 0 | 0 | 0 | 2016-07-11 | 2016-07-11 | 0 | 0 | 0 | [20 empty] | 2017-03-24 |  | 2017-08-31 |  | EXP | [6 empty] | 2017-08-03 | 2017-08-03 | 2017-08-03 | Connected |  | No
National Grid | NORTH ANDOVER | 177511 | 1845 | 27 | Solar | 14_7J3 | 2016-07-12 01:00 | 2016-07-12 | 0 | 0 | 0 | 2016-07-12 | 2016-07-12 | 0 | 0 | 0 | [20 empty] | 2016-07-12 | 2016-07-14 01:00 | 2017-07-17 |  | EXP | [6 empty] | 2016-07-12 | 2016-07-12 | 2016-07-25 | Connected |  | No
National Grid | EAST BRIDGEWATER | 177515 | 2333 | 143.2 | Solar | 07_797W23 | 2016-07-14 01:00 | 2016-07-14 | 1 | 1 | 0 | 2016-07-15 | 2016-07-15 | 0 | 0 | 0 | [20 empty] | 2016-08-23 |  | 2017-07-19 | Yes | EXP |  | 2016-12-05 | 2017-01-05 | 21 | 0 | 21 | 2017-02-15 | 2017-02-15 | 2017-02-23 | Connected |  | No
National Grid | RANDOLPH | 176957 | 2368 | 105 | Solar | 07_5W3 | 2016-07-15 01:00 | 2016-07-15 | 2 | 2 | 0 | 2016-07-19 | 2016-07-19 | 0 | 0 | 0 | [20 empty] | 2016-07-20 | 2016-07-16 01:00 | 2017-02-01 |  | EXP | [6 empty] | 2017-02-22 | 2017-02-22 | 2017-03-08 | Connected |  | No
National Grid | DUDLEY | 176959 | 1571 | 9 | Solar | 01_412L4 | 2016-07-16 01:00 | 2016-07-18 | 2 | 2 | 0 | 2016-07-20 | 2016-07-20 | 0 | 0 | 0 | [20 empty] | 2016-07-26 |  | 2017-07-23 | Yes | EXP |  | 2017-03-24 | 2017-05-04 | 28 | 0 | 28 | 2017-06-27 | 2017-06-27 | 2017-06-27 | Connected |  | No
National Grid | GLOUCESTER | 176960 | 1930 | 45 | Solar | 12_51T1 | 2016-07-17 01:00 | 2016-07-18 | 1 | 1 | 0 | 2016-07-19 | 2016-07-19 | 0 | 0 | 0 | [20 empty] | 2016-08-10 |  | 2017-07-23 |  | EXP | [6 empty] | 2017-02-13 | 2017-02-13 | 2017-02-13 | Connected |  | No
National Grid | HAVERHILL | 176961 | 1830 | 6.76 | Solar | 14_76L3 | 2016-07-18 01:00 | 2016-07-18 | 2 | 2 | 0 | 2016-07-20 | 2016-08-05 | 12 | 0 | 12 | [22 empty] | 2017-07-23 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LEOMINSTER | 176962 | 1453 | 3.8 | Solar | 01_225W4 | 2016-07-18 01:00 | 2016-07-19 | 1 | 1 | 0 | 2016-07-20 | 2017-07-26 | 254 | 0 | 254 | [20 empty] | 2016-07-26 | 2016-07-18 01:00 | 2017-07-24 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SAUGUS | 176963 | 1906 | 15.2 | Solar | 12_25W1 | 2016-07-18 01:00 | 2016-07-19 | 0 | 0 | 0 | 2016-07-19 | 2016-08-23 | 0 | 0 | 0 | [20 empty] | 2016-07-26 |  | 2018-10-12 | Yes | EXP |  | 2018-01-18 | 2018-03-05 | 30 | 0 | 30 |  |  | 2018-09-26 | Connected |  | Yes
National Grid | NORTH GRAFTON | 176964 | 1536 | 10 | Solar |  | 2016-07-19 01:00 | 2016-07-19 | 4 | 4 | 0 | 2016-07-25 | 2017-07-26 | 251 | 0 | 251 | [20 empty] | 2016-08-08 | 2016-07-19 01:00 | 2017-07-24 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MENDON | 176965 | 1756 | 7.6 | Solar | 05_332W1 | 2016-07-19 01:00 | 2016-07-19 | 4 | 4 | 0 | 2016-07-25 | 2016-07-25 | 0 | 0 | 0 | [20 empty] | 2016-08-05 |  | 2017-07-24 | Yes | EXP |  | 2016-12-05 | 2017-03-13 | 66 | 0 | 66 | 2017-03-17 | 2017-03-17 | 2017-03-17 | Connected |  | No
National Grid | HAVERHILL | 176994 | 1830 | 82 | Solar | 14_48L2 | 2016-07-19 01:00 | 2016-07-20 | 3 | 3 | 0 | 2016-07-25 | 2016-07-25 | 0 | 0 | 0 | [20 empty] | 2016-07-27 |  | 2017-07-25 |  | EXP | [6 empty] | 2016-12-02 | 2016-12-02 | 2016-12-02 | Connected |  | No
National Grid | LEOMINSTER | 176995 | 1453 | 6 | Solar | 01_225W4 | 2016-07-19 01:00 | 2016-07-20 | 3 | 3 | 0 | 2016-07-25 | 2017-07-13 | 242 | 0 | 242 | [20 empty] | 2016-08-04 |  | 2017-07-25 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | DUDLEY | 176996 | 1571 | 3.8 | Solar | 01_412L4 | 2016-07-19 01:00 | 2016-07-20 | 3 | 3 | 0 | 2016-07-25 | 2017-07-13 | 242 | 0 | 242 | [20 empty] | 2016-08-04 | 2016-07-19 01:00 | 2017-07-25 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | REHOBOTH | 176997 | 2769 | 10 | Solar | 05_7L5 | 2016-07-19 01:00 | 2016-07-20 | 3 | 3 | 0 | 2016-07-25 | 2016-07-25 | 0 | 0 | 0 | [20 empty] | 2016-08-04 |  | 2017-07-25 | Yes | EXP |  | 2016-09-29 | 2016-10-11 | 7 | 0 | 7 | 2017-03-01 | 2017-03-01 | 2017-03-03 | Connected |  | No
National Grid | GREAT BARRINGTON | 176998 | 1230 | 113.4 | Solar | 09_1109W1 | 2016-07-19 01:00 | 2016-07-20 | 3 | 3 | 0 | 2016-07-25 | 2016-07-25 | 0 | 0 | 0 | [20 empty] | 2016-08-29 | 2016-07-21 01:00 | 2017-07-25 |  | EXP | [6 empty] | 2017-01-17 | 2017-01-17 | 2017-01-23 | Connected |  | No
National Grid | WORCESTER | 177001 | 1604 | 52.25 | Solar | 01_10J383 | 2016-07-21 01:00 | 2016-07-21 | 4 | 4 | 0 | 2016-07-26 | 2016-07-26 | 0 | 0 | 0 | [20 empty] | 2016-09-09 |  | 2017-07-26 | Yes | EXP |  | 2017-04-05 | 2017-04-19 | 9 | 0 | 9 | 2017-06-08 | 2017-06-08 | 2017-06-08 | Connected |  | No
National Grid | METHUEN | 177002 | 1844 | 195 | Solar | 14_74L2 | 2016-07-21 01:00 | 2016-07-22 | 0 | 0 | 0 | 2016-07-22 | 2018-02-21 | 389 | 6 | 383 | [20 empty] | 2016-08-22 | 2016-07-26 01:00 | 2018-02-28 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | PEPPERELL | 177032 | 1463 | 10 | Solar | 01_210L1 | 2016-07-26 01:00 | 2016-07-26 | 3 | 3 | 0 | 2016-07-29 | 2016-07-29 | 0 | 0 | 0 | [20 empty] | 2016-08-05 |  | 2017-07-31 | Yes | EXP |  | 2016-12-29 | 2017-01-05 | 4 | 0 | 4 | 2017-02-16 | 2017-02-16 | 2017-02-16 | Connected |  | No
National Grid | SOMERSET | 177033 | 2725 | 225 | Solar | 05_11W84 | 2016-07-26 01:00 | 2016-07-27 | 1 | 1 | 0 | [5 empty] | 2016-09-15 | 2016-10-13 | 19 | 0 | 19 | 2016-07-28 | 2016-08-25 | 20 | 0 | 20 | 2016-09-15 | 2016-10-13 | 19 | 0 | 19 | [7 empty] | 2017-08-01 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | GRANBY | 177034 | 1033 | 3960 | Solar | 09_527L1 | 2016-07-26 01:00 | 2016-07-27 | 0 | 0 | 0 | [10 empty] | 2016-07-27 | 2016-08-24 | 20 | 5 | 15 | [12 empty] | 2017-08-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | GRANBY | 177035 | 1033 | 990 | Solar | 09_527L1 | 2016-07-26 01:00 | 2016-07-27 | 0 | 0 | 0 | [10 empty] | 2016-07-27 | 2016-08-24 | 20 | 5 | 15 | [12 empty] | 2017-08-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | GRANBY | 177036 | 1033 | 1980 | Solar | 09_527L1 | 2016-07-26 01:00 | 2016-07-27 | 0 | 0 | 0 | [10 empty] | 2016-07-27 | 2016-08-24 | 20 | 5 | 15 | [11 empty] | 2016-07-26 01:00 | 2017-08-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NANTUCKET | 177037 | 2554 | 396 | Solar | 04_101L5 | 2016-07-26 01:00 | 2016-07-27 | 4 | 4 | 0 | [10 empty] | 2016-08-02 | 2016-10-10 | 48 | 23 | 25 | [10 empty] | 2017-01-25 |  | 2017-08-01 | Yes | STD |  | 2017-05-12 | 2017-06-29 | 33 | 0 | 33 | 2017-06-27 | 2017-06-27 | 2017-07-05 | Connected |  | No
National Grid | NANTUCKET | 177131 | 2554 | 0 |  | 04_101L5 | 2016-07-26 01:00 | 2016-07-27 | 123 | 0 | 123 | [26 empty] | 2016-07-27 01:00 | 2017-08-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LEICESTER | 177038 | 1524 | 800 | Solar | 01_21W1 | 2016-07-27 01:00 | 2016-07-28 | 3 | 3 | 0 | [10 empty] | 2016-08-02 | 2016-10-26 | 59 | 44 | 15 | [10 empty] | 2017-08-11 | 2016-07-27 01:00 | 2019-03-15 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | LEICESTER | 177039 | 1524 | 800 | Solar | 01_23W3 | 2016-07-27 01:00 | 2016-07-28 | 3 | 3 | 0 | [10 empty] | 2016-08-02 | 2016-10-26 | 59 | 44 | 15 | [10 empty] | 2017-08-11 | 2016-07-27 01:00 | 2019-03-15 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | LEICESTER | 177040 | 1524 | 2592 | Solar | 01_21W1 | 2016-07-27 01:00 | 2016-07-28 | 3 | 3 | 0 | [10 empty] | 2016-08-02 | 2016-10-26 | 59 | 44 | 15 | [10 empty] | 2017-08-11 |  | 2021-05-31 | Yes | STD |  | 2020-11-05 | 2021-04-15 | 110 | 0 | 110 | 2021-05-03 | 2021-05-03 | 2021-06-15 | Connected |  | No
National Grid | NEWBURYPORT | 177069 | 1950 | 150 | Solar | 14_36L2 | 2016-07-29 01:00 | 2016-07-29 | 0 | 0 | 0 | 2016-07-29 | 2017-11-08 | 315 | 26 | 289 | [22 empty] | 2017-12-29 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LAWRENCE | 177070 | 1840 | 108 | Solar | 14_6J4 | 2016-07-29 01:00 | 2016-08-02 | 0 | 0 | 0 | 2016-08-02 | 2016-08-02 | 0 | 0 | 0 | [20 empty] | 2016-08-03 |  | 2017-08-07 |  | EXP | [6 empty] | 2017-03-08 | 2017-03-08 | 2017-03-08 | Connected |  | No
National Grid | LAWRENCE | 177071 | 1841 | 90 | Solar | 14_6J6 | 2016-07-29 01:00 | 2016-08-02 | 0 | 0 | 0 | 2016-08-02 | 2016-08-02 | 0 | 0 | 0 | [20 empty] | 2016-08-03 |  | 2017-08-07 |  | EXP | [6 empty] | 2017-04-25 | 2017-04-25 | 2017-04-25 | Connected |  | No
National Grid | LAWRENCE | 177072 | 1841 | 75 | Solar | 14_6J4 | 2016-07-29 01:00 | 2016-08-02 | 0 | 0 | 0 | 2016-08-02 | 2016-08-02 | 0 | 0 | 0 | [20 empty] | 2016-08-03 |  | 2017-08-07 |  | EXP | [6 empty] | 2017-01-12 | 2017-01-12 | 2017-01-12 | Connected |  | No
National Grid | NEWBURYPORT | 177073 | 1950 | 36 | Solar | 14_60L3 | 2016-08-03 01:00 | 2016-08-04 | 1 | 0 | 1 | 2016-08-05 | 2016-08-05 | 0 | 0 | 0 | [20 empty] | 2016-08-08 | 2016-08-03 01:00 | 2017-08-09 |  | EXP | [6 empty] | 2016-12-29 | 2016-12-29 | 2016-12-27 | Connected |  | Yes
National Grid | SALISBURY | 177074 | 1952 | 10 | Solar | 14_7L2 | 2016-08-03 01:00 | 2016-08-04 | 1 | 1 | 0 | 2016-08-05 | 2017-04-26 | 179 | 0 | 179 | [20 empty] | 2016-08-11 |  | 2017-08-09 | Yes | EXP |  | 2016-10-17 | 2016-10-26 | 7 | 0 | 7 |  |  |  | Withdrawn |  | Yes
National Grid | LYNN | 177075 | 1902 | 10 | Solar | 12_1384 | 2016-08-03 01:00 | 2016-08-04 | 1 | 1 | 0 | 2016-08-05 | 2016-09-19 | 30 | 0 | 30 | [21 empty] | 2016-08-03 01:00 | 2017-08-09 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | UXBRIDGE | 177076 | 1569 | 252 | Solar | 05_321W6 | 2016-08-03 01:00 | 2016-08-05 | 0 | 0 | 0 | [10 empty] | 2016-08-05 | 2016-08-18 | 9 | 1 | 8 | [10 empty] | 2017-06-09 |  | 2021-03-12 | Yes | STD |  | 2018-06-27 | 2018-12-21 | 177 | 0 | 177 |  |  | 2021-03-04 | Connected |  | No
National Grid | WILBRAHAM | 177108 | 1095 | 1600 | Solar | 09_507L3 | 2016-08-03 01:00 | 2016-08-05 | 4 | 4 | 0 | [10 empty] | 2016-08-11 | 2016-09-14 | 23 | 10 | 13 | [12 empty] | 2019-06-10 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WILBRAHAM | 177109 | 1095 | 640 | Solar | 09_507L3 | 2016-08-03 01:00 | 2016-08-05 | 4 | 4 | 0 | [10 empty] | 2016-08-11 | 2016-09-14 | 23 | 10 | 13 | [12 empty] | 2017-08-10 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WILBRAHAM | 177110 | 1095 | 1120 | Solar | 09_507L3 | 2016-08-03 01:00 | 2016-08-05 | 4 | 4 | 0 | [10 empty] | 2016-08-11 | 2016-09-14 | 23 | 10 | 13 | [12 empty] | 2019-06-10 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WILBRAHAM | 177107 | 1095 | 1600 | Solar | 09_507L1 | 2016-08-04 01:00 | 2016-08-05 | 4 | 4 | 0 | [10 empty] | 2016-08-11 | 2016-09-14 | 23 | 10 | 13 | [12 empty] | 2019-06-10 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | OXFORD | 177113 | 1540 | 936 | Solar | 01_406L3 | 2016-08-04 01:00 | 2016-08-09 | 128 | 128 | 0 | [27 empty] | 2017-08-14 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LAWRENCE | 177026 | 1843 | 23 | Solar | 14_1J8 | 2016-08-05 01:00 | 2016-08-16 | 1 | 0 | 1 | 2016-08-17 | 2016-08-29 | 8 | 0 | 8 | [20 empty] | 2016-08-29 |  | 2018-06-29 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 177114 | 1844 | 3.8 | Solar | 14_75L6 | 2016-08-05 01:00 | 2016-08-09 | 1 | 1 | 0 | 2016-08-10 | 2017-02-10 | 125 | 0 | 125 | [20 empty] | 2016-08-15 | 2016-08-05 01:00 | 2017-08-14 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BELLINGHAM | 177115 | 2019 | 10 | Solar | 05_108W60 | 2016-08-05 01:00 | 2016-08-09 | 1 | 1 | 0 | 2016-08-10 | 2016-08-10 | 0 | 0 | 0 | [20 empty] | 2016-08-15 |  | 2017-08-14 | Yes | EXP |  | 2016-12-05 | 2017-01-16 | 28 | 0 | 28 | 2017-03-16 | 2017-03-16 | 2017-03-20 | Connected |  | No
National Grid | WORCESTER | 177112 | 1606 | 4400 | Natural Gas | 01_HT31 | 2016-08-08 01:00 | 2016-08-09 | 0 | 0 | 0 | [25 empty] | 2016-09-27 |  | 2018-08-30 |  | STD |  | 2018-05-28 | 2018-05-27 | 0 | 0 | 0 |  |  | 2019-02-04 | Connected |  | Yes
National Grid | SWANSEA | 177145 | 2777 | 15.2 | Solar | 05_11W83 | 2016-08-08 01:00 | 2016-08-09 | 4 | 4 | 0 | 2016-08-15 | 2016-08-15 | 0 | 0 | 0 | [20 empty] | 2016-08-16 |  | 2017-08-14 |  | EXP | [6 empty] | 2017-01-05 | 2017-01-05 | 2017-01-06 | Connected |  | No
National Grid | GLOUCESTER | 177146 | 1930 | 25 | Solar | 12_24J2 | 2016-08-08 01:00 | 2016-08-09 | 0 | 0 | 0 | 2016-08-09 | 2016-08-09 | 0 | 0 | 0 | [20 empty] | 2016-08-10 | 2016-08-08 01:00 | 2017-08-14 |  | EXP | [6 empty] | 2017-01-09 | 2017-01-09 | 2017-01-09 | Connected |  | No
National Grid | PALMER | 177148 | 1069 | 4 | Solar | 09_523L4 | 2016-08-08 01:00 | 2016-08-10 | 22 | 22 | 0 | 2016-09-12 | 2016-09-12 | 0 | 0 | 0 | [20 empty] | 2016-09-19 |  | 2017-08-15 | Yes | EXP |  | 2017-04-11 | 2017-05-11 | 21 | 0 | 21 | 2017-05-15 | 2017-05-15 | 2017-05-18 | Connected |  | No
National Grid | HOPEDALE | 177147 | 1747 | 480 | Solar | 05_332W1 | 2016-08-09 01:00 | 2016-08-09 | 0 | 0 | 0 | 2016-08-09 | 2016-09-08 | 21 | 4 | 17 | [21 empty] | 2016-08-09 01:00 | 2017-08-14 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 177149 | 2301 | 10 | Solar | 07_94W40 | 2016-08-09 01:00 | 2016-08-10 | 2 | 2 | 0 | 2016-08-12 | 2016-08-12 | 0 | 0 | 0 | [20 empty] | 2016-08-18 | 2016-08-10 01:00 | 2017-08-15 | Yes | EXP |  | 2017-10-09 | 2017-11-07 | 15 | 0 | 15 | 2017-11-15 | 2017-11-15 | 2017-11-28 | Connected |  | No
National Grid | LOWELL | 177150 | 1852 | 7.56 | Solar | 14_3L5 | 2016-08-10 01:00 | 2016-08-11 | 3 | 3 | 0 | 2016-08-16 | 2016-08-16 | 0 | 0 | 0 | [20 empty] | 2016-08-19 |  | 2017-08-16 | Yes | EXP |  | 2016-12-14 | 2017-01-06 | 15 | 0 | 15 | 2017-01-12 | 2017-01-12 | 2017-01-12 | Connected |  | No
National Grid | SALEM | 177151 | 1970 | 5.2 | Solar | 12_2W1 | 2016-08-11 01:00 | 2016-08-11 | 3 | 3 | 0 | 2016-08-16 | 2017-06-09 | 203 | 0 | 203 | [20 empty] | 2016-08-19 |  | 2017-08-16 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FALL RIVER | 177153 | 2724 | 60 | Solar | 05_115W55 | 2016-08-12 01:00 | 2016-08-12 | 1 | 1 | 0 | 2016-08-15 | 2016-08-15 | 0 | 0 | 0 | [20 empty] | 2016-08-19 | 2016-08-12 01:00 | 2017-08-17 |  | EXP | [6 empty] | 2016-12-12 | 2016-12-12 | 2016-12-14 | Connected |  | No
National Grid | SOUTHBOROUGH | 177181 | 1772 | 650 | Solar | 05_310W6 | 2016-08-12 01:00 | 2016-08-12 | 0 | 0 | 0 | [10 empty] | 2016-08-12 | 2016-10-18 | 45 | 26 | 19 | [10 empty] | 2017-03-13 | 2016-08-12 01:00 | 2018-02-23 | Yes | STD |  | 2017-07-06 | 2017-12-19 | 109 | 0 | 109 | 2018-02-15 | 2018-02-15 | 2018-02-16 | Connected |  | No
National Grid | FALL RIVER | 177182 | 2723 | 120 | Solar | 05_115W52 | 2016-08-12 01:00 | 2016-08-12 | 0 | 0 | 0 | 2016-08-12 | 2016-08-12 | 0 | 0 | 0 | [20 empty] | 2016-09-08 | 2016-08-12 01:00 | 2017-08-17 | Yes | EXP |  | 2017-01-05 | 2017-05-04 | 82 | 0 | 82 | 2017-05-05 | 2017-05-05 | 2017-05-08 | Connected |  | No
National Grid | ORANGE | 177183 | 1364 | 990 | Solar | 09_705W2 | 2016-08-12 01:00 | 2016-08-12 | 2 | 2 | 0 | [10 empty] | 2016-08-16 | 2016-10-06 | 36 | 19 | 17 | [10 empty] | 2017-08-30 |  | 2020-11-30 | Yes | STD |  | 2020-01-31 | 2020-10-15 | 259 | 5 | 254 |  |  | 2020-11-20 | Connected |  | No
National Grid | LEOMINSTER | 177185 | 1453 | 225 | Solar | 01_207W3 | 2016-08-12 01:00 | 2016-08-15 | 2 | 2 | 0 | 2016-08-17 | 2016-08-17 | 0 | 0 | 0 | [20 empty] | 2016-09-13 |  | 2017-11-20 |  | EXP | [6 empty] | 2017-09-13 | 2017-09-13 | 2017-09-13 | Connected |  | No
National Grid | WINCHENDON | 177186 | 1475 | 498 | Solar | 01_612W1 | 2016-08-12 01:00 | 2016-08-16 | 30 | 30 | 0 | 2016-09-28 | 2017-03-20 | 116 | 25 | 91 | [22 empty] | 2017-08-21 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WINCHENDON | 177187 | 1475 | 498 | Solar | 01_612W1 | 2016-08-12 01:00 | 2016-08-16 | 30 | 30 | 0 | 2016-09-28 | 2017-03-20 | 116 | 25 | 91 | [21 empty] | 2016-08-15 01:00 | 2017-08-21 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SOUTH EASTON | 177184 | 2375 | 270 | Solar | 07_92W44 | 2016-08-15 01:00 | 2016-08-15 | 0 | 0 | 0 | 2016-08-15 | 2016-08-15 | 0 | 0 | 0 | [20 empty] | 2016-09-01 |  | 2017-08-20 |  | EXP |  | 2017-02-22 | 2017-06-20 | 82 | 0 | 82 | 2017-08-09 | 2017-08-09 | 2017-08-14 | Connected |  | No
National Grid | HAVERHILL | 177188 | 1830 | 51 | Solar | 14_48L2 | 2016-08-15 01:00 | 2016-08-16 | 1 | 1 | 0 | 2016-08-17 | 2016-08-17 | 0 | 0 | 0 | [20 empty] | 2016-08-29 |  | 2018-01-21 |  | EXP | [6 empty] | 2017-12-20 | 2017-12-20 | 2018-01-08 | Connected |  | No
National Grid | LAWRENCE | 177189 | 1843 | 23 | Solar | 14_1J8 | 2016-08-15 01:00 | 2016-08-16 | 1 | 1 | 0 | 2016-08-17 | 2016-08-17 | 0 | 0 | 0 | [20 empty] | 2016-08-29 |  | 2017-12-21 |  | EXP | [6 empty] | 2017-11-29 | 2017-11-29 | 2017-11-29 | Connected |  | No
National Grid | TEWKSBURY | 177217 | 1876 | 72 | Solar | 14_20L3 | 2016-08-15 01:00 | 2016-08-16 | 1 | 1 | 0 | 2016-08-17 | 2016-08-17 | 0 | 0 | 0 | [20 empty] | 2016-08-18 |  | 2018-01-21 |  | EXP | [6 empty] | 2017-11-28 | 2017-11-28 | 2017-11-28 | Connected |  | No
National Grid | LEOMINSTER | 177219 | 1453 | 36 | Solar | 01_207W6 | 2016-08-15 01:00 | 2016-08-16 | 1 | 1 | 0 | 2016-08-17 | 2016-08-17 | 0 | 0 | 0 | [20 empty] | 2016-09-22 |  | 2018-01-21 |  | EXP | [6 empty] | 2017-12-13 | 2017-12-13 | 2017-12-13 | Connected |  | No
National Grid | BELCHERTOWN | 177221 | 1007 | 144 | Solar | 09_509L2 | 2016-08-16 01:00 | 2016-08-16 | 21 | 21 | 0 | 2016-09-15 | 2016-09-15 | 0 | 0 | 0 | [20 empty] | 2016-09-27 | 2016-08-16 01:00 | 2017-08-21 |  | EXP | [6 empty] | 2017-03-30 | 2017-03-30 | 2017-04-05 | Connected |  | No
National Grid | HAVERHILL | 177224 | 1835 | 995 | Landfill Gas | 14_2356 | 2016-08-16 01:00 | 2016-08-16 | 0 | 0 | 0 | [10 empty] | 2016-08-16 | 2016-08-26 | 8 | 3 | 5 | [10 empty] | 2017-03-17 |  | 2020-11-30 | Yes | STD |  | 2020-03-11 | 2020-07-06 | 117 | 0 | 117 | 2020-11-04 | 2020-11-04 | 2020-11-12 | Connected |  | No
National Grid | WEYMOUTH | 177255 | 2190 | 35 | Solar | 07_99W32 | 2016-08-17 01:00 | 2016-08-17 | 282 | 282 | 0 | 2017-10-03 | 2017-10-03 | 0 | 0 | 0 | [20 empty] | 2017-10-04 |  | 2018-02-28 |  | EXP | [6 empty] | 2018-01-22 | 2018-01-22 | 2018-01-19 | Connected |  | No
National Grid | AMESBURY | 177256 | 1913 | 43.2 | Solar | 14_5J15 | 2016-08-17 01:00 | 2016-08-17 | 7 | 7 | 0 | [25 empty] | 2016-10-05 |  | 2017-08-22 |  | EXP | [6 empty] | 2017-08-23 | 2017-08-23 | 2017-08-22 | Connected |  | No
National Grid | MARLBOROUGH | 177257 | 1752 | 396 | Solar | 05_311W4 | 2016-08-17 01:00 | 2016-08-18 | 2 | 2 | 0 | 2016-08-22 | 2016-08-22 | 0 | 0 | 0 | [20 empty] | 2016-09-21 |  | 2017-08-23 |  | EXP | [6 empty] | 2017-04-21 | 2017-04-21 | 2017-04-28 | Connected |  | No
National Grid | GRANBY | 177258 | 1033 | 10 | Solar | 09_527L1 | 2016-08-18 01:00 | 2016-08-19 | 1 | 1 | 0 | 2016-08-22 | 2017-01-17 | 99 | 0 | 99 | [20 empty] | 2016-09-07 | 2016-08-18 01:00 | 2017-08-24 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | STOUGHTON | 177260 | 2072 | 180 | Solar | 07_913W69 | 2016-08-18 01:00 | 2016-08-19 | 6 | 6 | 0 | 2016-08-29 | 2016-08-29 | 0 | 0 | 0 | [20 empty] | 2016-09-26 |  | 2017-08-24 | Yes | EXP |  | 2017-07-18 | 2017-08-03 | 12 | 0 | 12 | 2017-09-25 | 2017-09-25 | 2017-09-25 | Connected |  | No
National Grid | STOUGHTON | 177261 | 2072 | 448 | Solar | 07_913W69 | 2016-08-18 01:00 | 2016-08-19 | 26 | 7 | 19 | [10 empty] | 2016-09-27 | 2016-11-28 | 41 | 38 | 3 | [10 empty] | 2017-07-06 | 2016-08-19 01:00 | 2018-07-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WARE | 177259 | 1082 | 65 | Hydro | 09_509L2 | 2016-08-19 01:00 | 2016-08-19 | 5 | 5 | 0 | 2016-08-26 | 2016-08-26 | 0 | 0 | 0 | [20 empty] | 2016-11-16 |  | 2017-07-15 | Yes | EXP |  | 2017-03-02 | 2017-05-08 | 46 | 0 | 46 | 2017-07-26 | 2017-07-26 | 2017-08-03 | Connected |  | No
National Grid | WEBSTER | 177263 | 1570 | 19 | Solar | 01_412L1 | 2016-08-23 01:00 | 2016-08-24 | 2 | 2 | 0 | 2016-08-26 | 2017-07-26 | 227 | 0 | 227 | [20 empty] | 2016-08-31 |  | 2017-08-29 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RANDOLPH | 177291 | 2368 | 23.4 | Solar | 07_5W2 | 2016-08-24 01:00 | 2016-08-25 | 2 | 2 | 0 | 2016-08-29 | 2016-08-29 | 0 | 0 | 0 | [20 empty] | 2016-08-31 |  | 2017-08-30 |  | EXP | [6 empty] | 2016-10-28 | 2016-10-28 | 2016-11-08 | Connected |  | No
National Grid | ABINGTON | 177292 | 2351 | 20 | Solar | 07_64J1 | 2016-08-24 01:00 | 2016-08-25 | 2 | 2 | 0 | 2016-08-29 | 2016-09-08 | 7 | 0 | 7 | [22 empty] | 2017-08-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTPORT | 177294 | 2790 | 17.6 | Solar | 05_115W45 | 2016-08-24 01:00 | 2016-08-29 | 7 | 7 | 0 | [27 empty] | 2017-09-03 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MEDFORD | 177293 | 2155 | 64 | Solar | 12_37W2 | 2016-08-25 01:00 | 2016-08-26 | 1 | 0 | 1 | 2016-08-29 | 2016-08-29 | 0 | 0 | 0 | [20 empty] | 2016-08-30 | 2016-08-26 01:00 | 2017-08-31 |  | EXP | [6 empty] | 2017-11-15 | 2017-11-15 | 2017-11-15 | Connected |  | No
National Grid | NORWELL | 177295 | 2061 | 12.8 | Solar | 07_96W43 | 2016-08-26 01:00 | 2016-08-29 | 0 | 0 | 0 | 2016-08-29 | 2016-08-29 | 0 | 0 | 0 | [20 empty] | 2016-09-30 |  | 2017-09-03 | Yes | EXP |  | 2017-02-24 | 2017-02-24 | 0 | 0 | 0 | 2017-08-10 | 2017-08-10 | 2017-08-10 | Connected |  | No
National Grid | HAVERHILL | 177296 | 1830 | 60 | Solar | 14_76L3 | 2016-08-26 01:00 | 2016-08-29 | 0 | 0 | 0 | 2016-08-29 | 2016-08-29 | 0 | 0 | 0 | [20 empty] | 2016-08-31 |  | 2017-09-03 |  | EXP | [6 empty] | 2017-03-27 | 2017-03-27 | 2017-03-27 | Connected |  | No
National Grid | BYFIELD | 177297 | 1922 | 16 | Solar | 14_34M1 | 2016-08-26 01:00 | 2016-08-29 | 7 | 7 | 0 | 2016-09-08 | 2016-09-08 | 0 | 0 | 0 | [20 empty] | 2016-09-09 |  | 2017-09-03 |  | EXP | [6 empty] | 2016-11-21 | 2016-11-21 | 2016-11-23 | Connected |  | No
National Grid | NORTH BROOKFIELD | 177331 | 1535 | 990 | Solar | 09_604W2 | 2016-08-29 01:00 | 2016-08-30 | 0 | 0 | 0 | [10 empty] | 2016-08-30 | 2016-12-15 | 73 | 57 | 16 | [12 empty] | 2017-09-04 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MARLBOROUGH | 177333 | 1752 | 784 | Solar | 05_310W4 | 2016-08-30 01:00 | 2016-08-30 | 0 | 0 | 0 | [10 empty] | 2016-08-30 | 2016-09-28 | 20 | 2 | 18 | [12 empty] | 2017-09-04 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | NANTUCKET | 177334 | 2554 | 27 | Solar | 04_101L7 | 2016-08-31 01:00 | 2016-08-31 | 2 | 2 | 0 | 2016-09-02 | 2016-09-02 | 0 | 0 | 0 | [20 empty] | 2016-09-21 |  | 2017-09-05 |  | EXP | [6 empty] | 2016-11-22 | 2016-11-22 | 2016-11-28 | Connected |  | No
National Grid | SOUTH HAMILTON | 177335 | 1982 | 186.5 | Solar | 12_51T2 | 2016-08-31 01:00 | 2016-08-31 | 2 | 2 | 0 | 2016-09-02 | 2016-09-02 | 0 | 0 | 0 | [20 empty] | 2016-09-09 | 2016-08-31 01:00 | 2017-09-05 |  | EXP | [6 empty] | 2017-01-09 | 2017-01-09 | 2017-01-09 | Connected |  | No
National Grid | WILLIAMSTOWN | 177336 | 1267 | 775.1 | Solar | 09_1003W1 | 2016-08-31 01:00 | 2016-09-01 | 0 | 0 | 0 | [10 empty] | 2016-09-01 | 2016-10-25 | 36 | 23 | 13 | [10 empty] | 2017-08-09 |  | 2027-04-24 | Yes | STD |  | 2016-11-03 | 2017-01-26 | 55 | 0 | 55 |  |  |  | Completion Documents |  | No
National Grid | SHIRLEY | 177337 | 1464 | 16 | Solar | 01_227W3 | 2016-09-01 01:00 | 2016-09-01 | 12 | 12 | 0 | 2016-09-20 | 2016-09-20 | 0 | 0 | 0 | [20 empty] | 2016-09-21 |  | 2017-09-06 |  | EXP | [6 empty] | 2017-03-23 | 2017-03-23 | 2017-03-23 | Connected |  | No
National Grid | SAUGUS | 177338 | 1906 | 433 | Solar | 12_23W1 | 2016-09-01 01:00 | 2016-09-01 | 2 | 2 | 0 | [10 empty] | 2016-09-06 | 2016-11-18 | 51 | 46 | 5 | [11 empty] | 2016-09-01 01:00 | 2017-09-06 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ABINGTON | 177339 | 2351 | 36 | Solar | 07_93W42 | 2016-09-01 01:00 | 2016-09-01 | 2 | 2 | 0 | 2016-09-06 | 2016-09-06 | 0 | 0 | 0 | [20 empty] | 2016-09-08 |  | 2017-09-06 | Yes | EXP |  | 2016-10-14 | 2016-10-26 | 8 | 0 | 8 | 2017-07-24 | 2017-07-24 | 2017-07-26 | Connected |  | No
National Grid | BROCKTON | 177368 | 2302 | 5.2 | Solar | 07_911W77 | 2016-09-02 01:00 | 2016-09-02 | 1 | 1 | 0 | 2016-09-06 | 2017-02-02 | 101 | 0 | 101 | [20 empty] | 2016-09-08 |  | 2017-09-07 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MEDFORD | 177371 | 2155 | 60 | Solar | 12_9C4 | 2016-09-06 01:00 | 2016-09-08 | 5 | 5 | 0 | 2016-09-14 | 2016-11-21 | 46 | 45 | 1 | [22 empty] | 2017-09-13 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HOLLAND | 177372 | 1521 | 2000 | Solar | 09_516L1 | 2016-09-07 01:00 | 2016-09-08 | 0 | 0 | 0 | [10 empty] | 2016-09-08 | 2016-10-24 | 31 | 17 | 14 | [10 empty] | 2017-05-10 |  | 2017-09-13 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LOWELL | 177373 | 1852 | 57.6 | Solar | 14_16L6 | 2016-09-08 01:00 | 2016-09-08 | 2 | 2 | 0 | 2016-09-12 | 2016-09-12 | 0 | 0 | 0 | [20 empty] | 2016-09-13 |  | 2017-09-13 |  | EXP | [6 empty] | 2017-01-05 | 2017-01-05 | 2017-01-05 | Connected |  | No
National Grid | GLOUCESTER | 177374 | 1930 | 345 | Solar | 12_51T3 | 2016-09-08 01:00 | 2016-09-08 | 2 | 2 | 0 | 2016-09-12 | 2018-03-13 | 361 | 2 | 359 | [20 empty] | 2016-09-27 |  | 2018-06-29 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MELROSE | 177407 | 2176 | 56 | Solar | 12_25W4 | 2016-09-09 01:00 | 2016-09-20 | 17 | 17 | 0 | 2016-10-04 | 2016-11-09 | 60 | 60 | 0 | [20 empty] | 2017-01-04 |  | 2018-07-31 |  | EXP | [8 empty] | 2018-12-12 | Connected |  | No
National Grid | WINTHROP | 177408 | 2152 | 184 | Solar | 12_22J7 | 2016-09-09 01:00 | 2016-09-12 | 16 | 16 | 0 | 2016-11-09 | 2016-12-16 | 174 | 174 | 0 | [20 empty] | 2017-06-19 | 2016-09-11 01:00 | 2018-11-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 177409 | 1507 | 1980 | Solar | 01_406L1 | 2016-09-11 01:00 | 2016-09-12 | 22 | 22 | 0 | [10 empty] | 2016-10-13 | 2016-11-01 | 13 | 0 | 13 | [10 empty] | 2017-04-28 | 2016-09-11 01:00 | 2020-12-31 | Yes | STD |  | 2020-09-29 | 2020-12-02 | 64 | 0 | 64 |  |  | 2020-12-21 | Connected |  | No
National Grid | SHEFFIELD | 177410 | 1257 | 1980 | Solar | 09_1109W1 | 2016-09-11 01:00 | 2016-09-12 | 22 | 22 | 0 | [10 empty] | 2016-10-13 | 2016-11-01 | 13 | 0 | 13 | [10 empty] | 2017-05-03 | 2016-09-11 01:00 | 2021-04-30 | Yes | STD |  | 2019-09-06 | 2021-01-05 | 487 | 5 | 482 |  |  | 2021-04-16 | Connected |  | No
National Grid | OXFORD | 177412 | 1540 | 1740 | Solar | 01_406L3 | 2016-09-11 01:00 | 2016-09-12 | 22 | 22 | 0 | [10 empty] | 2016-10-13 | 2016-11-01 | 13 | 0 | 13 | [10 empty] | 2017-05-02 |  | 2020-08-24 | Yes | STD |  | 2019-08-29 | 2019-11-22 | 85 | 0 | 85 |  |  | 2020-08-12 | Connected |  | No
National Grid | PEPPERELL | 177411 | 1463 | 20 | Solar | 01_226L2 | 2016-09-12 01:00 | 2016-09-12 | 10 | 10 | 0 | 2016-09-26 | 2017-02-10 | 93 | 0 | 93 | [20 empty] | 2016-10-05 | 2016-09-12 01:00 | 2017-09-17 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 177413 | 1841 | 3.8 | Solar | 14_6J2 | 2016-09-12 01:00 | 2016-09-13 | 1 | 1 | 0 | 2016-09-14 | 2017-11-07 | 282 | 0 | 282 | [20 empty] | 2016-09-19 | 2016-09-12 01:00 | 2017-11-18 | Yes | EXP | [9 empty] | Withdrawn |  | No
National Grid | EAST BROOKFIELD | 177414 | 1515 | 20.2 | Solar | 01_552L3 | 2016-09-12 01:00 | 2016-09-13 | 10 | 10 | 0 | 2016-09-27 | 2016-09-27 | 0 | 0 | 0 | [20 empty] | 2016-09-29 | 2016-09-15 01:00 | 2017-09-18 | Yes | EXP |  | 2016-12-28 | 2017-01-05 | 5 | 0 | 5 | 2017-01-12 | 2017-01-12 | 2017-01-12 | Connected |  | No
National Grid | SPENCER | 177415 | 1562 | 995 | Landfill Gas | 01_552L1 | 2016-09-15 01:00 | 2016-09-15 | 7 | 7 | 0 | [10 empty] | 2016-09-26 | 2016-10-18 | 15 | 0 | 15 | [10 empty] | 2017-04-28 |  | 2019-11-12 |  | STD |  | 2019-01-09 | 2019-02-24 | 46 | 0 | 46 |  |  | 2019-10-31 | Connected |  | No
National Grid | DUNSTABLE | 177416 | 1827 | 995 | Landfill Gas | 01_210L1 | 2016-09-15 01:00 | 2016-09-15 | 7 | 7 | 0 | [10 empty] | 2016-09-26 | 2016-10-19 | 16 | 0 | 16 | [12 empty] | 2017-09-20 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ATHOL | 177445 | 1331 | 336 | Solar | 09_702W2 | 2016-09-16 01:00 | 2016-09-16 | 0 | 0 | 0 | 2016-09-16 |  | 381 | 0 | 381 | [20 empty] | 2016-10-11 | 2016-09-16 01:00 | 2019-01-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | ATHOL | 177446 | 1331 | 311 | Solar | 09_702W1 | 2016-09-16 01:00 | 2016-09-16 | 0 | 0 | 0 | 2016-09-16 | 2016-09-16 | 0 | 0 | 0 | [20 empty] | 2016-10-19 |  | 2017-09-21 |  | EXP |  | 2017-10-16 | 2017-12-06 | 30 | 0 | 30 | 2017-12-13 | 2017-12-13 | 2022-10-22 | Connected |  | No
National Grid | FALL RIVER | 177448 | 2723 | 96 | Solar | 05_115W45 | 2016-09-20 01:00 | 2016-09-20 | 0 | 0 | 0 | 2016-09-20 | 2016-12-08 | 54 | 2 | 52 | [21 empty] | 2016-09-20 01:00 | 2017-09-25 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HANOVER | 177450 | 2339 | 84 | Solar | 07_95W1 | 2016-09-20 01:00 | 2016-09-20 | 4 | 4 | 0 | 2016-09-26 | 2016-09-26 | 0 | 0 | 0 | [20 empty] | 2016-09-26 | 2016-09-20 01:00 | 2017-09-25 |  | EXP | [6 empty] | 2017-05-09 | 2017-05-09 | 2017-05-11 | Connected |  | No
National Grid | UXBRIDGE | 177451 | 1569 | 4000 | Solar | 05_321W9 | 2016-09-20 01:00 | 2016-09-21 | 0 | 0 | 0 | [10 empty] | 2016-09-22 | 2016-12-14 | 57 | 42 | 15 | [10 empty] | 2017-09-20 | 2016-09-21 01:00 | 2023-01-31 | Yes | STD |  | 2022-08-02 | 2022-10-05 | 64 | 0 | 64 |  |  | 2023-01-26 | Connected |  | No
National Grid | UXBRIDGE | 177452 | 1569 | 2000 | Solar | 05_321W9 | 2016-09-21 01:00 | 2016-09-21 | 0 | 0 | 0 | [10 empty] | 2016-09-21 | 2016-12-14 | 57 | 42 | 15 | [10 empty] | 2017-09-20 |  | 2019-04-22 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | STOUGHTON | 177482 | 2072 | 57.6 | Solar | 07_75W7 | 2016-09-21 01:00 | 2016-09-22 | 4 | 4 | 0 | 2016-09-27 | 2016-09-27 | 0 | 0 | 0 | [20 empty] | 2016-10-19 |  | 2017-09-27 |  | EXP | [6 empty] | 2017-04-10 | 2017-04-10 | 2017-04-13 | Connected |  | No
National Grid | TOPSFIELD | 177483 | 1983 | 19 | Solar | 12_26L1 | 2016-09-22 01:00 | 2016-09-26 | 2 | 2 | 0 | 2016-09-27 | 2016-09-27 | 0 | 0 | 0 | [20 empty] | 2016-10-12 | 2016-09-22 01:00 | 2017-10-13 |  | EXP | [6 empty] | 2017-09-26 | 2017-09-26 | 2017-09-26 | Connected |  | No
National Grid | NANTUCKET | 177484 | 2554 | 19.7 | Solar | 04_101L2 | 2016-09-22 01:00 | 2016-09-26 | 1 | 1 | 0 | 2016-09-27 | 2016-09-27 | 0 | 0 | 0 | [20 empty] | 2016-10-03 |  | 2017-10-01 | Yes | EXP |  | 2017-02-21 | 2017-03-16 | 17 | 0 | 17 | 2017-01-04 | 2017-01-04 | 2017-03-21 | Connected |  | No
National Grid | FRANKLIN | 177485 | 2038 | 128 | Solar | 05_344W6 | 2016-09-22 01:00 | 2016-09-26 | 5 | 5 | 0 | 2016-10-03 | 2016-10-03 | 0 | 0 | 0 | [20 empty] | 2016-10-28 | 2016-09-23 01:00 | 2017-10-01 |  | EXP | [6 empty] | 2017-12-04 | 2017-12-04 | 2017-12-18 | Connected |  | No
National Grid | DIGHTON | 177486 | 2715 | 8 | Solar | 05_19W73 | 2016-09-23 01:00 | 2016-09-26 | 1 | 1 | 0 | 2016-09-27 | 2016-09-27 | 0 | 0 | 0 | [20 empty] | 2016-09-29 |  | 2017-10-01 | Yes | EXP |  | 2017-03-31 | 2017-04-13 | 9 | 0 | 9 | 2017-05-01 | 2017-05-01 | 2017-05-03 | Connected |  | No
National Grid | NORTHBOROUGH | 177487 | 1532 | 5.2 | Solar | 05_313W4 | 2016-09-23 01:00 | 2016-09-26 | 3 | 3 | 0 | 2016-09-29 | 2016-09-29 | 0 | 0 | 0 | [20 empty] | 2016-10-11 | 2016-09-23 01:00 | 2017-10-01 |  | EXP | [6 empty] | 2017-05-10 | 2017-05-10 | 2017-05-12 | Connected |  | No
National Grid | SOUTHBOROUGH | 177488 | 1772 | 7.6 | Solar | 05_317W3 | 2016-09-23 01:00 | 2016-09-26 | 3 | 3 | 0 | 2016-09-29 | 2016-09-29 | 0 | 0 | 0 | [20 empty] | 2016-10-05 |  | 2017-10-01 | Yes | EXP |  | 2017-08-22 | 2017-09-12 | 14 | 0 | 14 | 2017-09-25 | 2017-09-25 | 2017-09-28 | Connected |  | No
National Grid | AUBURN | 177489 | 1501 | 288 | Solar | 01_26W1 | 2016-09-23 01:00 | 2016-09-26 | 1 | 1 | 0 | 2016-09-27 | 2016-09-27 | 0 | 0 | 0 | [20 empty] | 2016-11-22 | 2016-09-23 01:00 | 2017-10-01 |  | EXP | [6 empty] | 2017-06-14 | 2017-06-14 | 2017-06-14 | Connected |  | No
National Grid | DUNSTABLE | 177490 | 1827 | 3.8 | Solar | 01_210L1 | 2016-09-23 01:00 | 2016-09-26 | 3 | 3 | 0 | 2016-09-29 | 2016-09-29 | 0 | 0 | 0 | [20 empty] | 2016-10-05 |  | 2017-10-01 | Yes | EXP |  | 2017-04-10 | 2017-04-25 | 10 | 0 | 10 | 2017-05-17 | 2017-05-17 | 2017-05-17 | Connected |  | No
National Grid | PEPPERELL | 177520 | 1463 | 1132.2 | Solar | 01_226L1 | 2016-09-27 01:00 | 2016-09-29 | 7 | 7 | 0 | [10 empty] | 2016-10-11 | 2016-12-27 | 52 | 40 | 12 | [11 empty] | 2016-09-29 01:00 | 2017-10-04 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BELLINGHAM | 177521 | 2019 | 7.6 | Solar | 05_108W60 | 2016-09-29 01:00 | 2016-09-29 | 3 | 3 | 0 | 2016-10-04 | 2016-10-04 | 0 | 0 | 0 | [20 empty] | 2016-10-05 |  | 2017-10-04 | Yes | EXP |  | 2017-01-03 | 2017-01-16 | 9 | 0 | 9 | 2017-02-16 | 2017-02-16 | 2017-02-22 | Connected |  | No
National Grid | SEEKONK | 177526 | 2771 | 6 | Solar | 05_7L1 | 2016-09-30 01:00 | 2016-10-04 | 0 | 0 | 0 | 2016-10-04 | 2016-10-04 | 0 | 0 | 0 | [20 empty] | 2016-10-05 | 2016-10-03 01:00 | 2017-10-09 |  | EXP | [6 empty] | 2017-02-13 | 2017-02-13 | 2017-02-16 | Connected |  | No
National Grid | MARLBOROUGH | 176966 | 1752 | 6 | Solar | 05_311W2 | 2016-10-03 01:00 | 2016-10-04 | 0 | 0 | 0 | 2016-10-04 | 2016-10-04 | 0 | 0 | 0 | [20 empty] | 2016-10-11 |  | 2017-05-12 | Yes | EXP |  | 2016-11-22 | 2016-11-23 | 1 | 0 | 1 | 2017-05-15 | 2017-05-15 | 2017-05-15 | Connected |  | No
National Grid | NEWBURYPORT | 176968 | 1950 | 20 | Solar | 14_60L1 | 2016-10-04 01:00 | 2016-10-04 | 2 | 2 | 0 | 2016-10-06 | 2016-10-06 | 0 | 0 | 0 | [20 empty] | 2016-10-13 | 2016-10-04 01:00 | 2017-10-09 |  | EXP | [6 empty] | 2017-08-31 | 2017-08-31 | 2017-08-31 | Connected |  | No
National Grid | BROCKTON | 176969 | 2301 | 540 | Solar | 07_98W19 | 2016-10-04 01:00 | 2016-10-04 | 4 | 4 | 0 | [10 empty] | 2016-10-10 | 2016-11-07 | 19 | 8 | 11 | [10 empty] | 2017-04-06 |  | 2018-06-26 | Yes | STD |  | 2017-12-01 | 2018-06-12 | 193 | 0 | 193 | 2018-04-05 | 2018-04-05 | 2018-06-22 | Connected |  | No
National Grid | METHUEN | 176972 | 1844 | 7.6 | Solar | 14_74L1 | 2016-10-05 01:00 | 2016-10-06 | 2 | 2 | 0 | 2016-10-10 | 2017-02-23 | 91 | 0 | 91 | [20 empty] | 2016-10-12 |  | 2017-10-11 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MILFORD | 176974 | 1757 | 6.45 | Solar | 05_336W3 | 2016-10-06 01:00 | 2016-10-07 | 5 | 5 | 0 | 2016-10-17 | 2017-01-17 | 61 | 0 | 61 | [20 empty] | 2016-10-21 | 2016-10-07 01:00 | 2017-10-12 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LYNN | 177003 | 1904 | 6.6 | Solar | 12_29W1 | 2016-10-07 01:00 | 2016-10-07 | 1 | 1 | 0 | 2016-10-11 | 2016-10-11 | 0 | 0 | 0 | [20 empty] | 2016-10-17 | 2016-10-10 01:00 | 2018-03-30 | Yes | EXP |  | 2017-10-09 | 2017-10-11 | 1 | 0 | 1 | 2018-02-12 | 2018-02-12 | 2018-03-23 | Connected |  | No
National Grid | ADAMS | 177004 | 1220 | 240 | Solar | 09_1021W2 | 2016-10-10 01:00 | 2016-10-11 | 0 | 0 | 0 | 2016-10-11 | 2017-04-10 | 123 | 19 | 104 | [20 empty] | 2016-12-09 | 2016-10-10 01:00 | 2017-10-16 | Yes | EXP | [9 empty] | Withdrawn |  | No
National Grid | CHELMSFORD | 177005 | 1824 | 720 | Solar | 14_2L1 | 2016-10-10 01:00 | 2016-10-11 | 0 | 0 | 0 | [10 empty] | 2016-10-11 | 2016-12-15 | 45 | 33 | 12 | [10 empty] | 2018-01-08 | 2016-10-11 01:00 | 2020-10-30 | Yes | STD |  | 2019-08-06 | 2020-10-16 | 438 | 5 | 433 |  |  | 2020-10-21 | Connected |  | No
National Grid | GARDNER | 177006 | 1440 | 10 | Solar | 01_607W4 | 2016-10-11 01:00 | 2016-10-12 | 1 | 1 | 0 | 2016-10-13 | 2016-10-17 | 0 | 0 | 0 | [20 empty] | 2016-10-17 |  | 2019-09-30 |  | EXP |  | 2017-05-05 | 2017-05-05 | 39 | 0 | 39 | 2018-03-13 | 2018-03-13 | 2019-09-13 | Connected |  | No
National Grid | ATTLEBORO | 177007 | 2703 | 997 | Solar | 05_9L2 | 2016-10-13 01:00 | 2016-10-13 | 6 | 6 | 0 | [10 empty] | 2016-10-21 | 2016-11-01 | 7 | 0 | 7 | [11 empty] | 2016-10-13 01:00 | 2017-10-18 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ANDOVER | 177008 | 1810 | 494.5 | Solar | 14_54L3 | 2016-10-13 01:00 | 2016-10-14 | 0 | 0 | 0 | 2016-10-14 | 2016-11-21 | 0 | 0 | 0 | 2017-02-16 | 2017-03-16 | 0 | 0 | 0 | [5 empty] | 2017-02-16 | 2017-03-16 | 0 | 0 | 0 | [5 empty] | 2017-03-31 |  | 2018-04-09 | Yes | EXP |  | 2017-06-01 | 2017-06-01 | 0 | 0 | 0 | 2018-04-03 | 2018-04-03 | 2018-04-03 | Connected |  | No
National Grid | DUNSTABLE | 177009 | 1827 | 18 | Solar | 01_210L1 | 2016-10-13 01:00 | 2016-10-14 | 1 | 1 | 0 | 2016-10-17 | 2016-10-17 | 0 | 0 | 0 | [20 empty] | 2016-10-17 |  | 2017-10-19 |  | EXP | [6 empty] | 2017-01-05 | 2017-01-05 | 2017-01-05 | Connected |  | No
National Grid | QUINCY | 177010 | 2169 | 720 | Solar | 07_3W1 | 2016-10-14 01:00 | 2016-10-25 | 0 | 0 | 0 | [10 empty] | 2016-10-25 | 2017-01-20 | 58 | 44 | 14 | [10 empty] | 2018-02-06 | 2016-10-14 01:00 | 2019-08-15 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MARLBOROUGH | 177011 | 1752 | 10 | Solar | 05_311W2 | 2016-10-14 01:00 | 2016-10-18 | 1 | 1 | 0 | 2016-10-19 | 2016-10-19 | 0 | 0 | 0 | [20 empty] | 2016-10-24 | 2016-10-14 01:00 | 2017-10-23 | Yes | EXP |  | 2017-01-20 | 2017-03-02 | 28 | 0 | 28 | 2017-03-29 | 2017-03-29 | 2017-03-31 | Connected |  | Yes
National Grid | DRACUT | 177087 | 1826 | 0.24 | Solar | 14_78L1 | 2016-10-14 01:00 | 2016-10-20 | 0 | 0 | 0 | 2016-10-20 | 2016-11-14 | 0 | 0 | 0 | [20 empty] | 2016-12-13 | 2016-10-14 01:00 | 2019-06-11 |  | EXP | [8 empty] | 2019-04-10 | Connected |  | No
National Grid | DRACUT | 177116 | 1826 | 150 | Solar | 14_78L1 | 2016-10-14 01:00 | 2016-10-20 | 0 | 0 | 0 | 2016-10-20 | 2016-11-14 | 0 | 0 | 0 | [20 empty] | 2017-01-26 | 2016-10-17 01:00 | 2019-03-11 | Yes | EXP | [8 empty] | 2019-02-26 | Connected |  | No
National Grid | WESTBOROUGH | 177043 | 1581 | 792 | Solar | 05_312W1 | 2016-10-17 01:00 | 2016-10-31 | 0 | 0 | 0 | [10 empty] | 2016-10-26 | 2017-02-07 | 69 | 56 | 13 | [10 empty] | 2018-04-06 |  | 2022-03-28 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | HAMILTON | 177044 | 1982 | 630 | Solar | 12_51T2 | 2016-10-17 01:00 | 2016-10-18 | 5 | 5 | 0 | [26 empty] | 2016-10-17 01:00 | 2017-10-23 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | COHASSET | 177045 | 2025 | 696 | Solar | 07_96W41 | 2016-10-17 01:00 | 2016-10-25 | 0 | 0 | 0 | [10 empty] | 2016-10-25 | 2017-01-23 | 59 | 44 | 15 | [10 empty] | 2018-02-06 |  | 2021-10-15 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | HALIFAX | 177046 | 2338 | 1350 | Solar | 07_912W75 | 2016-10-17 01:00 | 2016-10-18 | 5 | 5 | 0 | [26 empty] | 2016-10-17 01:00 | 2017-10-23 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HANSON | 177047 | 2341 | 876 | Solar | 07_797W24 | 2016-10-17 01:00 | 2016-10-25 | 0 | 0 | 0 | [10 empty] | 2016-10-25 | 2017-01-20 | 58 | 43 | 15 | [10 empty] | 2018-03-06 |  | 2021-12-15 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | ABINGTON | 177048 | 2351 | 1320 | Solar | 07_93W42 | 2016-10-17 01:00 | 2016-10-18 | 5 | 5 | 0 | [26 empty] | 2016-10-17 01:00 | 2017-10-23 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SPENCER | 177078 | 1562 | 22.8 | Solar | 01_552L1 | 2016-10-17 01:00 | 2016-10-18 | 1 | 1 | 0 | 2016-10-19 | 2016-10-19 | 0 | 0 | 0 | [20 empty] | 2016-10-24 |  | 2017-10-23 | Yes | EXP |  | 2017-03-28 | 2017-05-22 | 38 | 0 | 38 | 2017-08-29 | 2017-08-29 | 2017-09-01 | Connected |  | No
National Grid | WORCESTER | 177041 | 1602 | 4400 | Solar | 01_8W2 | 2016-10-18 01:00 | 2016-10-26 | 0 | 0 | 0 | [25 empty] | 2016-10-26 | 2016-10-18 01:00 | 2016-10-23 |  | STD | [6 empty] | 2016-10-26 | 2016-10-26 | 2016-10-26 | Connected |  | No
National Grid | SCITUATE | 177080 | 2066 | 312 | Solar | 07_915W82 | 2016-10-18 01:00 | 2016-10-19 | 4 | 4 | 0 | [10 empty] | 2016-10-25 | 2017-01-23 | 59 | 43 | 16 | [10 empty] | 2018-01-09 | 2016-10-18 01:00 | 2021-11-08 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | SOUTHBOROUGH | 177081 | 1772 | 600 | Solar | 05_314W2 | 2016-10-18 01:00 | 2016-10-19 | 5 | 5 | 0 | [10 empty] | 2016-10-26 | 2017-01-13 | 53 | 46 | 7 | [10 empty] | 2017-06-20 |  | 2021-03-06 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | LYNN | 177082 | 1905 | 750 | Solar | 12_1393 | 2016-10-18 01:00 | 2016-10-19 | 5 | 5 | 0 | [10 empty] | 2016-10-26 | 2017-01-13 | 53 | 42 | 11 | [12 empty] | 2017-10-24 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | REVERE | 177083 | 2151 | 750 | Solar | 12_35J3 | 2016-10-18 01:00 | 2016-10-19 | 5 | 5 | 0 | [10 empty] | 2016-10-26 | 2017-01-09 | 49 | 39 | 10 | [11 empty] | 2016-10-18 01:00 | 2017-10-24 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WEYMOUTH | 177084 | 2184 | 180 | Solar | 07_6W1 | 2016-10-18 01:00 | 2016-10-31 | 0 | 0 | 0 | 2017-10-27 | 2017-11-27 | 18 | 0 | 18 | 2018-01-12 | 2018-02-16 | 24 | 0 | 24 | [5 empty] | 2018-01-12 | 2018-02-16 | 24 | 0 | 24 | [5 empty] | 2018-03-30 |  | 2021-06-09 | Yes | EXP | [9 empty] | Withdrawn |  | No
National Grid | SALEM | 177085 | 1970 | 540 | Solar | 12_49W6 | 2016-10-18 01:00 | 2016-10-19 | 5 | 5 | 0 | [10 empty] | 2016-10-26 | 2017-01-10 | 50 | 39 | 11 | [12 empty] | 2017-10-24 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WHITMAN | 177086 | 2382 | 720 | Solar | 07_93W43 | 2016-10-18 01:00 | 2016-10-19 | 6 | 6 | 0 | [26 empty] | 2016-10-19 01:00 | 2017-10-24 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | AYER | 176586 | 1432 | 236 | Solar | 01_201W2 | 2016-10-19 01:00 | 2016-10-19 | 0 | 0 | 0 | 2016-10-19 | 2016-10-19 | 0 | 0 | 0 | [20 empty] | 2017-01-06 |  | 2017-04-16 | Yes | EXP | [6 empty] | 2017-01-10 | 2017-01-10 | 2018-01-04 | Connected |  | No
National Grid | BEVERLY | 177117 | 1915 | 360 | Solar | 12_12L6 | 2016-10-19 01:00 | 2016-10-20 | 4 | 4 | 0 | 2016-10-26 | 2016-12-01 | 24 | 0 | 24 | [22 empty] | 2017-10-25 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | HAVERHILL | 177118 | 1832 | 510 | Solar | 14_48L2 | 2016-10-19 01:00 | 2016-10-20 | 4 | 4 | 0 | [10 empty] | 2016-10-26 | 2017-01-10 | 50 | 39 | 11 | [12 empty] | 2017-10-25 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BEVERLY | 177119 | 1915 | 390 | Solar | 12_51L2 | 2016-10-19 01:00 | 2016-10-20 | 4 | 4 | 0 | 2016-10-26 | 2018-02-14 | 319 | 36 | 283 | [22 empty] | 2017-10-25 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | GLOUCESTER | 177120 | 1930 | 420 | Solar | 12_24J8 | 2016-10-19 01:00 | 2016-10-20 | 4 | 4 | 0 | 2016-10-26 | 2018-02-14 | 319 | 44 | 275 | [22 empty] | 2017-10-25 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | ANDOVER | 177121 | 1810 | 540 | Solar | 14_59L6 | 2016-10-19 01:00 | 2016-10-20 | 25 | 25 | 0 | [10 empty] | 2016-11-28 | 2017-02-03 | 46 | 36 | 10 | [12 empty] | 2017-10-25 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTFORD | 177122 | 1886 | 830 | Solar | 14_58L3 | 2016-10-20 01:00 | 2016-10-21 | 0 | 0 | 0 | [10 empty] | 2016-10-21 | 2017-02-03 | 70 | 58 | 12 | [11 empty] | 2016-10-20 01:00 | 2017-10-26 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | DIGHTON | 177123 | 2715 | 3625 | Solar | 05_19W74 | 2016-10-20 01:00 | 2016-10-21 | 0 | 0 | 0 | [10 empty] | 2016-10-24 | 2017-01-04 | 48 | 35 | 13 | [10 empty] | 2017-07-21 | 2016-10-20 01:00 | 2024-04-30 | Yes | STD |  | 2023-09-29 | 2024-02-05 | 129 | 45 | 84 |  |  |  | Completion Documents |  | No
National Grid | DIGHTON | 177124 | 2715 | 2000 | Solar | 05_19W74 | 2016-10-20 01:00 | 2016-10-21 | 0 | 0 | 0 | [10 empty] | 2016-10-21 | 2017-01-04 | 49 | 35 | 14 | [10 empty] | 2017-07-21 | 2016-10-20 01:00 | 2019-04-22 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | HALIFAX | 177125 | 2338 | 1560 | Solar | 07_912W75 | 2016-10-20 01:00 | 2016-10-21 | 0 | 0 | 0 | [10 empty] | 2016-10-21 | 2016-11-22 | 21 | 6 | 15 | [10 empty] | 2017-07-11 |  | 2020-12-31 | Yes | STD |  | 2020-05-20 | 2020-12-12 | 207 | 5 | 202 |  |  | 2020-12-31 | Connected |  | No
National Grid | GLOUCESTER | 177155 | 1930 | 20 | Solar | 12_51T1 | 2016-10-24 01:00 | 2016-10-24 | 4 | 4 | 0 | 2016-10-28 | 2016-10-28 | 0 | 0 | 0 | [20 empty] | 2016-10-31 |  | 2017-10-29 |  | EXP | [6 empty] | 2016-12-20 | 2016-12-20 | 2016-12-20 | Connected |  | No
National Grid | NORWELL | 177157 | 2061 | 20.5 | Solar | 07_96W44 | 2016-10-26 01:00 | 2016-10-26 | 7 | 7 | 0 | 2016-11-04 | 2016-11-04 | 0 | 0 | 0 | [20 empty] | 2016-11-04 | 2016-10-26 01:00 | 2017-10-31 |  | EXP | [6 empty] | 2017-02-22 | 2017-02-22 | 2017-02-28 | Connected |  | No
National Grid | WORCESTER | 177158 | 1603 | 10 | Solar | 01_6W2 | 2016-10-26 01:00 | 2016-10-27 | 3 | 3 | 0 | 2016-11-01 | 2016-11-01 | 0 | 0 | 0 | [20 empty] | 2016-11-03 | 2016-10-27 01:00 | 2017-11-01 | Yes | EXP |  | 2017-04-17 | 2017-04-25 | 5 | 0 | 5 | 2017-05-18 | 2017-05-18 | 2017-05-18 | Connected |  | No
National Grid | GARDNER | 177159 | 1440 | 10 | Solar | 01_607W5 | 2016-10-27 01:00 | 2016-10-28 | 2 | 2 | 0 | 2016-11-01 | 2016-11-01 | 0 | 0 | 0 | [20 empty] | 2016-11-03 |  | 2018-03-02 | Yes | EXP |  | 2017-07-17 | 2017-08-29 | 31 | 0 | 31 | 2018-01-25 | 2018-01-25 | 2018-01-25 | Connected |  | No
National Grid | BYFIELD | 177160 | 1922 | 32 | Solar | 14_60L2 | 2016-10-28 01:00 | 2016-10-28 | 2 | 2 | 0 | 2016-11-01 | 2016-11-01 | 0 | 0 | 0 | [20 empty] | 2016-11-02 | 2016-10-28 01:00 | 2017-11-02 |  | EXP | [6 empty] | 2017-03-21 | 2017-03-21 | 2017-03-21 | Connected |  | No
National Grid | AMESBURY | 177161 | 1913 | 80 | Solar | 14_275L2 | 2016-10-28 01:00 | 2016-11-01 | 2 | 2 | 0 | 2016-11-03 | 2016-11-03 | 0 | 0 | 0 | [20 empty] | 2016-11-09 |  | 2017-11-06 |  | EXP |  | 2017-01-09 | 2017-05-09 | 83 | 0 | 83 | 2017-06-12 | 2017-06-12 | 2017-06-12 | Connected |  | No
National Grid | BROCKTON | 177162 | 2301 | 79 | Solar | 07_911W13 | 2016-10-28 01:00 | 2016-11-01 | 0 | 0 | 0 | 2016-11-01 | 2018-01-28 | 303 | 2 | 301 | [20 empty] | 2016-11-14 |  | 2018-02-06 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SWANSEA | 177194 | 2777 | 28 | Solar | 05_11W83 | 2016-10-31 01:00 | 2016-11-01 | 2 | 2 | 0 | 2016-11-03 | 2016-11-03 | 0 | 0 | 0 | [20 empty] | 2016-11-07 |  | 2017-11-06 |  | EXP | [6 empty] | 2017-05-18 | 2017-05-18 | 2017-05-22 | Connected |  | No
National Grid | PLAINVILLE | 178790 | 2762 | 10 | Solar | 05_3451W3 | 2016-10-31 01:00 | 2016-11-01 | 4 | 4 | 0 | 2016-11-07 | 2016-12-19 | 28 | 18 | 10 | [21 empty] | 2016-11-01 01:00 | 2017-11-06 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WILLIAMSTOWN | 177195 | 1267 | 4000 | Diesel | 09_1003W2 | 2016-11-01 01:00 | 2016-11-01 | 28 | 28 | 0 | [10 empty] | 2016-12-13 | 2017-01-25 | 28 | 16 | 12 | [10 empty] | 2017-08-09 |  | 2051-09-01 | Yes | STD |  | 2019-07-13 | 2020-03-27 | 257 | 0 | 257 |  |  |  | Completion Documents |  | No
National Grid | SCITUATE | 177196 | 2066 | 46 | Solar | 07_915W35 | 2016-11-01 01:00 | 2016-11-01 | 7 | 7 | 0 | 2016-11-10 | 2017-01-24 | 48 | 0 | 48 | [20 empty] | 2016-11-14 | 2016-11-01 01:00 | 2017-11-06 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEBSTER | 177197 | 1570 | 7.6 | Solar | 01_412L1 | 2016-11-01 01:00 | 2016-11-02 | 3 | 3 | 0 | 2016-11-07 | 2016-11-15 | 5 | 0 | 5 | [20 empty] | 2016-11-15 | 2016-11-01 01:00 | 2018-05-07 | Yes | EXP |  | 2017-10-20 | 2018-04-11 | 101 | 0 | 101 |  |  | 2018-05-21 | Connected |  | No
National Grid | WILBRAHAM | 177227 | 1095 | 10 | Solar | 09_507L2 | 2016-11-01 01:00 | 2016-11-02 | 3 | 3 | 0 | 2016-11-07 | 2016-11-07 | 0 | 0 | 0 | [20 empty] | 2016-11-15 |  | 2017-11-07 | Yes | EXP |  | 2017-02-08 | 2017-02-25 | 12 | 0 | 12 | 2017-03-30 | 2017-03-30 | 2017-04-05 | Connected |  | No
National Grid | EAST PEPPERELL | 177228 | 1463 | 38 | Solar | 01_226L1 | 2016-11-02 01:00 | 2016-11-03 | 2 | 2 | 0 | 2016-11-07 | 2016-11-07 | 0 | 0 | 0 | [20 empty] | 2016-11-07 | 2016-11-03 01:00 | 2017-11-08 |  | EXP | [6 empty] | 2016-12-29 | 2016-12-29 | 2016-12-29 | Connected |  | No
National Grid | ATTLEBORO | 177231 | 2703 | 72 | Solar | 05_2J3 | 2016-11-03 01:00 | 2016-11-04 | 8 | 8 | 0 | 2016-11-17 | 2016-11-17 | 0 | 0 | 0 | [20 empty] | 2016-11-22 |  | 2017-11-09 |  | EXP |  | 2017-03-02 | 2017-03-20 | 12 | 0 | 12 | 2017-05-16 | 2017-05-16 | 2017-05-22 | Connected |  | No
National Grid | EAST LONGMEADOW | 177232 | 1028 | 109.9 | Solar | 09_508L5 | 2016-11-03 01:00 | 2016-11-04 | 1 | 1 | 0 | 2016-11-07 | 2016-11-07 | 0 | 0 | 0 | [20 empty] | 2016-11-07 |  | 2017-11-09 |  | EXP | [6 empty] | 2017-01-11 | 2017-01-11 | 2017-01-13 | Connected |  | No
National Grid | NORTHBOROUGH | 177233 | 1532 | 156 | Solar | 05_313W3 | 2016-11-04 01:00 | 2016-11-07 | 1 | 1 | 0 | 2016-11-08 | 2017-10-25 | 240 | 0 | 240 | [20 empty] | 2016-11-09 |  | 2017-11-12 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHARLTON | 177235 | 1507 | 54.2 | Solar | 01_415L2 | 2016-11-07 | 2016-11-08 | 2 | 2 | 0 | 2016-11-10 | 2016-11-10 | 0 | 0 | 0 | [20 empty] | 2017-01-10 |  | 2017-11-13 |  | EXP | [6 empty] | 2017-05-24 | 2017-05-24 | 2017-05-24 | Connected |  | No
National Grid | NORTH EASTON | 177236 | 2356 | 5.86 | Solar | 07_92W43 | 2016-11-07 | 2016-11-08 | 28 | 28 | 0 | 2016-12-19 | 2017-01-17 | 18 | 18 | 0 | [22 empty] | 2017-11-13 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SALEM | 177264 | 1970 | 784 | Solar | 12_29W6 | 2016-11-08 | 2016-11-08 | 4 | 4 | 0 | [10 empty] | 2016-11-15 | 2017-01-18 | 42 | 29 | 13 | [12 empty] | 2017-11-13 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | ANDOVER | 177265 | 1810 | 161 | Solar | 14_8T1 | 2016-11-08 | 2016-11-08 | 12 | 12 | 0 | 2016-11-28 | 2016-11-28 | 0 | 0 | 0 | [20 empty] | 2017-01-04 |  | 2017-11-13 |  | EXP | [6 empty] | 2017-03-30 | 2017-03-30 | 2017-03-30 | Connected |  | No
National Grid | ANDOVER | 177266 | 1810 | 143 | Solar | 14_8T1 | 2016-11-08 | 2016-11-08 | 12 | 12 | 0 | 2016-11-28 | 2016-11-28 | 0 | 0 | 0 | [20 empty] | 2017-01-04 |  | 2017-11-13 |  | EXP | [6 empty] | 2017-04-07 | 2017-04-07 | 2017-03-30 | Connected |  | No
National Grid | WHITMAN | 177267 | 2382 | 10 | Solar | 07_91W47 | 2016-11-08 | 2016-11-09 | 1 | 1 | 0 | 2016-11-10 | 2016-11-10 | 0 | 0 | 0 | [20 empty] | 2016-11-14 | 2016-11-08 | 2017-11-14 |  | EXP | [6 empty] | 2017-10-10 | 2017-10-10 | 2017-10-10 | Connected |  | No
National Grid | BRIDGEWATER | 177268 | 2324 | 10 | Solar | 07_912W21 | 2016-11-08 | 2016-11-09 | 1 | 1 | 0 | 2016-11-10 | 2016-11-10 | 0 | 0 | 0 | [20 empty] | 2016-11-22 |  | 2018-02-28 | Yes | EXP |  | 2018-01-18 | 2018-02-01 | 10 | 0 | 10 | 2018-02-16 | 2018-02-16 | 2018-02-16 | Connected |  | No
National Grid | SALEM | 177927 | 1970 | 784 | Solar | 12_29W6 | 2016-11-08 | 2016-11-08 | 4 | 0 | 4 | [10 empty] | 2016-11-15 | 2017-01-18 | 42 | 29 | 13 | [10 empty] | 2017-09-26 |  | 2018-06-15 |  | STD | [8 empty] | 2018-06-14 | Connected |  | No
National Grid | EAST LONGMEADOW | 177270 | 1028 | 86.4 | Solar | 09_508L5 | 2016-11-10 | 2016-11-10 | 2 | 2 | 0 | 2016-11-15 | 2016-11-15 | 0 | 0 | 0 | [20 empty] | 2016-11-15 |  | 2017-11-15 |  | EXP | [6 empty] | 2017-01-11 | 2017-01-11 | 2017-01-17 | Connected |  | No
National Grid | FRANKLIN | 177340 | 2038 | 480 | Solar | 05_341W1 | 2016-11-11 | 2016-11-21 | 4 | 4 | 0 | 2016-11-28 | 2017-09-21 | 205 | 14 | 191 | [22 empty] | 2017-11-26 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SPENCER | 177271 | 1562 | 40 | Solar | 01_21W1 | 2016-11-14 | 2016-11-15 | 1 | 1 | 0 | 2016-11-16 | 2016-11-16 | 0 | 0 | 0 | [20 empty] | 2016-11-28 |  | 2017-11-20 |  | EXP | [6 empty] | 2017-02-17 | 2017-02-17 | 2017-02-16 | Connected |  | No
National Grid | HANSON | 177302 | 2341 | 532.8 | Solar | 07_797W24 | 2016-11-15 | 2016-11-15 | 0 | 0 | 0 | [10 empty] | 2016-11-15 | 2017-03-06 | 74 | 59 | 15 | [10 empty] | 2018-03-06 | 2016-11-15 | 2018-12-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | STOUGHTON | 177304 | 2072 | 650 | Solar | 07_913W17 | 2016-11-15 | 2016-11-16 | 4 | 4 | 0 | [10 empty] | 2016-11-22 | 2016-12-20 | 19 | 3 | 16 | [10 empty] | 2017-04-25 |  | 2018-07-10 |  | STD |  | 2017-10-09 | 2018-07-02 | 266 | 0 | 266 |  |  | 2018-07-09 | Connected |  | No
National Grid | BELLINGHAM | 177305 | 2019 | 50.4 | Solar | 05_108W60 | 2016-11-15 | 2016-11-16 | 10 | 10 | 0 | 2016-11-30 | 2016-11-30 | 0 | 0 | 0 | [20 empty] | 2016-12-05 | 2016-11-16 | 2017-11-21 |  | EXP | [6 empty] | 2017-05-10 | 2017-05-10 | 2017-05-17 | Connected |  | No
National Grid | WEYMOUTH | 177306 | 2188 | 936 | Solar | 07_99W32 | 2016-11-16 | 2017-11-30 | 0 | 0 | 0 | [10 empty] | 2017-12-01 | 2017-12-18 | 11 | 0 | 11 | [10 empty] | 2018-06-19 |  | 2021-08-11 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | CLINTON | 177307 | 1510 | 15.2 | Solar | 01_216W2 | 2016-11-16 | 2016-11-17 | 3 | 3 | 0 | 2016-11-22 | 2016-11-22 | 0 | 0 | 0 | [20 empty] | 2016-11-22 |  | 2017-11-22 |  | EXP | [6 empty] | 2017-06-08 | 2017-06-08 | 2017-06-08 | Connected |  | No
National Grid | SAUGUS | 177308 | 1906 | 7.6 | Solar | 12_19W2 | 2016-11-16 | 2016-11-17 | 3 | 3 | 0 | 2016-11-22 | 2017-06-09 | 136 | 0 | 136 | [20 empty] | 2016-12-01 |  | 2017-11-22 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTON | 177309 | 2766 | 287 | Solar | 05_4J2 | 2016-11-17 | 2016-11-17 | 3 | 3 | 0 | 2016-11-22 | 2016-11-22 | 0 | 0 | 0 | [20 empty] | 2016-12-23 |  | 2017-11-22 |  | EXP | [6 empty] | 2017-06-21 | 2017-06-21 | 2017-06-22 | Connected |  | No
National Grid | STOUGHTON | 177310 | 2072 | 22.8 | Solar | 07_913W43 | 2016-11-17 | 2016-11-18 | 2 | 2 | 0 | 2016-11-22 | 2016-11-22 | 0 | 0 | 0 | [20 empty] | 2016-11-22 |  | 2017-11-23 |  | EXP | [6 empty] | 2017-06-27 | 2017-06-27 | 2017-06-30 | Connected |  | Yes
National Grid | BRADFORD | 177341 | 1835 | 750 | Solar | 14_43L3 | 2016-11-18 | 2016-11-21 | 4 | 4 | 0 | [10 empty] | 2016-11-28 | 2016-12-28 | 21 | 0 | 21 | [12 empty] | 2017-11-26 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 177344 | 1604 | 15.2 | Solar | 01_9J360 | 2016-11-22 | 2016-11-23 | 3 | 3 | 0 | 2016-11-29 | 2016-11-29 | 0 | 0 | 0 | [20 empty] | 2016-11-30 |  | 2018-01-26 |  | EXP | [6 empty] | 2018-01-09 | 2018-01-09 | 2018-01-09 | Connected |  | No
National Grid | BOLTON | 177345 | 1740 | 15.2 | Solar | 01_225W1 | 2016-11-22 | 2016-11-23 | 3 | 3 | 0 | 2016-11-29 | 2016-11-29 | 0 | 0 | 0 | [20 empty] | 2016-11-30 |  | 2017-11-28 |  | EXP | [6 empty] | 2017-08-02 | 2017-08-02 | 2017-08-02 | Connected |  | No
National Grid | SAUGUS | 177346 | 1906 | 7.6 | Solar | 12_19W1 | 2016-11-22 | 2016-11-23 | 3 | 3 | 0 | 2016-11-29 | 2016-11-29 | 0 | 0 | 0 | [20 empty] | 2016-11-30 |  | 2017-11-28 |  | EXP | [6 empty] | 2018-01-09 | 2018-01-09 | 2017-08-14 | Connected |  | No
National Grid | EVERETT | 177347 | 2149 | 7.6 | Solar | 12_37J4 | 2016-11-22 | 2016-11-23 | 3 | 3 | 0 | 2016-11-29 | 2016-11-29 | 0 | 0 | 0 | [20 empty] | 2016-11-30 |  | 2017-11-28 |  | EXP | [6 empty] | 2017-04-17 | 2017-04-17 | 2017-04-24 | Connected |  | No
National Grid | UPTON | 177348 | 1568 | 7.6 | Solar | 05_320W1 | 2016-11-23 | 2016-11-23 | 3 | 3 | 0 | 2016-11-29 | 2016-12-14 | 11 | 0 | 11 | [20 empty] | 2016-12-06 |  | 2017-11-28 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 177349 | 1608 | 88 | Solar | 01_HT50 | 2016-11-23 | 2016-11-28 | 2 | 2 | 0 | [10 empty] | 2016-11-29 | 2016-12-05 | 4 | 4 | 0 | [10 empty] | 2018-06-27 |  | 2017-12-03 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | ROCKLAND | 177379 | 2370 | 1000 | Solar | 07_99W61 | 2016-11-23 | 2016-11-28 | 1 | 1 | 0 | [27 empty] | 2017-12-03 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MARLBOROUGH | 177383 | 1752 | 366.3 | Solar | 05_318W1 | 2016-11-28 | 2016-11-29 | 0 | 0 | 0 | 2016-11-29 | 2016-11-29 | 0 | 0 | 0 | [20 empty] | 2016-12-22 |  | 2017-12-04 |  | EXP | [6 empty] | 2017-06-22 | 2017-06-22 | 2017-06-27 | Connected |  | No
National Grid | BELLINGHAM | 177384 | 2019 | 12 | Solar | 05_108W51 | 2016-11-28 | 2016-11-29 | 2 | 2 | 0 | 2016-12-01 | 2016-12-01 | 0 | 0 | 0 | [20 empty] | 2016-12-02 |  | 2017-12-04 |  | EXP | [6 empty] | 2017-06-14 | 2017-06-14 | 2017-06-19 | Connected |  | No
National Grid | BEVERLY | 177385 | 1915 | 7.6 | Solar | 12_12L2 | 2016-11-28 | 2016-11-30 | 1 | 1 | 0 | 2016-12-01 | 2017-06-09 | 130 | 0 | 130 | [20 empty] | 2016-12-06 |  | 2017-12-05 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SUTTON | 177386 | 1590 | 17.25 | Solar | 01_304W6 | 2016-11-29 | 2016-11-30 | 14 | 14 | 0 | 2016-12-20 | 2016-12-20 | 0 | 0 | 0 | [20 empty] | 2016-12-22 | 2016-11-29 | 2017-12-05 |  | EXP | [6 empty] | 2017-05-05 | 2017-05-05 | 2017-05-08 | Connected |  | No
National Grid | LEOMINSTER | 177417 | 1453 | 7.6 | Solar | 01_219W2 | 2016-11-29 | 2016-12-01 | 0 | 0 | 0 | 2016-12-01 | 2016-12-01 | 0 | 0 | 0 | [20 empty] | 2016-12-06 |  | 2017-12-06 | Yes | EXP |  | 2017-07-25 | 2017-09-26 | 44 | 0 | 44 | 2017-10-23 | 2017-10-23 | 2017-10-20 | Connected |  | No
National Grid | FLORENCE | 177387 | 1062 | 92.16 | Solar | 09_909W2 | 2016-11-30 | 2016-12-01 | 0 | 0 | 0 | 2016-12-01 | 2018-02-14 | 295 | 0 | 295 | [21 empty] | 2016-12-01 | 2017-12-06 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | AMESBURY | 177418 | 1913 | 1050 | Solar | 14_275L4 | 2016-12-01 | 2016-12-02 | 2 | 2 | 0 | [10 empty] | 2016-12-06 | 2017-03-03 | 59 | 44 | 15 | [10 empty] | 2018-04-26 |  | 2020-01-06 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | RUTLAND | 177420 | 1543 | 5 | Solar | 01_55W1 | 2016-12-05 | 2016-12-06 | 2 | 2 | 0 | 2016-12-08 | 2016-12-08 | 0 | 0 | 0 | [20 empty] | 2016-12-08 |  | 2017-12-11 |  | EXP | [6 empty] | 2017-03-07 | 2017-03-07 | 2017-03-07 | Connected |  | No
National Grid | NORTH BROOKFIELD | 177421 | 1535 | 17.6 | Solar | 09_604W2 | 2016-12-05 | 2016-12-06 | 2 | 2 | 0 | 2016-12-08 | 2017-11-17 | 231 | 0 | 231 | [20 empty] | 2016-12-12 |  | 2017-12-11 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BELLINGHAM | 177422 | 2019 | 7.6 | Solar | 05_344W4 | 2016-12-05 | 2016-12-06 | 2 | 2 | 0 | 2016-12-08 | 2016-12-08 | 0 | 0 | 0 | [20 empty] | 2016-12-09 |  | 2017-12-11 |  | EXP | [6 empty] | 2017-07-05 | 2017-07-05 | 2017-07-05 | Connected |  | No
National Grid | SWANSEA | 177423 | 2777 | 1260 | Solar | 05_11W81 | 2016-12-06 | 2016-12-07 | 6 | 6 | 0 | [10 empty] | 2016-12-15 | 2017-01-12 | 18 | 4 | 14 | [10 empty] | 2017-07-25 | 2016-12-06 | 2020-06-11 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | STOUGHTON | 177424 | 2072 | 7.6 | Solar | 07_913W47 | 2016-12-06 | 2016-12-07 | 2 | 2 | 0 | 2016-12-09 | 2016-12-12 | 1 | 0 | 1 | [20 empty] | 2016-12-12 | 2016-12-06 | 2017-12-12 |  | EXP | [6 empty] | 2017-05-02 | 2017-05-02 | 2017-05-02 | Connected |  | No
National Grid | METHUEN | 177425 | 1844 | 7.6 | Solar | 14_63L1 | 2016-12-06 | 2016-12-07 | 3 | 2 | 1 | 2016-12-12 | 2016-12-12 | 0 | 0 | 0 | [20 empty] | 2016-12-12 |  | 2017-12-12 | Yes | EXP |  | 2017-10-16 | 2017-11-16 | 17 | 0 | 17 | 2017-11-21 | 2017-11-21 | 2017-11-21 | Connected |  | No
National Grid | WEYMOUTH | 177454 | 2190 | 7.6 | Solar | 07_8W1 | 2016-12-06 | 2016-12-07 | 2 | 2 | 0 | 2016-12-09 | 2018-01-28 | 277 | 0 | 277 | [20 empty] | 2016-12-12 | 2016-12-06 | 2018-02-14 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | CHELMSFORD | 177455 | 1824 | 10 | Solar | 14_24L1 | 2016-12-06 | 2016-12-07 | 2 | 2 | 0 | 2016-12-09 | 2016-12-09 | 0 | 0 | 0 | [20 empty] | 2016-12-15 |  | 2017-12-12 | Yes | EXP |  | 2017-10-03 | 2017-10-17 | 9 | 0 | 9 | 2017-10-17 | 2017-10-17 | 2017-10-17 | Connected |  | No
National Grid | NEWBURYPORT | 177456 | 1950 | 594 | Solar | 14_60L3 | 2016-12-07 | 2016-12-07 | 40 | 25 | 15 | 2017-02-06 | 2017-02-06 | 0 | 0 | 0 | 2017-05-22 | 2017-03-27 | 0 | 0 | 0 | [5 empty] | 2017-05-22 | 2017-03-27 | 0 | 0 | 0 | [5 empty] | 2017-06-23 | 2016-12-07 | 2017-12-12 |  | EXP | [6 empty] | 2017-10-11 | 2017-10-11 | 2017-10-17 | Connected |  | Yes
National Grid | MARLBOROUGH | 177457 | 1752 | 3.8 | Solar | 05_311W2 | 2016-12-07 | 2016-12-09 | 1 | 1 | 0 | 2016-12-12 | 2016-12-15 | 323 | 0 | 323 | [20 empty] | 2016-12-15 |  | 2018-12-30 | Yes | EXP |  | 2017-12-27 | 2018-10-26 | 303 | 0 | 303 |  |  | 2018-10-26 | Connected |  | No
National Grid | REHOBOTH | 177458 | 2769 | 15.2 | Solar | 05_8L4 | 2016-12-07 | 2016-12-09 | 1 | 1 | 0 | 2016-12-12 | 2016-12-12 | 0 | 0 | 0 | [20 empty] | 2016-12-12 |  | 2017-12-14 |  | EXP | [6 empty] | 2017-09-21 | 2017-09-21 | 2017-09-26 | Connected |  | No
National Grid | SUTTON | 177459 | 1590 | 3000 | Solar | 05_320W5 | 2016-12-09 | 2016-12-12 | 43 | 43 | 0 | [10 empty] | 2017-02-14 | 2017-05-10 | 59 | 45 | 14 | [12 empty] | 2017-12-17 |  | STD | [9 empty] | Terminated |  | No
National Grid | NORWELL | 177460 | 2061 | 20 | Solar | 07_96W43 | 2016-12-09 | 2016-12-12 | 0 | 0 | 0 | 2016-12-12 | 2016-12-12 | 0 | 0 | 0 | [20 empty] | 2016-12-14 | 2016-12-12 | 2017-12-17 |  | EXP | [6 empty] | 2017-01-30 | 2017-01-30 | 2017-02-09 | Connected |  | No
National Grid | LAWRENCE | 176943 | 1841 | 5.75 | Solar | 14_74L3 | 2016-12-12 | 2016-12-20 | 1 | 1 | 0 | 2016-12-21 | 2016-12-21 | 0 | 0 | 0 | [20 empty] | 2016-12-22 | 2016-12-12 | 2017-12-25 | Yes | EXP |  | 2017-06-20 | 2017-07-05 | 10 | 0 | 10 | 2017-09-21 | 2017-09-21 | 2017-09-21 | Connected |  | No
National Grid | NORTON | 177461 | 2766 | 998 | Solar | 05_4L1 | 2016-12-12 | 2016-12-14 | 14 | 0 | 14 | [25 empty] | 2017-01-05 |  | 2019-03-29 | Yes | STD |  | 2017-09-01 | 2018-01-12 | 84 | 0 | 84 |  |  | 2019-03-28 | Connected |  | No
National Grid | AMESBURY | 177462 | 1913 | 43.2 | Solar | 14_5J11 | 2016-12-12 | 2016-12-12 | 7 | 7 | 0 | 2016-12-20 | 2016-12-20 | 0 | 0 | 0 | [20 empty] | 2016-12-22 |  | 2017-12-17 |  | EXP | [6 empty] | 2017-08-23 | 2017-08-23 | 2017-08-23 | Connected |  | No
National Grid | CHELMSFORD | 177491 | 1824 | 330 | Solar | 14_24L1 | 2016-12-12 | 2016-12-13 | 3 | 3 | 0 | 2017-01-27 | 2017-03-06 | 0 | 0 | 0 | 2017-03-21 | 2017-04-19 | 36 | 36 | 0 | [5 empty] | 2017-03-21 | 2017-04-19 | 36 | 36 | 0 | [5 empty] | 2017-07-06 |  | 2019-03-20 |  | EXP | [8 empty] | 2019-01-31 | Connected |  | No
National Grid | CLINTON | 177492 | 1510 | 7.6 | Solar | 01_216W5 | 2016-12-13 | 2016-12-13 | 6 | 6 | 0 | 2016-12-21 | 2016-12-21 | 0 | 0 | 0 | [20 empty] | 2016-12-21 |  | 2017-12-18 |  | EXP | [6 empty] | 2017-09-22 | 2017-09-22 | 2017-09-22 | Connected |  | No
National Grid | QUINCY | 177493 | 2169 | 42 | Solar | 07_3W2 | 2016-12-13 | 2016-12-13 | 0 | 0 | 0 | 2016-12-13 | 2016-12-13 | 0 | 0 | 0 | [20 empty] | 2016-12-14 |  | 2017-12-18 |  | EXP | [6 empty] | 2017-05-11 | 2017-05-11 | 2017-05-17 | Connected |  | No
National Grid | ATTLEBORO | 177494 | 2703 | 3.8 | Solar | 05_9L1 | 2016-12-13 | 2016-12-14 | 4 | 4 | 0 | 2016-12-20 | 2018-01-28 | 270 | 0 | 270 | [20 empty] | 2016-12-21 | 2016-12-13 | 2017-12-19 |  | EXP | [6 empty] | 2018-01-25 | 2018-01-25 |  | Withdrawn |  | No
National Grid | HAVERHILL | 177495 | 1830 | 7.6 | Solar | 14_47L1 | 2016-12-13 | 2016-12-14 | 4 | 4 | 0 | 2016-12-20 | 2016-12-20 | 0 | 0 | 0 | [20 empty] | 2016-12-21 |  | 2017-12-19 | Yes | EXP |  | 2017-07-05 | 2017-07-24 | 13 | 0 | 13 | 2017-11-13 | 2017-11-13 | 2017-09-25 | Connected |  | No
National Grid | AUBURN | 177496 | 1501 | 15.2 | Solar | 01_26W2 | 2016-12-13 | 2016-12-14 | 4 | 4 | 0 | 2016-12-20 | 2016-12-20 | 0 | 0 | 0 | [20 empty] | 2016-12-20 | 2016-12-14 | 2017-12-19 |  | EXP | [6 empty] | 2017-02-07 | 2017-02-07 | 2017-02-07 | Connected |  | No
National Grid | ROCKPORT | 177497 | 1966 | 15.2 | Solar | 12_40J2 | 2016-12-14 | 2016-12-14 | 4 | 3 | 1 | 2016-12-20 | 2016-12-21 | 1 | 0 | 1 | [20 empty] | 2016-12-21 |  | 2018-10-12 |  | EXP |  | 2016-05-28 | 2017-02-03 | 169 | 3 | 166 |  |  | 2018-10-03 | Connected |  | No
National Grid | OXFORD | 176939 | 1540 | 10 | Solar | 01_406L3 | 2016-12-16 | 2016-12-19 | 3 | 2 | 1 | 2016-12-22 | 2016-12-22 | 0 | 0 | 0 | [20 empty] | 2016-12-23 | 2016-12-19 | 2017-12-24 |  | EXP | [6 empty] | 2017-07-12 | 2017-07-12 | 2017-07-12 | Connected |  | No
National Grid | FALL RIVER | 176941 | 2721 | 7.6 | Solar | 05_115W52 | 2016-12-19 | 2016-12-19 | 3 | 2 | 1 | 2016-12-22 | 2016-12-22 | 0 | 0 | 0 | [20 empty] | 2017-01-03 |  | 2018-02-28 | Yes | EXP |  | 2017-09-15 | 2017-12-11 | 53 | 0 | 53 | 2018-02-20 | 2018-02-20 | 2018-03-06 | Connected |  | No
National Grid | EVERETT | 176945 | 2149 | 43.2 | Solar | 12_10J5 | 2016-12-20 | 2016-12-21 | 9 | 8 | 1 | 2017-01-05 | 2017-06-09 | 107 | 0 | 107 | [20 empty] | 2017-01-05 |  | 2017-12-26 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MILLBURY | 176946 | 1527 | 3.8 | Solar | 01_304W3 | 2016-12-21 | 2016-12-21 | 4 | 3 | 1 | 2016-12-28 | 2016-12-28 | 0 | 0 | 0 | [20 empty] | 2017-01-04 |  | 2017-12-26 |  | EXP | [6 empty] | 2017-08-17 | 2017-08-17 | 2017-08-16 | Connected |  | No
National Grid | LEOMINSTER | 176977 | 1453 | 35 | Solar | 01_219W3 | 2016-12-27 | 2016-12-27 | 4 | 3 | 1 | 2017-01-03 | 2017-01-03 | 0 | 0 | 0 | [20 empty] | 2017-01-03 |  | 2018-01-02 |  | EXP | [6 empty] | 2017-03-30 | 2017-03-30 | 2017-03-30 | Connected |  | No
National Grid | BROCKTON | 176978 | 2301 | 112 | Solar | 07_98W19 | 2016-12-27 | 2016-12-28 | 2 | 1 | 1 | 2016-12-30 | 2016-12-30 | 0 | 0 | 0 | [20 empty] | 2017-01-03 | 2016-12-28 | 2018-01-02 |  | EXP | [6 empty] | 2017-05-05 | 2017-05-05 | 2017-05-05 | Connected |  | No
National Grid | RANDOLPH | 176979 | 2368 | 5.2 | Solar | 07_97W5 | 2016-12-28 | 2016-12-29 | 4 | 4 | 0 | 2017-01-05 | 2017-01-05 | 0 | 0 | 0 | [20 empty] | 2017-01-06 | 2016-12-29 | 2018-01-03 | Yes | EXP |  | 2017-07-24 | 2017-08-10 | 13 | 0 | 13 | 2017-09-05 | 2017-09-05 | 2017-09-07 | Connected |  | No
National Grid | WORCESTER | 176980 | 1606 | 6.6 | Solar | 01_24W3 | 2016-12-29 | 2017-01-02 | 1 | 1 | 0 | 2017-01-04 | 2017-01-04 | 0 | 0 | 0 | [20 empty] | 2017-01-06 | 2016-12-29 | 2018-01-07 | Yes | EXP |  | 2017-06-07 | 2017-07-12 | 24 | 0 | 24 | 2017-09-28 | 2017-09-28 | 2017-09-28 | Connected |  | No
National Grid | SOMERSET | 176981 | 2726 | 5.2 | Solar | 05_19W72 | 2016-12-29 | 2017-01-02 | 1 | 1 | 0 | 2017-01-04 | 2017-01-04 | 0 | 0 | 0 | [20 empty] | 2017-01-06 |  | 2018-01-07 | Yes | EXP |  | 2017-05-01 | 2017-06-08 | 27 | 0 | 27 | 2017-06-28 | 2017-06-28 | 2017-06-30 | Connected |  | No
National Grid | TYNGSBORO | 177013 | 1879 | 7.6 | Solar | 14_211L2 | 2017-01-05 | 2017-01-05 | 8 | 8 | 0 | 2017-01-18 | 2017-01-18 | 0 | 0 | 0 | [20 empty] | 2017-01-18 |  | 2018-01-10 |  | EXP | [6 empty] | 2017-08-03 | 2017-08-03 | 2017-08-02 | Connected |  | No
National Grid | BEVERLY | 177018 | 1915 | 60 | Solar | 12_12L6 | 2017-01-09 | 2017-01-09 | 4 | 4 | 0 | 2017-01-13 | 2017-02-08 | 37 | 37 | 0 | [20 empty] | 2017-03-09 |  | 2018-08-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | REHOBOTH | 177020 | 2769 | 15.2 | Solar | 05_7L4 | 2017-01-09 | 2017-01-10 | 4 | 4 | 0 | 2017-01-17 | 2017-01-17 | 0 | 0 | 0 | [20 empty] | 2017-01-18 |  | 2018-01-15 |  | EXP | [6 empty] | 2017-08-15 | 2017-08-15 | 2017-08-21 | Connected |  | No
National Grid | REHOBOTH | 177021 | 2769 | 3.8 | Solar | 05_7L4 | 2017-01-09 | 2017-01-10 | 5 | 5 | 0 | 2017-01-18 | 2017-01-18 | 0 | 0 | 0 | [20 empty] | 2017-01-18 | 2017-01-11 | 2018-01-15 |  | EXP | [6 empty] | 2017-09-06 | 2017-09-06 | 2017-09-06 | Connected |  | No
National Grid | BELLINGHAM | 177051 | 2019 | 7.6 | Solar | 05_108W60 | 2017-01-11 | 2017-01-11 | 4 | 3 | 1 | 2017-01-18 | 2017-01-18 | 0 | 0 | 0 | [20 empty] | 2017-01-19 | 2017-01-11 | 2018-01-18 | Yes | EXP |  | 2017-03-08 | 2017-03-01 | 0 | 0 | 0 | 2017-06-19 | 2017-06-19 | 2017-06-22 | Connected |  | No
National Grid | SEEKONK | 177052 | 2771 | 15.2 | Solar | 05_7L1 | 2017-01-11 | 2017-01-11 | 3 | 2 | 1 | 2017-01-17 | 2017-01-17 | 0 | 0 | 0 | [20 empty] | 2017-01-20 |  | 2018-01-16 | Yes | EXP |  | 2017-06-14 | 2017-06-22 | 6 | 0 | 6 | 2017-09-27 | 2017-09-27 | 2017-10-03 | Connected |  | No
National Grid | METHUEN | 177053 | 1844 | 7.6 | Solar | 14_74L3 | 2017-01-11 | 2017-01-11 | 4 | 3 | 1 | 2017-01-18 | 2017-01-18 | 0 | 0 | 0 | [20 empty] | 2017-01-23 |  | 2018-01-16 |  | EXP | [6 empty] | 2017-05-30 | 2017-05-30 | 2017-05-30 | Connected |  | No
National Grid | HOPEDALE | 177054 | 1747 | 8 | Solar | 05_335W9 | 2017-01-12 | 2017-01-12 | 18 | 17 | 1 | 2017-02-08 | 2017-02-08 | 0 | 0 | 0 | [20 empty] | 2017-02-09 |  | 2018-01-17 |  | EXP | [6 empty] | 2017-06-01 | 2017-06-01 | 2017-06-09 | Connected |  | No
National Grid | FRANKLIN | 177055 | 2038 | 1000 | Solar | 05_344W5 | 2017-01-12 | 2017-01-13 | 1 | 0 | 1 | [10 empty] | 2017-01-17 | 2017-01-31 | 10 | 1 | 9 | [10 empty] | 2017-05-31 | 2017-01-16 | 2019-04-16 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HUBBARDSTON | 177057 | 1452 | 4900.5 | Solar | 09_604W4 | 2017-01-16 | 2017-01-17 | 2 | 2 | 0 | [10 empty] | 2017-01-19 | 2017-02-03 | 11 | 4 | 7 | [10 empty] | 2017-05-22 |  | 2021-09-24 | Yes | STD |  | 2019-02-28 | 2020-10-27 | 608 | 5 | 603 | 2021-06-04 | 2021-06-04 | 2021-09-24 | Connected |  | No
National Grid | WINCHENDON | 177058 | 1475 | 4500 | Solar | 01_607W1 | 2017-01-17 | 2017-01-18 | 1 | 1 | 0 | [10 empty] | 2017-01-19 | 2017-02-09 | 15 | 1 | 14 | [12 empty] | 2018-01-23 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WINCHENDON | 177059 | 1475 | 900 | Solar | 01_607W1 | 2017-01-17 | 2017-01-18 | 1 | 0 | 1 | [10 empty] | 2017-01-19 | 2017-02-09 | 15 | 1 | 14 | [11 empty] | 2017-01-17 | 2018-01-23 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WINCHENDON | 177089 | 1475 | 4950 | Solar | 01_607W5 | 2017-01-17 | 2017-01-19 | 0 | 0 | 0 | [10 empty] | 2017-01-19 | 2017-02-10 | 16 | 1 | 15 | [10 empty] | 2017-05-22 |  | 2019-04-22 | Yes | STD |  | 2018-09-26 | 2019-06-11 | 257 | 0 | 257 | 2019-08-01 | 2019-08-01 | 2019-10-29 | Connected |  | No
National Grid | WINCHENDON | 177090 | 1475 | 4500 | Solar | 01_607W1 | 2017-01-17 | 2017-01-19 | 0 | 0 | 0 | [10 empty] | 2017-01-19 | 2017-02-10 | 16 | 1 | 15 | [12 empty] | 2018-01-24 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SALEM | 177088 | 1970 | 432.6 | Solar | 12_2W1 | 2017-01-18 | 2017-01-19 | 2 | 0 | 2 | 2017-01-23 | 2017-01-23 | 0 | 0 | 0 | [20 empty] | 2017-02-21 |  | 2018-01-24 |  | EXP | [6 empty] | 2017-08-08 | 2017-08-08 | 2017-08-08 | Connected |  | No
National Grid | CHARLTON | 177091 | 1507 | 7.6 | Solar | 01_406L1 | 2017-01-18 | 2017-01-19 | 4 | 3 | 1 | 2017-01-25 | 2017-08-14 | 139 | 0 | 139 | [20 empty] | 2017-01-27 |  | 2018-01-24 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BARRE | 177092 | 1005 | 40.25 | Solar | 09_604W3 | 2017-01-19 | 2017-01-19 | 0 | 0 | 0 | 2017-01-19 | 2017-01-19 | 0 | 0 | 0 | [20 empty] | 2017-01-23 | 2017-01-20 | 2018-01-24 |  | EXP | [6 empty] | 2017-05-15 | 2017-05-15 | 2017-05-15 | Connected |  | No
National Grid | LEOMINSTER | 177095 | 1453 | 7.6 | Solar | 01_225W4 | 2017-01-20 | 2017-01-23 | 2 | 2 | 0 | 2017-01-25 | 2017-01-25 | 0 | 0 | 0 | [20 empty] | 2017-01-27 |  | 2018-01-28 |  | EXP |  | 2017-06-15 | 2017-07-28 | 30 | 0 | 30 | 2017-08-28 | 2017-08-28 | 2017-08-28 | Connected |  | No
National Grid | RUTLAND | 177129 | 1543 | 0 |  | 01_55W1 | 2017-01-23 | 2017-01-23 | 0 | 0 | 0 | [27 empty] | 2018-01-28 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | RUTLAND | 177130 | 1543 | 7.25 | Solar | 01_55W1 | 2017-01-23 | 2017-01-23 | 10 | 9 | 1 | 2017-02-06 | 2017-02-06 | 0 | 0 | 0 | [20 empty] | 2017-02-06 |  | 2018-01-28 |  | EXP | [6 empty] | 2017-05-31 | 2017-05-31 | 2017-05-31 | Connected |  | No
National Grid | TYNGSBORO | 177132 | 1879 | 566.1 | Solar | 14_211L1 | 2017-01-23 | 2017-01-24 | 3 | 3 | 0 | [26 empty] | 2017-01-23 | 2018-01-29 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WEYMOUTH | 177133 | 2189 | 99.9 | Solar | 07_12W2 | 2017-01-23 | 2017-01-24 | 4 | 4 | 0 | 2017-01-27 | 2017-11-30 | 206 | 82 | 124 | [20 empty] | 2017-06-01 |  | 2018-01-29 | Yes | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTPORT | 177134 | 2790 | 15.2 | Solar | 05_115W45 | 2017-01-24 | 2017-01-24 | 3 | 2 | 1 | 2017-01-27 | 2017-01-27 | 0 | 0 | 0 | [20 empty] | 2017-01-30 |  | 2018-01-29 |  | EXP | [6 empty] | 2017-10-26 | 2017-10-26 | 2017-11-17 | Connected |  | No
National Grid | SALEM | 177135 | 1970 | 3.8 | Solar | 12_2W1 | 2017-01-24 | 2017-01-24 | 3 | 2 | 1 | 2017-01-27 | 2017-01-27 | 0 | 0 | 0 | [20 empty] | 2017-01-30 | 2017-01-24 | 2018-01-29 |  | EXP | [6 empty] | 2018-01-11 | 2018-01-11 | 2018-01-11 | Connected |  | No
National Grid | FRANKLIN | 177163 | 2038 | 3.8 | Solar | 05_341W1 | 2017-01-24 | 2017-01-24 | 3 | 2 | 1 | 2017-01-27 | 2017-01-27 | 0 | 0 | 0 | [20 empty] | 2017-01-30 |  | 2018-01-29 |  | EXP | [6 empty] | 2017-09-21 | 2017-09-21 | 2017-09-21 | Connected |  | No
National Grid | METHUEN | 177164 | 1844 | 7.6 | Solar | 14_74L1 | 2017-01-24 | 2017-01-24 | 3 | 2 | 1 | 2017-01-27 | 2017-06-05 | 88 | 0 | 88 | [20 empty] | 2017-01-30 |  | 2018-01-29 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SOUTH EASTON | 177165 | 2375 | 99.9 | Solar | 07_98W48 | 2017-01-24 | 2017-02-16 | 14 | 12 | 2 | 2017-02-14 | 2017-02-15 | 1 | 0 | 1 | [20 empty] | 2017-02-15 | 2017-01-25 | 2018-01-30 |  | EXP | [8 empty] | 2018-09-12 | Connected |  | Yes
National Grid | GRANBY | 177166 | 1033 | 3000 | Solar | 09_527L1 | 2017-01-25 | 2017-01-25 | 2 | 0 | 2 | [10 empty] | 2017-01-27 | 2017-03-01 | 22 | 14 | 8 | [10 empty] | 2018-06-26 | 2017-01-25 | 2021-08-16 | Yes | STD |  | 2020-06-02 | 2021-01-11 | 224 | 5 | 219 | 2021-07-22 | 2021-07-22 | 2021-07-29 | Connected |  | No
National Grid | SWANSEA | 177167 | 2777 | 2.75 | Solar | 05_11W81 | 2017-01-25 | 2017-01-26 | 80 | 78 | 2 | 2017-05-22 | 2017-05-22 | 0 | 0 | 0 | [20 empty] | 2017-05-23 |  | 2018-01-31 |  | EXP |  | 2017-07-18 | 2017-07-24 | 4 | 0 | 4 | 2017-11-03 | 2017-11-03 | 2017-11-03 | Connected |  | No
National Grid | WEBSTER | 177168 | 1570 | 4980 | Solar | 01_412L1 | 2017-01-26 | 2017-01-26 | 4 | 0 | 4 | [10 empty] | 2017-02-01 | 2017-04-05 | 45 | 33 | 12 | [10 empty] | 2018-05-02 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WEBSTER | 177171 | 1570 | 7.6 | Solar | 01_412L1 | 2017-01-27 | 2017-01-30 | 4 | 4 | 0 | 2017-02-03 | 2017-11-29 | 200 | 0 | 200 | [20 empty] | 2017-02-06 |  | 2018-02-04 |  | EXP |  | 2017-06-19 | 2017-08-09 | 36 | 0 | 36 |  |  |  | Withdrawn |  | Yes
National Grid | EAST BRIDGEWATER | 177198 | 2333 | 7.6 | Solar | 07_797W23 | 2017-02-01 | 2017-02-01 | 2 | 2 | 0 | 2017-02-03 | 2017-02-03 | 0 | 0 | 0 | [20 empty] | 2017-02-07 |  | 2018-02-06 |  | EXP | [6 empty] | 2017-10-23 | 2017-10-23 | 2017-10-23 | Connected |  | No
National Grid | EAST BRIDGEWATER | 177199 | 2333 | 3.8 | Solar | 07_797W23 | 2017-02-01 | 2017-02-01 | 2 | 2 | 0 | 2017-02-03 | 2017-02-03 | 0 | 0 | 0 | [20 empty] | 2017-02-07 |  | 2018-02-06 |  | EXP | [6 empty] | 2017-08-21 | 2017-08-21 | 2017-08-21 | Connected |  | No
National Grid | GRANBY | 177200 | 1033 | 2.4 | Solar | 09_527L1 | 2017-02-01 | 2017-02-02 | 1 | 0 | 1 | 2017-02-03 | 2017-02-03 | 0 | 0 | 0 | [20 empty] | 2017-02-06 |  | 2018-02-07 |  | EXP | [6 empty] | 2017-08-29 | 2017-08-29 | 2017-08-28 | Connected |  | No
National Grid | WILBRAHAM | 177201 | 1095 | 7.6 | Solar | 09_507L1 | 2017-02-01 | 2017-02-02 | 1 | 0 | 1 | 2017-02-03 | 2017-11-29 | 200 | 0 | 200 | [20 empty] | 2017-02-06 |  | 2018-02-07 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LAWRENCE | 177202 | 1843 | 3.8 | Solar | 14_61L3 | 2017-02-01 | 2017-02-03 | 0 | 0 | 0 | 2017-02-17 | 2017-02-21 | 0 | 0 | 0 | [20 empty] | 2017-02-21 |  | 2018-07-31 |  | EXP | [8 empty] | 2018-04-29 | Connected |  | No
National Grid | WORCESTER | 177203 | 1606 | 379.7 | Solar | 01_24W2 | 2017-02-01 | 2017-02-02 | 3 | 2 | 1 | [27 empty] | 2018-02-07 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 177204 | 1607 | 299.8 | Solar | 01_8W2 | 2017-02-01 | 2017-02-02 | 3 | 2 | 1 | [27 empty] | 2018-02-07 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 177205 | 2301 | 153.2 | Solar | 07_911W25 | 2017-02-01 | 2017-02-02 | 11 | 2 | 9 | [27 empty] | 2018-02-07 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LYNN | 177206 | 1905 | 133.2 | Solar | 12_21J29 | 2017-02-01 | 2017-02-02 | 3 | 2 | 1 | [27 empty] | 2018-02-07 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SAUGUS | 177207 | 1906 | 259.8 | Solar | 12_25W3 | 2017-02-01 | 2017-02-02 | 3 | 1 | 2 | [27 empty] | 2018-02-07 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BILLERICA | 177237 | 1862 | 472.9 | Solar | 14_70L4 | 2017-02-01 | 2017-02-02 | 3 | 1 | 2 | [27 empty] | 2018-02-07 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | REHOBOTH | 153683 | 2769 | 15.2 | Solar | 05_7L5 | 2017-02-02 | 2017-02-02 | 3 | 0 | 3 | [25 empty] | 2017-02-07 |  | 2018-02-02 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | AUBURN | 177238 | 1501 | 186.6 | Solar | 01_26W2 | 2017-02-03 | 2017-02-03 | 2 | 1 | 1 | [26 empty] | 2017-02-03 | 2018-02-08 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | ATTLEBORO | 177239 | 2703 | 1080 | Solar | 05_9L2 | 2017-02-03 | 2017-02-03 | 22 | 21 | 1 | [10 empty] | 2017-03-07 | 2017-05-15 | 50 | 37 | 13 | [10 empty] | 2017-09-12 | 2017-02-03 | 2023-04-02 | Yes | STD |  | 2021-10-11 | 2022-03-01 | 142 | 4 | 138 |  |  | 2023-03-31 | Connected |  | No
National Grid | WILBRAHAM | 177240 | 1095 | 4000 | Solar | 09_507L1 | 2017-02-03 | 2017-02-06 | 8 | 4 | 4 | [10 empty] | 2017-02-16 | 2017-02-22 | 3 | 0 | 3 | [10 empty] | 2017-07-20 |  | 2020-12-31 | Yes | STD |  | 2019-08-24 | 2020-10-27 | 431 | 11 | 420 | 2020-11-13 | 2020-11-13 | 2020-12-23 | Connected |  | No
National Grid | FOXBOROUGH | 178791 | 2035 | 86.6 | Solar | 05_3422W3 | 2017-02-03 | 2017-02-03 | 2 | 2 | 0 | 2017-02-07 | 2017-11-30 | 199 | 66 | 133 | [20 empty] | 2017-05-30 |  | 2018-02-08 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SALEM | 177244 | 1970 | 191 | Solar | 12_49W6 | 2017-02-06 | 2017-02-06 | 4 | 0 | 4 | 2017-02-10 | 2017-02-10 | 0 | 0 | 0 | [20 empty] | 2017-02-15 |  | 2018-02-11 |  | EXP |  | 2017-07-27 | 2017-07-31 | 2 | 0 | 2 | 2017-10-05 | 2017-10-05 | 2017-10-18 | Connected |  | No
National Grid | SALISBURY | 177273 | 1952 | 20 | Solar | 14_7L2 | 2017-02-06 | 2017-02-06 | 6 | 2 | 4 | 2017-02-14 | 2017-02-14 | 0 | 0 | 0 | [20 empty] | 2017-02-15 | 2017-02-06 | 2018-02-11 |  | EXP | [6 empty] | 2017-05-15 | 2017-05-15 | 2017-05-15 | Connected |  | No
National Grid | SHIRLEY | 177274 | 1464 | 500 | Solar | 01_227W3 | 2017-02-06 | 2017-02-07 | 45 | 44 | 1 | [10 empty] | 2017-04-12 | 2017-04-24 | 7 | 0 | 7 | [10 empty] | 2019-01-09 |  | 2023-02-18 | Yes | STD |  | 2019-10-30 | 2019-10-29 | 0 | 0 | 0 |  |  | 2022-10-10 | Connected |  | No
National Grid | WESTBOROUGH | 177275 | 1581 | 4500 | Solar | 05_312W5 | 2017-02-06 | 2017-02-07 | 14 | 13 | 1 | [10 empty] | 2017-02-28 | 2017-03-02 | 2 | 0 | 2 | [12 empty] | 2018-12-15 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | EVERETT | 177276 | 2149 | 5.2 | Solar | 12_37W6 | 2017-02-06 | 2017-02-07 | 4 | 4 | 0 | 2017-02-13 | 2017-11-29 | 194 | 0 | 194 | [20 empty] | 2017-02-14 | 2017-02-08 | 2018-02-12 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHARLTON | 177278 | 1507 | 1980 | Solar | 01_406L1 | 2017-02-08 | 2017-02-09 | 30 | 28 | 2 | [10 empty] | 2017-03-24 | 2017-05-04 | 28 | 14 | 14 | [5 empty] | 2018-01-13 | 2020-02-14 | 523 | 0 | 523 | 2017-10-20 |  | 2020-01-31 | Yes | STD |  | 2019-05-03 | 2020-01-22 | 263 | 0 | 263 |  |  | 2020-01-22 | Connected |  | No
National Grid | NANTUCKET | 177279 | 2554 | 3600 | Solar | 04_101L7 | 2017-02-08 | 2017-02-09 | 136 | 134 | 2 | [27 empty] | 2018-02-14 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SUTTON | 177280 | 1590 | 2800 | Solar | 05_320W5 | 2017-02-08 | 2017-02-09 | 4 | 2 | 2 | [26 empty] | 2017-02-08 | 2018-02-14 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WEBSTER | 177281 | 1570 | 1000 | Solar | 01_412L2 | 2017-02-08 | 2017-02-09 | 6 | 5 | 1 | [10 empty] | 2017-02-17 | 2017-02-22 | 2 | 0 | 2 | [10 empty] | 2018-09-21 | 2017-02-08 | 2021-11-12 | Yes | STD |  | 2021-02-06 | 2021-08-13 | 189 | 0 | 189 | 2021-08-16 | 2021-08-16 | 2021-11-02 | Connected |  | No
National Grid | CHARLTON | 274206 | 1507 | 0 | Solar | 01_406L1 | 2017-02-08 | 2020-08-21 | [23 empty] | 2020-01-23 | 2020-02-14 | 17 | 1 | 16 | 2017-10-20 | 2017-02-09 | 2021-08-25 |  | STD | [9 empty] | Connected |  | No
National Grid | PALMER | 177311 | 1069 | 3468 | Solar | 09_523L4 | 2017-02-09 | 2017-02-10 | 3 | 0 | 3 | [10 empty] | 2017-02-15 | 2017-02-22 | 4 | 0 | 4 | [10 empty] | 2017-12-04 | 2017-02-09 | 2019-10-01 |  | STD |  | 2018-12-06 | 2019-02-21 | 77 | 0 | 77 |  |  | 2019-09-17 | Connected |  | No
National Grid | CHESHIRE | 177312 | 1225 | 1980 | Solar | 09_1021W1 | 2017-02-09 | 2017-02-10 | 3 | 0 | 3 | [10 empty] | 2017-02-15 | 2017-02-22 | 4 | 0 | 4 | [10 empty] | 2018-07-20 | 2017-02-10 | 2021-12-30 | Yes | STD |  | 2019-07-25 | 2021-11-30 | 860 | 194 | 666 |  |  | 2021-12-13 | Connected |  | No
National Grid | PALMER | 177313 | 1069 | 4290 | Solar | 09_503L1 | 2017-02-10 | 2017-02-13 | 6 | 2 | 4 | [10 empty] | 2017-02-22 | 2017-02-23 | 1 | 0 | 1 | [10 empty] | 2018-06-22 | 2017-02-10 | 2020-08-21 | Yes | STD |  | 2019-07-16 | 2019-10-15 | 91 | 0 | 91 |  |  | 2020-08-20 | Connected |  | No
National Grid | NEW BRAINTREE | 177314 | 1531 | 1650 | Solar | 09_604W3 | 2017-02-10 | 2017-02-13 | 2 | 0 | 2 | [10 empty] | 2017-02-15 | 2017-02-22 | 4 | 0 | 4 | [10 empty] | 2017-12-04 | 2017-02-10 | 2023-12-08 | Yes | STD |  | 2022-08-04 | 2023-01-31 | 181 | 0 | 181 | 2023-02-01 | 2023-02-01 | 2023-11-21 | Connected |  | No
National Grid | NEW BRAINTREE | 177315 | 1531 | 1800 | Solar | 09_604W3 | 2017-02-10 | 2017-02-13 | 18 | 16 | 2 | [10 empty] | 2017-03-10 | 2017-03-24 | 10 | 0 | 10 | [10 empty] | 2018-09-07 | 2017-02-10 |  | Yes | STD | [9 empty] | Study |  | No
National Grid | NEW BRAINTREE | 177316 | 1531 | 1000 | Solar | 09_604W3 | 2017-02-10 | 2017-02-13 | 2 | 0 | 2 | [10 empty] | 2017-02-15 | 2017-02-22 | 4 | 0 | 4 | [10 empty] | 2018-06-07 |  |  | Yes | STD |  | 2023-02-08 | 2023-03-07 | 28 | 0 | 28 |  |  |  | Study |  | No
National Grid | CHARLTON | 177317 | 1507 | 1393 | Solar | 01_415L2 | 2017-02-14 | 2017-02-15 | 16 | 15 | 1 | [10 empty] | 2017-03-10 | 2017-04-03 | 16 | 0 | 16 | [10 empty] | 2018-02-26 |  | 2020-05-29 |  | STD |  | 2019-06-08 | 2019-11-21 | 166 | 0 | 166 |  |  | 2020-06-05 | Connected |  | No
National Grid | HUBBARDSTON | 177318 | 1452 | 2000 | Solar | 01_602W2 | 2017-02-14 | 2017-02-15 | 9 | 8 | 1 | [10 empty] | 2017-03-01 | 2017-03-27 | 18 | 7 | 11 | [12 empty] | 2018-02-20 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | EAST LONGMEADOW | 177319 | 1028 | 10 | Solar | 09_508L1 | 2017-02-14 | 2017-02-15 | 5 | 3 | 2 | 2017-02-23 | 2017-02-23 | 0 | 0 | 0 | [20 empty] | 2017-02-23 |  | 2018-06-29 |  | EXP | [8 empty] | 2018-04-29 | Connected |  | No
National Grid | NORTHBOROUGH | 177320 | 1532 | 26.6 | Solar | 05_313W1 | 2017-02-15 | 2017-02-15 | 5 | 3 | 2 | 2017-02-23 | 2017-02-23 | 0 | 0 | 0 | [20 empty] | 2017-02-23 |  | 2018-02-20 |  | EXP | [6 empty] | 2017-09-28 | 2017-09-28 | 2017-10-23 | Connected |  | No
National Grid | SWANSEA | 177350 | 2777 | 7.6 | Solar | 05_11W84 | 2017-02-15 | 2017-02-15 | 5 | 3 | 2 | 2017-02-23 |  | 274 | 0 | 274 | [20 empty] | 2017-02-24 | 2017-02-15 | 2018-02-20 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BELLINGHAM | 177352 | 2019 | 10 | Solar | 05_335W1 | 2017-02-15 | 2017-02-16 | 4 | 3 | 1 | 2017-02-23 | 2017-02-23 | 0 | 0 | 0 | [20 empty] | 2017-02-24 | 2017-02-15 | 2018-02-21 | Yes | EXP |  | 2017-10-31 | 2017-11-29 | 15 | 0 | 15 | 2018-02-20 | 2018-02-20 | 2018-02-26 | Connected |  | No
National Grid | SALEM | 177353 | 1970 | 3.8 | Solar | 12_29W2 | 2017-02-15 | 2017-02-16 | 4 | 3 | 1 | 2017-02-23 | 2017-02-23 | 0 | 0 | 0 | [20 empty] | 2017-02-27 |  | 2019-07-17 |  | EXP |  | 2018-05-24 | 2018-05-24 | 0 | 0 | 0 |  |  |  | Withdrawn |  | No
National Grid | NEW BRAINTREE | 177354 | 1531 | 499 | Solar | 09_604W3 | 2017-02-15 | 2017-02-16 | 47 | 47 | 0 | [10 empty] | 2017-04-26 | 2017-04-26 | 0 | 0 | 0 | [10 empty] | 2018-06-07 | 2017-02-15 | 2021-02-26 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | REHOBOTH | 177356 | 2769 | 22.8 | Solar | 05_7L4 | 2017-02-15 | 2017-02-16 | 4 | 3 | 1 | 2017-02-23 | 2017-02-23 | 0 | 0 | 0 | [20 empty] | 2017-02-27 |  | 2018-02-21 | Yes | EXP |  | 2017-06-28 | 2017-07-12 | 9 | 0 | 9 | 2017-09-18 | 2017-09-18 | 2017-09-21 | Connected |  | No
National Grid | HAVERHILL | 177355 | 1832 | 7.6 | Solar | 14_74L5 | 2017-02-16 | 2017-02-16 | 4 | 3 | 1 | 2017-02-23 | 2017-02-23 | 0 | 0 | 0 | [20 empty] | 2017-02-27 |  | 2018-02-21 |  | EXP | [6 empty] | 2017-07-12 | 2017-07-12 | 2017-07-12 | Connected |  | No
National Grid | NORTH BILLERICA | 177357 | 1862 | 168 | Solar | 14_70L5 | 2017-02-16 | 2017-05-11 | 1 | 0 | 1 | 2017-05-25 | 2017-05-25 | 0 | 0 | 0 | [20 empty] | 2017-06-19 |  | 2018-02-21 |  | EXP | [6 empty] | 2017-12-28 | 2017-12-28 | 2018-01-08 | Connected |  | No
National Grid | REVERE | 177358 | 2151 | 7.6 | Solar | 12_16W4 | 2017-02-16 | 2017-02-16 | 4 | 3 | 1 | 2017-02-23 | 2017-02-23 | 0 | 0 | 0 | [20 empty] | 2017-02-27 |  | 2018-02-21 |  | EXP | [6 empty] | 2017-10-10 | 2017-10-10 | 2017-08-31 | Connected |  | No
National Grid | SOUTHBOROUGH | 177389 | 1772 | 15.2 | Solar | 05_317W4 | 2017-02-16 | 2017-02-16 | 4 | 3 | 1 | 2017-02-23 | 2017-02-23 | 0 | 0 | 0 | [20 empty] | 2017-02-24 |  | 2018-02-21 |  | EXP | [6 empty] | 2017-06-08 | 2017-06-08 | 2017-06-13 | Connected |  | No
National Grid | NORTHBOROUGH | 177390 | 1532 | 15.2 | Solar | 05_313W3 | 2017-02-16 | 2017-02-16 | 4 | 3 | 1 | 2017-02-23 |  | 274 | 0 | 274 | [20 empty] | 2017-02-24 | 2017-02-17 | 2018-02-21 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GARDNER | 177393 | 1440 | 4950 | Solar | 01_607W1 | 2017-02-17 | 2017-02-20 | 4 | 0 | 4 | [10 empty] | 2017-02-27 | 2017-03-14 | 11 | 0 | 11 | [10 empty] | 2017-11-30 |  | 2020-12-31 | Yes | STD |  | 2019-12-12 | 2020-12-31 | 385 | 5 | 380 | 2020-12-30 | 2020-12-30 | 2019-12-31 | Connected |  | No
National Grid | ORANGE | 177395 | 1364 | 995 | Landfill Gas | 09_702W3 | 2017-02-21 | 2017-02-21 | 3 | 0 | 3 | [10 empty] | 2017-02-24 | 2017-03-09 | 9 | 0 | 9 | [11 empty] | 2017-02-21 | 2018-02-26 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 177396 | 1844 | 6 | Solar | 14_75L6 | 2017-02-21 | 2017-02-21 | 6 | 1 | 5 | 2017-03-01 | 2017-03-01 | 0 | 0 | 0 | [20 empty] | 2017-03-03 |  | 2018-02-26 | Yes | EXP |  | 2017-10-16 | 2017-10-20 | 4 | 0 | 4 | 2017-06-27 | 2017-06-27 | 2017-11-02 | Connected |  | No
National Grid | WRENTHAM | 178792 | 2093 | 28.8 | Solar | 05_3422W1 | 2017-02-23 | 2017-02-23 | 2 | 0 | 2 | 2017-02-27 | 2017-04-03 | 25 | 0 | 25 | [22 empty] | 2018-02-28 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WRENTHAM | 178793 | 2093 | 133.2 | Solar | 05_3422W1 | 2017-02-23 | 2017-02-23 | 2 | 0 | 2 | 2017-02-27 | 2017-02-27 | 0 | 0 | 0 | [20 empty] | 2017-04-06 |  | 2018-02-28 |  | EXP | [6 empty] | 2017-10-03 | 2017-10-03 | 2017-10-16 | Connected |  | No
National Grid | EAST BRIDGEWATER | 177426 | 2333 | 7.6 | Solar | 07_797W20 | 2017-02-27 | 2017-02-28 | 6 | 6 | 0 | 2017-03-08 | 2017-03-09 | 1 | 0 | 1 | [20 empty] | 2017-03-09 | 2017-02-27 | 2018-03-05 |  | EXP | [8 empty] | 2018-10-04 | Connected |  | No
National Grid | WINCHENDON | 177429 | 1475 | 4980 | Solar | 01_612W1 | 2017-02-27 | 2017-03-01 | 20 | 18 | 2 | [10 empty] | 2017-03-29 | 2017-04-14 | 12 | 0 | 12 | [10 empty] | 2017-11-20 | 2017-02-27 | 2020-02-28 | Yes | STD |  | 2019-10-04 | 2019-12-20 | 77 | 0 | 77 |  |  | 2020-01-30 | Connected |  | No
National Grid | WINCHENDON | 177430 | 1475 | 1000 | Solar | 01_612W3 | 2017-02-27 | 2017-03-01 | 16 | 14 | 2 | [10 empty] | 2017-03-23 | 2017-04-14 | 16 | 0 | 16 | [10 empty] | 2017-11-15 |  | 2020-12-31 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | WINCHENDON | 177431 | 1475 | 1000 | Solar | 01_612W3 | 2017-02-27 | 2017-03-01 | 16 | 14 | 2 | [10 empty] | 2017-03-23 | 2017-04-14 | 16 | 0 | 16 | [12 empty] | 2018-03-06 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ATTLEBORO | 177427 | 2703 | 997 | Solar | 05_9L2 | 2017-02-28 | 2017-02-28 | 5 | 3 | 2 | [10 empty] | 2017-03-07 | 2017-03-24 | 13 | 3 | 10 | [11 empty] | 2017-02-28 | 2018-09-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NEW BRAINTREE | 177428 | 1531 | 997 | Solar | 09_604W3 | 2017-02-28 | 2017-03-01 | 27 | 25 | 2 | [10 empty] | 2017-04-07 | 2017-04-26 | 12 | 7 | 5 | [10 empty] | 2017-12-04 | 2017-02-28 | 2023-05-03 | Yes | STD |  | 2022-11-18 | 2023-04-18 | 153 | 43 | 110 |  |  | 2023-04-26 | Connected |  | Yes
National Grid | WINCHENDON | 177468 | 1475 | 3150 | Solar | 01_612W3 | 2017-02-28 | 2017-03-02 | 19 | 18 | 1 | [10 empty] | 2017-03-29 | 2017-04-20 | 15 | 4 | 11 | [10 empty] | 2017-11-20 | 2017-02-28 | 2019-12-31 | Yes | STD |  | 2019-08-29 | 2019-12-26 | 119 | 0 | 119 |  |  | 2019-12-26 | Connected |  | No
National Grid | WINCHENDON | 177469 | 1475 | 4979.98 | Solar | 01_612W3 | 2017-02-28 | 2017-03-02 | 19 | 18 | 1 | [10 empty] | 2017-03-29 | 2017-04-20 | 15 | 4 | 11 | [5 empty] | 2017-12-16 | 2018-10-10 | 74 | 0 | 74 | 2017-11-20 |  | 2019-12-31 | Yes | STD |  | 2019-09-14 | 2019-12-26 | 103 | 0 | 103 |  |  | 2019-12-26 | Connected |  | No
National Grid | WINCHENDON | 177470 | 1475 | 2000 | Solar | 01_612W3 | 2017-02-28 | 2017-03-02 | 15 | 14 | 1 | [10 empty] | 2017-03-23 | 2017-04-20 | 19 | 4 | 15 | [11 empty] | 2017-03-01 | 2018-03-07 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH DIGHTON | 177463 | 2764 | 528 | Solar | 05_19W73 | 2017-03-01 | 2017-03-02 | 31 | 25 | 6 | [10 empty] | 2017-04-13 | 2017-05-09 | 17 | 5 | 12 | [10 empty] | 2017-11-09 |  | 2019-05-07 | Yes | STD |  | 2018-05-22 | 2018-07-30 | 68 | 0 | 68 | 2018-12-06 | 2018-12-06 | 2019-05-07 | Connected |  | No
National Grid | NORTH DIGHTON | 177464 | 2764 | 96 | Solar | 05_19W74 | 2017-03-01 | 2017-03-02 | 15 | 13 | 2 | 2017-03-23 | 2017-04-11 | 13 | 0 | 13 | 2017-06-21 | 2017-06-27 | 4 | 1 | 3 | [5 empty] | 2017-06-21 | 2017-06-27 | 4 | 1 | 3 | [5 empty] | 2017-07-27 |  | 2018-03-07 |  | EXP | [8 empty] | 2018-05-22 | Connected |  | Yes
National Grid | NORTH DIGHTON | 177465 | 2764 | 192 | Solar | 05_19W74 | 2017-03-01 | 2017-03-15 | 15 | 13 | 2 | 2017-03-23 | 2017-04-11 | 42 | 28 | 14 | 2017-06-21 | 2017-06-27 | 4 | 1 | 3 | [5 empty] | 2017-06-21 | 2017-06-27 | 4 | 1 | 3 | [5 empty] | 2017-07-27 |  | 2018-03-07 |  | EXP | [8 empty] | 2018-07-10 | Connected |  | Yes
National Grid | REHOBOTH | 177466 | 2769 | 168 | Solar | 05_7L4 | 2017-03-01 | 2017-03-15 | 20 | 13 | 7 | 2017-03-23 | 2017-04-12 | 21 | 6 | 15 | 2017-05-03 | 2017-05-03 | 0 | 0 | 0 | [5 empty] | 2017-05-03 | 2017-05-03 | 0 | 0 | 0 | [5 empty] | 2017-05-03 |  | 2018-03-07 |  | EXP | [8 empty] | 2018-07-10 | Connected |  | Yes
National Grid | REHOBOTH | 177467 | 2769 | 192 | Solar | 05_7L4 | 2017-03-01 | 2017-03-14 | 15 | 13 | 2 | 2017-03-23 | 2017-04-12 | 21 | 6 | 15 | 2017-05-03 | 2017-05-03 | 0 | 0 | 0 | [5 empty] | 2017-05-03 | 2017-05-03 | 0 | 0 | 0 | [5 empty] | 2017-05-03 |  | 2018-03-07 |  | EXP | [8 empty] | 2018-06-19 | Connected |  | No
National Grid | RANDOLPH | 177471 | 2368 | 3.8 | Solar | 07_97W2 | 2017-03-02 | 2017-03-03 | 10 | 9 | 1 | 2017-03-17 | 2017-03-21 | 258 | 0 | 258 | [20 empty] | 2017-03-21 |  | 2018-03-08 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTHBRIDGE | 177472 | 1534 | 15.2 | Solar | 05_320W3 | 2017-03-02 | 2017-03-03 | 239 | 238 | 1 | 2018-02-12 | 2018-05-31 | 77 | 76 | 1 | [20 empty] | 2018-06-08 | 2017-03-03 | 2020-06-30 |  | EXP | [8 empty] | 2020-06-02 | Connected |  | No
National Grid | STOUGHTON | 177500 | 2072 | 6 | Solar | 07_913W18 | 2017-03-03 | 2017-03-06 | 45 | 38 | 7 | 2017-05-09 | 2017-05-09 | 0 | 0 | 0 | [20 empty] | 2017-05-09 | 2017-03-03 | 2018-03-11 | Yes | EXP |  | 2018-01-12 | 2018-02-16 | 24 | 0 | 24 | 2018-02-28 | 2018-02-28 | 2018-03-06 | Connected |  | No
National Grid | GARDNER | 177501 | 1440 | 9 | Solar | 01_607W5 | 2017-03-03 | 2017-03-06 | 4 | 3 | 1 | 2017-03-10 | 2017-03-10 | 0 | 0 | 0 | [20 empty] | 2017-03-20 |  | 2018-03-11 | Yes | EXP |  | 2017-05-01 | 2017-07-10 | 48 | 0 | 48 | 2017-07-25 | 2017-07-25 | 2017-07-24 | Connected |  | No
National Grid | WESTPORT | 176947 | 2790 | 11.4 | Solar | 05_115W45 | 2017-03-06 | 2017-03-07 | 8 | 7 | 1 | 2017-03-17 | 2017-03-20 | 1 | 0 | 1 | [20 empty] | 2017-03-20 |  | 2020-01-21 |  | EXP | [8 empty] | 2020-01-11 | Connected |  | No
National Grid | SOUTHBRIDGE | 177502 | 1550 | 2000 |  | 01_413L4 | 2017-03-06 | 2017-03-06 | 0 | 0 | 0 | [27 empty] | 2018-03-11 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | REHOBOTH | 177503 | 2769 | 22.8 | Solar | 05_7L5 | 2017-03-06 | 2017-03-06 | 9 | 7 | 2 | 2017-03-17 | 2017-03-21 | 258 | 0 | 258 | [20 empty] | 2017-03-21 |  | 2018-03-11 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BELLINGHAM | 177504 | 2019 | 10 | Solar | 05_108W51 | 2017-03-06 | 2017-03-06 | 9 | 7 | 2 | 2017-03-17 | 2017-03-17 | 0 | 0 | 0 | [20 empty] | 2017-03-21 | 2017-03-06 | 2018-03-11 |  | EXP | [6 empty] | 2017-08-30 | 2017-08-30 | 2017-09-06 | Connected |  | No
National Grid | HAVERHILL | 177505 | 1830 | 7.6 | Solar | 14_47L1 | 2017-03-06 | 2017-03-06 | 9 | 3 | 6 | 2017-03-17 | 2017-03-17 | 0 | 0 | 0 | [20 empty] | 2017-03-21 |  | 2018-03-11 | Yes | EXP |  | 2017-07-10 | 2017-07-31 | 15 | 0 | 15 | 2017-09-08 | 2017-09-08 | 2017-09-08 | Connected |  | No
National Grid | EAST LONGMEADOW | 177506 | 1028 | 15.2 | Solar | 09_508L1 | 2017-03-06 | 2017-03-07 | 0 | 0 | 0 | [26 empty] | 2017-03-06 | 2018-03-12 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | EAST LONGMEADOW | 177507 | 1028 | 11.4 | Solar | 09_508L1 | 2017-03-06 | 2017-03-07 | 8 | 7 | 1 | 2017-03-17 | 2017-03-17 | 0 | 0 | 0 | [20 empty] | 2017-03-21 |  | 2018-03-12 | Yes | EXP |  | 2017-06-23 | 2017-06-26 | 1 | 0 | 1 | 2017-09-13 | 2017-09-13 | 2017-09-13 | Connected |  | No
National Grid | FOXBOROUGH | 178794 | 2035 | 57.6 | Solar | 05_3432W2 | 2017-03-06 | 2017-03-06 | 2 | 0 | 2 | 2017-03-08 | 2017-03-09 | 265 | 0 | 265 | [20 empty] | 2017-03-09 | 2017-03-06 | 2018-03-11 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | PLAINVILLE | 178795 | 2762 | 4950 | Solar | 05_3451W3 | 2017-03-06 | 2017-03-06 | 4 | 0 | 4 | [10 empty] | 2017-03-10 | 2017-03-28 | 12 | 0 | 12 | [10 empty] | 2017-09-25 |  | 2019-12-31 | Yes | STD |  | 2019-03-08 | 2019-03-08 | 0 | 0 | 0 | 2019-10-16 | 2019-10-16 | 2019-12-30 | Connected |  | No
National Grid | BEVERLY | 176984 | 1915 | 1104 | Solar | 12_12L4 | 2017-03-07 | 2017-03-08 | 229 | 225 | 4 | [27 empty] | 2018-03-13 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | QUINCY | 176985 | 2169 | 466.2 | Solar | 07_1W4 | 2017-03-09 | 2017-03-10 | 12 | 12 | 0 | 2017-03-28 | 2017-03-28 | 0 | 0 | 0 | [20 empty] | 2017-04-03 |  | 2018-03-15 |  | EXP | [6 empty] | 2017-12-07 | 2017-12-07 | 2017-12-12 | Connected |  | No
National Grid | SOMERSET | 176988 | 2726 | 3.8 | Solar | 05_18J5 | 2017-03-10 | 2017-03-10 | 4 | 2 | 2 | 2017-03-16 | 2017-03-16 | 0 | 0 | 0 | [20 empty] | 2017-03-21 | 2017-03-10 | 2018-03-15 |  | EXP | [6 empty] | 2017-06-05 | 2017-06-05 | 2017-06-07 | Connected |  | No
National Grid | EAST BRIDGEWATER | 176989 | 2333 | 7.6 | Solar | 07_797W42 | 2017-03-10 | 2017-03-10 | 5 | 3 | 2 | 2017-03-17 | 2017-03-17 | 0 | 0 | 0 | [20 empty] | 2017-03-21 |  | 2018-03-15 |  | EXP |  | 2017-08-22 | 2017-08-31 | 7 | 0 | 7 | 2018-01-29 | 2018-01-29 | 2018-02-07 | Connected |  | No
National Grid | RANDOLPH | 176991 | 2368 | 3.8 | Solar | 07_97W3 | 2017-03-13 01:00 | 2017-03-15 | 9 | 7 | 2 | 2017-03-28 |  | 251 | 0 | 251 | [20 empty] | 2017-03-29 |  | 2018-03-20 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WEST BRIDGEWATER | 176992 | 2379 | 7.6 | Solar | 07_98W44 | 2017-03-15 01:00 | 2017-03-15 | 9 | 7 | 2 | 2017-03-28 | 2017-06-14 | 54 | 0 | 54 | [20 empty] | 2017-03-30 |  | 2018-03-20 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | OAKHAM | 176993 | 1068 | 16 | Solar | 09_604W2 | 2017-03-15 01:00 | 2017-03-17 | 10 | 10 | 0 | 2017-03-31 | 2017-03-31 | 0 | 0 | 0 | [20 empty] | 2017-04-04 |  | 2018-03-20 |  | EXP | [6 empty] | 2017-12-13 | 2017-12-13 | 2017-12-13 | Connected |  | No
National Grid | WARE | 177024 | 1082 | 15.2 | Solar | 09_501L2 | 2017-03-16 01:00 | 2017-03-16 | 8 | 7 | 1 | 2017-03-28 | 2017-03-28 | 0 | 0 | 0 | [20 empty] | 2017-03-29 |  | 2018-03-21 |  | EXP | [6 empty] | 2017-09-19 | 2017-09-19 | 2017-09-19 | Connected |  | No
National Grid | WESTFORD | 177025 | 1886 | 86.4 | Solar | 14_57L3 | 2017-03-16 01:00 | 2017-03-16 | 6 | 5 | 1 | 2017-03-24 | 2018-03-13 | 229 | 0 | 229 | [20 empty] | 2017-03-28 | 2017-03-16 01:00 | 2018-03-21 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HAMILTON | 177027 | 1982 | 731 | Solar | 12_51T1 | 2017-03-16 01:00 | 2017-03-17 | 12 | 10 | 2 | [10 empty] | 2017-04-04 | 2017-05-05 | 22 | 8 | 14 | [10 empty] | 2018-01-31 | 2017-03-17 01:00 | 2021-08-18 | Yes | STD |  | 2019-11-08 | 2020-04-22 | 166 | 0 | 166 |  |  | 2021-08-18 | Connected |  | No
National Grid | NORTON | 177029 | 2766 | 3330 | Solar | 05_4L2 | 2017-03-17 01:00 | 2017-03-17 | 9 | 7 | 2 | [10 empty] | 2017-03-30 | 2017-04-27 | 19 | 4 | 15 | [10 empty] | 2017-08-21 |  | 2020-09-15 | Yes | STD |  | 2020-03-06 | 2020-05-22 | 77 | 0 | 77 |  |  | 2020-09-10 | Connected |  | No
National Grid | SOUTHBRIDGE | 177030 | 1550 | 224 | Solar | 01_413L1 | 2017-03-19 01:00 | 2017-03-20 | 69 | 68 | 1 | 2017-06-27 | 2017-06-27 | 0 | 0 | 0 | 2017-12-07 | 2018-01-04 | 106 | 0 | 106 | [5 empty] | 2017-12-07 | 2018-01-04 | 106 | 0 | 106 | [5 empty] | 2017-09-14 |  | 2018-03-30 |  | EXP | [6 empty] | 2018-03-14 | 2018-03-14 | 2018-03-14 | Connected |  | No
National Grid | AUBURN | 177031 | 1501 | 3.8 | Solar | 01_26W1 | 2017-03-20 01:00 | 2017-03-20 | 6 | 5 | 1 | 2017-03-28 | 2017-03-28 | 0 | 0 | 0 | [20 empty] | 2017-03-29 |  | 2018-03-25 |  | EXP | [6 empty] | 2017-10-17 | 2017-10-17 | 2017-10-17 | Connected |  | No
National Grid | WEYMOUTH | 177060 | 2188 | 480 | Solar | 07_12W1 | 2017-03-20 01:00 | 2017-03-20 | 85 | 83 | 2 | 2017-07-20 | 2017-10-10 | 56 | 24 | 32 | [22 empty] | 2018-03-25 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WEYMOUTH | 177061 | 2188 | 300 | Solar | 07_12W1 | 2017-03-20 01:00 | 2017-03-20 | 90 | 88 | 2 | 2017-07-27 | 2017-10-10 | 51 | 18 | 33 | 2017-08-31 | 2017-10-10 | 26 | 0 | 26 | [5 empty] | 2017-08-31 | 2017-10-10 | 26 | 0 | 26 | [7 empty] | 2018-03-25 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WEYMOUTH | 177062 | 2188 | 420 | Solar | 07_12W1 | 2017-03-20 01:00 | 2017-03-20 | 110 | 108 | 2 | 2017-08-24 | 2017-10-10 | 31 | 0 | 31 | [22 empty] | 2018-03-25 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WEYMOUTH | 177063 | 2188 | 360 | Solar | 07_12W1 | 2017-03-20 01:00 | 2017-03-20 | 110 | 108 | 2 | 2017-08-24 | 2017-10-10 | 31 | 0 | 31 | [22 empty] | 2018-03-25 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 177064 | 1844 | 3.8 | Solar | 14_63L2 | 2017-03-20 01:00 | 2017-03-20 | 9 | 8 | 1 | 2017-03-31 | 2018-03-13 | 224 | 0 | 224 | [20 empty] | 2017-04-04 |  | 2018-03-25 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | EAST LONGMEADOW | 177065 | 1028 | 230.4 | Solar | 09_508L2 | 2017-03-20 01:00 | 2017-03-29 | 16 | 16 | 0 | 2017-04-12 | 2017-04-12 | 0 | 0 | 0 | [20 empty] | 2017-05-08 | 2017-03-20 01:00 | 2018-03-26 |  | EXP | [6 empty] | 2018-01-08 | 2018-01-08 | 2018-01-08 | Connected |  | No
National Grid | WEYMOUTH | 177066 | 2188 | 3.8 | Solar | 07_6W1 | 2017-03-20 01:00 | 2017-03-21 | 7 | 7 | 0 | 2017-03-30 | 2017-03-30 | 0 | 0 | 0 | [20 empty] | 2017-04-03 | 2017-03-20 01:00 | 2018-03-26 | Yes | EXP |  | 2017-08-15 | 2017-09-01 | 13 | 0 | 13 | 2017-11-07 | 2017-11-07 | 2017-11-07 | Connected |  | No
National Grid | ATHOL | 177067 | 1331 | 3276 | Solar | 09_702W3 | 2017-03-20 01:00 | 2017-03-21 | 4 | 1 | 3 | [10 empty] | 2017-03-27 | 2017-04-07 | 9 | 0 | 9 | [10 empty] | 2017-12-04 |  | 2020-03-05 | Yes | STD |  | 2019-04-09 | 2019-06-06 | 58 | 0 | 58 |  |  | 2020-03-05 | Connected |  | No
National Grid | REHOBOTH | 177068 | 2769 | 15.2 | Solar | 05_8L4 | 2017-03-21 01:00 | 2017-03-21 | 7 | 6 | 1 | 2017-03-30 | 2017-03-30 | 0 | 0 | 0 | [20 empty] | 2017-03-31 |  | 2018-03-26 |  | EXP | [6 empty] | 2017-09-21 | 2017-09-21 | 2017-09-26 | Connected |  | No
National Grid | GRANBY | 177693 | 1033 | 7.6 | Solar | 09_527L2 | 2017-03-21 01:00 | 2017-03-21 | 5 | 5 | 0 | 2017-03-28 | 2017-03-29 | 1 | 0 | 1 | [20 empty] | 2017-03-29 |  | 2019-03-28 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 177694 | 1605 | 5 | Solar | 01_24W2 | 2017-03-21 01:00 | 2017-03-21 | 10 | 10 | 0 | 2017-04-04 | 2018-02-14 | 211 | 0 | 211 | [20 empty] | 2017-04-06 |  | 2018-03-26 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BELCHERTOWN | 177695 | 1007 | 11.4 | Solar | 09_527L2 | 2017-03-21 01:00 | 2017-03-21 | 7 | 7 | 0 | 2017-03-30 | 2017-07-25 | 80 | 0 | 80 | [20 empty] | 2017-04-03 |  | 2018-03-26 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTH DIGHTON | 177696 | 2764 | 11.4 | Solar | 05_19W73 | 2017-03-21 01:00 | 2017-03-21 | 7 | 7 | 0 | 2017-03-30 | 2017-03-30 | 0 | 0 | 0 | [20 empty] | 2017-03-31 |  | 2018-03-26 |  | EXP | [6 empty] | 2018-01-09 | 2018-01-09 | 2018-01-12 | Connected |  | No
National Grid | WEBSTER | 177697 | 1570 | 3990 | Solar | 01_412L1 | 2017-03-21 01:00 | 2017-03-22 | 9 | 8 | 1 | [10 empty] | 2017-04-04 | 2017-04-24 | 13 | 0 | 13 | [11 empty] | 2017-03-21 01:00 | 2018-03-27 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 177698 | 1844 | 7.6 | Solar | 14_63L2 | 2017-03-21 01:00 | 2017-03-22 | 7 | 7 | 0 | 2017-03-31 | 2018-02-09 | 210 | 0 | 210 | [20 empty] | 2017-04-04 |  | 2018-03-27 | Yes | EXP | [9 empty] | Withdrawn |  | No
National Grid | CLARKSBURG | 177699 | 1247 | 3000 | Solar | 09_1015W2 | 2017-03-21 01:00 | 2017-03-22 | 9 | 8 | 1 | [10 empty] | 2017-04-04 | 2017-05-10 | 25 | 12 | 13 | [10 empty] | 2018-11-20 |  | 2020-09-07 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LAWRENCE | 177700 | 1843 | 7.6 | Solar | 14_8L1 | 2017-03-21 01:00 | 2017-03-22 | 4 | 4 | 0 | 2017-03-28 | 2017-03-28 | 0 | 0 | 0 | [20 empty] | 2017-03-30 |  | 2018-03-27 |  | EXP | [6 empty] | 2017-06-20 | 2017-06-20 | 2017-07-12 | Connected |  | No
National Grid | DRACUT | 177701 | 1826 | 7.6 | Solar | 14_21L2 | 2017-03-21 01:00 | 2017-03-22 | 6 | 6 | 0 | 2017-03-30 | 2017-03-30 | 0 | 0 | 0 | [20 empty] | 2017-03-31 |  | 2018-03-27 |  | EXP | [6 empty] | 2017-10-03 | 2017-10-03 | 2017-10-03 | Connected |  | No
National Grid | METHUEN | 177732 | 1844 | 8.32 | Solar | 14_74L1 | 2017-03-22 01:00 | 2017-03-22 | 27 | 27 | 0 | 2017-05-01 | 2017-11-06 | 126 | 0 | 126 | [20 empty] | 2017-05-03 | 2017-03-22 01:00 | 2018-03-27 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOMERSET | 177733 | 2726 | 3.8 | Solar | 05_19W72 | 2017-03-22 01:00 | 2017-03-22 | 4 | 4 | 0 | 2017-03-28 | 2017-03-28 | 0 | 0 | 0 | [20 empty] | 2017-03-29 | 2017-03-22 01:00 | 2018-03-27 | Yes | EXP |  | 2017-08-09 | 2017-09-12 | 23 | 0 | 23 | 2017-10-16 | 2017-10-16 | 2017-10-18 | Connected |  | No
National Grid | GRANBY | 177734 | 1033 | 10 | Solar | 09_527L1 | 2017-03-22 01:00 | 2017-03-22 | 4 | 4 | 0 | 2017-03-28 | 2017-03-28 | 0 | 0 | 0 | [20 empty] | 2017-03-29 | 2017-03-23 01:00 | 2018-03-27 | Yes | EXP | [6 empty] | 2018-01-05 | 2018-01-05 | 2018-01-08 | Connected |  | No
National Grid | SOMERSET | 177736 | 2725 | 3.6 | Solar | 05_11W84 | 2017-03-23 01:00 | 2017-03-23 | 6 | 6 | 0 | 2017-03-31 | 2017-03-31 | 0 | 0 | 0 | [20 empty] | 2017-04-04 | 2017-03-23 01:00 | 2018-03-28 | Yes | EXP |  | 2017-08-09 | 2017-08-14 | 3 | 0 | 3 | 2018-03-01 | 2018-03-01 | 2018-03-23 | Connected |  | No
National Grid | RANDOLPH | 177737 | 2368 | 10 | Solar | 07_5W3 | 2017-03-23 01:00 | 2017-03-24 | 2 | 1 | 1 | 2017-03-28 | 2017-03-29 | 1 | 0 | 1 | [20 empty] | 2017-03-29 | 2017-03-24 01:00 | 2018-06-30 | Yes | EXP |  | 2017-12-28 | 2018-01-19 | 14 | 0 | 14 | 2018-04-17 | 2018-04-17 | 2018-06-08 | Connected |  | No
National Grid | REVERE | 177738 | 2151 | 6 | Solar | 12_7W2 | 2017-03-24 01:00 | 2017-03-27 | 4 | 4 | 0 | 2017-03-31 | 2017-04-04 | 2 | 0 | 2 | [20 empty] | 2017-04-04 | 2017-03-28 01:00 | 2018-08-10 | Yes | EXP |  | 2017-10-24 | 2017-11-29 | 19 | 0 | 19 |  |  | 2018-08-29 | Connected |  | Yes
National Grid | WEST BROOKFIELD | 177777 | 1585 | 3960 | Solar | 01_525L2 | 2017-03-28 01:00 | 2017-03-29 | 13 | 12 | 1 | [10 empty] | 2017-04-18 | 2017-05-11 | 17 | 0 | 17 | [10 empty] | 2018-11-28 | 2017-03-28 01:00 | 2024-08-16 | Yes | STD | [9 empty] | Design |  | No
National Grid | WARREN | 177778 | 1083 | 8200 | Solar | 09_501L1 | 2017-03-28 01:00 | 2017-03-29 | 13 | 12 | 1 | [10 empty] | 2017-04-18 | 2017-05-11 | 17 | 0 | 17 | [10 empty] | 2018-11-28 |  |  | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | GRANBY | 177779 | 1033 | 4150 | Solar | 09_527L1 | 2017-03-30 01:00 | 2017-03-30 | 6 | 6 | 0 | [10 empty] | 2017-04-07 | 2017-05-11 | 23 | 8 | 15 | [11 empty] | 2017-03-30 01:00 | 2018-04-04 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | GARDNER | 178796 | 1440 | 2500 | Solar | 01_607W5 | 2017-03-30 01:00 | 2017-03-30 | 6 | 6 | 0 | [10 empty] | 2017-04-07 | 2017-05-08 | 20 | 7 | 13 | [10 empty] | 2017-12-01 | 2017-03-31 01:00 | 2019-07-30 | Yes | STD |  | 2018-09-26 | 2019-07-15 | 291 | 0 | 291 | 2019-08-01 | 2019-08-01 | 2019-09-19 | Connected |  | No
National Grid | BELLINGHAM | 177810 | 2019 | 7.6 | Solar | 05_335W1 | 2017-03-31 01:00 | 2017-03-31 | 5 | 2 | 3 | 2017-04-07 | 2017-04-07 | 0 | 0 | 0 | [20 empty] | 2017-04-10 |  | 2018-04-05 |  | EXP | [6 empty] | 2017-12-14 | 2017-12-14 | 2018-01-30 | Connected |  | No
National Grid | WILBRAHAM | 177811 | 1095 | 15.2 | Solar | 09_507L2 | 2017-03-31 01:00 | 2017-03-31 | 5 | 2 | 3 | 2017-04-07 | 2017-04-07 | 0 | 0 | 0 | [20 empty] | 2017-04-10 |  | 2018-11-30 |  | EXP | [6 empty] | 2018-01-24 | 2018-01-24 | 2018-01-24 | Connected |  | No
National Grid | DUNSTABLE | 177812 | 1827 | 15.2 | Solar | 01_210L1 | 2017-03-31 01:00 | 2017-03-31 | 5 | 2 | 3 | 2017-04-07 | 2017-04-07 | 0 | 0 | 0 | [20 empty] | 2017-04-10 |  | 2018-04-05 |  | EXP | [6 empty] | 2017-08-22 | 2017-08-22 | 2017-08-22 | Connected |  | No
National Grid | RANDOLPH | 177813 | 2368 | 7.6 | Solar | 07_97W3 | 2017-03-31 01:00 | 2017-03-31 | 5 | 2 | 3 | 2017-04-07 | 2017-04-07 | 0 | 0 | 0 | [20 empty] | 2017-04-10 |  | 2018-04-05 |  | EXP | [6 empty] | 2017-12-15 | 2017-12-15 | 2017-12-15 | Connected |  | No
National Grid | LYNN | 177814 | 1904 | 3.8 | Solar | 12_24W1 | 2017-03-31 01:00 | 2017-03-31 | 5 | 2 | 3 | 2017-04-07 | 2018-03-02 | 219 | 0 | 219 | [20 empty] | 2017-04-10 | 2017-03-31 01:00 | 2018-04-05 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | GLOUCESTER | 177815 | 1930 | 15.2 | Solar | 12_52L1 | 2017-03-31 01:00 | 2017-03-31 | 7 | 4 | 3 | 2017-04-11 | 2017-04-12 | 1 | 0 | 1 | [20 empty] | 2017-04-12 |  | 2018-08-10 | Yes | EXP |  | 2018-01-24 | 2018-02-23 | 21 | 0 | 21 |  |  | 2018-07-30 | Connected |  | No
National Grid | BELLINGHAM | 177816 | 2019 | 7.6 | Solar | 05_344W4 | 2017-04-04 01:00 | 2017-04-04 | 5 | 1 | 4 | 2017-04-11 |  | 241 | 0 | 241 | [20 empty] | 2017-04-12 |  | 2018-04-09 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BOXFORD | 177817 | 1921 | 11.4 | Solar | 14_56L3 | 2017-04-04 01:00 | 2017-04-05 | 2 | 0 | 2 | 2017-04-07 | 2017-04-07 | 0 | 0 | 0 | [20 empty] | 2017-04-10 |  | 2018-04-10 |  | EXP | [6 empty] | 2017-09-22 | 2017-09-22 | 2017-09-22 | Connected |  | No
National Grid | CHARLTON | 177818 | 1507 | 13.76 | Solar | 01_415L2 | 2017-04-04 01:00 | 2017-04-05 | 218 | 216 | 2 | [27 empty] | 2018-04-10 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOMERSET | 177848 | 2726 | 300 | Natural Gas | 05_11W84 | 2017-04-06 01:00 | 2017-04-07 | 54 | 54 | 0 | 2017-06-26 |  | 189 | 53 | 136 | 2017-08-17 | 2017-10-16 | 40 | 22 | 18 | [5 empty] | 2017-08-17 | 2017-10-16 | 40 | 22 | 18 | [5 empty] | 2017-12-15 | 2017-04-06 01:00 | 2018-04-12 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ROCKLAND | 177849 | 2370 | 166.5 | Solar | 07_99W63 | 2017-04-06 01:00 | 2017-04-07 | 7 | 7 | 0 | 2017-04-19 | 2017-04-19 | 0 | 0 | 0 | [20 empty] | 2017-05-23 |  | 2018-04-12 |  | EXP |  | 2017-05-24 | 2017-06-21 | 19 | 0 | 19 | 2017-12-15 | 2017-12-15 | 2017-12-21 | Connected |  | No
National Grid | MONSON | 177851 | 1057 | 250 | Solar | 09_139L1 | 2017-04-10 01:00 | 2017-04-11 | 200 | 198 | 2 | [27 empty] | 2018-04-16 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MONSON | 177852 | 1057 | 250 | Solar | 09_139L1 | 2017-04-10 01:00 | 2017-04-11 | 200 | 198 | 2 | [27 empty] | 2018-04-16 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MONSON | 177853 | 1057 | 250 | Solar | 09_139L1 | 2017-04-10 01:00 | 2017-04-11 | 200 | 198 | 2 | [27 empty] | 2018-04-16 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MONSON | 177854 | 1057 | 250 | Solar | 09_139L1 | 2017-04-10 01:00 | 2017-04-11 | 200 | 198 | 2 | [26 empty] | 2017-04-11 01:00 | 2018-04-16 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | EAST BRIDGEWATER | 177855 | 2333 | 3.8 | Solar | 07_797W29 | 2017-04-11 01:00 | 2017-04-11 | 3 | 3 | 0 | 2017-04-14 | 2017-04-17 | 2 | 0 | 2 | [20 empty] | 2017-04-17 | 2017-04-11 01:00 | 2020-07-30 | Yes | EXP |  | 2017-06-28 | 2017-07-17 | 12 | 0 | 12 |  |  | 2020-06-01 | Connected |  | No
National Grid | EAST BRIDGEWATER | 177856 | 2333 | 3.8 | Solar | 07_797W29 | 2017-04-11 01:00 | 2017-04-11 | 3 | 2 | 1 | 2017-04-14 | 2017-04-14 | 0 | 0 | 0 | [20 empty] | 2017-04-19 | 2017-04-11 01:00 | 2018-04-16 |  | EXP |  | 2017-06-28 | 2017-07-17 | 12 | 0 | 12 | 2017-10-16 | 2017-10-16 | 2017-10-16 | Connected |  | No
National Grid | OXFORD | 177886 | 1540 | 10 | Solar | 01_406L4 | 2017-04-11 01:00 | 2017-04-12 | 2 | 0 | 2 | 2017-04-14 | 2017-04-14 | 0 | 0 | 0 | [20 empty] | 2017-04-17 |  | 2018-04-17 | Yes | EXP |  | 2017-08-04 | 2017-09-05 | 21 | 0 | 21 | 2017-10-17 | 2017-10-17 | 2017-10-17 | Connected |  | No
National Grid | METHUEN | 177887 | 1844 | 300 | Natural Gas | 14_74L2 | 2017-04-11 01:00 | 2017-04-12 | 40 | 40 | 0 | 2017-06-14 | 2017-07-07 | 0 | 0 | 0 | [20 empty] | 2017-07-07 |  | 2018-04-17 |  | EXP | [6 empty] | 2018-04-05 | 2018-04-05 | 2018-04-05 | Connected |  | No
National Grid | MARLBOROUGH | 177888 | 1752 | 300 | Natural Gas | 05_311W5 | 2017-04-11 01:00 | 2017-04-12 | 55 | 52 | 3 | 2017-06-30 | 2017-07-27 | 18 | 0 | 18 | [20 empty] | 2017-07-27 |  | 2018-04-17 |  | EXP | [8 empty] | 2018-09-27 | Connected |  | No
National Grid | UPTON | 177890 | 1568 | 15.2 | Solar | 05_320W1 | 2017-04-12 01:00 | 2017-04-13 | 4 | 3 | 1 | 2017-04-20 | 2017-04-20 | 0 | 0 | 0 | [20 empty] | 2017-04-21 |  | 2018-04-18 |  | EXP | [6 empty] | 2017-08-29 | 2017-08-29 | 2017-09-05 | Connected |  | No
National Grid | SOMERSET | 177891 | 2726 | 3.8 | Solar | 05_19W74 | 2017-04-13 01:00 | 2017-04-13 | 6 | 6 | 0 | 2017-04-24 | 2017-04-24 | 0 | 0 | 0 | [20 empty] | 2017-04-27 | 2017-04-13 01:00 | 2018-04-18 |  | EXP | [6 empty] | 2017-10-27 | 2017-10-27 | 2017-10-27 | Connected |  | No
National Grid | NORTH BROOKFIELD | 177892 | 1535 | 4200 | Solar | 01_552L3 | 2017-04-13 01:00 | 2017-04-14 | 4 | 4 | 0 | [10 empty] | 2017-04-21 | 2017-05-24 | 23 | 11 | 12 | [10 empty] | 2018-04-11 |  | 2021-06-07 | Yes | STD |  | 2020-09-23 | 2021-04-14 | 203 | 0 | 203 |  |  | 2021-06-04 | Connected |  | No
National Grid | NORTH BROOKFIELD | 177893 | 1535 | 2490 | Solar | 01_552L3 | 2017-04-13 01:00 | 2017-04-14 | 4 | 4 | 0 | [10 empty] | 2017-04-21 | 2017-05-24 | 23 | 11 | 12 | [10 empty] | 2018-04-11 |  | 2020-07-09 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BRIDGEWATER | 177894 | 2324 | 1950 | Solar | 07_912W55 | 2017-04-14 01:00 | 2017-04-14 | 11 | 11 | 0 | [10 empty] | 2017-05-02 | 2017-05-25 | 17 | 0 | 17 | [11 empty] | 2017-04-17 01:00 | 2019-04-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SHEFFIELD | 177925 | 1222 | 2079 | Solar | 09_1108W2 | 2017-04-17 01:00 | 2017-04-17 | 32 | 30 | 2 | [10 empty] | 2017-06-02 | 2017-08-15 | 51 | 33 | 18 | [10 empty] | 2018-02-08 |  | 2021-05-07 | Yes | STD |  | 2020-02-06 | 2020-10-01 | 239 | 9 | 230 | 2020-10-19 | 2020-10-19 | 2021-05-07 | Connected |  | No
National Grid | FALL RIVER | 177926 | 2721 | 7.6 | Solar | 05_115W53 | 2017-04-18 01:00 | 2017-04-18 | 4 | 4 | 0 | 2017-04-24 | 2017-04-24 | 0 | 0 | 0 | [20 empty] | 2017-04-27 | 2017-04-18 01:00 | 2018-04-23 |  | EXP | [6 empty] | 2017-10-26 | 2017-10-26 | 2017-10-26 | Connected |  | No
National Grid | AYER | 177928 | 1432 | 750 | Solar | 01_201W1 | 2017-04-18 01:00 | 2017-04-19 | 9 | 8 | 1 | [10 empty] | 2017-05-02 | 2017-08-01 | 63 | 47 | 16 | [10 empty] | 2018-04-30 | 2017-04-19 01:00 | 2020-06-10 | Yes | STD |  | 2019-12-06 | 2020-01-16 | 41 | 0 | 41 |  |  | 2020-06-16 | Connected |  | No
National Grid | CHELMSFORD | 177929 | 1824 | 396 | Solar | 14_24L1 | 2017-04-19 01:00 | 2017-04-19 | 9 | 8 | 1 | 2017-05-02 | 2017-06-05 | 27 | 7 | 20 | [20 empty] | 2017-06-14 |  | 2019-02-11 |  | EXP | [8 empty] | 2019-02-11 | Connected |  | No
National Grid | LEICESTER | 177930 | 1524 | 2000 | Solar | 01_21W2 | 2017-04-19 01:00 | 2017-04-20 | 235 | 234 | 1 | [27 empty] | 2018-04-25 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | EAST BRIDGEWATER | 177931 | 2333 | 7.6 | Solar | 07_797W23 | 2017-04-20 01:00 | 2017-04-20 | 7 | 7 | 0 | 2017-05-01 | 2017-05-01 | 0 | 0 | 0 | [20 empty] | 2017-05-02 |  | 2018-04-25 |  | EXP | [6 empty] | 2017-09-05 | 2017-09-05 | 2017-09-05 | Connected |  | No
National Grid | FALL RIVER | 177932 | 2720 | 180 | Solar | 05_28W41 | 2017-04-20 01:00 | 2017-04-20 | 14 | 13 | 1 | 2017-05-10 | 2017-05-10 | 0 | 0 | 0 | 2017-06-29 | 2017-07-27 | 19 | 1 | 18 | [5 empty] | 2017-06-29 | 2017-07-27 | 19 | 1 | 18 | [5 empty] | 2017-09-20 |  | 2018-04-25 |  | EXP | [6 empty] | 2017-12-08 | 2017-12-08 | 2017-12-15 | Connected |  | No
National Grid | NORTH BILLERICA | 177965 | 1862 | 480 | Solar | 14_70L1 | 2017-04-21 01:00 | 2017-04-24 | 25 | 22 | 3 | 2017-05-30 | 2018-03-26 | 189 | 46 | 143 | 2017-10-05 | 2017-11-17 | 24 | 0 | 24 | [5 empty] | 2017-10-05 | 2017-11-17 | 24 | 0 | 24 | [7 empty] | 2018-04-29 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTHBOROUGH | 177966 | 1532 | 480 | Solar | 05_313W3 | 2017-04-21 01:00 | 2017-04-24 | 197 | 194 | 3 | [26 empty] | 2017-04-24 01:00 | 2018-04-29 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FRANKLIN | 177968 | 2038 | 10 | Solar | 05_341W1 | 2017-04-24 01:00 | 2017-04-24 | 26 | 26 | 0 | 2017-05-31 | 2017-05-31 | 0 | 0 | 0 | [20 empty] | 2017-06-01 | 2017-04-25 01:00 | 2018-04-29 | Yes | EXP |  | 2017-08-29 | 2017-09-08 | 7 | 0 | 7 | 2017-10-24 | 2017-10-24 | 2017-10-24 | Connected |  | No
National Grid | WESTBOROUGH | 177970 | 1581 | 414 | Solar | 05_314W4 | 2017-04-25 01:00 | 2017-04-26 | 28 | 26 | 2 | 2017-06-06 | 2017-06-06 | 0 | 0 | 0 | [20 empty] | 2017-07-13 | 2017-04-26 01:00 | 2017-05-01 | Yes | EXP |  | 2017-09-22 | 2017-10-13 | 14 | 0 | 14 | 2017-11-27 | 2017-11-27 | 2017-11-27 | Connected |  | No
National Grid | QUINCY | 178001 | 2169 | 86.4 | Solar | 07_1W6 | 2017-04-26 01:00 | 2017-04-27 | 1 | 1 | 0 | 2017-04-28 | 2017-04-28 | 0 | 0 | 0 | [20 empty] | 2017-05-01 |  | 2018-05-02 | Yes | EXP |  | 2018-01-29 | 2018-02-07 | 7 | 0 | 7 | 2018-04-04 | 2018-04-04 | 2018-04-10 | Connected |  | No
National Grid | QUINCY | 178002 | 2169 | 66.6 | Solar | 07_3W3 | 2017-04-26 01:00 | 2017-04-27 | 1 | 1 | 0 | 2017-04-28 | 2017-04-28 | 0 | 0 | 0 | [20 empty] | 2017-05-01 | 2017-04-26 01:00 | 2018-05-02 |  | EXP | [6 empty] | 2018-03-22 | 2018-03-22 | 2018-04-10 | Connected |  | No
National Grid | CHARLTON | 178003 | 1507 | 4500 | Solar | 01_415L1 | 2017-04-26 01:00 | 2017-04-27 | 17 | 0 | 17 | [10 empty] | 2017-05-22 | 2017-06-13 | 15 | 0 | 15 | [10 empty] | 2018-05-25 |  | 2020-08-24 | Yes | STD |  | 2020-02-26 | 2020-08-24 | 180 | 0 | 180 |  |  | 2020-08-24 | Connected |  | No
National Grid | CHARLTON | 178004 | 1507 | 3500 | Solar | 01_415L1 | 2017-04-26 01:00 | 2017-04-27 | 17 | 14 | 3 | [10 empty] | 2017-05-22 | 2017-06-13 | 15 | 2 | 13 | [12 empty] | 2018-05-02 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | UPTON | 178005 | 1568 | 15.2 | Solar | 05_312W4 | 2017-04-27 01:00 | 2017-04-27 | 8 | 8 | 0 | 2017-05-09 | 2017-05-09 | 0 | 0 | 0 | [20 empty] | 2017-05-09 |  | 2018-05-02 |  | EXP | [6 empty] | 2017-08-24 | 2017-08-24 | 2017-08-29 | Connected |  | No
National Grid | SWANSEA | 178006 | 2777 | 20 | Solar | 05_11W82 | 2017-04-28 01:00 | 2017-04-28 | 10 | 10 | 0 | 2017-05-12 | 2017-05-12 | 0 | 0 | 0 | [20 empty] | 2017-05-16 |  | 2018-05-03 |  | EXP | [6 empty] | 2017-08-02 | 2017-08-02 | 2017-08-08 | Connected |  | No
National Grid | SWANSEA | 178007 | 2777 | 15 | Solar | 05_11W82 | 2017-04-28 01:00 | 2017-04-28 | 10 | 10 | 0 | 2017-05-12 | 2017-05-12 | 0 | 0 | 0 | [20 empty] | 2017-05-15 | 2017-04-28 01:00 | 2018-05-03 |  | EXP | [6 empty] | 2017-08-02 | 2017-08-02 | 2017-08-07 | Connected |  | No
National Grid | SOUTH EASTON | 178008 | 2375 | 990 | Solar | 07_92W79 | 2017-04-28 01:00 | 2017-04-28 | 8 | 0 | 8 | [10 empty] | 2017-05-10 | 2017-06-27 | 34 | 19 | 15 | [10 empty] | 2018-05-23 | 2017-04-28 01:00 | 2019-12-31 | Yes | STD |  | 2019-01-24 | 2019-02-06 | 13 | 0 | 13 | 2019-09-03 | 2019-09-03 | 2019-12-31 | Connected |  | No
National Grid | GOSHEN | 178009 | 1032 | 3995 | Solar | 09_909W3 | 2017-04-28 01:00 | 2017-05-01 | 15 | 11 | 4 | [10 empty] | 2017-05-22 | 2017-06-07 | 11 | 0 | 11 | [10 empty] | 2017-12-01 |  | 2019-06-10 | Yes | STD | [8 empty] | 2019-05-03 | Connected |  | No
National Grid | GOSHEN | 178010 | 1032 | 1000 | Solar | 09_909W3 | 2017-04-28 01:00 | 2017-05-01 | 15 | 11 | 4 | [10 empty] | 2017-05-22 | 2017-06-07 | 11 | 0 | 11 | [12 empty] | 2018-05-06 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | EAST LONGMEADOW | 178041 | 1028 | 17.6 | Solar | 09_508L4 | 2017-05-01 01:00 | 2017-05-01 | 13 | 13 | 0 | 2017-05-18 | 2017-05-18 | 0 | 0 | 0 | [20 empty] | 2017-05-22 | 2017-05-01 01:00 | 2018-05-06 |  | EXP | [6 empty] | 2017-08-09 | 2017-08-09 | 2017-08-09 | Connected |  | No
National Grid | STOUGHTON | 178042 | 2072 | 960 | Solar | 07_75W7 | 2017-05-01 01:00 | 2017-05-01 | 15 | 13 | 2 | [5 empty] | 2017-07-12 | 2017-07-27 | 11 | 0 | 11 | 2017-05-22 | 2017-06-16 | 18 | 4 | 14 | 2017-07-12 | 2017-07-27 | 11 | 0 | 11 | [5 empty] | 2017-10-27 |  | 2020-07-31 | Yes | STD |  | 2019-08-20 | 2020-06-03 | 286 | 0 | 286 | 2020-06-04 | 2020-06-04 | 2020-08-04 | Connected |  | No
National Grid | ATTLEBORO | 178043 | 2703 | 1382 | Solar | 05_9L6 | 2017-05-03 01:00 | 2017-05-04 | 2 | 0 | 2 | [10 empty] | 2017-05-08 | 2017-05-30 | 15 | 0 | 15 | [10 empty] | 2017-11-29 |  | 2019-02-15 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 178044 | 1507 | 4900 | Solar | 01_413L4 | 2017-05-04 01:00 | 2017-05-05 | 3 | 1 | 2 | [10 empty] | 2017-05-10 | 2017-06-02 | 16 | 0 | 16 | [12 empty] | 2018-05-10 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | RANDOLPH | 178045 | 2368 | 51.75 | Solar | 07_97W4 | 2017-05-05 01:00 | 2017-05-05 | 14 | 13 | 1 | 2017-05-25 | 2017-05-25 | 0 | 0 | 0 | [20 empty] | 2017-05-26 |  | 2018-05-10 |  | EXP | [6 empty] | 2017-09-29 | 2017-09-29 | 2017-10-04 | Connected |  | No
National Grid | SWANSEA | 178046 | 2777 | 3.8 | Solar | 05_11W84 | 2017-05-05 01:00 | 2017-05-05 | 2 | 2 | 0 | 2017-05-09 | 2017-05-09 | 0 | 0 | 0 | [20 empty] | 2017-05-10 | 2017-05-05 01:00 | 2018-05-10 |  | EXP | [6 empty] | 2017-10-27 | 2017-10-27 | 2017-10-27 | Connected |  | No
National Grid | WORCESTER | 178047 | 1610 | 800 | Solar | 01_HT22 | 2017-05-05 01:00 | 2017-05-08 | 15 | 13 | 2 | [10 empty] | 2017-05-30 | 2017-06-15 | 12 | 0 | 12 | [5 empty] | 2018-01-18 | 2020-04-06 | 556 | 0 | 556 | 2018-02-15 | 2017-05-05 01:00 | 2021-06-17 | Yes | STD |  | 2020-10-16 | 2021-04-21 | 187 | 0 | 187 |  |  | 2021-06-02 | Connected |  | No
National Grid | NORTHBOROUGH | 178048 | 1532 | 750 | Solar | 05_318W1 | 2017-05-05 01:00 | 2017-05-08 | 15 | 13 | 2 | [10 empty] | 2017-05-30 | 2017-06-15 | 12 | 0 | 12 | [5 empty] | 2018-01-16 | 2019-10-25 | 449 | 20 | 429 | 2018-12-21 |  | 2021-02-19 | Yes | STD |  | 2020-01-04 | 2020-12-16 | 347 | 5 | 342 |  |  | 2021-02-12 | Connected |  | No
National Grid | STOUGHTON | 178049 | 2072 | 56 | Solar | 07_913W17 | 2017-05-05 01:00 | 2017-05-08 | 43 | 42 | 1 | 2017-07-10 | 2017-07-10 | 0 | 0 | 0 | [20 empty] | 2017-07-17 |  | 2018-05-13 |  | EXP | [6 empty] | 2017-09-08 | 2017-09-08 | 2017-10-30 | Connected |  | No
National Grid | NORTHBRIDGE | 178078 | 1534 | 3220 | Solar | 05_320W5 | 2017-05-05 01:00 | 2017-05-08 | 13 | 0 | 13 | [10 empty] | 2017-05-25 | 2017-06-15 | 14 | 0 | 14 | [10 empty] | 2018-05-02 | 2017-05-05 01:00 | 2021-10-08 |  | STD | [8 empty] | 2021-12-30 | Connected |  | No
National Grid | SPENCER | 178079 | 1562 | 2200 | Solar | 01_552L1 | 2017-05-05 01:00 | 2017-05-08 | 76 | 75 | 1 | [10 empty] | 2017-08-24 | 2017-09-28 | 24 | 9 | 15 | [10 empty] | 2018-04-17 |  | 2024-08-30 | Yes | STD |  | 2020-02-21 |  | 1516 | 15 | 1501 |  |  |  | Construction |  | No
National Grid | WORCESTER | 184789 | 1608 | 249.8 | Solar | 01_4J324 | 2017-05-08 | 2018-05-09 | 19 | 0 | 19 | [5 empty] | 2018-08-23 | 2019-03-12 | 135 | 21 | 114 | [5 empty] | 2018-08-23 | 2019-03-12 | 135 | 21 | 114 | [6 empty] | 2017-05-08 01:00 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | DIGHTON | 178080 | 2715 | 2800 | Solar | 05_19W72 | 2017-05-08 01:00 | 2017-05-19 | 121 | 121 | 0 | [10 empty] | 2017-11-08 | 2017-11-29 | 13 | 0 | 13 | [10 empty] | 2018-07-05 | 2017-05-08 01:00 | 2020-12-02 | Yes | STD |  | 2019-10-12 | 2020-09-21 | 346 | 126 | 220 |  |  | 2020-12-07 | Connected |  | No
National Grid | FALL RIVER | 178081 | 2721 | 10 | Solar | 05_115W52 | 2017-05-08 01:00 | 2017-05-09 | 6 | 6 | 0 | 2017-05-17 | 2017-05-17 | 0 | 0 | 0 | [20 empty] | 2017-05-18 | 2017-05-08 01:00 | 2018-05-14 |  | EXP |  | 2017-10-23 | 2017-11-09 | 8 | 0 | 8 | 2017-11-09 | 2017-11-09 | 2017-11-28 | Connected |  | No
National Grid | ORANGE | 178085 | 1364 | 4995 | Solar | 09_705W3 | 2017-05-08 01:00 | 2017-05-10 | 16 | 14 | 2 | [10 empty] | 2017-06-02 | 2017-06-26 | 16 | 0 | 16 | [10 empty] | 2018-01-08 | 2017-05-08 01:00 | 2021-10-27 | Yes | STD |  | 2021-07-30 | 2021-09-24 | 57 | 3 | 54 |  |  | 2021-10-27 | Connected |  | No
National Grid | ORANGE | 178086 | 1364 | 4995 | Solar | 09_705W3 | 2017-05-08 01:00 | 2017-05-10 | 16 | 14 | 2 | [10 empty] | 2017-06-02 | 2017-06-26 | 16 | 0 | 16 | [10 empty] | 2018-01-08 |  | 2021-10-27 | Yes | STD |  | 2021-07-30 | 2021-09-24 | 57 | 3 | 54 |  |  | 2021-10-27 | Connected |  | No
National Grid | DRACUT | 178082 | 1826 | 16.08 | Solar | 14_78L1 | 2017-05-09 01:00 | 2017-05-09 | 195 | 195 | 0 | [27 empty] | 2018-05-14 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | PALMER | 178083 | 1069 | 5000 | Solar | 09_503L4 | 2017-05-09 01:00 | 2017-05-09 | 17 | 14 | 3 | [10 empty] | 2017-06-02 | 2017-06-30 | 20 | 3 | 17 | [11 empty] | 2017-05-09 01:00 | 2018-05-14 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH BROOKFIELD | 178087 | 1535 | 4300 | Solar | 01_0012 | 2017-05-09 01:00 | 2017-05-10 | 18 | 16 | 2 | [10 empty] | 2017-06-06 | 2017-08-28 | 58 | 49 | 9 | [10 empty] | 2018-02-09 | 2017-05-09 01:00 | 2022-01-10 | Yes | STD |  | 2020-06-17 | 2021-10-11 | 380 | 5 | 375 | 2021-11-16 | 2021-11-16 | 2021-12-30 | Connected |  | No
National Grid | NORTH BROOKFIELD | 178116 | 1535 | 1500 | Solar | 01_0012 | 2017-05-09 01:00 | 2017-05-10 | 16 | 14 | 2 | [10 empty] | 2017-06-02 | 2017-08-28 | 60 | 49 | 11 | [10 empty] | 2018-02-08 |  | 2021-10-16 | Yes | STD | [8 empty] | 2021-10-04 | Connected |  | No
National Grid | PEPPERELL | 178118 | 1463 | 10 | Solar | 01_226L2 | 2017-05-11 01:00 | 2017-05-11 | 4 | 4 | 0 | 2017-05-17 | 2018-02-14 | 181 | 0 | 181 | [20 empty] | 2017-05-18 |  | 2018-05-16 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | QUINCY | 178119 | 2169 | 300 | Natural Gas | 07_11W4 | 2017-05-11 01:00 | 2017-05-11 | 35 | 31 | 4 | 2017-06-30 | 2017-09-25 | 101 | 42 | 59 | [20 empty] | 2017-09-25 |  | 2018-05-16 |  | EXP | [8 empty] | 2018-09-14 | Connected |  | No
National Grid | BELCHERTOWN | 178120 | 1007 | 3960 | Solar | 09_527L1 | 2017-05-11 01:00 | 2017-05-12 | 219 | 218 | 1 | [27 empty] | 2018-05-17 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BILLERICA | 177548 | 1821 | 11.4 | Solar | 14_18L2 | 2017-05-12 01:00 | 2017-05-15 | 5 | 5 | 0 | 2017-05-22 | 2017-05-22 | 0 | 0 | 0 | [20 empty] | 2017-05-22 |  | 2018-05-20 |  | EXP | [6 empty] | 2017-11-28 | 2017-11-28 | 2017-11-28 | Connected |  | No
National Grid | HANCOCK | 178121 | 1237 | 2058 | Solar | 09_1003W2 | 2017-05-12 01:00 | 2017-05-12 | 168 | 167 | 1 | [27 empty] | 2018-05-17 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HAMPDEN | 178122 | 1036 | 3480 | Solar | 09_139L1 | 2017-05-12 01:00 | 2017-05-12 | 42 | 0 | 42 | [10 empty] | 2017-07-13 | 2017-08-03 | 15 | 0 | 15 | [10 empty] | 2018-04-12 |  | 2019-07-05 |  | STD |  | 2019-04-13 | 2019-10-15 | 185 | 0 | 185 |  |  | 2019-11-27 | Connected |  | No
National Grid | SAUGUS | 178123 | 1906 | 300 | Natural Gas | 12_25W3 | 2017-05-12 01:00 | 2017-05-31 | 22 | 19 | 3 | 2017-06-14 | 2017-07-11 | 18 | 0 | 18 | [20 empty] | 2017-07-11 |  | 2018-09-07 |  | EXP | [8 empty] | 2018-08-14 | Connected |  | No
National Grid | SWANSEA | 178125 | 2777 | 3.8 | Solar | 05_19W73 | 2017-05-12 01:00 | 2017-05-15 | 5 | 5 | 0 | 2017-05-22 | 2017-05-22 | 0 | 0 | 0 | [20 empty] | 2017-05-22 |  | 2018-05-20 |  | EXP | [6 empty] | 2017-11-07 | 2017-11-07 | 2017-11-07 | Connected |  | No
National Grid | SEEKONK | 177549 | 2771 | 7.6 | Solar | 05_9L5 | 2017-05-15 01:00 | 2017-05-16 | 6 | 5 | 1 | 2017-05-24 | 2017-05-24 | 0 | 0 | 0 | [20 empty] | 2017-05-24 |  | 2018-05-21 |  | EXP | [6 empty] | 2018-02-15 | 2018-02-15 | 2018-02-15 | Connected |  | No
National Grid | BILLERICA | 177550 | 1821 | 10 | Solar | 14_70L5 | 2017-05-15 01:00 | 2017-05-16 | 4 | 3 | 1 | 2017-05-22 | 2018-03-13 | 189 | 0 | 189 | [20 empty] | 2017-05-23 |  | 2018-05-21 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SAUGUS | 177551 | 1906 | 3.8 | Solar | 12_19W1 | 2017-05-15 01:00 | 2017-05-16 | 6 | 5 | 1 | 2017-05-24 | 2018-03-02 | 187 | 0 | 187 | [20 empty] | 2017-05-24 | 2017-05-15 01:00 | 2018-05-21 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 177552 | 1507 | 3500 | Solar | 01_415L2 | 2017-05-15 01:00 | 2017-05-16 | 18 | 15 | 3 | [10 empty] | 2017-06-12 | 2017-07-14 | 23 | 6 | 17 | [10 empty] | 2018-03-01 | 2017-05-15 01:00 | 2022-12-20 | Yes | STD | [8 empty] | 2022-12-19 | Connected |  | No
National Grid | MILLBURY | 178124 | 1527 | 1000 | Solar | 01_304W4 | 2017-05-15 01:00 | 2017-05-15 | 18 | 14 | 4 | [10 empty] | 2017-06-09 | 2017-07-03 | 16 | 0 | 16 | [10 empty] | 2017-11-09 |  | 2019-06-28 | Yes | STD |  | 2018-12-13 | 2019-05-23 | 161 | 0 | 161 |  |  | 2019-06-27 | Connected |  | No
National Grid | BLACKSTONE | 177554 | 1504 | 15.2 | Solar | 05_321W9 | 2017-05-16 01:00 | 2017-05-17 | 3 | 3 | 0 | 2017-05-22 | 2017-05-22 | 213 | 0 | 213 | [20 empty] | 2017-05-22 | 2017-05-16 01:00 | 2020-01-07 |  | EXP | [8 empty] | 2020-01-03 | Connected |  | No
National Grid | BROCKTON | 177555 | 2302 | 10 | Solar | 07_911W56 | 2017-05-16 01:00 | 2017-05-17 | 1 | 1 | 0 | 2017-05-18 | 2017-05-18 | 0 | 0 | 0 | [20 empty] | 2017-05-22 | 2017-05-16 01:00 | 2018-05-22 | Yes | EXP |  | 2017-08-28 | 2017-09-09 | 9 | 0 | 9 | 2017-11-08 | 2017-11-08 | 2017-11-28 | Connected |  | No
National Grid | SHUTESBURY | 177556 | 1072 | 10 | Solar | 09_704W1 | 2017-05-16 01:00 | 2017-05-17 | 6 | 6 | 0 | 2017-05-25 | 2017-05-25 | 0 | 0 | 0 | [20 empty] | 2017-05-26 |  | 2018-05-22 | Yes | EXP |  | 2017-07-18 | 2017-07-26 | 6 | 0 | 6 | 2017-12-13 | 2017-12-13 | 2017-12-13 | Connected |  | Yes
National Grid | WORCESTER | 177587 | 1606 | 300 | Natural Gas | 01_HT45 | 2017-05-17 01:00 | 2017-05-18 | 18 | 15 | 3 | 2017-06-14 | 2017-06-14 | 0 | 0 | 0 | [20 empty] | 2017-07-07 |  | 2018-05-23 |  | EXP | [6 empty] | 2018-04-12 | 2018-04-12 | 2018-04-12 | Connected |  | No
National Grid | NORTHAMPTON | 177588 | 1060 | 4980 | Solar | 09_901W1 | 2017-05-17 01:00 | 2017-05-18 | 5 | 2 | 3 | [10 empty] | 2017-05-25 | 2017-06-23 | 20 | 6 | 14 | [11 empty] | 2017-05-18 01:00 | 2018-05-23 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MILFORD | 177589 | 1757 | 7.6 | Solar | 05_335W2 | 2017-05-18 01:00 | 2017-05-19 | 11 | 11 | 0 | 2017-06-06 | 2017-06-06 | 0 | 0 | 0 | [20 empty] | 2017-06-08 |  | 2018-05-24 |  | EXP |  | 2017-08-29 | 2017-10-12 | 30 | 0 | 30 | 2017-11-08 | 2017-11-08 | 2017-11-28 | Connected |  | No
National Grid | FLORENCE | 177590 | 1062 | 6 | Solar | 09_909W1 | 2017-05-18 01:00 | 2017-05-22 | 63 | 63 | 0 | 2017-08-21 | 2017-08-21 | 0 | 0 | 0 | [20 empty] | 2017-08-28 |  | 2018-05-27 |  | EXP | [6 empty] | 2018-02-15 | 2018-02-15 | 2018-02-15 | Connected |  | No
National Grid | WORCESTER | 177592 | 1605 | 339.7 | Solar | 01_24W2 | 2017-05-21 01:00 | 2017-05-22 | 37 | 33 | 4 | 2017-07-14 | 2017-07-14 | 0 | 0 | 0 | [20 empty] | 2017-08-22 | 2017-05-22 01:00 | 2018-05-27 |  | EXP | [6 empty] | 2018-02-12 | 2018-02-12 | 2018-02-12 | Connected |  | No
National Grid | GARDNER | 177593 | 1440 | 4990 | Solar | 01_607W5 | 2017-05-22 01:00 | 2017-05-23 | 16 | 15 | 1 | [10 empty] | 2017-06-15 | 2017-07-24 | 26 | 10 | 16 | [10 empty] | 2018-03-01 |  | 2020-12-31 | Yes | STD |  | 2020-07-11 | 2020-12-01 | 173 | 5 | 168 |  |  | 2020-12-31 | Connected |  | No
National Grid | WORCESTER | 177625 | 1607 | 1800 | Solar | 01_8W1 | 2017-05-23 01:00 | 2017-05-23 | 12 | 11 | 1 | [10 empty] | 2017-06-09 | 2017-07-03 | 16 | 0 | 16 | [12 empty] | 2018-05-28 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | RANDOLPH | 177626 | 2368 | 10 | Solar | 07_97W3 | 2017-05-23 01:00 | 2017-05-24 | 3 | 3 | 0 | 2017-05-30 | 2017-06-01 | 208 | 0 | 208 | [20 empty] | 2017-06-01 | 2017-05-23 01:00 | 2018-05-29 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTHAMPTON | 177630 | 1060 | 80.5 | Solar | 09_901W2 | 2017-05-23 01:00 | 2017-05-24 | 2 | 0 | 2 | 2017-05-26 | 2017-06-01 | 3 | 0 | 3 | [20 empty] | 2017-06-01 | 2017-05-24 01:00 | 2018-05-29 |  | EXP |  | 2017-02-28 | 2017-08-08 | 112 | 0 | 112 |  |  | 2018-05-17 | Connected |  | No
National Grid | SOUTH EASTON | 177631 | 2375 | 296 | Solar | 07_92W54 | 2017-05-24 01:00 | 2017-05-31 | 22 | 22 | 0 | 2017-06-29 | 2017-07-19 | 186 | 8 | 178 | 2017-08-07 | 2017-08-29 | 16 | 1 | 15 | [5 empty] | 2017-08-07 | 2017-08-29 | 16 | 1 | 15 | [5 empty] | 2017-09-20 | 2017-05-24 01:00 | 2018-08-30 | Yes | EXP |  | 2018-02-21 | 2018-04-17 | 27 | 0 | 27 |  |  | 2018-08-16 | Connected |  | No
National Grid | BELLINGHAM | 177664 | 2019 | 15.2 | Solar | 05_108W51 | 2017-05-24 01:00 | 2017-05-25 | 2 | 2 | 0 | 2017-05-30 | 2017-05-30 | 0 | 0 | 0 | [20 empty] | 2017-06-01 | 2017-05-24 01:00 | 2018-05-30 |  | EXP |  | 2017-10-24 | 2017-11-15 | 10 | 0 | 10 | 2017-12-15 | 2017-12-15 | 2017-12-27 | Connected |  | Yes
National Grid | GRANBY | 177665 | 1033 | 7.6 | Solar | 09_527L1 | 2017-05-24 01:00 | 2017-05-25 | 5 | 5 | 0 | 2017-06-02 | 2017-06-06 | 0 | 0 | 0 | [20 empty] | 2017-06-05 |  | 2018-08-31 | Yes | EXP |  | 2018-01-30 | 2018-02-12 | 9 | 0 | 9 |  |  | 2018-06-11 | Connected |  | No
National Grid | WEYMOUTH | 177666 | 2191 | 3.8 | Solar | 07_6W2 | 2017-05-24 01:00 | 2017-05-25 | 3 | 3 | 0 | 2017-05-31 | 2017-06-01 | 207 | 0 | 207 | [20 empty] | 2017-06-01 | 2017-05-24 01:00 | 2018-05-30 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BLACKSTONE | 177667 | 1504 | 10 | Solar | 05_108W60 | 2017-05-24 01:00 | 2017-05-25 | 3 | 3 | 0 | 2017-05-31 | 2017-05-31 | 0 | 0 | 0 | [20 empty] | 2017-06-01 | 2017-05-25 01:00 | 2018-05-30 | Yes | EXP |  | 2017-10-02 | 2017-11-30 | 35 | 0 | 35 | 2017-12-20 | 2017-12-20 | 2018-01-05 | Connected |  | No
National Grid | CHARLTON | 177669 | 1507 | 2000 | Solar | 01_406L3 | 2017-05-25 01:00 | 2017-05-26 | 2 | 0 | 2 | [10 empty] | 2017-05-31 | 2017-06-26 | 18 | 0 | 18 | [10 empty] | 2018-05-21 |  | 2020-06-29 | Yes | STD |  | 2019-12-12 | 2020-06-12 | 183 | 0 | 183 |  |  | 2020-06-29 | Connected |  | No
National Grid | WARREN | 177670 | 1083 | 3000 | Solar | 09_516L1 | 2017-05-25 01:00 | 2017-05-26 | 2 | 0 | 2 | [10 empty] | 2017-05-31 | 2017-06-15 | 11 | 0 | 11 | [10 empty] | 2018-06-08 |  | 2020-08-27 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SPENCER | 177671 | 1562 | 2000 | Solar | 01_2236W3 | 2017-05-25 01:00 | 2017-05-26 | 4 | 3 | 1 | [10 empty] | 2017-06-02 | 2017-06-29 | 19 | 3 | 16 | [11 empty] | 2017-05-25 01:00 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | UXBRIDGE | 177672 | 1569 | 2000 | Solar | 05_321W9 | 2017-05-25 01:00 | 2017-05-26 | 6 | 5 | 1 | [10 empty] | 2017-06-06 | 2017-07-07 | 22 | 4 | 18 | [10 empty] | 2017-12-28 | 2017-05-25 01:00 | 2020-05-01 | Yes | STD |  | 2019-04-03 | 2020-02-07 | 309 | 0 | 309 | 2020-02-10 | 2020-02-10 | 2020-03-31 | Connected |  | No
National Grid | ATTLEBORO | 177702 | 2763 | 3469 | Solar | 05_2274 | 2017-05-25 01:00 | 2017-05-26 | 54 | 53 | 1 | [10 empty] | 2017-08-14 | 2017-09-01 | 14 | 0 | 14 | [10 empty] | 2018-09-18 | 2017-05-25 01:00 | 2020-12-31 | Yes | STD | [8 empty] | 2020-12-31 | Connected |  | No
National Grid | WARREN | 177703 | 1083 | 1500 | Solar | 01_408L2 | 2017-05-25 01:00 | 2017-05-26 | 2 | 0 | 2 | [10 empty] | 2017-05-31 | 2017-06-21 | 15 | 0 | 15 | [10 empty] | 2018-10-02 | 2017-05-26 01:00 | 2020-06-15 | Yes | STD |  | 2019-10-03 | 2019-12-27 | 85 | 0 | 85 |  |  | 2020-06-15 | Connected |  | No
National Grid | SOUTHBRIDGE | 177747 | 1550 | 2500 | Solar | 01_413L8 | 2017-05-26 01:00 | 2017-06-01 | 6 | 4 | 2 | [10 empty] | 2017-06-09 | 2017-07-07 | 19 | 2 | 17 | [10 empty] | 2018-02-14 | 2017-05-26 01:00 | 2020-12-31 | Yes | STD |  | 2020-07-15 | 2020-12-02 | 141 | 5 | 136 | 2020-12-14 | 2020-12-14 | 2020-12-30 | Connected |  | No
National Grid | SOUTHBRIDGE | 177748 | 1550 | 1500 | Solar | 01_413L3 | 2017-05-26 01:00 | 2017-06-01 | 6 | 4 | 2 | [10 empty] | 2017-06-09 | 2017-07-07 | 19 | 2 | 17 | [10 empty] | 2018-02-14 | 2017-05-30 01:00 | 2020-10-31 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | SWANSEA | 177710 | 2777 | 7.6 | Solar | 05_11W81 | 2017-05-30 01:00 | 2017-05-30 | 7 | 7 | 0 | 2017-06-08 | 2017-06-08 | 0 | 0 | 0 | [20 empty] | 2017-06-09 |  | 2018-06-04 |  | EXP |  | 2017-09-28 | 2017-10-13 | 10 | 0 | 10 | 2017-10-25 | 2017-10-25 | 2017-10-30 | Connected |  | No
National Grid | LEICESTER | 177741 | 1524 | 1740 | Solar | 01_406L1 | 2017-05-30 01:00 | 2017-05-31 | 105 | 100 | 5 | [10 empty] | 2017-11-01 | 2017-12-06 | 20 | 9 | 11 | [11 empty] | 2017-05-30 01:00 | 2018-06-05 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ATHOL | 177742 | 1331 | 200 | Solar | 09_702W3 | 2017-05-30 01:00 | 2017-07-03 | 32 | 29 | 3 | 2017-07-17 | 2017-08-21 | 25 | 2 | 23 | 2017-09-05 | 2017-10-03 | 0 | 0 | 0 | [5 empty] | 2017-09-05 | 2017-10-03 | 0 | 0 | 0 | [5 empty] | 2017-10-24 |  | 2018-09-21 |  | EXP | [8 empty] | 2018-09-11 | Connected |  | No
National Grid | NORTH BROOKFIELD | 177743 | 1535 | 5 | Solar | 01_525L1 | 2017-05-31 01:00 | 2017-06-01 | 47 | 47 | 0 | 2017-08-08 | 2017-08-08 | 0 | 0 | 0 | [20 empty] | 2017-08-23 |  | 2018-05-31 |  | EXP | [6 empty] | 2017-12-19 | 2017-12-19 | 2017-12-20 | Connected |  | No
National Grid | NORTH BROOKFIELD | 177746 | 1535 | 15 | Solar | 01_525L1 | 2017-05-31 01:00 | 2017-05-31 | 48 | 48 | 0 | 2017-08-08 | 2017-08-08 | 0 | 0 | 0 | [20 empty] | 2017-08-23 | 2017-05-31 01:00 | 2018-06-05 |  | EXP | [6 empty] | 2017-12-26 | 2017-12-26 | 2017-12-26 | Connected |  | No
National Grid | WARE | 177782 | 1082 | 1320 | Solar | 09_501L2 | 2017-05-31 01:00 | 2017-06-01 | 14 | 12 | 2 | [10 empty] | 2017-06-21 | 2017-07-11 | 13 | 0 | 13 | [10 empty] | 2017-12-07 | 2017-06-01 01:00 | 2021-12-16 | Yes | STD |  | 2019-11-27 | 2021-03-03 | 463 | 6 | 457 | 2021-11-17 | 2021-11-17 | 2021-12-10 | Connected |  | No
National Grid | WILLIAMSBURG | 177781 | 1096 | 8.8 | Solar | 09_909W3 | 2017-06-01 01:00 | 2017-06-01 | 4 | 4 | 0 | 2017-06-07 | 2017-06-07 | 0 | 0 | 0 | [20 empty] | 2017-06-08 |  | 2018-06-06 | Yes | EXP |  | 2017-08-24 | 2017-08-28 | 2 | 0 | 2 | 2017-09-01 | 2017-09-01 | 2017-09-01 | Connected |  | No
National Grid | BELCHERTOWN | 177784 | 1007 | 3.8 | Solar | 09_527L2 | 2017-06-01 01:00 | 2017-06-02 | 6 | 6 | 0 | 2017-06-12 | 2017-06-29 | 13 | 0 | 13 | [20 empty] | 2017-06-13 |  | 2018-06-07 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SOUTHBOROUGH | 177785 | 1772 | 56 | Solar | 05_314W2 | 2017-06-01 01:00 | 2017-06-02 | 4 | 3 | 1 | 2017-06-08 | 2017-06-08 | 0 | 0 | 0 | [20 empty] | 2017-06-09 | 2017-06-01 01:00 | 2018-06-07 |  | EXP | [6 empty] | 2018-03-22 | 2018-03-22 | 2018-04-02 | Connected |  | No
National Grid | MARLBOROUGH | 177786 | 1752 | 3.8 | Solar | 05_311W2 | 2017-06-01 01:00 | 2017-06-02 | 7 | 5 | 2 | 2017-06-13 | 2017-06-13 | 198 | 0 | 198 | [20 empty] | 2017-06-13 |  | 2018-12-28 |  | EXP | [8 empty] | 2018-10-26 | Connected |  | No
National Grid | NORTON | 177787 | 2766 | 3.8 | Solar | 05_8L2 | 2017-06-01 01:00 | 2017-06-02 | 3 | 3 | 0 | 2017-06-07 | 2017-06-08 | 202 | 0 | 202 | [20 empty] | 2017-06-08 | 2017-06-02 01:00 | 2018-06-07 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | REHOBOTH | 177788 | 2769 | 7.6 | Solar | 05_8L4 | 2017-06-02 01:00 | 2017-06-02 | 13 | 13 | 0 | 2017-06-21 | 2017-06-21 | 0 | 0 | 0 | [20 empty] | 2017-06-23 | 2017-06-05 01:00 | 2018-06-07 |  | EXP |  | 2017-08-24 | 2017-09-19 | 17 | 0 | 17 | 2017-09-19 | 2017-09-19 | 2017-09-27 | Connected |  | No
National Grid | WEST BROOKFIELD | 177789 | 1585 | 4500 | Solar | 01_525L2 | 2017-06-05 01:00 | 2017-06-06 | 4 | 4 | 0 | [10 empty] | 2017-06-12 | 2017-07-05 | 16 | 0 | 16 | [10 empty] | 2018-02-06 |  | 2020-07-15 | Yes | STD |  | 2019-06-28 | 2020-06-01 | 339 | 0 | 339 |  |  | 2020-07-14 | Connected |  | No
National Grid | ATTLEBORO | 177821 | 2703 | 300 | Natural Gas | 05_9L5 | 2017-06-05 01:00 | 2017-06-07 | 6 | 6 | 0 | 2017-06-15 | 2017-06-15 | 0 | 0 | 0 | [20 empty] | 2017-07-10 |  | 2018-02-28 |  | EXP | [6 empty] | 2018-03-22 | 2018-03-22 | 2018-03-29 | Connected |  | No
National Grid | SEEKONK | 177822 | 2771 | 300 | Natural Gas | 05_7L2 | 2017-06-06 01:00 | 2017-06-07 | 6 | 0 | 6 | 2017-06-15 | 2017-06-15 | 0 | 0 | 0 | [20 empty] | 2017-07-10 |  | 2018-02-28 |  | EXP | [6 empty] | 2018-02-26 | 2018-02-26 | 2017-12-29 | Connected |  | No
National Grid | NORTH DIGHTON | 177823 | 2764 | 15.2 | Solar | 05_19W73 | 2017-06-06 01:00 | 2017-06-07 | 4 | 4 | 0 | 2017-06-13 | 2017-06-13 | 0 | 0 | 0 | [20 empty] | 2017-06-13 | 2017-06-06 01:00 | 2018-06-12 |  | EXP | [6 empty] | 2017-10-18 | 2017-10-18 | 2017-10-24 | Connected |  | Yes
National Grid | METHUEN | 177824 | 1844 | 9.6 | Solar | 14_63L1 | 2017-06-06 01:00 | 2017-06-08 | 3 | 3 | 0 | 2017-06-13 | 2017-06-13 | 0 | 0 | 0 | [20 empty] | 2017-06-13 |  | 2018-06-13 | Yes | EXP |  | 2017-08-08 | 2017-08-16 | 6 | 0 | 6 | 2018-02-14 | 2018-02-14 | 2018-02-20 | Connected |  | No
National Grid | BROCKTON | 177826 | 2302 | 60 | Solar | 07_91W48 | 2017-06-08 01:00 | 2017-06-08 | 3 | 3 | 0 | 2017-06-13 | 2017-06-13 | 0 | 0 | 0 | [20 empty] | 2017-06-16 |  | 2018-06-13 |  | EXP | [6 empty] | 2017-08-25 | 2017-08-25 | 2017-09-08 | Connected |  | No
National Grid | LYNN | 177827 | 1902 | 10 | Solar | 12_1384 | 2017-06-09 01:00 | 2017-06-09 | 7 | 0 | 7 | 2017-06-20 | 2017-09-22 | 66 | 0 | 66 | [21 empty] | 2017-06-09 01:00 | 2018-06-14 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOUTHBRIDGE | 177858 | 1550 | 2000 | Solar | 01_413L8 | 2017-06-09 01:00 | 2017-06-12 | 7 | 6 | 1 | [10 empty] | 2017-06-21 | 2017-07-12 | 14 | 0 | 14 | [10 empty] | 2018-02-14 |  | 2020-12-31 | Yes | STD |  | 2020-03-17 | 2020-12-02 | 261 | 5 | 256 | 2020-12-11 | 2020-12-11 | 2020-12-30 | Connected |  | No
National Grid | ATHOL | 177860 | 1331 | 6740 | Solar | 09_702W3 | 2017-06-13 01:00 | 2017-06-13 | 24 | 24 | 0 | [10 empty] | 2017-07-18 | 2017-08-11 | 18 | 0 | 18 | [11 empty] | 2017-06-13 01:00 | 2018-06-18 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTMINSTER | 177862 | 1473 | 9536 | Solar | 01_607W4 | 2017-06-13 01:00 | 2017-06-13 | 6 | 6 | 0 | [10 empty] | 2017-06-21 | 2017-07-19 | 19 | 3 | 16 | [10 empty] | 2019-01-24 | 2017-06-13 01:00 | 2020-06-12 | Yes | STD |  | 2019-09-13 | 2019-11-14 | 62 | 0 | 62 |  |  | 2020-06-16 | Connected |  | No
National Grid | NEWBURYPORT | 177863 | 1950 | 990 | Solar | 14_36L2 | 2017-06-13 01:00 | 2017-06-14 | 8 | 7 | 1 | [10 empty] | 2017-06-26 | 2017-07-31 | 24 | 9 | 15 | [10 empty] | 2018-03-13 |  | 2024-03-15 | Yes | STD |  | 2020-05-29 | 2021-03-31 | 306 | 5 | 301 |  |  |  | Withdrawn |  | No
National Grid | FRANKLIN | 177864 | 2038 | 60 | Solar | 05_348W7 | 2017-06-14 01:00 | 2017-06-14 | 18 | 17 | 1 | 2017-07-11 | 2017-07-11 | 0 | 0 | 0 | [20 empty] | 2017-07-17 | 2017-06-14 01:00 | 2018-06-19 |  | EXP | [6 empty] | 2017-09-07 | 2017-09-07 | 2017-09-14 | Connected |  | No
National Grid | EAST LONGMEADOW | 177865 | 1028 | 4000 | Solar | 09_508L4 | 2017-06-14 01:00 | 2017-06-15 | 144 | 144 | 0 | [10 empty] | 2018-01-11 | 2018-03-23 | 50 | 35 | 15 | [10 empty] | 2018-11-05 | 2017-06-15 01:00 |  | Yes | STD | [9 empty] | Study |  | No
National Grid | SAUGUS | 177866 | 1906 | 3.8 | Solar | 12_23W2 | 2017-06-15 01:00 | 2017-06-15 | 6 | 6 | 0 | 2017-06-23 | 2017-06-28 | 0 | 0 | 0 | [20 empty] | 2017-06-28 |  | 2018-06-20 | Yes | EXP |  | 2018-01-18 | 2018-03-28 | 37 | 0 | 37 |  |  | 2018-05-30 | Connected |  | No
National Grid | LYNN | 177896 | 1904 | 7.6 | Solar | 12_24W1 | 2017-06-15 01:00 | 2017-06-15 | 9 | 9 | 0 | 2017-06-28 | 2018-02-12 | 150 | 0 | 150 | [20 empty] | 2017-06-29 | 2017-06-15 01:00 | 2018-06-20 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BELLINGHAM | 177897 | 2019 | 10 | Solar | 05_335W1 | 2017-06-15 01:00 | 2017-06-15 | 6 | 6 | 0 | 2017-06-23 | 2017-06-23 | 0 | 0 | 0 | [20 empty] | 2017-06-28 |  | 2018-06-20 | Yes | EXP |  | 2017-10-31 | 2017-11-29 | 15 | 0 | 15 | 2017-12-20 | 2017-12-20 | 2017-12-27 | Connected |  | Yes
National Grid | BELCHERTOWN | 177898 | 1007 | 7.6 | Solar | 09_509L1 | 2017-06-15 01:00 | 2017-06-15 | 10 | 10 | 0 | 2017-06-29 | 2017-06-30 | 1 | 0 | 1 | [20 empty] | 2017-06-30 |  | 2018-06-20 |  | EXP | [8 empty] | 2018-06-01 | Connected |  | No
National Grid | HAVERHILL | 177899 | 1830 | 8.4 | Solar | 14_76L3 | 2017-06-15 01:00 | 2017-06-16 | 107 | 107 | 0 | [26 empty] | 2017-06-15 01:00 | 2018-06-21 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LANCASTER | 177900 | 1523 | 3875 | Solar | 01_227W1 | 2017-06-15 01:00 | 2017-06-16 | 22 | 22 | 0 | [10 empty] | 2017-07-19 | 2017-09-22 | 46 | 0 | 46 | [10 empty] | 2019-02-04 |  | 2021-06-18 | Yes | STD |  | 2020-11-04 | 2021-03-12 | 128 | 0 | 128 | 2021-05-20 | 2021-05-20 | 2021-06-11 | Connected |  | No
National Grid | BRIDGEWATER | 177901 | 2324 | 300 | Natural Gas | 07_912W21 | 2017-06-15 01:00 | 2017-06-16 | 6 | 6 | 0 | 2017-06-26 | 2018-01-26 | 141 | 2 | 139 | 2017-08-17 | 2017-09-14 | 19 | 0 | 19 | [5 empty] | 2017-08-17 | 2017-09-14 | 19 | 0 | 19 | [6 empty] | 2017-06-15 01:00 | 2018-06-21 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EAST LONGMEADOW | 177902 | 1028 | 4990 | Solar | 09_508L5 | 2017-06-15 01:00 | 2017-06-16 | 43 | 43 | 0 | [10 empty] | 2017-08-17 | 2017-09-21 | 24 | 8 | 16 | [10 empty] | 2019-03-05 |  | 2019-11-15 | Yes | STD |  | 2019-03-06 | 2019-04-19 | 44 | 0 | 44 |  |  | 2019-10-31 | Connected |  | No
National Grid | WORCESTER | 177934 | 1602 | 15.2 | Solar | 01_23W1 | 2017-06-19 01:00 | 2017-07-14 | 27 | 27 | 0 | 2017-07-28 | 2017-07-28 | 0 | 0 | 0 | [20 empty] | 2017-07-31 |  | 2018-06-25 |  | EXP | [6 empty] | 2018-01-25 | 2018-01-25 | 2018-01-25 | Connected |  | No
National Grid | MILFORD | 177935 | 1757 | 34.2 | Solar | 05_336W4 | 2017-06-20 01:00 | 2017-06-20 | 143 | 143 | 0 | 2018-01-24 | 2018-01-24 | 0 | 0 | 0 | [20 empty] | 2018-01-24 |  | 2018-06-25 |  | EXP | [8 empty] | 2018-04-27 | Connected |  | No
National Grid | EVERETT | 177936 | 2149 | 300 | Natural Gas | 12_2338 | 2017-06-20 01:00 | 2017-06-20 | 4 | 0 | 4 | 2017-06-26 | 2017-08-01 | 26 | 26 | 0 | [20 empty] | 2017-08-23 |  | 2018-07-27 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORWELL | 177937 | 2061 | 18 | Solar | 07_96W43 | 2017-06-20 01:00 | 2017-06-20 | 7 | 7 | 0 | 2017-06-29 | 2017-06-29 | 0 | 0 | 0 | [20 empty] | 2017-06-30 |  | 2018-06-25 |  | EXP | [6 empty] | 2017-11-14 | 2017-11-14 | 2017-12-05 | Connected |  | No
National Grid | WILLIAMSBURG | 177939 | 1096 | 4536 | Solar | 09_909W3 | 2017-06-22 01:00 | 2017-06-27 | 2 | 1 | 1 | [10 empty] | 2017-06-29 | 2017-07-19 | 13 | 0 | 13 | [11 empty] | 2017-06-22 01:00 | 2018-07-02 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NEWBURYPORT | 177940 | 1950 | 125 | Solar | 14_36L2 | 2017-06-22 01:00 | 2018-02-12 | 0 | 0 | 0 | 2018-02-12 | 2018-02-13 | 1 | 0 | 1 | [20 empty] | 2018-02-12 |  | 2019-12-31 | Yes | EXP | [8 empty] | 2019-12-31 | Connected |  | No
National Grid | DUDLEY | 177938 | 1571 | 96 | Solar | 01_412L4 | 2017-06-26 01:00 | 2017-07-24 | 28 | 27 | 1 | 2017-08-07 | 2017-08-07 | 0 | 0 | 0 | [20 empty] | 2017-08-09 |  | 2018-07-02 |  | EXP | [6 empty] | 2017-12-08 | 2017-12-08 | 2017-12-08 | Connected |  | No
National Grid | HAVERHILL | 177941 | 1832 | 120 | Solar | 14_32J1 | 2017-06-26 01:00 | 2017-06-27 | 105 | 105 | 0 | [10 empty] | 2017-12-05 | 2018-02-12 | 47 | 27 | 20 | [10 empty] | 2018-09-25 |  | 2019-05-02 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HAVERHILL | 177942 | 1830 | 3.8 | Solar | 14_47L1 | 2017-06-26 01:00 | 2017-06-27 | 6 | 5 | 1 | 2017-07-06 | 2018-03-26 | 163 | 0 | 163 | [20 empty] | 2017-07-07 |  | 2018-07-02 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NANTUCKET | 177972 | 2554 | 18 | Solar | 04_101L8 | 2017-06-26 01:00 | 2017-06-27 | 12 | 11 | 1 | 2017-07-14 |  | 176 | 0 | 176 | [20 empty] | 2017-07-17 |  | 2018-07-02 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HARDWICK | 177973 | 1037 | 1500 | Solar | 09_501L2 | 2017-06-27 01:00 | 2017-06-27 | 152 | 151 | 1 | [27 empty] | 2018-07-02 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LEOMINSTER | 177974 | 1453 | 6 | Solar | 01_219W5 | 2017-06-27 01:00 | 2017-06-27 | 37 | 36 | 1 | 2017-08-18 | 2017-08-28 | 6 | 0 | 6 | [20 empty] | 2017-08-28 | 2017-06-27 01:00 | 2018-07-02 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | FALL RIVER | 177975 | 2720 | 660 | Solar | 05_28W42 | 2017-06-27 01:00 | 2017-06-28 | 25 | 25 | 0 | [10 empty] | 2017-08-03 | 2017-08-29 | 18 | 3 | 15 | [10 empty] | 2018-01-23 | 2017-06-27 01:00 | 2018-11-30 | Yes | STD |  | 2018-09-08 | 2018-11-08 | 61 | 0 | 61 |  |  | 2018-11-27 | Connected |  | Yes
National Grid | FALL RIVER | 177976 | 2720 | 960 | Solar | 05_28W42 | 2017-06-27 01:00 | 2017-06-28 | 25 | 25 | 0 | [10 empty] | 2017-08-03 | 2017-08-29 | 18 | 3 | 15 | [10 empty] | 2018-01-23 | 2017-06-27 01:00 | 2018-11-30 | Yes | STD | [8 empty] | 2018-11-27 | Connected |  | Yes
National Grid | FALL RIVER | 177977 | 2720 | 480 | Solar | 05_28W42 | 2017-06-27 01:00 | 2017-06-28 | 25 | 19 | 6 | [10 empty] | 2017-08-03 | 2017-08-29 | 18 | 3 | 15 | [10 empty] | 2018-01-23 |  | 2018-11-30 | Yes | STD |  | 2018-11-28 | 2018-11-27 | 0 | 0 | 0 |  |  | 2018-11-27 | Connected |  | Yes
National Grid | SAUGUS | 177978 | 1906 | 7.6 | Solar | 12_23W2 | 2017-06-28 01:00 | 2017-06-28 | 5 | 2 | 3 | 2017-07-06 | 2017-07-14 | 6 | 0 | 6 | [20 empty] | 2017-07-07 |  | 2018-07-03 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MONSON | 177979 | 1057 | 7.6 | Solar | 09_139L1 | 2017-06-28 01:00 | 2017-06-28 | 5 | 5 | 0 | 2017-07-06 | 2017-07-06 | 0 | 0 | 0 | [20 empty] | 2017-07-06 |  | 2018-07-03 |  | EXP | [8 empty] | 2018-07-02 | Connected |  | No
National Grid | WEYMOUTH | 178014 | 2188 | 3.8 | Solar | 07_6W1 | 2017-06-29 01:00 | 2017-06-29 | 4 | 3 | 1 | 2017-07-06 |  | 182 | 0 | 182 | [20 empty] | 2017-07-07 |  | 2018-07-04 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SOMERSET | 178015 | 2726 | 15.2 | Solar | 05_19W74 | 2017-06-29 01:00 | 2017-06-29 | 19 | 18 | 1 | [26 empty] | 2017-06-29 01:00 | 2018-07-04 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BELLINGHAM | 178016 | 2019 | 15.2 | Solar | 05_344W4 | 2017-06-29 01:00 | 2017-06-29 | 4 | 3 | 1 | 2017-07-06 | 2017-07-06 | 0 | 0 | 0 | [20 empty] | 2017-07-07 |  | 2018-07-04 |  | EXP |  | 2017-12-26 | 2017-12-20 | 0 | 0 | 0 | 2018-01-16 | 2018-01-16 | 2018-01-22 | Connected |  | No
National Grid | QUINCY | 178017 | 2169 | 15.2 | Solar | 07_1W5 | 2017-06-29 01:00 | 2017-06-29 | 4 | 3 | 1 | 2017-07-06 | 2017-07-06 | 0 | 0 | 0 | [20 empty] | 2017-07-06 |  | 2018-07-04 |  | EXP | [6 empty] | 2018-03-06 | 2018-03-06 | 2018-03-23 | Connected |  | No
National Grid | WEYMOUTH | 178018 | 2188 | 7.6 | Solar | 07_6W1 | 2017-06-29 01:00 | 2017-06-29 | 4 | 3 | 1 | 2017-07-06 | 2018-02-05 | 140 | 0 | 140 | [20 empty] | 2017-07-07 |  | 2018-07-04 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | AVON | 178019 | 2322 | 300 | Natural Gas | 07_75W1 | 2017-06-29 01:00 | 2017-06-30 | 8 | 6 | 2 | 2017-07-13 | 2017-08-07 | 177 | 0 | 177 | [20 empty] | 2017-08-07 | 2017-06-29 01:00 | 2018-07-05 |  | EXP | [6 empty] | 2017-08-18 | 2017-08-18 | 2018-12-20 | Connected |  | Yes
National Grid | HALIFAX | 178020 | 2338 | 828 | Solar | 07_912W75 | 2017-06-29 01:00 | 2017-08-22 | 48 | 48 | 0 | [10 empty] | 2017-10-30 | 2017-11-27 | 17 | 0 | 17 | [10 empty] | 2018-07-11 |  | 2021-08-12 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | BARRE | 178050 | 1005 | 6740 | Solar | 09_501L2 | 2017-06-29 01:00 | 2017-06-30 | 27 | 27 | 0 | [10 empty] | 2017-08-09 | 2017-09-01 | 17 | 0 | 17 | [10 empty] | 2018-08-28 | 2017-06-29 01:00 | 2018-07-05 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | PALMER | 178051 | 1069 | 4950 | Solar | 09_503L1 | 2017-06-29 01:00 | 2017-06-30 | 28 | 27 | 1 | [10 empty] | 2017-08-10 | 2017-08-31 | 15 | 0 | 15 | [10 empty] | 2018-02-20 |  | 2020-10-08 | Yes | STD |  | 2019-08-06 | 2019-10-16 | 71 | 0 | 71 | 2020-07-30 | 2020-07-30 | 2020-10-07 | Connected |  | No
National Grid | HANOVER | 178052 | 2339 | 1000 | Solar | 07_95W2 | 2017-06-30 01:00 | 2017-06-30 | 9 | 8 | 1 | [10 empty] | 2017-07-14 | 2017-08-07 | 16 | 0 | 16 | [11 empty] | 2017-06-30 01:00 | 2018-07-05 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WEST BRIDGEWATER | 178053 | 2379 | 1128 | Solar | 07_92W54 | 2017-06-30 01:00 | 2017-06-30 | 11 | 0 | 11 | [10 empty] | 2017-07-18 | 2017-10-26 | 72 | 57 | 15 | [10 empty] | 2018-09-19 |  | 2021-02-12 | Yes | STD |  | 2020-06-30 | 2020-11-13 | 136 | 5 | 131 | 2021-01-28 | 2021-01-28 | 2021-02-12 | Connected |  | No
National Grid | ATHOL | 178055 | 1331 | 8140 | Solar | 09_702W3 | 2017-07-03 01:00 | 2017-07-06 | 8 | 7 | 1 | [10 empty] | 2017-07-18 | 2017-08-11 | 18 | 0 | 18 | [12 empty] | 2018-07-11 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | AUBURN | 178054 | 1501 | 10 | Solar | 01_26W2 | 2017-07-05 01:00 | 2017-07-27 | 25 | 25 | 0 | 2017-08-10 | 2017-08-10 | 0 | 0 | 0 | [20 empty] | 2017-08-15 |  | 2018-07-11 |  | EXP | [8 empty] | 2018-05-25 | Connected |  | Yes
National Grid | ABINGTON | 178089 | 2351 | 756 | Solar | 07_93W42 | 2017-07-06 01:00 | 2017-07-06 | 81 | 81 | 0 | [25 empty] | 2018-07-13 |  | 2020-01-13 |  | CMPX | [9 empty] | Withdrawn |  | No
National Grid | ATTLEBORO | 178090 | 2703 | 100 | Solar | 05_9L2 | 2017-07-07 01:00 | 2017-07-07 | 32 | 32 | 0 | 2017-08-22 | 2017-08-29 | 5 | 0 | 5 | [20 empty] | 2017-08-29 |  | 2018-07-12 |  | EXP | [8 empty] | 2018-08-21 | Connected |  | No
National Grid | WEYMOUTH | 178091 | 2190 | 3.8 | Solar | 07_99W32 | 2017-07-07 01:00 | 2017-07-10 | 7 | 6 | 1 | 2017-07-19 | 2017-07-19 | 0 | 0 | 0 | [20 empty] | 2017-07-20 | 2017-07-10 01:00 | 2018-07-15 |  | EXP | [6 empty] | 2018-01-05 | 2018-01-05 | 2018-01-05 | Connected |  | No
National Grid | BELLINGHAM | 178094 | 2019 | 10 | Solar | 05_335W1 | 2017-07-10 01:00 | 2017-07-10 | 5 | 4 | 1 | 2017-07-17 | 2017-07-17 | 0 | 0 | 0 | [20 empty] | 2017-07-19 |  | 2018-07-15 |  | EXP | [6 empty] | 2017-09-28 | 2017-09-28 | 2017-10-02 | Connected |  | No
National Grid | DUDLEY | 178095 | 1571 | 7.6 | Solar | 01_412L4 | 2017-07-10 01:00 | 2017-07-10 | 7 | 6 | 1 | 2017-07-19 | 2017-07-20 | 0 | 0 | 0 | [20 empty] | 2017-07-20 |  | 2018-07-15 |  | EXP | [8 empty] | 2018-10-30 | Connected |  | Yes
National Grid | FALL RIVER | 177913 | 2720 | 2000 | Solar | 05_28W50 | 2017-07-11 01:00 | 2017-08-17 | 1 | 0 | 1 | [10 empty] | 2017-08-18 | 2017-08-22 | 2 | 0 | 2 | [10 empty] | 2018-04-05 | 2017-07-11 01:00 | 2019-06-24 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WARREN | 178097 | 1083 | 4000 | Solar | 09_516L3 | 2017-07-11 01:00 | 2017-07-11 | 12 | 12 | 0 | [10 empty] | 2017-07-27 | 2017-08-22 | 18 | 11 | 7 | [10 empty] | 2018-02-20 |  | 2021-08-20 | Yes | STD |  | 2019-09-07 | 2020-04-29 | 236 | 77 | 159 | 2021-07-01 | 2021-07-01 | 2021-08-20 | Connected |  | No
National Grid | METHUEN | 178126 | 1844 | 7.6 | Solar | 14_63L1 | 2017-07-11 01:00 | 2017-07-12 | 3 | 3 | 0 | 2017-07-17 | 2017-07-17 | 0 | 0 | 0 | [20 empty] | 2017-07-18 |  | 2018-07-17 |  | EXP | [6 empty] | 2017-10-18 | 2017-10-18 | 2017-10-18 | Connected |  | No
National Grid | LOWELL | 178127 | 1854 | 10 | Solar | 14_77L1 | 2017-07-11 01:00 | 2017-07-12 | 4 | 4 | 0 | 2017-07-18 | 2017-07-18 | 0 | 0 | 0 | [20 empty] | 2017-07-19 |  | 2018-07-17 |  | EXP | [6 empty] | 2018-01-24 | 2018-01-24 | 2018-01-24 | Connected |  | No
National Grid | WESTPORT | 178128 | 2790 | 7.6 | Solar | 05_115W45 | 2017-07-11 01:00 | 2017-07-12 | 5 | 5 | 0 | 2017-07-19 | 2017-07-19 | 0 | 0 | 0 | [20 empty] | 2017-07-19 |  | 2018-07-17 |  | EXP | [6 empty] | 2017-10-23 | 2017-10-23 | 2017-10-23 | Connected |  | No
National Grid | WILBRAHAM | 178129 | 1095 | 3.23 | Solar | 09_507L2 | 2017-07-12 01:00 | 2017-07-12 | 5 | 0 | 5 | 2017-07-19 | 2018-03-02 | 149 | 16 | 133 | [20 empty] | 2017-08-14 | 2017-07-12 01:00 | 2018-07-17 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WARREN | 178130 | 1083 | 3500 | Solar | 09_516L3 | 2017-07-12 01:00 | 2017-07-12 | 29 | 28 | 1 | [10 empty] | 2017-08-22 | 2017-09-13 | 15 | 0 | 15 | [10 empty] | 2019-02-27 |  | 2020-06-10 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | MEDFORD | 178131 | 2155 | 7.6 | Solar | 12_11J13 | 2017-07-12 01:00 | 2017-07-12 | 3 | 0 | 3 | 2017-07-17 | 2017-07-17 | 0 | 0 | 0 | [20 empty] | 2017-07-19 |  | 2018-07-17 |  | EXP | [6 empty] | 2017-10-17 | 2017-10-17 | 2017-10-17 | Connected |  | No
National Grid | FALL RIVER | 178132 | 2721 | 3.8 | Solar | 05_115W53 | 2017-07-12 01:00 | 2017-07-13 | 4 | 4 | 0 | 2017-07-19 |  | 173 | 0 | 173 | [20 empty] | 2017-07-20 |  | 2018-07-18 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BELCHERTOWN | 178133 | 1007 | 9980 | Solar | 09_527L2 | 2017-07-12 01:00 | 2017-07-13 | 32 | 32 | 0 | [10 empty] | 2017-08-28 | 2017-09-19 | 15 | 0 | 15 | [10 empty] | 2018-02-27 |  | 2022-12-21 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTMINSTER | 178134 | 1473 | 15.2 | Solar | 01_602W2 | 2017-07-12 01:00 | 2017-07-13 | 4 | 4 | 0 | 2017-07-19 | 2017-07-19 | 0 | 0 | 0 | [20 empty] | 2017-07-20 |  | 2018-07-18 |  | EXP | [6 empty] | 2018-01-25 | 2018-01-25 | 2018-01-25 | Connected |  | No
National Grid | NORTHAMPTON | 177558 | 1060 | 22.8 | Solar | 09_901W1 | 2017-07-13 01:00 | 2017-07-13 | 5 | 4 | 1 | [25 empty] | 2017-07-20 |  | 2018-09-28 |  | EXP | [8 empty] | 2018-08-14 | Connected |  | Yes
National Grid | GLOUCESTER | 177559 | 1930 | 3 | Solar | 12_51T1 | 2017-07-13 01:00 | 2017-07-14 | 22 | 22 | 0 | 2017-08-15 | 2018-02-12 | 117 | 7 | 110 | [20 empty] | 2017-08-28 |  | 2018-07-19 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ATTLEBORO | 177560 | 2703 | 594 | Solar | 05_9L4 | 2017-07-13 01:00 | 2017-07-14 | 25 | 12 | 13 | [10 empty] | 2017-08-17 | 2017-09-06 | 13 | 0 | 13 | [11 empty] | 2017-07-13 01:00 | 2019-09-18 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BELLINGHAM | 177561 | 2019 | 10 | Solar | 05_348W7 | 2017-07-13 01:00 | 2017-07-14 | 11 | 11 | 0 | 2017-07-31 | 2017-07-31 | 0 | 0 | 0 | [20 empty] | 2017-08-01 | 2017-07-13 01:00 | 2018-07-19 |  | EXP | [6 empty] | 2018-01-12 | 2018-01-12 | 2018-01-19 | Connected |  | No
National Grid | ORANGE | 177562 | 1364 | 4980 | Solar | 09_705W2 | 2017-07-13 01:00 | 2017-07-14 | 9 | 9 | 0 | [10 empty] | 2017-07-27 | 2017-08-21 | 17 | 0 | 17 | [10 empty] | 2017-12-05 |  | 2021-06-01 | Yes | STD |  | 2020-10-15 | 2021-03-25 | 161 | 0 | 161 |  |  | 2021-04-14 | Connected |  | No
National Grid | BEVERLY | 177563 | 1915 | 10 | Solar | 12_18L1 | 2017-07-14 01:00 | 2018-01-03 | 9 | 0 | 9 | 2018-01-03 | 2018-01-26 | 16 | 0 | 16 | [20 empty] | 2018-01-26 |  | 2018-09-28 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | EAST LONGMEADOW | 177564 | 1028 | 10 | Solar | 09_508L5 | 2017-07-14 01:00 | 2017-07-17 | 2 | 2 | 0 | 2017-07-19 | 2018-07-19 | 0 | 0 | 0 | [20 empty] | 2017-07-20 |  | 2018-07-22 |  | EXP | [8 empty] | 2018-10-23 | Connected |  | Yes
National Grid | NORTON | 177565 | 2766 | 7.6 | Solar | 05_8L4 | 2017-07-14 01:00 | 2017-07-17 | 2 | 2 | 0 | 2017-07-19 | 2017-07-19 | 0 | 0 | 0 | [20 empty] | 2017-07-20 |  | 2018-07-22 |  | EXP | [6 empty] | 2017-11-07 | 2017-11-07 | 2017-11-07 | Connected |  | No
National Grid | ABINGTON | 177595 | 2351 | 323 | Solar | 07_99W62 | 2017-07-17 01:00 | 2017-07-17 | 10 | 10 | 0 | 2017-07-31 | 2017-08-30 | 165 | 3 | 162 | [20 empty] | 2017-08-30 | 2017-07-18 01:00 | 2018-07-22 |  | EXP | [8 empty] | 2018-06-12 | Connected |  | No
National Grid | NEWBURYPORT | 177596 | 1950 | 180 | Solar | 14_36L2 | 2017-07-18 01:00 | 2017-07-18 | 73 | 69 | 4 | [10 empty] | 2017-10-27 | 2017-11-27 | 18 | 0 | 18 | [10 empty] | 2018-05-17 | 2017-07-18 01:00 | 2021-08-31 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | HOLBROOK | 177597 | 2343 | 324 | Solar | 07_10W1 | 2017-07-18 01:00 | 2017-08-29 | 43 | 43 | 0 | [10 empty] | 2017-10-30 | 2017-11-27 | 17 | 0 | 17 | [10 empty] | 2018-07-11 |  | 2021-08-20 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | ESSEX | 177599 | 1929 | 28.75 | Solar | 12_51T2 | 2017-07-19 01:00 | 2017-08-31 | 40 | 31 | 9 | 2017-09-14 | 2017-09-14 | 0 | 0 | 0 | [20 empty] | 2017-09-14 |  | 2018-07-24 |  | EXP | [6 empty] | 2018-03-09 | 2018-03-09 | 2018-03-09 | Connected |  | No
National Grid | ESSEX | 177600 | 1929 | 28.75 | Solar | 12_51T2 | 2017-07-19 01:00 | 2017-07-19 | 40 | 31 | 9 | 2017-09-15 | 2017-09-15 | 0 | 0 | 0 | [20 empty] | 2017-09-15 |  | 2018-07-24 |  | EXP | [6 empty] | 2018-03-16 | 2018-03-16 | 2018-04-25 | Connected |  | No
National Grid | NANTUCKET | 177601 | 2554 | 57.6 | Solar | 04_101L7 | 2017-07-19 01:00 | 2017-07-19 | 18 | 17 | 1 | 2017-08-14 | 2017-08-14 | 0 | 0 | 0 | [20 empty] | 2017-08-15 |  | 2018-07-24 |  | EXP | [6 empty] | 2017-12-08 | 2017-12-08 | 2017-12-21 | Connected |  | No
National Grid | BLACKSTONE | 177602 | 1504 | 7.04 | Solar | 05_108W60 | 2017-07-19 01:00 | 2017-07-19 | 7 | 6 | 1 | 2017-07-28 | 2017-07-28 | 0 | 0 | 0 | [20 empty] | 2017-08-01 |  | 2018-07-24 |  | EXP | [6 empty] | 2017-09-29 | 2017-09-29 | 2017-10-03 | Connected |  | No
National Grid | NEWBURYPORT | 177603 | 1950 | 12 | Solar | 14_47L2 | 2017-07-19 01:00 | 2017-07-19 | 11 | 11 | 0 | 2017-08-03 | 2017-10-25 | 57 | 0 | 57 | [20 empty] | 2017-08-04 |  | 2018-07-24 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WARE | 177604 | 1082 | 7.6 | Solar | 09_523L4 | 2017-07-19 01:00 | 2017-07-20 | 6 | 0 | 6 | 2017-07-28 | 2017-07-28 | 0 | 0 | 0 | [20 empty] | 2017-08-01 | 2017-07-19 01:00 | 2018-07-25 |  | EXP | [6 empty] | 2018-03-28 | 2018-03-28 | 2018-03-28 | Connected |  | No
National Grid | SPENCER | 177634 | 1562 | 2000 | Solar | 01_552L1 | 2017-07-19 01:00 | 2017-07-20 | 8 | 0 | 8 | [10 empty] | 2017-08-01 | 2017-08-21 | 14 | 0 | 14 | [10 empty] | 2018-05-09 | 2017-07-19 01:00 | 2020-06-26 | Yes | STD |  | 2019-10-29 | 2020-05-20 | 202 | 0 | 202 |  |  | 2020-06-26 | Connected |  | No
National Grid | WEST BRIDGEWATER | 177635 | 2379 | 8 | Solar | 07_797W19 | 2017-07-19 01:00 | 2017-07-20 | 23 | 18 | 5 | 2017-08-22 | 2017-08-22 | 0 | 0 | 0 | [20 empty] | 2017-08-28 |  | 2018-07-25 | Yes | EXP |  | 2017-12-20 | 2017-12-30 | 7 | 0 | 7 | 2018-02-27 | 2018-02-27 | 2018-03-06 | Connected |  | No
National Grid | WARREN | 177637 | 1083 | 8730 | Solar | 09_516L2 | 2017-07-20 01:00 | 2017-07-20 | 32 | 0 | 32 | [10 empty] | 2017-09-05 | 2017-09-28 | 17 | 0 | 17 | [10 empty] | 2018-06-06 | 2017-07-20 01:00 | 2021-03-19 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WEST BROOKFIELD | 177638 | 1585 | 4282 | Solar | 09_501L1 | 2017-07-20 01:00 | 2017-07-20 | 114 | 104 | 10 | [10 empty] | 2018-01-11 | 2018-01-11 | 0 | 0 | 0 | [10 empty] | 2018-11-28 | 2017-07-20 01:00 |  | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | WARREN | 177639 | 1585 | 1582 | Solar | 09_501L1 | 2017-07-20 01:00 | 2017-07-20 | 114 | 104 | 10 | [10 empty] | 2018-01-11 | 2018-01-11 | 0 | 0 | 0 | [10 empty] | 2018-11-21 |  | 2024-08-16 | Yes | STD | [9 empty] | Design |  | No
National Grid | WEST BROOKFIELD | 177640 | 1585 | 2980 | Solar | 09_501L1 | 2017-07-20 01:00 | 2017-07-21 | 113 | 104 | 9 | [10 empty] | 2018-01-11 | 2018-01-11 | 0 | 0 | 0 | [10 empty] | 2018-11-28 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WARREN | 177641 | 1083 | 3200 | Solar | 09_501L1 | 2017-07-20 01:00 | 2017-07-21 | 113 | 104 | 9 | [10 empty] | 2018-01-11 | 2018-01-11 | 0 | 0 | 0 | [10 empty] | 2018-11-28 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 177643 | 1844 | 10 | Solar | 14_74L6 | 2017-07-20 01:00 | 2017-07-21 | 5 | 0 | 5 | 2017-07-28 | 2018-02-14 | 131 | 0 | 131 | [20 empty] | 2017-08-01 |  | 2018-07-26 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BEVERLY | 177673 | 1915 | 100 | Solar | 12_18J3 | 2017-07-20 01:00 | 2017-07-21 | 23 | 19 | 4 | 2017-08-23 | 2017-08-29 | 0 | 0 | 0 | [20 empty] | 2017-08-29 |  | 2018-07-26 |  | EXP | [8 empty] | 2018-11-09 | Connected |  | Yes
National Grid | HARDWICK | 177674 | 1037 | 4980 | Solar | 09_501L2 | 2017-07-20 01:00 | 2017-07-21 | 15 | 0 | 15 | [10 empty] | 2017-08-11 | 2017-09-06 | 17 | 0 | 17 | [10 empty] | 2018-05-22 |  | 2019-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTBOROUGH | 177676 | 1581 | 56 | Solar | 05_312W5 | 2017-07-21 01:00 | 2017-07-24 | 8 | 4 | 4 | 2017-08-03 | 2017-08-03 | 0 | 0 | 0 | [20 empty] | 2017-08-04 |  | 2018-07-29 |  | EXP | [6 empty] | 2017-12-27 | 2017-12-27 | 2017-12-27 | Connected |  | Yes
National Grid | PALMER | 177678 | 1069 | 72 | Solar | 09_503L1 | 2017-07-21 01:00 | 2017-07-24 | 9 | 6 | 3 | 2017-08-04 |  | 161 | 0 | 161 | [20 empty] | 2017-08-15 |  | 2018-07-29 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WILBRAHAM | 177679 | 1095 | 300 | Natural Gas | 09_507L3 | 2017-07-24 01:00 | 2017-08-01 | 13 | 13 | 0 | 2017-08-15 | 2017-09-01 | 0 | 0 | 0 | [20 empty] | 2017-09-01 |  | 2018-07-30 |  | EXP | [8 empty] | 2018-10-10 | Connected |  | Yes
National Grid | BOXFORD | 177680 | 1921 | 45.6 | Solar | 14_33L2 | 2017-07-25 01:00 | 2017-08-30 | 35 | 33 | 2 | 2017-09-13 | 2017-09-13 | 0 | 0 | 0 | [20 empty] | 2017-09-13 |  | 2018-07-30 |  | EXP | [6 empty] | 2018-02-13 | 2018-02-13 | 2018-02-13 | Connected |  | No
National Grid | NORTHAMPTON | 177682 | 1060 | 90 | Solar | 09_901W3 | 2017-07-25 01:00 | 2017-07-26 | 7 | 6 | 1 | 2017-08-04 | 2017-08-04 | 0 | 0 | 0 | [20 empty] | 2017-08-28 |  | 2018-07-31 |  | EXP | [6 empty] | 2018-03-02 | 2018-03-02 | 2018-03-22 | Connected |  | No
National Grid | SOMERSET | 177712 | 2725 | 1000 | Solar | 05_11W84 | 2017-07-25 01:00 | 2017-07-26 | 19 | 0 | 19 | [10 empty] | 2017-08-22 | 2017-12-15 | 79 | 0 | 79 | [11 empty] | 2017-07-26 01:00 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BEVERLY | 177713 | 1915 | 108 | Solar | 12_51L1 | 2017-07-26 01:00 | 2017-09-07 | 30 | 29 | 1 | 2017-09-07 | 2017-09-12 | 0 | 0 | 0 | [20 empty] | 2017-09-12 | 2017-07-26 01:00 | 2018-07-31 |  | EXP |  | 2017-09-12 | 2017-09-12 | 29 | 29 | 0 |  |  | 2018-05-29 | Connected |  | No
National Grid | WESTMINSTER | 177715 | 1473 | 4686 | Solar | 01_609W1 | 2017-07-26 01:00 | 2017-07-27 | 51 | 51 | 0 | [10 empty] | 2017-10-06 | 2017-10-25 | 13 | 0 | 13 | [10 empty] | 2018-07-17 |  | 2022-10-31 | Yes | STD |  | 2022-08-26 | 2022-10-12 | 48 | 0 | 48 | 2022-10-13 | 2022-10-13 | 2022-11-18 | Connected |  | No
National Grid | BILLERICA | 177716 | 1821 | 112 | Solar | 14_92L3 | 2017-07-26 01:00 | 2017-07-27 | 6 | 6 | 0 | 2017-08-04 | 2017-08-04 | 0 | 0 | 0 | [20 empty] | 2017-08-15 |  | 2018-08-01 |  | EXP | [6 empty] | 2018-01-24 | 2018-01-24 | 2018-01-24 | Connected |  | No
National Grid | SEEKONK | 177717 | 2771 | 15.2 | Solar | 05_7L1 | 2017-07-27 01:00 | 2017-07-27 | 5 | 5 | 0 | 2017-08-03 | 2017-10-20 | 54 | 0 | 54 | [20 empty] | 2017-08-04 |  | 2018-08-01 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MELROSE | 177718 | 2176 | 3.8 | Solar | 12_16W6 | 2017-07-27 01:00 | 2017-07-27 | 9 | 9 | 0 | 2017-08-09 | 2018-02-12 | 121 | 0 | 121 | [20 empty] | 2017-08-14 |  | 2018-08-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | PALMER | 177719 | 1069 | 3.8 | Solar | 09_523L1 | 2017-07-27 01:00 | 2017-07-27 | 9 | 9 | 0 | 2017-08-09 | 2017-08-15 | 4 | 0 | 4 | [20 empty] | 2017-08-15 | 2017-07-27 01:00 | 2018-08-01 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SWANSEA | 177751 | 2777 | 5.2 | Solar | 05_11W81 | 2017-07-27 01:00 | 2017-07-27 | 9 | 9 | 0 | 2017-08-09 | 2017-08-09 | 0 | 0 | 0 | [20 empty] | 2017-08-18 |  | 2018-08-01 |  | EXP |  | 2017-08-24 | 2017-09-09 | 11 | 0 | 11 | 2017-11-27 | 2017-11-27 | 2017-12-01 | Connected |  | No
National Grid | MALDEN | 177754 | 2148 | 6 | Solar | 12_16W6 | 2017-07-31 01:00 | 2017-08-01 | 8 | 8 | 0 | 2017-08-11 | 2017-08-15 | 2 | 0 | 2 | [20 empty] | 2017-08-15 |  | 2018-08-06 |  | EXP | [8 empty] | 2018-06-12 | Connected |  | Yes
National Grid | NORTH BILLERICA | 177755 | 1862 | 396 | Solar | 14_70L1 | 2017-08-01 01:00 | 2017-08-01 | 84 | 84 | 0 | [10 empty] | 2017-11-30 | 2017-12-20 | 14 | 0 | 14 | [10 empty] | 2018-06-28 |  | 2019-09-02 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH BILLERICA | 177756 | 1862 | 324 | Solar | 14_70L1 | 2017-08-01 01:00 | 2017-08-02 | 83 | 83 | 0 | [10 empty] | 2017-11-30 | 2017-12-20 | 14 | 0 | 14 | [10 empty] | 2018-06-28 | 2017-08-01 01:00 | 2019-09-02 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | FRANKLIN | 177757 | 2038 | 612 | Solar | 05_344W6 | 2017-08-01 01:00 | 2017-08-22 | 69 | 69 | 0 | [10 empty] | 2017-12-01 | 2017-12-20 | 13 | 0 | 13 | [10 empty] | 2018-11-21 |  | 2021-11-30 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | SCITUATE | 177758 | 2066 | 360 | Solar | 07_915W36 | 2017-08-02 01:00 | 2017-08-22 | 48 | 48 | 0 | [10 empty] | 2017-10-30 | 2017-11-27 | 17 | 0 | 17 | [10 empty] | 2018-07-11 | 2017-08-02 01:00 | 2020-12-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 177759 | 2302 | 648 | Solar | 07_91W48 | 2017-08-02 01:00 | 2017-08-22 | 69 | 69 | 0 | [10 empty] | 2017-12-01 | 2017-12-18 | 11 | 0 | 11 | [10 empty] | 2018-08-27 |  | 2020-02-01 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | MALDEN | 177760 | 2148 | 468 | Solar | 12_5C3 | 2017-08-02 01:00 | 2017-08-02 | 95 | 95 | 0 | [10 empty] | 2017-12-27 | 2018-01-25 | 19 | 0 | 19 | [11 empty] | 2017-08-02 01:00 | 2019-08-07 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 177761 | 2302 | 360 | Solar | 07_911W56 | 2017-08-02 01:00 | 2017-08-22 | 69 | 69 | 0 | [10 empty] | 2017-12-01 | 2017-12-27 | 18 | 0 | 18 | [10 empty] | 2018-07-11 |  | 2021-06-25 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | SOUTH ATTLEBORO | 177791 | 2703 | 612 | Solar | 05_9L5 | 2017-08-02 01:00 | 2017-08-03 | 126 | 126 | 0 | [26 empty] | 2017-08-02 01:00 | 2018-08-08 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WEYMOUTH | 177792 | 2189 | 468 | Solar | 07_9W2 | 2017-08-02 01:00 | 2017-08-23 | 68 | 68 | 0 | [10 empty] | 2017-11-30 | 2017-12-18 | 12 | 0 | 12 | [10 empty] | 2018-07-11 | 2017-08-02 01:00 | 2021-10-19 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | HOLBROOK | 177793 | 2343 | 10 | Solar | 07_2W1 | 2017-08-02 01:00 | 2017-08-14 | 8 | 8 | 0 | 2017-08-15 | 2017-08-16 | 154 | 0 | 154 | [20 empty] | 2017-08-16 |  | 2018-09-07 | Yes | EXP |  | 2018-02-02 | 2018-02-06 | 2 | 0 | 2 |  |  | 2018-08-21 | Connected |  | Yes
National Grid | REVERE | 177794 | 2151 | 7.6 | Solar | 12_7W1 | 2017-08-02 01:00 | 2017-08-03 | 4 | 0 | 4 | 2017-08-09 | 2017-08-14 | 0 | 0 | 0 | [20 empty] | 2017-08-14 | 2017-08-02 01:00 | 2018-08-08 |  | EXP | [8 empty] | 2018-08-01 | Connected |  | No
National Grid | STOUGHTON | 177795 | 2072 | 38.2 | Solar | 07_94W43 | 2017-08-02 01:00 | 2017-08-03 | 6 | 6 | 0 | 2017-08-11 | 2017-08-11 | 0 | 0 | 0 | [20 empty] | 2017-08-15 |  | 2018-08-08 | Yes | EXP |  | 2017-11-27 | 2017-12-06 | 7 | 0 | 7 | 2018-04-06 | 2018-04-06 | 2018-04-17 | Connected |  | No
National Grid | SOUTH ATTLEBORO | 178321 | 2703 | 612 | Solar | 05_9L5 | 2017-08-02 01:00 | 2017-08-03 | 126 | 0 | 126 | [10 empty] | 2018-02-13 | 2018-03-29 | 20 | 0 | 20 | [12 empty] | 2019-04-03 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SAUGUS | 177796 | 1906 | 15.2 | Solar | 12_23W2 | 2017-08-03 01:00 | 2017-08-03 | 9 | 8 | 1 | 2017-08-16 | 2017-08-17 | 1 | 0 | 1 | [20 empty] | 2017-08-17 | 2017-08-03 01:00 | 2018-08-08 |  | EXP | [8 empty] | 2018-10-10 | Connected |  | Yes
National Grid | FRANKLIN | 177797 | 2038 | 636 | Solar | 05_344W6 | 2017-08-03 01:00 | 2017-08-22 | 48 | 48 | 0 | [10 empty] | 2017-10-30 | 2017-12-20 | 35 | 21 | 14 | [10 empty] | 2018-11-21 | 2017-08-03 01:00 | 2021-11-30 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | LOWELL | 177798 | 1851 | 233.1 | Solar | 14_16L2 | 2017-08-03 01:00 | 2017-08-04 | 14 | 14 | 0 | 2017-08-18 | 2017-08-24 | 0 | 0 | 0 | [20 empty] | 2017-09-07 |  | 2018-08-09 | Yes | EXP |  | 2018-02-12 | 2018-03-07 | 13 | 0 | 13 | 2018-03-09 | 2018-03-09 | 2018-03-09 | Connected |  | No
National Grid | LOWELL | 177799 | 1852 | 266.4 | Solar | 14_2381 | 2017-08-03 01:00 | 2017-08-04 | 14 | 14 | 0 | 2017-08-18 | 2017-08-24 | 0 | 0 | 0 | [20 empty] | 2017-09-20 | 2017-08-03 01:00 | 2018-08-09 |  | EXP |  | 2018-01-15 | 2018-01-15 | 0 | 0 | 0 | 2018-01-08 | 2018-01-08 | 2018-01-08 | Connected |  | No
National Grid | LOWELL | 177800 | 1852 | 266.4 | Solar | 14_16L2 | 2017-08-03 01:00 | 2017-08-04 | 14 | 14 | 0 | 2017-08-24 | 2017-09-07 | 5 | 5 | 0 | [20 empty] | 2017-09-07 |  | 2020-11-30 |  | EXP | [8 empty] | 2020-10-28 | Connected |  | No
National Grid | NORWELL | 177828 | 2061 | 280 | Solar | 07_95W4 | 2017-08-04 01:00 | 2017-08-04 | 7 | 7 | 0 | 2017-08-15 | 2017-08-15 | 0 | 0 | 0 | [20 empty] | 2017-09-05 |  | 2018-08-09 |  | EXP | [6 empty] | 2017-12-19 | 2017-12-19 | 2017-12-27 | Connected |  | No
National Grid | WORCESTER | 177829 | 1605 | 7.6 | Solar | 01_27W4 | 2017-08-04 01:00 | 2017-08-07 | 4 | 0 | 4 | 2017-08-11 | 2017-08-15 | 2 | 0 | 2 | [20 empty] | 2017-08-15 | 2017-08-08 01:00 | 2018-08-12 |  | EXP | [8 empty] | 2018-06-05 | Connected |  | No
National Grid | WESTMINSTER | 177832 | 1473 | 900 | Solar | 01_607W4 | 2017-08-08 01:00 | 2017-08-09 | 10 | 5 | 5 | [10 empty] | 2017-08-23 | 2017-09-26 | 24 | 24 | 0 | [10 empty] | 2018-05-04 |  | 2021-10-08 | Yes | STD |  | 2021-01-07 | 2021-09-21 | 258 | 80 | 178 | 2021-09-22 | 2021-09-22 | 2021-10-07 | Connected |  | No
National Grid | DOUGLAS | 177833 | 1516 | 1980 | Solar | 05_321W1 | 2017-08-09 01:00 | 2017-08-09 | 12 | 0 | 12 | [10 empty] | 2017-08-25 | 2017-09-20 | 17 | 0 | 17 | [10 empty] | 2018-03-29 |  | 2019-07-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | DOUGLAS | 177834 | 1516 | 3000 | Solar | 05_321W1 | 2017-08-09 01:00 | 2017-08-09 | 12 | 12 | 0 | [10 empty] | 2017-08-25 | 2017-09-20 | 17 | 0 | 17 | [10 empty] | 2018-03-29 | 2017-08-09 01:00 | 2019-07-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | GRAFTON | 177835 | 1519 | 1760 | Solar | 01_304W1 | 2017-08-09 01:00 | 2017-08-09 | 12 | 0 | 12 | [10 empty] | 2017-08-25 | 2017-09-20 | 17 | 0 | 17 | [10 empty] | 2018-05-03 |  | 2022-07-16 | Yes | STD |  | 2021-11-25 | 2022-03-14 | 110 | 0 | 110 |  |  | 2022-03-21 | Connected |  | No
National Grid | BILLERICA | 177836 | 1821 | 15.2 | Solar | 14_70L6 | 2017-08-09 01:00 | 2017-08-09 | 5 | 5 | 0 | 2017-08-16 | 2017-08-16 | 0 | 0 | 0 | [20 empty] | 2017-08-17 |  | 2018-08-14 |  | EXP | [6 empty] | 2018-03-14 | 2018-03-14 | 2018-03-16 | Connected |  | No
National Grid | METHUEN | 177837 | 1844 | 15.2 | Solar | 14_75L6 | 2017-08-09 01:00 | 2017-08-09 | 5 | 5 | 0 | 2017-08-16 | 2017-08-16 | 0 | 0 | 0 | [20 empty] | 2017-08-17 |  | 2018-08-14 |  | EXP | [6 empty] | 2018-02-15 | 2018-02-15 | 2018-02-15 | Connected |  | No
National Grid | MILLBURY | 177867 | 1527 | 7.6 | Solar | 01_304W3 | 2017-08-09 01:00 | 2017-08-10 | 4 | 4 | 0 | 2017-08-16 | 2017-08-16 | 0 | 0 | 0 | [20 empty] | 2017-08-17 |  | 2018-08-15 |  | EXP | [6 empty] | 2018-03-29 | 2018-03-29 | 2018-03-29 | Connected |  | No
National Grid | EVERETT | 177868 | 2149 | 3.8 | Solar | 12_16W2 | 2017-08-09 01:00 | 2017-08-10 | 4 | 4 | 0 | 2017-08-16 | 2018-02-12 | 116 | 0 | 116 | [20 empty] | 2017-08-17 |  | 2018-08-15 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LEEDS | 177869 | 1053 | 176 | Solar | 09_909W3 | 2017-08-09 01:00 | 2017-08-10 | 15 | 15 | 0 | 2017-08-24 | 2017-08-31 | 0 | 0 | 0 | [20 empty] | 2017-09-01 | 2017-08-09 01:00 | 2018-08-15 |  | EXP | [6 empty] | 2018-03-02 | 2018-03-02 | 2018-03-02 | Connected |  | No
National Grid | ORANGE | 177870 | 1364 | 840 | Solar | 09_705W2 | 2017-08-09 01:00 | 2017-08-10 | 8 | 0 | 8 | [10 empty] | 2017-08-22 | 2018-09-25 | 275 | 0 | 275 | [10 empty] | 2018-03-30 |  | 2021-12-16 | Yes | STD |  | 2020-10-03 | 2021-04-22 | 201 | 0 | 201 | 2021-10-18 | 2021-10-18 | 2021-12-08 | Connected |  | No
National Grid | PEPPERELL | 177871 | 1463 | 160 | Solar | 01_226L1 | 2017-08-11 01:00 | 2017-08-11 | 3 | 3 | 0 | 2017-08-16 | 2017-08-16 | 0 | 0 | 0 | [20 empty] | 2017-08-17 |  | 2018-08-16 |  | EXP | [6 empty] | 2018-01-04 | 2018-01-04 | 2018-01-04 | Connected |  | No
National Grid | LOWELL | 177872 | 1854 | 6 | Solar | 14_21L3 | 2017-08-14 01:00 | 2017-08-14 | 170 | 0 | 170 | [26 empty] | 2017-08-14 01:00 | 2018-08-19 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ABINGTON | 177873 | 2351 | 5 | Solar | 07_64J1 | 2017-08-14 01:00 | 2017-08-15 | 1 | 0 | 1 | 2017-08-16 | 2017-08-16 | 0 | 0 | 0 | [20 empty] | 2017-08-17 | 2017-08-14 01:00 | 2018-08-20 |  | EXP |  | 2017-10-04 | 2017-10-23 | 12 | 0 | 12 | 2018-02-20 | 2018-02-20 | 2018-02-27 | Connected |  | No
National Grid | BLACKSTONE | 177874 | 1504 | 3600 | Solar | 05_108W60 | 2017-08-14 01:00 | 2017-08-15 | 9 | 9 | 0 | [10 empty] | 2017-08-28 | 2017-09-25 | 19 | 0 | 19 | [10 empty] | 2018-04-10 |  | 2022-09-26 | Yes | STD |  | 2022-01-22 | 2022-06-01 | 131 | 0 | 131 |  |  | 2022-08-03 | Connected |  | No
National Grid | ATTLEBORO | 177875 | 2703 | 120 | Solar | 05_9L1 | 2017-08-15 01:00 | 2017-08-15 | 12 | 12 | 0 | 2017-08-31 |  | 142 | 3 | 139 | [20 empty] | 2017-09-29 |  | 2018-08-20 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 177904 | 1844 | 20 | Solar | 14_74L5 | 2017-08-15 01:00 | 2017-08-15 | 15 | 15 | 0 | 2017-08-29 | 2017-09-06 | 0 | 0 | 0 | [20 empty] | 2017-09-08 |  | 2018-08-20 |  | EXP | [6 empty] | 2017-12-14 | 2017-12-14 | 2017-12-14 | Connected |  | No
National Grid | WEST WARREN | 177905 | 1092 | 10 | Solar | 09_516L3 | 2017-08-15 01:00 | 2017-08-15 | 118 | 118 | 0 | [27 empty] | 2018-08-20 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | COHASSET | 177907 | 2025 | 43.2 | Solar | 07_18J1 | 2017-08-16 01:00 | 2017-08-16 | 13 | 13 | 0 | 2017-09-05 | 2017-09-05 | 0 | 0 | 0 | [20 empty] | 2017-09-08 |  | 2018-08-21 |  | EXP | [6 empty] | 2017-10-27 | 2017-10-27 | 2017-11-13 | Connected |  | No
National Grid | AVON | 177908 | 2322 | 112 | Solar | 07_75W5 | 2017-08-16 01:00 | 2017-08-16 | 9 | 9 | 0 | 2017-08-29 | 2017-08-29 | 0 | 0 | 0 | [20 empty] | 2017-08-30 | 2017-08-16 01:00 | 2018-08-21 |  | EXP | [6 empty] | 2017-12-19 | 2017-12-19 | 2017-12-21 | Connected |  | No
National Grid | BLACKSTONE | 177909 | 1504 | 11.4 | Solar | 05_108W60 | 2017-08-16 01:00 | 2017-08-16 | 13 | 13 | 0 | 2017-09-05 | 2017-09-05 | 0 | 0 | 0 | [20 empty] | 2017-09-07 |  | 2018-08-21 | Yes | EXP |  | 2018-01-18 | 2018-02-14 | 19 | 0 | 19 | 2018-02-27 | 2018-02-27 | 2018-03-06 | Connected |  | No
National Grid | LAWRENCE | 177910 | 1841 | 7.6 | Solar | 14_6J2 | 2017-08-16 01:00 | 2017-08-16 | 13 | 13 | 0 | 2017-09-05 | 2017-09-05 | 0 | 0 | 0 | [20 empty] | 2017-09-07 |  | 2020-08-25 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | DRACUT | 177911 | 1826 | 7.6 | Solar | 14_75L2 | 2017-08-16 01:00 | 2017-08-16 | 13 | 13 | 0 | 2017-09-30 | 2017-10-11 | 0 | 0 | 0 | [20 empty] | 2017-09-07 |  | 2018-08-21 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | AUBURN | 177912 | 1501 | 9 | Solar | 01_26W3 | 2017-08-17 01:00 | 2017-08-17 | 8 | 2 | 6 | 2017-08-29 | 2017-08-30 | 0 | 0 | 0 | [20 empty] | 2017-08-30 | 2017-08-18 01:00 | 2018-08-22 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MARLBOROUGH | 177943 | 1752 | 333.2 | Solar | 05_311W1 | 2017-08-18 01:00 | 2017-08-18 | 127 | 91 | 36 | 2018-02-21 | 2018-02-13 | 0 | 0 | 0 | [20 empty] | 2018-04-19 | 2017-08-18 01:00 | 2021-02-10 |  | EXP | [8 empty] | 2021-02-10 | Connected |  | No
National Grid | PALMER | 177944 | 1069 | 432.9 | Solar | 09_523L2 | 2017-08-18 01:00 | 2017-08-21 | 10 | 0 | 10 | 2017-09-05 | 2017-10-11 | 26 | 0 | 26 | 2018-01-03 | 2018-01-19 | 11 | 0 | 11 | [5 empty] | 2018-01-03 | 2018-01-19 | 11 | 0 | 11 | [5 empty] | 2018-04-06 |  | 2020-01-31 | Yes | EXP | [8 empty] | 2020-01-15 | Connected |  | No
National Grid | SPENCER | 177945 | 1562 | 42.3 | Solar | 01_552L3 | 2017-08-21 01:00 | 2017-11-06 | 57 | 49 | 8 | 2017-11-20 | 2017-11-20 | 0 | 0 | 0 | [20 empty] | 2017-11-20 |  | 2018-08-26 |  | EXP | [8 empty] | 2018-06-19 | Connected |  | Yes
National Grid | WILLIAMSTOWN | 177948 | 1267 | 33.3 | Solar | 09_1003W2 | 2017-08-21 01:00 | 2017-08-23 | 59 | 58 | 1 | 2017-11-27 | 2018-02-14 | 54 | 0 | 54 | [20 empty] | 2017-11-27 |  | 2018-08-28 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORWELL | 156595 | 2061 | 15.2 | Solar | 07_915W35 | 2017-08-23 01:00 | 2017-08-23 | 1 | 0 | 1 | [27 empty] | 2018-08-23 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 177950 | 1604 | 3.8 | Solar | 01_10J383 | 2017-08-23 01:00 | 2017-08-24 | 9 | 9 | 0 | 2017-09-07 | 2017-09-07 | 0 | 0 | 0 | [20 empty] | 2017-09-11 |  | 2018-08-24 |  | EXP | [6 empty] | 2017-12-14 | 2017-12-14 | 2017-12-14 | Connected |  | No
National Grid | EVERETT | 177951 | 2149 | 3.8 | Solar | 12_16W7 | 2017-08-24 01:00 | 2017-08-24 | 9 | 9 | 0 | 2017-09-07 | 2017-09-12 | 3 | 0 | 3 | [20 empty] | 2017-09-12 |  | 2018-08-29 |  | EXP | [8 empty] | 2018-05-03 | Connected |  | No
National Grid | RANDOLPH | 177952 | 2368 | 10 | Solar | 07_5W4 | 2017-08-24 01:00 | 2017-08-24 | 10 | 10 | 0 | 2017-09-08 |  | 137 | 0 | 137 | [20 empty] | 2017-09-12 |  | 2018-08-29 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RANDOLPH | 177953 | 2368 | 109.25 | Solar | 07_97W1 | 2017-08-24 01:00 | 2017-08-28 | 5 | 5 | 0 | 2017-09-05 | 2017-09-05 | 0 | 0 | 0 | [20 empty] | 2017-09-08 |  | 2018-09-02 |  | EXP | [6 empty] | 2017-12-18 | 2017-12-18 | 2017-12-21 | Connected |  | No
National Grid | BEVERLY | 177981 | 1915 | 128 | Solar | 12_18J4 | 2017-08-24 01:00 | 2017-10-09 | 29 | 29 | 0 | 2017-10-09 | 2017-10-09 | 0 | 0 | 0 | [20 empty] | 2017-10-10 |  | 2018-09-02 |  | EXP | [6 empty] | 2018-01-25 | 2018-01-25 | 2018-01-25 | Connected |  | No
National Grid | MILFORD | 177982 | 1757 | 168 | Solar | 05_336W3 | 2017-08-28 01:00 | 2017-08-28 | 5 | 5 | 0 | 2017-09-05 | 2017-09-05 | 0 | 0 | 0 | [20 empty] | 2017-09-08 |  | 2018-09-02 |  | EXP | [6 empty] | 2018-02-07 | 2018-02-07 | 2018-02-20 | Connected |  | No
National Grid | AVON | 177985 | 2322 | 15.36 | Solar | 07_911W59 | 2017-08-28 01:00 | 2017-08-30 | 143 | 142 | 1 | [27 empty] | 2018-09-04 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTHBOROUGH | 177986 | 1532 | 366.3 | Solar | 05_312W3 | 2017-08-28 01:00 | 2017-08-30 | 99 | 96 | 3 | 2018-02-01 | 2018-03-06 | 22 | 0 | 22 | 2018-03-19 | 2018-04-13 | 19 | 0 | 19 | [5 empty] | 2018-03-19 | 2018-04-13 | 19 | 0 | 19 | [5 empty] | 2018-04-27 |  | 2018-09-04 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | REHOBOTH | 177987 | 2769 | 15.2 | Solar | 05_7L5 | 2017-08-28 01:00 | 2017-08-30 | 35 | 31 | 4 | 2017-10-20 | 2017-10-20 | 0 | 0 | 0 | [20 empty] | 2017-10-20 |  | 2018-09-04 |  | EXP | [6 empty] | 2017-12-11 | 2017-12-11 | 2017-12-19 | Connected |  | No
National Grid | NORTH QUINCY | 177988 | 2171 | 3 | Solar | 07_4J1 | 2017-08-28 01:00 | 2017-08-30 | 5 | 0 | 5 | 2017-09-07 |  | 138 | 0 | 138 | [20 empty] | 2017-09-08 |  | 2018-09-04 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH ANDOVER | 177989 | 1845 | 15.2 | Solar | 14_55L1 | 2017-08-28 01:00 | 2017-09-26 | 27 | 26 | 1 | 2017-10-10 | 2017-10-10 | 0 | 0 | 0 | [20 empty] | 2017-10-10 |  | 2018-09-04 |  | EXP | [6 empty] | 2017-12-28 | 2017-12-28 | 2017-12-28 | Connected |  | No
National Grid | HUBBARDSTON | 178021 | 1452 | 900 | Solar | 01_602W2 | 2017-08-29 01:00 | 2017-08-31 | 8 | 8 | 0 | [10 empty] | 2017-09-13 | 2017-09-26 | 9 | 0 | 9 | [12 empty] | 2018-09-05 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HUBBARDSTON | 178022 | 1452 | 500 | Solar | 01_609W1 | 2017-08-29 01:00 | 2017-08-31 | 8 | 8 | 0 | [10 empty] | 2017-09-13 | 2017-10-23 | 24 | 12 | 12 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BRIDGEWATER | 178023 | 2324 | 576 | Solar | 07_912W73 | 2017-08-30 01:00 | 2017-08-31 | 66 | 66 | 0 | [10 empty] | 2017-12-14 | 2017-12-27 | 8 | 0 | 8 | [12 empty] | 2019-09-05 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LOWELL | 178024 | 1854 | 5.47 | Solar | 14_21L3 | 2017-08-31 01:00 | 2017-08-31 | 29 | 27 | 2 | 2017-10-13 | 2018-02-14 | 78 | 0 | 78 | [20 empty] | 2017-10-16 |  | 2018-09-05 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ATHOL | 178025 | 1331 | 4980 | Solar | 09_702W2 | 2017-08-31 01:00 | 2017-09-01 | 23 | 22 | 1 | [10 empty] | 2017-10-03 | 2017-10-30 | 19 | 5 | 14 | [10 empty] | 2018-07-11 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MEDFORD | 178026 | 2155 | 166.75 | Solar | 12_9C2 | 2017-08-31 01:00 | 2017-09-01 | 21 | 20 | 1 | 2017-10-03 | 2017-10-03 | 0 | 0 | 0 | [20 empty] | 2017-10-03 |  | 2019-12-16 |  | EXP | [8 empty] | 2020-01-23 | Connected |  | No
National Grid | ATTLEBORO | 178027 | 2703 | 57.6 | Solar | 05_8L3 | 2017-08-31 01:00 | 2017-09-01 | 29 | 28 | 1 | 2017-10-16 |  | 112 | 0 | 112 | [20 empty] | 2017-10-16 |  | 2018-11-30 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LANCASTER | 178028 | 1523 | 69 | Solar | 01_225W1 | 2017-08-31 01:00 | 2017-09-01 | 1 | 0 | 1 | 2017-09-05 | 2018-02-12 | 103 | 0 | 103 | [20 empty] | 2017-09-08 |  | 2018-09-06 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WARE | 178030 | 1082 | 4998 | Solar | 09_501L2 | 2017-09-01 01:00 | 2017-09-04 | 12 | 8 | 4 | [10 empty] | 2017-09-21 | 2017-10-12 | 14 | 0 | 14 | [11 empty] | 2017-09-01 01:00 | 2018-09-09 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WARE | 178059 | 1082 | 3000 | Solar | 09_501L2 | 2017-09-01 01:00 | 2017-09-04 | 13 | 0 | 13 | [10 empty] | 2017-09-22 | 2017-10-17 | 17 | 0 | 17 | [10 empty] | 2018-09-14 | 2017-09-01 01:00 | 2021-07-08 | Yes | STD |  | 2020-05-29 | 2021-03-29 | 304 | 88 | 216 |  |  | 2021-07-08 | Connected |  | No
National Grid | EAST BROOKFIELD | 178060 | 1515 | 4980 | Solar | 01_552L3 | 2017-09-01 01:00 | 2017-09-04 | 12 | 0 | 12 | [10 empty] | 2017-09-21 | 2017-11-03 | 31 | 0 | 31 | [10 empty] | 2018-05-23 |  | 2021-07-06 | Yes | STD |  | 2020-04-02 | 2020-09-11 | 163 | 5 | 158 |  |  | 2021-07-06 | Connected |  | No
National Grid | PALMER | 178061 | 1069 | 2640 | Solar | 09_503L1 | 2017-09-01 01:00 | 2017-09-04 | 17 | 10 | 7 | [10 empty] | 2017-09-26 | 2017-11-07 | 28 | 15 | 13 | [10 empty] | 2018-10-26 | 2017-09-05 01:00 | 2020-09-14 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NEW MARLBOROUGH | 178062 | 1230 | 1000 | Solar | 09_1109W1 | 2017-09-05 01:00 | 2017-09-05 | 15 | 8 | 7 | [10 empty] | 2017-09-26 | 2017-10-18 | 15 | 0 | 15 | [10 empty] | 2018-02-22 | 2017-09-05 01:00 | 2021-07-30 | Yes | STD |  | 2019-12-13 | 2021-04-02 | 476 | 301 | 175 |  |  | 2021-07-12 | Connected |  | No
National Grid | NEW MARLBOROUGH | 178063 | 1230 | 2000 | Solar | 09_1109W1 | 2017-09-05 01:00 | 2017-09-05 | 15 | 8 | 7 | [10 empty] | 2017-09-26 | 2017-10-18 | 15 | 0 | 15 | [10 empty] | 2018-02-22 |  | 2021-11-11 | Yes | STD |  | 2021-01-07 | 2021-04-16 | 99 | 0 | 99 |  |  | 2021-10-18 | Connected |  | No
National Grid | STURBRIDGE | 178064 | 1566 | 9 | Solar | 01_413L7 | 2017-09-05 01:00 | 2017-09-05 | 0 | 0 | 0 | 2017-09-05 |  | 140 | 15 | 125 | [20 empty] | 2017-09-27 |  | 2018-09-10 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BELLINGHAM | 178065 | 2019 | 15.2 | Solar | 05_344W4 | 2017-09-05 01:00 | 2017-09-05 | 10 | 9 | 1 | 2017-09-19 | 2017-09-19 | 0 | 0 | 0 | [20 empty] | 2017-09-20 | 2017-09-05 01:00 | 2018-09-10 |  | EXP | [6 empty] | 2017-11-13 | 2017-11-13 | 2017-11-28 | Connected |  | No
National Grid | WEYMOUTH | 178066 | 2188 | 240 | Solar | 07_12W6 | 2017-09-05 01:00 | 2017-09-16 | 45 | 45 | 0 | [10 empty] | 2017-11-21 | 2017-12-13 | 14 | 0 | 14 | [10 empty] | 2018-05-15 | 2017-09-05 01:00 | 2021-04-15 | Yes | STD |  | 2020-09-16 | 2021-03-24 | 189 | 0 | 189 |  |  | 2021-04-15 | Connected |  | No
National Grid | WEYMOUTH | 178067 | 2188 | 240 | Solar | 07_12W6 | 2017-09-05 01:00 | 2017-09-16 | 45 | 45 | 0 | [10 empty] | 2017-11-21 | 2017-12-13 | 14 | 0 | 14 | [10 empty] | 2018-05-15 | 2017-09-05 01:00 | 2021-04-15 | Yes | STD |  | 2020-09-16 | 2021-03-24 | 189 | 0 | 189 |  |  | 2021-04-13 | Connected |  | No
National Grid | WEYMOUTH | 178098 | 2188 | 240 | Solar | 07_12W6 | 2017-09-05 01:00 | 2017-09-16 | 45 | 45 | 0 | [10 empty] | 2017-11-21 | 2017-12-13 | 14 | 0 | 14 | [10 empty] | 2018-05-15 | 2017-09-05 01:00 | 2021-04-15 | Yes | STD |  | 2020-09-16 | 2021-03-24 | 189 | 0 | 189 |  |  | 2021-04-14 | Connected |  | No
National Grid | WEYMOUTH | 178099 | 2188 | 492 | Solar | 07_12W6 | 2017-09-05 01:00 | 2017-09-16 | 45 | 45 | 0 | [10 empty] | 2017-11-21 | 2017-12-13 | 14 | 0 | 14 | [10 empty] | 2018-05-15 | 2017-09-05 01:00 | 2021-04-15 | Yes | STD |  | 2020-09-16 | 2021-03-24 | 189 | 0 | 189 |  |  | 2021-04-13 | Connected |  | No
National Grid | WEYMOUTH | 178100 | 2188 | 240 | Solar | 07_12W6 | 2017-09-05 01:00 | 2017-09-16 | 45 | 45 | 0 | [10 empty] | 2017-11-21 | 2017-12-13 | 14 | 0 | 14 | [10 empty] | 2018-05-15 |  | 2021-04-15 | Yes | STD |  | 2020-09-29 | 2021-03-24 | 175 | 0 | 175 |  |  | 2021-04-15 | Connected |  | No
National Grid | SWANSEA | 178101 | 2777 | 3.8 | Solar | 05_11W84 | 2017-09-08 01:00 | 2017-09-08 | 7 | 7 | 0 | 2017-09-19 | 2017-09-20 | 1 | 0 | 1 | [20 empty] | 2017-09-20 | 2017-09-08 01:00 | 2018-09-13 |  | EXP | [8 empty] | 2018-07-25 | Connected |  | No
National Grid | PALMER | 178102 | 1069 | 4980 | Solar | 09_523L1 | 2017-09-08 01:00 | 2017-09-11 | 3 | 0 | 3 | [10 empty] | 2017-09-14 | 2017-10-09 | 17 | 0 | 17 | [10 empty] | 2018-05-21 |  | 2023-12-29 | Yes | STD |  | 2023-01-31 | 2023-09-12 | 225 | 121 | 104 |  |  | 2023-12-29 | Connected |  | No
National Grid | OXFORD | 178103 | 1540 | 249.8 | Solar | 01_406L3 | 2017-09-08 01:00 | 2018-01-29 | 10 | 0 | 10 | 2018-02-12 | 2018-03-19 | 24 | 0 | 24 | [20 empty] | 2018-06-21 |  | 2019-09-16 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | PHILLIPSTON | 178105 | 1331 | 8730 | Solar | 09_702W1 | 2017-09-08 01:00 | 2017-09-11 | 30 | 20 | 10 | [10 empty] | 2017-10-24 | 2017-11-15 | 10 | 0 | 10 | [12 empty] | 2018-09-16 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | PHILLIPSTON | 178106 | 1331 | 3230 | Solar | 09_702W1 | 2017-09-08 01:00 | 2017-09-11 | 34 | 0 | 34 | [10 empty] | 2017-10-31 | 2017-11-15 | 6 | 0 | 6 | [12 empty] | 2018-09-16 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH ANDOVER | 177528 | 1845 | 66.6 | Solar | 14_71L1 | 2017-09-11 01:00 | 2017-09-11 | 21 | 20 | 1 | 2017-10-11 | 2017-10-11 | 0 | 0 | 0 | [20 empty] | 2017-10-12 | 2017-09-11 01:00 | 2018-06-29 |  | EXP | [8 empty] | 2018-06-19 | Connected |  | Yes
National Grid | FALL RIVER | 177533 | 2720 | 9.92 | Solar | 05_28W50 | 2017-09-11 01:00 | 2017-10-11 | 22 | 22 | 0 | 2017-10-13 | 2017-10-16 | 113 | 0 | 113 | [20 empty] | 2017-10-16 |  | 2018-11-30 | Yes | EXP |  | 2018-07-26 | 2018-08-21 | 26 | 0 | 26 |  |  | 2018-11-26 | Connected |  | Yes
National Grid | SWANSEA | 195428 | 2777 | 1500 | Solar | 05_19W73 | 2017-09-13 | 2018-09-14 | 7 | 0 | 7 | [10 empty] | 2018-09-26 | 2019-07-29 | 37 | 6 | 31 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BILLERICA | 177535 | 1821 | 999 | Solar | 14_18L3 | 2017-09-14 01:00 | 2017-09-14 | 23 | 23 | 0 | [10 empty] | 2017-10-16 | 2017-11-09 | 18 | 0 | 18 | [10 empty] | 2018-06-18 |  | 2019-09-19 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | STURBRIDGE | 177536 | 1566 | 19 | Solar | 01_415L1 | 2017-09-14 01:00 | 2017-09-14 | 13 | 13 | 0 | 2017-09-28 | 2017-10-03 | 0 | 0 | 0 | [20 empty] | 2017-10-04 |  | 2018-09-19 |  | EXP | [6 empty] | 2018-01-04 | 2018-01-04 | 2018-01-02 | Connected |  | No
National Grid | NORTH ANDOVER | 177537 | 1845 | 300 | Solar | 14_43L7 | 2017-09-14 01:00 | 2017-09-27 | 18 | 18 | 0 | 2017-10-11 | 2017-11-01 | 0 | 0 | 0 | 2017-11-13 | 2017-11-13 | 0 | 0 | 0 | [5 empty] | 2017-11-13 | 2017-11-13 | 0 | 0 | 0 | [5 empty] | 2018-02-05 |  | 2018-09-19 |  | EXP | [8 empty] | 2018-05-11 | Connected |  | No
National Grid | LAWRENCE | 177566 | 1841 | 15.2 | Solar | 14_53J2 | 2017-09-14 01:00 | 2017-09-14 | 9 | 9 | 0 | 2017-09-27 | 2017-09-27 | 0 | 0 | 0 | [20 empty] | 2017-09-27 |  | 2018-09-19 |  | EXP | [6 empty] | 2018-01-09 | 2018-01-09 | 2018-01-09 | Connected |  | No
National Grid | BELLINGHAM | 177567 | 2019 | 7.6 | Solar | 05_344W4 | 2017-09-14 01:00 | 2017-09-14 | 9 | 9 | 0 | 2017-09-27 | 2017-09-27 | 124 | 0 | 124 | [20 empty] | 2017-09-27 |  | 2018-09-19 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BEVERLY | 177568 | 1915 | 15.2 | Solar | 12_18L1 | 2017-09-14 01:00 | 2017-09-14 | 9 | 9 | 0 | 2017-09-27 | 2017-10-24 | 18 | 0 | 18 | [20 empty] | 2017-09-27 |  | 2018-09-19 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH BILLERICA | 177569 | 1862 | 15.2 | Solar | 14_70L1 | 2017-09-14 01:00 | 2017-09-14 | 9 | 9 | 0 | 2017-09-27 | 2017-09-27 | 0 | 0 | 0 | [20 empty] | 2017-09-27 |  | 2018-09-19 |  | EXP | [8 empty] | 2018-06-07 | Connected |  | Yes
National Grid | WESTBOROUGH | 177570 | 1581 | 15.2 | Solar | 05_312W1 | 2017-09-15 01:00 | 2017-09-15 | 8 | 8 | 0 | 2017-09-27 | 2017-09-27 | 124 | 0 | 124 | [20 empty] | 2017-09-27 |  | 2018-09-20 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH CHELMSFORD | 177572 | 1863 | 7.6 | Solar | 14_73L1 | 2017-09-15 01:00 | 2017-09-15 | 8 | 8 | 0 | 2017-09-27 | 2018-03-26 | 105 | 0 | 105 | [20 empty] | 2017-09-27 |  | 2018-09-20 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | HARDWICK | 177573 | 1037 | 4400 | Solar | 09_604W3 | 2017-09-18 01:00 | 2017-09-19 | 17 | 10 | 7 | [10 empty] | 2017-10-13 | 2017-11-14 | 16 | 5 | 11 | [5 empty] | 2020-07-10 | 2020-10-07 | 63 | 3 | 60 |  |  |  |  | STD | [9 empty] | Group Study |  | No
National Grid | GRAFTON | 177574 | 1519 | 120.75 | Solar | 01_328W3 | 2017-09-18 01:00 | 2017-09-19 | 36 | 29 | 7 | 2017-11-17 | 2017-11-26 | 3 | 0 | 3 | [20 empty] | 2017-11-27 |  | 2018-09-24 |  | EXP | [8 empty] | 2018-09-11 | Connected |  | No
National Grid | BILLERICA | 177575 | 1821 | 480 | Solar | 14_18L1 | 2017-09-19 01:00 | 2017-09-19 | 28 | 19 | 9 | 2017-11-03 | 2017-12-11 | 12 | 12 | 0 | 2018-02-09 | 2018-02-20 | 6 | 0 | 6 | [5 empty] | 2018-02-09 | 2018-02-20 | 6 | 0 | 6 | [5 empty] | 2018-03-23 | 2017-09-19 01:00 | 2018-09-24 |  | EXP | [8 empty] | 2018-06-19 | Connected |  | No
National Grid | WORCESTER | 177605 | 1606 | 1530.048 | Solar | 01_HT48 | 2017-09-19 01:00 | 2017-09-19 | 102 | 102 | 0 | [10 empty] | 2018-02-26 | 2018-06-22 | 28 | 0 | 28 | [10 empty] | 2019-05-16 |  | 2024-07-23 | Yes | STD |  | 2023-10-12 |  | 187 | 3 | 184 |  |  |  | Construction |  | No
National Grid | LAWRENCE | 177608 | 1841 | 42 | Solar | 14_43L1 | 2017-09-20 01:00 | 2017-09-21 | 12 | 11 | 1 | 2017-10-09 | 2017-10-10 | 1 | 0 | 1 | 2018-02-09 | 2018-02-09 | 0 | 0 | 0 | [5 empty] | 2018-02-09 | 2018-02-09 | 0 | 0 | 0 | [5 empty] | 2017-10-10 |  | 2018-09-26 |  | EXP | [8 empty] | 2018-07-16 | Connected |  | No
National Grid | BEVERLY | 177609 | 1915 | 92 | Solar | 12_18J4 | 2017-09-21 01:00 | 2017-09-21 | 6 | 5 | 1 | 2017-09-29 | 2017-09-29 | 0 | 0 | 0 | [20 empty] | 2017-10-02 | 2017-09-21 01:00 | 2018-09-26 |  | EXP | [6 empty] | 2017-12-18 | 2017-12-18 | 2017-12-29 | Connected |  | No
National Grid | GREAT BARRINGTON | 177611 | 1230 | 212.75 | Solar | 09_1109W1 | 2017-09-21 01:00 | 2017-09-22 | 22 | 0 | 22 | 2017-10-24 | 2017-11-20 | 19 | 0 | 19 | [20 empty] | 2018-07-10 |  | 2019-02-14 | Yes | EXP | [8 empty] | 2019-03-01 | Connected |  | No
National Grid | NORWELL | 177613 | 2061 | 15.2 | Solar | 07_915W35 | 2017-09-22 01:00 | 2017-09-22 | 24 | 24 | 0 | 2017-10-27 | 2017-10-27 | 0 | 0 | 0 | [20 empty] | 2017-11-01 | 2017-09-22 01:00 | 2018-09-27 |  | EXP | [6 empty] | 2018-02-28 | 2018-02-28 | 2018-03-06 | Connected |  | No
National Grid | EAST BROOKFIELD | 177614 | 1515 | 1000 | Solar | 01_552L3 | 2017-09-22 01:00 | 2017-09-25 | 10 | 0 | 10 | [10 empty] | 2017-10-09 | 2017-10-31 | 16 | 0 | 16 | [10 empty] | 2018-05-14 | 2017-09-22 01:00 | 2020-12-21 | Yes | STD |  | 2020-05-20 | 2020-09-11 | 115 | 5 | 110 |  |  | 2020-12-14 | Connected |  | No
National Grid | ATTLEBORO | 177644 | 2703 | 4268 | Solar | 05_8L4 | 2017-09-22 01:00 | 2017-10-24 | 17 | 17 | 0 | [10 empty] | 2017-11-16 | 2017-12-14 | 18 | 0 | 18 | [10 empty] | 2018-07-13 |  | 2020-12-11 | Yes | STD |  | 2019-09-24 | 2020-11-19 | 422 | 5 | 417 |  |  | 2020-12-28 | Connected |  | No
National Grid | AUBURN | 177645 | 1501 | 10 | Solar | 01_26W1 | 2017-09-25 01:00 | 2017-09-26 | 27 | 27 | 0 | 2017-11-13 | 2017-11-14 | 1 | 0 | 1 | [20 empty] | 2017-11-14 |  | 2018-10-01 |  | EXP | [8 empty] | 2018-11-27 | Connected |  | No
National Grid | DRACUT | 177646 | 1826 | 11.4 | Solar | 14_75L6 | 2017-09-26 01:00 | 2017-09-27 | 7 | 7 | 0 | 2017-10-06 | 2017-10-10 | 117 | 0 | 117 | [20 empty] | 2017-10-10 |  | 2018-10-02 |  | EXP | [8 empty] | 2018-05-17 | Connected |  | No
National Grid | SPENCER | 177649 | 1562 | 7.6 | Solar | 01_552L1 | 2017-09-27 01:00 | 2017-09-27 | 8 | 8 | 0 | 2017-10-10 | 2017-10-11 | 1 | 0 | 1 | [20 empty] | 2017-10-11 |  | 2018-10-02 |  | EXP | [8 empty] | 2018-06-29 | Connected |  | No
National Grid | BROOKFIELD | 177650 | 1506 | 500 | Solar | 01_525L2 | 2017-09-27 01:00 | 2017-09-29 | 63 | 58 | 5 | [10 empty] | 2018-01-10 | 2018-02-01 | 15 | 0 | 15 | [11 empty] | 2017-09-28 01:00 | 2018-10-04 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HAMPDEN | 177651 | 1036 | 2000 | Solar | 09_139L1 | 2017-09-28 01:00 | 2017-09-29 | 10 | 4 | 6 | [10 empty] | 2017-10-16 | 2017-11-14 | 15 | 3 | 12 | [10 empty] | 2017-11-28 |  | 2021-03-31 | Yes | STD | [6 empty] | 2020-11-20 | 2020-11-20 | 2021-03-30 | Connected |  | No
National Grid | WORCESTER | 177653 | 1605 | 464 | Solar | 01_27W2 | 2017-09-29 01:00 | 2017-09-29 | 14 | 8 | 6 | 2017-10-20 | 2018-01-23 | 57 | 0 | 57 | [22 empty] | 2018-10-04 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 177683 | 1604 | 488 | Solar | 01_10J383 | 2017-09-29 01:00 | 2017-09-29 | 36 | 30 | 6 | 2017-11-30 | 2017-12-21 | 0 | 0 | 0 | [20 empty] | 2018-01-12 |  | 2020-10-23 |  | EXP |  | 2020-01-29 | 2020-04-16 | 78 | 0 | 78 |  |  | 2020-10-23 | Connected |  | No
National Grid | LANCASTER | 177684 | 1523 | 4990 | Solar |  | 2017-09-29 01:00 | 2017-09-29 | 11 | 5 | 6 | [10 empty] | 2017-10-17 | 2017-11-08 | 11 | 0 | 11 | [12 empty] | 2018-10-04 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WHITMAN | 177685 | 2382 | 10 | Solar | 07_93W43 | 2017-09-29 01:00 | 2017-10-02 | 4 | 0 | 4 | 2017-10-06 | 2017-10-10 | 117 | 0 | 117 | [20 empty] | 2017-10-10 |  | 2018-10-07 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MELROSE | 177687 | 2176 | 6.54 | Solar | 12_16W6 | 2017-09-29 01:00 | 2017-10-02 | 5 | 5 | 0 | 2017-10-06 | 2018-02-12 | 80 | 12 | 68 | [20 empty] | 2017-10-26 | 2017-10-03 01:00 | 2018-10-07 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BERLIN | 177688 | 1503 | 4950 | Solar | 05_318W3 | 2017-10-03 01:00 | 2017-10-03 | 15 | 12 | 3 | [10 empty] | 2017-10-24 | 2017-11-27 | 21 | 6 | 15 | [10 empty] | 2018-05-21 |  | 2021-08-05 | Yes | STD |  | 2021-03-14 | 2021-07-30 | 138 | 0 | 138 | 2021-06-18 | 2021-06-18 | 2021-07-30 | Connected |  | No
National Grid | DRACUT | 177689 | 1826 | 100 | Solar | 14_78L9 | 2017-10-03 01:00 | 2017-10-03 | 2 | 2 | 0 | 2017-10-27 | 2017-10-27 | 0 | 0 | 0 | [20 empty] | 2017-10-27 |  | 2018-10-08 |  | EXP | [8 empty] | 2018-06-19 | Connected |  | No
National Grid | CLARKSBURG | 177690 | 1247 | 1230 | Solar | 09_1015W2 | 2017-10-03 01:00 | 2017-10-04 | 3 | 0 | 3 | [10 empty] | 2017-10-10 | 2017-11-01 | 14 | 0 | 14 | [12 empty] | 2018-10-09 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | FALL RIVER | 177691 | 2720 | 1620 | Solar | 05_28W50 | 2017-10-03 01:00 | 2017-10-04 | 3 | 0 | 3 | [10 empty] | 2017-10-10 | 2017-11-01 | 14 | 0 | 14 | [12 empty] | 2018-10-09 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MILFORD | 177723 | 1757 | 33.3 | Solar | 05_335W5 | 2017-10-03 01:00 | 2016-06-30 | 3 | 0 | 3 | 2017-10-04 | 2017-10-04 | 0 | 0 | 0 | [20 empty] | 2017-12-06 |  | 2018-10-09 |  | EXP | [6 empty] | 2018-02-26 | 2018-02-26 | 2018-03-06 | Connected |  | No
National Grid | LAWRENCE | 177722 | 1843 | 6 | Solar | 14_61L3 | 2017-10-04 01:00 | 2017-10-04 | 19 | 17 | 2 | 2017-11-08 | 2018-03-14 | 76 | 0 | 76 | [20 empty] | 2017-11-13 |  | 2018-10-09 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NEW BRAINTREE | 177724 | 1531 | 4800 | Solar | 09_604W3 | 2017-10-04 01:00 | 2017-10-04 | 10 | 0 | 10 | [10 empty] | 2017-10-18 | 2017-11-08 | 15 | 0 | 15 | [5 empty] | 2020-07-10 | 2020-10-07 | 63 | 3 | 60 | 2018-06-14 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | EAST DOUGLAS | 177725 | 1516 | 4982 | Solar | 05_320W2 | 2017-10-04 01:00 | 2017-10-04 | 25 | 0 | 25 | [10 empty] | 2017-11-08 | 2017-12-07 | 18 | 0 | 18 | [10 empty] | 2018-05-08 |  | 2019-04-05 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 177726 | 1507 | 7.6 | Solar | 01_406L1 | 2017-10-04 01:00 | 2017-10-05 | 9 | 8 | 1 | 2017-10-19 | 2017-10-25 | 4 | 0 | 4 | [21 empty] | 2017-10-04 01:00 | 2018-10-10 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | EAST LONGMEADOW | 177727 | 1028 | 16 | Solar | 09_508L1 | 2017-10-04 01:00 | 2018-01-22 | 10 | 0 | 10 | 2018-02-05 | 2018-02-05 | 0 | 0 | 0 | [20 empty] | 2018-02-06 | 2017-10-04 01:00 | 2019-08-22 | Yes | EXP | [8 empty] | 2019-05-31 | Connected |  | No
National Grid | NEW MARLBOROUGH | 177728 | 1230 | 4930 | Solar | 09_1109W1 | 2017-10-04 01:00 | 2017-10-05 | 42 | 41 | 1 | [10 empty] | 2017-12-06 | 2018-01-11 | 26 | 11 | 15 | [10 empty] | 2018-06-12 |  | 2021-06-30 | Yes | STD |  | 2019-10-26 | 2021-04-12 | 534 | 228 | 306 |  |  | 2021-06-15 | Connected |  | No
National Grid | ANDOVER | 177730 | 1810 | 20 | Solar | 14_59L6 | 2017-10-05 01:00 | 2017-10-05 | 0 | 0 | 0 | 2018-02-13 | 2018-02-13 | 0 | 0 | 0 | [20 empty] | 2018-02-13 |  | 2018-10-10 |  | EXP | [8 empty] | 2018-06-05 | Connected |  | Yes
National Grid | EAST LONGMEADOW | 177763 | 1028 | 72 | Solar | 09_508L5 | 2017-10-05 01:00 | 2017-12-01 | 42 | 42 | 0 | 2017-12-15 | 2017-12-15 | 0 | 0 | 0 | [20 empty] | 2017-12-18 |  | 2018-10-11 |  | EXP | [6 empty] | 2018-04-20 | 2018-04-20 | 2018-04-20 | Connected |  | No
National Grid | BROCKTON | 177764 | 2301 | 9.92 | Solar | 07_98W46 | 2017-10-05 01:00 | 2017-11-01 | 25 | 25 | 0 | 2017-11-21 | 2017-11-27 | 92 | 0 | 92 | [20 empty] | 2017-11-27 |  | 2018-10-11 |  | EXP | [8 empty] | 2019-09-25 | Connected |  | No
National Grid | PALMER | 177765 | 1069 | 3014 | Solar | 09_503L1 | 2017-10-05 01:00 | 2017-10-06 | 10 | 3 | 7 | [10 empty] | 2017-10-23 | 2017-11-27 | 18 | 7 | 11 | [12 empty] | 2018-10-11 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WENDELL | 177766 | 1379 | 2790 | Solar | 09_705W1 | 2017-10-05 01:00 | 2017-10-06 | 11 | 4 | 7 | [10 empty] | 2017-10-24 | 2017-11-15 | 10 | 0 | 10 | [5 empty] | 2020-07-10 | 2020-10-02 | 60 | 3 | 57 |  |  |  |  | STD | [9 empty] | Group Study |  | No
National Grid | WARREN | 177767 | 1083 | 5000 | Solar | 09_516L2 | 2017-10-06 01:00 | 2017-10-06 | 17 | 17 | 0 | [10 empty] | 2017-11-08 | 2017-12-13 | 23 | 5 | 18 | [5 empty] | 2020-07-10 | 2020-10-02 | 60 | 3 | 57 |  |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HARDWICK | 177768 | 1031 | 5000 | Solar | 09_501L2 | 2017-10-06 01:00 | 2017-10-09 | 77 | 70 | 7 | [10 empty] | 2018-01-31 | 2018-02-22 | 15 | 0 | 15 | [5 empty] | 2020-07-10 | 2020-10-07 | 63 | 3 | 60 |  |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SEEKONK | 177769 | 2771 | 10 | Solar | 05_9L5 | 2017-10-09 01:00 | 2017-10-31 | 14 | 14 | 0 | 2017-10-31 | 2017-11-02 | 102 | 0 | 102 | [20 empty] | 2017-11-02 |  | 2018-10-15 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | PEMBROKE | 177770 | 2359 | 15.2 | Solar | 07_910W52 | 2017-10-09 01:00 | 2017-10-10 | 14 | 14 | 0 | 2017-10-31 | 2017-11-02 | 2 | 0 | 2 | [20 empty] | 2017-11-02 |  | 2018-10-15 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | REVERE | 177801 | 2151 | 15.2 | Solar | 12_16W8 | 2017-10-09 01:00 | 2017-10-11 | 13 | 10 | 3 | 2017-10-25 | 2017-10-31 | 0 | 0 | 0 | [20 empty] | 2017-11-01 |  | 2018-10-16 |  | EXP | [6 empty] | 2017-12-13 | 2017-12-13 | 2017-12-13 | Connected |  | No
National Grid | BOXFORD | 177771 | 1921 | 15.2 | Solar | 14_56L3 | 2017-10-10 01:00 | 2017-10-11 | 13 | 4 | 9 | 2017-11-06 | 2017-11-06 | 0 | 0 | 0 | [20 empty] | 2017-11-07 | 2017-10-11 01:00 | 2018-10-16 |  | EXP | [8 empty] | 2018-05-23 | Connected |  | No
National Grid | EAST BRIDGEWATER | 177803 | 2333 | 499.5 | Solar | 07_797W29 | 2017-10-11 01:00 | 2017-10-24 | 103 | 96 | 7 | 2018-03-23 | 2018-04-26 | 24 | 0 | 24 | [20 empty] | 2018-05-04 |  | 2021-02-12 | Yes | EXP |  | 2019-07-19 | 2020-08-04 | 382 | 0 | 382 |  |  | 2021-02-09 | Connected |  | No
National Grid | WORCESTER | 177804 | 1604 | 584 | Solar | 01_HT3 | 2017-10-11 01:00 | 2017-10-12 | 14 | 2 | 12 | [10 empty] | 2017-11-08 | 2017-11-28 | 12 | 0 | 12 | [12 empty] | 2018-10-17 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | ESSEX | 162552 | 1929 | 10 | Solar | 12_51T1 | 2017-10-12 01:00 | 2017-10-12 | 1 | 0 | 1 | [27 empty] | 2018-10-12 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SEEKONK | 177805 | 2771 | 496 | Solar | 05_7L5 | 2017-10-12 01:00 | 2017-10-24 | 30 | 23 | 7 | [10 empty] | 2017-12-08 | 2018-01-05 | 19 | 0 | 19 | [10 empty] | 2018-07-23 | 2017-10-12 01:00 | 2019-07-26 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LANCASTER | 177806 | 1523 | 15 | Solar | 01_216W3 | 2017-10-12 01:00 | 2017-10-13 | 8 | 0 | 8 | 2017-10-25 | 2017-12-29 | 68 | 0 | 68 | [20 empty] | 2017-10-26 |  | 2019-09-26 | Yes | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BOLTON | 177807 | 1740 | 20 | Solar | 01_225W1 | 2017-10-12 01:00 | 2017-10-13 | 10 | 0 | 10 | 2017-10-27 | 2017-10-27 | 0 | 0 | 0 | [20 empty] | 2017-10-27 |  | 2018-10-18 |  | EXP | [6 empty] | 2017-12-28 | 2017-12-28 | 2017-12-28 | Connected |  | No
National Grid | SAUGUS | 177808 | 1906 | 7.6 | Solar | 12_7J903 | 2017-10-12 01:00 | 2017-10-13 | 8 | 0 | 8 | 2017-10-25 | 2018-03-26 | 86 | 0 | 86 | [20 empty] | 2017-10-26 |  | 2018-10-18 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | PETERSHAM | 177809 | 1366 | 50 | Solar | 09_604W1 | 2017-10-12 01:00 | 2017-10-13 | 10 | 0 | 10 | 2017-10-27 | 2017-12-05 | 24 | 0 | 24 | [20 empty] | 2018-02-05 |  | 2018-10-18 |  | EXP | [8 empty] | 2018-08-27 | Connected |  | Yes
National Grid | MEDFORD | 177838 | 2155 | 3.8 | Solar | 12_37W4 | 2017-10-13 01:00 | 2017-10-13 | 11 | 10 | 1 | 2017-10-31 | 2018-03-02 | 78 | 0 | 78 | [20 empty] | 2017-11-02 |  | 2018-10-18 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | PEPPERELL | 177839 | 1463 | 266.4 | Solar | 01_226L1 | 2017-10-13 01:00 | 2017-10-16 | 54 | 50 | 4 | 2018-01-11 | 2018-02-05 | 0 | 0 | 0 | 2018-02-28 | 2018-07-26 | 26 | 0 | 26 | [5 empty] | 2018-02-28 | 2018-07-26 | 26 | 0 | 26 | [6 empty] | 2017-10-17 01:00 | 2018-10-21 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTHBRIDGE | 177840 | 1534 | 4980 | Solar | 05_320W3 | 2017-10-17 01:00 | 2017-10-17 | 17 | 12 | 5 | [10 empty] | 2017-11-08 | 2017-11-30 | 18 | 3 | 15 | [10 empty] | 2018-06-13 | 2017-10-17 01:00 | 2021-12-31 | Yes | STD |  | 2021-09-04 | 2021-12-30 | 118 | 4 | 114 |  |  | 2021-12-28 | Connected |  | No
National Grid | NORTHBRIDGE | 177841 | 1534 | 4980 | Solar | 05_321W5 | 2017-10-17 01:00 | 2017-11-01 | 5 | 0 | 5 | [10 empty] | 2017-11-08 | 2017-11-15 | 4 | 0 | 4 | [10 empty] | 2018-05-22 |  | 2021-04-21 | Yes | STD |  | 2020-11-06 | 2021-02-25 | 111 | 0 | 111 | 2021-03-17 | 2021-03-17 | 2021-04-21 | Connected |  | No
National Grid | WORCESTER | 177844 | 1605 | 17.6 | Solar | 01_11J330 | 2017-10-17 01:00 | 2018-01-03 | 53 | 53 | 0 | 2018-01-17 | 2018-01-18 | 0 | 0 | 0 | [20 empty] | 2018-01-18 |  | 2018-10-24 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | TYNGSBORO | 177845 | 1879 | 910 | Solar | 14_211L2 | 2017-10-17 01:00 | 2017-10-19 | 17 | 10 | 7 | [10 empty] | 2017-11-21 | 2017-12-14 | 16 | 0 | 16 | [12 empty] | 2018-10-24 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ROCHDALE | 177846 | 1542 | 1460 | Solar | 01_21W1 | 2017-10-17 01:00 | 2017-10-19 | 13 | 0 | 13 | [10 empty] | 2017-11-15 | 2017-12-11 | 17 | 0 | 17 | [11 empty] | 2017-10-17 01:00 | 2018-10-24 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ROCHDALE | 177847 | 1542 | 900 | Solar | 01_406L1 | 2017-10-17 01:00 | 2017-10-19 | 13 | 0 | 13 | [10 empty] | 2017-11-15 | 2017-12-11 | 17 | 0 | 17 | [12 empty] | 2019-10-01 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | WARE | 177876 | 1082 | 900 | Solar | 09_501L1 | 2017-10-17 01:00 | 2017-10-19 | 22 | 21 | 1 | [20 empty] | 2020-07-10 | 2020-10-07 | 63 | 3 | 60 |  |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WARE | 177877 | 1082 | 900 | Solar | 09_501L1 | 2017-10-17 01:00 | 2017-10-19 | 22 | 21 | 1 | [20 empty] | 2020-07-10 | 2020-10-07 | 63 | 3 | 60 |  | 2017-10-17 01:00 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MONSON | 177878 | 1057 | 250 | Solar | 09_139L1 | 2017-10-17 01:00 | 2017-10-19 | 15 | 0 | 15 | 2017-11-09 | 2017-12-11 | 19 | 0 | 19 | 2018-02-22 | 2018-03-22 | 20 | 0 | 20 | [5 empty] | 2018-02-22 | 2018-03-22 | 20 | 0 | 20 | [5 empty] | 2018-06-27 |  | 2020-09-11 | Yes | EXP |  | 2019-07-26 | 2020-08-03 | 372 | 0 | 372 |  |  | 2020-09-10 | Connected |  | No
National Grid | WILBRAHAM | 177879 | 1095 | 7.6 | Solar | 09_507L1 | 2017-10-18 01:00 | 2017-10-30 | 10 | 10 | 0 | 2017-11-13 | 2017-11-14 | 0 | 0 | 0 | [20 empty] | 2017-11-14 |  | 2018-10-24 |  | EXP | [8 empty] | 2018-08-24 | Connected |  | Yes
National Grid | SALISBURY | 177880 | 1952 | 15.2 | Solar | 14_7L4 | 2017-10-18 01:00 | 2017-10-19 | 7 | 6 | 1 | 2017-10-31 | 2017-11-02 | 102 | 0 | 102 | [20 empty] | 2017-11-02 |  | 2018-10-24 |  | EXP | [8 empty] | 2018-07-18 | Connected |  | No
National Grid | EASTON | 177881 | 2356 | 19.6 | Solar | 07_92W78 | 2017-10-18 01:00 | 2017-10-19 | 8 | 2 | 6 | 2017-11-07 | 2017-11-07 | 0 | 0 | 0 | [20 empty] | 2017-11-07 |  | 2018-10-24 |  | EXP | [6 empty] | 2018-03-07 | 2018-03-07 | 2018-03-19 | Connected |  | No
National Grid | WINCHENDON | 177882 | 1475 | 3300 | Solar | 01_607W1 | 2017-10-18 01:00 | 2017-10-19 | 42 | 0 | 42 | [10 empty] | 2017-12-21 | 2017-12-21 | 0 | 0 | 0 | [10 empty] | 2018-09-11 |  | 2018-10-24 |  | STD |  | 2018-10-10 | 2019-03-01 | 142 | 0 | 142 |  |  |  | Withdrawn |  | No
National Grid | ANDOVER | 177883 | 1810 | 20 | Solar | 14_62L2 | 2017-10-19 01:00 | 2017-10-19 | 58 | 52 | 6 | [27 empty] | 2018-10-24 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | CLINTON | 177884 | 1510 | 38 | Solar | 01_216W6 | 2017-10-19 01:00 | 2017-10-20 | 10 | 10 | 0 | 2017-11-13 | 2017-11-13 | 0 | 0 | 0 | [20 empty] | 2017-11-14 |  | 2018-10-25 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEICESTER | 177885 | 1524 | 4950 | Solar | 01_2236W3 | 2017-10-20 01:00 | 2017-10-20 | 4 | 0 | 4 | [10 empty] | 2017-10-26 | 2017-11-28 | 16 | 5 | 11 | [5 empty] | 2020-07-10 | 2020-10-02 | 59 | 3 | 56 |  |  |  |  | STD | [9 empty] | Group Study |  | No
National Grid | BEVERLY | 177914 | 1915 | 365 | Natural Gas | 12_72L1 | 2017-10-20 01:00 | 2017-10-20 | 55 | 0 | 55 | [10 empty] | 2018-01-11 | 2018-02-16 | 25 | 0 | 25 | [10 empty] | 2018-10-19 |  | 2019-06-28 |  | STD | [8 empty] | 2019-06-13 | Connected |  | No
National Grid | BEVERLY | 177916 | 1915 | 144 | Solar | 12_51L1 | 2017-10-20 01:00 | 2017-10-23 | 4 | 0 | 4 | 2017-10-27 | 2017-11-01 | 3 | 0 | 3 | [20 empty] | 2017-11-01 |  | 2018-10-28 |  | EXP | [8 empty] | 2018-05-29 | Connected |  | No
National Grid | EAST LONGMEADOW | 177917 | 1028 | 72 | Solar | 09_508L5 | 2017-10-20 01:00 | 2017-10-23 | 12 | 5 | 7 | 2017-11-14 | 2017-11-16 | 0 | 0 | 0 | [20 empty] | 2017-11-17 |  | 2018-10-28 |  | EXP | [8 empty] | 2018-10-11 | Connected |  | No
National Grid | FALL RIVER | 177918 | 2721 | 312 | Solar | 05_106W42 | 2017-10-20 01:00 | 2017-10-23 | 5 | 0 | 5 | 2017-11-03 | 2017-12-04 | 18 | 0 | 18 | [20 empty] | 2017-12-04 |  | 2018-10-28 |  | EXP | [8 empty] | 2018-08-03 | Connected |  | No
National Grid | GARDNER | 177919 | 1440 | 3300 | Solar | 01_607W1 | 2017-10-23 01:00 | 2017-10-25 | 5 | 0 | 5 | [10 empty] | 2017-11-08 |  | 100 | 0 | 100 | [11 empty] | 2017-10-23 01:00 | 2018-10-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WINCHENDON | 177920 | 1475 | 9765 | Solar | 01_612W3 | 2017-10-23 01:00 | 2017-10-25 | 13 | 8 | 5 | [10 empty] | 2017-11-21 | 2017-12-19 | 19 | 0 | 19 | [13 empty] | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | HOLBROOK | 177921 | 2343 | 10 | Solar | 07_2W1 | 2017-10-23 01:00 | 2017-10-26 | 2 | 0 | 2 | 2017-11-06 | 2017-11-07 | 2 | 0 | 2 | [20 empty] | 2017-11-07 |  | 2018-10-31 |  | EXP | [8 empty] | 2019-05-03 | Connected |  | No
National Grid | NORTH ANDOVER | 177954 | 1845 | 20 | Solar | 14_56L2 | 2017-10-23 01:00 | 2017-10-26 | 101 | 100 | 1 | [27 empty] | 2018-10-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HUBBARDSTON | 177955 | 1452 | 3300 | Solar | 09_604W4 | 2017-10-23 01:00 | 2017-10-26 | 37 | 0 | 37 | [10 empty] | 2017-12-21 | 2018-01-02 | 7 | 0 | 7 | [10 empty] | 2018-07-31 |  | 2018-10-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | PALMER | 177956 | 1069 | 1980 | Solar | 09_523L4 | 2017-10-23 01:00 | 2017-10-26 | 104 | 100 | 4 | [27 empty] | 2018-10-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ATHOL | 177957 | 1331 | 1980 | Solar | 09_702W3 | 2017-10-23 01:00 | 2017-10-26 | 51 | 0 | 51 | [10 empty] | 2018-01-11 | 2018-02-01 | 14 | 0 | 14 | [10 empty] | 2018-06-12 |  | 2018-10-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | PLAINVILLE | 178797 | 2762 | 2310 | Solar | 05_3451W3 | 2017-10-23 01:00 | 2017-11-04 | 31 | 29 | 2 | [10 empty] | 2017-12-21 | 2018-01-04 | 8 | 0 | 8 | [10 empty] | 2018-08-15 |  | 2018-10-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 177922 | 1507 | 4980 | Solar | 01_415L2 | 2017-10-24 01:00 | 2017-10-26 | 7 | 3 | 4 | [10 empty] | 2017-11-14 | 2017-12-08 | 17 | 0 | 17 | [12 empty] | 2018-10-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | GLOUCESTER | 177959 | 1930 | 20 | Solar | 12_51T3 | 2017-10-24 01:00 | 2017-10-26 | 2 | 0 | 2 | 2017-11-06 | 2017-11-07 | 102 | 0 | 102 | [20 empty] | 2017-11-07 |  | 2018-10-31 |  | EXP | [8 empty] | 2018-07-10 | Connected |  | Yes
National Grid | RANDOLPH | 177961 | 2368 | 8.96 | Solar | 07_97W2 | 2017-10-24 01:00 | 2017-10-26 | 12 | 11 | 1 | 2017-11-21 | 2017-11-27 | 2 | 0 | 2 | [20 empty] | 2017-11-27 |  | 2018-10-31 |  | EXP | [8 empty] | 2018-11-26 | Connected |  | Yes
National Grid | LYNN | 177962 | 1905 | 3.8 | Solar | 12_29W3 | 2017-10-24 01:00 | 2017-10-26 | 15 | 14 | 1 | 2017-11-27 | 2018-02-15 | 55 | 0 | 55 | [20 empty] | 2017-11-27 |  | 2018-10-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | RANDOLPH | 177991 | 2368 | 15.2 | Solar | 07_97W1 | 2017-10-24 01:00 | 2017-10-27 | 14 | 14 | 0 | 2017-11-27 | 2017-11-30 | 3 | 0 | 3 | [20 empty] | 2017-11-27 |  | 2018-11-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SALISBURY | 177992 | 1952 | 7.6 | Solar | 14_7L4 | 2017-10-24 01:00 | 2017-10-27 | 5 | 5 | 0 | 2017-11-13 | 2017-11-14 | 0 | 0 | 0 | [20 empty] | 2017-11-14 |  | 2018-11-01 |  | EXP | [8 empty] | 2019-02-05 | Connected |  | Yes
National Grid | METHUEN | 177993 | 1844 | 15.2 | Solar | 14_74L2 | 2017-10-24 01:00 | 2017-10-27 | 14 | 14 | 0 | 2017-11-27 | 2017-11-27 | 0 | 0 | 0 | [20 empty] | 2017-11-27 |  | 2018-11-01 |  | EXP | [8 empty] | 2018-07-18 | Connected |  | No
National Grid | DIGHTON | 177995 | 2715 | 20 | Solar | 05_19W73 | 2017-10-24 01:00 | 2017-10-27 | 8 | 8 | 0 | 2017-11-16 | 2017-11-16 | 0 | 0 | 0 | [20 empty] | 2017-11-17 |  | 2018-11-01 |  | EXP | [6 empty] | 2017-12-27 | 2017-12-27 | 2018-01-05 | Connected |  | No
National Grid | HARDWICK | 177996 | 1037 | 1610 | Solar | 09_501L2 | 2017-10-25 01:00 | 2017-10-27 | 51 | 51 | 0 | [10 empty] | 2018-01-22 | 2018-02-14 | 17 | 0 | 17 | [12 empty] | 2018-11-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HARDWICK | 177997 | 1037 | 1610 | Solar | 09_501L2 | 2017-10-25 01:00 | 2017-10-27 | 51 | 51 | 0 | [10 empty] | 2018-01-22 | 2018-02-14 | 17 | 0 | 17 | [12 empty] | 2018-11-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WINCHENDON | 177998 | 1475 | 660 | Solar | 01_607W1 | 2017-10-25 01:00 | 2017-10-27 | 25 | 25 | 0 | [10 empty] | 2017-12-12 | 2018-01-19 | 25 | 16 | 9 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WINCHENDON | 177999 | 1475 | 2904 | Solar | 01_612T2 | 2017-10-25 01:00 | 2017-10-27 | 25 | 25 | 0 | [10 empty] | 2017-12-12 | 2018-01-10 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | CHELMSFORD | 178000 | 1824 | 7.6 | Solar | 14_24L2 | 2017-10-25 01:00 | 2017-10-27 | 62 | 62 | 0 | 2018-02-06 | 2018-02-07 | 1 | 0 | 1 | [20 empty] | 2018-02-07 | 2017-10-25 01:00 | 2018-11-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BEVERLY | 178031 | 1915 | 5.2 | Solar | 12_72L1 | 2017-10-25 01:00 | 2017-10-27 | 24 | 24 | 0 | 2017-12-11 | 2017-12-11 | 0 | 0 | 0 | [20 empty] | 2017-12-11 |  | 2019-10-15 | Yes | EXP |  | 2018-08-08 | 2018-10-05 | 58 | 0 | 58 |  |  |  | Withdrawn |  | Yes
National Grid | LOWELL | 177958 | 1854 | 6 | Solar | 14_21L3 | 2017-10-26 01:00 | 2017-10-26 | 80 | 79 | 1 | [27 empty] | 2018-10-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CLINTON | 178032 | 1510 | 299 | Solar | 01_216W1 | 2017-10-26 01:00 | 2017-11-16 | 17 | 17 | 0 | 2017-11-30 | 2018-01-04 | 8 | 8 | 0 | [20 empty] | 2018-01-04 |  | 2019-11-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CLINTON | 178033 | 1510 | 296 | Solar | 01_216W2 | 2017-10-26 01:00 | 2017-11-16 | 17 | 17 | 0 | 2017-11-30 | 2018-01-04 | 8 | 8 | 0 | [20 empty] | 2018-01-04 |  | 2019-11-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOUTHBOROUGH | 178034 | 1772 | 92 | Solar | 05_314W2 | 2017-10-26 01:00 | 2017-10-27 | 5 | 0 | 5 | 2017-11-13 |  | 98 | 0 | 98 | [20 empty] | 2017-11-15 |  | 2018-11-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HOPEDALE | 178035 | 1747 | 20 | Solar | 05_335W9 | 2017-10-26 01:00 | 2017-10-27 | 67 | 67 | 0 | 2018-02-13 | 2018-02-13 | 36 | 0 | 36 | [20 empty] | 2018-02-13 |  | 2018-11-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOMERSET | 178036 | 2725 | 9.86 | Solar | 05_11W84 | 2017-10-27 01:00 | 2017-10-31 | 39 | 39 | 0 | 2018-01-04 | 2018-01-08 | 2 | 0 | 2 | [20 empty] | 2018-01-08 |  | 2018-11-05 |  | EXP | [8 empty] | 2018-05-17 | Connected |  | No
National Grid | SWAMPSCOTT | 178037 | 1907 | 11.4 | Solar | 12_22W3 | 2017-10-27 01:00 | 2017-10-31 | 4 | 4 | 0 | 2017-11-13 | 2017-11-13 | 0 | 0 | 0 | [20 empty] | 2017-11-13 |  | 2018-11-05 |  | EXP | [8 empty] | 2018-07-03 | Connected |  | No
National Grid | ESSEX | 178038 | 1929 | 17.6 | Solar | 12_51T2 | 2017-10-27 01:00 | 2017-10-31 | 66 | 66 | 0 | 2018-02-13 | 2018-03-22 | 15 | 0 | 15 | [20 empty] | 2018-02-13 |  | 2019-03-30 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MONSON | 178039 | 1057 | 2490 | Solar | 09_0507 | 2017-10-27 01:00 | 2017-10-31 | 9 | 0 | 9 | [10 empty] | 2017-11-14 | 2017-12-11 | 17 | 0 | 17 | [10 empty] | 2018-09-25 |  | 2021-02-26 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH ANDOVER | 178069 | 1845 | 20 | Solar | 14_56L2 | 2017-10-30 01:00 | 2017-10-31 | 66 | 66 | 0 | 2018-02-13 | 2018-02-13 | 36 | 0 | 36 | [20 empty] | 2018-02-13 |  | 2018-11-05 |  | EXP | [8 empty] | 2018-10-16 | Connected |  | Yes
National Grid | MANCHESTER | 178070 | 1944 | 144 | Solar | 12_51T1 | 2017-10-31 01:00 | 2017-11-01 | 9 | 9 | 0 | 2017-11-20 | 2017-11-30 | 6 | 0 | 6 | [20 empty] | 2017-11-30 |  | 2018-11-06 |  | EXP | [8 empty] | 2018-08-27 | Connected |  | No
National Grid | NEWBURY | 178071 | 1951 | 15.2 | Solar | 14_60L1 | 2017-10-31 01:00 | 2017-11-01 | 0 | 0 | 0 | 2017-11-06 | 2018-02-12 | 65 | 0 | 65 | [20 empty] | 2017-11-07 |  | 2018-11-06 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | QUINCY | 178072 | 2169 | 7.6 | Solar | 07_3W2 | 2017-11-01 01:00 | 2017-11-01 | 9 | 9 | 0 | 2017-11-20 |  | 93 | 0 | 93 | [20 empty] | 2017-11-21 |  | 2018-11-06 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LENOX | 178073 | 1240 | 120.75 | Solar | 09_1103W2 | 2017-11-02 01:00 | 2017-11-02 | 8 | 8 | 0 | 2017-11-17 | 2017-11-17 | 0 | 0 | 0 | [20 empty] | 2017-11-17 |  | 2018-11-07 |  | EXP | [6 empty] | 2018-03-14 | 2018-03-14 | 2018-04-11 | Connected |  | No
National Grid | ESSEX | 178074 | 1929 | 20 | Solar | 12_51T1 | 2017-11-02 01:00 | 2017-11-02 | 91 | 91 | 0 | 2018-04-05 | 2018-04-05 | 0 | 0 | 0 | [20 empty] | 2018-04-06 |  | 2018-11-07 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEST NEWBURY | 178075 | 1985 | 3375 | Solar | 14_47L2 | 2017-11-03 01:00 | 2017-11-03 | 24 | 19 | 5 | [10 empty] | 2017-12-12 | 2018-01-09 | 18 | 4 | 14 | [12 empty] | 2018-11-08 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | AUBURN | 178076 | 1501 | 4750 | Solar | 01_2236W4 | 2017-11-03 01:00 | 2017-11-03 | 24 | 19 | 5 | [10 empty] | 2017-12-12 | 2018-01-09 | 18 | 7 | 11 | [5 empty] | 2020-07-10 | 2020-10-02 | 60 | 3 | 57 |  |  |  |  | STD | [9 empty] | Group Study |  | No
National Grid | AVON | 178077 | 2322 | 15.2 | Solar | 07_75W5 | 2017-11-03 01:00 | 2017-11-03 | 55 | 55 | 0 | 2018-01-29 |  | 47 | 0 | 47 | [20 empty] | 2018-01-29 |  | 2020-11-27 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | TOPSFIELD | 178107 | 1983 | 103.5 | Solar | 12_26L1 | 2017-11-03 01:00 | 2017-11-06 | 41 | 41 | 0 | 2018-01-08 | 2018-01-08 | 0 | 0 | 0 | [20 empty] | 2018-01-08 |  | 2019-09-16 |  | EXP | [8 empty] | 2019-09-23 | Connected |  | No
National Grid | GARDNER | 177538 | 1440 | 4990 | Solar | 01_607W1 | 2017-11-06 | 2017-11-07 | 26 | 16 | 10 | [10 empty] | 2017-12-15 | 2018-01-10 | 16 | 0 | 16 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | GARDNER | 177539 | 1440 | 4990 | Solar | 01_607W6 | 2017-11-06 | 2017-11-07 | 23 | 13 | 10 | [10 empty] | 2017-12-12 | 2018-01-10 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | OAKHAM | 177540 | 1068 | 4400 | Solar | 09_1194T1 | 2017-11-06 | 2017-11-07 | 37 | 36 | 1 | [10 empty] | 2018-01-03 | 2018-02-20 | 32 | 15 | 17 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | OAKHAM | 177541 | 1068 | 4400 | Solar | 09_1194T1 | 2017-11-06 | 2017-11-07 | 20 | 20 | 0 | [10 empty] | 2017-12-07 | 2018-02-20 | 49 | 32 | 17 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 178108 | 2301 | 48 | Solar | 07_92W44 | 2017-11-06 | 2017-11-06 | 16 | 16 | 0 | 2017-11-30 | 2017-12-01 | 1 | 0 | 1 | [20 empty] | 2017-12-01 |  | 2018-11-11 |  | EXP | [6 empty] | 2018-03-26 | 2018-03-26 | 2018-07-23 | Connected |  | No
National Grid | HUBBARDSTON | 178109 | 1452 | 3396 | Solar | 01_609W1 | 2017-11-06 | 2017-11-07 | 22 | 0 | 22 | [10 empty] | 2017-12-11 | 2018-01-09 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | HUBBARDSTON | 178110 | 1452 | 8730 | Solar | 01_609W1 | 2017-11-06 | 2017-11-07 | 22 | 10 | 12 | [10 empty] | 2017-12-11 | 2018-01-09 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | GLOUCESTER | 178111 | 1930 | 15 | Solar | 12_51T1 | 2017-11-06 | 2018-03-09 | 81 | 80 | 1 | 2018-03-23 | 2018-04-27 | 53 | 0 | 53 | [20 empty] | 2018-05-14 |  | 2018-11-12 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | GARDNER | 178112 | 1440 | 4990 | Solar | 01_607W6 | 2017-11-06 | 2017-11-07 | 23 | 13 | 10 | [10 empty] | 2017-12-12 | 2018-01-10 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | GARDNER | 178113 | 1440 | 4990 | Solar | 01_607W1 | 2017-11-06 | 2017-11-07 | 23 | 13 | 10 | [10 empty] | 2017-12-12 | 2018-01-10 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | GARDNER | 178114 | 1440 | 4990 | Solar | 01_607W7 | 2017-11-06 | 2017-11-07 | 23 | 13 | 10 | [10 empty] | 2017-12-12 | 2018-01-10 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | GARDNER | 178115 | 1440 | 4990 | Solar | 01_607W7 | 2017-11-06 | 2017-11-07 | 23 | 13 | 10 | [10 empty] | 2017-12-12 | 2018-01-10 | 19 | 0 | 19 | [11 empty] | 2017-11-07 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WARE | 177542 | 1082 | 4000 | Solar | 09_509L2 | 2017-11-07 | 2017-11-08 | 51 | 42 | 9 | [10 empty] | 2018-01-25 | 2018-02-15 | 15 | 0 | 15 | [10 empty] | 2018-08-31 |  |  | Yes | STD | [9 empty] | Study |  | No
National Grid | WARE | 177543 | 1082 | 500 | Solar | 09_509L2 | 2017-11-07 | 2017-11-08 | 50 | 42 | 8 | [10 empty] | 2018-01-25 | 2018-02-15 | 15 | 0 | 15 | [10 empty] | 2018-08-31 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WARE | 177544 | 1082 | 500 | Solar | 09_509L2 | 2017-11-07 | 2017-11-08 | 51 | 42 | 9 | [10 empty] | 2018-01-25 | 2018-02-15 | 15 | 0 | 15 | [10 empty] | 2018-08-31 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WARE | 177545 | 1082 | 500 | Solar | 09_509L2 | 2017-11-07 | 2017-11-08 | 50 | 42 | 8 | [10 empty] | 2018-01-25 | 2018-02-15 | 15 | 0 | 15 | [10 empty] | 2018-08-31 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WARE | 177546 | 1082 | 500 | Solar | 09_509L2 | 2017-11-07 | 2017-11-08 | 50 | 42 | 8 | [10 empty] | 2018-01-25 | 2018-02-15 | 15 | 0 | 15 | [10 empty] | 2018-08-31 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WARE | 177547 | 1082 | 500 | Solar | 09_509L2 | 2017-11-07 | 2017-11-08 | 50 | 42 | 8 | [10 empty] | 2018-01-25 | 2018-02-15 | 15 | 0 | 15 | [12 empty] | 2018-11-13 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WARE | 177576 | 1082 | 500 | Solar | 09_509L2 | 2017-11-07 | 2017-11-08 | 52 | 42 | 10 | [10 empty] | 2018-01-24 | 2018-02-15 | 16 | 0 | 16 | [12 empty] | 2018-11-13 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WARE | 177577 | 1082 | 500 | Solar | 09_509L2 | 2017-11-07 | 2017-11-08 | 50 | 42 | 8 | [10 empty] | 2018-01-25 | 2018-02-15 | 15 | 0 | 15 | [10 empty] | 2018-08-31 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WARE | 177578 | 1082 | 500 | Solar | 09_509L2 | 2017-11-07 | 2017-11-08 | 50 | 42 | 8 | [10 empty] | 2018-01-25 | 2018-02-15 | 15 | 0 | 15 | [10 empty] | 2018-08-31 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WARE | 177579 | 1082 | 500 | Solar | 09_509L2 | 2017-11-07 | 2017-11-08 | 50 | 42 | 8 | [10 empty] | 2018-01-25 | 2018-02-15 | 15 | 0 | 15 | [10 empty] | 2018-08-31 | 2017-11-07 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WARE | 177580 | 1082 | 4000 | Solar | 09_509L2 | 2017-11-07 | 2017-11-08 | 50 | 42 | 8 | [10 empty] | 2018-01-25 | 2018-02-15 | 15 | 0 | 15 | [10 empty] | 2018-08-31 |  |  | Yes | STD | [9 empty] | Study |  | No
National Grid | WARE | 177581 | 1082 | 500 | Solar | 09_509L2 | 2017-11-07 | 2017-11-08 | 50 | 42 | 8 | [10 empty] | 2018-01-25 | 2018-02-15 | 15 | 0 | 15 | [10 empty] | 2018-08-31 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WARE | 177582 | 1082 | 500 | Solar | 09_509L2 | 2017-11-07 | 2017-11-08 | 50 | 42 | 8 | [10 empty] | 2018-01-25 | 2018-02-15 | 15 | 0 | 15 | [10 empty] | 2018-08-31 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WARE | 177583 | 1082 | 500 | Solar | 09_509L2 | 2017-11-07 | 2017-11-08 | 50 | 42 | 8 | [10 empty] | 2018-01-25 | 2018-02-15 | 15 | 0 | 15 | [10 empty] | 2018-08-31 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WARE | 177584 | 1082 | 500 | Solar | 09_509L2 | 2017-11-07 | 2017-11-08 | 50 | 42 | 8 | [10 empty] | 2018-01-25 | 2018-02-15 | 15 | 0 | 15 | [10 empty] | 2018-08-31 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WARE | 177585 | 1082 | 500 | Solar | 09_509L2 | 2017-11-07 | 2017-11-08 | 50 | 42 | 8 | [10 empty] | 2018-01-25 | 2018-02-15 | 15 | 0 | 15 | [10 empty] | 2018-08-31 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WARE | 177615 | 1082 | 500 | Solar | 09_509L2 | 2017-11-07 | 2017-11-08 | 50 | 42 | 8 | [10 empty] | 2018-01-25 | 2018-02-15 | 15 | 0 | 15 | [10 empty] | 2018-08-31 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH ADAMS | 177617 | 1247 | 10 | Solar | 09_1015W2 | 2017-11-07 | 2017-11-08 | 11 | 0 | 11 | 2017-11-27 | 2018-02-12 | 52 | 0 | 52 | [20 empty] | 2017-11-27 |  | 2018-11-13 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WARE | 177618 | 1082 | 500 | Solar | 09_509L2 | 2017-11-07 | 2017-11-09 | 50 | 42 | 8 | [10 empty] | 2018-01-25 | 2018-02-15 | 15 | 0 | 15 | [10 empty] | 2018-08-31 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ATHOL | 177619 | 1331 | 2200 | Solar | 09_702W1 | 2017-11-08 | 2017-11-09 | 55 | 30 | 25 | [10 empty] | 2018-02-01 | 2018-04-11 | 37 | 22 | 15 | [12 empty] | 2018-11-14 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LYNN | 177620 | 1904 | 10 | Solar | 12_29W4 | 2017-11-08 | 2017-11-09 | 99 | 89 | 10 | [27 empty] | 2018-11-14 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 177621 | 1844 | 15.2 | Solar | 14_74L1 | 2017-11-09 | 2017-11-10 | 11 | 10 | 1 | 2017-11-29 | 2017-11-30 | 0 | 0 | 0 | [20 empty] | 2017-06-13 |  | 2018-11-15 |  | EXP | [8 empty] | 2018-10-02 | Connected |  | Yes
National Grid | HOLBROOK | 177622 | 2343 | 7.6 | Solar | 07_2W1 | 2017-11-09 | 2017-11-27 | 15 | 14 | 1 | 2017-12-05 | 2017-12-06 | 83 | 0 | 83 | [20 empty] | 2017-12-06 |  | 2018-11-15 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTON | 177623 | 2766 | 11.4 | Solar | 05_4L2 | 2017-11-09 | 2017-11-27 | 15 | 14 | 1 | 2017-12-05 | 2017-12-06 | 83 | 0 | 83 | [20 empty] | 2017-12-06 |  | 2018-11-15 |  | EXP | [8 empty] | 2018-07-18 | Connected |  | No
National Grid | ANDOVER | 177624 | 1810 | 15.2 | Solar | 14_59L1 | 2017-11-09 | 2017-11-21 | 1 | 0 | 1 | 2017-12-05 | 2018-01-04 | 0 | 0 | 0 | [20 empty] | 2017-12-06 | 2017-11-09 | 2018-11-15 |  | EXP | [8 empty] | 2018-06-05 | Connected |  | No
National Grid | PALMER | 177654 | 1069 | 1986 | Solar | 09_523L2 | 2017-11-09 | 2017-11-10 | 9 | 0 | 9 | [10 empty] | 2017-11-28 | 2017-12-20 | 16 | 0 | 16 | [10 empty] | 2018-06-22 | 2017-11-09 | 2024-04-17 | Yes | STD | [8 empty] | 2023-12-29 | Connected |  | No
National Grid | TEWKSBURY | 177655 | 1876 | 2838 | Solar | 14_59L3 | 2017-11-09 | 2017-11-10 | 19 | 19 | 0 | [10 empty] | 2017-12-11 | 2018-01-30 | 34 | 0 | 34 | [10 empty] | 2018-09-28 |  | 2022-04-10 | Yes | STD |  | 2021-11-17 | 2022-01-13 | 57 | 0 | 57 |  |  | 2022-02-18 | Connected |  | No
National Grid | WILBRAHAM | 177656 | 1095 | 15.2 | Solar | 09_507L1 | 2017-11-10 | 2017-11-10 | 15 | 0 | 15 | 2017-12-05 | 2017-12-06 | 1 | 0 | 1 | [20 empty] | 2017-12-06 |  | 2018-11-15 |  | EXP | [8 empty] | 2018-12-21 | Connected |  | Yes
National Grid | WEST BRIDGEWATER | 177657 | 2379 | 1000 | Solar | 07_797W20 | 2017-11-10 | 2017-11-22 | 15 | 14 | 1 | [10 empty] | 2017-12-14 | 2018-01-12 | 19 | 0 | 19 | [10 empty] | 2018-06-13 |  | 2018-11-19 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LYNN | 177658 | 1904 | 66.6 | Solar | 12_29W5 | 2017-11-13 | 2018-01-26 | 49 | 49 | 0 | 2018-01-26 | 2018-01-29 | 0 | 0 | 0 | [20 empty] | 2018-01-29 |  | 2019-04-19 |  | EXP | [8 empty] | 2019-02-04 | Connected |  | No
National Grid | FALL RIVER | 177659 | 2720 | 240 | Solar | 05_28W41 | 2017-11-13 | 2017-11-14 | 51 | 42 | 9 | 2018-01-29 | 2018-02-08 | 47 | 0 | 47 | [20 empty] | 2018-02-09 |  | 2018-11-19 |  | EXP | [8 empty] | 2018-06-19 | Connected |  | Yes
National Grid | EAST LONGMEADOW | 177660 | 1028 | 15.2 | Solar | 09_508L4 | 2017-11-13 | 2017-12-11 | 50 | 50 | 0 | 2018-01-29 |  | 47 | 0 | 47 | [20 empty] | 2018-01-29 |  | 2018-11-19 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 177661 | 2302 | 16 | Solar | 07_911W56 | 2017-11-13 | 2018-02-16 | 64 | 64 | 0 | 2018-02-16 | 2018-06-22 | 33 | 0 | 33 | [20 empty] | 2018-06-22 |  | 2018-11-19 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH ANDOVER | 177662 | 1845 | 249 | Solar | 14_71L3 | 2017-11-13 | 2017-11-14 | 15 | 5 | 10 | 2017-12-06 | 2017-12-20 | 10 | 0 | 10 | [20 empty] | 2017-12-21 |  | 2019-12-02 |  | EXP | [8 empty] | 2019-12-16 | Connected |  | No
National Grid | WESTMINSTER | 177663 | 1473 | 4980 | Solar | 01_610W3 | 2017-11-13 | 2017-11-14 | 9 | 0 | 9 | [10 empty] | 2017-11-29 | 2017-12-20 | 15 | 0 | 15 | [10 empty] | 2018-07-17 |  | 2018-11-19 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | PETERSHAM | 178292 | 1366 | 14.2 | Solar | 09_604W1 | 2017-11-13 | 2018-05-23 | 0 | 0 | 0 | 2018-05-23 | 2018-05-22 | 0 | 0 | 0 | [20 empty] | 2018-09-11 |  | 2018-11-19 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 178293 | 1843 | 160 | Solar | 14_1J2 | 2017-11-14 | 2018-01-08 | 35 | 26 | 9 | 2018-01-08 | 2018-01-09 | 0 | 0 | 0 | [20 empty] | 2018-01-09 |  | 2019-12-23 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOMERSET | 178294 | 2725 | 2050 | Solar | 05_11W84 | 2017-11-14 | 2017-11-15 | 49 | 49 | 0 | [10 empty] | 2018-01-29 | 2018-03-23 | 27 | 14 | 13 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | LAWRENCE | 178295 | 1841 | 15.2 | Solar | 14_8L2 | 2017-11-15 | 2018-01-22 | 3 | 0 | 3 | 2018-05-17 | 2018-06-21 | 24 | 0 | 24 | [20 empty] | 2018-06-21 |  | 2018-11-21 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GRAFTON | 178296 | 1519 | 10 | Solar | 01_304W1 | 2017-11-15 | 2017-11-16 | 63 | 49 | 14 | 2018-02-20 | 2018-02-21 | 32 | 0 | 32 | [20 empty] | 2018-02-21 | 2017-11-15 | 2018-11-21 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 178297 | 1507 | 2640 | Solar | 01_415L1 | 2017-11-15 | 2017-12-04 | 23 | 21 | 2 | [10 empty] | 2018-01-08 | 2018-02-13 | 25 | 14 | 11 | [5 empty] | 2018-08-14 | 2018-11-06 | 60 | 0 | 60 | 2018-07-06 |  |  | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | WEST BROOKFIELD | 178298 | 1585 | 4980 | Solar | 01_525L1 | 2017-11-15 | 2017-11-16 | 34 | 23 | 11 | [10 empty] | 2018-01-08 | 2018-02-09 | 23 | 12 | 11 | [10 empty] | 2018-08-16 |  | 2019-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | UPTON | 178334 | 1568 | 10 | Solar | 05_312W4 | 2017-11-15 | 2017-11-17 | 70 | 59 | 11 | 2018-03-09 | 2019-05-24 | 48 | 0 | 48 | [20 empty] | 2018-03-12 | 2017-11-16 | 2018-11-22 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTMINSTER | 178300 | 1473 | 4875 | Solar | 01_610W3 | 2017-11-16 | 2017-11-16 | 20 | 0 | 20 | [10 empty] | 2017-12-18 | 2018-01-17 | 20 | 0 | 20 | [10 empty] | 2018-10-01 |  | 2023-03-31 | Yes | STD |  | 2022-08-12 | 2023-01-03 | 145 | 0 | 145 | 2023-03-09 | 2023-03-09 | 2023-03-31 | Connected |  | No
National Grid | WESTMINSTER | 178301 | 1473 | 1440 | Solar | 01_609W2 | 2017-11-16 | 2017-11-16 | 23 | 10 | 13 | [10 empty] | 2017-12-20 | 2018-01-18 | 18 | 0 | 18 | [11 empty] | 2017-11-16 | 2018-11-21 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTMINSTER | 178331 | 1473 | 3000 | Solar | 01_609W2 | 2017-11-16 | 2017-11-16 | 20 | 0 | 20 | [10 empty] | 2017-12-18 | 2018-01-19 | 22 | 0 | 22 | [10 empty] | 2018-10-17 |  | 2021-03-26 | Yes | STD |  | 2020-06-05 | 2021-03-05 | 273 | 41 | 232 | 2021-02-18 | 2021-02-18 | 2021-03-12 | Connected |  | No
National Grid | WESTMINSTER | 178332 | 1473 | 1875 | Solar | 01_609W1 | 2017-11-16 | 2017-11-17 | 65 | 53 | 12 | [10 empty] | 2018-02-23 | 2018-03-27 | 11 | 0 | 11 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | CHELMSFORD | 178333 | 1824 | 7.6 | Solar | 14_16L4 | 2017-11-17 | 2017-11-17 | 37 | 36 | 1 | 2018-01-12 | 2018-03-02 | 33 | 0 | 33 | [20 empty] | 2018-01-16 |  | 2018-11-22 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | STOUGHTON | 178335 | 2072 | 60.8 | Solar | 07_913W43 | 2017-11-17 | 2017-11-20 | 69 | 69 | 0 | [27 empty] | 2018-11-25 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | OAKHAM | 178336 | 1068 | 1000 | Solar | 09_604W2 | 2017-11-17 | 2017-11-20 | 11 | 0 | 11 | [10 empty] | 2017-12-06 | 2017-12-27 | 14 | 0 | 14 | [12 empty] | 2018-11-25 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BEVERLY | 178337 | 1915 | 6 | Solar | 12_18L1 | 2017-11-17 | 2017-11-20 | 93 | 92 | 1 | [27 empty] | 2018-11-25 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 178338 | 1844 | 5 | Solar | 14_5J42 | 2017-11-17 | 2017-11-17 | 48 | 47 | 1 | 2018-01-31 | 2018-01-31 | 0 | 0 | 0 | [20 empty] | 2018-01-31 | 2017-11-20 | 2018-11-25 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LOWELL | 178339 | 1854 | 10 | Solar | 14_77L3 | 2017-11-20 | 2018-01-09 | 33 | 32 | 1 | 2018-01-09 | 2018-01-10 | 1 | 0 | 1 | [20 empty] | 2018-01-10 | 2017-11-20 | 2018-11-25 | Yes | EXP | [8 empty] | 2018-07-10 | Connected |  | Yes
National Grid | AMESBURY | 178340 | 1913 | 3294 | Solar | 14_275L4 | 2017-11-20 | 2017-11-21 | 63 | 50 | 13 | [10 empty] | 2018-02-23 | 2018-03-28 | 12 | 0 | 12 | [10 empty] | 2018-11-07 |  | 2019-12-31 | Yes | STD |  | 2019-10-11 | 2020-05-20 | 222 | 0 | 222 |  |  | 2019-12-26 | Connected |  | No
National Grid | METHUEN | 178369 | 1844 | 20 | Solar | 14_74L1 | 2017-11-20 | 2018-01-26 | 44 | 8 | 36 | 2018-01-26 | 2018-02-10 | 0 | 0 | 0 | [20 empty] | 2018-01-30 |  | 2019-03-22 |  | EXP | [8 empty] | 2019-03-23 | Connected |  | No
National Grid | METHUEN | 178370 | 1844 | 20 | Solar | 14_74L1 | 2017-11-20 | 2017-01-26 | 44 | 44 | 0 | 2018-01-26 | 2018-01-30 | 0 | 0 | 0 | [20 empty] | 2018-01-30 |  | 2018-11-26 |  | EXP | [8 empty] | 2019-04-09 | Connected |  | No
National Grid | METHUEN | 178371 | 1844 | 20 | Solar | 14_74L1 | 2017-11-20 | 2018-01-26 | 44 | 44 | 0 | 2018-01-26 | 2018-01-30 | 48 | 0 | 48 | [20 empty] | 2018-01-30 |  | 2019-02-15 |  | EXP | [8 empty] | 2019-05-24 | Connected |  | No
National Grid | METHUEN | 178372 | 1844 | 20 | Solar | 14_74L1 | 2017-11-20 | 2018-01-26 | 44 | 44 | 0 | 2018-01-26 | 2018-01-30 | 0 | 0 | 0 | [20 empty] | 2018-01-30 |  | 2019-02-15 |  | EXP | [8 empty] | 2019-03-23 | Connected |  | No
National Grid | WARE | 178373 | 1082 | 7.6 | Solar | 09_523L4 | 2017-11-20 | 2017-11-21 | 92 | 87 | 5 | 2018-07-10 | 2018-07-09 | 0 | 0 | 0 | [20 empty] | 2018-07-09 |  | 2018-11-26 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BEVERLY | 178374 | 1915 | 57.5 | Solar | 12_12L4 | 2017-11-21 | 2017-11-23 | 10 | 0 | 10 | 2017-12-08 | 2018-01-02 | 0 | 0 | 0 | [20 empty] | 2018-01-02 |  | 2018-11-27 |  | EXP | [8 empty] | 2018-07-25 | Connected |  | Yes
National Grid | NEWBURYPORT | 178375 | 1950 | 7.6 | Solar | 14_60L4 | 2017-11-21 | 2017-11-22 | 10 | 0 | 10 | 2017-12-07 | 2017-12-07 | 0 | 0 | 0 | [20 empty] | 2017-12-07 | 2017-11-21 | 2019-02-15 |  | EXP | [8 empty] | 2019-11-12 | Connected |  | No
National Grid | WILLIAMSBURG | 178376 | 1096 | 4950 | Solar | 09_909W3 | 2017-11-21 | 2017-11-22 | 18 | 0 | 18 | [10 empty] | 2017-12-20 | 2018-01-22 | 21 | 0 | 21 | [10 empty] | 2018-06-12 |  | 2022-09-29 | Yes | STD |  | 2021-01-27 | 2022-09-22 | 604 | 156 | 448 |  |  | 2022-09-29 | Connected |  | No
National Grid | BROCKTON | 178377 | 2302 | 7.6 | Solar | 07_911W56 | 2017-11-21 | 2017-11-22 | 16 | 6 | 10 | 2017-12-15 | 2017-12-19 | 2 | 0 | 2 | [20 empty] | 2017-12-19 |  | 2018-11-27 |  | EXP | [8 empty] | 2018-06-26 | Connected |  | No
National Grid | WESTMINSTER | 178378 | 1473 | 5000 | Solar | 01_610W3 | 2017-11-22 | 2017-11-22 | 44 | 35 | 9 | [10 empty] | 2018-01-29 | 2018-02-25 | 19 | 0 | 19 | [11 empty] | 2017-11-22 | 2018-11-27 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HAVERHILL | 178408 | 1830 | 10 | Solar | 14_76L3 | 2017-11-22 | 2018-02-12 | 52 | 51 | 1 | 2018-02-12 | 2018-02-12 | 37 | 0 | 37 | [20 empty] | 2018-02-12 |  | 2018-12-02 | Yes | EXP |  | 2018-06-19 | 2018-07-17 | 28 | 0 | 28 |  |  | 2018-08-23 | Connected |  | Yes
National Grid | EAST BRIDGEWATER | 178409 | 2333 | 10000 | Other | 07_797W23 | 2017-11-22 | 2017-11-27 | 89 | 82 | 7 | [27 empty] | 2018-12-02 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ANDOVER | 178410 | 1810 | 34.5 | Solar | 14_54L3 | 2017-11-22 | 2017-11-27 | 8 | 0 | 8 | 2017-12-07 | 2018-05-23 | 0 | 0 | 0 | [20 empty] | 2018-05-23 |  | 2018-12-02 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 178411 | 2301 | 43.2 | Solar | 07_94W40 | 2017-11-27 | 2017-11-27 | 44 | 42 | 2 | 2018-01-31 | 2018-01-31 | 0 | 0 | 0 | [20 empty] | 2018-01-31 | 2017-11-27 | 2018-12-02 |  | EXP | [6 empty] | 2018-03-28 | 2018-03-28 | 2018-03-30 | Connected |  | No
National Grid | CHESHIRE | 178412 | 1225 | 4980 | Solar | 09_1021W1 | 2017-11-27 | 2017-11-27 | 17 | 0 | 17 | [10 empty] | 2017-12-20 | 2018-01-18 | 19 | 0 | 19 | [10 empty] | 2018-07-10 |  | 2021-01-27 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | RANDOLPH | 178414 | 2368 | 7.6 | Solar | 07_5W4 | 2017-11-27 | 2017-11-28 | 28 | 27 | 1 | 2018-01-09 | 2018-01-10 | 1 | 0 | 1 | [20 empty] | 2018-01-10 | 2017-11-27 | 2018-12-03 |  | EXP | [8 empty] | 2019-04-30 | Connected |  | No
National Grid | SALISBURY | 178415 | 1952 | 6.6 | Solar | 14_7L4 | 2017-11-27 | 2018-01-16 | 32 | 31 | 1 | 2018-01-16 | 2018-01-16 | 0 | 0 | 0 | [20 empty] | 2018-01-16 |  | 2018-12-03 | Yes | EXP |  | 2018-06-22 | 2018-08-03 | 42 | 0 | 42 |  |  | 2018-11-15 | Connected |  | Yes
National Grid | UPTON | 178416 | 1568 | 2450 | Solar | 05_335W3 | 2017-11-28 | 2017-12-16 | 3 | 3 | 0 | [10 empty] | 2017-12-21 | 2018-01-22 | 20 | 0 | 20 | [10 empty] | 2018-07-17 | 2017-11-29 | 2020-04-09 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BEVERLY | 178448 | 1915 | 33.3 | Solar | 12_51L2 | 2017-11-29 | 2018-01-08 | 4 | 4 | 0 | 2018-01-08 | 2018-01-08 | 0 | 0 | 0 | [20 empty] | 2018-01-08 |  | 2018-12-05 |  | EXP |  | 2018-03-16 | 2018-03-16 | 4 | 4 | 0 |  |  | 2018-08-14 | Connected |  | No
National Grid | MILFORD | 178449 | 1757 | 7.6 | Solar | 05_336W3 | 2017-11-29 | 2017-11-30 | 45 | 42 | 3 | 2018-02-06 | 2018-02-06 | 0 | 0 | 0 | [20 empty] | 2018-02-06 |  | 2018-12-05 |  | EXP | [8 empty] | 2018-11-26 | Connected |  | No
National Grid | DRACUT | 178450 | 1826 | 3.8 | Solar | 14_21L1 | 2017-11-29 | 2018-01-29 | 39 | 36 | 3 | 2018-01-29 | 2018-03-21 | 25 | 0 | 25 | [20 empty] | 2018-01-31 |  | 2020-12-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WILBRAHAM | 178451 | 1095 | 15.2 | Solar | 09_507L1 | 2017-11-29 | 2018-01-09 | 32 | 32 | 0 | 2018-01-23 | 2018-07-17 | 0 | 0 | 0 | [20 empty] | 2018-01-25 | 2017-11-29 | 2020-07-15 |  | EXP | [8 empty] | 2020-06-05 | Connected |  | No
National Grid | REVERE | 178452 | 2151 | 10 | Solar | 12_7W2 | 2017-11-29 | 2018-01-29 | 38 | 36 | 2 | 2018-01-29 | 2018-01-29 | 0 | 0 | 0 | [20 empty] | 2018-01-31 | 2017-11-29 | 2019-11-25 | Yes | EXP |  | 2019-01-08 | 2019-04-19 | 101 | 0 | 101 |  |  | 2019-11-06 | Connected |  | No
National Grid | LOWELL | 178453 | 1851 | 7.6 | Solar | 14_2L2 | 2017-11-29 | 2018-01-29 | 38 | 36 | 2 | 2018-01-29 | 2018-01-30 | 0 | 0 | 0 | [20 empty] | 2018-01-30 |  | 2019-09-19 | Yes | EXP |  | 2018-06-06 | 2018-06-20 | 14 | 0 | 14 |  |  | 2019-09-05 | Connected |  | No
National Grid | WORCESTER | 178456 | 1605 | 496 | Solar | 01_HT48 | 2017-11-30 | 2017-12-01 | 34 | 12 | 22 | [5 empty] | 2018-03-19 | 2018-03-23 | 4 | 0 | 4 | 2018-01-23 | 2018-02-28 | 51 | 0 | 51 | 2018-03-19 | 2018-03-23 | 4 | 0 | 4 | [7 empty] | 2018-12-06 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | SEEKONK | 178457 | 2771 | 480 | Solar | 05_7L5 | 2017-11-30 | 2017-12-01 | 35 | 0 | 35 | 2018-01-23 | 2018-02-28 | 26 | 9 | 17 | 2018-04-13 | 2018-06-11 | 41 | 21 | 20 | [5 empty] | 2018-04-13 | 2018-06-11 | 41 | 21 | 20 | [5 empty] | 2018-06-29 |  | 2020-04-15 |  | EXP | [8 empty] | 2020-06-17 | Connected |  | No
National Grid | METHUEN | 178489 | 1844 | 7 | Solar | 14_74L1 | 2017-11-30 | 2018-01-04 | 0 | 0 | 0 | 2018-01-04 | 2018-01-05 | 0 | 0 | 0 | [20 empty] | 2018-01-05 |  | 2018-12-06 |  | EXP | [8 empty] | 2018-10-23 | Connected |  | Yes
National Grid | CHARLTON | 178454 | 1507 | 4430 | Solar | 01_415L1 | 2017-12-01 | 2017-12-01 | 7 | 0 | 7 | [10 empty] | 2017-12-12 | 2018-01-03 | 14 | 0 | 14 | [11 empty] | 2017-12-01 | 2018-12-06 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MILLBURY | 178488 | 1527 | 499.5 | Solar | 01_304W5 | 2017-12-01 | 2017-12-01 | 36 | 13 | 23 | [5 empty] | 2018-02-27 | 2018-03-12 | 9 | 0 | 9 | 2018-01-23 | 2018-02-27 | 51 | 51 | 0 | 2018-02-27 | 2018-03-12 | 9 | 0 | 9 | [5 empty] | 2020-08-20 |  | 2022-09-28 | Yes | STD | [8 empty] | 2022-09-27 | Connected |  | No
National Grid | PALMER | 178491 | 1069 | 4000 | Solar | 09_523L4 | 2017-12-01 | 2017-12-04 | 41 | 40 | 1 | [10 empty] | 2018-02-02 | 2018-02-28 | 17 | 0 | 17 | [11 empty] | 2017-12-01 | 2018-12-09 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTHBRIDGE | 178492 | 1534 | 4980 | Solar | 05_320W1 | 2017-12-01 | 2017-12-14 | 45 | 43 | 2 | [10 empty] | 2018-02-16 | 2018-03-26 | 25 | 0 | 25 | [10 empty] | 2018-08-23 | 2017-12-01 | 2021-03-31 | Yes | STD |  | 2020-12-19 | 2021-03-24 | 95 | 0 | 95 |  |  | 2021-03-31 | Connected |  | No
National Grid | NORTHBRIDGE | 178493 | 1534 | 4980 | Solar | 05_320W1 | 2017-12-01 | 2017-12-14 | 45 | 43 | 2 | [10 empty] | 2018-02-16 | 2018-03-26 | 25 | 0 | 25 | [10 empty] | 2018-08-23 |  | 2021-03-31 | Yes | STD |  | 2021-01-14 | 2021-03-31 | 76 | 0 | 76 |  |  | 2021-03-31 | Connected |  | No
National Grid | NORTHBRIDGE | 178494 | 1534 | 2320 | Solar | 05_321W1 | 2017-12-01 | 2017-12-04 | 51 | 41 | 10 | [10 empty] | 2018-02-16 | 2018-03-26 | 14 | 0 | 14 | [12 empty] | 2018-12-09 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BRIMFIELD | 178495 | 1010 | 3000 | Solar | 09_503L4 | 2017-12-04 | 2017-12-04 | 42 | 41 | 1 | [10 empty] | 2018-02-01 | 2018-03-03 | 21 | 7 | 14 | [10 empty] | 2018-08-06 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BARRE | 178496 | 1005 | 10 | Solar | 09_604W4 | 2017-12-04 | 2018-01-29 | 46 | 46 | 0 | 2018-02-12 | 2018-02-12 | 0 | 0 | 0 | [20 empty] | 2018-02-12 |  | 2018-12-10 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | DRACUT | 178497 | 1826 | 7.6 | Solar | 14_75L3 | 2017-12-04 | 2018-03-16 | 64 | 59 | 5 | 2018-03-26 | 2018-03-26 | 0 | 0 | 0 | [20 empty] | 2018-03-26 |  | 2018-12-10 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | AUBURN | 178527 | 1501 | 2800 | Solar | 01_2236W5 | 2017-12-04 | 2017-12-05 | 26 | 26 | 0 | [10 empty] | 2018-01-12 | 2018-02-06 | 16 | 1 | 15 | [5 empty] | 2020-07-10 | 2020-10-02 | 60 | 3 | 57 |  |  |  |  | STD | [9 empty] | Group Study |  | No
National Grid | NEWBURY | 178529 | 1951 | 5000 | Solar | 14_60L4 | 2017-12-04 | 2017-12-05 | 21 | 21 | 0 | [10 empty] | 2018-01-05 | 2018-02-08 | 23 | 11 | 12 | [12 empty] | 2018-12-10 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WINCHENDON | 178530 | 1475 | 1250 | Solar | 01_607W1 | 2017-12-04 | 2017-12-05 | 22 | 22 | 0 | [10 empty] | 2018-01-08 | 2018-02-01 | 17 | 0 | 17 | [12 empty] | 2018-12-10 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LAWRENCE | 178531 | 1840 | 60 | Solar | 14_6J5 | 2017-12-05 | 2018-01-02 | 18 | 0 | 18 | 2018-01-02 | 2018-01-02 | 0 | 0 | 0 | [20 empty] | 2018-01-03 |  | 2018-12-10 |  | EXP | [8 empty] | 2018-08-10 | Connected |  | Yes
National Grid | RUTLAND | 178532 | 1543 | 7.6 | Solar | 01_55W1 | 2017-12-05 | 2017-12-05 | 83 | 82 | 1 | 2018-06-06 | 2018-06-05 | 0 | 0 | 0 | [20 empty] | 2018-06-05 |  | 2018-12-10 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MARLBOROUGH | 178533 | 1752 | 110 | Solar | 05_311W2 | 2017-12-05 | 2017-12-06 | 26 | 9 | 17 | 2018-01-16 | 2018-02-08 | 17 | 0 | 17 | [20 empty] | 2018-02-08 | 2017-12-05 | 2018-12-11 |  | EXP | [8 empty] | 2018-12-21 | Connected |  | No
National Grid | SOUTHBRIDGE | 178534 | 1550 | 3744 | Solar | 01_413L3 | 2017-12-05 | 2017-12-06 | 55 | 0 | 55 | [25 empty] | 2018-02-26 | 2017-12-07 | 2020-12-31 | Yes | STD |  | 2020-06-12 | 2020-11-23 | 165 | 5 | 160 | 2020-12-14 | 2020-12-14 | 2020-12-31 | Connected |  | No
National Grid | RUTLAND | 178535 | 1543 | 7.6 | Solar | 01_55W1 | 2017-12-07 | 2017-12-08 | 17 | 0 | 17 | 2018-01-04 | 2018-01-05 | 1 | 0 | 1 | [20 empty] | 2018-01-05 |  | 2019-03-22 | Yes | EXP | [8 empty] | 2018-12-21 | Connected |  | No
National Grid | TEWKSBURY | 178536 | 1876 | 15.2 | Solar | 14_70L8 | 2017-12-07 | 2018-01-02 | 15 | 0 | 15 | 2018-01-02 | 2018-01-03 | 1 | 0 | 1 | [20 empty] | 2018-01-03 |  | 2019-03-22 |  | EXP | [8 empty] | 2018-12-19 | Connected |  | Yes
National Grid | WILBRAHAM | 178566 | 1095 | 15.2 | Solar | 09_507L3 | 2017-12-07 | 2017-12-19 | 0 | 0 | 0 | 2018-01-02 | 2018-01-03 | 0 | 0 | 0 | [20 empty] | 2018-01-03 |  | 2018-12-13 |  | EXP | [8 empty] | 2019-11-12 | Connected |  | No
National Grid | GARDNER | 178567 | 1440 | 4950 | Solar | 01_602W2 | 2017-12-07 | 2017-12-08 | 19 | 0 | 19 | [10 empty] | 2018-01-08 | 2018-02-07 | 21 | 7 | 14 | [12 empty] | 2018-12-13 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | OXFORD | 178568 | 1540 | 6995 | Solar | 01_406L5 | 2017-12-07 | 2017-12-08 | 40 | 21 | 19 | [10 empty] | 2018-02-07 | 2018-03-07 | 16 | 0 | 16 | [5 empty] | 2020-07-10 | 2020-10-02 | 60 | 3 | 57 |  |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | OXFORD | 178569 | 1540 | 10 | Solar | 01_406L4 | 2017-12-07 | 2017-12-08 | 17 | 0 | 17 | 2018-01-04 | 2018-01-04 | 0 | 0 | 0 | [20 empty] | 2018-01-05 |  | 2018-12-13 |  | EXP | [8 empty] | 2018-06-05 | Connected |  | No
National Grid | MILLBURY | 178571 | 1527 | 8640 | Solar | 01_304W5 | 2017-12-08 | 2017-12-11 | 2 | 0 | 2 | [26 empty] | 2017-12-08 | 2018-12-16 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MILLBURY | 178572 | 1527 | 4980 | Solar | 01_304W5 | 2017-12-08 | 2017-12-11 | 42 | 0 | 42 | [10 empty] | 2018-02-09 | 2018-03-07 | 17 | 0 | 17 | [10 empty] | 2018-08-07 |  | 2022-10-28 | Yes | STD |  | 2022-01-22 | 2022-05-03 | 102 | 0 | 102 | 2022-09-21 | 2022-09-21 | 2022-10-26 | Connected |  | No
National Grid | SOUTH EASTON | 178573 | 2375 | 415 | Solar | 07_92W54 | 2017-12-11 | 2017-12-13 | 77 | 57 | 20 | [27 empty] | 2018-12-18 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | TOPSFIELD | 178574 | 1983 | 11.4 | Solar | 14_33L2 | 2017-12-11 | 2017-12-19 | 0 | 0 | 0 | 2018-01-02 | 2018-01-03 | 0 | 0 | 0 | [20 empty] | 2018-01-03 |  | 2020-07-15 |  | EXP | [8 empty] | 2020-03-23 | Connected |  | No
National Grid | WORCESTER | 178575 | 1607 | 15.2 | Solar | 01_8W1 | 2017-12-11 | 2017-12-13 | 12 | 0 | 12 | 2018-01-02 | 2018-01-03 | 10 | 0 | 10 | [20 empty] | 2018-01-03 |  | 2018-12-18 |  | EXP | [8 empty] | 2018-10-23 | Connected |  | No
National Grid | SOMERSET | 178605 | 2726 | 10 | Solar | 05_19W72 | 2017-12-12 | 2017-12-13 | 14 | 0 | 14 | 2018-01-04 | 2018-01-05 | 1 | 0 | 1 | [20 empty] | 2018-01-05 |  | 2018-12-18 |  | EXP |  | 2018-05-30 | 2018-06-25 | 26 | 0 | 26 |  |  | 2018-07-11 | Connected |  | No
National Grid | WARE | 178606 | 1082 | 10 | Solar | 09_501L2 | 2017-12-12 | 2017-12-13 | 77 | 61 | 16 | [27 empty] | 2018-12-18 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | TYNGSBORO | 178607 | 1879 | 150 | Solar | 14_211L1 | 2017-12-12 | 2018-01-19 | 24 | 12 | 12 | 2018-01-19 | 2018-01-22 | 0 | 0 | 0 | [20 empty] | 2018-01-22 |  | 2018-12-18 |  | EXP | [8 empty] | 2018-06-19 | Connected |  | No
National Grid | MALDEN | 178608 | 2148 | 15.2 | Solar | 12_16J4 | 2017-12-12 | 2017-12-12 | 0 | 0 | 0 | 2018-01-02 | 2018-01-03 | 0 | 0 | 0 | [20 empty] | 2018-01-03 |  | 2019-03-22 |  | EXP | [8 empty] | 2019-06-06 | Connected |  | No
National Grid | SWANSEA | 178609 | 2777 | 6 | Solar | 05_11W81 | 2017-12-13 | 2017-12-13 | 49 | 35 | 14 | [25 empty] | 2018-02-26 |  | 2018-12-18 |  | EXP | [8 empty] | 2018-11-26 | Connected |  | Yes
National Grid | OAKHAM | 178610 | 1068 | 4950 | Solar | 09_1194T1 | 2017-12-14 | 2017-12-14 | 32 | 3 | 29 | [10 empty] | 2018-01-26 | 2018-02-20 | 16 | 0 | 16 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | CHELMSFORD | 178611 | 1824 | 450 | Other | 14_24L2 | 2017-12-14 | 2018-05-11 | 0 | 0 | 0 | 2018-05-11 | 2018-05-11 | 0 | 0 | 0 | 2018-06-15 | 2018-09-18 | 66 | 40 | 26 | [5 empty] | 2018-06-15 | 2018-09-18 | 66 | 40 | 26 | [5 empty] | 2018-09-25 |  | 2021-04-30 |  | EXP | [8 empty] | 2021-04-14 | Connected |  | No
National Grid | STOUGHTON | 178612 | 2072 | 166.5 | Solar | 07_913W69 | 2017-12-14 | 2017-12-14 | 31 | 11 | 20 | 2018-01-31 | 2018-01-31 | 45 | 0 | 45 | [20 empty] | 2018-01-31 |  | 2018-12-19 |  | EXP | [8 empty] | 2018-12-06 | Connected |  | No
National Grid | MARLBOROUGH | 178613 | 1752 | 240 | Solar | 05_311W5 | 2017-12-14 | 2017-12-15 | 51 | 41 | 10 | [27 empty] | 2018-12-20 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | GARDNER | 178614 | 1440 | 2000 | Solar | 01_602W2 | 2017-12-14 | 2017-12-15 | 30 | 0 | 30 | [10 empty] | 2018-01-29 | 2018-02-20 | 15 | 1 | 14 | [5 empty] | 2020-07-10 | 2020-10-01 | 59 | 3 | 56 |  |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | FRANKLIN | 178645 | 2038 | 10 | Solar | 05_344W1 | 2017-12-14 | 2018-05-17 | 1 | 0 | 1 | 2018-05-17 | 2018-06-27 | 28 | 0 | 28 | [20 empty] | 2018-06-29 | 2017-12-15 | 2018-12-20 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BILLERICA | 178502 | 1821 | 250 | Solar | 14_92L2 | 2017-12-15 | 2018-01-25 | 23 | 4 | 19 | [10 empty] | 2018-02-28 | 2018-02-28 | 0 | 0 | 0 | [10 empty] | 2018-02-28 |  | 2019-12-20 | Yes | STD | [8 empty] | 2019-12-20 | Connected |  | No
National Grid | NORWELL | 178643 | 2061 | 153.2 | Solar | 07_96W40 | 2017-12-15 | 2017-12-15 | 31 | 21 | 10 | 2018-02-01 | 2018-02-05 | 2 | 0 | 2 | [20 empty] | 2018-02-05 | 2017-12-15 | 2018-12-20 |  | EXP | [8 empty] | 2018-07-10 | Connected |  | No
National Grid | WILBRAHAM | 178644 | 1095 | 1000 | Solar | 09_139L3 | 2017-12-15 | 2017-12-15 | 14 | 0 | 14 | [10 empty] | 2018-01-05 | 2018-02-06 | 21 | 0 | 21 | [10 empty] | 2018-06-14 |  | 2020-12-31 | Yes | STD |  | 2020-04-24 | 2020-10-27 | 187 | 5 | 182 | 2020-12-09 | 2020-12-09 | 2020-12-22 | Connected |  | No
National Grid | WINCHENDON | 178646 | 1475 | 4980 | Solar | 01_607W1 | 2017-12-15 | 2017-12-15 | 75 | 51 | 24 | [10 empty] | 2018-05-30 | 2018-05-29 | 0 | 0 | 0 | [12 empty] | 2018-12-20 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | DOUGLAS | 178647 | 1516 | 1750 | Solar | 05_320W2 | 2017-12-15 | 2017-12-15 | 27 | 0 | 27 | [26 empty] | 2017-12-15 | 2018-12-20 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ROCKLAND | 178648 | 2370 | 244 | Solar | 07_99W63 | 2017-12-15 | 2017-12-18 | 10 | 0 | 10 | [10 empty] | 2018-01-02 | 2018-01-30 | 19 | 0 | 19 | [10 empty] | 2018-06-21 |  | 2021-08-06 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | NORWELL | 178649 | 2061 | 72 | Solar | 07_96W40 | 2017-12-15 | 2017-12-18 | 23 | 14 | 9 | 2018-01-23 | 2018-01-24 | 1 | 0 | 1 | [20 empty] | 2018-01-24 |  | 2018-12-23 |  | EXP | [8 empty] | 2018-07-10 | Connected |  | No
National Grid | CHESHIRE | 178650 | 1225 | 5000 | Solar | 09_1021W2 | 2017-12-18 | 2017-12-18 | 23 | 0 | 23 | [10 empty] | 2018-01-23 | 2018-02-14 | 16 | 2 | 14 | [12 empty] | 2018-12-23 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | STOUGHTON | 178651 | 2072 | 10 | Solar | 07_913W43 | 2017-12-18 | 2018-05-10 | 0 | 0 | 0 | 2018-07-11 | 2018-07-10 | 0 | 0 | 0 | [20 empty] | 2018-07-10 |  | 2018-12-23 |  | EXP | [8 empty] | 2019-05-14 | Connected |  | No
National Grid | WENDELL | 178652 | 1379 | 1125 | Solar | 09_705W1 | 2017-12-18 | 2017-12-19 | 30 | 14 | 16 | [10 empty] | 2018-02-02 | 2018-02-24 | 15 | 0 | 15 | [12 empty] | 2018-12-24 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | RANDOLPH | 178683 | 2368 | 149.4 | Solar | 07_97W3 | 2017-12-18 | 2017-12-19 | 49 | 41 | 8 | 2018-03-12 | 2018-03-14 | 2 | 0 | 2 | [20 empty] | 2018-03-14 |  | 2020-06-30 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | AMESBURY | 178684 | 1913 | 20 | Solar | 14_66L1 | 2017-12-18 | 2018-01-18 | 17 | 17 | 0 | 2018-02-01 | 2018-02-01 | 0 | 0 | 0 | [20 empty] | 2018-02-01 |  | 2018-12-24 |  | EXP | [8 empty] | 2018-05-01 | Connected |  | No
National Grid | DRACUT | 178685 | 1826 | 7.6 | Solar | 14_78L1 | 2017-12-18 | 2017-12-19 | 8 | 0 | 8 | 2018-01-02 | 2018-01-03 | 0 | 0 | 0 | [20 empty] | 2018-01-03 | 2017-12-19 | 2018-12-24 |  | EXP | [8 empty] | 2018-11-07 | Connected |  | No
National Grid | WESTPORT | 178686 | 2790 | 1500 | Solar | 05_115W52 | 2017-12-19 | 2017-12-20 | 27 | 0 | 27 | [25 empty] | 2018-03-19 | 2017-12-19 | 2018-12-06 | Yes | STD |  | 2018-08-03 | 2020-02-20 | 566 | 0 | 566 |  |  | 2018-12-06 | Connected |  | No
National Grid | WESTPORT | 178687 | 2790 | 3500 | Solar | 05_115W52 | 2017-12-19 | 2017-12-20 | 37 | 0 | 37 | [25 empty] | 2018-03-19 |  | 2018-12-05 | Yes | STD |  | 2018-08-03 | 2018-10-09 | 67 | 0 | 67 |  |  | 2018-11-27 | Connected |  | No
National Grid | NORTH CHELMSFORD | 178690 | 1863 | 240 | Solar | 14_2L1 | 2017-12-20 | 2017-12-20 | 0 | 0 | 0 | 2017-12-20 | 2018-01-28 | 25 | 0 | 25 | [22 empty] | 2018-12-25 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | GREAT BARRINGTON | 178691 | 1230 | 304 | Solar | 09_1109W3 | 2017-12-20 | 2018-01-18 | 10 | 0 | 10 | 2018-02-01 | 2018-02-13 | 8 | 0 | 8 | 2018-03-20 | 2018-04-18 | 21 | 0 | 21 | [5 empty] | 2018-03-20 | 2018-04-18 | 21 | 0 | 21 | [5 empty] | 2018-06-04 |  | 2018-12-26 |  | EXP | [8 empty] | 2019-05-31 | Connected |  | Yes
National Grid | WINCHENDON | 178721 | 1475 | 1990 | Solar | 01_612W3 | 2017-12-20 | 2017-12-21 | 36 | 0 | 36 | [10 empty] | 2018-02-14 | 2018-03-12 | 11 | 0 | 11 | [12 empty] | 2019-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WINCHENDON | 178722 | 1475 | 1000 | Solar | 01_612W3 | 2017-12-20 | 2017-12-21 | 34 | 9 | 25 | [10 empty] | 2018-02-12 | 2018-03-12 | 13 | 0 | 13 | [12 empty] | 2019-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WINCHENDON | 178723 | 1475 | 4990 | Solar | 01_612W3 | 2017-12-20 | 2017-12-21 | 34 | 0 | 34 | [10 empty] | 2018-02-12 | 2018-03-12 | 13 | 0 | 13 | [5 empty] | 2020-07-10 | 2020-10-01 | 59 | 3 | 56 |  |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WINCHENDON | 178724 | 1475 | 1990 | Solar | 01_612W3 | 2017-12-20 | 2017-12-21 | 34 | 9 | 25 | [10 empty] | 2018-02-12 | 2018-03-12 | 13 | 0 | 13 | [12 empty] | 2019-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WINCHENDON | 178725 | 1475 | 1000 | Solar | 01_612W3 | 2017-12-20 | 2017-12-21 | 34 | 9 | 25 | [10 empty] | 2018-02-12 | 2018-03-12 | 13 | 0 | 13 | [12 empty] | 2019-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WINCHENDON | 178726 | 1475 | 4990 | Solar | 01_612W3 | 2017-12-20 | 2017-12-21 | 36 | 11 | 25 | [10 empty] | 2018-02-14 | 2018-03-12 | 11 | 0 | 11 | [5 empty] | 2020-07-10 | 2020-10-02 | 60 | 3 | 57 |  |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WINCHENDON | 178727 | 1475 | 1990 | Solar | 01_612W3 | 2017-12-20 | 2017-12-21 | 45 | 9 | 36 | [10 empty] | 2018-02-12 | 2018-07-26 | 37 | 0 | 37 | [12 empty] | 2019-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WINCHENDON | 178728 | 1475 | 1000 | Solar | 01_612W3 | 2017-12-20 | 2017-12-21 | 34 | 9 | 25 | [10 empty] | 2018-02-12 | 2018-07-26 | 37 | 0 | 37 | [11 empty] | 2017-12-20 | 2019-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WINCHENDON | 178729 | 1475 | 3900 | Solar | 01_612W3 | 2017-12-20 | 2017-12-21 | 34 | 33 | 1 | [10 empty] | 2018-02-12 | 2018-03-12 | 20 | 7 | 13 | [10 empty] | 2018-11-07 | 2017-12-21 | 2024-08-08 | Yes | STD |  | 2021-12-31 | 2022-05-03 | 124 | 78 | 46 |  |  |  | Completion Documents |  | No
National Grid | DIGHTON | 178152 | 2715 | 2700 | Solar | 05_19W74 | 2017-12-21 | 2018-01-10 | 7 | 4 | 3 | [10 empty] | 2018-01-19 | 2018-02-09 | 15 | 0 | 15 | [10 empty] | 2018-07-23 |  | 2024-05-20 | Yes | STD |  | 2021-06-04 | 2021-12-31 | 211 | 10 | 201 |  |  |  | Completion Documents |  | No
National Grid | CHARLTON | 178154 | 1507 | 5000 | Solar | 01_415L1 | 2017-12-21 | 2017-12-26 | 23 | 14 | 9 | [10 empty] | 2018-01-30 | 2018-02-21 | 15 | 1 | 14 | [11 empty] | 2017-12-21 | 2018-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BELLINGHAM | 178155 | 2019 | 4400 | Solar | 05_335W1 | 2017-12-21 | 2018-01-12 | 20 | 4 | 16 | [10 empty] | 2018-02-12 | 2018-03-29 | 33 | 20 | 13 | [5 empty] | 2019-01-23 | 2019-08-05 | 136 | 68 | 68 | 2018-11-15 |  | 2021-12-30 | Yes | STD |  | 2021-03-18 | 2021-10-12 | 203 | 83 | 120 |  |  | 2021-12-15 | Connected |  | No
National Grid | LAWRENCE | 178156 | 1843 | 176 | Solar | 14_1319 | 2017-12-22 | 2018-02-01 | 33 | 29 | 4 | 2018-02-13 | 2018-02-14 | 0 | 0 | 0 | [20 empty] | 2018-02-14 |  | 2019-01-31 |  | EXP | [8 empty] | 2019-01-30 | Connected |  | No
National Grid | NORTH BROOKFIELD | 178157 | 1535 | 990 | Solar | 01_552L3 | 2017-12-22 | 2017-12-26 | 27 | 0 | 27 | [10 empty] | 2018-02-05 | 2018-02-28 | 16 | 0 | 16 | [10 empty] | 2018-07-10 | 2017-12-22 | 2018-12-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HALIFAX | 178158 | 2338 | 4950 | Solar | 07_912W75 | 2017-12-22 | 2017-12-26 | 31 | 0 | 31 | [10 empty] | 2018-02-09 | 2018-02-20 | 6 | 0 | 6 | [10 empty] | 2018-06-01 | 2017-12-26 | 2019-12-18 | Yes | STD | [6 empty] | 2019-12-17 | 2019-12-17 | 2019-12-18 | Connected |  | No
National Grid | ROYALSTON | 178159 | 1368 | 3420 | Solar | 09_701J1 | 2017-12-26 | 2017-12-27 | 32 | 24 | 8 | [10 empty] | 2018-02-13 | 2018-03-14 | 20 | 0 | 20 | [5 empty] | 2020-03-03 | 2020-06-05 | 66 | 0 | 66 | 2018-08-16 | 2017-12-26 | 2022-04-26 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | ROCKLAND | 178160 | 2370 | 230 | Solar | 07_99W63 | 2017-12-26 | 2017-12-27 | 13 | 10 | 3 | [10 empty] | 2018-01-16 | 2018-01-30 | 10 | 0 | 10 | [10 empty] | 2018-06-21 |  | 2019-07-10 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | RUTLAND | 178188 | 1543 | 294 | Solar | 01_55W1 | 2017-12-28 | 2017-01-30 | 0 | 0 | 0 | 2018-02-13 | 2018-03-09 | 17 | 0 | 17 | [20 empty] | 2018-12-05 |  | 2020-02-03 |  | EXP | [8 empty] | 2020-02-13 | Connected |  | No
National Grid | RUTLAND | 178189 | 1543 | 296 | Solar | 01_55W1 | 2017-12-28 | 2018-01-30 | 10 | 0 | 10 | 2018-02-13 | 2018-08-30 | 36 | 0 | 36 | 2018-10-25 | 2018-11-05 | 9 | 0 | 9 | [5 empty] | 2018-10-25 | 2018-11-05 | 9 | 0 | 9 | [5 empty] | 2018-11-07 | 2018-01-02 | 2020-02-03 |  | EXP | [8 empty] | 2020-02-13 | Connected |  | No
National Grid | WILLIAMSBURG | 178190 | 1039 | 1600 | Solar | 09_909W3 | 2018-01-02 | 2018-01-03 | 22 | 12 | 10 | [10 empty] | 2018-02-02 | 2018-03-13 | 13 | 0 | 13 | [10 empty] | 2018-11-13 | 2018-01-02 | 2020-03-11 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | DUDLEY | 178192 | 1571 | 3630 | Solar | 01_412L4 | 2018-01-02 | 2018-01-03 | 35 | 9 | 26 | [10 empty] | 2018-02-23 | 2018-04-02 | 15 | 0 | 15 | [10 empty] | 2020-06-23 |  |  | Yes | STD |  | 2023-07-07 | 2023-09-21 | 77 | 0 | 77 |  |  |  | Study |  | No
National Grid | SWANSEA | 178193 | 2777 | 6.6 | Solar | 05_11W83 | 2018-01-02 | 2018-01-03 | 24 | 0 | 24 | 2018-02-07 | 2018-02-13 | 4 | 0 | 4 | [20 empty] | 2018-02-13 | 2018-01-03 | 2019-01-08 |  | EXP | [8 empty] | 2018-10-09 | Connected |  | Yes
National Grid | SPENCER | 178194 | 1562 | 2450 | Solar | 01_552L3 | 2018-01-03 | 2018-01-03 | 10 | 0 | 10 | [10 empty] | 2018-02-07 | 2018-04-17 | 20 | 0 | 20 | [10 empty] | 2018-10-02 |  | 2020-03-20 | Yes | STD |  | 2019-12-06 | 2020-02-19 | 75 | 0 | 75 |  |  | 2020-03-16 | Connected |  | No
National Grid | TEWKSBURY | 178225 | 1876 | 10 | Solar | 14_20L2 | 2018-01-03 | 2018-03-01 | 38 | 32 | 6 | 2018-03-05 | 2018-03-05 | 0 | 0 | 0 | [20 empty] | 2018-03-06 | 2018-01-03 | 2019-01-10 |  | EXP |  | 2018-05-09 | 2018-05-08 | 0 | 0 | 0 |  |  | 2018-11-15 | Connected |  | Yes
National Grid | LAWRENCE | 178226 | 1841 | 11.4 | Solar | 14_74L6 | 2018-01-03 | 2018-01-12 | 15 | 9 | 6 | 2018-01-29 | 2018-01-31 | 0 | 0 | 0 | [20 empty] | 2018-01-31 |  | 2019-01-10 | Yes | EXP | [8 empty] | 2019-12-12 | Connected |  | No
National Grid | METHUEN | 178227 | 1844 | 7.6 | Solar | 14_5J42 | 2018-01-03 | 2018-01-05 | 15 | 9 | 6 | 2018-01-29 | 2018-04-10 | 39 | 0 | 39 | [20 empty] | 2018-01-30 |  | 2019-01-10 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 178228 | 1841 | 10.4 | Solar | 14_8L2 | 2018-01-03 | 2018-01-29 | 15 | 9 | 6 | 2018-01-29 | 2018-01-29 | 0 | 0 | 0 | [20 empty] | 2018-01-29 |  | 2019-01-10 |  | EXP | [8 empty] | 2019-11-08 | Connected |  | No
National Grid | SEEKONK | 178229 | 2771 | 15.2 | Solar | 05_7L4 | 2018-01-03 | 2018-01-05 | 38 | 32 | 6 | 2018-03-06 | 2018-03-07 | 1 | 0 | 1 | [20 empty] | 2018-03-07 |  | 2019-01-10 |  | EXP | [8 empty] | 2018-11-26 | Connected |  | Yes
National Grid | SALISBURY | 178230 | 1952 | 7.6 | Solar | 14_7L2 | 2018-01-03 | 2018-01-05 | 21 | 15 | 6 | 2018-02-06 | 2018-03-22 | 20 | 0 | 20 | [20 empty] | 2018-02-07 | 2018-01-05 | 2019-01-10 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | ADAMS | 178231 | 1220 | 4998 | Solar | 09_1021W2 | 2018-01-05 | 2018-01-08 | 20 | 0 | 20 | [10 empty] | 2018-02-05 | 2018-03-01 | 17 | 0 | 17 | [10 empty] | 2018-07-18 |  | 2022-12-30 | Yes | STD |  | 2021-01-12 | 2021-10-12 | 272 | 60 | 212 |  |  | 2022-12-22 | Connected |  | No
National Grid | WORCESTER | 178232 | 1606 | 43.2 | Solar | 01_24W5 | 2018-01-05 | 2018-01-11 | 0 | 0 | 0 | 2018-01-25 | 2018-02-05 | 0 | 0 | 0 | [20 empty] | 2018-01-26 |  | 2019-01-13 |  | EXP | [8 empty] | 2018-06-08 | Connected |  | No
National Grid | RUTLAND | 178233 | 1543 | 133.2 | Solar | 01_55W1 | 2018-01-07 | 2018-01-11 | 0 | 0 | 0 | 2018-01-25 | 2018-01-25 | 0 | 0 | 0 | [20 empty] | 2018-01-25 |  | 2021-04-16 |  | EXP | [8 empty] | 2021-05-19 | Connected |  | No
National Grid | MARLBOROUGH | 178234 | 1752 | 1200 | Landfill Gas | 05_317W1 | 2018-01-08 | 2018-01-08 | 36 | 3 | 33 | [10 empty] | 2018-03-01 | 2018-04-13 | 20 | 0 | 20 | [12 empty] | 2019-01-13 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SWANSEA | 178265 | 2777 | 4998 | Solar | 05_11W84 | 2018-01-08 | 2018-01-26 | 27 | 20 | 7 | [10 empty] | 2018-03-06 | 2018-04-10 | 25 | 0 | 25 | [10 empty] | 2018-09-18 | 2018-01-08 | 2020-07-09 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LANCASTER | 178266 | 1523 | 990 | Solar | 01_225W3 | 2018-01-08 | 2018-01-08 | 21 | 4 | 17 | [10 empty] | 2018-02-07 | 2018-03-19 | 16 | 0 | 16 | [10 empty] | 2018-12-10 |  | 2020-08-17 | Yes | STD |  | 2020-01-17 | 2020-06-04 | 139 | 0 | 139 | 2020-06-18 | 2020-06-18 | 2020-08-10 | Connected |  | No
National Grid | NORTH BROOKFIELD | 178267 | 1535 | 4980 | Solar | 01_552L3 | 2018-01-08 | 2018-01-09 | 20 | 3 | 17 | [10 empty] | 2018-02-07 | 2018-03-10 | 16 | 0 | 16 | [11 empty] | 2018-01-09 | 2019-01-14 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | STOUGHTON | 178269 | 2072 | 233.33 | Solar | 07_94W42 | 2018-01-09 | 2018-01-26 | 11 | 0 | 11 | [10 empty] | 2018-02-12 | 2018-03-21 | 26 | 0 | 26 | [10 empty] | 2018-09-18 | 2018-01-09 | 2020-12-31 | Yes | STD | [6 empty] | 2020-12-28 | 2020-12-28 | 2020-12-30 | Connected |  | No
National Grid | STOUGHTON | 178270 | 2072 | 936 | Solar | 07_94W42 | 2018-01-09 | 2018-01-26 | 11 | 0 | 11 | [10 empty] | 2018-02-12 | 2018-03-21 | 26 | 0 | 26 | [10 empty] | 2018-09-18 | 2018-01-09 | 2020-11-30 | Yes | STD | [8 empty] | 2020-11-30 | Connected |  | Yes
National Grid | WESTBOROUGH | 178271 | 1581 | 766.6 | Solar | 05_312W2 | 2018-01-09 | 2018-01-26 | 11 | 0 | 11 | [10 empty] | 2018-02-12 | 2018-03-10 | 18 | 0 | 18 | [10 empty] | 2018-07-25 | 2018-01-09 | 2021-02-26 | Yes | STD |  | 2020-10-28 | 2020-12-14 | 47 | 0 | 47 | 2021-02-16 | 2021-02-16 | 2021-02-26 | Connected |  | No
National Grid | NORTON | 178272 | 2766 | 966.6 | Solar | 05_4L1 | 2018-01-09 | 2018-01-26 | 11 | 0 | 11 | [10 empty] | 2018-02-12 | 2018-03-10 | 18 | 0 | 18 | [10 empty] | 2018-07-25 |  | 2021-03-23 | Yes | STD | [6 empty] | 2021-02-09 | 2021-02-09 | 2021-03-23 | Connected |  | No
National Grid | OXFORD | 178302 | 1540 | 4400 | Solar | 01_406L3 | 2018-01-09 | 2018-01-10 | 35 | 12 | 23 | [10 empty] | 2018-03-09 | 2018-04-05 | 13 | 0 | 13 | [5 empty] | 2020-07-10 | 2020-10-02 | 60 | 3 | 57 |  |  |  |  | STD | [9 empty] | Group Study |  | No
National Grid | WARREN | 178303 | 1083 | 6400 | Solar | 09_516L3 | 2018-01-09 | 2018-01-10 | 35 | 12 | 23 | [10 empty] | 2018-03-09 | 2018-04-04 | 12 | 0 | 12 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH BROOKFIELD | 178304 | 1535 | 2780 | Solar | 01_552L3 | 2018-01-09 | 2018-01-10 | 41 | 21 | 20 | [10 empty] | 2018-03-09 | 2018-04-07 | 15 | 0 | 15 | [10 empty] | 2018-06-26 |  | 2019-01-15 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH BROOKFIELD | 178305 | 1535 | 1855 | Solar | 09_604W3 | 2018-01-09 | 2018-01-10 | 41 | 21 | 20 | [10 empty] | 2018-03-09 | 2018-04-07 | 15 | 0 | 15 | [12 empty] | 2019-01-15 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WARREN | 178306 | 1083 | 4750 | Solar | 09_516L3 | 2018-01-09 | 2018-01-10 | 41 | 31 | 10 | [10 empty] | 2018-03-09 | 2018-04-04 | 12 | 0 | 12 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH BROOKFIELD | 178307 | 1535 | 996 | Solar | 01_552L3 | 2018-01-09 | 2018-01-10 | 41 | 41 | 0 | [10 empty] | 2018-03-09 | 2018-04-07 | 15 | 0 | 15 | [12 empty] | 2019-01-15 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | EVERETT | 178308 | 2149 | 3807.99 | Natural Gas | 12_37W9 | 2018-01-10 | 2018-01-11 | 43 | 25 | 18 | [10 empty] | 2018-03-30 | 2018-04-26 | 15 | 0 | 15 | [10 empty] | 2019-01-09 |  | 2019-06-07 |  | STD | [6 empty] | 2019-05-31 | 2019-05-31 | 2019-06-07 | Connected |  | No
National Grid | HAVERHILL | 178343 | 1832 | 500 | Solar | 14_74L5 | 2018-01-10 | 2018-01-11 | 11 | 11 | 0 | [5 empty] | 2018-05-10 | 2018-11-16 | 133 | 109 | 24 | 2018-03-12 | 2018-04-09 | 15 | 0 | 15 | 2018-05-10 | 2018-11-16 | 133 | 109 | 24 | [5 empty] | 2018-12-20 |  | 2019-11-15 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LEICESTER | 178344 | 1524 | 498 | Solar | 01_21W1 | 2018-01-11 | 2018-01-26 | 13 | 3 | 10 | [10 empty] | 2018-02-13 | 2018-03-01 | 11 | 1 | 10 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTHBOROUGH | 178345 | 1532 | 72 | Solar | 05_313W1 | 2018-01-11 | 2018-01-12 | 25 | 15 | 10 | 2018-02-20 | 2018-02-20 | 32 | 0 | 32 | [20 empty] | 2018-02-20 |  | 2019-01-17 |  | EXP | [8 empty] | 2018-12-20 | Connected |  | Yes
National Grid | NORTHBOROUGH | 178346 | 1532 | 56 | Solar | 05_313W1 | 2018-01-11 | 2018-01-12 | 29 | 19 | 10 | 2018-02-02 | 2018-02-21 | 28 | 0 | 28 | [20 empty] | 2018-02-26 |  | 2019-01-17 |  | EXP | [8 empty] | 2018-11-26 | Connected |  | Yes
National Grid | UXBRIDGE | 178349 | 1569 | 49.88 | Solar | 05_321W2 | 2018-01-12 | 2018-01-12 | 14 | 4 | 10 | 2018-02-02 | 2018-02-02 | 0 | 0 | 0 | [20 empty] | 2018-02-02 |  | 2019-01-17 |  | EXP | [8 empty] | 2018-07-18 | Connected |  | No
National Grid | UXBRIDGE | 178350 | 1569 | 24.94 | Solar | 05_321W2 | 2018-01-12 | 2018-01-12 | 29 | 4 | 25 | [25 empty] | 2018-02-02 | 2018-01-12 | 2019-01-17 |  | EXP | [8 empty] | 2018-07-18 | Connected |  | No
National Grid | LEOMINSTER | 178351 | 1453 | 5 | Solar | 01_207W2 | 2018-01-12 | 2018-02-27 | 9 | 9 | 0 | 2018-03-27 | 2018-03-28 | 1 | 0 | 1 | [20 empty] | 2018-03-28 |  | 2019-05-17 | Yes | EXP | [8 empty] | 2019-05-09 | Connected |  | No
National Grid | NEWBURY | 178380 | 1951 | 20 | Solar | 14_60L1 | 2018-01-15 | 2018-04-10 | 0 | 0 | 0 | 2018-04-10 | 2018-05-23 | 32 | 3 | 29 | [20 empty] | 2018-05-24 |  | 2019-01-20 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MILLBURY | 178381 | 1527 | 8.96 | Solar | 01_304W5 | 2018-01-15 | 2018-02-13 | 0 | 0 | 0 | 2018-02-27 | 2018-02-27 | 0 | 0 | 0 | [20 empty] | 2018-02-27 |  | 2019-01-21 |  | EXP | [8 empty] | 2018-07-31 | Connected |  | Yes
National Grid | BLACKSTONE | 178382 | 1504 | 7.6 | Solar | 05_321W9 | 2018-01-15 | 2018-01-16 | 56 | 27 | 29 | [27 empty] | 2019-01-21 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BEVERLY | 178383 | 1915 | 15.2 | Solar | 12_12L2 | 2018-01-15 | 2018-01-16 | 38 | 13 | 25 | 2018-03-27 | 2018-06-08 | 0 | 0 | 0 | [20 empty] | 2018-03-28 |  | 2019-01-21 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHELMSFORD | 178384 | 1824 | 3.8 | Solar | 14_16L1 | 2018-01-15 | 2018-01-16 | 32 | 3 | 29 | 2018-03-08 | 2018-03-08 | 0 | 0 | 0 | [20 empty] | 2018-03-13 |  | 2019-01-21 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | FLORENCE | 178385 | 1062 | 3.8 | Solar | 09_909W4 | 2018-01-15 | 2018-05-02 | 27 | 27 | 0 | [25 empty] | 2018-06-21 |  | 2019-01-21 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EVERETT | 178386 | 2149 | 7.6 | Solar | 12_37W6 | 2018-01-15 | 2018-01-16 | 0 | 0 | 0 | 2018-01-29 | 2018-02-20 | 0 | 0 | 0 | [20 empty] | 2018-02-20 |  | 2019-01-21 |  | EXP | [8 empty] | 2019-09-25 | Connected |  | No
National Grid | FOXBOROUGH | 178802 | 2035 | 4680 | Solar | 05_3432W1 | 2018-01-15 | 2018-01-30 | 8 | 0 | 8 | [10 empty] | 2018-02-13 | 2018-03-09 | 17 | 0 | 17 | [10 empty] | 2018-10-15 |  | 2020-08-10 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SOUTHBOROUGH | 178387 | 1772 | 10 | Solar | 05_317W1 | 2018-01-16 | 2018-01-17 | 16 | 0 | 16 | 2018-02-08 | 2018-02-08 | 0 | 0 | 0 | [20 empty] | 2018-02-08 |  | 2019-01-22 |  | EXP | [8 empty] | 2018-06-01 | Connected |  | No
National Grid | LOWELL | 178418 | 1854 | 6 | Solar | 14_21L3 | 2018-01-16 | 2018-01-17 | 22 | 0 | 22 | 2018-01-31 | 2018-02-16 | 0 | 0 | 0 | [20 empty] | 2018-02-16 |  | 2019-01-22 |  | EXP | [8 empty] | 2018-06-08 | Connected |  | Yes
National Grid | ANDOVER | 178419 | 1810 | 19 | Solar | 14_54L3 | 2018-01-16 | 2018-02-20 | 23 | 0 | 23 | 2018-02-20 | 2018-02-21 | 0 | 0 | 0 | [20 empty] | 2018-02-21 |  | 2019-01-22 |  | EXP | [8 empty] | 2018-11-07 | Connected |  | Yes
National Grid | AUBURN | 178422 | 1501 | 4000 | Solar | 01_7J386 | 2018-01-16 | 2018-01-17 | 24 | 0 | 24 | [10 empty] | 2018-02-21 | 2018-03-20 | 19 | 1 | 18 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SEEKONK | 178436 | 2771 | 20 | Solar | 05_7L1 | 2018-01-16 | 2018-03-06 | 0 | 0 | 0 | 2018-03-07 | 2018-03-07 | 0 | 0 | 0 | [20 empty] | 2018-03-07 | 2018-01-17 | 2019-03-11 |  | EXP | [8 empty] | 2018-08-15 | Connected |  | Yes
National Grid | BROOKFIELD | 178421 | 1506 | 3375 | Solar | 01_525L2 | 2018-01-17 | 2018-01-17 | 13 | 0 | 13 | [10 empty] | 2018-02-05 | 2018-02-26 | 14 | 0 | 14 | [10 empty] | 2018-09-11 |  | 2022-04-16 | Yes | STD |  | 2021-03-14 | 2021-12-02 | 264 | 7 | 257 | 2021-12-03 | 2021-12-03 | 2021-12-27 | Connected |  | No
National Grid | FALL RIVER | 178427 | 2721 | 42 | Solar | 05_115W52 | 2018-01-18 | 2018-01-18 | 15 | 0 | 15 | 2018-02-08 | 2018-02-09 | 39 | 0 | 39 | [20 empty] | 2018-02-09 |  | 2019-01-23 |  | EXP | [8 empty] | 2018-08-15 | Connected |  | No
National Grid | ATHOL | 178458 | 1331 | 10 | Solar | 09_702W1 | 2018-01-18 | 2018-02-20 | 10 | 2 | 8 | 2018-03-06 | 2018-03-27 | 0 | 0 | 0 | [20 empty] | 2018-03-27 |  | 2019-01-23 |  | EXP | [8 empty] | 2018-07-26 | Connected |  | Yes
National Grid | BELCHERTOWN | 178459 | 1007 | 8730 | Solar | 09_509L2 | 2018-01-18 | 2018-02-02 | 26 | 6 | 20 | [10 empty] | 2018-03-02 | 2018-04-05 | 13 | 0 | 13 | [12 empty] | 2019-01-27 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BELCHERTOWN | 178460 | 1007 | 4580 | Solar | 09_509L2 | 2018-01-18 | 2018-01-22 | 28 | 6 | 22 | [10 empty] | 2018-03-02 | 2018-04-05 | 13 | 0 | 13 | [11 empty] | 2018-01-19 | 2019-01-27 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HAMPDEN | 178461 | 1036 | 3875 | Solar | 09_139L1 | 2018-01-19 | 2018-01-22 | 25 | 0 | 25 | [10 empty] | 2018-02-27 | 2018-04-20 | 26 | 0 | 26 | [10 empty] | 2019-01-07 |  | 2022-11-30 | Yes | STD |  | 2022-01-14 | 2022-11-21 | 312 | 0 | 312 |  |  | 2022-11-30 | Connected |  | No
National Grid | GRANBY | 178462 | 1033 | 8300 | Solar | 09_527L1 | 2018-01-22 | 2018-01-23 | 24 | 0 | 24 | [10 empty] | 2018-02-27 | 2018-04-03 | 25 | 0 | 25 | [11 empty] | 2018-01-22 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BLACKSTONE | 178463 | 1504 | 3630 | Solar | 05_321W6 | 2018-01-22 | 2018-01-23 | 69 | 45 | 24 | [10 empty] | 2018-05-01 | 2018-05-15 | 10 | 0 | 10 | [10 empty] | 2019-01-31 |  | 2025-01-21 |  | STD | [9 empty] | Construction |  | No
National Grid | NEWBURYPORT | 178464 | 1950 | 199.8 | Solar | 14_60L4 | 2018-01-22 | 2018-03-06 | 0 | 0 | 0 | 2018-03-21 | 2018-03-06 | 0 | 0 | 0 | [20 empty] | 2018-03-06 |  | 2019-01-28 |  | EXP | [8 empty] | 2018-06-28 | Connected |  | Yes
National Grid | DOUGLAS | 178465 | 1516 | 1750 | Solar | 05_320W2 | 2018-01-22 | 2018-01-23 | 27 | 10 | 17 | [10 empty] | 2018-03-12 | 2018-05-05 | 40 | 19 | 21 | [12 empty] | 2019-01-28 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WENDELL DEPOT | 178466 | 1380 | 4800 | Solar | 09_705W1 | 2018-01-23 | 2018-01-24 | 23 | 0 | 23 | [10 empty] | 2018-02-27 | 2018-03-22 | 6 | 1 | 5 | [12 empty] | 2019-01-29 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | AUBURN | 178467 | 1501 | 299.7 | Solar | 01_26W1 | 2018-01-23 | 2018-02-08 | 2 | 2 | 0 | 2018-02-22 | 2018-02-22 | 0 | 0 | 0 | [20 empty] | 2018-02-22 |  | 2020-02-28 |  | EXP | [8 empty] | 2020-04-30 | Connected |  | No
National Grid | AUBURN | 178498 | 1501 | 276.4 | Solar | 01_406L2 | 2018-01-23 | 2018-02-08 | 0 | 0 | 0 | 2018-02-22 | 2018-02-22 | 0 | 0 | 0 | [20 empty] | 2018-02-22 |  | 2019-12-31 |  | EXP | [8 empty] | 2019-12-31 | Connected |  | No
National Grid | ANDOVER | 178499 | 1810 | 20 | Solar | 14_8L1 | 2018-01-23 | 2018-02-08 | 11 | 0 | 11 | 2018-02-08 | 2018-02-08 | 0 | 0 | 0 | [20 empty] | 2018-02-08 |  | 2019-01-29 |  | EXP | [8 empty] | 2018-08-02 | Connected |  | Yes
National Grid | HOUSATONIC | 178503 | 1236 | 37.8 | Solar | 09_1109W1 | 2018-01-24 | 2018-01-25 | 26 | 1 | 25 | 2018-03-20 | 2018-03-20 | 240 | 0 | 240 | [20 empty] | 2018-03-21 | 2018-01-24 | 2019-01-30 |  | EXP | [8 empty] | 2018-12-05 | Connected |  | Yes
National Grid | BROCKTON | 178505 | 2301 | 9.92 | Solar | 07_98W46 | 2018-01-24 | 2018-01-25 | 20 | 10 | 10 | 2018-02-23 | 2018-04-02 | 29 | 10 | 19 | [20 empty] | 2018-04-02 | 2018-01-25 | 2019-10-31 | Yes | EXP | [8 empty] | 2019-10-10 | Connected |  | Yes
National Grid | STOUGHTON | 178506 | 2072 | 2000 | Solar | 07_94W42 | 2018-01-25 | 2018-02-08 | 25 | 13 | 12 | [10 empty] | 2018-03-16 | 2018-05-01 | 33 | 15 | 18 | [10 empty] | 2018-11-27 |  | 2023-04-21 | Yes | STD |  | 2022-07-30 | 2023-01-14 | 169 | 0 | 169 |  |  | 2023-05-08 | Connected |  | No
National Grid | MILFORD | 178537 | 1757 | 486 | Solar | 05_336W1 | 2018-01-25 | 2018-01-26 | 24 | 0 | 24 | 2018-03-05 | 2019-07-08 | 103 | 0 | 103 | [22 empty] | 2019-01-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WEBSTER | 178538 | 1570 | 7.6 | Solar | 01_412L1 | 2018-01-25 | 2018-01-26 | 9 | 0 | 9 | 2018-02-08 | 2018-02-09 | 39 | 0 | 39 | [20 empty] | 2018-02-09 | 2018-01-26 | 2019-01-31 |  | EXP | [8 empty] | 2019-09-11 | Connected |  | No
National Grid | METHUEN | 178539 | 1844 | 7.6 | Solar | 14_74L1 | 2018-01-26 | 2018-01-26 | 9 | 1 | 8 | 2018-02-08 | 2018-02-09 | 0 | 0 | 0 | [20 empty] | 2018-02-09 | 2018-01-26 | 2019-01-31 | Yes | EXP |  | 2018-06-12 | 2018-06-21 | 9 | 0 | 9 |  |  | 2018-08-20 | Connected |  | Yes
National Grid | SPENCER | 178540 | 1562 | 4940 | Solar | 01_552L2 | 2018-01-26 | 2018-01-26 | 23 | 10 | 13 | [10 empty] | 2018-02-28 | 2018-03-28 | 20 | 0 | 20 | [10 empty] | 2018-09-20 |  | 2020-12-31 | Yes | STD |  | 2020-07-11 | 2020-11-25 | 138 | 5 | 133 | 2020-12-04 | 2020-12-04 | 2020-12-30 | Connected |  | No
National Grid | UXBRIDGE | 178541 | 1569 | 6 | Solar | 05_321W2 | 2018-01-29 | 2018-01-29 | 6 | 0 | 6 | 2018-02-06 |  | 41 | 0 | 41 | [20 empty] | 2018-02-07 |  | 2019-02-03 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEOMINSTER | 178543 | 1453 | 3.8 | Solar | 01_225W4 | 2018-01-29 | 2018-01-30 | 19 | 0 | 19 | 2018-02-27 | 2018-02-27 | 27 | 0 | 27 | [20 empty] | 2018-02-27 |  | 2019-02-04 |  | EXP | [8 empty] | 2018-10-24 | Connected |  | No
National Grid | TEWKSBURY | 178546 | 1876 | 604 | Solar | 14_70L1 | 2018-01-29 | 2018-01-31 | 36 | 31 | 5 | [10 empty] | 2018-03-22 | 2018-04-18 | 18 | 0 | 18 | [10 empty] | 2018-11-05 |  | 2020-06-08 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | TEWKSBURY | 178576 | 1876 | 524 | Solar | 14_70L1 | 2018-01-29 | 2018-01-31 | 36 | 31 | 5 | [10 empty] | 2018-03-22 | 2018-04-18 | 18 | 0 | 18 | [10 empty] | 2018-11-05 |  | 2020-06-08 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BILLERICA | 178577 | 1862 | 316 | Solar | 14_70L1 | 2018-01-30 | 2018-01-31 | 24 | 3 | 21 | [10 empty] | 2018-03-22 | 2018-04-18 | 19 | 0 | 19 | [10 empty] | 2018-11-05 | 2018-01-30 | 2020-06-08 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 178578 | 1507 | 4950 | Solar | 01_415L1 | 2018-01-30 | 2018-01-31 | 21 | 8 | 13 | [10 empty] | 2018-03-14 | 2018-05-18 | 24 | 0 | 24 | [10 empty] | 2019-01-11 |  | 2022-04-22 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | OAKHAM | 178579 | 1068 | 2500 | Solar | 09_1194T1 | 2018-01-31 | 2018-01-31 | 21 | 0 | 21 | [10 empty] | 2018-03-14 | 2018-04-10 | 16 | 0 | 16 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | TEWKSBURY | 178580 | 1876 | 402 | Solar | 14_70L1 | 2018-01-31 | 2018-02-01 | 35 | 25 | 10 | [10 empty] | 2018-03-22 | 2018-04-18 | 19 | 0 | 19 | [10 empty] | 2018-11-05 |  | 2020-06-08 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MARLBOROUGH | 178581 | 1752 | 10 | Solar | 05_311W4 | 2018-01-31 | 2018-02-01 | 20 | 0 | 20 | 2018-03-16 | 2018-03-21 | 3 | 0 | 3 | [20 empty] | 2018-03-21 |  | 2019-11-25 |  | EXP |  | 2018-07-28 | 2018-08-29 | 32 | 0 | 32 |  |  | 2019-10-07 | Connected |  | No
National Grid | MALDEN | 178582 | 2148 | 37.8 | Solar | 12_16W3 | 2018-01-31 | 2018-03-16 | 20 | 0 | 20 | 2018-04-13 | 2018-05-02 | 13 | 0 | 13 | [20 empty] | 2018-05-02 | 2018-01-31 | 2019-02-06 |  | EXP | [8 empty] | 2018-09-05 | Connected |  | Yes
National Grid | SOUTH GRAFTON | 178583 | 1560 | 225 | Solar | 05_320W3 | 2018-01-31 | 2018-02-02 | 0 | 0 | 0 | 2018-02-16 | 2018-02-16 | 0 | 0 | 0 | [20 empty] | 2018-02-16 |  | 2019-02-06 | Yes | EXP | [8 empty] | 2019-02-20 | Connected |  | Yes
National Grid | TEWKSBURY | 178584 | 1876 | 158 | Solar | 14_70L1 | 2018-01-31 | 2018-02-01 | 23 | 3 | 20 | [10 empty] | 2018-03-22 | 2018-04-17 | 18 | 0 | 18 | [10 empty] | 2018-11-05 | 2018-01-31 | 2020-06-08 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NANTUCKET | 178585 | 2554 | 1000 | Solar | 04_101L5 | 2018-01-31 | 2018-02-12 | 17 | 10 | 7 | [10 empty] | 2018-03-08 | 2018-03-12 | 3 | 3 | 0 | [10 empty] | 2018-09-26 | 2018-01-31 | 2019-12-20 | Yes | STD |  | 2019-05-22 | 2019-12-03 | 195 | 0 | 195 |  |  | 2019-12-13 | Connected |  | No
National Grid | SOUTHBRIDGE | 178615 | 1550 | 2800 | Solar | 01_413L8 | 2018-01-31 | 2018-02-01 | 20 | 0 | 20 | [10 empty] | 2018-03-15 | 2018-04-09 | 15 | 0 | 15 | [10 empty] | 2018-11-01 |  | 2020-12-31 | Yes | STD |  | 2020-04-03 | 2020-12-02 | 244 | 5 | 239 | 2020-12-03 | 2020-12-03 | 2020-12-30 | Connected |  | No
National Grid | BILLERICA | 178616 | 1862 | 444 | Solar | 14_70L1 | 2018-01-31 | 2018-02-01 | 35 | 30 | 5 | [10 empty] | 2018-03-22 | 2018-04-17 | 18 | 0 | 18 | [10 empty] | 2018-11-05 |  | 2020-06-08 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | GREAT BARRINGTON | 178617 | 1230 | 11.4 | Solar | 09_1109W3 | 2018-01-31 | 2018-02-01 | 20 | 0 | 20 | 2018-03-07 | 2018-03-07 | 0 | 0 | 0 | [20 empty] | 2018-03-07 | 2018-01-31 | 2020-09-16 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | AMESBURY | 178618 | 1913 | 7.6 | Solar | 14_275L4 | 2018-01-31 | 2018-03-07 | 20 | 0 | 20 | 2018-03-07 | 2018-04-04 | 0 | 0 | 0 | [20 empty] | 2018-03-08 | 2018-01-31 | 2019-11-29 | Yes | EXP | [8 empty] | 2019-11-15 | Connected |  | No
National Grid | WARE | 178619 | 1082 | 7.6 | Solar | 09_501L2 | 2018-01-31 | 2018-02-01 | 20 | 0 | 20 | 2018-03-07 | 2018-03-08 | 1 | 0 | 1 | [20 empty] | 2018-03-08 |  | 2019-06-17 | Yes | EXP |  | 2019-03-07 | 2019-03-06 | 0 | 0 | 0 |  |  | 2019-05-17 | Connected |  | No
National Grid | FALL RIVER | 178620 | 2721 | 144 | Solar | 05_106W42 | 2018-02-01 | 2018-02-02 | 19 | 0 | 19 | 2018-03-05 | 2018-03-05 | 0 | 0 | 0 | [20 empty] | 2018-03-05 | 2018-02-01 | 2019-02-07 |  | EXP | [8 empty] | 2018-07-10 | Connected |  | No
National Grid | SHEFFIELD | 178621 | 1257 | 2125 | Solar | 09_1108W2 | 2018-02-01 | 2018-02-02 | 19 | 0 | 19 | [10 empty] | 2018-03-05 | 2018-04-17 | 20 | 10 | 10 | [10 empty] | 2018-11-29 |  | 2023-03-25 | Yes | STD |  | 2019-09-06 | 2021-11-03 | 790 | 149 | 641 |  |  | 2022-12-05 | Connected |  | No
National Grid | DUNSTABLE | 178622 | 1827 | 7.6 | Solar | 01_210L1 | 2018-02-01 | 2018-02-02 | 19 | 0 | 19 | 2018-03-02 | 2018-12-20 | 189 | 0 | 189 | [20 empty] | 2018-03-02 |  | 2019-02-07 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WRENTHAM | 178803 | 2093 | 15.2 | Solar | 05_3422W1 | 2018-02-01 | 2018-03-13 | 32 | 0 | 32 | 2018-04-26 | 2018-04-26 | 0 | 0 | 0 | [20 empty] | 2018-04-26 |  | 2019-02-07 |  | EXP | [8 empty] | 2018-12-20 | Connected |  | Yes
National Grid | BELCHERTOWN | 178623 | 1007 | 8.96 | Solar | 09_509L2 | 2018-02-02 | 2018-02-02 | 27 | 8 | 19 | 2018-03-29 | 2018-03-30 | 1 | 0 | 1 | [20 empty] | 2018-03-30 | 2018-02-02 | 2019-02-07 |  | EXP | [8 empty] | 2018-08-03 | Connected |  | Yes
National Grid | SOUTHBRIDGE | 178653 | 1550 | 4300 | Solar | 01_413L8 | 2018-02-02 | 2018-02-02 | 19 | 0 | 19 | [10 empty] | 2018-03-15 | 2018-04-09 | 15 | 0 | 15 | [10 empty] | 2018-11-01 |  | 2020-12-31 | Yes | STD |  | 2020-03-17 | 2020-12-02 | 261 | 5 | 256 | 2020-12-03 | 2020-12-03 | 2020-12-24 | Connected |  | No
National Grid | DIGHTON | 178656 | 2715 | 4875 | Solar | 05_19W73 | 2018-02-02 | 2018-02-05 | 42 | 24 | 18 | [26 empty] | 2018-02-05 | 2019-02-10 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTHAMPTON | 178658 | 1060 | 3564 | Solar | 09_909W4 | 2018-02-05 | 2018-02-06 | 21 | 21 | 0 | [10 empty] | 2018-03-08 | 2018-04-11 | 24 | 4 | 20 | [10 empty] | 2018-08-24 |  | 2020-12-31 | Yes | STD |  | 2020-05-08 | 2020-11-18 | 195 | 5 | 190 | 2020-11-20 | 2020-11-20 | 2020-12-31 | Connected |  | No
National Grid | PEPPERELL | 178659 | 1463 | 415 | Solar | 01_226L1 | 2018-02-05 | 2018-03-07 | 9 | 0 | 9 | 2018-03-20 | 2018-04-24 | 25 | 0 | 25 | 2018-07-11 | 2018-08-06 | 18 | 0 | 18 | [5 empty] | 2018-07-11 | 2018-08-06 | 18 | 0 | 18 | [5 empty] | 2018-08-13 | 2018-02-06 | 2020-10-21 |  | EXP | [8 empty] | 2020-10-21 | Connected |  | No
National Grid | SPENCER | 178660 | 1562 | 1000 | Solar | 01_55K11 | 2018-02-06 | 2018-02-06 | 31 | 14 | 17 | [10 empty] | 2018-04-06 | 2018-05-02 | 10 | 0 | 10 | [10 empty] | 2018-12-04 |  | 2021-11-22 | Yes | STD |  | 2021-01-09 | 2021-10-21 | 285 | 3 | 282 |  |  | 2021-11-03 | Connected |  | No
National Grid | DIGHTON | 178694 | 2715 | 5.2 | Solar | 05_19W74 | 2018-02-06 | 2018-02-07 | 16 | 0 | 16 | 2018-03-14 | 2018-04-29 | 32 | 0 | 32 | [20 empty] | 2018-05-02 |  | 2019-02-12 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEOMINSTER | 178695 | 1453 | 500 | Solar | 01_219W1 | 2018-02-06 | 2018-02-19 | 9 | 0 | 9 | [5 empty] | 2018-06-21 | 2018-07-19 | 19 | 0 | 19 | 2018-03-05 | 2018-04-11 | 28 | 8 | 20 | 2018-06-21 | 2018-07-19 | 19 | 0 | 19 | [5 empty] | 2018-07-25 |  | 2019-11-01 |  | STD | [8 empty] | 2019-12-23 | Connected |  | No
National Grid | WESTFORD | 178697 | 1886 | 7.6 | Solar | 14_57L2 | 2018-02-06 | 2018-02-07 | 16 | 0 | 16 | 2018-02-20 | 2018-03-08 | 0 | 0 | 0 | [20 empty] | 2018-03-08 | 2018-02-07 | 2019-02-12 |  | EXP | [8 empty] | 2019-10-01 | Connected |  | No
National Grid | SALISBURY | 178204 | 1952 | 4000 | Solar | 14_7L4 | 2018-02-07 | 2018-02-20 | 1 | 0 | 1 | [10 empty] | 2018-02-21 | 2018-04-18 | 28 | 21 | 7 | [10 empty] | 2018-11-15 |  | 2021-02-25 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | GRANBY | 178698 | 1033 | 4400 | Solar | 09_527L1 | 2018-02-07 | 2018-02-08 | 25 | 10 | 15 | [10 empty] | 2018-04-02 | 2018-04-27 | 14 | 0 | 14 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH GRAFTON | 178699 | 1536 | 2000 | Solar | 01_304W4 | 2018-02-07 | 2018-02-08 | 20 | 5 | 15 | [10 empty] | 2018-03-26 | 2018-04-23 | 164 | 42 | 122 | [11 empty] | 2018-02-08 | 2019-02-13 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTHAMPTON | 178700 | 1062 | 4320 | Solar | 09_909W4 | 2018-02-08 | 2018-02-08 | 42 | 37 | 5 | [10 empty] | 2018-04-09 | 2018-05-02 | 17 | 0 | 17 | [10 empty] | 2019-02-04 |  | 2019-12-17 | Yes | STD |  | 2019-09-11 | 2019-11-19 | 69 | 0 | 69 |  |  | 2019-12-20 | Connected |  | No
National Grid | WARE | 178701 | 1082 | 5000 | Solar | 09_501L1 | 2018-02-08 | 2018-02-09 | 22 | 8 | 14 | [10 empty] | 2018-03-29 | 2018-05-04 | 16 | 0 | 16 | [12 empty] | 2019-02-14 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | STOUGHTON | 178702 | 2072 | 358 | Solar | 07_94W42 | 2018-02-09 | 2018-02-26 | 10 | 0 | 10 | 2018-03-12 | 2018-05-11 | 44 | 0 | 44 | 2018-06-21 | 2018-07-20 | 21 | 4 | 17 | [5 empty] | 2018-06-21 | 2018-07-20 | 21 | 4 | 17 | [5 empty] | 2018-08-03 |  | 2020-06-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTH GRAFTON | 178730 | 1536 | 11.4 | Solar | 01_328W3 | 2018-02-09 | 2018-02-09 | 38 | 24 | 14 | [27 empty] | 2019-02-14 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BELLINGHAM | 178693 | 2019 | 10 | Solar | 05_344W4 | 2018-02-09 10:18 | 2018-02-09 | 70 | 0 | 70 | 2018-05-21 | 2018-05-21 | 0 | 0 | 0 | [20 empty] | 2018-06-06 |  | 2019-02-12 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WILLIAMSTOWN | 178161 | 1267 | 233.1 | Solar | 09_1003W1 | 2018-02-12 | 2018-04-03 | 10 | 0 | 10 | 2018-04-17 | 2018-05-07 | 14 | 0 | 14 | [20 empty] | 2018-09-27 |  | 2019-02-18 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | PALMER | 178162 | 1069 | 2490 | Solar | 09_0504 | 2018-02-12 | 2018-02-13 | 31 | 2 | 29 | [10 empty] | 2018-04-13 | 2018-04-17 | 1 | 0 | 1 | [12 empty] | 2019-02-18 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | GRANBY | 178731 | 1033 | 4400 | Solar | 09_527L1 | 2018-02-12 | 2018-02-13 | 22 | 10 | 12 | [10 empty] | 2018-04-02 | 2018-04-27 | 14 | 0 | 14 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 178734 | 1603 | 3.8 | Solar | 01_6W2 | 2018-02-12 | 2018-02-21 | 0 | 0 | 0 | 2018-03-07 | 2018-12-20 | 189 | 0 | 189 | [20 empty] | 2018-03-19 | 2018-02-12 | 2019-02-18 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEBSTER | 178735 | 1570 | 3.8 | Solar | 01_412L5 | 2018-02-12 | 2018-02-13 | 12 | 0 | 12 | 2018-03-15 | 2018-03-16 | 2 | 0 | 2 | [20 empty] | 2018-03-16 |  | 2019-11-21 | Yes | EXP |  | 2019-04-23 | 2019-04-22 | 0 | 0 | 0 |  |  | 2019-08-16 | Connected |  | No
National Grid | SPENCER | 178736 | 1562 | 7.6 | Solar | 01_552L1 | 2018-02-12 | 2018-03-01 | 0 | 0 | 0 | 2018-03-15 | 2018-12-20 | 189 | 0 | 189 | [20 empty] | 2018-03-16 | 2018-02-12 | 2019-02-18 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EAST LONGMEADOW | 178737 | 1028 | 11.4 | Solar | 09_508L5 | 2018-02-12 | 2018-03-23 | 0 | 0 | 0 | 2018-03-23 | 2018-05-14 | 36 | 0 | 36 | [20 empty] | 2018-05-14 |  | 2019-08-12 | Yes | EXP |  | 2019-03-07 | 2019-03-06 | 0 | 0 | 0 |  |  | 2019-08-03 | Connected |  | No
National Grid | WILLIAMSTOWN | 178738 | 1267 | 50 | Solar | 09_1003W2 | 2018-02-12 | 2018-03-13 | 10 | 0 | 10 | 2018-03-27 | 2018-04-27 | 23 | 0 | 23 | [20 empty] | 2019-03-14 | 2018-02-13 | 2019-02-18 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SOMERSET | 178164 | 2726 | 617 | Solar | 05_19W74 | 2018-02-13 | 2018-02-14 | 33 | 0 | 33 | [10 empty] | 2018-04-03 | 2018-04-30 | 19 | 0 | 19 | [10 empty] | 2018-11-16 |  | 2022-05-13 | Yes | STD |  | 2020-05-27 | 2021-08-31 | 461 | 8 | 453 |  |  | 2022-05-13 | Connected |  | No
National Grid | SALISBURY | 178166 | 1952 | 11.4 | Solar | 14_7L4 | 2018-02-14 | 2018-02-15 | 3 | 3 | 0 | [25 empty] | 2018-02-21 |  | 2019-02-20 |  | EXP | [8 empty] | 2019-10-03 | Connected |  | No
National Grid | PEMBROKE | 178167 | 2359 | 11.4 | Solar | 07_910W25 | 2018-02-14 | 2018-02-15 | 3 | 3 | 0 | [25 empty] | 2018-02-21 |  | 2019-02-20 |  | EXP | [8 empty] | 2019-09-30 | Connected |  | No
National Grid | WESTPORT | 178798 | 2790 | 6 | Solar | 05_115W45 | 2018-02-14 | 2018-02-14 | 18 | 0 | 18 | 2018-03-28 | 2018-03-28 | 1 | 0 | 1 | [20 empty] | 2018-03-28 | 2018-02-15 | 2019-02-19 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHARLTON | 178200 | 1507 | 4999 | Solar | 01_415L3 | 2018-02-15 | 2018-02-15 | 4 | 3 | 1 | [10 empty] | 2018-02-22 | 2018-03-20 | 7 | 0 | 7 | [10 empty] | 2018-11-06 |  |  | Yes | STD | [9 empty] | Study |  | No
National Grid | MANCHESTER | 178201 | 1944 | 10 | Solar | 12_51T1 | 2018-02-15 | 2018-02-16 | 9 | 9 | 0 | 2018-03-08 | 2018-03-08 | 24 | 0 | 24 | [20 empty] | 2018-03-08 | 2018-02-16 | 2019-02-21 |  | EXP | [8 empty] | 2019-05-07 | Connected |  | No
National Grid | FOXBOROUGH | 178799 | 2035 | 432.9 | Solar | 05_3424W1 | 2018-02-16 | 2018-03-07 | 0 | 0 | 0 | [10 empty] | 2018-03-07 | 2018-04-20 | 33 | 8 | 25 | [10 empty] | 2018-11-19 |  | 2020-09-11 | Yes | STD |  | 2020-01-10 | 2020-05-08 | 119 | 0 | 119 |  |  | 2020-09-03 | Connected |  | No
National Grid | WILLIAMSTOWN | 178205 | 1267 | 2.76 | Solar | 09_1001W1 | 2018-02-19 | 2018-02-20 | 8 | 8 | 0 | 2018-03-08 | 2018-10-11 | 143 | 0 | 143 | [20 empty] | 2018-03-12 |  | 2019-02-25 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NEW BRAINTREE | 178235 | 1531 | 2500 | Solar | 09_1194T1 | 2018-02-19 | 2018-02-20 | 6 | 6 | 0 | [10 empty] | 2018-02-28 | 2018-04-28 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | PALMER | 178238 | 1069 | 6 | Solar | 09_503L1 | 2018-02-20 | 2018-02-20 | 8 | 8 | 0 | [25 empty] | 2018-03-27 |  | 2019-02-25 |  | EXP | [8 empty] | 2018-08-07 | Connected |  | Yes
National Grid | NORTH BROOKFIELD | 178239 | 1535 | 2000 | Solar | 01_525L1 | 2018-02-20 | 2018-02-20 | 8 | 8 | 0 | [10 empty] | 2018-03-07 |  | 24 | 0 | 24 | [12 empty] | 2019-02-25 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NEWBURY | 178240 | 1951 | 10 | Solar | 14_60L1 | 2018-02-20 | 2018-02-20 | 6 | 6 | 0 | 2018-02-28 | 2018-02-28 | 0 | 0 | 0 | [20 empty] | 2018-02-28 |  | 2019-02-25 |  | EXP | [8 empty] | 2018-10-17 | Connected |  | No
National Grid | BEVERLY | 178243 | 1915 | 15.04 | Solar | 12_12L2 | 2018-02-20 | 2018-02-21 | 31 | 31 | 0 | [27 empty] | 2019-02-26 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | REVERE | 178244 | 2151 | 153.2 | Solar | 12_7W4 | 2018-02-20 | 2018-02-21 | 3 | 0 | 3 | 2018-06-14 | 2018-07-10 | 18 | 14 | 4 | 2018-04-04 | 2018-06-14 | 51 | 44 | 7 | [5 empty] | 2018-04-04 | 2018-06-14 | 51 | 44 | 7 | [5 empty] | 2018-07-12 | 2018-02-21 | 2021-07-31 |  | EXP | [8 empty] | 2021-07-14 | Connected |  | No
National Grid | BROOKFIELD | 178274 | 1506 | 4998 | Solar | 01_408L2 | 2018-02-21 | 2018-02-21 | 0 | 0 | 0 | [10 empty] | 2018-02-21 | 2018-05-24 | 67 | 49 | 18 | [10 empty] | 2018-10-25 |  | 2026-04-17 | Yes | STD | [9 empty] | Design |  | No
National Grid | FALL RIVER | 178275 | 2720 | 990 | Solar | 05_28W41 | 2018-02-21 | 2018-02-22 | 1 | 1 | 0 | [10 empty] | 2018-02-23 | 2018-05-08 | 29 | 0 | 29 | [12 empty] | 2019-02-27 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WARREN | 178276 | 1083 | 825 | Solar | 09_516L3 | 2018-02-22 | 2018-02-22 | 1 | 0 | 1 | [10 empty] | 2018-02-23 | 2018-04-06 | 19 | 12 | 7 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | FRANKLIN | 178800 | 2038 | 20.16 | Solar | 05_348W5 | 2018-02-22 | 2018-02-23 | 29 | 29 | 0 | [27 empty] | 2019-02-28 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOUTHFIELD | 178278 | 1259 | 10 | Solar | 09_1109W1 | 2018-02-23 | 2018-02-23 | 5 | 5 | 0 | 2018-03-07 | 2018-10-11 | 143 | 0 | 143 | [20 empty] | 2018-03-07 |  | 2019-02-28 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 178279 | 2302 | 7.6 | Solar | 07_91W40 | 2018-02-23 | 2018-02-23 | 5 | 5 | 0 | 2018-03-16 | 2018-03-21 | 3 | 0 | 3 | [20 empty] | 2018-03-21 | 2018-02-23 | 2020-09-16 |  | EXP | [8 empty] | 2020-07-18 | Connected |  | No
National Grid | NORTHBRIDGE | 178280 | 1534 | 2930 | Solar | 05_320W3 | 2018-02-23 | 2018-02-26 | 2 | 0 | 2 | [10 empty] | 2018-02-28 | 2018-03-27 | 19 | 0 | 19 | [10 empty] | 2018-09-18 |  | 2024-09-18 | Yes | STD |  | 2022-05-21 |  | 696 | 600 | 96 |  |  |  | Construction |  | No
National Grid | STURBRIDGE | 178281 | 1566 | 7.6 | Solar | 01_413L2 | 2018-02-23 | 2018-02-26 | 4 | 4 | 0 | 2018-03-02 | 2018-03-02 | 0 | 0 | 0 | [20 empty] | 2018-03-02 |  | 2019-03-03 |  | EXP | [8 empty] | 2018-12-21 | Connected |  | No
National Grid | CHESHIRE | 178282 | 1225 | 4375 | Solar | 09_1021W2 | 2018-02-23 | 2018-02-26 | 4 | 4 | 0 | [10 empty] | 2018-03-06 | 2018-04-25 | 37 | 15 | 22 | [10 empty] | 2018-12-17 |  | 2021-08-18 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ORANGE | 178311 | 1368 | 1625 | Solar | 09_702W2 | 2018-02-26 | 2018-02-26 | 11 | 11 | 0 | [10 empty] | 2018-03-28 | 2018-07-24 | 15 | 0 | 15 | [12 empty] | 2019-03-03 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WEST NEWBURY | 178312 | 1985 | 7.6 | Solar | 14_47L2 | 2018-02-26 | 2018-02-26 | 4 | 4 | 0 | 2018-03-05 | 2018-03-05 | 24 | 0 | 24 | [20 empty] | 2018-03-05 | 2018-02-26 | 2019-03-03 |  | EXP | [8 empty] | 2019-10-11 | Connected |  | No
National Grid | CHELMSFORD | 178313 | 1824 | 875 | Solar | 14_58L2 | 2018-02-26 | 2018-02-26 | 0 | 0 | 0 | [10 empty] | 2018-02-26 | 2018-04-06 | 29 | 0 | 29 | [10 empty] | 2018-08-27 |  | 2022-04-04 | Yes | STD |  | 2021-04-20 | 2021-10-12 | 175 | 3 | 172 |  |  | 2022-03-28 | Connected |  | No
National Grid | HAVERHILL | 178314 | 1830 | 2800 | Solar | 14_2329 | 2018-02-26 | 2018-02-26 | 2 | 2 | 0 | [10 empty] | 2018-02-28 | 2018-04-11 | 19 | 10 | 9 | [10 empty] | 2018-12-06 |  | 2021-03-31 |  | STD |  | 2020-01-17 | 2021-01-04 | 353 | 5 | 348 |  |  | 2021-03-11 | Connected |  | No
National Grid | REHOBOTH | 178316 | 2769 | 7.6 | Solar | 05_7L4 | 2018-02-26 | 2018-02-27 | 3 | 3 | 0 | 2018-03-16 | 2018-10-30 | 156 | 3 | 153 | [20 empty] | 2018-03-26 |  | 2019-03-04 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEST NEWBURY | 178352 | 1985 | 10 | Solar | 14_47L2 | 2018-02-27 | 2018-02-28 | 2 | 2 | 0 | 2018-03-13 | 2018-03-13 | 0 | 0 | 0 | [20 empty] | 2018-03-13 |  | 2019-03-05 |  | EXP | [8 empty] | 2019-10-15 | Connected |  | No
National Grid | SOUTHBRIDGE | 178353 | 1550 | 5 | Solar | 01_413L1 | 2018-02-27 | 2018-02-28 | 2 | 2 | 0 | 2018-03-06 | 2018-03-06 | 239 | 0 | 239 | [20 empty] | 2018-03-06 |  | 2019-03-05 |  | EXP | [8 empty] | 2018-09-12 | Connected |  | No
National Grid | NORTHBOROUGH | 178354 | 1532 | 480 | Solar | 05_313W3 | 2018-02-27 | 2018-02-28 | 2 | 2 | 0 | 2018-03-02 | 2018-11-16 | 169 | 9 | 160 | [22 empty] | 2019-03-05 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | FOXBOROUGH | 178801 | 2035 | 275 | Solar | 05_3431W2 | 2018-02-27 | 2018-02-28 | 10 | 10 | 0 | 2018-03-29 | 2018-04-02 | 2 | 0 | 2 | [20 empty] | 2018-04-02 |  | 2019-03-05 |  | EXP | [8 empty] | 2018-10-12 | Connected |  | No
National Grid | DUDLEY | 178355 | 1571 | 2990 | Solar | 01_412L4 | 2018-02-28 | 2018-03-01 | 1 | 1 | 0 | [10 empty] | 2018-03-02 | 2018-06-15 | 24 | 0 | 24 | [12 empty] | 2019-03-06 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORWELL | 178356 | 2061 | 358.4 | Solar | 07_96W40 | 2018-02-28 | 2018-03-01 | 7 | 0 | 7 | 2018-03-12 | 2018-08-29 | 121 | 17 | 104 | [20 empty] | 2018-08-29 |  | 2020-03-06 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SAUGUS | 178358 | 1906 | 11.4 | Solar | 12_13J3 | 2018-03-01 | 2018-03-02 | 10 | 0 | 10 | 2018-03-16 | 2018-04-25 | 28 | 0 | 28 | [20 empty] | 2018-05-10 |  | 2020-03-23 |  | EXP | [8 empty] | 2020-01-17 | Connected |  | No
National Grid | LEOMINSTER | 178359 | 1453 | 17.28 | Solar | 01_207W3 | 2018-03-01 | 2018-04-12 | 10 | 0 | 10 | 2018-04-27 | 2018-04-26 | 0 | 0 | 0 | [20 empty] | 2018-07-16 |  | 2019-03-07 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WINCHENDON | 178389 | 1475 | 15.2 | Solar | 01_612W1 | 2018-03-01 | 2018-03-02 | 11 | 11 | 0 | 2018-04-03 | 2018-04-30 | 19 | 0 | 19 | [21 empty] | 2018-03-01 | 2019-03-07 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MILFORD | 178390 | 1757 | 15.2 | Solar | 05_336W3 | 2018-03-01 | 2018-03-02 | 0 | 0 | 0 | 2018-03-16 | 2018-03-21 | 3 | 0 | 3 | [20 empty] | 2018-03-21 |  | 2019-10-31 | Yes | EXP | [8 empty] | 2019-10-24 | Connected |  | No
National Grid | SAUGUS | 178391 | 1906 | 476 | Solar | 12_23W1 | 2018-03-02 | 2018-03-02 | 4 | 0 | 4 | 2018-03-08 | 2018-05-29 | 58 | 37 | 21 | [20 empty] | 2018-07-23 |  | 2020-12-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SWANSEA | 178392 | 2777 | 10 | Solar | 05_11W83 | 2018-03-02 | 2018-03-02 | 41 | 40 | 1 | 2018-04-04 | 2018-04-30 | 18 | 0 | 18 | [20 empty] | 2018-09-13 | 2018-03-02 | 2019-03-07 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH DIGHTON | 178393 | 2764 | 10 | Solar | 05_19W74 | 2018-03-02 | 2018-03-06 | 8 | 0 | 8 | 2018-03-29 | 2018-05-04 | 54 | 0 | 54 | [20 empty] | 2018-09-06 |  | 2019-03-11 |  | EXP | [8 empty] | 2018-11-26 | Connected |  | Yes
National Grid | FALL RIVER | 178394 | 2721 | 2470 | Solar | 05_115W53 | 2018-03-02 | 2018-03-06 | 0 | 0 | 0 | [10 empty] | 2018-03-06 | 2018-04-12 | 18 | 0 | 18 | [12 empty] | 2019-03-11 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SWANSEA | 178395 | 2777 | 7.6 | Solar | 05_11W83 | 2018-03-02 | 2018-03-06 | 0 | 0 | 0 | 2018-03-16 | 2018-03-21 | 3 | 0 | 3 | [20 empty] | 2018-03-21 |  | 2019-03-11 |  | EXP | [8 empty] | 2018-12-20 | Connected |  | No
National Grid | WARE | 178396 | 1082 | 19.2 | Solar | 09_501L2 | 2018-03-04 | 2018-03-06 | 1 | 1 | 0 | 2018-03-20 | 2018-03-30 | 8 | 0 | 8 | [20 empty] | 2018-03-20 |  | 2019-03-11 |  | EXP | [8 empty] | 2018-07-27 | Connected |  | No
National Grid | ATHOL | 178397 | 1331 | 3332 | Solar | 09_702W2 | 2018-03-05 | 2018-03-06 | 0 | 0 | 0 | [10 empty] | 2018-03-07 | 2018-04-17 | 20 | 7 | 13 | [5 empty] | 2019-01-09 | 2020-01-06 | 249 | 42 | 207 |  |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTFORD | 178428 | 1886 | 22.72 | Solar | 14_58L1 | 2018-03-05 | 2018-03-06 | 39 | 37 | 2 | [25 empty] | 2018-12-21 |  | 2019-03-11 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ORANGE | 178430 | 1364 | 636 | Solar | 09_705W3 | 2018-03-05 | 2018-03-06 | 19 | 19 | 0 | [27 empty] | 2019-03-11 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SHEFFIELD | 178431 | 1257 | 636 | Solar | 09_1108W2 | 2018-03-05 | 2018-03-06 | 19 | 19 | 0 | [27 empty] | 2019-03-11 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | PEPPERELL | 178432 | 1463 | 636 | Solar | 01_226L2 | 2018-03-05 | 2018-03-06 | 19 | 19 | 0 | [27 empty] | 2019-03-11 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | PETERSHAM | 178434 | 1366 | 636 | Solar | 09_604W1 | 2018-03-05 | 2018-03-06 | 19 | 19 | 0 | [27 empty] | 2019-03-11 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ORANGE | 178435 | 1364 | 636 | Solar | 09_705W2 | 2018-03-05 | 2018-03-06 | 19 | 19 | 0 | [27 empty] | 2019-03-11 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH BILLERICA | 178438 | 1862 | 7.6 | Solar | 14_70L1 | 2018-03-06 | 2018-03-07 | 0 | 0 | 0 | 2018-03-16 | 2018-03-16 | 0 | 0 | 0 | [20 empty] | 2018-03-16 |  | 2019-03-12 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTH BILLERICA | 178469 | 1862 | 11.4 | Solar | 14_70L5 | 2018-03-06 | 2018-03-07 | 0 | 0 | 0 | 2018-03-16 | 2018-03-16 | 0 | 0 | 0 | [20 empty] | 2018-03-16 |  | 2021-05-17 |  | EXP | [8 empty] | 2021-04-16 | Connected |  | No
National Grid | MEDFORD | 178470 | 2155 | 60 | Solar | 12_37W3 | 2018-03-06 | 2018-03-07 | 0 | 0 | 0 | 2018-03-13 | 2018-03-13 | 0 | 0 | 0 | [20 empty] | 2018-03-13 |  |  |  | EXP | [8 empty] | 2020-08-14 | Connected |  | No
National Grid | NORTH CHELMSFORD | 178471 | 1863 | 7.6 | Solar | 14_2L2 | 2018-03-06 | 2018-03-07 | 0 | 0 | 0 | 2018-03-16 | 2018-03-21 | 3 | 0 | 3 | [20 empty] | 2018-03-21 | 2018-03-07 | 2019-03-12 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | FRANKLIN | 178472 | 2038 | 905.8 | Solar | 05_344W3 | 2018-03-07 | 2018-03-21 | 0 | 0 | 0 | [10 empty] | 2018-03-14 | 2018-05-03 | 36 | 0 | 36 | [10 empty] | 2019-02-15 | 2018-03-07 | 2022-11-28 | Yes | STD |  | 2020-06-13 | 2022-01-28 | 595 | 182 | 413 |  |  | 2022-11-28 | Connected |  | No
National Grid | ROCKLAND | 178473 | 2370 | 10 | Solar | 07_93W40 | 2018-03-07 | 2018-03-07 | 6 | 0 | 6 | 2018-03-15 | 2018-05-09 | 39 | 0 | 39 | [20 empty] | 2018-05-11 |  | 2019-03-12 | Yes | EXP | [8 empty] | 2018-12-14 | Connected |  | No
National Grid | REHOBOTH | 178474 | 2769 | 636 | Solar | 05_7L5 | 2018-03-07 | 2018-03-07 | 19 | 19 | 0 | [27 empty] | 2019-03-12 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MILFORD | 178508 | 1757 | 5.06 | Solar | 05_335W9 | 2018-03-07 | 2018-03-08 | 5 | 0 | 5 | 2018-03-15 | 2019-06-05 | 85 | 0 | 85 | [20 empty] | 2018-05-11 |  | 2019-03-13 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 178509 | 2301 | 60 | Solar | 07_98W44 | 2018-03-08 | 2018-03-08 | 0 | 0 | 0 | 2018-03-19 | 2019-03-20 | 55 | 41 | 14 | [20 empty] | 2018-03-20 | 2018-03-08 | 2019-03-13 |  | EXP | [8 empty] | 2019-05-30 | Connected |  | No
National Grid | WHITMAN | 178510 | 2382 | 6 | Solar | 07_797W29 | 2018-03-08 | 2018-03-08 | 0 | 0 | 0 | 2018-03-15 | 2018-05-09 | 270 | 0 | 270 | [20 empty] | 2018-05-11 |  | 2019-03-13 | Yes | EXP | [8 empty] | 2018-10-23 | Connected |  | No
National Grid | WEST NEWBURY | 178511 | 1985 | 7.6 | Solar | 14_47L1 | 2018-03-08 | 2018-03-08 | 0 | 0 | 0 | 2018-03-16 | 2018-03-21 | 3 | 0 | 3 | [20 empty] | 2018-03-21 |  | 2019-03-13 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOMERSET | 178512 | 2726 | 16.6 | Solar | 05_18J7 | 2018-03-08 | 2018-03-08 | 0 | 0 | 0 | 2018-03-12 | 2018-03-12 | 0 | 0 | 0 | [20 empty] | 2018-03-12 | 2018-03-08 | 2019-03-13 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RANDOLPH | 178514 | 2368 | 10 | Solar | 07_5W3 | 2018-03-08 | 2018-03-09 | 25 | 0 | 25 | 2018-04-13 | 2018-05-09 | 18 | 0 | 18 | [20 empty] | 2018-05-11 |  | 2019-08-01 | Yes | EXP | [8 empty] | 2019-08-01 | Connected |  | No
National Grid | SWANSEA | 178548 | 2777 | 6 | Solar | 05_11W81 | 2018-03-09 | 2018-03-29 | 24 | 24 | 0 | 2018-04-27 | 2018-05-04 | 5 | 0 | 5 | [20 empty] | 2018-05-04 |  | 2019-03-18 |  | EXP | [8 empty] | 2018-10-23 | Connected |  | No
National Grid | SWANSEA | 178549 | 2777 | 5 | Solar | 05_11W81 | 2018-03-09 | 2018-03-29 | 22 | 0 | 22 | 2018-04-27 | 2018-05-08 | 7 | 0 | 7 | [20 empty] | 2018-05-08 |  | 2019-03-18 |  | EXP | [8 empty] | 2018-10-29 | Connected |  | No
National Grid | METHUEN | 178551 | 1844 | 9 | Solar | 14_43L2 | 2018-03-09 | 2018-03-13 | 18 | 18 | 0 | 2018-04-12 | 2018-05-09 | 30 | 0 | 30 | [20 empty] | 2018-04-30 |  | 2019-03-18 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EVERETT | 178254 | 2149 | 33.3 | Solar | 12_37W9 | 2018-03-12 01:00 | 2018-03-28 | 28 | 0 | 28 | 2018-05-08 | 2018-05-07 | 0 | 0 | 0 | [20 empty] | 2018-05-09 |  | 2019-04-02 |  | EXP | [8 empty] | 2018-12-19 | Connected |  | Yes
National Grid | EVERETT | 178283 | 2149 | 133.2 | Solar | 12_37W9 | 2018-03-12 01:00 | 2018-04-27 | 8 | 0 | 8 | 2018-05-09 | 2018-05-09 | 0 | 0 | 0 | [20 empty] | 2018-05-09 | 2018-03-12 01:00 | 2019-04-02 |  | EXP | [8 empty] | 2019-01-25 | Connected |  | No
National Grid | BELCHERTOWN | 178552 | 1007 | 2800 | Solar | 09_509L1 | 2018-03-12 01:00 | 2018-03-13 | 16 | 16 | 0 | [10 empty] | 2018-04-03 | 2018-05-30 | 41 | 26 | 15 | [10 empty] | 2022-08-04 |  | 2025-03-01 | Yes | STD | [9 empty] | Design |  | No
National Grid | MELROSE | 178553 | 2176 | 120 | Solar | 12_25W5 | 2018-03-12 01:00 | 2018-03-13 | 0 | 0 | 0 | 2018-03-16 | 2018-03-16 | 1 | 0 | 1 | [20 empty] | 2018-10-17 | 2018-03-12 01:00 | 2019-11-14 |  | EXP | [8 empty] | 2019-12-18 | Connected |  | No
National Grid | BROCKTON | 178556 | 2301 | 133.2 | Solar | 07_797W19 | 2018-03-12 01:00 | 2018-03-29 | 1 | 0 | 1 | 2018-03-30 | 2018-04-05 | 4 | 0 | 4 | 2018-04-06 | 2018-05-16 | 28 | 8 | 20 | [5 empty] | 2018-04-06 | 2018-05-16 | 28 | 8 | 20 | [5 empty] | 2018-05-30 |  | 2022-01-10 | Yes | EXP |  | 2021-02-12 | 2021-12-17 | 309 | 6 | 303 |  |  | 2021-12-30 | Connected |  | No
National Grid | FISKDALE | 178586 | 1518 | 1.84 | Solar | 01_408L2 | 2018-03-13 01:00 | 2018-03-14 | 24 | 24 | 0 | [25 empty] | 2018-05-01 |  | 2019-03-19 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BOXFORD | 178587 | 1921 | 20 | Solar | 14_56L3 | 2018-03-13 01:00 | 2018-03-14 | 13 | 0 | 13 | 2018-04-02 | 2018-04-30 | 20 | 0 | 20 | [20 empty] | 2018-05-11 |  | 2019-03-19 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LOWELL | 178588 | 1852 | 350 | Solar | 14_16L2 | 2018-03-13 01:00 | 2018-03-14 | 1 | 0 | 1 | 2018-05-16 | 2018-05-29 | 8 | 0 | 8 | [20 empty] | 2018-05-30 |  | 2019-12-02 |  | EXP | [8 empty] | 2019-12-16 | Connected |  | No
National Grid | BEVERLY | 178590 | 1915 | 3.2 | Solar | 12_72L1 | 2018-03-14 01:00 | 2018-04-23 | 0 | 0 | 0 | 2018-04-24 | 2018-05-10 | 12 | 0 | 12 | [20 empty] | 2018-05-11 |  | 2019-03-20 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 178591 | 1841 | 3.8 | Solar | 14_74L6 | 2018-03-14 01:00 | 2018-03-15 | 24 | 24 | 0 | 2018-05-18 | 2018-05-18 | 0 | 0 | 0 | [20 empty] | 2018-05-22 |  | 2019-03-20 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | AUBURN | 178592 | 1501 | 5000 | Solar | 01_2236W5 | 2018-03-14 01:00 | 2018-04-18 | 17 | 0 | 17 | [10 empty] | 2018-05-14 | 2018-06-06 | 17 | 0 | 17 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | MARLBOROUGH | 178593 | 1752 | 240 | Solar | 05_311W5 | 2018-03-14 01:00 | 2018-04-10 | 24 | 24 | 0 | [5 empty] | 2018-04-10 | 2018-04-24 | 8 | 8 | 0 | [5 empty] | 2018-04-10 | 2018-04-24 | 8 | 8 | 0 | [7 empty] | 2019-03-20 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MENDON | 178594 | 1756 | 19 | Solar | 05_335W1 | 2018-03-14 01:00 | 2018-03-15 | 9 | 9 | 0 | 2018-03-30 | 2018-03-29 | 1 | 0 | 1 | [20 empty] | 2018-03-30 | 2018-03-15 01:00 | 2019-03-20 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SPENCER | 178595 | 1562 | 3000 | Solar | 01_552L2 | 2018-03-15 01:00 | 2018-03-15 | 3 | 0 | 3 | [10 empty] | 2018-03-20 | 2018-04-12 | 17 | 0 | 17 | [10 empty] | 2018-09-20 |  | 2020-12-31 | Yes | STD |  | 2020-07-11 | 2020-11-25 | 138 | 5 | 133 | 2020-12-04 | 2020-12-04 | 2020-12-30 | Connected |  | No
National Grid | SOUTH GRAFTON | 178624 | 1560 | 5 | Solar | 05_320W3 | 2018-03-15 01:00 | 2018-03-15 | 41 | 24 | 17 | [25 empty] | 2018-05-01 |  | 2019-03-20 |  | EXP | [8 empty] | 2018-07-02 | Connected |  | No
National Grid | GLOUCESTER | 178625 | 1930 | 11.4 | Solar | 12_28L2 | 2018-03-15 01:00 | 2018-03-16 | 14 | 0 | 14 | 2018-04-05 | 2018-04-27 | 16 | 0 | 16 | [20 empty] | 2018-04-30 |  | 2019-03-21 |  | EXP | [8 empty] | 2019-09-06 | Connected |  | No
National Grid | LYNN | 178626 | 1902 | 3.8 | Solar | 12_29W5 | 2018-03-15 01:00 | 2018-03-16 | 2 | 2 | 0 | [27 empty] | 2019-03-21 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEOMINSTER | 178627 | 1453 | 7.6 | Solar | 01_219W2 | 2018-03-15 01:00 | 2018-03-16 | 13 | 13 | 0 | 2018-04-05 | 2018-04-24 | 21 | 0 | 21 | [20 empty] | 2018-05-01 |  | 2019-03-21 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | REVERE | 178628 | 2151 | 3.8 | Solar | 12_7J3 | 2018-03-15 01:00 | 2018-03-16 | 13 | 13 | 0 | 2018-04-05 | 2018-05-11 | 26 | 0 | 26 | [20 empty] | 2018-05-11 |  | 2019-03-21 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EAST LONGMEADOW | 178629 | 1028 | 350 | Solar | 09_508L4 | 2018-03-15 01:00 | 2018-03-16 | 1 | 1 | 0 | 2018-03-20 | 2018-05-19 | 42 | 0 | 42 | 2018-08-22 | 2018-10-11 | 35 | 12 | 23 | [5 empty] | 2018-08-22 | 2018-10-11 | 35 | 12 | 23 | [5 empty] | 2019-02-20 | 2018-03-15 01:00 | 2022-03-02 |  | EXP | [8 empty] | 2021-12-30 | Connected |  | No
National Grid | EAST LONGMEADOW | 178630 | 1028 | 233.1 | Solar | 09_508L4 | 2018-03-15 01:00 | 2018-03-16 | 2 | 2 | 0 | 2018-03-21 | 2018-05-19 | 41 | 0 | 41 | 2018-07-30 | 2019-01-18 | 118 | 6 | 112 | [5 empty] | 2018-07-30 | 2019-01-18 | 118 | 6 | 112 | [5 empty] | 2018-11-28 |  | 2020-12-21 | Yes | EXP |  | 2020-06-30 | 2020-11-04 | 128 | 5 | 123 |  |  | 2020-12-21 | Connected |  | No
National Grid | METHUEN | 178631 | 1844 | 7.6 | Solar | 14_75L3 | 2018-03-15 01:00 | 2018-03-16 | 13 | 13 | 0 | 2018-04-05 | 2018-04-30 | 17 | 0 | 17 | [20 empty] | 2018-05-14 |  | 2019-03-21 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | COHASSET | 178632 | 2025 | 10 | Solar | 07_96W41 | 2018-03-15 01:00 | 2018-03-16 | 4 | 4 | 0 | 2018-03-23 | 2019-10-28 | 402 | 0 | 402 | [20 empty] | 2018-03-23 |  | 2019-03-21 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | DRACUT | 178663 | 1826 | 42 | Solar | 14_78L1 | 2018-03-16 01:00 | 2018-03-16 | 5 | 0 | 5 | 2018-03-23 | 2018-04-27 | 25 | 0 | 25 | [20 empty] | 2018-05-09 | 2018-03-16 01:00 | 2019-03-21 |  | EXP |  | 2018-10-31 | 2019-02-07 | 99 | 0 | 99 |  |  | 2019-05-01 | Connected |  | No
National Grid | HAMPDEN | 178664 | 1036 | 7636 | Solar | 09_139L1 | 2018-03-16 01:00 | 2018-03-16 | 20 | 20 | 0 | [10 empty] | 2018-04-16 | 2018-06-11 | 40 | 20 | 20 | [10 empty] | 2018-12-27 | 2018-03-16 01:00 | 2024-09-23 | Yes | STD | [9 empty] | Construction |  | No
National Grid | BLACKSTONE | 178665 | 1504 | 4200 | Solar | 05_108W60 | 2018-03-16 01:00 | 2018-03-20 | 0 | 0 | 0 | [10 empty] | 2018-03-21 | 2018-04-17 | 19 | 0 | 19 | [10 empty] | 2018-08-29 |  | 2022-08-05 | Yes | STD |  | 2022-02-09 | 2022-07-06 | 146 | 0 | 146 |  |  | 2022-07-19 | Connected |  | No
National Grid | WORCESTER | 178666 | 1604 | 2112 | Solar | 01_8W1 | 2018-03-16 01:00 | 2018-03-19 | 2 | 2 | 0 | [10 empty] | 2018-03-21 | 2018-04-13 | 17 | 0 | 17 | [12 empty] | 2019-03-24 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ERVING | 178667 | 1344 | 4990 | Solar | 09_705W3 | 2018-03-16 01:00 | 2018-03-19 | 10 | 10 | 0 | [10 empty] | 2018-04-02 | 2018-05-30 | 42 | 27 | 15 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WINCHENDON | 178668 | 1475 | 4990 | Solar | 01_612T2 | 2018-03-16 01:00 | 2018-03-19 | 2 | 2 | 0 | [10 empty] | 2018-03-21 | 2018-05-31 | 84 | 33 | 51 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | ROYALSTON | 178669 | 1368 | 4990 | Solar | 09_701J1 | 2018-03-16 01:00 | 2018-03-19 | 10 | 9 | 1 | [10 empty] | 2018-05-24 | 2018-05-31 | 5 | 5 | 0 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BELCHERTOWN | 178670 | 1007 | 4875 | Solar | 09_509L1 | 2018-03-19 01:00 | 2018-03-19 | 2 | 1 | 1 | [10 empty] | 2018-03-21 | 2018-05-11 | 22 | 0 | 22 | [12 empty] | 2019-03-24 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ATHOL | 178671 | 1331 | 8300 | Solar | 09_702W2 | 2018-03-19 01:00 | 2018-03-20 | 26 | 26 | 0 | [27 empty] | 2019-03-25 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SWANSEA | 178672 | 2777 | 7.6 | Solar | 05_11W83 | 2018-03-20 01:00 | 2018-04-03 | 25 | 0 | 25 | 2018-05-08 | 2018-06-13 | 0 | 0 | 0 | [20 empty] | 2018-05-11 |  | 2019-03-26 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEOMINSTER | 178704 | 1453 | 10 | Solar | 01_207W2 | 2018-03-20 01:00 | 2018-03-21 | 22 | 20 | 2 | 2018-09-24 | 2018-09-24 | 0 | 0 | 0 | [20 empty] | 2018-09-25 |  | 2019-03-26 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LOWELL | 178705 | 1851 | 249.8 | Solar | 14_2L3 | 2018-03-21 01:00 | 2018-03-21 | 11 | 0 | 11 | 2018-04-05 | 2018-05-29 | 38 | 13 | 25 | [20 empty] | 2018-05-30 |  | 2021-03-31 |  | EXP | [8 empty] | 2020-12-16 | Connected |  | No
National Grid | FOXBOROUGH | 178804 | 2035 | 400 | Natural Gas | 05_3424W3 | 2018-03-21 01:00 | 2018-03-21 | 10 | 9 | 1 | [10 empty] | 2018-04-04 | 2018-05-22 | 23 | 11 | 12 | [10 empty] | 2019-02-04 |  | 2019-09-06 |  | STD |  | 2019-09-06 | 2019-09-05 | 0 | 0 | 0 | 2019-09-06 | 2019-09-06 | 2019-09-05 | Connected |  | No
National Grid | THORNDIKE | 178136 | 1079 | 15.2 | Solar | 09_523L4 | 2018-03-22 01:00 | 2018-03-23 | 4 | 4 | 0 | 2018-03-29 | 2018-03-29 | 1 | 0 | 1 | [20 empty] | 2018-03-29 |  | 2019-03-28 |  | EXP | [8 empty] | 2019-12-06 | Connected |  | No
National Grid | WORCESTER | 178137 | 1603 | 3.8 | Solar | 01_6W2 | 2018-03-22 01:00 | 2018-03-23 | 9 | 9 | 0 | 2018-04-05 | 2018-04-05 | 0 | 0 | 0 | [20 empty] | 2018-05-01 |  | 2019-03-28 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LOWELL | 178138 | 1854 | 3.8 | Solar | 14_77L2 | 2018-03-22 01:00 | 2018-03-23 | 4 | 4 | 0 | 2018-03-29 | 2018-04-29 | 16 | 0 | 16 | [20 empty] | 2018-03-29 |  | 2019-03-28 |  | EXP | [8 empty] | 2019-09-04 | Connected |  | No
National Grid | DRACUT | 178139 | 1826 | 7.6 | Solar | 14_75L1 | 2018-03-22 01:00 | 2018-03-23 | 9 | 9 | 0 | 2018-04-05 | 2018-04-29 | 11 | 0 | 11 | [20 empty] | 2018-04-06 |  | 2019-03-28 |  | EXP | [8 empty] | 2019-08-05 | Connected |  | No
National Grid | WILLIAMSTOWN | 178140 | 1267 | 17.6 | Solar | 09_1003W2 | 2018-03-22 01:00 | 2018-03-23 | 15 | 0 | 15 | 2018-04-13 | 2018-04-30 | 11 | 0 | 11 | [20 empty] | 2018-05-03 |  | 2020-04-15 |  | EXP | [8 empty] | 2020-05-06 | Connected |  | No
National Grid | MARLBOROUGH | 178141 | 1752 | 7.6 | Solar | 05_311W5 | 2018-03-22 01:00 | 2018-03-23 | 18 | 9 | 9 | 2018-04-05 | 2018-04-30 | 17 | 0 | 17 | [20 empty] | 2019-03-13 | 2018-03-23 01:00 | 2019-03-28 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | PEMBROKE | 178143 | 2359 | 4998 | Solar | 07_910W25 | 2018-03-23 01:00 | 2018-03-23 | 5 | 0 | 5 | [10 empty] | 2018-04-02 | 2018-04-25 | 17 | 0 | 17 | [10 empty] | 2018-09-06 |  | 2020-06-02 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | WARE | 178170 | 1082 | 2200 | Solar | 09_501L2 | 2018-03-23 01:00 | 2018-03-26 | 16 | 16 | 0 | [10 empty] | 2018-04-18 | 2018-05-09 | 3 | 0 | 3 | [5 empty] | 2020-07-10 | 2020-10-07 | 63 | 3 | 60 |  |  |  |  | STD | [9 empty] | Group Study |  | No
National Grid | SPENCER | 178171 | 1562 | 4400 | Solar | 01_552L4 | 2018-03-23 01:00 | 2018-03-26 | 16 | 16 | 0 | [10 empty] | 2018-04-18 | 2018-05-09 | 3 | 0 | 3 | [5 empty] | 2020-07-10 | 2020-10-02 | 59 | 3 | 56 |  |  |  |  | STD | [9 empty] | Group Study |  | No
National Grid | AUBURN | 178172 | 1501 | 7800 | Solar | 01_406L1 | 2018-03-23 01:00 | 2018-03-26 | 7 | 7 | 0 | [10 empty] | 2018-04-04 | 2018-06-26 | 59 | 43 | 16 | [12 empty] | 2019-03-31 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BELCHERTOWN | 178173 | 1007 | 3190 | Solar | 09_523L2 | 2018-03-23 01:00 | 2018-03-26 | 9 | 9 | 0 | [10 empty] | 2018-04-06 | 2018-04-28 | 10 | 0 | 10 | [5 empty] | 2020-07-10 | 2020-10-02 | 60 | 3 | 57 |  |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | FLORENCE | 178174 | 1062 | 7.6 | Solar | 09_909W4 | 2018-03-23 01:00 | 2018-03-26 | 5 | 0 | 5 | 2018-04-02 | 2018-05-08 | 26 | 0 | 26 | [20 empty] | 2018-05-08 |  | 2019-03-31 |  | EXP | [8 empty] | 2019-10-30 | Connected |  | No
National Grid | WESTPORT | 178175 | 2790 | 15.2 | Solar | 05_115W45 | 2018-03-23 01:00 | 2018-03-26 | 2 | 1 | 1 | 2018-03-28 | 2018-03-28 | 1 | 0 | 1 | [20 empty] | 2018-06-13 | 2018-03-23 01:00 | 2019-03-31 |  | EXP | [8 empty] | 2018-10-02 | Connected |  | Yes
National Grid | REVERE | 178212 | 2151 | 3.8 | Solar | 12_7W2 | 2018-03-23 01:00 | 2018-05-01 | 9 | 0 | 9 | 2018-05-14 | 2018-06-18 | 24 | 0 | 24 | [20 empty] | 2018-06-18 |  | 2019-07-31 | Yes | EXP | [9 empty] | Withdrawn |  | No
National Grid | MONSON | 178214 | 1057 | 4980 | Solar | 09_503L2 | 2018-03-23 01:00 | 2018-03-27 | 12 | 12 | 0 | [10 empty] | 2018-04-12 | 2018-05-04 | 6 | 0 | 6 | [11 empty] | 2018-03-26 01:00 | 2019-04-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH DIGHTON | 178213 | 2764 | 2000 | Solar | 05_19W74 | 2018-03-26 01:00 | 2018-03-27 | 5 | 5 | 0 | [10 empty] | 2018-04-03 | 2018-04-30 | 13 | 0 | 13 | [10 empty] | 2019-04-18 |  | 2024-05-05 | Yes | STD |  | 2022-01-14 | 2024-02-01 | 748 | 680 | 68 |  |  | 2024-04-15 | Connected |  | No
National Grid | HUBBARDSTON | 178326 | 1452 | 5000 | Solar | 01_602W2 | 2018-03-26 01:00 | 2018-03-30 | 2 | 0 | 2 | [10 empty] | 2018-04-03 | 2018-05-04 | 32 | 10 | 22 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BLACKSTONE | 178247 | 1504 | 4990 | Solar | 05_108W60 | 2018-03-27 01:00 | 2018-03-28 | 4 | 4 | 0 | [10 empty] | 2018-04-03 | 2018-04-29 | 13 | 0 | 13 | [12 empty] | 2019-04-02 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WILLIAMSTOWN | 178248 | 1267 | 21.44 | Solar | 09_1003W2 | 2018-03-27 01:00 | 2018-03-28 | 17 | 17 | 0 | [26 empty] | 2018-03-27 01:00 | 2019-04-02 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WILBRAHAM | 178249 | 1095 | 4000 | Solar | 09_523L1 | 2018-03-27 01:00 | 2018-03-28 | 11 | 11 | 0 | [10 empty] | 2018-04-12 | 2018-06-13 | 44 | 31 | 13 | [10 empty] | 2018-11-20 |  | 2025-04-07 | Yes | STD | [9 empty] | Construction |  | No
National Grid | ROYALSTON | 178250 | 1368 | 2000 | Solar | 09_702W2 | 2018-03-27 01:00 | 2018-03-28 | 11 | 11 | 0 | [10 empty] | 2018-04-12 | 2018-06-13 | 44 | 31 | 13 | [11 empty] | 2018-03-27 01:00 | 2019-04-02 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 178252 | 1602 | 11.4 | Solar | 01_6W2 | 2018-03-27 01:00 | 2018-03-28 | 4 | 0 | 4 | 2018-04-03 | 2018-04-30 | 19 | 0 | 19 | [20 empty] | 2018-05-02 |  | 2020-04-10 | Yes | EXP | [8 empty] | 2020-03-20 | Connected |  | No
National Grid | WORCESTER | 178253 | 1602 | 7.6 | Solar | 01_23W3 | 2018-03-27 01:00 | 2018-03-28 | 4 | 0 | 4 | 2018-04-03 | 2018-04-30 | 19 | 0 | 19 | [20 empty] | 2018-05-02 |  | 2019-04-02 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 178284 | 1605 | 684 | Solar | 01_27W4 | 2018-03-28 01:00 | 2018-03-28 | 17 | 11 | 6 | [10 empty] | 2018-05-30 | 2018-05-29 | 0 | 0 | 0 | [11 empty] | 2018-03-28 01:00 | 2019-04-02 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SOUTHBRIDGE | 178286 | 1550 | 5 | Solar | 01_413L2 | 2018-03-28 01:00 | 2018-03-29 | 6 | 0 | 6 | 2018-04-06 | 2018-04-30 | 16 | 0 | 16 | [20 empty] | 2018-05-02 |  | 2019-04-03 | Yes | EXP | [8 empty] | 2019-03-26 | Connected |  | No
National Grid | EAST LONGMEADOW | 178287 | 1028 | 376.6 | Solar | 09_508L4 | 2018-03-28 01:00 | 2018-03-29 | 16 | 15 | 1 | [26 empty] | 2018-03-28 01:00 | 2019-04-03 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | HAMILTON | 178288 | 1982 | 7.6 | Solar | 12_51L3 | 2018-03-28 01:00 | 2018-03-29 | 7 | 0 | 7 | 2018-04-09 | 2018-05-09 | 22 | 0 | 22 | [20 empty] | 2018-05-21 |  | 2021-07-15 | Yes | EXP | [8 empty] | 2021-06-22 | Connected |  | No
National Grid | CLINTON | 178289 | 1510 | 11.4 | Solar | 01_216W5 | 2018-03-28 01:00 | 2018-03-29 | 7 | 7 | 0 | 2018-04-09 | 2018-04-30 | 15 | 0 | 15 | [20 empty] | 2018-05-02 |  | 2019-04-03 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 178290 | 1507 | 1000 | Solar | 01_415L2 | 2018-03-28 01:00 | 2018-03-29 | 3 | 3 | 0 | [10 empty] | 2018-04-03 | 2018-05-10 | 28 | 6 | 22 | [12 empty] | 2019-04-03 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 178291 | 1608 | 200 | Solar | 01_4J324 | 2018-03-28 01:00 | 2018-03-29 | 15 | 15 | 0 | 2018-04-20 | 2018-05-22 | 22 | 0 | 22 | [20 empty] | 2018-11-15 | 2018-03-29 01:00 | 2019-12-02 |  | EXP | [8 empty] | 2019-11-07 | Connected |  | No
National Grid | PEMBROKE | 178285 | 2359 | 3200 | Solar | 07_910W25 | 2018-03-29 01:00 | 2018-04-10 | 1 | 1 | 0 | [10 empty] | 2018-04-02 | 2018-04-27 | 19 | 0 | 19 | [10 empty] | 2018-12-11 |  | 2022-12-30 | Yes | STD |  | 2021-12-15 | 2022-07-25 | 223 | 141 | 82 |  |  | 2022-12-28 | Connected |  | No
National Grid | HUBBARDSTON | 178322 | 1452 | 2510 | Solar | 01_607W2 | 2018-03-29 01:00 | 2018-03-30 | 2 | 2 | 0 | [10 empty] | 2018-04-03 | 2018-04-25 | 13 | 0 | 13 | [5 empty] | 2020-07-10 | 2020-10-02 | 60 | 3 | 57 |  |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | CLINTON | 178323 | 1510 | 249.8 | Solar | 01_216W5 | 2018-03-29 01:00 | 2018-05-17 | 9 | 0 | 9 | 2018-05-30 | 2018-05-30 | 0 | 0 | 0 | [20 empty] | 2018-07-27 |  | 2020-12-31 |  | EXP | [8 empty] | 2021-02-19 | Connected |  | No
National Grid | WEBSTER | 178324 | 1570 | 2000 | Solar | 01_412L2 | 2018-03-29 01:00 | 2018-03-30 | 6 | 5 | 1 | [10 empty] | 2018-04-09 | 2018-05-12 | 25 | 10 | 15 | [11 empty] | 2018-03-30 01:00 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | QUINCY | 178325 | 2169 | 6 | Solar | 07_1W2 | 2018-03-30 01:00 | 2018-03-30 | 7 | 0 | 7 | 2018-04-10 | 2018-04-30 | 14 | 0 | 14 | [20 empty] | 2018-05-16 |  | 2019-04-04 | Yes | EXP | [8 empty] | 2018-10-29 | Connected |  | Yes
National Grid | MARLBOROUGH | 178327 | 1752 | 1300 | Solar | 05_318W1 | 2018-03-30 01:00 | 2018-03-30 | 2 | 2 | 0 | [10 empty] | 2018-04-03 | 2018-06-18 | 54 | 32 | 22 | [12 empty] | 2019-04-04 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HAMPDEN | 178328 | 1036 | 8980 | Solar | 09_139L1 | 2018-03-30 01:00 | 2018-03-30 | 11 | 11 | 0 | [10 empty] | 2018-04-16 | 2018-06-19 | 20 | 0 | 20 | [12 empty] | 2019-04-04 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | STOUGHTON | 178329 | 2072 | 249 | Solar | 07_913W69 | 2018-03-30 01:00 | 2018-03-30 | 19 | 0 | 19 | 2018-04-27 | 2018-04-26 | 0 | 0 | 0 | [22 empty] | 2019-04-04 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | TYNGSBORO | 178330 | 1879 | 7.6 | Solar | 14_2L1 | 2018-03-30 01:00 | 2018-04-02 | 5 | 0 | 5 | 2018-04-09 | 2018-04-30 | 15 | 0 | 15 | [20 empty] | 2018-05-02 |  | 2020-09-23 |  | EXP | [8 empty] | 2020-08-20 | Connected |  | No
National Grid | RUTLAND | 178360 | 1543 | 4300 | Solar | 01_55W3 | 2018-03-30 01:00 | 2018-04-02 | 3 | 3 | 0 | [10 empty] | 2018-04-05 | 2018-05-21 | 33 | 18 | 15 | [10 empty] | 2020-10-14 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | RUTLAND | 178361 | 1543 | 3000 | Solar | 01_55W1 | 2018-03-30 01:00 | 2018-04-02 | 3 | 3 | 0 | [10 empty] | 2018-04-05 | 2018-05-21 | 33 | 18 | 15 | [12 empty] | 2019-04-07 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 178362 | 1844 | 3.8 | Solar | 14_43L2 | 2018-03-30 01:00 | 2018-04-02 | 5 | 5 | 0 | 2018-04-09 | 2018-04-30 | 15 | 0 | 15 | [20 empty] | 2018-05-14 |  | 2019-04-07 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | ANDOVER | 178363 | 1810 | 4920 | Solar | 14_59L4 | 2018-03-30 01:00 | 2018-04-02 | 4 | 4 | 0 | [10 empty] | 2018-04-06 | 2019-04-18 | 260 | 9 | 251 | [12 empty] | 2019-04-07 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | HAYDENVILLE | 178364 | 1039 | 7.6 | Solar | 09_909W3 | 2018-03-30 01:00 | 2018-04-02 | 5 | 0 | 5 | 2018-04-09 | 2018-04-23 | 10 | 0 | 10 | [20 empty] | 2018-04-26 |  | 2019-11-15 |  | EXP | [8 empty] | 2019-10-08 | Connected |  | No
National Grid | QUINCY | 178365 | 2169 | 7.6 | Solar | 07_1W2 | 2018-03-30 01:00 | 2018-04-02 | 4 | 0 | 4 | 2018-04-06 | 2018-04-30 | 16 | 0 | 16 | [20 empty] | 2018-05-14 |  | 2019-04-07 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RUTLAND | 178367 | 1543 | 1500 | Solar | 09_1194T3 | 2018-04-02 01:00 | 2018-04-02 | 3 | 3 | 0 | [10 empty] | 2018-04-05 | 2018-05-24 | 36 | 20 | 16 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | RUTLAND | 178368 | 1543 | 4950 | Solar | 09_1194T3 | 2018-04-02 01:00 | 2018-04-02 | 3 | 3 | 0 | [10 empty] | 2018-04-05 | 2018-05-24 | 36 | 19 | 17 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | RUTLAND | 178398 | 1543 | 5300 | Solar | 09_1194T3 | 2018-04-02 01:00 | 2018-04-02 | 3 | 3 | 0 | [10 empty] | 2018-04-05 | 2018-05-24 | 36 | 19 | 17 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | RUTLAND | 178399 | 1543 | 4900 | Solar | 09_1194T3 | 2018-04-02 01:00 | 2018-04-02 | 3 | 3 | 0 | [10 empty] | 2018-04-05 | 2018-05-24 | 36 | 19 | 17 | [11 empty] | 2018-04-02 01:00 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | CLARKSBURG | 178400 | 1247 | 248 | Solar | 09_1015W2 | 2018-04-02 01:00 | 2018-04-02 | 4 | 3 | 1 | 2018-04-06 | 2018-05-26 | 25 | 15 | 10 | [20 empty] | 2018-11-20 | 2018-04-02 01:00 | 2021-04-28 | Yes | EXP |  | 2021-02-18 | 2021-03-19 | 0 | 0 | 0 |  |  | 2021-04-26 | Connected |  | No
National Grid | SHEFFIELD | 178401 | 1257 | 244 | Solar | 09_1108W2 | 2018-04-02 01:00 | 2018-04-02 | 4 | 0 | 4 | 2018-04-06 | 2018-05-26 | 25 | 15 | 10 | [20 empty] | 2018-11-20 |  | 2021-04-20 | Yes | EXP |  | 2020-05-29 | 2020-10-16 | 141 | 5 | 136 |  |  | 2021-04-12 | Connected |  | No
National Grid | RUTLAND | 178402 | 1543 | 2900 | Solar | 09_1194T3 | 2018-04-02 01:00 | 2018-04-02 | 4 | 3 | 1 | [10 empty] | 2018-04-06 | 2018-05-24 | 35 | 19 | 16 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | RUTLAND | 178403 | 1543 | 3900 | Solar | 09_1194T3 | 2018-04-02 01:00 | 2018-04-02 | 4 | 3 | 1 | [10 empty] | 2018-04-06 | 2018-05-24 | 35 | 19 | 16 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | RUTLAND | 178404 | 1543 | 3400 | Solar | 09_1194T3 | 2018-04-02 01:00 | 2018-04-02 | 4 | 3 | 1 | [10 empty] | 2018-04-06 | 2018-05-24 | 35 | 19 | 16 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | RUTLAND | 178405 | 1543 | 4900 | Solar | 09_1194T3 | 2018-04-02 01:00 | 2018-04-02 | 4 | 3 | 1 | [10 empty] | 2018-04-06 | 2018-05-24 | 35 | 19 | 16 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | ERVING | 178406 | 1344 | 4990 | Solar | 09_705W3 | 2018-04-02 01:00 | 2018-04-02 | 3 | 2 | 1 | [10 empty] | 2018-04-05 | 2018-05-30 | 39 | 23 | 16 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | AVON | 178407 | 2322 | 498 | Solar | 07_75W3 | 2018-04-02 01:00 | 2018-04-03 | 12 | 3 | 9 | [5 empty] | 2018-08-20 | 2018-10-16 | 41 | 14 | 27 | 2018-04-20 | 2018-07-25 | 67 | 42 | 25 | 2018-08-20 | 2018-10-16 | 41 | 14 | 27 | [5 empty] | 2018-11-28 |  | 2019-10-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | AVON | 178439 | 2322 | 132 | Solar | 07_68J1 | 2018-04-02 01:00 | 2018-04-03 | 12 | 3 | 9 | 2018-04-20 | 2018-07-25 | 60 | 36 | 24 | 2018-09-05 | 2018-10-17 | 30 | 11 | 19 | [5 empty] | 2018-09-05 | 2018-10-17 | 30 | 11 | 19 | [7 empty] | 2019-04-08 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | EAST LONGMEADOW | 178440 | 1028 | 7.6 | Solar | 09_508L4 | 2018-04-02 01:00 | 2018-04-03 | 4 | 0 | 4 | 2018-04-09 | 2018-04-30 | 15 | 0 | 15 | [20 empty] | 2018-05-17 |  | 2019-04-15 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MARLBOROUGH | 178441 | 1752 | 5 | Solar | 05_311W2 | 2018-04-02 01:00 | 2018-04-03 | 5 | 0 | 5 | 2018-04-10 | 2018-04-30 | 14 | 0 | 14 | [20 empty] | 2018-05-11 | 2018-04-02 01:00 | 2019-04-08 |  | EXP | [8 empty] | 2019-05-29 | Connected |  | No
National Grid | DUDLEY | 178442 | 1571 | 9 | Solar | 01_412L4 | 2018-04-02 01:00 | 2018-04-03 | 5 | 0 | 5 | 2018-04-10 | 2018-04-30 | 14 | 0 | 14 | [20 empty] | 2018-06-07 |  | 2019-05-06 | Yes | EXP |  | 2019-03-30 | 2019-03-29 | 0 | 0 | 0 |  |  | 2019-05-02 | Connected |  | No
National Grid | FALL RIVER | 178444 | 2724 | 7.6 | Solar | 05_115W42 | 2018-04-03 01:00 | 2018-04-17 | 8 | 0 | 8 | 2018-04-27 | 2018-05-09 | 8 | 0 | 8 | [20 empty] | 2018-05-10 |  | 2019-04-09 |  | EXP | [8 empty] | 2018-11-20 | Connected |  | Yes
National Grid | MILFORD | 178445 | 1757 | 7.6 | Solar | 05_336W3 | 2018-04-03 01:00 | 2018-04-04 | 4 | 4 | 0 | 2018-04-10 | 2018-05-09 | 81 | 0 | 81 | [20 empty] | 2018-05-09 |  | 2019-04-09 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LEOMINSTER | 178446 | 1453 | 7.6 | Solar | 01_207W6 | 2018-04-03 01:00 | 2018-04-04 | 3 | 3 | 0 | [25 empty] | 2018-04-09 |  | 2019-04-09 |  | EXP | [8 empty] | 2018-11-29 | Connected |  | No
National Grid | BELLINGHAM | 178447 | 2019 | 1382 | Solar | 05_335W1 | 2018-04-03 01:00 | 2018-04-11 | 9 | 0 | 9 | [10 empty] | 2018-04-24 | 2018-06-05 | 30 | 11 | 19 | [10 empty] | 2018-10-23 |  | 2021-11-19 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BELLINGHAM | 178478 | 2019 | 270 | Solar | 05_335W1 | 2018-04-03 01:00 | 2018-04-11 | 1 | 0 | 1 | [10 empty] | 2018-04-12 | 2018-06-05 | 38 | 11 | 27 | [10 empty] | 2018-10-23 |  | 2021-11-19 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | OXFORD | 178479 | 1540 | 5000 | Solar | 01_406L1 | 2018-04-03 01:00 | 2018-04-04 | 4 | 4 | 0 | [27 empty] | 2019-04-09 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SPENCER | 178480 | 1562 | 4999 | Solar | 01_525L1 | 2018-04-03 01:00 | 2018-04-04 | 12 | 12 | 0 | [10 empty] | 2018-05-01 | 2018-06-04 | 23 | 0 | 23 | [5 empty] | 2020-07-10 | 2020-10-02 | 60 | 3 | 57 |  |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SPENCER | 178481 | 1562 | 5000 | Solar | 01_552L1 | 2018-04-03 01:00 | 2018-04-05 | 11 | 11 | 0 | [10 empty] | 2018-05-01 | 2018-04-30 | 0 | 0 | 0 | [12 empty] | 2019-04-10 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ORANGE | 178482 | 1364 | 1350 | Solar | 09_702W2 | 2018-04-03 01:00 | 2018-04-05 | 11 | 11 | 0 | [10 empty] | 2018-04-27 | 2018-06-01 | 24 | 0 | 24 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | EAST BROOKFIELD | 178483 | 1515 | 4999 | Solar | 01_552L3 | 2018-04-03 01:00 | 2018-04-05 | 18 | 18 | 0 | [10 empty] | 2018-05-01 | 2018-06-05 | 24 | 0 | 24 | [5 empty] | 2020-07-10 | 2020-10-02 | 60 | 3 | 57 |  |  |  |  | STD | [9 empty] | Group Study |  | No
National Grid | WARREN | 178484 | 1083 | 3000 | Solar | 01_408L2 | 2018-04-03 01:00 | 2018-04-05 | 8 | 8 | 0 | [10 empty] | 2018-04-18 | 2018-05-10 | 3 | 0 | 3 | [10 empty] | 2019-01-18 |  | 2023-06-27 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | REHOBOTH | 178485 | 2769 | 1000 | Solar | 05_7L5 | 2018-04-03 01:00 | 2018-04-05 | 11 | 9 | 2 | [10 empty] | 2018-06-25 | 2018-08-24 | 44 | 26 | 18 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH ADAMS | 178596 | 1247 | 4999 | Solar | 09_1001W1 | 2018-04-03 01:00 | 2018-04-06 | 10 | 10 | 0 | [10 empty] | 2018-04-27 | 2018-08-18 | 79 | 65 | 14 | [12 empty] | 2019-04-11 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ANDOVER | 178518 | 1810 | 10 | Solar | 14_71L1 | 2018-04-04 01:00 | 2018-04-05 | 6 | 0 | 6 | 2018-04-13 | 2018-05-21 | 26 | 0 | 26 | [20 empty] | 2018-05-22 | 2018-04-04 01:00 | 2019-04-10 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BELLINGHAM | 178519 | 2019 | 7.6 | Solar | 05_108W60 | 2018-04-04 01:00 | 2018-04-27 | 14 | 0 | 14 | 2018-05-17 | 2018-05-21 | 2 | 0 | 2 | [20 empty] | 2018-06-07 |  | 2019-11-30 | Yes | EXP | [8 empty] | 2019-10-23 | Connected |  | No
National Grid | AUBURN | 178522 | 1501 | 2297.7 | Solar | 01_26W2 | 2018-04-04 01:00 | 2018-04-05 | 11 | 11 | 0 | [10 empty] | 2018-05-11 | 2018-05-10 | 0 | 0 | 0 | [12 empty] | 2019-04-10 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTHAMPTON | 178523 | 1060 | 66.6 | Solar | 09_909W1 | 2018-04-04 01:00 | 2018-04-05 | 11 | 11 | 0 | [27 empty] | 2019-04-10 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LAWRENCE | 178524 | 1841 | 10 | Solar | 14_74L6 | 2018-04-04 01:00 | 2018-05-15 | 11 | 10 | 1 | 2018-05-18 | 2018-05-29 | 10 | 0 | 10 | [20 empty] | 2018-05-29 |  | 2019-04-10 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GLOUCESTER | 178526 | 1930 | 3.8 | Solar | 12_51T1 | 2018-04-04 01:00 | 2018-05-15 | 11 | 10 | 1 | 2018-05-16 | 2018-05-22 | 19 | 0 | 19 | [20 empty] | 2018-05-22 |  | 2019-04-10 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | GLOUCESTER | 178557 | 1930 | 11.4 | Solar | 12_51T1 | 2018-04-04 01:00 | 2018-05-15 | 11 | 10 | 1 | 2018-05-15 | 2018-05-22 | 0 | 0 | 0 | [20 empty] | 2018-05-22 |  | 2019-04-10 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH GRAFTON | 178558 | 1536 | 9.92 | Solar | 01_328W3 | 2018-04-05 01:00 | 2018-04-06 | 4 | 4 | 0 | 2018-04-12 | 2018-04-30 | 12 | 0 | 12 | [20 empty] | 2018-05-02 | 2018-04-05 01:00 | 2019-04-11 |  | EXP | [8 empty] | 2018-08-02 | Connected |  | Yes
National Grid | NEWBURY | 178560 | 1951 | 432.9 | Solar | 14_60L1 | 2018-04-05 01:00 | 2018-04-06 | 6 | 6 | 0 | [5 empty] | 2018-07-02 | 2018-10-09 | 69 | 0 | 69 | 2018-04-16 | 2018-06-15 | 44 | 19 | 25 | 2018-07-02 | 2018-10-09 | 69 | 0 | 69 | [5 empty] | 2019-04-12 |  | 2024-09-16 | Yes | STD | [9 empty] | Construction |  | No
National Grid | WINCHENDON | 178561 | 1475 | 1666 | Solar | 01_607W3 | 2018-04-05 01:00 | 2018-04-06 | 6 | 6 | 0 | [10 empty] | 2018-04-16 | 2018-10-26 | 137 | 70 | 67 | [12 empty] | 2019-04-11 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | GREAT BARRINGTON | 178562 | 1230 | 2500 | Solar | 09_1109W3 | 2018-04-05 01:00 | 2018-04-06 | 9 | 9 | 0 | [10 empty] | 2018-04-20 | 2018-07-21 | 64 | 48 | 16 | [12 empty] | 2019-04-11 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | RUTLAND | 178563 | 1543 | 2500 | Solar | 01_55W1 | 2018-04-05 01:00 | 2018-04-06 | 6 | 6 | 0 | [10 empty] | 2018-04-16 | 2018-07-20 | 68 | 52 | 16 | [12 empty] | 2019-04-11 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | DOUGLAS | 178564 | 1516 | 4998 | Solar | 05_320W2 | 2018-04-05 01:00 | 2018-04-06 | 10 | 9 | 1 | [10 empty] | 2018-05-23 | 2018-09-06 | 74 | 66 | 8 | [10 empty] | 2019-03-08 |  | 2020-04-11 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | OXFORD | 178565 | 1537 | 4998 | Solar | 01_406L1 | 2018-04-05 01:00 | 2018-04-06 | 6 | 6 | 0 | [10 empty] | 2018-04-16 | 2018-07-09 | 59 | 35 | 24 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | HAMPDEN | 178597 | 1036 | 2500 | Solar | 09_139L1 | 2018-04-06 01:00 | 2018-04-09 | 9 | 8 | 1 | [10 empty] | 2018-05-24 | 2018-06-11 | 11 | 0 | 11 | [10 empty] | 2019-02-13 |  | 2020-09-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MILLBURY | 178598 | 1527 | 2500 | Solar | 01_304W6 | 2018-04-06 01:00 | 2018-04-09 | 5 | 5 | 0 | [10 empty] | 2018-04-16 | 2018-07-21 | 68 | 53 | 15 | [12 empty] | 2019-04-14 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | EAST BRIDGEWATER | 178599 | 2333 | 72 | Solar | 07_797W23 | 2018-04-06 01:00 | 2018-04-09 | 1 | 0 | 1 | 2018-04-10 | 2018-04-18 | 30 | 0 | 30 | [20 empty] | 2018-04-18 |  | 2019-04-14 |  | EXP | [8 empty] | 2018-12-18 | Connected |  | No
National Grid | WINCHENDON | 178600 | 1475 | 2500 | Solar | 01_612W4 | 2018-04-06 01:00 | 2018-04-09 | 9 | 9 | 0 | [10 empty] | 2018-05-08 | 2018-08-17 | 55 | 55 | 0 | [5 empty] | 2020-07-10 | 2020-10-02 | 59 | 3 | 56 |  |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WINCHENDON | 178601 | 1475 | 4998 | Solar | 01_612W3 | 2018-04-06 01:00 | 2018-04-09 | 22 | 9 | 13 | [10 empty] | 2018-05-14 | 0 | 1479 | 0 | 1479 | [12 empty] | 2019-04-14 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | EAST BRIDGEWATER | 178602 | 2333 | 500 | Solar | 07_797W23 | 2018-04-06 01:00 | 2018-04-09 | 12 | 4 | 8 | [10 empty] | 2018-05-07 | 2018-07-11 | 50 | 11 | 39 | [11 empty] | 2018-04-09 01:00 | 2019-04-14 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 178603 | 1844 | 3.8 | Solar | 14_43L2 | 2018-04-09 01:00 | 2018-04-10 | 13 | 0 | 13 | 2018-04-27 | 2018-05-10 | 9 | 0 | 9 | [20 empty] | 2018-05-10 |  | 2019-11-29 | Yes | EXP |  | 2019-09-12 | 2019-10-15 | 33 | 0 | 33 |  |  | 2019-10-23 | Connected |  | No
National Grid | ORANGE | 178604 | 1364 | 3000 | Solar | 09_705W3 | 2018-04-09 01:00 | 2018-04-10 | 20 | 20 | 0 | [10 empty] | 2018-06-12 | 2018-06-21 | 31 | 0 | 31 | [5 empty] | 2020-07-10 | 2020-10-02 | 60 | 3 | 57 |  |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | CHELMSFORD | 178633 | 1824 | 9 | Solar | 14_16L4 | 2018-04-09 01:00 | 2018-04-10 | 7 | 7 | 0 | 2018-04-25 | 2018-05-21 | 0 | 0 | 0 | [20 empty] | 2018-05-21 |  | 2019-04-15 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MONSON | 178634 | 1057 | 2000 | Solar | 09_514L1 | 2018-04-09 01:00 | 2018-04-10 | 7 | 6 | 1 | [10 empty] | 2018-04-20 | 2018-07-02 | 51 | 32 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | DRACUT | 178635 | 1826 | 5 | Solar | 14_21L1 | 2018-04-09 01:00 | 2018-04-10 | 6 | 0 | 6 | 2018-04-18 | 2018-05-21 | 23 | 0 | 23 | [20 empty] | 2018-05-21 |  | 2019-04-15 |  | EXP | [8 empty] | 2019-03-20 | Connected |  | No
National Grid | NORTHBOROUGH | 178636 | 1532 | 10 | Solar | 05_313W2 | 2018-04-09 01:00 | 2018-04-10 | 8 | 0 | 8 | 2018-04-20 | 2018-04-30 | 6 | 0 | 6 | [20 empty] | 2018-09-12 |  | 2019-04-15 |  | EXP | [8 empty] | 2019-06-12 | Connected |  | No
National Grid | TEWKSBURY | 178637 | 1876 | 7.6 | Solar | 14_59L3 | 2018-04-09 01:00 | 2018-04-10 | 1 | 0 | 1 | 2018-05-18 | 2018-05-21 | 2 | 0 | 2 | [20 empty] | 2018-05-21 |  | 2019-04-15 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BELCHERTOWN | 178640 | 1007 | 1000 | Solar | 09_523L2 | 2018-04-09 01:00 | 2018-04-10 | 4 | 3 | 1 | [10 empty] | 2018-04-16 | 2018-06-14 | 43 | 27 | 16 | [5 empty] | 2020-07-10 | 2020-10-02 | 60 | 3 | 57 |  |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BEVERLY | 178641 | 1915 | 15.2 | Solar | 12_18L1 | 2018-04-10 01:00 | 2018-05-21 | 27 | 7 | 20 | 2018-05-21 | 2018-05-21 | 0 | 0 | 0 | [20 empty] | 2018-05-21 |  | 2019-04-15 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTHAMPTON | 178642 | 1060 | 57.6 | Solar | 09_901W1 | 2018-04-10 01:00 | 2018-04-11 | 7 | 0 | 7 | 2018-04-20 | 2018-05-21 | 21 | 0 | 21 | [20 empty] | 2018-06-27 |  | 2019-04-16 |  | EXP | [8 empty] | 2019-11-26 | Connected |  | No
National Grid | OAKHAM | 178673 | 1068 | 4990 | Solar | 09_1194T1 | 2018-04-10 01:00 | 2018-04-11 | 3 | 3 | 0 | [10 empty] | 2018-04-16 | 2018-07-05 | 57 | 42 | 15 | [11 empty] | 2018-04-10 01:00 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SUTTON | 178674 | 1590 | 1000 | Solar | 05_320W5 | 2018-04-10 01:00 | 2018-04-11 | 3 | 3 | 0 | [10 empty] | 2018-05-18 | 2018-08-14 | 61 | 43 | 18 | [10 empty] | 2019-04-10 |  | 2020-12-16 | Yes | STD |  | 2020-01-29 | 2020-10-26 | 272 | 5 | 267 | 2020-11-10 | 2020-11-10 | 2020-12-04 | Connected |  | No
National Grid | PALMER | 178675 | 1069 | 2500 | Solar | 09_523L2 | 2018-04-10 01:00 | 2018-04-11 | 6 | 6 | 0 | [10 empty] | 2018-04-20 | 2018-09-06 | 97 | 54 | 43 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SAUGUS | 178676 | 1906 | 7.6 | Solar | 12_7J903 | 2018-04-10 01:00 | 2018-04-11 | 0 | 0 | 0 | 2018-04-30 | 2018-05-04 | 4 | 0 | 4 | [20 empty] | 2018-05-04 |  | 2020-01-08 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GRANBY | 178677 | 1033 | 7.6 | Solar | 09_527L1 | 2018-04-11 01:00 | 2018-04-12 | 53 | 29 | 24 | 2018-05-22 | 2018-06-19 | 0 | 0 | 0 | [20 empty] | 2018-07-21 |  | 2019-04-17 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | OXFORD | 178678 | 1540 | 7.6 | Solar | 01_26W3 | 2018-04-11 01:00 | 2018-04-12 | 29 | 28 | 1 | 2018-05-21 | 2018-05-21 | 0 | 0 | 0 | [20 empty] | 2018-05-23 |  | 2019-04-17 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTBOROUGH | 178679 | 1581 | 15.2 | Solar | 05_312W4 | 2018-04-11 01:00 | 2018-04-27 | 16 | 0 | 16 | 2018-05-21 | 2018-05-21 | 0 | 0 | 0 | [20 empty] | 2018-05-21 |  | 2019-04-17 |  | EXP | [8 empty] | 2019-11-15 | Connected |  | No
National Grid | SUTTON | 178681 | 1590 | 4950 | Solar | 01_304W5 | 2018-04-11 01:00 | 2018-04-12 | 5 | 5 | 0 | [10 empty] | 2018-04-20 | 2018-11-05 | 139 | 119 | 20 | [12 empty] | 2019-04-17 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SUTTON | 178682 | 1590 | 4000 | Solar | 01_304W6 | 2018-04-11 01:00 | 2018-04-12 | 5 | 5 | 0 | [10 empty] | 2018-04-20 | 2018-11-05 | 137 | 0 | 137 | [12 empty] | 2019-04-17 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | DOUGLAS | 178711 | 1516 | 250 | Solar | 05_320W2 | 2018-04-11 01:00 | 2018-04-12 | 30 | 0 | 30 | [27 empty] | 2019-04-17 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | DOUGLAS | 178713 | 1516 | 1000 | Solar | 05_320W2 | 2018-04-11 01:00 | 2018-04-12 | 6 | 0 | 6 | [10 empty] | 2018-05-11 | 2018-05-25 | 10 | 0 | 10 | [12 empty] | 2019-04-17 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | DOUGLAS | 178714 | 1516 | 500 | Solar | 05_320W2 | 2018-04-11 01:00 | 2018-04-12 | 6 | 0 | 6 | [10 empty] | 2018-05-11 | 2018-05-25 | 10 | 0 | 10 | [12 empty] | 2019-04-17 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | DOUGLAS | 178715 | 1516 | 1000 | Solar | 05_320W2 | 2018-04-11 01:00 | 2018-04-12 | 6 | 0 | 6 | [10 empty] | 2018-05-11 | 2018-05-10 | 0 | 0 | 0 | [12 empty] | 2019-04-17 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | DOUGLAS | 178716 | 1516 | 250 | Solar | 05_320W2 | 2018-04-11 01:00 | 2018-04-12 | 6 | 0 | 6 | [10 empty] | 2018-05-08 | 2018-05-07 | 0 | 0 | 0 | [12 empty] | 2019-04-17 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | DOUGLAS | 178717 | 1516 | 1000 | Solar | 05_320W2 | 2018-04-11 01:00 | 2018-04-12 | 6 | 0 | 6 | [10 empty] | 2018-05-08 | 2018-05-25 | 0 | 0 | 0 | [12 empty] | 2019-04-17 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BELLINGHAM | 173418 | 2019 | 10 | Solar | 05_335W1 | 2018-04-11 10:06 | 2018-05-08 | 26 | 2 | 24 | 2018-06-14 | 2018-07-26 | 29 | 0 | 29 | [20 empty] | 2018-07-30 |  |  |  | EXP | [8 empty] | 2019-02-14 | Connected |  | No
National Grid | REVERE | 173375 | 2151 | 10 | Solar | 12_16W8 | 2018-04-11 12:25 | 2018-05-01 | 0 | 0 | 0 | 2018-05-10 | 2018-05-30 | 13 | 0 | 13 | [20 empty] | 2018-06-01 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | REVERE | 173414 | 2151 | 7.6 | Solar | 12_35J3 | 2018-04-11 12:34 | 2018-05-01 | 0 | 0 | 0 | 2018-05-09 | 2018-05-31 | 14 | 0 | 14 | [21 empty] | 2018-04-11 13:49 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | DRACUT | 173451 | 1826 | 11.4 | Solar | 14_78L1 | 2018-04-11 13:49 | 2018-06-26 | 10 | 5 | 5 | 2018-07-11 | 2018-07-16 | 3 | 0 | 3 | [20 empty] | 2018-07-17 |  | 2019-08-30 | Yes | EXP |  | 2019-04-23 | 2019-04-22 | 0 | 0 | 0 |  |  | 2019-08-08 | Connected |  | No
National Grid | WESTFORD | 178144 | 1886 | 20 | Solar | 14_57L2 | 2018-04-12 01:00 | 2018-04-13 | 10 | 0 | 10 | 2018-05-01 | 2018-05-30 | 20 | 0 | 20 | [20 empty] | 2019-03-13 |  | 2020-10-22 |  | EXP | [8 empty] | 2020-02-18 | Connected |  | No
National Grid | ANDOVER | 178145 | 1810 | 10 | Solar | 14_50L1 | 2018-04-12 01:00 | 2018-04-13 | 374 | 34 | 340 | [27 empty] | 2019-04-18 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BELCHERTOWN | 178146 | 1007 | 9380 | Solar | 09_509L2 | 2018-04-12 01:00 | 2018-04-13 | 1 | 0 | 1 | [10 empty] | 2018-04-16 | 2018-06-06 | 34 | 0 | 34 | [12 empty] | 2019-04-18 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BELCHERTOWN | 178147 | 1007 | 9380 | Solar | 09_509L2 | 2018-04-12 01:00 | 2018-04-13 | 1 | 0 | 1 | [10 empty] | 2018-04-16 | 2018-06-11 | 37 | 0 | 37 | [12 empty] | 2019-04-18 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BELCHERTOWN | 178148 | 1007 | 9380 | Solar | 09_509L2 | 2018-04-12 01:00 | 2018-04-13 | 1 | 0 | 1 | [10 empty] | 2018-04-16 | 2018-06-06 | 34 | 0 | 34 | [12 empty] | 2019-04-18 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BELCHERTOWN | 178149 | 1007 | 9380 | Solar | 09_509L2 | 2018-04-12 01:00 | 2018-04-13 | 1 | 0 | 1 | [10 empty] | 2018-04-16 | 2018-06-11 | 37 | 0 | 37 | [12 empty] | 2019-04-18 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BELCHERTOWN | 178150 | 1007 | 9380 | Solar | 09_509L2 | 2018-04-12 01:00 | 2018-04-13 | 1 | 0 | 1 | [10 empty] | 2018-04-16 | 2018-06-06 | 34 | 0 | 34 | [12 empty] | 2019-04-18 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BELCHERTOWN | 178151 | 1007 | 9380 | Solar | 09_509L2 | 2018-04-12 01:00 | 2018-04-13 | 1 | 0 | 1 | [10 empty] | 2018-04-16 | 2018-06-06 | 34 | 0 | 34 | [12 empty] | 2019-04-18 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BELCHERTOWN | 178179 | 1007 | 9380 | Solar | 09_509L2 | 2018-04-12 01:00 | 2018-04-13 | 1 | 0 | 1 | [10 empty] | 2018-04-16 | 2018-06-06 | 34 | 0 | 34 | [12 empty] | 2019-04-18 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BELCHERTOWN | 178180 | 1007 | 9380 | Solar | 09_509L2 | 2018-04-12 01:00 | 2018-04-13 | 1 | 0 | 1 | [10 empty] | 2018-04-16 | 2018-06-06 | 34 | 0 | 34 | [12 empty] | 2019-04-18 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ADAMS | 178718 | 1220 | 4990 | Solar | 09_1021W2 | 2018-04-12 01:00 | 2018-04-13 | 1 | 0 | 1 | [10 empty] | 2018-04-16 | 2018-06-28 | 53 | 32 | 21 | [12 empty] | 2019-04-18 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | TYNGSBORO | 178719 | 1879 | 86.19 | Solar | 14_211L1 | 2018-04-12 01:00 | 2018-04-13 | 380 | 24 | 356 | [27 empty] | 2019-04-18 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH BILLERICA | 178720 | 1862 | 1950 | Solar | 14_70L1 | 2018-04-12 01:00 | 2018-04-13 | 5 | 0 | 5 | [10 empty] | 2018-04-20 | 2018-05-26 | 26 | 7 | 19 | [10 empty] | 2018-11-20 | 2018-04-12 09:12 | 2021-07-29 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 172485 | 1609 | 6 | Solar | 01_23W2 | 2018-04-12 09:12 | 2018-05-23 | 9 | 0 | 9 | 2018-06-06 | 2018-07-07 | 21 | 0 | 21 | [20 empty] | 2018-07-24 |  |  | Yes | EXP | [8 empty] | 2019-03-13 | Connected |  | No
National Grid | GRANBY | 173510 | 1033 | 3.8 | Solar | 09_527L1 | 2018-04-12 10:10 | 2018-05-01 | 8 | 0 | 8 | [25 empty] | 2018-06-13 | 2018-04-12 11:58 |  |  | EXP | [8 empty] | 2019-10-30 | Connected |  | No
National Grid | DOUGLAS | 178712 | 1516 | 4998 | Solar | 05_320W2 | 2018-04-12 11:58 | 2018-07-03 | 14 | 1 | 13 | [10 empty] | 2018-07-24 | 2018-07-28 | 4 | 0 | 4 | [10 empty] | 2018-12-26 |  | 2022-01-26 | Yes | STD |  | 2021-06-09 | 2021-12-28 | 203 | 7 | 196 |  |  | 2022-01-24 | Connected |  | No
National Grid | BEVERLY | 178181 | 1915 | 3.8 | Solar | 12_72L1 | 2018-04-13 01:00 | 2018-04-13 | 13 | 0 | 13 | 2018-05-02 | 2018-05-02 | 22 | 0 | 22 | [20 empty] | 2018-05-02 |  | 2019-04-18 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LEOMINSTER | 178182 | 1453 | 3.8 | Solar | 01_207W6 | 2018-04-13 01:00 | 2018-04-23 | 7 | 0 | 7 | 2018-05-02 | 2018-05-02 | 0 | 0 | 0 | [20 empty] | 2018-05-07 |  | 2019-04-21 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 178183 | 1844 | 7.6 | Solar | 14_74L3 | 2018-04-13 01:00 | 2018-04-16 | 21 | 21 | 0 | 2018-05-02 | 2018-05-25 | 0 | 0 | 0 | [22 empty] | 2019-04-21 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | CHELMSFORD | 178184 | 1824 | 3.8 | Solar | 14_70L3 | 2018-04-13 01:00 | 2018-04-16 | 0 | 0 | 0 | 2018-05-01 | 2018-05-23 | 30 | 0 | 30 | [20 empty] | 2019-02-12 |  | 2019-04-21 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LAWRENCE | 178185 | 1841 | 7.6 | Solar | 14_8L2 | 2018-04-13 01:00 | 2018-04-16 | 5 | 0 | 5 | 2018-04-23 | 2018-05-22 | 21 | 0 | 21 | [20 empty] | 2018-05-22 |  | 2019-04-21 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SAUGUS | 178186 | 1906 | 15.2 | Solar | 12_25W2 | 2018-04-13 01:00 | 2018-04-16 | 6 | 0 | 6 | 2018-04-25 | 2018-05-21 | 18 | 0 | 18 | [20 empty] | 2018-05-22 |  | 2019-04-21 |  | EXP | [8 empty] | 2019-01-25 | Connected |  | No
National Grid | SEEKONK | 178187 | 2771 | 15.2 | Solar | 05_9L5 | 2018-04-13 01:00 | 2018-05-01 | 13 | 0 | 13 | 2018-05-18 | 2018-05-18 | 0 | 0 | 0 | [20 empty] | 2018-05-23 |  | 2019-04-21 |  | EXP | [8 empty] | 2019-08-14 | Connected |  | No
National Grid | WORCESTER | 178216 | 1602 | 7.6 | Solar | 01_6W2 | 2018-04-13 01:00 | 2018-04-16 | 14 | 0 | 14 | 2018-05-04 | 2018-05-08 | 2 | 0 | 2 | [20 empty] | 2018-05-08 |  | 2019-04-21 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | AUBURN | 178217 | 1501 | 3.8 | Solar | 01_26W3 | 2018-04-13 01:00 | 2018-07-02 | 9 | 0 | 9 | 2018-07-16 | 2018-07-16 | 0 | 0 | 0 | [20 empty] | 2018-07-16 |  | 2019-04-21 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LAWRENCE | 178218 | 1843 | 10 | Solar | 14_1J1 | 2018-04-13 01:00 | 2018-04-16 | 10 | 0 | 10 | 2018-05-01 | 2018-05-23 | 16 | 0 | 16 | [20 empty] | 2018-05-23 |  | 2019-04-21 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | TEWKSBURY | 178219 | 1876 | 7.6 | Solar | 14_59L3 | 2018-04-13 01:00 | 2018-04-16 | 10 | 0 | 10 | 2018-04-30 | 2018-05-23 | 0 | 0 | 0 | [20 empty] | 2018-05-22 |  | 2019-04-21 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MILFORD | 178221 | 1757 | 15.2 | Solar | 05_335W5 | 2018-04-13 01:00 | 2018-05-01 | 13 | 0 | 13 | 2018-05-18 | 2018-05-18 | 0 | 0 | 0 | [20 empty] | 2018-06-07 |  | 2019-04-21 |  | EXP | [8 empty] | 2018-11-26 | Connected |  | Yes
National Grid | ALFORD | 178222 | 1230 | 7.6 | Solar | 09_1109W3 | 2018-04-13 01:00 | 2018-04-16 | 24 | 0 | 24 | 2018-05-18 | 2018-05-18 | 0 | 0 | 0 | [20 empty] | 2018-05-18 |  | 2019-10-21 |  | EXP | [8 empty] | 2019-09-11 | Connected |  | No
National Grid | HUBBARDSTON | 178224 | 1452 | 2375 | Solar | 01_602W2 | 2018-04-16 01:00 | 2018-04-16 | 1 | 1 | 0 | [10 empty] | 2018-04-18 | 2018-05-09 | 3 | 0 | 3 | [12 empty] | 2019-04-21 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | AUBURN | 178255 | 1501 | 1375 | Solar | 01_406L1 | 2018-04-16 01:00 | 2018-04-16 | 2 | 1 | 1 | [10 empty] | 2018-04-18 | 2018-05-09 | 3 | 0 | 3 | [11 empty] | 2018-04-16 01:00 | 2019-04-21 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 178256 | 1603 | 900 | Solar | 01_23W1 | 2018-04-16 01:00 | 2018-04-17 | 15 | 15 | 0 | [10 empty] | 2018-05-09 | 2018-06-06 | 19 | 0 | 19 | [10 empty] | 2019-08-16 |  | 2023-08-16 | Yes | STD |  | 2021-01-13 | 2023-08-03 | 933 | 7 | 926 | 2023-07-21 | 2023-07-21 | 2023-08-14 | Connected |  | No
National Grid | MILLBURY | 173709 | 1527 | 3.8 | Solar | 01_304W3 | 2018-04-16 12:38 | 2018-06-05 | 0 | 0 | 0 | 2018-06-05 | 2018-06-19 | 10 | 0 | 10 | [20 empty] | 2018-07-24 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTH EASTON | 178257 | 2356 | 15 | Solar | 07_92W78 | 2018-04-17 01:00 | 2018-04-17 | 31 | 29 | 2 | 2018-06-08 | 2019-11-27 | 180 | 0 | 180 | [20 empty] | 2019-03-13 |  | 2019-04-22 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WINCHENDON | 178258 | 1475 | 4999 | Solar | 01_612W3 | 2018-04-17 01:00 | 2018-04-17 | 4 | 3 | 1 | [10 empty] | 2018-04-27 | 2018-08-18 | 79 | 67 | 12 | [5 empty] | 2020-07-10 | 2020-10-02 | 60 | 3 | 57 |  |  |  |  | STD | [9 empty] | Group Study |  | No
National Grid | BLACKSTONE | 178259 | 1504 | 4990 | Solar | 05_321W2 | 2018-04-17 01:00 | 2018-04-17 | 6 | 5 | 1 | [10 empty] | 2018-04-30 | 2018-06-21 | 22 | 21 | 1 | [11 empty] | 2018-04-17 01:00 | 2019-04-22 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BELLINGHAM | 178261 | 2019 | 100 | Solar | 05_335W1 | 2018-04-17 01:00 | 2018-04-18 | 61 | 15 | 46 | 2018-07-13 | 2018-09-27 | 54 | 54 | 0 | 2018-10-18 | 2018-11-20 | 22 | 3 | 19 | [5 empty] | 2018-10-18 | 2018-11-20 | 22 | 3 | 19 | [5 empty] | 2018-12-17 |  | 2020-06-15 | Yes | EXP |  | 2020-02-11 | 2020-02-13 | 2 | 0 | 2 |  |  | 2020-06-08 | Connected |  | No
National Grid | RUTLAND | 178262 | 1543 | 7.6 | Solar | 01_55W1 | 2018-04-17 01:00 | 2018-04-23 | 19 | 0 | 19 | 2018-05-18 | 2018-05-18 | 0 | 0 | 0 | [20 empty] | 2018-05-18 |  | 2019-04-23 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MALDEN | 178263 | 2148 | 16.32 | Solar | 12_16W6 | 2018-04-17 01:00 | 2018-05-18 | 3 | 3 | 0 | 2018-05-18 | 2018-05-18 | 0 | 0 | 0 | [20 empty] | 2018-05-18 |  | 2019-04-23 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | OXFORD | 173764 | 1540 | 10 | Solar | 01_406L4 | 2018-04-17 10:23 | 2018-07-10 | 0 | 0 | 0 | 2018-07-10 | 2018-07-11 | 1 | 0 | 1 | [20 empty] | 2018-07-24 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | STOUGHTON | 178739 | 2072 | 249 | Solar | 07_75W1 | 2018-04-18 01:00 | 2018-04-19 | 31 | 0 | 31 | [27 empty] | 2019-04-24 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SAUGUS | 178740 | 1906 | 15.2 | Solar | 12_25W2 | 2018-04-18 01:00 | 2018-04-19 | 2 | 0 | 2 | 2018-04-20 | 2018-05-22 | 2 | 0 | 2 | [20 empty] | 2018-05-30 | 2018-04-18 15:29 | 2019-04-24 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | DUDLEY | 178264 | 1571 | 1250 | Solar | 01_412L4 | 2018-04-18 15:29 | 2018-04-19 | 8 | 8 | 0 | [10 empty] | 2018-05-01 | 2018-06-25 | 39 | 14 | 25 | [10 empty] | 2021-03-15 |  | 2024-09-06 | Yes | STD | [9 empty] | Construction |  | No
National Grid | TEWKSBURY | 174098 | 1876 | 3.8 | Solar | 14_20L5 | 2018-04-21 12:07 | 2018-05-29 | 1 | 0 | 1 | 2018-05-29 | 2018-06-04 | 0 | 0 | 0 | [20 empty] | 2018-05-29 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | TEWKSBURY | 183612 | 1876 | 7.6 | Solar | 14_59L3 | 2018-04-23 15:50 | 2018-07-02 | 0 | 0 | 0 | 2018-07-02 | 2018-07-03 | 1 | 0 | 1 | [20 empty] | 2018-07-12 |  |  |  | EXP | [8 empty] | 2019-10-25 | Connected |  | No
National Grid | REVERE | 173494 | 2151 | 10 | Solar | 12_16W8 | 2018-04-24 09:54 | 2018-05-04 | 1 | 0 | 1 | 2018-05-08 | 2018-05-25 | 13 | 0 | 13 | [20 empty] | 2018-05-26 |  |  |  | EXP | [8 empty] | 2019-05-22 | Connected |  | No
National Grid | WORCESTER | 166072 | 1603 | 7.6 | Solar | 01_6W2 | 2018-04-24 12:11 | 2018-05-23 | 9 | 0 | 9 | 2018-07-27 | 2018-07-26 | 0 | 0 | 0 | [20 empty] | 2018-09-28 | 2018-04-25 08:52 | 2020-11-18 |  | EXP | [8 empty] | 2020-10-20 | Connected |  | No
National Grid | EVERETT | 183731 | 2149 | 11.4 | Solar | 12_16W7 | 2018-04-25 08:52 | 2018-07-23 | 3 | 0 | 3 | 2018-07-27 | 2018-07-30 | 1 | 0 | 1 | [20 empty] | 2018-07-31 |  | 2019-11-25 | Yes | EXP |  | 2019-04-23 | 2019-04-22 | 0 | 0 | 0 |  |  | 2019-11-01 | Connected |  | No
National Grid | PALMER | 183826 | 1069 | 3.8 | Solar | 09_516L3 | 2018-04-25 10:34 | 2018-07-16 | 9 | 0 | 9 | 2018-07-30 | 2018-08-02 | 3 | 0 | 3 | [20 empty] | 2018-09-25 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | UXBRIDGE | 184491 | 1569 | 1800 | Solar | 05_321W2 | 2018-04-28 | 2018-05-07 | 17 | 17 | 0 | [10 empty] | 2018-05-31 | 2018-06-27 | 19 | 0 | 19 | [11 empty] | 2018-04-28 08:53 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | DUNSTABLE | 184039 | 1827 | 4500 | Solar | 01_210L1 | 2018-04-28 08:53 | 2018-04-30 | 44 | 0 | 44 | [10 empty] | 2018-06-27 | 2018-07-16 | 13 | 5 | 8 | [10 empty] | 2019-01-14 |  | 2020-12-31 | Yes | STD |  | 2020-02-19 | 2020-08-01 | 163 | 0 | 163 |  |  | 2020-12-31 | Connected |  | No
National Grid | UXBRIDGE | 184499 | 1569 | 1666 | Solar | 05_321W2 | 2018-04-30 | 2018-05-07 | 17 | 17 | 0 | [10 empty] | 2018-05-31 | 2018-06-27 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | CHELMSFORD | 184582 | 1824 | 233.1 | Solar | 14_24L1 | 2018-04-30 | 2018-05-30 | 0 | 0 | 0 | 2018-05-31 | 2019-10-03 | 339 | 66 | 273 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LOWELL | 184041 | 1851 | 73.3 | Solar | 14_2L3 | 2018-04-30 09:11 | 2018-05-01 | 0 | 0 | 0 | 2018-05-01 | 2018-05-30 | 20 | 0 | 20 | [20 empty] | 2018-05-30 |  | 2019-04-27 |  | EXP | [8 empty] | 2019-01-08 | Connected |  | Yes
National Grid | WEBSTER | 184051 | 1570 | 2375 | Solar | 01_412L1 | 2018-04-30 13:03 | 2018-05-01 | 14 | 13 | 1 | [10 empty] | 2018-05-22 | 2018-06-28 | 27 | 2 | 25 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | LYNN | 183811 | 1902 | 5 | Solar | 12_29W5 | 2018-04-30 13:34 | 2018-05-04 | 1 | 0 | 1 | 2018-05-07 | 2018-05-30 | 16 | 0 | 16 | [20 empty] | 2018-05-31 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SUTTON | 184056 | 1590 | 999 | Battery Add-On | 01_304W6 | 2018-05-01 | 2018-05-03 | 6 | 0 | 6 | [10 empty] | 2018-05-10 | 2018-06-19 | 28 | 4 | 24 | [10 empty] | 2018-11-30 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SPENCER | 184382 | 1562 | 7.6 | Solar | 01_552L1 | 2018-05-02 17:10 | 2018-06-07 | 2 | 0 | 2 | 2018-06-12 | 2018-06-12 | 0 | 0 | 0 | [20 empty] | 2018-06-12 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WENDELL | 184433 | 1379 | 2600 | Solar | 09_705W1 | 2018-05-03 15:14 | 2018-05-04 | 11 | 1 | 10 | [10 empty] | 2018-05-22 | 2018-06-01 | 7 | 0 | 7 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | HALIFAX | 184458 | 2338 | 4950 | Solar | 07_912W74 | 2018-05-04 | 2018-05-07 | 6 | 6 | 0 | [10 empty] | 2018-05-15 | 2018-06-15 | 23 | 4 | 19 | [10 empty] | 2018-10-11 |  | 2021-01-25 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | UXBRIDGE | 184500 | 1569 | 1666 | Solar | 05_321W2 | 2018-05-04 | 2018-05-07 | 18 | 18 | 0 | [10 empty] | 2018-06-01 | 2018-06-28 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | MARLBOROUGH | 184521 | 1752 | 17.6 | Solar | 05_311W3 | 2018-05-04 | 2018-05-14 | 16 | 2 | 14 | 2018-06-06 | 2018-07-05 | 20 | 0 | 20 | [20 empty] | 2018-07-23 |  |  |  | EXP | [8 empty] | 2018-11-26 | Connected |  | Yes
National Grid | WARREN | 184437 | 1083 | 4998 | Solar |  | 2018-05-04 21:36 | 2018-05-07 | 10 | 0 | 10 | [29 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | HAVERHILL | 184579 | 1830 | 37.6 | Solar | 14_48L4 | 2018-05-07 09:53 | 2018-05-07 | 0 | 0 | 0 | 2018-05-17 |  | 23 | 15 | 8 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTHAMPTON | 184686 | 1060 | 66.6 | Solar | 09_909W1 | 2018-05-07 15:27 | 2018-05-08 | 20 | 0 | 20 | 2018-06-07 | 2018-07-25 | 33 | 0 | 33 | [20 empty] | 2018-08-02 |  | 2020-06-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BERLIN | 184729 | 1503 | 16.64 | Solar | 05_318W3 | 2018-05-07 18:02 | 2018-06-28 | 9 | 0 | 9 | 2018-07-13 | 2018-07-16 | 1 | 0 | 1 | [20 empty] | 2018-12-24 | 2018-05-08 11:11 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BRIMFIELD | 184096 | 1010 | 1875 | Solar | 09_503L4 | 2018-05-08 11:11 | 2018-05-09 | 8 | 0 | 8 | [20 empty] | 2019-01-09 | 2020-07-13 | 380 | 357 | 23 | 2020-08-04 | 2018-05-08 14:05 | 2022-02-01 | Yes | CMPX |  | 2021-08-06 | 2021-12-01 | 118 | 7 | 111 |  |  | 2021-12-29 | Connected |  | No
National Grid | MILLBURY | 184779 | 1527 | 249.8 | Solar | 01_304W3 | 2018-05-08 14:05 | 2018-05-09 | 20 | 4 | 16 | 2018-06-07 | 2018-06-13 | 4 | 0 | 4 | [20 empty] | 2018-07-19 |  | 2020-07-16 | Yes | EXP | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 184808 | 1844 | 25.2 | Solar | 14_74L2 | 2018-05-08 15:44 | 2018-05-09 | 6 | 0 | 6 | 2018-05-17 | 2018-06-05 | 12 | 0 | 12 | [20 empty] | 2018-06-05 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FRANKLIN | 184555 | 2038 | 990 | Solar | 05_348W7 | 2018-05-09 | 2018-06-01 | 16 | 0 | 16 | [10 empty] | 2018-06-26 | 2018-07-27 | 23 | 2 | 21 | [10 empty] | 2019-02-22 |  | 2020-09-04 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | FRANKLIN | 184559 | 2038 | 990 | Solar | 05_348W7 | 2018-05-09 | 2018-06-01 | 17 | 10 | 7 | [10 empty] | 2018-06-26 | 2018-07-27 | 23 | 2 | 21 | [10 empty] | 2019-02-22 |  | 2020-09-04 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HEATH | 184560 | 1346 | 990 | Solar | 09_1019W1 | 2018-05-09 | 2018-06-01 | 1 | 0 | 1 | [10 empty] | 2018-06-15 | 2018-10-29 | 0 | 0 | 0 | [11 empty] | 2018-05-09 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LANCASTER | 184857 | 1523 | 4980 | Solar | 01_227W1 | 2018-05-09 | 2018-05-22 | 10 | 0 | 10 | [10 empty] | 2018-06-07 | 2018-07-25 | 33 | 13 | 20 | [10 empty] | 2019-03-11 |  | 2024-01-17 | Yes | STD |  | 2022-08-12 | 2023-01-18 | 160 | 0 | 160 | 2023-12-15 | 2023-12-15 | 2023-12-29 | Connected |  | No
National Grid | HANSON | 184675 | 2341 | 1328 | Solar | 07_93W43 | 2018-05-09 10:53 | 2018-05-10 | 55 | 52 | 3 | [10 empty] | 2018-07-30 | 2018-08-30 | 24 | 15 | 9 | [10 empty] | 2019-03-20 |  | 2021-01-02 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BLACKSTONE | 184667 | 1504 | 2200 | Solar | 05_332W1 | 2018-05-09 11:28 | 2018-05-10 | 18 | 12 | 6 | [10 empty] | 2018-06-13 | 2018-08-09 | 41 | 35 | 6 | [12 empty] | 2020-12-09 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WILBRAHAM | 184777 | 1095 | 4980 | Solar |  | 2018-05-09 11:38 | 2018-05-10 | 8 | 0 | 8 | [29 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BARRE | 184659 | 1005 | 5120 | Solar |  | 2018-05-09 13:29 | 2018-05-10 | 22 | 0 | 22 | [10 empty] | 2018-06-13 | 2018-06-12 | 0 | 0 | 0 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | GLOUCESTER | 183953 | 1930 | 6.44 | Solar | 12_24J10 | 2018-05-09 13:37 | 2018-05-10 | 8 | 0 | 8 | 2018-05-22 | 2018-06-25 | 24 | 0 | 24 | [20 empty] | 2018-06-25 |  |  |  | EXP | [8 empty] | 2018-09-11 | Connected |  | Yes
National Grid | NORTH BROOKFIELD | 184669 | 1005 | 1800 | Solar | 01_525L1 | 2018-05-09 16:08 | 2018-05-22 | 4 | 0 | 4 | [10 empty] | 2018-06-13 | 2018-08-13 | 43 | 41 | 2 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | ATHOL | 184672 | 1331 | 2000 | Solar | 09_1193W1 | 2018-05-09 16:29 | 2018-05-10 | 13 | 0 | 13 | [10 empty] | 2018-06-05 | 2018-08-09 | 49 | 45 | 4 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WARWICK | 184632 | 1378 | 990 | Solar | 09_705W3 | 2018-05-10 | 2018-06-01 | 111 | 0 | 111 | [10 empty] | 2018-06-15 | 2018-06-22 | 5 | 0 | 5 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WILLIAMSBURG | 184647 | 1096 | 990 | Solar |  | 2018-05-10 | 2018-06-01 | 1 | 0 | 1 | [10 empty] | 2018-06-05 | 2018-06-19 | 10 | 0 | 10 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | HAVERHILL | 184923 | 1835 | 250 | Solar | 14_43L8 | 2018-05-10 | 2018-05-18 | 6 | 0 | 6 | 2018-05-18 | 2018-05-29 | 6 | 0 | 6 | [20 empty] | 2018-05-31 |  |  |  | EXP | [8 empty] | 2019-07-25 | Connected |  | No
National Grid | BELCHERTOWN | 185023 | 1007 | 500 | Solar | 09_509L2 | 2018-05-10 | 2018-05-11 | 33 | 33 | 0 | [10 empty] | 2018-06-27 | 2018-07-03 | 4 | 0 | 4 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | HAVERHILL | 185057 | 1835 | 250 | Solar | 14_43L8 | 2018-05-10 | 2018-05-15 | 2 | 0 | 2 | 2018-05-17 | 2018-05-31 | 9 | 0 | 9 | [20 empty] | 2018-06-01 | 2018-05-10 09:55 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SALISBURY | 184636 | 1952 | 7.6 | Solar | 14_7L4 | 2018-05-10 09:55 | 2018-05-11 | 11 | 0 | 11 | 2018-05-17 | 2018-06-04 | 11 | 0 | 11 | [20 empty] | 2018-06-04 |  |  |  | EXP | [8 empty] | 2019-04-25 | Connected |  | No
National Grid | CHELMSFORD | 185021 | 1824 | 3.8 | Solar | 14_24L1 | 2018-05-10 12:21 | 2018-05-11 | 4 | 0 | 4 | 2018-05-17 | 2018-06-04 | 11 | 0 | 11 | [20 empty] | 2018-06-04 | 2018-05-10 15:53 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | GRAFTON | 185050 | 1519 | 240 | Solar | 01_304W1 | 2018-05-10 15:53 | 2018-05-11 | 17 | 0 | 17 | [10 empty] | 2018-06-07 | 2018-06-11 | 2 | 0 | 2 | [10 empty] | 2018-10-26 |  | 2022-10-27 | Yes | STD |  | 2019-10-22 | 2020-07-29 | 282 | 247 | 35 |  |  | 2022-04-15 | Connected |  | No
National Grid | WINCHENDON | 184650 | 1475 | 990 | Solar | 01_612W3 | 2018-05-11 | 2018-06-01 | 1 | 0 | 1 | [10 empty] | 2018-06-05 | 2018-06-14 | 7 | 0 | 7 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BELCHERTOWN | 184655 | 1007 | 990 | Solar | 09_509L1 | 2018-05-11 | 2018-06-01 | 1 | 0 | 1 | [10 empty] | 2018-06-05 | 2018-06-26 | 15 | 0 | 15 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BELCHERTOWN | 185083 | 1007 | 499.9 | Solar | 09_509L2 | 2018-05-11 | 2018-05-14 | 16 | 0 | 16 | [10 empty] | 2018-06-07 | 2018-06-19 | 9 | 2 | 7 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SUTTON | 184400 | 1590 | 6 | Solar | 01_304W2 | 2018-05-11 09:41 | 2018-05-14 | 16 | 0 | 16 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 185125 | 1844 | 7.6 | Solar | 14_63L2 | 2018-05-11 15:02 | 2018-06-14 | 0 | 0 | 0 | 2018-06-13 | 2018-06-15 | 2 | 0 | 2 | [20 empty] | 2018-06-18 |  |  |  | EXP | [8 empty] | 2019-09-30 | Connected |  | No
National Grid | BELCHERTOWN | 184683 | 1007 | 990 | Solar | 09_509L1 | 2018-05-14 | 2018-06-01 | 1 | 0 | 1 | [10 empty] | 2018-06-05 | 2018-06-15 | 8 | 0 | 8 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTHAMPTON | 184687 | 1062 | 990 | Solar | 09_909W2 | 2018-05-14 | 2018-06-01 | 1 | 0 | 1 | [10 empty] | 2018-06-05 | 2018-06-29 | 18 | 0 | 18 | [10 empty] | 2019-01-23 |  | 2020-07-22 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTHAMPTON | 185190 | 1062 | 467 | Solar | 09_909W1 | 2018-05-15 | 2018-05-16 | 15 | 0 | 15 | [10 empty] | 2018-06-08 | 2018-06-07 | 0 | 0 | 0 | [10 empty] | 2018-12-13 | 2018-05-15 | 2020-03-02 |  | STD | [8 empty] | 2019-12-30 | Connected |  | No
National Grid | NORTON | 185512 | 2766 | 2000 | Solar | 07_92W79 | 2018-05-15 | 2018-05-18 | 21 | 4 | 17 | [10 empty] | 2018-06-19 | 2018-07-27 | 28 | 11 | 17 | [10 empty] | 2019-02-28 |  | 2025-02-23 | Yes | STD | [9 empty] | Design |  | No
National Grid | REVERE | 184518 | 2151 | 10 | Solar | 12_7W2 | 2018-05-15 09:51 | 2018-06-12 | 0 | 0 | 0 | 2018-06-12 | 2018-06-12 | 0 | 0 | 0 | [20 empty] | 2018-06-12 |  |  |  | EXP | [8 empty] | 2018-08-29 | Connected |  | Yes
National Grid | HANOVER | 184731 | 2339 | 25 | Solar | 07_910W51 | 2018-05-15 11:28 | 2018-05-16 | 40 | 20 | 20 | 2018-07-13 | 2018-07-13 | 0 | 0 | 0 | [20 empty] | 2018-07-30 |  |  |  | EXP | [8 empty] | 2018-11-21 | Connected |  | No
National Grid | ORANGE | 178742 | 1364 | 990 | Solar |  | 2018-05-16 | 2018-06-27 | 74 | 0 | 74 | [27 empty] | 2019-04-24 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORWELL | 184689 | 2061 | 990 | Solar | 07_95W5 | 2018-05-16 | 2018-05-29 | 19 | 0 | 19 | [10 empty] | 2018-06-26 | 2018-08-13 | 34 | 15 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | GOSHEN | 185024 | 1032 | 499 | Solar |  | 2018-05-16 | 2018-05-17 | 7 | 0 | 7 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | BELCHERTOWN | 185029 | 1007 | 500 | Solar | 09_509L2 | 2018-05-16 | 2018-05-17 | 23 | 14 | 9 | [10 empty] | 2018-06-05 | 2018-07-03 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SOUTH GRAFTON | 185495 | 1560 | 250 | Solar | 05_320W3 | 2018-05-16 | 2018-05-17 | 14 | 0 | 14 | 2018-06-08 | 2018-06-08 | 0 | 0 | 0 | [20 empty] | 2018-07-20 |  |  |  | EXP | [8 empty] | 2019-07-22 | Connected |  | No
National Grid | FRANKLIN | 173748 | 2038 | 5 | Solar | 05_348W5 | 2018-05-16 11:51 | 2018-05-25 | 16 | 8 | 8 | 2018-06-19 | 2018-07-25 | 28 | 0 | 28 | [20 empty] | 2018-07-27 |  |  |  | EXP | [8 empty] | 2018-10-03 | Connected |  | Yes
National Grid | WARREN | 184046 | 1082 | 4998 | Solar | 09_516L3 | 2018-05-16 13:45 | 2018-05-04 | 26 | 0 | 26 | [10 empty] | 2018-06-13 | 2018-07-11 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | MALDEN | 185547 | 2148 | 17.85 | Solar | 12_16W6 | 2018-05-16 15:59 | 2018-05-17 | 35 | 25 | 10 | 2018-06-22 | 2018-06-25 | 1 | 0 | 1 | [20 empty] | 2018-06-25 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WARREN | 184047 | 1082 | 4998 | Solar | 09_516L3 | 2018-05-16 16:44 | 2018-05-17 | 27 | 24 | 3 | [10 empty] | 2018-06-12 | 2018-07-11 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | EAST BROOKFIELD | 185007 | 1515 | 1000 | Solar | 01_525L2 | 2018-05-17 09:50 | 2018-05-18 | 32 | 15 | 17 | [10 empty] | 2018-07-05 | 2018-09-11 | 36 | 5 | 31 | [11 empty] | 2018-05-17 12:31 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SOUTH EASTON | 185614 | 2375 | 294 | Solar | 07_92W54 | 2018-05-17 12:31 | 2018-05-18 | 49 | 35 | 14 | 2018-07-30 | 2018-10-06 | 49 | 25 | 24 | 2018-10-09 | 2018-11-29 | 35 | 17 | 18 | [5 empty] | 2018-10-09 | 2018-11-29 | 35 | 17 | 18 | [5 empty] | 2019-01-02 | 2018-05-17 12:38 | 2021-04-19 | Yes | EXP | [9 empty] | Withdrawn |  | No
National Grid | SOUTH EASTON | 185461 | 2375 | 422 | Solar | 07_92W54 | 2018-05-17 12:38 | 2018-05-18 | 49 | 30 | 19 | 2018-07-30 | 2018-10-22 | 60 | 25 | 35 | 2018-11-06 | 2018-12-14 | 25 | 0 | 25 | [5 empty] | 2018-11-06 | 2018-12-14 | 25 | 0 | 25 | [5 empty] | 2019-01-02 | 2018-05-17 13:53 | 2021-05-02 | Yes | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTON | 185564 | 2760 | 2000 | Solar | 07_92W79 | 2018-05-17 13:53 | 2018-05-18 | 21 | 4 | 17 | [10 empty] | 2018-06-19 | 2018-07-27 | 28 | 11 | 17 | [10 empty] | 2019-02-28 |  |  | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | WARE | 185571 | 1082 | 2000 | Solar |  | 2018-05-17 14:00 | 2018-05-18 | 31 | 5 | 26 | [10 empty] | 2018-09-04 | 2018-10-10 | 26 | 0 | 26 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WENDELL | 185644 | 1379 | 220 | Solar | 09_705W1 | 2018-05-17 14:22 | 2018-05-18 | 32 | 17 | 15 | 2018-07-05 | 2018-09-07 | 45 | 0 | 45 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | BILLERICA | 185699 | 1862 | 360 | Solar | 14_70L5 | 2018-05-18 10:27 | 2018-05-21 | 53 | 47 | 6 | 2018-06-22 | 2018-08-02 | 29 | 6 | 23 | [20 empty] | 2018-12-05 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | ANDOVER | 184342 | 1810 | 10 | Solar | 14_71L1 | 2018-05-18 13:52 | 2018-05-21 | 1 | 0 | 1 | 2018-05-22 | 2018-05-30 | 5 | 0 | 5 | [20 empty] | 2018-05-31 |  |  |  | EXP | [8 empty] | 2019-04-09 | Connected |  | No
National Grid | EAST LONGMEADOW | 185731 | 1028 | 500 | Solar | 09_508L1 | 2018-05-18 15:35 | 2018-05-21 | 6 | 0 | 6 | [10 empty] | 2018-06-04 | 2018-06-13 | 7 | 0 | 7 | [11 empty] | 2018-05-18 16:45 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BELLINGHAM | 185770 | 2019 | 11.4 | Solar | 05_108W60 | 2018-05-18 16:45 | 2018-07-05 | 5 | 0 | 5 | 2018-07-13 | 2018-07-13 | 0 | 0 | 0 | [20 empty] | 2018-07-30 | 2018-05-21 10:34 |  | Yes | EXP |  | 2019-07-11 | 2019-07-10 | 0 | 0 | 0 |  |  | 2019-11-08 | Connected |  | No
National Grid | DOUGLAS | 185136 | 1516 | 4980 | Solar | 05_320W2 | 2018-05-21 10:34 | 2018-05-22 | 34 | 29 | 5 | [10 empty] | 2018-07-11 | 2018-09-12 | 45 | 15 | 30 | [10 empty] | 2019-07-11 | 2018-05-21 12:21 | 2024-01-08 | Yes | STD |  | 2022-08-12 | 2023-07-19 | 342 | 174 | 168 |  |  | 2023-12-14 | Connected |  | No
National Grid | LANCASTER | 185527 | 1523 | 4950 | Solar | 01_207W3 | 2018-05-21 12:21 | 2018-06-11 | 6 | 0 | 6 | [10 empty] | 2018-06-20 | 2018-08-01 | 30 | 5 | 25 | [10 empty] | 2019-01-11 |  | 2021-04-30 | Yes | STD | [8 empty] | 2021-04-07 | Connected |  | No
National Grid | MONROE | 184704 | 1350 | 4980 | Solar | 09_1019W1 | 2018-05-22 | 2018-07-24 | 1 | 1 | 0 | [10 empty] | 2018-07-25 | 2018-08-08 | 11 | 9 | 2 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WILBRAHAM | 185238 | 1095 | 5000 | Solar | 09_507L1 | 2018-05-22 | 2018-05-23 | 272 | 0 | 272 | [10 empty] | 2018-06-15 | 2019-06-25 | 257 | 0 | 257 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | MALDEN | 185756 | 2148 | 150 | Solar | 12_5J10 | 2018-05-22 | 2018-05-23 | 4 | 0 | 4 | 2018-05-31 | 2018-06-04 | 3 | 2 | 1 | [20 empty] | 2018-06-14 |  | 2019-12-02 |  | EXP | [8 empty] | 2020-01-17 | Connected |  | No
National Grid | DOUGLAS | 185462 | 1516 | 15.2 | Solar | 05_320W2 | 2018-05-22 10:23 | 2018-05-30 | 11 | 8 | 3 | 2018-06-14 | 2018-07-24 | 27 | 0 | 27 | [20 empty] | 2018-07-30 | 2018-05-22 11:32 |  |  | EXP | [8 empty] | 2019-07-04 | Connected |  | No
National Grid | SOMERSET | 172587 | 2726 | 3.8 | Solar | 05_11W82 | 2018-05-22 11:32 | 2018-06-14 | 11 | 2 | 9 | 2018-06-29 | 2018-06-29 | 0 | 0 | 0 | [20 empty] | 2018-07-13 |  |  | Yes | EXP | [8 empty] | 2019-06-10 | Connected |  | No
National Grid | TYNGSBOROUGH | 185918 | 1879 | 37.8 | Solar | 14_211L1 | 2018-05-22 12:26 | 2018-05-23 | 4 | 0 | 4 | 2018-05-30 | 2018-05-30 | 0 | 0 | 0 | [20 empty] | 2018-05-30 | 2018-05-22 12:50 |  |  | EXP | [8 empty] | 2019-06-18 | Connected |  | No
National Grid | CHARLEMONT | 184045 | 1339 | 2500 | Solar | 09_1019W1 | 2018-05-22 12:50 | 2018-05-23 | 42 | 25 | 17 | [10 empty] | 2018-06-12 | 2018-06-25 | 10 | 9 | 1 | [10 empty] | 2019-03-01 |  | 2021-09-15 | Yes | STD |  | 2020-05-07 | 2021-07-29 | 185 | 5 | 180 | 2021-07-14 | 2021-07-14 | 2021-09-15 | Connected |  | No
National Grid | BROCKTON | 183971 | 2302 | 9.92 | Solar | 07_911W77 | 2018-05-22 13:39 | 2018-05-07 | 27 | 13 | 14 | 2018-06-14 | 2018-07-24 | 27 | 0 | 27 | [20 empty] | 2018-07-25 |  |  |  | EXP | [8 empty] | 2019-11-21 | Connected |  | No
National Grid | SHIRLEY | 184835 | 1464 | 7.6 | Solar | 01_227W3 | 2018-05-23 10:05 | 2018-05-24 | 8 | 0 | 8 | 2018-06-06 | 2018-06-28 | 16 | 0 | 16 | [20 empty] | 2018-08-06 |  |  |  | EXP | [8 empty] | 2018-09-25 | Connected |  | Yes
National Grid | HAVERHILL | 185025 | 1832 | 14.72 | Solar | 14_48L1 | 2018-05-23 10:17 | 2018-05-24 | 3 | 0 | 3 | 2018-05-31 | 2018-05-31 | 0 | 0 | 0 | [20 empty] | 2018-06-06 |  |  |  | EXP | [8 empty] | 2018-12-18 | Connected |  | Yes
National Grid | NORTHAMPTON | 184488 | 1060 | 66.6 | Solar |  | 2018-05-23 12:05 | 2018-05-24 | 25 | 0 | 25 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | MILFORD | 183593 | 1757 | 6 | Solar | 05_336W3 | 2018-05-23 13:30 | 2018-05-24 | 19 | 13 | 6 | 2018-06-21 | 2018-07-26 | 24 | 0 | 24 | [20 empty] | 2018-08-03 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 186105 | 1844 | 15.2 | Solar | 14_74L1 | 2018-05-23 14:03 | 2018-05-24 | 3 | 0 | 3 | 2018-05-31 | 2018-05-31 | 1 | 0 | 1 | [20 empty] | 2018-06-01 | 2018-05-24 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FRANKLIN | 185621 | 2038 | 996 | Solar | 05_3422W1 | 2018-05-24 | 2018-05-25 | 23 | 4 | 19 | [10 empty] | 2018-06-28 | 2018-08-02 | 25 | 3 | 22 | [10 empty] | 2019-07-10 | 2018-05-24 | 2023-03-24 | Yes | STD |  | 2021-10-23 | 2023-01-27 | 461 | 4 | 457 |  |  | 2023-03-14 | Connected |  | No
National Grid | TYNGSBOROUGH | 186232 | 1879 | 249.8 | Solar | 14_211L1 | 2018-05-24 | 2018-05-25 | 2 | 0 | 2 | 2018-05-31 | 2018-07-17 | 33 | 11 | 22 | [20 empty] | 2018-12-13 |  | 2021-08-31 | Yes | EXP | [8 empty] | 2021-08-20 | Connected |  | No
National Grid | WARREN | 186081 | 1083 | 4950 | Solar | 09_516L2 | 2018-05-24 10:06 | 2018-05-25 | 31 | 30 | 1 | [10 empty] | 2018-07-25 | 2018-07-24 | 0 | 0 | 0 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | NEW MARLBOROUGH | 186212 | 1230 | 7.6 | Solar | 09_1109W1 | 2018-05-24 12:58 | 2018-05-25 | 11 | 0 | 11 | 2018-06-12 | 2018-06-12 | 0 | 0 | 0 | [20 empty] | 2018-07-18 |  | 2019-10-28 |  | EXP | [8 empty] | 2019-09-27 | Connected |  | No
National Grid | BEVERLY | 186214 | 1915 | 9.92 | Solar | 12_12L2 | 2018-05-24 12:58 | 2018-05-25 | 2 | 0 | 2 | 2018-06-25 | 2018-06-27 | 2 | 0 | 2 | [20 empty] | 2018-06-27 |  |  |  | EXP | [8 empty] | 2019-11-12 | Connected |  | No
National Grid | LEOMINSTER | 184325 | 1453 | 7.6 | Solar | 01_219W4 | 2018-05-24 13:47 | 2018-05-25 | 21 | 20 | 1 | 2018-06-21 | 2018-06-21 | 0 | 0 | 0 | [20 empty] | 2018-07-26 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SALEM | 186237 | 1970 | 3.8 | Solar | 12_2W1 | 2018-05-24 14:47 | 2018-07-11 | 2 | 0 | 2 | 2018-07-13 | 2018-07-16 | 0 | 0 | 0 | [20 empty] | 2018-07-22 | 2018-05-24 16:47 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FRANKLIN | 185866 | 2038 | 4990 | Solar | 05_348W7 | 2018-05-24 16:47 | 2018-05-25 | 21 | 17 | 4 | [10 empty] | 2018-06-26 | 2018-07-23 | 18 | 0 | 18 | [10 empty] | 2019-07-11 |  | 2023-12-02 | Yes | STD |  | 2022-08-12 | 2022-12-16 | 127 | 1 | 126 |  |  | 2023-12-29 | Connected |  | Yes
National Grid | MONROE | 184702 | 1350 | 4980 | Solar | 09_1019W1 | 2018-05-25 | 2018-07-24 | 1 | 1 | 0 | [10 empty] | 2018-07-25 | 2018-09-21 | 42 | 16 | 26 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | ADAMS | 185520 | 1220 | 1000 | Solar | 09_1003 | 2018-05-25 | 2018-05-31 | 25 | 15 | 10 | [10 empty] | 2018-07-06 | 2018-08-10 | 26 | 21 | 5 | [10 empty] | 2019-10-31 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | CHESHIRE | 185567 | 1220 | 1000 | Solar | 09_1021W2 | 2018-05-25 | 2018-05-31 | 25 | 15 | 10 | [10 empty] | 2018-07-06 | 2018-08-10 | 26 | 20 | 6 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | MONSON | 185765 | 1057 | 4990 | Solar | 09_503L2 | 2018-05-25 | 2018-05-29 | 27 | 4 | 23 | [10 empty] | 2019-02-27 | 2019-03-11 | 8 | 0 | 8 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | MILLBURY | 186422 | 1527 | 15.2 | Solar | 01_304W3 | 2018-05-25 16:56 | 2018-05-29 | 9 | 0 | 9 | 2018-06-12 | 2018-06-13 | 1 | 0 | 1 | [20 empty] | 2018-06-15 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EAST BRIDGEWATER | 186427 | 2333 | 7.6 | Solar | 07_797W42 | 2018-05-25 17:16 | 2018-05-29 | 24 | 19 | 5 | 2018-06-15 | 2018-07-24 | 30 | 0 | 30 | [20 empty] | 2018-08-03 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WILBRAHAM | 186355 | 1095 | 21 | Solar | 09_139L3 | 2018-05-25 18:53 | 2018-05-29 | 0 | 0 | 0 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HALIFAX | 183820 | 2338 | 10 | Solar | 07_797W24 | 2018-05-25 19:07 | 2018-05-29 | 5 | 0 | 5 | 2018-06-06 | 2018-07-06 | 21 | 0 | 21 | [20 empty] | 2018-07-30 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LAWRENCE | 184904 | 1843 | 7.6 | Solar | 14_8L1 | 2018-05-28 10:06 | 2018-05-29 | 1 | 0 | 1 | 2018-05-31 | 2018-05-31 | 8 | 0 | 8 | [20 empty] | 2018-10-17 |  | 2020-01-08 |  | EXP |  | 2019-10-24 | 2019-11-04 | 11 | 0 | 11 |  |  | 2019-11-20 | Connected |  | No
National Grid | WENHAM | 186491 | 1984 | 15.2 | Solar | 12_18L2 | 2018-05-29 10:48 | 2018-05-30 | 10 | 0 | 10 | 2018-06-13 | 2018-06-13 | 0 | 0 | 0 | [20 empty] | 2018-06-13 |  |  |  | EXP | [8 empty] | 2018-08-11 | Connected |  | Yes
National Grid | BROCKTON | 186523 | 2302 | 10 | Solar | 07_911W56 | 2018-05-29 12:05 | 2018-07-31 | 8 | 0 | 8 | 2018-08-10 | 2018-08-13 | 1 | 0 | 1 | [20 empty] | 2018-08-16 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | REHOBOTH | 178744 | 2769 | 726 | Solar | 05_7L5 | 2018-05-29 12:17 | 2018-06-28 | 1 | 1 | 0 | [10 empty] | 2018-06-29 | 2018-07-20 | 14 | 0 | 14 | [10 empty] | 2019-02-01 |  | 2020-05-15 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SOUTH LANCASTER | 186590 | 1561 | 15.2 | Solar | 01_216W4 | 2018-05-29 15:11 | 2018-05-30 | 8 | 0 | 8 | 2018-06-12 | 2018-06-12 | 1 | 0 | 1 | [20 empty] | 2018-08-15 |  |  |  | EXP | [8 empty] | 2019-11-08 | Connected |  | No
National Grid | OAKHAM | 186270 | 1068 | 4998 | Solar | 09_604W2 | 2018-05-29 17:58 | 2018-05-30 | 50 | 49 | 1 | [10 empty] | 2018-09-26 | 2018-10-12 | 12 | 0 | 12 | [5 empty] | 2020-07-10 | 2020-10-07 | 63 | 3 | 60 |  |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH DIGHTON | 185430 | 2764 | 4998 | Solar | 05_19W73 | 2018-05-29 20:31 | 2018-05-30 | 61 | 44 | 17 | [10 empty] | 2018-08-24 | 2018-09-21 | 19 | 0 | 19 | [12 empty] | 2019-10-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | PEPPERELL | 178743 | 1463 | 990 | Solar | 01_226L2 | 2018-05-30 | 2018-07-17 | 2 | 2 | 0 | [10 empty] | 2018-07-19 | 2018-08-01 | 10 | 2 | 8 | [11 empty] | 2018-05-30 | 2019-04-24 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | TYNGSBORO | 186708 | 1879 | 249.8 | Solar | 14_211L1 | 2018-05-30 | 2018-05-31 | 1 | 0 | 1 | 2018-06-04 | 2018-06-13 | 7 | 0 | 7 | [20 empty] | 2018-06-15 |  | 2020-10-30 |  | EXP |  | 2020-09-25 | 2020-09-24 | 0 | 0 | 0 |  |  | 2020-10-28 | Connected |  | No
National Grid | SALEM | 186728 | 1970 | 88 | Solar | 12_2370 | 2018-05-30 | 2018-06-01 | 0 | 0 | 0 | 2018-06-04 | 2018-07-03 | 21 | 0 | 21 | [20 empty] | 2018-07-10 |  | 2020-05-26 |  | EXP | [8 empty] | 2020-08-11 | Connected |  | No
National Grid | SHEFFIELD | 178745 | 1257 | 924 | Solar | 09_1108W2 | 2018-05-30 01:00 | 2018-07-19 | 0 | 0 | 0 | [10 empty] | 2018-07-19 | 2018-07-20 | 1 | 0 | 1 | [12 empty] | 2019-04-24 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LOWELL | 186665 | 1850 | 3.8 | Solar | 14_75L5 | 2018-05-30 10:07 | 2018-06-26 | 10 | 9 | 1 | 2018-07-11 | 2018-07-13 | 0 | 0 | 0 | [20 empty] | 2018-07-16 |  |  |  | EXP | [8 empty] | 2019-09-19 | Connected |  | No
National Grid | HEATH | 184696 | 1346 | 528 | Solar | 09_1019W1 | 2018-05-31 | 2018-05-10 | 15 | 0 | 15 | [10 empty] | 2018-07-12 | 2018-07-18 | 15 | 12 | 3 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTHBRIDGE | 184698 | 1534 | 594 | Solar | 05_321W5 | 2018-05-31 | 2018-07-24 | 6 | 2 | 4 | [10 empty] | 2018-08-01 | 2018-09-27 | 45 | 22 | 23 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SUTTON | 184748 | 1590 | 594 | Solar | 01_304W6 | 2018-05-31 | 2018-08-13 | 3 | 0 | 3 | [10 empty] | 2018-08-17 | 2018-08-22 | 4 | 2 | 2 | [10 empty] | 2019-07-15 |  | 2020-08-21 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | FLORIDA | 184798 | 1247 | 4648 | Solar | 09_1015W1 | 2018-05-31 | 2018-07-24 | 1 | 1 | 0 | [10 empty] | 2018-07-25 | 2018-07-27 | 2 | 0 | 2 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SALEM | 186726 | 1970 | 88 | Solar | 12_49W2 | 2018-05-31 | 2018-06-01 | 0 | 0 | 0 | 2018-06-04 | 2018-06-11 | 5 | 0 | 5 | [20 empty] | 2018-06-12 |  | 2020-05-26 |  | EXP | [8 empty] | 2020-06-09 | Connected |  | No
National Grid | WORCESTER | 184545 | 1602 | 7.6 | Solar | 01_23W3 | 2018-05-31 09:53 | 2018-06-01 | 3 | 0 | 3 | 2018-06-07 | 2018-06-07 | 0 | 0 | 0 | [20 empty] | 2018-07-26 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 186222 | 1841 | 100.8 | Solar | 14_2355 | 2018-05-31 12:20 | 2018-06-01 | 0 | 0 | 0 | 2018-06-04 | 2018-06-12 | 6 | 0 | 6 | [20 empty] | 2018-06-15 |  | 2020-03-11 |  | EXP | [8 empty] | 2020-03-05 | Connected |  | No
National Grid | SOUTH GRAFTON | 185413 | 1560 | 4998 | Solar |  | 2018-05-31 14:35 | 2018-06-01 | 738 | 37 | 701 | [29 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | ATHOL | 185368 | 1331 | 4998 | Solar | 09_1193W3 | 2018-05-31 14:45 | 2018-06-01 | 24 | 21 | 3 | [10 empty] | 2018-07-06 | 2018-10-12 | 69 | 26 | 43 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WINCHENDON | 186861 | 1475 | 4980 | Solar |  | 2018-05-31 19:54 | 2018-06-01 | 49 | 49 | 0 | [29 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BRIDGEWATER | 186863 | 2324 | 4998 | Solar | 07_797W1 | 2018-05-31 20:07 | 2018-06-01 | 47 | 4 | 43 | [10 empty] | 2018-08-08 | 2018-09-04 | 20 | 0 | 20 | [10 empty] | 2019-10-08 |  | 2020-11-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | PHILLIPSTON | 186877 | 1331 | 4998 | Solar |  | 2018-05-31 20:58 | 2018-06-01 | 739 | 54 | 685 | [29 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | DUDLEY | 186220 | 1571 | 250 | Solar |  | 2018-06-01 | 2018-06-06 | 3 | 0 | 3 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | MARLBOROUGH | 186922 | 1752 | 230 | Solar | 05_313W4 | 2018-06-01 | 2018-06-08 | 4 | 0 | 4 | 2018-06-15 | 2018-07-24 | 26 | 0 | 26 | [20 empty] | 2018-08-01 |  | 2020-12-17 |  | EXP | [8 empty] | 2020-12-01 | Connected |  | No
National Grid | WARREN | 186901 | 1083 | 4980 | Solar | 01_525L2 | 2018-06-01 10:53 | 2018-06-04 | 0 | 0 | 0 | [10 empty] | 2018-08-17 | 2018-08-17 | 0 | 0 | 0 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH QUINCY | 183802 | 2171 | 10 | Solar | 07_4J1 | 2018-06-01 13:32 | 2018-06-01 | 10 | 9 | 1 | 2018-06-15 | 2018-07-24 | 26 | 0 | 26 | [20 empty] | 2018-07-30 |  |  |  | EXP | [8 empty] | 2019-06-13 | Connected |  | No
National Grid | BELCHERTOWN | 185030 | 1007 | 1000 | Solar | 09_509L2 | 2018-06-04 | 2018-06-05 | 5 | 3 | 2 | [10 empty] | 2018-07-05 | 2018-07-03 | 0 | 0 | 0 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTMINSTER | 184587 | 1473 | 3000 | Solar | 01_602W3 | 2018-06-04 10:30 | 2018-06-05 | 11 | 0 | 11 | [10 empty] | 2018-06-20 | 2018-07-11 | 29 | 0 | 29 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | DRACUT | 187051 | 1826 | 9.92 | Solar | 14_75L1 | 2018-06-04 12:13 | 2018-06-05 | 8 | 0 | 8 | 2018-06-16 | 2018-06-19 | 2 | 0 | 2 | [20 empty] | 2018-06-20 |  |  |  | EXP | [8 empty] | 2019-05-01 | Connected |  | No
National Grid | METHUEN | 186476 | 1844 | 15.04 | Solar | 14_43L4 | 2018-06-04 15:27 | 2018-06-05 | 0 | 0 | 0 | 2018-06-05 | 2018-06-05 | 0 | 0 | 0 | [20 empty] | 2018-06-13 |  |  |  | EXP | [8 empty] | 2018-07-20 | Connected |  | No
National Grid | WEYMOUTH | 183596 | 2188 | 17.25 | Solar | 07_12W2 | 2018-06-04 16:41 | 2018-06-05 | 0 | 0 | 0 | 2018-06-06 | 2018-07-06 | 21 | 0 | 21 | [20 empty] | 2018-07-30 |  |  |  | EXP | [8 empty] | 2019-03-20 | Connected |  | No
National Grid | WORCESTER | 187209 | 1603 | 200 | Solar | 01_6J316 | 2018-06-05 | 2018-06-06 | 3 | 0 | 3 | [10 empty] | 2018-06-12 | 2018-07-17 | 24 | 0 | 24 | [10 empty] | 2018-07-17 | 2018-06-06 11:46 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | FLORENCE | 187299 | 1062 | 10 | Solar | 09_909W4 | 2018-06-06 11:46 | 2018-09-14 | 3 | 3 | 0 | 2018-09-19 | 2018-09-24 | 3 | 0 | 3 | [20 empty] | 2018-09-24 | 2018-06-06 13:03 | 2019-04-17 | Yes | EXP | [8 empty] | 2018-11-21 | Connected |  | Yes
National Grid | BEVERLY | 187345 | 1915 | 3.8 | Solar | 12_12L2 | 2018-06-06 13:03 | 2018-06-22 | 0 | 0 | 0 | 2018-06-25 | 2018-06-25 | 0 | 0 | 0 | [20 empty] | 2018-06-25 |  |  |  | EXP | [8 empty] | 2019-08-03 | Connected |  | No
National Grid | AVON | 184781 | 2322 | 18.9 | Solar | 07_75W3 | 2018-06-06 14:10 | 2018-05-24 | 48 | 35 | 13 | 2018-08-02 | 2018-08-15 | 9 | 0 | 9 | [20 empty] | 2018-08-15 |  |  |  | EXP | [8 empty] | 2019-07-15 | Connected |  | No
National Grid | WORCESTER | 186780 | 1610 | 788 | Solar | 01_HT15 | 2018-06-06 16:27 | 2018-06-07 | 9 | 6 | 3 | [10 empty] | 2018-06-13 | 2018-08-17 | 46 | 31 | 15 | [10 empty] | 2019-07-10 |  | 2020-12-25 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MENDON | 185870 | 1756 | 1000 | Solar | 05_335W1 | 2018-06-07 | 2018-06-08 | 732 | 0 | 732 | [29 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | LEEDS | 187389 | 1053 | 72 | Solar | 09_909W3 | 2018-06-07 | 2018-06-08 | 14 | 4 | 10 | 2018-06-28 | 2018-08-20 | 36 | 0 | 36 | [20 empty] | 2018-08-20 |  |  |  | EXP | [8 empty] | 2019-02-19 | Connected |  | No
National Grid | MARLBOROUGH | 186667 | 1752 | 7.6 | Solar | 05_311W4 | 2018-06-07 09:15 | 2018-06-08 | 4 | 0 | 4 | 2018-06-15 | 2018-07-25 | 30 | 0 | 30 | [20 empty] | 2018-08-03 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SALEM | 184469 | 1970 | 3.8 | Solar | 12_29W4 | 2018-06-07 09:44 | 2018-06-08 | 16 | 7 | 9 | 2018-06-29 | 2018-06-29 | 0 | 0 | 0 | [20 empty] | 2018-06-29 | 2018-06-07 11:31 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | DIGHTON | 170590 | 2715 | 15.4 | Solar | 05_19W73 | 2018-06-07 11:31 | 2018-06-14 | 8 | 8 | 0 | 2018-06-26 | 2018-07-30 | 23 | 0 | 23 | [20 empty] | 2018-08-03 |  | 2019-12-24 | Yes | EXP |  | 2019-07-06 | 2019-08-01 | 26 | 0 | 26 |  |  | 2019-12-11 | Connected |  | No
National Grid | ATHOL | 186829 | 1331 | 250 | Solar | 09_702W2 | 2018-06-07 13:25 | 2018-06-08 | 17 | 16 | 1 | 2018-07-10 | 2018-07-27 | 14 | 13 | 1 | [21 empty] | 2018-06-07 13:35 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MILLBURY | 186042 | 1527 | 3400 | Solar | 01_304W4 | 2018-06-07 13:35 | 2018-06-08 | 28 | 26 | 2 | [10 empty] | 2018-07-19 | 2018-07-30 | 8 | 7 | 1 | [10 empty] | 2019-12-12 |  | 2023-08-04 | Yes | STD |  | 2022-04-02 | 2023-01-13 | 287 | 0 | 287 | 2023-06-07 | 2023-06-07 | 2023-07-25 | Connected |  | No
National Grid | FOXBOROUGH | 184044 | 2035 | 292 | Natural Gas | 05_3431W2 | 2018-06-07 23:01 | 2018-06-08 | 8 | 0 | 8 | [10 empty] | 2018-06-20 | 2018-08-13 | 37 | 29 | 8 | [10 empty] | 2019-03-01 |  | 2020-03-31 |  | STD | [6 empty] | 2020-03-31 | 2020-03-31 | 2020-03-30 | Connected |  | No
National Grid | BELLINGHAM | 187511 | 2019 | 15.2 | Solar |  | 2018-06-08 09:22 | 2018-06-11 | 4 | 0 | 4 | 2018-06-18 | 2018-06-26 | 6 | 0 | 6 | [20 empty] | 2018-06-25 |  | 2020-06-08 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WRENTHAM | 185160 | 2093 | 10.56 | Solar | 05_3422W1 | 2018-06-08 10:20 | 2018-05-17 | 18 | 7 | 11 | 2018-06-13 | 2018-07-09 | 17 | 0 | 17 | [20 empty] | 2018-07-23 |  |  |  | EXP | [8 empty] | 2018-12-27 | Connected |  | No
National Grid | NORTON | 185888 | 2766 | 9.6 | Solar | 05_8L2 | 2018-06-08 10:43 | 2018-06-12 | 25 | 14 | 11 | 2018-07-18 | 2018-08-01 | 10 | 0 | 10 | [20 empty] | 2018-08-01 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 187541 | 1844 | 11.4 | Solar | 14_74L1 | 2018-06-08 11:06 | 2018-06-11 | 10 | 0 | 10 | 2018-06-25 | 2018-06-25 | 0 | 0 | 0 | [20 empty] | 2018-06-26 |  | 2020-06-08 |  | EXP | [8 empty] | 2020-06-05 | Connected |  | No
National Grid | CLINTON | 187526 | 1510 | 149.9 | Solar | 01_216W2 | 2018-06-08 11:41 | 2018-06-11 | 0 | 0 | 0 | [25 empty] | 2018-07-17 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | EAST LONGMEADOW | 187558 | 1028 | 15.2 | Solar | 09_508L1 | 2018-06-08 12:42 | 2018-06-11 | 18 | 10 | 8 | 2018-07-06 | 2018-07-06 | 0 | 0 | 0 | [20 empty] | 2018-12-14 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | TYNGSBOROUGH | 187599 | 1879 | 240 | Solar | 14_211L2 | 2018-06-08 17:32 | 2018-06-18 | 3 | 0 | 3 | 2018-06-22 | 2018-06-25 | 1 | 0 | 1 | [20 empty] | 2018-07-11 |  |  |  | EXP | [8 empty] | 2019-08-14 | Connected |  | No
National Grid | REHOBOTH | 187621 | 2769 | 4998 | Solar | 05_7L5 | 2018-06-10 00:27 | 2018-06-11 | 57 | 3 | 54 | [10 empty] | 2018-08-30 | 2018-09-27 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WARREN | 187500 | 1083 | 4998 | Solar | 09_516L3 | 2018-06-10 00:33 | 2018-06-11 | 27 | 19 | 8 | [10 empty] | 2018-07-18 | 2018-10-12 | 62 | 28 | 34 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | DOUGLAS | 187549 | 1516 | 2500 | Solar |  | 2018-06-10 00:59 | 2018-06-11 | 37 | 0 | 37 | [10 empty] | 2018-08-03 | 2019-10-15 | 300 | 0 | 300 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | MENDON | 186842 | 1756 | 2875 | Solar | 05_332W1 | 2018-06-11 | 2018-06-14 | 22 | 0 | 22 | [10 empty] | 2018-07-18 | 2018-08-28 | 30 | 5 | 25 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | LOWELL | 184905 | 1851 | 7.6 | Solar | 14_2L2 | 2018-06-11 10:15 | 2018-06-12 | 1 | 0 | 1 | 2018-06-13 | 2018-06-19 | 4 | 0 | 4 | [20 empty] | 2018-06-20 |  | 2020-06-11 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | EAST LONGMEADOW | 187656 | 1028 | 7.6 | Solar | 09_508L1 | 2018-06-11 10:34 | 2018-07-12 | 0 | 0 | 0 | 2018-07-13 | 2018-07-16 | 1 | 0 | 1 | [20 empty] | 2018-07-24 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHESHIRE | 187314 | 1225 | 3.36 | Solar | 09_1021W2 | 2018-06-11 10:55 | 2018-07-24 | 10 | 0 | 10 | 2018-08-07 | 2018-09-17 | 28 | 0 | 28 | [20 empty] | 2018-08-24 |  |  |  | EXP | [8 empty] | 2018-11-13 | Connected |  | No
National Grid | LEICESTER | 187430 | 1524 | 4998 | Solar | 01_2236W2 | 2018-06-11 12:06 | 2018-07-05 | 0 | 0 | 0 | [10 empty] | 2018-07-06 | 2018-07-18 | 9 | 8 | 1 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | FRANKLIN | 187501 | 2038 | 2500 | Solar | 05_348W5 | 2018-06-11 13:24 | 2018-06-29 | 39 | 37 | 2 | [10 empty] | 2018-08-24 | 2018-09-21 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | ATTLEBORO | 184255 | 2703 | 7.6 | Solar | 05_9L1 | 2018-06-11 13:46 | 2018-06-12 | 13 | 3 | 10 | 2018-06-28 | 2018-06-29 | 1 | 0 | 1 | [20 empty] | 2018-07-13 |  |  |  | EXP | [8 empty] | 2018-11-26 | Connected |  | Yes
National Grid | BELCHERTOWN | 184809 | 1007 | 990 | Solar | 09_523L2 | 2018-06-12 | 2018-08-20 | 28 | 1 | 27 | [29 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | HAVERHILL | 187781 | 1832 | 179.9 | Solar | 14_48L1 | 2018-06-12 | 2018-06-13 | 1 | 0 | 1 | 2018-06-14 | 2018-06-19 | 3 | 0 | 3 | [20 empty] | 2018-06-20 |  | 2019-11-28 |  | EXP | [8 empty] | 2019-12-20 | Connected |  | No
National Grid | ORANGE | 187787 | 1364 | 15.2 | Solar | 09_702W2 | 2018-06-12 09:10 | 2018-06-13 | 54 | 51 | 3 | 2018-08-28 | 2018-08-28 | 0 | 0 | 0 | [20 empty] | 2018-10-26 |  | 2019-10-18 |  | EXP | [8 empty] | 2019-09-13 | Connected |  | No
National Grid | RANDOLPH | 187799 | 2368 | 15.2 | Solar | 07_97W2 | 2018-06-12 09:52 | 2018-06-13 | 12 | 0 | 12 | 2018-06-22 | 2018-07-26 | 25 | 0 | 25 | [20 empty] | 2018-08-03 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHESHIRE | 184852 | 1225 | 1320 | Solar | 09_1021W2 | 2018-06-13 | 2018-08-20 | 257 | 6 | 251 | [10 empty] | 2018-10-04 | 2018-10-03 | 0 | 0 | 0 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | AVON | 187901 | 2322 | 240 | Solar | 07_75W5 | 2018-06-13 | 2018-07-23 | 10 | 7 | 3 | 2018-08-06 | 2018-09-07 | 23 | 0 | 23 | [20 empty] | 2018-09-10 | 2018-06-13 | 2020-02-29 |  | EXP | [8 empty] | 2020-02-13 | Connected |  | No
National Grid | AMESBURY | 187940 | 1913 | 999.9 | Solar | 14_275L4 | 2018-06-13 | 2018-07-03 | 4 | 3 | 1 | [10 empty] | 2018-07-10 | 2018-08-19 | 29 | 10 | 19 | [10 empty] | 2019-05-28 |  | 2021-05-17 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ADAMS | 187941 | 1220 | 7.6 | Solar | 09_1021W2 | 2018-06-13 08:24 | 2018-06-28 | 17 | 13 | 4 | 2018-07-24 | 2018-07-27 | 3 | 0 | 3 | [20 empty] | 2018-08-03 | 2018-06-13 10:39 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LYNN | 185702 | 1904 | 7.6 | Solar | 12_29W4 | 2018-06-13 10:39 | 2018-06-14 | 30 | 25 | 5 | 2018-07-27 | 2018-07-31 | 2 | 0 | 2 | [20 empty] | 2018-07-31 |  | 2019-09-20 | Yes | EXP |  | 2019-05-17 | 2019-05-16 | 0 | 0 | 0 |  |  | 2019-08-27 | Connected |  | No
National Grid | WORCESTER | 186320 | 1602 | 3.8 | Solar | 01_23W3 | 2018-06-13 10:49 | 2018-06-14 | 28 | 0 | 28 | 2018-07-26 | 2018-07-26 | 0 | 0 | 0 | [20 empty] | 2018-12-04 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BELLINGHAM | 186502 | 2019 | 10 | Solar | 05_344W4 | 2018-06-13 10:50 | 2018-06-14 | 7 | 0 | 7 | 2018-06-26 | 2018-07-30 | 23 | 0 | 23 | [20 empty] | 2018-08-03 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BEVERLY | 187972 | 1915 | 15.2 | Solar | 12_12L2 | 2018-06-13 10:59 | 2018-06-14 | 10 | 2 | 8 | 2018-06-28 | 2018-06-29 | 1 | 0 | 1 | [20 empty] | 2018-06-29 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | UPTON | 186263 | 1568 | 17.6 | Solar | 05_320W1 | 2018-06-13 13:35 | 2018-06-14 | 12 | 6 | 6 | 2018-07-02 | 2018-07-02 | 0 | 0 | 0 | [20 empty] | 2018-07-30 | 2018-06-13 14:04 |  |  | EXP | [8 empty] | 2018-10-09 | Connected |  | Yes
National Grid | LEOMINSTER | 187836 | 1453 | 9.84 | Solar | 01_207W6 | 2018-06-13 14:04 | 2018-06-14 | 10 | 5 | 5 | 2018-06-28 | 2018-07-27 | 20 | 0 | 20 | [20 empty] | 2018-08-01 |  | 2019-08-30 | Yes | EXP |  | 2019-03-09 | 2019-03-08 | 0 | 0 | 0 |  |  | 2019-08-10 | Connected |  | No
National Grid | LANCASTER | 188006 | 1523 | 11.4 | Solar | 01_227W1 | 2018-06-13 14:24 | 2018-06-14 | 4 | 0 | 4 | 2018-06-21 | 2018-07-20 | 20 | 0 | 20 | [20 empty] | 2018-07-27 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | ATHOL | 188028 | 1331 | 5000 | Solar | 09_702W1 | 2018-06-13 16:54 | 2018-06-14 | 21 | 21 | 0 | [10 empty] | 2018-07-16 | 2018-08-15 | 23 | 16 | 7 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WRENTHAM | 188112 | 2093 | 302.4 | Solar | 05_3422W2 | 2018-06-14 14:18 | 2018-06-28 | 10 | 10 | 0 | [10 empty] | 2018-07-13 | 2018-09-20 | 49 | 25 | 24 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | DRACUT | 188124 | 1826 | 15.2 | Solar | 14_78L1 | 2018-06-14 14:38 | 2018-06-15 | 1 | 0 | 1 | 2018-06-18 | 2018-07-11 | 16 | 0 | 16 | [20 empty] | 2018-07-19 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WRENTHAM | 188139 | 2093 | 259.2 | Solar | 05_3422W1 | 2018-06-14 14:53 | 2018-06-28 | 10 | 10 | 0 | [10 empty] | 2018-07-13 | 2018-09-20 | 49 | 25 | 24 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | EAST LONGMEADOW | 188147 | 1028 | 7.6 | Solar | 09_139L5 | 2018-06-14 15:19 | 2018-09-11 | 3 | 3 | 0 | 2018-09-14 | 2018-09-20 | 4 | 0 | 4 | [20 empty] | 2018-09-20 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEST NEWBURY | 188160 | 1985 | 15.2 | Solar | 14_47L1 | 2018-06-14 16:53 | 2018-06-15 | 5 | 0 | 5 | 2018-06-25 | 2018-07-02 | 5 | 0 | 5 | [20 empty] | 2018-06-26 | 2018-06-14 17:01 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEST BRIDGEWATER | 188061 | 2379 | 1400 | Solar | 07_98W44 | 2018-06-14 17:01 | 2018-06-15 | 10 | 9 | 1 | [10 empty] | 2018-06-29 | 2018-08-03 | 24 | 0 | 24 | [10 empty] | 2018-12-12 |  | 2022-11-29 | Yes | STD |  | 2021-06-05 | 2021-09-23 | 111 | 3 | 108 |  |  | 2022-10-18 | Connected |  | No
National Grid | MILFORD | 188185 | 1757 | 249.8 | Solar | 05_336W1 | 2018-06-15 | 2018-06-20 | 7 | 0 | 7 | 2018-07-02 | 2018-07-30 | 20 | 19 | 1 | 2018-08-03 | 2018-11-01 | 63 | 43 | 20 | [5 empty] | 2018-08-03 | 2018-11-01 | 63 | 43 | 20 | [5 empty] | 2018-11-21 |  | 2020-04-14 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | HAVERHILL | 188201 | 1830 | 150 | Solar | 14_48L2 | 2018-06-15 | 2018-06-18 | 3 | 0 | 3 | 2018-06-22 | 2018-06-25 | 1 | 0 | 1 | [20 empty] | 2018-06-26 |  | 2019-12-02 |  | EXP | [8 empty] | 2019-10-29 | Connected |  | No
National Grid | WHITMAN | 188219 | 2382 | 249.8 | Solar | 07_93W43 | 2018-06-15 | 2018-06-20 | 7 | 0 | 7 | 2018-07-02 | 2018-07-03 | 1 | 0 | 1 | [20 empty] | 2018-07-30 |  | 2020-06-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WRENTHAM | 188212 | 2093 | 172.8 | Solar | 05_3422W1 | 2018-06-15 10:49 | 2018-06-18 | 19 | 2 | 17 | [10 empty] | 2018-07-16 | 2018-09-20 | 47 | 24 | 23 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | GLOUCESTER | 186691 | 1930 | 6 | Solar | 12_51T3 | 2018-06-15 10:52 | 2018-06-18 | 9 | 5 | 4 | 2018-06-29 | 2018-07-09 | 5 | 0 | 5 | [20 empty] | 2018-06-29 |  | 2019-05-30 |  | EXP | [8 empty] | 2018-11-16 | Connected |  | Yes
National Grid | EAST LONGMEADOW | 186850 | 1028 | 7.6 | Solar | 09_139L5 | 2018-06-15 10:53 | 2018-06-18 | 20 | 17 | 3 | 2018-07-17 | 2018-07-26 | 7 | 0 | 7 | [20 empty] | 2018-11-15 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WRENTHAM | 188144 | 2093 | 345.6 | Solar | 05_3422W1 | 2018-06-15 10:54 | 2018-06-28 | 11 | 11 | 0 | [10 empty] | 2018-07-16 | 2018-09-20 | 47 | 24 | 23 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WRENTHAM | 188150 | 2093 | 172.8 | Solar | 05_3422W1 | 2018-06-15 10:54 | 2018-06-18 | 18 | 1 | 17 | [10 empty] | 2018-07-13 | 2018-09-20 | 48 | 25 | 23 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WRENTHAM | 188233 | 2093 | 302.4 | Solar | 05_3422W2 | 2018-06-15 12:03 | 2018-06-28 | 10 | 10 | 0 | [10 empty] | 2018-07-13 | 2018-09-15 | 45 | 25 | 20 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WRENTHAM | 188239 | 2093 | 259.2 | Solar | 05_3422W2 | 2018-06-15 12:12 | 2018-06-28 | 11 | 11 | 0 | [10 empty] | 2018-07-16 | 2018-09-20 | 48 | 25 | 23 | [11 empty] | 2018-06-15 14:07 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | EAST LONGMEADOW | 188034 | 1028 | 3.8 | Solar | 09_139L5 | 2018-06-15 14:07 | 2018-06-18 | 2 | 0 | 2 | 2018-07-03 | 2018-07-05 | 2 | 0 | 2 | [20 empty] | 2018-08-10 | 2018-06-15 16:12 | 2020-03-04 | Yes | EXP |  | 2019-10-17 | 2019-10-30 | 13 | 0 | 13 |  |  | 2019-10-31 | Connected |  | No
National Grid | TYNGSBORO | 185409 | 1879 | 4999 | Solar | 14_211L1 | 2018-06-15 16:12 | 2018-06-18 | 32 | 32 | 0 | [10 empty] | 2018-08-02 | 2018-08-17 | 12 | 12 | 0 | [10 empty] | 2019-01-25 |  | 2021-08-06 | Yes | STD |  | 2020-03-04 | 2021-05-27 | 450 | 5 | 445 |  |  | 2021-08-02 | Connected |  | No
National Grid | WRENTHAM | 188280 | 2093 | 259.2 | Solar | 05_3422W2 | 2018-06-15 17:44 | 2018-06-28 | 10 | 10 | 0 | [10 empty] | 2018-07-13 | 2018-09-20 | 49 | 25 | 24 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | FRANKLIN | 187783 | 2038 | 180 | Solar | 05_344W5 | 2018-06-17 | 2018-06-19 | 5 | 0 | 5 | 2018-06-29 | 2019-08-22 | 289 | 70 | 219 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WRENTHAM | 188300 | 2093 | 259.2 | Solar | 05_3422W2 | 2018-06-18 06:16 | 2018-06-28 | 11 | 11 | 0 | [10 empty] | 2018-07-16 | 2018-09-20 | 47 | 24 | 23 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WRENTHAM | 188301 | 2093 | 302.4 | Solar | 05_3422W1 | 2018-06-18 06:30 | 2018-06-28 | 10 | 10 | 0 | [10 empty] | 2018-07-13 | 2018-09-20 | 48 | 25 | 23 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WRENTHAM | 188303 | 2093 | 172.8 | Solar | 05_3422W1 | 2018-06-18 06:46 | 2018-06-28 | 6 | 5 | 1 | [10 empty] | 2018-07-09 | 2018-07-24 | 11 | 0 | 11 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WRENTHAM | 188304 | 2093 | 302.4 | Solar | 05_3422W1 | 2018-06-18 06:56 | 2018-06-28 | 13 | 13 | 0 | [10 empty] | 2018-07-18 | 2018-09-20 | 46 | 25 | 21 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WRENTHAM | 188306 | 2093 | 259.2 | Solar | 05_3422W1 | 2018-06-18 07:11 | 2018-06-28 | 11 | 11 | 0 | [10 empty] | 2018-07-16 | 2018-09-20 | 48 | 25 | 23 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 188327 | 1844 | 7.6 | Solar | 14_63L2 | 2018-06-18 09:12 | 2018-06-19 | 7 | 3 | 4 | 2018-06-28 | 2018-06-29 | 1 | 0 | 1 | [20 empty] | 2018-06-29 |  |  |  | EXP | [8 empty] | 2019-05-14 | Connected |  | No
National Grid | SOUTH HAMILTON | 184467 | 1982 | 51.75 | Solar | 12_51L3 | 2018-06-18 09:43 | 2018-06-18 | 0 | 0 | 0 | 2018-06-22 | 2018-06-27 | 3 | 0 | 3 | [20 empty] | 2018-06-27 |  | 2019-10-07 |  | EXP | [8 empty] | 2019-04-17 | Connected |  | No
National Grid | PEPPERELL | 188134 | 1463 | 1000 | Solar | 01_226L1 | 2018-06-18 09:46 | 2018-06-19 | 23 | 23 | 0 | [10 empty] | 2018-07-23 | 2018-07-24 | 1 | 0 | 1 | [10 empty] | 2019-09-27 |  | 2020-09-03 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MONSON | 185764 | 1057 | 4990 | Solar | 09_503L2 | 2018-06-18 10:41 | 2018-06-18 | 13 | 13 | 0 | [10 empty] | 2019-02-27 | 2019-03-23 | 18 | 0 | 18 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | RANDOLPH | 186757 | 2368 | 7.6 | Solar | 07_5W3 | 2018-06-18 10:53 | 2018-06-19 | 9 | 2 | 7 | 2018-07-02 | 2018-07-02 | 0 | 0 | 0 | [20 empty] | 2018-07-13 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ATHOL | 188362 | 1331 | 8300 | Solar | 09_702W2 | 2018-06-18 12:23 | 2018-06-19 | 30 | 30 | 0 | [10 empty] | 2018-08-01 | 2018-08-17 | 13 | 12 | 1 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | MALDEN | 188457 | 2148 | 9.92 | Solar | 12_16W1 | 2018-06-18 18:00 | 2018-07-25 | 21 | 21 | 0 | 2018-08-22 | 2018-08-22 | 0 | 0 | 0 | [20 empty] | 2018-08-22 |  | 2019-11-15 |  | EXP | [8 empty] | 2019-10-06 | Connected |  | No
National Grid | SAUGUS | 188535 | 1906 | 3.8 | Solar | 12_13J3 | 2018-06-19 15:02 | 2018-06-20 | 1 | 0 | 1 | 2018-06-22 | 2018-06-22 | 0 | 0 | 0 | [20 empty] | 2018-06-24 |  | 2021-09-22 |  | EXP | [8 empty] | 2021-07-28 | Connected |  | No
National Grid | ATTLEBORO | 188562 | 2703 | 15.2 | Solar | 05_1J4 | 2018-06-19 17:02 | 2018-06-26 | 2 | 0 | 2 | 2018-06-29 | 2018-07-19 | 13 | 0 | 13 | [20 empty] | 2019-02-12 |  |  |  | EXP | [8 empty] | 2019-11-28 | Connected |  | No
National Grid | DIGHTON | 188745 | 2715 | 129.6 | Solar | 05_19W73 | 2018-06-20 | 2018-08-08 | 10 | 0 | 10 | 2018-08-21 | 2018-08-22 | 32 | 31 | 1 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ANDOVER | 186432 | 1810 | 20 | Solar | 14_62L2 | 2018-06-20 10:50 | 2018-06-21 | 42 | 35 | 7 | 2018-08-21 | 2018-09-25 | 24 | 0 | 24 | [20 empty] | 2018-08-22 | 2018-06-20 10:54 |  |  | EXP | [8 empty] | 2019-03-22 | Connected |  | No
National Grid | ORANGE | 186988 | 1364 | 6 | Solar | 09_705W2 | 2018-06-20 10:54 | 2018-06-21 | 4 | 0 | 4 | 2018-06-28 | 2018-06-29 | 1 | 0 | 1 | [20 empty] | 2018-08-28 | 2018-06-20 14:09 |  | Yes | EXP | [8 empty] | 2019-06-11 | Connected |  | No
National Grid | BLACKSTONE | 186698 | 1504 | 4560 | Solar | 05_332W1 | 2018-06-20 14:09 | 2018-06-21 | 9 | 6 | 3 | [10 empty] | 2018-07-05 | 2018-08-08 | 25 | 6 | 19 | [10 empty] | 2019-01-30 |  | 2024-05-20 | Yes | STD |  | 2023-01-14 |  | 458 | 249 | 209 |  |  |  | Construction |  | No
National Grid | CHARLTON | 188710 | 1507 | 250 | Solar | 01_415L2 | 2018-06-20 16:44 | 2018-06-21 | 4 | 0 | 4 | 2018-06-28 | 2018-10-23 | 0 | 0 | 0 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | WARE | 188725 | 1082 | 15.2 | Solar | 09_501L2 | 2018-06-20 17:30 | 2018-06-21 | 4 | 0 | 4 | 2018-06-28 | 2018-06-28 | 0 | 0 | 0 | [20 empty] | 2018-11-16 |  | 2019-09-20 |  | EXP | [8 empty] | 2019-09-03 | Connected |  | No
National Grid | RANDOLPH | 188743 | 2368 | 7.6 | Solar | 07_5W3 | 2018-06-20 20:33 | 2018-06-29 | 10 | 8 | 2 | 2018-07-16 | 2018-07-18 | 2 | 0 | 2 | [20 empty] | 2018-07-23 |  |  |  | EXP |  | 2019-04-24 | 2019-05-08 | 14 | 0 | 14 |  |  | 2019-10-28 | Connected |  | No
National Grid | BROCKTON | 184909 | 2302 | 125 | Natural Gas | 07_91W46 | 2018-06-21 | 2018-06-28 | 15 | 12 | 3 | 2018-07-20 | 2018-09-13 | 39 | 17 | 22 | 2018-10-12 | 2018-11-21 | 28 | 21 | 7 | [5 empty] | 2018-10-12 | 2018-11-21 | 28 | 21 | 7 | [5 empty] | 2018-12-06 |  | 2019-06-07 |  | EXP | [8 empty] | 2019-07-17 | Connected |  | No
National Grid | BRIDGEWATER | 188766 | 2324 | 200 | Solar | 07_797W1 | 2018-06-21 | 2018-06-26 | 3 | 0 | 3 | 2018-07-02 | 2018-08-13 | 30 | 6 | 24 | [20 empty] | 2018-08-22 | 2018-06-21 12:51 |  |  | EXP | [8 empty] | 2019-03-11 | Connected |  | No
National Grid | LOWELL | 188816 | 1854 | 10 | Solar | 14_77L3 | 2018-06-21 12:51 | 2018-07-06 | 2 | 0 | 2 | 2018-07-11 | 2018-07-23 | 14 | 0 | 14 | [20 empty] | 2018-07-26 |  | 2020-07-22 | Yes | EXP |  | 2019-10-04 | 2019-10-22 | 18 | 0 | 18 |  |  | 2020-07-03 | Connected |  | No
National Grid | GRANBY | 188659 | 1033 | 2376 | Solar | 09_527L1 | 2018-06-21 13:56 | 2018-08-29 | 12 | 0 | 12 | [10 empty] | 2018-09-18 | 2018-11-08 | 78 | 27 | 51 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | GRANBY | 188660 | 1033 | 240 | Solar | 09_527L1 | 2018-06-21 13:58 | 2018-06-22 | 60 | 31 | 29 | [10 empty] | 2018-09-18 | 2018-11-08 | 77 | 26 | 51 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | GRANBY | 188676 | 1033 | 470 | Solar | 09_527L1 | 2018-06-21 13:59 | 2018-06-22 | 13 | 0 | 13 | [10 empty] | 2018-11-07 | 2018-11-08 | 43 | 3 | 40 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | GRANBY | 188688 | 1033 | 456 | Solar | 09_527L1 | 2018-06-21 14:22 | 2018-06-22 | 63 | 44 | 19 | [29 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SALEM | 188870 | 1970 | 3.8 | Solar | 12_2W1 | 2018-06-21 16:38 | 2018-07-23 | 3 | 0 | 3 | 2018-07-27 | 2018-07-27 | 2 | 0 | 2 | [20 empty] | 2018-07-31 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SOUTH HAMILTON | 184417 | 1982 | 24 | Solar | 12_51L3 | 2018-06-22 09:42 | 2018-06-25 | 2 | 2 | 0 | 2018-06-27 | 2018-06-28 | 1 | 0 | 1 | [20 empty] | 2018-07-06 |  | 2019-11-01 |  | EXP | [8 empty] | 2019-10-29 | Connected |  | No
National Grid | SALEM | 186574 | 1970 | 3.8 | Solar | 12_2W1 | 2018-06-22 10:51 | 2018-06-25 | 2 | 1 | 1 | 2018-06-27 | 2018-06-28 | 1 | 0 | 1 | [20 empty] | 2018-06-28 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SALEM | 187385 | 1970 | 3.8 | Solar | 12_2W1 | 2018-06-22 10:56 | 2018-06-25 | 7 | 4 | 3 | 2018-06-28 | 2018-06-28 | 1 | 0 | 1 | [20 empty] | 2018-07-02 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LAWRENCE | 186700 | 1840 | 15.2 | Solar | 14_2J4 | 2018-06-22 12:20 | 2018-06-25 | 0 | 0 | 0 | 2018-06-25 | 2018-07-10 | 11 | 10 | 1 | [20 empty] | 2018-07-12 |  |  |  | EXP | [8 empty] | 2018-11-07 | Connected |  | No
National Grid | FLORIDA | 186395 | 1247 | 4625 | Solar | 09_1015W1 | 2018-06-22 15:32 | 2018-06-25 | 60 | 41 | 19 | [10 empty] | 2018-09-18 | 2018-10-10 | 16 | 10 | 6 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | NEW MARLBOROUGH | 185701 | 1244 | 5000 | Solar | 09_1108W2 | 2018-06-25 | 2018-06-28 | 9 | 0 | 9 | [10 empty] | 2018-07-13 | 2018-07-26 | 10 | 8 | 2 | [11 empty] | 2018-06-25 11:23 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LYNN | 187782 | 1902 | 7.6 | Solar | 12_29W4 | 2018-06-25 11:23 | 2018-06-27 | 27 | 26 | 1 | 2018-08-06 | 2018-08-09 | 3 | 0 | 3 | [20 empty] | 2018-08-09 | 2018-06-25 13:27 |  | Yes | EXP |  | 2018-12-27 | 2019-01-03 | 7 | 0 | 7 |  |  | 2019-05-10 | Connected |  | No
National Grid | WEST NEWBURY | 183620 | 1985 | 15.2 | Solar | 14_47L1 | 2018-06-25 13:27 | 2018-06-26 | 0 | 0 | 0 | 2018-06-27 | 2018-06-27 | 0 | 0 | 0 | [20 empty] | 2018-06-27 |  |  | Yes | EXP | [8 empty] | 2019-11-14 | Connected |  | No
National Grid | BELLINGHAM | 187518 | 2019 | 3.8 | Solar | 05_344W4 | 2018-06-25 14:02 | 2018-06-28 | 1 | 0 | 1 | 2018-07-02 | 2018-07-05 | 25 | 0 | 25 | [20 empty] | 2018-07-05 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 187893 | 2302 | 11.4 | Solar | 07_91W43 | 2018-06-25 14:05 | 2018-06-26 | 3 | 0 | 3 | 2018-07-02 | 2018-07-05 | 2 | 0 | 2 | [20 empty] | 2018-07-18 |  | 2020-01-27 |  | EXP | [8 empty] | 2020-01-03 | Connected |  | No
National Grid | MARLBOROUGH | 186377 | 1752 | 740 | Solar | 05_310W6 | 2018-06-25 15:37 | 2018-06-26 | 38 | 28 | 10 | 2018-08-20 | 2018-09-17 | 19 | 0 | 19 | [20 empty] | 2018-10-10 |  | 2020-12-31 |  | EXP | [8 empty] | 2020-12-23 | Connected |  | No
National Grid | MONSON | 189080 | 1057 | 200 | Solar | 01_304W4 | 2018-06-25 17:42 | 2018-06-26 | 1 | 0 | 1 | 2018-06-28 | 2018-07-31 | 22 | 0 | 22 | [21 empty] | 2018-06-26 10:24 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | GRAFTON | 185476 | 1519 | 6 | Solar | 01_304W2 | 2018-06-26 10:24 | 2018-06-27 | 5 | 2 | 3 | 2018-07-05 | 2018-07-20 | 11 | 0 | 11 | [20 empty] | 2018-07-23 |  | 2019-07-01 | Yes | EXP |  | 2019-04-10 | 2019-04-18 | 8 | 0 | 8 |  |  | 2019-06-20 | Connected |  | No
National Grid | GRAFTON | 185479 | 1519 | 5 | Solar | 01_304W2 | 2018-06-26 10:25 | 2018-06-27 | 11 | 7 | 4 | 2018-07-13 | 2018-07-16 | 2 | 1 | 1 | [20 empty] | 2018-07-20 |  |  |  | EXP | [8 empty] | 2019-10-05 | Connected |  | No
National Grid | BELCHERTOWN | 187670 | 1007 | 1350 | Solar | 09_523L1 | 2018-06-26 11:21 | 2018-06-27 | 2 | 0 | 2 | [10 empty] | 2018-06-29 | 2018-07-06 | 4 | 0 | 4 | [10 empty] | 2019-09-20 |  | 2021-06-23 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTBOROUGH | 189184 | 1581 | 15.2 | Solar | 05_314W3 | 2018-06-26 11:47 | 2018-06-29 | 15 | 9 | 6 | 2018-07-23 | 2018-07-26 | 3 | 0 | 3 | [20 empty] | 2018-08-15 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SAUGUS | 173305 | 1906 | 3.8 | Solar | 12_13J3 | 2018-06-26 11:48 | 2018-06-27 | 12 | 8 | 4 | 2018-07-13 | 2018-07-13 | 0 | 0 | 0 | [20 empty] | 2018-07-16 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | PALMER | 189148 | 1069 | 200 | Solar | 01_304W4 | 2018-06-26 12:40 | 2018-06-27 | 0 | 0 | 0 | 2018-06-28 | 2018-07-31 | 22 | 0 | 22 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | MONSON | 189157 | 1057 | 200 | Solar | 01_304W4 | 2018-06-26 12:43 | 2018-06-27 | 0 | 0 | 0 | 2018-06-28 | 2018-07-31 | 22 | 0 | 22 | [21 empty] | 2018-06-26 13:17 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | REVERE | 189054 | 2151 | 10 | Solar | 12_16W4 | 2018-06-26 13:17 | 2018-08-01 | 3 | 1 | 2 | 2018-08-06 | 2018-08-09 | 3 | 0 | 3 | [20 empty] | 2018-08-09 |  | 2020-06-26 | Yes | EXP |  | 2020-05-07 | 2020-05-18 | 9 | 0 | 9 |  |  | 2020-06-03 | Connected |  | No
National Grid | SPENCER | 189203 | 1562 | 3.8 | Solar | 01_552L1 | 2018-06-26 13:23 | 2018-07-11 | 24 | 0 | 24 | 2018-08-15 | 2018-08-15 | 0 | 0 | 0 | [20 empty] | 2018-12-21 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | REVERE | 189147 | 2151 | 10 | Solar | 12_16W4 | 2018-06-26 13:26 | 2018-09-06 | 6 | 1 | 5 | 2018-09-14 | 2018-09-17 | 1 | 0 | 1 | [20 empty] | 2018-10-11 |  |  |  | EXP | [8 empty] | 2018-12-07 | Connected |  | No
National Grid | SOUTHBOROUGH | 187658 | 1772 | 100 | Solar | 05_314W2 | 2018-06-26 13:58 | 2018-06-29 | 0 | 0 | 0 | 2018-07-02 | 2018-08-03 | 153 | 22 | 131 | 2018-08-15 | 2018-10-11 | 40 | 18 | 22 | [5 empty] | 2018-08-15 | 2018-10-11 | 40 | 18 | 22 | [9 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | UXBRIDGE | 188595 | 1569 | 2178 | Solar | 05_321W9 | 2018-06-26 14:10 | 2018-06-27 | 15 | 2 | 13 | [10 empty] | 2018-07-19 | 2020-02-21 | 173 | 0 | 173 | [10 empty] | 2019-07-05 |  | 2020-07-31 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | MENDON | 189220 | 1756 | 19 | Battery Add-On | 05_321W6 | 2018-06-26 15:55 | 2018-07-19 | 25 | 0 | 25 | 2018-08-24 | 2018-08-24 | 0 | 0 | 0 | [20 empty] | 2018-08-27 |  |  |  | EXP | [8 empty] | 2019-08-21 | Connected |  | No
National Grid | NORTH ANDOVER | 189257 | 1845 | 15.2 | Solar | 14_56L2 | 2018-06-26 16:03 | 2018-06-27 | 0 | 0 | 0 | 2018-06-28 | 2018-06-28 | 0 | 0 | 0 | [20 empty] | 2018-07-02 | 2018-06-26 16:36 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 189268 | 1604 | 15.2 | Solar | 01_27W1 | 2018-06-26 16:36 | 2018-06-27 | 0 | 0 | 0 | 2018-06-28 | 2018-06-28 | 0 | 0 | 0 | [20 empty] | 2018-08-27 |  | 2019-10-13 | Yes | EXP |  | 2020-05-02 | 2020-05-01 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Yes
National Grid | EAST LONGMEADOW | 189273 | 1028 | 19 | Solar | 09_508L1 | 2018-06-26 16:57 | 2018-06-27 | 0 | 0 | 0 | 2018-06-28 | 2018-06-28 | 1 | 0 | 1 | [20 empty] | 2018-09-28 |  |  |  | EXP | [8 empty] | 2019-10-07 | Connected |  | No
National Grid | BILLERICA | 189305 | 1821 | 7.6 | Solar | 14_70L6 | 2018-06-27 09:02 | 2018-08-30 | 9 | 6 | 3 | 2018-09-14 | 2019-10-15 | 148 | 0 | 148 | [20 empty] | 2018-09-29 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BELLINGHAM | 189314 | 2019 | 10 | Solar | 05_344W4 | 2018-06-27 09:31 | 2018-10-26 | 16 | 11 | 5 | 2018-11-21 | 2018-12-07 | 10 | 0 | 10 | [20 empty] | 2018-12-07 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | ATHOL | 189059 | 1331 | 5000 | Solar | 09_705W3 | 2018-06-27 11:16 | 2018-06-28 | 20 | 20 | 0 | [10 empty] | 2018-07-27 | 2018-08-22 | 19 | 13 | 6 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BELCHERTOWN | 188851 | 1007 | 4950 | Solar | 09_509L1 | 2018-06-27 11:19 | 2018-06-28 | 9 | 3 | 6 | [10 empty] | 2018-07-12 | 2018-08-16 | 25 | 8 | 17 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | PEPPERELL | 185818 | 1463 | 999 | Solar | 01_226L1 | 2018-06-27 15:24 | 2018-06-28 | 11 | 11 | 0 | [10 empty] | 2018-07-16 | 2018-07-19 | 4 | 3 | 1 | [10 empty] | 2019-09-27 |  | 2020-09-03 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BILLERICA | 189415 | 1821 | 15.2 | Solar | 14_18L2 | 2018-06-27 16:00 | 2018-06-28 | 0 | 0 | 0 | 2018-06-28 | 2018-06-28 | 0 | 0 | 0 | [20 empty] | 2018-06-28 | 2018-06-27 16:41 | 2020-02-21 |  | EXP | [8 empty] | 2020-01-22 | Connected |  | No
National Grid | RANDOLPH | 189432 | 2368 | 7.6 | Solar | 07_97W5 | 2018-06-27 16:41 | 2018-07-06 | 9 | 0 | 9 | 2018-07-20 | 2018-08-01 | 8 | 0 | 8 | [20 empty] | 2018-08-27 |  | 2020-08-12 | Yes | EXP | [9 empty] | Meter Installation |  | Yes
National Grid | FOXBOROUGH | 189459 | 2035 | 7.6 | Solar | 05_3424W1 | 2018-06-27 19:37 | 2018-06-28 | 44 | 24 | 20 | 2018-08-30 | 2018-09-07 | 5 | 0 | 5 | [20 empty] | 2018-09-11 |  |  |  | EXP | [8 empty] | 2019-03-29 | Connected |  | No
National Grid | DUDLEY | 187735 | 1571 | 466.6 | Solar | 01_412L5 | 2018-06-28 | 2018-06-29 | 21 | 12 | 9 | [10 empty] | 2018-07-30 | 2018-08-14 | 12 | 2 | 10 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | HUBBARDSTON | 189429 | 1452 | 3000 | Solar | 09_604W4 | 2018-06-28 | 2018-06-29 | 7 | 7 | 0 | [10 empty] | 2018-07-25 | 2018-09-13 | 36 | 9 | 27 | [5 empty] | 2020-07-10 | 2020-10-07 | 63 | 3 | 60 |  |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | TEWKSBURY | 189478 | 1876 | 7.6 | Solar | 14_59L3 | 2018-06-28 08:42 | 2018-06-29 | 1 | 0 | 1 | 2018-07-02 | 2018-07-09 | 20 | 0 | 20 | [20 empty] | 2018-07-11 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NEWBURYPORT | 187091 | 1950 | 86.4 | Solar | 14_36L2 | 2018-06-28 11:20 | 2018-06-29 | 0 | 0 | 0 | 2018-07-02 | 2018-07-02 | 0 | 0 | 0 | [20 empty] | 2018-07-02 |  |  |  | EXP | [8 empty] | 2018-12-31 | Connected |  | Yes
National Grid | LANCASTER | 186058 | 1523 | 4600 | Solar | 01_219W5 | 2018-06-28 11:27 | 2018-06-29 | 23 | 14 | 9 | [10 empty] | 2018-08-02 | 2018-08-02 | 1 | 1 | 0 | [10 empty] | 2018-12-12 |  | 2021-06-28 |  | STD |  | 2020-12-04 | 2021-06-10 | 188 | 0 | 188 |  |  | 2021-06-21 | Connected |  | No
National Grid | ORANGE | 189146 | 1364 | 990 | Solar | 09_705W2 | 2018-06-28 12:10 | 2018-06-29 | 12 | 12 | 0 | [10 empty] | 2018-07-18 | 2018-09-21 | 46 | 0 | 46 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | AUBURN | 189536 | 1501 | 17.6 | Solar | 01_26W3 | 2018-06-28 13:17 | 2018-06-29 | 13 | 11 | 2 | 2018-07-19 | 2018-07-27 | 5 | 0 | 5 | [20 empty] | 2018-08-24 |  |  |  | EXP | [8 empty] | 2019-04-27 | Connected |  | No
National Grid | EGREMONT | 188497 | 1258 | 3652 | Solar | 09_1108W1 | 2018-06-29 | 2018-08-13 | 22 | 14 | 8 | [10 empty] | 2018-09-13 | 2018-09-13 | 0 | 0 | 0 | [11 empty] | 2018-06-29 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | FALL RIVER | 189617 | 2720 | 249.8 | Solar | 05_28W41 | 2018-06-29 | 2018-07-02 | 6 | 5 | 1 | 2018-07-11 | 2018-09-11 | 43 | 21 | 22 | 2018-09-28 | 2018-12-07 | 48 | 19 | 29 | [5 empty] | 2018-09-28 | 2018-12-07 | 48 | 19 | 29 | [5 empty] | 2019-03-18 |  | 2021-12-30 | Yes | EXP |  | 2021-10-23 | 2021-11-19 | 28 | 4 | 24 |  |  | 2021-12-30 | Connected |  | No
National Grid | LOWELL | 189667 | 1852 | 249.8 | Solar | 14_20L3 | 2018-06-29 | 2018-07-06 | 2 | 0 | 2 | 2018-07-11 | 2018-07-11 | 0 | 0 | 0 | [20 empty] | 2018-07-30 |  | 2020-07-31 |  | EXP | [8 empty] | 2020-08-03 | Connected |  | No
National Grid | HAYDENVILLE | 189354 | 1039 | 10 | Solar | 09_909W3 | 2018-06-29 09:52 | 2018-08-01 | 15 | 0 | 15 | 2018-08-23 | 2018-12-19 | 81 | 21 | 60 | 2018-11-19 | 2019-01-18 | 40 | 0 | 40 | [5 empty] | 2018-11-19 | 2019-01-18 | 40 | 0 | 40 | [5 empty] | 2018-12-19 |  |  |  | EXP | [8 empty] | 2019-04-01 | Connected |  | Yes
National Grid | ATHOL | 185392 | 1331 | 4998 | Solar | 09_702W1 | 2018-06-29 10:21 | 2018-06-01 | 32 | 28 | 4 | [10 empty] | 2018-07-18 | 2018-10-12 | 62 | 39 | 23 | [11 empty] | 2018-06-29 11:06 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ATTLEBORO | 188158 | 2703 | 4482 | Solar | 05_8L3 | 2018-06-29 11:06 | 2018-07-02 | 12 | 0 | 12 | [10 empty] | 2018-07-20 | 2018-09-28 | 49 | 26 | 23 | [10 empty] | 2020-09-30 |  |  | Yes | STD |  | 2022-09-17 | 2023-06-20 | 277 | 268 | 9 |  |  |  | Study |  | No
National Grid | BEVERLY | 189636 | 1915 | 11.4 | Solar | 12_12L2 | 2018-06-29 12:15 | 2018-10-05 | 3 | 3 | 0 | 2018-10-10 | 2018-10-11 | 1 | 0 | 1 | [20 empty] | 2018-10-11 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SPENCER | 189663 | 1562 | 15.2 | Solar | 01_552L1 | 2018-06-29 14:21 | 2018-07-02 | 8 | 7 | 1 | 2018-07-13 | 2018-07-16 | 1 | 0 | 1 | [20 empty] | 2018-08-24 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | HOLBROOK | 189677 | 2343 | 15.2 | Solar | 07_2W1 | 2018-06-29 15:25 | 2018-07-02 | 8 | 7 | 1 | 2018-07-12 | 2018-07-12 | 0 | 0 | 0 | [20 empty] | 2018-07-13 |  |  |  | EXP | [8 empty] | 2019-11-21 | Connected |  | No
National Grid | STOUGHTON | 189720 | 2072 | 15.2 | Solar | 07_913W67 | 2018-06-29 18:58 | 2018-08-15 | 10 | 0 | 10 | 2018-08-30 | 2018-10-12 | 182 | 0 | 182 | [20 empty] | 2018-09-12 |  | 2020-06-29 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BELLINGHAM | 171881 | 2019 | 10 | Solar | 05_108W60 | 2018-07-01 22:26 | 2018-07-03 | 5 | 5 | 0 | 2018-07-11 | 2018-09-28 | 56 | 0 | 56 | [20 empty] | 2018-10-09 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEOMINSTER | 187189 | 1453 | 200 | Solar | 01_207W2 | 2018-07-02 | 2018-07-05 | 15 | 1 | 14 | 2018-07-26 | 2018-07-26 | 0 | 0 | 0 | [20 empty] | 2018-09-06 | 2018-07-02 09:51 | 2019-12-31 |  | EXP | [8 empty] | 2019-12-18 | Connected |  | No
National Grid | LYNN | 189736 | 1905 | 7.6 | Solar | 12_29W3 | 2018-07-02 09:51 | 2018-08-01 | 2 | 0 | 2 | 2018-08-06 | 2018-08-09 | 3 | 0 | 3 | [20 empty] | 2018-08-09 |  | 2019-11-15 | Yes | EXP |  | 2019-04-23 | 2019-04-22 | 0 | 0 | 0 |  |  | 2019-10-10 | Connected |  | No
National Grid | CHESHIRE | 185016 | 1225 | 1000 | Solar | 09_1021W2 | 2018-07-02 11:25 | 2018-07-03 | 17 | 16 | 1 | [10 empty] | 2018-07-27 | 2018-08-15 | 14 | 12 | 2 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | AUBURN | 189789 | 1501 | 15.2 | Solar | 01_26W3 | 2018-07-02 13:33 | 2018-07-03 | 5 | 4 | 1 | 2018-07-11 | 2018-07-11 | 0 | 0 | 0 | [20 empty] | 2018-10-23 | 2018-07-02 14:07 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 189805 | 1603 | 10 | Solar | 01_7J387 | 2018-07-02 14:07 | 2018-10-19 | 4 | 4 | 0 | 2018-10-25 | 2018-11-02 | 6 | 0 | 6 | [20 empty] | 2018-11-02 |  | 2019-12-05 | Yes | EXP |  | 2019-07-17 | 2019-09-04 | 49 | 0 | 49 |  |  | 2019-10-29 | Connected |  | No
National Grid | EAST LONGMEADOW | 184049 | 1028 | 19 | Solar | 09_139L5 | 2018-07-02 18:13 | 2018-07-03 | 18 | 5 | 13 | 2018-07-27 | 2018-07-30 | 1 | 0 | 1 | [20 empty] | 2018-07-31 |  |  |  | EXP | [8 empty] | 2019-11-22 | Connected |  | No
National Grid | AYER | 184741 | 1432 | 530 | Solar |  | 2018-07-03 | 2018-07-05 | 124 | 25 | 99 | [29 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | AYER | 184743 | 1432 | 630 | Solar | 09_527L1 | 2018-07-03 | 2018-07-05 | 124 | 25 | 99 | [29 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | REVERE | 189881 | 2151 | 3.8 | Solar | 12_7J7 | 2018-07-03 09:47 | 2018-10-23 | 5 | 0 | 5 | 2018-10-31 | 2018-11-13 | 8 | 0 | 8 | [20 empty] | 2019-02-13 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RANDOLPH | 189885 | 2368 | 7.6 | Solar | 07_97W1 | 2018-07-03 10:12 | 2018-08-29 | 14 | 11 | 3 | 2018-09-20 | 2018-11-04 | 32 | 0 | 32 | [20 empty] | 2018-10-29 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MARLBOROUGH | 189707 | 1752 | 472.5 | Natural Gas | 05_317W2 | 2018-07-03 11:46 | 2018-07-05 | 33 | 24 | 9 | [5 empty] | 2018-10-19 | 2018-11-01 | 9 | 0 | 9 | 2018-08-20 | 2018-09-24 | 24 | 0 | 24 | 2018-10-19 | 2018-11-01 | 9 | 0 | 9 | [5 empty] | 2019-10-30 |  | 2019-12-31 |  | STD | [8 empty] | 2019-12-31 | Connected |  | No
National Grid | MARLBOROUGH | 189709 | 1752 | 381.5 | Natural Gas | 05_313W4 | 2018-07-03 11:56 | 2018-07-05 | 32 | 23 | 9 | [5 empty] | 2018-10-19 | 2018-11-01 | 9 | 0 | 9 | 2018-08-20 | 2018-09-24 | 24 | 0 | 24 | 2018-10-19 | 2018-11-01 | 9 | 0 | 9 | [5 empty] | 2019-10-30 |  | 2020-05-13 |  | STD | [8 empty] | 2019-12-31 | Connected |  | No
National Grid | WILBRAHAM | 189780 | 1095 | 746 | Solar | 09_507L2 | 2018-07-03 14:53 | 2018-07-05 | 61 | 46 | 15 | [10 empty] | 2018-08-29 | 2018-08-28 | 0 | 0 | 0 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SALEM | 188370 | 1906 | 7.6 | Solar | 12_29W6 | 2018-07-03 17:49 | 2018-07-05 | 3 | 0 | 3 | 2018-07-11 | 2018-07-18 | 14 | 0 | 14 | [20 empty] | 2018-07-19 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTHBOROUGH | 188768 | 1532 | 120 | Solar | 05_313W2 | 2018-07-04 12:58 | 2018-07-05 | 8 | 0 | 8 | 2018-07-18 | 2019-08-22 | 276 | 26 | 250 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | PEMBROKE | 186391 | 2359 | 249.8 | Solar | 07_910W51 | 2018-07-05 | 2018-07-06 | 9 | 0 | 9 | 2018-07-20 | 2018-08-24 | 26 | 4 | 22 | 2018-08-31 | 2018-09-11 | 5 | 0 | 5 | [5 empty] | 2018-08-31 | 2018-09-11 | 5 | 0 | 5 | [9 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | ROCKLAND | 187879 | 2370 | 1850 | Solar | 07_93W40 | 2018-07-05 | 2018-07-06 | 20 | 7 | 13 | [10 empty] | 2018-08-03 | 2018-12-20 | 95 | 27 | 68 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SOMERSET | 188458 | 2726 | 8.36 | Solar | 05_18J5 | 2018-07-05 09:31 | 2018-07-05 | 21 | 0 | 21 | 2018-08-06 | 2018-09-07 | 23 | 0 | 23 | [20 empty] | 2018-09-10 | 2018-07-05 10:23 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MILFORD | 189831 | 1757 | 10 | Solar | 05_335W5 | 2018-07-05 10:23 | 2018-08-09 | 7 | 0 | 7 | 2018-08-21 | 2018-08-22 | 1 | 0 | 1 | [20 empty] | 2018-08-22 |  |  |  | EXP | [8 empty] | 2019-02-28 | Connected |  | No
National Grid | ATTLEBORO | 189870 | 2703 | 10 | Solar | 05_8L4 | 2018-07-05 10:28 | 2018-08-02 | 8 | 8 | 0 | 2018-08-14 | 2018-08-14 | 0 | 0 | 0 | [20 empty] | 2018-08-27 |  |  |  | EXP | [8 empty] | 2019-03-28 | Connected |  | No
National Grid | BILLERICA | 189998 | 1821 | 15.2 | Solar | 14_18L1 | 2018-07-05 10:41 | 2018-07-06 | 2 | 0 | 2 | 2018-07-11 | 2018-07-12 | 14 | 0 | 14 | [20 empty] | 2018-07-16 |  | 2019-08-12 |  | EXP | [8 empty] | 2019-08-14 | Connected |  | No
National Grid | ATTLEBORO | 189370 | 2760 | 5 | Solar | 05_9L1 | 2018-07-05 10:46 | 2018-08-02 | 6 | 0 | 6 | 2018-08-13 | 2018-08-13 | 0 | 0 | 0 | [20 empty] | 2018-08-14 | 2018-07-06 |  |  | EXP | [8 empty] | 2018-10-29 | Connected |  | Yes
National Grid | METHUEN | 188961 | 1844 | 1750 | Solar | 14_63L2 | 2018-07-06 | 2018-08-24 | 8 | 3 | 5 | [10 empty] | 2018-09-06 | 2018-10-10 | 23 | 3 | 20 | [10 empty] | 2019-03-29 |  | 2021-09-27 | Yes | STD |  | 2021-06-22 | 2021-08-02 | 42 | 0 | 42 |  |  | 2021-09-22 | Connected |  | No
National Grid | LEICESTER | 188842 | 1524 | 2280 | Solar |  | 2018-07-06 09:33 | 2018-07-09 | 14 | 13 | 1 | [10 empty] | 2018-07-27 | 2018-08-21 | 17 | 16 | 1 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WILBRAHAM | 190105 | 1095 | 7.6 | Solar | 09_507L3 | 2018-07-06 09:59 | 2018-07-30 | 21 | 0 | 21 | 2018-08-29 | 2018-09-10 | 8 | 0 | 8 | [20 empty] | 2018-11-09 | 2018-07-06 11:40 | 2019-10-21 |  | EXP | [8 empty] | 2019-09-17 | Connected |  | No
National Grid | MILFORD | 188704 | 1757 | 10 | Solar | 05_336W3 | 2018-07-06 11:40 | 2018-08-10 | 1 | 1 | 0 | 2018-08-13 | 2018-08-15 | 2 | 0 | 2 | [20 empty] | 2018-08-27 | 2018-07-06 13:48 |  | Yes | EXP | [8 empty] | 2019-04-23 | Connected |  | No
National Grid | EAST LONGMEADOW | 190139 | 1028 | 3.8 | Solar | 09_508L1 | 2018-07-06 13:48 | 2018-08-22 | 4 | 0 | 4 | 2018-08-29 | 2018-09-28 | 21 | 0 | 21 | [20 empty] | 2018-09-28 |  | 2020-12-31 | Yes | EXP | [8 empty] | 2020-10-22 | Connected |  | No
National Grid | ATTLEBORO | 184801 | 2703 | 990 | Solar | 05_9L4 | 2018-07-09 | 2018-08-17 | 26 | 1 | 25 | [10 empty] | 2018-09-25 | 2018-10-22 | 20 | 1 | 19 | [10 empty] | 2019-05-24 |  | 2021-01-02 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MEDFORD | 190186 | 2155 | 50 | Solar | 12_64J4 | 2018-07-09 | 2018-07-11 | 2 | 0 | 2 | 2018-07-16 | 2018-07-16 | 0 | 0 | 0 | [20 empty] | 2018-07-18 | 2018-07-09 09:30 | 2019-12-30 |  | EXP | [8 empty] | 2019-12-30 | Connected |  | No
National Grid | ESSEX | 169987 | 1929 | 10 | Solar | 12_51T2 | 2018-07-09 09:30 | 2018-07-10 | 11 | 8 | 3 | 2018-07-25 | 2018-07-25 | 0 | 0 | 0 | [20 empty] | 2018-07-26 |  | 2019-10-01 | Yes | EXP | [8 empty] | 2019-09-25 | Connected |  | No
National Grid | SAUGUS | 185047 | 1906 | 13.6 | Solar | 12_25W1 | 2018-07-09 09:48 | 2018-07-10 | 7 | 3 | 4 | 2018-07-19 | 2018-07-27 | 6 | 0 | 6 | [20 empty] | 2018-07-31 |  |  |  | EXP | [8 empty] | 2018-11-13 | Connected |  | Yes
National Grid | BRIMFIELD | 184331 | 1010 | 7.6 | Solar | 09_516L1 | 2018-07-09 15:27 | 2018-07-10 | 0 | 0 | 0 | 2018-07-10 | 2018-07-10 | 0 | 0 | 0 | [20 empty] | 2018-08-06 |  | 2019-10-18 |  | EXP | [8 empty] | 2019-09-09 | Connected |  | No
National Grid | SUTTON | 190183 | 1590 | 250 | Solar | 05_320W5 | 2018-07-10 | 2018-07-19 | 1 | 0 | 1 | 2018-07-23 | 2018-07-25 | 2 | 0 | 2 | [20 empty] | 2018-07-31 |  |  |  | EXP | [8 empty] | 2019-09-11 | Connected |  | No
National Grid | EAST PEPPERELL | 190303 | 1463 | 3.8 | Solar | 01_210L1 | 2018-07-10 09:06 | 2018-08-22 | 14 | 14 | 0 | 2018-09-12 | 2018-09-13 | 1 | 0 | 1 | [20 empty] | 2018-09-28 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTBOROUGH | 190317 | 1581 | 3.8 | Solar | 05_312W4 | 2018-07-10 10:12 | 2018-08-03 | 9 | 2 | 7 | 2018-08-16 | 2018-08-16 | 0 | 0 | 0 | [20 empty] | 2018-08-27 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | REHOBOTH | 173295 | 2769 | 3.8 | Solar | 05_7L5 | 2018-07-10 10:22 | 2018-07-11 | 6 | 0 | 6 | 2018-07-20 | 2018-08-22 | 23 | 0 | 23 | [20 empty] | 2018-08-27 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BELLINGHAM | 187250 | 2019 | 11.4 | Solar | 05_344W4 | 2018-07-10 11:41 | 2018-07-13 | 11 | 7 | 4 | 2018-07-30 | 2018-07-31 | 1 | 0 | 1 | [20 empty] | 2018-08-03 |  |  |  | EXP | [8 empty] | 2019-11-07 | Connected |  | No
National Grid | DRACUT | 184581 | 1826 | 15.2 | Solar | 14_75L1 | 2018-07-10 12:08 | 2018-07-11 | 1 | 0 | 1 | 2018-07-13 | 2018-07-13 | 0 | 0 | 0 | [20 empty] | 2018-07-12 |  |  |  | EXP | [8 empty] | 2019-10-07 | Connected |  | No
National Grid | GRAFTON | 190346 | 1519 | 10 | Solar | 01_304W2 | 2018-07-10 12:18 | 2018-08-01 | 19 | 0 | 19 | 2018-08-29 | 2018-09-12 | 9 | 0 | 9 | [20 empty] | 2018-09-28 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | TYNGSBORO | 190345 | 1879 | 7.6 | Solar | 14_211L2 | 2018-07-10 12:26 | 2018-07-11 | 2 | 0 | 2 | 2018-07-13 | 2018-07-20 | 5 | 0 | 5 | [20 empty] | 2018-07-20 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WEST BROOKFIELD | 190339 | 1585 | 250 | Solar | 01_525L2 | 2018-07-10 13:06 | 2018-07-11 | 28 | 0 | 28 | 2018-08-21 | 2019-01-03 | 91 | 21 | 70 | 2018-11-20 | 2019-01-03 | 28 | 0 | 28 | [5 empty] | 2018-11-20 | 2019-01-03 | 28 | 0 | 28 | [6 empty] | 2018-07-10 13:54 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | RANDOLPH | 190363 | 2368 | 7.6 | Solar | 07_5W1 | 2018-07-10 13:54 | 2018-08-21 | 5 | 4 | 1 | 2018-08-28 | 2018-09-07 | 7 | 0 | 7 | [20 empty] | 2018-09-07 |  | 2020-05-18 | Yes | EXP |  | 2019-11-16 | 2019-12-10 | 24 | 0 | 24 |  |  | 2019-12-24 | Connected |  | No
National Grid | HAWLEY | 184444 | 1339 | 4998 | Solar | 09_1019W1 | 2018-07-10 15:43 | 2018-07-23 | 8 | 0 | 8 | [10 empty] | 2018-08-03 | 2019-08-15 | 107 | 4 | 103 | [10 empty] | 2018-12-27 | 2018-07-10 16:28 | 2021-03-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | RANDOLPH | 188196 | 2368 | 400 | Solar | 07_5W3 | 2018-07-10 16:28 | 2018-07-11 | 5 | 0 | 5 | [5 empty] | 2018-09-25 | 2018-10-25 | 23 | 3 | 20 | [5 empty] | 2018-09-25 | 2018-10-25 | 23 | 3 | 20 | [5 empty] | 2018-11-27 | 2018-07-10 17:23 | 2020-07-07 | Yes | EXP | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 188740 | 1844 | 7.6 | Solar | 14_63L1 | 2018-07-10 17:23 | 2018-07-11 | 39 | 33 | 6 | 2018-12-17 | 2018-12-31 | 9 | 0 | 9 | [20 empty] | 2019-01-17 |  | 2020-02-18 | Yes | EXP |  | 2019-05-21 | 2019-07-12 | 52 | 0 | 52 |  |  | 2020-01-10 | Connected |  | No
National Grid | ORANGE | 189259 | 1364 | 1518 | Solar | 09_705W2 | 2018-07-11 | 2018-08-13 | 8 | 0 | 8 | [10 empty] | 2018-08-24 | 2018-08-24 | 0 | 0 | 0 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SOMERSET | 190436 | 2726 | 250 | Solar | 05_19W72 | 2018-07-11 | 2018-08-08 | 5 | 0 | 5 | 2018-08-16 | 2018-09-17 | 21 | 0 | 21 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 190446 | 2302 | 15.2 | Solar | 07_712J1 | 2018-07-11 11:32 | 2018-07-31 | 8 | 0 | 8 | 2018-08-13 | 2018-08-13 | 0 | 0 | 0 | [20 empty] | 2018-08-14 |  |  |  | EXP | [8 empty] | 2019-10-29 | Connected |  | No
National Grid | RANDOLPH | 190453 | 2368 | 5 | Solar | 07_97W1 | 2018-07-11 12:02 | 2018-07-31 | 9 | 0 | 9 | 2018-08-14 | 2018-08-17 | 3 | 0 | 3 | 2018-09-26 | 2018-10-30 | 24 | 0 | 24 | [5 empty] | 2018-09-26 | 2018-10-30 | 24 | 0 | 24 | [5 empty] | 2018-11-01 |  |  |  | EXP | [8 empty] | 2019-11-08 | Connected |  | No
National Grid | WEYMOUTH | 190503 | 2188 | 7.6 | Solar | 07_6W1 | 2018-07-11 16:10 | 2018-08-07 | 8 | 8 | 0 | 2018-08-17 | 2018-08-17 | 0 | 0 | 0 | [20 empty] | 2018-08-27 | 2018-07-11 17:23 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BELLINGHAM | 190511 | 2019 | 10 | Solar | 05_344W4 | 2018-07-11 17:23 | 2018-10-16 | 10 | 7 | 3 | 2018-10-30 | 2018-11-06 | 5 | 0 | 5 | [20 empty] | 2018-11-13 | 2018-07-11 17:43 |  | Yes | EXP | [8 empty] | 2019-05-10 | Connected |  | No
National Grid | EAST LONGMEADOW | 190514 | 1028 | 9.6 | Solar | 09_139L5 | 2018-07-11 17:43 | 2018-08-15 | 10 | 0 | 10 | 2018-08-30 | 2018-10-04 | 25 | 3 | 22 | [20 empty] | 2018-10-24 |  | 2019-10-29 | Yes | EXP |  | 2019-05-11 | 2019-05-28 | 17 | 0 | 17 |  |  |  | Withdrawn |  | Yes
National Grid | LOWELL | 190106 | 1852 | 6 | Solar | 14_70L3 | 2018-07-11 17:53 | 2018-07-18 | 0 | 0 | 0 | 2018-07-19 | 2018-09-26 | 49 | 1 | 48 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 190628 | 1603 | 5 | Solar | 01_7J386 | 2018-07-13 08:35 | 2018-07-27 | 23 | 0 | 23 | 2018-08-30 | 2018-08-29 | 0 | 0 | 0 | [20 empty] | 2018-11-15 | 2018-07-13 11:53 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 190326 | 1603 | 10 | Solar | 01_7J387 | 2018-07-13 11:53 | 2018-07-18 | 27 | 0 | 27 | 2018-08-27 | 2018-08-27 | 0 | 0 | 0 | [20 empty] | 2018-10-16 | 2018-07-13 13:48 |  | Yes | EXP |  | 2019-10-17 | 2019-10-16 | 0 | 0 | 0 |  |  | 2019-11-06 | Connected |  | No
National Grid | MARLBOROUGH | 190641 | 1752 | 11.4 | Solar | 05_311W3 | 2018-07-13 13:48 | 2018-08-08 | 23 | 9 | 14 | 2018-09-11 | 2018-09-13 | 2 | 0 | 2 | [20 empty] | 2018-10-11 | 2018-07-13 17:11 |  | Yes | EXP | [8 empty] | 2019-07-17 | Connected |  | No
National Grid | RUTLAND | 190717 | 1543 | 10 | Solar | 01_55W1 | 2018-07-13 17:11 | 2018-09-11 | 30 | 24 | 6 | 2018-10-24 | 2018-10-29 | 3 | 0 | 3 | [20 empty] | 2018-10-30 |  | 2019-08-28 | Yes | EXP |  | 2019-04-23 | 2019-04-22 | 0 | 0 | 0 |  |  | 2019-05-23 | Connected |  | No
National Grid | EAST LONGMEADOW | 184584 | 1028 | 15.2 | Solar | 09_522L4 | 2018-07-15 22:17 | 2018-07-16 | 21 | 0 | 21 | 2018-08-15 | 2019-11-01 | 304 | 0 | 304 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | REVERE | 184583 | 2151 | 15.2 | Solar | 12_7J6 | 2018-07-15 22:27 | 2018-07-18 | 1 | 0 | 1 | 2018-07-19 | 2018-07-20 | 1 | 0 | 1 | [20 empty] | 2018-07-20 |  |  |  | EXP | [8 empty] | 2019-02-06 | Connected |  | Yes
National Grid | MONSON | 184321 | 1057 | 11.4 | Solar | 09_503L2 | 2018-07-15 22:54 | 2018-07-16 | 18 | 0 | 18 | 2018-08-10 | 2018-08-13 | 1 | 0 | 1 | [20 empty] | 2018-11-16 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | HAMPDEN | 184311 | 1036 | 7.6 | Solar | 09_139L1 | 2018-07-15 23:02 | 2018-07-16 | 21 | 0 | 21 | 2018-08-15 | 2018-08-15 | 0 | 0 | 0 | [20 empty] | 2018-11-21 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | TEWKSBURY | 184053 | 1876 | 3.8 | Solar | 14_20L5 | 2018-07-15 23:10 | 2018-07-16 | 2 | 0 | 2 | 2018-07-19 | 2018-08-01 | 9 | 0 | 9 | [20 empty] | 2018-08-01 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BOLTON | 188838 | 1740 | 1560 | Solar | 01_216W6 | 2018-07-16 07:50 | 2018-07-17 | 1 | 0 | 1 | [10 empty] | 2018-07-19 | 2018-07-20 | 2 | 2 | 0 | [10 empty] | 2020-07-13 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WEST BRIDGEWATER | 189857 | 2379 | 999 | Solar | 07_797W20 | 2018-07-16 11:50 | 2018-07-17 | 29 | 0 | 29 | [10 empty] | 2018-08-28 | 2020-03-09 | 186 | 4 | 182 | [10 empty] | 2019-07-11 |  | 2021-04-29 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WEBSTER | 190782 | 1570 | 23.04 | Solar | 01_412L2 | 2018-07-16 12:30 | 2018-07-17 | 31 | 0 | 31 | 2018-08-30 | 2018-08-29 | 0 | 0 | 0 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GRANBY | 190691 | 1033 | 4400 | Solar | 09_527L1 | 2018-07-16 13:57 | 2018-07-17 | 17 | 17 | 0 | [10 empty] | 2018-08-09 | 2018-10-09 | 44 | 15 | 29 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WEBSTER | 189710 | 1570 | 2000 | Solar | 01_412L1 | 2018-07-16 17:23 | 2018-07-17 | 14 | 8 | 6 | [10 empty] | 2018-08-07 | 2018-11-30 | 78 | 25 | 53 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SUTTON | 184565 | 1590 | 264 | Solar | 05_320W5 | 2018-07-17 | 2018-08-20 | 6 | 0 | 6 | [10 empty] | 2018-08-29 | 2018-10-01 | 23 | 1 | 22 | [10 empty] | 2019-04-12 |  | 2020-08-03 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH ADAMS | 190889 | 1247 | 100 | Natural Gas | 09_1015W1 | 2018-07-17 | 2018-07-30 | 22 | 0 | 22 | [10 empty] | 2018-08-30 | 2018-10-31 | 44 | 20 | 24 | [10 empty] | 2019-12-03 |  | 2023-01-13 |  | STD |  | 2021-06-04 | 2021-09-08 | 0 | 0 | 0 |  |  | 2022-01-12 | Connected |  | No
National Grid | NORTH ANDOVER | 190956 | 1845 | 77 | Solar | 14_54L3 | 2018-07-17 | 2018-07-24 | 9 | 6 | 3 | 2018-08-06 | 2018-08-17 | 9 | 0 | 9 | 2018-10-05 | 2018-10-04 | 0 | 0 | 0 | [5 empty] | 2018-10-05 | 2018-10-04 | 0 | 0 | 0 | [5 empty] | 2018-10-23 |  | 2019-10-01 |  | EXP | [8 empty] | 2019-12-16 | Connected |  | No
National Grid | MONSON | 190886 | 1057 | 3.8 | Solar | 09_503L2 | 2018-07-17 10:15 | 2018-09-21 | 8 | 0 | 8 | 2018-10-04 | 2018-10-29 | 17 | 0 | 17 | [20 empty] | 2018-10-29 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SWAMPSCOTT | 190057 | 1907 | 9 | Solar | 12_1J904 | 2018-07-17 11:20 | 2018-10-09 | 6 | 0 | 6 | 2018-10-18 | 2018-11-16 | 20 | 11 | 9 | [20 empty] | 2018-12-19 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RUTLAND | 185992 | 1543 | 8.4 | Solar | 01_55W1 | 2018-07-17 12:25 | 2018-07-18 | 19 | 0 | 19 | 2018-08-15 | 2018-09-14 | 21 | 0 | 21 | [20 empty] | 2018-09-26 |  |  |  | EXP | [8 empty] | 2018-11-21 | Connected |  | Yes
National Grid | SAUGUS | 190922 | 1906 | 7.6 | Solar | 12_19W1 | 2018-07-17 12:29 | 2018-08-06 | 3 | 0 | 3 | 2018-08-10 | 2018-08-13 | 1 | 0 | 1 | [20 empty] | 2018-08-27 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | DIGHTON | 170569 | 2715 | 15.4 | Solar | 05_19W73 | 2018-07-17 12:49 | 2018-07-18 | 19 | 7 | 12 | 2018-08-14 | 2018-08-15 | 1 | 0 | 1 | [20 empty] | 2018-08-22 |  | 2019-12-24 |  | EXP | [8 empty] | 2019-12-11 | Connected |  | No
National Grid | BROCKTON | 190934 | 2301 | 3.8 | Solar | 07_911W13 | 2018-07-17 13:01 | 2018-10-18 | 5 | 5 | 0 | 2018-10-25 | 2018-11-02 | 6 | 0 | 6 | [20 empty] | 2018-11-02 | 2018-07-17 18:43 | 2020-07-17 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTON | 188651 | 2766 | 1380 | Solar | 05_4L1 | 2018-07-17 18:43 | 2018-07-18 | 21 | 12 | 9 | [10 empty] | 2018-08-16 | 2018-09-27 | 33 | 13 | 20 | [10 empty] | 2019-02-04 |  | 2023-01-18 | Yes | STD |  | 2021-06-05 | 2022-09-29 | 482 | 373 | 109 |  |  | 2023-03-27 | Connected |  | No
National Grid | GRANBY | 190067 | 1033 | 5000 | Solar | 09_527L1 | 2018-07-18 09:16 | 2018-07-19 | 10 | 2 | 8 | [10 empty] | 2018-08-02 | 2018-08-24 | 17 | 17 | 0 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WINCHENDON | 190055 | 1475 | 2000 | Solar | 01_612W1 | 2018-07-18 09:28 | 2018-07-19 | 160 | 0 | 160 | [10 empty] | 2018-09-18 | 2019-01-03 | 144 | 72 | 72 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | ATHOL | 185922 | 1331 | 480 | Solar | 09_705W3 | 2018-07-18 12:50 | 2018-07-19 | 1 | 0 | 1 | [10 empty] | 2018-07-23 | 2018-08-08 | 12 | 0 | 12 | [10 empty] | 2018-08-10 |  |  |  | STD | [8 empty] | 2019-07-12 | Connected |  | No
National Grid | HAVERHILL | 191108 | 1830 | 52.2 | Solar | 14_48L4 | 2018-07-18 17:40 | 2018-07-19 | 13 | 11 | 2 | 2018-08-07 | 2018-08-09 | 2 | 0 | 2 | [20 empty] | 2018-08-09 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH EASTON | 191163 | 2356 | 50 | Solar | 07_92W78 | 2018-07-19 | 2018-08-02 | 4 | 0 | 4 | 2018-08-09 | 2018-08-21 | 8 | 0 | 8 | [20 empty] | 2018-08-21 |  |  |  | EXP | [8 empty] | 2019-03-07 | Connected |  | Yes
National Grid | FRANKLIN | 191137 | 2038 | 250 | Solar | 05_344W6 | 2018-07-19 07:19 | 2018-07-30 | 22 | 14 | 8 | [5 empty] | 2019-01-08 | 2019-02-05 | 19 | 0 | 19 | 2018-08-29 | 2018-11-21 | 58 | 25 | 33 | 2019-01-08 | 2019-02-05 | 19 | 0 | 19 | [9 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | STURBRIDGE | 191126 | 1566 | 3.8 | Solar | 01_413L2 | 2018-07-19 08:47 | 2018-10-19 | 4 | 4 | 0 | 2018-10-25 | 2018-11-02 | 6 | 0 | 6 | [20 empty] | 2018-11-02 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WEST BROOKFIELD | 186387 | 1585 | 250 | Solar |  | 2018-07-19 10:28 | 2018-07-20 | 703 | 20 | 683 | [26 empty] | 2018-07-19 14:47 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MENDON | 185872 | 1756 | 1000 | Solar | 05_335W1 | 2018-07-19 14:47 | 2018-06-29 | 15 | 14 | 1 | [10 empty] | 2018-07-20 | 2018-09-10 | 36 | 14 | 22 | [10 empty] | 2019-01-17 |  | 2021-11-23 | Yes | STD |  | 2019-11-01 | 2021-07-02 | 609 | 362 | 247 |  |  | 2021-10-22 | Connected |  | No
National Grid | AMESBURY | 191148 | 1913 | 6.96 | Solar | 14_5J11 | 2018-07-19 14:54 | 2018-07-31 | 0 | 0 | 0 | 2018-08-01 | 2018-09-05 | 24 | 0 | 24 | [20 empty] | 2018-09-25 | 2018-07-19 18:03 | 2019-07-31 |  | EXP | [8 empty] | 2019-02-14 | Connected |  | No
National Grid | LOWELL | 191228 | 1851 | 3 | Solar | 14_2L2 | 2018-07-19 18:03 | 2018-08-01 | 31 | 25 | 6 | 2018-09-14 | 2018-09-18 | 2 | 0 | 2 | [20 empty] | 2018-10-09 |  |  | Yes | EXP | [8 empty] | 2019-05-10 | Connected |  | No
National Grid | GRAFTON | 191356 | 1519 | 250 | Solar | 01_328W3 | 2018-07-20 | 2018-07-24 | 2 | 0 | 2 | 2018-07-27 | 2018-08-30 | 24 | 0 | 24 | [20 empty] | 2018-12-12 | 2018-07-20 10:32 | 2020-03-19 |  | EXP | [8 empty] | 2020-03-20 | Connected |  | No
National Grid | HAVERHILL | 191116 | 1832 | 1594 | Solar | 14_48L1 | 2018-07-20 10:32 | 2018-07-23 | 25 | 16 | 9 | [10 empty] | 2018-08-27 | 2018-10-15 | 36 | 16 | 20 | [10 empty] | 2020-05-06 |  | 2024-03-22 | Yes | STD |  | 2023-08-29 | 2024-01-05 | 130 | 3 | 127 |  |  | 2024-02-28 | Connected |  | No
National Grid | WESTBOROUGH | 191397 | 1581 | 7.6 | Solar | 05_312W1 | 2018-07-20 16:04 | 2018-08-31 | 3 | 3 | 0 | 2018-09-06 | 2018-09-13 | 5 | 0 | 5 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 191411 | 2302 | 7.6 | Solar | 07_69J1 | 2018-07-20 18:01 | 2018-08-14 | 278 | 0 | 278 | 2018-10-11 | 2018-12-20 | 48 | 40 | 8 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BELLINGHAM | 191437 | 2019 | 7.6 | Solar | 05_108W60 | 2018-07-22 16:34 | 2018-08-30 | 20 | 11 | 9 | 2018-10-02 | 2018-10-04 | 2 | 0 | 2 | [20 empty] | 2018-12-06 |  | 2020-07-22 |  | EXP | [8 empty] | 2020-07-08 | Connected |  | No
National Grid | PEPPERELL | 185273 | 1463 | 5310 | Solar | 01_226L2 | 2018-07-23 13:21 | 2018-07-24 | 12 | 12 | 0 | [10 empty] | 2018-08-09 | 2018-08-14 | 3 | 0 | 3 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BEVERLY | 188503 | 1915 | 8.32 | Solar | 12_12L2 | 2018-07-23 14:24 | 2018-07-24 | 5 | 3 | 2 | 2018-07-31 | 2018-08-09 | 7 | 0 | 7 | [20 empty] | 2018-08-09 |  |  |  | EXP | [8 empty] | 2018-10-30 | Connected |  | Yes
National Grid | STURBRIDGE | 191478 | 1518 | 15.2 | Solar | 01_408L1 | 2018-07-23 17:44 | 2018-07-24 | 26 | 0 | 26 | 2018-08-30 | 2018-10-02 | 23 | 1 | 22 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MARLBOROUGH | 191688 | 1752 | 133.2 | Solar | 05_313W4 | 2018-07-24 | 2018-07-31 | 26 | 17 | 9 | 2018-09-06 | 2018-10-12 | 27 | 3 | 24 | [20 empty] | 2018-10-16 |  | 2020-09-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SWAMPSCOTT | 191643 | 1907 | 10 | Solar | 12_29W4 | 2018-07-24 08:45 | 2018-08-20 | 7 | 0 | 7 | 2018-08-30 | 2018-10-02 | 22 | 0 | 22 | [20 empty] | 2018-11-01 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTHBRIDGE | 191709 | 1534 | 8 | Solar | 05_320W3 | 2018-07-24 11:53 | 2018-08-03 | 5 | 0 | 5 | 2018-08-13 | 2018-08-15 | 2 | 0 | 2 | [20 empty] | 2018-08-27 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LYNN | 191753 | 1902 | 7.6 | Solar | 12_29W5 | 2018-07-24 13:52 | 2018-08-07 | 41 | 38 | 3 | 2018-10-04 | 2018-10-08 | 2 | 0 | 2 | [20 empty] | 2018-10-17 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | TOPSFIELD | 191835 | 1983 | 22.8 | Solar | 12_26L1 | 2018-07-25 | 2018-08-16 | 12 | 0 | 12 | 2018-09-05 | 2018-11-05 | 47 | 36 | 11 | [20 empty] | 2018-12-12 |  |  |  | EXP | [8 empty] | 2019-03-19 | Connected |  | No
National Grid | WESTMINSTER | 189902 | 1473 | 950 | Solar | 01_602W3 | 2018-07-25 04:51 | 2018-07-26 | 101 | 12 | 89 | [10 empty] | 2018-09-18 | 2018-12-19 | 62 | 0 | 62 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | NEW MARLBOROUGH | 191267 | 1230 | 4400 | Solar | 09_1109W1 | 2018-07-25 10:13 | 2018-07-26 | 16 | 16 | 0 | [10 empty] | 2018-08-17 | 2018-11-27 | 69 | 26 | 43 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | NEWBURY | 190362 | 1951 | 15.2 | Solar | 14_60L1 | 2018-07-25 12:45 | 2018-07-26 | 23 | 23 | 0 | 2018-08-29 | 2018-08-31 | 1 | 0 | 1 | [20 empty] | 2018-09-07 |  |  |  | EXP | [8 empty] | 2019-01-09 | Connected |  | No
National Grid | MEDFORD | 191794 | 2155 | 66.6 | Solar | 12_64J4 | 2018-07-25 14:19 | 2018-07-26 | 0 | 0 | 0 | 2018-07-27 | 2018-07-30 | 1 | 0 | 1 | [20 empty] | 2018-07-31 |  | 2019-12-16 |  | EXP | [8 empty] | 2019-12-30 | Connected |  | No
National Grid | ATHOL | 190726 | 1331 | 4940 | Solar | 09_702W2 | 2018-07-26 17:46 | 2018-07-27 | 19 | 0 | 19 | [10 empty] | 2018-08-24 | 2018-08-28 | 3 | 3 | 0 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | ATTLEBORO | 192159 | 2703 | 10 | Solar | 05_8L4 | 2018-07-30 10:23 | 2018-08-09 | 19 | 16 | 3 | 2018-09-06 | 2018-10-22 | 33 | 13 | 20 | [20 empty] | 2018-11-02 |  |  |  | EXP | [8 empty] | 2019-04-25 | Connected |  | No
National Grid | HANOVER | 185230 | 2339 | 500 | Solar | 07_95W1 | 2018-07-30 10:25 | 2018-07-31 | 38 | 0 | 38 | [10 empty] | 2018-09-25 | 2018-10-22 | 40 | 0 | 40 | [11 empty] | 2018-07-30 13:34 |  |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | SWAMPSCOTT | 192216 | 1907 | 7.6 | Solar | 12_22W2 | 2018-07-30 13:34 | 2018-07-31 | 0 | 0 | 0 | 2018-08-02 | 2018-08-10 | 6 | 0 | 6 | [20 empty] | 2018-08-27 |  | 2019-09-30 | Yes | EXP |  | 2019-03-16 | 2019-03-15 | 0 | 0 | 0 |  |  | 2019-08-21 | Connected |  | No
National Grid | METHUEN | 192225 | 1844 | 7.6 | Solar | 14_75L6 | 2018-07-30 14:00 | 2018-09-17 | 2 | 0 | 2 | 2018-09-20 | 2018-09-28 | 6 | 0 | 6 | [20 empty] | 2018-12-13 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SPENCER | 192241 | 1562 | 10 | Solar | 01_21W1 | 2018-07-30 16:14 | 2018-08-24 | 24 | 23 | 1 | 2018-09-28 | 2018-10-08 | 7 | 7 | 0 | [20 empty] | 2018-10-08 | 2018-07-31 11:20 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MILLBURY | 173360 | 1527 | 7.6 | Solar | 01_304W3 | 2018-07-31 11:20 | 2018-08-03 | 1 | 0 | 1 | 2018-08-07 | 2018-08-09 | 2 | 0 | 2 | [20 empty] | 2018-08-09 | 2018-07-31 12:16 |  | Yes | EXP |  | 2019-04-03 | 2019-04-02 | 0 | 0 | 0 |  |  | 2019-04-18 | Connected |  | No
National Grid | PALMER | 192328 | 1069 | 7.6 | Solar | 09_523L4 | 2018-07-31 12:16 | 2018-09-27 | 29 | 26 | 3 | 2018-11-08 | 2018-11-29 | 12 | 0 | 12 | [20 empty] | 2018-12-19 |  | 2019-08-28 | Yes | EXP |  | 2019-04-19 | 2019-04-18 | 0 | 0 | 0 |  |  | 2019-05-25 | Connected |  | No
National Grid | GRANBY | 192330 | 1033 | 11.4 | Solar | 09_527L1 | 2018-07-31 12:35 | 2018-08-16 | 12 | 0 | 12 | 2018-09-05 | 2018-10-02 | 19 | 0 | 19 | [20 empty] | 2018-11-01 | 2018-07-31 12:47 | 2020-09-14 |  | EXP | [8 empty] | 2020-07-23 | Connected |  | No
National Grid | BELLINGHAM | 192331 | 2019 | 3.8 | Solar | 05_344W4 | 2018-07-31 12:47 | 2018-08-22 | 3 | 3 | 0 | 2018-08-27 | 2018-08-27 | 0 | 0 | 0 | [20 empty] | 2018-08-27 | 2018-07-31 14:07 | 2020-05-14 | Yes | EXP |  | 2019-11-06 | 2019-12-17 | 41 | 0 | 41 |  |  | 2020-01-28 | Connected |  | No
National Grid | FALL RIVER | 192209 | 2721 | 17.6 | Solar | 05_115W45 | 2018-07-31 14:07 | 2018-08-15 | 12 | 2 | 10 | 2018-08-31 | 2018-09-12 | 7 | 0 | 7 | [20 empty] | 2018-10-04 |  |  | Yes | EXP | [8 empty] | 2019-03-27 | Connected |  | No
National Grid | GARDNER | 192422 | 1440 | 100 | Solar | 01_607W2 | 2018-08-01 | 2018-08-03 | 11 | 0 | 11 | 2018-08-21 | 2018-08-21 | 0 | 0 | 0 | [20 empty] | 2018-08-27 |  | 2020-01-07 |  | EXP |  | 2019-11-13 | 2019-11-12 | 0 | 0 | 0 |  |  | 2020-01-07 | Connected |  | No
National Grid | BELLINGHAM | 192457 | 2019 | 3.8 | Solar | 05_344W4 | 2018-08-01 13:20 | 2018-08-21 | 5 | 4 | 1 | 2018-08-28 | 2018-09-11 | 9 | 0 | 9 | [20 empty] | 2018-09-11 | 2018-08-01 13:38 | 2019-10-30 |  | EXP | [8 empty] | 2019-10-10 | Connected |  | No
National Grid | EAST BRIDGEWATER | 191425 | 2333 | 10 | Solar | 07_797W42 | 2018-08-01 13:38 | 2018-08-14 | 24 | 13 | 11 | 2018-09-19 | 2018-09-27 | 6 | 0 | 6 | [20 empty] | 2018-09-28 | 2018-08-01 14:36 |  | Yes | EXP | [8 empty] | 2019-04-20 | Connected |  | No
National Grid | SALEM | 192482 | 1970 | 7.6 | Solar | 12_2W1 | 2018-08-01 14:36 | 2018-08-30 | 22 | 22 | 0 | 2018-10-02 | 2018-10-02 | 0 | 0 | 0 | [20 empty] | 2018-10-02 |  | 2020-04-22 | Yes | EXP |  | 2019-11-15 | 2019-12-23 | 38 | 0 | 38 |  |  | 2020-01-06 | Connected |  | No
National Grid | MARLBOROUGH | 191496 | 1752 | 10 | Solar | 05_311W2 | 2018-08-01 15:15 | 2018-08-08 | 9 | 4 | 5 | 2018-08-22 | 2018-08-21 | 0 | 0 | 0 | [20 empty] | 2019-03-11 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 189036 | 1604 | 57.6 | Solar | 01_8W1 | 2018-08-01 15:28 | 2018-08-02 |  |  |  | 2018-08-02 | 2019-02-14 | 134 | 26 | 108 | [20 empty] | 2019-02-20 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | SOUTH EASTON | 192507 | 2375 | 15.2 | Solar | 07_92W79 | 2018-08-01 16:17 | 2018-08-03 | 8 | 0 | 8 | 2018-08-16 | 2018-08-16 | 0 | 0 | 0 | [20 empty] | 2018-08-27 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RANDOLPH | 192557 | 2368 | 15.2 | Solar | 07_97W2 | 2018-08-02 10:17 | 2018-08-03 | 7 | 0 | 7 | 2018-08-16 | 2018-08-17 | 1 | 0 | 1 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | QUINCY | 186049 | 2171 | 1005.6 | Solar | 07_11W3 | 2018-08-02 11:29 | 2018-08-03 | 44 | 38 | 6 | [10 empty] | 2018-10-05 | 2018-12-28 | 60 | 40 | 20 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | MELROSE | 192454 | 2176 | 10 | Solar | 12_25W5 | 2018-08-02 12:45 | 2018-08-09 | 2 | 2 | 0 | 2018-08-13 | 2018-08-13 | 0 | 0 | 0 | [20 empty] | 2018-08-27 |  |  |  | EXP | [8 empty] | 2019-03-21 | Connected |  | No
National Grid | PETERSHAM | 178746 | 1366 | 990 | Solar | 09_604W1 | 2018-08-02 14:14 | 2018-08-03 | 5 | 0 | 5 | [10 empty] | 2018-08-13 | 2018-09-05 | 16 | 1 | 15 | [11 empty] | 2018-08-04 16:10 | 2019-04-24 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | AUBURN | 191422 | 1501 | 10 | Solar | 01_406L2 | 2018-08-04 16:10 | 2018-09-11 | 3 | 3 | 0 | 2018-09-14 | 2018-09-26 | 8 | 0 | 8 | [20 empty] | 2018-09-26 |  | 2019-06-28 | Yes | EXP |  | 2019-03-26 | 2019-04-01 | 6 | 0 | 6 |  |  | 2019-06-24 | Connected |  | No
National Grid | BROCKTON | 191161 | 2301 | 250 | Solar | 07_94W40 | 2018-08-04 18:26 | 2018-08-01 | 17 | 0 | 17 | 2018-08-24 | 2018-08-24 | 0 | 0 | 0 | [20 empty] | 2018-08-27 |  | 2021-04-09 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WALES | 189866 | 1081 | 4000 | Solar | 09_516L1 | 2018-08-06 | 2018-08-13 | 38 | 0 | 38 | [10 empty] | 2018-10-08 | 2018-12-15 | 51 | 30 | 21 | [5 empty] | 2020-07-10 | 2020-10-02 | 60 | 3 | 57 |  |  |  |  | STD | [9 empty] | Group Study |  | No
National Grid | WORCESTER | 192164 | 1603 | 249.8 | Solar | 01_HT27 | 2018-08-06 | 2018-08-08 | 18 | 0 | 18 | 2018-09-05 | 2018-09-28 | 17 | 0 | 17 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | LEICESTER | 192732 | 1524 | 4580 | Solar | 01_21W1 | 2018-08-06 | 2018-08-08 | 256 | 20 | 236 | [10 empty] | 2018-09-24 | 2018-10-17 | 17 | 12 | 5 | [11 empty] | 2018-08-06 08:37 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 192789 | 2301 | 10 | Solar | 07_20W13 | 2018-08-06 08:37 | 2018-08-30 | 7 | 6 | 1 | 2018-09-10 | 2018-09-26 | 12 | 0 | 12 | [20 empty] | 2018-09-26 | 2018-08-06 08:56 | 2019-10-30 | Yes | EXP |  | 2019-04-26 | 2019-05-17 | 21 | 0 | 21 |  |  | 2019-10-07 | Connected |  | No
National Grid | FALL RIVER | 192619 | 2721 | 10 | Solar | 05_115W45 | 2018-08-06 08:56 | 2018-08-22 | 7 | 2 | 5 | 2018-08-31 | 2018-09-13 | 8 | 0 | 8 | [20 empty] | 2018-09-28 |  |  | Yes | EXP | [8 empty] | 2019-03-28 | Connected |  | No
National Grid | BROCKTON | 188889 | 2302 | 10 | Solar | 07_911W56 | 2018-08-06 17:13 | 2018-08-07 | [28 empty] | 2018-08-07 |  |  |  | EXP | [9 empty] | Connected |  | No
National Grid | WESTPORT | 186693 | 2790 | 3300 | Solar | 05_115W52 | 2018-08-07 | 2018-08-28 | 15 | 1 | 14 | [10 empty] | 2018-09-24 | 2018-11-01 | 29 | 10 | 19 | [10 empty] | 2020-02-19 | 2018-08-07 09:44 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 192232 | 1607 | 199.8 | Solar | 01_8W1 | 2018-08-07 09:44 | 2018-08-08 | 10 | 0 | 10 | 2018-08-23 | 2018-09-07 | 10 | 0 | 10 | [20 empty] | 2018-12-12 |  | 2021-02-17 | Yes | EXP |  | 2019-12-21 | 2021-03-01 | 437 | 268 | 169 |  |  | 2021-03-16 | Connected |  | No
National Grid | DRACUT | 192918 | 1826 | 7.6 | Solar | 14_78L1 | 2018-08-07 09:49 | 2018-10-18 | 7 | 7 | 0 | 2018-10-29 | 2018-11-06 | 6 | 0 | 6 | [20 empty] | 2018-11-06 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEST NEWBURY | 192934 | 1985 | 7.6 | Solar | 14_47L1 | 2018-08-07 10:45 | 2018-08-24 | 3 | 3 | 0 | 2018-08-29 | 2018-09-11 | 8 | 0 | 8 | [20 empty] | 2018-09-11 | 2018-08-07 17:50 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHELMSFORD | 184585 | 1824 | 1920 | Solar | 14_2384 | 2018-08-07 17:50 | 2018-08-09 | 10 | 0 | 10 | [10 empty] | 2018-08-23 | 2018-11-27 | 58 | 38 | 20 | [10 empty] | 2019-03-05 |  | 2021-12-30 | Yes | STD | [8 empty] | 2021-12-30 | Connected |  | No
National Grid | FALL RIVER | 189412 | 2723 | 740 | Solar | 05_106W82 | 2018-08-08 | 2018-08-16 | 44 | 37 | 7 | [10 empty] | 2018-10-18 | 2018-11-15 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | REVERE | 192939 | 2151 | 7.6 | Solar | 12_7W2 | 2018-08-08 14:52 | 2018-08-16 | 12 | 0 | 12 | 2018-09-05 | 2018-09-28 | 17 | 0 | 17 | [20 empty] | 2018-10-04 | 2018-08-08 17:09 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SALISBURY | 193070 | 1952 | 246.5 | Solar | 14_7L4 | 2018-08-08 17:09 | 2018-08-09 | 9 | 0 | 9 | [5 empty] | 2018-10-26 | 2018-11-01 | 5 | 1 | 4 | 2018-08-23 | 2018-09-26 | 24 | 6 | 18 | 2018-10-26 | 2018-11-01 | 5 | 1 | 4 | [5 empty] | 2020-04-15 |  | 2022-11-23 | Yes | STD | [8 empty] | 2022-10-25 | Connected |  | No
National Grid | UXBRIDGE | 187429 | 1569 | 1250 | Solar | 05_321W4 | 2018-08-08 17:31 | 2018-08-09 | 11 | 6 | 5 | [10 empty] | 2018-08-24 | 2018-12-14 | 76 | 35 | 41 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 193107 | 1605 | 10 | Solar | 01_24W1 | 2018-08-08 23:28 | 2018-09-05 | 38 | 28 | 10 | 2018-10-29 | 2018-12-20 | 36 | 8 | 28 | 2018-11-06 | 2019-09-17 | 215 | 8 | 207 | [5 empty] | 2018-11-06 | 2019-09-17 | 215 | 8 | 207 | [5 empty] | 2018-12-26 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LYNN | 193190 | 1902 | 5 | Solar | 12_1394 | 2018-08-09 16:51 | 2018-09-13 | 27 | 26 | 1 | 2018-10-23 | 2018-11-13 | 14 | 0 | 14 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WILBRAHAM | 192640 | 1095 | 250 | Solar | 09_523L1 | 2018-08-10 | 2018-08-13 | 15 | 0 | 15 | 2018-09-05 | 2018-12-05 | 81 | 44 | 37 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | LAWRENCE | 190234 | 1841 | 70.2 | Solar | 14_8L2 | 2018-08-10 09:29 | 2018-08-13 | 11 | 0 | 11 | 2018-08-29 | 2018-08-28 | 0 | 0 | 0 | [20 empty] | 2018-10-17 | 2018-08-10 09:59 | 2020-06-30 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | DRACUT | 193202 | 1826 | 15.2 | Solar | 14_78L1 | 2018-08-10 09:59 | 2018-08-30 | 6 | 6 | 0 | 2018-09-11 | 2018-09-19 | 6 | 0 | 6 | [20 empty] | 2018-09-19 |  | 2020-07-07 | Yes | EXP |  | 2019-02-14 | 2019-03-11 | 25 | 0 | 25 |  |  | 2020-06-19 | Connected |  | No
National Grid | LAWRENCE | 193240 | 1841 | 6 | Solar | 14_74L3 | 2018-08-10 14:36 | 2018-09-28 | 42 | 34 | 8 | 2018-12-03 | 2019-01-02 | 21 | 10 | 11 | [20 empty] | 2019-01-02 | 2018-08-10 16:39 | 2020-08-10 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SWANSEA | 193254 | 2777 | 6 | Solar | 05_11W83 | 2018-08-10 16:39 | 2018-09-18 | 15 | 15 | 0 | 2018-10-09 | 2018-10-17 | 7 | 6 | 1 | [20 empty] | 2018-10-17 |  | 2019-10-30 | Yes | EXP |  | 2019-05-08 | 2019-05-07 | 0 | 0 | 0 |  |  | 2019-06-04 | Connected |  | No
National Grid | LEOMINSTER | 193270 | 1453 | 3.8 | Solar | 01_219W6 | 2018-08-11 15:42 | 2018-09-20 | 3 | 3 | 0 | 2018-09-25 | 2018-09-25 | 0 | 0 | 0 | [20 empty] | 2018-09-24 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FALL RIVER | 193191 | 2721 | 199.9 | Solar | 05_115W53 | 2018-08-13 | 2018-09-14 | 21 | 17 | 4 | 2018-10-16 | 2018-11-20 | 23 | 0 | 23 | 2018-12-07 | 2019-01-24 | 32 | 12 | 20 | [5 empty] | 2018-12-07 | 2019-01-24 | 32 | 12 | 20 | [9 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | FALL RIVER | 193334 | 2721 | 119.9 | Solar | 05_115W53 | 2018-08-13 | 2018-10-12 | 6 | 1 | 5 | 2018-10-23 | 2018-12-28 | 45 | 29 | 16 | [20 empty] | 2018-12-28 |  | 2020-06-30 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FALL RIVER | 193337 | 2721 | 290 | Solar | 05_115W53 | 2018-08-13 | 2018-10-10 | 2 | 0 | 2 | 2018-10-15 | 2018-11-20 | 26 | 5 | 21 | 2018-12-07 | 2019-01-24 | 32 | 11 | 21 | [5 empty] | 2018-12-07 | 2019-01-24 | 32 | 11 | 21 | [6 empty] | 2018-08-13 19:45 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTHAMPTON | 193373 | 1060 | 5 | Solar | 09_901W1 | 2018-08-13 19:45 | 2018-08-24 | 24 | 23 | 1 | 2018-09-28 | 2018-10-08 | 7 | 7 | 0 | [20 empty] | 2018-10-08 |  | 2020-02-24 | Yes | EXP |  | 2019-11-01 | 2019-11-04 | 3 | 0 | 3 |  |  | 2020-01-31 | Connected |  | No
National Grid | EAST LONGMEADOW | 189959 | 1028 | 83.3 | Solar | 09_508L5 | 2018-08-14 | 2018-08-17 | 0 | 0 | 0 | 2018-08-17 | 2018-08-20 | 1 | 0 | 1 | [20 empty] | 2018-09-20 |  | 2020-09-30 |  | EXP | [8 empty] | 2024-02-14 | Connected |  | No
National Grid | WESTBOROUGH | 193382 | 1581 | 3.8 | Solar | 05_317W1 | 2018-08-14 01:46 | 2018-08-30 | 2 | 2 | 0 | 2018-09-04 | 2018-09-07 | 3 | 0 | 3 | [20 empty] | 2018-09-07 | 2018-08-14 10:09 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MILLBURY | 193416 | 1527 | 24 | Solar | 01_304W5 | 2018-08-14 10:09 | 2018-08-15 | 13 | 0 | 13 | 2018-09-05 | 2018-10-04 | 21 | 0 | 21 | [20 empty] | 2018-10-04 |  |  | Yes | EXP |  | 2019-08-21 | 2019-09-11 | 21 | 0 | 21 |  |  | 2019-12-05 | Connected |  | No
National Grid | HAVERHILL | 193466 | 1832 | 15.2 | Solar | 14_74L5 | 2018-08-14 13:38 | 2018-08-15 | 13 | 0 | 13 | 2018-09-05 | 2018-10-04 | 22 | 2 | 20 | [20 empty] | 2018-10-29 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BRIMFIELD | 188873 | 1010 | 150 | Solar | 09_516L1 | 2018-08-14 14:23 | 2018-08-15 | 13 | 4 | 9 | 2018-09-05 | 2018-10-19 | 83 | 2 | 81 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTH GRAFTON | 193486 | 1536 | 3.8 | Solar | 01_328W2 | 2018-08-14 14:29 | 2018-08-24 | 13 | 2 | 11 | 2018-09-13 | 2018-09-13 | 0 | 0 | 0 | [20 empty] | 2018-12-11 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BRIMFIELD | 190328 | 1010 | 2820 | Solar | 09_503L4 | 2018-08-14 15:39 | 2018-08-15 | 3 | 0 | 3 | [10 empty] | 2018-08-21 | 2018-10-09 | 34 | 9 | 25 | [11 empty] | 2018-08-14 17:59 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | DOUGLAS | 193521 | 1516 | 2000 | Solar | 05_320W5 | 2018-08-14 17:59 | 2018-08-15 | 8 | 0 | 8 | [10 empty] | 2018-08-28 | 2018-10-31 | 46 | 27 | 19 | [10 empty] | 2020-08-10 |  | 2024-04-24 | Yes | STD |  | 2023-07-12 |  | 280 | 98 | 182 |  |  |  | Construction |  | No
National Grid | GARDNER | 193550 | 1440 | 250 | Solar | 01_607W4 | 2018-08-15 | 2018-08-17 | 6 | 0 | 6 | 2018-08-28 | 2018-08-27 | 0 | 0 | 0 | [21 empty] | 2018-08-15 11:27 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MENDON | 193531 | 1756 | 7.6 | Solar | 05_321W6 | 2018-08-15 11:27 | 2018-09-20 | 7 | 0 | 7 | 2018-10-02 | 2018-11-05 | 25 | 0 | 25 | [20 empty] | 2018-12-20 |  |  | Yes | EXP | [8 empty] | 2019-11-15 | Connected |  | No
National Grid | NORTH GRAFTON | 193597 | 1536 | 3.8 | Solar | 01_328W2 | 2018-08-15 13:41 | 2018-08-28 | 7 | 7 | 0 | 2018-09-10 | 2018-09-11 | 1 | 0 | 1 | [20 empty] | 2018-09-11 | 2018-08-15 15:10 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RANDOLPH | 193636 | 2368 | 10 | Solar | 07_97W3 | 2018-08-15 15:10 | 2018-08-29 | 46 | 22 | 24 | 2018-11-02 | 2018-11-19 | 10 | 0 | 10 | [20 empty] | 2019-01-03 |  | 2020-10-08 | Yes | EXP |  | 2019-10-23 | 2019-11-13 | 21 | 0 | 21 |  |  | 2020-01-03 | Connected |  | No
National Grid | LEOMINSTER | 193664 | 1453 | 7.6 | Solar | 01_219W3 | 2018-08-15 17:56 | 2018-08-30 | 4 | 4 | 0 | 2018-09-06 | 2018-09-06 | 0 | 0 | 0 | [20 empty] | 2018-09-07 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTHAMPTON | 190337 | 1053 | 3800 | Solar | 09_909W3 | 2018-08-16 | 2018-08-22 | 3 | 0 | 3 | [10 empty] | 2018-08-29 | 2018-09-07 | 7 | 7 | 0 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WEBSTER | 190340 | 1570 | 1500 | Solar | 01_412L2 | 2018-08-16 | 2018-08-22 | 3 | 0 | 3 | [10 empty] | 2018-09-13 | 2018-11-12 | 42 | 8 | 34 | [11 empty] | 2018-08-16 11:49 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 186717 | 2302 | 7.6 | Solar | 07_911W56 | 2018-08-16 11:49 | 2018-08-22 | 28 | 18 | 10 | 2018-10-02 | 2018-10-02 | 0 | 0 | 0 | [20 empty] | 2018-10-16 | 2018-08-17 | 2020-09-23 | Yes | EXP |  | 2019-10-22 | 2019-10-30 | 8 | 0 | 8 |  |  | 2020-06-11 | Connected |  | No
National Grid | GRAFTON | 193678 | 1519 | 250 | Solar | 01_304W1 | 2018-08-17 | 2018-08-21 | 4 | 0 | 4 | 2018-08-28 | 2018-08-28 | 0 | 0 | 0 | 2019-09-27 | 2019-11-26 | 40 | 20 | 20 | [5 empty] | 2019-09-27 | 2019-11-26 | 40 | 20 | 20 | [5 empty] | 2019-12-12 |  | 2021-05-17 | Yes | EXP | [8 empty] | 2021-04-28 | Connected |  | No
National Grid | WORCESTER | 193768 | 1606 | 10 | Solar | 01_24W3 | 2018-08-17 10:38 | 2018-10-03 | 7 | 7 | 0 | 2018-10-15 | 2018-10-16 | 2 | 1 | 1 | [20 empty] | 2018-11-01 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | TYNGSBORO | 193772 | 1879 | 15.2 | Solar | 14_211L2 | 2018-08-17 10:47 | 2018-08-20 | 7 | 0 | 7 | 2018-08-30 | 2018-10-02 | 22 | 0 | 22 | [20 empty] | 2018-11-01 | 2018-08-17 14:45 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EAST LONGMEADOW | 193803 | 1028 | 299.7 | Solar | 09_508L5 | 2018-08-17 14:45 | 2018-08-20 | 3 | 0 | 3 | 2018-08-24 | 2018-10-02 | 27 | 26 | 1 | [20 empty] | 2019-01-17 |  | 2020-11-24 | Yes | EXP | [8 empty] | 2020-11-24 | Connected |  | No
National Grid | STURBRIDGE | 193813 | 1566 | 86.4 | Solar | 01_408L1 | 2018-08-17 14:46 | 2018-08-20 | 3 | 0 | 3 | 2018-08-24 | 2019-08-21 | 248 | 0 | 248 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | MARLBOROUGH | 193822 | 1752 | 15.2 | Solar | 05_311W2 | 2018-08-17 14:59 | 2018-08-22 | 82 | 26 | 56 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WILLIAMSTOWN | 191459 | 1267 | 35.4 | Solar | 09_1003W1 | 2018-08-20 | 2018-08-22 | 0 | 0 | 0 | 2018-08-23 | 2018-08-28 | 3 | 0 | 3 | [20 empty] | 2018-08-28 |  |  |  | EXP | [8 empty] | 2019-03-08 | Connected |  | No
National Grid | BILLERICA | 192826 | 1821 | 3.64 | Solar | 14_92L2 | 2018-08-20 11:29 | 2018-09-05 | 7 | 1 | 6 | 2018-09-14 | 2018-12-21 | 68 | 3 | 65 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MARLBOROUGH | 193918 | 1752 | 6 | Solar | 05_311W3 | 2018-08-20 12:09 | 2018-09-07 | 27 | 24 | 3 | 2018-10-15 | 2018-10-17 | 2 | 0 | 2 | [20 empty] | 2018-10-17 |  |  |  | EXP | [8 empty] | 2019-02-12 | Connected |  | No
National Grid | WORCESTER | 193914 | 1607 | 60 | Solar | 01_8W1 | 2018-08-20 15:30 | 2018-08-21 | 6 | 0 | 6 | 2018-08-30 | 2018-10-04 | 24 | 0 | 24 | [20 empty] | 2018-11-01 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GRANBY | 193939 | 1033 | 2500 | Solar | 09_527L1 | 2018-08-20 16:05 | 2018-08-21 | 18 | 0 | 18 | [10 empty] | 2018-09-18 | 2019-01-26 | 136 | 52 | 84 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 194001 | 2301 | 15.2 | Solar | 07_911W13 | 2018-08-20 19:49 | 2018-08-21 | 3 | 2 | 1 | 2018-08-24 | 2018-08-24 | 0 | 0 | 0 | [20 empty] | 2018-08-24 |  | 2019-10-30 |  | EXP | [8 empty] | 2019-10-07 | Connected |  | No
National Grid | DRACUT | 194002 | 1826 | 15.2 | Solar | 14_78L3 | 2018-08-20 20:09 | 2018-08-21 | 20 | 10 | 10 | 2018-10-11 | 2019-01-28 | 71 | 53 | 18 | [20 empty] | 2019-01-30 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MELROSE | 191843 | 2176 | 50 | Solar | 12_25W4 | 2018-08-21 | 2018-09-05 | 8 | 2 | 6 | [25 empty] | 2019-04-04 |  | 2019-11-29 |  | EXP | [8 empty] | 2019-11-19 | Connected |  | No
National Grid | BEVERLY | 193913 | 1915 | 112.5 | Solar | 12_12L4 | 2018-08-21 10:40 | 2018-08-22 | 6 | 5 | 1 | 2018-08-30 | 2018-10-04 | 50 | 0 | 50 | [20 empty] | 2019-03-04 |  | 2019-11-15 |  | EXP | [8 empty] | 2019-12-17 | Connected |  | No
National Grid | ABINGTON | 194058 | 2351 | 9.92 | Solar | 07_712J1 | 2018-08-21 12:49 | 2018-08-22 | 31 | 24 | 7 | 2018-10-11 | 2018-10-11 | 1 | 1 | 0 | [20 empty] | 2018-11-15 |  |  |  | EXP | [8 empty] | 2019-07-02 | Connected |  | No
National Grid | WINCHENDON | 192564 | 1475 | 4950 | Solar | 01_612W1 | 2018-08-21 13:57 | 2018-08-22 | 4 | 1 | 3 | [10 empty] | 2018-08-28 | 2018-09-28 | 69 | 3 | 66 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | PALMER | 193761 | 1069 | 680 | Solar | 09_514L1 | 2018-08-22 08:38 | 2018-08-23 | 18 | 14 | 4 | [10 empty] | 2018-09-20 | 2018-11-03 | 36 | 10 | 26 | [5 empty] | 2020-07-10 | 2020-10-02 | 60 | 3 | 57 |  |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LEOMINSTER | 194206 | 1453 | 10 | Solar | 01_225W4 | 2018-08-22 14:18 | 2018-08-29 | 248 | 248 | 0 | 2019-08-14 | 2019-08-13 | 0 | 0 | 0 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | AMESBURY | 193105 | 1913 | 130 | Solar | 14_66L1 | 2018-08-22 14:23 | 2018-08-30 |  |  |  | 2018-08-30 | 2019-01-28 | 100 | 0 | 100 | [21 empty] | 2018-08-22 14:31 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | EAST BRIDGEWATER | 186356 | 2333 | 15.2 | Solar | 07_797W23 | 2018-08-22 14:31 | 2018-10-01 | 9 | 9 | 0 | 2018-10-12 | 2018-10-16 | 2 | 0 | 2 | [20 empty] | 2018-10-16 |  | 2019-08-20 | Yes | EXP |  | 2019-05-10 | 2019-06-05 | 26 | 0 | 26 |  |  | 2019-08-08 | Connected |  | No
National Grid | AMESBURY | 194215 | 1913 | 325 | Solar | 14_275L4 | 2018-08-22 17:27 | 2018-08-23 | 3 | 0 | 3 | 2018-08-29 | 2019-01-28 | 101 | 1 | 100 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 193103 | 1844 | 650 | Solar | 14_43L4 | 2018-08-22 17:52 | 2018-08-23 | 45 | 3 | 42 | [10 empty] | 2018-10-26 | 2019-01-31 | 62 | 26 | 36 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | HAVERHILL | 194210 | 1835 | 120 | Solar | 14_43L8 | 2018-08-22 17:56 | 2018-08-23 | 36 | 0 | 36 | 2018-10-16 | 2019-01-28 | 68 | 26 | 42 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTBOROUGH | 194239 | 1581 | 15.2 | Solar | 05_312W4 | 2018-08-22 18:07 | 2018-08-23 | 19 | 19 | 0 | 2018-09-20 | 2019-09-17 | 248 | 0 | 248 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HAVERHILL | 194203 | 1835 | 240 | Solar | 14_43L8 | 2018-08-22 18:29 | 2018-08-23 | 3 | 0 | 3 | 2018-08-29 | 2019-01-28 | 101 | 0 | 101 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | HAVERHILL | 194207 | 1835 | 180 | Solar | 14_43L8 | 2018-08-22 19:04 | 2018-08-23 | 4 | 0 | 4 | 2018-08-30 | 2019-09-17 | 149 | 0 | 149 | [21 empty] | 2018-08-22 19:07 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BEVERLY | 194242 | 1915 | 10 | Solar | 12_12L2 | 2018-08-22 19:07 | 2018-08-31 | 7 | 6 | 1 | 2018-09-12 | 2018-09-19 | 7 | 2 | 5 | [20 empty] | 2018-09-19 |  | 2019-05-10 | Yes | EXP |  | 2018-11-30 | 2019-04-12 | 133 | 0 | 133 |  |  | 2019-04-19 | Connected |  | No
National Grid | SOUTHBRIDGE | 192559 | 1550 | 5786 | Solar | 01_413L6 | 2018-08-23 08:29 | 2018-08-24 | 16 | 11 | 5 | [10 empty] | 2018-09-18 | 2019-03-28 | 214 | 110 | 104 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | AUBURN | 194034 | 1501 | 150 | Solar | 01_26W2 | 2018-08-23 09:53 | 2018-08-24 | 0 | 0 | 0 | 2018-08-27 | 2018-08-24 | 0 | 0 | 0 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | SOUTHBRIDGE | 194187 | 1550 | 333 | Solar | 01_413L3 | 2018-08-23 09:55 | 2018-08-24 | 0 | 0 | 0 | 2018-08-24 | 2018-09-21 | 20 | 19 | 1 | 2018-11-15 | 2019-03-11 | 76 | 0 | 76 | [5 empty] | 2018-11-15 | 2019-03-11 | 76 | 0 | 76 | [9 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 194135 | 1844 | 130 | Solar | 14_75L4 | 2018-08-23 12:32 | 2018-08-24 | 0 | 0 | 0 | 2018-08-27 | 2019-01-28 | 103 | 26 | 77 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 194175 | 1844 | 65 | Solar | 14_43L2 | 2018-08-23 12:45 | 2018-08-24 | 35 | 0 | 35 | 2018-10-17 | 2018-11-19 | 22 | 3 | 19 | [20 empty] | 2018-11-27 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | HAVERHILL | 194190 | 1835 | 240 | Solar | 14_43L8 | 2018-08-23 13:37 | 2018-08-24 | 2 | 0 | 2 | 2018-08-29 | 2019-01-28 | 101 | 0 | 101 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | AMESBURY | 193104 | 1913 | 455 | Solar | 14_66L2 | 2018-08-23 14:39 | 2018-08-24 | 2 | 0 | 2 | [10 empty] | 2018-08-29 | 2019-01-28 | 101 | 22 | 79 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | HAVERHILL | 194241 | 1835 | 120 | Solar | 14_43L8 | 2018-08-23 14:43 | 2018-08-24 | 3 | 0 | 3 | 2018-08-30 | 2019-09-17 | 148 | 0 | 148 | [20 empty] | 2018-10-29 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | HAVERHILL | 194218 | 1835 | 300 | Solar | 14_43L8 | 2018-08-23 15:14 | 2018-08-24 | 2 | 0 | 2 | 2018-08-29 | 2018-09-26 | 19 | 0 | 19 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | SALEM | 194178 | 1970 | 146 | Solar | 12_49W2 | 2018-08-24 | 2018-08-29 | 0 | 0 | 0 | 2018-08-30 | 2018-10-04 | 24 | 0 | 24 | [20 empty] | 2018-10-11 |  | 2020-05-26 |  | EXP | [8 empty] | 2020-07-27 | Connected |  | No
National Grid | LEOMINSTER | 194293 | 1453 | 250 | Solar | 01_219W4 | 2018-08-24 | 2018-08-29 | 3 | 0 | 3 | 2018-09-05 | 2019-11-21 | 304 | 56 | 248 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | AUBURN | 194297 | 1501 | 250 | Solar | 01_26W1 | 2018-08-24 | 2018-08-27 | 1 | 0 | 1 | 2018-08-29 | 2018-09-13 | 11 | 11 | 0 | [21 empty] | 2018-08-24 11:58 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BOXFORD | 189024 | 1921 | 20 | Solar | 14_56L3 | 2018-08-24 11:58 | 2018-08-27 | 22 | 15 | 7 | 2018-09-27 | 2018-09-28 | 1 | 0 | 1 | [20 empty] | 2018-10-08 |  |  |  | EXP |  | 2019-03-22 | 2019-03-21 | 0 | 0 | 0 |  |  | 2019-07-03 | Connected |  | No
National Grid | NORTH CHELMSFORD | 194444 | 1863 | 7.6 | Solar | 14_73L2 | 2018-08-26 22:19 | 2018-10-29 | 3 | 3 | 0 | 2018-11-01 | 2018-11-14 | 8 | 0 | 8 | [20 empty] | 2018-11-14 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HANOVER | 191825 | 2339 | 249.8 | Solar | 07_910W52 | 2018-08-27 | 2018-08-28 | 8 | 0 | 8 | 2018-09-11 | 2018-10-12 | 23 | 0 | 23 | [20 empty] | 2018-11-02 |  | 2020-12-31 |  | EXP | [8 empty] | 2020-12-30 | Connected |  | No
National Grid | LAWRENCE | 194466 | 1840 | 480 | Solar | 14_2J8 | 2018-08-27 | 2018-09-17 | 4 | 0 | 4 | 2018-09-24 | 2018-11-05 | 31 | 6 | 25 | [20 empty] | 2019-06-14 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | FALL RIVER | 191028 | 2722 | 233.1 | Solar | 05_115W52 | 2018-08-27 15:52 | 2018-08-30 | 8 | 1 | 7 | 2018-09-11 | 2018-12-12 | 63 | 30 | 33 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | ANDOVER | 194474 | 1810 | 480 | Solar | 14_62L2 | 2018-08-27 16:39 | 2018-08-28 | 5 | 5 | 0 | 2018-09-05 | 2018-12-11 | 66 | 0 | 66 | [20 empty] | 2019-03-13 |  | 2020-09-04 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 191213 | 2301 | 16.2 | Solar | 07_91W43 | 2018-08-28 10:44 | 2018-08-29 | 12 | 2 | 10 | 2018-09-17 | 2018-09-24 | 5 | 0 | 5 | [20 empty] | 2018-11-07 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MILFORD | 194481 | 1757 | 7.6 | Solar | 05_336W3 | 2018-08-28 11:04 | 2018-09-13 | 8 | 8 | 0 | 2018-09-25 | 2018-09-25 | 0 | 0 | 0 | [20 empty] | 2018-09-25 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | DRACUT | 194659 | 1826 | 7.6 | Solar | 14_78L3 | 2018-08-28 16:16 | 2018-08-31 | 8 | 0 | 8 | 2018-09-14 | 2018-09-19 | 3 | 0 | 3 | [20 empty] | 2018-09-26 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTHAMPTON | 190049 | 1060 | 990 | Solar | 09_909W2 | 2018-08-28 17:42 | 2018-08-29 | 59 | 28 | 31 | [10 empty] | 2018-11-26 | 2019-03-22 | 81 | 62 | 19 | [10 empty] | 2021-03-23 |  |  |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | TEWKSBURY | 192658 | 1876 | 10 | Solar | 14_70L8 | 2018-08-28 19:18 | 2018-09-13 | 17 | 17 | 0 | 2018-10-09 | 2018-12-07 | 41 | 27 | 14 | [20 empty] | 2018-12-19 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOUTH EASTON | 186104 | 2375 | 500 | Solar | 07_92W54 | 2018-08-29 | 2018-09-10 | 15 | 5 | 10 | [10 empty] | 2018-10-01 | 2018-10-26 | 20 | 1 | 19 | [10 empty] | 2019-05-17 |  | 2020-05-15 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | HANOVER | 194677 | 2339 | 400 | Solar | 07_910W52 | 2018-08-29 08:38 | 2018-08-31 | 6 | 0 | 6 | 2018-09-11 | 2018-10-12 | 23 | 0 | 23 | [20 empty] | 2018-10-23 | 2018-08-29 11:38 |  |  | EXP | [8 empty] | 2019-11-15 | Connected |  | Yes
National Grid | REVERE | 194567 | 2151 | 7.6 | Solar | 12_16W8 | 2018-08-29 11:38 | 2018-09-10 | 0 | 0 | 0 | 2018-09-11 | 2018-09-11 | 0 | 0 | 0 | [20 empty] | 2018-09-11 |  | 2019-05-28 | Yes | EXP |  | 2019-04-23 | 2019-04-22 | 0 | 0 | 0 |  |  | 2019-05-10 | Connected |  | No
National Grid | UXBRIDGE | 193087 | 1569 | 4280 | Solar | 05_321W1 | 2018-08-29 14:50 | 2018-08-30 | 13 | 13 | 0 | [10 empty] | 2018-09-20 | 2018-10-19 | 21 | 4 | 17 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | MALDEN | 188285 | 2148 | 6 | Solar | 12_16J4 | 2018-08-29 20:21 | 2018-07-30 | 41 | 30 | 11 | 2018-09-26 | 2018-09-25 | 0 | 0 | 0 | [20 empty] | 2018-10-16 |  |  |  | EXP | [8 empty] | 2019-09-19 | Connected |  | No
National Grid | MARLBOROUGH | 194004 | 1752 | 136 | Solar | 05_311W5 | 2018-08-30 | 2018-09-18 | 8 | 5 | 3 | 2018-09-28 | 2018-11-14 | 54 | 25 | 29 | [20 empty] | 2018-12-05 |  | 2019-12-12 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MARLBOROUGH | 194787 | 1752 | 7.6 | Solar | 05_311W3 | 2018-08-30 10:42 | 2018-10-03 | 29 | 25 | 4 | 2018-11-15 | 2018-12-06 | 13 | 0 | 13 | [20 empty] | 2018-12-11 | 2018-08-30 10:59 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | REHOBOTH | 194753 | 2769 | 3060 | Solar | 05_7L4 | 2018-08-30 10:59 | 2018-08-31 | 16 | 4 | 12 | [10 empty] | 2018-09-26 | 2018-10-23 | 19 | 0 | 19 | [10 empty] | 2020-08-13 |  | 2025-01-15 | Yes | STD | [9 empty] | Construction |  | No
National Grid | WRENTHAM | 193188 | 2093 | 1500 | Solar | 05_3422W1 | 2018-08-30 16:08 | 2018-09-25 | 16 | 8 | 8 | [10 empty] | 2018-10-18 | 2018-11-15 | 20 | 1 | 19 | [10 empty] | 2020-07-13 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | CLINTON | 194838 | 1510 | 3.8 | Solar | 01_216W3 | 2018-08-30 16:31 | 2018-09-28 | 21 | 21 | 0 | 2018-10-30 | 2018-11-07 | 6 | 0 | 6 | [20 empty] | 2018-11-07 | 2018-08-31 10:46 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 194731 | 1844 | 10 | Solar | 14_74L4 | 2018-08-31 10:46 | 2018-09-13 | 4 | 4 | 0 | 2018-09-19 | 2018-09-24 | 3 | 0 | 3 | [20 empty] | 2018-09-25 |  | 2019-05-21 | Yes | EXP |  | 2019-03-09 | 2019-04-09 | 31 | 0 | 31 |  |  | 2019-04-16 | Connected |  | No
National Grid | EAST BRIDGEWATER | 194877 | 2333 | 3.8 | Solar | 07_797W29 | 2018-08-31 11:46 | 2018-09-26 | 4 | 4 | 0 | 2018-10-02 | 2018-10-03 | 1 | 0 | 1 | [20 empty] | 2018-10-03 |  | 2019-10-18 |  | EXP | [8 empty] | 2019-09-09 | Connected |  | No
National Grid | METHUEN | 193954 | 1844 | 357 | Hydro | 14_5J45 | 2018-08-31 11:53 | 2018-09-04 | 18 | 18 | 0 | [10 empty] | 2018-09-28 | 2018-09-27 | 0 | 0 | 0 | [10 empty] | 2019-06-13 |  | 2021-02-26 |  | STD | [8 empty] | 2021-02-12 | Connected |  | No
National Grid | METHUEN | 194880 | 1844 | 3.8 | Solar | 14_63L1 | 2018-08-31 11:57 | 2018-10-19 | 7 | 0 | 7 | 2018-10-31 | 2018-11-12 | 7 | 0 | 7 | [20 empty] | 2018-12-24 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | FRANKLIN | 194876 | 2038 | 9.92 | Solar | 05_344W1 | 2018-08-31 15:22 | 2018-10-02 | 8 | 7 | 1 | 2018-10-15 | 2018-10-18 | 3 | 0 | 3 | [20 empty] | 2018-11-02 |  |  |  | EXP | [8 empty] | 2019-04-23 | Connected |  | No
National Grid | FALL RIVER | 194988 | 2724 | 7.6 | Solar | 05_115W42 | 2018-09-04 09:55 | 2018-10-02 | 19 | 19 | 0 | 2018-10-30 | 2018-11-07 | 6 | 0 | 6 | [20 empty] | 2018-11-07 | 2018-09-04 11:17 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RANDOLPH | 194453 | 2368 | 3.8 | Solar | 07_97W5 | 2018-09-04 11:17 | 2018-09-28 | 6 | 6 | 0 | 2018-10-08 | 2018-10-09 | 1 | 0 | 1 | [20 empty] | 2018-10-09 | 2018-09-04 12:04 | 2019-03-05 | Yes | EXP | [8 empty] | 2018-12-14 | Connected |  | No
National Grid | RANDOLPH | 194982 | 2368 | 7.6 | Solar | 07_97W2 | 2018-09-04 12:04 | 2018-09-14 | 17 | 17 | 0 | 2018-10-09 | 2018-10-11 | 2 | 0 | 2 | [20 empty] | 2018-10-11 |  | 2019-05-21 |  | EXP |  | 2018-11-09 | 2019-02-27 | 110 | 0 | 110 |  |  | 2019-04-18 | Connected |  | No
National Grid | LYNN | 195033 | 1904 | 22.8 | Solar | 12_24W2 | 2018-09-04 15:16 | 2018-10-17 | 10 | 10 | 0 | 2018-10-18 | 2018-10-19 | 1 | 0 | 1 | [20 empty] | 2018-11-21 | 2018-09-04 17:51 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | DUDLEY | 195056 | 1571 | 7.6 | Solar | 01_412L4 | 2018-09-04 17:51 | 2018-09-27 | 21 | 21 | 0 | 2018-10-29 | 2018-11-14 | 11 | 2 | 9 | [20 empty] | 2018-11-14 |  | 2019-11-08 | Yes | EXP |  | 2019-07-11 | 2019-09-16 | 67 | 0 | 67 |  |  | 2019-10-09 | Connected |  | No
National Grid | RUTLAND | 195060 | 1543 | 10 | Solar | 01_55W1 | 2018-09-04 18:32 | 2018-09-28 | 11 | 10 | 1 | 2018-10-15 | 2018-10-16 | 1 | 0 | 1 | [20 empty] | 2018-10-16 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MANCHESTER BY THE SEA | 195069 | 1944 | 7.6 | Solar | 12_51T1 | 2018-09-05 09:35 | 2018-09-19 | 10 | 4 | 6 | 2018-10-03 | 2018-10-03 | 0 | 0 | 0 | [20 empty] | 2018-10-17 |  |  |  | EXP | [8 empty] | 2018-12-14 | Connected |  | No
National Grid | BROCKTON | 193582 | 2301 | 490 | Solar | 07_94W40 | 2018-09-05 10:56 | 2018-09-06 | 17 | 10 | 7 | [10 empty] | 2018-10-02 | 2019-02-23 | 154 | 83 | 71 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | MELROSE | 195099 | 2176 | 7.6 | Solar | 12_25W5 | 2018-09-05 12:10 | 2018-09-24 | 3 | 3 | 0 | 2018-09-27 | 2018-09-27 | 0 | 0 | 0 | [20 empty] | 2018-09-27 | 2018-09-05 12:42 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GARDNER | 195106 | 1440 | 10 | Solar | 01_607W5 | 2018-09-05 12:42 | 2018-11-30 | 20 | 13 | 7 | 2019-01-02 | 2019-01-09 | 5 | 0 | 5 | [20 empty] | 2019-01-11 |  | 2020-12-31 | Yes | EXP | [8 empty] | 2020-04-21 | Connected |  | No
National Grid | METHUEN | 195141 | 1844 | 15.2 | Solar | 14_63L2 | 2018-09-05 15:07 | 2018-09-05 | 31 | 26 | 5 | 2018-10-18 | 2018-10-22 | 2 | 0 | 2 | [20 empty] | 2018-10-22 |  | 2019-07-05 |  | EXP | [8 empty] | 2019-06-21 | Connected |  | No
National Grid | HUDSON | 195130 | 1749 | 479.904 | Solar | 05_318W3 | 2018-09-06 | 2018-09-17 | 4 | 0 | 4 | 2018-09-24 | 2018-10-29 | 26 | 1 | 25 | [20 empty] | 2018-11-08 | 2018-09-06 15:29 | 2020-05-31 |  | EXP | [8 empty] | 2020-09-01 | Connected |  | No
National Grid | RANDOLPH | 195014 | 2368 | 7.6 | Solar | 07_97W5 | 2018-09-06 15:29 | 2018-09-20 | 3 | 3 | 0 | 2018-09-25 | 2018-09-25 | 22 | 0 | 22 | [20 empty] | 2018-09-24 |  | 2019-03-05 | Yes | EXP | [8 empty] | 2019-01-16 | Connected |  | No
National Grid | WENDELL | 192888 | 1379 | 1000 | Solar | 09_705W1 | 2018-09-07 13:46 | 2018-09-10 | 11 | 0 | 11 | [10 empty] | 2018-09-26 | 2018-11-07 | 30 | 11 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 195391 | 2301 | 7.6 | Solar | 07_911W13 | 2018-09-07 23:08 | 2018-09-27 | 14 | 8 | 6 | 2018-10-18 | 2018-11-19 | 22 | 11 | 11 | [20 empty] | 2019-01-07 |  | 2019-05-07 |  | EXP | [8 empty] | 2019-05-04 | Connected |  | No
National Grid | MARLBOROUGH | 185773 | 1752 | 7000 | Solar | 05_310W5 | 2018-09-07 23:47 | 2018-09-10 | 62 | 32 | 30 | [29 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SPENCER | 189868 | 1535 | 4800 | Solar | 01_552L1 | 2018-09-10 13:14 | 2018-09-11 | 26 | 17 | 9 | [10 empty] | 2018-10-19 | 2018-12-08 | 33 | 14 | 19 | [11 empty] | 2018-09-10 14:11 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | AMESBURY | 195497 | 1913 | 7.6 | Solar | 14_5J11 | 2018-09-10 14:11 | 2018-10-19 | 7 | 0 | 7 | 2018-10-31 | 2018-11-12 | 7 | 0 | 7 | [20 empty] | 2018-11-28 |  | 2020-10-30 | Yes | EXP |  | 2020-02-14 | 2020-02-18 | 4 | 0 | 4 |  |  | 2020-05-04 | Connected |  | No
National Grid | LEOMINSTER | 189869 | 1453 | 4999 | Solar | 01_207W6 | 2018-09-10 15:47 | 2018-09-11 | 2 | 0 | 2 | [10 empty] | 2018-09-14 | 2018-11-19 | 46 | 20 | 26 | [10 empty] | 2021-05-18 |  | 2022-09-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH GRAFTON | 195088 | 1536 | 10 | Solar | 01_304W1 | 2018-09-10 16:52 | 2018-10-19 | 9 | 8 | 1 | 2018-11-01 | 2018-11-13 | 7 | 0 | 7 | [20 empty] | 2018-12-21 |  |  |  | EXP | [8 empty] | 2019-05-07 | Connected |  | No
National Grid | WARREN | 188705 | 1083 | 7999 | Solar | 09_516L1 | 2018-09-10 20:39 | 2018-09-11 | 2 | 0 | 2 | [10 empty] | 2018-09-14 | 2018-11-17 | 45 | 26 | 19 | [5 empty] | 2020-07-10 | 2020-10-02 | 60 | 3 | 57 |  |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HAVERHILL | 193992 | 1835 | 650 | Solar | 14_43L8 | 2018-09-11 08:40 | 2018-09-18 | 9 | 0 | 9 | [10 empty] | 2018-10-02 | 2019-01-31 | 81 | 0 | 81 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 195563 | 1844 | 180 | Solar | 14_63L2 | 2018-09-11 09:08 | 2018-09-12 | 15 | 0 | 15 | 2018-10-04 | 2018-11-13 | 28 | 3 | 25 | [20 empty] | 2019-03-19 |  | 2020-06-30 |  | EXP | [8 empty] | 2020-02-20 | Connected |  | No
National Grid | SUTTON | 189175 | 1590 | 2050 | Solar | 01_304W6 | 2018-09-11 10:07 | 2018-09-18 | 23 | 15 | 8 | [10 empty] | 2018-10-19 | 2018-11-23 | 23 | 4 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 195599 | 1603 | 7.6 | Solar | 01_7J386 | 2018-09-11 11:27 | 2018-10-19 | 26 | 20 | 6 | 2018-12-04 | 2018-12-18 | 10 | 0 | 10 | [20 empty] | 2019-03-11 | 2018-09-11 14:59 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GARDNER | 195651 | 1440 | 5 | Solar | 01_607W4 | 2018-09-11 14:59 | 2018-10-03 | 15 | 15 | 0 | 2018-10-25 | 2018-11-01 | 5 | 0 | 5 | [20 empty] | 2018-11-01 |  | 2019-04-26 | Yes | EXP | [8 empty] | 2019-03-13 | Connected |  | No
National Grid | MALDEN | 192277 | 2148 | 340 | Solar | 12_37W1 | 2018-09-11 15:29 | 2018-09-12 | 1 | 0 | 1 | 2018-09-14 | 2018-10-23 | 27 | 0 | 27 | [20 empty] | 2019-02-22 | 2018-09-11 17:25 | 2021-05-10 |  | EXP |  | 2020-02-13 | 2021-05-06 | 449 | 5 | 444 |  |  | 2021-05-19 | Connected |  | No
National Grid | EAST BRIDGEWATER | 193184 | 2333 | 780 | Solar | 07_797W29 | 2018-09-11 17:25 | 2018-09-12 | 10 | 9 | 1 | [10 empty] | 2018-09-26 | 2018-11-06 | 30 | 11 | 19 | [10 empty] | 2019-03-08 |  | 2021-11-10 | Yes | STD |  | 2021-06-11 | 2021-09-27 | 90 | 3 | 87 | 2021-10-01 | 2021-10-01 | 2021-10-07 | Connected |  | No
National Grid | SALEM | 195677 | 1970 | 5 | Solar | 12_29W6 | 2018-09-11 18:46 | 2018-10-26 | 12 | 11 | 1 | 2018-11-13 | 2018-11-16 | 2 | 0 | 2 | [20 empty] | 2018-11-16 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SEEKONK | 195174 | 2771 | 480 | Solar | 05_7L2 | 2018-09-12 | 2018-09-14 | 8 | 5 | 3 | 2018-09-26 | 2018-10-30 | 24 | 0 | 24 | [20 empty] | 2018-11-16 |  | 2020-06-30 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WARD HILL | 195374 | 1835 | 240 | Solar | 14_43L8 | 2018-09-12 | 2018-09-14 | 4 | 0 | 4 | 2018-09-24 | 2018-10-30 | 27 | 11 | 16 | [20 empty] | 2019-03-19 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | REVERE | 195384 | 2151 | 499.9 | Solar | 12_7W2 | 2018-09-12 | 2018-09-14 | 5 | 0 | 5 | 2018-09-24 | 2018-10-26 | 24 | 0 | 24 | [20 empty] | 2018-11-05 |  | 2020-12-31 |  | EXP | [8 empty] | 2020-10-22 | Connected |  | No
National Grid | BERLIN | 195692 | 1503 | 1 | Solar | 05_318W3 | 2018-09-12 09:01 | 2020-03-10 | [32 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | FLORIDA | 189359 | 1247 | 4000 | Solar | 09_1015W1 | 2018-09-12 09:29 | 2018-09-13 | 16 | 3 | 13 | [10 empty] | 2018-10-08 | 2018-11-08 | 94 | 42 | 52 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | GLOUCESTER | 195777 | 1930 | 147.6 | Solar | 12_51T1 | 2018-09-12 17:02 | 2018-09-13 | 4 | 0 | 4 | 2018-09-20 | 2018-10-18 | 20 | 0 | 20 | 2019-09-13 | 2019-09-12 | 0 | 0 | 0 | [5 empty] | 2019-09-13 | 2019-09-12 | 0 | 0 | 0 | [5 empty] | 2019-09-12 |  | 2020-12-31 |  | EXP | [8 empty] | 2020-12-31 | Connected |  | No
National Grid | HAVERHILL | 193993 | 1835 | 650 | Solar | 14_43L6 | 2018-09-12 17:27 | 2018-09-13 | 13 | 5 | 8 | [10 empty] | 2018-10-03 | 2019-01-31 | 80 | 0 | 80 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | QUINCY | 195170 | 2169 | 360 | Solar | 07_3W1 | 2018-09-13 | 2018-09-14 | 8 | 6 | 2 | 2018-09-26 | 2018-11-02 | 28 | 3 | 25 | 2018-11-20 | 2019-03-11 | 74 | 24 | 50 | [5 empty] | 2018-11-20 | 2019-03-11 | 74 | 24 | 50 | [5 empty] | 2019-03-26 |  | 2020-08-21 |  | EXP | [8 empty] | 2020-08-21 | Connected |  | No
National Grid | PALMER | 195866 | 1069 | 13.8 | Solar | 09_514L1 | 2018-09-13 12:49 | 2018-10-03 | 1 | 0 | 1 | 2018-10-05 | 2018-10-09 | 2 | 0 | 2 | [20 empty] | 2018-11-21 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BELCHERTOWN | 184596 | 1007 | 4998 | Solar | 09_509L1 | 2018-09-13 12:51 | 2018-09-18 | 20 | 11 | 9 | [10 empty] | 2018-10-16 | 2018-12-18 | 43 | 24 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SHUTESBURY | 184597 | 1002 | 4998 | Solar | 09_704W1 | 2018-09-13 12:53 | 2018-09-18 | 19 | 10 | 9 | [10 empty] | 2018-10-15 | 2018-12-19 | 64 | 45 | 19 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | SHUTESBURY | 184598 | 1002 | 2998 | Solar | 09_704W1 | 2018-09-13 12:53 | 2018-09-18 | 19 | 10 | 9 | [10 empty] | 2018-10-15 | 2018-12-19 | 45 | 26 | 19 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | SHUTESBURY | 184599 | 1072 | 4998 | Solar | 09_704W1 | 2018-09-13 12:54 | 2018-09-14 | 25 | 16 | 9 | [10 empty] | 2018-10-19 | 2018-12-18 | 40 | 21 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SHUTESBURY | 184600 | 1072 | 4998 | Solar | 09_704W1 | 2018-09-13 12:55 | 2018-09-18 | 19 | 10 | 9 | [10 empty] | 2018-10-15 | 2018-12-18 | 44 | 25 | 19 | [11 empty] | 2018-09-13 16:56 |  |  | STD | [9 empty] | Group Study |  | No
National Grid | MEDFORD | 195807 | 2155 | 496 | Solar | 12_11J13 | 2018-09-13 16:56 | 2018-09-14 | 6 | 4 | 2 | 2018-09-24 | 2018-10-01 | 5 | 0 | 5 | 2018-12-03 | 2019-01-17 | 32 | 5 | 27 | [5 empty] | 2018-12-03 | 2019-01-17 | 32 | 5 | 27 | [5 empty] | 2019-03-28 |  | 2020-10-16 | Yes | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | REVERE | 195927 | 2151 | 7.6 | Solar | 12_16W8 | 2018-09-13 17:45 | 2018-10-23 | 0 | 0 | 0 | 2018-10-24 | 2018-10-29 | 3 | 0 | 3 | [20 empty] | 2018-11-21 | 2018-09-13 19:19 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | GARDNER | 195930 | 1440 | 7.6 | Solar | 01_607W5 | 2018-09-13 19:19 | 2018-09-14 | 3 | 3 | 0 | 2018-09-19 | 2018-09-24 | 3 | 0 | 3 | [20 empty] | 2018-09-24 |  | 2022-01-06 | Yes | EXP |  | 2021-07-24 | 2021-09-01 | 38 | 3 | 35 |  |  | 2021-09-01 | Connected |  | No
National Grid | ROYALSTON | 195813 | 1368 | 7999 | Solar | 09_701J1 | 2018-09-14 13:51 | 2018-09-17 | 4 | 0 | 4 | [10 empty] | 2018-10-03 | 2018-11-21 | 34 | 26 | 8 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | PETERSHAM | 195814 | 1366 | 3000 | Solar | 09_705W4 | 2018-09-14 13:57 | 2018-09-17 | 11 | 0 | 11 | [10 empty] | 2018-10-03 | 2018-11-08 | 65 | 35 | 30 | [5 empty] | 2020-07-10 | 2020-10-02 | 60 | 3 | 57 |  |  |  |  | STD | [9 empty] | Group Study |  | No
National Grid | ATHOL | 195816 | 1331 | 4200 | Solar | 09_705W4 | 2018-09-14 14:09 | 2018-09-17 | 14 | 0 | 14 | [10 empty] | 2018-10-08 | 2018-11-08 | 62 | 14 | 48 | [5 empty] | 2020-07-10 | 2020-10-02 | 60 | 3 | 57 |  |  |  |  | STD | [9 empty] | Group Study |  | No
National Grid | PALMER | 192369 | 1069 | 410 | Solar | 09_0504 | 2018-09-14 15:05 | 2018-09-17 | 127 | 26 | 101 | [10 empty] | 2018-11-29 | 2019-03-22 | 77 | 26 | 51 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SOUTH EASTON | 192458 | 2375 | 710 | Solar | 07_98W48 | 2018-09-14 15:08 | 2018-09-17 | 10 | 2 | 8 | [10 empty] | 2018-10-02 | 2018-12-03 | 42 | 23 | 19 | [10 empty] | 2019-08-08 |  | 2021-05-18 |  | STD | [8 empty] | 2021-05-12 | Connected |  | No
National Grid | MONSON | 194853 | 1057 | 10 | Solar | 09_503L2 | 2018-09-16 01:13 | 2018-10-10 | 13 | 13 | 0 | 2018-10-30 | 2018-11-07 | 6 | 0 | 6 | [20 empty] | 2018-11-07 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HALIFAX | 194382 | 2338 | 2000 | Solar | 07_912W74 | 2018-09-17 | 2018-10-29 | 8 | 0 | 8 | [10 empty] | 2018-11-09 | 2019-01-07 | 37 | 8 | 29 | [10 empty] | 2020-02-20 | 2018-09-17 | 2020-01-07 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | FRANKLIN | 195928 | 2038 | 10 | Solar | 05_344W1 | 2018-09-17 | 2018-09-18 | 9 | 2 | 7 | 2018-10-02 | 2018-10-05 | 3 | 0 | 3 | [20 empty] | 2019-01-24 |  | 2019-08-31 | Yes | EXP | [8 empty] | 2019-05-10 | Connected |  | No
National Grid | NORTH EASTON | 196083 | 2356 | 366.6 | Solar | 07_92W78 | 2018-09-17 | 2018-09-19 | 8 | 5 | 3 | 2018-10-02 | 2018-11-12 | 29 | 7 | 22 | 2018-11-29 | 2019-01-10 | 28 | 8 | 20 | [5 empty] | 2018-11-29 | 2019-01-10 | 28 | 8 | 20 | [5 empty] | 2019-02-22 |  | 2020-08-24 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LYNN | 188941 | 1905 | 499.5 | Solar | 12_16J2 | 2018-09-17 12:32 | 2018-09-18 | 3 | 0 | 3 | 2018-09-24 | 2019-10-08 | 165 | 1 | 164 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | EAST LONGMEADOW | 188191 | 1028 | 480 | Solar | 09_522L2 | 2018-09-17 13:50 | 2018-09-18 | 3 | 1 | 2 | [5 empty] | 2018-12-27 | 2019-03-08 | 49 | 39 | 10 | 2018-09-24 | 2018-12-06 | 54 | 27 | 27 | 2018-12-27 | 2019-03-08 | 49 | 39 | 10 | [6 empty] | 2018-09-17 14:03 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | DRACUT | 196115 | 1826 | 10 | Solar | 14_78L1 | 2018-09-17 14:03 | 2018-10-05 | 19 | 18 | 1 | 2018-10-31 | 2018-11-27 | 16 | 3 | 13 | [20 empty] | 2018-11-27 |  | 2019-05-27 | Yes | EXP |  | 2019-02-21 | 2019-02-20 | 0 | 0 | 0 |  |  | 2019-05-13 | Connected |  | No
National Grid | WINCHENDON | 192506 | 1475 | 6.4 | Solar | 01_612W3 | 2018-09-17 15:35 | 2018-10-19 | 11 | 11 | 0 | 2018-11-05 | 2018-11-21 | 11 | 0 | 11 | [20 empty] | 2018-11-21 |  |  |  | EXP | [8 empty] | 2019-02-21 | Connected |  | No
National Grid | WORCESTER | 196201 | 1605 | 7.6 | Solar | 01_24W1 | 2018-09-18 12:33 | 2018-10-10 | 3 | 3 | 0 | 2018-10-15 | 2019-01-07 | 57 | 54 | 3 | [20 empty] | 2019-01-16 | 2018-09-18 13:11 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 193702 | 1605 | 832.5 | Solar | 01_27W2 | 2018-09-18 13:11 | 2018-10-05 | 18 | 0 | 18 | [10 empty] | 2018-11-01 | 2019-04-01 | 101 | 82 | 19 | [10 empty] | 2020-08-04 |  | 2024-04-25 | Yes | STD |  | 2023-05-18 |  | 332 | 144 | 188 |  |  | 2024-04-15 | Connected |  | No
National Grid | HAVERHILL | 193994 | 1835 | 540 | Solar | 14_43L6 | 2018-09-18 15:20 | 2018-09-19 | 9 | 0 | 9 | [10 empty] | 2018-10-03 | 2019-01-31 | 80 | 0 | 80 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | LEOMINSTER | 196233 | 1453 | 7.6 | Solar | 01_219W6 | 2018-09-18 15:21 | 2018-12-04 | 147 | 145 | 2 | 2019-08-12 | 2019-08-23 | 9 | 0 | 9 | [20 empty] | 2019-08-26 |  | 2021-06-15 |  | EXP | [8 empty] | 2021-05-28 | Connected |  | No
National Grid | ORANGE | 196214 | 1364 | 5 | Solar | 09_705W2 | 2018-09-18 15:30 | 2018-09-26 | 14 | 8 | 6 | 2018-10-17 | 2018-10-17 | 0 | 0 | 0 | [20 empty] | 2018-11-15 |  |  |  | EXP | [8 empty] | 2019-03-27 | Connected |  | No
National Grid | WESTMINSTER | 192451 | 1473 | 3780 | Solar | 01_610W3 | 2018-09-18 20:28 | 2018-09-21 | 10 | 0 | 10 | [10 empty] | 2018-10-05 | 2018-11-17 | 30 | 0 | 30 | [5 empty] | 2020-07-10 | 2020-10-02 | 60 | 3 | 57 |  |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | AUBURN | 194766 | 1501 | 650 | Solar | 01_26W3 | 2018-09-19 | 2018-09-25 | 8 | 4 | 4 | [10 empty] | 2018-10-17 | 2018-11-20 | 23 | 5 | 18 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | FRANKLIN | 194820 | 2038 | 600 | Solar | 05_344W6 | 2018-09-19 | 2018-09-25 | 5 | 2 | 3 | [10 empty] | 2018-10-02 | 2019-01-22 | 73 | 9 | 64 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | STOUGHTON | 194829 | 2072 | 600 | Solar | 07_75W7 | 2018-09-19 | 2018-09-25 | 5 | 2 | 3 | [10 empty] | 2018-10-02 | 2018-11-06 | 59 | 7 | 52 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | MARLBOROUGH | 196371 | 1752 | 100 | Solar | 05_311W1 | 2018-09-19 | 2018-09-26 | 7 | 0 | 7 | 2018-10-08 | 2018-12-02 | 37 | 14 | 23 | [20 empty] | 2018-12-19 | 2018-09-19 | 2020-06-01 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | ROCKLAND | 196387 | 2370 | 100 | Solar | 07_99W61 | 2018-09-19 | 2018-09-26 | 7 | 0 | 7 | 2018-10-08 | 2018-11-13 | 25 | 4 | 21 | 2018-11-29 | 2018-12-19 | 14 | 0 | 14 | [5 empty] | 2018-11-29 | 2018-12-19 | 14 | 0 | 14 | [5 empty] | 2019-01-24 |  | 2020-06-01 | Yes | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTBOROUGH | 196392 | 1582 | 496 | Solar | 05_314W5 | 2018-09-19 | 2018-09-25 | 5 | 2 | 3 | [10 empty] | 2018-10-02 | 2019-02-26 | 97 | 57 | 40 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 196395 | 1603 | 100 | Solar | 01_7J387 | 2018-09-19 | 2018-09-26 | 3 | 0 | 3 | 2018-10-02 | 2018-11-06 | 29 | 4 | 25 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 196401 | 1604 | 66.6 | Solar | 01_HT28 | 2018-09-19 | 2018-10-08 | 0 | 0 | 0 | 2018-10-09 | 2018-11-19 | 28 | 12 | 16 | [20 empty] | 2018-11-26 |  | 2020-06-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SOUTHBRIDGE | 196406 | 1550 | 66.6 | Solar | 01_413L1 | 2018-09-19 | 2018-10-08 | 0 | 0 | 0 | 2018-10-09 | 2018-11-12 | 24 | 8 | 16 | [20 empty] | 2018-11-15 |  | 2020-05-01 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | HAVERHILL | 196416 | 1830 | 66.6 | Solar | 14_48L3 | 2018-09-19 | 2018-10-08 | 0 | 0 | 0 | 2018-10-09 | 2018-10-31 | 16 | 0 | 16 | [20 empty] | 2018-11-05 |  | 2020-07-01 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LOWELL | 196418 | 1854 | 100 | Solar | 14_77L1 | 2018-09-19 | 2018-10-02 | 2 | 0 | 2 | 2018-10-05 | 2018-11-12 | 26 | 2 | 24 | [20 empty] | 2018-11-21 |  | 2020-07-06 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WEBSTER | 196422 | 1570 | 66.6 | Solar | 01_412L2 | 2018-09-19 | 2018-10-08 | 0 | 0 | 0 | 2018-10-09 | 2018-10-31 | 16 | 0 | 16 | [20 empty] | 2018-11-06 |  | 2020-06-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MALDEN | 188939 | 2148 | 499.5 | Solar | 12_16J2 | 2018-09-19 12:05 | 2018-09-20 | 1 | 0 | 1 | 2018-09-24 | 2019-10-08 | 165 | 1 | 164 | [21 empty] | 2018-09-19 13:13 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SAUGUS | 194313 | 1906 | 7.6 | Solar | 12_7J903 | 2018-09-19 13:13 | 2018-10-10 | 2 | 0 | 2 | 2018-10-15 | 2018-10-15 | 0 | 0 | 0 | [20 empty] | 2018-11-02 | 2018-09-19 13:24 | 2020-10-12 |  | EXP |  | 2019-05-02 | 2019-05-14 | 12 | 0 | 12 |  |  | 2020-02-07 | Connected |  | No
National Grid | CHELMSFORD | 194082 | 1824 | 9 | Solar | 14_16L4 | 2018-09-19 13:24 | 2018-10-08 | 1 | 0 | 1 | 2018-10-10 | 2018-10-10 | 0 | 0 | 0 | [20 empty] | 2018-11-01 |  |  |  | EXP |  | 2019-03-07 | 2019-03-19 | 12 | 0 | 12 |  |  | 2019-05-25 | Connected |  | No
National Grid | BROCKTON | 196383 | 2302 | 7.6 | Solar | 07_91W40 | 2018-09-19 15:10 | 2018-10-18 | 23 | 23 | 0 | 2018-11-21 | 2018-12-11 | 12 | 0 | 12 | [20 empty] | 2018-12-11 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTHAMPTON | 196403 | 1060 | 72 | Solar | 09_901W2 | 2018-09-19 15:48 | 2018-09-20 | 1 | 0 | 1 | 2018-09-24 | 2018-10-26 | 24 | 0 | 24 | [20 empty] | 2018-10-26 |  | 2022-02-07 |  | EXP | [8 empty] | 2022-01-25 | Connected |  | No
National Grid | EAST BRIDGEWATER | 192138 | 2333 | 4975 | Solar | 07_797W42 | 2018-09-20 | 2018-09-24 | 5 | 0 | 5 | [10 empty] | 2018-10-02 | 2018-11-08 | 28 | 9 | 19 | [12 empty] | 2020-06-30 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 196491 | 1606 | 5 | Solar | 01_24W3 | 2018-09-20 10:55 | 2018-09-27 | 19 | 18 | 1 | 2018-10-25 | 2018-10-30 | 3 | 0 | 3 | [20 empty] | 2018-11-01 |  |  |  | EXP | [8 empty] | 2019-04-11 | Connected |  | No
National Grid | BEVERLY | 185017 | 1915 | 458 | Solar | 12_18J4 | 2018-09-21 | 2018-10-01 | 0 | 0 | 0 | 2018-10-02 | 2018-11-26 | 36 | 25 | 11 | [20 empty] | 2018-11-26 |  | 2020-08-31 |  | EXP | [8 empty] | 2020-08-27 | Connected |  | No
National Grid | MILFORD | 196600 | 1757 | 106.6 | Solar | 05_335W5 | 2018-09-21 10:06 | 2018-09-28 | 26 | 9 | 17 | 2018-11-05 | 2018-11-26 | 12 | 0 | 12 | [20 empty] | 2018-11-30 |  |  |  | EXP | [8 empty] | 2019-07-16 | Connected |  | No
National Grid | BEVERLY | 196655 | 1915 | 3.8 | Solar | 12_72L1 | 2018-09-21 14:08 | 2018-10-10 | 5 | 5 | 0 | 2018-10-17 | 2018-10-18 | 1 | 0 | 1 | [20 empty] | 2018-10-18 | 2018-09-21 14:23 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | HAVERHILL | 196059 | 1830 | 2000 | Solar | 14_47L1 | 2018-09-21 14:23 | 2018-10-11 | 20 | 13 | 7 | [10 empty] | 2018-11-08 | 2019-01-07 | 37 | 19 | 18 | [10 empty] | 2020-08-05 | 2018-09-21 16:08 | 2025-02-27 | Yes | STD | [9 empty] | Design |  | No
National Grid | WESTBOROUGH | 196685 | 1581 | 8.7 | Solar | 05_312W1 | 2018-09-21 16:08 | 2018-10-22 | 3 | 3 | 0 | 2018-10-25 | 2018-10-31 | 4 | 0 | 4 | [20 empty] | 2018-10-31 |  | 2019-06-10 | Yes | EXP |  | 2019-03-16 | 2019-03-15 | 0 | 0 | 0 |  |  | 2019-04-19 | Connected |  | No
National Grid | NORTON | 197071 | 2766 | 240 | Solar | 05_4L2 | 2018-09-24 | 2018-10-02 | 1 | 0 | 1 | 2018-10-04 | 2018-11-15 | 39 | 8 | 31 | 2018-12-31 | 2019-02-11 | 28 | 8 | 20 | [5 empty] | 2018-12-31 | 2019-02-11 | 28 | 8 | 20 | [5 empty] | 2019-03-12 | 2018-09-24 10:50 | 2021-01-02 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SHUTESBURY | 196745 | 1072 | 10 | Solar | 09_705W1 | 2018-09-24 10:50 | 2018-09-28 | 18 | 17 | 1 | 2018-10-25 | 2018-10-30 | 3 | 0 | 3 | [20 empty] | 2018-10-30 |  | 2019-03-11 | Yes | EXP |  | 2019-02-02 | 2019-02-22 | 20 | 0 | 20 |  |  | 2019-03-05 | Connected |  | No
National Grid | BILLERICA | 193712 | 1821 | 1491 | Solar | 14_70L2 | 2018-09-24 17:20 | 2018-09-25 | 37 | 25 | 12 | [10 empty] | 2018-11-14 | 2019-04-02 | 145 | 77 | 68 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | BOLTON | 196197 | 1740 | 15.2 | Solar | 01_216W6 | 2018-09-25 09:57 | 2018-09-26 | 12 | 11 | 1 | 2018-10-11 | 2018-12-04 | 35 | 25 | 10 | [20 empty] | 2018-12-13 | 2018-09-25 13:37 |  |  | EXP | [8 empty] | 2019-05-04 | Connected |  | No
National Grid | OXFORD | 196917 | 1540 | 9.2 | Solar | 01_26W3 | 2018-09-25 13:37 | 2018-09-28 | 10 | 9 | 1 | 2018-10-12 | 2018-10-12 | 0 | 0 | 0 | [20 empty] | 2018-10-12 |  | 2019-03-08 | Yes | EXP |  | 2018-12-25 | 2019-01-08 | 14 | 0 | 14 |  |  | 2019-03-04 | Connected |  | No
National Grid | ORANGE | 191051 | 1364 | 1860 | Solar | 09_705W3 | 2018-09-25 15:31 | 2018-09-26 | 107 | 0 | 107 | [10 empty] | 2018-11-26 | 2018-12-21 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SALEM | 196948 | 1970 | 8.64 | Solar | 12_29W2 | 2018-09-25 15:47 | 2018-09-28 | 13 | 7 | 6 | 2018-10-18 | 2018-10-19 | 1 | 0 | 1 | [20 empty] | 2018-11-21 | 2018-09-25 16:29 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GREAT BARRINGTON | 193884 | 1230 | 2000 | Solar | 09_1102W1 | 2018-09-25 16:29 | 2018-09-26 | 3 | 0 | 3 | [10 empty] | 2018-10-02 | 2018-11-05 | 25 | 6 | 19 | [10 empty] | 2019-03-22 |  | 2022-02-12 | Yes | STD |  | 2021-06-16 | 2021-11-03 | 141 | 8 | 133 |  |  | 2021-12-22 | Connected |  | No
National Grid | NORTH GRAFTON | 196967 | 1536 | 6 | Solar | 01_304W1 | 2018-09-26 09:52 | 2018-10-17 | 2 | 2 | 0 | 2018-10-19 | 2018-11-13 | 16 | 0 | 16 | [20 empty] | 2018-12-21 | 2018-09-26 12:16 |  |  | EXP | [8 empty] | 2019-01-31 | Connected |  | No
National Grid | WILLIAMSBURG | 185248 | 1096 | 4675 | Solar | 09_909W1 | 2018-09-26 12:16 | 2018-09-27 | 7 | 0 | 7 | [10 empty] | 2018-10-09 | 2018-11-05 | 19 | 0 | 19 | [10 empty] | 2021-01-11 | 2018-09-26 12:55 | 2024-01-16 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTHAMPTON | 197016 | 1060 | 7.6 | Solar | 09_909W2 | 2018-09-26 12:55 | 2018-10-08 | 6 | 0 | 6 | 2018-10-22 | 2018-11-16 | 19 | 19 | 0 | [20 empty] | 2018-12-05 | 2018-09-26 14:26 |  | Yes | EXP | [8 empty] | 2019-04-26 | Connected |  | No
National Grid | RUTLAND | 197026 | 1543 | 8.4 | Solar | 01_55W1 | 2018-09-26 14:26 | 2018-09-28 | 27 | 17 | 10 | 2018-11-09 | 2018-12-20 | 27 | 13 | 14 | [20 empty] | 2018-12-24 |  |  | Yes | EXP |  | 2019-06-18 | 2019-06-17 | 0 | 0 | 0 |  |  | 2019-08-01 | Connected |  | Yes
National Grid | WEYMOUTH | 195005 | 2188 | 720 | Solar | 07_12W1 | 2018-09-27 | 2018-09-27 | 19 | 0 | 19 | [10 empty] | 2018-10-26 | 2018-11-27 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | PALMER | 197020 | 1069 | 3840 | Solar | 09_503L1 | 2018-09-27 | 2018-09-28 | 22 | 0 | 22 | [10 empty] | 2018-10-30 | 2018-11-28 | 18 | 0 | 18 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | EVERETT | 174063 | 2149 | 3.8 | Solar | 12_16W7 | 2018-09-27 09:48 | 2018-10-02 | 24 | 20 | 4 | 2018-11-06 | 2018-11-28 | 13 | 0 | 13 | [20 empty] | 2018-12-21 | 2018-09-27 10:22 | 2019-11-15 |  | EXP | [8 empty] | 2019-10-09 | Connected |  | No
National Grid | REVERE | 197013 | 2151 | 3 | Solar | 12_7W2 | 2018-09-27 10:22 | 2018-10-15 | 3 | 3 | 0 | 2018-10-18 | 2018-10-19 | 1 | 0 | 1 | [20 empty] | 2018-10-19 |  | 2019-05-20 | Yes | EXP |  | 2019-02-12 | 2019-04-11 | 58 | 0 | 58 |  |  | 2019-04-27 | Connected |  | No
National Grid | REVERE | 197019 | 2151 | 7.6 | Solar | 12_7W2 | 2018-09-27 10:23 | 2018-10-15 | 3 | 3 | 0 | 2018-10-18 | 2018-10-19 | 1 | 0 | 1 | [20 empty] | 2018-10-19 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MENDON | 196342 | 1756 | 19.52 | Solar | 05_321W6 | 2018-09-27 11:05 | 2018-09-28 | 4 | 0 | 4 | 2018-10-04 | 2018-10-18 | 10 | 0 | 10 | [20 empty] | 2018-11-21 |  |  |  | EXP | [8 empty] | 2019-02-20 | Connected |  | No
National Grid | GRANBY | 197086 | 1033 | 13.8 | Solar | 09_527L1 | 2018-09-27 12:47 | 2018-10-30 | 0 | 0 | 0 | 2018-10-31 | 2018-11-12 | 7 | 0 | 7 | [20 empty] | 2018-11-21 |  | 2019-08-30 |  | EXP | [8 empty] | 2019-08-12 | Connected |  | No
National Grid | AUBURN | 197089 | 1501 | 3.8 | Solar | 01_26W3 | 2018-09-27 13:22 | 2018-10-10 | 3 | 3 | 0 | 2018-10-15 | 2018-10-17 | 2 | 0 | 2 | [20 empty] | 2018-10-17 |  |  |  | EXP | [8 empty] | 2019-03-26 | Connected |  | No
National Grid | WORCESTER | 197101 | 1609 | 25 | Solar | 01_4J324 | 2018-09-27 14:35 | 2018-09-28 | 8 | 5 | 3 | 2018-10-11 | 2018-11-26 | 29 | 18 | 11 | [20 empty] | 2018-12-12 |  | 2020-10-02 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 197109 | 1607 | 7.6 | Solar | 01_27W1 | 2018-09-27 15:19 | 2018-10-12 | 4 | 3 | 1 | 2018-10-19 | 2018-11-13 | 16 | 0 | 16 | [20 empty] | 2018-12-26 | 2018-09-27 15:47 | 2019-08-30 |  | EXP | [8 empty] | 2019-07-26 | Connected |  | No
National Grid | LOWELL | 197115 | 1854 | 3.8 | Solar | 14_77L3 | 2018-09-27 15:47 | 2018-10-31 | 3 | 3 | 0 | 2018-11-05 | 2018-11-26 | 12 | 0 | 12 | [20 empty] | 2018-11-27 | 2018-09-28 12:58 | 2020-04-22 | Yes | EXP |  | 2019-11-14 | 2019-11-15 | 1 | 0 | 1 |  |  | 2020-01-22 | Connected |  | No
National Grid | WILBRAHAM | 197167 | 1095 | 15.2 | Solar | 09_507L1 | 2018-09-28 12:58 | 2018-10-01 | 2 | 2 | 0 | 2018-10-03 | 2018-10-03 | 0 | 0 | 0 | [20 empty] | 2018-10-03 |  | 2019-09-20 | Yes | EXP |  | 2019-01-15 | 2019-02-04 | 20 | 0 | 20 |  |  | 2019-09-03 | Connected |  | No
National Grid | HAWLEY | 196124 | 1339 | 4998 | Solar | 09_1019W1 | 2018-09-28 13:06 | 2018-10-01 | 30 | 21 | 9 | [10 empty] | 2018-11-14 | 2018-12-13 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | GREAT BARRINGTON | 196116 | 1230 | 4998 | Solar | 09_1109W2 | 2018-09-28 13:51 | 2018-10-01 | 30 | 21 | 9 | [10 empty] | 2018-11-14 | 2018-12-12 | 18 | 0 | 18 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTMINSTER | 195202 | 1473 | 2310 | Solar | 01_607W4 | 2018-09-28 17:14 | 2018-10-01 | 16 | 16 | 0 | [10 empty] | 2018-10-23 | 2018-12-18 | 38 | 19 | 19 | [5 empty] | 2020-07-10 | 2020-10-02 | 60 | 3 | 57 |  | 2018-09-28 17:39 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | RANDOLPH | 197198 | 2368 | 7.6 | Solar | 07_97W1 | 2018-09-28 17:39 | 2018-10-12 | 4 | 3 | 1 | 2018-10-18 | 2018-10-19 | 1 | 0 | 1 | [20 empty] | 2018-10-19 |  | 2019-09-30 | Yes | EXP |  | 2019-07-18 | 2019-08-07 | 19 | 0 | 19 |  |  | 2019-09-06 | Connected |  | No
National Grid | CHARLTON | 195208 | 1507 | 6930 | Solar | 01_415L2 | 2018-10-01 08:37 | 2018-10-02 | 15 | 15 | 0 | [10 empty] | 2018-10-23 | 2018-12-04 | 28 | 9 | 19 | [11 empty] | 2018-10-01 13:33 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 197281 | 1604 | 10 | Solar | 01_9J360 | 2018-10-01 13:33 | 2018-10-18 | 3 | 3 | 0 | 2018-10-23 | 2018-10-23 | 0 | 0 | 0 | [20 empty] | 2018-10-23 |  | 2019-06-04 | Yes | EXP |  | 2019-03-21 | 2019-03-20 | 0 | 0 | 0 |  |  | 2019-05-04 | Connected |  | No
National Grid | WORCESTER | 197318 | 1610 | 200 | Solar | 01_HT15 | 2018-10-01 14:06 | 2018-10-02 | 5 | 3 | 2 | 2018-10-09 | 2018-11-14 | 63 | 35 | 28 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | CLINTON | 197325 | 1510 | 7.6 | Solar | 01_216W3 | 2018-10-01 14:49 | 2018-10-18 | 3 | 3 | 0 | 2018-10-23 | 2018-10-29 | 4 | 0 | 4 | [20 empty] | 2018-10-30 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NEW BRAINTREE | 193356 | 1531 | 4998 | Solar | 09_604W3 | 2018-10-01 14:57 | 2018-10-02 | 9 | 0 | 9 | [10 empty] | 2018-10-16 | 2018-12-20 | 45 | 26 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BARRE | 192362 | 1005 | 2400 | Solar | 09_604W4 | 2018-10-01 14:58 | 2018-10-02 | 18 | 9 | 9 | [10 empty] | 2018-10-26 | 2018-11-27 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BELCHERTOWN | 192377 | 1007 | 4998 | Solar | 09_509L2 | 2018-10-01 14:58 | 2018-10-02 | 19 | 10 | 9 | [10 empty] | 2018-10-29 | 2019-01-04 | 45 | 26 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 197393 | 1844 | 7.6 | Solar | 14_63L2 | 2018-10-01 17:55 | 2018-10-23 | 4 | 4 | 0 | 2018-10-29 | 2018-11-06 | 6 | 0 | 6 | [20 empty] | 2018-11-06 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NANTUCKET | 197532 | 2554 | 9.92 | Solar | 04_101L7 | 2018-10-02 16:21 | 2018-10-10 | 9 | 9 | 0 | 2018-10-23 | 2018-10-29 | 5 | 1 | 4 | [20 empty] | 2018-10-29 | 2018-10-03 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LOWELL | 197063 | 1851 | 7.68 | Solar | 14_2L2 | 2018-10-03 | 2018-10-09 | 3 | 3 | 0 | 2018-10-12 | 2018-10-16 | 3 | 2 | 1 | [20 empty] | 2018-10-16 |  | 2019-05-29 | Yes | EXP |  | 2019-02-01 | 2019-01-31 | 0 | 0 | 0 |  |  | 2019-04-16 | Connected |  | No
National Grid | NORTH ANDOVER | 194950 | 1845 | 10 | Solar | 14_54L3 | 2018-10-03 14:51 | 2018-10-04 | 0 | 0 | 0 | 2018-10-05 | 2018-10-09 | 2 | 0 | 2 | [20 empty] | 2018-10-08 |  |  |  | EXP | [8 empty] | 2019-03-15 | Connected |  | No
National Grid | MEDFORD | 195969 | 2155 | 240 | Solar | 12_64J4 | 2018-10-04 | 2018-10-08 | 15 | 15 | 0 | 2018-10-29 | 2019-01-09 | 48 | 25 | 23 | [20 empty] | 2019-03-26 | 2018-10-04 | 2019-12-16 |  | EXP | [8 empty] | 2019-12-30 | Connected |  | No
National Grid | SOUTHBRIDGE | 197148 | 1550 | 996 | Solar | 01_413L2 | 2018-10-04 | 2018-10-11 | 22 | 12 | 10 | [10 empty] | 2018-11-05 | 2018-12-05 | 19 | 0 | 19 | [10 empty] | 2020-10-29 |  |  | Yes | STD | [9 empty] | Study |  | No
National Grid | LAWRENCE | 197441 | 1841 | 3.8 | Solar | 14_6J2 | 2018-10-04 09:54 | 2018-10-19 | 203 | 23 | 180 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 196571 | 1840 | 43.2 | Solar | 14_2J3 | 2018-10-04 13:01 | 2018-10-09 | 18 | 1 | 17 | 2018-11-02 | 2018-11-19 | 10 | 0 | 10 | [20 empty] | 2018-11-29 |  | 2020-06-30 |  | EXP | [8 empty] | 2020-05-18 | Connected |  | No
National Grid | GREAT BARRINGTON | 197783 | 1230 | 240 | Solar | 09_1109W3 | 2018-10-05 | 2018-10-08 | 189 | 21 | 168 | [10 empty] | 2018-11-05 | 2019-01-05 | 40 | 21 | 19 | [11 empty] | 2018-10-08 12:27 |  |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | SAUGUS | 194862 | 1906 | 17.6 | Solar | 12_23W2 | 2018-10-08 12:27 | 2018-10-09 | 6 | 0 | 6 | 2018-10-18 | 2018-10-22 | 2 | 0 | 2 | [20 empty] | 2018-11-21 |  | 2021-06-15 | Yes | EXP |  | 2019-12-18 | 2020-02-24 | 68 | 0 | 68 |  |  | 2021-06-02 | Connected |  | No
National Grid | EVERETT | 194606 | 2149 | 336 | Solar | 12_2338 | 2018-10-08 13:28 | 2018-10-09 | 4 | 0 | 4 | [25 empty] | 2018-12-03 |  | 2021-08-30 |  | EXP | [8 empty] | 2021-07-28 | Connected |  | No
National Grid | WORCESTER | 197375 | 1605 | 10 | Solar | 01_27W2 | 2018-10-08 16:16 | 2018-10-10 | 13 | 13 | 0 | 2018-10-30 | 2018-10-30 | 0 | 0 | 0 | [21 empty] | 2018-10-08 16:54 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 197977 | 1843 | 10 | Solar | 14_8L1 | 2018-10-08 16:54 | 2018-10-31 | 16 | 16 | 0 | 2018-11-27 | 2018-12-12 | 11 | 0 | 11 | [20 empty] | 2018-12-14 |  | 2019-08-28 | Yes | EXP |  | 2019-04-23 | 2019-05-03 | 10 | 0 | 10 |  |  | 2019-07-23 | Connected |  | No
National Grid | FALL RIVER | 197978 | 2721 | 6 | Solar | 05_115W45 | 2018-10-08 16:57 | 2018-10-30 | 43 | 41 | 2 | 2019-01-04 | 2019-01-11 | 5 | 0 | 5 | [20 empty] | 2019-01-15 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BRIMFIELD | 194417 | 1010 | 3000 | Solar | 09_503L4 | 2018-10-09 | 2018-10-15 | 0 | 0 | 0 | [10 empty] | 2018-10-29 | 2019-01-29 | 61 | 42 | 19 | [11 empty] | 2018-10-09 07:38 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HAVERHILL | 189468 | 1830 | 2800 | Solar | 14_47L1 | 2018-10-09 07:38 | 2018-10-08 | 5 | 0 | 5 | [10 empty] | 2018-10-15 | 2018-11-13 | 21 | 1 | 20 | [10 empty] | 2019-05-31 |  | 2025-10-20 |  | STD | [9 empty] | Design |  | No
National Grid | CHARLTON | 198041 | 1507 | 15.2 | Solar | 01_406L1 | 2018-10-09 10:44 | 2018-10-10 | 2 | 0 | 2 | 2018-10-15 | 2018-10-16 | 1 | 0 | 1 | [20 empty] | 2018-11-02 | 2018-10-09 11:48 |  |  | EXP | [8 empty] | 2019-10-05 | Connected |  | No
National Grid | METHUEN | 198050 | 1844 | 5 | Solar | 14_63L1 | 2018-10-09 11:48 | 2018-10-12 | 7 | 6 | 1 | 2018-10-23 | 2018-11-02 | 8 | 4 | 4 | [20 empty] | 2018-11-05 |  | 2019-05-22 | Yes | EXP |  | 2019-01-29 | 2019-02-05 | 7 | 0 | 7 |  |  | 2019-03-15 | Connected |  | No
National Grid | HAYDENVILLE | 194591 | 1039 | 4000 | Solar | 09_909W3 | 2018-10-09 16:36 | 2018-10-10 | 5 | 0 | 5 | [10 empty] | 2018-10-18 | 2018-12-01 | 29 | 10 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | ESSEX | 189490 | 1929 | 10 | Solar | 12_51T1 | 2018-10-09 17:22 | 2018-10-10 | 1 | 0 | 1 | 2018-10-12 | 2018-10-12 | 0 | 0 | 0 | [20 empty] | 2018-10-16 |  |  |  | EXP | [8 empty] | 2019-01-30 | Connected |  | No
National Grid | ABINGTON | 194141 | 2351 | 660 | Solar | 07_99W32 | 2018-10-09 21:51 | 2018-10-10 | 15 | 5 | 10 | [10 empty] | 2018-10-31 | 2018-11-30 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | HAYDENVILLE | 194600 | 1039 | 4950 | Solar | 09_909W3 | 2018-10-11 09:49 | 2018-10-12 | 10 | 0 | 10 | [10 empty] | 2018-11-02 | 2019-01-18 | 50 | 32 | 18 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH ANDOVER | 198292 | 1845 | 9.92 | Solar | 14_55L1 | 2018-10-11 11:31 | 2018-10-17 | 11 | 4 | 7 | 2018-11-02 | 2018-12-04 | 19 | 7 | 12 | [20 empty] | 2018-12-07 |  | 2020-04-24 |  | EXP | [8 empty] | 2020-04-06 | Connected |  | No
National Grid | CHARLTON | 195142 | 1507 | 4500 | Solar | 01_415L1 | 2018-10-11 13:09 | 2018-10-22 | [13 empty] | 2018-10-22 | 2018-12-20 | 40 | 21 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SAUGUS | 194758 | 1906 | 375 | Natural Gas | 12_23W1 | 2018-10-12 11:51 | 2018-10-15 | 12 | 0 | 12 | [10 empty] | 2018-11-01 | 2019-01-17 | 51 | 27 | 24 | [10 empty] | 2020-07-02 |  | 2020-12-31 |  | STD |  | 2020-10-28 | 2020-10-27 | 0 | 0 | 0 | 2020-10-28 | 2020-10-28 | 2020-12-17 | Connected |  | No
National Grid | WORCESTER | 198437 | 1602 | 3.8 | Solar | 01_23W3 | 2018-10-12 14:29 | 2018-10-17 | 69 | 25 | 44 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEOMINSTER | 198460 | 1453 | 7.6 | Solar | 01_207W1 | 2018-10-12 17:38 | 2018-10-18 | 22 | 21 | 1 | 2018-11-21 | 2018-12-10 | 11 | 0 | 11 | [20 empty] | 2018-12-21 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | PALMER | 192365 | 1069 | 7999 | Solar | 09_523L4 | 2018-10-15 13:46 | 2018-10-19 | 13 | 0 | 13 | [10 empty] | 2018-11-13 | 2019-01-08 | 37 | 19 | 18 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | HAVERHILL | 194214 | 1835 | 100 | Solar | 14_43L8 | 2018-10-15 23:56 | 2018-10-15 | 0 | 0 | 0 | 2018-10-16 | 2018-11-17 | 22 | 0 | 22 | [20 empty] | 2018-11-27 | 2018-10-16 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | HAVERHILL | 196058 | 1830 | 240 | Solar | 14_76L1 | 2018-10-16 | 2018-10-19 | 8 | 0 | 8 | [10 empty] | 2018-11-01 | 2018-11-21 | 13 | 0 | 13 | [10 empty] | 2020-01-27 |  |  | Yes | STD | [9 empty] | Study |  | No
National Grid | ROYALSTON | 198058 | 1368 | 2400 | Solar | 09_701J1 | 2018-10-16 | 2018-10-22 | 23 | 13 | 10 | [10 empty] | 2018-11-27 | 2019-01-14 | 56 | 14 | 42 | [11 empty] | 2018-10-16 10:31 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | REVERE | 195285 | 2151 | 10 | Solar | 12_16W4 | 2018-10-16 10:31 | 2018-10-25 | 14 | 9 | 5 | 2018-11-16 | 2018-12-18 | 20 | 8 | 12 | [20 empty] | 2018-12-28 | 2018-10-16 11:59 |  | Yes | EXP |  | 2019-07-09 | 2019-07-15 | 6 | 0 | 6 |  |  | 2019-08-20 | Connected |  | No
National Grid | PALMER | 198660 | 1069 | 10 | Solar | 09_516L3 | 2018-10-16 11:59 | 2018-10-23 | 5 | 5 | 0 | 2018-10-29 | 2018-11-05 | 5 | 0 | 5 | [20 empty] | 2018-11-05 |  | 2019-04-30 | Yes | EXP |  | 2019-01-15 | 2019-01-28 | 13 | 0 | 13 |  |  | 2019-03-26 | Connected |  | No
National Grid | WORCESTER | 198669 | 1602 | 5 | Solar | 01_23W3 | 2018-10-16 13:07 | 2018-11-30 | 87 | 83 | 4 | 2019-02-21 | 2019-02-21 | 0 | 0 | 0 | [20 empty] | 2019-02-22 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 198686 | 1843 | 7.6 | Solar | 14_1J9 | 2018-10-16 14:59 | 2018-10-31 | 33 | 25 | 8 | [26 empty] | 2018-10-16 18:46 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEYMOUTH | 198035 | 2190 | 9 | Solar | 07_8W1 | 2018-10-16 18:46 | 2018-12-12 | 10 | 10 | 0 | 2018-12-28 | 2019-01-10 | 9 | 4 | 5 | [20 empty] | 2019-01-16 |  | 2019-10-22 | Yes | EXP |  | 2019-04-24 | 2019-05-31 | 37 | 0 | 37 |  |  | 2019-08-01 | Connected |  | No
National Grid | BOXFORD | 198628 | 1921 | 20 | Solar | 14_56L3 | 2018-10-17 | 2018-10-29 | 3 | 3 | 0 | 2018-11-01 | 2018-11-19 | 11 | 0 | 11 | [20 empty] | 2019-01-17 |  |  |  | EXP | [8 empty] | 2019-04-04 | Connected |  | No
National Grid | PALMER | 195621 | 1069 | 4885 | Solar | 09_503L1 | 2018-10-17 14:44 | 2018-10-23 | 10 | 0 | 10 | [10 empty] | 2018-11-07 | 2018-12-15 | 30 | 28 | 2 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 198809 | 1603 | 7.6 | Solar | 01_7J387 | 2018-10-17 16:18 | 2018-11-01 | 5 | 0 | 5 | 2018-11-09 | 2018-12-04 | 14 | 0 | 14 | [20 empty] | 2018-12-24 | 2018-10-18 00:18 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HAVERHILL | 196057 | 1830 | 960 | Solar | 14_76L1 | 2018-10-18 00:18 | 2018-10-19 | 8 | 0 | 8 | [25 empty] | 2020-01-27 | 2018-10-18 07:41 |  | Yes | CMPX | [9 empty] | Study |  | No
National Grid | DRACUT | 193380 | 1826 | 7.6 | Solar | 14_21L1 | 2018-10-18 07:41 | 2018-10-19 | 4 | 4 | 0 | 2018-10-25 | 2018-11-02 | 6 | 0 | 6 | [20 empty] | 2018-11-02 | 2018-10-18 11:55 | 2021-07-15 | Yes | EXP |  | 2020-11-14 | 2020-12-10 | 26 | 0 | 26 |  |  | 2020-12-29 | Connected |  | No
National Grid | HAVERHILL | 196056 | 1830 | 3600 | Solar | 14_76L1 | 2018-10-18 11:55 | 2018-10-19 | 8 | 0 | 8 | [25 empty] | 2020-01-23 |  |  | Yes | CMPX | [9 empty] | Study |  | No
National Grid | GARDNER | 193346 | 1440 | 2040 | Solar | 01_601W4 | 2018-10-18 15:11 | 2018-10-19 | 17 | 16 | 1 | [26 empty] | 2018-10-18 15:22 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | EAST PEPPERELL | 198924 | 1463 | 10 | Solar | 01_226L2 | 2018-10-18 15:22 | 2019-01-22 | 39 | 35 | 4 | 2019-03-19 | 2019-03-22 | 3 | 0 | 3 | [20 empty] | 2019-04-03 |  | 2021-01-14 | Yes | EXP |  | 2020-06-03 | 2020-06-18 | 15 | 0 | 15 |  |  | 2020-07-03 | Connected |  | No
National Grid | BELLINGHAM | 198992 | 2038 | 250 | Solar | 05_344W4 | 2018-10-19 | 2018-10-23 | 15 | 3 | 12 | 2018-11-15 | 2018-12-06 | 13 | 1 | 12 | [20 empty] | 2018-12-18 | 2018-10-19 12:46 | 2020-01-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SALEM | 198887 | 1970 | 900 | Natural Gas | 12_2W2 | 2018-10-19 12:46 | 2018-10-22 | 15 | 4 | 11 | [10 empty] | 2018-11-13 | 2019-04-02 | 96 | 76 | 20 | [10 empty] | 2020-01-27 |  |  |  | STD |  | 2020-02-25 | 2020-02-24 | 0 | 0 | 0 |  |  | 2020-04-03 | Connected |  | No
National Grid | NORTH ANDOVER | 198828 | 1845 | 10 | Solar | 14_55L2 | 2018-10-19 13:08 | 2018-10-29 | 3 | 3 | 0 | 2018-11-01 | 2018-11-13 | 7 | 0 | 7 | [20 empty] | 2018-11-13 | 2018-10-19 13:13 | 2019-07-01 |  | EXP | [8 empty] | 2019-06-19 | Connected |  | No
National Grid | REVERE | 198866 | 2151 | 7.6 | Solar | 12_7W2 | 2018-10-19 13:13 | 2018-10-25 | 7 | 1 | 6 | 2018-11-06 | 2018-11-27 | 12 | 0 | 12 | [20 empty] | 2018-12-21 |  | 2020-01-27 | Yes | EXP |  | 2019-06-05 | 2019-06-22 | 17 | 0 | 17 |  |  | 2020-01-16 | Connected |  | No
National Grid | BILLERICA | 199034 | 1821 | 7.6 | Solar | 14_92L6 | 2018-10-19 15:36 | 2018-10-31 | 1 | 0 | 1 | 2018-11-02 | 2018-11-20 | 11 | 0 | 11 | [20 empty] | 2018-12-11 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTPORT | 199068 | 2790 | 10 | Solar | 05_115W45 | 2018-10-21 19:11 | 2018-10-23 | 12 | 6 | 6 | 2018-11-09 | 2019-01-21 | 45 | 26 | 19 | [20 empty] | 2019-01-31 |  |  |  | EXP | [8 empty] | 2019-03-26 | Connected |  | No
National Grid | GARDNER | 195209 | 1440 | 8290 | Solar | 01_607W1 | 2018-10-22 09:30 | 2018-10-23 | 0 | 0 | 0 | [10 empty] | 2018-10-23 | 2018-12-06 | 30 | 11 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | STURBRIDGE | 199144 | 1566 | 11.4 | Solar | 01_413L2 | 2018-10-22 12:22 | 2019-02-22 | 0 | 0 | 0 | 2019-02-25 | 2019-03-08 | 9 | 0 | 9 | [20 empty] | 2019-03-19 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BONDSVILLE | 199150 | 1009 | 7.6 | Solar | 09_523L2 | 2018-10-22 12:53 | 2018-10-23 | 2 | 2 | 0 | 2018-10-25 | 2018-10-29 | 2 | 0 | 2 | [20 empty] | 2018-10-29 |  | 2019-10-07 |  | EXP | [8 empty] | 2019-08-29 | Connected |  | No
National Grid | SOUTHBRIDGE | 193984 | 1550 | 72 | Solar | 01_413L1 | 2018-10-23 12:08 | 2018-10-24 | 178 | 28 | 150 | 2018-12-14 | 2019-01-29 | 29 | 13 | 16 | [21 empty] | 2018-10-24 09:59 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NEWBURYPORT | 199289 | 1950 | 7.6 | Solar | 14_47L2 | 2018-10-24 09:59 | 2018-11-20 | 20 | 19 | 1 | 2018-12-21 | 2019-01-07 | 12 | 0 | 12 | [20 empty] | 2019-01-16 | 2018-10-24 17:47 | 2019-12-20 | Yes | EXP |  | 2019-10-17 | 2019-10-25 | 8 | 0 | 8 |  |  | 2019-11-15 | Connected |  | No
National Grid | GRAFTON | 193132 | 1519 | 4000 | Solar | 01_304W1 | 2018-10-24 17:47 | 2018-10-25 | 11 | 5 | 6 | [20 empty] | 2021-05-21 | 2023-05-01 | 486 | 322 | 164 | 2021-03-11 | 2018-10-25 | 2024-12-21 | Yes | CMPX | [9 empty] | Design |  | No
National Grid | ATTLEBORO | 197724 | 2703 | 1700 | Solar | 05_8L1 | 2018-10-25 | 2018-10-26 | 13 | 4 | 9 | [10 empty] | 2018-11-15 | 2018-12-14 | 19 | 0 | 19 | [10 empty] | 2020-08-03 |  | 2024-07-14 | Yes | STD |  | 2023-02-04 |  | 437 | 313 | 124 |  |  |  | Construction |  | No
National Grid | BROCKTON | 199415 | 2302 | 430 | Solar | 07_91W46 | 2018-10-25 | 2018-11-02 | 7 | 4 | 3 | [10 empty] | 2018-11-14 | 2018-12-27 | 29 | 10 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WARREN | 198034 | 1083 | 2400 | Solar | 09_516L3 | 2018-10-25 13:12 | 2018-10-26 | 19 | 15 | 4 | [10 empty] | 2018-11-27 | 2019-06-15 | 238 | 125 | 113 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | DRACUT | 199466 | 1826 | 10 | Solar | 14_75L3 | 2018-10-25 16:26 | 2018-10-31 | 1 | 0 | 1 | 2018-11-02 | 2019-02-28 | 77 | 35 | 42 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GARDNER | 192916 | 1440 | 2040 | Solar | 01_607W4 | 2018-10-25 16:33 | 2018-10-26 | 232 | 26 | 206 | [29 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WILBRAHAM | 194350 | 1095 | 3110 | Solar | 09_507L2 | 2018-10-26 | 2018-10-31 | 16 | 0 | 16 | [10 empty] | 2018-11-27 | 2018-12-24 | 19 | 0 | 19 | [10 empty] | 2020-10-15 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SHIRLEY | 199446 | 1464 | 250 | Solar | 01_227W3 | 2018-10-26 | 2018-10-29 | 1 | 0 | 1 | 2018-10-31 | 2018-11-15 | 10 | 0 | 10 | 2018-11-16 | 2019-01-08 | 33 | 0 | 33 | [5 empty] | 2018-11-16 | 2019-01-08 | 33 | 0 | 33 | [9 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | STOCKBRIDGE | 199448 | 1262 | 60 | Solar | 09_1102W1 | 2018-10-26 | 2018-10-29 | 5 | 1 | 4 | 2018-11-06 | 2018-12-26 | 32 | 13 | 19 | [20 empty] | 2019-01-29 | 2018-10-26 13:58 |  |  | EXP | [8 empty] | 2019-09-25 | Connected |  | No
National Grid | WRENTHAM | 199488 | 2152 | 10 | Solar | 12_22J3 | 2018-10-26 13:58 | 2018-11-06 | 13 | 8 | 5 | 2018-11-28 | 2018-12-12 | 10 | 0 | 10 | [20 empty] | 2018-12-21 |  |  | Yes | EXP |  | 2019-06-20 | 2019-07-29 | 38 | 0 | 38 |  |  | 2019-10-30 | Connected |  | No
National Grid | SWANSEA | 199525 | 2777 | 1000 | Solar | 05_11W81 | 2018-10-26 14:32 | 2018-10-26 | 15 | 9 | 6 | [10 empty] | 2018-11-19 | 2018-12-18 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | LOWELL | 199543 | 1854 | 10 | Solar | 14_77L2 | 2018-10-26 15:12 | 2018-11-13 | 32 | 28 | 4 | 2019-01-04 | 2019-01-10 | 4 | 0 | 4 | [20 empty] | 2019-01-17 | 2018-10-26 18:50 | 2019-06-17 |  | EXP | [8 empty] | 2019-06-01 | Connected |  | No
National Grid | LAWRENCE | 199566 | 1843 | 7.6 | Solar | 14_8L1 | 2018-10-26 18:50 | 2018-10-31 | 13 | 7 | 6 | 2018-11-21 | 2018-12-07 | 10 | 0 | 10 | [20 empty] | 2018-12-12 |  |  | Yes | EXP |  | 2019-06-05 | 2019-06-04 | 0 | 0 | 0 |  |  | 2019-10-15 | Connected |  | No
National Grid | FOXBOROUGH | 196782 | 2035 | 464 | Solar | 05_3432W2 | 2018-10-29 | 2018-10-30 | 27 | 18 | 9 | 2018-12-11 | 2018-12-28 | 13 | 1 | 12 | 2019-02-13 | 2019-04-30 | 54 | 34 | 20 | [5 empty] | 2019-02-13 | 2019-04-30 | 54 | 34 | 20 | [5 empty] | 2019-06-27 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHELMSFORD | 199628 | 1824 | 3.8 | Solar | 14_24L3 | 2018-10-29 11:48 | 2018-11-08 | 25 | 24 | 1 | 2018-12-19 | 2018-12-31 | 7 | 0 | 7 | [20 empty] | 2019-02-15 |  | 2019-10-11 |  | EXP | [8 empty] | 2019-08-27 | Connected |  | No
National Grid | HOLLAND | 197057 | 1521 | 850 | Solar | 09_516L1 | 2018-10-29 14:14 | 2018-10-30 | 107 | 7 | 100 | [10 empty] | 2019-01-25 | 2019-02-27 | 21 | 8 | 13 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SAUGUS | 199773 | 1906 | 7.6 | Solar | 12_13J3 | 2018-10-30 14:40 | 2018-10-31 | 6 | 0 | 6 | 2018-11-09 | 2019-03-04 | 75 | 60 | 15 | [20 empty] | 2019-03-12 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | PHILLIPSTON | 196252 | 1331 | 250 | Solar | 09_701J1 | 2018-10-31 | 2018-11-15 | 10 | 5 | 5 | 2018-12-04 | 2019-01-08 | 23 | 8 | 15 | [21 empty] | 2018-10-31 15:02 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MILLBURY | 199870 | 1527 | 10 | Solar | 01_304W5 | 2018-10-31 15:02 | 2019-09-20 | 3 | 1 | 2 | 2019-01-02 | 2019-03-18 | 52 | 47 | 5 | 2020-05-13 | 2020-06-09 | 18 | 0 | 18 | [5 empty] | 2020-05-13 | 2020-06-09 | 18 | 0 | 18 | [5 empty] | 2019-04-03 |  | 2021-01-06 | Yes | EXP | [8 empty] | 2020-12-14 | Connected |  | No
National Grid | WALES | 199732 | 1081 | 450 | Solar | 09_516L1 | 2018-10-31 16:08 | 2018-11-01 | 5 | 0 | 5 | 2018-11-09 | 2018-12-10 | 17 | 0 | 17 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | WEST BRIDGEWATER | 198658 | 2379 | 433.3 | Solar | 07_797W20 | 2018-11-01 08:43 | 2018-11-05 | 3 | 0 | 3 | 2018-11-08 | 2019-01-05 | 37 | 23 | 14 | 2019-01-10 | 2019-03-11 | 40 | 21 | 19 | [5 empty] | 2019-01-10 | 2019-03-11 | 40 | 21 | 19 | [5 empty] | 2019-03-25 |  | 2021-01-02 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LEICESTER | 199985 | 1524 | 7.6 | Solar | 01_21W1 | 2018-11-01 13:24 | 2018-12-18 | 8 | 0 | 8 | 2019-01-02 | 2019-01-09 | 5 | 0 | 5 | [20 empty] | 2019-01-31 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LAWRENCE | 199996 | 1841 | 6 | Solar | 14_8L2 | 2018-11-01 14:04 | 2018-11-16 | 1 | 0 | 1 | 2018-11-20 | 2018-12-21 | 21 | 14 | 7 | [20 empty] | 2018-12-24 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | UPTON | 195450 | 1568 | 2450 | Solar | 05_335W3 | 2018-11-01 15:04 | 2018-11-20 | 16 | 0 | 16 | [10 empty] | 2019-01-08 | 2019-02-05 | 0 | 0 | 0 | [11 empty] | 2018-11-01 15:48 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | REVERE | 200027 | 2151 | 10 | Solar | 12_7W2 | 2018-11-01 15:48 | 2018-11-19 | 2 | 1 | 1 | 2018-11-26 | 2019-01-05 | 28 | 15 | 13 | [20 empty] | 2019-01-17 |  | 2020-07-17 | Yes | EXP |  | 2019-07-26 | 2019-07-31 | 5 | 0 | 5 |  |  | 2020-07-13 | Connected |  | No
National Grid | LAWRENCE | 200094 | 1843 | 10 | Solar | 14_1J9 | 2018-11-02 11:12 | 2018-11-16 | 9 | 2 | 7 | 2018-12-04 | 2018-12-14 | 8 | 0 | 8 | [20 empty] | 2018-12-24 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SAUGUS | 199443 | 1906 | 3.8 | Solar | 12_7J903 | 2018-11-02 11:52 | 2018-11-16 | 7 | 0 | 7 | 2018-11-30 | 2018-11-30 | 0 | 0 | 0 | [20 empty] | 2019-01-09 |  |  |  | EXP | [8 empty] | 2019-04-25 | Connected |  | No
National Grid | EAST BRIDGEWATER | 195864 | 2333 | 7.6 | Solar | 07_797W42 | 2018-11-02 12:03 | 2018-11-05 | 6 | 0 | 6 | 2018-11-15 | 2018-12-07 | 14 | 0 | 14 | [20 empty] | 2018-12-11 | 2018-11-02 15:23 | 2020-11-13 |  | EXP | [8 empty] | 2020-05-21 | Connected |  | No
National Grid | QUINCY | 195989 | 2169 | 10 | Solar | 07_1W2 | 2018-11-02 15:23 | 2018-11-05 | 59 | 54 | 5 | 2019-02-04 | 2019-02-05 | 1 | 0 | 1 | [20 empty] | 2019-02-06 |  | 2019-10-08 | Yes | EXP |  | 2019-04-10 | 2019-05-31 | 51 | 0 | 51 |  |  | 2019-10-08 | Connected |  | No
National Grid | UPTON | 198326 | 1568 | 10 | Solar | 05_320W1 | 2018-11-02 17:57 | 2018-11-09 | 1 | 1 | 0 | 2018-11-14 | 2018-11-16 | 2 | 0 | 2 | [20 empty] | 2018-11-20 | 2018-11-05 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | QUINCY | 199529 | 2169 | 7.6 | Solar | 07_1W2 | 2018-11-05 | 2018-11-06 | 9 | 7 | 2 | 2018-11-21 | 2018-12-18 | 17 | 0 | 17 | [20 empty] | 2018-12-17 | 2018-11-05 | 2019-11-15 | Yes | EXP | [8 empty] | 2019-10-10 | Connected |  | No
National Grid | LOWELL | 200444 | 1851 | 201.6 | Solar | 14_16L3 | 2018-11-05 | 2018-11-07 | 1 | 0 | 1 | [5 empty] | 2019-06-13 | 2019-06-12 | 0 | 0 | 0 | [5 empty] | 2019-06-13 | 2019-06-12 | 0 | 0 | 0 | [5 empty] | 2019-07-16 |  | 2024-06-25 | Yes | EXP |  | 2024-03-01 |  | 46 | 46 | 0 |  |  |  | Construction |  | No
National Grid | BEVERLY | 200315 | 1915 | 3.8 | Solar | 12_12L2 | 2018-11-05 09:29 | 2018-11-06 | 57 | 55 | 2 | 2019-01-29 | 2019-11-01 | 159 | 0 | 159 | [20 empty] | 2019-01-30 | 2018-11-05 10:23 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LYNN | 198918 | 1902 | 7.6 | Solar | 12_29W4 | 2018-11-05 10:23 | 2018-11-06 | 0 | 0 | 0 | 2018-11-06 | 2018-11-20 | 9 | 0 | 9 | [20 empty] | 2018-11-20 |  | 2020-11-05 | Yes | EXP |  | 2019-11-15 | 2019-11-27 | 12 | 0 | 12 |  |  | 2020-01-16 | Connected |  | No
National Grid | HAVERHILL | 199477 | 1830 | 7.6 | Solar | 14_76L3 | 2018-11-05 10:52 | 2018-11-06 | 5 | 0 | 5 | 2018-11-15 | 2018-11-27 | 6 | 0 | 6 | [20 empty] | 2019-01-16 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | REVERE | 200168 | 2151 | 3.8 | Solar | 12_7W2 | 2018-11-05 11:35 | 2018-11-16 | 3 | 3 | 0 | 2018-11-21 | 2018-12-10 | 11 | 0 | 11 | [20 empty] | 2018-12-14 |  |  |  | EXP | [8 empty] | 2019-02-12 | Connected |  | No
National Grid | WORCESTER | 197997 | 1603 | 6 | Solar | 01_6W2 | 2018-11-05 12:02 | 2019-01-04 | 6 | 0 | 6 | 2019-01-15 | 2019-01-23 | 5 | 0 | 5 | [20 empty] | 2019-02-13 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MILLBURY | 200350 | 1527 | 7.6 | Solar | 01_304W3 | 2018-11-05 12:19 | 2018-11-06 | 5 | 0 | 5 | 2018-11-15 | 2018-12-04 | 11 | 0 | 11 | [20 empty] | 2019-10-22 | 2018-11-05 12:28 | 2021-03-18 |  | EXP | [8 empty] | 2020-12-31 | Connected |  | No
National Grid | REHOBOTH | 200359 | 2769 | 15.2 | Solar | 05_7L5 | 2018-11-05 12:28 | 2018-11-06 | 3 | 3 | 0 | 2018-11-09 | 2019-01-31 | 54 | 38 | 16 | [20 empty] | 2019-01-31 |  | 2019-10-14 | Yes | EXP |  | 2019-05-08 | 2019-06-12 | 35 | 0 | 35 |  |  | 2019-07-20 | Connected |  | No
National Grid | LAWRENCE | 200394 | 1843 | 3.8 | Solar | 14_61L3 | 2018-11-05 14:21 | 2018-11-19 | 18 | 9 | 9 | 2018-12-18 | 2019-01-08 | 13 | 0 | 13 | [20 empty] | 2019-02-05 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LYNN | 196937 | 1905 | 3.84 | Solar | 12_21J32 | 2018-11-05 15:53 | 2018-11-06 | 3 | 2 | 1 | 2018-11-09 | 2018-11-16 | 4 | 0 | 4 | [20 empty] | 2018-11-16 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTON | 199757 | 2766 | 7.6 | Solar | 05_4L2 | 2018-11-05 17:09 | 2018-11-29 | 3 | 3 | 0 | 2018-12-04 | 2018-12-28 | 18 | 3 | 15 | [20 empty] | 2018-12-28 |  |  |  | EXP | [8 empty] | 2019-04-04 | Connected |  | No
National Grid | FLORIDA | 197015 | 1247 | 8980 | Solar | 09_1015W1 | 2018-11-06 | 2018-11-07 | 19 | 0 | 19 | [10 empty] | 2018-12-10 | 2019-01-08 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTFORD | 198756 | 1886 | 174 | Solar | 14_57L3 | 2018-11-06 | 2018-11-27 | 0 | 0 | 0 | 2018-11-28 | 2018-12-13 | 11 | 0 | 11 | 2019-04-15 | 2019-05-01 | 12 | 0 | 12 | [5 empty] | 2019-04-15 | 2019-05-01 | 12 | 0 | 12 | [5 empty] | 2019-06-14 |  | 2020-10-15 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | FALL RIVER | 199674 | 2723 | 133.2 | Solar | 05_115W43 | 2018-11-06 | 2018-11-07 | 10 | 2 | 8 | 2018-11-27 | 2019-01-05 | 27 | 13 | 14 | [20 empty] | 2019-02-25 |  | 2020-12-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | REHOBOTH | 196777 | 2769 | 4998 | Solar | 05_8L4 | 2018-11-06 12:20 | 2018-11-07 | 9 | 0 | 9 | [10 empty] | 2018-11-26 | 2019-01-09 | 31 | 12 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | EAST LONGMEADOW | 200188 | 1028 | 376.6 | Solar | 09_508L4 | 2018-11-06 14:18 | 2018-11-07 | 9 | 8 | 1 | 2018-11-21 | 2018-12-28 | 25 | 8 | 17 | [21 empty] | 2018-11-06 14:41 | 2020-07-01 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SOMERSET | 200437 | 2726 | 10 | Solar | 05_18J5 | 2018-11-06 14:41 | 2018-11-26 | 58 | 57 | 1 | 2019-02-15 | 2019-03-06 | 13 | 12 | 1 | [20 empty] | 2019-03-06 |  | 2019-12-06 | Yes | EXP |  | 2019-06-06 | 2019-07-19 | 43 | 0 | 43 |  |  | 2019-08-06 | Connected |  | No
National Grid | WHITINSVILLE | 199879 | 1588 | 6 | Solar | 05_320W3 | 2018-11-06 18:11 | 2018-11-07 | 28 | 28 | 0 | 2018-12-21 | 2019-01-05 | 9 | 0 | 9 | [20 empty] | 2019-01-17 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LOWELL | 200569 | 1852 | 7.6 | Solar | 14_75L2 | 2018-11-06 18:17 | 2019-02-25 | 0 | 0 | 0 | 2019-02-25 | 2019-03-08 | 9 | 0 | 9 | [20 empty] | 2019-03-19 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HAMPDEN | 199336 | 1036 | 7.6 | Solar | 09_139L1 | 2018-11-07 12:58 | 2018-11-08 | 88 | 84 | 4 | 2019-03-19 | 2019-03-22 | 3 | 0 | 3 | [20 empty] | 2019-03-25 |  | 2019-11-08 |  | EXP | [8 empty] | 2019-10-11 | Connected |  | No
National Grid | SPENCER | 195817 | 1562 | 1 | Solar | 01_552L1 | 2018-11-07 14:14 | 2019-01-22 | 151 | 25 | 126 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | LEOMINSTER | 200671 | 1453 | 7.6 | Solar | 01_219W2 | 2018-11-07 17:26 | 2018-11-14 | 21 | 13 | 8 | 2018-12-18 | 2019-01-08 | 14 | 5 | 9 | [20 empty] | 2019-02-04 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LYNN | 192763 | 1902 | 8 | Solar | 12_1384 | 2018-11-07 19:45 | 2018-11-08 | 59 | 26 | 33 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | REVERE | 200545 | 2151 | 10 | Solar | 12_35J4 | 2018-11-08 08:47 | 2018-11-19 | 6 | 3 | 3 | 2018-11-29 | 2018-12-18 | 13 | 0 | 13 | [20 empty] | 2018-12-28 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | REVERE | 200644 | 2151 | 10 | Solar | 12_7W2 | 2018-11-08 08:52 | 2018-11-16 | 2 | 0 | 2 | 2018-11-21 | 2018-12-07 | 10 | 0 | 10 | [20 empty] | 2018-12-17 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEST STOCKBRIDGE | 199441 | 1266 | 10 | Solar | 09_1109W3 | 2018-11-08 12:58 | 2018-11-09 | 8 | 3 | 5 | 2018-11-28 | 2018-12-18 | 14 | 0 | 14 | [20 empty] | 2018-12-21 |  | 2019-12-20 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEOMINSTER | 198844 | 1453 | 10 | Solar | 01_207W2 | 2018-11-08 13:05 | 2018-11-13 | 5 | 0 | 5 | 2018-11-21 | 2018-12-11 | 12 | 0 | 12 | [20 empty] | 2018-12-13 | 2018-11-08 13:59 |  |  | EXP | [8 empty] | 2019-04-11 | Connected |  | No
National Grid | WESTBOROUGH | 200739 | 1581 | 3.8 | Solar | 05_312W1 | 2018-11-08 13:59 | 2018-12-04 | 26 | 20 | 6 | 2019-01-11 | 2019-02-15 | 3 | 0 | 3 | [20 empty] | 2019-01-17 |  | 2020-05-19 | Yes | EXP |  | 2020-01-14 | 2020-01-27 | 13 | 0 | 13 |  |  | 2020-02-06 | Connected |  | No
National Grid | LEOMINSTER | 199248 | 1453 | 7.6 | Solar | 01_219W6 | 2018-11-08 16:00 | 2018-11-09 | 13 | 10 | 3 | 2018-12-04 | 2018-12-13 | 7 | 0 | 7 | [20 empty] | 2018-12-14 | 2018-11-08 16:10 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | DRACUT | 198227 | 1826 | 6 | Solar | 14_75L2 | 2018-11-08 16:10 | 2018-11-09 | 21 | 17 | 4 | 2018-12-14 | 2018-12-28 | 9 | 0 | 9 | [20 empty] | 2018-12-28 | 2018-11-08 17:25 | 2019-09-16 | Yes | EXP |  | 2019-04-05 | 2019-04-18 | 13 | 0 | 13 |  |  | 2019-09-10 | Connected |  | No
National Grid | METHUEN | 200801 | 1844 | 7.6 | Solar | 14_74L4 | 2018-11-08 17:25 | 2018-12-28 | 2 | 2 | 0 | 2019-01-02 | 2019-01-09 | 5 | 0 | 5 | [20 empty] | 2019-01-17 | 2018-11-08 18:00 | 2020-03-10 | Yes | EXP |  | 2019-09-05 | 2019-09-26 | 21 | 0 | 21 |  |  | 2019-10-09 | Connected |  | No
National Grid | WESTBOROUGH | 200805 | 1581 | 7.6 | Solar | 05_312W1 | 2018-11-08 18:00 | 2018-12-11 | 6 | 0 | 6 | 2018-12-20 | 2019-01-03 | 8 | 0 | 8 | [20 empty] | 2019-02-25 |  | 2020-11-08 | Yes | EXP |  | 2020-03-04 | 2020-03-25 | 21 | 0 | 21 |  |  | 2020-07-16 | Connected |  | No
National Grid | ANDOVER | 200806 | 1810 | 4.8 | Solar | 14_62L2 | 2018-11-08 18:54 | 2018-11-28 | 5 | 0 | 5 | 2018-12-06 | 2018-12-21 | 11 | 0 | 11 | [20 empty] | 2019-01-11 |  |  |  | EXP | [8 empty] | 2019-06-04 | Connected |  | No
National Grid | MARLBOROUGH | 200830 | 1752 | 10 | Solar | 05_311W5 | 2018-11-09 | 2018-11-14 | 4 | 0 | 4 | 2018-11-21 | 2018-12-18 | 17 | 0 | 17 | [20 empty] | 2018-12-17 |  |  |  | EXP | [8 empty] | 2019-03-27 | Connected |  | No
National Grid | WILLIAMSTOWN | 200510 | 1267 | 18 | Solar | 09_1003W2 | 2018-11-09 14:22 | 2019-03-13 | 2 | 2 | 0 | 2019-03-15 | 2019-04-01 | 12 | 3 | 9 | [20 empty] | 2019-04-10 |  | 2021-10-29 |  | EXP | [8 empty] | 2021-10-14 | Connected |  | No
National Grid | WILLIAMSTOWN | 200518 | 1267 | 60 | Solar | 09_1003W2 | 2018-11-09 14:37 | 2018-11-13 | 42 | 33 | 9 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | REVERE | 198416 | 2151 | 3.8 | Solar | 12_7W2 | 2018-11-09 14:52 | 2018-11-13 | 5 | 0 | 5 | 2018-11-21 | 2018-12-18 | 17 | 2 | 15 | [20 empty] | 2019-01-09 |  | 2020-11-20 |  | EXP | [8 empty] | 2020-10-08 | Connected |  | No
National Grid | CHELMSFORD | 196414 | 1824 | 9.6 | Solar | 14_16L4 | 2018-11-09 15:04 | 2018-11-13 | 16 | 15 | 1 | 2018-12-10 | 2018-12-13 | 3 | 0 | 3 | [20 empty] | 2018-12-14 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WILLIAMSTOWN | 200515 | 1267 | 53.3 | Solar | 09_1003W1 | 2018-11-09 15:16 | 2018-11-13 | 51 | 42 | 9 | 2019-01-30 | 2019-04-05 | 47 | 26 | 21 | [20 empty] | 2019-04-08 |  | 2022-02-26 |  | EXP | [8 empty] | 2021-10-14 | Connected |  | No
National Grid | RANDOLPH | 197323 | 2368 | 3.8 | Solar | 07_97W1 | 2018-11-09 15:56 | 2018-11-13 | 4 | 0 | 4 | 2018-11-21 | 2018-12-18 | 17 | 0 | 17 | [20 empty] | 2018-12-21 | 2018-11-10 10:28 | 2021-11-18 |  | EXP | [8 empty] | 2021-02-24 | Connected |  | No
National Grid | ATTLEBORO | 195799 | 2703 | 6 | Solar | 05_8L4 | 2018-11-10 10:28 | 2018-11-14 | 3 | 3 | 0 | 2018-11-19 | 2018-12-14 | 17 | 10 | 7 | [20 empty] | 2018-12-18 |  | 2019-05-23 | Yes | EXP |  | 2019-03-20 | 2019-03-19 | 0 | 0 | 0 |  |  | 2019-03-29 | Connected |  | No
National Grid | WILBRAHAM | 200996 | 1095 | 7.6 | Solar | 09_507L2 | 2018-11-12 14:09 | 2018-11-14 | 2 | 0 | 2 | 2018-11-19 | 2018-12-06 | 11 | 0 | 11 | [20 empty] | 2018-12-18 | 2018-11-12 15:03 | 2020-03-20 |  | EXP | [8 empty] | 2020-03-02 | Connected |  | No
National Grid | RANDOLPH | 201002 | 2368 | 15.2 | Solar | 07_97W2 | 2018-11-12 15:03 | 2018-11-14 | 2 | 0 | 2 | 2018-11-19 | 2018-12-06 | 11 | 0 | 11 | [20 empty] | 2019-06-27 |  | 2020-07-22 | Yes | EXP |  | 2020-01-30 | 2020-02-20 | 21 | 0 | 21 |  |  | 2020-07-14 | Connected |  | No
National Grid | EAST BRIDGEWATER | 201018 | 2333 | 7.6 | Solar | 07_797W42 | 2018-11-12 15:59 | 2018-11-14 | 3 | 1 | 2 | 2018-11-19 | 2018-12-06 | 11 | 0 | 11 | [20 empty] | 2018-12-18 |  | 2019-11-29 |  | EXP | [8 empty] | 2019-11-14 | Connected |  | No
National Grid | MONROE | 200718 | 1350 | 4998 | Solar | 09_1019W1 | 2018-11-12 20:01 | 2018-11-16 | 9 | 1 | 8 | [10 empty] | 2018-12-03 | 2018-12-28 | 18 | 0 | 18 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | HARDWICK | 200895 | 1037 | 1660 | Solar | 09_501L2 | 2018-11-12 20:34 | 2018-11-16 | 8 | 1 | 7 | [10 empty] | 2018-12-03 | 2019-01-30 | 56 | 21 | 35 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | HARDWICK | 200896 | 1037 | 4998 | Solar | 09_501L2 | 2018-11-12 20:49 | 2018-11-13 | 11 | 6 | 5 | [10 empty] | 2018-12-03 | 2018-12-29 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTMINSTER | 200898 | 1473 | 4998 | Solar | 01_610W3 | 2018-11-12 21:02 | 2018-11-16 | 7 | 0 | 7 | [10 empty] | 2018-12-03 | 2019-01-25 | 37 | 18 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 189778 | 1603 | 10 | Solar | 01_7J387 | 2018-11-13 07:48 | 2018-11-14 | 11 | 7 | 4 | 2018-12-04 | 2018-12-14 | 8 | 0 | 8 | [20 empty] | 2018-12-18 |  | 2020-11-13 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LOWELL | 201056 | 1854 | 7.6 | Solar | 14_77L3 | 2018-11-13 08:24 | 2018-12-04 | 41 | 34 | 7 | 2019-01-31 | 2019-02-05 | 5 | 0 | 5 | [20 empty] | 2019-02-06 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ATHOL | 200891 | 1331 | 10 | Solar | 09_702W1 | 2018-11-13 11:27 | 2018-11-21 | 7 | 0 | 7 | 2018-12-05 | 2018-12-21 | 12 | 0 | 12 | [20 empty] | 2019-01-16 |  | 2019-11-07 |  | EXP | [8 empty] | 2019-05-10 | Connected |  | No
National Grid | COHASSET | 200495 | 2025 | 7.5 | Solar | 07_96W41 | 2018-11-13 12:04 | 2019-04-12 | 0 | 0 | 0 | 2019-04-12 | 2019-05-03 | 16 | 16 | 0 | [20 empty] | 2019-05-13 |  |  |  | EXP | [8 empty] | 2019-10-02 | Connected |  | No
National Grid | WEYMOUTH | 199236 | 2191 | 10 | Solar | 07_6W2 | 2018-11-13 12:42 | 2018-11-14 | 49 | 45 | 4 | 2019-01-29 | 2019-01-31 | 2 | 0 | 2 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HAWLEY | 197531 | 1037 | 4998 | Solar | 09_1019W1 | 2018-11-13 13:58 | 2018-11-14 | 14 | 13 | 1 | [10 empty] | 2018-12-07 | 2019-01-25 | 33 | 9 | 24 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | HARDWICK | 197527 | 1082 | 4998 | Solar | 09_501L2 | 2018-11-13 17:40 | 2018-11-16 | 9 | 1 | 8 | [10 empty] | 2018-12-03 | 2018-12-28 | 18 | 0 | 18 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | LEOMINSTER | 197643 | 1453 | 10 | Solar | 01_225W3 | 2018-11-13 19:02 | 2018-11-14 | 108 | 103 | 5 | 2019-04-23 | 2019-06-04 | 29 | 25 | 4 | [20 empty] | 2019-09-17 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | TEWKSBURY | 198677 | 1876 | 6 | Solar | 14_14L2 | 2018-11-13 19:42 | 2018-11-14 | 11 | 4 | 7 | 2018-12-04 | 2018-12-21 | 13 | 0 | 13 | [20 empty] | 2019-01-07 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MONTEREY | 197613 | 1245 | 875 | Solar | 09_1109W1 | 2018-11-14 | 2018-11-15 | 8 | 0 | 8 | [10 empty] | 2018-11-30 | 2019-01-15 | 31 | 12 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BEVERLY | 201091 | 1915 | 3.8 | Solar | 12_12L2 | 2018-11-14 10:10 | 2018-11-29 | 7 | 2 | 5 | 2018-12-11 | 2018-12-13 | 2 | 0 | 2 | [21 empty] | 2018-11-14 10:36 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 201180 | 1603 | 5 | Solar | 01_7J386 | 2018-11-14 10:36 | 2019-01-09 | 7 | 0 | 7 | 2019-01-22 | 2019-01-25 | 3 | 0 | 3 | [20 empty] | 2019-02-22 |  | 2020-11-13 | Yes | EXP | [8 empty] | 2020-01-13 | Connected |  | No
National Grid | SALISBURY | 200995 | 1952 | 7.6 | Solar | 14_7L1 | 2018-11-14 13:47 | 2018-11-14 | 39 | 37 | 2 | 2019-01-10 | 2019-01-21 | 7 | 4 | 3 | [20 empty] | 2019-01-22 |  |  |  | EXP | [8 empty] | 2019-04-10 | Connected |  | No
National Grid | PHILLIPSTON | 190867 | 1331 | 4998 | Solar | 09_604W4 | 2018-11-14 14:08 | 2018-11-15 | 10 | 1 | 9 | [10 empty] | 2018-12-03 | 2019-01-25 | 56 | 20 | 36 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTHBOROUGH | 196299 | 1532 | 236 | Solar | 05_313W3 | 2018-11-14 17:49 | 2018-11-15 | 3 | 0 | 3 | 2018-11-21 | 2018-12-19 | 18 | 2 | 16 | 2019-06-11 | 2019-06-10 | 0 | 0 | 0 | [5 empty] | 2019-06-11 | 2019-06-10 | 0 | 0 | 0 | [9 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | WINCHENDON | 200441 | 1475 | 4998 | Solar | 01_607W3 | 2018-11-15 07:38 | 2018-11-29 | 0 | 0 | 0 | [10 empty] | 2018-11-30 | 2019-01-25 | 57 | 20 | 37 | [11 empty] | 2018-11-15 10:25 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | FLORENCE | 201270 | 1062 | 3 | Solar | 09_909W4 | 2018-11-15 10:25 | 2018-12-10 | 7 | 0 | 7 | 2018-12-20 | 2019-01-03 | 8 | 0 | 8 | [20 empty] | 2019-01-14 |  |  | Yes | EXP | [8 empty] | 2019-09-28 | Connected |  | No
National Grid | NORTHBOROUGH | 196297 | 1532 | 496 | Solar | 05_313W3 | 2018-11-15 11:37 | 2018-11-16 | 2 | 0 | 2 | 2018-11-21 | 2018-12-21 | 20 | 2 | 18 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 201073 | 1604 | 396 | Solar | 01_27W1 | 2018-11-15 15:24 | 2018-11-16 | 4 | 2 | 2 | 2018-11-26 | 2018-12-10 | 10 | 2 | 8 | [20 empty] | 2018-12-12 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 201105 | 2301 | 496 | Solar | 07_98W10 | 2018-11-15 15:25 | 2018-11-16 | 13 | 12 | 1 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WENDELL | 188655 | 1379 | 3100 | Solar | 09_705W1 | 2018-11-16 | 2018-11-19 | 8 | 0 | 8 | [10 empty] | 2018-12-04 | 2019-01-09 | 24 | 0 | 24 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SOUTH EASTON | 201301 | 2375 | 250 | Solar | 07_92W44 | 2018-11-16 | 2018-11-19 | 0 | 0 | 0 | 2018-11-20 | 2018-12-26 | 23 | 5 | 18 | [20 empty] | 2018-12-27 |  | 2019-12-31 |  | EXP | [8 empty] | 2019-12-19 | Connected |  | No
National Grid | GRANBY | 201376 | 1033 | 10 | Solar | 09_527L2 | 2018-11-16 12:37 | 2018-11-21 | 25 | 24 | 1 | 2018-12-31 | 2019-01-09 | 7 | 0 | 7 | [20 empty] | 2019-01-17 |  |  |  | EXP | [8 empty] | 2019-02-13 | Connected |  | No
National Grid | MONSON | 201377 | 1057 | 7.6 | Solar | 09_139L1 | 2018-11-16 12:40 | 2018-11-19 | 21 | 21 | 0 | 2018-12-20 | 2018-12-31 | 6 | 0 | 6 | [20 empty] | 2019-01-02 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LOWELL | 198546 | 1854 | 7.6 | Solar | 14_21L3 | 2018-11-16 12:56 | 2018-11-19 | 3 | 3 | 0 | 2018-11-26 | 2018-12-11 | 11 | 0 | 11 | [20 empty] | 2018-12-11 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NEWBURYPORT | 198160 | 1950 | 7.6 | Solar | 14_47L2 | 2018-11-16 13:38 | 2018-11-19 | 0 | 0 | 0 | 2018-11-20 | 2018-12-18 | 18 | 2 | 16 | [20 empty] | 2018-12-19 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BILLERICA | 201405 | 1821 | 15.2 | Solar | 14_92L4 | 2018-11-16 14:58 | 2018-11-19 | 3 | 3 | 0 | 2018-11-26 | 2018-12-11 | 11 | 0 | 11 | [20 empty] | 2018-12-18 | 2018-11-17 10:55 | 2020-11-16 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HOPEDALE | 188692 | 1747 | 499.5 | Solar | 05_335W9 | 2018-11-17 10:55 | 2018-11-19 | 33 | 25 | 8 | 2019-01-09 | 2019-02-08 | 22 | 4 | 18 | 2019-03-01 | 2019-07-02 | 87 | 53 | 34 | [5 empty] | 2019-03-01 | 2019-07-02 | 87 | 53 | 34 | [5 empty] | 2019-07-11 |  | 2021-01-18 | Yes | EXP | [9 empty] | Withdrawn |  | No
National Grid | MILLBURY | 201445 | 1527 | 7.6 | Solar | 01_304W3 | 2018-11-17 21:37 | 2018-11-20 | 7 | 5 | 2 | 2018-12-04 | 2018-12-20 | 12 | 0 | 12 | [20 empty] | 2018-12-21 |  | 2019-10-21 |  | EXP | [8 empty] | 2019-09-12 | Connected |  | No
National Grid | METHUEN | 194325 | 1844 | 7.6 | Solar | 14_63L2 | 2018-11-18 21:09 | 2018-11-19 | 6 | 0 | 6 | 2018-11-30 | 2018-12-18 | 12 | 0 | 12 | [20 empty] | 2019-02-04 |  | 2020-11-27 |  | EXP | [8 empty] | 2020-02-18 | Connected |  | No
National Grid | ATTLEBORO | 200411 | 2703 | 492 | Solar | 05_9L4 | 2018-11-19 | 2018-12-05 | 11 | 5 | 6 | [5 empty] | 2019-04-02 | 2019-05-02 | 22 | 0 | 22 | 2018-12-20 | 2019-02-07 | 32 | 17 | 15 | 2019-04-02 | 2019-05-02 | 22 | 0 | 22 | [5 empty] | 2019-12-19 | 2018-11-19 07:30 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | EAST BRIDGEWATER | 194734 | 2333 | 10 | Solar | 07_797W29 | 2018-11-19 07:30 | 2018-11-20 | 0 | 0 | 0 | 2018-11-20 | 2018-12-07 | 11 | 0 | 11 | [20 empty] | 2018-12-11 |  | 2020-03-27 | Yes | EXP |  | 2019-11-15 | 2019-12-12 | 27 | 0 | 27 |  |  | 2019-12-12 | Connected |  | No
National Grid | HAYDENVILLE | 198406 | 1039 | 3400 | Solar | 09_909W3 | 2018-11-19 09:40 | 2018-11-20 | 7 | 0 | 7 | [10 empty] | 2018-12-04 | 2019-10-08 | 191 | 25 | 166 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | RUTLAND | 199325 | 1543 | 4998 | Solar | 01_55W1 | 2018-11-19 10:13 | 2018-11-20 | 4 | 0 | 4 | [10 empty] | 2018-11-29 | 2019-01-23 | 37 | 13 | 24 | [5 empty] | 2020-07-10 | 2020-10-07 | 63 | 3 | 60 |  |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | RUTLAND | 199337 | 1543 | 4998 | Solar | 01_55W1 | 2018-11-19 12:02 | 2018-11-20 | 9 | 0 | 9 | [10 empty] | 2018-12-06 | 2019-02-05 | 41 | 17 | 24 | [5 empty] | 2020-07-10 | 2020-10-07 | 63 | 3 | 60 |  | 2018-11-19 15:12 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WEBSTER | 201618 | 1570 | 10 | Solar | 01_412L5 | 2018-11-19 15:12 | 2018-12-28 | 3 | 0 | 3 | 2019-01-04 | 2019-01-10 | 4 | 0 | 4 | [20 empty] | 2019-02-19 |  | 2021-01-07 | Yes | EXP | [8 empty] | 2021-02-23 | Connected |  | No
National Grid | AMESBURY | 201623 | 1913 | 7.6 | Solar | 14_5J13 | 2018-11-19 15:28 | 2018-12-28 | 197 | 26 | 171 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | TEWKSBURY | 199222 | 1876 | 820 | Solar | 14_14L3 | 2018-11-20 10:19 | 2018-11-21 | 3 | 0 | 3 | [10 empty] | 2018-11-29 | 2019-03-07 | 68 | 43 | 25 | [11 empty] | 2018-11-20 12:35 |  |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | WESTBOROUGH | 201712 | 1581 | 7.6 | Solar | 05_314W5 | 2018-11-20 12:35 | 2018-12-10 | 4 | 0 | 4 | 2018-12-17 | 2019-01-02 | 10 | 0 | 10 | [20 empty] | 2019-01-03 |  | 2020-04-14 | Yes | EXP |  | 2019-11-13 | 2019-11-27 | 14 | 0 | 14 |  |  | 2020-01-14 | Connected |  | No
National Grid | LAWRENCE | 201742 | 1843 | 372 | Solar | 14_61L1 | 2018-11-21 13:37 | 2018-11-26 | 4 | 4 | 0 | 2018-11-30 | 2018-12-26 | 17 | 0 | 17 | [20 empty] | 2018-12-26 |  | 2021-07-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MARLBOROUGH | 201858 | 1752 | 10 | Solar | 05_311W3 | 2018-11-21 15:12 | 2018-12-28 | 19 | 19 | 0 | 2019-01-28 | 2019-01-29 | 1 | 0 | 1 | [20 empty] | 2019-01-30 |  | 2020-01-30 |  | EXP | [8 empty] | 2020-01-14 | Connected |  | No
National Grid | BARRE | 194815 | 1005 | 250 | Solar | 09_604W4 | 2018-11-21 23:35 | 2018-11-26 | 17 | 10 | 7 | 2018-12-20 | 2019-01-03 | 8 | 0 | 8 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | BRADFORD | 201984 | 1835 | 3.8 | Solar | 14_43L3 | 2018-11-26 12:28 | 2018-12-14 | 4 | 0 | 4 | 2018-12-21 | 2019-01-07 | 9 | 0 | 9 | [20 empty] | 2019-01-22 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HADENVILLE | 198758 | 1039 | 3500 | Solar | 09_909W3 | 2018-11-26 13:50 | 2018-11-27 | 1 | 0 | 1 | [10 empty] | 2018-11-29 | 2019-02-07 | 52 | 31 | 21 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | REVERE | 196955 | 2151 | 3.8 | Solar | 12_7W2 | 2018-11-26 14:22 | 2018-11-27 | 49 | 44 | 5 | 2019-02-05 | 2019-02-07 | 2 | 0 | 2 | [20 empty] | 2019-02-07 |  | 2020-11-26 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTH QUINCY | 202010 | 2171 | 6.4 | Solar | 07_11W1 | 2018-11-26 14:23 | 2018-11-30 | 14 | 14 | 0 | 2018-12-21 | 2019-01-07 | 9 | 0 | 9 | [20 empty] | 2019-01-17 | 2018-11-26 15:29 |  |  | EXP | [8 empty] | 2019-02-21 | Connected |  | No
National Grid | STOUGHTON | 202031 | 2072 | 100 | Solar | 07_913W69 | 2018-11-26 15:29 | 2018-11-27 | 7 | 2 | 5 | 2018-12-06 | 2019-01-04 | 20 | 7 | 13 | 2019-02-15 | 2019-03-25 | 25 | 6 | 19 | [5 empty] | 2019-02-15 | 2019-03-25 | 25 | 6 | 19 | [5 empty] | 2019-04-19 |  | 2020-10-30 | Yes | EXP | [8 empty] | 2020-10-26 | Connected |  | No
National Grid | HOLLAND | 197062 | 1521 | 450 | Solar | 09_516L1 | 2018-11-27 08:34 | 2018-11-28 | 5 | 0 | 5 | 2018-12-06 | 2019-01-28 | 34 | 17 | 17 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTBOROUGH | 194780 | 1581 | 7.6 | Solar | 05_314W4 | 2018-11-27 08:35 | 2018-11-27 | 6 | 0 | 6 | 2018-12-06 | 2019-10-15 | 160 | 0 | 160 | [20 empty] | 2019-03-11 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTPORT | 196024 | 2790 | 7.6 | Solar | 05_115W52 | 2018-11-27 09:29 | 2018-11-28 | 5 | 0 | 5 | 2018-12-06 | 2018-12-18 | 8 | 0 | 8 | [20 empty] | 2018-12-13 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LYNN | 201985 | 1902 | 7.6 | Solar | 12_1J901 | 2018-11-27 10:01 | 2018-12-05 | 8 | 0 | 8 | 2018-12-18 | 2019-01-02 | 9 | 0 | 9 | [20 empty] | 2019-01-16 | 2018-11-27 10:05 |  |  | EXP | [8 empty] | 2019-06-16 | Connected |  | No
National Grid | LOWELL | 202097 | 1851 | 3.8 | Solar | 14_16L3 | 2018-11-27 10:05 | 2018-12-28 | 19 | 19 | 0 | 2019-01-28 | 2019-02-04 | 5 | 0 | 5 | [20 empty] | 2019-02-04 | 2018-11-27 10:27 | 2020-11-27 | Yes | EXP |  | 2020-07-17 | 2020-08-12 | 26 | 0 | 26 |  |  | 2020-08-17 | Connected |  | No
National Grid | MILLBURY | 202103 | 1527 | 3.8 | Solar | 01_304W3 | 2018-11-27 10:27 | 2018-12-14 | 4 | 0 | 4 | 2018-12-21 | 2019-01-07 | 9 | 0 | 9 | [20 empty] | 2019-01-18 |  | 2020-05-14 | Yes | EXP |  | 2019-11-23 | 2020-01-03 | 41 | 0 | 41 |  |  | 2020-02-27 | Connected |  | No
National Grid | BEVERLY | 201284 | 1915 | 180 | Solar | 12_12L2 | 2018-11-27 10:54 | 2018-11-28 | 0 | 0 | 0 | 2018-11-28 | 2018-12-28 | 21 | 3 | 18 | [20 empty] | 2018-12-28 |  |  |  | EXP | [8 empty] | 2019-11-21 | Connected |  | No
National Grid | CHELMSFORD | 202054 | 1824 | 4975 | Solar | 14_2L4 | 2018-11-27 11:27 | 2018-11-28 | 157 | 2 | 155 | [10 empty] | 2018-12-07 | 2019-02-19 | 49 | 25 | 24 | [12 empty] | 2021-09-27 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 191612 | 1507 | 272 | Solar | 01_406L1 | 2018-11-27 11:28 | 2018-11-28 | 0 | 0 | 0 | [10 empty] | 2018-11-28 | 2019-03-22 | 108 | 56 | 52 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | BERLIN | 202205 | 1503 | 20 | Solar | 05_318W3 | 2018-11-27 18:11 | 2018-11-28 | 5 | 0 | 5 | 2018-12-06 | 2018-12-21 | 11 | 0 | 11 | [20 empty] | 2019-03-11 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTBOROUGH | 202201 | 1581 | 120 | Solar | 05_314W3 | 2018-11-28 | 2018-12-12 | 10 | 5 | 5 | 2018-12-28 | 2019-02-20 | 36 | 16 | 20 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | LAWRENCE | 202326 | 1843 | 450 | Solar | 14_2326 | 2018-11-28 | 2018-12-13 | 43 | 38 | 5 | 2019-02-15 | 2019-03-25 | 26 | 12 | 14 | [20 empty] | 2019-04-10 |  | 2020-06-30 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTBOROUGH | 202461 | 1581 | 75 | Solar | 05_314W3 | 2018-11-28 | 2018-12-12 | 10 | 5 | 5 | 2018-12-28 | 2019-02-20 | 36 | 16 | 20 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTBOROUGH | 203260 | 1581 | 60 | Solar | 05_314W3 | 2018-11-28 | 2018-12-12 | 10 | 5 | 5 | 2018-12-28 | 2019-02-20 | 36 | 16 | 20 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTBOROUGH | 203263 | 1581 | 90 | Solar | 05_314W3 | 2018-11-28 | 2018-12-12 | 10 | 5 | 5 | 2018-12-28 | 2019-02-20 | 36 | 16 | 20 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTBOROUGH | 203266 | 1581 | 60 | Solar | 05_314W3 | 2018-11-28 | 2018-12-12 | 10 | 5 | 5 | 2018-12-28 | 2019-02-20 | 35 | 15 | 20 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTBOROUGH | 203267 | 1581 | 105 | Solar | 05_314W3 | 2018-11-28 | 2018-12-12 | 10 | 5 | 5 | 2018-12-28 | 2019-02-20 | 36 | 16 | 20 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTBOROUGH | 203268 | 1581 | 105 | Solar | 05_314W3 | 2018-11-28 | 2018-12-12 | 10 | 5 | 5 | 2018-12-28 | 2019-02-20 | 36 | 16 | 20 | [21 empty] | 2018-11-28 18:02 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LAWRENCE | 202318 | 1843 | 7.6 | Solar | 14_61L3 | 2018-11-28 18:02 | 2018-12-28 | 7 | 0 | 7 | 2019-01-10 | 2019-01-11 | 1 | 0 | 1 | [20 empty] | 2019-02-26 | 2018-11-29 09:30 | 2020-11-28 | Yes | EXP | [8 empty] | 2020-10-24 | Connected |  | No
National Grid | LEOMINSTER | 196330 | 1453 | 7.6 | Solar | 01_207W2 | 2018-11-29 09:30 | 2018-11-30 | 13 | 6 | 7 | 2018-12-20 | 2019-01-04 | 9 | 0 | 9 | [20 empty] | 2019-03-11 |  | 2021-01-27 | Yes | EXP |  | 2021-05-26 | 2021-06-24 | 29 | 0 | 29 |  |  | 2021-10-12 | Connected |  | Yes
National Grid | WORCESTER | 202335 | 1610 | 72 | Solar | 01_4J324 | 2018-11-29 09:42 | 2018-11-30 | 2 | 0 | 2 | 2018-12-05 | 2019-01-03 | 17 | 13 | 4 | [20 empty] | 2019-01-17 |  | 2019-12-17 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BELCHERTOWN | 197687 | 1007 | 3.8 | Solar | 09_509L2 | 2018-11-29 13:44 | 2018-11-30 | 6 | 0 | 6 | 2018-12-11 | 2020-03-27 | 269 | 0 | 269 | [20 empty] | 2019-01-16 |  | 2020-11-29 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MARLBOROUGH | 202096 | 1752 | 450 | Solar | 05_311W6 | 2018-11-30 14:10 | 2018-12-03 | 15 | 11 | 4 | 2018-12-24 | 2019-05-07 | 92 | 26 | 66 | [21 empty] | 2018-12-03 11:45 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SAUGUS | 199644 | 1906 | 11.4 | Solar | 12_16W1 | 2018-12-03 11:45 | 2018-12-04 | 9 | 0 | 9 | 2018-12-18 | 2019-01-02 | 9 | 0 | 9 | [20 empty] | 2019-01-07 |  | 2020-12-03 | Yes | EXP |  | 2020-01-29 | 2020-02-05 | 7 | 0 | 7 |  |  | 2020-04-15 | Connected |  | No
National Grid | SALISBURY | 198767 | 1952 | 13.8 | Solar | 14_7L2 | 2018-12-03 12:00 | 2018-12-04 | 7 | 0 | 7 | 2018-12-14 | 2018-12-28 | 9 | 0 | 9 | [20 empty] | 2019-03-25 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH BROOKFIELD | 195871 | 1535 | 2000 | Solar | 01_525L1 | 2018-12-04 | 2018-12-07 | 11 | 5 | 6 | [10 empty] | 2018-12-26 | 2019-01-24 | 37 | 0 | 37 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | QUINCY | 201688 | 2169 | 66.6 | Solar | 07_1J11 | 2018-12-04 10:46 | 2018-12-05 | 11 | 6 | 5 | 2019-03-06 | 2019-03-27 | 16 | 16 | 0 | [21 empty] | 2018-12-04 17:35 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | DRACUT | 199149 | 1826 | 10 | Solar | 14_75L5 | 2018-12-04 17:35 | 2018-12-05 | 24 | 16 | 8 | 2019-01-11 | 2019-01-21 | 5 | 0 | 5 | [20 empty] | 2019-01-22 |  | 2019-10-02 | Yes | EXP |  | 2019-05-01 | 2019-06-11 | 41 | 0 | 41 |  |  | 2019-09-03 | Connected |  | No
National Grid | BROCKTON | 191685 | 2301 | 136 | Solar | 07_797W19 | 2018-12-05 14:26 | 2018-12-06 | 4 | 0 | 4 | 2018-12-13 | 2018-12-28 | 10 | 0 | 10 | [21 empty] | 2018-12-05 15:38 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MILFORD | 195290 | 1757 | 710 | Other | 05_335W4 | 2018-12-05 15:38 | 2018-12-06 | 69 | 45 | 24 | [10 empty] | 2019-03-19 | 2019-04-24 | 26 | 24 | 2 | [10 empty] | 2019-11-27 |  | 2024-06-26 |  | STD | [9 empty] | Design |  | No
National Grid | NORTHBOROUGH | 196296 | 1532 | 794 | Solar |  | 2018-12-05 17:58 | 2018-12-06 | 12 | 3 | 9 | [10 empty] | 2018-12-24 | 2019-01-25 | 44 | 2 | 42 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | TYNGSBORO | 203063 | 1879 | 250 | Solar | 14_211L1 | 2018-12-06 | 2018-12-11 | 14 | 10 | 4 | 2019-01-03 | 2019-01-29 | 17 | 0 | 17 | 2019-07-12 | 2019-07-11 | 0 | 0 | 0 | [5 empty] | 2019-07-12 | 2019-07-11 | 0 | 0 | 0 | [5 empty] | 2019-07-23 | 2018-12-06 | 2021-06-09 |  | EXP | [8 empty] | 2021-06-09 | Connected |  | No
National Grid | WORCESTER | 203085 | 1606 | 150 | Solar | 01_24W2 | 2018-12-06 | 2018-12-12 | 14 | 12 | 2 | 2019-01-03 | 2019-01-08 | 3 | 0 | 3 | 2019-01-18 | 2019-04-30 | 70 | 4 | 66 | [5 empty] | 2019-01-18 | 2019-04-30 | 70 | 4 | 66 | [5 empty] | 2019-05-17 |  | 2020-09-25 | Yes | EXP |  | 2020-02-14 | 2020-03-12 | 27 | 0 | 27 |  |  | 2020-09-25 | Connected |  | No
National Grid | EAST LONGMEADOW | 202531 | 1028 | 486 | Solar | 09_522L2 | 2018-12-06 11:03 | 2018-12-07 | 3 | 0 | 3 | 2018-12-13 | 2019-01-08 | 16 | 6 | 10 | [20 empty] | 2019-01-17 |  | 2020-08-28 |  | EXP | [8 empty] | 2020-07-21 | Connected |  | No
National Grid | GRANBY | 198592 | 1033 | 5000 | Solar | 09_527L1 | 2018-12-06 11:13 | 2018-12-07 | 11 | 2 | 9 | [10 empty] | 2018-12-24 | 2019-01-22 | 37 | 0 | 37 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WALES | 200636 | 1081 | 1560 | Solar | 09_516L1 | 2018-12-06 11:40 | 2018-12-07 | 103 | 26 | 77 | [10 empty] | 2019-01-29 | 2019-03-13 | 11 | 11 | 0 | [12 empty] | 2021-01-01 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ANDOVER | 202797 | 1810 | 10 | Solar | 14_50L3 | 2018-12-06 11:50 | 2018-12-07 | 7 | 0 | 7 | 2018-12-19 | 2019-09-05 | 149 | 21 | 128 | [20 empty] | 2019-03-05 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTFORD | 202799 | 1886 | 10 | Solar | 14_58L3 | 2018-12-06 11:54 | 2018-12-12 | 2 | 0 | 2 | 2018-12-17 | 2019-02-06 | 34 | 25 | 9 | [20 empty] | 2019-02-07 |  |  |  | EXP | [8 empty] | 2019-05-04 | Connected |  | No
National Grid | OAKHAM | 198424 | 1068 | 2000 | Battery Add-On | 09_604W2 | 2018-12-06 16:18 | 2018-12-07 | 29 | 20 | 9 | [10 empty] | 2019-01-22 | 2019-03-13 | 36 | 17 | 19 | [10 empty] | 2023-02-27 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH CHELMSFORD | 198842 | 1863 | 3.8 | Solar | 14_2L2 | 2018-12-06 16:20 | 2018-12-07 | 8 | 0 | 8 | 2018-12-20 | 2019-01-16 | 18 | 8 | 10 | [20 empty] | 2019-02-13 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SUTTON | 202902 | 1590 | 10 | Battery Add-On | 01_304W6 | 2018-12-06 17:23 | 2018-12-12 | 2 | 0 | 2 | 2018-12-17 | 2018-12-28 | 8 | 0 | 8 | [20 empty] | 2019-01-02 | 2018-12-06 18:43 |  |  | EXP | [8 empty] | 2019-04-03 | Connected |  | Yes
National Grid | WEBSTER | 202707 | 1570 | 10 | Solar | 01_412L1 | 2018-12-06 18:43 | 2018-12-07 | 25 | 20 | 5 | 2019-01-15 | 2019-01-23 | 5 | 0 | 5 | [20 empty] | 2019-01-23 |  | 2019-10-30 | Yes | EXP |  | 2019-06-26 | 2019-08-26 | 61 | 0 | 61 |  |  | 2019-09-16 | Connected |  | No
National Grid | RANDOLPH | 202727 | 2368 | 7.6 | Solar | 07_5W2 | 2018-12-06 19:02 | 2018-12-07 | 7 | 0 | 7 | 2018-12-19 | 2020-01-22 | 201 | 0 | 201 | [20 empty] | 2019-02-07 | 2018-12-07 06:59 | 2020-12-06 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | FLORENCE | 197077 | 1062 | 6 | Solar | 09_909W2 | 2018-12-07 06:59 | 2019-01-03 | 5 | 0 | 5 | 2019-01-11 | 2019-01-23 | 7 | 0 | 7 | [20 empty] | 2019-01-29 |  |  | Yes | EXP |  | 2019-03-20 | 2019-03-19 | 0 | 0 | 0 |  |  | 2019-07-16 | Connected |  | No
National Grid | WEBSTER | 201422 | 1570 | 500 | Solar | 01_412L6 | 2018-12-07 09:55 | 2018-12-10 | 18 | 9 | 9 | [10 empty] | 2019-01-07 | 2019-02-05 | 24 | 0 | 24 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | GRANBY | 201380 | 1033 | 3000 | Solar | 09_527L1 | 2018-12-07 10:55 | 2018-12-10 | 100 | 26 | 74 | [10 empty] | 2019-01-30 | 2019-04-02 | 43 | 26 | 17 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | PALMER | 201424 | 1069 | 4290 | Solar | 09_503L1 | 2018-12-07 16:25 | 2018-12-10 | 20 | 12 | 8 | [10 empty] | 2019-01-10 | 2019-02-06 | 0 | 0 | 0 | [11 empty] | 2018-12-10 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BERLIN | 202568 | 1503 | 15.2 | Solar | 05_318W3 | 2018-12-10 | 2018-12-13 | 6 | 0 | 6 | 2018-12-24 | 2019-01-08 | 9 | 0 | 9 | [20 empty] | 2019-01-08 |  | 2021-09-23 | Yes | EXP |  | 2021-04-07 | 2021-04-14 | 7 | 0 | 7 |  |  | 2021-04-23 | Connected |  | No
National Grid | LEOMINSTER | 203373 | 1453 | 19.52 | Solar | 01_207W3 | 2018-12-10 15:37 | 2018-12-11 | 13 | 5 | 8 | 2019-01-02 | 2019-02-20 | 28 | 23 | 5 | [20 empty] | 2019-02-20 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LEOMINSTER | 199725 | 1453 | 10 | Solar | 01_225W4 | 2018-12-11 19:05 | 2018-12-12 | 5 | 0 | 5 | 2018-12-20 | 2020-03-27 | 247 | 0 | 247 | [20 empty] | 2019-03-11 | 2018-12-12 14:45 | 2020-12-11 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 201443 | 2302 | 8.96 | Solar | 07_911W56 | 2018-12-12 14:45 | 2018-12-18 | 36 | 32 | 4 | 2019-02-11 | 2019-02-15 | 4 | 0 | 4 | [20 empty] | 2019-02-19 |  | 2019-08-30 |  | EXP |  | 2019-04-09 | 2019-05-01 | 22 | 0 | 22 |  |  | 2019-08-16 | Connected |  | No
National Grid | GRANBY | 201291 | 1033 | 3000 | Solar | 09_527L1 | 2018-12-12 16:38 | 2018-12-13 | 84 | 63 | 21 | [10 empty] | 2019-02-25 | 2019-03-20 | 0 | 0 | 0 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | NORWELL | 202681 | 2061 | 10 | Solar | 07_96W43 | 2018-12-12 19:10 | 2018-12-18 | 16 | 14 | 2 | 2019-01-11 | 2019-01-16 | 3 | 0 | 3 | [20 empty] | 2019-01-16 |  | 2019-07-01 |  | EXP | [8 empty] | 2019-06-12 | Connected |  | No
National Grid | WESTBOROUGH | 203444 | 1581 | 10 | Solar | 05_312W1 | 2018-12-12 19:14 | 2018-12-13 | 6 | 0 | 6 | 2018-12-24 | 2019-01-08 | 9 | 0 | 9 | [20 empty] | 2019-01-31 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORWELL | 203337 | 2061 | 30 | Solar | 07_915W35 | 2018-12-12 19:18 | 2018-12-13 | 7 | 0 | 7 | 2018-12-26 | 2019-01-08 | 8 | 0 | 8 | [20 empty] | 2019-02-26 |  | 2019-11-07 |  | EXP | [8 empty] | 2019-07-30 | Connected |  | No
National Grid | BOXFORD | 203369 | 1921 | 5 | Solar | 14_56L3 | 2018-12-12 19:23 | 2018-12-13 | 7 | 0 | 7 | 2018-12-26 | 2019-02-01 | 26 | 9 | 17 | [20 empty] | 2019-02-25 | 2018-12-12 19:31 | 2019-11-07 |  | EXP | [8 empty] | 2019-08-21 | Connected |  | No
National Grid | LYNN | 201447 | 1904 | 7.6 | Solar | 12_24W1 | 2018-12-12 19:31 | 2018-12-13 | 7 | 0 | 7 | 2018-12-26 | 2019-01-10 | 11 | 4 | 7 | [20 empty] | 2019-01-14 |  | 2021-04-14 | Yes | EXP |  | 2020-11-03 | 2021-02-08 | 97 | 0 | 97 |  |  | 2021-03-17 | Connected |  | Yes
National Grid | MENDON | 203356 | 1756 | 2600 | Solar | 05_321W6 | 2018-12-13 14:30 | 2018-12-14 | 69 | 50 | 19 | [10 empty] | 2019-02-21 | 2019-03-26 | 24 | 6 | 18 | [10 empty] | 2020-12-28 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | OXFORD | 198666 | 1540 | 6 | Solar | 01_406L4 | 2018-12-13 15:12 | 2018-12-14 | 6 | 0 | 6 | 2018-12-26 | 2019-01-07 | 7 | 0 | 7 | [20 empty] | 2019-01-08 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NANTUCKET | 202585 | 2554 | 25 | Solar | 04_101L8 | 2018-12-13 17:05 | 2018-12-14 | 5 | 1 | 4 | 2018-12-24 | 2019-02-04 | 27 | 14 | 13 | [20 empty] | 2019-02-04 |  |  |  | EXP | [8 empty] | 2019-10-07 | Connected |  | No
National Grid | WARE | 191403 | 1082 | 2200 | Solar | 09_501L2 | 2018-12-14 | 2019-01-10 | 13 | 5 | 8 | [10 empty] | 2019-01-31 | 2019-02-25 | 0 | 0 | 0 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | HARDWICK | 191405 | 1082 | 3300 | Solar | 09_501L2 | 2018-12-14 | 2019-01-10 | 13 | 5 | 8 | [10 empty] | 2019-01-31 | 2019-02-26 | 0 | 0 | 0 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | WILBRAHAM | 203478 | 1095 | 10 | Solar | 09_507L1 | 2018-12-17 15:32 | 2018-12-18 | 8 | 0 | 8 | 2019-01-02 | 2019-01-09 | 5 | 0 | 5 | [20 empty] | 2019-02-19 | 2018-12-17 15:49 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTHAMPTON | 203430 | 1062 | 2340 | Battery Add-On | 09_909W4 | 2018-12-17 15:49 | 2018-12-18 | 22 | 14 | 8 | [10 empty] | 2019-01-22 | 2019-02-18 | 18 | 0 | 18 | [10 empty] | 2019-11-26 |  | 2020-12-31 | Yes | STD |  | 2020-05-08 | 2020-10-21 | 167 | 5 | 162 |  |  | 2020-12-23 | Connected |  | No
National Grid | LENOX | 204149 | 1240 | 250 | Solar | 09_1103W1 | 2018-12-18 | 2018-12-28 | 6 | 0 | 6 | 2019-01-09 | 2019-02-07 | 20 | 1 | 19 | [20 empty] | 2019-02-20 | 2018-12-18 10:41 | 2020-02-20 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | TOPSFIELD | 203602 | 1983 | 10 | Solar | 12_26L1 | 2018-12-18 10:41 | 2018-12-19 | 7 | 0 | 7 | 2019-01-02 | 2020-01-29 | 242 | 19 | 223 | [20 empty] | 2019-02-20 |  | 2020-03-03 | Yes | EXP | [8 empty] | 2020-01-09 | Connected |  | No
National Grid | MANCHESTER | 203910 | 1944 | 10 | Solar | 12_28L2 | 2018-12-18 16:50 | 2018-12-19 | 7 | 0 | 7 | 2019-01-02 | 2019-01-09 | 5 | 0 | 5 | [20 empty] | 2019-01-16 |  |  |  | EXP | [8 empty] | 2019-04-09 | Connected |  | No
National Grid | WORCESTER | 204126 | 1607 | 313.2 | Solar | 01_8W2 | 2018-12-18 17:18 | 2018-12-19 | 21 | 17 | 4 | 2019-01-23 | 2019-02-27 | 24 | 8 | 16 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | AUBURN | 204134 | 1501 | 333 | Solar | 01_26W2 | 2018-12-18 17:20 | 2018-12-19 | 14 | 12 | 2 | 2019-01-11 | 2019-02-08 | 19 | 0 | 19 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTH OXFORD | 204158 | 1537 | 306.4 | Solar | 01_406L1 | 2018-12-18 17:22 | 2018-12-19 | 14 | 12 | 2 | 2019-01-11 | 2019-02-12 | 21 | 2 | 19 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 204159 | 2302 | 213.2 | Solar | 07_712J1 | 2018-12-18 17:25 | 2018-12-19 | 23 | 16 | 7 | 2019-01-25 | 2019-02-27 | 22 | 3 | 19 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | WEYMOUTH | 204176 | 2189 | 99.9 | Solar | 07_12W4 | 2018-12-18 17:28 | 2018-12-19 | 14 | 9 | 5 | 2019-01-10 | 2019-01-11 | 1 | 0 | 1 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 204161 | 1606 | 426.4 | Solar | 01_24W2 | 2018-12-18 17:33 | 2018-12-19 | 22 | 17 | 5 | 2019-01-23 | 2019-02-12 | 15 | 2 | 13 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | BILLERICA | 204163 | 1862 | 453 | Solar | 14_70L4 | 2018-12-18 17:36 | 2018-12-19 | 14 | 12 | 2 | 2019-01-11 | 2019-02-04 | 15 | 3 | 12 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 204168 | 2301 | 173.2 | Solar | 07_911W25 | 2018-12-18 17:38 | 2018-12-19 | 14 | 12 | 2 | 2019-01-11 | 2019-02-21 | 27 | 2 | 25 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | LYNN | 204170 | 1905 | 139.9 | Solar | 12_21J29 | 2018-12-18 17:42 | 2018-12-19 | 13 | 8 | 5 | 2019-01-10 | 2019-02-07 | 19 | 0 | 19 | 2019-03-11 | 2019-03-21 | 8 | 0 | 8 | [5 empty] | 2019-03-11 | 2019-03-21 | 8 | 0 | 8 | [9 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | SAUGUS | 204173 | 1906 | 259.8 | Solar | 12_25W3 | 2018-12-18 17:44 | 2018-12-19 | 19 | 12 | 7 | 2019-01-18 | 2019-02-22 | 23 | 5 | 18 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | REVERE | 203133 | 2151 | 7.6 | Solar | 12_7W2 | 2018-12-19 08:27 | 2018-12-20 | 6 | 0 | 6 | 2019-01-02 | 2019-01-09 | 5 | 0 | 5 | [20 empty] | 2019-02-22 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | DRACUT | 203291 | 1826 | 3.8 | Solar | 14_75L1 | 2018-12-19 08:39 | 2018-12-20 | 1 | 0 | 1 | 2018-12-24 | 2019-02-05 | 28 | 0 | 28 | [20 empty] | 2019-01-17 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 203334 | 2302 | 3.8 | Solar | 07_69J1 | 2018-12-19 08:57 | 2018-12-20 | 1 | 0 | 1 | 2018-12-24 | 2020-03-26 | 314 | 0 | 314 | [20 empty] | 2019-01-18 |  | 2020-12-19 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SOUTH ATTLEBORO | 202263 | 2703 | 7.6 | Solar | 05_9L3 | 2018-12-19 12:50 | 2018-12-20 | 8 | 1 | 7 | 2019-01-28 | 2019-10-15 | 146 | 0 | 146 | [20 empty] | 2019-01-30 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ANDOVER | 203934 | 1810 | 10 | Battery Add-On | 14_50L1 | 2018-12-19 14:18 | 2018-12-20 | 6 | 0 | 6 | 2019-01-02 | 2019-01-08 | 4 | 0 | 4 | [20 empty] | 2019-02-05 | 2018-12-20 18:40 | 2019-11-07 |  | EXP | [8 empty] | 2019-06-11 | Connected |  | No
National Grid | GLOUCESTER | 204210 | 1930 | 32.6 | Solar | 12_51T1 | 2018-12-20 18:40 | 2018-12-21 | 7 | 0 | 7 | 2019-01-04 | 2019-01-10 | 4 | 0 | 4 | [20 empty] | 2019-01-16 |  | 2020-01-03 | Yes | EXP |  | 2019-08-23 | 2019-12-18 | 117 | 0 | 117 |  |  | 2020-07-31 | Connected |  | No
National Grid | WORCESTER | 202543 | 1606 | 249.9 | Solar | 01_24W4 | 2018-12-21 | 2019-01-03 | 5 | 0 | 5 | 2019-01-11 | 2019-02-08 | 19 | 0 | 19 | [21 empty] | 2018-12-21 08:02 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | AMESBURY | 203345 | 1913 | 13.8 | Solar | 14_5J13 | 2018-12-21 08:02 | 2018-12-24 | 22 | 22 | 0 | 2019-01-25 | 2019-01-29 | 1 | 0 | 1 | [20 empty] | 2019-01-29 |  | 2020-03-26 | Yes | EXP |  | 2019-10-18 | 2020-02-21 | 126 | 0 | 126 |  |  | 2020-02-25 | Connected |  | No
National Grid | NEWBURYPORT | 198970 | 1950 | 7.6 | Solar | 14_47L2 | 2018-12-21 17:36 | 2018-12-24 | 0 | 0 | 0 | [26 empty] | 2018-12-26 13:19 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEST BRIDGEWATER | 204400 | 2379 | 480 | Solar | 07_92W54 | 2018-12-26 13:19 | 2018-12-27 | 14 | 5 | 9 | 2019-01-18 | 2019-02-15 | 19 | 2 | 17 | 2019-04-09 | 2019-04-29 | 14 | 0 | 14 | [5 empty] | 2019-04-09 | 2019-04-29 | 14 | 0 | 14 | [5 empty] | 2019-05-09 |  | 2021-02-19 | Yes | EXP |  | 2020-12-22 | 2020-12-21 | 0 | 0 | 0 |  |  | 2021-02-17 | Connected |  | No
National Grid | MENDON | 204286 | 1756 | 60 | Solar | 05_321W6 | 2018-12-27 | 2019-01-07 | 14 | 13 | 1 | 2019-01-11 | 2019-02-08 | 19 | 0 | 19 | [20 empty] | 2019-02-20 |  |  |  | EXP | [8 empty] | 2019-07-31 | Connected |  | Yes
National Grid | MENDON | 204309 | 1756 | 240 | Solar | 05_321W6 | 2018-12-27 | 2019-01-03 | 2 | 0 | 2 | 2019-01-08 | 2019-01-11 | 3 | 0 | 3 | 2019-01-23 | 2019-04-29 | 67 | 0 | 67 | [5 empty] | 2019-01-23 | 2019-04-29 | 67 | 0 | 67 | [5 empty] | 2019-05-02 |  | 2020-01-21 |  | EXP | [8 empty] | 2020-01-23 | Connected |  | No
National Grid | WINTHROP | 204747 | 2152 | 168 | Solar | 12_22J7 | 2018-12-27 | 2018-12-28 | 0 | 0 | 0 | 2018-12-31 | 2019-01-11 | 8 | 0 | 8 | [20 empty] | 2019-01-14 |  | 2020-06-30 |  | EXP | [8 empty] | 2020-03-30 | Connected |  | No
National Grid | GLOUCESTER | 203625 | 1930 | 3.8 | Solar | 12_28L2 | 2018-12-27 10:17 | 2018-12-28 | 4 | 0 | 4 | 2019-01-07 | 2019-10-23 | 155 | 0 | 155 | [20 empty] | 2019-03-11 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | FRANKLIN | 204783 | 2038 | 10 | Solar | 05_344W5 | 2018-12-27 12:37 | 2018-12-28 | 4 | 0 | 4 | 2019-01-04 | 2020-02-06 | 274 | 269 | 5 | [20 empty] | 2020-02-12 | 2018-12-27 14:19 | 2020-12-27 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 204748 | 2302 | 1380 | Solar | 07_91W46 | 2018-12-27 14:19 | 2018-12-28 | 13 | 5 | 8 | [10 empty] | 2019-01-17 | 2019-02-28 | 29 | 11 | 18 | [10 empty] | 2020-09-14 |  | 2024-04-29 | Yes | STD | [9 empty] | Construction |  | No
National Grid | NORTON | 204801 | 2766 | 20 | Solar | 05_8L3 | 2018-12-27 14:29 | 2018-12-28 | 8 | 3 | 5 | 2019-01-11 | 2019-01-21 | 6 | 4 | 2 | [20 empty] | 2019-02-05 |  |  |  | EXP | [8 empty] | 2019-03-28 | Connected |  | No
National Grid | CHELMSFORD | 203428 | 1824 | 3.8 | Solar | 14_16L4 | 2018-12-27 14:57 | 2018-12-28 | 19 | 19 | 0 | 2019-01-28 | 2019-10-09 | 143 | 0 | 143 | [20 empty] | 2019-01-29 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | REVERE | 203538 | 2151 | 3.8 | Solar | 12_16W8 | 2018-12-27 15:07 | 2018-12-28 | 19 | 19 | 0 | 2019-01-28 | 2019-10-09 | 143 | 0 | 143 | [20 empty] | 2019-01-29 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTPORT | 204363 | 2790 | 10 | Solar | 05_115W45 | 2018-12-27 15:36 | 2018-12-28 | 4 | 0 | 4 | 2019-01-07 | 2019-01-11 | 4 | 0 | 4 | [20 empty] | 2019-03-11 |  | 2019-11-07 |  | EXP | [8 empty] | 2019-06-11 | Connected |  | No
National Grid | BROCKTON | 204836 | 2302 | 300 | Solar | 07_98W44 | 2018-12-27 17:07 | 2018-12-28 | 9 | 5 | 4 | 2019-01-11 | 2019-02-27 | 31 | 16 | 15 | [20 empty] | 2019-06-06 |  | 2023-09-03 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FRANKLIN | 202003 | 2038 | 7490 | Solar | 05_348W7 | 2018-12-28 10:01 | 2018-12-31 | 166 | 26 | 140 | [10 empty] | 2019-08-27 | 2019-10-14 | 33 | 16 | 17 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 204844 | 2302 | 180 | Solar | 07_91W47 | 2018-12-28 11:21 | 2018-12-31 | 7 | 4 | 3 | 2019-01-10 | 2019-02-11 | 22 | 2 | 20 | [20 empty] | 2019-03-01 |  | 2020-03-08 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTON | 204908 | 2766 | 16.4 | Solar | 05_8L2 | 2018-12-28 16:47 | 2018-12-31 | 31 | 28 | 3 | 2019-02-14 | 2019-02-19 | 2 | 0 | 2 | [20 empty] | 2019-02-20 |  |  |  | EXP | [8 empty] | 2019-03-12 | Connected |  | No
National Grid | PEPPERELL | 204874 | 1463 | 7.6 | Solar | 01_226L2 | 2018-12-31 08:55 | 2019-01-02 | 17 | 17 | 0 | 2019-01-28 | 2019-01-28 | 0 | 0 | 0 | [20 empty] | 2019-01-28 |  | 2019-12-30 |  | EXP | [8 empty] | 2019-12-02 | Connected |  | No
National Grid | REVERE | 204942 | 2151 | 3.8 | Solar | 12_7W2 | 2018-12-31 10:48 | 2019-01-02 | 17 | 17 | 0 | 2019-01-28 | 2019-10-09 | 142 | 0 | 142 | [20 empty] | 2019-01-29 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | DUDLEY | 203677 | 1571 | 9.57 | Solar | 01_412L5 | 2018-12-31 14:22 | 2019-01-02 | 7 | 1 | 6 | 2019-01-18 | 2019-01-21 | 1 | 0 | 1 | [20 empty] | 2019-02-13 | 2019-01-01 13:09 |  |  | EXP | [8 empty] | 2019-10-18 | Connected |  | No
National Grid | BEVERLY | 203722 | 1915 | 10 | Solar | 12_12L2 | 2019-01-01 13:09 | 2019-01-02 | 6 | 0 | 6 | 2019-01-11 | 2019-02-12 | 22 | 2 | 20 | [20 empty] | 2019-02-19 |  |  | Yes | EXP |  | 2019-05-15 | 2019-05-14 | 0 | 0 | 0 |  |  | 2019-06-06 | Connected |  | No
National Grid | SOUTH ATTLEBORO | 205070 | 2703 | 10 | Solar | 05_9L6 | 2019-01-03 12:27 | 2019-01-04 | 5 | 0 | 5 | 2019-01-14 | 2019-02-12 | 21 | 13 | 8 | [20 empty] | 2019-03-05 |  |  |  | EXP | [8 empty] | 2019-05-03 | Connected |  | No
National Grid | RANDOLPH | 203646 | 2368 | 5 | Solar | 07_5W3 | 2019-01-03 12:31 | 2019-01-04 | 0 | 0 | 0 | 2019-01-07 | 2019-09-25 | 136 | 0 | 136 | [20 empty] | 2019-01-18 | 2019-01-03 12:40 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTH GRAFTON | 205004 | 1536 | 10 | Solar | 01_328W3 | 2019-01-03 12:40 | 2019-01-04 | 7 | 0 | 7 | 2019-01-16 | 2019-01-23 | 4 | 0 | 4 | [20 empty] | 2019-03-11 | 2019-01-03 12:51 | 2020-12-18 | Yes | EXP |  | 2020-01-07 | 2020-02-28 | 52 | 0 | 52 |  |  | 2020-11-16 | Connected |  | No
National Grid | SOUTHFIELD | 204820 | 1259 | 10 | Solar | 09_1109W1 | 2019-01-03 12:51 | 2019-01-04 | 5 | 0 | 5 | 2019-01-14 | 2019-02-05 | 16 | 16 | 0 | [20 empty] | 2019-03-11 |  | 2020-05-12 | Yes | EXP |  | 2020-03-13 | 2020-03-27 | 14 | 0 | 14 |  |  | 2020-04-20 | Connected |  | No
National Grid | MENDON | 204297 | 1756 | 108 | Solar | 05_321W6 | 2019-01-04 | 2019-01-07 | 3 | 0 | 3 | 2019-01-11 | 2019-02-06 | 17 | 3 | 14 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | LYNN | 205221 | 1901 | 33.3 | Solar | 12_1391 | 2019-01-04 10:35 | 2019-01-07 | 1 | 1 | 0 | 2019-01-08 | 2019-01-11 | 4 | 2 | 2 | [20 empty] | 2019-02-25 |  | 2021-01-25 |  | EXP | [8 empty] | 2021-09-17 | Connected |  | No
National Grid | FRANKLIN | 199270 | 2038 | 250 | Solar | 05_344W2 | 2019-01-04 11:59 | 2019-01-07 | 1 | 0 | 1 | 2019-01-09 | 2019-02-06 | 19 | 0 | 19 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | SOUTHBRIDGE | 184817 | 1550 | 478 | Solar | 01_413L1 | 2019-01-04 13:42 | 2019-01-07 | 1 | 0 | 1 | [10 empty] | 2019-01-09 | 2019-03-25 | 52 | 27 | 25 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WARE | 191399 | 1082 | 996 | Solar | 09_501L2 | 2019-01-04 16:32 | 2019-01-07 | 16 | 8 | 8 | [10 empty] | 2019-01-30 | 2019-02-21 | 0 | 0 | 0 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | METHUEN | 205269 | 1844 | 1500 | Solar | 14_74L1 | 2019-01-04 17:46 | 2019-01-07 | 24 | 15 | 9 | [10 empty] | 2019-02-11 | 2019-03-06 | 16 | 0 | 16 | [10 empty] | 2020-08-11 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NANTUCKET | 203329 | 2554 | 10 | Solar | 04_101L5 | 2019-01-04 21:09 | 2019-01-07 | 6 | 0 | 6 | 2019-01-16 | 2019-02-20 | 23 | 10 | 13 | [20 empty] | 2019-02-19 | 2019-01-07 07:25 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LYNN | 204587 | 1904 | 3.8 | Solar | 12_29W1 | 2019-01-07 07:25 | 2019-01-08 | 8 | 0 | 8 | 2019-01-22 | 2019-01-25 | 3 | 0 | 3 | [20 empty] | 2019-03-11 | 2019-01-07 12:01 | 2021-09-16 | Yes | EXP | [8 empty] | 2021-01-06 | Connected |  | No
National Grid | LEOMINSTER | 205332 | 1453 | 9.6 | Solar | 01_207W2 | 2019-01-07 12:01 | 2019-01-22 | 10 | 1 | 9 | 2019-02-06 | 2020-04-20 | 301 | 0 | 301 | [20 empty] | 2019-02-19 |  | 2020-07-22 | Yes | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HAMILTON | 205162 | 1982 | 5 | Solar | 12_51T2 | 2019-01-07 14:48 | 2019-01-08 | 7 | 0 | 7 | 2019-01-18 | 2019-01-24 | 3 | 0 | 3 | [20 empty] | 2019-02-05 |  | 2020-07-22 |  | EXP | [8 empty] | 2020-07-23 | Connected |  | No
National Grid | NORTHAMPTON | 204335 | 1060 | 233.1 | Solar | 09_905W1 | 2019-01-07 15:01 | 2019-01-08 | 8 | 2 | 6 | 2019-01-22 | 2019-05-01 | 70 | 48 | 22 | 2019-05-22 | 2019-08-27 | 68 | 7 | 61 | [5 empty] | 2019-05-22 | 2019-08-27 | 68 | 7 | 61 | [5 empty] | 2019-09-12 |  | 2020-08-03 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WEYMOUTH | 205175 | 2190 | 10 | Solar | 07_99W32 | 2019-01-07 17:12 | 2019-01-08 | 7 | 0 | 7 | 2019-01-22 | 2019-03-08 | 33 | 25 | 8 | [20 empty] | 2019-03-19 |  |  |  | EXP | [8 empty] | 2019-04-30 | Connected |  | No
National Grid | BROOKFIELD | 205262 | 1506 | 7.6 | Solar | 01_552L3 | 2019-01-07 17:36 | 2019-01-08 | 7 | 0 | 7 | 2019-01-18 | 2019-01-24 | 3 | 0 | 3 | [20 empty] | 2019-03-01 |  |  |  | EXP | [8 empty] | 2019-07-24 | Connected |  | No
National Grid | WARE | 191401 | 1082 | 3300 | Solar | 09_501L2 | 2019-01-09 12:48 | 2019-01-15 | 9 | 1 | 8 | [10 empty] | 2019-01-29 | 2019-02-20 | 15 | 0 | 15 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | SPENCER | 193213 | 1562 | 4400 | Solar | 01_552L1 | 2019-01-09 12:58 | 2019-01-10 | 13 | 5 | 8 | [10 empty] | 2019-01-31 | 2019-02-27 | 0 | 0 | 0 | [11 empty] | 2019-01-09 15:54 |  |  | STD | [9 empty] | Group Study |  | No
National Grid | AMESBURY | 202349 | 1913 | 7.6 | Solar | 14_275L2 | 2019-01-09 15:54 | 2019-01-10 | 6 | 0 | 6 | 2019-01-22 | 2019-01-25 | 3 | 0 | 3 | [20 empty] | 2019-03-11 |  | 2020-09-16 | Yes | EXP |  | 2020-04-17 | 2020-05-12 | 25 | 0 | 25 |  |  | 2020-07-25 | Connected |  | No
National Grid | NORTHBOROUGH | 205688 | 1532 | 250 | Solar | 05_313W2 | 2019-01-10 | 2019-01-14 | 2 | 0 | 2 | 2019-01-17 | 2019-02-14 | 19 | 0 | 19 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | FALL RIVER | 203924 | 2723 | 10 | Solar | 05_106W82 | 2019-01-10 16:15 | 2019-01-11 | 7 | 0 | 7 | 2019-01-24 | 2019-10-15 | 148 | 0 | 148 | [20 empty] | 2019-03-11 | 2019-01-10 16:56 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOUTHBRIDGE | 204532 | 1550 | 7.6 | Solar | 01_413L2 | 2019-01-10 16:56 | 2019-01-11 | 7 | 0 | 7 | 2019-01-24 | 2019-01-25 | 1 | 0 | 1 | [20 empty] | 2019-03-06 |  | 2020-08-19 | Yes | EXP |  | 2020-06-24 | 2020-06-30 | 6 | 0 | 6 |  |  | 2020-07-30 | Connected |  | No
National Grid | FALL RIVER | 203810 | 2720 | 250 | Solar | 05_28W41 | 2019-01-11 | 2018-12-21 | 7 | 4 | 3 | 2019-01-03 | 2019-01-10 | 5 | 0 | 5 | 2019-02-12 | 2019-03-07 | 16 | 0 | 16 | [5 empty] | 2019-02-12 | 2019-03-07 | 16 | 0 | 16 | [5 empty] | 2019-03-19 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | QUINCY | 204113 | 2169 | 86.6 | Solar | 07_3W3 | 2019-01-11 12:41 | 2019-01-14 | 11 | 6 | 5 | 2019-01-30 | 2019-03-04 | 22 | 5 | 17 | [20 empty] | 2019-03-19 | 2019-01-11 13:11 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | STURBRIDGE | 204724 | 1566 | 7.6 | Solar | 01_413L7 | 2019-01-11 13:11 | 2019-01-14 | 19 | 10 | 9 | 2019-02-12 | 2019-02-15 | 3 | 0 | 3 | [20 empty] | 2019-02-28 |  |  | Yes | EXP |  | 2019-04-18 | 2019-05-28 | 40 | 0 | 40 |  |  | 2019-06-29 | Connected |  | No
National Grid | NEW SALEM | 203390 | 1355 | 1000 | Solar | 09_702W3 | 2019-01-11 13:24 | 2019-01-14 | 8 | 0 | 8 | [10 empty] | 2019-01-28 | 2019-02-25 | 19 | 6 | 13 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTMINSTER | 201267 | 1473 | 996 | Solar | 01_602W3 | 2019-01-11 14:18 | 2019-01-14 | 20 | 13 | 7 | [10 empty] | 2019-02-12 | 2019-03-18 | 24 | 18 | 6 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | WARREN | 196531 | 1010 | 3 | Solar | 09_516L3 | 2019-01-14 09:45 | 2019-01-15 | 180 | 26 | 154 | [26 empty] | 2019-01-14 11:45 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LOWELL | 204310 | 1851 | 2649 | Natural Gas | 14_319 | 2019-01-14 11:45 | 2019-01-15 | 24 | 16 | 8 | [10 empty] | 2019-02-20 | 2020-02-10 | 245 | 221 | 24 | [10 empty] | 2020-08-31 |  | 2022-07-20 | Yes | STD |  | 2021-04-23 | 2021-10-12 | 62 | 0 | 62 |  |  | 2022-05-03 | Connected |  | No
National Grid | PALMER | 205907 | 1069 | 10 | Solar | 09_523L2 | 2019-01-14 13:54 | 2019-06-18 |  |  |  | 2019-06-18 | 2019-07-16 | 20 | 18 | 2 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | REHOBOTH | 205992 | 2769 | 7.6 | Solar | 05_8L4 | 2019-01-15 08:45 | 2019-01-16 | 9 | 0 | 9 | 2019-01-31 | 2019-10-15 | 178 | 0 | 178 | [20 empty] | 2019-03-11 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 202001 | 1507 | 1000 | Solar | 01_415L2 | 2019-01-15 10:26 | 2019-01-16 | 27 | 19 | 8 | [10 empty] | 2019-02-26 | 2019-06-27 | 87 | 72 | 15 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SAUGUS | 194460 | 1906 | 720 | Solar |  | 2019-01-15 10:49 | 2019-01-16 | 0 | 0 | 0 | [29 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SAUGUS | 194458 | 1906 | 720 | Solar | 12_23W1 | 2019-01-15 10:52 | 2019-01-16 | 28 | 20 | 8 | [10 empty] | 2019-02-27 | 2019-03-25 | 18 | 0 | 18 | [11 empty] | 2019-01-15 14:04 | 2021-09-27 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORWELL | 203231 | 2061 | 10 | Solar | 07_96W43 | 2019-01-15 14:04 | 2019-01-16 | 9 | 0 | 9 | 2019-01-31 | 2019-02-06 | 4 | 0 | 4 | [20 empty] | 2019-02-26 |  |  | Yes | EXP | [8 empty] | 2019-10-01 | Connected |  | No
National Grid | WESTFORD | 206199 | 1886 | 72 | Solar | 14_57L4 | 2019-01-16 | 2019-01-18 | 8 | 3 | 5 | 2019-02-01 | 2019-03-11 | 26 | 14 | 12 | [20 empty] | 2019-03-19 |  |  |  | EXP | [8 empty] | 2019-11-15 | Connected |  | No
National Grid | SWANSEA | 197466 | 2777 | 480 | Solar | 05_11W84 | 2019-01-16 08:47 | 2019-01-17 | 12 | 4 | 8 | 2019-02-05 | 2019-03-21 | 23 | 11 | 12 | 2019-04-10 | 2019-05-07 | 19 | 0 | 19 | [5 empty] | 2019-04-10 | 2019-05-07 | 19 | 0 | 19 | [7 empty] | 2020-05-04 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LEOMINSTER | 204026 | 1453 | 500 | Solar | 01_225W3 | 2019-01-16 14:50 | 2019-01-17 | 15 | 7 | 8 | [10 empty] | 2019-02-08 | 2019-02-27 | 12 | 5 | 7 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 204947 | 1844 | 3.8 | Solar | 14_63L2 | 2019-01-16 15:38 | 2019-01-17 | 9 | 8 | 1 | 2019-01-31 | 2019-02-04 | 2 | 0 | 2 | [20 empty] | 2019-02-05 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BRIDGEWATER | 203795 | 2324 | 7.6 | Solar | 07_912W55 | 2019-01-16 16:49 | 2019-01-17 | 8 | 0 | 8 | 2019-01-31 | 2019-02-04 | 2 | 0 | 2 | [20 empty] | 2019-03-06 | 2019-01-16 17:12 |  |  | EXP | [8 empty] | 2019-06-13 | Connected |  | No
National Grid | GRAFTON | 199009 | 1519 | 10 | Solar | 01_304W1 | 2019-01-16 17:12 | 2019-01-17 | 8 | 0 | 8 | 2019-01-31 | 2019-02-05 | 3 | 0 | 3 | [20 empty] | 2019-02-13 |  |  | Yes | EXP |  | 2019-06-22 | 2019-06-21 | 0 | 0 | 0 |  |  | 2019-07-25 | Connected |  | No
National Grid | MARLBOROUGH | 205105 | 1752 | 5 | Solar | 05_311W5 | 2019-01-17 14:59 | 2019-01-18 | 8 | 8 | 0 | 2019-01-31 | 2019-09-06 | 152 | 0 | 152 | [20 empty] | 2019-02-05 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEOMINSTER | 204484 | 1453 | 10 | Solar | 01_225W4 | 2019-01-17 17:05 | 2019-01-18 | 9 | 0 | 9 | 2019-02-04 | 2019-04-12 | 19 | 0 | 19 | [20 empty] | 2019-03-05 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTH GRAFTON | 204685 | 1536 | 10 | Solar | 01_304W1 | 2019-01-17 18:26 | 2019-01-18 | 9 | 0 | 9 | 2019-02-04 | 2019-02-05 | 1 | 0 | 1 | [20 empty] | 2019-03-11 | 2019-01-21 11:24 | 2019-11-07 |  | EXP | [8 empty] | 2019-07-02 | Connected |  | No
National Grid | RANDOLPH | 202819 | 2368 | 7.6 | Solar | 07_97W1 | 2019-01-21 11:24 | 2019-01-22 | 7 | 7 | 0 | 2019-01-31 | 2019-02-07 | 5 | 0 | 5 | [20 empty] | 2019-02-07 | 2019-01-22 08:18 | 2020-03-26 | Yes | EXP |  | 2019-11-07 | 2020-01-10 | 64 | 0 | 64 |  |  | 2020-01-21 | Connected |  | No
National Grid | LAWRENCE | 205028 | 1843 | 7.6 | Solar | 14_61L3 | 2019-01-22 08:18 | 2019-01-23 | 10 | 0 | 10 | 2019-02-07 | 2019-02-07 | 0 | 0 | 0 | [20 empty] | 2019-03-01 | 2019-01-22 14:50 | 2020-10-21 | Yes | EXP |  | 2020-04-25 | 2020-05-26 | 31 | 0 | 31 |  |  | 2020-06-18 | Connected |  | No
National Grid | BROCKTON | 206424 | 2302 | 5.76 | Solar | 07_911W57 | 2019-01-22 14:50 | 2019-01-23 | 10 | 0 | 10 | 2019-02-07 | 2019-02-11 | 2 | 0 | 2 | [20 empty] | 2019-02-19 |  |  | Yes | EXP |  | 2019-06-26 | 2019-06-25 | 0 | 0 | 0 |  |  | 2019-07-04 | Connected |  | No
National Grid | LAWRENCE | 206881 | 1843 | 278 | Solar | 14_2326 | 2019-01-23 | 2019-01-29 | 29 | 23 | 6 | 2019-03-12 | 2019-03-25 | 9 | 4 | 5 | [20 empty] | 2019-04-10 |  | 2020-06-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | FALL RIVER | 206944 | 2721 | 420 | Solar | 05_115W53 | 2019-01-24 | 2019-01-28 | 8 | 6 | 2 | 2019-02-08 | 2019-02-14 | 4 | 0 | 4 | [20 empty] | 2019-02-25 |  | 2020-06-30 |  | EXP | [8 empty] | 2020-06-05 | Connected |  | No
National Grid | REVERE | 203604 | 2151 | 3.8 | Solar | 12_16W4 | 2019-01-24 11:08 | 2019-01-25 | 4 | 4 | 0 | 2019-01-31 | 2020-02-13 | 228 | 0 | 228 | [20 empty] | 2019-02-05 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 205248 | 1844 | 10 | Solar | 14_63L2 | 2019-01-25 15:37 | 2019-01-28 | 32 | 26 | 6 | 2019-03-15 | 2019-03-21 | 4 | 0 | 4 | [20 empty] | 2019-03-21 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MELROSE | 206824 | 2176 | 10 | Solar | 12_25W4 | 2019-01-25 16:14 | 2019-01-28 | 10 | 0 | 10 | 2019-02-12 | 2019-02-15 | 3 | 0 | 3 | [20 empty] | 2019-03-11 |  | 2019-11-07 |  | EXP | [8 empty] | 2019-05-14 | Connected |  | No
National Grid | ANDOVER | 206827 | 1810 | 10 | Solar | 14_54L3 | 2019-01-25 16:49 | 2019-01-28 | 10 | 0 | 10 | 2019-07-30 | 2020-07-27 | 249 | 121 | 128 | [21 empty] | 2019-01-28 | 2020-10-14 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | TYNGSBOROUGH | 207367 | 1879 | 72 | Solar | 14_211L1 | 2019-01-28 | 2019-02-14 | 7 | 2 | 5 | 2019-02-27 | 2019-04-10 | 30 | 21 | 9 | 2019-04-22 | 2019-08-08 | 77 | 9 | 68 | [5 empty] | 2019-04-22 | 2019-08-08 | 77 | 9 | 68 | [5 empty] | 2019-08-29 | 2019-01-28 10:33 | 2021-12-28 |  | EXP |  | 2021-12-10 | 2021-12-09 | 0 | 0 | 0 |  |  | 2021-12-23 | Connected |  | No
National Grid | UPTON | 207296 | 1568 | 15.2 | Solar | 05_312W4 | 2019-01-28 10:33 | 2019-01-29 | 9 | 0 | 9 | 2019-02-12 | 2019-02-19 | 4 | 0 | 4 | [20 empty] | 2019-03-12 |  | 2020-09-23 | Yes | EXP | [9 empty] | Withdrawn |  | No
National Grid | STOUGHTON | 207438 | 2072 | 3.8 | Solar | 07_913W67 | 2019-01-29 08:05 | 2019-01-30 | 9 | 0 | 9 | 2019-02-13 | 2019-02-20 | 4 | 0 | 4 | [20 empty] | 2019-03-12 | 2019-01-29 10:25 |  |  | EXP | [8 empty] | 2019-11-18 | Connected |  | No
National Grid | RANDOLPH | 205636 | 2368 | 13.8 | Solar | 07_97W1 | 2019-01-29 10:25 | 2019-01-30 | 0 | 0 | 0 | 2019-01-31 | 2019-02-04 | 4 | 2 | 2 | [20 empty] | 2019-02-05 |  | 2020-10-23 | Yes | EXP |  | 2019-11-07 | 2020-01-16 | 70 | 0 | 70 |  |  | 2020-10-05 | Connected |  | No
National Grid | NORTHBOROUGH | 207452 | 1532 | 10 | Solar | 05_313W1 | 2019-01-29 10:25 | 2019-01-30 | 9 | 0 | 9 | 2019-02-13 | 2019-03-08 | 16 | 13 | 3 | [20 empty] | 2019-03-19 |  |  |  | EXP | [8 empty] | 2019-07-19 | Connected |  | No
National Grid | LOWELL | 207472 | 1854 | 73.3 | Solar | 14_2L4 | 2019-01-29 13:12 | 2019-01-30 | 1 | 0 | 1 | 2019-02-01 | 2019-03-20 | 32 | 13 | 19 | [20 empty] | 2019-03-22 |  |  |  | EXP | [8 empty] | 2019-11-12 | Connected |  | No
National Grid | SHEFFIELD | 206961 | 1257 | 250 | Solar | 09_1108W1 | 2019-01-29 14:53 | 2019-01-30 | 17 | 12 | 5 | 2019-02-25 | 2019-03-25 | 20 | 6 | 14 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | SHEFFIELD | 206967 | 1257 | 250 | Solar | 09_1108W1 | 2019-01-29 14:55 | 2019-01-30 | 22 | 17 | 5 | 2019-03-05 | 2019-03-25 | 14 | 2 | 12 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 207134 | 1606 | 240 | Solar | 01_24W2 | 2019-01-30 | 2019-01-31 | 8 | 2 | 6 | 2019-02-12 | 2019-04-09 | 39 | 20 | 19 | 2019-08-07 | 2019-09-04 | 19 | 1 | 18 | [5 empty] | 2019-08-07 | 2019-09-04 | 19 | 1 | 18 | [9 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | LEOMINSTER | 204913 | 1453 | 3.8 | Solar | 01_207W2 | 2019-01-30 10:45 | 2019-01-31 | 8 | 0 | 8 | 2019-02-13 | 2019-02-19 | 3 | 0 | 3 | [20 empty] | 2019-03-11 | 2019-01-30 12:02 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | EAST LONGMEADOW | 207492 | 1028 | 6 | Solar | 09_508L1 | 2019-01-30 12:02 | 2019-01-31 | 3 | 3 | 0 | 2019-02-05 | 2019-02-05 | 0 | 0 | 0 | [20 empty] | 2019-02-06 | 2019-01-30 12:09 | 2019-08-30 | Yes | EXP |  | 2019-06-01 | 2019-07-02 | 31 | 0 | 31 |  |  | 2019-08-12 | Connected |  | No
National Grid | DUDLEY | 207488 | 1571 | 10 | Solar | 01_412L5 | 2019-01-30 12:09 | 2019-01-31 | 3 | 3 | 0 | 2019-02-05 | 2019-02-05 | 0 | 0 | 0 | [20 empty] | 2019-02-06 |  | 2019-11-25 | Yes | EXP |  | 2019-05-25 | 2019-07-12 | 48 | 0 | 48 |  |  | 2019-09-10 | Connected |  | No
National Grid | SOUTH ATTLEBORO | 203529 | 2703 | 3.8 | Solar | 05_9L6 | 2019-01-30 13:49 | 2019-01-31 | 8 | 0 | 8 | 2019-02-13 | 2019-02-19 | 3 | 0 | 3 | [20 empty] | 2019-03-12 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 207061 | 1609 | 15.2 | Solar | 01_23W2 | 2019-01-30 15:09 | 2019-02-01 | 7 | 0 | 7 | 2019-02-13 | 2019-02-20 | 4 | 0 | 4 | [20 empty] | 2019-02-28 | 2019-01-31 11:07 |  |  | EXP | [8 empty] | 2019-05-14 | Connected |  | No
National Grid | MILLBURY | 207293 | 1527 | 10 | Solar | 01_304W3 | 2019-01-31 11:07 | 2019-02-01 | 6 | 6 | 0 | 2019-02-12 | 2019-02-19 | 4 | 0 | 4 | [20 empty] | 2019-02-21 | 2019-02-01 08:32 | 2019-10-17 | Yes | EXP |  | 2019-04-23 | 2019-05-30 | 37 | 0 | 37 |  |  | 2019-06-24 | Connected |  | No
National Grid | HANOVER | 207469 | 2339 | 10 | Solar | 07_910W51 | 2019-02-01 08:32 | 2019-02-04 | 4 | 4 | 0 | 2019-02-08 | 2019-02-21 | 9 | 3 | 6 | [20 empty] | 2019-02-22 |  | 2019-10-22 | Yes | EXP |  | 2019-05-11 | 2019-05-28 | 17 | 0 | 17 |  |  | 2019-06-11 | Connected |  | No
National Grid | SCITUATE | 206251 | 2066 | 5 | Solar | 07_915W36 | 2019-02-01 09:45 | 2019-02-04 | 6 | 0 | 6 | 2019-02-13 | 2019-02-19 | 3 | 0 | 3 | [20 empty] | 2019-02-28 |  | 2019-11-07 |  | EXP | [8 empty] | 2019-05-10 | Connected |  | No
National Grid | FLORENCE | 205909 | 1062 | 9.71 | Solar | 09_909W4 | 2019-02-01 13:42 | 2019-02-04 | 8 | 7 | 1 | 2019-02-14 | 2019-02-19 | 2 | 0 | 2 | [20 empty] | 2019-02-20 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SAUGUS | 207669 | 1906 | 10 | Solar | 12_16W1 | 2019-02-01 13:58 | 2019-02-21 | 2 | 1 | 1 | 2019-02-25 | 2019-02-27 | 2 | 0 | 2 | [20 empty] | 2019-03-04 |  | 2019-11-15 |  | EXP | [8 empty] | 2019-10-07 | Connected |  | No
National Grid | STOUGHTON | 199038 | 2072 | 72 | Solar | 07_913W69 | 2019-02-01 20:35 | 2019-02-04 | 28 | 20 | 8 | 2019-03-18 | 2019-04-23 | 26 | 14 | 12 | [20 empty] | 2019-04-29 | 2019-02-02 09:52 | 2020-07-31 |  | EXP | [8 empty] | 2020-07-30 | Connected |  | No
National Grid | NORTH EASTON | 208014 | 2356 | 15 | Solar | 07_92W78 | 2019-02-02 09:52 | 2019-02-04 | 6 | 0 | 6 | 2019-02-13 | 2019-02-15 | 2 | 0 | 2 | [20 empty] | 2019-03-11 |  | 2023-01-06 | Yes | EXP |  | 2022-04-16 | 2022-12-20 | 249 | 0 | 249 |  |  | 2023-01-05 | Connected |  | No
National Grid | LYNN | 205264 | 1904 | 7.6 | Solar | 12_29W1 | 2019-02-04 07:46 | 2019-02-05 | 3 | 3 | 0 | 2019-02-08 | 2019-02-15 | 5 | 0 | 5 | [20 empty] | 2019-02-19 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WRENTHAM | 208008 | 2093 | 7.6 | Solar | 05_3422W4 | 2019-02-04 10:20 | 2019-02-05 | 3 | 3 | 0 | 2019-02-08 | 2019-02-15 | 5 | 0 | 5 | [20 empty] | 2019-02-20 |  |  |  | EXP | [8 empty] | 2019-04-11 | Connected |  | No
National Grid | HARVARD | 206095 | 1451 | 10 | Solar | 01_201W2 | 2019-02-04 10:50 | 2019-02-05 | 2 | 2 | 0 | 2019-02-08 | 2019-02-27 | 12 | 8 | 4 | [20 empty] | 2019-03-01 |  | 2019-07-19 |  | EXP | [8 empty] | 2019-07-10 | Connected |  | No
National Grid | PEMBROKE | 207842 | 2359 | 7.6 | Solar | 07_910W52 | 2019-02-05 08:04 | 2019-02-06 | 5 | 0 | 5 | 2019-02-14 | 2019-02-19 | 2 | 0 | 2 | [20 empty] | 2019-03-06 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WEYMOUTH | 208280 | 2188 | 3.8 | Solar | 07_6W1 | 2019-02-05 08:46 | 2019-02-06 | 5 | 0 | 5 | 2019-02-14 | 2019-02-20 | 3 | 0 | 3 | [20 empty] | 2019-03-12 | 2019-02-05 13:45 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LYNN | 207594 | 1905 | 6 | Solar | 12_29W1 | 2019-02-05 13:45 | 2019-02-06 | 6 | 6 | 0 | 2019-02-14 | 2019-02-20 | 3 | 0 | 3 | [20 empty] | 2019-02-21 | 2019-02-06 10:35 | 2020-02-05 | Yes | EXP |  | 2019-09-25 | 2019-11-19 | 55 | 0 | 55 |  |  | 2019-12-03 | Connected |  | No
National Grid | MONSON | 204943 | 1057 | 7.6 | Solar | 09_503L2 | 2019-02-06 10:35 | 2019-02-07 | 6 | 0 | 6 | 2019-02-19 | 2019-02-21 | 2 | 0 | 2 | [20 empty] | 2019-03-12 |  | 2020-09-16 | Yes | EXP | [8 empty] | 2020-06-19 | Connected |  | No
National Grid | WESTMINSTER | 206349 | 1473 | 2340 | Solar | 01_602W2 | 2019-02-06 11:02 | 2019-02-07 | 140 | 26 | 114 | [29 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BEVERLY | 204469 | 1915 | 20 | Solar | 12_12L4 | 2019-02-06 11:56 | 2019-02-07 | 27 | 22 | 5 | 2019-03-19 | 2019-04-12 | 19 | 10 | 9 | [20 empty] | 2019-04-12 |  | 2019-09-30 |  | EXP | [8 empty] | 2019-11-15 | Connected |  | No
National Grid | METHUEN | 204929 | 1844 | 7.6 | Solar | 14_63L1 | 2019-02-06 13:49 | 2019-02-07 | 14 | 7 | 7 | 2019-03-01 | 2019-03-13 | 8 | 0 | 8 | [20 empty] | 2019-04-02 |  |  |  | EXP | [8 empty] | 2019-10-31 | Connected |  | No
National Grid | TOPSFIELD | 208665 | 1983 | 15 | Solar | 12_26L1 | 2019-02-06 16:57 | 2019-02-07 | 3 | 0 | 3 | 2019-02-13 | 2019-02-15 | 2 | 0 | 2 | [20 empty] | 2019-03-11 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | STOUGHTON | 207895 | 2072 | 480 | Solar | 07_913W69 | 2019-02-07 | 2019-02-11 | 10 | 1 | 9 | 2019-02-26 | 2019-05-07 | 51 | 29 | 22 | 2019-05-10 | 2019-06-25 | 32 | 3 | 29 | [5 empty] | 2019-05-10 | 2019-06-25 | 32 | 3 | 29 | [5 empty] | 2019-06-26 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | CLINTON | 208503 | 1510 | 86.6 | Solar | 01_216W2 | 2019-02-07 11:58 | 2019-02-12 | 24 | 17 | 7 | 2019-03-20 | 2019-07-30 | 93 | 88 | 5 | 2019-08-08 | 2020-08-25 | 264 | 182 | 82 | [5 empty] | 2019-08-08 | 2020-08-25 | 264 | 182 | 82 | [5 empty] | 2020-09-04 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | AUBURN | 205077 | 1501 | 7.6 | Solar | 01_26W1 | 2019-02-07 12:24 | 2019-02-08 | 16 | 16 | 0 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 205072 | 1844 | 5 | Solar | 14_63L1 | 2019-02-07 13:55 | 2019-02-08 | 0 | 0 | 0 | [26 empty] | 2019-02-07 14:58 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 202595 | 1843 | 7.6 | Solar | 14_1J9 | 2019-02-07 14:58 | 2019-02-08 | 4 | 4 | 0 | 2019-02-14 | 2019-02-19 | 2 | 0 | 2 | [20 empty] | 2019-02-21 |  | 2020-05-28 | Yes | EXP |  | 2020-01-16 | 2020-02-07 | 22 | 0 | 22 |  |  | 2020-02-11 | Connected |  | No
National Grid | SWANSEA | 207776 | 2777 | 60 | Solar | 05_11W85 | 2019-02-08 10:08 | 2019-02-11 | 9 | 4 | 5 | 2019-02-25 | 2019-03-04 | 5 | 0 | 5 | [20 empty] | 2019-03-19 | 2019-02-08 11:16 |  |  | EXP | [8 empty] | 2019-06-14 | Connected |  | No
National Grid | RUTLAND | 208913 | 1543 | 7.6 | Solar | 01_55W1 | 2019-02-08 11:16 | 2019-02-11 | 6 | 0 | 6 | 2019-02-21 | 2019-02-21 | 0 | 0 | 0 | [20 empty] | 2019-03-12 |  | 2020-07-22 | Yes | EXP |  | 2019-10-05 | 2019-12-02 | 58 | 0 | 58 |  |  | 2020-02-28 | Connected |  | No
National Grid | WILLIAMSTOWN | 208997 | 1267 | 57.64 | Solar | 09_1003W2 | 2019-02-08 15:56 | 2019-02-11 | 30 | 25 | 5 | 2019-03-26 | 2019-04-04 | 7 | 3 | 4 | [20 empty] | 2019-04-19 |  | 2022-02-27 |  | EXP | [8 empty] | 2021-10-14 | Connected |  | No
National Grid | WEBSTER | 206984 | 1570 | 3.8 | Solar | 01_412L2 | 2019-02-10 17:44 | 2019-02-11 | 5 | 0 | 5 | 2019-02-20 | 2019-02-20 | 0 | 0 | 0 | [20 empty] | 2019-03-12 |  |  |  | EXP | [8 empty] | 2019-11-13 | Connected |  | No
National Grid | NEWBURYPORT | 207035 | 1950 | 7.6 | Solar | 14_47L2 | 2019-02-10 18:41 | 2019-02-11 | 26 | 26 | 0 | 2019-03-21 | 2019-03-27 | 4 | 0 | 4 | [20 empty] | 2019-03-28 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 206222 | 1843 | 3.8 | Solar | 14_61L2 | 2019-02-11 11:25 | 2019-02-12 | 5 | 0 | 5 | 2019-02-21 | 2019-02-21 | 0 | 0 | 0 | [20 empty] | 2019-03-12 | 2019-02-11 12:12 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MILFORD | 207501 | 1757 | 7.6 | Solar | 05_336W3 | 2019-02-11 12:12 | 2019-02-12 | 5 | 0 | 5 | 2019-02-21 | 2019-02-21 | 0 | 0 | 0 | [20 empty] | 2019-03-12 |  | 2020-07-22 | Yes | EXP |  | 2019-11-01 | 2020-01-15 | 75 | 0 | 75 |  |  | 2020-04-22 | Connected |  | No
National Grid | CHARLTON | 209264 | 1507 | 17.28 | Solar | 01_406L3 | 2019-02-11 14:36 | 2019-02-12 | 49 | 49 | 0 | 2019-04-23 | 2020-04-08 | 242 | 241 | 1 | [20 empty] | 2020-04-09 | 2019-02-11 19:32 | 2021-01-08 |  | EXP | [8 empty] | 2020-12-08 | Connected |  | Yes
National Grid | MEDFORD | 206779 | 2155 | 7.6 | Solar | 12_37W5 | 2019-02-11 19:32 | 2019-02-12 | 3 | 3 | 0 | 2019-02-15 | 2019-02-19 | 1 | 0 | 1 | [20 empty] | 2019-02-21 |  | 2020-05-28 | Yes | EXP |  | 2020-03-25 | 2020-04-07 | 13 | 0 | 13 |  |  | 2020-05-14 | Connected |  | No
National Grid | WORCESTER | 209361 | 1606 | 72 | Solar | 01_24W2 | 2019-02-12 | 2019-04-04 | 4 | 0 | 4 | 2019-04-11 | 2019-04-25 | 10 | 0 | 10 | [20 empty] | 2019-05-17 | 2019-02-12 12:16 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WILBRAHAM | 203931 | 1095 | 10 | Solar | 09_514L1 | 2019-02-12 12:16 | 2019-02-13 | 3 | 3 | 0 | 2019-02-19 | 2019-02-20 | 1 | 0 | 1 | [20 empty] | 2019-02-21 |  | 2019-11-11 | Yes | EXP |  | 2019-08-24 | 2019-09-16 | 23 | 0 | 23 |  |  | 2019-10-09 | Connected |  | No
National Grid | PEMBROKE | 209527 | 2359 | 3.8 | Solar | 07_910W52 | 2019-02-12 14:52 | 2019-02-13 | 6 | 0 | 6 | 2019-02-25 | 2019-02-26 | 1 | 0 | 1 | [20 empty] | 2019-03-12 |  | 2020-07-23 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | AUBURN | 208525 | 1501 | 2340 | Solar | 01_26W1 | 2019-02-13 | 2019-02-14 | 176 | 51 | 125 | [26 empty] | 2019-02-13 10:09 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ATTLEBORO | 205771 | 2703 | 10 | Solar | 05_9L3 | 2019-02-13 10:09 | 2019-02-14 | 12 | 12 | 0 | 2019-03-06 | 2019-03-15 | 7 | 0 | 7 | [20 empty] | 2019-03-15 | 2019-02-13 12:52 | 2020-03-13 | Yes | EXP |  | 2019-11-15 | 2020-01-08 | 48 | 0 | 48 |  |  | 2020-01-17 | Connected |  | No
National Grid | TOPSFIELD | 208186 | 1983 | 10 | Solar | 12_26L1 | 2019-02-13 12:52 | 2019-02-14 | 3 | 3 | 0 | 2019-02-20 | 2019-03-07 | 12 | 8 | 4 | [20 empty] | 2019-03-08 |  | 2019-10-30 | Yes | EXP |  | 2019-06-28 | 2019-07-24 | 26 | 0 | 26 |  |  | 2019-07-27 | Connected |  | No
National Grid | WESTBOROUGH | 208290 | 1581 | 3 | Solar | 05_314W4 | 2019-02-13 12:52 | 2019-02-14 | 6 | 1 | 5 | 2019-02-26 | 2019-03-08 | 8 | 0 | 8 | [20 empty] | 2019-03-19 |  |  |  | EXP | [8 empty] | 2019-04-30 | Connected |  | No
National Grid | NORTON | 206720 | 2766 | 180 | Solar | 05_4L1 | 2019-02-13 14:03 | 2019-02-19 | 13 | 10 | 3 | 2019-03-08 | 2019-04-05 | 20 | 14 | 6 | 2019-04-11 | 2019-07-17 | 67 | 47 | 20 | [5 empty] | 2019-04-11 | 2019-07-17 | 67 | 47 | 20 | [5 empty] | 2019-07-29 |  | 2020-09-10 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LAWRENCE | 208645 | 1843 | 10 | Solar | 14_1J9 | 2019-02-13 18:55 | 2019-02-14 | 5 | 0 | 5 | 2019-02-25 | 2019-03-15 | 15 | 14 | 1 | [20 empty] | 2019-04-03 | 2019-02-14 10:22 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RANDOLPH | 208541 | 2368 | 10 | Solar | 07_97W1 | 2019-02-14 10:22 | 2019-02-15 | 4 | 4 | 0 | 2019-02-22 | 2019-02-22 | 0 | 0 | 0 | [20 empty] | 2019-02-27 | 2019-02-14 10:33 | 2019-09-30 | Yes | EXP |  | 2019-06-21 | 2019-08-09 | 49 | 0 | 49 |  |  | 2019-08-21 | Connected |  | No
National Grid | MALDEN | 207027 | 2148 | 7.6 | Solar | 12_16W7 | 2019-02-14 10:33 | 2019-02-19 | 3 | 3 | 0 | 2019-02-22 | 2019-02-22 | 0 | 0 | 0 | [20 empty] | 2019-02-27 | 2019-02-14 15:23 | 2019-10-11 | Yes | EXP |  | 2019-08-21 | 2019-08-29 | 8 | 0 | 8 |  |  | 2019-09-20 | Connected |  | No
National Grid | WEYMOUTH | 205952 | 2191 | 13.6 | Solar | 07_6W2 | 2019-02-14 15:23 | 2019-02-15 | 2 | 1 | 1 | 2019-02-21 | 2019-02-21 | 0 | 0 | 0 | [20 empty] | 2019-02-22 |  | 2019-09-30 | Yes | EXP |  | 2019-05-16 | 2019-06-06 | 21 | 0 | 21 |  |  | 2019-08-16 | Connected |  | No
National Grid | RUTLAND | 210006 | 1543 | 7.6 | Solar | 01_55W1 | 2019-02-15 08:40 | 2019-02-19 | 7 | 0 | 7 | 2019-03-01 | 2019-03-15 | 11 | 3 | 8 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | LYNN | 206834 | 1902 | 3.8 | Solar | 12_29W4 | 2019-02-15 09:04 | 2019-02-19 | 7 | 0 | 7 | 2019-03-01 | 2019-03-13 | 8 | 0 | 8 | [20 empty] | 2019-04-02 | 2019-02-15 10:09 |  |  | EXP | [8 empty] | 2019-11-01 | Connected |  | No
National Grid | BROCKTON | 210009 | 2302 | 6 | Solar | 07_911W56 | 2019-02-15 10:09 | 2019-03-11 | 8 | 0 | 8 | 2019-03-22 | 2019-03-27 | 3 | 0 | 3 | [20 empty] | 2019-04-01 |  |  | Yes | EXP |  | 2019-07-27 | 2019-08-13 | 17 | 0 | 17 |  |  | 2019-09-06 | Connected |  | No
National Grid | BARRE | 202897 | 1005 | 20 | Solar | 09_604W4 | 2019-02-18 | 2019-02-20 | 0 | 0 | 0 | 2019-02-21 | 2019-03-19 | 19 | 11 | 8 | [20 empty] | 2019-04-26 |  | 2020-02-24 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 208566 | 1844 | 3.8 | Solar | 14_74L1 | 2019-02-18 09:12 | 2019-02-19 | 7 | 0 | 7 | 2019-03-01 | 2019-03-12 | 7 | 0 | 7 | [20 empty] | 2019-03-19 | 2019-02-19 08:34 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | DUDLEY | 208138 | 1571 | 10 | Solar | 01_412L5 | 2019-02-19 08:34 | 2019-02-20 | 0 | 0 | 0 | 2019-02-20 | 2019-02-21 | 1 | 0 | 1 | [20 empty] | 2019-02-21 |  | 2019-11-05 | Yes | EXP |  | 2019-09-17 | 2019-09-18 | 1 | 0 | 1 |  |  | 2019-09-23 | Connected |  | No
National Grid | BROCKTON | 208398 | 2302 | 7.6 | Solar | 07_911W56 | 2019-02-19 14:28 | 2019-02-20 | 0 | 0 | 0 | 2019-02-21 | 2019-02-21 | 0 | 0 | 0 | [20 empty] | 2019-02-22 | 2019-02-19 20:36 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MILLBURY | 209039 | 1527 | 10 | Solar | 01_304W3 | 2019-02-19 20:36 | 2019-02-20 | 27 | 26 | 1 | 2019-04-01 | 2019-03-29 | 0 | 0 | 0 | [20 empty] | 2019-07-31 |  | 2021-05-17 |  | EXP |  | 2020-10-02 | 2020-12-08 | 67 | 0 | 67 |  |  | 2021-04-30 | Connected |  | No
National Grid | NORTHBOROUGH | 201086 | 1532 | 2460 | Solar | 05_313W3 | 2019-02-20 08:57 | 2019-02-21 | 226 | 26 | 200 | [10 empty] | 2020-01-21 | 2020-08-19 | 148 | 0 | 148 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 204022 | 1603 | 3.8 | Solar | 01_6W2 | 2019-02-21 07:48 | 2019-02-22 | 10 | 10 | 0 | 2019-03-08 | 2019-03-21 | 9 | 0 | 9 | [20 empty] | 2019-03-22 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | STURBRIDGE | 200645 | 1566 | 20 | Solar | 01_413L7 | 2019-02-21 09:46 | 2019-02-22 | 36 | 25 | 11 | 2019-04-15 | 2019-04-17 | 2 | 0 | 2 | [20 empty] | 2019-04-19 | 2019-02-21 10:52 |  |  | EXP | [8 empty] | 2019-09-12 | Connected |  | No
National Grid | WORCESTER | 209675 | 1604 | 7.6 | Solar | 01_27W5 | 2019-02-21 10:52 | 2019-02-22 | 0 | 0 | 0 | 2019-02-25 | 2019-02-27 | 2 | 0 | 2 | [20 empty] | 2019-03-01 |  | 2019-10-10 | Yes | EXP |  | 2019-05-30 | 2019-07-15 | 46 | 0 | 46 |  |  | 2019-08-27 | Connected |  | No
National Grid | SALEM | 203384 | 1970 | 10 | Solar | 12_2W1 | 2019-02-21 14:49 | 2019-02-22 | 0 | 0 | 0 | 2019-02-25 | 2019-03-06 | 7 | 0 | 7 | [20 empty] | 2019-03-08 | 2019-02-21 14:57 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 207111 | 1841 | 7.6 | Solar | 14_8L2 | 2019-02-21 14:57 | 2019-02-22 | 7 | 0 | 7 | 2019-03-06 | 2019-03-26 | 15 | 8 | 7 | [20 empty] | 2019-04-02 |  | 2020-07-22 | Yes | EXP |  | 2020-01-16 | 2020-02-28 | 43 | 0 | 43 |  |  | 2020-06-18 | Connected |  | No
National Grid | EAST BRIDGEWATER | 210891 | 2333 | 10 | Solar | 07_797W42 | 2019-02-21 17:05 | 2019-02-22 | 7 | 0 | 7 | 2019-03-06 | 2019-03-15 | 7 | 0 | 7 | [20 empty] | 2019-04-03 |  |  |  | EXP | [8 empty] | 2019-08-07 | Connected |  | No
National Grid | LEOMINSTER | 211055 | 1453 | 50 | Solar | 01_219W2 | 2019-02-22 | 2019-02-26 | 10 | 7 | 3 | 2019-03-12 | 2019-03-26 | 11 | 6 | 5 | [20 empty] | 2019-04-03 |  | 2020-06-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WINCHENDON | 205568 | 1475 | 984 | Solar | 01_612W1 | 2019-02-22 12:31 | 2019-02-25 | 21 | 14 | 7 | [10 empty] | 2019-03-26 | 2019-04-26 | 23 | 16 | 7 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WINCHENDON | 206008 | 1475 | 500 | Solar | 01_612W1 | 2019-02-22 13:09 | 2019-02-25 | 21 | 14 | 7 | [10 empty] | 2019-08-05 | 2019-08-02 | 75 | 75 | 0 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | MENDON | 209959 | 1756 | 1000 | Battery Add-On | 05_335W1 | 2019-02-25 11:24 | 2019-02-26 | 15 | 6 | 9 | [10 empty] | 2019-10-11 | 2020-05-04 | 139 | 125 | 14 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WHITINSVILLE | 208111 | 1588 | 3.8 | Solar | 05_320W5 | 2019-02-25 14:43 | 2019-02-26 | 6 | 0 | 6 | 2019-03-07 | 2019-03-15 | 6 | 0 | 6 | [20 empty] | 2019-04-03 | 2019-02-25 16:58 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BELLINGHAM | 200884 | 2019 | 500 | Solar | 05_344W4 | 2019-02-25 16:58 | 2019-02-26 | 15 | 9 | 6 | [10 empty] | 2019-03-19 | 2019-04-09 | 16 | 8 | 8 | [10 empty] | 2019-08-08 |  | 2021-04-07 | Yes | STD |  | 2020-09-30 | 2020-12-22 | 83 | 0 | 83 | 2021-03-30 | 2021-03-30 | 2021-04-07 | Connected |  | No
National Grid | BEVERLY | 189641 | 1915 | 5 | Solar | 12_51L3 | 2019-02-26 10:48 | 2019-02-27 | 5 | 0 | 5 | 2019-03-07 | 2019-03-18 | 8 | 2 | 6 | [20 empty] | 2019-04-03 | 2019-02-26 11:29 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SAUGUS | 210282 | 1906 | 5 | Solar | 12_23W2 | 2019-02-26 11:29 | 2019-02-27 | 5 | 5 | 0 | 2019-03-06 | 2019-03-15 | 7 | 0 | 7 | [20 empty] | 2019-03-18 |  | 2019-12-30 | Yes | EXP |  | 2019-10-03 | 2019-11-26 | 54 | 0 | 54 |  |  | 2019-12-06 | Connected |  | No
National Grid | STOUGHTON | 204378 | 2072 | 13.8 | Solar | 07_913W67 | 2019-02-26 22:38 | 2019-02-27 | 9 | 9 | 0 | 2019-03-13 | 2019-03-20 | 5 | 0 | 5 | [20 empty] | 2019-03-21 |  | 2019-12-13 |  | EXP | [8 empty] | 2019-11-26 | Connected |  | No
National Grid | NORTH BROOKFIELD | 211642 | 1535 | 4980 | Solar | 01_552L3 | 2019-02-27 17:15 | 2019-02-28 | 24 | 17 | 7 | [10 empty] | 2019-04-03 | 2019-04-24 | 15 | 0 | 15 | [11 empty] | 2019-02-27 19:07 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | FALL RIVER | 205831 | 2712 | 4.8 | Solar | 05_115W45 | 2019-02-27 19:07 | 2019-02-28 | 12 | 11 | 1 | 2019-03-18 | 2019-03-21 | 4 | 2 | 2 | [20 empty] | 2019-03-22 |  | 2019-11-13 | Yes | EXP |  | 2019-05-08 | 2019-06-06 | 29 | 0 | 29 |  |  | 2019-07-05 | Connected |  | No
National Grid | GRAFTON | 211835 | 1519 | 1760 | Solar | 01_304W1 | 2019-02-27 19:24 | 2019-02-28 | 25 | 17 | 8 | [10 empty] | 2019-04-05 | 2019-07-08 | 65 | 49 | 16 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | ANDOVER | 195724 | 1810 | 400 | Natural Gas | 14_8T1 | 2019-02-28 13:58 | 2019-03-01 | 302 | 26 | 276 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | SAUGUS | 209880 | 1906 | 7.6 | Solar | 12_13J3 | 2019-02-28 14:13 | 2019-03-01 | 6 | 0 | 6 | 2019-03-12 | 2019-04-25 | 33 | 25 | 8 | [20 empty] | 2019-04-30 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WEYMOUTH | 209081 | 2188 | 7.6 | Solar | 07_6W1 | 2019-03-01 12:48 | 2019-03-04 | 6 | 0 | 6 | 2019-03-13 | 2019-03-20 | 5 | 0 | 5 | [20 empty] | 2019-04-03 | 2019-03-01 14:22 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | AMESBURY | 208390 | 1913 | 7.6 | Solar | 14_275L2 | 2019-03-01 14:22 | 2019-03-04 | 0 | 0 | 0 | 2019-03-05 | 2019-03-15 | 8 | 0 | 8 | [20 empty] | 2019-03-18 | 2019-03-01 15:21 | 2020-09-01 | Yes | EXP |  | 2020-04-18 | 2020-05-06 | 18 | 0 | 18 |  |  | 2020-08-19 | Connected |  | No
National Grid | GREAT BARRINGTON | 210723 | 1230 | 10 | Solar | 09_1109W2 | 2019-03-01 15:21 | 2019-03-04 | 58 | 32 | 26 | 2019-05-23 | 2019-06-05 | 8 | 0 | 8 | [20 empty] | 2019-06-05 | 2019-03-04 14:47 | 2020-01-29 |  | EXP |  | 2019-09-13 | 2019-11-13 | 61 | 0 | 61 |  |  | 2019-12-05 | Connected |  | No
National Grid | ATTLEBORO | 210131 | 2703 | 13.8 | Solar | 05_8L3 | 2019-03-04 14:47 | 2019-03-05 | 5 | 0 | 5 | 2019-03-13 | 2019-03-20 | 5 | 0 | 5 | [20 empty] | 2019-03-29 |  |  | Yes | EXP | [8 empty] | 2019-09-24 | Connected |  | No
National Grid | LAWRENCE | 206502 | 1843 | 7.6 | Solar | 14_61L3 | 2019-03-04 15:06 | 2019-03-05 | 5 | 0 | 5 | 2019-03-13 | 2019-03-19 | 4 | 0 | 4 | [21 empty] | 2019-03-04 15:18 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | REVERE | 210788 | 2151 | 7.6 | Solar | 12_7J4 | 2019-03-04 15:18 | 2019-03-05 | 0 | 0 | 0 | 2019-03-06 | 2019-03-15 | 7 | 0 | 7 | [20 empty] | 2019-03-18 |  | 2020-07-21 | Yes | EXP |  | 2020-02-25 | 2020-03-19 | 23 | 0 | 23 |  |  | 2020-05-26 | Connected |  | No
National Grid | PLAINVILLE | 212066 | 2762 | 17.6 | Solar | 05_3422W3 | 2019-03-04 15:57 | 2019-03-05 | 7 | 7 | 0 | 2019-03-15 | 2019-03-27 | 9 | 2 | 7 | [20 empty] | 2019-03-28 | 2019-03-04 17:11 | 2020-04-30 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | UPTON | 207419 | 1568 | 25 | Solar | 05_335W3 | 2019-03-04 17:11 | 2019-03-05 | 0 | 0 | 0 | 2019-03-06 | 2019-03-19 | 10 | 3 | 7 | [20 empty] | 2019-03-20 |  | 2019-12-17 | Yes | EXP | [8 empty] | 2019-07-03 | Connected |  | No
National Grid | FALL RIVER | 212413 | 2724 | 233.3 | Solar | 05_106W42 | 2019-03-04 19:50 | 2019-03-05 | 8 | 4 | 4 | 2019-03-18 | 2019-03-27 | 7 | 3 | 4 | 2019-04-17 | 2019-05-07 | 14 | 0 | 14 | [5 empty] | 2019-04-17 | 2019-05-07 | 14 | 0 | 14 | [9 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH CHELMSFORD | 209967 | 1863 | 910 | Solar | 14_2L1 | 2019-03-04 22:21 | 2019-03-05 | 10 | 9 | 1 | [10 empty] | 2019-03-20 | 2019-08-22 | 101 | 35 | 66 | [11 empty] | 2019-03-05 11:44 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HARVARD | 212493 | 1451 | 10 | Solar | 01_216W6 | 2019-03-05 11:44 | 2019-03-06 | 4 | 0 | 4 | 2019-03-13 | 2019-03-20 | 5 | 0 | 5 | [20 empty] | 2019-04-03 |  | 2020-03-06 | Yes | EXP |  | 2019-09-05 | 2019-09-11 | 6 | 0 | 6 |  |  | 2020-02-04 | Connected |  | No
National Grid | METHUEN | 211661 | 1844 | 5 | Solar | 14_63L1 | 2019-03-05 13:12 | 2019-03-06 | 0 | 0 | 0 | 2019-03-07 | 2019-03-15 | 6 | 0 | 6 | [20 empty] | 2019-03-15 | 2019-03-06 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MILFORD | 212788 | 1757 | 109.9 | Solar | 05_335W3 | 2019-03-06 | 2019-03-07 | 4 | 1 | 3 | 2019-03-13 | 2019-03-21 | 6 | 0 | 6 | 2019-04-04 | 2019-08-27 | 102 | 62 | 40 | [5 empty] | 2019-04-04 | 2019-08-27 | 102 | 62 | 40 | [5 empty] | 2019-09-12 | 2019-03-06 07:00 | 2021-04-14 | Yes | EXP |  | 2020-02-12 | 2020-08-14 | 184 | 0 | 184 |  |  | 2021-04-14 | Connected |  | No
National Grid | NEWBURYPORT | 201008 | 1950 | 10 | Solar | 14_47L2 | 2019-03-06 07:00 | 2019-03-07 | 7 | 0 | 7 | 2019-03-19 | 2019-03-27 | 6 | 0 | 6 | [20 empty] | 2019-04-05 |  |  | Yes | EXP |  | 2019-09-06 | 2019-09-23 | 17 | 0 | 17 |  |  | 2019-10-25 | Connected |  | No
National Grid | SAUGUS | 210103 | 1906 | 57.6 | Solar | 12_19W1 | 2019-03-07 14:36 | 2019-03-08 | 2 | 0 | 2 | 2019-03-13 | 2019-03-21 | 6 | 0 | 6 | [20 empty] | 2019-04-02 |  | 2020-01-31 |  | EXP | [8 empty] | 2020-02-12 | Connected |  | No
National Grid | ANDOVER | 213038 | 1810 | 10 | Solar | 14_50L1 | 2019-03-08 07:57 | 2019-03-29 | 5 | 0 | 5 | 2019-04-08 | 2019-04-12 | 4 | 0 | 4 | [20 empty] | 2019-03-11 | 2019-03-08 09:44 |  |  | EXP | [8 empty] | 2019-08-06 | Connected |  | No
National Grid | FOXBOROUGH | 197444 | 2035 | 2085 | Natural Gas | 05_3424W3 | 2019-03-08 09:44 | 2019-03-11 | 20 | 12 | 8 | [10 empty] | 2019-04-08 | 2019-04-17 | 8 | 4 | 4 | [10 empty] | 2019-09-25 |  | 2019-12-31 | Yes | STD | [8 empty] | 2019-12-23 | Connected |  | No
National Grid | BOXFORD | 210231 | 1921 | 15.2 | Solar | 14_33L1 | 2019-03-08 11:54 | 2019-03-21 | 10 | 10 | 0 | 2019-04-04 | 2019-04-08 | 2 | 0 | 2 | [20 empty] | 2019-04-09 |  | 2019-07-26 |  | EXP | [8 empty] | 2019-06-25 | Connected |  | No
National Grid | BOXFORD | 213064 | 1921 | 17.6 | Solar | 14_56L3 | 2019-03-11 07:53 | 2019-03-12 | 7 | 0 | 7 | 2019-03-22 | 2019-03-27 | 3 | 0 | 3 | [20 empty] | 2019-04-05 |  |  |  | EXP | [8 empty] | 2019-05-03 | Connected |  | No
National Grid | ATTLEBORO | 209085 | 2703 | 3.8 | Solar | 05_8L4 | 2019-03-12 08:15 | 2019-03-13 | 6 | 0 | 6 | 2019-03-22 | 2019-03-27 | 3 | 0 | 3 | [20 empty] | 2019-04-05 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SALEM | 213359 | 1970 | 19 | Solar | 12_2W2 | 2019-03-12 08:29 | 2019-03-13 | 6 | 0 | 6 | 2019-03-22 | 2019-03-27 | 3 | 0 | 3 | [20 empty] | 2019-04-05 |  |  |  | EXP | [8 empty] | 2019-06-12 | Connected |  | No
National Grid | WORCESTER | 206472 | 1605 | 250 | Solar | 01_24W2 | 2019-03-12 14:06 | 2019-03-13 | 4 | 2 | 2 | 2019-03-19 | 2019-04-11 | 17 | 11 | 6 | 2019-05-31 | 2019-10-25 | 102 | 26 | 76 | [5 empty] | 2019-05-31 | 2019-10-25 | 102 | 26 | 76 | [6 empty] | 2019-03-12 14:29 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 206478 | 1602 | 250 | Solar | 01_23W3 | 2019-03-12 14:29 | 2019-03-13 | 1 | 1 | 0 | [10 empty] | 2019-03-15 | 2019-04-12 | 20 | 10 | 10 | [10 empty] | 2020-05-08 | 2019-03-12 16:03 | 2023-03-23 | Yes | STD |  | 2021-10-05 | 2022-08-19 | 319 | 4 | 315 |  |  | 2023-03-09 | Connected |  | No
National Grid | WALES | 211308 | 1081 | 15 | Solar | 09_503L2 | 2019-03-12 16:03 | 2019-03-13 | 2 | 1 | 1 | 2019-03-18 | 2019-03-21 | 3 | 0 | 3 | [20 empty] | 2019-03-22 |  | 2019-11-22 | Yes | EXP |  | 2019-08-06 | 2019-08-14 | 8 | 0 | 8 |  |  | 2019-08-21 | Connected |  | No
National Grid | SAUGUS | 213005 | 1906 | 60 | Solar | 12_19W1 | 2019-03-13 14:51 | 2019-03-14 | 3 | 1 | 2 | 2019-03-19 | 2019-03-21 | 2 | 0 | 2 | [20 empty] | 2019-04-02 | 2019-03-13 16:07 | 2020-01-31 |  | EXP | [8 empty] | 2020-01-27 | Connected |  | No
National Grid | WORCESTER | 206484 | 1604 | 480 | Solar | 01_27W1 | 2019-03-13 16:07 | 2019-03-14 | 32 | 25 | 7 | [10 empty] | 2019-04-29 | 2019-05-23 | 18 | 0 | 18 | [10 empty] | 2020-06-29 |  | 2023-06-30 | Yes | STD | [8 empty] | 2023-06-16 | Connected |  | No
National Grid | BROCKTON | 213914 | 2302 | 100 | Solar | 07_91W46 | 2019-03-14 | 2019-03-15 | 2 | 0 | 2 | 2019-03-20 | 2019-03-29 | 7 | 0 | 7 | 2019-04-05 | 2019-06-03 | 41 | 15 | 26 | [5 empty] | 2019-04-05 | 2019-06-03 | 41 | 15 | 26 | [9 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | UPTON | 213781 | 1568 | 17.6 | Solar | 05_335W3 | 2019-03-14 09:52 | 2019-03-15 | 4 | 0 | 4 | 2019-03-22 | 2019-10-11 | 143 | 140 | 3 | [20 empty] | 2019-10-22 |  | 2020-11-05 |  | EXP | [8 empty] | 2020-01-15 | Connected |  | No
National Grid | MEDFORD | 213815 | 2155 | 5 | Solar | 12_17J2 | 2019-03-14 11:46 | 2019-09-09 | 2 | 0 | 2 | 2019-09-12 | 2019-09-20 | 6 | 0 | 6 | [20 empty] | 2019-03-15 |  | 2020-03-16 |  | EXP | [8 empty] | 2020-02-19 | Connected |  | No
National Grid | BEVERLY | 210634 | 1915 | 9.92 | Solar | 12_18L2 | 2019-03-14 12:27 | 2019-03-15 | 0 | 0 | 0 | 2019-03-18 | 2019-04-11 | 18 | 15 | 3 | [20 empty] | 2019-04-12 |  | 2019-07-26 |  | EXP | [8 empty] | 2019-07-15 | Connected |  | No
National Grid | WEBSTER | 207611 | 1570 | 500 | Solar | 01_412L2 | 2019-03-14 12:31 | 2019-03-15 | 33 | 26 | 7 | [10 empty] | 2019-05-01 | 2019-06-03 | 23 | 5 | 18 | [11 empty] | 2019-03-14 12:33 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 210574 | 1604 | 10 | Solar | 01_27W5 | 2019-03-14 12:33 | 2019-03-15 | 0 | 0 | 0 | 2019-03-18 | 2019-03-20 | 2 | 0 | 2 | [20 empty] | 2019-03-21 |  | 2019-11-19 | Yes | EXP |  | 2019-05-21 | 2019-05-29 | 8 | 0 | 8 |  |  | 2019-06-19 | Connected |  | No
National Grid | WEST NEWBURY | 213962 | 1985 | 30 | Solar | 14_47L2 | 2019-03-15 09:56 | 2019-03-18 | 5 | 0 | 5 | 2019-03-26 | 2019-03-27 | 1 | 0 | 1 | [20 empty] | 2019-04-03 |  |  |  | EXP | [8 empty] | 2019-05-03 | Connected |  | No
National Grid | SALISBURY | 213965 | 1952 | 17.6 | Solar | 14_7L2 | 2019-03-15 10:03 | 2019-03-18 | 5 | 0 | 5 | 2019-03-26 | 2019-03-28 | 2 | 0 | 2 | [20 empty] | 2019-04-05 |  | 2019-11-07 |  | EXP | [8 empty] | 2019-07-22 | Connected |  | No
National Grid | NORTH QUINCY | 213972 | 2171 | 30 | Solar | 07_4J1 | 2019-03-15 10:45 | 2019-03-18 | 5 | 0 | 5 | 2019-03-26 | 2019-03-28 | 2 | 0 | 2 | [20 empty] | 2019-04-05 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTH GRAFTON | 213993 | 1536 | 7.6 | Solar | 01_304W1 | 2019-03-15 12:05 | 2019-03-18 | 5 | 0 | 5 | 2019-03-26 | 2019-03-27 | 1 | 0 | 1 | [20 empty] | 2019-04-03 | 2019-03-15 13:18 |  |  | EXP | [8 empty] | 2019-09-05 | Connected |  | No
National Grid | SALEM | 208985 | 1970 | 7.6 | Solar | 12_29W2 | 2019-03-15 13:18 | 2019-03-18 | 1 | 1 | 0 | 2019-03-19 | 2019-03-20 | 1 | 0 | 1 | [20 empty] | 2019-03-21 |  | 2020-02-21 | Yes | EXP |  | 2019-08-16 | 2019-10-02 | 47 | 0 | 47 |  |  | 2019-10-31 | Connected |  | No
National Grid | WARREN | 213652 | 1083 | 7.36 | Solar | 01_525L2 | 2019-03-15 18:33 | 2019-03-18 | 5 | 0 | 5 | 2019-03-26 | 2019-03-27 | 1 | 0 | 1 | [20 empty] | 2019-04-05 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | FALL RIVER | 210964 | 2721 | 7.6 | Solar | 05_115W53 | 2019-03-17 08:04 | 2019-03-18 | 1 | 1 | 0 | 2019-03-20 | 2019-08-28 | 113 | 25 | 88 | [21 empty] | 2019-03-18 18:10 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | RANDOLPH | 208421 | 2368 | 10 | Solar | 07_97W1 | 2019-03-18 18:10 | 2019-03-19 | 0 | 0 | 0 | 2019-03-20 | 2019-03-22 | 2 | 0 | 2 | [20 empty] | 2019-03-25 |  | 2020-09-02 | Yes | EXP |  | 2020-03-04 | 2020-05-12 | 69 | 0 | 69 |  |  | 2020-05-13 | Connected |  | No
National Grid | DRACUT | 211523 | 1826 | 23.4 | Solar | 14_75L3 | 2019-03-19 08:37 | 2019-03-20 | 5 | 3 | 2 | 2019-03-27 | 2019-03-28 | 1 | 0 | 1 | [20 empty] | 2019-03-29 |  | 2020-03-19 |  | EXP | [8 empty] | 2020-04-10 | Connected |  | No
National Grid | NEWBURYPORT | 210060 | 1950 | 7.6 | Solar | 14_36L2 | 2019-03-19 12:04 | 2019-03-20 | 142 | 26 | 116 | [26 empty] | 2019-03-19 12:12 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 209250 | 1609 | 9.92 | Solar | 01_23W2 | 2019-03-19 12:12 | 2019-03-20 | 6 | 0 | 6 | 2019-03-29 | 2019-04-29 | 22 | 19 | 3 | [20 empty] | 2019-05-07 |  | 2020-04-29 | Yes | EXP |  | 2020-02-22 | 2020-02-21 | 0 | 0 | 0 |  |  | 2020-04-21 | Connected |  | No
National Grid | THORNDIKE | 214399 | 1079 | 15.2 | Solar | 09_523L4 | 2019-03-19 12:44 | 2019-03-20 | 6 | 0 | 6 | 2019-03-29 | 2019-07-02 | 66 | 38 | 28 | [21 empty] | 2019-03-19 13:31 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 206485 | 1604 | 210 | Solar | 01_8J365 | 2019-03-19 13:31 | 2019-03-20 | 2 | 0 | 2 | [10 empty] | 2019-03-25 | 2019-04-30 | 26 | 21 | 5 | [10 empty] | 2020-08-11 |  | 2023-06-22 | Yes | STD | [8 empty] | 2023-06-20 | Connected |  | No
National Grid | PEPPERELL | 213711 | 1463 | 8.64 | Solar | 01_226L1 | 2019-03-19 14:12 | 2019-03-20 | 8 | 8 | 0 | 2019-04-01 | 2019-04-08 | 5 | 0 | 5 | [20 empty] | 2019-04-09 |  | 2019-05-30 |  | EXP | [8 empty] | 2019-05-10 | Connected |  | No
National Grid | WARE | 205168 | 1082 | 3500 | Solar | 09_501L2 | 2019-03-19 21:09 | 2019-03-20 | 25 | 17 | 8 | [10 empty] | 2019-04-24 | 2019-05-18 | 0 | 0 | 0 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | STURBRIDGE | 214422 | 1566 | 3.655 | Solar | 01_415L1 | 2019-03-20 11:53 | 2019-05-02 | 23 | 19 | 4 | 2019-06-06 | 2019-06-27 | 16 | 13 | 3 | [20 empty] | 2019-07-09 | 2019-03-20 12:28 | 2021-09-17 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LAWRENCE | 212730 | 1841 | 7.6 | Solar | 14_8L2 | 2019-03-20 12:28 | 2019-03-21 | 5 | 0 | 5 | 2019-03-29 | 2019-03-28 | 0 | 0 | 0 | [20 empty] | 2019-04-05 |  | 2020-06-17 | Yes | EXP |  | 2020-01-16 | 2020-02-07 | 22 | 0 | 22 |  |  | 2020-04-17 | Connected |  | No
National Grid | STOUGHTON | 212974 | 2072 | 6 | Solar | 07_913W43 | 2019-03-20 12:57 | 2019-03-21 | 5 | 0 | 5 | 2019-03-29 | 2019-04-24 | 19 | 19 | 0 | [20 empty] | 2019-04-26 | 2019-03-20 15:07 |  |  | EXP | [8 empty] | 2019-10-16 | Connected |  | No
National Grid | FALL RIVER | 209761 | 2724 | 7.04 | Solar | 05_115W42 | 2019-03-20 15:07 | 2019-03-21 | 5 | 0 | 5 | 2019-03-29 | 2019-04-05 | 5 | 0 | 5 | [20 empty] | 2019-04-12 |  |  | Yes | EXP | [8 empty] | 2019-10-03 | Connected |  | No
National Grid | WORCESTER | 206477 | 1607 | 360 | Solar | 01_8W1 | 2019-03-21 09:39 | 2019-03-22 | 8 | 7 | 1 | 2019-04-03 | 2019-05-22 | 35 | 21 | 14 | 2019-10-16 | 2020-01-23 | 67 | 50 | 17 | [5 empty] | 2019-10-16 | 2020-01-23 | 67 | 50 | 17 | [9 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 214779 | 2302 | 7.6 | Solar | 07_911W77 | 2019-03-21 11:41 | 2019-03-22 | 14 | 14 | 0 | 2019-04-11 | 2019-04-15 | 2 | 0 | 2 | [20 empty] | 2019-04-15 |  | 2020-04-14 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHARLTON | 213693 | 1507 | 30 | Solar | 01_415L1 | 2019-03-21 14:36 | 2019-03-22 | 43 | 40 | 3 | 2019-05-22 | 2020-06-17 | 267 | 73 | 194 | [21 empty] | 2019-03-21 16:46 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 209355 | 2302 | 12 | Solar | 07_911W56 | 2019-03-21 16:46 | 2019-03-22 | 21 | 21 | 0 | 2019-04-22 | 2019-04-24 | 2 | 0 | 2 | [20 empty] | 2019-04-24 |  | 2019-11-25 | Yes | EXP |  | 2019-09-22 | 2019-10-08 | 16 | 0 | 16 |  |  | 2019-10-29 | Connected |  | No
National Grid | STOUGHTON | 208597 | 2072 | 1000 | Solar | 07_913W17 | 2019-03-22 | 2019-03-27 | 20 | 11 | 9 | [10 empty] | 2019-04-24 | 2019-05-15 | 15 | 0 | 15 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | AYER | 208607 | 1432 | 500 | Solar | 01_201W1 | 2019-03-22 | 2019-03-26 | 21 | 12 | 9 | [10 empty] | 2019-04-24 | 2019-05-23 | 21 | 0 | 21 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BILLERICA | 214979 | 1821 | 3.8 | Solar | 14_92L2 | 2019-03-22 12:38 | 2019-03-25 | 86 | 86 | 0 | 2019-07-23 | 2019-08-02 | 8 | 0 | 8 | [20 empty] | 2019-08-05 | 2019-03-22 13:08 | 2019-11-29 |  | EXP | [8 empty] | 2019-11-13 | Connected |  | No
National Grid | SOUTH ATTLEBORO | 210655 | 2703 | 20 | Solar | 05_9L6 | 2019-03-22 13:08 | 2019-03-25 | 6 | 1 | 5 | 2019-04-03 | 2019-04-08 | 3 | 0 | 3 | [20 empty] | 2019-04-17 |  |  |  | EXP | [8 empty] | 2019-09-11 | Connected |  | No
National Grid | TOPSFIELD | 214988 | 1983 | 20.8 | Solar | 12_26L1 | 2019-03-22 13:18 | 2019-03-25 | 3 | 0 | 3 | 2019-03-29 | 2019-04-11 | 10 | 7 | 3 | [20 empty] | 2019-04-17 |  |  |  | EXP | [8 empty] | 2019-08-16 | Connected |  | No
National Grid | DRACUT | 214576 | 1826 | 3 | Solar | 14_78L1 | 2019-03-22 16:29 | 2019-03-25 | 4 | 0 | 4 | 2019-04-01 | 2019-09-26 | 125 | 25 | 100 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 212812 | 1844 | 7.6 | Solar | 14_8L2 | 2019-03-23 11:38 | 2019-03-25 | 0 | 0 | 0 | 2019-03-26 | 2019-03-28 | 2 | 0 | 2 | [20 empty] | 2019-03-28 |  | 2019-08-30 |  | EXP | [8 empty] | 2019-08-16 | Connected |  | No
National Grid | HAVERHILL | 208615 | 1830 | 500 | Solar | 14_65L1 | 2019-03-25 | 2019-03-26 | 21 | 12 | 9 | [10 empty] | 2019-04-30 | 2020-03-17 | 213 | 42 | 171 | [11 empty] | 2019-03-25 15:10 | 2020-11-10 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | REVERE | 214054 | 2151 | 10 | Solar | 12_16W7 | 2019-03-25 15:10 | 2019-03-26 | 15 | 14 | 1 | 2019-04-16 | 2019-04-18 | 2 | 0 | 2 | [20 empty] | 2019-04-19 |  | 2019-12-16 | Yes | EXP |  | 2019-06-27 | 2019-08-21 | 55 | 0 | 55 |  |  | 2019-08-24 | Connected |  | No
National Grid | WORCESTER | 206476 | 1607 | 120 | Solar | 01_8W1 | 2019-03-26 15:28 | 2019-05-22 |  |  |  | 2019-05-22 | 2019-06-10 | 13 | 3 | 10 | 2019-10-16 | 2020-01-23 | 67 | 50 | 17 | [5 empty] | 2019-10-16 | 2020-01-23 | 67 | 50 | 17 | [9 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | SPENCER | 208846 | 1562 | 6 | Solar | 01_552L1 | 2019-03-26 18:26 | 2019-03-27 | 69 | 26 | 43 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 208613 | 2301 | 972 | Solar | 07_94W41 | 2019-03-27 | 2019-03-28 | 17 | 10 | 7 | [10 empty] | 2019-04-22 | 2019-05-14 | 16 | 0 | 16 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 208621 | 1844 | 900 | Solar | 14_74L1 | 2019-03-27 | 2019-03-29 | 16 | 9 | 7 | [10 empty] | 2019-04-22 | 2019-05-17 | 20 | 4 | 16 | [11 empty] | 2019-03-28 | 2021-04-15 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 214604 | 1844 | 150 | Solar | 05_2285 | 2019-03-28 | 2019-04-02 | 12 | 6 | 6 | 2019-04-18 | 2019-06-04 | 33 | 7 | 26 | 2019-08-07 | 2019-10-18 | 51 | 13 | 38 | [5 empty] | 2019-08-07 | 2019-10-18 | 51 | 13 | 38 | [5 empty] | 2019-10-30 |  | 2022-03-28 | Yes | EXP |  | 2021-10-05 | 2022-03-17 | 164 | 4 | 160 |  |  | 2022-03-25 | Connected |  | No
National Grid | SCITUATE | 215949 | 2066 | 20 | Solar | 07_915W82 | 2019-03-29 13:12 | 2019-04-01 | 4 | 0 | 4 | 2019-04-08 | 2019-04-18 | 9 | 9 | 0 | [20 empty] | 2019-04-24 | 2019-04-01 11:11 | 2019-11-07 |  | EXP | [8 empty] | 2019-08-21 | Connected |  | No
National Grid | NORTH EGREMONT | 213059 | 1252 | 10 | Solar | 09_1109W3 | 2019-04-01 11:11 | 2019-04-02 | 2 | 2 | 0 | 2019-04-04 | 2019-04-08 | 2 | 0 | 2 | [20 empty] | 2019-04-09 | 2019-04-01 12:06 | 2019-11-05 | Yes | EXP |  | 2019-05-22 | 2019-06-25 | 34 | 0 | 34 |  |  | 2019-08-10 | Connected |  | No
National Grid | SOUTHFIELD | 214597 | 1259 | 10 | Solar | 09_1109W1 | 2019-04-01 12:06 | 2019-04-02 | 8 | 1 | 7 | 2019-04-15 | 2019-04-18 | 3 | 0 | 3 | [20 empty] | 2019-04-24 |  |  | Yes | EXP | [8 empty] | 2019-09-04 | Connected |  | No
National Grid | LAWRENCE | 215897 | 1843 | 400 | Solar | 14_1J5 | 2019-04-01 12:08 | 2019-04-02 | 19 | 7 | 12 | 2019-04-08 | 2019-04-25 | 13 | 0 | 13 | 2019-07-10 | 2019-07-09 | 0 | 0 | 0 | [5 empty] | 2019-07-10 | 2019-07-09 | 0 | 0 | 0 | [5 empty] | 2019-07-09 | 2019-04-01 15:11 | 2019-12-16 |  | EXP | [8 empty] | 2019-12-20 | Connected |  | No
National Grid | BELCHERTOWN | 216596 | 1007 | 15.2 | Solar | 09_509L1 | 2019-04-01 15:11 | 2019-04-02 | 5 | 0 | 5 | 2019-04-10 | 2019-05-02 | 17 | 15 | 2 | [20 empty] | 2019-05-08 |  |  | Yes | EXP |  | 2019-08-06 | 2019-08-19 | 13 | 0 | 13 |  |  | 2019-09-18 | Connected |  | No
National Grid | EAST BRIDGEWATER | 216476 | 2333 | 201.6 | Solar | 07_912W74 | 2019-04-01 16:59 | 2019-04-02 | 1 | 1 | 0 | 2019-04-03 | 2019-04-04 | 1 | 0 | 1 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EAST BRIDGEWATER | 216496 | 2333 | 201.6 | Solar | 07_912W74 | 2019-04-01 17:20 | 2019-04-02 | 1 | 1 | 0 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EAST BRIDGEWATER | 216492 | 2333 | 201.6 | Solar | 07_912W74 | 2019-04-01 17:30 | 2019-04-02 | 1 | 1 | 0 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NEWBURYPORT | 216789 | 1950 | 55 | Solar | 14_60L3 | 2019-04-02 | 2019-04-04 | 6 | 5 | 1 | 2019-04-12 | 2019-04-17 | 3 | 0 | 3 | 2019-05-23 | 2019-06-20 | 19 | 0 | 19 | [5 empty] | 2019-05-23 | 2019-06-20 | 19 | 0 | 19 | [5 empty] | 2019-07-12 |  | 2020-07-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BRIDGEWATER | 216694 | 2324 | 19 | Solar | 07_912W55 | 2019-04-02 08:09 | 2019-04-03 | 4 | 0 | 4 | 2019-04-10 | 2019-04-12 | 2 | 0 | 2 | [20 empty] | 2019-04-18 | 2019-04-02 09:53 | 2019-11-07 |  | EXP | [8 empty] | 2019-07-30 | Connected |  | No
National Grid | LAWRENCE | 213800 | 1843 | 6 | Solar | 14_61L3 | 2019-04-02 09:53 | 2019-04-03 | 6 | 6 | 0 | 2019-04-11 | 2019-04-15 | 2 | 0 | 2 | [20 empty] | 2019-04-16 |  | 2019-07-30 | Yes | EXP |  | 2019-07-09 | 2019-07-16 | 7 | 0 | 7 |  |  | 2019-07-18 | Connected |  | No
National Grid | SAUGUS | 214350 | 1906 | 3.8 | Solar | 12_7J903 | 2019-04-02 10:28 | 2019-04-03 | 4 | 0 | 4 | 2019-04-10 | 2019-04-12 | 2 | 0 | 2 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RANDOLPH | 215677 | 2368 | 10 | Solar | 07_5W1 | 2019-04-02 10:37 | 2019-04-03 | 4 | 0 | 4 | 2019-04-10 | 2019-04-12 | 2 | 0 | 2 | [20 empty] | 2019-04-18 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SALEM | 216823 | 1970 | 3.8 | Solar | 12_29W2 | 2019-04-02 11:34 | 2019-04-03 | 14 | 10 | 4 | 2019-04-24 | 2019-04-24 | 0 | 0 | 0 | [20 empty] | 2019-04-26 | 2019-04-02 11:45 |  |  | EXP | [8 empty] | 2019-11-21 | Connected |  | No
National Grid | HOLBROOK | 215628 | 2343 | 7.6 | Solar | 07_10W1 | 2019-04-02 11:45 | 2019-04-03 | 6 | 6 | 0 | 2019-04-11 | 2019-04-15 | 2 | 0 | 2 | [20 empty] | 2019-04-15 | 2019-04-02 12:00 | 2020-05-27 | Yes | EXP |  | 2020-01-30 | 2020-02-19 | 20 | 0 | 20 |  |  | 2020-03-24 | Connected |  | No
National Grid | LAWRENCE | 215537 | 1841 | 10 | Solar | 14_74L6 | 2019-04-02 12:00 | 2019-04-03 | 6 | 6 | 0 | 2019-04-11 | 2019-04-15 | 2 | 0 | 2 | [20 empty] | 2019-04-15 | 2019-04-02 12:04 | 2020-02-05 | Yes | EXP |  | 2019-11-06 | 2019-11-22 | 16 | 0 | 16 |  |  | 2019-11-26 | Connected |  | No
National Grid | SAUGUS | 215396 | 1906 | 5 | Solar | 12_16W3 | 2019-04-02 12:04 | 2019-04-03 | 4 | 0 | 4 | 2019-04-10 | 2019-04-12 | 2 | 0 | 2 | [20 empty] | 2019-04-18 |  | 2020-02-17 | Yes | EXP |  | 2020-01-30 | 2020-01-29 | 0 | 0 | 0 |  |  | 2020-02-19 | Connected |  | No
National Grid | MANCHESTER | 217096 | 1944 | 10 | Solar | 12_51T1 | 2019-04-03 09:46 | 2019-04-04 | 3 | 0 | 3 | 2019-04-10 | 2019-04-22 | 9 | 8 | 1 | [20 empty] | 2019-04-24 |  | 2019-11-07 |  | EXP | [8 empty] | 2019-08-19 | Connected |  | No
National Grid | THORNDIKE | 217150 | 1079 | 7.6 | Solar | 09_523L4 | 2019-04-03 11:36 | 2019-04-04 | 321 | 25 | 296 | [27 empty] | 2020-07-06 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTMINSTER | 217237 | 1473 | 10 | Solar | 01_609W1 | 2019-04-03 15:57 | 2019-04-04 | 0 | 0 | 0 | 2019-04-05 | 2019-04-15 | 7 | 6 | 1 | [20 empty] | 2019-04-15 |  | 2019-06-28 |  | EXP | [8 empty] | 2019-06-05 | Connected |  | No
National Grid | SOUTH GRAFTON | 216239 | 1560 | 3.8 | Solar | 05_320W3 | 2019-04-04 11:56 | 2019-04-05 | 5 | 0 | 5 | 2019-04-15 | 2019-04-16 | 1 | 0 | 1 | [20 empty] | 2019-04-22 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SEEKONK | 216590 | 2771 | 6 | Solar | 05_7L3 | 2019-04-04 13:55 | 2019-04-05 | 72 | 70 | 2 | 2019-07-12 | 2019-07-22 | 6 | 0 | 6 | [20 empty] | 2019-07-23 |  | 2019-11-25 |  | EXP | [8 empty] | 2019-10-10 | Connected |  | No
National Grid | PEPPERELL | 218005 | 1463 | 15.2 | Solar | 01_226L2 | 2019-04-05 17:14 | 2019-04-08 | 4 | 0 | 4 | 2019-04-15 | 2019-04-16 | 1 | 0 | 1 | [20 empty] | 2019-04-24 |  |  |  | EXP | [8 empty] | 2019-10-07 | Connected |  | No
National Grid | STOUGHTON | 213840 | 2072 | 250 | Solar | 07_913W69 | 2019-04-08 12:50 | 2019-04-09 | 6 | 0 | 6 | [10 empty] | 2019-04-18 | 2019-05-10 | 17 | 3 | 14 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SPENCER | 200549 | 1562 | 363.2 | Solar | 01_21W1 | 2019-04-09 | 2019-05-30 | 22 | 21 | 1 | 2019-07-01 | 2019-07-02 | 1 | 0 | 1 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NEWBURYPORT | 218135 | 1950 | 18.85 | Solar | 14_36L1 | 2019-04-09 09:10 | 2019-04-10 | 3 | 3 | 0 | 2019-04-15 | 2019-04-16 | 1 | 0 | 1 | [20 empty] | 2019-04-17 |  | 2019-08-20 |  | EXP | [8 empty] | 2019-08-15 | Connected |  | No
National Grid | GRANBY | 218290 | 1033 | 20 | Solar | 09_527L1 | 2019-04-09 09:10 | 2019-04-10 | 23 | 16 | 7 | 2019-05-14 | 2019-06-10 | 19 | 8 | 11 | [20 empty] | 2019-06-18 | 2019-04-09 15:34 | 2019-11-07 |  | EXP | [8 empty] | 2019-08-26 | Connected |  | No
National Grid | SAUGUS | 217215 | 1906 | 3 | Solar | 12_16W3 | 2019-04-09 15:34 | 2019-04-10 | 5 | 0 | 5 | 2019-04-18 | 2019-04-30 | 8 | 0 | 8 | [20 empty] | 2019-05-09 |  | 2020-04-02 | Yes | EXP |  | 2020-02-19 | 2020-02-26 | 7 | 0 | 7 |  |  | 2020-03-12 | Connected |  | No
National Grid | ROCKLAND | 218741 | 2370 | 7.6 | Solar | 07_99W61 | 2019-04-10 13:07 | 2019-04-11 | 7 | 0 | 7 | 2019-04-23 | 2019-04-24 | 1 | 0 | 1 | [20 empty] | 2019-04-30 |  | 2020-12-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WEST STOCKBRIDGE | 218174 | 1266 | 15.37 | Solar | 09_1109W3 | 2019-04-10 13:21 | 2019-04-11 | 2 | 2 | 0 | 2019-04-15 | 2019-04-16 | 1 | 0 | 1 | [20 empty] | 2019-04-17 | 2019-04-10 14:25 | 2019-07-30 |  | EXP | [8 empty] | 2019-06-24 | Connected |  | No
National Grid | BILLERICA | 213493 | 1821 | 10 | Solar | 14_92L2 | 2019-04-10 14:25 | 2019-04-11 | 48 | 47 | 1 | 2019-06-20 | 2019-06-24 | 2 | 0 | 2 | [20 empty] | 2019-06-25 | 2019-04-10 15:22 | 2020-07-31 | Yes | EXP |  | 2020-02-22 | 2020-06-03 | 102 | 0 | 102 |  |  | 2020-07-10 | Connected |  | No
National Grid | LOWELL | 217114 | 1850 | 10 | Solar | 14_75L5 | 2019-04-10 15:22 | 2019-04-11 | 11 | 11 | 0 | 2019-04-26 | 2019-04-29 | 1 | 0 | 1 | [20 empty] | 2019-04-30 |  | 2020-03-31 | Yes | EXP |  | 2019-09-27 | 2019-10-23 | 26 | 0 | 26 |  |  | 2019-10-28 | Connected |  | No
National Grid | EAST LONGMEADOW | 218868 | 1028 | 10 | Solar | 09_139L5 | 2019-04-11 09:12 | 2019-04-12 | 0 | 0 | 0 | 2019-04-12 | 2019-04-17 | 3 | 0 | 3 | [20 empty] | 2019-04-18 |  | 2019-08-12 |  | EXP | [8 empty] | 2019-07-31 | Connected |  | No
National Grid | WORCESTER | 219190 | 1603 | 3.8 | Solar | 01_6W2 | 2019-04-11 15:55 | 2019-06-20 | 4 | 0 | 4 | 2019-06-27 | 2019-07-10 | 8 | 0 | 8 | [20 empty] | 2019-07-18 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SAUGUS | 219604 | 1906 | 7.6 | Solar | 12_25W1 | 2019-04-12 14:31 | 2019-04-15 | 119 | 114 | 5 | 2019-10-03 | 2019-10-04 | 1 | 0 | 1 | [20 empty] | 2019-10-08 | 2019-04-12 14:51 | 2020-09-16 |  | EXP | [8 empty] | 2020-07-30 | Connected |  | No
National Grid | DRACUT | 212099 | 1826 | 10 | Solar | 14_75L3 | 2019-04-12 14:51 | 2019-04-15 | 30 | 30 | 0 | 2019-05-29 | 2019-06-07 | 7 | 0 | 7 | [20 empty] | 2019-06-07 |  | 2020-02-21 | Yes | EXP |  | 2019-12-19 | 2020-01-29 | 41 | 0 | 41 |  |  | 2020-01-31 | Connected |  | No
National Grid | NORWELL | 202209 | 2061 | 366.6 | Solar | 07_96W44 | 2019-04-12 18:12 | 2019-04-15 | 4 | 2 | 2 | 2019-04-19 | 2019-05-07 | 12 | 9 | 3 | 2019-06-14 | 2019-07-01 | 11 | 0 | 11 | [5 empty] | 2019-06-14 | 2019-07-01 | 11 | 0 | 11 | [5 empty] | 2019-07-26 |  | 2021-04-02 |  | EXP |  | 2020-10-13 | 2021-01-06 | 85 | 0 | 85 |  |  | 2021-02-24 | Connected |  | No
National Grid | PEPPERELL | 186572 | 1463 | 1590 | Solar | 01_226L1 | 2019-04-15 14:14 | 2019-04-16 | 36 | 29 | 7 | [10 empty] | 2019-06-06 | 2019-07-02 | 0 | 0 | 0 | [11 empty] | 2019-04-15 17:20 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTBOROUGH | 205806 | 1581 | 7.6 | Solar | 05_314W5 | 2019-04-15 17:20 | 2019-04-16 | 39 | 32 | 7 | 2019-06-13 | 2019-06-17 | 2 | 0 | 2 | [20 empty] | 2019-06-18 |  | 2020-03-06 | Yes | EXP | [8 empty] | 2019-11-21 | Connected |  | No
National Grid | EAST BRIDGEWATER | 206156 | 2333 | 3.8 | Solar | 07_797W42 | 2019-04-17 13:36 | 2019-04-18 | 42 | 40 | 2 | 2019-06-19 | 2019-06-20 | 1 | 0 | 1 | [20 empty] | 2019-06-28 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | FALL RIVER | 211048 | 2720 | 492 | Solar | 05_28W42 | 2019-04-17 14:06 | 2019-04-18 | 5 | 0 | 5 | 2019-04-26 | 2019-05-13 | 11 | 4 | 7 | [21 empty] | 2019-04-17 18:34 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 215214 | 1841 | 7.6 | Solar | 14_74L3 | 2019-04-17 18:34 | 2019-04-18 | 4 | 0 | 4 | 2019-04-25 | 2019-04-29 | 2 | 0 | 2 | [20 empty] | 2019-05-03 | 2019-04-18 15:08 | 2020-09-17 | Yes | EXP |  | 2020-03-04 | 2020-03-19 | 15 | 0 | 15 |  |  | 2020-07-10 | Connected |  | No
National Grid | SAUGUS | 218392 | 1906 | 5 | Solar | 12_16W3 | 2019-04-18 15:08 | 2019-04-19 | 6 | 5 | 1 | 2019-04-29 | 2019-05-07 | 6 | 0 | 6 | [20 empty] | 2019-05-08 |  | 2020-04-24 | Yes | EXP | [8 empty] | 2020-02-20 | Connected |  | No
National Grid | MARLBOROUGH | 219586 | 1752 | 800 | Solar | 05_311W4 | 2019-04-19 | 2019-08-12 | 0 | 0 | 0 | [10 empty] | 2019-08-12 | 2019-10-29 | 54 | 40 | 14 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | FALL RIVER | 220893 | 2723 | 489 | Solar | 05_106W82 | 2019-04-19 11:14 | 2019-04-22 | 1 | 0 | 1 | 2019-04-24 | 2019-05-08 | 10 | 0 | 10 | 2019-05-23 | 2019-06-11 | 12 | 0 | 12 | [5 empty] | 2019-05-23 | 2019-06-11 | 12 | 0 | 12 | [9 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | BILLERICA | 221173 | 1821 | 15.2 | Solar | 14_92L6 | 2019-04-19 11:52 | 2019-04-22 | 22 | 16 | 6 | [26 empty] | 2019-04-19 18:32 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LAWRENCE | 221314 | 1841 | 7.6 | Solar | 14_74L3 | 2019-04-19 18:32 | 2019-06-05 | 0 | 0 | 0 | 2019-06-06 | 2019-06-10 | 2 | 0 | 2 | [20 empty] | 2019-06-11 | 2019-04-22 07:46 | 2020-07-16 | Yes | EXP |  | 2020-03-04 | 2020-05-21 | 78 | 0 | 78 |  |  | 2020-06-05 | Connected |  | No
National Grid | LAWRENCE | 209338 | 1841 | 11.4 | Solar | 14_8L2 | 2019-04-22 07:46 | 2019-04-23 | 3 | 0 | 3 | 2019-04-29 | 2019-05-02 | 3 | 0 | 3 | [20 empty] | 2019-05-08 |  | 2020-07-22 | Yes | EXP |  | 2020-04-25 | 2020-06-12 | 48 | 0 | 48 |  |  | 2020-07-07 | Connected |  | No
National Grid | SOMERSET | 221739 | 2726 | 10 | Solar | 05_18J7 | 2019-04-23 10:49 | 2019-04-24 | 4 | 0 | 4 | 2019-05-01 | 2019-05-03 | 2 | 0 | 2 | [20 empty] | 2019-05-13 |  | 2019-11-07 |  | EXP | [8 empty] | 2019-07-22 | Connected |  | No
National Grid | MANCHESTER | 221773 | 1944 | 10 | Solar | 12_51T1 | 2019-04-23 12:33 | 2019-04-24 | 4 | 0 | 4 | 2019-05-01 | 2019-05-06 | 3 | 0 | 3 | [20 empty] | 2019-05-16 |  | 2019-11-07 |  | EXP | [8 empty] | 2019-06-28 | Connected |  | No
National Grid | MALDEN | 221781 | 2148 | 100 | Solar | 12_37W7 | 2019-04-23 12:52 | 2019-04-24 | 1 | 0 | 1 | 2019-04-26 | 2019-05-13 | 11 | 3 | 8 | 2019-06-25 | 2019-07-30 | 24 | 0 | 24 | [5 empty] | 2019-06-25 | 2019-07-30 | 24 | 0 | 24 | [5 empty] | 2019-08-02 |  | 2020-08-03 |  | EXP | [8 empty] | 2020-03-09 | Connected |  | No
National Grid | WESTBOROUGH | 209564 | 1581 | 700 | Solar | 05_312W1 | 2019-04-24 | 2019-05-07 | 26 | 18 | 8 | [10 empty] | 2019-06-12 | 2019-07-08 | 0 | 0 | 0 | [11 empty] | 2019-04-24 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | GRAFTON | 222039 | 1560 | 240 | Solar | 05_320W3 | 2019-04-24 | 2019-05-13 | 14 | 11 | 3 | [5 empty] | 2019-08-06 | 2019-08-28 | 17 | 1 | 16 | 2019-06-04 | 2019-06-24 | 14 | 4 | 10 | 2019-08-06 | 2019-08-28 | 17 | 1 | 16 | [5 empty] | 2020-04-27 |  | 2022-01-28 | Yes | STD | [6 empty] | 2021-12-03 | 2021-12-03 | 2022-01-24 | Connected |  | No
National Grid | BLACKSTONE | 215920 | 1504 | 4950 | Solar | 05_108W60 | 2019-04-24 07:50 | 2019-04-25 | 11 | 2 | 9 | [10 empty] | 2019-05-10 | 2019-06-01 | 14 | 0 | 14 | [10 empty] | 2020-01-24 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BLACKSTONE | 215927 | 1504 | 3960 | Solar | 05_108W60 | 2019-04-24 07:52 | 2019-04-25 | 10 | 2 | 8 | [10 empty] | 2019-05-10 | 2019-06-04 | 16 | 0 | 16 | [10 empty] | 2019-10-22 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | DIGHTON | 215929 | 2779 | 2970 | Solar | 05_19W74 | 2019-04-24 07:53 | 2019-04-25 | 11 | 3 | 8 | [10 empty] | 2019-05-10 | 2019-06-06 | 18 | 0 | 18 | [10 empty] | 2019-11-05 | 2019-04-24 09:13 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 220789 | 2302 | 6 | Solar | 07_911W56 | 2019-04-24 09:13 | 2019-04-25 | 4 | 4 | 0 | 2019-04-30 | 2019-05-01 | 1 | 0 | 1 | [20 empty] | 2019-05-02 |  | 2020-04-14 | Yes | EXP |  | 2019-10-02 | 2019-10-15 | 13 | 0 | 13 |  |  | 2019-10-22 | Connected |  | No
National Grid | LYNN | 220688 | 1904 | 3 | Solar | 12_29W3 | 2019-04-24 09:35 | 2019-04-25 | 4 | 4 | 0 | 2019-04-30 | 2019-05-01 | 1 | 0 | 1 | [20 empty] | 2019-05-02 | 2019-04-24 10:43 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | ROCKLAND | 221137 | 2370 | 10 | Solar | 07_95W4 | 2019-04-24 10:43 | 2019-04-25 | 7 | 0 | 7 | 2019-05-07 | 2019-05-24 | 13 | 0 | 13 | [20 empty] | 2019-06-05 | 2019-04-24 10:47 | 2020-06-09 | Yes | EXP |  | 2019-10-04 | 2019-10-14 | 10 | 0 | 10 |  |  | 2020-01-21 | Connected |  | No
National Grid | SAUGUS | 219650 | 1906 | 7.6 | Solar | 12_23W1 | 2019-04-24 10:47 | 2019-04-25 | 5 | 5 | 0 | 2019-05-02 | 2019-05-03 | 1 | 0 | 1 | [20 empty] | 2019-05-03 |  | 2020-06-11 | Yes | EXP |  | 2020-02-25 | 2020-03-10 | 14 | 0 | 14 |  |  | 2020-05-15 | Connected |  | Yes
National Grid | WRENTHAM | 217708 | 2093 | 25 | Solar | 05_3422W2 | 2019-04-24 11:50 | 2019-04-25 | 7 | 0 | 7 | 2019-05-07 | 2019-06-03 | 19 | 10 | 9 | [20 empty] | 2019-06-04 |  | 2020-05-06 |  | EXP | [8 empty] | 2019-12-09 | Connected |  | No
National Grid | WESTBOROUGH | 209566 | 1581 | 433.3 | Solar | 05_312W1 | 2019-04-24 15:24 | 2019-04-25 | 8 | 6 | 2 | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 2019-07-12 | 2019-08-19 | 26 | 0 | 26 | [5 empty] | 2019-07-12 | 2019-08-19 | 26 | 0 | 26 | [9 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTBOROUGH | 209562 | 1581 | 700 | Solar | 05_312W1 | 2019-04-25 | 2019-05-07 | 26 | 18 | 8 | [10 empty] | 2019-06-12 | 2019-07-08 | 0 | 0 | 0 | [11 empty] | 2019-04-25 16:31 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ALFORD | 222580 | 1230 | 20.4 | Solar | 09_1109W3 | 2019-04-25 16:31 | 2019-04-26 | 6 | 0 | 6 | 2019-05-07 | 2019-05-24 | 13 | 0 | 13 | [20 empty] | 2019-05-29 |  | 2020-03-10 | Yes | EXP |  | 2019-11-19 | 2019-11-18 | 0 | 0 | 0 |  |  | 2020-01-15 | Connected |  | No
National Grid | DUNSTABLE | 222601 | 1827 | 17.6 | Solar | 01_210L1 | 2019-04-25 18:25 | 2019-04-26 | 6 | 0 | 6 | 2019-05-07 | 2019-05-29 | 15 | 2 | 13 | [20 empty] | 2019-06-04 | 2019-04-25 21:44 | 2020-08-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTBOROUGH | 222595 | 1581 | 432 | Solar | 05_314W3 | 2019-04-25 21:44 | 2019-04-26 | 6 | 5 | 1 | [10 empty] | 2019-05-06 | 2019-05-23 | 13 | 0 | 13 | [10 empty] | 2019-12-20 |  | 2024-09-09 | Yes | STD | [9 empty] | Construction |  | No
National Grid | WESTBOROUGH | 222837 | 1581 | 144 | Solar | 05_312W5 | 2019-04-26 | 2019-05-15 | 22 | 15 | 7 | 2019-06-17 | 2019-06-24 | 5 | 0 | 5 | 2019-07-19 | 2019-09-19 | 44 | 26 | 18 | [5 empty] | 2019-07-19 | 2019-09-19 | 44 | 26 | 18 | [5 empty] | 2020-02-26 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 222991 | 1844 | 153.3 | Solar | 14_74L2 | 2019-04-26 17:14 | 2019-04-29 | 14 | 9 | 5 | 2019-05-17 | 2019-06-13 | 18 | 4 | 14 | 2019-08-13 | 2019-09-18 | 26 | 26 | 0 | [5 empty] | 2019-08-13 | 2019-09-18 | 26 | 26 | 0 | [7 empty] | 2021-09-27 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WEYMOUTH | 223125 | 2188 | 60 | Solar | 07_12W1 | 2019-04-27 09:42 | 2019-04-29 | 16 | 12 | 4 | 2019-05-22 | 2020-06-17 | 268 | 153 | 115 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | SALEM | 223128 | 1970 | 120 | Solar | 12_2W1 | 2019-04-27 10:31 | 2019-04-29 | 17 | 17 | 0 | 2019-05-22 | 2019-06-13 | 16 | 7 | 9 | [20 empty] | 2019-08-15 |  | 2021-08-13 |  | EXP | [8 empty] | 2021-08-19 | Connected |  | No
National Grid | BROCKTON | 223130 | 2301 | 133.2 | Solar | 07_797W19 | 2019-04-27 11:00 | 2019-04-29 | 16 | 13 | 3 | 2019-05-22 | 2019-06-27 | 26 | 16 | 10 | 2019-07-26 | 2020-09-04 | 61 | 58 | 3 | [5 empty] | 2019-07-26 | 2020-09-04 | 61 | 58 | 3 | [5 empty] | 2020-09-28 | 2019-04-27 11:23 | 2023-01-03 |  | EXP |  | 2021-02-25 | 2021-12-08 | 286 | 67 | 219 |  |  | 2022-03-07 | Connected |  | No
National Grid | RANDOLPH | 223131 | 2368 | 199.8 | Solar | 07_97W2 | 2019-04-27 11:23 | 2019-04-29 | 16 | 11 | 5 | 2019-05-22 | 2019-06-11 | 13 | 3 | 10 | 2019-07-19 | 2020-07-30 | 260 | 151 | 109 | [5 empty] | 2019-07-19 | 2020-07-30 | 260 | 151 | 109 | [5 empty] | 2020-09-04 |  | 2022-10-11 | Yes | EXP |  | 2021-05-11 | 2022-01-04 | 239 | 226 | 13 |  |  | 2022-09-15 | Connected |  | No
National Grid | EVERETT | 223132 | 2149 | 133.2 | Solar | 12_8W1 | 2019-04-27 12:00 | 2019-04-29 | 17 | 15 | 2 | 2019-05-22 | 2019-06-13 | 16 | 5 | 11 | [20 empty] | 2019-08-14 |  | 2021-03-31 |  | EXP | [8 empty] | 2021-05-20 | Connected |  | No
National Grid | MEDFORD | 223134 | 2155 | 106 | Solar | 12_64J5 | 2019-04-27 14:47 | 2019-04-29 | 16 | 11 | 5 | 2019-05-22 | 2019-06-11 | 13 | 3 | 10 | [20 empty] | 2019-06-17 |  | 2021-06-21 |  | EXP | [8 empty] | 2021-05-28 | Connected |  | No
National Grid | MALDEN | 223160 | 2148 | 133.2 | Solar | 12_16J6 | 2019-04-29 06:51 | 2019-04-30 | 12 | 7 | 5 | 2019-05-17 | 2019-06-05 | 12 | 0 | 12 | [20 empty] | 2019-06-07 |  | 2021-06-21 |  | EXP | [8 empty] | 2021-05-27 | Connected |  | No
National Grid | WESTFORD | 223164 | 1886 | 99.9 | Solar | 14_57L4 | 2019-04-29 07:27 | 2019-04-30 | 12 | 8 | 4 | 2019-05-17 | 2019-05-31 | 9 | 0 | 9 | [20 empty] | 2019-06-18 |  | 2021-06-21 |  | EXP | [8 empty] | 2021-03-30 | Connected |  | No
National Grid | BEVERLY | 223495 | 1915 | 11.4 | Solar | 12_12L2 | 2019-04-29 13:33 | 2019-04-30 | 102 | 101 | 1 | 2019-09-23 | 2019-09-26 | 3 | 0 | 3 | [20 empty] | 2019-09-27 | 2019-04-29 17:53 | 2019-11-29 |  | EXP | [8 empty] | 2019-10-31 | Connected |  | No
National Grid | REVERE | 223563 | 2151 | 106.6 | Solar | 12_16W4 | 2019-04-29 17:53 | 2019-04-30 | 12 | 7 | 5 | 2019-05-17 | 2019-06-06 | 13 | 2 | 11 | [20 empty] | 2019-07-03 |  | 2021-08-06 | Yes | EXP |  | 2020-11-04 | 2021-04-07 | 154 | 0 | 154 |  |  | 2021-08-05 | Connected |  | No
National Grid | LYNN | 223576 | 1905 | 33.3 | Solar | 12_21J27 | 2019-04-29 18:25 | 2019-04-30 | 283 | 51 | 232 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTFORD | 223575 | 1886 | 15 | Solar | 14_58L1 | 2019-04-29 18:31 | 2019-04-30 | 5 | 0 | 5 | 2019-05-08 | 2019-06-03 | 17 | 0 | 17 | [20 empty] | 2019-06-06 |  | 2020-04-29 |  | EXP | [8 empty] | 2020-02-05 | Connected |  | No
National Grid | RANDOLPH | 223582 | 2368 | 186.6 | Solar | 07_5W3 | 2019-04-29 19:04 | 2019-04-30 | 15 | 9 | 6 | 2019-05-22 | 2019-06-14 | 16 | 8 | 8 | [20 empty] | 2019-08-01 |  | 2021-05-21 |  | EXP | [8 empty] | 2021-06-14 | Connected |  | No
National Grid | WEYMOUTH | 223586 | 2190 | 100 | Solar | 07_99W32 | 2019-04-29 20:13 | 2019-04-30 | 16 | 14 | 2 | 2019-05-22 | 2019-06-11 | 13 | 3 | 10 | 2019-07-17 | 2020-08-20 | 277 | 240 | 37 | [5 empty] | 2019-07-17 | 2020-08-20 | 277 | 240 | 37 | [5 empty] | 2020-09-09 |  | 2022-06-23 |  | EXP |  | 2021-03-02 | 2021-06-10 | 100 | 0 | 100 |  |  | 2021-12-27 | Connected |  | No
National Grid | WRENTHAM | 223811 | 2093 | 10 | Solar | 05_3422W1 | 2019-04-30 | 2019-05-01 | 0 | 0 | 0 | 2019-05-02 | 2019-05-07 | 3 | 3 | 0 | [20 empty] | 2019-05-07 | 2019-04-30 09:41 | 2019-07-08 |  | EXP | [8 empty] | 2019-07-01 | Connected |  | No
National Grid | AUBURN | 223683 | 1501 | 10 | Solar | 01_26W1 | 2019-04-30 09:41 | 2019-05-01 | 4 | 0 | 4 | 2019-05-08 | 2019-06-03 | 17 | 0 | 17 | [20 empty] | 2019-06-12 |  | 2022-08-16 | Yes | EXP |  | 2020-09-23 | 2020-11-18 | 56 | 0 | 56 |  |  |  | Withdrawn |  | No
National Grid | WEST NEWBURY | 223680 | 1985 | 7 | Solar | 14_47L2 | 2019-04-30 09:55 | 2019-07-15 | 40 | 36 | 4 | 2019-09-12 | 2019-10-18 | 26 | 20 | 6 | [20 empty] | 2019-10-23 | 2019-05-01 11:45 | 2020-09-11 |  | EXP | [8 empty] | 2020-03-04 | Connected |  | No
National Grid | METHUEN | 219723 | 1844 | 5 | Solar | 14_63L1 | 2019-05-01 11:45 | 2019-05-02 | 0 | 0 | 0 | 2019-05-02 | 2019-05-03 | 1 | 0 | 1 | [20 empty] | 2019-05-03 | 2019-05-02 13:29 | 2020-01-21 | Yes | EXP |  | 2019-07-16 | 2019-08-12 | 27 | 0 | 27 |  |  | 2019-10-08 | Connected |  | No
National Grid | ATTLEBORO | 222415 | 2703 | 5 | Solar | 05_9L3 | 2019-05-02 13:29 | 2019-05-07 | 3 | 3 | 0 | 2019-05-10 | 2019-05-30 | 13 | 0 | 13 | [20 empty] | 2019-05-30 |  | 2019-11-15 | Yes | EXP | [8 empty] | 2019-10-09 | Connected |  | No
National Grid | BELCHERTOWN | 225069 | 1007 | 20 | Solar | 09_509L2 | 2019-05-03 09:43 | 2019-05-06 | 2 | 0 | 2 | 2019-05-09 | 2019-05-29 | 13 | 0 | 13 | [20 empty] | 2019-05-31 |  | 2019-11-07 |  | EXP | [8 empty] | 2019-08-09 | Connected |  | No
National Grid | WARE | 225183 | 1082 | 30 | Solar | 09_501L2 | 2019-05-03 18:05 | 2019-05-06 | 2 | 0 | 2 | 2019-05-09 | 2019-05-29 | 13 | 0 | 13 | [20 empty] | 2019-06-04 | 2019-05-03 18:06 | 2019-11-07 |  | EXP | [8 empty] | 2019-07-09 | Connected |  | No
National Grid | LAWRENCE | 225186 | 1841 | 7.6 | Solar | 14_8L2 | 2019-05-03 18:06 | 2019-05-16 | 0 | 0 | 0 | 2019-05-17 | 2019-06-04 | 11 | 0 | 11 | [20 empty] | 2019-06-25 |  | 2021-10-23 | Yes | EXP |  | 2020-12-09 | 2021-01-08 | 30 | 0 | 30 |  |  | 2021-05-27 | Connected |  | No
National Grid | FALL RIVER | 217169 | 2720 | 240 | Solar | 05_28W51 | 2019-05-06 | 2019-05-08 | 8 | 0 | 8 | 2019-05-22 | 2019-06-12 | 15 | 2 | 13 | 2019-07-03 | 2019-08-29 | 40 | 0 | 40 | [5 empty] | 2019-07-03 | 2019-08-29 | 40 | 0 | 40 | [5 empty] | 2019-09-04 |  | 2020-06-12 |  | EXP | [8 empty] | 2020-04-16 | Connected |  | No
National Grid | BEVERLY | 225352 | 1915 | 10 | Solar | 12_51T1 | 2019-05-06 11:35 | 2019-05-07 | 8 | 8 | 0 | 2019-05-17 | 2019-05-28 | 6 | 0 | 6 | [20 empty] | 2019-05-28 | 2019-05-07 | 2019-12-30 |  | EXP | [8 empty] | 2019-11-18 | Connected |  | Yes
National Grid | MEDFORD | 225166 | 2155 | 280 | Other | 12_9C2 | 2019-05-07 | 2019-06-21 | 8 | 7 | 1 | [10 empty] | 2019-07-03 | 2019-08-09 | 26 | 8 | 18 | [10 empty] | 2020-08-20 | 2019-05-07 10:44 | 2022-02-06 | Yes | STD |  | 2021-07-23 | 2021-07-22 | 0 | 0 | 0 |  |  | 2021-12-30 | Connected |  | No
National Grid | EAST LONGMEADOW | 224421 | 1028 | 5 | Solar | 09_139L5 | 2019-05-07 10:44 | 2019-05-08 | 6 | 6 | 0 | 2019-05-16 | 2019-06-03 | 11 | 0 | 11 | [20 empty] | 2019-06-04 | 2019-05-07 11:46 | 2020-02-28 | Yes | EXP |  | 2019-10-25 | 2019-10-30 | 5 | 0 | 5 |  |  | 2019-11-07 | Connected |  | No
National Grid | ATHOL | 222507 | 1331 | 7.6 | Solar | 09_702W1 | 2019-05-07 11:46 | 2019-05-08 | 2 | 2 | 0 | 2019-05-10 | 2019-05-30 | 13 | 0 | 13 | [20 empty] | 2019-05-31 |  | 2020-01-22 | Yes | EXP |  | 2019-08-21 | 2019-10-10 | 50 | 0 | 50 |  |  | 2019-10-29 | Connected |  | No
National Grid | STURBRIDGE | 225333 | 1566 | 10 | Solar | 01_413L2 | 2019-05-07 13:42 | 2019-05-08 | 54 | 53 | 1 | 2019-07-22 | 2019-07-31 | 7 | 0 | 7 | [20 empty] | 2019-07-31 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LOWELL | 225135 | 1852 | 486 | Solar | 14_2381 | 2019-05-07 16:57 | 2019-05-08 | 21 | 20 | 1 | 2019-06-07 | 2019-06-13 | 4 | 0 | 4 | [21 empty] | 2019-05-07 17:00 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LYNN | 216929 | 1902 | 7.6 | Solar | 12_29W5 | 2019-05-07 17:00 | 2019-05-08 | 0 | 0 | 0 | 2019-05-09 | 2019-06-05 | 18 | 0 | 18 | [20 empty] | 2019-06-04 |  | 2021-05-12 |  | EXP |  | 2020-05-27 | 2020-10-24 | 151 | 5 | 146 |  |  | 2021-02-05 | Connected |  | No
National Grid | WEBSTER | 226260 | 1570 | 150 | Solar | 01_412L2 | 2019-05-08 | 2019-05-10 | 7 | 0 | 7 | 2019-05-22 | 2019-06-21 | 21 | 9 | 12 | [21 empty] | 2019-05-08 16:19 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | DRACUT | 218549 | 1826 | 3 | Solar | 14_78L1 | 2019-05-08 16:19 | 2019-05-09 | 7 | 7 | 0 | 2019-05-20 | 2019-06-03 | 9 | 0 | 9 | [20 empty] | 2019-06-04 | 2019-05-08 17:07 | 2020-03-31 | Yes | EXP |  | 2019-10-17 | 2019-10-25 | 8 | 0 | 8 |  |  | 2019-11-01 | Connected |  | No
National Grid | MILLVILLE | 225439 | 1529 | 6 | Solar | 05_321W9 | 2019-05-08 17:07 | 2019-05-09 | 1 | 1 | 0 | 2019-05-10 | 2019-05-30 | 12 | 1 | 11 | [20 empty] | 2019-05-30 | 2019-05-09 11:12 | 2020-04-14 | Yes | EXP |  | 2019-10-24 | 2019-11-26 | 33 | 0 | 33 |  |  | 2019-12-16 | Connected |  | No
National Grid | BILLERICA | 225966 | 1821 | 6 | Solar | 14_18L2 | 2019-05-09 11:12 | 2019-05-10 | 2 | 1 | 1 | 2019-05-14 | 2019-05-31 | 12 | 0 | 12 | [20 empty] | 2019-06-04 | 2019-05-09 15:27 | 2020-07-31 | Yes | EXP |  | 2020-04-15 | 2020-04-16 | 1 | 0 | 1 |  |  | 2020-04-20 | Connected |  | No
National Grid | WORCESTER | 224318 | 1603 | 7.6 | Solar | 01_7J387 | 2019-05-09 15:27 | 2019-05-10 | 4 | 4 | 0 | 2019-05-16 | 2019-06-05 | 14 | 3 | 11 | [20 empty] | 2019-06-05 |  | 2020-02-28 | Yes | EXP |  | 2019-08-31 | 2019-09-13 | 13 | 0 | 13 |  |  | 2019-11-07 | Connected |  | No
National Grid | ANDOVER | 227099 | 1810 | 20 | Solar | 14_50L1 | 2019-05-13 09:28 | 2019-05-14 | 0 | 0 | 0 | 2019-05-15 | 2019-05-30 | 10 | 0 | 10 | [20 empty] | 2019-05-31 |  | 2019-11-07 |  | EXP | [8 empty] | 2019-08-28 | Connected |  | No
National Grid | GRAFTON | 222250 | 1519 | 10 | Solar | 01_304W1 | 2019-05-13 12:57 | 2019-05-14 | 8 | 1 | 7 | 2019-05-28 | 2019-06-06 | 7 | 0 | 7 | [20 empty] | 2019-06-18 |  |  |  | EXP | [8 empty] | 2019-09-13 | Connected |  | No
National Grid | SALEM | 228309 | 1970 | 10 | Solar | 12_29W2 | 2019-05-15 12:31 | 2019-05-16 | 4 | 3 | 1 | 2019-05-23 | 2019-06-04 | 7 | 0 | 7 | [20 empty] | 2019-06-05 |  | 2019-07-30 |  | EXP | [8 empty] | 2019-07-25 | Connected |  | No
National Grid | PEMBROKE | 228439 | 2359 | 17.6 | Solar | 07_95W2 | 2019-05-15 15:45 | 2019-05-16 | 0 | 0 | 0 | 2019-05-17 | 2019-05-31 | 202 | 29 | 173 | [20 empty] | 2019-06-04 |  |  |  | EXP | [8 empty] | 2019-12-10 | Connected |  | No
National Grid | REVERE | 215113 | 2151 | 7.6 | Solar | 12_35J3 | 2019-05-15 17:46 | 2019-05-16 | 0 | 0 | 0 | 2019-05-17 | 2019-08-08 | 59 | 48 | 11 | [20 empty] | 2019-08-09 |  | 2020-10-23 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | DRACUT | 218706 | 1826 | 7.6 | Solar | 14_75L3 | 2019-05-16 13:08 | 2019-05-17 | 5 | 0 | 5 | 2019-05-28 | 2019-06-06 | 7 | 0 | 7 | [20 empty] | 2019-06-18 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORWELL | 220756 | 2061 | 105.6 | Solar | 07_96W40 | 2019-05-16 15:00 | 2019-05-17 | 10 | 1 | 9 | 2019-06-03 | 2019-06-24 | 16 | 6 | 10 | [20 empty] | 2019-07-03 |  | 2019-12-31 |  | EXP | [8 empty] | 2020-04-01 | Connected |  | No
National Grid | WESTBOROUGH | 228960 | 1581 | 10 | Solar | 05_312W1 | 2019-05-17 09:20 | 2019-05-20 | 4 | 0 | 4 | 2019-05-28 | 2019-06-06 | 7 | 0 | 7 | [20 empty] | 2019-06-18 | 2019-05-17 14:10 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | FALL RIVER | 214093 | 2721 | 7.36 | Solar | 05_115W53 | 2019-05-17 14:10 | 2019-05-20 | 7 | 1 | 6 | 2019-05-31 | 2019-06-11 | 7 | 0 | 7 | [20 empty] | 2019-06-18 |  |  | Yes | EXP | [8 empty] | 2019-10-03 | Connected |  | No
National Grid | SOUTHBOROUGH | 229154 | 1772 | 7.6 | Solar | 05_314W2 | 2019-05-18 14:43 | 2019-05-20 | 3 | 0 | 3 | 2019-05-24 | 2019-06-14 | 15 | 9 | 6 | [20 empty] | 2019-06-18 |  | 2019-08-30 |  | EXP | [8 empty] | 2019-08-12 | Connected |  | No
National Grid | MARLBOROUGH | 229547 | 1752 | 240 | Solar | 05_311W6 | 2019-05-20 | 2019-05-23 | 9 | 4 | 5 | 2019-06-06 | 2019-08-02 | 40 | 27 | 13 | 2019-09-03 | 2019-10-07 | 25 | 11 | 14 | [5 empty] | 2019-09-03 | 2019-10-07 | 25 | 11 | 14 | [9 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 227161 | 1603 | 5 | Solar | 01_7J386 | 2019-05-20 10:29 | 2019-05-21 | 63 | 11 | 52 | 2019-05-29 | 2019-06-21 | 18 | 9 | 9 | [20 empty] | 2019-06-24 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SPENCER | 220677 | 1562 | 5.12 | Solar | 01_552L1 | 2019-05-20 12:08 | 2019-05-21 | 68 | 67 | 1 | 2019-08-28 | 2019-09-10 | 8 | 0 | 8 | [20 empty] | 2019-09-11 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 226537 | 1606 | 4405 | Solar | 01_24W5 | 2019-05-20 16:54 | 2019-05-21 | 8 | 1 | 7 | [10 empty] | 2019-06-03 | 2019-06-27 | 0 | 0 | 0 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BRIMFIELD | 229566 | 1010 | 15.2 | Solar | 09_503L4 | 2019-05-20 18:22 | 2019-05-21 | 6 | 0 | 6 | 2019-05-31 | 2019-06-06 | 4 | 0 | 4 | [20 empty] | 2019-06-18 |  |  |  | EXP | [8 empty] | 2019-09-18 | Connected |  | Yes
National Grid | MILLBURY | 229816 | 1527 | 10 | Solar | 01_304W5 | 2019-05-21 12:51 | 2019-05-22 | 5 | 0 | 5 | 2019-05-31 | 2019-06-06 | 4 | 0 | 4 | [20 empty] | 2019-06-18 | 2019-05-21 23:19 |  |  | EXP | [8 empty] | 2019-11-14 | Connected |  | No
National Grid | BILLERICA | 230013 | 1821 | 15.2 | Solar | 14_92L6 | 2019-05-21 23:19 | 2019-05-22 | 3 | 1 | 2 | 2019-05-29 | 2019-06-06 | 6 | 0 | 6 | [20 empty] | 2019-06-07 | 2019-05-22 07:54 | 2019-11-01 | Yes | EXP |  | 2019-07-25 | 2019-10-02 | 69 | 0 | 69 |  |  | 2019-10-08 | Connected |  | No
National Grid | MONROE | 216209 | 1350 | 230 | Hydro | 09_1019W1 | 2019-05-22 07:54 | 2019-05-23 | 27 | 22 | 5 | [10 empty] | 2019-07-02 | 2019-08-22 | 36 | 22 | 14 | [10 empty] | 2020-07-27 |  | 2024-02-01 | Yes | STD | [8 empty] | 2023-10-12 | Connected |  | Yes
National Grid | SALEM | 230204 | 1970 | 22.6 | Solar | 12_29W2 | 2019-05-22 17:32 | 2019-05-23 | 4 | 0 | 4 | 2019-05-31 | 2019-06-06 | 4 | 0 | 4 | [20 empty] | 2019-06-18 |  | 2019-11-07 |  | EXP | [8 empty] | 2019-09-03 | Connected |  | No
National Grid | LAWRENCE | 225517 | 1840 | 23.4 | Solar | 14_2J2 | 2019-05-23 23:09 | 2019-05-24 | 19 | 12 | 7 | 2019-06-24 | 2019-06-26 | 2 | 0 | 2 | [20 empty] | 2019-07-02 |  | 2020-07-15 |  | EXP | [8 empty] | 2020-01-17 | Connected |  | No
National Grid | CHESHIRE | 201129 | 1225 | 5000 | Solar | 09_1021W2 | 2019-05-24 | 2019-06-05 | 14 | 8 | 6 | [10 empty] | 2019-06-25 | 2019-07-22 | 0 | 0 | 0 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | UPTON | 230666 | 1568 | 22.1 | Solar | 05_312W4 | 2019-05-24 09:10 | 2019-05-28 | 15 | 10 | 5 | 2019-06-19 | 2019-06-24 | 3 | 0 | 3 | [20 empty] | 2019-06-24 | 2019-05-24 10:04 | 2019-07-19 |  | EXP | [8 empty] | 2019-07-26 | Connected |  | No
National Grid | NORTON | 230608 | 2766 | 17.6 | Solar | 05_8L2 | 2019-05-24 10:04 | 2019-05-28 | 6 | 0 | 6 | 2019-06-06 | 2019-08-13 | 47 | 26 | 21 | [20 empty] | 2019-08-13 |  | 2020-07-15 | Yes | EXP |  | 2019-11-07 | 2020-01-22 | 76 | 0 | 76 |  |  | 2020-02-12 | Connected |  | No
National Grid | NORTHBOROUGH | 224878 | 1532 | 10 | Solar | 05_313W1 | 2019-05-28 12:17 | 2019-05-29 | 1 | 0 | 1 | 2019-05-31 | 2019-06-06 | 4 | 0 | 4 | [20 empty] | 2019-06-07 |  |  |  | EXP | [8 empty] | 2019-08-13 | Connected |  | No
National Grid | LEOMINSTER | 231390 | 1453 | 10 | Solar | 01_225W3 | 2019-05-28 15:30 | 2019-05-29 | 22 | 17 | 5 | 2019-06-28 | 2019-08-02 | 23 | 14 | 9 | [20 empty] | 2019-08-07 |  |  |  | EXP | [8 empty] | 2019-10-28 | Connected |  | No
National Grid | REVERE | 231907 | 2151 | 5 | Solar | 12_35J3 | 2019-05-30 09:04 | 2019-06-21 | 4 | 4 | 0 | 2019-06-27 | 2019-07-01 | 2 | 0 | 2 | [20 empty] | 2019-07-01 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WILLIAMSTOWN | 232178 | 1267 | 22 | Solar | 09_1003W2 | 2019-05-30 13:24 | 2019-05-31 | 0 | 0 | 0 | 2019-06-03 | 2019-06-10 | 5 | 0 | 5 | [20 empty] | 2019-06-13 |  | 2020-05-30 |  | EXP | [8 empty] | 2020-01-31 | Connected |  | No
National Grid | NORTH DIGHTON | 232600 | 2764 | 15.2 | Solar | 05_19W74 | 2019-05-31 15:34 | 2019-06-03 | 7 | 0 | 7 | 2019-06-13 | 2019-06-12 | 0 | 0 | 0 | [20 empty] | 2019-06-18 |  | 2020-06-09 |  | EXP | [8 empty] | 2020-01-16 | Connected |  | No
National Grid | NORTHAMPTON | 232983 | 1060 | 28 | Solar | 09_909W1 | 2019-06-03 13:45 | 2019-06-04 | 6 | 0 | 6 | 2019-06-13 | 2019-06-13 | 0 | 0 | 0 | [20 empty] | 2019-06-18 |  | 2019-11-07 |  | EXP | [8 empty] | 2019-08-09 | Connected |  | No
National Grid | TYNGSBOROUGH | 200571 | 1879 | 883.2 | Solar | 14_211L1 | 2019-06-04 | 2019-07-16 | 10 | 4 | 6 | [10 empty] | 2019-07-30 | 2019-08-28 | 21 | 5 | 16 | [12 empty] | 2021-09-27 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTHAMPTON | 228970 | 1060 | 303.4 | Solar | 09_901W3 | 2019-06-04 10:30 | 2019-06-05 | 8 | 6 | 2 | 2019-06-17 | 2022-05-26 | 740 | 415 | 325 | [21 empty] | 2019-06-05 10:39 | 2022-11-10 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MELROSE | 222080 | 2176 | 7.6 | Solar | 12_25W5 | 2019-06-05 10:39 | 2019-06-06 | 0 | 0 | 0 | 2019-06-07 | 2019-06-11 | 2 | 0 | 2 | [20 empty] | 2019-06-13 | 2019-06-05 10:52 | 2021-09-08 | Yes | EXP | [8 empty] | 2023-01-27 | Connected |  | Yes
National Grid | LYNN | 223585 | 1904 | 7.6 | Solar | 12_24W1 | 2019-06-05 10:52 | 2019-06-06 | 0 | 0 | 0 | 2019-06-07 | 2019-06-12 | 3 | 0 | 3 | [20 empty] | 2019-06-14 | 2019-06-05 13:29 | 2020-06-03 | Yes | EXP |  | 2019-12-05 | 2019-12-16 | 11 | 0 | 11 |  |  | 2020-03-13 | Connected |  | No
National Grid | DRACUT | 223770 | 1826 | 10 | Solar | 14_75L3 | 2019-06-05 13:29 | 2019-06-06 | 4 | 0 | 4 | 2019-06-13 | 2019-06-13 | 0 | 0 | 0 | [20 empty] | 2019-06-17 |  | 2021-10-20 | Yes | EXP |  | 2020-09-05 | 2020-09-28 | 23 | 0 | 23 |  |  | 2021-01-08 | Connected |  | No
National Grid | ANDOVER | 233871 | 1810 | 10 | Solar | 14_62L2 | 2019-06-06 13:11 | 2019-06-07 | 16 | 13 | 3 | 2019-07-01 | 2019-08-01 | 22 | 15 | 7 | [20 empty] | 2019-08-07 | 2019-06-07 01:00 |  |  | EXP | [8 empty] | 2019-10-10 | Connected |  | No
National Grid | WORCESTER | 218065 | 1603 | 792.6 | Solar | 01_6W2 | 2019-06-07 01:00 | 2019-06-10 | 70 | 69 | 1 | [10 empty] | 2019-09-18 | 2019-10-04 | 12 | 3 | 9 | [10 empty] | 2020-08-20 | 2019-06-07 13:57 | 2023-04-27 | Yes | STD |  | 2021-06-04 | 2023-03-09 | 644 | 7 | 637 | 2023-03-10 | 2023-03-10 | 2023-04-17 | Connected |  | No
National Grid | MILLBURY | 219923 | 1527 | 7.6 | Solar | 01_304W3 | 2019-06-07 13:57 | 2019-06-10 | 6 | 0 | 6 | 2019-06-19 | 2019-06-26 | 5 | 0 | 5 | [20 empty] | 2019-07-02 | 2019-06-10 11:32 | 2020-09-16 | Yes | EXP |  | 2020-05-29 | 2020-06-23 | 25 | 0 | 25 |  |  | 2020-07-25 | Connected |  | No
National Grid | METHUEN | 216261 | 1844 | 10 | Solar | 14_63L1 | 2019-06-10 11:32 | 2019-06-11 | 8 | 2 | 6 | 2019-06-24 | 2019-06-26 | 2 | 0 | 2 | [20 empty] | 2019-07-02 |  | 2020-09-16 | Yes | EXP |  | 2020-05-27 | 2020-06-01 | 5 | 0 | 5 |  |  | 2020-07-02 | Connected |  | No
National Grid | BROCKTON | 226520 | 2302 | 4061 | Solar | 07_91W41 | 2019-06-11 14:23 | 2019-06-12 | 15 | 9 | 6 | [10 empty] | 2019-07-03 | 2019-07-30 | 18 | 0 | 18 | [11 empty] | 2019-06-12 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WEYMOUTH | 236381 | 2189 | 150 | Solar | 07_12W3 | 2019-06-12 | 2019-06-14 | 11 | 8 | 3 | 2019-07-01 | 2019-08-15 | 32 | 26 | 6 | [20 empty] | 2019-09-10 |  | 2020-10-30 | Yes | EXP |  | 2020-08-08 | 2020-08-14 | 6 | 0 | 6 |  |  | 2020-10-21 | Connected |  | No
National Grid | PETERSHAM | 235906 | 1366 | 17.28 | Solar | 09_604W1 | 2019-06-12 09:57 | 2019-06-13 | 6 | 2 | 4 | 2019-06-27 | 2019-07-26 | 20 | 12 | 8 | [20 empty] | 2019-08-01 | 2019-06-12 17:37 |  |  | EXP | [8 empty] | 2019-09-16 | Connected |  | No
National Grid | REVERE | 225696 | 2151 | 7.6 | Solar | 12_7J7 | 2019-06-12 17:37 | 2019-06-13 | 3 | 0 | 3 | 2019-06-19 | 2019-06-20 | 1 | 0 | 1 | [20 empty] | 2019-06-28 | 2019-06-13 12:55 | 2021-04-23 | Yes | EXP |  | 2020-10-03 | 2020-11-18 | 46 | 0 | 46 |  |  | 2021-01-08 | Connected |  | No
National Grid | BOXFORD | 236527 | 1921 | 21.4 | Solar | 14_56L3 | 2019-06-13 12:55 | 2019-06-14 | 2 | 0 | 2 | 2019-06-19 | 2019-06-20 | 1 | 0 | 1 | [20 empty] | 2019-06-28 |  | 2020-06-13 | Yes | EXP | [8 empty] | 2020-01-29 | Connected |  | No
National Grid | BROCKTON | 228923 | 2302 | 15 | Solar | 07_911W56 | 2019-06-13 20:37 | 2019-06-14 | 3 | 1 | 2 | 2019-06-19 | 2019-06-20 | 1 | 0 | 1 | [20 empty] | 2019-06-20 |  | 2019-11-08 |  | EXP | [8 empty] | 2019-10-22 | Connected |  | No
National Grid | RANDOLPH | 234633 | 2368 | 10 | Solar | 07_5W3 | 2019-06-14 11:41 | 2019-06-17 | 6 | 5 | 1 | 2019-06-25 | 2019-07-01 | 4 | 0 | 4 | [20 empty] | 2019-07-01 | 2019-06-17 14:44 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BEVERLY | 230494 | 1915 | 9.92 | Solar | 12_18L1 | 2019-06-17 14:44 | 2019-06-18 | 5 | 5 | 0 | 2019-06-25 | 2019-07-01 | 4 | 0 | 4 | [20 empty] | 2019-07-01 | 2019-06-17 17:34 | 2019-10-15 | Yes | EXP |  | 2019-08-16 | 2019-09-09 | 24 | 0 | 24 |  |  | 2019-09-25 | Connected |  | No
National Grid | SAUGUS | 205535 | 1906 | 7.6 | Solar | 12_19W1 | 2019-06-17 17:34 | 2019-06-18 | 3 | 0 | 3 | 2019-06-24 | 2019-06-26 | 2 | 0 | 2 | [20 empty] | 2019-07-02 |  | 2020-06-17 | Yes | EXP |  | 2019-09-17 | 2019-10-25 | 38 | 0 | 38 |  |  | 2020-03-20 | Connected |  | No
National Grid | CLINTON | 217500 | 1510 | 3.8 | Solar | 01_216W3 | 2019-06-18 06:52 | 2019-06-19 | 87 | 83 | 4 | 2019-10-24 | 2019-10-30 | 4 | 0 | 4 | [20 empty] | 2019-11-06 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LEOMINSTER | 230771 | 1453 | 7.6 | Solar | 01_219W6 | 2019-06-18 12:55 | 2019-06-19 | 3 | 0 | 3 | 2019-06-25 | 2019-08-29 | 47 | 30 | 17 | [20 empty] | 2019-09-05 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ATHOL | 238129 | 1331 | 25 | Solar | 09_702W1 | 2019-06-18 13:39 | 2019-06-19 | 15 | 15 | 0 | 2019-07-11 | 2019-07-30 | 13 | 2 | 11 | [20 empty] | 2019-07-30 | 2019-06-18 13:48 | 2020-08-25 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | EAST LONGMEADOW | 235072 | 1028 | 7.6 | Solar | 09_508L1 | 2019-06-18 13:48 | 2019-06-19 | 3 | 0 | 3 | 2019-06-25 | 2019-07-09 | 10 | 5 | 5 | [20 empty] | 2019-07-18 |  | 2020-09-16 | Yes | EXP |  | 2020-05-14 | 2020-05-27 | 13 | 0 | 13 |  |  | 2020-07-28 | Connected |  | No
National Grid | ORANGE | 238143 | 1364 | 25 | Solar | 09_705W2 | 2019-06-18 14:11 | 2019-06-19 | 15 | 15 | 0 | 2019-07-11 | 2019-07-30 | 13 | 2 | 11 | [20 empty] | 2019-07-30 | 2019-06-18 14:38 | 2020-08-25 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | ORANGE | 238155 | 1364 | 25 | Solar | 09_705W2 | 2019-06-18 14:38 | 2019-06-19 | 15 | 15 | 0 | 2019-07-11 | 2019-07-26 | 12 | 2 | 10 | [20 empty] | 2019-07-29 |  | 2020-09-01 | Yes | EXP |  | 2020-03-19 | 2020-06-15 | 88 | 0 | 88 |  |  | 2020-06-23 | Connected |  | No
National Grid | AVON | 187201 | 2322 | 490 | Solar | 07_75W5 | 2019-06-18 15:37 | 2019-06-19 | 3 | 0 | 3 | 2019-06-24 | 2019-08-05 | 30 | 26 | 4 | [20 empty] | 2019-08-05 |  | 2020-08-11 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SAUGUS | 233774 | 1906 | 3.8 | Solar | 12_16W3 | 2019-06-19 11:21 | 2019-06-20 | 13 | 13 | 0 | 2019-07-10 | 2019-07-24 | 11 | 1 | 10 | [20 empty] | 2019-07-24 |  | 2020-06-19 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ESSEX | 238751 | 1929 | 10 | Solar | 12_51T2 | 2019-06-19 11:58 | 2019-06-20 | 0 | 0 | 0 | 2019-06-21 | 2019-07-01 | 7 | 5 | 2 | [20 empty] | 2019-07-01 | 2019-06-19 13:51 | 2019-09-06 |  | EXP | [8 empty] | 2019-08-28 | Connected |  | No
National Grid | WESTBOROUGH | 221730 | 1581 | 10 | Solar | 05_312W4 | 2019-06-19 13:51 | 2019-06-20 | 3 | 0 | 3 | 2019-06-27 | 2019-07-01 | 2 | 0 | 2 | [20 empty] | 2019-07-10 |  | 2020-11-08 | Yes | EXP |  | 2020-07-07 | 2020-10-10 | 96 | 5 | 91 |  |  | 2020-11-12 | Connected |  | No
National Grid | MARLBOROUGH | 233077 | 1752 | 25 | Solar | 05_311W1 | 2019-06-19 14:31 | 2019-06-20 | 1 | 1 | 0 | 2019-06-21 | 2019-06-25 | 2 | 0 | 2 | [20 empty] | 2019-06-25 | 2019-06-19 15:09 | 2019-12-30 |  | EXP | [8 empty] | 2019-11-14 | Connected |  | No
National Grid | WORCESTER | 232897 | 1604 | 7.6 | Solar | 01_9J360 | 2019-06-19 15:09 | 2019-06-20 | 12 | 12 | 0 | 2019-07-09 | 2019-07-17 | 6 | 0 | 6 | [20 empty] | 2019-07-18 |  | 2020-07-20 | Yes | EXP |  | 2020-04-09 | 2020-05-15 | 34 | 0 | 34 |  |  | 2020-05-18 | Connected |  | No
National Grid | NORTON | 229911 | 2766 | 10 | Solar | 05_8L2 | 2019-06-19 21:07 | 2019-06-20 | 4 | 0 | 4 | 2019-06-27 | 2019-07-10 | 8 | 0 | 8 | [20 empty] | 2019-07-18 | 2019-06-20 12:39 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOUTH GRAFTON | 232606 | 1560 | 6.72 | Solar | 05_320W3 | 2019-06-20 12:39 | 2019-06-21 | 5 | 0 | 5 | 2019-07-01 | 2019-08-06 | 24 | 23 | 1 | [20 empty] | 2019-08-13 | 2019-06-21 11:32 | 2020-09-30 | Yes | EXP | [8 empty] | 2020-08-21 | Connected |  | No
National Grid | FALL RIVER | 228014 | 2720 | 10 | Solar | 05_28W40 | 2019-06-21 11:32 | 2019-06-24 | 7 | 7 | 0 | 2019-07-05 | 2019-07-17 | 8 | 0 | 8 | [20 empty] | 2019-07-18 | 2019-06-21 12:00 | 2019-10-10 |  | EXP |  | 2019-08-30 | 2019-09-13 | 14 | 0 | 14 |  |  | 2019-09-23 | Connected |  | No
National Grid | MEDFORD | 235994 | 2155 | 7.6 | Solar | 12_37W5 | 2019-06-21 12:00 | 2019-06-24 | 4 | 0 | 4 | 2019-07-01 | 2019-07-10 | 6 | 0 | 6 | [20 empty] | 2019-07-18 |  | 2020-06-21 | Yes | EXP |  | 2020-03-06 | 2020-03-09 | 3 | 0 | 3 |  |  | 2020-05-01 | Connected |  | No
National Grid | EAST LONGMEADOW | 223863 | 1028 | 8.74 | Solar | 09_139L5 | 2019-06-21 13:13 | 2019-06-24 | 4 | 0 | 4 | 2019-07-01 | 2019-07-08 | 3 | 0 | 3 | [20 empty] | 2019-07-16 | 2019-06-21 17:58 | 2020-06-21 |  | EXP | [8 empty] | 2020-06-04 | Connected |  | No
National Grid | STOUGHTON | 239659 | 2072 | 250 | Solar | 07_913W69 | 2019-06-21 17:58 | 2019-06-24 | 5 | 0 | 5 | 2019-07-01 | 2019-07-24 | 16 | 3 | 13 | 2019-08-01 | 2019-11-25 | 80 | 42 | 38 | [5 empty] | 2019-08-01 | 2019-11-25 | 80 | 42 | 38 | [5 empty] | 2020-01-06 |  | 2023-01-06 | Yes | EXP |  | 2021-02-04 | 2022-11-03 | 638 | 544 | 94 |  |  | 2022-12-05 | Connected |  | No
National Grid | BELCHERTOWN | 239719 | 1007 | 172.8 | Solar | 09_509L1 | 2019-06-24 | 2019-07-05 | 4 | 0 | 4 | [10 empty] | 2019-07-12 | 2019-08-09 | 20 | 8 | 12 | [11 empty] | 2019-06-24 08:40 |  |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | OXFORD | 210192 | 1540 | 3000 | Natural Gas | 01_412L3 | 2019-06-24 08:40 | 2019-06-25 | 14 | 0 | 14 | [10 empty] | 2019-07-17 | 2019-07-25 | 0 | 0 | 0 | [10 empty] | 2020-07-22 |  | 2023-09-09 | Yes | STD | [8 empty] | 2023-06-22 | Connected |  | No
National Grid | REVERE | 229044 | 2151 | 7.245 | Solar | 12_16W7 | 2019-06-24 10:00 | 2019-06-25 | 0 | 0 | 0 | 2019-06-25 | 2019-07-01 | 4 | 0 | 4 | [20 empty] | 2019-07-01 | 2019-06-24 16:07 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 222923 | 2302 | 7.6 | Solar | 07_911W56 | 2019-06-24 16:07 | 2019-06-25 | 0 | 0 | 0 | 2019-06-26 | 2019-07-01 | 3 | 0 | 3 | [20 empty] | 2019-07-02 |  | 2020-11-20 | Yes | EXP |  | 2020-07-10 | 2020-07-22 | 12 | 0 | 12 |  |  | 2020-10-30 | Connected |  | No
National Grid | SEEKONK | 231935 | 2771 | 500 | Solar | 05_7L5 | 2019-06-25 | 2019-07-16 | 10 | 5 | 5 | [10 empty] | 2019-07-30 | 2019-08-30 | 23 | 9 | 14 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SALEM | 224995 | 1970 | 3.8 | Solar | 12_29W4 | 2019-06-25 12:14 | 2019-06-26 | 5 | 0 | 5 | 2019-07-05 | 2019-07-15 | 6 | 0 | 6 | [20 empty] | 2019-07-23 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | RANDOLPH | 225653 | 2368 | 7.6 | Solar | 07_5W3 | 2019-06-25 12:28 | 2019-06-26 | 0 | 0 | 0 | 2019-06-27 | 2019-07-01 | 2 | 0 | 2 | [20 empty] | 2019-07-01 |  | 2020-10-20 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RANDOLPH | 217727 | 2368 | 10 | Solar | 07_5W3 | 2019-06-25 13:05 | 2019-06-26 | 5 | 5 | 0 | 2019-07-03 | 2019-10-07 | 65 | 51 | 14 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WILBRAHAM | 195698 | 1095 | 1 | Solar | 09_139L3 | 2019-06-25 14:26 | 2019-06-26 | 66 | 0 | 66 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | BELLINGHAM | 215936 | 2019 | 10 | Solar | 05_108W60 | 2019-06-25 14:38 | 2019-06-26 | 5 | 0 | 5 | 2019-07-05 | 2019-07-22 | 11 | 0 | 11 | [20 empty] | 2019-08-01 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EAST BRIDGEWATER | 239807 | 2333 | 45.6 | Solar | 07_912W74 | 2019-06-25 14:50 | 2019-06-26 | 3 | 1 | 2 | [10 empty] | 2019-07-01 | 2019-07-15 | 9 | 1 | 8 | [10 empty] | 2019-11-15 |  | 2021-05-31 |  | STD | [8 empty] | 2021-05-19 | Connected |  | No
National Grid | EAST BRIDGEWATER | 239862 | 2333 | 45.6 | Solar | 07_912W74 | 2019-06-25 14:54 | 2019-06-26 | 3 | 1 | 2 | [10 empty] | 2019-07-01 | 2019-07-15 | 9 | 1 | 8 | [10 empty] | 2019-11-22 |  | 2021-05-31 |  | STD | [8 empty] | 2021-07-13 | Connected |  | No
National Grid | EAST BRIDGEWATER | 239875 | 2333 | 45.6 | Solar | 07_912W74 | 2019-06-25 14:58 | 2019-06-26 | 3 | 1 | 2 | [10 empty] | 2019-07-01 | 2019-07-15 | 9 | 2 | 7 | [10 empty] | 2019-11-22 |  | 2021-05-31 |  | STD | [8 empty] | 2021-05-19 | Connected |  | No
National Grid | EAST BRIDGEWATER | 239925 | 2333 | 45.6 | Solar | 07_912W74 | 2019-06-25 15:01 | 2019-06-26 | 3 | 1 | 2 | [10 empty] | 2019-07-01 | 2019-07-15 | 8 | 0 | 8 | [10 empty] | 2019-11-22 |  | 2021-05-31 |  | STD | [8 empty] | 2021-05-19 | Connected |  | No
National Grid | EAST BRIDGEWATER | 239915 | 2333 | 45.6 | Solar | 07_912W74 | 2019-06-25 15:04 | 2019-06-26 | 3 | 1 | 2 | [10 empty] | 2019-07-01 | 2019-07-15 | 9 | 1 | 8 | [10 empty] | 2019-11-22 |  | 2021-05-31 |  | STD | [8 empty] | 2021-05-19 | Connected |  | No
National Grid | EAST BRIDGEWATER | 239897 | 2333 | 45.6 | Solar | 07_912W74 | 2019-06-25 15:07 | 2019-06-26 | 3 | 1 | 2 | [10 empty] | 2019-07-01 | 2019-07-15 | 9 | 0 | 9 | [10 empty] | 2019-11-22 |  | 2021-05-31 |  | STD | [8 empty] | 2021-05-19 | Connected |  | No
National Grid | EAST BRIDGEWATER | 239903 | 2333 | 45.6 | Solar | 07_912W74 | 2019-06-25 15:10 | 2019-06-26 | 3 | 1 | 2 | [10 empty] | 2019-07-01 | 2019-07-15 | 9 | 7 | 2 | [10 empty] | 2019-11-22 |  | 2021-05-31 |  | STD | [8 empty] | 2021-07-13 | Connected |  | No
National Grid | EAST BRIDGEWATER | 239889 | 2333 | 45.6 | Solar | 07_912W74 | 2019-06-25 15:13 | 2019-06-26 | 3 | 1 | 2 | [10 empty] | 2019-07-01 | 2019-07-15 | 9 | 1 | 8 | [10 empty] | 2019-11-22 |  | 2021-05-31 |  | STD | [8 empty] | 2021-05-19 | Connected |  | No
National Grid | EAST BRIDGEWATER | 239819 | 2333 | 22.8 | Solar | 07_912W74 | 2019-06-25 15:16 | 2019-06-26 | 3 | 1 | 2 | [10 empty] | 2019-07-01 | 2019-07-15 | 9 | 1 | 8 | [10 empty] | 2019-11-22 |  | 2021-05-31 |  | STD | [8 empty] | 2021-05-19 | Connected |  | No
National Grid | EAST BRIDGEWATER | 239881 | 2333 | 45.6 | Solar | 07_912W74 | 2019-06-25 15:19 | 2019-06-26 | 3 | 1 | 2 | [10 empty] | 2019-07-01 | 2019-07-15 | 9 | 1 | 8 | [10 empty] | 2019-11-22 |  | 2021-05-31 |  | STD | [8 empty] | 2021-05-19 | Connected |  | No
National Grid | EAST BRIDGEWATER | 239842 | 2333 | 45.6 | Solar | 07_912W74 | 2019-06-25 15:22 | 2019-06-26 | 3 | 1 | 2 | [10 empty] | 2019-07-01 | 2019-07-15 | 9 | 1 | 8 | [10 empty] | 2019-11-22 |  | 2021-05-31 |  | STD | [8 empty] | 2021-05-19 | Connected |  | No
National Grid | METHUEN | 215445 | 1844 | 10 | Solar | 14_74L4 | 2019-06-25 16:08 | 2019-06-26 | 5 | 5 | 0 | 2019-07-03 | 2019-07-15 | 7 | 0 | 7 | [20 empty] | 2019-07-15 | 2019-06-25 17:48 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MILLBURY | 224988 | 1527 | 2.4 | Solar | 01_304W4 | 2019-06-25 17:48 | 2019-06-26 | 104 | 102 | 2 | 2019-10-24 | 2019-10-30 | 4 | 0 | 4 | [20 empty] | 2019-11-06 | 2019-06-25 20:54 | 2021-06-10 | Yes | EXP |  | 2021-01-12 | 2021-02-04 | 23 | 0 | 23 |  |  | 2021-02-17 | Connected |  | No
National Grid | WINTHROP | 231769 | 2152 | 6 | Solar | 12_22J3 | 2019-06-25 20:54 | 2019-06-26 | 5 | 5 | 0 | 2019-07-03 | 2019-07-10 | 4 | 0 | 4 | [20 empty] | 2019-07-10 | 2019-06-26 14:56 | 2020-04-16 | Yes | EXP |  | 2020-01-11 | 2020-01-23 | 12 | 0 | 12 |  |  | 2020-02-06 | Connected |  | No
National Grid | WESTBOROUGH | 240960 | 1581 | 6 | Solar | 05_312W1 | 2019-06-26 14:56 | 2019-07-30 | 7 | 7 | 0 | 2019-08-08 | 2019-08-15 | 5 | 0 | 5 | [20 empty] | 2019-08-16 | 2019-06-26 15:04 | 2020-05-01 | Yes | EXP |  | 2019-11-13 | 2019-11-27 | 14 | 0 | 14 |  |  | 2019-12-13 | Connected |  | No
National Grid | SOMERSET | 239803 | 2726 | 6 | Solar | 05_19W72 | 2019-06-26 15:04 | 2019-06-27 | 7 | 3 | 4 | 2019-07-09 | 2019-07-15 | 4 | 0 | 4 | [20 empty] | 2019-07-23 | 2019-06-26 17:49 | 2020-06-26 |  | EXP |  | 2019-11-07 | 2019-12-19 | 42 | 0 | 42 |  |  | 2020-01-21 | Connected |  | No
National Grid | RANDOLPH | 230807 | 2368 | 13.6 | Solar | 07_97W2 | 2019-06-26 17:49 | 2019-06-27 | 5 | 5 | 0 | 2019-07-08 | 2019-07-24 | 12 | 0 | 12 | [20 empty] | 2019-07-24 |  | 2020-06-01 | Yes | EXP |  | 2020-01-24 | 2020-02-05 | 12 | 0 | 12 |  |  | 2020-02-06 | Connected |  | No
National Grid | SEEKONK | 241012 | 2771 | 7.6 | Solar | 05_7L1 | 2019-06-26 18:14 | 2019-06-27 | 4 | 0 | 4 | 2019-07-05 | 2019-07-18 | 10 | 6 | 4 | [20 empty] | 2019-07-19 | 2019-06-27 11:08 |  |  | EXP | [8 empty] | 2019-09-25 | Connected |  | No
National Grid | METHUEN | 239280 | 1844 | 7.6 | Solar | 14_63L1 | 2019-06-27 11:08 | 2019-06-28 | 2 | 2 | 0 | 2019-07-02 | 2019-07-10 | 5 | 0 | 5 | [20 empty] | 2019-07-10 | 2019-06-27 11:16 | 2020-04-22 | Yes | EXP |  | 2020-01-03 | 2020-01-02 | 0 | 0 | 0 |  |  | 2020-01-10 | Connected |  | No
National Grid | WORCESTER | 236417 | 1603 | 7.6 | Solar | 01_6W2 | 2019-06-27 11:16 | 2019-06-28 | 5 | 5 | 0 | 2019-07-08 | 2019-07-19 | 9 | 0 | 9 | [20 empty] | 2019-07-19 | 2019-06-27 14:29 | 2020-06-27 | Yes | EXP |  | 2020-03-28 | 2020-04-22 | 25 | 0 | 25 |  |  | 2020-04-24 | Connected |  | No
National Grid | LEEDS | 227986 | 1053 | 10 | Solar | 09_909W3 | 2019-06-27 14:29 | 2019-06-28 | 5 | 0 | 5 | 2019-07-09 | 2019-07-19 | 8 | 0 | 8 | [20 empty] | 2019-07-23 |  | 2020-06-27 | Yes | EXP |  | 2019-12-06 | 2019-12-20 | 14 | 0 | 14 |  |  | 2020-01-17 | Connected |  | No
National Grid | LEOMINSTER | 241463 | 1453 | 22.8 | Solar | 01_207W6 | 2019-07-01 12:48 | 2019-07-02 | 5 | 0 | 5 | 2019-07-11 | 2019-07-31 | 14 | 9 | 5 | 2019-08-07 | 2019-09-09 | 22 | 6 | 16 | [5 empty] | 2019-08-07 | 2019-09-09 | 22 | 6 | 16 | [5 empty] | 2019-09-20 |  | 2020-07-31 |  | EXP | [8 empty] | 2020-09-01 | Connected |  | No
National Grid | LEOMINSTER | 241466 | 1453 | 22.8 | Solar | 01_207W6 | 2019-07-01 13:17 | 2019-07-02 | 5 | 0 | 5 | 2019-07-11 | 2019-07-31 | 14 | 9 | 5 | 2019-08-07 | 2019-09-09 | 22 | 6 | 16 | [5 empty] | 2019-08-07 | 2019-09-09 | 22 | 6 | 16 | [5 empty] | 2019-09-20 |  | 2020-07-31 |  | EXP | [8 empty] | 2020-09-01 | Connected |  | No
National Grid | LEOMINSTER | 241465 | 1453 | 22.8 | Solar | 01_207W6 | 2019-07-01 13:23 | 2019-07-02 | 5 | 0 | 5 | 2019-07-11 | 2019-07-31 | 14 | 9 | 5 | 2019-08-07 | 2019-09-09 | 22 | 6 | 16 | [5 empty] | 2019-08-07 | 2019-09-09 | 22 | 6 | 16 | [5 empty] | 2019-09-20 |  | 2020-08-31 |  | EXP | [8 empty] | 2020-09-01 | Connected |  | No
National Grid | LEOMINSTER | 241464 | 1453 | 22.8 | Solar | 01_207W6 | 2019-07-01 13:27 | 2019-07-02 | 5 | 0 | 5 | 2019-07-11 | 2019-07-31 | 14 | 9 | 5 | 2019-08-07 | 2019-09-09 | 22 | 6 | 16 | [5 empty] | 2019-08-07 | 2019-09-09 | 22 | 6 | 16 | [5 empty] | 2019-09-20 |  | 2020-07-31 |  | EXP | [8 empty] | 2020-09-01 | Connected |  | No
National Grid | LEOMINSTER | 241462 | 1453 | 22.8 | Solar | 01_207W6 | 2019-07-01 13:31 | 2019-07-02 | 5 | 0 | 5 | 2019-07-11 | 2019-07-31 | 14 | 9 | 5 | 2019-08-07 | 2019-09-09 | 22 | 6 | 16 | [5 empty] | 2019-08-07 | 2019-09-09 | 22 | 6 | 16 | [5 empty] | 2019-09-20 |  | 2020-07-31 |  | EXP | [8 empty] | 2020-09-01 | Connected |  | No
National Grid | LEOMINSTER | 241461 | 1453 | 22.8 | Solar | 01_207W6 | 2019-07-01 13:33 | 2019-07-02 | 5 | 0 | 5 | 2019-07-11 | 2019-07-31 | 14 | 9 | 5 | 2019-08-07 | 2019-09-09 | 22 | 6 | 16 | [5 empty] | 2019-08-07 | 2019-09-09 | 22 | 6 | 16 | [5 empty] | 2019-09-20 |  | 2020-07-31 |  | EXP | [8 empty] | 2020-09-01 | Connected |  | No
National Grid | FLORENCE | 234095 | 1062 | 10 | Solar | 09_909W4 | 2019-07-01 15:46 | 2019-07-02 | 0 | 0 | 0 | 2019-07-03 | 2019-07-08 | 2 | 0 | 2 | [20 empty] | 2019-07-09 | 2019-07-01 16:33 | 2019-11-15 |  | EXP | [8 empty] | 2019-10-28 | Connected |  | No
National Grid | MILLBURY | 219134 | 1527 | 4.56 | Solar | 01_304W3 | 2019-07-01 16:33 | 2019-07-02 | 22 | 18 | 4 | 2019-08-05 | 2019-08-14 | 7 | 0 | 7 | [20 empty] | 2019-08-20 |  | 2020-08-03 | Yes | EXP | [8 empty] | 2020-07-23 | Connected |  | No
National Grid | SPENCER | 231646 | 1562 | 6.4 | Solar | 01_552L1 | 2019-07-02 14:31 | 2019-07-03 | 10 | 10 | 0 | 2019-07-18 | 2019-10-01 | 53 | 45 | 8 | [20 empty] | 2019-10-02 | 2019-07-03 10:53 | 2020-07-03 |  | EXP | [8 empty] | 2020-01-06 | Connected |  | No
National Grid | LYNN | 241200 | 1905 | 7.6 | Solar | 12_6J2 | 2019-07-03 10:53 | 2019-07-05 | 3 | 0 | 3 | 2019-07-11 | 2019-07-22 | 7 | 0 | 7 | [20 empty] | 2019-08-01 |  | 2020-08-03 | Yes | EXP |  | 2020-05-20 | 2020-06-17 | 28 | 0 | 28 |  |  | 2020-07-21 | Connected |  | No
National Grid | DIGHTON | 235724 | 2715 | 7.6 | Solar | 05_19W73 | 2019-07-03 14:14 | 2019-07-05 | 8 | 8 | 0 | 2019-07-17 | 2019-07-31 | 10 | 0 | 10 | [20 empty] | 2019-07-31 |  | 2019-10-21 |  | EXP | [8 empty] | 2019-09-05 | Connected |  | No
National Grid | MILLBURY | 228730 | 1527 | 7.6 | Solar | 01_304W4 | 2019-07-05 13:08 | 2019-07-08 | 63 | 58 | 5 | 2019-10-04 | 2019-10-14 | 6 | 0 | 6 | [20 empty] | 2019-10-15 | 2019-07-05 14:15 | 2020-07-05 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MEDFORD | 233361 | 2155 | 7.6 | Solar | 12_37W4 | 2019-07-05 14:15 | 2019-07-08 | 5 | 0 | 5 | 2019-07-16 | 2019-07-22 | 4 | 0 | 4 | [20 empty] | 2019-08-01 |  | 2021-08-20 | Yes | EXP |  | 2020-10-15 | 2021-08-09 | 293 | 0 | 293 |  |  | 2021-08-14 | Connected |  | No
National Grid | WEYMOUTH | 235878 | 2188 | 7.6 | Solar | 07_6W1 | 2019-07-05 14:26 | 2019-07-08 | 25 | 25 | 0 | 2019-08-12 | 2019-08-19 | 5 | 0 | 5 | [20 empty] | 2019-08-19 | 2019-07-05 20:06 | 2020-08-25 |  | EXP | [8 empty] | 2020-07-21 | Connected |  | No
National Grid | LEOMINSTER | 233067 | 1453 | 7.6 | Solar | 01_225W3 | 2019-07-05 20:06 | 2019-07-08 | 0 | 0 | 0 | 2019-07-09 | 2019-07-17 | 6 | 0 | 6 | [20 empty] | 2019-07-18 | 2019-07-08 12:37 | 2020-05-28 | Yes | EXP |  | 2019-12-17 | 2020-01-24 | 38 | 0 | 38 |  |  | 2020-02-14 | Connected |  | No
National Grid | WILLIAMSTOWN | 242042 | 1267 | 6.72 | Solar | 09_1003W1 | 2019-07-08 12:37 | 2019-07-09 | 4 | 0 | 4 | 2019-07-16 | 2019-07-22 | 4 | 0 | 4 | [20 empty] | 2019-08-01 | 2019-07-08 13:19 | 2020-07-08 | Yes | EXP |  | 2020-04-10 | 2020-06-03 | 52 | 0 | 52 |  |  | 2020-06-15 | Connected |  | No
National Grid | MILFORD | 241367 | 1757 | 10 | Solar | 05_335W2 | 2019-07-08 13:19 | 2019-07-09 | 7 | 7 | 0 | 2019-07-18 | 2019-07-31 | 9 | 0 | 9 | [20 empty] | 2019-07-31 |  | 2020-03-17 | Yes | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 228343 | 1841 | 10 | Solar | 14_63L1 | 2019-07-08 13:45 | 2019-07-09 | 6 | 6 | 0 | 2019-07-18 | 2019-08-01 | 10 | 0 | 10 | [20 empty] | 2019-08-02 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTFORD | 242635 | 1886 | 10 | Solar | 14_57L1 | 2019-07-09 15:49 | 2019-07-10 | 3 | 0 | 3 | 2019-07-16 | 2019-07-31 | 12 | 3 | 9 | [20 empty] | 2019-08-07 |  | 2020-07-09 |  | EXP | [8 empty] | 2020-04-29 | Connected |  | No
National Grid | TYNGSBOROUGH | 242048 | 1879 | 16 | Solar | 14_57L3 | 2019-07-09 17:14 | 2019-07-10 | 9 | 9 | 0 | 2019-07-24 | 2019-08-02 | 7 | 0 | 7 | [20 empty] | 2019-08-05 | 2019-07-09 18:06 | 2019-11-11 |  | EXP | [8 empty] | 2019-10-28 | Connected |  | No
National Grid | RANDOLPH | 239710 | 2368 | 7.6 | Solar | 07_5W3 | 2019-07-09 18:06 | 2019-07-10 | 14 | 9 | 5 | 2019-07-31 | 2019-08-12 | 8 | 0 | 8 | [20 empty] | 2019-08-14 |  | 2021-04-08 | Yes | EXP |  | 2021-01-06 | 2021-01-21 | 15 | 0 | 15 |  |  | 2021-02-19 | Connected |  | No
National Grid | REVERE | 234798 | 2151 | 7.6 | Solar | 12_7W2 | 2019-07-10 15:48 | 2019-07-11 | 5 | 0 | 5 | 2019-07-19 | 2019-07-31 | 8 | 0 | 8 | [20 empty] | 2019-08-02 |  | 2020-07-10 |  | EXP | [8 empty] | 2020-07-30 | Connected |  | No
National Grid | DRACUT | 189632 | 1826 | 11.4 | Solar | 14_78L3 | 2019-07-10 18:19 | 2019-07-11 | 134 | 126 | 8 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | REVERE | 240171 | 2151 | 10 | Solar | 12_35J2 | 2019-07-11 11:25 | 2019-07-12 | 6 | 6 | 0 | 2019-07-22 | 2019-07-31 | 7 | 0 | 7 | [20 empty] | 2019-07-31 |  | 2019-11-29 |  | EXP | [8 empty] | 2019-11-19 | Connected |  | No
National Grid | WORCESTER | 198897 | 1602 | 3000 | Natural Gas | 01_27W3 | 2019-07-11 15:37 | 2019-07-12 | 35 | 25 | 10 | [10 empty] | 2019-09-03 | 2019-10-14 | 29 | 21 | 8 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | LYNN | 241818 | 1902 | 10 | Solar | 12_29W4 | 2019-07-12 11:19 | 2019-07-15 | 8 | 8 | 0 | 2019-07-25 | 2019-08-02 | 6 | 0 | 6 | [20 empty] | 2019-08-05 |  | 2020-02-05 |  | EXP | [8 empty] | 2019-12-18 | Connected |  | No
National Grid | NEWBURYPORT | 243484 | 1950 | 53 | Solar | 14_36L2 | 2019-07-15 11:30 | 2019-07-16 | 11 | 3 | 8 | 2019-07-31 | 2019-08-21 | 16 | 8 | 8 | [21 empty] | 2019-07-15 12:52 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MALDEN | 237449 | 2148 | 7.6 | Solar | 12_16W6 | 2019-07-15 12:52 | 2019-07-16 | 16 | 16 | 0 | 2019-08-07 | 2019-08-14 | 5 | 0 | 5 | [20 empty] | 2019-08-19 |  | 2020-03-10 | Yes | EXP |  | 2019-10-11 | 2020-01-07 | 88 | 0 | 88 |  |  | 2020-01-12 | Connected |  | No
National Grid | GRANBY | 219076 | 1033 | 2.88 | Solar | 09_527L1 | 2019-07-15 15:53 | 2019-07-16 | 10 | 3 | 7 | 2019-07-31 | 2019-08-13 | 9 | 0 | 9 | [20 empty] | 2019-08-20 | 2019-07-15 17:32 | 2021-02-10 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | DRACUT | 234804 | 1826 | 10 | Solar | 14_75L3 | 2019-07-15 17:32 | 2019-07-16 | 0 | 0 | 0 | 2019-07-17 | 2019-07-24 | 5 | 0 | 5 | [20 empty] | 2019-07-25 |  | 2020-12-07 | Yes | EXP |  | 2020-10-28 | 2020-11-09 | 12 | 0 | 12 |  |  | 2020-11-17 | Connected |  | No
National Grid | ESSEX | 242810 | 1929 | 7.6 | Solar | 12_51T2 | 2019-07-16 11:03 | 2019-07-17 | 0 | 0 | 0 | 2019-07-18 | 2019-07-26 | 6 | 0 | 6 | [20 empty] | 2019-07-29 | 2019-07-16 12:22 |  |  | EXP | [8 empty] | 2019-09-25 | Connected |  | No
National Grid | CLINTON | 242400 | 1510 | 9.92 | Solar | 01_216W3 | 2019-07-16 12:22 | 2019-07-17 | 4 | 0 | 4 | 2019-07-24 | 2019-08-05 | 9 | 2 | 7 | [20 empty] | 2019-08-07 | 2019-07-16 12:40 | 2020-07-16 | Yes | EXP | [8 empty] | 2020-06-13 | Connected |  | No
National Grid | WORCESTER | 241416 | 1604 | 7.36 | Solar | 01_9J360 | 2019-07-16 12:40 | 2019-07-17 | 1 | 1 | 0 | 2019-07-18 | 2019-07-31 | 10 | 1 | 9 | [20 empty] | 2019-08-01 |  | 2020-11-09 | Yes | EXP |  | 2020-08-22 | 2020-10-02 | 41 | 0 | 41 |  |  | 2020-11-04 | Connected |  | No
National Grid | SPENCER | 234351 | 1562 | 10 | Solar | 01_552L1 | 2019-07-16 15:18 | 2019-07-17 | 7 | 7 | 0 | 2019-07-26 | 2019-08-14 | 13 | 0 | 13 | [20 empty] | 2019-08-15 |  | 2020-07-15 |  | EXP | [8 empty] | 2020-03-18 | Connected |  | No
National Grid | WRENTHAM | 243834 | 2093 | 25.2 | Solar | 05_3422W1 | 2019-07-16 16:41 | 2019-07-17 | 4 | 0 | 4 | 2019-07-24 | 2019-08-02 | 7 | 0 | 7 | [20 empty] | 2019-08-07 |  | 2019-11-07 |  | EXP | [8 empty] | 2019-10-02 | Connected |  | No
National Grid | PALMER | 227774 | 1069 | 5000 | Solar | 09_523L1 | 2019-07-17 10:21 | 2019-07-18 | 22 | 16 | 6 | [10 empty] | 2019-08-19 | 2019-09-09 | 14 | 0 | 14 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | TYNGSBORO | 243897 | 1879 | 22 | Solar | 14_57L3 | 2019-07-17 10:22 | 2019-07-18 | 14 | 9 | 5 | 2019-08-08 | 2019-08-16 | 6 | 0 | 6 | [20 empty] | 2019-08-26 | 2019-07-17 13:42 | 2019-11-07 |  | EXP | [8 empty] | 2019-09-30 | Connected |  | No
National Grid | BOLTON | 243391 | 1740 | 10 | Solar | 01_216W6 | 2019-07-17 13:42 | 2019-07-18 | 0 | 0 | 0 | 2019-07-19 | 2019-08-05 | 12 | 2 | 10 | [20 empty] | 2019-08-06 |  | 2020-03-04 | Yes | EXP |  | 2019-11-14 | 2019-11-26 | 12 | 0 | 12 |  |  | 2020-01-28 | Connected |  | No
National Grid | HOLBROOK | 240208 | 2343 | 7.68 | Solar | 07_911W77 | 2019-07-18 09:43 | 2019-07-19 | 7 | 0 | 7 | 2019-07-31 | 2019-08-08 | 6 | 0 | 6 | [20 empty] | 2019-08-13 |  |  |  | EXP | [8 empty] | 2019-11-14 | Connected |  | No
National Grid | DRACUT | 242622 | 1826 | 5 | Solar | 14_78L1 | 2019-07-18 14:54 | 2019-07-19 | 19 | 19 | 0 | 2019-08-15 | 2019-08-20 | 3 | 0 | 3 | [20 empty] | 2019-08-20 |  | 2020-07-17 |  | EXP | [8 empty] | 2020-02-10 | Connected |  | No
National Grid | TOPSFIELD | 243633 | 1983 | 9.84 | Solar | 12_26L1 | 2019-07-19 09:16 | 2019-07-22 | 5 | 5 | 0 | 2019-07-29 | 2019-08-07 | 7 | 0 | 7 | [20 empty] | 2019-08-07 |  | 2019-11-11 |  | EXP | [8 empty] | 2019-10-16 | Connected |  | No
National Grid | REVERE | 234799 | 2151 | 10 | Solar | 12_7J2 | 2019-07-19 12:03 | 2019-07-22 | 6 | 0 | 6 | 2019-07-31 | 2019-08-09 | 7 | 0 | 7 | [20 empty] | 2019-08-13 | 2019-07-22 | 2020-12-31 |  | EXP | [8 empty] | 2020-08-13 | Connected |  | No
National Grid | BEVERLY | 244606 | 1915 | 146 | Solar | 12_12J7 | 2019-07-22 | 2019-07-24 | 17 | 14 | 3 | [5 empty] | 2019-11-01 | 2019-11-01 | 1 | 1 | 0 | 2019-08-19 | 2019-10-01 | 30 | 17 | 13 | 2019-11-01 | 2019-11-01 | 1 | 1 | 0 | [5 empty] | 2020-05-18 |  | 2023-01-18 | Yes | STD |  | 2023-03-25 | 2023-03-24 | 0 | 0 | 0 |  |  | 2023-04-13 | Connected |  | No
National Grid | BEVERLY | 244619 | 1915 | 115.2 | Solar | 12_12L6 | 2019-07-22 | 2019-07-24 | 20 | 14 | 6 | 2019-08-22 | 2019-09-30 | 26 | 17 | 9 | 2020-01-22 | 2020-05-05 | 64 | 54 | 10 | [5 empty] | 2020-01-22 | 2020-05-05 | 64 | 54 | 10 | [5 empty] | 2020-05-27 | 2019-07-22 06:56 | 2022-05-02 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | OXFORD | 244524 | 1540 | 249.8 | Solar | 01_406L3 | 2019-07-22 06:56 | 2019-07-23 | 4 | 3 | 1 | [10 empty] | 2019-07-29 | 2019-08-12 | 11 | 5 | 6 | [10 empty] | 2022-10-04 |  | 2023-11-10 | Yes | STD |  | 2022-11-01 | 2023-05-03 | 184 | 0 | 184 |  |  | 2023-10-17 | Connected |  | No
National Grid | CHARLTON | 244622 | 1507 | 10 | Solar | 01_415L2 | 2019-07-22 10:20 | 2019-07-23 | 0 | 0 | 0 | 2019-07-24 | 2019-08-02 | 7 | 0 | 7 | [20 empty] | 2019-08-05 |  | 2019-09-30 |  | EXP | [8 empty] | 2019-09-26 | Connected |  | No
National Grid | BRIDGEWATER | 244408 | 2324 | 4990 | Solar | 07_912W55 | 2019-07-22 14:22 | 2019-07-23 | 25 | 19 | 6 | [10 empty] | 2019-08-27 | 2019-10-02 | 25 | 16 | 9 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WHITMAN | 234837 | 2382 | 7.6 | Solar | 07_93W43 | 2019-07-22 15:56 | 2019-07-23 | 1 | 0 | 1 | 2019-07-25 | 2019-08-02 | 6 | 0 | 6 | [20 empty] | 2019-08-05 |  |  |  | EXP | [8 empty] | 2019-09-16 | Connected |  | No
National Grid | SALEM | 235959 | 1970 | 3.8 | Solar | 12_2W1 | 2019-07-22 16:14 | 2019-07-23 | 3 | 3 | 0 | 2019-07-26 | 2019-08-05 | 6 | 0 | 6 | [20 empty] | 2019-08-06 |  | 2020-08-04 |  | EXP | [8 empty] | 2020-01-06 | Connected |  | No
National Grid | BELCHERTOWN | 244028 | 1007 | 16 | Solar | 09_509L2 | 2019-07-22 17:25 | 2019-07-23 | 5 | 0 | 5 | 2019-07-31 | 2019-08-09 | 7 | 0 | 7 | [20 empty] | 2019-08-13 |  |  |  | EXP | [8 empty] | 2020-01-22 | Connected |  | No
National Grid | WORCESTER | 236472 | 1604 | 7.6 | Solar | 01_9J337 | 2019-07-22 17:49 | 2019-07-23 | 0 | 0 | 0 | 2019-07-24 | 2019-08-02 | 7 | 0 | 7 | [20 empty] | 2019-08-05 |  | 2019-12-30 |  | EXP | [8 empty] | 2019-12-10 | Connected |  | No
National Grid | BROCKTON | 215043 | 2302 | 3.8 | Solar | 07_911W56 | 2019-07-23 13:34 | 2019-07-24 | 52 | 26 | 26 | [26 empty] | 2019-07-23 17:22 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | OXFORD | 245016 | 1540 | 10 | Solar | 01_406L1 | 2019-07-23 17:22 | 2019-10-03 | 4 | 3 | 1 | 2019-10-09 | 2019-10-11 | 2 | 0 | 2 | [20 empty] | 2019-10-14 |  | 2020-07-07 | Yes | EXP |  | 2020-02-19 | 2020-02-20 | 1 | 0 | 1 |  |  |  | Withdrawn |  | Yes
National Grid | WEYMOUTH | 244318 | 2190 | 10 | Solar | 07_12W4 | 2019-07-23 18:17 | 2019-07-24 | 2 | 2 | 0 | 2019-07-26 | 2019-08-05 | 6 | 0 | 6 | [20 empty] | 2019-08-06 |  | 2020-08-25 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 244231 | 1844 | 7.6 | Solar | 14_63L2 | 2019-07-23 19:42 | 2019-07-24 | 7 | 2 | 5 | 2019-08-05 | 2019-08-13 | 6 | 0 | 6 | [20 empty] | 2019-08-14 |  | 2020-08-03 |  | EXP | [8 empty] | 2020-01-22 | Connected |  | No
National Grid | MILFORD | 240285 | 1757 | 7.6 | Solar | 05_336W3 | 2019-07-24 11:14 | 2019-07-25 | 0 | 0 | 0 | 2019-07-26 | 2019-08-06 | 7 | 0 | 7 | [20 empty] | 2019-08-06 |  | 2019-10-04 |  | EXP | [8 empty] | 2019-09-26 | Connected |  | No
National Grid | ATTLEBORO | 245118 | 2703 | 25.2 | Solar | 05_9L1 | 2019-07-24 11:20 | 2019-07-25 | 3 | 0 | 3 | 2019-07-31 | 2019-08-12 | 8 | 0 | 8 | [20 empty] | 2019-08-14 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | RANDOLPH | 228709 | 2368 | 7.6 | Solar | 07_97W2 | 2019-07-24 13:33 | 2019-07-25 | 3 | 0 | 3 | 2019-07-31 | 2019-08-13 | 9 | 0 | 9 | [20 empty] | 2019-08-14 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | TYNGSBORO | 241760 | 1879 | 7.6 | Solar | 14_2L1 | 2019-07-24 15:21 | 2019-07-25 | 0 | 0 | 0 | 2019-07-26 | 2019-08-08 | 8 | 0 | 8 | [20 empty] | 2019-08-19 | 2019-07-24 15:57 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 243356 | 1604 | 3.8 | Solar | 01_27W5 | 2019-07-24 15:57 | 2019-07-25 | 2 | 0 | 2 | 2019-07-30 | 2019-08-07 | 6 | 0 | 6 | [20 empty] | 2019-08-08 |  | 2020-07-23 | Yes | EXP |  | 2020-04-17 | 2020-06-09 | 53 | 0 | 53 |  |  | 2020-06-25 | Connected |  | No
National Grid | LYNN | 242778 | 1905 | 3.8 | Solar | 12_29W3 | 2019-07-24 16:12 | 2019-07-25 | 2 | 0 | 2 | 2019-07-30 | 2019-08-07 | 6 | 0 | 6 | [20 empty] | 2019-08-08 | 2019-07-24 16:36 | 2020-11-09 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BELCHERTOWN | 241092 | 1007 | 10.32 | Solar | 09_523L2 | 2019-07-24 16:36 | 2019-07-25 | 1 | 0 | 1 | 2019-07-29 | 2019-08-08 | 8 | 0 | 8 | [20 empty] | 2019-08-09 | 2019-07-24 16:59 | 2021-01-11 | Yes | EXP |  | 2020-02-07 | 2020-02-06 | 0 | 0 | 0 |  |  | 2020-12-18 | Connected |  | No
National Grid | CHELMSFORD | 243846 | 1824 | 14.5 | Solar | 14_24L1 | 2019-07-24 16:59 | 2019-07-25 | 3 | 0 | 3 | 2019-07-31 | 2019-09-06 | 26 | 16 | 10 | [20 empty] | 2019-09-11 |  | 2020-07-24 | Yes | EXP | [8 empty] | 2020-07-17 | Connected |  | No
National Grid | WHITMAN | 239824 | 2382 | 7.6 | Solar | 07_93W43 | 2019-07-24 17:12 | 2019-07-25 | 50 | 47 | 3 | 2019-10-04 | 2019-10-08 | 2 | 0 | 2 | [20 empty] | 2019-10-09 |  | 2020-08-25 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MILLBURY | 244233 | 1527 | 3.8 | Solar | 01_304W4 | 2019-07-24 17:33 | 2019-07-25 | 1 | 0 | 1 | 2019-07-29 | 2019-08-06 | 6 | 0 | 6 | [20 empty] | 2019-08-07 | 2019-07-24 18:10 | 2019-12-02 |  | EXP | [8 empty] | 2019-11-15 | Connected |  | No
National Grid | MILLBURY | 242650 | 1527 | 3.8 | Solar | 01_304W4 | 2019-07-24 18:10 | 2019-07-25 | 6 | 5 | 1 | 2019-08-05 | 2019-08-13 | 6 | 0 | 6 | [20 empty] | 2019-08-14 |  | 2020-08-03 | Yes | EXP |  | 2020-02-01 | 2020-02-26 | 25 | 0 | 25 |  |  | 2020-03-02 | Connected |  | No
National Grid | SAUGUS | 234682 | 1906 | 3.8 | Solar | 12_25W1 | 2019-07-24 18:29 | 2019-07-25 | 27 | 26 | 1 | 2019-09-03 | 2019-09-13 | 8 | 0 | 8 | [20 empty] | 2019-09-16 |  | 2020-12-07 |  | EXP | [8 empty] | 2020-11-17 | Connected |  | No
National Grid | WORCESTER | 230757 | 1602 | 7.6 | Solar | 01_23W3 | 2019-07-24 18:30 | 2019-07-25 | 1 | 0 | 1 | 2019-07-29 | 2019-08-07 | 7 | 0 | 7 | [20 empty] | 2019-08-07 |  | 2019-10-15 |  | EXP | [8 empty] | 2019-09-10 | Connected |  | No
National Grid | LAWRENCE | 244642 | 1843 | 200 | Solar | 14_8T2 | 2019-07-25 | 2019-07-31 | 7 | 3 | 4 | 2019-08-09 | 2019-08-30 | 15 | 3 | 12 | 2019-10-07 | 2019-11-18 | 28 | 0 | 28 | [5 empty] | 2019-10-07 | 2019-11-18 | 28 | 0 | 28 | [6 empty] | 2019-07-25 14:09 | 2021-09-27 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HANOVER | 243592 | 2339 | 999 | Solar | 07_95W2 | 2019-07-25 14:09 | 2019-07-26 | 12 | 7 | 5 | [10 empty] | 2019-08-13 | 2019-09-04 | 16 | 3 | 13 | [10 empty] | 2020-04-06 | 2019-07-25 15:21 | 2024-05-04 | Yes | STD |  | 2021-07-20 | 2023-09-15 | 788 | 631 | 157 |  |  |  | Completion Documents |  | No
National Grid | BEVERLY | 226580 | 1915 | 1950 | Natural Gas | 12_72L1 | 2019-07-25 15:21 | 2019-07-26 | 65 | 58 | 7 | [10 empty] | 2019-10-30 | 2020-01-31 | 63 | 31 | 32 | [10 empty] | 2021-11-17 |  | 2024-07-26 | Yes | STD |  | 2023-05-17 |  | 334 | 176 | 158 |  |  |  | Construction |  | Yes
National Grid | LEOMINSTER | 245424 | 1453 | 12.6 | Solar | 01_207W4 | 2019-07-25 16:02 | 2019-07-26 | 2 | 0 | 2 | 2019-07-31 | 2019-08-12 | 8 | 0 | 8 | [20 empty] | 2019-08-14 |  | 2019-11-07 |  | EXP | [8 empty] | 2019-09-30 | Connected |  | No
National Grid | RUTLAND | 245447 | 1543 | 10 | Solar | 01_55W1 | 2019-07-25 17:42 | 2019-07-26 | 2 | 0 | 2 | 2019-07-31 | 2019-08-19 | 14 | 7 | 7 | [20 empty] | 2019-08-26 |  |  |  | EXP | [8 empty] | 2019-10-28 | Connected |  | No
National Grid | HAVERHILL | 245548 | 1830 | 17.6 | Solar | 14_76L1 | 2019-07-26 | 2019-07-29 | 0 | 0 | 0 | 2019-07-30 | 2019-08-08 | 7 | 0 | 7 | [20 empty] | 2019-08-09 | 2019-07-29 16:55 | 2020-07-26 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BEVERLY | 243349 | 1915 | 2000 | Solar | 12_12L4 | 2019-07-29 16:55 | 2019-07-30 | 29 | 24 | 5 | [10 empty] | 2019-09-10 | 2019-10-08 | 21 | 17 | 4 | [10 empty] | 2021-06-02 | 2019-07-30 12:16 | 2023-06-01 | Yes | STD |  | 2022-09-28 | 2023-01-19 | 114 | 0 | 114 |  |  | 2023-05-31 | Connected |  | No
National Grid | BROCKTON | 234807 | 2301 | 10 | Solar | 07_98W46 | 2019-07-30 12:16 | 2019-07-31 | 0 | 0 | 0 | 2019-08-01 | 2019-08-13 | 8 | 0 | 8 | [20 empty] | 2019-08-19 |  | 2023-07-19 | Yes | EXP |  | 2021-01-12 | 2021-01-25 | 13 | 0 | 13 |  |  | 2023-01-07 | Connected |  | No
National Grid | NORTHBOROUGH | 246090 | 1532 | 17.6 | Solar | 05_314W4 | 2019-07-30 13:09 | 2019-07-31 | 0 | 0 | 0 | 2019-08-01 | 2019-08-12 | 7 | 0 | 7 | [20 empty] | 2019-08-12 |  | 2020-11-09 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SAUGUS | 246187 | 1906 | 10 | Solar | 12_23W2 | 2019-07-30 18:53 | 2019-07-31 | 48 | 47 | 1 | 2019-10-08 | 2019-10-14 | 4 | 0 | 4 | [20 empty] | 2019-10-14 |  | 2020-07-29 |  | EXP | [8 empty] | 2020-06-19 | Connected |  | No
National Grid | BROCKTON | 246245 | 2301 | 100 | Solar | 07_797W19 | 2019-07-31 | 2019-08-01 | 4 | 1 | 3 | 2019-08-08 | 2019-08-15 | 5 | 0 | 5 | [20 empty] | 2019-08-19 |  | 2020-09-23 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 245629 | 2302 | 10 | Solar | 07_911W56 | 2019-07-31 10:46 | 2019-08-01 | 4 | 0 | 4 | 2019-08-08 | 2019-08-14 | 4 | 0 | 4 | [20 empty] | 2019-08-07 | 2019-07-31 14:43 | 2020-07-31 |  | EXP | [8 empty] | 2020-04-22 | Connected |  | No
National Grid | WEST BRIDGEWATER | 245587 | 2379 | 7.6 | Solar | 07_797W19 | 2019-07-31 14:43 | 2019-08-01 | 4 | 4 | 0 | 2019-08-08 | 2019-08-16 | 6 | 0 | 6 | [20 empty] | 2019-08-19 | 2019-07-31 17:10 | 2020-12-31 | Yes | EXP |  | 2020-09-02 | 2020-09-18 | 16 | 0 | 16 |  |  | 2020-10-17 | Connected |  | No
National Grid | HARVARD | 243831 | 1451 | 6.38 | Solar | 01_201W2 | 2019-07-31 17:10 | 2019-08-01 | 0 | 0 | 0 | 2019-08-02 | 2019-08-13 | 7 | 0 | 7 | [20 empty] | 2019-08-13 |  | 2019-11-15 | Yes | EXP |  | 2019-09-25 | 2019-10-02 | 7 | 0 | 7 |  |  | 2019-10-25 | Connected |  | No
National Grid | LAWRENCE | 242394 | 1841 | 3.8 | Solar | 14_8L2 | 2019-08-01 12:48 | 2019-08-02 | 0 | 0 | 0 | 2019-08-02 | 2019-08-12 | 6 | 0 | 6 | [20 empty] | 2019-08-12 | 2019-08-02 10:37 | 2020-07-31 |  | EXP | [8 empty] | 2020-02-06 | Connected |  | No
National Grid | RANDOLPH | 234729 | 2368 | 7.6 | Solar | 07_97W1 | 2019-08-02 10:37 | 2019-08-05 | 0 | 0 | 0 | 2019-08-06 | 2019-08-14 | 6 | 0 | 6 | [20 empty] | 2019-08-15 |  | 2020-10-02 | Yes | EXP |  | 2020-03-28 | 2020-05-08 | 41 | 0 | 41 |  |  | 2020-07-16 | Connected |  | No
National Grid | WORCESTER | 246025 | 1606 | 6 | Solar | 01_24W3 | 2019-08-05 10:32 | 2019-08-06 | 10 | 4 | 6 | 2019-08-21 | 2019-08-21 | 0 | 0 | 0 | [20 empty] | 2019-08-28 |  |  |  | EXP | [8 empty] | 2019-11-15 | Connected |  | No
National Grid | FRANKLIN | 246153 | 2038 | 20 | Solar | 05_348W7 | 2019-08-05 14:41 | 2019-08-06 | 3 | 0 | 3 | 2019-08-12 | 2019-08-19 | 6 | 1 | 5 | [20 empty] | 2019-08-26 | 2019-08-06 12:34 | 2021-09-16 |  | EXP | [8 empty] | 2020-10-20 | Connected |  | No
National Grid | HARVARD | 247186 | 1451 | 15.2 | Solar | 01_201W2 | 2019-08-06 12:34 | 2019-08-07 | 0 | 0 | 0 | 2019-08-08 | 2019-08-15 | 5 | 0 | 5 | [20 empty] | 2019-08-16 |  | 2020-05-01 | Yes | EXP |  | 2019-10-29 | 2019-11-07 | 9 | 0 | 9 |  |  | 2020-01-14 | Connected |  | No
National Grid | BLACKSTONE | 215931 | 1504 | 4990 | Solar | 05_332W1 | 2019-08-06 14:57 | 2019-08-07 | 9 | 3 | 6 | [10 empty] | 2019-08-20 | 2019-09-12 | 16 | 2 | 14 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | ANDOVER | 247404 | 1810 | 15.25 | Solar | 14_59L1 | 2019-08-07 11:00 | 2019-08-08 | 0 | 0 | 0 | 2019-08-08 | 2019-08-14 | 4 | 0 | 4 | [20 empty] | 2019-08-15 |  | 2019-10-11 |  | EXP | [8 empty] | 2019-10-07 | Connected |  | No
National Grid | TYNGSBORO | 240929 | 1879 | 10 | Solar | 14_211L2 | 2019-08-07 13:53 | 2019-08-08 | 3 | 0 | 3 | 2019-08-14 | 2019-08-19 | 3 | 0 | 3 | [20 empty] | 2019-08-26 |  |  |  | EXP | [8 empty] | 2019-11-15 | Connected |  | No
National Grid | HANOVER | 246486 | 2339 | 18.56 | Solar | 07_95W1 | 2019-08-07 16:21 | 2019-08-08 | 0 | 0 | 0 | 2019-08-09 | 2019-08-19 | 6 | 0 | 6 | [20 empty] | 2019-08-20 |  | 2019-10-25 |  | EXP | [8 empty] | 2019-10-14 | Connected |  | No
National Grid | WEYMOUTH | 224808 | 2188 | 3.8 | Solar | 07_6W1 | 2019-08-08 13:53 | 2019-08-09 | 2 | 0 | 2 | 2019-08-14 | 2019-08-19 | 3 | 0 | 3 | [20 empty] | 2019-08-26 | 2019-08-08 14:08 | 2021-08-17 |  | EXP | [8 empty] | 2020-12-18 | Connected |  | No
National Grid | SAUGUS | 247703 | 1906 | 7.6 | Solar | 12_23W2 | 2019-08-08 14:08 | 2019-08-09 | 23 | 19 | 4 | 2019-09-12 | 2019-09-20 | 6 | 0 | 6 | [20 empty] | 2019-09-20 |  | 2021-06-15 | Yes | EXP |  | 2020-02-01 | 2020-03-03 | 31 | 0 | 31 |  |  |  | Withdrawn |  | No
National Grid | NORTH BILLERICA | 243050 | 1862 | 7.6 | Solar | 14_70L1 | 2019-08-09 14:29 | 2019-08-12 | 111 | 111 | 0 | 2020-01-21 | 2020-02-05 | 11 | 0 | 11 | [20 empty] | 2020-02-06 | 2019-08-12 12:45 | 2020-08-09 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | QUINCY | 248196 | 2169 | 7.6 | Solar | 07_1W5 | 2019-08-12 12:45 | 2019-08-13 | 0 | 0 | 0 | 2019-08-13 | 2019-08-21 | 6 | 0 | 6 | [20 empty] | 2019-08-21 |  | 2020-04-24 | Yes | EXP |  | 2019-10-23 | 2019-11-09 | 16 | 0 | 16 |  |  | 2019-11-14 | Connected |  | No
National Grid | WESTFORD | 247730 | 1886 | 10 | Solar | 14_58L3 | 2019-08-12 14:50 | 2019-08-13 | 0 | 0 | 0 | 2019-08-14 | 2019-08-19 | 3 | 0 | 3 | [20 empty] | 2019-08-20 |  | 2020-08-13 |  | EXP | [8 empty] | 2019-12-18 | Connected |  | No
National Grid | NORTH ANDOVER | 246224 | 1845 | 7.6 | Solar | 14_7J1 | 2019-08-12 15:13 | 2019-08-13 | 12 | 11 | 1 | 2019-08-29 | 2019-09-10 | 7 | 0 | 7 | [20 empty] | 2019-09-11 | 2019-08-12 16:11 | 2020-02-26 |  | EXP | [8 empty] | 2020-01-28 | Connected |  | No
National Grid | HAVERHILL | 248292 | 1832 | 7.6 | Solar | 14_48L2 | 2019-08-12 16:11 | 2020-01-31 | 0 | 0 | 0 | 2020-01-31 | 2020-01-30 | 0 | 0 | 0 | [20 empty] | 2019-08-14 |  | 2020-11-06 | Yes | EXP |  | 2020-05-27 | 2020-06-11 | 15 | 0 | 15 |  |  | 2020-06-15 | Connected |  | No
National Grid | BOLTON | 248297 | 1740 | 10 | Solar | 01_216W6 | 2019-08-12 16:28 | 2019-08-13 | 7 | 7 | 0 | 2019-08-22 | 2019-09-06 | 10 | 0 | 10 | [20 empty] | 2019-09-09 | 2019-08-13 16:25 | 2019-11-22 |  | EXP | [8 empty] | 2019-10-22 | Connected |  | No
National Grid | RANDOLPH | 242725 | 2368 | 10 | Solar | 07_5W1 | 2019-08-13 16:25 | 2019-08-14 | 15 | 15 | 0 | 2019-09-05 | 2019-09-17 | 8 | 0 | 8 | [20 empty] | 2019-09-17 | 2019-08-13 16:51 | 2020-05-01 | Yes | EXP |  | 2019-11-16 | 2019-12-19 | 33 | 0 | 33 |  |  | 2020-04-01 | Connected |  | No
National Grid | BROCKTON | 248607 | 2302 | 7.6 | Solar | 07_91W40 | 2019-08-13 16:51 | 2019-08-29 | 3 | 0 | 3 | 2019-09-05 | 2019-09-16 | 7 | 0 | 7 | [20 empty] | 2019-09-23 |  | 2020-09-30 | Yes | EXP | [8 empty] | 2020-09-04 | Connected |  | No
National Grid | WEST NEWBURY | 248584 | 1985 | 10 | Solar | 14_47L2 | 2019-08-14 10:56 | 2019-08-15 | 0 | 0 | 0 | 2019-08-15 | 2019-08-20 | 3 | 0 | 3 | [20 empty] | 2019-08-20 | 2019-08-14 11:38 | 2019-10-21 |  | EXP | [8 empty] | 2019-10-02 | Connected |  | No
National Grid | NORTON | 248702 | 2766 | 10 | Solar | 05_4L1 | 2019-08-14 11:38 | 2019-08-15 | 0 | 0 | 0 | 2019-08-15 | 2019-08-23 | 6 | 0 | 6 | [20 empty] | 2019-08-23 |  | 2020-09-25 | Yes | EXP |  | 2020-04-03 | 2020-05-22 | 49 | 0 | 49 |  |  | 2020-07-16 | Connected |  | No
National Grid | DUNSTABLE | 248827 | 1827 | 20 | Solar | 14_57L3 | 2019-08-14 17:39 | 2019-08-15 | 3 | 3 | 0 | 2019-08-20 | 2019-08-21 | 1 | 0 | 1 | [20 empty] | 2019-08-21 | 2019-08-14 17:46 | 2020-09-08 |  | EXP | [8 empty] | 2020-08-19 | Connected |  | No
National Grid | MEDFORD | 248807 | 2155 | 216 | Solar | 12_9C4 | 2019-08-14 17:46 | 2019-08-15 | 11 | 4 | 7 | 2019-09-03 | 2019-09-16 | 18 | 9 | 9 | 2019-10-09 | 2019-11-25 | 32 | 8 | 24 | [5 empty] | 2019-10-09 | 2019-11-25 | 32 | 8 | 24 | [5 empty] | 2019-12-06 |  | 2022-04-01 | Yes | EXP |  | 2021-05-07 | 2021-05-14 | 7 | 0 | 7 |  |  | 2022-02-09 | Connected |  | No
National Grid | LAWRENCE | 248995 | 1843 | 250 | Solar | 14_61L3 | 2019-08-15 | 2019-08-19 | 10 | 2 | 8 | 2019-09-03 | 2019-09-13 | 8 | 0 | 8 | [20 empty] | 2019-09-18 |  | 2020-09-23 |  | EXP | [8 empty] | 2020-02-26 | Connected |  | No
National Grid | OXFORD | 201189 | 1540 | 3.8 | Solar | 01_406L3 | 2019-08-15 08:06 | 2019-08-16 | 0 | 0 | 0 | 2019-08-16 | 2019-08-23 | 5 | 0 | 5 | [20 empty] | 2019-08-23 | 2019-08-15 09:14 | 2019-10-14 |  | EXP | [8 empty] | 2019-09-12 | Connected |  | No
National Grid | ANDOVER | 243231 | 1810 | 10 | Solar | 14_59L6 | 2019-08-15 09:14 | 2019-08-16 | 3 | 0 | 3 | 2019-08-22 | 2019-09-09 | 11 | 0 | 11 | [20 empty] | 2019-09-11 |  | 2020-08-15 | Yes | EXP | [8 empty] | 2020-01-22 | Connected |  | No
National Grid | TOPSFIELD | 243526 | 1983 | 4000 | Solar | 12_26L1 | 2019-08-15 15:55 | 2019-08-16 | 19 | 11 | 8 | [10 empty] | 2019-09-13 | 2019-10-07 | 17 | 9 | 8 | [10 empty] | 2021-05-06 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SAUGUS | 231877 | 1906 | 3.8 | Solar | 12_13J3 | 2019-08-15 17:28 | 2019-08-16 | 6 | 1 | 5 | 2019-08-27 | 2019-09-09 | 8 | 0 | 8 | [20 empty] | 2019-09-19 |  | 2020-08-26 |  | EXP | [8 empty] | 2020-05-21 | Connected |  | No
National Grid | AUBURN | 247021 | 1501 | 10 | Solar | 01_26W1 | 2019-08-19 12:03 | 2019-08-20 | 4 | 3 | 1 | 2019-08-27 | 2019-09-09 | 8 | 0 | 8 | [20 empty] | 2019-09-10 |  | 2019-11-25 |  | EXP | [8 empty] | 2019-10-23 | Connected |  | No
National Grid | STOUGHTON | 246680 | 2072 | 99.9 | Solar | 07_913W18 | 2019-08-20 | 2020-01-31 | 21 | 17 | 4 | 2020-03-03 | 2020-10-21 | 170 | 100 | 70 | [20 empty] | 2020-10-26 | 2019-08-20 09:09 |  |  | EXP | [8 empty] | 2021-05-06 | Connected |  | Yes
National Grid | RANDOLPH | 244985 | 2368 | 8.82 | Solar | 07_97W1 | 2019-08-20 09:09 | 2019-08-21 | 3 | 3 | 0 | 2019-08-26 | 2019-09-11 | 11 | 0 | 11 | [20 empty] | 2019-09-11 | 2019-08-20 13:13 | 2020-04-23 | Yes | EXP |  | 2019-10-23 | 2019-11-08 | 16 | 0 | 16 |  |  | 2019-12-18 | Connected |  | No
National Grid | HARVARD | 207974 | 1451 | 9.8 | Solar | 01_201W2 | 2019-08-20 13:13 | 2019-08-21 | 49 | 47 | 2 | 2019-10-31 | 2019-11-07 | 6 | 1 | 5 | [20 empty] | 2019-11-13 |  | 2020-11-18 | Yes | EXP | [8 empty] | 2020-09-04 | Connected |  | No
National Grid | WRENTHAM | 249752 | 2093 | 3.8 | Solar | 05_3422W2 | 2019-08-20 14:17 | 2019-08-21 | 12 | 6 | 6 | 2019-09-10 | 2019-09-17 | 5 | 0 | 5 | [20 empty] | 2019-09-24 | 2019-08-22 14:22 | 2020-08-20 |  | EXP | [8 empty] | 2020-02-12 | Connected |  | No
National Grid | BOXFORD | 247814 | 1921 | 45 | Solar | 14_55L1 | 2019-08-22 14:22 | 2019-08-23 | 0 | 0 | 0 | 2019-08-23 | 2019-09-11 | 12 | 0 | 12 | [20 empty] | 2019-09-11 |  | 2020-09-17 |  | EXP |  | 2020-01-11 | 2020-02-07 | 27 | 0 | 27 |  |  |  | Withdrawn |  | No
National Grid | MEDFORD | 250240 | 2155 | 7.6 | Solar | 12_37W4 | 2019-08-22 15:09 | 2019-08-23 | 18 | 18 | 0 | 2019-09-19 | 2019-09-20 | 1 | 0 | 1 | [20 empty] | 2019-09-23 |  | 2021-06-15 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | REVERE | 220757 | 2151 | 7.6 | Solar | 12_16W7 | 2019-08-22 15:19 | 2019-08-23 | 44 | 39 | 5 | [26 empty] | 2019-08-23 14:16 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHESHIRE | 249212 | 1225 | 3 | Solar | 09_1021W2 | 2019-08-23 14:16 | 2019-08-26 | 0 | 0 | 0 | 2019-08-27 | 2019-09-11 | 10 | 0 | 10 | [20 empty] | 2019-09-11 |  | 2020-07-08 | Yes | EXP |  | 2020-05-08 | 2020-06-05 | 28 | 0 | 28 |  |  | 2020-06-08 | Connected |  | No
National Grid | MARLBOROUGH | 250657 | 1752 | 7.6 | Solar | 05_310W5 | 2019-08-26 10:31 | 2019-11-01 | 0 | 0 | 0 | 2019-11-04 | 2019-11-07 | 3 | 0 | 3 | [20 empty] | 2019-11-08 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTHAMPTON | 250724 | 1062 | 10 | Solar | 09_901W3 | 2019-08-26 13:20 | 2019-08-27 | 4 | 0 | 4 | 2019-09-04 | 2019-09-16 | 8 | 0 | 8 | [20 empty] | 2019-09-23 | 2019-08-26 13:43 |  |  | EXP | [8 empty] | 2019-11-23 | Connected |  | No
National Grid | DRACUT | 250354 | 1826 | 7.6 | Solar | 14_78L1 | 2019-08-26 13:43 | 2019-08-27 | 4 | 4 | 0 | 2019-09-04 | 2019-09-13 | 7 | 0 | 7 | [20 empty] | 2019-09-16 | 2019-08-27 14:39 | 2020-08-26 | Yes | EXP |  | 2020-03-13 | 2020-06-02 | 81 | 0 | 81 |  |  | 2020-07-24 | Connected |  | No
National Grid | LOWELL | 250967 | 1851 | 7.6 | Solar | 14_2L2 | 2019-08-27 14:39 | 2019-08-28 | 1 | 1 | 0 | 2019-08-29 | 2019-09-11 | 8 | 0 | 8 | [20 empty] | 2019-09-11 | 2019-08-28 10:21 | 2020-08-28 | Yes | EXP |  | 2020-01-09 | 2020-03-12 | 62 | 0 | 62 |  |  | 2020-03-24 | Connected |  | No
National Grid | CLINTON | 251196 | 1510 | 7.6 | Solar | 01_216W6 | 2019-08-28 10:21 | 2019-10-09 | 3 | 0 | 3 | 2019-10-15 | 2019-10-15 | 0 | 0 | 0 | [20 empty] | 2019-10-22 |  | 2021-10-08 | Yes | EXP | [8 empty] | 2021-04-27 | Connected |  | No
National Grid | STOUGHTON | 246166 | 2072 | 2000 | Solar | 07_94W42 | 2019-08-28 10:26 | 2019-08-29 | 22 | 17 | 5 | [10 empty] | 2019-10-01 | 2019-10-03 | 2 | 0 | 2 | [11 empty] | 2019-08-28 15:15 | 2020-05-14 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 242735 | 1844 | 10 | Solar | 14_63L1 | 2019-08-28 15:15 | 2019-08-29 | 1 | 1 | 0 | 2019-08-30 | 2019-09-12 | 8 | 0 | 8 | [20 empty] | 2019-09-12 |  | 2020-06-11 | Yes | EXP |  | 2020-01-16 | 2020-02-20 | 35 | 0 | 35 |  |  | 2020-02-24 | Connected |  | No
National Grid | LOWELL | 213621 | 1852 | 266.4 | Solar | 14_301 | 2019-08-30 09:11 | 2019-09-03 | 37 | 32 | 5 | 2019-10-25 | 2019-11-06 | 8 | 0 | 8 | 2019-11-15 | 2020-02-18 | 63 | 34 | 29 | [5 empty] | 2019-11-15 | 2020-02-18 | 63 | 34 | 29 | [5 empty] | 2020-02-24 | 2019-08-30 13:36 | 2023-09-22 |  | EXP | [8 empty] | 2023-06-27 | Connected |  | No
National Grid | CHELMSFORD | 249645 | 1824 | 3.8 | Solar | 14_16L1 | 2019-08-30 13:36 | 2019-09-03 | 1 | 0 | 1 | 2019-09-05 | 2019-09-17 | 8 | 1 | 7 | [20 empty] | 2019-09-24 |  | 2021-10-13 | Yes | EXP |  | 2020-08-04 | 2020-08-21 | 17 | 0 | 17 |  |  | 2020-11-18 | Connected |  | No
National Grid | DRACUT | 229113 | 1826 | 7.6 | Solar | 14_78L1 | 2019-08-30 14:08 | 2019-09-03 | 2 | 2 | 0 | 2019-09-05 | 2019-09-17 | 8 | 0 | 8 | [20 empty] | 2019-09-17 | 2019-09-03 15:33 | 2020-09-01 |  | EXP | [8 empty] | 2020-04-13 | Connected |  | No
National Grid | WORCESTER | 232530 | 1604 | 7.6 | Solar | 01_18J394 | 2019-09-03 15:33 | 2019-09-04 | 14 | 10 | 4 | 2019-09-25 | 2019-10-14 | 13 | 7 | 6 | [20 empty] | 2019-10-22 | 2019-09-04 11:08 | 2021-10-20 | Yes | EXP | [8 empty] | 2020-10-24 | Connected |  | No
National Grid | WINCHENDON | 250818 | 1475 | 3300 | Solar | 01_607W5 | 2019-09-04 11:08 | 2019-09-05 | 3 | 0 | 3 | [25 empty] | 2021-05-19 |  | 2023-05-15 | Yes | STD |  | 2022-01-28 | 2023-01-23 | 359 | 0 | 359 |  |  | 2023-05-04 | Connected |  | No
National Grid | ROWE | 252302 | 1367 | 25 | Solar | 09_1019W1 | 2019-09-04 12:54 | 2019-09-05 | 5 | 5 | 0 | 2019-09-12 | 2019-10-29 | 32 | 10 | 22 | [20 empty] | 2019-10-31 | 2019-09-04 15:11 | 2020-09-02 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | GARDNER | 251773 | 1440 | 12.76 | Solar | 01_607W5 | 2019-09-04 15:11 | 2019-09-05 | 1 | 0 | 1 | 2019-09-09 | 2019-09-25 | 13 | 8 | 5 | [20 empty] | 2019-09-26 | 2019-09-04 15:23 | 2020-09-04 | Yes | EXP |  | 2020-02-05 | 2020-02-21 | 16 | 0 | 16 |  |  | 2020-03-12 | Connected |  | No
National Grid | AUBURN | 248514 | 1501 | 10 | Solar | 01_26W1 | 2019-09-04 15:23 | 2019-09-05 | 0 | 0 | 0 | 2019-09-06 | 2019-09-16 | 6 | 0 | 6 | [20 empty] | 2019-09-17 |  | 2020-05-11 | Yes | EXP |  | 2019-12-21 | 2020-01-24 | 34 | 0 | 34 |  |  | 2020-02-10 | Connected |  | No
National Grid | WENHAM | 252036 | 1984 | 20 | Solar | 12_51T1 | 2019-09-04 16:43 | 2019-09-05 | 4 | 0 | 4 | 2019-09-12 | 2019-09-17 | 3 | 0 | 3 | [20 empty] | 2019-09-24 |  | 2022-12-14 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | PEMBROKE | 249662 | 2359 | 3200 | Solar | 07_910W25 | 2019-09-05 | 2019-09-10 | 48 | 46 | 2 | [10 empty] | 2019-11-20 | 2020-05-07 | 116 | 94 | 22 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | UXBRIDGE | 252243 | 1569 | 20 | Solar | 05_321W2 | 2019-09-05 11:13 | 2019-09-06 | 8 | 8 | 0 | 2019-09-18 | 2019-09-20 | 2 | 0 | 2 | [20 empty] | 2019-09-23 |  | 2020-09-04 |  | EXP | [8 empty] | 2020-09-29 | Connected |  | No
National Grid | HAVERHILL | 250814 | 1835 | 230.4 | Solar | 14_43L8 | 2019-09-05 12:11 | 2019-09-06 | 21 | 17 | 4 | 2019-10-08 | 2019-11-06 | 21 | 12 | 9 | [20 empty] | 2019-11-22 | 2019-09-06 | 2021-04-02 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MEDFORD | 252575 | 2155 | 150 | Solar | 12_11J3 | 2019-09-06 | 2019-09-10 | 0 | 0 | 0 | 2019-09-11 | 2019-09-26 | 12 | 1 | 11 | 2019-10-22 | 2019-11-25 | 23 | 0 | 23 | [5 empty] | 2019-10-22 | 2019-11-25 | 23 | 0 | 23 | [5 empty] | 2019-12-10 |  | 2020-09-29 | Yes | EXP |  | 2020-07-29 | 2020-08-25 | 27 | 0 | 27 |  |  | 2020-09-28 | Connected |  | No
National Grid | MEDFORD | 252582 | 2155 | 200 | Solar | 12_37W2 | 2019-09-06 | 2019-09-10 | 0 | 0 | 0 | 2019-09-11 | 2020-01-21 | 88 | 26 | 62 | 2019-10-30 | 2020-01-21 | 57 | 25 | 32 | [5 empty] | 2019-10-30 | 2020-01-21 | 57 | 25 | 32 | [7 empty] | 2021-09-27 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | STOUGHTON | 208164 | 2072 | 2000 | Solar | 07_94W42 | 2019-09-06 09:43 | 2019-09-09 | 8 | 0 | 8 | [10 empty] | 2019-09-20 | 2019-10-03 | 9 | 4 | 5 | [11 empty] | 2019-09-06 18:03 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | PALMER | 225328 | 1069 | 8.51 | Solar | 09_514L1 | 2019-09-06 18:03 | 2019-09-09 | 0 | 0 | 0 | 2019-09-10 | 2019-09-17 | 5 | 0 | 5 | [20 empty] | 2019-09-17 |  | 2020-09-09 | Yes | EXP |  | 2020-05-29 | 2020-06-11 | 13 | 0 | 13 |  |  | 2020-07-20 | Connected |  | No
National Grid | DRACUT | 253040 | 1826 | 17.6 | Solar | 14_78L1 | 2019-09-09 11:33 | 2019-09-10 | 1 | 0 | 1 | 2019-09-12 | 2019-09-17 | 3 | 0 | 3 | [20 empty] | 2019-09-23 |  | 2020-09-09 |  | EXP | [8 empty] | 2020-01-31 | Connected |  | No
National Grid | FLORENCE | 253195 | 1062 | 21.5 | Solar | 09_909W1 | 2019-09-09 17:59 | 2019-09-10 | 0 | 0 | 0 | 2019-09-11 | 2019-09-18 | 5 | 0 | 5 | [20 empty] | 2019-09-18 |  | 2020-09-08 |  | EXP | [8 empty] | 2020-03-18 | Connected |  | No
National Grid | NORTHBOROUGH | 253609 | 1532 | 15.2 | Solar | 05_313W1 | 2019-09-11 12:34 | 2019-09-12 | 3 | 3 | 0 | 2019-09-17 | 2019-09-20 | 3 | 0 | 3 | [20 empty] | 2019-09-23 | 2019-09-11 12:54 | 2020-09-10 |  | EXP | [8 empty] | 2020-02-12 | Connected |  | No
National Grid | SALISBURY | 252060 | 1952 | 7.6 | Solar | 14_7L4 | 2019-09-11 12:54 | 2019-09-12 | 4 | 0 | 4 | 2019-09-19 | 2019-09-20 | 1 | 0 | 1 | [20 empty] | 2019-09-30 | 2019-09-11 14:44 | 2020-09-11 | Yes | EXP |  | 2020-02-01 | 2020-02-05 | 4 | 0 | 4 |  |  | 2020-02-14 | Connected |  | No
National Grid | LOWELL | 251766 | 1854 | 7.6 | Solar | 14_77L3 | 2019-09-11 14:44 | 2019-09-12 | 2 | 2 | 0 | 2019-09-17 | 2019-09-20 | 3 | 0 | 3 | [20 empty] | 2019-10-15 | 2019-09-12 11:43 | 2021-06-17 | Yes | EXP | [8 empty] | 2021-01-26 | Connected |  | No
National Grid | BROCKTON | 246170 | 2302 | 10 | Solar | 07_91W48 | 2019-09-12 11:43 | 2019-09-13 | 40 | 40 | 0 | 2019-11-13 | 2019-11-18 | 3 | 0 | 3 | [20 empty] | 2019-11-18 |  | 2020-09-12 | Yes | EXP |  | 2020-02-14 | 2020-03-02 | 17 | 0 | 17 |  |  | 2020-08-11 | Connected |  | No
National Grid | NORWELL | 202211 | 2061 | 233.3 | Solar | 07_96W44 | 2019-09-12 15:35 | 2019-09-13 | 5 | 0 | 5 | 2019-09-23 | 2019-09-26 | 4 | 2 | 2 | 2019-10-30 | 2019-11-25 | 17 | 0 | 17 | [5 empty] | 2019-10-30 | 2019-11-25 | 17 | 0 | 17 | [5 empty] | 2019-12-10 |  | 2021-08-31 |  | EXP |  | 2020-10-13 | 2021-01-06 | 85 | 0 | 85 |  |  | 2021-02-24 | Connected |  | No
National Grid | WOLLASTON | 211163 | 2170 | 262.5 | Natural Gas | 07_11W2 | 2019-09-13 10:33 | 2019-09-16 | 37 | 32 | 5 | 2019-11-06 | 2019-12-06 | 20 | 11 | 9 | 2020-01-03 | 2020-04-16 | 73 | 38 | 35 | [5 empty] | 2020-01-03 | 2020-04-16 | 73 | 38 | 35 | [5 empty] | 2020-04-24 | 2019-09-13 10:36 | 2020-12-07 |  | EXP | [8 empty] | 2020-12-17 | Connected |  | No
National Grid | BEVERLY | 243338 | 1915 | 842 | Solar | 12_12L4 | 2019-09-13 10:36 | 2019-09-16 | 20 | 16 | 4 | [10 empty] | 2019-10-15 | 2019-10-29 | 10 | 0 | 10 | [10 empty] | 2021-06-16 |  | 2023-04-26 | Yes | STD |  | 2023-02-17 | 2023-02-16 | 0 | 0 | 0 | 2023-04-04 | 2023-04-04 | 2023-05-23 | Connected |  | No
National Grid | WHITMAN | 211156 | 2382 | 210 | Natural Gas | 07_797W29 | 2019-09-13 10:38 | 2019-09-16 | 36 | 27 | 9 | 2019-11-06 | 2019-11-25 | 13 | 4 | 9 | 2019-12-30 | 2020-04-01 | 65 | 46 | 19 | [5 empty] | 2019-12-30 | 2020-04-01 | 65 | 46 | 19 | [5 empty] | 2020-04-01 |  | 2020-09-25 |  | EXP | [8 empty] | 2020-09-24 | Connected |  | No
National Grid | PLAINVILLE | 211153 | 2762 | 210 | Natural Gas | 05_3337W1 | 2019-09-13 10:42 | 2019-09-16 | 36 | 27 | 9 | 2019-11-06 | 2019-11-19 | 8 | 0 | 8 | 2019-12-26 | 2020-04-13 | 75 | 50 | 25 | [5 empty] | 2019-12-26 | 2020-04-13 | 75 | 50 | 25 | [9 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORWELL | 211150 | 2061 | 262.5 | Natural Gas | 07_96W44 | 2019-09-13 10:47 | 2019-09-16 | 36 | 27 | 9 | 2019-11-06 | 2019-11-19 | 8 | 0 | 8 | 2020-01-03 | 2020-04-27 | 79 | 46 | 33 | [5 empty] | 2020-01-03 | 2020-04-27 | 79 | 46 | 33 | [5 empty] | 2020-05-05 |  | 2020-09-30 |  | EXP | [8 empty] | 2020-08-26 | Connected |  | No
National Grid | PEMBROKE | 211159 | 2359 | 262.5 | Natural Gas | 07_910W51 | 2019-09-13 10:54 | 2019-09-16 | 36 | 27 | 9 | 2019-11-06 | 2019-11-19 | 8 | 0 | 8 | 2019-12-26 | 2020-04-27 | 84 | 46 | 38 | [5 empty] | 2019-12-26 | 2020-04-27 | 84 | 46 | 38 | [5 empty] | 2020-05-22 | 2019-09-13 12:13 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GARDNER | 247451 | 1440 | 6.24 | Solar | 01_607W5 | 2019-09-13 12:13 | 2019-09-16 | 26 | 23 | 3 | 2019-10-23 | 2019-10-30 | 5 | 0 | 5 | [20 empty] | 2019-11-06 |  | 2021-02-05 | Yes | EXP | [8 empty] | 2021-01-14 | Connected |  | No
National Grid | HARVARD | 253910 | 1451 | 22.8 | Solar | 01_225W1 | 2019-09-13 16:07 | 2019-09-16 | 4 | 4 | 0 | 2019-09-20 | 2019-10-02 | 8 | 5 | 3 | [20 empty] | 2019-10-03 |  | 2021-04-15 |  | EXP | [8 empty] | 2021-01-05 | Connected |  | No
National Grid | EVERETT | 253372 | 2149 | 7.6 | Solar | 12_37W9 | 2019-09-14 10:22 | 2019-09-16 | 1 | 1 | 0 | 2019-09-18 | 2019-09-20 | 2 | 1 | 1 | [20 empty] | 2019-09-23 | 2019-09-17 10:15 | 2021-09-08 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEST BRIDGEWATER | 254306 | 2379 | 20 | Solar | 07_797W19 | 2019-09-17 10:15 | 2019-09-18 | 0 | 0 | 0 | 2019-09-18 | 2019-09-20 | 2 | 0 | 2 | [20 empty] | 2019-09-23 | 2019-09-17 10:18 | 2020-06-22 | Yes | EXP |  | 2019-12-19 | 2020-01-14 | 26 | 0 | 26 |  |  | 2020-04-03 | Connected |  | No
National Grid | BROCKTON | 244132 | 2302 | 999 | Solar | 07_91W48 | 2019-09-17 10:18 | 2019-09-18 | 12 | 8 | 4 | [10 empty] | 2019-10-07 | 2020-01-15 | 68 | 49 | 19 | [10 empty] | 2021-06-17 |  | 2023-02-24 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH BILLERICA | 253690 | 1862 | 10 | Solar | 14_70L3 | 2019-09-17 15:58 | 2019-09-18 | 8 | 2 | 6 | 2019-10-01 | 2019-10-28 | 19 | 17 | 2 | [20 empty] | 2019-10-29 | 2019-09-18 13:23 | 2020-09-17 |  | EXP | [8 empty] | 2020-01-18 | Connected |  | No
National Grid | SOUTHBOROUGH | 254944 | 1772 | 15.2 | Solar | 05_310W6 | 2019-09-18 13:23 | 2019-09-19 | 1 | 1 | 0 | 2019-09-23 | 2019-09-23 | 0 | 0 | 0 | [20 empty] | 2019-09-24 |  | 2020-05-11 | Yes | EXP |  | 2019-11-13 | 2020-01-07 | 55 | 0 | 55 |  |  | 2020-01-14 | Connected |  | No
National Grid | MARLBOROUGH | 255015 | 1752 | 7.6 | Solar | 05_311W2 | 2019-09-18 14:56 | 2019-10-03 | 0 | 0 | 0 | 2019-10-04 | 2019-10-08 | 3 | 1 | 2 | [20 empty] | 2019-10-09 | 2019-09-19 10:23 | 2020-09-18 |  | EXP | [8 empty] | 2020-05-29 | Connected |  | No
National Grid | MILLBURY | 248216 | 1527 | 7.6 | Solar | 01_304W1 | 2019-09-19 10:23 | 2019-09-20 | 10 | 10 | 0 | 2019-10-07 | 2019-10-10 | 3 | 0 | 3 | [20 empty] | 2019-10-10 |  | 2020-06-08 | Yes | EXP |  | 2020-01-16 | 2020-01-31 | 15 | 0 | 15 |  |  | 2020-02-13 | Connected |  | No
National Grid | REHOBOTH | 255162 | 2769 | 15.2 | Solar | 05_3J3 | 2019-09-19 10:40 | 2019-09-20 | 2 | 0 | 2 | 2019-09-25 | 2019-09-26 | 1 | 0 | 1 | [20 empty] | 2019-10-01 |  | 2020-09-24 |  | EXP | [8 empty] | 2020-02-10 | Connected |  | No
National Grid | FALL RIVER | 197438 | 2720 | 1400 | Natural Gas | 05_106W45 | 2019-09-20 11:39 | 2019-09-23 | 33 | 28 | 5 | [10 empty] | 2019-11-08 | 2019-12-09 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | PEMBROKE | 255341 | 2359 | 57.6 | Solar | 07_910W52 | 2019-09-20 12:49 | 2019-09-23 | 7 | 2 | 5 | 2019-10-02 | 2019-11-06 | 24 | 11 | 13 | [20 empty] | 2019-11-19 | 2019-09-21 11:04 | 2020-01-31 |  | EXP | [8 empty] | 2020-01-30 | Connected |  | No
National Grid | BILLERICA | 216947 | 1821 | 10 | Solar | 14_92L1 | 2019-09-21 11:04 | 2019-09-23 | 2 | 2 | 0 | 2019-09-26 | 2019-09-26 | 0 | 0 | 0 | [20 empty] | 2019-09-30 | 2019-09-23 14:14 | 2020-05-28 | Yes | EXP |  | 2019-12-27 | 2019-12-26 | 0 | 0 | 0 |  |  | 2020-01-22 | Connected |  | No
National Grid | QUINCY | 254182 | 2169 | 7.6 | Solar | 07_1W2 | 2019-09-23 14:14 | 2019-09-24 | 5 | 4 | 1 | 2019-10-02 | 2019-10-08 | 4 | 0 | 4 | [20 empty] | 2019-10-09 | 2019-09-23 14:34 | 2020-11-06 | Yes | EXP | [8 empty] | 2020-06-09 | Connected |  | No
National Grid | CHELMSFORD | 255612 | 1824 | 3.8 | Solar | 14_24L1 | 2019-09-23 14:34 | 2019-09-24 | 0 | 0 | 0 | 2019-09-25 | 2019-09-26 | 1 | 0 | 1 | [20 empty] | 2019-09-26 |  | 2020-05-19 | Yes | EXP |  | 2020-01-29 | 2020-02-25 | 27 | 0 | 27 |  |  | 2020-03-31 | Connected |  | No
National Grid | SOUTHBOROUGH | 255931 | 1772 | 10 | Solar | 05_317W4 | 2019-09-23 16:54 | 2019-09-24 | 2 | 2 | 0 | 2019-09-26 | 2019-09-26 | 0 | 0 | 0 | [20 empty] | 2019-09-30 |  | 2020-09-22 |  | EXP | [8 empty] | 2020-02-13 | Connected |  | No
National Grid | SAUGUS | 253386 | 1906 | 262.5 | Natural Gas | 12_25W3 | 2019-09-24 10:07 | 2019-09-25 | 27 | 24 | 3 | 2019-11-05 | 2019-11-18 | 8 | 0 | 8 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ROYALSTON | 252830 | 1368 | 10 | Solar | 09_702W2 | 2019-09-24 16:38 | 2019-09-25 | 3 | 0 | 3 | 2019-10-01 | 2019-10-08 | 5 | 0 | 5 | [20 empty] | 2019-10-14 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BILLERICA | 253359 | 1821 | 7.6 | Solar | 14_18L3 | 2019-09-24 19:39 | 2019-09-25 | 0 | 0 | 0 | 2019-09-26 | 2019-09-26 | 0 | 0 | 0 | [20 empty] | 2019-09-26 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RANDOLPH | 249024 | 2368 | 6 | Solar | 07_97W1 | 2019-09-25 10:42 | 2019-09-26 | 14 | 14 | 0 | 2019-10-17 | 2019-10-29 | 8 | 0 | 8 | [20 empty] | 2019-10-30 | 2019-09-25 15:27 | 2020-09-24 |  | EXP | [8 empty] | 2020-01-13 | Connected |  | No
National Grid | RANDOLPH | 247656 | 2368 | 5 | Solar | 07_97W3 | 2019-09-25 15:27 | 2019-09-26 | 2 | 0 | 2 | 2019-10-01 | 2019-10-28 | 19 | 16 | 3 | [20 empty] | 2019-11-04 |  | 2020-09-25 | Yes | EXP |  | 2020-03-04 | 2020-05-08 | 65 | 0 | 65 |  |  | 2020-06-18 | Connected |  | No
National Grid | ASHLEY FALLS | 249462 | 1222 | 18 | Solar | 09_1108W2 | 2019-09-27 11:23 | 2019-09-30 | 45 | 41 | 4 | 2019-12-06 | 2020-01-08 | 21 | 0 | 21 | [20 empty] | 2020-01-08 |  | 2021-08-15 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WINCHENDON | 256917 | 1475 | 7.6 | Solar | 01_612W3 | 2019-09-27 11:39 | 2019-09-30 | 1 | 0 | 1 | 2019-10-02 | 2019-10-04 | 2 | 0 | 2 | [20 empty] | 2019-10-04 |  |  |  | EXP | [8 empty] | 2019-11-18 | Connected |  | No
National Grid | REVERE | 195873 | 2151 | 10 | Solar | 12_16W4 | 2019-09-27 14:40 | 2019-09-30 | 1 | 0 | 1 | 2019-10-02 | 2019-10-04 | 2 | 0 | 2 | [20 empty] | 2019-10-08 | 2019-09-27 16:17 | 2021-09-15 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 255172 | 1844 | 7.6 | Solar | 14_74L3 | 2019-09-27 16:17 | 2019-09-30 | 2 | 1 | 1 | 2019-10-03 | 2019-10-07 | 2 | 0 | 2 | [20 empty] | 2019-10-07 |  | 2020-09-27 | Yes | EXP |  | 2020-02-12 | 2020-03-12 | 29 | 0 | 29 |  |  | 2020-06-16 | Connected |  | No
National Grid | NORTH ADAMS | 257042 | 1247 | 10 | Solar | 09_1001W1 | 2019-09-27 17:41 | 2019-09-30 | 1 | 0 | 1 | 2019-10-02 | 2019-10-03 | 1 | 0 | 1 | [20 empty] | 2019-10-04 |  | 2020-09-28 |  | EXP | [8 empty] | 2020-02-06 | Connected |  | No
National Grid | BOLTON | 241787 | 1740 | 9.28 | Solar | 05_318W3 | 2019-09-30 09:44 | 2019-10-01 | 4 | 1 | 3 | 2019-10-08 | 2019-10-10 | 2 | 0 | 2 | [20 empty] | 2019-10-17 | 2019-09-30 14:37 | 2020-09-30 |  | EXP | [8 empty] | 2020-04-24 | Connected |  | No
National Grid | NORTHAMPTON | 253402 | 1060 | 10 | Solar | 09_905W1 | 2019-09-30 14:37 | 2019-10-01 | 1 | 1 | 0 | 2019-10-02 | 2019-10-07 | 3 | 0 | 3 | [20 empty] | 2019-10-07 |  | 2020-05-21 | Yes | EXP |  | 2019-12-19 | 2019-12-18 | 0 | 0 | 0 |  |  | 2019-12-19 | Connected |  | No
National Grid | WEYMOUTH | 248006 | 2190 | 7.6 | Solar | 07_99W32 | 2019-10-01 15:37 | 2019-10-02 | 1 | 0 | 1 | 2019-10-04 | 2019-10-08 | 2 | 0 | 2 | [20 empty] | 2019-10-14 | 2019-10-01 16:40 | 2020-10-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | TYNGSBORO | 254655 | 1879 | 10 | Solar | 14_211L2 | 2019-10-01 16:40 | 2019-10-02 | 2 | 2 | 0 | 2019-10-07 | 2019-10-14 | 5 | 0 | 5 | [20 empty] | 2019-10-15 | 2019-10-01 23:34 | 2020-10-01 | Yes | EXP |  | 2020-01-09 | 2020-04-17 | 99 | 0 | 99 |  |  | 2020-05-19 | Connected |  | No
National Grid | LYNN | 252203 | 1904 | 11.4 | Solar | 12_29W1 | 2019-10-01 23:34 | 2019-10-02 | 25 | 25 | 0 | 2019-11-07 | 2019-11-08 | 1 | 0 | 1 | [20 empty] | 2019-11-12 | 2019-10-02 11:37 | 2020-12-07 | Yes | EXP |  | 2020-08-05 | 2020-11-16 | 104 | 5 | 99 |  |  | 2020-11-24 | Connected |  | No
National Grid | REVERE | 256448 | 2151 | 10 | Solar | 12_16W8 | 2019-10-02 11:37 | 2019-10-03 | 2 | 0 | 2 | 2019-10-08 | 2019-10-11 | 3 | 0 | 3 | [20 empty] | 2019-10-22 |  | 2021-10-13 | Yes | EXP |  | 2020-07-02 | 2021-03-29 | 271 | 5 | 266 |  |  | 2021-06-15 | Connected |  | No
National Grid | EVERETT | 254430 | 2149 | 3.8 | Solar | 12_37W10 | 2019-10-02 13:02 | 2019-10-03 | 2 | 0 | 2 | 2019-10-08 | 2019-10-10 | 2 | 0 | 2 | [20 empty] | 2019-10-17 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BEVERLY | 257220 | 1915 | 33.3 | Solar | 12_12L4 | 2019-10-02 15:16 | 2019-10-03 | 9 | 5 | 4 | 2019-10-18 | 2019-10-29 | 7 | 0 | 7 | 2019-11-08 | 2020-08-18 | 185 | 58 | 127 | [5 empty] | 2019-11-08 | 2020-08-18 | 185 | 58 | 127 | [6 empty] | 2019-10-02 16:09 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BELCHERTOWN | 246259 | 1007 | 9.84 | Solar | 09_509L1 | 2019-10-02 16:09 | 2019-10-03 | 3 | 2 | 1 | 2019-10-08 | 2019-10-14 | 4 | 0 | 4 | [20 empty] | 2019-10-14 | 2019-10-03 10:55 | 2020-05-18 | Yes | EXP |  | 2019-12-19 | 2020-01-03 | 15 | 0 | 15 |  |  | 2020-05-15 | Connected |  | No
National Grid | EAST LONGMEADOW | 244368 | 1028 | 4400 | Solar | 09_522L4 | 2019-10-03 10:55 | 2019-10-04 | 13 | 4 | 9 | [10 empty] | 2019-10-24 | 2019-11-22 | 21 | 14 | 7 | [10 empty] | 2022-06-27 |  |  | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | MARLBOROUGH | 249197 | 1752 | 7.6 | Solar | 05_311W3 | 2019-10-03 16:38 | 2019-10-04 | 6 | 5 | 1 | 2019-10-15 | 2019-10-18 | 3 | 0 | 3 | [20 empty] | 2019-10-21 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GRAFTON | 205913 | 1519 | 1380 | Natural Gas | 01_328W1 | 2019-10-04 09:03 | 2019-10-07 | 14 | 9 | 5 | [10 empty] | 2019-10-28 | 2021-04-29 | 376 | 122 | 254 | [11 empty] | 2019-10-04 10:49 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BILLERICA | 197046 | 1821 | 2500 | Natural Gas | 14_92L4 | 2019-10-04 10:49 | 2019-10-07 | 23 | 19 | 4 | [10 empty] | 2019-11-08 | 2019-12-19 | 28 | 13 | 15 | [10 empty] | 2020-05-08 | 2019-10-04 13:13 | 2025-01-02 | Yes | STD |  | 2020-10-28 | 2021-09-23 | 134 | 0 | 134 |  |  |  | Completion Documents |  | No
National Grid | SAUGUS | 256490 | 1906 | 10 | Solar | 12_13J3 | 2019-10-04 13:13 | 2019-10-07 | 9 | 9 | 0 | 2019-10-21 | 2019-10-30 | 7 | 0 | 7 | [20 empty] | 2019-10-31 |  | 2020-10-04 | Yes | EXP |  | 2020-04-08 | 2020-05-15 | 37 | 0 | 37 |  |  | 2020-05-28 | Connected |  | Yes
National Grid | WESTFORD | 258486 | 1886 | 10 | Solar | 14_58L1 | 2019-10-05 19:46 | 2019-10-07 | 4 | 0 | 4 | 2019-10-15 | 2019-10-16 | 1 | 0 | 1 | [20 empty] | 2019-10-22 |  | 2020-10-05 |  | EXP | [8 empty] | 2020-01-24 | Connected |  | No
National Grid | BELLINGHAM | 251916 | 2019 | 7.6 | Solar | 05_344W4 | 2019-10-07 11:14 | 2019-10-08 | 15 | 15 | 0 | 2019-10-31 | 2019-11-08 | 6 | 0 | 6 | [20 empty] | 2019-11-12 |  | 2020-12-07 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | AVON | 252794 | 2322 | 7.6 | Solar | 07_75W5 | 2019-10-07 11:33 | 2019-10-08 | 3 | 0 | 3 | 2019-10-15 | 2019-10-16 | 1 | 0 | 1 | [20 empty] | 2019-10-22 | 2019-10-07 12:56 | 2021-10-14 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | OXFORD | 243055 | 1540 | 10 | Solar | 01_406L3 | 2019-10-07 12:56 | 2019-10-08 | 4 | 4 | 0 | 2019-10-15 | 2019-10-29 | 10 | 0 | 10 | [20 empty] | 2019-10-29 |  | 2020-10-07 | Yes | EXP |  | 2020-07-14 | 2020-08-21 | 38 | 0 | 38 |  |  | 2020-09-04 | Connected |  | No
National Grid | METHUEN | 250742 | 1844 | 7.6 | Solar | 14_63L1 | 2019-10-07 13:45 | 2019-10-08 | 3 | 0 | 3 | 2019-10-15 | 2019-10-30 | 12 | 8 | 4 | [20 empty] | 2019-11-06 | 2019-10-07 14:36 | 2020-10-07 |  | EXP | [8 empty] | 2020-01-31 | Connected |  | No
National Grid | WESTMINSTER | 257644 | 1473 | 30 | Battery Add-On | 01_609W1 | 2019-10-07 14:36 | 2019-11-06 | 0 | 0 | 0 | 2019-11-07 | 2019-11-13 | 4 | 3 | 1 | [20 empty] | 2019-11-14 | 2019-10-07 17:13 | 2020-06-24 | Yes | EXP |  | 2020-01-03 | 2020-01-09 | 6 | 0 | 6 |  |  | 2020-03-04 | Connected |  | No
National Grid | GRANBY | 258757 | 1033 | 7.6 | Solar | 09_527L1 | 2019-10-07 17:13 | 2019-10-08 | 3 | 0 | 3 | 2019-10-15 | 2019-10-16 | 1 | 0 | 1 | [20 empty] | 2019-10-22 |  | 2020-10-07 | Yes | EXP |  | 2020-06-02 | 2020-06-03 | 1 | 0 | 1 |  |  | 2020-07-23 | Connected |  | No
National Grid | LYNN | 255456 | 1905 | 7.6 | Solar | 12_29W3 | 2019-10-07 18:31 | 2019-10-08 | 0 | 0 | 0 | 2019-10-09 | 2019-10-11 | 2 | 0 | 2 | [20 empty] | 2019-10-11 | 2019-10-08 08:02 | 2020-10-09 |  | EXP | [8 empty] | 2020-07-01 | Connected |  | No
National Grid | CHELMSFORD | 257941 | 1824 | 10 | Solar | 14_24L1 | 2019-10-08 08:02 | 2019-10-09 | 3 | 0 | 3 | 2019-10-16 | 2019-10-22 | 4 | 0 | 4 | [20 empty] | 2019-10-27 |  | 2020-10-08 | Yes | EXP |  | 2020-03-10 | 2020-03-11 | 1 | 0 | 1 |  |  | 2020-05-15 | Connected |  | No
National Grid | WORCESTER | 256583 | 1602 | 3.8 | Solar | 01_6W2 | 2019-10-08 11:35 | 2019-10-09 | 0 | 0 | 0 | 2019-10-10 | 2019-10-11 | 1 | 0 | 1 | [20 empty] | 2019-10-14 |  | 2020-10-07 |  | EXP | [8 empty] | 2020-04-17 | Connected |  | No
National Grid | NORTON | 258893 | 2766 | 10 | Solar | 05_8L3 | 2019-10-08 13:22 | 2019-10-09 | 0 | 0 | 0 | 2019-10-10 | 2019-10-10 | 0 | 0 | 0 | [20 empty] | 2019-10-10 |  | 2019-12-13 |  | EXP | [8 empty] | 2019-12-11 | Connected |  | No
National Grid | MILFORD | 259098 | 1757 | 233.2 | Solar | 05_336W1 | 2019-10-09 | 2019-10-15 | 6 | 3 | 3 | 2019-10-24 | 2019-12-30 | 45 | 20 | 25 | 2020-02-14 | 2020-04-22 | 46 | 13 | 33 | [5 empty] | 2020-02-14 | 2020-04-22 | 46 | 13 | 33 | [5 empty] | 2020-06-04 | 2019-10-09 11:53 | 2020-12-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SPENCER | 256903 | 1562 | 10 | Solar | 01_552L1 | 2019-10-09 11:53 | 2019-10-10 | 1 | 1 | 0 | 2019-10-15 | 2019-10-16 | 1 | 0 | 1 | [20 empty] | 2019-10-23 | 2019-10-09 13:45 | 2020-10-09 | Yes | EXP |  | 2020-02-05 | 2020-03-02 | 26 | 0 | 26 |  |  | 2020-04-22 | Connected |  | No
National Grid | LEOMINSTER | 245798 | 1453 | 7.6 | Solar | 01_219W4 | 2019-10-09 13:45 | 2019-10-10 | 2 | 0 | 2 | 2019-10-16 | 2019-10-22 | 4 | 0 | 4 | [20 empty] | 2019-10-27 | 2019-10-10 13:09 | 2020-10-09 | Yes | EXP |  | 2020-09-16 | 2020-09-21 | 5 | 0 | 5 |  |  |  | Withdrawn |  | Yes
National Grid | LEOMINSTER | 240618 | 1453 | 3.8 | Solar | 01_207W1 | 2019-10-10 13:09 | 2019-10-11 | 1 | 0 | 1 | 2019-10-15 | 2019-10-18 | 3 | 0 | 3 | [20 empty] | 2019-10-21 | 2019-10-10 14:33 | 2020-07-07 | Yes | EXP |  | 2020-02-12 | 2020-02-22 | 10 | 0 | 10 |  |  | 2020-04-21 | Connected |  | No
National Grid | NEW SALEM | 255796 | 1355 | 10 | Solar | 09_705W2 | 2019-10-10 14:33 | 2019-10-11 | 1 | 0 | 1 | 2019-10-15 | 2019-10-21 | 4 | 0 | 4 | [20 empty] | 2019-10-22 |  | 2020-10-12 | Yes | EXP |  | 2020-03-07 | 2020-06-16 | 101 | 0 | 101 |  |  | 2020-06-18 | Connected |  | No
National Grid | NEWBURYPORT | 258094 | 1950 | 3.8 | Solar | 14_36L1 | 2019-10-10 15:22 | 2019-10-11 | 5 | 0 | 5 | 2019-10-22 | 2019-10-24 | 2 | 0 | 2 | [20 empty] | 2019-10-29 |  | 2021-10-20 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 251517 | 1844 | 7.6 | Solar | 14_63L1 | 2019-10-10 16:07 | 2019-09-24 | 14 | 12 | 2 | 2019-10-16 | 2019-10-22 | 4 | 0 | 4 | [20 empty] | 2019-10-27 |  | 2020-10-10 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | PLAINVILLE | 259106 | 2762 | 10 | Solar | 05_3451W3 | 2019-10-10 16:37 | 2019-10-11 | 5 | 0 | 5 | 2019-10-22 | 2019-10-23 | 1 | 0 | 1 | [20 empty] | 2019-10-29 | 2019-10-10 17:30 | 2020-10-10 |  | EXP | [8 empty] | 2020-01-28 | Connected |  | No
National Grid | BILLERICA | 256057 | 1821 | 10 | Solar | 14_70L2 | 2019-10-10 17:30 | 2019-10-11 | 1 | 0 | 1 | 2019-10-15 | 2019-10-15 | 0 | 0 | 0 | [20 empty] | 2019-10-15 | 2019-10-11 14:52 | 2020-07-07 | Yes | EXP |  | 2020-01-29 | 2020-02-25 | 27 | 0 | 27 |  |  | 2020-06-08 | Connected |  | No
National Grid | LYNN | 254139 | 1902 | 10 | Solar | 12_29W4 | 2019-10-11 14:52 | 2019-10-15 | 4 | 0 | 4 | 2019-10-22 | 2019-10-23 | 1 | 0 | 1 | [20 empty] | 2019-10-29 |  | 2021-10-19 | Yes | EXP |  | 2020-05-27 | 2020-06-12 | 16 | 0 | 16 |  |  | 2020-10-21 | Connected |  | No
National Grid | MEDFORD | 258934 | 2155 | 3.8 | Solar | 12_37W4 | 2019-10-12 17:34 | 2019-10-15 | 0 | 0 | 0 | 2019-10-15 | 2019-10-15 | 0 | 0 | 0 | [20 empty] | 2019-10-14 | 2019-10-14 11:52 | 2020-11-09 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CLINTON | 256639 | 1510 | 7.6 | Solar | 01_216W5 | 2019-10-14 11:52 | 2019-10-15 | 4 | 0 | 4 | 2019-10-22 | 2019-10-23 | 1 | 0 | 1 | [20 empty] | 2019-10-29 | 2019-10-14 12:31 | 2021-10-21 | Yes | EXP | [8 empty] | 2021-03-31 | Connected |  | No
National Grid | WORCESTER | 257227 | 1604 | 7.6 | Solar | 01_9J360 | 2019-10-14 12:31 | 2019-10-15 | 0 | 0 | 0 | 2019-10-16 | 2019-10-18 | 2 | 0 | 2 | [20 empty] | 2019-10-21 | 2019-10-14 13:08 | 2020-10-14 | Yes | EXP | [8 empty] | 2020-06-30 | Connected |  | No
National Grid | WESTPORT | 257375 | 2790 | 10 | Solar | 05_115W45 | 2019-10-14 13:08 | 2019-10-15 | 5 | 5 | 0 | 2019-10-22 | 2019-10-25 | 3 | 0 | 3 | [20 empty] | 2019-10-28 | 2019-10-14 13:09 | 2020-07-07 |  | EXP |  | 2019-12-20 | 2020-02-19 | 61 | 0 | 61 |  |  | 2020-02-20 | Connected |  | No
National Grid | SALEM | 256763 | 1970 | 5 | Solar | 12_2W1 | 2019-10-14 13:09 | 2019-10-15 | 4 | 0 | 4 | 2019-10-22 | 2019-10-29 | 5 | 0 | 5 | [20 empty] | 2019-11-13 | 2019-10-14 13:55 | 2020-10-14 | Yes | EXP |  | 2020-06-10 | 2020-06-22 | 12 | 0 | 12 |  |  | 2020-07-06 | Connected |  | No
National Grid | BROCKTON | 251819 | 2301 | 7.6 | Solar | 07_98W46 | 2019-10-14 13:55 | 2019-10-15 | 4 | 0 | 4 | 2019-10-22 | 2019-10-24 | 2 | 0 | 2 | [20 empty] | 2019-10-29 |  | 2021-03-29 | Yes | EXP |  | 2021-08-10 | 2021-08-10 | 0 | 0 | 0 |  |  | 2022-02-07 | Connected |  | No
National Grid | RANDOLPH | 229007 | 2368 | 7.6 | Solar | 07_97W1 | 2019-10-15 12:06 | 2019-10-16 | 4 | 0 | 4 | 2019-10-23 | 2019-10-29 | 4 | 0 | 4 | [20 empty] | 2019-12-04 |  | 2021-05-05 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EAST BRIDGEWATER | 260147 | 2339 | 10 | Solar | 07_797W29 | 2019-10-15 15:18 | 2019-10-16 | 0 | 0 | 0 | 2019-10-17 | 2019-10-29 | 8 | 0 | 8 | [20 empty] | 2019-10-30 |  | 2020-10-14 |  | EXP | [8 empty] | 2020-04-13 | Connected |  | No
National Grid | NORTH EASTON | 255776 | 2356 | 24.885 | Solar | 07_92W78 | 2019-10-15 15:27 | 2019-10-16 | 17 | 13 | 4 | 2019-11-12 | 2019-11-18 | 4 | 0 | 4 | [20 empty] | 2019-11-26 |  | 2020-10-15 |  | EXP | [8 empty] | 2020-02-07 | Connected |  | No
National Grid | HAMILTON | 260576 | 1936 | 13.6 | Solar | 12_51T2 | 2019-10-17 | 2019-10-18 | 5 | 3 | 2 | 2019-10-25 | 2019-11-04 | 6 | 0 | 6 | [20 empty] | 2019-11-05 |  | 2020-02-28 |  | EXP | [8 empty] | 2020-02-11 | Connected |  | No
National Grid | WEST NEWBURY | 260717 | 1985 | 20 | Solar | 14_47L1 | 2019-10-17 | 2019-10-21 | 29 | 28 | 1 | 2019-12-03 | 2019-12-26 | 16 | 0 | 16 | [20 empty] | 2020-01-02 | 2019-10-17 11:27 | 2020-10-17 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | AUBURN | 258441 | 1501 | 10 | Solar | 01_26W3 | 2019-10-17 11:27 | 2019-10-18 | 3 | 0 | 3 | 2019-10-24 | 2019-10-30 | 4 | 0 | 4 | [20 empty] | 2019-11-06 | 2019-10-17 11:32 | 2021-03-04 |  | EXP | [8 empty] | 2020-10-21 | Connected |  | No
National Grid | LYNN | 251755 | 1904 | 10 | Solar | 12_24W2 | 2019-10-17 11:32 | 2019-10-18 | 1 | 0 | 1 | 2019-10-22 | 2019-10-24 | 2 | 0 | 2 | [20 empty] | 2019-10-25 |  | 2020-10-17 | Yes | EXP |  | 2020-02-25 | 2020-04-13 | 48 | 0 | 48 |  |  | 2020-04-29 | Connected |  | No
National Grid | LAWRENCE | 256506 | 1843 | 7.6 | Solar | 14_61L3 | 2019-10-17 16:31 | 2019-10-18 | 3 | 0 | 3 | 2019-10-24 | 2019-10-29 | 3 | 0 | 3 | [21 empty] | 2019-10-17 17:19 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 259289 | 1844 | 7.6 | Solar | 14_63L2 | 2019-10-17 17:19 | 2019-10-18 | 2 | 0 | 2 | 2019-10-23 | 2019-10-30 | 5 | 0 | 5 | [20 empty] | 2019-10-31 |  | 2020-07-07 | Yes | EXP |  | 2020-03-13 | 2020-06-01 | 80 | 0 | 80 |  |  | 2020-06-05 | Connected |  | No
National Grid | RANDOLPH | 239082 | 2368 | 10 | Solar | 07_5W3 | 2019-10-17 17:48 | 2019-10-18 | 3 | 0 | 3 | 2019-10-24 | 2019-10-30 | 4 | 0 | 4 | [20 empty] | 2019-11-06 | 2019-10-17 17:54 | 2021-02-03 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 256585 | 2302 | 7.6 | Solar | 07_91W42 | 2019-10-17 17:54 | 2019-10-18 | 2 | 1 | 1 | 2019-10-22 | 2019-10-29 | 5 | 0 | 5 | [20 empty] | 2019-10-30 | 2019-10-17 18:37 | 2021-06-09 | Yes | EXP |  | 2020-01-14 | 2020-01-13 | 0 | 0 | 0 |  |  | 2020-11-13 | Connected |  | No
National Grid | BROCKTON | 257196 | 2302 | 7.6 | Solar | 07_911W57 | 2019-10-17 18:37 | 2019-10-18 | 7 | 5 | 2 | 2019-10-30 | 2019-11-08 | 7 | 0 | 7 | [20 empty] | 2019-11-12 |  | 2020-07-21 | Yes | EXP |  | 2020-01-11 | 2020-02-14 | 34 | 0 | 34 |  |  | 2020-03-02 | Connected |  | No
National Grid | BARRE | 260756 | 1005 | 10 | Solar | 09_604W4 | 2019-10-17 18:37 | 2019-10-18 | 5 | 3 | 2 | 2019-10-28 | 2019-11-04 | 5 | 0 | 5 | [20 empty] | 2019-11-05 |  | 2020-10-16 |  | EXP | [8 empty] | 2020-06-18 | Connected |  | No
National Grid | SCITUATE | 260128 | 2066 | 9.86 | Solar | 07_915W82 | 2019-10-18 13:36 | 2019-10-21 | 5 | 0 | 5 | 2019-10-28 | 2019-10-30 | 2 | 0 | 2 | [20 empty] | 2019-11-06 | 2019-10-18 17:01 | 2020-10-18 |  | EXP | [8 empty] | 2020-04-23 | Connected |  | No
National Grid | GLOUCESTER | 260745 | 1930 | 5.76 | Solar | 12_51T1 | 2019-10-18 17:01 | 2019-11-12 | 1 | 0 | 1 | 2019-11-14 | 2019-11-21 | 5 | 0 | 5 | [20 empty] | 2019-11-22 | 2019-10-18 18:02 | 2020-07-09 | Yes | EXP |  | 2020-02-29 | 2020-02-28 | 0 | 0 | 0 |  |  | 2020-03-04 | Connected |  | No
National Grid | NORTHBOROUGH | 259202 | 1532 | 3.8 | Solar | 05_313W1 | 2019-10-18 18:02 | 2019-10-21 | 1 | 0 | 1 | 2019-10-23 | 2019-10-24 | 1 | 0 | 1 | [20 empty] | 2019-10-25 |  | 2020-10-18 | Yes | EXP |  | 2020-02-12 | 2020-04-02 | 50 | 0 | 50 |  |  | 2020-06-03 | Connected |  | No
National Grid | ANDOVER | 256188 | 1810 | 24 | Solar | 14_8L1 | 2019-10-20 21:41 | 2019-10-21 | 99 | 95 | 4 | [26 empty] | 2019-10-20 21:55 | 2020-10-20 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 260249 | 1844 | 9.86 | Solar | 14_75L3 | 2019-10-20 21:55 | 2019-10-21 | 14 | 9 | 5 | 2019-11-12 | 2019-11-21 | 7 | 0 | 7 | [20 empty] | 2019-12-04 |  | 2020-10-20 | Yes | EXP |  | 2020-04-21 | 2020-05-13 | 22 | 0 | 22 |  |  | 2020-08-25 | Connected |  | No
National Grid | SAUGUS | 261261 | 1906 | 7.6 | Solar | 12_23W2 | 2019-10-21 15:54 | 2019-10-22 | 3 | 2 | 1 | 2019-10-25 | 2019-11-06 | 8 | 2 | 6 | [20 empty] | 2019-11-06 |  | 2020-11-07 |  | EXP | [8 empty] | 2020-01-31 | Connected |  | No
National Grid | NORTHBRIDGE | 257134 | 1534 | 2930 | Battery Add-On | 05_320W3 | 2019-10-21 17:16 | 2019-10-22 | 13 | 9 | 4 | [10 empty] | 2019-11-08 | 2020-01-10 | 42 | 19 | 23 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BILLERICA | 259369 | 1821 | 3.8 | Solar | 14_70L8 | 2019-10-22 12:55 | 2019-10-23 | 0 | 0 | 0 | 2019-10-24 | 2019-10-29 | 3 | 0 | 3 | [20 empty] | 2019-10-31 | 2019-10-22 15:23 | 2020-10-21 |  | EXP | [8 empty] | 2020-02-04 | Connected |  | No
National Grid | LAWRENCE | 261505 | 1841 | 21.52 | Solar | 14_74L3 | 2019-10-22 15:23 | 2019-10-23 | 3 | 0 | 3 | 2019-10-28 | 2019-11-05 | 6 | 0 | 6 | [20 empty] | 2019-11-08 |  | 2020-11-15 | Yes | EXP |  | 2020-04-25 | 2020-07-06 | 72 | 0 | 72 |  |  | 2021-02-08 | Connected |  | No
National Grid | MILFORD | 261005 | 1757 | 7.6 | Solar | 05_335W5 | 2019-10-23 11:14 | 2019-10-24 | 0 | 0 | 0 | 2019-10-24 | 2019-10-29 | 3 | 0 | 3 | [20 empty] | 2019-10-31 |  | 2020-10-22 |  | EXP | [8 empty] | 2020-05-12 | Connected |  | No
National Grid | LAWRENCE | 240228 | 1843 | 10 | Solar | 14_61L3 | 2019-10-23 11:31 | 2019-10-24 | 4 | 0 | 4 | 2019-10-31 | 2019-11-08 | 6 | 0 | 6 | [20 empty] | 2019-11-14 | 2019-10-23 12:18 | 2020-10-30 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | PEMBROKE | 260959 | 2359 | 19.84 | Solar | 07_95W3 | 2019-10-23 12:18 | 2019-10-24 | 0 | 0 | 0 | 2019-10-24 | 2019-10-25 | 1 | 0 | 1 | [20 empty] | 2019-10-28 | 2019-10-24 09:46 | 2020-07-08 | Yes | EXP |  | 2020-01-31 | 2020-02-19 | 19 | 0 | 19 |  |  | 2020-06-15 | Connected |  | No
National Grid | METHUEN | 258970 | 1844 | 10 | Solar | 14_5J44 | 2019-10-24 09:46 | 2019-10-25 | 0 | 0 | 0 | 2019-10-28 | 2019-11-06 | 7 | 0 | 7 | [20 empty] | 2019-11-06 | 2019-10-25 11:02 | 2020-10-24 | Yes | EXP |  | 2020-02-27 | 2020-03-03 | 5 | 0 | 5 |  |  | 2020-03-04 | Connected |  | No
National Grid | WORCESTER | 261638 | 1605 | 10 | Solar | 01_24W1 | 2019-10-25 11:02 | 2019-10-28 | 0 | 0 | 0 | 2019-10-29 | 2019-11-05 | 5 | 0 | 5 | [20 empty] | 2019-11-05 |  | 2020-10-25 | Yes | EXP | [8 empty] | 2020-08-17 | Connected |  | No
National Grid | NEWBURYPORT | 259475 | 1950 | 53 | Solar | 14_36L2 | 2019-10-25 11:03 | 2019-10-28 | 15 | 13 | 2 | 2019-11-19 | 2020-03-13 | 51 | 28 | 23 | [20 empty] | 2020-03-13 |  |  |  | EXP | [8 empty] | 2020-09-29 | Connected |  | No
National Grid | MEDFORD | 243069 | 2155 | 7.6 | Solar | 12_37W4 | 2019-10-25 18:26 | 2019-10-28 | 2 | 0 | 2 | 2019-10-31 | 2019-11-05 | 3 | 0 | 3 | [20 empty] | 2019-11-08 | 2019-10-28 12:25 | 2020-10-30 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | STURBRIDGE | 260850 | 1566 | 10 | Solar | 01_413L2 | 2019-10-28 12:25 | 2019-10-29 | 3 | 3 | 0 | 2019-11-01 | 2019-11-08 | 5 | 0 | 5 | [20 empty] | 2019-11-12 |  | 2020-10-28 | Yes | EXP |  | 2020-02-19 | 2020-03-03 | 13 | 0 | 13 |  |  | 2020-03-06 | Connected |  | No
National Grid | FOXBOROUGH | 259189 | 2035 | 12 | Solar | 05_3422W3 | 2019-10-28 12:39 | 2019-10-29 | 4 | 0 | 4 | 2019-11-05 | 2019-11-08 | 3 | 0 | 3 | [20 empty] | 2019-11-14 |  | 2020-10-28 |  | EXP | [8 empty] | 2020-08-11 | Connected |  | No
National Grid | BEVERLY | 262490 | 1915 | 10 | Solar | 12_12J5 | 2019-10-28 15:15 | 2019-10-29 | 0 | 0 | 0 | 2019-10-30 | 2019-10-30 | 0 | 0 | 0 | [20 empty] | 2019-10-31 |  | 2020-10-27 |  | EXP | [8 empty] | 2020-01-23 | Connected |  | No
National Grid | MARLBOROUGH | 225197 | 1752 | 10 | Solar | 05_310W5 | 2019-10-28 16:36 | 2019-10-29 | 118 | 101 | 17 | [26 empty] | 2019-10-29 11:09 | 2020-10-28 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTHAMPTON | 260373 | 1062 | 8.41 | Solar | 09_909W4 | 2019-10-29 11:09 | 2019-10-30 | 4 | 0 | 4 | 2019-11-06 | 2019-11-08 | 2 | 0 | 2 | [20 empty] | 2019-11-14 |  | 2020-10-29 | Yes | EXP |  | 2020-05-16 | 2020-05-15 | 0 | 0 | 0 |  |  | 2020-05-21 | Connected |  | No
National Grid | SOMERSET | 259604 | 2725 | 7.6 | Solar | 05_11W84 | 2019-10-29 11:39 | 2019-10-30 | 0 | 0 | 0 | 2019-10-31 | 2019-11-08 | 6 | 0 | 6 | [20 empty] | 2019-11-12 | 2019-10-29 12:19 | 2020-10-29 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LOWELL | 261453 | 1854 | 7.6 | Solar | 14_77L3 | 2019-10-29 12:19 | 2019-10-30 | 4 | 0 | 4 | 2019-11-06 | 2019-11-07 | 1 | 0 | 1 | [20 empty] | 2019-11-13 |  | 2020-10-29 | Yes | EXP |  | 2020-03-04 | 2020-04-08 | 35 | 0 | 35 |  |  | 2020-07-30 | Connected |  | No
National Grid | HARVARD | 262760 | 1451 | 19.2 | Solar | 01_225W1 | 2019-10-29 16:26 | 2019-10-30 | 3 | 3 | 0 | 2019-11-05 | 2019-11-13 | 5 | 0 | 5 | [20 empty] | 2019-11-13 | 2019-10-29 16:48 | 2020-10-29 |  | EXP | [8 empty] | 2020-06-23 | Connected |  | No
National Grid | BEVERLY | 262763 | 1915 | 10 | Solar | 12_12L2 | 2019-10-29 16:48 | 2019-10-30 | 4 | 0 | 4 | 2019-11-06 | 2019-11-08 | 2 | 0 | 2 | [20 empty] | 2019-11-14 |  | 2021-10-21 | Yes | EXP | [8 empty] | 2020-10-20 | Connected |  | No
National Grid | ROWE | 262657 | 1367 | 25 | Solar | 09_1019W1 | 2019-10-30 14:20 | 2019-10-31 | 6 | 6 | 0 | 2019-11-08 | 2019-11-19 | 6 | 0 | 6 | [20 empty] | 2019-11-19 |  | 2020-10-29 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | ROWE | 262661 | 1367 | 25 | Solar | 09_1019W1 | 2019-10-30 14:20 | 2019-10-31 | 6 | 6 | 0 | 2019-11-08 | 2020-01-24 | 50 | 33 | 17 | [20 empty] | 2020-01-27 |  | 2020-10-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTFORD | 263166 | 1886 | 10 | Solar | 14_57L3 | 2019-10-31 11:16 | 2019-11-01 | 1 | 1 | 0 | 2019-11-04 | 2019-11-05 | 1 | 0 | 1 | [20 empty] | 2019-11-05 |  | 2020-02-07 |  | EXP | [8 empty] | 2020-01-24 | Connected |  | No
National Grid | COHASSET | 263280 | 2025 | 5 | Other | 07_96W41 | 2019-10-31 17:56 | 2019-11-01 | 44 | 39 | 5 | 2020-01-22 | 2020-02-10 | 13 | 0 | 13 | [20 empty] | 2020-02-18 | 2019-11-01 12:08 | 2020-10-31 |  | EXP | [8 empty] | 2020-07-23 | Connected |  | Yes
National Grid | WORCESTER | 260892 | 1604 | 6 | Solar | 01_27W1 | 2019-11-01 12:08 | 2019-11-04 | 40 | 38 | 2 | 2020-01-03 | 2020-01-24 | 14 | 0 | 14 | [20 empty] | 2020-01-24 |  | 2021-09-03 | Yes | EXP |  | 2021-05-06 | 2021-06-10 | 35 | 0 | 35 |  |  | 2021-08-10 | Connected |  | No
National Grid | QUINCY | 256122 | 2169 | 6 | Solar | 07_3W2 | 2019-11-01 14:31 | 2019-11-04 | 1 | 0 | 1 | 2019-11-06 | 2019-11-19 | 9 | 5 | 4 | [20 empty] | 2019-11-19 |  | 2020-04-10 |  | EXP | [8 empty] | 2020-03-27 | Connected |  | No
National Grid | DRACUT | 263447 | 1826 | 10 | Solar | 14_75L3 | 2019-11-01 15:56 | 2019-11-04 | 2 | 0 | 2 | 2019-11-07 | 2019-11-06 | 0 | 0 | 0 | [20 empty] | 2019-11-08 | 2019-11-04 13:37 | 2020-11-01 |  | EXP | [8 empty] | 2020-02-08 | Connected |  | No
National Grid | MILFORD | 212698 | 1757 | 7.6 | Solar | 05_335W3 | 2019-11-04 13:37 | 2019-11-05 | 13 | 13 | 0 | 2019-11-26 | 2019-12-19 | 16 | 0 | 16 | [20 empty] | 2019-12-31 | 2019-11-04 14:42 | 2021-02-18 | Yes | EXP |  | 2020-05-16 | 2020-06-02 | 17 | 0 | 17 |  |  | 2020-10-20 | Connected |  | No
National Grid | BELCHERTOWN | 261448 | 1007 | 7.6 | Solar | 09_509L2 | 2019-11-04 14:42 | 2019-11-05 | 0 | 0 | 0 | 2019-11-06 | 2019-11-13 | 4 | 0 | 4 | [20 empty] | 2019-11-13 |  | 2020-11-04 | Yes | EXP |  | 2020-01-25 | 2020-02-04 | 9 | 0 | 9 |  |  | 2020-05-19 | Connected |  | No
National Grid | WESTFORD | 263958 | 1886 | 10 | Solar | 14_58L3 | 2019-11-05 13:44 | 2019-11-06 | 0 | 0 | 0 | 2019-11-06 | 2019-11-08 | 2 | 0 | 2 | [20 empty] | 2019-11-12 | 2019-11-05 15:49 | 2020-01-30 |  | EXP | [8 empty] | 2020-01-28 | Connected |  | No
National Grid | LAWRENCE | 261851 | 1841 | 7.6 | Solar | 14_74L6 | 2019-11-05 15:49 | 2019-11-06 | 40 | 33 | 7 | 2020-01-09 | 2020-01-24 | 10 | 0 | 10 | [20 empty] | 2020-01-24 |  | 2021-01-15 | Yes | EXP |  | 2020-07-07 | 2020-07-10 | 3 | 0 | 3 |  |  | 2021-01-11 | Connected |  | No
National Grid | DRACUT | 264017 | 1826 | 19.08 | Solar | 14_78L3 | 2019-11-05 16:46 | 2019-11-06 | 2 | 0 | 2 | 2019-11-12 | 2019-11-22 | 8 | 0 | 8 | [20 empty] | 2019-12-04 | 2019-11-07 10:17 | 2020-11-05 |  | EXP | [8 empty] | 2020-02-21 | Connected |  | No
National Grid | WORCESTER | 256144 | 1603 | 10 | Solar | 01_7J387 | 2019-11-07 10:17 | 2019-11-08 | 0 | 0 | 0 | 2019-11-08 | 2019-11-13 | 2 | 0 | 2 | [20 empty] | 2019-11-14 |  | 2020-07-08 | Yes | EXP |  | 2020-02-14 | 2020-03-03 | 18 | 0 | 18 |  |  | 2020-05-05 | Connected |  | No
National Grid | EAST LONGMEADOW | 250508 | 1028 | 7.6 | Solar | 09_508L1 | 2019-11-07 16:44 | 2019-11-08 | 2 | 1 | 1 | 2019-11-14 | 2019-11-22 | 6 | 0 | 6 | [20 empty] | 2019-12-04 | 2019-11-08 11:52 | 2020-11-07 |  | EXP | [8 empty] | 2020-03-13 | Connected |  | No
National Grid | UXBRIDGE | 247851 | 1569 | 4966.6 | Solar | 05_321W1 | 2019-11-08 11:52 | 2019-11-12 | 9 | 6 | 3 | [10 empty] | 2019-11-25 | 2020-01-23 | 39 | 15 | 24 | [10 empty] | 2020-08-24 |  | 2024-01-03 | Yes | STD |  | 2023-02-09 | 2023-07-18 | 160 | 0 | 160 |  |  | 2023-12-18 | Connected |  | No
National Grid | NORWELL | 256924 | 2061 | 24 | Solar | 07_96W40 | 2019-11-08 17:47 | 2019-11-12 | 2 | 1 | 1 | 2019-11-15 | 2020-01-27 | 47 | 31 | 16 | [20 empty] | 2020-02-11 |  | 2020-11-08 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORWELL | 258675 | 2061 | 24 | Solar | 07_96W40 | 2019-11-08 17:49 | 2019-11-12 | 2 | 1 | 1 | 2019-11-15 | 2020-01-27 | 47 | 34 | 13 | [20 empty] | 2020-02-11 | 2019-11-11 12:54 | 2020-11-08 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LEOMINSTER | 264869 | 1453 | 20 | Solar | 01_225W4 | 2019-11-11 12:54 | 2019-11-12 | 1 | 0 | 1 | 2019-11-14 | 2019-11-19 | 3 | 0 | 3 | [20 empty] | 2019-11-26 |  | 2021-03-16 | Yes | EXP |  | 2020-06-24 | 2020-06-24 | 0 | 0 | 0 |  |  | 2020-08-14 | Connected |  | No
National Grid | REVERE | 263607 | 2151 | 10 | Solar | 12_16W4 | 2019-11-12 12:24 | 2019-11-13 | 6 | 6 | 0 | 2019-11-21 | 2019-11-21 | 0 | 0 | 0 | [20 empty] | 2019-11-22 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EGREMONT | 265046 | 1252 | 10 | Solar | 09_1109W3 | 2019-11-12 13:39 | 2019-11-13 | 9 | 6 | 3 | 2019-11-27 | 2019-12-19 | 15 | 0 | 15 | [20 empty] | 2019-12-20 | 2019-11-12 15:54 | 2020-11-12 |  | EXP | [8 empty] | 2020-04-09 | Connected |  | No
National Grid | LOWELL | 260377 | 1851 | 5 | Solar | 14_16L3 | 2019-11-12 15:54 | 2019-11-13 | 3 | 0 | 3 | 2019-11-19 | 2019-11-22 | 3 | 0 | 3 | [20 empty] | 2019-12-04 | 2019-11-13 07:05 | 2021-03-03 | Yes | EXP | [8 empty] | 2021-01-22 | Connected |  | No
National Grid | REVERE | 257961 | 2151 | 5 | Solar | 12_16W4 | 2019-11-13 07:05 | 2019-11-14 | 6 | 6 | 0 | 2019-11-21 | 2019-12-18 | 18 | 0 | 18 | [20 empty] | 2019-12-18 |  | 2020-11-13 | Yes | EXP |  | 2020-03-25 | 2020-04-07 | 13 | 0 | 13 |  |  | 2020-05-22 | Connected |  | No
National Grid | HANOVER | 265059 | 2339 | 400 | Solar | 07_96W44 | 2019-11-13 16:27 | 2019-11-14 | 5 | 3 | 2 | 2020-04-08 | 2020-04-07 | 0 | 0 | 0 | 2020-04-08 | 2020-06-23 | 52 | 0 | 52 | [5 empty] | 2020-04-08 | 2020-06-23 | 52 | 0 | 52 | [5 empty] | 2020-07-09 | 2019-11-14 09:24 | 2021-06-18 |  | EXP |  | 2020-11-10 | 2021-06-11 | 213 | 0 | 213 |  |  | 2021-06-22 | Connected |  | No
National Grid | GRAFTON | 265476 | 1519 | 21 | Solar | 01_304W1 | 2019-11-14 09:24 | 2019-11-15 | 3 | 0 | 3 | 2019-11-21 | 2020-01-08 | 32 | 16 | 16 | [20 empty] | 2020-01-17 |  | 2020-11-14 | Yes | EXP | [8 empty] | 2020-08-20 | Connected |  | No
National Grid | LAWRENCE | 219512 | 1841 | 10 | Solar | 14_43L4 | 2019-11-14 17:16 | 2019-11-15 | 3 | 2 | 1 | 2019-11-21 | 2019-11-22 | 1 | 0 | 1 | [20 empty] | 2019-11-25 | 2019-11-14 17:27 | 2021-07-21 |  | EXP | [8 empty] | 2021-02-11 | Connected |  | No
National Grid | HALIFAX | 264571 | 2338 | 7.6 | Solar | 07_912W75 | 2019-11-14 17:27 | 2019-11-15 | 17 | 16 | 1 | 2019-12-11 | 2020-01-10 | 20 | 0 | 20 | [20 empty] | 2020-01-13 |  | 2020-11-14 | Yes | EXP |  | 2020-07-29 | 2020-08-15 | 17 | 0 | 17 |  |  | 2020-10-07 | Connected |  | No
National Grid | NANTUCKET | 265329 | 2554 | 15.2 | Solar | 04_101L2 | 2019-11-15 14:42 | 2019-11-18 | 0 | 0 | 0 | 2019-11-19 | 2019-12-16 | 18 | 0 | 18 | [20 empty] | 2019-12-16 |  | 2020-11-16 |  | EXP | [8 empty] | 2020-06-17 | Connected |  | No
National Grid | BRIDGEWATER | 265791 | 2324 | 10 | Solar | 07_912W74 | 2019-11-15 15:14 | 2019-11-18 | 2 | 2 | 0 | 2019-11-20 | 2019-11-22 | 2 | 0 | 2 | [20 empty] | 2019-11-25 | 2019-11-15 15:32 | 2020-11-16 |  | EXP | [8 empty] | 2020-04-10 | Connected |  | No
National Grid | SWANSEA | 263922 | 2777 | 8.7 | Solar | 05_11W82 | 2019-11-15 15:32 | 2019-11-18 | 0 | 0 | 0 | 2019-11-19 | 2019-12-02 | 8 | 0 | 8 | [20 empty] | 2019-12-02 | 2019-11-16 13:02 | 2020-07-22 | Yes | EXP |  | 2020-01-10 | 2020-02-26 | 46 | 0 | 46 |  |  | 2020-02-27 | Connected |  | No
National Grid | ATHOL | 265840 | 1331 | 15.2 | Solar | 09_702W2 | 2019-11-16 13:02 | 2019-11-18 | 3 | 0 | 3 | 2019-11-22 | 2019-12-20 | 19 | 0 | 19 | [20 empty] | 2019-12-20 |  | 2022-08-31 | Yes | EXP |  | 2020-07-31 | 2020-08-17 | 17 | 0 | 17 |  |  | 2022-08-18 | Connected |  | No
National Grid | WESTFORD | 232316 | 1886 | 249 | Solar | 14_57L3 | 2019-11-19 | 2019-12-11 | 19 | 15 | 4 | 2020-04-02 | 2020-04-27 | 16 | 0 | 16 | 2020-05-21 | 2020-10-28 | 100 | 3 | 97 | [5 empty] | 2020-05-21 | 2020-10-28 | 100 | 3 | 97 | [5 empty] | 2020-10-13 | 2019-11-19 11:43 | 2021-12-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | FRANKLIN | 252380 | 2038 | 2999 | Solar | 05_344W2 | 2019-11-19 11:43 | 2019-11-20 | 21 | 20 | 1 | [10 empty] | 2019-12-20 | 2020-02-24 | 43 | 17 | 26 | [10 empty] | 2021-04-30 | 2019-11-19 16:35 | 2024-07-05 | Yes | STD | [9 empty] | Construction |  | No
National Grid | BLACKSTONE | 263498 | 1504 | 7.6 | Solar | 05_108W60 | 2019-11-19 16:35 | 2019-11-20 | 0 | 0 | 0 | 2019-11-21 | 2019-12-02 | 6 | 0 | 6 | [20 empty] | 2019-12-02 |  | 2020-11-19 | Yes | EXP |  | 2020-06-04 | 2020-07-07 | 33 | 0 | 33 |  |  | 2020-07-22 | Connected |  | No
National Grid | LEICESTER | 255873 | 1524 | 5000 | Solar | 01_21W2 | 2019-11-20 | 2019-11-22 | 5 | 2 | 3 | [10 empty] | 2019-12-03 | 2019-12-09 | 4 | 0 | 4 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | GARDNER | 261017 | 1440 | 10 | Solar | 01_607W1 | 2019-11-20 10:27 | 2019-11-21 | 3 | 0 | 3 | 2019-11-27 | 2019-12-20 | 16 | 0 | 16 | [20 empty] | 2019-12-20 | 2019-11-20 10:40 | 2020-11-20 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MILLBURY | 265736 | 1527 | 10 | Solar | 01_304W3 | 2019-11-20 10:40 | 2019-11-21 | 0 | 0 | 0 | 2019-11-22 | 2019-11-22 | 0 | 0 | 0 | [20 empty] | 2019-11-25 |  | 2020-07-22 | Yes | EXP |  | 2020-03-28 | 2020-03-30 | 2 | 0 | 2 |  |  | 2020-04-06 | Connected |  | No
National Grid | LEOMINSTER | 246795 | 1453 | 10 | Solar | 01_225W3 | 2019-11-20 10:45 | 2019-11-21 | 76 | 76 | 0 | 2020-03-13 | 2020-06-18 | 68 | 46 | 22 | [20 empty] | 2020-06-19 | 2019-11-21 10:05 | 2020-11-20 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SUTTON | 266587 | 1590 | 15.2 | Solar | 05_320W5 | 2019-11-21 10:05 | 2019-11-22 | 0 | 0 | 0 | 2019-11-25 | 2020-02-04 | 48 | 25 | 23 | [20 empty] | 2020-02-05 |  | 2020-11-21 | Yes | EXP |  | 2020-04-01 | 2020-04-07 | 6 | 0 | 6 |  |  | 2020-07-17 | Connected |  | No
National Grid | RANDOLPH | 265635 | 2368 | 4.55 | Solar | 07_97W2 | 2019-11-21 12:03 | 2019-11-22 | 83 | 80 | 3 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEICESTER | 255867 | 1524 | 2000 | Solar | 01_2236W2 | 2019-11-21 14:21 | 2019-11-22 | 4 | 2 | 2 | [10 empty] | 2019-11-27 | 2019-12-09 | 7 | 0 | 7 | [11 empty] | 2019-11-21 14:30 |  |  | STD | [9 empty] | Group Study |  | No
National Grid | NORWELL | 262162 | 2061 | 100 | Solar | 07_96W40 | 2019-11-21 14:30 | 2019-11-22 | 11 | 5 | 6 | 2019-12-10 | 2020-01-27 | 32 | 9 | 23 | [20 empty] | 2020-02-11 |  | 2022-08-25 | Yes | EXP |  | 2020-07-21 | 2022-07-26 | 736 | 348 | 388 |  |  |  | Withdrawn |  | No
National Grid | NORWELL | 262160 | 2061 | 24 | Solar | 07_96W40 | 2019-11-21 14:32 | 2019-11-22 | 11 | 5 | 6 | 2019-12-10 | 2020-01-27 | 32 | 9 | 23 | [20 empty] | 2020-02-11 |  | 2020-11-21 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTH GRAFTON | 266020 | 1536 | 7.6 | Solar | 01_304W1 | 2019-11-21 15:54 | 2019-11-22 | 12 | 12 | 0 | 2019-12-11 | 2019-12-26 | 11 | 0 | 11 | [20 empty] | 2020-01-02 |  | 2020-12-21 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ANDOVER | 266776 | 1810 | 6.67 | Solar | 14_75L2 | 2019-11-22 09:36 | 2019-11-25 | 0 | 0 | 0 | 2019-11-26 | 2019-12-19 | 16 | 0 | 16 | [20 empty] | 2019-12-20 |  | 2020-11-25 |  | EXP | [8 empty] | 2020-02-06 | Connected |  | No
National Grid | FRANKLIN | 266941 | 2038 | 10 | Solar | 05_341W1 | 2019-11-22 17:32 | 2019-11-25 | 45 | 44 | 1 | 2020-01-29 | 2020-02-05 | 5 | 0 | 5 | [20 empty] | 2020-02-05 |  | 2020-11-25 |  | EXP | [8 empty] | 2020-06-15 | Connected |  | No
National Grid | FLORENCE | 265140 | 1062 | 20 | Solar | 09_909W4 | 2019-11-24 19:06 | 2019-11-25 | 5 | 0 | 5 | 2019-12-04 | 2019-12-26 | 15 | 0 | 15 | [20 empty] | 2020-01-10 |  | 2020-11-24 |  | EXP | [8 empty] | 2020-02-06 | Connected |  | No
National Grid | WESTFORD | 264770 | 1886 | 9.86 | Solar | 14_57L4 | 2019-11-25 10:14 | 2019-11-26 | 5 | 0 | 5 | 2019-12-05 | 2019-12-20 | 11 | 0 | 11 | [20 empty] | 2020-01-29 | 2019-11-25 13:22 | 2020-11-25 |  | EXP | [8 empty] | 2020-09-05 | Connected |  | No
National Grid | RANDOLPH | 267109 | 2368 | 7.6 | Solar | 07_5W3 | 2019-11-25 13:22 | 2019-11-26 | 4 | 4 | 0 | 2019-12-03 | 2019-12-23 | 14 | 0 | 14 | [20 empty] | 2019-12-27 |  | 2020-11-25 | Yes | EXP |  | 2020-02-07 | 2020-02-06 | 0 | 0 | 0 |  |  | 2020-03-10 | Connected |  | No
National Grid | TOPSFIELD | 267108 | 1983 | 17.6 | Battery Add-On | 14_33L1 | 2019-11-25 13:57 | 2019-11-26 | 23 | 17 | 6 | 2020-01-03 | 2020-01-24 | 14 | 0 | 14 | [20 empty] | 2020-01-29 | 2019-11-25 14:23 | 2021-04-19 |  | EXP | [8 empty] | 2020-04-22 | Connected |  | No
National Grid | ALFORD | 265790 | 1230 | 9.8 | Solar | 09_1109W3 | 2019-11-25 14:23 | 2019-11-26 | 4 | 0 | 4 | 2019-12-04 | 2019-12-23 | 13 | 0 | 13 | [20 empty] | 2020-01-10 | 2019-11-25 14:37 | 2020-11-25 | Yes | EXP |  | 2020-05-01 | 2020-06-26 | 56 | 0 | 56 |  |  | 2020-07-02 | Connected |  | No
National Grid | WEST NEWBURY | 263544 | 1985 | 15 | Solar | 14_47L1 | 2019-11-25 14:37 | 2019-11-26 | 5 | 0 | 5 | 2019-12-05 | 2019-12-23 | 12 | 0 | 12 | [20 empty] | 2020-01-29 | 2019-11-26 13:19 | 2020-11-25 | Yes | EXP | [8 empty] | 2020-10-21 | Connected |  | No
National Grid | BROCKTON | 266977 | 2301 | 7.6 | Solar | 07_94W40 | 2019-11-26 13:19 | 2019-11-27 | 2 | 0 | 2 | 2019-12-03 | 2019-12-20 | 13 | 0 | 13 | [20 empty] | 2019-12-30 | 2019-11-27 | 2020-12-29 | Yes | EXP |  | 2020-07-21 | 2020-08-12 | 22 | 0 | 22 |  |  | 2020-12-19 | Connected |  | No
National Grid | BILLERICA | 254107 | 1821 | 100 | Solar | 14_18L3 | 2019-11-27 | 2019-11-29 | 9 | 0 | 9 | 2019-12-16 | 2020-01-22 | 25 | 1 | 24 | [20 empty] | 2020-01-24 |  |  | Yes | EXP |  | 2020-08-04 | 2020-08-27 | 23 | 0 | 23 |  |  | 2020-09-21 | Connected |  | No
National Grid | MEDFORD | 268101 | 2155 | 7.6 | Solar | 12_17J3 | 2019-12-03 15:17 | 2019-12-04 | 5 | 4 | 1 | 2019-12-11 | 2020-01-03 | 15 | 0 | 15 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LYNN | 265737 | 1902 | 7.6 | Solar | 12_29W5 | 2019-12-04 15:40 | 2019-12-05 | 3 | 0 | 3 | 2019-12-11 | 2019-12-23 | 8 | 0 | 8 | [20 empty] | 2020-01-03 | 2019-12-04 16:26 | 2021-10-14 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SAUGUS | 267636 | 1906 | 3.8 | Solar | 12_23W2 | 2019-12-04 16:26 | 2019-12-05 | 3 | 0 | 3 | 2019-12-11 | 2019-12-23 | 8 | 0 | 8 | [20 empty] | 2020-01-29 |  | 2021-06-03 | Yes | EXP |  | 2020-11-04 | 2021-01-19 | 76 | 0 | 76 |  |  | 2021-04-14 | Connected |  | No
National Grid | WORCESTER | 265671 | 1602 | 7.6 | Solar | 01_6W2 | 2019-12-04 16:55 | 2019-12-05 | 9 | 9 | 0 | 2019-12-18 | 2019-12-22 | 3 | 0 | 3 | [20 empty] | 2019-12-30 | 2019-12-05 | 2020-05-25 |  | EXP | [8 empty] | 2020-04-29 | Connected |  | No
National Grid | BEVERLY | 268435 | 1915 | 175 | Solar | 12_12J7 | 2019-12-05 | 2019-12-11 | 0 | 0 | 0 | [5 empty] | 2019-12-11 | 2020-01-03 | 15 | 0 | 15 | 2019-12-11 | 2019-12-10 | 0 | 0 | 0 | 2019-12-11 | 2020-01-03 | 15 | 0 | 15 | [5 empty] | 2020-05-18 | 2019-12-05 08:37 | 2023-01-31 | Yes | STD | [8 empty] | 2023-05-05 | Connected |  | No
National Grid | HANOVER | 268394 | 2339 | 11.4 | Solar | 07_95W1 | 2019-12-05 08:37 | 2019-12-06 | 0 | 0 | 0 | 2019-12-06 | 2020-01-08 | 21 | 0 | 21 | [20 empty] | 2020-01-08 | 2019-12-05 12:05 | 2020-12-05 | Yes | EXP |  | 2020-04-14 | 2020-05-20 | 36 | 0 | 36 |  |  | 2020-08-11 | Connected |  | No
National Grid | SALEM | 263264 | 1970 | 6 | Solar | 12_2W1 | 2019-12-05 12:05 | 2019-12-06 | 6 | 0 | 6 | 2019-12-16 | 2019-12-23 | 5 | 0 | 5 | [20 empty] | 2020-01-29 |  | 2020-12-05 | Yes | EXP | [8 empty] | 2020-08-13 | Connected |  | No
National Grid | BILLERICA | 268241 | 1821 | 3.8 | Solar | 14_18L1 | 2019-12-05 13:12 | 2019-12-06 | 3 | 3 | 0 | 2019-12-11 | 2019-12-23 | 8 | 0 | 8 | [20 empty] | 2019-12-31 | 2019-12-06 09:34 | 2020-12-05 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MARLBOROUGH | 251090 | 1752 | 75 | Natural Gas | 05_311W1 | 2019-12-06 09:34 | 2019-12-09 | 12 | 7 | 5 | [10 empty] | 2019-12-27 | 2020-01-16 | 13 | 0 | 13 | [10 empty] | 2021-01-15 |  | 2022-06-02 | Yes | STD |  | 2021-08-21 | 2022-03-21 | 213 | 21 | 192 |  |  | 2022-05-05 | Connected |  | Yes
National Grid | PEMBROKE | 268709 | 2359 | 7.6 | Solar | 07_910W52 | 2019-12-06 18:03 | 2019-12-09 | 6 | 6 | 0 | 2019-12-17 | 2020-01-24 | 26 | 3 | 23 | [20 empty] | 2020-01-24 |  | 2021-02-15 |  | EXP | [8 empty] | 2021-01-28 | Connected |  | No
National Grid | SHIRLEY | 231499 | 1464 | 250 | Solar | 01_227W3 | 2019-12-09 | 2019-12-16 | 19 | 14 | 5 | 2020-03-16 | 2020-04-05 | 15 | 15 | 0 | 2020-05-19 | 2020-10-28 | 102 | 3 | 99 | [5 empty] | 2020-05-19 | 2020-10-28 | 102 | 3 | 99 | [5 empty] | 2020-10-13 |  | 2021-12-28 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | FOXBOROUGH | 268549 | 2035 | 10 | Solar | 05_3432W1 | 2019-12-09 13:06 | 2019-12-10 | 0 | 0 | 0 | 2019-12-11 | 2019-12-26 | 10 | 0 | 10 | [20 empty] | 2020-01-02 | 2019-12-09 16:27 | 2020-12-09 |  | EXP | [8 empty] | 2020-07-09 | Connected |  | No
National Grid | HUBBARDSTON | 257344 | 1452 | 9.765 | Solar | 01_609W1 | 2019-12-09 16:27 | 2019-12-10 | 2 | 2 | 0 | 2019-12-12 | 2019-12-23 | 7 | 0 | 7 | [20 empty] | 2020-01-02 |  | 2020-12-09 | Yes | EXP |  | 2020-05-29 | 2020-06-15 | 17 | 0 | 17 |  |  | 2020-09-22 | Connected |  | No
National Grid | MARLBOROUGH | 268191 | 1752 | 7.6 | Solar | 05_311W2 | 2019-12-09 17:50 | 2019-12-10 | 4 | 0 | 4 | 2019-12-16 | 2020-01-10 | 17 | 0 | 17 | [20 empty] | 2020-01-21 | 2019-12-10 15:02 | 2021-02-18 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ADAMS | 267172 | 1220 | 8.7 | Solar | 09_1021W1 | 2019-12-10 15:02 | 2019-12-11 | 4 | 4 | 0 | 2019-12-17 | 2020-01-10 | 16 | 0 | 16 | [20 empty] | 2020-01-10 |  | 2020-12-10 | Yes | EXP |  | 2020-04-10 | 2020-05-07 | 27 | 0 | 27 |  |  | 2020-06-12 | Connected |  | No
National Grid | SHIRLEY | 232315 | 1464 | 250 | Solar | 01_227W3 | 2019-12-11 | 2019-12-16 | 20 | 15 | 5 | 2020-01-15 | 2020-04-05 | 56 | 36 | 20 | 2020-05-19 | 2020-09-16 | 98 | 3 | 95 | [5 empty] | 2020-05-19 | 2020-09-16 | 98 | 3 | 95 | [5 empty] | 2020-09-16 |  | 2021-12-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 269213 | 1844 | 9.84 | Solar | 14_63L2 | 2019-12-11 11:25 | 2019-12-12 | 2 | 2 | 0 | 2019-12-16 | 2019-12-26 | 7 | 0 | 7 | [20 empty] | 2020-01-02 | 2019-12-12 14:48 | 2020-12-11 |  | EXP | [8 empty] | 2020-07-27 | Connected |  | No
National Grid | WORCESTER | 265291 | 1604 | 7.6 | Solar | 01_18J394 | 2019-12-12 14:48 | 2019-12-13 | 12 | 3 | 9 | 2020-01-03 | 2020-01-24 | 14 | 0 | 14 | [20 empty] | 2020-01-29 |  | 2021-04-01 | Yes | EXP |  | 2021-01-20 | 2021-01-22 | 2 | 0 | 2 |  |  | 2021-02-23 | Connected |  | Yes
National Grid | WARREN | 268866 | 1083 | 5.76 | Solar | 09_516L3 | 2019-12-12 15:06 | 2019-12-13 | 2 | 1 | 1 | 2019-12-17 | 2020-01-22 | 23 | 0 | 23 | [20 empty] | 2020-01-23 | 2019-12-13 15:37 | 2021-09-10 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MENDON | 263346 | 1756 | 3 | Solar | 05_321W6 | 2019-12-13 15:37 | 2019-12-16 | 20 | 16 | 4 | 2020-01-15 | 2020-02-04 | 13 | 0 | 13 | [20 empty] | 2020-02-05 |  | 2020-12-13 | Yes | EXP |  | 2020-04-25 | 2020-06-10 | 46 | 0 | 46 |  |  | 2020-06-15 | Connected |  | No
National Grid | TEWKSBURY | 270035 | 1876 | 9.84 | Solar | 14_20L1 | 2019-12-17 13:05 | 2019-12-18 | 0 | 0 | 0 | 2019-12-18 | 2020-01-22 | 22 | 0 | 22 | [20 empty] | 2020-01-23 | 2019-12-17 15:17 | 2020-12-17 |  | EXP | [8 empty] | 2020-06-17 | Connected |  | No
National Grid | METHUEN | 268864 | 1844 | 10 | Solar | 14_74L4 | 2019-12-17 15:17 | 2019-12-18 | 2 | 0 | 2 | 2019-12-23 | 2020-01-10 | 12 | 0 | 12 | [20 empty] | 2020-01-21 |  | 2020-12-17 | Yes | EXP |  | 2020-07-16 | 2020-08-19 | 34 | 0 | 34 |  |  | 2020-10-28 | Connected |  | No
National Grid | REVERE | 269219 | 2151 | 3.8 | Solar | 12_16W8 | 2019-12-18 11:47 | 2019-12-19 | 16 | 16 | 0 | [27 empty] | 2020-12-18 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BILLERICA | 268931 | 1821 | 3.8 | Solar | 14_18L1 | 2019-12-18 12:40 | 2019-12-19 | 0 | 0 | 0 | 2019-12-19 | 2020-01-22 | 21 | 0 | 21 | [20 empty] | 2020-01-23 | 2019-12-20 11:44 | 2020-12-18 |  | EXP | [8 empty] | 2020-03-13 | Connected |  | No
National Grid | BRADFORD | 270545 | 1835 | 25 | Solar | 14_65L3 | 2019-12-20 11:44 | 2019-12-23 | 4 | 0 | 4 | 2019-12-31 | 2020-01-23 | 15 | 0 | 15 | [20 empty] | 2020-01-23 | 2019-12-20 15:06 | 2020-12-20 | Yes | EXP |  | 2020-03-10 | 2020-04-02 | 23 | 0 | 23 |  |  | 2020-09-14 | Connected |  | No
National Grid | MELROSE | 269791 | 2176 | 3 | Solar | 12_25W5 | 2019-12-20 15:06 | 2019-12-23 | 6 | 0 | 6 | 2020-01-03 | 2020-01-24 | 14 | 0 | 14 | [20 empty] | 2020-01-29 | 2019-12-26 07:56 | 2020-12-20 | Yes | EXP | [8 empty] | 2020-10-23 | Connected |  | No
National Grid | PEMBROKE | 270336 | 2359 | 400 | Solar | 07_910W51 | 2019-12-26 07:56 | 2019-12-27 | 13 | 12 | 1 | [10 empty] | 2020-01-16 | 2020-02-05 | 13 | 0 | 13 | [10 empty] | 2020-08-03 | 2019-12-26 12:55 | 2023-01-02 | Yes | STD |  | 2022-01-27 | 2022-06-08 | 133 | 0 | 133 |  |  | 2022-09-20 | Connected |  | No
National Grid | METHUEN | 270454 | 1844 | 7.6 | Solar | 14_74L3 | 2019-12-26 12:55 | 2019-12-27 | 5 | 0 | 5 | 2020-01-07 | 2020-01-21 | 9 | 0 | 9 | [20 empty] | 2020-01-28 | 2019-12-26 14:42 | 2020-12-26 | Yes | EXP |  | 2020-09-23 | 2020-10-13 | 20 | 0 | 20 |  |  | 2020-10-27 | Connected |  | No
National Grid | SAUGUS | 269234 | 1906 | 7.6 | Solar | 12_23W2 | 2019-12-26 14:42 | 2019-12-27 | 5 | 0 | 5 | 2020-01-07 | 2020-01-24 | 12 | 0 | 12 | [20 empty] | 2020-01-29 |  | 2021-03-12 | Yes | EXP |  | 2020-10-03 | 2021-01-18 | 107 | 0 | 107 |  |  | 2021-02-05 | Connected |  | No
National Grid | GOSHEN | 271260 | 1096 | 25 | Solar | 09_909W3 | 2019-12-31 09:16 | 2020-01-02 | 19 | 18 | 1 | 2020-01-30 | 2020-02-11 | 8 | 0 | 8 | [20 empty] | 2020-02-11 |  | 2021-01-04 |  | EXP | [8 empty] | 2020-09-28 | Connected |  | No
National Grid | BELCHERTOWN | 271263 | 1007 | 25 | Solar | 09_509L1 | 2019-12-31 10:00 | 2020-01-02 | 19 | 18 | 1 | 2020-01-30 | 2020-02-11 | 8 | 0 | 8 | [20 empty] | 2020-02-11 | 2019-12-31 13:05 | 2021-01-04 |  | EXP | [8 empty] | 2020-07-21 | Connected |  | No
National Grid | WORCESTER | 264740 | 1602 | 8.64 | Solar | 01_1J369 | 2019-12-31 13:05 | 2020-01-02 | 31 | 26 | 5 | 2020-02-20 | 2020-03-04 | 9 | 0 | 9 | [20 empty] | 2020-03-04 |  | 2021-02-22 | Yes | EXP |  | 2020-09-23 | 2021-01-25 | 124 | 0 | 124 |  |  | 2021-02-02 | Connected |  | No
National Grid | NEWBURYPORT | 270895 | 1950 | 10 | Solar | 14_36L2 | 2019-12-31 14:27 | 2020-01-02 | 6 | 0 | 6 | 2020-01-13 | 2020-01-24 | 8 | 0 | 8 | [20 empty] | 2020-01-29 |  | 2020-12-31 |  | EXP | [8 empty] | 2020-10-08 | Connected |  | No
National Grid | WARE | 271476 | 1082 | 6.72 | Solar | 09_523L4 | 2020-01-02 10:10 | 2020-01-03 | 37 | 36 | 1 | 2020-02-25 | 2020-03-04 | 6 | 0 | 6 | [20 empty] | 2020-03-04 | 2020-01-02 11:39 | 2021-01-02 |  | EXP | [8 empty] | 2020-04-28 | Connected |  | No
National Grid | BELLINGHAM | 268733 | 2019 | 7.6 | Solar | 05_344W4 | 2020-01-02 11:39 | 2020-01-03 | 5 | 0 | 5 | 2020-01-13 | 2020-01-24 | 8 | 0 | 8 | [20 empty] | 2020-02-05 |  | 2021-09-22 | Yes | EXP | [8 empty] | 2021-08-14 | Connected |  | No
National Grid | HOLBROOK | 271946 | 2343 | 15.2 | Solar | 07_97W3 | 2020-01-06 | 2020-01-10 | 6 | 6 | 0 | 2020-01-21 | 2020-02-04 | 10 | 0 | 10 | [20 empty] | 2020-02-05 |  | 2021-01-08 |  | EXP | [8 empty] | 2020-04-08 | Connected |  | No
National Grid | SOMERSET | 271016 | 2726 | 999 | Solar | 05_11W82 | 2020-01-06 12:25 | 2020-01-07 | 9 | 7 | 2 | [10 empty] | 2020-01-21 | 2020-02-20 | 22 | 10 | 12 | [10 empty] | 2020-07-01 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BYFIELD | 270193 | 1922 | 10 | Solar | 14_60L2 | 2020-01-06 13:29 | 2020-01-07 | 0 | 0 | 0 | 2020-01-08 | 2020-01-21 | 9 | 1 | 8 | [20 empty] | 2020-01-21 | 2020-01-08 | 2021-01-06 |  | EXP | [8 empty] | 2020-07-09 | Connected |  | No
National Grid | PEMBROKE | 265163 | 2359 | 250 | Solar | 07_910W51 | 2020-01-08 | 2020-01-09 | 11 | 11 | 0 | 2020-01-28 | 2020-03-03 | 25 | 12 | 13 | 2020-04-10 | 2020-05-05 | 16 | 0 | 16 | [5 empty] | 2020-04-10 | 2020-05-05 | 16 | 0 | 16 | [5 empty] | 2020-07-13 |  | 2023-06-12 | Yes | EXP |  | 2021-06-28 | 2022-06-22 | 360 | 160 | 200 |  |  | 2023-04-11 | Connected |  | No
National Grid | ANDOVER | 272817 | 1810 | 15.25 | Solar | 14_59L1 | 2020-01-10 14:59 | 2020-01-13 | 5 | 0 | 5 | 2020-01-22 | 2020-02-10 | 13 | 0 | 13 | [20 empty] | 2020-02-18 |  | 2021-01-10 |  | EXP | [8 empty] | 2020-07-23 | Connected |  | No
National Grid | SALEM | 273131 | 1970 | 10 | Solar | 12_49W6 | 2020-01-14 09:34 | 2020-01-15 | 0 | 0 | 0 | 2020-01-15 | 2020-01-30 | 11 | 4 | 7 | [20 empty] | 2020-01-31 |  | 2021-01-15 |  | EXP | [8 empty] | 2020-03-24 | Connected |  | No
National Grid | FRANKLIN | 273152 | 2038 | 27.6 | Solar | 05_348W7 | 2020-01-14 10:56 | 2020-01-15 | 3 | 3 | 0 | 2020-01-21 | 2020-02-04 | 10 | 0 | 10 | [20 empty] | 2020-02-05 |  | 2021-01-15 |  | EXP | [8 empty] | 2020-09-28 | Connected |  | No
National Grid | MILFORD | 273620 | 1757 | 486.6 | Solar | 05_335W9 | 2020-01-16 | 2020-01-23 | 1 | 0 | 1 | 2020-01-27 | 2020-02-07 | 9 | 0 | 9 | [20 empty] | 2020-02-11 |  | 2021-02-26 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WARREN | 256705 | 1083 | 2800 | Solar | 09_516L3 | 2020-01-16 14:42 | 2020-01-17 | 46 | 46 | 0 | [10 empty] | 2020-03-25 | 2020-04-28 | 23 | 9 | 14 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | DUDLEY | 268311 | 1571 | 10 | Solar | 01_412L4 | 2020-01-17 10:34 | 2020-02-10 | 1 | 1 | 0 | 2020-02-11 | 2020-02-19 | 5 | 0 | 5 | [20 empty] | 2020-02-19 | 2020-01-21 10:02 | 2021-02-10 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | REVERE | 270600 | 2151 | 3.8 | Solar | 12_35J3 | 2020-01-21 10:02 | 2020-01-22 | 32 | 29 | 3 | 2020-03-10 | 2020-03-23 | 9 | 0 | 9 | [20 empty] | 2020-03-23 |  | 2022-11-01 | Yes | EXP |  | 2020-10-03 | 2020-12-15 | 73 | 0 | 73 |  |  | 2022-10-26 | Connected |  | No
National Grid | AYER | 274261 | 1432 | 100 | Solar | HVDC Converter to Sandy Pond | 2020-01-22 | 2020-01-23 | 13 | 7 | 6 | 2020-02-11 | 2020-02-13 | 2 | 1 | 1 | [20 empty] | 2020-02-13 | 2020-01-23 09:59 | 2020-10-30 |  | EXP | [8 empty] | 2020-09-04 | Connected |  | No
National Grid | HOPEDALE | 273947 | 1747 | 7.6 | Solar | 05_335W9 | 2020-01-23 09:59 | 2020-01-24 | 42 | 35 | 7 | 2020-04-15 | 2020-05-01 | 11 | 0 | 11 | [20 empty] | 2020-05-06 | 2020-01-23 10:05 | 2022-05-04 |  | EXP |  | 2021-07-31 | 2021-10-04 | 63 | 3 | 60 |  |  | 2021-12-08 | Connected |  | No
National Grid | WESTFORD | 273553 | 1886 | 7.6 | Solar | 14_57L2 | 2020-01-23 10:05 | 2020-01-24 | 8 | 3 | 5 | 2020-02-06 | 2020-02-12 | 4 | 0 | 4 | [20 empty] | 2020-02-18 | 2020-01-23 14:00 | 2021-07-15 | Yes | EXP |  | 2021-04-06 | 2021-04-15 | 9 | 0 | 9 |  |  | 2021-04-30 | Connected |  | No
National Grid | WORCESTER | 273828 | 1603 | 7.6 | Solar | 01_7J387 | 2020-01-23 14:00 | 2020-01-24 | 16 | 14 | 2 | 2020-02-19 | 2020-03-05 | 11 | 0 | 11 | [20 empty] | 2020-03-16 | 2020-01-23 14:45 | 2021-08-12 | Yes | EXP |  | 2021-02-03 | 2021-03-15 | 40 | 0 | 40 |  |  | 2021-04-07 | Connected |  | No
National Grid | TEWKSBURY | 273439 | 1876 | 15 | Solar | 14_75L2 | 2020-01-23 14:45 | 2020-01-24 | 2 | 2 | 0 | 2020-01-28 | 2020-03-16 | 33 | 29 | 4 | [20 empty] | 2020-03-17 |  | 2021-01-25 | Yes | EXP |  | 2020-06-06 | 2020-06-13 | 7 | 0 | 7 |  |  | 2020-06-15 | Connected |  | No
National Grid | MILFORD | 273779 | 1757 | 60 | Solar | 05_336W4 | 2020-01-23 15:51 | 2020-01-24 | 9 | 5 | 4 | 2020-02-07 | 2020-02-20 | 8 | 4 | 4 | [20 empty] | 2020-02-24 | 2020-01-24 09:17 | 2021-06-02 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTBOROUGH | 271250 | 1581 | 400 | Solar | 05_312W4 | 2020-01-24 09:17 | 2020-01-27 | 5 | 1 | 4 | [10 empty] | 2020-02-03 | 2020-03-21 | 34 | 32 | 2 | [10 empty] | 2020-08-24 |  | 2022-03-10 | Yes | STD |  | 2021-08-05 | 2021-08-10 | 6 | 0 | 6 |  |  | 2022-03-07 | Connected |  | No
National Grid | EAST BRIDGEWATER | 273621 | 2333 | 7.6 | Solar | 07_797W23 | 2020-01-28 08:32 | 2020-01-29 | 5 | 5 | 0 | 2020-02-05 | 2020-02-10 | 3 | 0 | 3 | [20 empty] | 2020-02-10 |  | 2021-01-29 |  | EXP | [8 empty] | 2020-04-22 | Connected |  | No
National Grid | WEST NEWBURY | 277157 | 1985 | 12.6 | Battery Add-On | 14_34M1 | 2020-01-30 08:26 | 2020-01-31 | 1 | 1 | 0 | 2020-02-03 | 2020-02-11 | 6 | 0 | 6 | [20 empty] | 2020-02-11 |  | 2021-01-29 |  | EXP | [8 empty] | 2020-09-21 | Connected |  | No
National Grid | FALL RIVER | 273678 | 2720 | 4200 | Solar | 05_106W46 | 2020-01-30 11:34 | 2020-01-31 | 13 | 9 | 4 | [10 empty] | 2020-02-20 | 2020-03-24 | 24 | 14 | 10 | [10 empty] | 2020-08-12 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HALIFAX | 271025 | 2338 | 7.6 | Solar | 07_912W75 | 2020-01-30 12:34 | 2020-01-31 | 11 | 11 | 0 | 2020-02-19 | 2020-03-04 | 10 | 0 | 10 | [20 empty] | 2020-03-05 | 2020-01-30 15:22 | 2021-02-18 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SWANSEA | 274437 | 2777 | 6 | Solar | 05_11W84 | 2020-01-30 15:22 | 2020-01-31 | 7 | 3 | 4 | 2020-02-12 | 2020-02-12 | 0 | 0 | 0 | [20 empty] | 2020-02-18 |  | 2021-02-05 | Yes | EXP |  | 2020-06-25 | 2020-08-12 | 48 | 0 | 48 |  |  | 2020-10-16 | Connected |  | No
National Grid | LOWELL | 270081 | 1851 | 37.8 | Solar | 14_16L3 | 2020-01-31 10:17 | 2020-02-03 | 0 | 0 | 0 | [25 empty] | 2020-02-07 |  | 2024-06-25 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | LOWELL | 270083 | 1851 | 95.4 | Solar | 14_16L3 | 2020-01-31 10:35 | 2020-02-03 | 0 | 0 | 0 | [25 empty] | 2020-02-07 |  | 2024-06-25 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | ANDOVER | 266407 | 1810 | 17.6 | Solar | 14_50L2 | 2020-01-31 11:59 | 2020-02-03 | 4 | 3 | 1 | 2020-02-07 | 2020-02-11 | 2 | 0 | 2 | [20 empty] | 2020-02-11 |  | 2021-02-03 |  | EXP | [8 empty] | 2020-07-27 | Connected |  | No
National Grid | BOLTON | 277546 | 1740 | 9.6 | Solar | 01_225W1 | 2020-01-31 15:26 | 2020-02-03 | 3 | 0 | 3 | 2020-02-07 | 2020-02-14 | 5 | 1 | 4 | [20 empty] | 2020-02-25 |  | 2021-01-22 |  | EXP | [8 empty] | 2020-11-10 | Connected |  | No
National Grid | NORTHAMPTON | 277573 | 1060 | 20 | Solar | 09_901W2 | 2020-01-31 18:42 | 2020-02-03 | 10 | 9 | 1 | 2020-02-18 | 2020-03-16 | 20 | 4 | 16 | [20 empty] | 2020-03-17 |  | 2021-02-02 |  | EXP | [8 empty] | 2020-11-13 | Connected |  | No
National Grid | LAWRENCE | 273652 | 1841 | 10 | Solar | 14_63L1 | 2020-02-03 11:52 | 2020-02-04 | 2 | 0 | 2 | 2020-02-07 | 2020-02-11 | 2 | 0 | 2 | [20 empty] | 2020-02-18 |  | 2021-07-08 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BRIDGEWATER | 268344 | 2324 | 7.6 | Solar | 07_912W21 | 2020-02-03 13:58 | 2020-02-04 | 2 | 0 | 2 | 2020-02-07 | 2020-02-13 | 4 | 0 | 4 | [20 empty] | 2020-02-18 |  |  |  | EXP | [8 empty] | 2020-07-25 | Connected |  | No
National Grid | CHELMSFORD | 273784 | 1863 | 8.88 | Solar | 14_73L2 | 2020-02-03 16:59 | 2020-02-04 | 1 | 1 | 0 | 2020-02-06 | 2020-02-11 | 3 | 0 | 3 | [20 empty] | 2020-02-11 | 2020-02-03 17:20 | 2021-02-03 |  | EXP | [8 empty] | 2020-04-20 | Connected |  | No
National Grid | WESTFORD | 277368 | 1886 | 9.84 | Solar | 14_57L2 | 2020-02-03 17:20 | 2020-02-04 | 1 | 0 | 1 | 2020-02-06 | 2020-02-19 | 8 | 0 | 8 | [20 empty] | 2020-02-19 |  | 2021-02-03 | Yes | EXP |  | 2020-07-11 | 2020-07-27 | 16 | 0 | 16 |  |  | 2020-08-18 | Connected |  | No
National Grid | MENDON | 278122 | 1756 | 17.8 | Other | 05_321W6 | 2020-02-05 | 2020-02-11 | 0 | 0 | 0 | 2020-02-12 | 2020-02-14 | 3 | 1 | 2 | [20 empty] | 2020-02-14 | 2020-02-05 11:32 | 2021-02-11 |  | EXP | [8 empty] | 2020-12-22 | Connected |  | No
National Grid | BELLINGHAM | 239323 | 2019 | 10 | Solar | 05_344W4 | 2020-02-05 11:32 | 2020-02-06 | 3 | 0 | 3 | 2020-02-12 | 2020-02-12 | 0 | 0 | 0 | [20 empty] | 2020-02-18 | 2020-02-05 12:56 | 2022-02-09 | Yes | EXP |  | 2020-07-15 | 2020-07-28 | 13 | 0 | 13 |  |  |  | Withdrawn |  | Yes
National Grid | LANCASTER | 272564 | 1523 | 4000 | Solar | 01_227W1 | 2020-02-05 12:56 | 2020-02-06 | 10 | 8 | 2 | [10 empty] | 2020-02-21 | 2020-03-13 | 15 | 7 | 8 | [10 empty] | 2021-03-25 |  | 2022-09-08 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | TEWKSBURY | 278152 | 1876 | 383 | Solar | 14_14L1 | 2020-02-05 13:47 | 2020-02-06 | 5 | 0 | 5 | 2020-02-14 | 2020-03-03 | 15 | 4 | 11 | [20 empty] | 2020-03-04 |  | 2021-03-19 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | GREAT BARRINGTON | 278010 | 1230 | 57.6 | Solar | 09_1109W2 | 2020-02-05 15:31 | 2020-02-06 | 7 | 4 | 3 | 2020-02-18 | 2020-03-18 | 21 | 0 | 21 | 2020-05-04 | 2020-11-05 | 131 | 101 | 30 | [5 empty] | 2020-05-04 | 2020-11-05 | 131 | 101 | 30 | [5 empty] | 2020-11-12 |  |  |  | EXP | [8 empty] | 2021-04-13 | Connected |  | No
National Grid | SEEKONK | 278241 | 2771 | 12 | Solar | 05_7L1 | 2020-02-05 16:06 | 2020-02-06 | 9 | 9 | 0 | 2020-02-20 | 2020-03-16 | 18 | 4 | 14 | [20 empty] | 2020-03-17 | 2020-02-06 15:05 | 2021-09-10 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SALISBURY | 277711 | 1952 | 5 | Solar | 14_7L4 | 2020-02-06 15:05 | 2020-02-07 | 6 | 6 | 0 | 2020-02-19 | 2020-03-04 | 11 | 2 | 9 | [20 empty] | 2020-03-05 | 2020-02-06 15:08 | 2021-02-18 | Yes | EXP |  | 2020-06-09 | 2020-06-11 | 2 | 0 | 2 |  |  | 2020-06-13 | Connected |  | No
National Grid | REVERE | 277078 | 2151 | 3.8 | Solar | 12_16W8 | 2020-02-06 15:08 | 2020-02-07 | 6 | 2 | 4 | 2020-02-19 | 2020-03-04 | 10 | 0 | 10 | [20 empty] | 2020-03-11 | 2020-02-06 16:12 | 2021-03-31 | Yes | EXP |  | 2020-06-24 | 2021-01-11 | 202 | 5 | 197 |  |  | 2021-03-20 | Connected |  | No
National Grid | FRANKLIN | 206339 | 2038 | 499.5 | Solar | 05_344W2 | 2020-02-06 16:12 | 2020-02-07 | 10 | 6 | 4 | [10 empty] | 2020-02-24 | 2020-03-10 | 12 | 1 | 11 | [10 empty] | 2020-09-17 |  | 2023-10-05 | Yes | STD |  | 2023-04-30 | 2023-04-30 | 1 | 1 | 0 |  |  | 2023-10-20 | Connected |  | No
National Grid | DIGHTON | 195446 | 2715 | 2000 | Solar | 05_19W74 | 2020-02-07 10:54 | 2020-02-10 | 38 | 28 | 10 | [29 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SEEKONK | 278753 | 2771 | 80 | Solar | 05_6J1 | 2020-02-10 13:23 | 2020-02-11 | 3 | 2 | 1 | 2020-02-14 | 2020-04-03 | 35 | 13 | 22 | 2020-05-08 | 2020-07-23 | 43 | 2 | 41 | [5 empty] | 2020-05-08 | 2020-07-23 | 43 | 2 | 41 | [5 empty] | 2020-08-06 |  | 2021-03-03 |  | EXP |  | 2020-09-23 | 2020-11-20 | 58 | 0 | 58 |  |  | 2020-12-23 | Connected |  | No
National Grid | MILFORD | 260025 | 1757 | 250 | Solar | 05_336W1 | 2020-02-11 | 2019-10-18 | 12 | 11 | 1 | 2019-11-05 | 2020-03-04 | 81 | 34 | 47 | 2020-03-30 | 2020-08-05 | 91 | 1 | 90 | [5 empty] | 2020-03-30 | 2020-08-05 | 91 | 1 | 90 | [5 empty] | 2020-09-02 | 2020-02-11 08:30 | 2022-09-07 |  | EXP |  | 2021-08-24 | 2021-08-23 | 0 | 0 | 0 |  |  | 2021-10-14 | Connected |  | No
National Grid | WORCESTER | 274013 | 1605 | 250 | Solar | 01_24W2 | 2020-02-11 08:30 | 2020-02-12 | 3 | 1 | 2 | [10 empty] | 2020-02-18 | 2020-05-12 | 60 | 43 | 17 | [10 empty] | 2020-12-03 |  | 2023-06-23 | Yes | STD |  | 2022-04-02 | 2023-06-06 | 430 | 0 | 430 | 2023-05-25 | 2023-05-25 | 2023-06-16 | Connected |  | No
National Grid | SPENCER | 264202 | 1562 | 5000 | Other | 01_552L1 | 2020-02-12 15:22 | 2020-02-13 | 22 | 22 | 0 | [10 empty] | 2020-03-17 | 2020-04-01 | 11 | 0 | 11 | [11 empty] | 2020-02-12 18:27 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | GLOUCESTER | 274362 | 1930 | 4.32 | Solar | 12_52L1 | 2020-02-12 18:27 | 2020-02-13 | 8 | 8 | 0 | 2020-02-27 | 2020-03-16 | 12 | 0 | 12 | [20 empty] | 2020-03-17 |  | 2021-02-26 | Yes | EXP |  | 2020-07-23 | 2020-09-15 | 55 | 5 | 50 |  |  | 2020-09-16 | Connected |  | No
National Grid | WEYMOUTH | 279479 | 2190 | 7.6 | Solar | 07_99W32 | 2020-02-13 18:15 | 2020-02-14 | 1 | 0 | 1 | 2020-02-19 | 2020-03-17 | 20 | 5 | 15 | [20 empty] | 2020-04-22 |  |  |  | EXP | [8 empty] | 2020-08-07 | Connected |  | No
National Grid | CHARLTON | 265320 | 1507 | 4950 | Other | 01_415L1 | 2020-02-14 11:18 | 2020-02-18 | 25 | 22 | 3 | [10 empty] | 2020-03-24 | 2020-03-23 | 0 | 0 | 0 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | HARVARD | 279637 | 1451 | 10.44 | Solar | 01_201W2 | 2020-02-14 18:48 | 2020-02-18 | 14 | 14 | 0 | 2020-03-09 | 2020-03-13 | 4 | 0 | 4 | [20 empty] | 2020-03-13 |  | 2021-03-05 |  | EXP | [8 empty] | 2020-04-02 | Connected |  | No
National Grid | WRENTHAM | 279731 | 2093 | 25 | Solar | 05_3422W4 | 2020-02-18 13:04 | 2020-02-19 | 6 | 6 | 0 | 2020-02-27 | 2020-03-10 | 8 | 0 | 8 | [20 empty] | 2020-03-10 | 2020-02-19 14:38 | 2021-03-20 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 280097 | 1507 | 8.64 | Solar | 01_413L4 | 2020-02-19 14:38 | 2020-02-20 | 3 | 0 | 3 | 2020-02-26 | 2020-03-10 | 9 | 0 | 9 | [20 empty] | 2020-03-18 | 2020-02-20 08:27 | 2021-02-03 | Yes | EXP | [8 empty] | 2021-03-12 | Connected |  | No
National Grid | LEOMINSTER | 272614 | 1453 | 499.9 | Solar | 01_225W3 | 2020-02-20 08:27 | 2020-02-21 | 5 | 2 | 3 | [10 empty] | 2020-02-28 | 2020-03-11 | 8 | 0 | 8 | [10 empty] | 2020-07-07 |  | 2024-04-01 | Yes | STD |  | 2024-01-26 |  | 81 | 36 | 45 |  |  | 2024-03-25 | Connected |  | No
National Grid | MILLBURY | 280278 | 1527 | 10 | Solar | 01_304W4 | 2020-02-20 16:10 | 2020-02-21 | 0 | 0 | 0 | 2020-02-24 | 2020-03-27 | 25 | 17 | 8 | [20 empty] | 2020-03-27 |  | 2021-02-19 |  | EXP | [8 empty] | 2020-12-03 | Connected |  | No
National Grid | LOWELL | 280389 | 1852 | 250 | Solar | 14_3L2 | 2020-02-21 | 2020-02-25 | 4 | 0 | 4 | 2020-03-03 | 2020-03-19 | 12 | 0 | 12 | [20 empty] | 2020-03-20 |  | 2021-04-21 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | PEPPERELL | 272824 | 1463 | 3.8 | Solar | 01_226L1 | 2020-02-21 09:51 | 2020-02-24 | 50 | 49 | 1 | 2020-05-01 | 2020-05-20 | 13 | 0 | 13 | [20 empty] | 2020-05-21 |  | 2021-04-29 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | TYNGSBORO | 268890 | 1879 | 249.5 | Solar | 14_211L1 | 2020-02-21 16:26 | 2020-02-24 | 25 | 23 | 2 | [10 empty] | 2020-03-30 | 2020-04-24 | 19 | 4 | 15 | [10 empty] | 2022-04-20 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH BROOKFIELD | 272131 | 1535 | 4950 | Other | 01_525L2 | 2020-02-24 14:19 | 2020-02-25 | 33 | 27 | 6 | [10 empty] | 2020-04-13 | 2020-05-11 | 19 | 9 | 10 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SPENCER | 265279 | 1562 | 10000 | Other | 01_552L1 | 2020-02-24 14:35 | 2020-02-25 | 15 | 11 | 4 | [10 empty] | 2020-08-24 | 2020-10-24 | 43 | 26 | 17 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | LEICESTER | 272127 | 1524 | 4950 | Other | 01_21W2 | 2020-02-24 14:59 | 2020-02-25 | 33 | 27 | 6 | [10 empty] | 2020-04-13 | 2020-05-11 | 19 | 9 | 10 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | ANDOVER | 279685 | 1810 | 10 | Solar | 14_59L1 | 2020-02-24 16:27 | 2020-02-25 | 0 | 0 | 0 | 2020-02-26 | 2020-03-10 | 9 | 0 | 9 | [20 empty] | 2020-03-10 | 2020-02-25 13:21 | 2021-02-25 |  | EXP | [8 empty] | 2020-06-08 | Connected |  | No
National Grid | SALEM | 279630 | 1970 | 10 | Solar | 12_2W1 | 2020-02-25 13:21 | 2020-02-26 | 0 | 0 | 0 | 2020-02-27 | 2020-03-05 | 5 | 0 | 5 | [20 empty] | 2020-03-06 |  | 2021-02-25 | Yes | EXP |  | 2020-05-15 | 2020-06-03 | 19 | 0 | 19 |  |  | 2020-06-04 | Connected |  | No
National Grid | STOUGHTON | 273969 | 2072 | 7.6 | Solar | 07_94W44 | 2020-02-26 09:00 | 2020-02-27 | 0 | 0 | 0 | 2020-02-27 | 2020-03-05 | 5 | 0 | 5 | [20 empty] | 2020-03-06 |  | 2021-02-26 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NANTUCKET | 278387 | 2554 | 15.2 | Solar | 04_101L2 | 2020-02-26 09:39 | 2020-02-27 | 3 | 0 | 3 | 2020-03-04 | 2020-03-18 | 10 | 0 | 10 | [20 empty] | 2020-04-22 |  | 2021-02-05 |  | EXP | [8 empty] | 2020-10-20 | Connected |  | No
National Grid | LAWRENCE | 278952 | 1841 | 7.6 | Solar | 14_8L2 | 2020-02-27 11:44 | 2020-02-28 | 25 | 25 | 0 | [26 empty] | 2020-02-27 12:08 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHARLTON | 265989 | 1507 | 4948 | Other | 01_413L4 | 2020-02-27 12:08 | 2020-02-28 | 13 | 7 | 6 | [10 empty] | 2020-03-18 | 2020-04-02 | 11 | 0 | 11 | [12 empty] | 2025-02-26 | Yes | STD | [9 empty] | Group Study |  | No
National Grid | SALEM | 281332 | 1970 | 12 | Solar | 12_2W1 | 2020-02-27 17:28 | 2020-02-28 | 3 | 3 | 0 | 2020-03-05 | 2020-03-12 | 5 | 0 | 5 | [20 empty] | 2020-03-12 | 2020-03-02 08:46 | 2021-03-03 |  | EXP | [8 empty] | 2020-07-29 | Connected |  | No
National Grid | LENOX | 268625 | 1240 | 4999 | Solar | 09_1103W1 | 2020-03-02 08:46 | 2020-03-03 | 42 | 37 | 5 | [10 empty] | 2020-05-04 | 2020-05-29 | 18 | 0 | 18 | [10 empty] | 2021-04-09 |  | 2024-08-21 | Yes | STD | [9 empty] | Construction |  | No
National Grid | WILLIAMSTOWN | 279879 | 1267 | 20 | Solar | 09_1001W1 | 2020-03-02 11:19 | 2020-03-03 | 0 | 0 | 0 | 2020-03-03 | 2020-03-04 | 1 | 0 | 1 | [20 empty] | 2020-03-05 | 2020-03-02 14:59 | 2021-03-02 |  | EXP | [8 empty] | 2020-12-14 | Connected |  | No
National Grid | FALL RIVER | 280942 | 2721 | 3.8 | Solar | 05_115W52 | 2020-03-02 14:59 | 2020-03-03 | 7 | 3 | 4 | 2020-03-12 | 2020-03-27 | 11 | 0 | 11 | [20 empty] | 2020-04-01 |  | 2021-02-26 | Yes | EXP | [8 empty] | 2020-10-29 | Connected |  | No
National Grid | SCITUATE | 281952 | 2066 | 8.12 | Solar | 07_65J1 | 2020-03-02 16:08 | 2020-03-03 | 0 | 0 | 0 | 2020-03-04 | 2020-03-04 | 0 | 0 | 0 | [20 empty] | 2020-03-05 | 2020-03-03 09:55 | 2021-03-02 |  | EXP | [8 empty] | 2020-05-14 | Connected |  | No
National Grid | NORTHAMPTON | 280785 | 1060 | 3.8 | Solar | 09_905W1 | 2020-03-03 09:55 | 2020-03-04 | 16 | 16 | 0 | 2020-03-26 | 2020-03-27 | 1 | 0 | 1 | [20 empty] | 2020-03-30 | 2020-03-03 13:29 | 2021-03-25 | Yes | EXP |  | 2020-10-08 | 2020-10-26 | 18 | 0 | 18 |  |  | 2020-10-28 | Connected |  | No
National Grid | EAST LONGMEADOW | 237300 | 1028 | 9.6 | Solar | 09_508L1 | 2020-03-03 13:29 | 2020-03-04 | 51 | 43 | 8 | 2020-05-15 | 2020-06-11 | 19 | 1 | 18 | [20 empty] | 2020-06-18 |  | 2021-04-14 | Yes | EXP |  | 2021-01-23 | 2021-02-04 | 12 | 0 | 12 |  |  | 2021-02-19 | Connected |  | No
National Grid | WESTMINSTER | 272136 | 1473 | 5000 | Other | 01_609W2 | 2020-03-03 14:55 | 2020-03-04 | 10 | 6 | 4 | [10 empty] | 2020-03-18 | 2020-04-02 | 11 | 0 | 11 | [11 empty] | 2020-03-03 15:08 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 277815 | 1844 | 7.6 | Solar | 14_74L1 | 2020-03-03 15:08 | 2020-03-04 | 3 | 0 | 3 | 2020-03-10 | 2020-03-16 | 4 | 0 | 4 | [20 empty] | 2020-03-31 |  |  | Yes | EXP |  | 2021-02-06 | 2021-02-12 | 6 | 0 | 6 |  |  | 2021-04-27 | Connected |  | No
National Grid | SOUTHBRIDGE | 273618 | 1550 | 5000 | Other | 01_413L3 | 2020-03-03 15:15 | 2020-03-04 | 10 | 7 | 3 | [10 empty] | 2020-03-18 | 2020-04-02 | 11 | 0 | 11 | [11 empty] | 2020-03-04 09:26 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | FALL RIVER | 278494 | 2721 | 5 | Solar | 05_115W53 | 2020-03-04 09:26 | 2020-03-05 | 10 | 7 | 3 | 2020-03-19 | 2020-03-27 | 6 | 0 | 6 | [20 empty] | 2020-04-10 | 2020-03-04 10:24 |  | Yes | EXP |  | 2020-07-03 | 2020-07-31 | 28 | 0 | 28 |  |  | 2020-08-25 | Connected |  | No
National Grid | LYNN | 277587 | 1904 | 10 | Solar | 12_24W1 | 2020-03-04 10:24 | 2020-03-05 | 7 | 3 | 4 | 2020-03-17 | 2020-03-27 | 8 | 0 | 8 | [20 empty] | 2020-04-02 | 2020-03-04 11:10 | 2022-12-21 | Yes | EXP |  | 2020-12-10 | 2021-03-11 | 91 | 0 | 91 |  |  | 2022-09-22 | Connected |  | No
National Grid | BEVERLY | 281100 | 1915 | 7.6 | Solar | 12_12L2 | 2020-03-04 11:10 | 2020-03-05 | 6 | 6 | 0 | 2020-03-13 | 2020-03-27 | 10 | 0 | 10 | [20 empty] | 2020-04-17 | 2020-03-04 11:13 | 2021-03-12 | Yes | EXP |  | 2020-09-18 | 2020-09-28 | 10 | 0 | 10 |  |  | 2020-11-04 | Connected |  | No
National Grid | LYNN | 280354 | 1905 | 7.6 | Solar | 12_7J901 | 2020-03-04 11:13 | 2020-03-05 | 63 | 62 | 1 | 2020-06-03 | 2020-07-07 | 24 | 0 | 24 | [20 empty] | 2020-07-08 | 2020-03-04 12:17 | 2021-06-02 | Yes | EXP |  | 2020-12-11 | 2021-03-16 | 95 | 0 | 95 |  |  | 2021-03-19 | Connected |  | No
National Grid | MEDFORD | 281295 | 2155 | 490 | Other | 12_2344 | 2020-03-04 12:17 | 2020-03-05 | 5 | 2 | 3 | [10 empty] | 2020-03-12 | 2020-04-30 | 34 | 16 | 18 | [10 empty] | 2021-02-04 |  | 2024-02-10 | Yes | STD | [8 empty] | 2023-12-29 | Connected |  | No
National Grid | STOUGHTON | 225530 | 2072 | 3.8 | Solar | 07_913W17 | 2020-03-05 08:15 | 2020-03-06 | 35 | 26 | 9 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RANDOLPH | 229376 | 2368 | 3.8 | Solar | 07_97W1 | 2020-03-05 08:30 | 2020-03-06 | 170 | 126 | 44 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 278631 | 1844 | 7.6 | Solar | 14_63L2 | 2020-03-05 10:06 | 2020-03-06 | 51 | 41 | 10 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SALEM | 278977 | 1970 | 9.36 | Solar | 12_29W2 | 2020-03-05 11:16 | 2020-03-06 | 3 | 0 | 3 | 2020-03-12 | 2020-03-27 | 11 | 0 | 11 | [20 empty] | 2020-04-03 | 2020-03-05 15:43 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | AMESBURY | 245163 | 1913 | 8256 | Solar | 14_275L2 | 2020-03-05 15:43 | 2020-03-06 | 15 | 11 | 4 | [10 empty] | 2020-03-27 | 2020-05-21 | 38 | 19 | 19 | [10 empty] | 2021-12-21 | 2020-03-05 15:51 | 2030-04-14 |  | STD | [9 empty] | Design |  | No
National Grid | PLAINVILLE | 278143 | 2762 | 4107 | Solar | 05_3451W3 | 2020-03-05 15:51 | 2020-03-06 | 9 | 7 | 2 | [10 empty] | 2020-03-19 | 2020-04-10 | 16 | 4 | 12 | [10 empty] | 2021-12-23 |  | 2024-02-22 | Yes | STD |  | 2023-09-26 | 2024-01-02 | 99 | 3 | 96 |  |  |  | Completion Documents |  | No
National Grid | HOPEDALE | 282586 | 1747 | 249 | Solar | 05_335W9 | 2020-03-05 17:46 | 2020-03-06 | 2 | 0 | 2 | 2020-03-11 | 2020-04-21 | 29 | 7 | 22 | 2020-04-22 | 2020-05-28 | 25 | 0 | 25 | [5 empty] | 2020-04-22 | 2020-05-28 | 25 | 0 | 25 | [5 empty] | 2020-05-28 |  | 2024-10-23 |  | EXP |  | 2020-12-23 |  | 1210 | 1061 | 149 |  |  |  | Construction |  | No
National Grid | NANTUCKET | 282436 | 2554 | 15.2 | Solar | 04_101L2 | 2020-03-05 18:31 | 2020-03-06 | 1 | 1 | 0 | 2020-03-10 | 2020-03-13 | 4 | 1 | 3 | [20 empty] | 2020-03-13 | 2020-03-06 16:20 | 2021-08-30 |  | EXP | [8 empty] | 2021-07-13 | Connected |  | No
National Grid | RANDOLPH | 276855 | 2368 | 10 | Solar | 07_97W1 | 2020-03-06 16:20 | 2020-03-09 | 36 | 35 | 1 | 2020-04-27 | 2020-05-07 | 8 | 0 | 8 | [20 empty] | 2020-05-07 |  | 2021-03-09 | Yes | EXP |  | 2020-07-29 | 2020-08-28 | 30 | 0 | 30 |  |  | 2020-10-07 | Connected |  | No
National Grid | FALL RIVER | 280777 | 2721 | 3.8 | Solar | 05_115W53 | 2020-03-10 10:22 | 2020-03-11 | 5 | 0 | 5 | 2020-03-19 | 2020-03-27 | 6 | 0 | 6 | [20 empty] | 2020-04-03 | 2020-03-10 13:03 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WINCHENDON | 268678 | 1475 | 5 | Solar | 01_607W5 | 2020-03-10 13:03 | 2020-03-11 | 18 | 18 | 0 | 2020-04-06 | 2020-04-23 | 12 | 0 | 12 | [20 empty] | 2020-04-24 |  | 2021-04-02 | Yes | EXP |  | 2020-09-03 | 2020-09-29 | 26 | 0 | 26 |  |  | 2020-12-08 | Connected |  | No
National Grid | WENHAM | 283128 | 1984 | 8.7 | Solar | 12_51T2 | 2020-03-10 14:07 | 2020-03-11 | 0 | 0 | 0 | 2020-03-12 | 2020-03-17 | 3 | 0 | 3 | [20 empty] | 2020-03-17 | 2020-03-11 09:56 | 2021-03-10 |  | EXP | [8 empty] | 2020-07-01 | Connected |  | No
National Grid | METHUEN | 281460 | 1844 | 10 | Solar | 14_74L4 | 2020-03-11 09:56 | 2020-03-23 | 0 | 0 | 0 | 2020-03-24 | 2020-03-27 | 3 | 0 | 3 | [20 empty] | 2020-03-30 |  | 2021-03-22 | Yes | EXP |  | 2020-05-27 | 2020-06-11 | 15 | 0 | 15 |  |  | 2020-06-15 | Connected |  | No
National Grid | WILLIAMSTOWN | 266810 | 1267 | 16.825 | Other | 09_1003W2 | 2020-03-11 10:47 | 2020-03-12 | 104 | 104 | 0 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | HARVARD | 283144 | 1451 | 7.6 | Solar | 01_201W2 | 2020-03-11 14:37 | 2020-03-12 | 34 | 26 | 8 | 2020-05-01 | 2020-05-20 | 13 | 0 | 13 | [20 empty] | 2020-05-26 |  | 2021-03-26 |  | EXP | [8 empty] | 2020-12-15 | Connected |  | No
National Grid | BOXFORD | 283459 | 1921 | 10 | Solar | 14_33L1 | 2020-03-12 11:12 | 2020-03-13 | 5 | 5 | 0 | 2020-03-20 | 2020-04-02 | 9 | 0 | 9 | [20 empty] | 2020-04-02 | 2020-03-12 12:30 | 2021-03-19 |  | EXP | [8 empty] | 2020-12-15 | Connected |  | No
National Grid | PEPPERELL | 274504 | 1462 | 6.38 | Solar | 01_210L1 | 2020-03-12 12:30 | 2020-03-13 | 1 | 1 | 0 | 2020-03-16 | 2020-03-27 | 9 | 0 | 9 | [20 empty] | 2020-03-30 |  | 2021-03-12 | Yes | EXP |  | 2020-06-30 | 2020-07-16 | 16 | 0 | 16 |  |  | 2020-07-20 | Connected |  | No
National Grid | HANOVER | 279002 | 2339 | 20.8 | Solar | 07_95W2 | 2020-03-13 08:19 | 2020-03-16 | 0 | 0 | 0 | 2020-03-17 | 2020-03-26 | 7 | 0 | 7 | [20 empty] | 2020-03-30 |  |  |  | EXP | [8 empty] | 2020-09-04 | Connected |  | No
National Grid | LYNN | 269148 | 1902 | 7.6 | Solar | 12_21J30 | 2020-03-16 13:25 | 2020-03-17 | 11 | 11 | 0 | 2020-04-02 | 2020-04-21 | 12 | 0 | 12 | [20 empty] | 2020-04-21 |  | 2021-04-01 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 265490 | 1507 | 4950 | Other | 01_415L1 | 2020-03-17 10:23 | 2020-03-18 | 27 | 24 | 3 | [10 empty] | 2020-04-27 | 2020-05-11 | 10 | 0 | 10 | [11 empty] | 2020-03-17 10:47 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 281257 | 1507 | 4948 | Other | 01_413L4 | 2020-03-17 10:47 | 2020-03-18 | 27 | 27 | 0 | [10 empty] | 2020-04-27 | 2020-05-09 | 10 | 0 | 10 | [12 empty] | 2025-03-05 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | NEWBURYPORT | 283910 | 1950 | 10 | Solar | 14_47L2 | 2020-03-17 12:01 | 2020-03-18 | 10 | 7 | 3 | 2020-04-02 | 2020-04-23 | 14 | 0 | 14 | [20 empty] | 2020-04-27 |  |  |  | EXP | [8 empty] | 2020-09-09 | Connected |  | Yes
National Grid | SEEKONK | 257553 | 2771 | 8.64 | Solar | 05_7L4 | 2020-03-17 15:21 | 2020-03-18 | 12 | 8 | 4 | 2020-04-06 | 2020-05-05 | 20 | 11 | 9 | [20 empty] | 2020-05-11 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH ANDOVER | 284117 | 1845 | 11.4 | Solar | 14_56L2 | 2020-03-17 17:19 | 2020-03-18 | 7 | 4 | 3 | [26 empty] | 2020-03-17 18:09 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BELLINGHAM | 284138 | 2019 | 15.2 | Solar | 05_344W4 | 2020-03-17 18:09 | 2020-03-18 | 19 | 19 | 0 | 2020-04-14 | 2020-05-07 | 16 | 0 | 16 | [20 empty] | 2020-05-07 |  | 2021-04-13 | Yes | EXP |  | 2020-07-15 | 2020-12-05 | 143 | 5 | 138 |  |  | 2020-12-16 | Connected |  | No
National Grid | NORTH ANDOVER | 284143 | 1845 | 12 | Solar | 14_56L2 | 2020-03-17 20:35 | 2020-03-18 | 13 | 13 | 0 | 2020-04-07 | 2020-04-23 | 11 | 0 | 11 | [20 empty] | 2020-04-24 |  | 2021-04-06 |  | EXP | [8 empty] | 2021-01-21 | Connected |  | No
National Grid | CHARLTON | 273360 | 1507 | 5000 | Other | 01_415L1 | 2020-03-19 14:28 | 2020-03-20 | 4 | 1 | 3 | [10 empty] | 2020-03-26 | 2020-04-07 | 8 | 0 | 8 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | HUBBARDSTON | 282891 | 1565 | 4950 | Other | 01_602W2 | 2020-03-19 14:43 | 2020-03-20 | 5 | 1 | 4 | [10 empty] | 2020-03-30 | 2020-04-29 | 21 | 8 | 13 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | RANDOLPH | 278528 | 2368 | 3.8 | Solar | 07_5W3 | 2020-03-19 17:37 | 2020-03-20 | 25 | 25 | 0 | 2020-04-28 | 2020-05-18 | 14 | 0 | 14 | [20 empty] | 2020-05-19 |  | 2021-04-26 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EAST LONGMEADOW | 284615 | 1028 | 10 | Solar | 09_139L1 | 2020-03-20 15:30 | 2020-03-23 | 7 | 7 | 0 | 2020-04-01 | 2020-05-05 | 24 | 6 | 18 | [20 empty] | 2020-05-05 |  | 2021-03-31 |  | EXP | [8 empty] | 2020-07-22 | Connected |  | No
National Grid | MARLBOROUGH | 233162 | 1752 | 133.2 | Solar | 05_310W5 | 2020-03-23 | 2020-03-26 | 3 | 0 | 3 | 2020-04-01 | 2020-04-21 | 13 | 5 | 8 | [20 empty] | 2020-05-20 | 2020-03-23 10:21 | 2021-05-18 |  | EXP | [8 empty] | 2021-07-22 | Connected |  | No
National Grid | STURBRIDGE | 284646 | 1566 | 9.84 | Solar | 01_413L7 | 2020-03-23 10:21 | 2020-04-13 | 0 | 0 | 0 | 2020-04-14 | 2020-05-01 | 12 | 2 | 10 | [20 empty] | 2020-05-01 | 2020-03-23 13:19 | 2021-04-13 | Yes | EXP |  | 2020-07-30 | 2020-09-10 | 42 | 5 | 37 |  |  |  | Withdrawn |  | Yes
National Grid | BROCKTON | 284129 | 2302 | 999 | Solar | 07_91W47 | 2020-03-23 13:19 | 2020-03-24 | 14 | 9 | 5 | [10 empty] | 2020-04-13 | 2020-05-04 | 14 | 0 | 14 | [10 empty] | 2020-08-25 | 2020-03-25 10:02 | 2022-09-27 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | RANDOLPH | 285089 | 2368 | 7.68 | Solar | 07_97W4 | 2020-03-25 10:02 | 2020-03-26 | 4 | 0 | 4 | 2020-04-02 | 2020-04-23 | 14 | 0 | 14 | [20 empty] | 2020-04-27 | 2020-03-25 15:22 | 2021-10-21 | Yes | EXP |  | 2021-01-29 | 2021-03-12 | 42 | 0 | 42 |  |  | 2021-04-13 | Connected |  | No
National Grid | BROCKTON | 279970 | 2301 | 10 | Solar | 07_911W25 | 2020-03-25 15:22 | 2020-03-26 | 44 | 43 | 1 | 2020-05-27 | 2020-06-17 | 15 | 0 | 15 | [20 empty] | 2020-06-18 |  | 2021-05-25 | Yes | EXP |  | 2020-09-03 | 2020-09-24 | 21 | 0 | 21 |  |  | 2021-01-19 | Connected |  | No
National Grid | FOXBOROUGH | 285186 | 2035 | 9.57 | Solar | 05_3431W1 | 2020-03-25 15:23 | 2020-03-26 | 1 | 1 | 0 | 2020-03-27 | 2020-04-02 | 4 | 0 | 4 | [20 empty] | 2020-04-02 |  | 2021-03-25 |  | EXP | [8 empty] | 2020-10-21 | Connected |  | No
National Grid | UXBRIDGE | 285198 | 1569 | 10 | Solar | 05_321W2 | 2020-03-25 16:25 | 2020-03-26 | 2 | 2 | 0 | 2020-03-31 | 2020-04-23 | 16 | 0 | 16 | [20 empty] | 2020-04-23 |  | 2021-03-30 |  | EXP | [8 empty] | 2020-07-23 | Connected |  | No
National Grid | NORTH ANDOVER | 285219 | 1845 | 23.78 | Solar | 14_56L2 | 2020-03-25 16:30 | 2020-03-26 | 4 | 0 | 4 | 2020-04-02 | 2020-04-16 | 10 | 1 | 9 | [20 empty] | 2020-04-19 |  |  |  | EXP | [8 empty] | 2020-09-03 | Connected |  | No
National Grid | NORTHBOROUGH | 285220 | 1532 | 15.2 | Solar | 05_313W4 | 2020-03-25 16:34 | 2020-03-26 | 2 | 0 | 2 | 2020-03-31 | 2020-04-23 | 16 | 0 | 16 | [20 empty] | 2020-04-24 | 2020-03-25 18:28 |  |  | EXP | [8 empty] | 2020-07-31 | Connected |  | No
National Grid | MARLBOROUGH | 233157 | 1752 | 166.6 | Solar | 05_311W3 | 2020-03-25 18:28 | 2020-03-26 | 3 | 0 | 3 | [10 empty] | 2020-04-01 | 2020-06-08 | 47 | 30 | 17 | [10 empty] | 2020-12-30 |  | 2021-10-20 | Yes | STD |  | 2021-08-20 | 2021-08-19 | 0 | 0 | 0 |  |  | 2021-10-20 | Connected |  | No
National Grid | NORTHAMPTON | 284382 | 1062 | 10 | Solar | 09_909W4 | 2020-03-26 16:23 | 2020-03-27 | 8 | 8 | 0 | 2020-04-09 | 2020-04-15 | 4 | 0 | 4 | [20 empty] | 2020-04-15 | 2020-03-27 11:23 | 2021-04-08 |  | EXP | [8 empty] | 2020-08-13 | Connected |  | No
National Grid | NORTH ANDOVER | 285483 | 1845 | 9.28 | Solar | 14_56L3 | 2020-03-27 11:23 | 2020-03-30 | 2 | 2 | 0 | 2020-04-01 | 2020-04-23 | 15 | 0 | 15 | [20 empty] | 2020-04-24 |  | 2021-03-31 | Yes | EXP |  | 2020-06-09 | 2020-06-25 | 16 | 0 | 16 |  |  | 2020-10-07 | Connected |  | No
National Grid | HUBBARDSTON | 283891 | 1452 | 17.6 | Battery Add-On | 01_609W1 | 2020-03-30 09:31 | 2020-03-31 | 5 | 5 | 0 | 2020-04-07 | 2020-04-14 | 5 | 0 | 5 | [20 empty] | 2020-04-15 |  | 2021-04-06 |  | EXP | [8 empty] | 2020-06-29 | Connected |  | No
National Grid | NORTH DIGHTON | 285962 | 2764 | 15.2 | Solar | 05_19W73 | 2020-03-31 19:34 | 2020-04-01 | 0 | 0 | 0 | 2020-04-02 | 2020-04-23 | 14 | 0 | 14 | [20 empty] | 2020-04-24 | 2020-04-01 01:18 | 2021-04-01 |  | EXP | [8 empty] | 2020-10-23 | Connected |  | No
National Grid | DRACUT | 285172 | 1826 | 5 | Solar | 14_21L1 | 2020-04-01 01:18 | 2020-05-21 | 5 | 4 | 1 | 2020-05-29 | 2020-06-24 | 18 | 0 | 18 | [20 empty] | 2020-06-29 |  | 2021-05-28 | Yes | EXP |  | 2020-10-24 | 2020-11-19 | 26 | 0 | 26 |  |  | 2020-11-20 | Connected |  | No
National Grid | LAWRENCE | 285114 | 1841 | 7.6 | Solar | 14_6J3 | 2020-04-01 08:41 | 2020-04-21 | 1 | 0 | 1 | 2020-04-23 | 2020-05-07 | 10 | 0 | 10 | [20 empty] | 2020-05-14 | 2020-04-01 12:02 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LENOX | 278382 | 1240 | 10 | Solar | 09_1103W1 | 2020-04-01 12:02 | 2020-04-02 | 1 | 1 | 0 | 2020-04-06 | 2020-04-24 | 13 | 0 | 13 | [20 empty] | 2020-04-24 |  | 2021-04-02 | Yes | EXP |  | 2020-06-06 | 2020-07-08 | 32 | 0 | 32 |  |  | 2020-08-25 | Connected |  | No
National Grid | MANCHESTER | 286147 | 1944 | 15.36 | Solar | 12_51T1 | 2020-04-01 18:53 | 2020-04-02 | 1 | 0 | 1 | 2020-04-06 | 2020-04-23 | 12 | 0 | 12 | [20 empty] | 2020-04-27 |  | 2021-10-22 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SPENCER | 281057 | 1562 | 10 | Solar | 01_552L1 | 2020-04-06 11:52 | 2020-04-07 | 16 | 16 | 0 | [26 empty] | 2020-04-06 11:58 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FALL RIVER | 281069 | 2721 | 5 | Solar | 05_115W53 | 2020-04-06 11:58 | 2020-04-07 | 9 | 9 | 0 | 2020-04-21 | 2020-05-04 | 9 | 0 | 9 | [20 empty] | 2020-05-05 | 2020-04-06 16:59 | 2021-04-19 | Yes | EXP |  | 2020-07-03 | 2020-07-31 | 28 | 0 | 28 |  |  | 2020-08-12 | Connected |  | Yes
National Grid | RANDOLPH | 282704 | 2368 | 7.6 | Solar | 07_5W3 | 2020-04-06 16:59 | 2020-04-07 | 2 | 2 | 0 | 2020-04-09 | 2020-04-23 | 9 | 0 | 9 | [20 empty] | 2020-04-23 | 2020-04-06 17:13 | 2021-04-07 | Yes | EXP |  | 2020-09-23 | 2020-10-08 | 15 | 0 | 15 |  |  | 2020-11-17 | Connected |  | No
National Grid | FRANKLIN | 286629 | 2038 | 7.6 | Solar | 05_348W7 | 2020-04-06 17:13 | 2020-04-07 | 2 | 0 | 2 | 2020-04-10 | 2020-05-20 | 28 | 16 | 12 | [20 empty] | 2020-05-26 |  | 2021-04-03 | Yes | EXP |  | 2020-07-28 | 2021-01-09 | 165 | 5 | 160 |  |  | 2021-01-14 | Connected |  | No
National Grid | NORTHBOROUGH | 286585 | 1532 | 250 | Solar | 05_313W4 | 2020-04-07 | 2020-04-09 | 2 | 0 | 2 | 2020-04-13 | 2020-04-23 | 7 | 1 | 6 | [20 empty] | 2020-06-02 |  | 2021-06-13 |  | EXP | [8 empty] | 2021-11-09 | Connected |  | No
National Grid | UPTON | 286836 | 1568 | 15.2 | Solar | 05_312W4 | 2020-04-07 11:04 | 2020-04-08 | 0 | 0 | 0 | 2020-04-09 | 2020-04-14 | 3 | 0 | 3 | [20 empty] | 2020-04-15 |  | 2021-04-07 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | RUTLAND | 284371 | 1543 | 4950 | Other | 01_55W1 | 2020-04-07 12:53 | 2020-04-08 | 12 | 9 | 3 | [10 empty] | 2020-04-27 | 2020-05-09 | 10 | 0 | 10 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | RUTLAND | 282553 | 1543 | 4950 | Other | 01_55W1 | 2020-04-07 14:33 | 2020-04-08 | 12 | 9 | 3 | [10 empty] | 2020-04-27 | 2020-05-09 | 10 | 0 | 10 | [11 empty] | 2020-04-08 14:56 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTHAMPTON | 281120 | 1060 | 3 | Solar | 09_901W3 | 2020-04-08 14:56 | 2020-04-09 | 1 | 1 | 0 | 2020-04-13 | 2020-04-23 | 7 | 0 | 7 | [20 empty] | 2020-04-24 | 2020-04-09 14:32 | 2021-04-09 | Yes | EXP |  | 2020-08-29 | 2020-09-09 | 11 | 0 | 11 |  |  | 2020-12-14 | Connected |  | No
National Grid | METHUEN | 282749 | 1844 | 10 | Solar | 14_63L1 | 2020-04-09 14:32 | 2020-04-10 | 6 | 4 | 2 | 2020-04-22 | 2020-05-06 | 10 | 0 | 10 | [20 empty] | 2020-05-11 | 2020-04-09 17:41 | 2021-03-12 | Yes | EXP |  | 2020-08-25 | 2020-10-13 | 49 | 0 | 49 |  |  | 2020-10-22 | Connected |  | No
National Grid | SAUGUS | 276489 | 1906 | 400 | Solar | 12_25W1 | 2020-04-09 17:41 | 2020-04-10 | 7 | 2 | 5 | [10 empty] | 2020-04-23 | 2020-06-01 | 27 | 7 | 20 | [10 empty] | 2020-10-23 | 2020-04-09 19:06 | 2022-05-13 | Yes | STD | [9 empty] | Withdrawn |  | Yes
National Grid | WESTBOROUGH | 287290 | 1581 | 29.72 | Solar | 05_312W1 | 2020-04-09 19:06 | 2020-04-10 | 0 | 0 | 0 | 2020-04-13 | 2020-05-04 | 14 | 2 | 12 | [20 empty] | 2020-05-05 | 2020-04-10 13:25 | 2021-04-09 | Yes | EXP |  | 2020-09-05 | 2020-11-10 | 66 | 0 | 66 |  |  | 2021-02-23 | Connected |  | No
National Grid | HANOVER | 287429 | 2339 | 11.4 | Solar | 07_95W5 | 2020-04-10 13:25 | 2020-04-13 | 11 | 11 | 0 | 2020-04-30 | 2020-05-18 | 12 | 0 | 12 | [20 empty] | 2020-05-19 |  | 2021-08-10 | Yes | EXP |  | 2020-08-27 | 2020-09-12 | 16 | 0 | 16 |  |  | 2021-07-13 | Connected |  | No
National Grid | ROYALSTON | 287445 | 1368 | 10 | Solar | 09_701J1 | 2020-04-10 15:30 | 2020-04-13 | 13 | 12 | 1 | 2020-04-29 | 2020-05-18 | 13 | 0 | 13 | [20 empty] | 2020-05-18 | 2020-04-11 23:15 | 2021-04-27 |  | EXP | [8 empty] | 2020-08-20 | Connected |  | No
National Grid | PEMBROKE | 286960 | 2359 | 100.8 | Solar | 07_910W51 | 2020-04-11 23:15 | 2020-04-13 | 7 | 3 | 4 | [10 empty] | 2020-04-23 | 2020-06-04 | 30 | 7 | 23 | [10 empty] | 2022-01-04 |  | 2024-07-16 | Yes | STD | [9 empty] | Construction |  | No
National Grid | HANOVER | 287104 | 2339 | 300 | Solar | 07_96W44 | 2020-04-11 23:16 | 2020-04-13 | 7 | 3 | 4 | [10 empty] | 2020-04-23 | 2020-05-14 | 15 | 0 | 15 | [10 empty] | 2021-03-10 | 2020-04-13 10:03 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | PEMBROKE | 287125 | 2359 | 43.2 | Solar | 07_910W51 | 2020-04-13 10:03 | 2020-04-14 | 6 | 3 | 3 | [10 empty] | 2020-04-23 | 2020-06-04 | 30 | 7 | 23 | [10 empty] | 2022-01-04 |  | 2023-12-04 | Yes | STD | [8 empty] | 2023-05-26 | Connected |  | No
National Grid | DUNSTABLE | 257041 | 1827 | 4890 | Solar | 01_226L2 | 2020-04-13 14:20 | 2020-04-14 | 25 | 21 | 4 | [10 empty] | 2020-05-20 | 2020-06-18 | 20 | 0 | 20 | [10 empty] | 2021-07-29 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTBOROUGH | 287637 | 1581 | 200 | Solar | 05_312W5 | 2020-04-13 14:45 | 2020-04-14 | 3 | 0 | 3 | [10 empty] | 2020-04-21 | 2020-05-07 | 12 | 1 | 11 | [10 empty] | 2021-08-03 | 2020-04-13 14:53 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | REVERE | 279550 | 2151 | 7.6 | Solar | 12_16W8 | 2020-04-13 14:53 | 2020-04-14 | 8 | 8 | 0 | 2020-04-28 | 2020-05-17 | 13 | 0 | 13 | [20 empty] | 2020-05-18 |  | 2021-04-26 | Yes | EXP |  | 2020-08-18 | 2020-12-12 | 116 | 0 | 116 |  |  | 2020-12-16 | Connected |  | No
National Grid | SOUTHBRIDGE | 241223 | 1550 | 400 | Solar | 01_413L3 | 2020-04-14 | 2020-04-15 | 17 | 11 | 6 | [10 empty] | 2020-05-12 | 2020-06-24 | 30 | 13 | 17 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | MILFORD | 287738 | 1757 | 8 | Solar | 05_335W5 | 2020-04-14 09:04 | 2020-04-15 | 0 | 0 | 0 | 2020-04-15 | 2020-04-30 | 10 | 0 | 10 | [20 empty] | 2020-05-01 | 2020-04-14 09:30 | 2021-04-14 |  | EXP | [8 empty] | 2020-10-27 | Connected |  | No
National Grid | NORTON | 282466 | 2766 | 7.6 | Solar | 05_8L3 | 2020-04-14 09:30 | 2020-04-15 | 4 | 4 | 0 | 2020-04-22 | 2020-05-07 | 12 | 0 | 12 | [20 empty] | 2020-05-07 |  | 2021-04-20 | Yes | EXP |  | 2021-01-21 | 2021-02-08 | 18 | 0 | 18 |  |  | 2021-02-09 | Connected |  | No
National Grid | LANCASTER | 287761 | 1523 | 11.52 | Solar | 01_216W3 | 2020-04-14 10:58 | 2020-04-15 | 3 | 0 | 3 | 2020-04-21 | 2020-05-05 | 10 | 0 | 10 | [20 empty] | 2020-05-11 | 2020-04-14 16:07 | 2021-09-24 |  | EXP | [8 empty] | 2021-12-01 | Connected |  | No
National Grid | SOMERSET | 278585 | 2726 | 7.6 | Solar | 05_19W72 | 2020-04-14 16:07 | 2020-04-15 | 2 | 2 | 0 | 2020-04-17 | 2020-05-04 | 10 | 0 | 10 | [20 empty] | 2020-05-04 | 2020-04-14 16:45 | 2021-04-15 | Yes | EXP |  | 2020-06-24 | 2020-08-27 | 64 | 0 | 64 |  |  | 2020-10-05 | Connected |  | Yes
National Grid | BELLINGHAM | 281369 | 2019 | 7.6 | Solar | 05_344W4 | 2020-04-14 16:45 | 2020-04-15 | 3 | 0 | 3 | 2020-04-21 | 2020-05-04 | 9 | 0 | 9 | [20 empty] | 2020-05-06 |  | 2021-03-31 |  | EXP |  | 2020-12-23 | 2021-01-08 | 16 | 0 | 16 |  |  | 2021-02-18 | Connected |  | No
National Grid | MARLBOROUGH | 287875 | 1752 | 17.7 | Solar | 05_311W1 | 2020-04-15 | 2020-05-22 | 8 | 7 | 1 | 2020-06-04 | 2020-07-07 | 23 | 0 | 23 | [20 empty] | 2020-07-07 |  | 2021-07-30 |  | EXP | [8 empty] | 2021-04-26 | Connected |  | No
National Grid | SUTTON | 287978 | 1590 | 7.6 | Solar | 01_304W2 | 2020-04-15 12:53 | 2020-04-21 | 11 | 9 | 2 | 2020-05-07 | 2020-05-18 | 7 | 0 | 7 | [20 empty] | 2020-05-20 | 2020-04-15 17:12 | 2021-04-03 |  | EXP | [8 empty] | 2020-10-13 | Connected |  | No
National Grid | MARLBOROUGH | 233442 | 1752 | 400 | Solar | 05_311W3 | 2020-04-15 17:12 | 2020-04-16 | 32 | 25 | 7 | [10 empty] | 2020-06-05 | 2020-07-07 | 22 | 0 | 22 | [10 empty] | 2020-12-30 | 2020-04-16 15:59 | 2021-11-30 | Yes | STD |  | 2021-09-08 | 2021-09-07 | 0 | 0 | 0 |  |  | 2021-11-24 | Connected |  | No
National Grid | MARLBOROUGH | 287957 | 1752 | 200 | Solar | 05_311W3 | 2020-04-16 15:59 | 2020-04-17 | 32 | 25 | 7 | [10 empty] | 2020-06-05 | 2020-07-07 | 22 | 0 | 22 | [10 empty] | 2020-12-30 |  | 2022-09-06 | Yes | STD |  | 2022-05-10 | 2022-05-09 | 0 | 0 | 0 |  |  | 2022-05-19 | Connected |  | No
National Grid | PEPPERELL | 287295 | 1463 | 200 | Solar | 01_226L1 | 2020-04-17 | 2020-04-21 | 27 | 21 | 6 | 2020-06-01 | 2020-07-14 | 32 | 7 | 25 | [20 empty] | 2020-07-15 |  | 2021-09-09 |  | EXP | [8 empty] | 2021-08-24 | Connected |  | No
National Grid | STOUGHTON | 273993 | 2072 | 10 | Solar | 07_913W43 | 2020-04-17 09:28 | 2020-04-21 | 27 | 27 | 0 | 2020-05-29 | 2020-06-24 | 18 | 0 | 18 | [20 empty] | 2020-06-29 | 2020-04-17 10:23 | 2021-05-28 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SALEM | 286474 | 1970 | 3.8 | Solar | 12_29W2 | 2020-04-17 10:23 | 2020-04-21 | 1 | 0 | 1 | 2020-04-23 | 2020-05-17 | 16 | 0 | 16 | [20 empty] | 2020-05-20 |  | 2021-10-21 | Yes | EXP |  | 2021-04-13 | 2021-05-03 | 20 | 0 | 20 |  |  | 2021-09-03 | Connected |  | No
National Grid | WEYMOUTH | 261964 | 2188 | 24 | Natural Gas | 07_9W2 | 2020-04-17 13:40 | 2020-04-21 | 0 | 0 | 0 | [10 empty] | 2020-04-21 | 2020-11-17 | 147 | 135 | 12 | [10 empty] | 2021-08-10 | 2020-04-17 13:56 | 2023-01-20 |  | STD | [8 empty] | 2022-12-23 | Connected |  | No
National Grid | RANDOLPH | 285394 | 2368 | 6 | Solar | 07_5W4 | 2020-04-17 13:56 | 2020-04-21 | 12 | 12 | 0 | 2020-05-07 | 2020-05-18 | 7 | 0 | 7 | [20 empty] | 2020-05-19 |  | 2021-05-05 | Yes | EXP |  | 2020-07-29 | 2020-09-18 | 52 | 5 | 47 |  |  | 2020-09-23 | Connected |  | No
National Grid | WORCESTER | 279312 | 1604 | 7.6 | Solar | 01_9J337 | 2020-04-20 08:33 | 2020-04-21 | 4 | 4 | 0 | 2020-04-28 | 2020-05-18 | 14 | 0 | 14 | [20 empty] | 2020-05-19 | 2020-04-20 09:52 | 2021-04-26 |  | EXP | [8 empty] | 2020-11-04 | Connected |  | No
National Grid | BRIDGEWATER | 287863 | 2324 | 499.9 | Solar | 07_912W55 | 2020-04-20 09:52 | 2020-04-21 | 13 | 9 | 4 | [10 empty] | 2020-05-08 | 2020-06-18 | 28 | 10 | 18 | [10 empty] | 2021-01-07 | 2020-04-20 12:13 | 2024-05-25 | Yes | STD |  | 2022-02-11 |  | 794 | 661 | 133 |  |  |  | Construction |  | No
National Grid | LYNN | 285404 | 1905 | 7.6 | Solar | 12_21J37 | 2020-04-20 12:13 | 2020-04-21 | 4 | 4 | 0 | 2020-04-28 | 2020-05-17 | 13 | 0 | 13 | [20 empty] | 2020-05-18 |  | 2021-04-26 | Yes | EXP |  | 2020-12-10 | 2021-02-15 | 67 | 0 | 67 |  |  | 2021-02-22 | Connected |  | No
National Grid | STOUGHTON | 288745 | 2072 | 6.96 | Solar | 07_913W67 | 2020-04-21 15:48 | 2020-04-22 | 5 | 5 | 0 | 2020-04-29 | 2020-05-18 | 13 | 0 | 13 | [20 empty] | 2020-05-18 | 2020-04-22 13:40 | 2021-06-03 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEOMINSTER | 285851 | 1453 | 6 | Solar | 01_219W2 | 2020-04-22 13:40 | 2020-04-23 | 3 | 1 | 2 | 2020-04-28 | 2020-05-07 | 7 | 0 | 7 | [20 empty] | 2020-05-14 |  | 2022-04-28 | Yes | EXP |  | 2021-05-07 | 2021-06-23 | 47 | 0 | 47 |  |  | 2021-09-24 | Connected |  | No
National Grid | NORTHBOROUGH | 288940 | 1532 | 11.4 | Solar | 05_313W3 | 2020-04-22 16:00 | 2020-04-23 | 6 | 6 | 0 | 2020-05-01 | 2020-05-20 | 13 | 0 | 13 | [20 empty] | 2020-05-20 | 2020-04-23 13:33 | 2021-04-29 |  | EXP | [8 empty] | 2020-10-01 | Connected |  | No
National Grid | HARVARD | 289076 | 1451 | 7.68 | Solar | 01_216W6 | 2020-04-23 13:33 | 2020-04-24 | 1 | 0 | 1 | 2020-04-28 | 2020-05-07 | 7 | 0 | 7 | [20 empty] | 2020-05-14 |  | 2022-08-18 | Yes | EXP |  | 2020-12-02 | 2020-12-11 | 9 | 0 | 9 |  |  |  | Withdrawn |  | Yes
National Grid | WESTBOROUGH | 289142 | 1581 | 7.6 | Solar | 05_312W1 | 2020-04-23 17:05 | 2020-04-24 | 31 | 26 | 5 | 2020-06-10 | 2020-07-08 | 20 | 0 | 20 | [20 empty] | 2020-07-09 |  | 2021-06-09 |  | EXP | [8 empty] | 2020-12-21 | Connected |  | No
National Grid | RANDOLPH | 286931 | 2368 | 7.6 | Solar | 07_5W4 | 2020-04-24 11:05 | 2020-04-27 | 3 | 2 | 1 | 2020-04-30 | 2020-05-18 | 12 | 0 | 12 | [20 empty] | 2020-05-19 |  | 2021-04-28 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTBOROUGH | 287647 | 1581 | 616 | Solar | 05_312W5 | 2020-04-24 14:23 | 2020-04-27 | 8 | 3 | 5 | [10 empty] | 2020-05-07 | 2020-05-21 | 10 | 0 | 10 | [10 empty] | 2021-06-09 |  | 2022-08-24 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MEDFORD | 280051 | 2155 | 462.5 | Solar | 12_37W1 | 2020-04-24 16:18 | 2020-04-27 | 12 | 8 | 4 | [10 empty] | 2020-05-13 | 2020-06-18 | 11 | 4 | 7 | [10 empty] | 2021-03-30 |  |  |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | WENDELL | 270599 | 1379 | 2791 | Battery Add-On | 09_705W1 | 2020-04-24 20:02 | 2020-04-27 | 22 | 18 | 4 | [10 empty] | 2020-05-28 | 2020-07-09 | 31 | 13 | 18 | [11 empty] | 2020-04-27 12:19 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | AVON | 285958 | 2322 | 249 | Solar | 07_97W5 | 2020-04-27 12:19 | 2020-04-28 | 23 | 16 | 7 | 2020-06-01 | 2020-07-14 | 32 | 7 | 25 | [20 empty] | 2020-07-15 |  | 2025-06-02 | Yes | EXP | [9 empty] | Design |  | No
National Grid | SALEM | 277189 | 1970 | 3.36 | Solar | 12_49W6 | 2020-04-27 13:38 | 2020-04-28 | 2 | 0 | 2 | 2020-05-01 | 2020-05-20 | 14 | 2 | 12 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | REHOBOTH | 286728 | 2769 | 7.6 | Solar | 05_8L4 | 2020-04-28 09:13 | 2020-04-29 | 1 | 0 | 1 | 2020-05-01 | 2020-05-20 | 13 | 0 | 13 | [20 empty] | 2020-05-26 | 2020-04-28 10:21 | 2021-04-03 |  | EXP | [8 empty] | 2020-10-13 | Connected |  | No
National Grid | RANDOLPH | 282699 | 2368 | 7.6 | Solar | 07_5W3 | 2020-04-28 10:21 | 2020-04-29 | 2 | 2 | 0 | 2020-05-01 | 2020-05-20 | 13 | 0 | 13 | [20 empty] | 2020-05-21 | 2020-04-28 16:00 | 2021-04-29 | Yes | EXP |  | 2020-07-29 | 2020-09-15 | 49 | 5 | 44 |  |  | 2020-09-17 | Connected |  | No
National Grid | WORCESTER | 283927 | 1606 | 10 | Solar | 01_24W3 | 2020-04-28 16:00 | 2020-04-29 | 1 | 1 | 0 | 2020-04-30 | 2020-05-18 | 12 | 0 | 12 | [20 empty] | 2020-05-19 |  | 2021-04-28 | Yes | EXP |  | 2020-11-07 | 2021-01-06 | 60 | 0 | 60 |  |  | 2021-01-08 | Connected |  | No
National Grid | SWAMPSCOTT | 289689 | 1907 | 12.96 | Solar | 12_9J2 | 2020-04-28 16:24 | 2020-04-29 | 4 | 1 | 3 | 2020-05-06 | 2020-05-20 | 10 | 0 | 10 | [20 empty] | 2020-05-26 |  | 2021-04-03 |  | EXP | [8 empty] | 2020-11-18 | Connected |  | No
National Grid | MARLBOROUGH | 289784 | 1752 | 8.41 | Solar | 05_311W5 | 2020-04-29 11:13 | 2020-04-30 | 3 | 0 | 3 | 2020-05-06 | 2020-05-20 | 10 | 0 | 10 | [20 empty] | 2020-05-26 |  | 2021-04-03 |  | EXP | [8 empty] | 2021-01-21 | Connected |  | No
National Grid | ATHOL | 285646 | 1331 | 10 | Solar | 09_702W2 | 2020-04-29 11:32 | 2020-04-30 | 2 | 2 | 0 | 2020-05-05 | 2020-05-20 | 11 | 0 | 11 | [20 empty] | 2020-05-21 |  | 2021-05-03 |  | EXP | [8 empty] | 2020-11-24 | Connected |  | No
National Grid | BROCKTON | 234850 | 2301 | 7.6 | Solar | 07_797W19 | 2020-04-29 12:46 | 2020-04-30 | 27 | 26 | 1 | 2020-06-10 | 2020-06-28 | 13 | 0 | 13 | [20 empty] | 2020-06-29 | 2020-04-30 14:42 | 2021-06-08 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTHAMPTON | 217557 | 1060 | 7.6 | Solar | 09_905W1 | 2020-04-30 14:42 | 2020-05-01 | 2 | 2 | 0 | 2020-05-05 | 2020-05-20 | 11 | 0 | 11 | [20 empty] | 2020-05-21 | 2020-04-30 16:50 | 2021-05-03 | Yes | EXP |  | 2020-09-09 | 2020-09-08 | 0 | 0 | 0 |  |  | 2020-12-04 | Connected |  | No
National Grid | PEMBROKE | 288164 | 2359 | 52.2 | Solar | 07_910W51 | 2020-04-30 16:50 | 2020-05-01 | 5 | 4 | 1 | [10 empty] | 2020-05-11 | 2020-06-04 | 18 | 7 | 11 | [10 empty] | 2022-01-04 | 2020-04-30 16:54 | 2024-07-16 | Yes | STD | [9 empty] | Construction |  | No
National Grid | PEMBROKE | 287677 | 2359 | 95.4 | Solar | 07_910W51 | 2020-04-30 16:54 | 2020-05-01 | 6 | 5 | 1 | [10 empty] | 2020-05-11 | 2020-06-04 | 17 | 7 | 10 | [10 empty] | 2022-01-04 |  | 2024-07-16 | Yes | STD | [9 empty] | Construction |  | No
National Grid | PEMBROKE | 287869 | 2359 | 115.2 | Solar | 07_910W51 | 2020-04-30 17:07 | 2020-05-01 | 5 | 4 | 1 | [10 empty] | 2020-05-11 | 2020-06-04 | 17 | 7 | 10 | [11 empty] | 2020-04-30 18:55 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | PEMBROKE | 287871 | 2359 | 144 | Solar | 07_910W51 | 2020-04-30 18:55 | 2020-05-01 | 6 | 5 | 1 | [10 empty] | 2020-05-11 | 2020-06-04 | 17 | 7 | 10 | [10 empty] | 2022-01-04 | 2020-04-30 19:00 | 2024-07-16 | Yes | STD | [9 empty] | Construction |  | No
National Grid | PEMBROKE | 287773 | 2359 | 57.6 | Solar | 07_910W51 | 2020-04-30 19:00 | 2020-05-01 | 6 | 5 | 1 | [10 empty] | 2020-05-11 | 2020-06-04 | 17 | 7 | 10 | [10 empty] | 2022-01-04 | 2020-04-30 19:03 | 2023-12-05 | Yes | STD |  | 2023-01-28 | 2023-01-27 | 0 | 0 | 0 |  |  | 2023-05-26 | Connected |  | No
National Grid | PEMBROKE | 287680 | 2359 | 72 | Solar | 07_910W51 | 2020-04-30 19:03 | 2020-05-01 | 5 | 4 | 1 | [10 empty] | 2020-05-11 | 2020-06-04 | 18 | 5 | 13 | [10 empty] | 2022-01-04 | 2020-04-30 19:07 | 2023-12-04 | Yes | STD | [8 empty] | 2023-06-07 | Connected |  | No
National Grid | PEMBROKE | 287776 | 2359 | 144 | Solar | 07_910W51 | 2020-04-30 19:07 | 2020-05-01 | 5 | 4 | 1 | [10 empty] | 2020-05-11 | 2020-06-04 | 17 | 7 | 10 | [10 empty] | 2022-01-04 | 2020-04-30 19:11 | 2024-07-16 | Yes | STD | [9 empty] | Construction |  | No
National Grid | PEMBROKE | 287784 | 2359 | 72 | Solar | 07_910W51 | 2020-04-30 19:11 | 2020-05-01 | 5 | 4 | 1 | [10 empty] | 2020-05-11 | 2020-06-04 | 17 | 7 | 10 | [10 empty] | 2022-01-04 | 2020-04-30 19:15 | 2023-12-04 | Yes | STD | [8 empty] | 2023-08-14 | Connected |  | No
National Grid | PEMBROKE | 287867 | 2359 | 72 | Solar | 07_910W51 | 2020-04-30 19:15 | 2020-05-01 | 5 | 4 | 1 | [10 empty] | 2020-05-11 | 2020-06-04 | 17 | 7 | 10 | [10 empty] | 2022-01-04 | 2020-04-30 19:17 | 2023-12-04 | Yes | STD | [8 empty] | 2023-08-15 | Connected |  | No
National Grid | PEMBROKE | 287707 | 2359 | 72 | Solar | 07_910W51 | 2020-04-30 19:17 | 2020-05-01 | 5 | 4 | 1 | [10 empty] | 2020-05-11 | 2020-06-04 | 17 | 7 | 10 | [10 empty] | 2022-01-04 | 2020-04-30 19:25 | 2023-12-04 | Yes | STD | [8 empty] | 2023-08-15 | Connected |  | No
National Grid | PEMBROKE | 288988 | 2359 | 28.8 | Solar | 07_910W51 | 2020-04-30 19:25 | 2020-05-01 | 6 | 5 | 1 | [10 empty] | 2020-05-11 | 2020-06-04 | 18 | 8 | 10 | [10 empty] | 2022-01-04 | 2020-04-30 19:29 | 2023-12-05 | Yes | STD |  | 2023-01-28 | 2023-01-27 | 0 | 0 | 0 |  |  | 2023-05-26 | Connected |  | No
National Grid | PEMBROKE | 288162 | 2359 | 72 | Solar | 07_910W51 | 2020-04-30 19:29 | 2020-05-01 | 5 | 4 | 1 | [10 empty] | 2020-05-11 | 2020-06-04 | 18 | 7 | 11 | [10 empty] | 2022-01-04 |  | 2023-12-04 | Yes | STD |  | 2023-05-16 | 2023-05-30 | 14 | 0 | 14 |  |  | 2023-06-12 | Connected |  | No
National Grid | NORTH ANDOVER | 290152 | 1845 | 10 | Solar | 14_56L1 | 2020-05-01 14:43 | 2020-05-04 | 0 | 0 | 0 | 2020-05-05 | 2020-05-20 | 11 | 0 | 11 | [20 empty] | 2020-05-21 | 2020-05-04 10:53 | 2021-05-03 |  | EXP | [8 empty] | 2020-10-19 | Connected |  | No
National Grid | PEMBROKE | 288984 | 2359 | 300 | Solar | 07_910W51 | 2020-05-04 10:53 | 2020-05-05 | 5 | 2 | 3 | [10 empty] | 2020-05-12 | 2020-06-04 | 16 | 7 | 9 | [10 empty] | 2022-01-04 | 2020-05-04 11:02 | 2024-07-16 | Yes | STD | [9 empty] | Construction |  | No
National Grid | PEMBROKE | 286961 | 2359 | 366.6 | Solar | 07_910W51 | 2020-05-04 11:02 | 2020-05-05 | 6 | 2 | 4 | [10 empty] | 2020-05-13 | 2020-06-04 | 15 | 7 | 8 | [10 empty] | 2022-01-04 |  | 2024-07-16 | Yes | STD | [9 empty] | Construction |  | No
National Grid | BOLTON | 290294 | 1740 | 15.2 | Solar | 01_225W1 | 2020-05-04 11:07 | 2020-05-05 | 5 | 5 | 0 | 2020-05-12 | 2020-05-21 | 7 | 2 | 5 | [20 empty] | 2020-05-21 |  | 2021-05-10 |  | EXP | [8 empty] | 2020-07-31 | Connected |  | No
National Grid | BOXFORD | 290378 | 1921 | 40.6 | Solar | 14_56L3 | 2020-05-04 14:15 | 2020-05-05 | 5 | 0 | 5 | 2020-05-13 | 2020-08-13 | 66 | 56 | 10 | [20 empty] | 2020-08-17 |  | 2021-11-09 |  | EXP | [8 empty] | 2021-02-24 | Connected |  | No
National Grid | WESTFORD | 290418 | 1886 | 10 | Solar | 14_58L1 | 2020-05-04 15:34 | 2020-05-05 | 4 | 0 | 4 | 2020-05-12 | 2020-05-19 | 5 | 0 | 5 | [20 empty] | 2020-05-26 |  | 2021-04-30 |  | EXP | [8 empty] | 2020-11-21 | Connected |  | No
National Grid | AMESBURY | 290419 | 1913 | 10 | Solar | 14_5J13 | 2020-05-04 15:44 | 2020-05-05 | 2 | 2 | 0 | 2020-05-07 | 2020-05-18 | 7 | 0 | 7 | [20 empty] | 2020-05-18 |  | 2021-05-05 |  | EXP | [8 empty] | 2020-08-06 | Connected |  | No
National Grid | METHUEN | 290050 | 1844 | 7.6 | Solar | 14_5J44 | 2020-05-05 12:01 | 2020-05-06 | 48 | 48 | 0 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | SALEM | 290691 | 1970 | 21 | Battery Add-On | 12_49W4 | 2020-05-06 08:52 | 2020-05-07 | 0 | 0 | 0 | 2020-05-07 | 2020-05-18 | 7 | 0 | 7 | [20 empty] | 2020-05-21 | 2020-05-06 09:57 | 2021-05-06 |  | EXP | [8 empty] | 2020-06-15 | Connected |  | No
National Grid | ATTLEBORO | 285550 | 2703 | 10 | Solar | 05_8L1 | 2020-05-06 09:57 | 2020-05-07 | 1 | 0 | 1 | 2020-05-11 | 2020-05-18 | 5 | 0 | 5 | [20 empty] | 2020-08-04 |  | 2021-05-06 | Yes | EXP |  | 2020-09-30 | 2020-10-22 | 22 | 0 | 22 |  |  | 2020-10-28 | Connected |  | No
National Grid | LEICESTER | 285112 | 1524 | 4948 | Other | 01_2236W3 | 2020-05-06 10:26 | 2020-05-07 | 4 | 1 | 3 | [10 empty] | 2020-08-24 | 2020-10-20 | 39 | 24 | 15 | [11 empty] | 2020-05-06 11:48 |  |  | STD | [9 empty] | Group Study |  | No
National Grid | SOUTHBRIDGE | 282511 | 1550 | 4948 | Other | 01_413L8 | 2020-05-06 11:48 | 2020-05-07 | 4 | 1 | 3 | [10 empty] | 2020-06-03 | 2020-06-26 | 16 | 0 | 16 | [12 empty] | 2025-04-09 | Yes | STD | [9 empty] | Group Study |  | No
National Grid | HANSON | 290756 | 2341 | 7.68 | Solar | 07_797W24 | 2020-05-06 12:00 | 2020-05-07 | 2 | 0 | 2 | 2020-05-12 | 2020-05-19 | 5 | 0 | 5 | [20 empty] | 2020-05-26 | 2020-05-06 12:05 | 2023-04-10 |  | EXP | [8 empty] | 2022-11-18 | Connected |  | No
National Grid | LYNN | 289054 | 1902 | 3 | Solar | 12_29W5 | 2020-05-06 12:05 | 2020-05-07 | 2 | 0 | 2 | 2020-05-12 | 2020-05-20 | 6 | 0 | 6 | [20 empty] | 2020-05-26 |  | 2021-10-21 | Yes | EXP |  | 2021-03-20 | 2021-05-04 | 45 | 0 | 45 |  |  | 2021-05-13 | Connected |  | No
National Grid | LANCASTER | 287827 | 1523 | 4950 | Other | 01_227W1 | 2020-05-06 12:15 | 2020-05-07 | 4 | 1 | 3 | [10 empty] | 2020-05-13 | 2020-06-02 | 13 | 1 | 12 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | HUBBARDSTON | 287828 | 1452 | 12000 | Other | 01_602W2 | 2020-05-06 12:37 | 2020-05-07 | 4 | 1 | 3 | [10 empty] | 2020-08-24 | 2020-10-20 | 39 | 25 | 14 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | LAWRENCE | 287307 | 1841 | 6 | Solar | 14_63L1 | 2020-05-06 13:33 | 2020-05-07 | 1 | 0 | 1 | 2020-05-11 | 2020-06-05 | 19 | 1 | 18 | [21 empty] | 2020-05-06 13:54 | 2020-06-30 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SWANSEA | 290789 | 2777 | 10 | Solar | 05_11W84 | 2020-05-06 13:54 | 2020-05-07 | 5 | 5 | 0 | 2020-05-15 | 2020-06-11 | 18 | 0 | 18 | [20 empty] | 2020-06-15 |  | 2021-05-07 |  | EXP |  | 2020-07-02 | 2020-08-31 | 59 | 0 | 59 |  |  | 2020-09-02 | Connected |  | No
National Grid | SOUTHBRIDGE | 282071 | 1550 | 4950 | Other | 01_413L3 | 2020-05-06 14:20 | 2020-05-07 | 4 | 1 | 3 | [10 empty] | 2020-05-13 | 2020-06-10 | 19 | 1 | 18 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | PLAINVILLE | 290815 | 2762 | 7.6 | Solar | 05_3451W3 | 2020-05-06 15:30 | 2020-05-07 | 2 | 0 | 2 | 2020-05-12 | 2020-06-05 | 17 | 0 | 17 | [20 empty] | 2020-06-08 |  | 2021-11-22 |  | EXP | [8 empty] | 2022-02-10 | Connected |  | No
National Grid | LAWRENCE | 289256 | 1841 | 3.8 | Solar | 14_63L1 | 2020-05-06 16:47 | 2020-05-07 | 0 | 0 | 0 | 2020-05-08 | 2020-05-20 | 8 | 0 | 8 | [20 empty] | 2020-05-21 |  | 2021-05-06 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHELMSFORD | 290312 | 1824 | 9.6 | Solar | 14_16L4 | 2020-05-07 07:59 | 2020-05-08 | 3 | 0 | 3 | 2020-05-13 | 2020-06-05 | 43 | 22 | 21 | [20 empty] | 2020-06-08 | 2020-05-07 08:23 | 2022-04-07 |  | EXP | [8 empty] | 2021-11-10 | Connected |  | No
National Grid | HAMPDEN | 272367 | 1036 | 9.89 | Solar | 09_139L5 | 2020-05-07 08:23 | 2020-05-08 | 14 | 14 | 0 | 2020-05-29 | 2020-06-24 | 18 | 0 | 18 | [20 empty] | 2020-06-29 |  | 2021-05-28 | Yes | EXP |  | 2020-11-14 | 2020-12-10 | 26 | 0 | 26 |  |  | 2020-12-12 | Connected |  | No
National Grid | SEEKONK | 288310 | 2771 | 5000 | Other | 05_7L5 | 2020-05-07 11:47 | 2020-05-08 | 78 | 72 | 6 | [10 empty] | 2020-08-27 | 2021-04-29 | 166 | 34 | 132 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 288315 | 2301 | 5000 | Other | 07_91W43 | 2020-05-07 11:49 | 2020-05-08 | 77 | 70 | 7 | [10 empty] | 2020-08-27 | 2021-04-29 | 166 | 26 | 140 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | MILLBURY | 290832 | 1527 | 1.68 | Solar | 01_304W1 | 2020-05-07 17:45 | 2020-05-08 | 10 | 5 | 5 | 2020-05-22 | 2020-07-22 | 43 | 22 | 21 | [20 empty] | 2020-07-28 |  | 2022-06-21 |  | EXP | [8 empty] | 2022-04-25 | Connected |  | No
National Grid | PEMBROKE | 291004 | 2359 | 499 | Solar | 07_910W52 | 2020-05-08 10:06 | 2020-05-11 | 26 | 21 | 5 | 2020-06-17 | 2020-07-13 | 18 | 4 | 14 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | COHASSET | 288906 | 2025 | 24 | Solar | 07_96W41 | 2020-05-08 11:13 | 2020-05-11 | 1 | 1 | 0 | 2020-05-12 | 2020-05-19 | 5 | 0 | 5 | [20 empty] | 2020-05-20 | 2020-05-08 12:18 | 2021-05-11 |  | EXP | [8 empty] | 2020-08-21 | Connected |  | No
National Grid | GRAFTON | 291144 | 1519 | 9.996 | Solar | 01_304W1 | 2020-05-08 12:18 | 2020-05-11 | 2 | 0 | 2 | 2020-05-14 | 2020-06-11 | 20 | 2 | 18 | [20 empty] | 2020-06-15 |  | 2021-04-23 | Yes | EXP | [8 empty] | 2021-03-09 | Connected |  | No
National Grid | LAWRENCE | 291189 | 1841 | 7.6 | Solar | 14_8L2 | 2020-05-08 12:54 | 2020-05-11 | 0 | 0 | 0 | 2020-05-12 | 2020-05-20 | 6 | 0 | 6 | [20 empty] | 2020-05-21 | 2020-05-08 15:42 | 2021-05-11 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LYNN | 286083 | 1904 | 3.8 | Solar | 12_29W3 | 2020-05-08 15:42 | 2020-05-11 | 12 | 12 | 0 | 2020-05-28 | 2020-06-24 | 19 | 0 | 19 | [20 empty] | 2020-06-29 |  | 2021-05-26 | Yes | EXP |  | 2020-12-05 | 2021-01-06 | 32 | 0 | 32 |  |  | 2021-01-07 | Connected |  | No
National Grid | SEEKONK | 291280 | 2771 | 6 | Solar | 05_7L1 | 2020-05-10 18:56 | 2020-05-11 | 3 | 0 | 3 | 2020-05-15 | 2020-06-11 | 18 | 0 | 18 | [20 empty] | 2020-06-15 |  |  |  | EXP | [8 empty] | 2020-08-27 | Connected |  | No
National Grid | STOUGHTON | 290740 | 2072 | 7.6 | Solar | 07_75W1 | 2020-05-11 08:16 | 2020-05-12 | 8 | 7 | 1 | 2020-05-26 | 2020-10-02 | 95 | 72 | 23 | [20 empty] | 2020-10-05 | 2020-05-11 09:31 | 2021-11-29 |  | EXP | [8 empty] | 2021-11-19 | Connected |  | No
National Grid | SALEM | 291146 | 1970 | 7.54 | Solar | 12_49W2 | 2020-05-11 09:31 | 2020-05-12 | 0 | 0 | 0 | 2020-05-13 | 2020-06-10 | 20 | 4 | 16 | [20 empty] | 2020-06-11 |  | 2021-05-11 | Yes | EXP |  | 2020-09-11 | 2020-09-22 | 11 | 0 | 11 |  |  | 2020-11-18 | Connected |  | No
National Grid | BLACKSTONE | 289521 | 1504 | 4990 | Solar | 05_332W1 | 2020-05-11 10:58 | 2020-05-12 | 7 | 3 | 4 | [10 empty] | 2020-05-21 | 2020-06-23 | 22 | 3 | 19 | [11 empty] | 2020-05-11 12:11 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HARVARD | 291401 | 1451 | 20 | Battery Add-On | 01_225W1 | 2020-05-11 12:11 | 2020-05-12 | 0 | 0 | 0 | 2020-05-13 | 2020-06-08 | 18 | 2 | 16 | [20 empty] | 2020-06-10 | 2020-05-11 15:51 | 2021-05-11 | Yes | EXP |  | 2020-08-27 | 2020-09-10 | 14 | 0 | 14 |  |  | 2020-12-09 | Connected |  | No
National Grid | PEMBROKE | 290029 | 2359 | 233.3 | Solar | 07_910W51 | 2020-05-11 15:51 | 2020-05-12 | 1 | 0 | 1 | [10 empty] | 2020-05-14 | 2020-06-04 | 14 | 7 | 7 | [10 empty] | 2022-01-04 | 2020-05-11 15:54 | 2024-07-16 | Yes | STD | [9 empty] | Construction |  | No
National Grid | PEMBROKE | 289948 | 2359 | 233.3 | Solar | 07_910W51 | 2020-05-11 15:54 | 2020-05-12 | 1 | 0 | 1 | [10 empty] | 2020-05-14 | 2020-06-04 | 14 | 7 | 7 | [10 empty] | 2022-01-04 |  | 2024-07-16 | Yes | STD | [9 empty] | Construction |  | No
National Grid | NORTHBRIDGE | 291554 | 1534 | 11.4 | Solar | 05_320W3 | 2020-05-12 09:48 | 2020-05-13 | 1 | 0 | 1 | 2020-05-15 | 2020-07-29 | 53 | 32 | 21 | [20 empty] | 2020-08-03 |  | 2022-05-18 |  | EXP | [8 empty] | 2022-03-30 | Connected |  | Yes
National Grid | LAWRENCE | 273564 | 1841 | 360 | Natural Gas | 14_74L4 | 2020-05-12 15:27 | 2020-05-13 | 16 | 10 | 6 | [10 empty] | 2020-06-05 | 2020-07-07 | 23 | 2 | 21 | [10 empty] | 2022-09-21 |  |  |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | BOLTON | 289477 | 1740 | 12 | Solar | 01_225W1 | 2020-05-12 15:32 | 2020-05-13 | 0 | 0 | 0 | 2020-05-14 | 2020-06-05 | 15 | 0 | 15 | [20 empty] | 2020-06-05 |  | 2021-06-15 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MALDEN | 291626 | 2148 | 24.36 | Solar | 12_16J6 | 2020-05-12 19:38 | 2020-05-13 | 1 | 0 | 1 | 2020-05-15 | 2020-06-11 | 18 | 0 | 18 | [20 empty] | 2020-06-11 |  | 2021-05-13 |  | EXP | [8 empty] | 2020-12-03 | Connected |  | No
National Grid | SCITUATE | 291812 | 2066 | 11.4 | Solar | 07_915W82 | 2020-05-13 14:47 | 2020-05-14 | 22 | 17 | 5 | 2020-06-17 | 2021-01-19 | 148 | 130 | 18 | [20 empty] | 2021-01-21 |  | 2022-03-06 |  | EXP | [8 empty] | 2022-04-20 | Connected |  | No
National Grid | SOUTH EASTON | 291859 | 2375 | 43.2 | Solar | 07_92W79 | 2020-05-13 21:36 | 2020-05-14 | 2 | 1 | 1 | 2020-05-19 | 2020-06-19 | 22 | 0 | 22 | [20 empty] | 2020-06-22 |  |  |  | EXP | [8 empty] | 2020-08-21 | Connected |  | No
National Grid | FOXBOROUGH | 291839 | 2035 | 10 | Solar | 05_3422W3 | 2020-05-14 11:30 | 2020-05-15 | 11 | 7 | 4 | 2020-06-03 | 2020-06-24 | 15 | 0 | 15 | [20 empty] | 2020-06-25 |  |  |  | EXP | [8 empty] | 2020-07-30 | Connected |  | No
National Grid | HANOVER | 289008 | 2339 | 200 | Solar | 07_96W44 | 2020-05-14 13:28 | 2020-05-15 | 4 | 0 | 4 | [10 empty] | 2020-05-22 | 2020-06-25 | 23 | 0 | 23 | [10 empty] | 2021-03-10 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | GARDNER | 291986 | 1440 | 5.76 | Solar | 01_602W2 | 2020-05-14 14:35 | 2020-05-15 | 0 | 0 | 0 | 2020-05-18 | 2020-06-11 | 17 | 0 | 17 | [20 empty] | 2020-06-12 |  | 2021-05-14 |  | EXP | [8 empty] | 2020-10-20 | Connected |  | No
National Grid | MARLBOROUGH | 291983 | 1752 | 249 | Solar | 05_311W2 | 2020-05-14 14:42 | 2020-05-15 | 4 | 0 | 4 | 2020-05-22 | 2020-06-24 | 22 | 0 | 22 | [21 empty] | 2020-05-14 19:26 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 292050 | 2301 | 499 | Solar | 07_98W10 | 2020-05-14 19:26 | 2020-05-15 | 10 | 3 | 7 | [10 empty] | 2020-06-01 | 2020-06-24 | 17 | 0 | 17 | [10 empty] | 2020-12-31 |  | 2024-10-31 | Yes | STD | [9 empty] | Construction |  | No
National Grid | EAST BROOKFIELD | 289281 | 1515 | 4950 | Other | 01_525L2 | 2020-05-15 11:30 | 2020-05-18 | 6 | 0 | 6 | [10 empty] | 2020-05-28 | 2020-06-23 | 18 | 0 | 18 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SPENCER | 289954 | 1562 | 12000 | Other | 01_552L3 | 2020-05-15 14:22 | 2020-05-18 | 4 | 0 | 4 | [10 empty] | 2020-08-24 | 2020-10-24 | 43 | 27 | 16 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | ORANGE | 289276 | 1364 | 7998 | Other | 09_702W3 | 2020-05-15 14:31 | 2020-05-18 | 4 | 0 | 4 | [10 empty] | 2020-05-26 | 2020-06-18 | 17 | 0 | 17 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | LEEDS | 288067 | 1053 | 4950 | Other | 09_909W3 | 2020-05-15 14:49 | 2020-05-18 | 8 | 0 | 8 | [10 empty] | 2020-06-01 | 2020-07-30 | 43 | 25 | 18 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SPENCER | 288064 | 1562 | 10000 | Other | 01_552L1 | 2020-05-15 15:47 | 2020-05-18 | 6 | 0 | 6 | [10 empty] | 2020-08-24 | 2020-09-27 | 24 | 20 | 4 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 282050 | 1507 | 4950 | Other | 01_413L4 | 2020-05-15 15:53 | 2020-05-18 | 4 | 0 | 4 | [10 empty] | 2020-05-26 | 2020-06-18 | 17 | 0 | 17 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | HUBBARDSTON | 289990 | 1452 | 4950 | Other | 01_609W1 | 2020-05-16 13:18 | 2020-05-18 | 4 | 0 | 4 | [10 empty] | 2020-05-26 | 2020-06-18 | 17 | 0 | 17 | [11 empty] | 2020-05-18 07:59 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | FALL RIVER | 282338 | 2720 | 975 | Solar | 05_28W51 | 2020-05-18 07:59 | 2020-05-19 | 42 | 33 | 9 | [10 empty] | 2020-07-17 | 2020-08-11 | 17 | 0 | 17 | [10 empty] | 2021-04-23 | 2020-05-18 09:34 | 2024-07-04 | Yes | STD |  | 2022-04-20 | 2024-03-07 | 688 | 537 | 151 |  |  |  | Completion Documents |  | Yes
National Grid | BARRE | 291503 | 1005 | 20 | Solar | 09_604W1 | 2020-05-18 09:34 | 2020-05-19 | 9 | 9 | 0 | 2020-06-03 | 2020-06-26 | 17 | 0 | 17 | [20 empty] | 2020-06-29 |  | 2022-05-04 | Yes | EXP |  | 2021-03-13 | 2021-03-24 | 11 | 0 | 11 |  |  |  | Withdrawn |  | Yes
National Grid | EAST BRIDGEWATER | 290149 | 2333 | 996 | Solar | 07_797W42 | 2020-05-18 11:33 | 2020-05-19 | 24 | 17 | 7 | [10 empty] | 2020-06-24 | 2020-07-31 | 27 | 7 | 20 | [11 empty] | 2020-05-18 12:47 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LAWRENCE | 285209 | 1843 | 4.08 | Solar | 14_61L1 | 2020-05-18 12:47 | 2020-05-19 | 1 | 0 | 1 | 2020-05-21 | 2020-06-17 | 18 | 0 | 18 | [20 empty] | 2020-06-24 |  | 2021-04-03 | Yes | EXP |  | 2020-11-17 | 2021-02-08 | 83 | 0 | 83 |  |  |  | Withdrawn |  | Yes
National Grid | NORTH GRAFTON | 286667 | 1536 | 10 | Solar | 01_304W4 | 2020-05-18 12:56 | 2020-05-19 | 0 | 0 | 0 | 2020-05-20 | 2020-06-17 | 19 | 0 | 19 | [20 empty] | 2020-06-18 | 2020-05-18 13:18 | 2021-05-18 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEOMINSTER | 283064 | 1453 | 7.6 | Solar | 01_219W2 | 2020-05-18 13:18 | 2020-05-19 | 1 | 0 | 1 | 2020-05-21 | 2020-06-17 | 19 | 2 | 17 | [20 empty] | 2020-06-24 |  | 2022-08-11 | Yes | EXP |  | 2021-09-24 | 2021-10-12 | 11 | 0 | 11 |  |  | 2022-02-25 | Connected |  | No
National Grid | PHILLIPSTON | 291614 | 1331 | 500 | Solar | 09_701J1 | 2020-05-18 13:42 | 2020-05-19 | 25 | 16 | 9 | [10 empty] | 2020-06-25 | 2020-07-29 | 24 | 0 | 24 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | ABINGTON | 292499 | 2351 | 24.57 | Solar | 07_93W42 | 2020-05-19 11:51 | 2020-05-20 | 1 | 1 | 0 | 2020-05-21 | 2020-06-10 | 13 | 0 | 13 | [20 empty] | 2020-06-10 | 2020-05-19 16:13 | 2021-05-19 |  | EXP | [8 empty] | 2020-08-06 | Connected |  | No
National Grid | ATTLEBORO | 292596 | 2703 | 5 | Solar | 05_9L6 | 2020-05-19 16:13 | 2020-05-20 | 0 | 0 | 0 | 2020-05-21 | 2020-06-17 | 18 | 0 | 18 | [20 empty] | 2020-06-24 | 2020-05-19 16:27 | 2021-06-16 | Yes | EXP |  | 2021-03-05 | 2021-04-20 | 46 | 0 | 46 |  |  | 2021-05-25 | Connected |  | No
National Grid | REVERE | 269654 | 2151 | 7.6 | Solar | 12_16W7 | 2020-05-19 16:27 | 2020-05-20 | 29 | 26 | 3 | 2020-07-02 | 2020-07-28 | 18 | 0 | 18 | [20 empty] | 2020-07-28 |  | 2021-07-28 | Yes | EXP |  | 2020-12-05 | 2021-01-04 | 30 | 0 | 30 |  |  | 2021-06-03 | Connected |  | No
National Grid | SOMERSET | 291755 | 2726 | 7.6 | Solar | 05_18J5 | 2020-05-19 17:08 | 2020-05-20 | 0 | 0 | 0 | 2020-05-21 | 2020-06-10 | 13 | 0 | 13 | [20 empty] | 2020-06-15 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTFORD | 292702 | 1886 | 16 | Solar | 14_58L1 | 2020-05-20 10:20 | 2020-05-21 | 1 | 0 | 1 | 2020-05-26 | 2020-06-17 | 16 | 0 | 16 | [20 empty] | 2020-06-18 |  | 2021-05-20 |  | EXP | [8 empty] | 2020-07-29 | Connected |  | No
National Grid | EAST LONGMEADOW | 281671 | 1028 | 9.84 | Solar | 09_139L5 | 2020-05-20 14:40 | 2020-05-21 | 1 | 0 | 1 | 2020-05-26 | 2020-06-10 | 11 | 0 | 11 | [20 empty] | 2020-06-11 |  | 2021-05-20 |  | EXP | [8 empty] | 2020-09-15 | Connected |  | No
National Grid | GARDNER | 282444 | 1440 | 831 | Natural Gas | 01_607W3 | 2020-05-20 15:15 | 2020-05-21 | 31 | 25 | 6 | [10 empty] | 2020-07-07 | 2020-08-04 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | MANCHESTER | 292808 | 1944 | 12.6 | Battery Add-On | 12_51T1 | 2020-05-20 15:49 | 2020-05-21 | 6 | 5 | 1 | 2020-06-01 | 2020-11-05 | 112 | 53 | 59 | [21 empty] | 2020-05-20 16:18 | 2021-05-28 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SEEKONK | 292469 | 2771 | 24 | Solar | 05_9L5 | 2020-05-20 16:18 | 2020-05-21 | 2 | 0 | 2 | 2020-05-27 | 2020-08-31 | 69 | 50 | 19 | [20 empty] | 2020-09-08 | 2020-05-20 16:55 | 2021-10-12 | Yes | EXP | [9 empty] | Completion Documents |  | No
National Grid | MALDEN | 291578 | 2148 | 7.6 | Solar | 12_16W1 | 2020-05-20 16:55 | 2020-05-21 | 3 | 0 | 3 | 2020-05-28 | 2020-06-18 | 15 | 0 | 15 | [20 empty] | 2020-06-24 |  | 2021-09-09 | Yes | EXP | [8 empty] | 2021-06-24 | Connected |  | No
National Grid | WILLIAMSTOWN | 292650 | 1267 | 17 | Solar | 09_1003W2 | 2020-05-21 09:12 | 2020-05-22 | 0 | 0 | 0 | 2020-05-26 | 2020-06-17 | 16 | 0 | 16 | [20 empty] | 2020-06-18 |  | 2021-09-10 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | RANDOLPH | 292717 | 2368 | 18.4 | Battery Add-On | 07_5W2 | 2020-05-21 09:46 | 2020-05-22 | 10 | 10 | 0 | 2020-06-09 | 2020-06-28 | 14 | 0 | 14 | [20 empty] | 2020-06-29 | 2020-05-21 12:58 | 2021-06-08 |  | EXP | [8 empty] | 2020-11-12 | Connected |  | No
National Grid | LAWRENCE | 289216 | 1841 | 7.6 | Solar | 14_74L6 | 2020-05-21 12:58 | 2020-05-22 | 2 | 0 | 2 | 2020-05-28 | 2020-06-18 | 15 | 0 | 15 | [20 empty] | 2020-06-24 |  | 2021-09-17 | Yes | EXP |  | 2021-01-20 | 2021-01-28 | 8 | 0 | 8 |  |  | 2021-07-16 | Connected |  | No
National Grid | NORTH ANDOVER | 292996 | 1845 | 10 | Solar | 14_54L3 | 2020-05-21 15:28 | 2020-05-22 | 0 | 0 | 0 | 2020-05-26 | 2020-06-10 | 11 | 0 | 11 | [20 empty] | 2020-06-10 |  | 2021-05-21 |  | EXP | [8 empty] | 2020-09-04 | Connected |  | No
National Grid | FRANKLIN | 293030 | 2038 | 17.6 | Solar | 05_344W4 | 2020-05-21 18:00 | 2020-05-22 | 14 | 14 | 0 | 2020-06-15 | 2020-07-09 | 18 | 0 | 18 | [20 empty] | 2020-07-09 |  | 2021-06-11 |  | EXP | [8 empty] | 2020-11-12 | Connected |  | No
National Grid | SUTTON | 292740 | 1590 | 192 | Solar | 01_304W6 | 2020-05-22 07:38 | 2020-05-26 | 15 | 11 | 4 | 2020-06-17 | 2020-07-17 | 22 | 0 | 22 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | LEOMINSTER | 195313 | 1453 | 995 | Solar | 01_207W3 | 2020-05-22 11:56 | 2020-05-26 | 15 | 11 | 4 | [10 empty] | 2020-06-17 | 2020-07-14 | 19 | 1 | 18 | [10 empty] | 2021-02-26 | 2020-05-22 12:51 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 281490 | 2302 | 6 | Solar | 07_91W40 | 2020-05-22 12:51 | 2020-05-26 | 1 | 0 | 1 | 2020-05-28 | 2020-06-19 | 16 | 0 | 16 | [20 empty] | 2020-06-29 |  | 2022-05-12 | Yes | EXP |  | 2021-08-12 | 2021-08-28 | 15 | 3 | 12 |  |  | 2021-09-13 | Connected |  | No
National Grid | WESTBOROUGH | 293197 | 1581 | 7.6 | Solar | 05_312W5 | 2020-05-22 16:33 | 2020-05-26 | 38 | 38 | 0 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | GLOUCESTER | 291501 | 1930 | 3.8 | Solar | 12_51T1 | 2020-05-25 09:22 | 2020-05-26 | 0 | 0 | 0 | 2020-05-27 | 2020-06-17 | 15 | 0 | 15 | [20 empty] | 2020-06-18 | 2020-05-26 11:26 | 2021-05-25 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | HALIFAX | 279925 | 2338 | 2500 | Solar | 07_912W75 | 2020-05-26 11:26 | 2020-05-27 | 19 | 12 | 7 | [10 empty] | 2020-06-23 | 2020-07-23 | 23 | 4 | 19 | [10 empty] | 2021-06-29 |  | 2025-04-24 | Yes | STD |  | 2024-01-10 |  | 98 | 60 | 38 |  |  |  | Construction |  | No
National Grid | SALEM | 290730 | 1970 | 100 | Solar | 12_49W2 | 2020-05-26 15:06 | 2020-05-27 | 15 | 12 | 3 | 2020-06-17 | 2020-07-17 | 22 | 0 | 22 | [20 empty] | 2020-07-22 |  | 2022-08-10 |  | EXP | [8 empty] | 2022-08-19 | Connected |  | No
National Grid | AUBURN | 286480 | 1501 | 7.6 | Solar | 01_26W3 | 2020-05-26 17:11 | 2020-05-27 | 5 | 0 | 5 | 2020-06-04 | 2020-07-07 | 23 | 0 | 23 | [20 empty] | 2020-07-14 | 2020-05-27 09:18 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ESSEX | 293270 | 1929 | 20 | Battery Add-On | 12_51T2 | 2020-05-27 09:18 | 2020-05-28 | 7 | 7 | 0 | 2020-06-09 | 2020-08-13 | 48 | 26 | 22 | [20 empty] | 2020-08-13 |  | 2022-04-09 | Yes | EXP |  | 2021-03-10 | 2021-04-05 | 26 | 0 | 26 |  |  |  | Withdrawn |  | No
National Grid | ATHOL | 280094 | 1331 | 3.8 | Solar | 09_702W1 | 2020-05-27 09:51 | 2020-05-28 | 1 | 1 | 0 | 2020-05-29 | 2020-06-19 | 15 | 0 | 15 | [20 empty] | 2020-06-19 |  | 2021-05-27 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | AYER | 293316 | 1432 | 7.6 | Solar | 01_201W2 | 2020-05-27 09:53 | 2020-05-28 | 4 | 0 | 4 | 2020-06-04 | 2020-07-07 | 23 | 0 | 23 | [20 empty] | 2020-07-14 |  | 2021-05-03 |  | EXP | [8 empty] | 2020-10-16 | Connected |  | No
National Grid | STOCKBRIDGE | 293359 | 1262 | 20 | Solar | 09_1102W1 | 2020-05-27 12:24 | 2020-05-28 | 2 | 0 | 2 | 2020-06-02 | 2020-08-15 | 53 | 41 | 12 | [20 empty] | 2020-08-17 |  | 2021-06-02 |  | EXP | [8 empty] | 2020-12-16 | Connected |  | No
National Grid | HARVARD | 293500 | 1451 | 200 | Solar | 01_216W6 | 2020-05-27 14:27 | 2020-05-28 | 14 | 12 | 2 | 2020-06-17 | 2020-07-17 | 22 | 0 | 22 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEST BRIDGEWATER | 292016 | 2379 | 7.83 | Solar | 07_797W20 | 2020-05-27 15:44 | 2020-05-28 | 4 | 0 | 4 | 2020-06-04 | 2020-07-07 | 23 | 0 | 23 | [20 empty] | 2020-07-14 | 2020-05-28 10:55 | 2021-05-03 |  | EXP | [8 empty] | 2021-01-06 | Connected |  | No
National Grid | WORCESTER | 293766 | 1605 | 17.6 | Battery Add-On | 01_24W1 | 2020-05-28 10:55 | 2020-05-29 | 0 | 0 | 0 | 2020-06-01 | 2020-06-23 | 16 | 0 | 16 | [20 empty] | 2020-06-24 |  | 2021-05-28 | Yes | EXP |  | 2020-09-01 | 2020-09-29 | 28 | 0 | 28 |  |  | 2020-09-30 | Connected |  | No
National Grid | WARE | 288610 | 1082 | 3.8 | Solar | 09_501L2 | 2020-05-28 13:39 | 2020-05-29 | 26 | 26 | 0 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | DUDLEY | 293823 | 1571 | 8.88 | Solar | 01_412L2 | 2020-05-28 13:50 | 2020-05-29 | 3 | 0 | 3 | 2020-06-04 | 2020-07-07 | 23 | 0 | 23 | [20 empty] | 2020-07-14 |  | 2021-05-22 |  | EXP | [8 empty] | 2020-12-16 | Connected |  | No
National Grid | GLOUCESTER | 293839 | 1930 | 10 | Solar | 12_28L2 | 2020-05-28 14:04 | 2020-05-29 | 12 | 12 | 0 | 2020-06-16 | 2020-07-05 | 14 | 0 | 14 | [20 empty] | 2020-07-08 |  | 2021-06-14 |  | EXP | [8 empty] | 2020-08-05 | Connected |  | No
National Grid | WENHAM | 293961 | 1984 | 15.08 | Solar | 12_51T2 | 2020-05-29 09:50 | 2020-06-01 | 3 | 0 | 3 | 2020-06-05 | 2020-10-14 | 92 | 82 | 10 | [20 empty] | 2020-10-14 | 2020-05-29 13:33 |  |  | EXP | [8 empty] | 2021-07-17 | Connected |  | No
National Grid | FLORENCE | 287922 | 1062 | 2.4 | Solar | 09_909W4 | 2020-05-29 13:33 | 2020-06-01 | 0 | 0 | 0 | 2020-06-02 | 2020-06-26 | 18 | 0 | 18 | [20 empty] | 2020-06-29 |  | 2021-06-01 | Yes | EXP |  | 2020-10-08 | 2020-10-21 | 13 | 0 | 13 |  |  | 2020-11-10 | Connected |  | No
National Grid | NEWBURYPORT | 276671 | 1950 | 400 | Solar | 14_60L3 | 2020-05-29 14:21 | 2020-06-01 | 26 | 20 | 6 | [10 empty] | 2020-07-10 | 2020-08-10 | 21 | 0 | 21 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | BLACKSTONE | 294047 | 1504 | 15.2 | Solar | 05_108W60 | 2020-05-29 15:00 | 2020-06-01 | 3 | 0 | 3 | 2020-06-05 | 2020-07-27 | 36 | 16 | 20 | [20 empty] | 2020-07-30 |  | 2021-05-03 |  | EXP | [8 empty] | 2020-11-14 | Connected |  | No
National Grid | FOXBOROUGH | 290810 | 2035 | 400 | Solar | 05_3424W1 | 2020-05-29 15:28 | 2020-06-01 | 38 | 21 | 17 | [10 empty] | 2020-08-03 | 2020-08-18 | 11 | 0 | 11 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | MELROSE | 294223 | 2176 | 11 | Solar | 12_25W5 | 2020-06-01 11:11 | 2020-06-02 | 3 | 3 | 0 | 2020-06-05 | 2020-06-26 | 15 | 0 | 15 | [20 empty] | 2020-06-29 |  | 2021-06-01 |  | EXP | [8 empty] | 2020-10-27 | Connected |  | No
National Grid | BOXFORD | 294246 | 1921 | 20 | Solar | 14_33L1 | 2020-06-01 11:46 | 2020-06-02 | 0 | 0 | 0 | 2020-06-03 | 2020-06-26 | 16 | 0 | 16 | [20 empty] | 2020-06-29 |  | 2021-06-01 |  | EXP | [8 empty] | 2021-02-16 | Connected |  | No
National Grid | BROCKTON | 293451 | 2301 | 1.92 | Solar | 07_98W46 | 2020-06-01 12:09 | 2020-06-02 | 2 | 0 | 2 | 2020-06-05 | 2020-06-29 | 16 | 0 | 16 | [20 empty] | 2020-06-29 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SOUTHFIELD | 292538 | 1259 | 7.6 | Solar | 09_1109W1 | 2020-06-02 09:08 | 2020-06-03 | 9 | 9 | 0 | 2020-06-16 | 2020-07-05 | 14 | 0 | 14 | [20 empty] | 2020-07-08 | 2020-06-02 12:10 | 2021-06-04 |  | EXP | [8 empty] | 2020-09-21 | Connected |  | No
National Grid | LEOMINSTER | 294443 | 1453 | 15.2 | Solar | 01_207W6 | 2020-06-02 12:10 | 2020-06-03 | 1 | 0 | 1 | 2020-06-05 | 2020-09-16 | 73 | 55 | 18 | [20 empty] | 2020-09-17 | 2020-06-02 16:03 | 2021-06-04 | Yes | EXP |  | 2021-01-20 | 2021-01-26 | 6 | 0 | 6 |  |  | 2021-04-29 | Connected |  | No
National Grid | SALEM | 270246 | 1970 | 6.3 | Solar | 12_2W1 | 2020-06-02 16:03 | 2020-06-03 | 1 | 0 | 1 | 2020-06-05 | 2020-07-07 | 22 | 0 | 22 | [20 empty] | 2020-07-14 |  | 2021-05-06 | Yes | EXP | [8 empty] | 2021-02-06 | Connected |  | No
National Grid | SUTTON | 294263 | 1590 | 10 | Solar | 01_304W6 | 2020-06-02 19:21 | 2020-06-03 | 8 | 8 | 0 | 2020-06-16 | 2020-07-09 | 17 | 0 | 17 | [20 empty] | 2020-07-09 | 2020-06-03 15:32 | 2021-06-14 |  | EXP | [8 empty] | 2021-02-17 | Connected |  | No
National Grid | MEDFORD | 294723 | 2155 | 8 | Solar | 12_11J13 | 2020-06-03 15:32 | 2020-06-04 | 17 | 14 | 3 | 2020-06-30 | 2020-07-23 | 17 | 0 | 17 | [20 empty] | 2020-07-24 |  | 2021-09-09 | Yes | EXP |  | 2020-12-11 | 2021-02-05 | 56 | 0 | 56 |  |  | 2021-02-19 | Connected |  | No
National Grid | BLACKSTONE | 294931 | 1504 | 8.88 | Solar | 05_321W9 | 2020-06-04 14:35 | 2020-06-05 | 9 | 9 | 0 | 2020-06-18 | 2020-07-05 | 12 | 0 | 12 | [20 empty] | 2020-07-07 |  | 2021-06-14 |  | EXP | [8 empty] | 2020-10-20 | Connected |  | No
National Grid | MENDON | 294557 | 1756 | 20 | Solar | 05_332W1 | 2020-06-04 20:35 | 2020-06-05 | 4 | 2 | 2 | 2020-06-12 | 2020-07-08 | 18 | 0 | 18 | [20 empty] | 2020-07-09 |  | 2021-07-25 |  | EXP | [8 empty] | 2021-10-06 | Connected |  | No
National Grid | MEDFORD | 290620 | 2155 | 60 | Solar | 12_9C2 | 2020-06-05 10:05 | 2020-06-08 | 46 | 39 | 7 | 2020-08-11 | 2020-10-12 | 43 | 26 | 17 | [20 empty] | 2020-10-13 |  | 2021-05-14 |  | EXP | [8 empty] | 2021-03-15 | Connected |  | No
National Grid | NORTON | 295120 | 2766 | 10 | Solar | 05_4L2 | 2020-06-05 15:29 | 2020-06-08 | 3 | 2 | 1 | 2020-06-12 | 2020-06-29 | 11 | 0 | 11 | [20 empty] | 2020-07-06 |  | 2021-06-07 |  | EXP | [8 empty] | 2020-08-19 | Connected |  | No
National Grid | WESTFORD | 295174 | 1886 | 7.68 | Solar | 14_57L1 | 2020-06-05 17:36 | 2020-06-08 | 24 | 23 | 1 | 2020-07-10 | 2020-07-29 | 13 | 0 | 13 | [20 empty] | 2020-07-30 | 2020-06-06 12:29 | 2021-07-06 |  | EXP | [8 empty] | 2020-11-07 | Connected |  | No
National Grid | RUTLAND | 294525 | 1543 | 10 | Solar | 01_55W1 | 2020-06-06 12:29 | 2020-06-08 | 2 | 0 | 2 | 2020-06-11 | 2020-06-30 | 13 | 0 | 13 | [20 empty] | 2020-07-06 |  | 2021-10-07 | Yes | EXP |  | 2021-04-07 | 2021-04-15 | 8 | 0 | 8 |  |  | 2021-08-14 | Connected |  | No
National Grid | SOUTHBOROUGH | 295196 | 1772 | 17.6 | Battery Add-On | 05_310W5 | 2020-06-06 14:21 | 2020-06-08 | 2 | 0 | 2 | 2020-06-11 | 2020-07-08 | 19 | 0 | 19 | [20 empty] | 2020-07-14 |  | 2021-05-28 |  | EXP | [8 empty] | 2021-01-22 | Connected |  | No
National Grid | HANSON | 295316 | 2341 | 7.6 | Solar | 07_95W3 | 2020-06-08 12:27 | 2020-06-09 | 1 | 0 | 1 | 2020-06-11 | 2020-06-28 | 12 | 0 | 12 | [20 empty] | 2020-06-29 |  | 2021-05-28 |  | EXP | [8 empty] | 2020-12-14 | Connected |  | No
National Grid | SOUTHBOROUGH | 295368 | 1772 | 8.7 | Solar | 05_310W5 | 2020-06-08 14:24 | 2020-06-09 | 3 | 2 | 1 | 2020-06-15 | 2020-07-05 | 15 | 0 | 15 | [20 empty] | 2020-07-08 |  | 2021-06-08 |  | EXP | [8 empty] | 2020-09-17 | Connected |  | No
National Grid | WESTBOROUGH | 293153 | 1581 | 86 | Solar | 05_312W1 | 2020-06-08 15:10 | 2020-06-09 | 12 | 6 | 6 | 2020-06-25 | 2020-07-29 | 24 | 0 | 24 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | CHELMSFORD | 295384 | 1824 | 10 | Solar | 14_73L1 | 2020-06-08 15:25 | 2020-06-09 | 4 | 4 | 0 | 2020-06-16 | 2020-07-07 | 15 | 5 | 10 | [20 empty] | 2020-07-08 | 2020-06-08 16:55 | 2021-06-07 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 293829 | 1843 | 3.8 | Solar | 14_61L3 | 2020-06-08 16:55 | 2020-06-09 | 1 | 0 | 1 | 2020-06-11 | 2020-06-29 | 12 | 0 | 12 | [20 empty] | 2020-06-29 |  | 2021-11-11 | Yes | EXP |  | 2020-11-18 | 2020-12-09 | 21 | 0 | 21 |  |  | 2021-08-06 | Connected |  | No
National Grid | NORTH EASTON | 295460 | 2356 | 7.6 | Solar | 07_92W43 | 2020-06-09 08:23 | 2020-06-10 | 3 | 3 | 0 | 2020-06-16 | 2020-07-05 | 14 | 0 | 14 | [20 empty] | 2020-07-07 | 2020-06-09 09:51 | 2021-06-10 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEICESTER | 281119 | 1524 | 2400 | Natural Gas | 01_406L1 | 2020-06-09 09:51 | 2020-06-10 | 25 | 17 | 8 | [10 empty] | 2020-07-15 | 2020-08-04 | 14 | 0 | 14 | [10 empty] | 2021-10-13 | 2020-06-09 10:29 | 2023-09-19 | Yes | STD | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 290049 | 1841 | 8.19 | Solar | 14_8L2 | 2020-06-09 10:29 | 2020-06-10 | 3 | 0 | 3 | 2020-06-16 | 2020-07-08 | 16 | 0 | 16 | [20 empty] | 2020-07-14 |  | 2022-02-25 | Yes | EXP |  | 2021-04-14 | 2021-09-22 | 161 | 3 | 158 |  |  | 2021-11-17 | Connected |  | Yes
National Grid | GLOUCESTER | 292006 | 1930 | 10 | Solar | 12_51T1 | 2020-06-09 15:46 | 2020-06-10 | 5 | 5 | 0 | 2020-06-17 | 2020-07-13 | 18 | 0 | 18 | [20 empty] | 2020-07-14 |  | 2021-06-14 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOUTHBOROUGH | 289768 | 1772 | 166.6 | Solar | 05_317W3 | 2020-06-10 13:32 | 2020-06-11 | 18 | 13 | 5 | 2020-07-07 | 2020-08-09 | 24 | 3 | 21 | [20 empty] | 2020-09-11 |  | 2021-07-20 |  | EXP | [8 empty] | 2021-02-18 | Connected |  | No
National Grid | NORTHAMPTON | 295561 | 1060 | 16.25 | Battery Add-On | 09_909W2 | 2020-06-10 14:38 | 2020-06-11 | 27 | 25 | 2 | 2020-07-21 | 2020-08-14 | 17 | 0 | 17 | [20 empty] | 2020-08-14 | 2020-06-10 16:28 | 2021-07-20 |  | EXP | [8 empty] | 2020-12-09 | Connected |  | No
National Grid | RANDOLPH | 287352 | 2368 | 7.6 | Solar | 07_97W2 | 2020-06-10 16:28 | 2020-06-11 | 2 | 0 | 2 | 2020-06-16 | 2020-07-08 | 16 | 0 | 16 | [20 empty] | 2020-07-14 | 2020-06-10 16:38 | 2021-06-30 | Yes | EXP |  | 2021-01-29 | 2021-03-11 | 41 | 0 | 41 |  |  | 2021-06-06 | Connected |  | No
National Grid | BELCHERTOWN | 292836 | 1007 | 2.16 | Solar | 09_509L2 | 2020-06-10 16:38 | 2020-06-11 | 2 | 0 | 2 | 2020-06-16 | 2020-07-09 | 17 | 0 | 17 | [20 empty] | 2020-07-14 |  | 2021-06-01 |  | EXP |  | 2020-12-15 | 2021-01-05 | 21 | 0 | 21 |  |  | 2021-02-24 | Connected |  | No
National Grid | WEYMOUTH | 295847 | 2188 | 10 | Solar | 07_12W5 | 2020-06-10 17:12 | 2020-06-11 | 7 | 5 | 2 | 2020-06-22 | 2020-07-06 | 10 | 0 | 10 | [20 empty] | 2020-07-08 |  | 2021-06-14 |  | EXP | [8 empty] | 2021-01-13 | Connected |  | No
National Grid | BELCHERTOWN | 294641 | 1007 | 18 | Solar | 09_509L2 | 2020-06-11 11:35 | 2020-06-12 | 4 | 0 | 4 | 2020-06-19 | 2020-07-20 | 21 | 0 | 21 | [20 empty] | 2020-07-28 |  | 2021-06-01 |  | EXP | [8 empty] | 2020-10-13 | Connected |  | No
National Grid | HAVERHILL | 295965 | 1830 | 9.36 | Solar | 14_76L1 | 2020-06-11 12:34 | 2020-06-12 | 16 | 11 | 5 | 2020-07-07 | 2020-08-03 | 19 | 0 | 19 | [20 empty] | 2020-08-04 |  | 2021-07-01 |  | EXP | [8 empty] | 2020-10-21 | Connected |  | No
National Grid | LEICESTER | 293665 | 1542 | 8.4 | Solar | 01_21W2 | 2020-06-11 14:23 | 2020-06-12 | 11 | 6 | 5 | 2020-06-30 | 2020-07-06 | 4 | 0 | 4 | [20 empty] | 2020-07-08 | 2020-06-12 14:32 | 2021-07-08 |  | EXP | [8 empty] | 2020-10-23 | Connected |  | No
National Grid | WRENTHAM | 295996 | 2093 | 5 | Solar | 05_3422W1 | 2020-06-12 14:32 | 2020-06-15 | 1 | 0 | 1 | 2020-06-17 | 2020-07-09 | 16 | 0 | 16 | [20 empty] | 2020-07-10 |  | 2021-06-14 | Yes | EXP |  | 2020-12-04 | 2021-01-19 | 46 | 0 | 46 |  |  | 2021-05-19 | Connected |  | No
National Grid | WEYMOUTH | 296209 | 2191 | 12 | Solar | 07_6W2 | 2020-06-12 16:10 | 2020-06-15 | 10 | 6 | 4 | 2020-06-30 | 2020-07-07 | 5 | 0 | 5 | [20 empty] | 2020-07-08 |  | 2021-10-25 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BEVERLY | 295399 | 1915 | 24 | Battery Add-On | 12_51T1 | 2020-06-13 10:09 | 2020-06-15 | 5 | 4 | 1 | 2020-06-23 | 2020-11-16 | 102 | 81 | 21 | [20 empty] | 2020-11-18 |  | 2022-03-03 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTH BILLERICA | 295835 | 1862 | 7.6 | Solar | 14_70L1 | 2020-06-13 10:40 | 2020-06-15 | 3 | 0 | 3 | 2020-06-19 | 2020-07-20 | 21 | 0 | 21 | [20 empty] | 2020-07-28 |  | 2021-06-01 |  | EXP | [8 empty] | 2020-10-22 | Connected |  | No
National Grid | COHASSET | 295339 | 2025 | 10 | Solar | 07_96W41 | 2020-06-13 11:42 | 2020-06-15 | 3 | 0 | 3 | 2020-06-19 | 2020-07-05 | 11 | 0 | 11 | [20 empty] | 2020-07-09 | 2020-06-15 10:25 | 2021-06-01 |  | EXP | [8 empty] | 2020-12-19 | Connected |  | No
National Grid | REVERE | 294945 | 2151 | 10 | Solar | 12_35J3 | 2020-06-15 10:25 | 2020-06-16 | 2 | 0 | 2 | 2020-06-19 | 2020-07-09 | 14 | 0 | 14 | [20 empty] | 2020-07-14 |  | 2022-04-08 | Yes | EXP |  | 2021-01-21 | 2021-02-18 | 28 | 0 | 28 |  |  |  | Withdrawn |  | Yes
National Grid | ATTLEBORO | 263147 | 2703 | 2000 | Solar | 05_8L1 | 2020-06-15 13:41 | 2020-06-16 | 24 | 19 | 5 | [10 empty] | 2020-07-20 | 2020-08-11 | 16 | 0 | 16 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BYFIELD | 291579 | 1922 | 10 | Solar | 14_60L2 | 2020-06-15 16:37 | 2020-06-16 | 3 | 2 | 1 | 2020-06-19 | 2020-07-22 | 23 | 8 | 15 | [20 empty] | 2020-07-22 |  | 2021-06-16 |  | EXP | [8 empty] | 2021-01-13 | Connected |  | No
National Grid | NORTHBRIDGE | 294823 | 1534 | 10 | Solar | 05_320W1 | 2020-06-16 08:04 | 2020-06-17 | 8 | 4 | 4 | 2020-06-30 | 2020-07-29 | 21 | 0 | 21 | [20 empty] | 2020-07-29 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SAUGUS | 296623 | 1906 | 20 | Solar | 12_23W2 | 2020-06-16 11:17 | 2020-06-17 | 14 | 14 | 0 | 2020-07-08 | 2020-07-29 | 15 | 0 | 15 | [20 empty] | 2020-07-29 |  | 2021-08-16 |  | EXP | [8 empty] | 2021-07-29 | Connected |  | No
National Grid | SEEKONK | 296695 | 2771 | 11.52 | Solar | 05_7L1 | 2020-06-16 13:10 | 2020-06-17 | 1 | 0 | 1 | 2020-06-19 | 2020-08-25 | 47 | 26 | 21 | [21 empty] | 2020-06-16 14:06 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | DOUGLAS | 296412 | 1516 | 10 | Solar | 05_320W2 | 2020-06-16 14:06 | 2020-06-17 | 1 | 1 | 0 | 2020-06-19 | 2020-07-09 | 14 | 0 | 14 | [20 empty] | 2020-07-10 | 2020-06-16 16:40 | 2021-06-16 | Yes | EXP |  | 2020-08-20 | 2020-09-15 | 26 | 0 | 26 |  |  | 2021-01-29 | Connected |  | No
National Grid | NORWELL | 296764 | 2061 | 10 | Solar | 07_96W44 | 2020-06-16 16:40 | 2020-06-17 | 4 | 0 | 4 | 2020-06-24 | 2020-07-22 | 20 | 0 | 20 | [20 empty] | 2020-07-28 |  | 2023-10-25 | Yes | EXP |  | 2020-12-15 | 2021-01-15 | 31 | 0 | 31 |  |  |  | Withdrawn |  | Yes
National Grid | MARLBOROUGH | 296692 | 1752 | 10 | Solar | 05_311W6 | 2020-06-16 18:16 | 2020-06-17 | 1 | 0 | 1 | 2020-06-19 | 2020-08-28 | 51 | 26 | 25 | [20 empty] | 2020-09-02 |  | 2021-06-01 |  | EXP | [8 empty] | 2021-01-13 | Connected |  | No
National Grid | WORCESTER | 291970 | 1602 | 3.8 | Solar | 01_6W2 | 2020-06-16 18:49 | 2020-06-17 | 0 | 0 | 0 | 2020-06-18 | 2020-07-17 | 21 | 0 | 21 | [20 empty] | 2020-07-20 |  | 2021-06-16 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | UXBRIDGE | 293133 | 1569 | 8.64 | Solar | 05_321W6 | 2020-06-17 10:02 | 2020-06-18 | 30 | 28 | 2 | 2020-07-31 | 2020-08-09 | 6 | 0 | 6 | [20 empty] | 2020-08-11 |  | 2021-07-30 |  | EXP | [8 empty] | 2021-01-19 | Connected |  | No
National Grid | SOUTHBRIDGE | 293474 | 1550 | 7.92 | Solar | 01_413L1 | 2020-06-17 10:21 | 2020-06-18 | 16 | 12 | 4 | 2020-07-10 | 2020-07-29 | 13 | 0 | 13 | [20 empty] | 2020-07-30 | 2020-06-17 10:44 | 2021-07-09 |  | EXP | [8 empty] | 2021-01-08 | Connected |  | No
National Grid | METHUEN | 283578 | 1844 | 9.57 | Solar | 14_74L1 | 2020-06-17 10:44 | 2020-06-18 | 1 | 0 | 1 | 2020-06-22 | 2020-07-13 | 15 | 0 | 15 | [20 empty] | 2020-07-14 |  | 2021-06-17 | Yes | EXP |  | 2021-02-10 | 2021-04-09 | 58 | 0 | 58 |  |  | 2021-04-13 | Connected |  | No
National Grid | HAVERHILL | 267314 | 1832 | 48.24 | Solar | 14_48L4 | 2020-06-18 06:32 | 2020-06-19 | 17 | 17 | 0 | 2020-07-14 | 2020-11-12 | 80 | 57 | 23 | [20 empty] | 2020-12-05 |  | 2021-06-22 |  | EXP | [8 empty] | 2021-05-08 | Connected |  | No
National Grid | HAVERHILL | 296655 | 1832 | 7.6 | Solar | 14_74L5 | 2020-06-18 13:05 | 2020-06-19 | 2 | 0 | 2 | 2020-06-24 | 2020-07-14 | 14 | 0 | 14 | [20 empty] | 2020-07-21 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LAWRENCE | 297222 | 1841 | 249 | Solar | 14_6J2 | 2020-06-18 14:43 | 2020-06-19 | 4 | 3 | 1 | [10 empty] | 2020-06-25 | 2020-07-23 | 20 | 0 | 20 | [10 empty] | 2021-04-02 | 2020-06-19 11:03 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SOMERSET | 289859 | 2726 | 10 | Solar | 05_19W72 | 2020-06-19 11:03 | 2020-06-22 | 21 | 17 | 4 | 2020-07-22 | 2020-08-10 | 13 | 0 | 13 | [20 empty] | 2020-08-13 |  | 2021-08-01 | Yes | EXP |  | 2021-01-06 | 2021-02-23 | 48 | 0 | 48 |  |  | 2021-03-09 | Connected |  | No
National Grid | TYNGSBORO | 297374 | 1879 | 18 | Solar | 14_57L3 | 2020-06-19 11:35 | 2020-06-22 | 0 | 0 | 0 | 2020-06-23 | 2020-07-23 | 22 | 0 | 22 | [20 empty] | 2020-07-23 |  | 2021-08-01 |  | EXP | [8 empty] | 2021-02-03 | Connected |  | No
National Grid | HUBBARDSTON | 297418 | 1452 | 150 | Solar | 09_604W4 | 2020-06-19 15:11 | 2020-06-22 | 5 | 5 | 0 | 2020-06-29 | 2020-07-29 | 22 | 0 | 22 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTH CHELMSFORD | 297463 | 1863 | 10 | Solar | 14_73L2 | 2020-06-20 12:03 | 2020-06-22 | 1 | 0 | 1 | 2020-06-24 | 2020-07-13 | 13 | 0 | 13 | [20 empty] | 2020-07-21 |  | 2021-08-01 |  | EXP | [8 empty] | 2020-12-09 | Connected |  | No
National Grid | BOLTON | 297124 | 1740 | 15.2 | Solar | 01_225W1 | 2020-06-20 15:08 | 2020-06-22 | 1 | 0 | 1 | 2020-06-24 | 2020-07-14 | 14 | 0 | 14 | [20 empty] | 2020-07-21 |  | 2021-08-01 |  | EXP | [8 empty] | 2021-01-07 | Connected |  | Yes
National Grid | HUBBARDSTON | 297555 | 1452 | 84 | Solar | 09_604W4 | 2020-06-22 10:55 | 2020-06-23 | 4 | 4 | 0 | 2020-06-29 | 2020-07-29 | 22 | 0 | 22 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 292552 | 2302 | 10 | Solar | 07_911W56 | 2020-06-22 12:03 | 2020-06-23 | 148 | 18 | 130 | [27 empty] | 2021-06-10 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BONDSVILLE | 297681 | 1009 | 3.36 | Solar | 09_523L2 | 2020-06-22 15:35 | 2020-06-23 | 4 | 0 | 4 | 2020-06-30 | 2020-07-14 | 10 | 0 | 10 | [20 empty] | 2020-07-21 | 2020-06-23 14:01 | 2021-05-28 |  | EXP | [8 empty] | 2021-01-20 | Connected |  | No
National Grid | DRACUT | 292693 | 1826 | 7.6 | Solar | 14_75L3 | 2020-06-23 14:01 | 2020-06-24 | 0 | 0 | 0 | 2020-06-25 | 2020-07-22 | 19 | 0 | 19 | [20 empty] | 2020-07-23 |  | 2020-11-26 | Yes | EXP | [8 empty] | 2020-10-16 | Connected |  | No
National Grid | NORTON | 297939 | 2766 | 10 | Solar | 05_8L2 | 2020-06-23 15:44 | 2020-06-24 | 3 | 0 | 3 | 2020-06-30 | 2020-07-29 | 21 | 0 | 21 | [20 empty] | 2020-08-03 |  | 2021-08-01 |  | EXP | [8 empty] | 2021-01-29 | Connected |  | No
National Grid | HOLBROOK | 296127 | 2343 | 9.57 | Solar | 07_2W1 | 2020-06-23 22:07 | 2020-06-24 | 3 | 0 | 3 | 2020-06-30 | 2020-07-07 | 5 | 0 | 5 | [20 empty] | 2020-07-14 |  |  |  | EXP | [8 empty] | 2020-11-05 | Connected |  | No
National Grid | HARVARD | 298017 | 1451 | 10 | Solar | 01_216W6 | 2020-06-24 06:20 | 2020-06-25 | 2 | 0 | 2 | 2020-06-30 | 2020-07-14 | 10 | 0 | 10 | [20 empty] | 2020-07-21 | 2020-06-25 10:01 | 2021-08-01 |  | EXP | [8 empty] | 2020-11-20 | Connected |  | No
National Grid | SOMERSET | 292543 | 2725 | 3.8 | Solar | 05_11W84 | 2020-06-25 10:01 | 2020-06-26 | 1 | 0 | 1 | 2020-06-30 | 2020-07-24 | 18 | 0 | 18 | [20 empty] | 2020-07-28 | 2020-06-25 13:43 | 2021-08-01 |  | EXP |  | 2020-12-16 | 2021-01-25 | 40 | 0 | 40 |  |  | 2021-02-09 | Connected |  | No
National Grid | STOUGHTON | 298308 | 2072 | 96 | Solar | 07_94W44 | 2020-06-25 13:43 | 2020-06-26 | 7 | 4 | 3 | 2020-07-07 | 2020-08-10 | 24 | 0 | 24 | [20 empty] | 2020-08-21 | 2020-06-26 08:56 | 2022-04-26 | Yes | EXP |  | 2021-03-11 | 2021-04-21 | 41 | 0 | 41 |  |  |  | Withdrawn |  | No
National Grid | WILLIAMSTOWN | 293844 | 1267 | 10 | Solar | 09_1001W1 | 2020-06-26 08:56 | 2020-06-29 | 10 | 5 | 5 | 2020-07-13 | 2020-08-23 | 30 | 13 | 17 | [20 empty] | 2020-08-24 |  | 2021-07-09 | Yes | EXP |  | 2020-12-12 | 2021-05-26 | 165 | 0 | 165 |  |  | 2021-05-27 | Connected |  | No
National Grid | HARVARD | 298159 | 1451 | 10 | Solar | 01_201W2 | 2020-06-26 10:09 | 2020-06-29 | 6 | 1 | 5 | 2020-07-08 | 2020-08-11 | 23 | 0 | 23 | [20 empty] | 2020-08-11 |  | 2021-07-01 |  | EXP | [8 empty] | 2020-11-04 | Connected |  | No
National Grid | LYNN | 290811 | 1904 | 10 | Solar | 12_29W4 | 2020-06-26 10:32 | 2020-06-29 | 5 | 0 | 5 | 2020-07-07 | 2020-08-03 | 19 | 0 | 19 | [20 empty] | 2020-08-05 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEST STOCKBRIDGE | 288929 | 1266 | 1000 | Solar | 09_1109W3 | 2020-06-26 12:19 | 2020-06-29 | 13 | 8 | 5 | [10 empty] | 2020-07-16 | 2020-08-08 | 17 | 0 | 17 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BEVERLY | 298665 | 1915 | 10 | Solar | 12_51T1 | 2020-06-26 15:49 | 2020-06-29 | 6 | 1 | 5 | 2020-07-07 | 2020-08-03 | 19 | 0 | 19 | [20 empty] | 2020-08-03 | 2020-06-26 16:04 | 2021-06-28 |  | EXP | [8 empty] | 2020-10-19 | Connected |  | No
National Grid | WORCESTER | 261693 | 1606 | 4900 | Natural Gas | 01_13J358 | 2020-06-26 16:04 | 2020-06-29 | 8 | 0 | 8 | [10 empty] | 2020-07-10 | 2020-08-19 | 29 | 9 | 20 | [10 empty] | 2021-04-07 |  | 2022-11-01 | Yes | STD |  | 2022-06-08 | 2022-10-19 | 134 | 0 | 134 |  |  | 2022-10-26 | Connected |  | No
National Grid | WORCESTER | 291231 | 1602 | 7.6 | Solar | 01_1J390 | 2020-06-26 18:02 | 2020-06-29 | 7 | 6 | 1 | 2020-07-09 | 2020-08-29 | 36 | 26 | 10 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | EVERETT | 298842 | 2149 | 7.6 | Solar | 12_16W7 | 2020-06-29 12:51 | 2020-06-30 | 39 | 38 | 1 | 2020-08-25 | 2020-09-15 | 14 | 0 | 14 | [20 empty] | 2020-09-16 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | FALL RIVER | 225621 | 2720 | 233.3 | Solar | 05_28W40 | 2020-06-29 13:22 | 2020-06-30 | 5 | 4 | 1 | 2020-07-07 | 2020-08-09 | 24 | 3 | 21 | [20 empty] | 2020-09-10 |  | 2021-08-13 |  | EXP | [8 empty] | 2021-08-06 | Connected |  | No
National Grid | MARLBOROUGH | 297691 | 1752 | 66.6 | Solar | 05_311W3 | 2020-06-30 13:23 | 2020-07-01 | 18 | 18 | 0 | 2020-07-28 | 2020-09-02 | 27 | 3 | 24 | [20 empty] | 2020-09-14 |  | 2021-09-10 |  | EXP | [8 empty] | 2021-08-19 | Connected |  | No
National Grid | METHUEN | 296373 | 1844 | 6.93 | Solar | 14_8L2 | 2020-06-30 13:30 | 2020-07-01 | 10 | 7 | 3 | 2020-07-15 | 2020-08-10 | 18 | 0 | 18 | [20 empty] | 2020-08-12 |  | 2021-06-29 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HAWLEY | 299097 | 1339 | 5.76 | Solar | 09_1019W1 | 2020-06-30 14:07 | 2020-07-01 | 6 | 2 | 4 | 2020-07-09 | 2020-07-29 | 14 | 0 | 14 | [20 empty] | 2020-07-30 |  | 2021-07-07 |  | EXP | [8 empty] | 2020-10-21 | Connected |  | No
National Grid | MANCHESTER | 299137 | 1944 | 8 | Solar | 12_23H2 | 2020-06-30 16:33 | 2020-07-01 | 20 | 16 | 4 | 2020-07-30 | 2020-10-23 | 58 | 41 | 17 | [22 empty] | 2021-07-29 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTFORD | 297469 | 1886 | 15.2 | Solar | 14_57L3 | 2020-06-30 21:05 | 2020-07-01 | 3 | 0 | 3 | 2020-07-07 | 2020-08-03 | 19 | 0 | 19 | [20 empty] | 2020-08-04 |  | 2021-07-09 |  | EXP | [8 empty] | 2020-12-11 | Connected |  | No
National Grid | LOWELL | 284540 | 1850 | 5.67 | Solar | 14_75L5 | 2020-07-01 08:46 | 2020-07-02 | 3 | 0 | 3 | 2020-07-08 | 2020-08-10 | 23 | 0 | 23 | [20 empty] | 2020-08-11 | 2020-07-01 10:54 | 2021-07-05 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BELLINGHAM | 297438 | 2019 | 7.6 | Solar | 05_335W1 | 2020-07-01 10:54 | 2020-07-02 | 2 | 0 | 2 | 2020-07-07 | 2020-08-03 | 19 | 0 | 19 | [20 empty] | 2020-08-04 |  | 2021-06-01 | Yes | EXP |  | 2020-11-04 | 2021-02-12 | 100 | 0 | 100 |  |  | 2021-06-01 | Connected |  | No
National Grid | WESTFORD | 299279 | 1886 | 10 | Solar | 14_57L3 | 2020-07-01 12:56 | 2020-07-02 | 3 | 0 | 3 | 2020-07-08 | 2020-09-15 | 49 | 26 | 23 | [20 empty] | 2020-09-16 |  | 2021-07-01 |  | EXP | [8 empty] | 2020-11-13 | Connected |  | No
National Grid | HALIFAX | 299346 | 2338 | 10 | Solar | 07_797W24 | 2020-07-01 16:06 | 2020-07-02 | 4 | 0 | 4 | 2020-07-09 | 2020-07-30 | 15 | 0 | 15 | [20 empty] | 2020-08-03 | 2020-07-02 10:41 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SOUTH ATTLEBORO | 299443 | 2703 | 7.44 | Solar | 05_9L3 | 2020-07-02 10:41 | 2020-07-03 | 3 | 1 | 2 | 2020-07-09 | 2020-08-03 | 16 | 0 | 16 | [20 empty] | 2020-08-03 | 2020-07-02 15:29 | 2021-07-05 |  | EXP |  | 2020-10-06 | 2020-10-26 | 20 | 0 | 20 |  |  | 2020-11-04 | Connected |  | No
National Grid | BELCHERTOWN | 299534 | 1007 | 30 | Solar | 09_523L2 | 2020-07-02 15:29 | 2020-07-03 | 27 | 25 | 2 | 2020-08-12 | 2020-08-24 | 8 | 0 | 8 | [20 empty] | 2020-08-25 |  | 2021-08-11 | Yes | EXP |  | 2020-10-08 | 2020-10-21 | 13 | 0 | 13 |  |  | 2020-10-21 | Connected |  | No
National Grid | WESTMINSTER | 299584 | 1473 | 7.68 | Solar | 01_609W1 | 2020-07-02 16:44 | 2020-07-03 | 3 | 0 | 3 | 2020-07-09 | 2020-09-16 | 49 | 26 | 23 | [20 empty] | 2020-09-24 |  | 2022-07-06 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 296132 | 1843 | 5.04 | Solar | 14_61L3 | 2020-07-02 17:28 | 2020-07-03 | 2 | 0 | 2 | 2020-07-08 | 2020-10-19 | 71 | 50 | 21 | [20 empty] | 2020-10-19 |  | 2021-10-30 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NEWBURY | 296240 | 1951 | 3.8 | Solar | 14_60L1 | 2020-07-03 12:19 | 2020-07-06 | 2 | 0 | 2 | 2020-07-09 | 2020-07-31 | 16 | 0 | 16 | [20 empty] | 2020-08-03 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOUTHBOROUGH | 299834 | 1772 | 10 | Solar | 05_317W4 | 2020-07-06 17:54 | 2020-07-07 | 16 | 14 | 2 | 2020-07-30 | 2020-08-09 | 7 | 0 | 7 | [20 empty] | 2020-08-11 |  | 2021-10-16 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | DUDLEY | 299874 | 1571 | 9.36 | Solar | 01_412L4 | 2020-07-07 00:12 | 2020-07-08 | 1 | 0 | 1 | 2020-07-10 | 2020-08-04 | 16 | 0 | 16 | [20 empty] | 2020-08-04 |  | 2021-07-08 |  | EXP | [8 empty] | 2020-10-20 | Connected |  | No
National Grid | ANDOVER | 299887 | 1810 | 6 | Solar | 14_54L3 | 2020-07-07 08:03 | 2020-07-08 | 1 | 0 | 1 | 2020-07-10 | 2020-07-29 | 13 | 0 | 13 | [20 empty] | 2020-07-30 |  | 2021-07-08 |  | EXP | [8 empty] | 2020-11-04 | Connected |  | No
National Grid | SALEM | 292831 | 1970 | 100 | Solar | 12_49W2 | 2020-07-08 12:13 | 2020-07-09 | 4 | 0 | 4 | 2020-07-16 | 2021-07-27 | 256 | 26 | 230 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ANDOVER | 300290 | 1810 | 20 | Solar | 14_62L2 | 2020-07-08 15:47 | 2020-07-09 | 2 | 2 | 0 | 2020-07-14 | 2020-08-11 | 19 | 0 | 19 | [20 empty] | 2020-08-11 |  | 2021-07-12 |  | EXP | [8 empty] | 2020-12-28 | Connected |  | No
National Grid | ESSEX | 300315 | 1929 | 17.7 | Solar | 12_51T1 | 2020-07-08 16:29 | 2020-07-09 | 2 | 2 | 0 | 2020-07-14 | 2020-08-11 | 19 | 0 | 19 | [20 empty] | 2020-08-11 |  | 2021-07-12 |  | EXP | [8 empty] | 2021-01-08 | Connected |  | No
National Grid | LAWRENCE | 298830 | 1841 | 7.6 | Solar | 14_74L3 | 2020-07-08 16:48 | 2020-07-09 | 4 | 0 | 4 | 2020-07-16 | 2020-08-18 | 23 | 0 | 23 | [20 empty] | 2020-08-26 | 2020-07-08 18:11 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SWAMPSCOTT | 290037 | 1907 | 7.68 | Solar | 12_22W3 | 2020-07-08 18:11 | 2020-07-09 | 4 | 0 | 4 | 2020-07-16 | 2020-08-10 | 17 | 0 | 17 | [20 empty] | 2020-08-13 |  | 2022-02-03 | Yes | EXP |  | 2021-01-20 | 2021-03-22 | 61 | 0 | 61 |  |  | 2022-01-03 | Connected |  | No
National Grid | MARLBOROUGH | 300432 | 1752 | 10 | Solar | 05_311W2 | 2020-07-09 11:07 | 2020-07-10 | 0 | 0 | 0 | 2020-07-13 | 2020-08-10 | 20 | 0 | 20 | [20 empty] | 2020-08-11 | 2020-07-09 14:38 | 2021-07-09 |  | EXP | [8 empty] | 2020-11-07 | Connected |  | No
National Grid | BELCHERTOWN | 295754 | 1007 | 7.54 | Solar | 09_509L1 | 2020-07-09 14:38 | 2020-07-10 | 5 | 0 | 5 | 2020-07-20 | 2020-08-10 | 15 | 0 | 15 | [20 empty] | 2020-08-13 |  | 2021-05-03 | Yes | EXP |  | 2021-02-21 | 2021-02-24 | 2 | 0 | 2 |  |  | 2021-04-28 | Connected |  | No
National Grid | AUBURN | 300516 | 1501 | 8.64 | Solar | 01_6W1 | 2020-07-09 16:06 | 2020-07-10 | 0 | 0 | 0 | 2020-07-13 | 2020-08-04 | 16 | 0 | 16 | [20 empty] | 2020-08-04 |  | 2021-08-04 |  | EXP | [8 empty] | 2020-12-08 | Connected |  | No
National Grid | AYER | 292576 | 1432 | 3.8 | Solar | 01_201W2 | 2020-07-09 16:50 | 2020-07-10 | 5 | 0 | 5 | 2020-07-20 | 2020-08-14 | 18 | 0 | 18 | [20 empty] | 2020-08-18 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BRIDGEWATER | 300578 | 2324 | 7.6 | Solar | 07_912W55 | 2020-07-10 08:35 | 2020-07-13 | 2 | 2 | 0 | 2020-07-16 | 2020-08-11 | 17 | 0 | 17 | [20 empty] | 2020-08-11 |  | 2021-08-11 |  | EXP | [8 empty] | 2021-01-15 | Connected |  | No
National Grid | GRANBY | 300661 | 1033 | 6.72 | Solar | 09_527L1 | 2020-07-10 13:40 | 2020-07-13 | 72 | 27 | 45 | 2020-10-23 | 2020-11-18 | 17 | 0 | 17 | [20 empty] | 2020-11-23 |  | 2022-02-18 |  | EXP | [8 empty] | 2021-11-29 | Connected |  | No
National Grid | REVERE | 298672 | 2151 | 4.32 | Solar | 12_35J3 | 2020-07-10 17:37 | 2020-07-13 | 4 | 0 | 4 | 2020-07-20 | 2020-11-03 | 75 | 49 | 26 | [20 empty] | 2020-11-09 | 2020-07-10 21:09 | 2022-03-29 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HALIFAX | 296274 | 2338 | 1500 | Solar | 07_912W75 | 2020-07-10 21:09 | 2020-07-13 | 14 | 9 | 5 | [10 empty] | 2020-07-31 | 2020-08-13 | 10 | 3 | 7 | [10 empty] | 2021-03-10 | 2020-07-11 07:44 | 2023-05-24 | Yes | STD |  | 2022-07-26 | 2023-05-12 | 290 | 0 | 290 |  |  | 2023-05-24 | Connected |  | No
National Grid | NORWELL | 300341 | 2061 | 30 | Solar | 07_96W43 | 2020-07-11 07:44 | 2020-07-13 | 85 | 71 | 14 | 2020-11-12 | 2020-12-07 | 16 | 3 | 13 | [20 empty] | 2020-12-08 |  | 2021-07-09 | Yes | EXP |  | 2021-02-18 | 2021-04-07 | 48 | 0 | 48 |  |  | 2021-06-04 | Connected |  | No
National Grid | DRACUT | 299147 | 1826 | 10 | Solar | 14_78L3 | 2020-07-13 11:59 | 2020-07-14 | 33 | 24 | 9 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SALEM | 296513 | 1970 | 3.36 | Solar | 12_49W6 | 2020-07-13 13:16 | 2020-07-14 | 3 | 0 | 3 | 2020-07-20 | 2020-08-14 | 18 | 0 | 18 | [20 empty] | 2020-08-18 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTBOROUGH | 300962 | 1581 | 3.8 | Solar | 05_312W5 | 2020-07-13 15:37 | 2020-07-14 | 299 | 114 | 185 | 2021-09-22 | 2021-10-26 | 24 | 0 | 24 | [20 empty] | 2021-12-09 |  | 2023-06-14 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | REHOBOTH | 298439 | 2769 | 3.8 | Solar | 05_7L5 | 2020-07-13 16:33 | 2020-07-14 | 0 | 0 | 0 | 2020-07-15 | 2020-08-04 | 14 | 0 | 14 | [20 empty] | 2020-08-05 |  | 2021-07-13 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | CHELMSFORD | 298402 | 1824 | 4.64 | Solar | 14_73L1 | 2020-07-14 09:46 | 2020-07-15 | 0 | 0 | 0 | 2020-07-16 | 2020-08-04 | 13 | 0 | 13 | [20 empty] | 2020-08-05 |  | 2021-09-10 |  | EXP | [8 empty] | 2021-08-05 | Connected |  | No
National Grid | HAMPDEN | 300267 | 1036 | 9.84 | Solar | 09_507L2 | 2020-07-14 09:54 | 2020-07-15 | 0 | 0 | 0 | 2020-07-16 | 2020-08-04 | 13 | 0 | 13 | [20 empty] | 2020-08-05 |  | 2021-07-14 |  | EXP | [8 empty] | 2020-10-01 | Connected |  | No
National Grid | TEWKSBURY | 300909 | 1876 | 22.6 | Solar | 14_70L8 | 2020-07-14 09:58 | 2020-07-15 | 17 | 17 | 0 | 2020-08-07 | 2020-08-15 | 6 | 1 | 5 | [20 empty] | 2020-08-17 |  | 2023-08-02 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTON | 301078 | 2766 | 7.6 | Solar | 05_8L3 | 2020-07-14 10:36 | 2020-07-15 | 2 | 0 | 2 | 2020-07-20 | 2020-08-08 | 15 | 0 | 15 | [20 empty] | 2020-08-12 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NANTUCKET | 295382 | 2554 | 249.98 | Solar | 04_101L8 | 2020-07-14 10:40 | 2020-07-15 | 35 | 27 | 8 | 2020-09-04 | 2020-11-06 | 43 | 23 | 20 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | WILBRAHAM | 301119 | 1095 | 7.6 | Solar | 09_507L3 | 2020-07-14 12:29 | 2020-07-15 | 5 | 0 | 5 | 2020-07-23 | 2020-08-20 | 16 | 0 | 16 | [20 empty] | 2020-08-20 |  | 2021-08-20 |  | EXP | [8 empty] | 2020-11-06 | Connected |  | No
National Grid | WALES | 301303 | 1081 | 6.48 | Solar | 09_516L1 | 2020-07-15 10:58 | 2020-07-16 | 0 | 0 | 0 | 2020-07-17 | 2020-08-08 | 16 | 0 | 16 | [20 empty] | 2020-08-10 | 2020-07-15 12:51 | 2021-07-15 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHESHIRE | 296791 | 1225 | 7.6 | Solar | 09_1021W2 | 2020-07-15 12:51 | 2020-07-16 | 1 | 1 | 0 | 2020-07-20 | 2020-08-23 | 25 | 9 | 16 | [20 empty] | 2020-08-24 | 2020-07-15 17:49 | 2021-07-15 | Yes | EXP |  | 2020-10-31 | 2021-03-17 | 137 | 0 | 137 |  |  | 2021-03-19 | Connected |  | No
National Grid | RANDOLPH | 297377 | 2368 | 7.6 | Solar | 07_5W3 | 2020-07-15 17:49 | 2020-07-16 | 4 | 0 | 4 | 2020-07-23 | 2020-08-11 | 13 | 0 | 13 | [20 empty] | 2020-08-13 |  | 2021-05-28 |  | EXP | [8 empty] | 2021-05-22 | Connected |  | No
National Grid | WESTPORT | 301536 | 2790 | 3.8 | Solar | 05_115W45 | 2020-07-16 10:00 | 2020-07-17 | 3 | 0 | 3 | 2020-07-23 | 2020-08-08 | 12 | 0 | 12 | [20 empty] | 2020-08-12 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MILLBURY | 301583 | 1527 | 7.92 | Solar | 01_304W5 | 2020-07-16 14:31 | 2020-07-17 | 12 | 12 | 0 | 2020-08-05 | 2020-08-14 | 7 | 0 | 7 | [20 empty] | 2020-08-14 |  | 2021-08-03 |  | EXP | [8 empty] | 2021-05-19 | Connected |  | No
National Grid | ANDOVER | 301678 | 1810 | 10 | Solar | 14_54L3 | 2020-07-16 16:34 | 2020-07-17 | 3 | 3 | 0 | 2020-07-22 | 2020-08-14 | 16 | 0 | 16 | [20 empty] | 2020-08-14 |  | 2021-07-19 |  | EXP | [8 empty] | 2020-10-20 | Connected |  | No
National Grid | SALEM | 230775 | 1970 | 66.6 | Solar | 12_3J6 | 2020-07-16 17:04 | 2020-07-17 | 11 | 5 | 6 | 2020-08-03 | 2020-08-28 | 20 | 3 | 17 | [20 empty] | 2020-09-11 |  | 2021-10-11 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | ANDOVER | 301740 | 1810 | 15.2 | Solar | 14_59L1 | 2020-07-17 08:53 | 2020-07-20 | 0 | 0 | 0 | 2020-07-21 | 2020-08-20 | 18 | 0 | 18 | [20 empty] | 2020-08-20 | 2020-07-17 09:01 | 2021-05-07 |  | EXP | [8 empty] | 2021-07-21 | Connected |  | No
National Grid | BELCHERTOWN | 294435 | 1007 | 5 | Solar | 09_523L2 | 2020-07-17 09:01 | 2020-07-20 | 5 | 0 | 5 | 2020-07-28 | 2020-08-17 | 14 | 0 | 14 | [20 empty] | 2020-08-20 |  | 2021-05-03 | Yes | EXP |  | 2021-04-23 | 2021-05-05 | 12 | 0 | 12 |  |  | 2021-06-09 | Connected |  | No
National Grid | SWANSEA | 298454 | 2777 | 23.4 | Solar | 05_11W84 | 2020-07-17 09:31 | 2020-07-20 | 0 | 0 | 0 | 2020-07-21 | 2020-08-14 | 19 | 3 | 16 | [20 empty] | 2020-08-17 | 2020-07-17 10:04 | 2021-12-10 |  | EXP | [8 empty] | 2021-09-03 | Connected |  | No
National Grid | HAVERHILL | 300239 | 1832 | 3.8 | Solar | 14_48L2 | 2020-07-17 10:04 | 2020-07-20 | 5 | 0 | 5 | 2020-07-28 | 2020-08-14 | 12 | 0 | 12 | [20 empty] | 2020-08-18 |  | 2021-06-18 | Yes | EXP |  | 2021-01-13 | 2021-01-19 | 6 | 0 | 6 |  |  | 2021-02-12 | Connected |  | No
National Grid | BEVERLY | 295936 | 1915 | 3.8 | Solar | 12_12L2 | 2020-07-17 11:33 | 2020-07-20 | 0 | 0 | 0 | 2020-07-21 | 2020-08-10 | 14 | 0 | 14 | [20 empty] | 2020-08-11 |  | 2021-07-19 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BLACKSTONE | 291242 | 1504 | 750 | Solar | 05_321W6 | 2020-07-17 12:58 | 2020-07-20 | 187 | 66 | 121 | [29 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BEVERLY | 298302 | 1915 | 390 | Solar | 12_12L4 | 2020-07-17 13:02 | 2020-07-20 | 63 | 25 | 38 | [10 empty] | 2020-10-19 | 2020-10-16 | 0 | 0 | 0 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | ATHOL | 286855 | 1331 | 4990 | Solar | 09_705W3 | 2020-07-17 13:08 | 2020-07-20 | 28 | 23 | 5 | [10 empty] | 2020-08-27 | 2020-10-08 | 29 | 13 | 16 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | FRANKLIN | 301858 | 2038 | 10 | Solar | 05_348W7 | 2020-07-17 14:41 | 2020-07-20 | 0 | 0 | 0 | 2020-07-21 | 2020-08-08 | 14 | 0 | 14 | [20 empty] | 2020-08-10 |  | 2021-07-19 |  | EXP | [8 empty] | 2020-10-17 | Connected |  | No
National Grid | SALISBURY | 301879 | 1952 | 19.5 | Solar | 14_7L4 | 2020-07-17 15:33 | 2020-07-20 | 0 | 0 | 0 | 2020-07-21 | 2020-08-14 | 17 | 0 | 17 | [20 empty] | 2020-08-14 | 2020-07-20 13:06 | 2021-07-19 |  | EXP | [8 empty] | 2020-11-06 | Connected |  | No
National Grid | LEOMINSTER | 288685 | 1453 | 10 | Solar | 01_225W4 | 2020-07-20 13:06 | 2020-07-21 | 4 | 0 | 4 | 2020-07-28 | 2020-08-11 | 11 | 3 | 8 | [20 empty] | 2020-08-13 |  | 2021-04-03 | Yes | EXP |  | 2021-01-20 | 2021-01-26 | 6 | 0 | 6 |  |  | 2021-02-19 | Connected |  | No
National Grid | SALEM | 302107 | 1970 | 86.4 | Solar | 12_49W6 | 2020-07-21 08:35 | 2020-07-22 | 5 | 0 | 5 | 2020-07-30 | 2020-08-28 | 22 | 3 | 19 | [20 empty] | 2021-01-05 |  | 2022-01-11 |  | EXP | [8 empty] | 2021-10-18 | Connected |  | No
National Grid | UXBRIDGE | 302294 | 1569 | 16.56 | Solar | 05_321W6 | 2020-07-21 11:37 | 2020-07-22 | 37 | 36 | 1 | 2020-09-15 | 2020-10-02 | 13 | 0 | 13 | [20 empty] | 2020-10-08 | 2020-07-21 17:49 | 2021-09-14 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | AYER | 282114 | 1432 | 66.6 | Solar | 01_201W2 | 2020-07-21 17:49 | 2020-07-22 | 15 | 9 | 6 | 2020-08-13 | 2020-10-21 | 48 | 25 | 23 | [20 empty] | 2020-11-13 |  | 2022-04-29 | Yes | EXP | [8 empty] | 2022-04-29 | Connected |  | No
National Grid | SCITUATE | 302775 | 2066 | 7.6 | Solar | 07_17J1 | 2020-07-23 12:43 | 2020-07-24 | 15 | 15 | 0 | 2020-08-17 | 2020-08-24 | 5 | 0 | 5 | [20 empty] | 2020-08-25 |  | 2021-08-13 |  | EXP | [8 empty] | 2021-01-23 | Connected |  | No
National Grid | FRANKLIN | 302923 | 2038 | 11.4 | Solar | 05_344W5 | 2020-07-24 08:38 | 2020-07-27 | 3 | 0 | 3 | 2020-07-31 | 2020-08-09 | 6 | 0 | 6 | [20 empty] | 2020-08-11 |  | 2021-07-30 |  | EXP | [8 empty] | 2020-10-16 | Connected |  | No
National Grid | ATHOL | 302782 | 1331 | 7.92 | Solar | 09_702W3 | 2020-07-24 09:46 | 2020-07-27 | 22 | 22 | 0 | 2020-08-27 | 2020-09-14 | 11 | 0 | 11 | [20 empty] | 2020-09-14 | 2020-07-24 10:24 | 2021-09-14 |  | EXP | [8 empty] | 2020-12-09 | Connected |  | No
National Grid | WENHAM | 302941 | 1984 | 15.2 | Solar | 12_18L2 | 2020-07-24 10:24 | 2020-07-27 | 0 | 0 | 0 | 2020-07-28 | 2020-09-16 | 36 | 21 | 15 | [20 empty] | 2020-09-17 |  | 2021-06-30 | Yes | EXP |  | 2021-01-05 | 2021-02-12 | 37 | 0 | 37 |  |  | 2021-02-24 | Connected |  | No
National Grid | ORANGE | 302982 | 1364 | 9.36 | Solar | 09_702W2 | 2020-07-24 12:05 | 2020-07-27 | 0 | 0 | 0 | 2020-07-28 | 2020-08-08 | 9 | 0 | 9 | [20 empty] | 2020-08-10 |  | 2021-07-26 |  | EXP | [8 empty] | 2020-11-07 | Connected |  | No
National Grid | SEEKONK | 303042 | 2771 | 17.6 | Solar | 05_7L5 | 2020-07-24 16:13 | 2020-07-27 | 3 | 0 | 3 | 2020-07-31 | 2020-08-09 | 6 | 3 | 3 | [20 empty] | 2020-08-11 |  | 2021-07-30 |  | EXP | [8 empty] | 2020-12-07 | Connected |  | No
National Grid | WESTMINSTER | 301762 | 1473 | 2300 | Solar | 01_609W2 | 2020-07-27 09:55 | 2020-07-28 | 4 | 1 | 3 | [10 empty] | 2020-08-04 | 2020-08-28 | 19 | 7 | 12 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | PEMBROKE | 303299 | 2359 | 20 | Solar | 07_910W25 | 2020-07-27 15:14 | 2020-07-28 | 0 | 0 | 0 | 2020-07-29 | 2020-08-09 | 8 | 0 | 8 | [20 empty] | 2020-08-10 |  | 2021-08-29 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | GLOUCESTER | 303344 | 1930 | 15.2 | Solar | 12_52L1 | 2020-07-27 17:51 | 2020-07-28 | 24 | 24 | 0 | 2020-08-31 | 2020-09-16 | 11 | 0 | 11 | [20 empty] | 2020-09-17 |  | 2022-04-11 |  | EXP | [8 empty] | 2022-02-10 | Connected |  | No
National Grid | WEYMOUTH | 303572 | 2190 | 8 | Solar | 07_99W32 | 2020-07-28 13:39 | 2020-07-29 | 3 | 3 | 0 | 2020-08-03 | 2020-08-09 | 5 | 0 | 5 | [20 empty] | 2020-08-11 |  | 2021-09-10 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HANOVER | 303246 | 2339 | 62.5 | Solar | 07_95W5 | 2020-07-28 18:50 | 2020-07-29 | 10 | 0 | 10 | 2020-08-13 | 2020-09-14 | 16 | 0 | 16 | [20 empty] | 2020-09-14 |  | 2024-07-23 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | HANOVER | 303247 | 2339 | 112.5 | Solar | 07_95W5 | 2020-07-28 18:50 | 2020-07-29 | 10 | 0 | 10 | 2020-08-13 | 2020-09-14 | 22 | 5 | 17 | [20 empty] | 2020-09-15 |  | 2024-09-09 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | NORTH BROOKFIELD | 297453 | 1535 | 420 | Solar | 09_604W3 | 2020-07-28 22:28 | 2020-07-29 | 43 | 36 | 7 | 2020-09-29 | 2020-11-19 | 34 | 15 | 19 | [21 empty] | 2020-07-29 16:47 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GLOUCESTER | 302762 | 1930 | 10 | Solar | 12_51T1 | 2020-07-29 16:47 | 2020-07-30 | 1 | 1 | 0 | 2020-08-03 | 2020-08-25 | 16 | 0 | 16 | [20 empty] | 2020-08-25 | 2020-07-30 12:23 | 2021-07-30 | Yes | EXP |  | 2021-01-21 | 2021-03-16 | 54 | 0 | 54 |  |  | 2021-05-06 | Connected |  | No
National Grid | ADAMS | 284440 | 1220 | 240 | Solar | 09_1021W2 | 2020-07-30 12:23 | 2020-07-31 | 9 | 3 | 6 | [10 empty] | 2020-08-13 | 2020-12-11 | 82 | 66 | 16 | [10 empty] | 2021-08-26 | 2020-07-30 14:46 | 2023-04-14 | Yes | STD |  | 2022-10-11 | 2023-01-14 | 96 | 0 | 96 |  |  | 2023-04-13 | Connected |  | No
National Grid | BROCKTON | 294957 | 2301 | 10 | Solar | 07_911W13 | 2020-07-30 14:46 | 2020-07-31 | 1 | 0 | 1 | 2020-08-04 | 2020-08-14 | 9 | 3 | 6 | [20 empty] | 2020-08-14 | 2020-07-30 14:57 | 2021-08-02 | Yes | EXP |  | 2020-11-04 | 2020-12-10 | 36 | 0 | 36 |  |  | 2020-12-29 | Connected |  | No
National Grid | BROCKTON | 293251 | 2302 | 7.6 | Solar | 07_712J1 | 2020-07-30 14:57 | 2020-07-31 | 34 | 27 | 7 | 2020-09-22 | 2020-10-21 | 20 | 0 | 20 | [20 empty] | 2020-10-21 | 2020-07-30 17:04 | 2021-07-29 | Yes | EXP |  | 2020-12-15 | 2021-01-08 | 24 | 0 | 24 |  |  | 2021-02-06 | Connected |  | No
National Grid | SAUGUS | 291136 | 1906 | 10 | Solar | 12_23W2 | 2020-07-30 17:04 | 2020-07-31 | 79 | 76 | 3 | 2020-11-25 | 2020-12-21 | 17 | 0 | 17 | [20 empty] | 2020-12-22 | 2020-07-30 17:29 | 2021-10-13 | Yes | EXP |  | 2021-03-25 | 2021-05-27 | 63 | 0 | 63 |  |  | 2021-06-03 | Connected |  | No
National Grid | LEOMINSTER | 295621 | 1453 | 9.8 | Solar | 01_207W6 | 2020-07-30 17:29 | 2020-07-31 | 1 | 0 | 1 | 2020-08-04 | 2020-08-25 | 15 | 0 | 15 | [20 empty] | 2020-08-25 |  | 2021-08-02 | Yes | EXP |  | 2021-05-04 | 2021-05-05 | 1 | 0 | 1 |  |  | 2021-05-24 | Connected |  | No
National Grid | REHOBOTH | 304219 | 2769 | 6.96 | Solar | 05_7L4 | 2020-07-30 18:09 | 2020-07-31 | 8 | 8 | 0 | 2020-08-13 | 2020-08-24 | 7 | 0 | 7 | [20 empty] | 2020-08-24 | 2020-07-30 21:03 | 2021-08-11 |  | EXP | [8 empty] | 2020-12-05 | Connected |  | No
National Grid | MILLBURY | 301597 | 1527 | 10 | Solar | 01_304W1 | 2020-07-30 21:03 | 2020-07-31 | 8 | 6 | 2 | 2020-08-13 | 2020-09-16 | 19 | 0 | 19 | [20 empty] | 2020-09-16 |  | 2021-08-05 | Yes | EXP | [8 empty] | 2021-01-15 | Connected |  | No
National Grid | GRANBY | 291194 | 1033 | 1.92 | Solar | 09_527L1 | 2020-07-31 10:46 | 2020-08-03 | 0 | 0 | 0 | 2020-08-04 | 2020-09-16 | 27 | 7 | 20 | [20 empty] | 2020-09-16 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | PETERSHAM | 298629 | 1366 | 9.36 | Solar | 09_604W1 | 2020-07-31 12:35 | 2020-08-03 | 0 | 0 | 0 | 2020-08-04 | 2020-08-25 | 15 | 0 | 15 | [20 empty] | 2020-08-25 | 2020-07-31 14:53 | 2021-08-02 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SALISBURY | 301380 | 1952 | 3.8 | Solar | 14_7L1 | 2020-07-31 14:53 | 2020-08-03 | 0 | 0 | 0 | 2020-08-04 | 2020-08-11 | 5 | 0 | 5 | [20 empty] | 2020-08-13 |  | 2021-05-20 | Yes | EXP |  | 2020-12-11 | 2021-01-04 | 23 | 0 | 23 |  |  | 2021-05-11 | Connected |  | No
National Grid | REVERE | 301272 | 2151 | 7.6 | Solar | 12_7W2 | 2020-08-03 09:41 | 2020-08-04 | 1 | 0 | 1 | 2020-08-06 | 2020-08-25 | 13 | 0 | 13 | [20 empty] | 2020-08-26 | 2020-08-03 12:28 | 2021-08-04 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CLINTON | 299739 | 1510 | 7.6 | Solar | 01_216W1 | 2020-08-03 12:28 | 2020-08-04 | 1 | 0 | 1 | 2020-08-06 | 2020-08-25 | 13 | 0 | 13 | [20 empty] | 2020-08-27 |  | 2022-06-08 | Yes | EXP | [8 empty] | 2021-10-05 | Connected |  | No
National Grid | BROCKTON | 290955 | 2301 | 57.6 | Solar | 07_797W19 | 2020-08-03 14:14 | 2020-08-04 | 7 | 3 | 4 | 2020-08-14 | 2020-09-14 | 20 | 0 | 20 | [20 empty] | 2020-09-15 |  | 2022-03-07 |  | EXP | [8 empty] | 2022-03-04 | Connected |  | No
National Grid | WILLIAMSTOWN | 299450 | 1267 | 6 | Solar | 09_1003W1 | 2020-08-03 14:50 | 2020-08-04 | 1 | 0 | 1 | 2020-08-06 | 2020-08-25 | 13 | 0 | 13 | [20 empty] | 2020-08-27 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WENHAM | 304665 | 1984 | 8.99 | Solar | 12_18L2 | 2020-08-04 16:25 | 2020-08-05 | 11 | 11 | 0 | 2020-08-20 | 2020-09-03 | 10 | 0 | 10 | [20 empty] | 2020-09-03 | 2020-08-04 18:23 | 2021-08-19 |  | EXP | [8 empty] | 2020-10-19 | Connected |  | No
National Grid | NANTUCKET | 284042 | 2554 | 2850 | Solar | 04_101L2 | 2020-08-04 18:23 | 2020-08-05 | 8 | 3 | 5 | [10 empty] | 2020-08-17 | 2020-10-06 | 35 | 18 | 17 | [10 empty] | 2021-12-13 |  | 2025-06-04 | Yes | STD | [9 empty] | Pending Withdraw |  | No
National Grid | METHUEN | 304996 | 1844 | 7.6 | Solar | 14_5J44 | 2020-08-04 18:32 | 2020-08-05 | 1 | 0 | 1 | 2020-08-07 | 2020-08-14 | 5 | 0 | 5 | [20 empty] | 2020-08-18 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | GREAT BARRINGTON | 305047 | 1230 | 11.75 | Solar | 09_1109W3 | 2020-08-05 08:28 | 2020-08-06 | 8 | 8 | 0 | 2020-08-18 | 2020-08-28 | 7 | 0 | 7 | [20 empty] | 2020-08-28 | 2020-08-05 10:17 | 2021-08-16 |  | EXP | [8 empty] | 2020-10-12 | Connected |  | No
National Grid | GREAT BARRINGTON | 305086 | 1230 | 20 | Solar | 09_1109W3 | 2020-08-05 10:17 | 2020-08-06 | 8 | 8 | 0 | 2020-08-18 | 2020-08-28 | 7 | 0 | 7 | [20 empty] | 2020-08-28 |  | 2021-08-16 | Yes | EXP |  | 2020-12-30 | 2021-01-25 | 26 | 0 | 26 |  |  | 2021-07-15 | Connected |  | No
National Grid | SAUGUS | 302630 | 1906 | 262.5 | Natural Gas | 12_25W3 | 2020-08-05 11:50 | 2020-08-06 | 39 | 28 | 11 | 2020-10-01 | 2020-11-04 | 23 | 0 | 23 | [20 empty] | 2020-11-10 | 2020-08-05 11:50 | 2022-02-21 |  | EXP | [8 empty] | 2022-02-18 | Connected |  | No
National Grid | NORTHAMPTON | 303203 | 1062 | 9.12 | Solar | 09_909W4 | 2020-08-05 11:50 | 2020-08-06 | 3 | 0 | 3 | 2020-08-12 | 2020-08-24 | 8 | 0 | 8 | [20 empty] | 2020-08-26 |  | 2021-05-03 | Yes | EXP | [8 empty] | 2021-01-28 | Connected |  | No
National Grid | BONDSVILLE | 294038 | 1009 | 9.84 | Solar | 09_523L2 | 2020-08-05 12:28 | 2020-08-06 | 3 | 0 | 3 | 2020-08-12 | 2020-08-25 | 9 | 0 | 9 | [20 empty] | 2020-08-27 | 2020-08-05 13:26 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 305161 | 2302 | 5.22 | Solar | 07_911W56 | 2020-08-05 13:26 | 2020-08-06 | 28 | 28 | 0 | 2020-09-16 | 2020-10-14 | 16 | 0 | 16 | [20 empty] | 2020-10-14 |  | 2021-09-15 | Yes | EXP |  | 2020-12-22 | 2021-01-08 | 17 | 0 | 17 |  |  | 2021-07-07 | Connected |  | No
National Grid | PLAINVILLE | 302661 | 2762 | 210 | Natural Gas | 05_3337W1 | 2020-08-05 15:27 | 2020-08-06 | 5 | 0 | 5 | 2020-09-17 | 2020-10-21 | 23 | 0 | 23 | [20 empty] | 2020-11-10 | 2020-08-06 10:20 |  |  | EXP | [8 empty] | 2021-07-26 | Connected |  | No
National Grid | AMESBURY | 300662 | 1913 | 7.6 | Solar | 14_275L2 | 2020-08-06 10:20 | 2020-08-07 | 3 | 1 | 2 | 2020-08-12 | 2020-08-23 | 7 | 0 | 7 | [20 empty] | 2020-08-26 |  | 2021-12-06 | Yes | EXP |  | 2021-03-24 | 2021-04-06 | 13 | 0 | 13 |  |  | 2021-10-05 | Connected |  | No
National Grid | WESTPORT | 304302 | 2790 | 3.8 | Solar | 05_115W45 | 2020-08-07 12:00 | 2020-08-10 | 1 | 0 | 1 | 2020-08-12 | 2020-08-25 | 9 | 0 | 9 | [20 empty] | 2020-08-27 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | PHILLIPSTON | 305628 | 1331 | 9.8 | Solar | 09_702W1 | 2020-08-07 17:08 | 2020-08-10 | 0 | 0 | 0 | 2020-08-11 | 2020-08-23 | 9 | 0 | 9 | [20 empty] | 2020-08-24 |  | 2022-02-26 |  | EXP | [8 empty] | 2021-11-29 | Connected |  | No
National Grid | FRANKLIN | 305559 | 2038 | 125 | Solar | 05_348W6 | 2020-08-07 17:39 | 2020-08-10 | 20 | 13 | 7 | 2020-09-08 | 2020-10-12 | 23 | 0 | 23 | [20 empty] | 2020-12-10 | 2020-08-07 18:36 | 2022-01-09 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | DRACUT | 301330 | 1826 | 7.6 | Solar | 14_78L1 | 2020-08-07 18:36 | 2020-08-10 | 0 | 0 | 0 | 2020-08-11 | 2020-08-25 | 10 | 0 | 10 | [20 empty] | 2020-08-26 |  | 2021-08-09 | Yes | EXP |  | 2020-10-28 | 2020-11-10 | 13 | 0 | 13 |  |  | 2021-01-25 | Connected |  | No
National Grid | HAVERHILL | 305828 | 1832 | 9.6 | Solar | 14_43L2 | 2020-08-10 12:47 | 2020-08-11 | 25 | 23 | 2 | 2020-09-16 | 2020-10-02 | 12 | 0 | 12 | [20 empty] | 2020-10-06 |  | 2021-09-15 |  | EXP | [8 empty] | 2020-12-01 | Connected |  | No
National Grid | WORCESTER | 265164 | 1609 | 125 | Natural Gas | 01_HT46 | 2020-08-10 14:05 | 2020-08-11 | 26 | 20 | 6 | [10 empty] | 2020-09-17 | 2020-11-05 | 35 | 18 | 17 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | FRANKLIN | 305614 | 2038 | 175 | Solar | 05_348W6 | 2020-08-11 13:08 | 2020-08-12 | 18 | 13 | 5 | 2020-09-08 | 2020-10-12 | 23 | 0 | 23 | [20 empty] | 2020-12-14 |  | 2022-01-09 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GRAFTON | 306191 | 1519 | 15.2 | Solar | 01_304W1 | 2020-08-11 16:49 | 2020-08-12 | 1 | 0 | 1 | 2020-08-14 | 2020-12-23 | 88 | 64 | 24 | [22 empty] | 2021-08-12 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MALDEN | 306220 | 2148 | 10 | Solar | 12_16W3 | 2020-08-11 19:11 | 2020-08-12 | 1 | 0 | 1 | 2020-08-14 | 2020-09-18 | 18 | 0 | 18 | [20 empty] | 2020-09-18 |  | 2021-05-03 |  | EXP | [8 empty] | 2020-11-18 | Connected |  | No
National Grid | NORTHBOROUGH | 306227 | 1532 | 11.4 | Solar | 05_313W2 | 2020-08-11 21:22 | 2020-08-12 | 1 | 0 | 1 | 2020-08-14 | 2020-08-24 | 6 | 0 | 6 | [20 empty] | 2020-08-24 | 2020-08-12 10:13 | 2021-08-12 |  | EXP | [8 empty] | 2020-11-17 | Connected |  | No
National Grid | BILLERICA | 304749 | 1821 | 10 | Solar | 14_70L5 | 2020-08-12 10:13 | 2020-08-13 | 2 | 0 | 2 | 2020-08-18 | 2020-08-24 | 4 | 0 | 4 | [20 empty] | 2020-08-26 |  | 2021-05-03 | Yes | EXP |  | 2020-12-11 | 2021-01-05 | 25 | 0 | 25 |  |  | 2021-02-11 | Connected |  | No
National Grid | WESTFORD | 306363 | 1886 | 20 | Battery Add-On | 14_58L1 | 2020-08-12 13:22 | 2020-08-13 | 1 | 1 | 0 | 2020-08-17 | 2020-08-24 | 5 | 0 | 5 | [20 empty] | 2020-08-25 | 2020-08-12 15:36 | 2021-08-13 |  | EXP | [8 empty] | 2021-01-08 | Connected |  | No
National Grid | ANDOVER | 306442 | 1810 | 25.2 | Solar | 14_59L1 | 2020-08-12 15:36 | 2020-08-13 | 21 | 21 | 0 | 2020-09-15 | 2020-10-02 | 13 | 0 | 13 | [20 empty] | 2020-10-06 | 2020-08-12 18:32 | 2021-09-14 |  | EXP |  | 2021-01-05 | 2021-01-19 | 14 | 0 | 14 |  |  | 2021-03-02 | Connected |  | No
National Grid | HUBBARDSTON | 296858 | 1452 | 12.285 | Solar | 09_604W4 | 2020-08-12 18:32 | 2020-08-13 | 3 | 2 | 1 | 2020-08-19 | 2020-09-16 | 15 | 0 | 15 | [20 empty] | 2020-09-16 | 2020-08-12 19:40 | 2021-08-01 | Yes | EXP |  | 2021-01-20 | 2021-02-11 | 22 | 0 | 22 |  |  | 2021-02-17 | Connected |  | Yes
National Grid | HOLBROOK | 305147 | 2343 | 7.6 | Solar | 07_2W1 | 2020-08-12 19:40 | 2020-08-13 | 2 | 0 | 2 | 2020-08-18 | 2020-09-16 | 16 | 0 | 16 | [20 empty] | 2020-09-16 |  | 2021-08-01 | Yes | EXP |  | 2021-01-05 | 2021-01-26 | 21 | 0 | 21 |  |  | 2021-05-04 | Connected |  | No
National Grid | LYNN | 301309 | 1905 | 7.6 | Solar | 12_21J37 | 2020-08-13 09:38 | 2020-08-14 | 1 | 0 | 1 | 2020-08-18 | 2020-09-16 | 16 | 0 | 16 | [20 empty] | 2020-09-16 |  | 2021-08-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 306595 | 2301 | 7.6 | Solar | 07_911W13 | 2020-08-13 10:37 | 2020-08-14 | 0 | 0 | 0 | 2020-08-17 | 2020-08-24 | 5 | 0 | 5 | [20 empty] | 2020-08-25 | 2020-08-13 11:15 | 2021-08-13 |  | EXP | [8 empty] | 2020-11-24 | Connected |  | No
National Grid | SOUTHBRIDGE | 198216 | 1550 | 3000 | Solar | 01_413L4 | 2020-08-13 11:15 | 2020-08-14 | 42 | 40 | 2 | [10 empty] | 2020-10-16 | 2020-11-10 | 17 | 0 | 17 | [11 empty] | 2020-08-13 11:45 | 2025-02-16 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | CHELMSFORD | 303103 | 1824 | 200 | Solar | 14_73L1 | 2020-08-13 11:45 | 2020-08-14 | 23 | 12 | 11 | 2020-09-17 | 2021-01-19 | 83 | 60 | 23 | 2021-01-27 | 2021-03-22 | 38 | 0 | 38 | [5 empty] | 2021-01-27 | 2021-03-22 | 38 | 0 | 38 | [5 empty] | 2021-04-06 |  | 2024-06-01 |  | EXP | [9 empty] | Construction |  | No
National Grid | FALL RIVER | 306648 | 2723 | 3.8 | Solar | 05_106W44 | 2020-08-13 12:17 | 2020-08-14 | 1 | 0 | 1 | 2020-08-18 | 2020-09-18 | 16 | 0 | 16 | [20 empty] | 2020-09-17 |  | 2021-05-03 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WRENTHAM | 297184 | 2093 | 10 | Solar | 05_348W1 | 2020-08-13 18:38 | 2020-08-14 | 1 | 1 | 0 | 2020-08-17 | 2020-08-24 | 5 | 0 | 5 | [20 empty] | 2020-08-25 |  | 2021-08-13 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MARLBOROUGH | 298911 | 1752 | 24.78 | Solar | 05_311W2 | 2020-08-14 10:02 | 2020-08-17 | 0 | 0 | 0 | 2020-08-18 | 2020-09-14 | 16 | 0 | 16 | [20 empty] | 2020-09-15 | 2020-08-14 12:11 | 2021-08-02 |  | EXP | [8 empty] | 2021-03-04 | Connected |  | No
National Grid | BOXFORD | 306879 | 1921 | 20 | Solar | 14_33L1 | 2020-08-14 12:11 | 2020-08-17 | 2 | 2 | 0 | 2020-08-19 | 2020-09-03 | 11 | 0 | 11 | [20 empty] | 2020-09-03 |  | 2021-08-17 | Yes | EXP |  | 2021-02-05 | 2021-02-04 | 0 | 0 | 0 |  |  | 2021-02-09 | Connected |  | No
National Grid | HAMILTON | 306908 | 1982 | 13.6 | Solar | 12_51L3 | 2020-08-14 15:47 | 2020-08-17 | 2 | 2 | 0 | 2020-08-19 | 2020-08-31 | 8 | 0 | 8 | [20 empty] | 2020-09-01 | 2020-08-14 17:38 | 2021-08-17 |  | EXP | [8 empty] | 2020-11-26 | Connected |  | No
National Grid | SOUTH HAMILTON | 301864 | 1982 | 7.6 | Solar | 12_51T2 | 2020-08-14 17:38 | 2020-08-17 | 1 | 0 | 1 | 2020-08-19 | 2020-09-03 | 11 | 0 | 11 | [20 empty] | 2020-09-08 |  | 2022-02-05 | Yes | EXP | [8 empty] | 2021-08-03 | Connected |  | No
National Grid | MONTEREY | 301413 | 1245 | 10 | Solar | 09_1109W1 | 2020-08-15 15:17 | 2020-08-17 | 14 | 14 | 0 | 2020-09-04 | 2020-09-20 | 10 | 0 | 10 | [20 empty] | 2020-09-21 |  | 2021-09-03 |  | EXP | [8 empty] | 2020-11-17 | Connected |  | No
National Grid | WESTFORD | 307057 | 1886 | 15.2 | Solar | 14_57L2 | 2020-08-17 08:33 | 2020-08-18 | 2 | 0 | 2 | 2020-08-21 | 2020-09-03 | 9 | 0 | 9 | [20 empty] | 2020-09-08 |  | 2021-08-02 |  | EXP | [8 empty] | 2020-10-22 | Connected |  | No
National Grid | REHOBOTH | 307102 | 2769 | 17.04 | Solar | 05_7L4 | 2020-08-17 10:43 | 2020-08-18 | 8 | 8 | 0 | 2020-08-28 | 2020-09-14 | 10 | 0 | 10 | [20 empty] | 2020-09-15 | 2020-08-17 12:17 | 2021-09-10 |  | EXP | [8 empty] | 2021-08-13 | Connected |  | No
National Grid | WESTFORD | 301130 | 1886 | 10 | Solar | 14_57L2 | 2020-08-17 12:17 | 2020-08-18 | 7 | 7 | 0 | 2020-08-27 | 2020-09-16 | 13 | 0 | 13 | [20 empty] | 2020-09-17 |  | 2021-08-26 | Yes | EXP |  | 2021-04-21 | 2021-04-30 | 9 | 0 | 9 |  |  | 2021-05-04 | Connected |  | No
National Grid | ORANGE | 290751 | 1364 | 4950 | Other | 09_705W2 | 2020-08-17 15:34 | 2020-08-18 | 23 | 20 | 3 | [10 empty] | 2020-09-22 | 2020-10-13 | 15 | 1 | 14 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | PHILLIPSTON | 297385 | 1331 | 4950 | Other | 09_702W1 | 2020-08-17 15:57 | 2020-08-18 | 25 | 20 | 5 | [10 empty] | 2020-09-25 | 2020-10-21 | 17 | 0 | 17 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | ORANGE | 299108 | 1364 | 4950 | Other | 09_702W3 | 2020-08-17 16:07 | 2020-08-18 | 31 | 29 | 2 | [10 empty] | 2020-10-01 | 2020-10-24 | 16 | 0 | 16 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | RANDOLPH | 307448 | 2368 | 8.99 | Solar | 07_5W2 | 2020-08-18 15:06 | 2020-08-19 | 19 | 19 | 0 | 2020-09-16 | 2020-10-02 | 12 | 0 | 12 | [20 empty] | 2020-10-06 | 2020-08-18 17:34 | 2021-09-15 |  | EXP | [8 empty] | 2021-01-27 | Connected |  | No
National Grid | REVERE | 299562 | 2151 | 6 | Solar | 12_16W8 | 2020-08-18 17:34 | 2020-08-19 | 1 | 0 | 1 | 2020-08-21 | 2020-09-09 | 12 | 0 | 12 | [20 empty] | 2020-09-16 |  | 2022-06-24 | Yes | EXP |  | 2021-02-09 | 2021-04-10 | 60 | 0 | 60 |  |  | 2022-05-04 | Connected |  | No
National Grid | ANDOVER | 306710 | 1810 | 133.2 | Solar | 14_59L6 | 2020-08-18 18:17 | 2020-08-19 | 33 | 28 | 5 | 2020-10-06 | 2020-11-04 | 20 | 0 | 20 | [20 empty] | 2020-12-21 |  | 2022-01-02 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | GRANBY | 307066 | 1033 | 150 | Solar | 09_527L1 | 2020-08-18 21:38 | 2020-08-19 | 19 | 12 | 7 | [10 empty] | 2020-09-17 | 2020-10-14 | 18 | 0 | 18 | [11 empty] | 2020-08-19 11:15 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HUBBARDSTON | 307522 | 1452 | 25 | Solar | 09_604W4 | 2020-08-19 11:15 | 2020-08-20 | 8 | 0 | 8 | 2020-09-01 | 2020-10-02 | 22 | 0 | 22 | [20 empty] | 2020-10-06 | 2020-08-19 11:16 | 2024-11-29 | Yes | EXP | [9 empty] | Construction |  | No
National Grid | HUBBARDSTON | 307520 | 1452 | 25 | Solar | 09_604W4 | 2020-08-19 11:16 | 2020-08-20 | 7 | 0 | 7 | 2020-09-01 | 2020-10-02 | 22 | 0 | 22 | [20 empty] | 2020-10-05 |  | 2023-04-09 | Yes | EXP | [9 empty] | Withdrawn |  | No
National Grid | LAWRENCE | 302207 | 1843 | 7.6 | Solar | 14_61L3 | 2020-08-19 12:29 | 2020-08-20 | 4 | 0 | 4 | 2020-08-27 | 2020-09-14 | 11 | 0 | 11 | [20 empty] | 2020-09-18 | 2020-08-19 18:35 | 2021-08-02 |  | EXP | [8 empty] | 2021-07-15 | Connected |  | No
National Grid | EAST LONGMEADOW | 307802 | 1028 | 7.6 | Solar | 09_508L1 | 2020-08-19 18:35 | 2020-08-20 | 0 | 0 | 0 | 2020-08-21 | 2020-09-03 | 9 | 0 | 9 | [20 empty] | 2020-09-03 | 2020-08-20 14:07 | 2021-08-19 | Yes | EXP |  | 2021-02-04 | 2021-02-03 | 0 | 0 | 0 |  |  | 2021-03-18 | Connected |  | No
National Grid | DUDLEY | 307951 | 1571 | 9.6 | Solar | 01_413L3 | 2020-08-20 14:07 | 2020-08-21 | 0 | 0 | 0 | 2020-08-24 | 2020-10-29 | 47 | 26 | 21 | [20 empty] | 2020-11-02 | 2020-08-22 14:51 | 2021-11-02 | Yes | EXP |  | 2021-03-11 | 2021-03-15 | 4 | 0 | 4 |  |  | 2021-04-12 | Connected |  | No
National Grid | DUNSTABLE | 308268 | 1827 | 15.36 | Solar | 01_210L1 | 2020-08-22 14:51 | 2020-08-24 | 0 | 0 | 0 | 2020-08-25 | 2020-09-16 | 15 | 0 | 15 | [20 empty] | 2020-09-17 | 2020-08-25 13:55 | 2021-09-10 | Yes | EXP |  | 2021-05-05 | 2021-05-24 | 19 | 0 | 19 |  |  | 2021-08-30 | Connected |  | No
National Grid | CHARLTON | 308483 | 1507 | 9992 | Other | 01_415L2 | 2020-08-25 13:55 | 2020-08-26 | 24 | 16 | 8 | [10 empty] | 2020-10-01 | 2020-10-26 | 16 | 0 | 16 | [11 empty] | 2020-08-25 13:59 | 2025-12-07 | Yes | STD | [9 empty] | Group Study |  | No
National Grid | CHARLTON | 308478 | 1507 | 9992 | Other | 01_415L1 | 2020-08-25 13:59 | 2020-08-26 | 24 | 16 | 8 | [10 empty] | 2020-10-01 | 2020-11-17 | 31 | 14 | 17 | [12 empty] | 2025-02-17 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | SWAMPSCOTT | 309022 | 1907 | 7.6 | Solar | 12_9J2 | 2020-08-26 13:13 | 2020-08-27 | 0 | 0 | 0 | 2020-08-28 | 2020-09-14 | 10 | 0 | 10 | [20 empty] | 2020-09-15 |  | 2021-08-26 |  | EXP | [8 empty] | 2020-12-16 | Connected |  | No
National Grid | ANDOVER | 309079 | 1810 | 3.8 | Solar | 14_59L6 | 2020-08-26 15:53 | 2020-08-27 | 13 | 13 | 0 | 2020-09-16 | 2020-10-02 | 12 | 0 | 12 | [20 empty] | 2020-10-06 | 2020-08-27 11:25 | 2021-09-15 |  | EXP | [8 empty] | 2021-06-02 | Connected |  | No
National Grid | SPENCER | 307858 | 1562 | 15.2 | Solar | 01_21W1 | 2020-08-27 11:25 | 2020-08-28 | 2 | 0 | 2 | 2020-09-02 | 2020-09-28 | 17 | 0 | 17 | [20 empty] | 2020-10-06 |  | 2023-11-15 | Yes | EXP |  | 2021-06-16 | 2022-01-17 | 216 | 7 | 209 |  |  |  | Withdrawn |  | Yes
National Grid | RUTLAND | 309418 | 1543 | 10 | Solar | 01_55W1 | 2020-08-27 18:28 | 2020-08-28 | 1 | 1 | 0 | 2020-08-31 | 2020-09-14 | 9 | 0 | 9 | [20 empty] | 2020-09-15 |  | 2021-08-27 |  | EXP | [8 empty] | 2020-12-30 | Connected |  | No
National Grid | LAWRENCE | 306308 | 1841 | 7.6 | Solar | 14_8L2 | 2020-08-28 17:21 | 2020-08-31 | 2 | 0 | 2 | 2020-09-03 | 2020-09-28 | 16 | 0 | 16 | [20 empty] | 2020-10-06 | 2020-08-28 17:36 | 2021-08-02 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | AMESBURY | 307055 | 1913 | 7.6 | Solar | 14_5J15 | 2020-08-28 17:36 | 2020-08-31 | 0 | 0 | 0 | 2020-09-01 | 2020-09-18 | 12 | 0 | 12 | [20 empty] | 2020-09-18 |  | 2021-08-30 | Yes | EXP |  | 2020-12-19 | 2021-01-21 | 33 | 0 | 33 |  |  | 2021-05-25 | Connected |  | No
National Grid | WILLIAMSTOWN | 309752 | 1267 | 15.2 | Solar | 09_1001W1 | 2020-08-31 09:58 | 2020-09-01 | 0 | 0 | 0 | 2020-09-02 | 2020-09-28 | 17 | 0 | 17 | [20 empty] | 2020-10-05 |  | 2021-08-02 |  | EXP | [8 empty] | 2021-07-03 | Connected |  | No
National Grid | TEWKSBURY | 309756 | 1879 | 13.6 | Solar | 14_20L4 | 2020-08-31 10:35 | 2020-09-01 | 2 | 2 | 0 | 2020-09-03 | 2020-09-17 | 9 | 0 | 9 | [20 empty] | 2020-09-18 |  | 2021-09-01 |  | EXP | [8 empty] | 2020-12-10 | Connected |  | No
National Grid | BROOKFIELD | 281385 | 1506 | 4948 | Other | 01_525L2 | 2020-08-31 11:04 | 2020-09-01 | 17 | 13 | 4 | [10 empty] | 2020-09-25 | 2020-10-20 | 16 | 0 | 16 | [11 empty] | 2020-08-31 11:08 |  |  | STD | [9 empty] | Group Study |  | No
National Grid | LOWELL | 305218 | 1854 | 10 | Solar | 14_21L3 | 2020-08-31 11:08 | 2020-09-01 | 2 | 0 | 2 | 2020-09-04 | 2020-09-28 | 15 | 0 | 15 | [20 empty] | 2020-10-06 |  | 2021-08-02 | Yes | EXP | [8 empty] | 2021-04-21 | Connected |  | No
National Grid | WESTMINSTER | 290747 | 1473 | 7998 | Other | 01_602W2 | 2020-08-31 11:21 | 2020-09-01 | 11 | 7 | 4 | [10 empty] | 2020-09-17 | 2020-10-08 | 15 | 0 | 15 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | WARE | 291680 | 1082 | 12000 | Other | 09_501L2 | 2020-08-31 11:46 | 2020-09-01 | 11 | 7 | 4 | [10 empty] | 2020-09-17 | 2020-10-08 | 15 | 3 | 12 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | HUBBARDSTON | 291210 | 1452 | 10000 | Other | 01_609W1 | 2020-08-31 15:01 | 2020-09-01 | 16 | 11 | 5 | [10 empty] | 2020-09-24 | 2020-10-16 | 15 | 0 | 15 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | FRANKLIN | 309857 | 2038 | 7.6 | Solar | 05_344W1 | 2020-08-31 15:02 | 2020-09-01 | 0 | 0 | 0 | 2020-09-02 | 2020-09-17 | 10 | 0 | 10 | [20 empty] | 2020-09-18 |  | 2021-09-01 |  | EXP | [8 empty] | 2020-12-07 | Connected |  | No
National Grid | WORCESTER | 307776 | 1606 | 9.12 | Solar | 01_24W2 | 2020-08-31 15:35 | 2020-09-01 | 11 | 11 | 0 | 2020-09-17 | 2020-10-12 | 15 | 0 | 15 | [20 empty] | 2020-10-14 | 2020-08-31 16:51 | 2021-10-14 |  | EXP | [8 empty] | 2021-04-16 | Connected |  | No
National Grid | NORTHAMPTON | 309324 | 1060 | 6 | Solar | 09_905W1 | 2020-08-31 16:51 | 2020-09-01 | 2 | 0 | 2 | 2020-09-04 | 2020-09-28 | 15 | 0 | 15 | [20 empty] | 2020-10-06 |  | 2021-11-08 | Yes | EXP |  | 2021-09-10 | 2021-10-01 | 19 | 0 | 19 |  |  | 2021-10-27 | Connected |  | Yes
National Grid | ANDOVER | 309991 | 1810 | 9.6 | Solar | 14_59L1 | 2020-09-01 09:09 | 2020-09-02 | 3 | 0 | 3 | 2020-09-09 | 2020-09-28 | 13 | 0 | 13 | [20 empty] | 2020-10-06 |  | 2021-09-08 |  | EXP | [8 empty] | 2021-06-05 | Connected |  | No
National Grid | WEST NEWBURY | 310000 | 1985 | 7.6 | Solar | 14_47L1 | 2020-09-01 09:41 | 2020-09-02 | 3 | 0 | 3 | 2020-09-09 | 2020-09-28 | 13 | 0 | 13 | [20 empty] | 2020-10-06 |  | 2021-08-02 |  | EXP | [8 empty] | 2020-11-18 | Connected |  | No
National Grid | SHIRLEY | 310063 | 1464 | 10 | Solar | 01_201W4 | 2020-09-01 11:09 | 2020-09-02 | 0 | 0 | 0 | 2020-09-03 | 2020-09-17 | 9 | 0 | 9 | [20 empty] | 2020-09-18 |  | 2021-09-01 |  | EXP | [8 empty] | 2020-12-21 | Connected |  | No
National Grid | WENHAM | 309531 | 1984 | 5.8 | Solar | 12_51L3 | 2020-09-01 11:40 | 2020-09-02 | 1 | 1 | 0 | 2020-09-03 | 2020-09-20 | 11 | 0 | 11 | [20 empty] | 2020-09-21 |  | 2021-09-20 |  | EXP | [8 empty] | 2020-12-23 | Connected |  | No
National Grid | BELCHERTOWN | 291205 | 1007 | 12000 | Other | 09_509L2 | 2020-09-02 12:53 | 2020-09-03 | 11 | 6 | 5 | [10 empty] | 2020-09-22 | 2020-10-08 | 12 | 0 | 12 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WEST BROOKFIELD | 283873 | 1585 | 9992 | Other | 01_525L2 | 2020-09-02 13:04 | 2020-09-03 | 11 | 5 | 6 | [10 empty] | 2020-09-22 | 2020-10-13 | 14 | 0 | 14 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | WESTMINSTER | 299242 | 1473 | 10000 | Solar | 01_609W1 | 2020-09-02 13:17 | 2020-09-03 | 11 | 6 | 5 | [10 empty] | 2020-09-22 | 2020-10-13 | 14 | 0 | 14 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH OXFORD | 295119 | 1537 | 10000 | Other | 01_406L1 | 2020-09-02 14:38 | 2020-09-03 | 11 | 6 | 5 | [10 empty] | 2020-09-22 | 2020-10-13 | 14 | 0 | 14 | [11 empty] | 2020-09-02 15:02 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MARLBOROUGH | 299754 | 1752 | 10 | Solar | 05_311W4 | 2020-09-02 15:02 | 2020-09-03 | 11 | 11 | 0 | 2020-09-21 | 2020-10-15 | 17 | 0 | 17 | [20 empty] | 2020-10-16 |  | 2021-10-15 | Yes | EXP |  | 2020-12-29 | 2021-03-01 | 62 | 0 | 62 |  |  | 2021-03-03 | Connected |  | No
National Grid | WESTMINSTER | 310476 | 1473 | 10 | Hydro | 01_609W2 | 2020-09-03 14:41 | 2020-09-04 | 23 | 17 | 6 | 2020-10-08 | 2020-11-13 | 18 | 0 | 18 | [20 empty] | 2020-11-13 |  | 2021-08-02 |  | EXP | [8 empty] | 2021-02-04 | Connected |  | No
National Grid | BELLINGHAM | 307866 | 2019 | 7.6 | Solar | 05_344W4 | 2020-09-03 20:14 | 2020-09-04 | 1 | 0 | 1 | 2020-09-09 | 2020-09-20 | 8 | 0 | 8 | [20 empty] | 2020-09-22 |  | 2021-09-08 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FRANKLIN | 310834 | 2038 | 11.4 | Solar | 05_344W5 | 2020-09-03 20:52 | 2020-09-04 | 1 | 0 | 1 | 2020-09-09 | 2020-09-20 | 8 | 0 | 8 | [20 empty] | 2020-09-22 |  | 2021-09-06 |  | EXP | [8 empty] | 2021-04-01 | Connected |  | No
National Grid | NORTH ANDOVER | 310835 | 1845 | 10 | Solar | 14_55L1 | 2020-09-03 22:14 | 2020-09-04 | 1 | 0 | 1 | 2020-09-09 | 2020-09-20 | 8 | 0 | 8 | [20 empty] | 2020-09-22 |  | 2021-09-07 |  | EXP | [8 empty] | 2021-01-19 | Connected |  | No
National Grid | MILFORD | 310848 | 1757 | 11.4 | Solar | 05_335W3 | 2020-09-04 07:41 | 2020-09-08 | 2 | 0 | 2 | 2020-09-11 | 2020-11-06 | 39 | 0 | 39 | [20 empty] | 2020-10-06 | 2020-09-04 15:43 | 2021-08-02 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SAUGUS | 306578 | 1906 | 6 | Solar | 12_23W1 | 2020-09-04 15:43 | 2020-09-08 | 2 | 0 | 2 | 2020-09-11 | 2020-09-28 | 11 | 0 | 11 | [20 empty] | 2020-10-08 | 2020-09-07 16:55 | 2021-09-01 | Yes | EXP | [8 empty] | 2021-08-06 | Connected |  | No
National Grid | WESTMINSTER | 311144 | 1473 | 9.6 | Solar | 01_609W1 | 2020-09-07 16:55 | 2020-09-08 | 0 | 0 | 0 | 2020-09-09 | 2020-10-02 | 17 | 0 | 17 | [20 empty] | 2020-10-06 | 2020-09-08 09:00 | 2021-09-07 | Yes | EXP | [8 empty] | 2021-06-03 | Connected |  | No
National Grid | MILLBURY | 299022 | 1527 | 1000 | Solar | 01_304W4 | 2020-09-08 09:00 | 2020-09-09 | 19 | 14 | 5 | [10 empty] | 2020-10-06 | 2020-10-29 | 16 | 0 | 16 | [11 empty] | 2020-09-08 12:30 |  | Yes | STD | [9 empty] | Study |  | No
National Grid | CHARLTON | 306145 | 1507 | 4948 | Other | 01_415L1 | 2020-09-08 12:30 | 2020-09-09 | 18 | 13 | 5 | [10 empty] | 2020-10-05 | 2020-10-26 | 14 | 0 | 14 | [12 empty] | 2025-04-02 | Yes | STD | [9 empty] | Group Study |  | No
National Grid | CHARLTON | 308485 | 1507 | 10000 | Other | 01_415L1 | 2020-09-08 12:32 | 2020-09-09 | 8 | 2 | 6 | [10 empty] | 2020-09-22 | 2020-10-09 | 13 | 0 | 13 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BRIMFIELD | 311431 | 1010 | 20 | Solar | 09_503L4 | 2020-09-08 16:53 | 2020-09-09 | 1 | 0 | 1 | 2020-09-11 | 2020-09-28 | 11 | 0 | 11 | [20 empty] | 2020-10-06 |  | 2021-09-01 |  | EXP | [8 empty] | 2021-05-10 | Connected |  | No
National Grid | HUBBARDSTON | 294861 | 1452 | 10000 | Other | 01_602W2 | 2020-09-09 13:15 | 2020-09-10 | 8 | 1 | 7 | [10 empty] | 2020-09-23 | 2020-10-16 | 16 | 0 | 16 | [11 empty] | 2020-09-09 14:37 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SUTTON | 311604 | 1590 | 19 | Solar | 01_304W5 | 2020-09-09 14:37 | 2020-09-10 | 3 | 3 | 0 | 2020-09-15 | 2020-10-02 | 13 | 0 | 13 | [20 empty] | 2020-10-06 |  | 2022-06-02 | Yes | EXP |  | 2021-01-12 | 2021-02-05 | 24 | 0 | 24 |  |  | 2022-04-22 | Connected |  | No
National Grid | HARVARD | 311609 | 1451 | 10 | Solar | 01_201W2 | 2020-09-09 15:05 | 2020-09-10 | 0 | 0 | 0 | 2020-09-11 | 2020-09-27 | 11 | 0 | 11 | [20 empty] | 2020-09-29 | 2020-09-10 09:44 | 2021-09-09 |  | EXP | [8 empty] | 2021-02-24 | Connected |  | No
National Grid | LEICESTER | 306359 | 1524 | 5 | Solar | 01_21W1 | 2020-09-10 09:44 | 2020-09-11 | 17 | 14 | 3 | 2020-10-07 | 2020-11-12 | 24 | 6 | 18 | [20 empty] | 2020-11-17 | 2020-09-10 14:06 | 2021-12-24 | Yes | EXP |  | 2021-11-09 | 2022-01-25 | 78 | 0 | 78 |  |  | 2022-02-12 | Connected |  | No
National Grid | BROCKTON | 309814 | 2302 | 7.6 | Solar | 07_911W77 | 2020-09-10 14:06 | 2020-09-11 | 41 | 39 | 2 | 2020-11-06 | 2020-11-23 | 10 | 0 | 10 | [20 empty] | 2020-12-03 |  | 2021-11-04 | Yes | EXP |  | 2021-02-03 | 2021-03-24 | 49 | 0 | 49 |  |  | 2021-04-02 | Connected |  | No
National Grid | METHUEN | 311773 | 1844 | 150 | Solar | 14_75L4 | 2020-09-10 14:13 | 2020-09-11 | 3 | 0 | 3 | 2020-09-17 | 2020-11-04 | 34 | 10 | 24 | [20 empty] | 2020-11-13 |  | 2024-10-22 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MARLBOROUGH | 311908 | 1752 | 10 | Solar | 05_311W3 | 2020-09-10 15:06 | 2020-09-11 | 0 | 0 | 0 | 2020-09-14 | 2020-09-27 | 10 | 0 | 10 | [20 empty] | 2020-09-29 |  | 2021-09-10 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BOLTON | 311915 | 1740 | 14.5 | Solar | 01_216W6 | 2020-09-10 15:50 | 2020-09-11 | 1 | 0 | 1 | 2020-09-15 | 2020-11-12 | 40 | 17 | 23 | [20 empty] | 2020-11-16 |  | 2021-09-01 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | QUINCY | 311801 | 2169 | 7.6 | Solar | 07_1W5 | 2020-09-10 17:55 | 2020-09-11 | 0 | 0 | 0 | 2020-09-14 | 2020-10-16 | 23 | 12 | 11 | [20 empty] | 2020-10-16 |  | 2021-10-15 |  | EXP | [8 empty] | 2020-12-23 | Connected |  | No
National Grid | STURBRIDGE | 312005 | 1518 | 15.2 | Solar | 01_408L2 | 2020-09-10 19:20 | 2020-09-11 | 1 | 0 | 1 | 2020-09-15 | 2020-09-28 | 9 | 0 | 9 | [20 empty] | 2020-10-06 |  | 2021-09-01 |  | EXP | [8 empty] | 2020-11-14 | Connected |  | No
National Grid | ANDOVER | 311831 | 1810 | 250 | Solar | 14_50L3 | 2020-09-11 09:07 | 2020-09-14 | 2 | 0 | 2 | 2020-09-17 | 2020-10-20 | 22 | 0 | 22 | [20 empty] | 2021-01-26 | 2020-09-11 12:10 | 2025-08-20 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | REHOBOTH | 306988 | 2769 | 11.4 | Solar | 05_7L5 | 2020-09-11 12:10 | 2020-09-14 | 2 | 2 | 0 | 2020-09-17 | 2020-10-06 | 13 | 0 | 13 | [20 empty] | 2020-10-07 |  | 2021-09-15 | Yes | EXP |  | 2021-02-04 | 2021-04-07 | 62 | 0 | 62 |  |  | 2021-08-17 | Connected |  | No
National Grid | SOUTHBOROUGH | 312249 | 1772 | 15.2 | Solar | 05_310W5 | 2020-09-11 19:16 | 2020-09-14 | 0 | 0 | 0 | 2020-09-15 | 2020-10-02 | 13 | 0 | 13 | [20 empty] | 2020-10-13 | 2020-09-14 08:03 | 2021-10-13 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WHITMAN | 306629 | 2382 | 3.8 | Solar | 07_797W29 | 2020-09-14 08:03 | 2020-09-15 | 14 | 14 | 0 | 2020-10-05 | 2020-11-06 | 23 | 0 | 23 | [20 empty] | 2020-11-06 |  | 2021-11-05 | Yes | EXP |  | 2021-02-18 | 2021-04-07 | 48 | 0 | 48 |  |  | 2021-04-13 | Connected |  | No
National Grid | LYNN | 302539 | 1904 | 10 | Solar | 12_29W4 | 2020-09-14 08:04 | 2020-09-15 | 4 | 0 | 4 | 2020-09-22 | 2020-10-16 | 17 | 2 | 15 | [20 empty] | 2020-10-20 |  | 2021-09-01 |  | EXP | [8 empty] | 2020-12-16 | Connected |  | No
National Grid | NORTHAMPTON | 312372 | 1060 | 57.6 | Solar | 09_901W3 | 2020-09-14 13:49 | 2020-09-15 | 1 | 0 | 1 | 2020-09-17 | 2020-12-14 | 59 | 37 | 22 | 2020-12-28 | 2021-02-18 | 35 | 0 | 35 | [5 empty] | 2020-12-28 | 2021-02-18 | 35 | 0 | 35 | [5 empty] | 2021-02-23 |  | 2022-07-22 |  | EXP | [8 empty] | 2022-06-03 | Connected |  | No
National Grid | SUTTON | 308498 | 1590 | 4990 | Solar | 01_304W6 | 2020-09-14 13:57 | 2020-09-15 | 9 | 2 | 7 | [10 empty] | 2020-09-29 | 2020-10-24 | 18 | 0 | 18 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BOLTON | 310710 | 1740 | 20 | Solar | 01_225W1 | 2020-09-14 17:24 | 2020-09-15 | 4 | 0 | 4 | 2020-09-22 | 2020-10-06 | 10 | 0 | 10 | [20 empty] | 2020-10-13 |  | 2022-07-14 |  | EXP | [8 empty] | 2021-02-24 | Connected |  | No
National Grid | CHELMSFORD | 312556 | 1824 | 7.6 | Solar | 14_24L2 | 2020-09-14 18:49 | 2020-09-15 | 1 | 0 | 1 | 2020-09-17 | 2020-10-05 | 12 | 0 | 12 | [20 empty] | 2020-10-06 |  | 2021-10-06 |  | EXP | [8 empty] | 2021-01-07 | Connected |  | No
National Grid | AUBURN | 312600 | 1501 | 10 | Solar | 01_26W2 | 2020-09-15 09:14 | 2020-09-16 | 0 | 0 | 0 | 2020-09-17 | 2020-10-02 | 11 | 0 | 11 | [20 empty] | 2020-10-06 |  | 2021-09-15 |  | EXP | [8 empty] | 2021-01-13 | Connected |  | No
National Grid | COHASSET | 310912 | 2025 | 6.67 | Solar | 07_915W37 | 2020-09-15 11:07 | 2020-09-16 | 13 | 13 | 0 | 2020-10-05 | 2020-10-30 | 18 | 0 | 18 | [20 empty] | 2020-11-03 | 2020-09-15 12:09 | 2021-11-03 |  | EXP | [8 empty] | 2020-12-19 | Connected |  | No
National Grid | SALISBURY | 306671 | 1952 | 9.8 | Solar | 14_7L2 | 2020-09-15 12:09 | 2020-09-16 | 3 | 0 | 3 | 2020-09-22 | 2020-10-13 | 14 | 0 | 14 | [20 empty] | 2020-10-20 | 2020-09-15 12:16 | 2022-12-14 | Yes | EXP |  | 2021-06-29 | 2021-08-06 | 38 | 0 | 38 |  |  | 2021-09-10 | Connected |  | Yes
National Grid | LYNN | 309907 | 1904 | 7.6 | Solar | 12_24W2 | 2020-09-15 12:16 | 2020-09-16 | 3 | 0 | 3 | 2020-09-22 | 2020-10-13 | 14 | 0 | 14 | [20 empty] | 2020-10-20 | 2020-09-15 15:46 | 2021-09-01 | Yes | EXP | [8 empty] | 2021-08-14 | Connected |  | No
National Grid | BEVERLY | 312832 | 1915 | 10 | Solar | 12_51T1 | 2020-09-15 15:46 | 2020-09-16 | 0 | 0 | 0 | 2020-09-17 | 2020-10-14 | 15 | 0 | 15 | [20 empty] | 2020-10-14 |  | 2021-10-14 | Yes | EXP |  | 2021-02-05 | 2021-03-05 | 28 | 0 | 28 |  |  | 2021-03-16 | Connected |  | No
National Grid | BROCKTON | 308244 | 2301 | 1.92 | Solar | 07_98W46 | 2020-09-15 16:34 | 2020-09-16 | 3 | 0 | 3 | 2020-09-22 | 2020-10-13 | 14 | 0 | 14 | [20 empty] | 2020-10-20 | 2020-09-15 16:39 | 2021-09-01 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | UXBRIDGE | 266700 | 1569 | 4948 | Other | 05_321W2 | 2020-09-15 16:39 | 2020-09-16 | 12 | 7 | 5 | [10 empty] | 2020-10-02 | 2020-10-27 | 17 | 0 | 17 | [10 empty] | 2023-01-09 | 2020-09-15 17:08 | 2025-10-16 | Yes | STD | [9 empty] | Pending Withdraw |  | No
National Grid | LANCASTER | 291030 | 1523 | 4948 | Other | 01_225W3 | 2020-09-15 17:08 | 2020-09-16 | 5 | 0 | 5 | [10 empty] | 2020-09-25 | 2020-10-20 | 16 | 0 | 16 | [11 empty] | 2020-09-15 17:38 | 2025-08-24 | Yes | STD | [9 empty] | Pending Withdraw |  | No
National Grid | MILLBURY | 303514 | 1527 | 9992 | Other | 01_304W5 | 2020-09-15 17:38 | 2020-09-16 | 18 | 13 | 5 | [10 empty] | 2020-10-13 | 2020-11-09 | 18 | 0 | 18 | [13 empty] | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | BOLTON | 312902 | 1740 | 22.8 | Solar | 01_225W1 | 2020-09-15 19:12 | 2020-09-16 | 0 | 0 | 0 | 2020-09-17 | 2020-11-16 | 38 | 17 | 21 | [20 empty] | 2020-11-16 | 2020-09-16 11:41 | 2021-11-15 |  | EXP | [8 empty] | 2021-07-19 | Connected |  | No
National Grid | EAST BRIDGEWATER | 300143 | 2333 | 9.8 | Solar | 07_797W23 | 2020-09-16 11:41 | 2020-09-17 | 2 | 0 | 2 | 2020-09-22 | 2020-10-20 | 19 | 0 | 19 | [20 empty] | 2020-10-20 |  | 2022-01-13 | Yes | EXP | [8 empty] | 2021-09-02 | Connected |  | No
National Grid | CHARLTON | 292506 | 1507 | 7998 | Other | 01_406L1 | 2020-09-16 15:19 | 2020-09-17 | 8 | 0 | 8 | [10 empty] | 2020-09-30 | 2020-10-24 | 17 | 0 | 17 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | ORANGE | 294566 | 1364 | 9992 | Solar | 09_705W3 | 2020-09-16 15:31 | 2020-09-17 | 13 | 9 | 4 | [10 empty] | 2020-10-06 | 2020-10-29 | 16 | 0 | 16 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | OXFORD | 306142 | 1540 | 7998 | Other | 01_406L4 | 2020-09-16 15:54 | 2020-09-17 | 9 | 3 | 6 | [10 empty] | 2020-10-01 | 2020-10-26 | 16 | 0 | 16 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | QUINCY | 313212 | 2169 | 10 | Solar | 07_1W5 | 2020-09-16 20:04 | 2020-09-17 | 0 | 0 | 0 | 2020-09-18 | 2020-10-05 | 11 | 0 | 11 | [20 empty] | 2020-10-06 |  | 2022-01-28 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SIASCONSET | 310959 | 2564 | 7.6 | Solar | 04_101L8 | 2020-09-17 04:08 | 2020-09-18 | 1 | 1 | 0 | 2020-09-22 | 2020-10-19 | 18 | 2 | 16 | [20 empty] | 2020-10-19 |  | 2021-09-20 |  | EXP | [8 empty] | 2021-01-08 | Connected |  | No
National Grid | NORTHAMPTON | 309180 | 1060 | 22.8 | Solar | 09_901W1 | 2020-09-17 08:55 | 2020-09-18 | 3 | 0 | 3 | 2020-09-24 | 2020-10-19 | 17 | 1 | 16 | [20 empty] | 2020-10-20 |  | 2021-09-01 |  | EXP | [8 empty] | 2021-01-19 | Connected |  | No
National Grid | SUTTON | 310798 | 1590 | 4990 | Solar | 01_304W6 | 2020-09-17 13:14 | 2020-09-18 | 8 | 1 | 7 | [10 empty] | 2020-10-01 | 2020-10-26 | 16 | 0 | 16 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | PLAINVILLE | 313374 | 2762 | 8.64 | Solar | 05_3451W3 | 2020-09-17 13:21 | 2020-09-18 | 0 | 0 | 0 | 2020-09-21 | 2020-10-05 | 10 | 0 | 10 | [20 empty] | 2020-10-06 |  | 2021-09-17 |  | EXP | [8 empty] | 2021-07-07 | Connected |  | No
National Grid | LOWELL | 313391 | 1852 | 10 | Solar | 14_70L3 | 2020-09-17 14:33 | 2020-09-18 | 26 | 25 | 1 | 2020-10-28 | 2020-11-23 | 17 | 0 | 17 | [20 empty] | 2020-12-03 |  | 2021-10-27 |  | EXP | [8 empty] | 2021-04-30 | Connected |  | Yes
National Grid | WESTFORD | 312114 | 1886 | 13.6 | Solar | 14_57L2 | 2020-09-17 15:27 | 2020-09-18 | 4 | 0 | 4 | 2020-09-25 | 2020-10-23 | 18 | 0 | 18 | [20 empty] | 2020-10-26 | 2020-09-17 17:04 | 2021-09-01 |  | EXP | [8 empty] | 2021-01-15 | Connected |  | Yes
National Grid | BELLINGHAM | 313308 | 2019 | 25 | Solar | 05_344W4 | 2020-09-17 17:04 | 2020-09-18 | 3 | 0 | 3 | 2020-09-24 | 2020-10-21 | 18 | 1 | 17 | [20 empty] | 2020-10-23 |  | 2021-10-22 |  | EXP | [8 empty] | 2021-06-04 | Connected |  | No
National Grid | PALMER | 308061 | 1069 | 2500 | Solar | 09_514L1 | 2020-09-17 17:35 | 2020-09-18 | 21 | 15 | 6 | [10 empty] | 2020-10-21 | 2020-11-17 | 18 | 0 | 18 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WEBSTER | 306367 | 1570 | 6 | Solar | 01_412L1 | 2020-09-18 12:26 | 2020-09-21 | 0 | 0 | 0 | 2020-09-22 | 2020-10-13 | 14 | 0 | 14 | [20 empty] | 2020-10-14 |  | 2021-09-20 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HAVERHILL | 313668 | 1832 | 6 | Solar | 14_43L6 | 2020-09-18 14:15 | 2020-09-21 | 0 | 0 | 0 | 2020-09-22 | 2020-10-06 | 10 | 0 | 10 | [20 empty] | 2020-10-07 |  | 2021-09-21 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MILLVILLE | 311259 | 1529 | 60 | Solar | 05_321W9 | 2020-09-18 16:14 | 2020-09-21 | 6 | 0 | 6 | 2020-09-30 | 2020-12-09 | 47 | 24 | 23 | [20 empty] | 2020-12-14 |  | 2022-07-20 |  | EXP | [8 empty] | 2022-07-01 | Connected |  | No
National Grid | LOWELL | 307087 | 1850 | 7.6 | Solar | 14_75L5 | 2020-09-18 16:16 | 2020-09-21 | 3 | 0 | 3 | 2020-09-25 | 2020-10-30 | 24 | 7 | 17 | [20 empty] | 2020-11-03 |  | 2021-09-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 306473 | 1844 | 10 | Solar | 14_63L1 | 2020-09-18 16:47 | 2020-09-21 | 3 | 0 | 3 | 2020-09-25 | 2020-10-26 | 20 | 0 | 20 | [20 empty] | 2020-10-26 |  | 2021-09-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOUTHBRIDGE | 300622 | 1550 | 4950 | Other | 01_413L3 | 2020-09-22 09:43 | 2020-09-23 | 6 | 1 | 5 | [10 empty] | 2020-10-02 | 2020-10-29 | 18 | 1 | 17 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | ATHOL | 312441 | 1331 | 4950 | Other | 09_702W3 | 2020-09-22 09:55 | 2020-09-23 | 5 | 0 | 5 | [10 empty] | 2020-10-01 | 2020-10-27 | 17 | 0 | 17 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WARREN | 311809 | 1083 | 12000 | Other | 09_516L3 | 2020-09-22 10:47 | 2020-09-23 | 5 | 0 | 5 | [10 empty] | 2020-10-01 | 2020-10-27 | 17 | 0 | 17 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 292786 | 1844 | 15.705 | Solar | 14_63L1 | 2020-09-22 11:28 | 2020-09-23 | 126 | 125 | 1 | 2021-03-24 | 2021-04-14 | 15 | 0 | 15 | [20 empty] | 2021-04-15 | 2020-09-22 13:13 | 2022-10-09 |  | EXP | [8 empty] | 2022-09-28 | Connected |  | No
National Grid | LEOMINSTER | 310355 | 1453 | 6 | Solar | 01_225W3 | 2020-09-22 13:13 | 2020-09-23 | 1 | 0 | 1 | 2020-09-25 | 2020-11-13 | 33 | 16 | 17 | [20 empty] | 2020-11-17 | 2020-09-22 13:54 | 2021-09-01 | Yes | EXP |  | 2021-05-25 | 2021-06-15 | 21 | 0 | 21 |  |  | 2021-08-06 | Connected |  | No
National Grid | MARLBOROUGH | 311656 | 1752 | 10 | Solar | 05_311W6 | 2020-09-22 13:54 | 2020-09-23 | 1 | 0 | 1 | 2020-09-25 | 2020-10-23 | 19 | 0 | 19 | [20 empty] | 2020-10-26 |  | 2021-09-01 | Yes | EXP |  | 2021-02-26 | 2021-03-12 | 14 | 0 | 14 |  |  | 2021-04-07 | Connected |  | No
National Grid | STOCKBRIDGE | 314341 | 1262 | 20 | Solar | 09_1103W1 | 2020-09-22 18:32 | 2020-09-23 | 1 | 1 | 0 | 2020-09-25 | 2020-10-24 | 20 | 0 | 20 | [20 empty] | 2020-10-26 |  | 2021-10-26 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SALISBURY | 311019 | 1952 | 7.6 | Solar | 14_7L4 | 2020-09-22 18:43 | 2020-09-23 | 0 | 0 | 0 | 2020-09-24 | 2020-10-19 | 16 | 0 | 16 | [20 empty] | 2020-10-20 |  | 2021-10-20 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | REVERE | 309830 | 2151 | 10 | Solar | 12_7J6 | 2020-09-23 18:57 | 2020-09-24 | 62 | 54 | 8 | [27 empty] | 2021-09-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 309398 | 2301 | 10 | Solar | 07_911W25 | 2020-09-24 09:08 | 2020-09-25 | 1 | 0 | 1 | 2020-09-29 | 2020-11-16 | 32 | 13 | 19 | [20 empty] | 2020-11-23 | 2020-09-24 12:27 | 2021-09-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SALEM | 266036 | 1970 | 7.6 | Solar | 12_2W1 | 2020-09-24 12:27 | 2020-09-25 | 0 | 0 | 0 | 2020-09-28 | 2020-10-15 | 12 | 0 | 12 | [20 empty] | 2020-01-02 |  | 2021-10-15 | Yes | EXP |  | 2021-02-05 | 2021-03-17 | 40 | 0 | 40 |  |  | 2021-03-20 | Connected |  | No
National Grid | WINTHROP | 312766 | 2152 | 3.8 | Solar | 12_22J7 | 2020-09-24 15:20 | 2020-09-25 | 1 | 0 | 1 | 2020-09-29 | 2020-11-23 | 37 | 20 | 17 | [20 empty] | 2020-11-25 |  | 2021-09-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MALDEN | 304213 | 2148 | 6 | Solar | 12_37W8 | 2020-09-24 15:29 | 2020-09-25 | 61 | 40 | 21 | 2020-12-24 | 2021-01-19 | 15 | 0 | 15 | [22 empty] | 2021-09-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RANDOLPH | 308462 | 2368 | 6 | Solar | 07_5W3 | 2020-09-24 15:30 | 2020-09-25 | 1 | 0 | 1 | 2020-09-29 | 2020-10-30 | 22 | 5 | 17 | [20 empty] | 2020-11-03 |  | 2021-09-01 |  | EXP | [8 empty] | 2021-05-11 | Connected |  | No
National Grid | FRANKLIN | 314915 | 2038 | 7.6 | Solar | 05_344W5 | 2020-09-24 15:46 | 2020-09-25 | 0 | 0 | 0 | 2020-09-28 | 2020-10-26 | 19 | 0 | 19 | [20 empty] | 2020-10-26 |  | 2021-10-26 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEBSTER | 315053 | 1570 | 50 | Solar | 01_412L5 | 2020-09-25 09:22 | 2020-09-28 | 6 | 1 | 5 | 2020-10-07 | 2020-11-17 | 27 | 8 | 19 | [20 empty] | 2020-11-18 |  |  |  | EXP | [8 empty] | 2021-02-03 | Connected |  | No
National Grid | NORTH ANDOVER | 315160 | 1845 | 15.2 | Solar | 14_56L2 | 2020-09-25 12:18 | 2020-09-28 | 3 | 0 | 3 | 2020-10-02 | 2020-11-04 | 18 | 0 | 18 | [20 empty] | 2020-11-03 | 2020-09-25 12:44 | 2021-09-01 |  | EXP | [8 empty] | 2021-05-10 | Connected |  | No
National Grid | ATHOL | 302401 | 1331 | 10 | Solar | 09_702W2 | 2020-09-25 12:44 | 2020-09-28 | 3 | 0 | 3 | 2020-10-02 | 2020-10-29 | 18 | 0 | 18 | [20 empty] | 2020-11-02 | 2020-09-25 13:59 | 2021-11-02 | Yes | EXP |  | 2021-01-27 | 2021-02-12 | 15 | 0 | 15 |  |  | 2021-03-31 | Connected |  | No
National Grid | GARDNER | 314893 | 1440 | 25 | Solar | 01_601W3 | 2020-09-25 13:59 | 2020-09-28 | 1 | 0 | 1 | 2020-09-30 | 2020-10-29 | 20 | 0 | 20 | [20 empty] | 2020-11-12 | 2020-09-25 14:41 | 2023-02-28 | Yes | EXP |  | 2021-09-10 | 2021-09-09 | 0 | 0 | 0 |  |  |  | Withdrawn |  | No
National Grid | SOMERSET | 300899 | 2726 | 10 | Solar | 05_19W72 | 2020-09-25 14:41 | 2020-09-28 | 26 | 24 | 2 | 2020-11-04 | 2020-11-23 | 12 | 0 | 12 | [20 empty] | 2020-12-03 | 2020-09-25 17:42 | 2021-11-03 | Yes | EXP |  | 2021-02-05 | 2021-04-06 | 60 | 0 | 60 |  |  | 2021-04-08 | Connected |  | No
National Grid | HOLBROOK | 297040 | 2343 | 10 | Solar | 07_10W1 | 2020-09-25 17:42 | 2020-09-28 | 3 | 0 | 3 | 2020-10-02 | 2020-10-29 | 18 | 0 | 18 | [20 empty] | 2020-11-03 | 2020-09-28 10:50 | 2021-09-01 | Yes | EXP | [8 empty] | 2021-06-11 | Connected |  | No
National Grid | QUINCY | 309572 | 2169 | 6.96 | Solar | 07_1W2 | 2020-09-28 10:50 | 2020-09-29 | 5 | 3 | 2 | 2020-10-06 | 2020-10-30 | 17 | 0 | 17 | [20 empty] | 2020-11-03 | 2020-09-28 12:01 | 2021-11-03 | Yes | EXP |  | 2021-01-13 | 2021-02-24 | 41 | 0 | 41 |  |  | 2021-03-10 | Connected |  | No
National Grid | STOUGHTON | 306593 | 2072 | 10 | Solar | 07_913W67 | 2020-09-28 12:01 | 2020-09-29 | 2 | 0 | 2 | 2020-10-02 | 2020-11-02 | 20 | 1 | 19 | [20 empty] | 2020-11-04 |  | 2021-09-01 | Yes | EXP |  | 2021-03-17 | 2021-04-07 | 21 | 0 | 21 |  |  | 2021-05-13 | Connected |  | No
National Grid | MEDFORD | 315641 | 2155 | 7.68 | Solar | 12_37W1 | 2020-09-28 22:58 | 2020-09-29 | 14 | 12 | 2 | 2020-10-20 | 2020-11-12 | 16 | 0 | 16 | [20 empty] | 2020-11-17 | 2020-09-29 11:26 | 2021-10-19 |  | EXP | [8 empty] | 2021-03-24 | Connected |  | No
National Grid | RUTLAND | 312260 | 1543 | 5.52 | Solar | 01_55W1 | 2020-09-29 11:26 | 2020-09-30 | 43 | 40 | 3 | 2020-12-04 | 2021-01-05 | 20 | 0 | 20 | [20 empty] | 2021-01-05 | 2020-09-29 11:59 | 2022-12-24 | Yes | EXP |  | 2021-01-28 | 2021-02-25 | 28 | 0 | 28 |  |  | 2022-12-08 | Connected |  | No
National Grid | LYNN | 310486 | 1902 | 7.6 | Solar | 12_22W2 | 2020-09-29 11:59 | 2020-09-30 | 0 | 0 | 0 | 2020-10-01 | 2020-10-29 | 19 | 0 | 19 | [20 empty] | 2020-11-13 | 2020-09-29 14:04 | 2021-09-01 | Yes | EXP |  | 2021-03-10 | 2021-06-11 | 93 | 0 | 93 |  |  | 2021-07-02 | Connected |  | No
National Grid | FRANKLIN | 311913 | 2038 | 10 | Solar | 05_348W7 | 2020-09-29 14:04 | 2020-09-30 | 2 | 0 | 2 | 2020-10-05 | 2020-11-09 | 24 | 5 | 19 | [20 empty] | 2020-11-12 | 2020-09-29 15:15 | 2022-03-10 | Yes | EXP |  | 2021-06-09 | 2021-09-10 | 92 | 3 | 89 |  |  | 2021-12-01 | Connected |  | No
National Grid | BROCKTON | 309629 | 2301 | 7.6 | Solar | 07_91W49 | 2020-09-29 15:15 | 2020-09-30 | 2 | 0 | 2 | 2020-10-05 | 2020-11-10 | 26 | 8 | 18 | [20 empty] | 2020-11-17 |  | 2022-01-24 | Yes | EXP |  | 2021-08-21 | 2021-08-30 | 3 | 0 | 3 |  |  | 2021-10-19 | Connected |  | No
National Grid | REVERE | 311805 | 2151 | 7.6 | Solar | 12_7W2 | 2020-09-29 15:51 | 2020-09-30 | 2 | 0 | 2 | 2020-10-05 | 2020-11-04 | 21 | 0 | 21 | [20 empty] | 2020-11-17 |  | 2021-09-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ANDOVER | 308036 | 1810 | 20 | Battery Add-On | 14_59L1 | 2020-09-30 07:10 | 2020-10-01 | 11 | 9 | 2 | 2020-10-19 | 2020-11-12 | 17 | 0 | 17 | [20 empty] | 2020-11-18 |  | 2022-04-15 |  | EXP | [8 empty] | 2022-03-25 | Connected |  | No
National Grid | FLORIDA | 308535 | 1247 | 2125 | Solar | 09_1015W1 | 2020-09-30 12:06 | 2020-10-01 | 4 | 0 | 4 | [10 empty] | 2020-10-08 | 2020-12-04 | 38 | 21 | 17 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | REVERE | 311130 | 2151 | 7.6 | Solar | 12_35J1 | 2020-09-30 13:20 | 2020-10-01 | 3 | 0 | 3 | 2020-10-07 | 2020-11-04 | 19 | 0 | 19 | [20 empty] | 2020-11-17 | 2020-10-01 07:55 | 2021-09-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 311151 | 2301 | 10 | Solar | 07_91W43 | 2020-10-01 07:55 | 2020-10-05 | 1 | 0 | 1 | 2020-10-07 | 2020-11-02 | 17 | 0 | 17 | [20 empty] | 2020-11-04 | 2020-10-01 16:48 | 2022-08-18 | Yes | EXP |  | 2021-08-10 | 2021-10-12 | 42 | 3 | 39 |  |  | 2021-12-20 | Connected |  | No
National Grid | BROCKTON | 313208 | 2301 | 7.6 | Solar | 07_91W49 | 2020-10-01 16:48 | 2020-10-02 | 2 | 0 | 2 | 2020-10-07 | 2020-10-30 | 16 | 0 | 16 | [20 empty] | 2020-11-03 | 2020-10-01 18:15 | 2024-05-20 | Yes | EXP |  | 2021-01-08 | 2021-01-21 | 13 | 0 | 13 |  |  | 2023-08-07 | Connected |  | No
National Grid | MALDEN | 313741 | 2148 | 7.6 | Solar | 12_37W10 | 2020-10-01 18:15 | 2020-10-02 | 2 | 0 | 2 | 2020-10-07 | 2020-11-02 | 17 | 0 | 17 | [20 empty] | 2020-11-04 | 2020-10-01 19:38 | 2021-11-13 | Yes | EXP |  | 2021-08-02 | 2021-08-11 | 9 | 0 | 9 |  |  | 2021-09-15 | Connected |  | Yes
National Grid | REVERE | 314661 | 2151 | 3.8 | Solar | 12_35J4 | 2020-10-01 19:38 | 2020-10-02 | 1 | 0 | 1 | 2020-10-06 | 2020-11-06 | 22 | 0 | 22 | [20 empty] | 2020-11-06 |  | 2021-11-05 | Yes | EXP |  | 2021-01-21 | 2021-04-08 | 77 | 0 | 77 |  |  | 2021-07-14 | Connected |  | No
National Grid | BRIDGEWATER | 316356 | 2324 | 100 | Solar | 07_912W73 | 2020-10-02 08:41 | 2020-10-05 | 20 | 14 | 6 | 2020-11-04 | 2020-12-30 | 32 | 13 | 19 | [20 empty] | 2020-12-31 |  |  |  | EXP | [8 empty] | 2023-01-03 | Connected |  | No
National Grid | BRIDGEWATER | 316450 | 2324 | 100 | Solar | 07_912W73 | 2020-10-02 08:42 | 2020-10-05 | 9 | 0 | 9 | 2020-10-20 | 2020-12-30 | 48 | 26 | 22 | [20 empty] | 2020-12-31 | 2020-10-02 09:05 | 2022-08-19 |  | EXP | [8 empty] | 2022-08-10 | Connected |  | No
National Grid | BRIDGEWATER | 316462 | 2324 | 250 | Solar | 07_912W73 | 2020-10-02 09:05 | 2020-10-05 | 10 | 0 | 10 | [10 empty] | 2020-10-20 | 2022-03-11 | 349 | 314 | 35 | [10 empty] | 2022-12-09 |  | 2024-05-28 | Yes | STD | [9 empty] | Completion Documents |  | No
National Grid | BRIDGEWATER | 316478 | 2324 | 100 | Solar | 07_797W1 | 2020-10-02 09:33 | 2020-10-05 | 20 | 14 | 6 | 2020-11-04 | 2020-12-30 | 37 | 15 | 22 | [20 empty] | 2020-12-31 |  | 2022-08-19 |  | EXP | [8 empty] | 2022-08-01 | Connected |  | No
National Grid | PEPPERELL | 314437 | 1463 | 3.8 | Solar | 01_226L1 | 2020-10-02 10:28 | 2020-10-05 | 1 | 0 | 1 | 2020-10-07 | 2020-11-01 | 17 | 0 | 17 | [20 empty] | 2020-11-03 | 2020-10-02 11:48 | 2021-10-01 |  | EXP | [8 empty] | 2021-03-12 | Connected |  | No
National Grid | RANDOLPH | 307716 | 2368 | 3.8 | Solar | 07_5W3 | 2020-10-02 11:48 | 2020-10-05 | 10 | 7 | 3 | 2020-10-21 | 2020-11-16 | 17 | 0 | 17 | [20 empty] | 2020-11-19 | 2020-10-02 14:28 | 2021-10-20 | Yes | EXP |  | 2021-04-17 | 2021-06-10 | 54 | 0 | 54 |  |  | 2021-07-29 | Connected |  | No
National Grid | STOUGHTON | 316717 | 2072 | 12 | Solar | 07_913W69 | 2020-10-02 14:28 | 2020-10-05 | 5 | 4 | 1 | 2020-10-13 | 2020-11-17 | 20 | 0 | 20 | [20 empty] | 2020-11-17 |  | 2022-01-24 | Yes | EXP |  | 2020-12-13 | 2020-12-30 | 17 | 0 | 17 |  |  | 2021-09-15 | Connected |  | No
National Grid | EVERETT | 310462 | 2149 | 10 | Solar | 12_16W7 | 2020-10-02 15:10 | 2020-10-05 | 1 | 0 | 1 | 2020-10-07 | 2020-11-04 | 19 | 0 | 19 | [20 empty] | 2020-11-16 |  | 2021-10-01 |  | EXP | [8 empty] | 2021-05-01 | Connected |  | Yes
National Grid | WORCESTER | 309736 | 1607 | 7.6 | Solar | 01_8W2 | 2020-10-02 15:39 | 2020-10-05 | 1 | 0 | 1 | 2020-10-07 | 2020-10-30 | 16 | 0 | 16 | [20 empty] | 2020-11-03 | 2020-10-02 17:23 | 2021-10-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BLACKSTONE | 304759 | 1504 | 9.8 | Solar | 05_108W60 | 2020-10-02 17:23 | 2020-10-05 | 8 | 8 | 0 | 2020-10-16 | 2020-11-12 | 18 | 0 | 18 | [20 empty] | 2020-11-17 |  | 2021-10-15 | Yes | EXP |  | 2021-03-31 | 2021-05-21 | 51 | 0 | 51 |  |  | 2021-05-27 | Connected |  | No
National Grid | SUTTON | 305873 | 1590 | 1750 | Solar | 01_304W6 | 2020-10-05 09:07 | 2020-10-06 | 11 | 6 | 5 | [10 empty] | 2020-10-22 | 2020-11-16 | 16 | 0 | 16 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTMINSTER | 311776 | 1473 | 4990 | Solar | 01_609W2 | 2020-10-05 10:14 | 2020-10-06 | 5 | 0 | 5 | [10 empty] | 2020-10-15 | 2020-11-09 | 17 | 0 | 17 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | NANTUCKET | 315235 | 2554 | 11.4 | Solar | 04_101L7 | 2020-10-05 11:28 | 2020-10-06 | 4 | 2 | 2 | 2020-10-13 | 2020-11-07 | 19 | 0 | 19 | [20 empty] | 2020-11-12 |  | 2021-10-05 |  | EXP | [8 empty] | 2021-06-25 | Connected |  | No
National Grid | ABINGTON | 316919 | 2351 | 17.6 | Battery Add-On | 07_93W42 | 2020-10-05 12:21 | 2020-10-06 | 3 | 1 | 2 | 2020-10-09 | 2020-11-02 | 15 | 0 | 15 | [20 empty] | 2020-11-03 | 2020-10-05 12:52 | 2022-07-11 |  | EXP | [8 empty] | 2022-01-06 | Connected |  | No
National Grid | LEOMINSTER | 294875 | 1453 | 4948 | Other | 01_225W4 | 2020-10-05 12:52 | 2020-10-06 | 1 | 0 | 1 | [10 empty] | 2020-10-08 | 2020-11-02 | 16 | 0 | 16 | [12 empty] | 2025-08-24 | Yes | STD | [9 empty] | Pending Withdraw |  | No
National Grid | NORTHBOROUGH | 317103 | 1532 | 10 | Solar | 05_313W1 | 2020-10-05 14:47 | 2020-10-06 | 2 | 0 | 2 | 2020-10-09 | 2020-11-03 | 16 | 0 | 16 | [20 empty] | 2020-11-04 |  | 2021-10-06 |  | EXP | [8 empty] | 2020-12-22 | Connected |  | No
National Grid | COHASSET | 317141 | 2025 | 7.6 | Solar | 07_18J1 | 2020-10-05 16:01 | 2020-10-06 | 18 | 16 | 2 | 2020-11-03 | 2020-11-23 | 14 | 1 | 13 | [20 empty] | 2020-12-03 |  | 2021-10-01 |  | EXP | [8 empty] | 2021-02-03 | Connected |  | No
National Grid | WARE | 315000 | 1082 | 5 | Solar | 09_501L2 | 2020-10-06 05:12 | 2020-11-03 | 70 | 48 | 22 | [26 empty] | 2020-10-06 09:50 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | PEPPERELL | 312534 | 1463 | 7.6 | Solar | 01_226L2 | 2020-10-06 09:50 | 2020-10-07 | 3 | 0 | 3 | 2020-10-13 | 2020-11-09 | 19 | 0 | 19 | [20 empty] | 2020-11-12 |  | 2021-10-01 | Yes | EXP |  | 2021-07-23 | 2021-07-26 | 4 | 0 | 4 |  |  | 2021-08-12 | Connected |  | No
National Grid | FALL RIVER | 317453 | 2721 | 50 | Solar | 05_115W53 | 2020-10-06 13:20 | 2020-10-07 | 18 | 13 | 5 | 2020-11-04 | 2020-12-03 | 19 | 0 | 19 | [20 empty] | 2021-01-07 |  |  |  | EXP | [8 empty] | 2021-03-05 | Connected |  | No
National Grid | ATTLEBORO | 317491 | 2703 | 50 | Solar | 05_8L3 | 2020-10-06 14:29 | 2020-10-07 | 5 | 0 | 5 | 2020-10-16 | 2020-11-16 | 20 | 0 | 20 | [20 empty] | 2020-12-05 |  |  |  | EXP | [8 empty] | 2021-02-02 | Connected |  | No
National Grid | LEOMINSTER | 317534 | 1453 | 50 | Solar | 01_207W2 | 2020-10-06 15:53 | 2020-10-07 | 5 | 0 | 5 | 2020-10-16 | 2020-12-04 | 33 | 12 | 21 | [20 empty] | 2020-12-07 |  |  |  | EXP | [8 empty] | 2021-02-06 | Connected |  | No
National Grid | LAWRENCE | 317552 | 1841 | 33.3 | Solar | 14_6J4 | 2020-10-06 16:42 | 2020-10-07 | 23 | 15 | 8 | 2020-11-09 | 2020-12-09 | 19 | 0 | 19 | [20 empty] | 2020-12-14 |  |  |  | EXP | [8 empty] | 2021-02-11 | Connected |  | No
National Grid | ATTLEBORO | 310170 | 2703 | 10 | Solar | 05_8L3 | 2020-10-06 17:33 | 2020-10-07 | 2 | 0 | 2 | 2020-10-13 | 2020-11-06 | 18 | 0 | 18 | [20 empty] | 2020-11-06 |  | 2022-01-28 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 309000 | 1606 | 7.6 | Solar | 01_24W5 | 2020-10-06 17:52 | 2020-10-07 | 3 | 0 | 3 | 2020-10-13 | 2020-11-10 | 20 | 0 | 20 | [20 empty] | 2020-11-23 |  | 2022-03-02 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | QUINCY | 317594 | 2169 | 10 | Solar | 07_1W2 | 2020-10-06 19:50 | 2020-10-07 | 2 | 0 | 2 | 2020-10-13 | 2020-11-07 | 19 | 0 | 19 | [20 empty] | 2020-11-12 |  | 2021-10-06 |  | EXP | [8 empty] | 2021-03-19 | Connected |  | No
National Grid | SOUTHBRIDGE | 313745 | 1550 | 10 | Solar | 01_413L2 | 2020-10-07 00:53 | 2020-10-08 | 13 | 12 | 1 | 2020-10-28 | 2020-11-23 | 17 | 0 | 17 | [20 empty] | 2020-12-03 |  | 2021-10-27 |  | EXP | [8 empty] | 2021-03-24 | Connected |  | No
National Grid | WESTPORT | 314962 | 2790 | 26 | Solar | 56_33F4 | 2020-10-07 12:46 | 2020-10-08 | 1 | 0 | 1 | 2020-10-13 | 2020-12-08 | 39 | 21 | 18 | [20 empty] | 2020-12-10 | 2020-10-07 14:11 | 2021-10-08 |  | EXP | [8 empty] | 2021-06-02 | Connected |  | No
National Grid | SALEM | 314997 | 1970 | 3.8 | Solar | 12_2W1 | 2020-10-07 14:11 | 2020-10-08 | 2 | 0 | 2 | 2020-10-13 | 2020-12-09 | 39 | 25 | 14 | [20 empty] | 2020-12-14 |  | 2022-07-07 | Yes | EXP | [8 empty] | 2021-09-21 | Connected |  | Yes
National Grid | CHELMSFORD | 317800 | 1824 | 10 | Solar | 14_24L2 | 2020-10-07 14:17 | 2020-10-08 | 19 | 17 | 2 | 2020-11-05 | 2020-11-22 | 11 | 0 | 11 | [20 empty] | 2020-11-30 | 2020-10-07 14:51 | 2021-11-04 |  | EXP | [8 empty] | 2021-01-30 | Connected |  | No
National Grid | SCITUATE | 317813 | 2066 | 15.2 | Solar | 07_915W82 | 2020-10-07 14:51 | 2020-10-08 | 1 | 0 | 1 | 2020-10-13 | 2020-11-09 | 19 | 0 | 19 | [20 empty] | 2020-11-12 |  | 2022-02-27 | Yes | EXP |  | 2021-01-14 | 2021-01-27 | 13 | 0 | 13 |  |  | 2021-12-20 | Connected |  | No
National Grid | PALMER | 317367 | 1069 | 187.5 | Solar | 09_523L4 | 2020-10-07 14:52 | 2020-10-08 | 28 | 24 | 4 | 2020-11-20 | 2021-02-23 | 63 | 43 | 20 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | BOXFORD | 317831 | 1921 | 25 | Solar | 14_56L3 | 2020-10-07 15:41 | 2020-10-08 | 1 | 0 | 1 | 2020-10-13 | 2020-11-10 | 20 | 0 | 20 | [20 empty] | 2020-11-23 |  | 2021-10-01 |  | EXP | [8 empty] | 2021-03-26 | Connected |  | No
National Grid | BEVERLY | 316425 | 1915 | 120 | Other | 12_12L4 | 2020-10-07 16:25 | 2020-10-08 | 6 | 0 | 6 | 2020-10-20 | 2020-11-17 | 19 | 0 | 19 | [20 empty] | 2020-12-14 |  |  |  | EXP | [8 empty] | 2021-05-28 | Connected |  | No
National Grid | CHELMSFORD | 314332 | 1824 | 10 | Solar | 14_16L2 | 2020-10-08 09:23 | 2020-10-09 | 1 | 0 | 1 | 2020-10-13 | 2020-11-19 | 27 | 7 | 20 | [20 empty] | 2020-12-02 |  | 2022-01-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | QUINCY | 306165 | 2169 | 100 | Solar | 07_3W3 | 2020-10-08 10:59 | 2020-10-09 | 27 | 20 | 7 | 2020-11-20 | 2020-12-21 | 20 | 0 | 20 | [20 empty] | 2021-01-14 |  | 2022-11-02 |  | EXP | [8 empty] | 2022-10-13 | Connected |  | No
National Grid | BROCKTON | 305003 | 2301 | 6 | Solar | 07_94W40 | 2020-10-08 12:45 | 2020-10-09 | 1 | 0 | 1 | 2020-10-13 | 2020-11-19 | 26 | 9 | 17 | [20 empty] | 2020-11-25 |  | 2021-10-01 |  | EXP | [8 empty] | 2021-05-04 | Connected |  | No
National Grid | HOLBROOK | 318107 | 2343 | 9.57 | Solar | 07_97W3 | 2020-10-08 15:03 | 2020-10-09 | 6 | 6 | 0 | 2020-10-20 | 2020-11-25 | 25 | 15 | 10 | [20 empty] | 2020-12-04 |  | 2021-10-19 |  | EXP | [8 empty] | 2021-02-24 | Connected |  | Yes
National Grid | SAUGUS | 315692 | 1906 | 3.8 | Solar | 12_23W3 | 2020-10-08 16:10 | 2020-10-09 | 1 | 0 | 1 | 2020-10-14 | 2020-11-19 | 26 | 6 | 20 | [20 empty] | 2020-12-02 |  | 2021-10-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BRIDGEWATER | 318180 | 2324 | 9.28 | Solar | 07_912W55 | 2020-10-08 16:16 | 2020-10-09 | 0 | 0 | 0 | 2020-10-13 | 2020-11-07 | 19 | 0 | 19 | [20 empty] | 2020-11-12 |  | 2021-10-08 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BLACKSTONE | 317793 | 1504 | 6 | Solar | 05_321W9 | 2020-10-08 16:26 | 2020-10-09 | 0 | 0 | 0 | 2020-10-13 | 2020-11-09 | 19 | 0 | 19 | [20 empty] | 2020-11-12 |  | 2021-10-08 |  | EXP | [8 empty] | 2021-02-03 | Connected |  | No
National Grid | SWANSEA | 318194 | 2777 | 5.76 | Solar | 05_11W84 | 2020-10-08 16:38 | 2020-10-09 | 7 | 6 | 1 | 2020-10-21 | 2020-11-20 | 21 | 0 | 21 | [20 empty] | 2020-12-01 |  | 2021-10-01 |  | EXP | [8 empty] | 2021-02-11 | Connected |  | No
National Grid | NORTH ANDOVER | 318384 | 1845 | 10 | Solar | 14_56L3 | 2020-10-09 13:45 | 2020-10-13 | 2 | 2 | 0 | 2020-10-15 | 2020-11-09 | 17 | 0 | 17 | [20 empty] | 2020-11-12 |  | 2021-10-14 |  | EXP | [8 empty] | 2021-01-07 | Connected |  | No
National Grid | DUDLEY | 318399 | 1571 | 19.2 | Solar | 01_413L3 | 2020-10-09 14:39 | 2020-10-13 | 40 | 39 | 1 | [27 empty] | 2021-10-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 318214 | 1844 | 6.38 | Solar | 14_74L3 | 2020-10-09 16:18 | 2020-10-13 | 0 | 0 | 0 | 2020-10-13 | 2020-11-07 | 19 | 0 | 19 | [20 empty] | 2020-11-12 |  | 2021-10-01 |  | EXP | [8 empty] | 2021-01-08 | Connected |  | No
National Grid | NORTHBOROUGH | 318450 | 1532 | 15.2 | Solar | 05_313W2 | 2020-10-09 16:26 | 2020-10-13 | 1 | 0 | 1 | 2020-10-15 | 2020-11-09 | 17 | 0 | 17 | [20 empty] | 2020-11-12 |  | 2021-10-01 |  | EXP | [8 empty] | 2021-02-04 | Connected |  | No
National Grid | WESTFORD | 317580 | 1886 | 9.28 | Solar | 14_73L2 | 2020-10-09 17:35 | 2020-10-13 | 0 | 0 | 0 | 2020-10-13 | 2020-11-07 | 19 | 0 | 19 | [20 empty] | 2020-11-12 |  | 2021-04-30 |  | EXP | [8 empty] | 2021-01-04 | Connected |  | No
National Grid | WESTFORD | 318483 | 1886 | 20 | Solar | 14_57L1 | 2020-10-09 20:00 | 2020-10-13 | 1 | 0 | 1 | 2020-10-15 | 2020-11-12 | 20 | 2 | 18 | [20 empty] | 2020-11-17 | 2020-10-09 20:52 | 2021-04-30 |  | EXP | [8 empty] | 2021-01-14 | Connected |  | No
National Grid | WESTBOROUGH | 318365 | 1581 | 10 | Solar | 05_314W4 | 2020-10-09 20:52 | 2020-10-13 | 0 | 0 | 0 | 2020-10-13 | 2020-11-09 | 19 | 0 | 19 | [20 empty] | 2020-11-12 | 2020-10-12 11:28 | 2021-04-30 | Yes | EXP |  | 2021-01-28 | 2021-02-17 | 20 | 0 | 20 |  |  | 2021-03-04 | Connected |  | No
National Grid | UXBRIDGE | 309606 | 1569 | 3.8 | Solar | 05_321W6 | 2020-10-12 11:28 | 2020-10-13 | 1 | 0 | 1 | 2020-10-15 | 2020-11-23 | 27 | 11 | 16 | [20 empty] | 2020-11-25 |  | 2023-12-11 | Yes | EXP |  | 2022-04-14 | 2022-06-01 | 49 | 0 | 49 |  |  | 2023-11-13 | Connected |  | No
National Grid | LYNN | 266087 | 1902 | 6 | Solar | 12_21J30 | 2020-10-12 14:04 | 2020-10-13 | 5 | 5 | 0 | 2020-10-20 | 2020-11-16 | 18 | 0 | 18 | [20 empty] | 2020-11-19 |  | 2021-10-18 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LYNN | 311321 | 1904 | 6.48 | Solar | 12_29W1 | 2020-10-12 15:21 | 2020-10-13 | 1 | 0 | 1 | 2020-10-15 | 2021-01-14 | 60 | 41 | 19 | [20 empty] | 2021-01-20 |  |  |  | EXP | [8 empty] | 2021-05-13 | Connected |  | No
National Grid | EAST LONGMEADOW | 313267 | 1028 | 4.8 | Solar | 09_508L1 | 2020-10-13 07:27 | 2020-10-14 | 4 | 0 | 4 | 2020-10-21 | 2021-01-15 | 58 | 41 | 17 | [20 empty] | 2021-01-22 | 2020-10-13 09:32 |  |  | EXP | [8 empty] | 2021-03-12 | Connected |  | No
National Grid | EVERETT | 318011 | 2149 | 250 | Solar | 12_2401 | 2020-10-13 09:32 | 2020-10-14 | 8 | 1 | 7 | [10 empty] | 2020-10-26 | 2020-12-29 | 44 | 21 | 23 | [10 empty] | 2021-09-23 |  | 2023-11-13 | Yes | STD |  | 2023-01-18 | 2023-10-31 | 287 | 0 | 287 |  |  | 2023-11-16 | Connected |  | No
National Grid | STOUGHTON | 310322 | 2072 | 249 | Solar | 07_913W43 | 2020-10-13 11:46 | 2020-10-14 | 12 | 4 | 8 | 2020-10-30 | 2020-12-03 | 22 | 0 | 22 | 2021-04-30 | 2022-04-21 | 244 | 33 | 211 | [5 empty] | 2021-04-30 | 2022-04-21 | 244 | 33 | 211 | [9 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | LAWRENCE | 315756 | 1841 | 7.6 | Solar | 14_6J3 | 2020-10-13 12:01 | 2020-10-14 | 39 | 38 | 1 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SHEFFIELD | 318410 | 1257 | 249 | Solar | 09_1109W2 | 2020-10-13 12:31 | 2020-10-14 | 9 | 0 | 9 | [10 empty] | 2020-10-28 | 2020-12-01 | 22 | 1 | 21 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WRENTHAM | 318964 | 2093 | 19.25 | Solar | 05_3422W1 | 2020-10-13 14:54 | 2020-10-14 | 1 | 1 | 0 | 2020-10-15 | 2020-11-12 | 20 | 3 | 17 | [20 empty] | 2020-11-13 |  |  |  | EXP | [8 empty] | 2021-02-11 | Connected |  | No
National Grid | NEW MARLBOROUGH | 318967 | 1230 | 10 | Solar | 09_1109W1 | 2020-10-13 15:12 | 2020-10-14 | 4 | 4 | 0 | 2020-10-20 | 2020-11-12 | 16 | 0 | 16 | [20 empty] | 2020-11-18 |  | 2021-10-18 |  | EXP | [8 empty] | 2020-12-21 | Connected |  | No
National Grid | METHUEN | 318966 | 1844 | 249 | Solar | 14_75L4 | 2020-10-13 17:51 | 2020-10-14 | 19 | 12 | 7 | 2020-11-10 | 2021-01-05 | 37 | 13 | 24 | [20 empty] | 2021-01-14 | 2020-10-13 18:50 | 2022-01-23 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WEYMOUTH | 310769 | 2188 | 10 | Solar | 07_6W1 | 2020-10-13 18:50 | 2020-10-14 | 4 | 0 | 4 | 2020-10-21 | 2020-11-23 | 22 | 6 | 16 | [20 empty] | 2020-11-25 |  | 2022-12-01 | Yes | EXP |  | 2022-06-02 | 2022-07-21 | 50 | 0 | 50 |  |  | 2022-09-22 | Connected |  | Yes
National Grid | NORTHBOROUGH | 319057 | 1532 | 249 | Solar | 05_312W3 | 2020-10-13 19:47 | 2020-10-14 | 15 | 8 | 7 | 2020-11-18 | 2021-02-22 | 63 | 50 | 13 | [20 empty] | 2021-03-10 | 2020-10-14 07:48 | 2023-08-01 |  | EXP | [8 empty] | 2023-07-24 | Connected |  | No
National Grid | HUBBARDSTON | 319090 | 1452 | 15.2 | Solar | 01_602W2 | 2020-10-14 07:48 | 2020-10-15 | 0 | 0 | 0 | 2020-10-16 | 2020-11-12 | 18 | 0 | 18 | [20 empty] | 2020-11-18 |  | 2021-10-15 | Yes | EXP |  | 2021-03-02 | 2021-03-19 | 17 | 0 | 17 |  |  | 2021-07-15 | Connected |  | No
National Grid | GARDNER | 312149 | 1440 | 7.6 | Solar | 01_607W5 | 2020-10-14 09:29 | 2020-10-15 | 3 | 0 | 3 | 2020-10-21 | 2020-11-17 | 18 | 0 | 18 | [20 empty] | 2020-11-23 | 2020-10-14 18:53 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH ANDOVER | 319343 | 1845 | 15.2 | Solar | 14_56L2 | 2020-10-14 18:53 | 2020-10-15 | 0 | 0 | 0 | 2020-10-16 | 2020-11-13 | 19 | 0 | 19 | [20 empty] | 2020-11-18 | 2020-10-15 16:25 | 2021-10-15 |  | EXP |  | 2021-01-22 | 2021-02-04 | 13 | 0 | 13 |  |  | 2021-06-07 | Connected |  | No
National Grid | NEWBURY | 316180 | 1951 | 6 | Solar | 14_60L1 | 2020-10-15 16:25 | 2020-10-16 | 2 | 0 | 2 | 2020-10-21 | 2020-11-19 | 20 | 0 | 20 | [20 empty] | 2020-12-02 |  |  | Yes | EXP | [8 empty] | 2021-08-07 | Connected |  | No
National Grid | AVON | 318608 | 2322 | 2.4 | Solar | 07_75W3 | 2020-10-16 08:32 | 2020-10-19 | 3 | 0 | 3 | 2020-10-23 | 2020-11-19 | 18 | 0 | 18 | [20 empty] | 2020-12-02 |  | 2021-12-07 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTON | 319548 | 2766 | 499 | Solar | 05_8L2 | 2020-10-16 12:23 | 2020-10-19 | 39 | 32 | 7 | 2020-12-15 | 2021-02-17 | 88 | 71 | 17 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | LEOMINSTER | 317408 | 1453 | 7.25 | Solar | 01_225W3 | 2020-10-16 17:13 | 2020-10-19 | 1 | 0 | 1 | 2020-10-21 | 2020-11-19 | 20 | 0 | 20 | [20 empty] | 2020-12-02 | 2020-10-16 18:03 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MILLBURY | 319874 | 1527 | 15.2 | Solar | 01_304W5 | 2020-10-16 18:03 | 2020-10-19 | 4 | 4 | 0 | 2020-10-26 | 2020-11-24 | 20 | 0 | 20 | [20 empty] | 2020-12-01 | 2020-10-19 07:54 | 2022-03-26 | Yes | EXP |  | 2021-03-05 | 2021-03-16 | 11 | 0 | 11 |  |  | 2021-09-10 | Connected |  | No
National Grid | LYNN | 310786 | 1904 | 7.68 | Solar | 12_29W3 | 2020-10-19 07:54 | 2020-10-20 | 1 | 1 | 0 | 2020-10-21 | 2020-11-17 | 18 | 0 | 18 | [20 empty] | 2020-11-19 |  | 2022-04-21 | Yes | EXP |  | 2021-01-20 | 2021-03-12 | 51 | 0 | 51 |  |  | 2021-10-14 | Connected |  | No
National Grid | HANOVER | 313773 | 2339 | 16 | Solar | 07_95W5 | 2020-10-19 16:27 | 2020-10-20 | 0 | 0 | 0 | 2020-10-21 | 2020-11-19 | 20 | 0 | 20 | [20 empty] | 2020-12-02 |  | 2022-01-08 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LENOX | 320117 | 1240 | 133.3 | Solar | 09_1103W2 | 2020-10-19 19:25 | 2020-10-20 | 5 | 0 | 5 | 2020-10-28 | 2020-11-30 | 22 | 1 | 21 | [20 empty] | 2021-01-14 |  | 2022-01-31 |  | EXP | [8 empty] | 2022-01-25 | Connected |  | No
National Grid | WEBSTER | 317070 | 1570 | 10 | Solar | 01_412L2 | 2020-10-19 19:33 | 2020-10-20 | 10 | 8 | 2 | 2020-11-04 | 2020-11-22 | 12 | 0 | 12 | [20 empty] | 2020-11-30 |  | 2022-04-11 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEYMOUTH | 319983 | 2190 | 35 | Natural Gas | 07_99W32 | 2020-10-20 08:03 | 2020-10-21 | 308 | 116 | 192 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | ANDOVER | 320280 | 1810 | 8 | Solar | 14_54L3 | 2020-10-20 09:08 | 2020-10-21 | 14 | 13 | 1 | 2020-11-12 | 2020-12-01 | 12 | 0 | 12 | [20 empty] | 2020-12-04 |  | 2021-11-10 |  | EXP | [8 empty] | 2021-04-12 | Connected |  | No
National Grid | HEATH | 320192 | 1346 | 10 | Solar | 09_1019W1 | 2020-10-20 10:35 | 2020-10-21 | 2 | 2 | 0 | 2020-10-23 | 2020-11-18 | 17 | 0 | 17 | [20 empty] | 2020-11-20 | 2020-10-20 11:10 | 2021-11-27 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTPORT | 320315 | 2790 | 15.6 | Solar | 05_115W45 | 2020-10-20 11:10 | 2020-10-21 | 66 | 59 | 7 | 2021-01-28 | 2021-02-24 | 18 | 0 | 18 | [20 empty] | 2021-02-24 |  | 2022-07-16 | Yes | EXP |  | 2021-04-03 | 2021-05-17 | 44 | 0 | 44 |  |  | 2021-10-26 | Connected |  | No
National Grid | NEW BRAINTREE | 319692 | 1531 | 250 | Solar | 09_604W3 | 2020-10-20 12:10 | 2020-10-21 | 31 | 25 | 6 | [10 empty] | 2020-12-08 | 2021-01-06 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | ROCKPORT | 320446 | 1966 | 8 | Solar | 12_40J2 | 2020-10-20 15:47 | 2020-10-21 | 0 | 0 | 0 | [26 empty] | 2020-10-20 15:49 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BELCHERTOWN | 311886 | 1007 | 8.4 | Solar | 09_527L1 | 2020-10-20 15:49 | 2020-11-02 | 1 | 0 | 1 | 2020-11-04 | 2020-12-09 | 18 | 0 | 18 | [20 empty] | 2020-12-14 | 2020-10-20 16:00 | 2022-06-04 | Yes | EXP |  | 2021-06-25 | 2021-08-02 | 38 | 0 | 38 |  |  | 2021-12-20 | Connected |  | No
National Grid | LYNN | 307291 | 1905 | 6.72 | Solar | 12_29W1 | 2020-10-20 16:00 | 2020-10-21 | 0 | 0 | 0 | 2020-10-22 | 2020-12-09 | 33 | 15 | 18 | [20 empty] | 2020-12-21 | 2020-10-20 16:08 | 2022-09-25 | Yes | EXP |  | 2021-09-09 | 2021-09-23 | 15 | 0 | 15 |  |  |  | Withdrawn |  | Yes
National Grid | LYNN | 313757 | 1902 | 7.83 | Solar | 12_29W4 | 2020-10-20 16:08 | 2020-10-21 | 0 | 0 | 0 | 2020-10-22 | 2020-11-19 | 19 | 0 | 19 | [20 empty] | 2020-12-02 |  | 2022-08-31 | Yes | EXP |  | 2021-06-30 | 2021-07-26 | 27 | 0 | 27 |  |  | 2021-09-27 | Connected |  | Yes
National Grid | LOWELL | 317751 | 1850 | 9.6 | Solar | 14_75L1 | 2020-10-20 17:36 | 2020-10-21 | 38 | 37 | 1 | 2020-12-16 | 2021-01-20 | 22 | 0 | 22 | [20 empty] | 2021-01-08 |  | 2021-12-13 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 307513 | 1610 | 3.8 | Solar | 01_8W1 | 2020-10-21 15:39 | 2020-10-22 | 2 | 0 | 2 | 2020-10-27 | 2020-11-30 | 23 | 1 | 22 | [20 empty] | 2020-12-09 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 313292 | 1507 | 10 | Solar | 01_406L1 | 2020-10-21 19:50 | 2020-10-22 | 0 | 0 | 0 | 2020-10-23 | 2020-11-17 | 16 | 0 | 16 | [20 empty] | 2020-11-19 |  | 2021-10-21 |  | EXP | [8 empty] | 2021-07-22 | Connected |  | No
National Grid | EAST LONGMEADOW | 316243 | 1028 | 9.8 | Solar | 09_508L1 | 2020-10-21 19:56 | 2020-10-22 | 0 | 0 | 0 | 2020-10-23 | 2020-11-17 | 16 | 0 | 16 | [20 empty] | 2020-11-19 | 2020-10-21 20:26 | 2021-10-21 |  | EXP | [8 empty] | 2021-03-16 | Connected |  | No
National Grid | LAWRENCE | 316168 | 1841 | 7.6 | Solar | 14_63L1 | 2020-10-21 20:26 | 2020-10-22 | 0 | 0 | 0 | 2020-10-23 | 2020-11-20 | 19 | 0 | 19 | [20 empty] | 2020-11-24 | 2020-10-22 11:18 | 2021-10-21 | Yes | EXP |  | 2021-02-10 | 2021-04-05 | 54 | 0 | 54 |  |  | 2021-04-27 | Connected |  | No
National Grid | TEWKSBURY | 308551 | 1876 | 933.3 | Solar | 14_20L1 | 2020-10-22 11:18 | 2020-10-23 | 7 | 0 | 7 | [10 empty] | 2020-11-03 | 2020-12-21 | 33 | 14 | 19 | [10 empty] | 2022-10-12 |  | 2024-02-24 |  | STD | [9 empty] | Withdrawn |  | No
National Grid | FOXBOROUGH | 317765 | 2035 | 200 | Solar | 05_3422W3 | 2020-10-22 12:25 | 2020-10-23 | 22 | 15 | 7 | 2020-11-25 | 2021-08-04 | 173 | 69 | 104 | 2021-05-11 | 2023-12-28 | 659 | 33 | 626 | [5 empty] | 2021-05-11 | 2023-12-28 | 659 | 33 | 626 | [5 empty] | 2024-01-31 | 2020-10-22 17:43 |  |  | EXP | [9 empty] | Conditional Approval |  | No
National Grid | TEWKSBURY | 321076 | 1876 | 6.38 | Solar | 14_59L3 | 2020-10-22 17:43 | 2020-10-23 | 1 | 1 | 0 | 2020-10-26 | 2020-12-04 | 27 | 9 | 18 | [20 empty] | 2020-12-10 | 2020-10-23 11:35 | 2021-10-22 | Yes | EXP |  | 2021-03-19 | 2021-03-18 | 0 | 0 | 0 |  |  | 2021-04-28 | Connected |  | No
National Grid | BROCKTON | 311832 | 2301 | 10.32 | Solar | 07_91W49 | 2020-10-23 11:35 | 2020-10-26 | 0 | 0 | 0 | 2020-10-27 | 2020-12-02 | 22 | 0 | 22 | [20 empty] | 2020-12-02 |  | 2023-07-26 | Yes | EXP |  | 2020-12-18 | 2021-01-26 | 39 | 0 | 39 |  |  |  | Withdrawn |  | Yes
National Grid | SAUGUS | 315451 | 1906 | 12.48 | Solar | 12_19W2 | 2020-10-23 11:40 | 2020-10-26 | 1 | 0 | 1 | 2020-10-28 | 2020-12-02 | 22 | 2 | 20 | [20 empty] | 2020-12-02 |  |  |  | EXP |  | 2021-03-25 | 2021-06-24 | 91 | 0 | 91 |  |  | 2021-08-14 | Connected |  | No
National Grid | WESTFORD | 321224 | 1886 | 10 | Solar | 14_57L2 | 2020-10-23 12:14 | 2020-10-26 | 1 | 0 | 1 | 2020-10-28 | 2020-11-24 | 18 | 0 | 18 | [20 empty] | 2020-12-04 | 2020-10-23 13:19 | 2021-10-27 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BELLINGHAM | 321256 | 2019 | 7.6 | Solar | 05_108W60 | 2020-10-23 13:19 | 2020-10-26 | 1 | 0 | 1 | 2020-10-28 | 2020-11-25 | 19 | 0 | 19 | [20 empty] | 2020-12-04 |  | 2021-10-27 | Yes | EXP |  | 2021-02-05 | 2021-02-12 | 7 | 0 | 7 |  |  |  | Withdrawn |  | Yes
National Grid | PEPPERELL | 321315 | 1463 | 8.41 | Solar | 01_226L2 | 2020-10-23 15:45 | 2020-10-26 | 16 | 15 | 1 | 2020-11-19 | 2020-12-11 | 15 | 0 | 15 | [20 empty] | 2020-12-21 | 2020-10-26 09:33 | 2021-11-18 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BOLTON | 295570 | 1740 | 25 | Solar | 01_216W6 | 2020-10-26 09:33 | 2020-10-27 | 0 | 0 | 0 | 2020-10-28 | 2020-11-24 | 18 | 0 | 18 | [20 empty] | 2020-12-04 |  | 2022-10-25 | Yes | EXP |  | 2021-04-07 | 2021-04-28 | 21 | 0 | 21 |  |  | 2022-07-27 | Connected |  | No
National Grid | MENDON | 314484 | 1756 | 7.6 | Solar | 05_332W1 | 2020-10-26 10:59 | 2020-10-27 | 5 | 3 | 2 | 2020-11-04 | 2020-11-23 | 13 | 1 | 12 | [20 empty] | 2020-11-30 | 2020-10-26 15:57 | 2021-11-03 |  | EXP | [8 empty] | 2021-01-26 | Connected |  | No
National Grid | BROCKTON | 315002 | 2302 | 7.6 | Solar | 07_91W40 | 2020-10-26 15:57 | 2020-10-27 | 0 | 0 | 0 | 2020-10-28 | 2020-11-24 | 18 | 0 | 18 | [20 empty] | 2020-11-25 |  |  | Yes | EXP |  | 2021-02-18 | 2021-02-24 | 5 | 0 | 5 |  |  | 2021-03-10 | Connected |  | No
National Grid | MONTEREY | 321762 | 1245 | 7.83 | Solar | 09_1109W1 | 2020-10-26 16:53 | 2020-10-27 | 0 | 0 | 0 | 2020-10-28 | 2020-11-30 | 22 | 1 | 21 | [20 empty] | 2020-12-04 |  | 2021-10-26 |  | EXP | [8 empty] | 2021-01-07 | Connected |  | No
National Grid | WESTFORD | 321713 | 1886 | 16 | Solar | 14_58L1 | 2020-10-26 17:12 | 2020-10-27 | 0 | 0 | 0 | 2020-10-28 | 2020-11-30 | 22 | 1 | 21 | [20 empty] | 2020-12-07 |  | 2022-04-17 |  | EXP | [8 empty] | 2021-11-23 | Connected |  | No
National Grid | WESTMINSTER | 321925 | 1473 | 7.6 | Solar | 01_602W3 | 2020-10-27 10:41 | 2020-10-28 | 0 | 0 | 0 | 2020-10-29 | 2020-11-22 | 16 | 0 | 16 | [20 empty] | 2020-11-30 |  | 2022-11-19 |  | EXP | [8 empty] | 2022-10-05 | Connected |  | No
National Grid | HAMPDEN | 273953 | 1036 | 3984 | Solar | 09_139L5 | 2020-10-27 12:12 | 2020-10-28 | 51 | 41 | 10 | [10 empty] | 2021-01-13 | 2021-02-09 | 18 | 0 | 18 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | ATHOL | 273962 | 1331 | 2500 | Solar | 09_702W2 | 2020-10-27 12:13 | 2020-10-28 | 67 | 58 | 9 | [10 empty] | 2021-02-08 | 2021-03-01 | 14 | 0 | 14 | [11 empty] | 2020-10-27 12:21 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | CHELMSFORD | 243763 | 1824 | 600 | Natural Gas | 14_2384 | 2020-10-27 12:21 | 2020-10-28 | 25 | 19 | 6 | [10 empty] | 2020-12-04 | 2021-01-14 | 28 | 9 | 19 | [10 empty] | 2021-07-07 |  | 2022-10-28 | Yes | STD |  | 2022-09-22 | 2022-09-21 | 0 | 0 | 0 |  |  | 2022-10-05 | Connected |  | No
National Grid | ABINGTON | 322008 | 2351 | 9.84 | Solar | 07_60J1 | 2020-10-27 13:07 | 2020-10-28 | 1 | 0 | 1 | 2020-10-30 | 2020-11-22 | 15 | 0 | 15 | [20 empty] | 2020-11-30 |  | 2021-10-27 |  | EXP | [8 empty] | 2021-01-28 | Connected |  | No
National Grid | NORTH BROOKFIELD | 290420 | 1535 | 5000 | Other | 01_552L3 | 2020-10-27 13:12 | 2020-10-28 | 38 | 30 | 8 | [10 empty] | 2020-12-23 | 2021-01-19 | 15 | 0 | 15 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 312794 | 1844 | 3.84 | Solar | 14_74L3 | 2020-10-27 13:12 | 2020-10-28 | 61 | 26 | 35 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEYMOUTH | 319521 | 2191 | 6.48 | Solar | 07_6W1 | 2020-10-27 13:31 | 2020-10-28 | 11 | 9 | 2 | 2020-11-16 | 2020-12-07 | 14 | 0 | 14 | [20 empty] | 2020-12-10 |  | 2021-11-12 |  | EXP | [8 empty] | 2021-02-17 | Connected |  | Yes
National Grid | HANOVER | 322067 | 2339 | 15.36 | Solar | 07_95W5 | 2020-10-27 15:26 | 2020-10-28 | 1 | 0 | 1 | 2020-10-30 | 2020-11-22 | 15 | 0 | 15 | [20 empty] | 2020-11-30 |  | 2021-10-27 |  | EXP | [8 empty] | 2021-06-14 | Connected |  | No
National Grid | BROCKTON | 316230 | 2302 | 7.6 | Solar | 07_911W77 | 2020-10-27 15:34 | 2020-10-28 | 0 | 0 | 0 | 2020-10-29 | 2020-11-30 | 21 | 1 | 20 | [20 empty] | 2020-12-09 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WEST STOCKBRIDGE | 322044 | 1266 | 9.86 | Solar | 09_1109W3 | 2020-10-27 15:41 | 2020-10-28 | 4 | 2 | 2 | 2020-11-04 | 2020-11-22 | 12 | 0 | 12 | [20 empty] | 2020-11-30 |  | 2021-11-03 |  | EXP | [8 empty] | 2021-01-28 | Connected |  | No
National Grid | REVERE | 318712 | 2151 | 7.6 | Solar | 12_7W2 | 2020-10-27 16:37 | 2020-10-28 | 3 | 0 | 3 | 2020-11-03 | 2020-11-23 | 13 | 0 | 13 | [20 empty] | 2020-11-25 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ADAMS | 291641 | 1220 | 5000 | Other | 09_1021W1 | 2020-10-28 12:05 | 2020-10-29 | 23 | 17 | 6 | [10 empty] | 2020-12-03 | 2021-02-08 | 44 | 26 | 18 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SWANSEA | 291768 | 2777 | 5000 | Other | 05_11W85 | 2020-10-28 12:07 | 2020-10-29 | 36 | 29 | 7 | [10 empty] | 2020-12-22 | 2021-01-19 | 17 | 0 | 17 | [10 empty] | 2021-11-02 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | STOUGHTON | 322312 | 2072 | 7.6 | Solar | 07_913W47 | 2020-10-28 13:26 | 2020-10-29 | 0 | 0 | 0 | 2020-10-30 | 2020-11-25 | 17 | 0 | 17 | [20 empty] | 2020-12-04 |  | 2021-10-28 |  | EXP | [8 empty] | 2021-03-09 | Connected |  | No
National Grid | LAWRENCE | 318215 | 1843 | 7.6 | Solar | 14_61L2 | 2020-10-28 17:56 | 2020-10-29 | 2 | 0 | 2 | 2020-11-03 | 2020-11-30 | 17 | 0 | 17 | [20 empty] | 2020-12-02 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SHUTESBURY | 300938 | 1072 | 4998 | Solar | 09_704W1 | 2020-10-29 12:09 | 2020-10-30 | 5 | 0 | 5 | [10 empty] | 2020-11-12 | 2021-01-05 | 36 | 20 | 16 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | SHUTESBURY | 300932 | 1072 | 2000 | Solar | 09_704W1 | 2020-10-29 12:17 | 2020-10-30 | 13 | 7 | 6 | [10 empty] | 2020-11-19 | 2021-01-18 | 39 | 21 | 18 | [11 empty] | 2020-10-29 15:43 |  |  | STD | [9 empty] | Group Study |  | No
National Grid | LAWRENCE | 317759 | 1843 | 7.6 | Solar | 14_61L3 | 2020-10-29 15:43 | 2020-10-30 | 1 | 0 | 1 | 2020-11-03 | 2020-11-23 | 13 | 0 | 13 | [20 empty] | 2020-11-25 | 2020-10-29 15:51 |  | Yes | EXP |  | 2021-04-17 | 2021-09-01 | 136 | 3 | 133 |  |  | 2021-09-08 | Connected |  | No
National Grid | CLINTON | 320293 | 1510 | 7.6 | Solar | 01_216W3 | 2020-10-29 15:51 | 2020-10-30 | 1 | 0 | 1 | 2020-11-03 | 2020-11-23 | 13 | 0 | 13 | [20 empty] | 2020-11-25 |  | 2021-10-29 | Yes | EXP |  | 2021-05-06 | 2021-05-07 | 1 | 0 | 1 |  |  | 2021-09-03 | Connected |  | No
National Grid | QUINCY | 321557 | 2169 | 21.46 | Solar | 07_1W9 | 2020-10-30 15:10 | 2020-11-02 | 12 | 9 | 3 | 2020-11-20 | 2020-12-21 | 20 | 0 | 20 | [20 empty] | 2021-01-07 |  | 2022-01-14 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEOMINSTER | 322879 | 1453 | 43.2 | Solar | 01_219W3 | 2020-11-02 09:24 | 2020-11-03 | 7 | 0 | 7 | 2020-11-16 | 2020-12-14 | 19 | 0 | 19 | [20 empty] | 2020-12-21 | 2020-11-02 11:10 | 2022-04-06 |  | EXP | [8 empty] | 2021-09-16 | Connected |  | No
National Grid | BLACKSTONE | 316764 | 1504 | 10 | Solar | 05_108W60 | 2020-11-02 11:10 | 2020-11-03 | 1 | 0 | 1 | 2020-11-05 | 2020-12-09 | 17 | 0 | 17 | [20 empty] | 2020-12-14 | 2020-11-02 14:05 |  | Yes | EXP |  | 2021-02-09 | 2021-05-18 | 98 | 0 | 98 |  |  | 2021-06-02 | Connected |  | No
National Grid | MILFORD | 319815 | 1757 | 9.8 | Solar | 05_335W5 | 2020-11-02 14:05 | 2020-11-03 | 1 | 0 | 1 | 2020-11-05 | 2020-12-09 | 17 | 0 | 17 | [20 empty] | 2020-12-14 |  | 2022-01-07 | Yes | EXP |  | 2021-03-23 | 2021-09-24 | 184 | 3 | 181 |  |  | 2022-01-03 | Connected |  | Yes
National Grid | RANDOLPH | 316225 | 2368 | 7.6 | Solar | 07_97W5 | 2020-11-02 14:25 | 2020-11-03 | 4 | 0 | 4 | 2020-11-10 | 2020-12-01 | 13 | 0 | 13 | [20 empty] | 2020-12-03 | 2020-11-02 14:31 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LYNN | 313176 | 1905 | 7.6 | Solar | 12_29W1 | 2020-11-02 14:31 | 2020-11-03 | 0 | 0 | 0 | 2020-11-04 | 2020-11-23 | 12 | 0 | 12 | [20 empty] | 2020-12-03 | 2020-11-02 14:42 | 2021-11-02 | Yes | EXP |  | 2021-03-25 | 2021-08-16 | 144 | 0 | 144 |  |  | 2021-09-07 | Connected |  | No
National Grid | STOUGHTON | 318701 | 2072 | 7.6 | Solar | 07_913W18 | 2020-11-02 14:42 | 2020-11-03 | 1 | 0 | 1 | 2020-11-05 | 2020-12-09 | 17 | 0 | 17 | [20 empty] | 2020-12-14 | 2020-11-02 17:01 |  | Yes | EXP |  | 2021-03-17 | 2021-04-06 | 20 | 0 | 20 |  |  | 2021-08-15 | Connected |  | No
National Grid | WORCESTER | 318228 | 1603 | 10 | Solar | 01_6W2 | 2020-11-02 17:01 | 2020-11-03 | 7 | 6 | 1 | 2020-11-16 | 2020-12-21 | 19 | 0 | 19 | [20 empty] | 2020-12-21 |  | 2022-10-14 | Yes | EXP |  | 2021-07-02 | 2021-10-13 | 104 | 3 | 101 |  |  | 2022-01-10 | Connected |  | No
National Grid | FRANKLIN | 322917 | 2038 | 10 | Solar | 05_348W7 | 2020-11-03 10:47 | 2020-11-04 | 1 | 0 | 1 | 2020-11-06 | 2020-11-23 | 10 | 0 | 10 | [20 empty] | 2020-12-03 |  | 2021-11-04 |  | EXP | [8 empty] | 2021-06-08 | Connected |  | No
National Grid | WEYMOUTH | 316632 | 2188 | 3.8 | Solar | 07_6W1 | 2020-11-03 13:32 | 2020-11-04 | 3 | 0 | 3 | 2020-11-10 | 2020-12-02 | 14 | 0 | 14 | [20 empty] | 2020-12-02 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 320644 | 1843 | 3.8 | Solar | 14_61L3 | 2020-11-03 14:56 | 2020-11-04 | 1 | 0 | 1 | 2020-11-06 | 2020-12-09 | 16 | 0 | 16 | [20 empty] | 2020-12-14 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 323572 | 1602 | 7.92 | Solar | 01_2J345 | 2020-11-03 15:29 | 2020-11-04 | 21 | 19 | 2 | 2020-12-08 | 2021-01-05 | 18 | 0 | 18 | [20 empty] | 2021-01-05 |  | 2021-12-06 |  | EXP | [8 empty] | 2021-04-15 | Connected |  | No
National Grid | EASTON | 320150 | 2375 | 8.64 | Solar | 07_92W44 | 2020-11-03 15:33 | 2020-11-04 | 10 | 9 | 1 | 2020-11-20 | 2020-12-11 | 14 | 0 | 14 | [20 empty] | 2020-12-21 | 2020-11-03 16:03 | 2021-11-19 |  | EXP | [8 empty] | 2021-02-12 | Connected |  | No
National Grid | BROCKTON | 315789 | 2301 | 9.8 | Solar | 07_91W43 | 2020-11-03 16:03 | 2020-11-04 | 1 | 0 | 1 | 2020-11-06 | 2020-12-09 | 16 | 0 | 16 | [20 empty] | 2020-12-14 | 2020-11-03 17:09 | 2023-03-08 | Yes | EXP |  | 2021-07-24 | 2021-07-26 | 3 | 0 | 3 |  |  |  | Completion Documents |  | Yes
National Grid | LAWRENCE | 314998 | 1841 | 7.6 | Solar | 14_6J5 | 2020-11-03 17:09 | 2020-11-04 | 1 | 0 | 1 | 2020-11-06 | 2020-12-09 | 16 | 0 | 16 | [20 empty] | 2020-12-14 |  |  | Yes | EXP |  | 2021-04-14 | 2021-06-30 | 77 | 0 | 77 |  |  | 2021-08-10 | Connected |  | No
National Grid | DUDLEY | 320511 | 1571 | 9.8 | Solar | 01_412L4 | 2020-11-04 15:43 | 2020-11-05 | 2 | 0 | 2 | 2020-11-10 | 2020-12-02 | 14 | 0 | 14 | [20 empty] | 2020-12-07 |  | 2022-01-24 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 321316 | 1844 | 7.6 | Solar | 14_74L1 | 2020-11-04 15:59 | 2020-11-05 | 2 | 0 | 2 | 2020-11-10 | 2020-12-02 | 14 | 0 | 14 | [20 empty] | 2020-12-07 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GRANBY | 323927 | 1033 | 7.6 | Solar | 09_527L1 | 2020-11-05 09:55 | 2020-11-06 | 12 | 10 | 2 | 2020-11-25 | 2020-12-21 | 18 | 1 | 17 | [20 empty] | 2020-12-22 |  | 2021-11-08 |  | EXP | [8 empty] | 2021-02-04 | Connected |  | No
National Grid | HARDWICK | 316407 | 1037 | 7998 | Other | 09_604W3 | 2020-11-05 10:03 | 2020-11-06 | 23 | 20 | 3 | [10 empty] | 2020-12-11 | 2021-01-10 | 18 | 0 | 18 | [11 empty] | 2020-11-05 10:51 |  |  | STD | [9 empty] | Group Study |  | No
National Grid | LANCASTER | 315362 | 1523 | 7998 | Other | 01_227W1 | 2020-11-05 10:51 | 2020-11-06 | 3 | 0 | 3 | [10 empty] | 2020-11-13 | 2020-11-30 | 11 | 1 | 10 | [12 empty] | 2025-08-24 | Yes | STD | [9 empty] | Pending Withdraw |  | No
National Grid | WINCHENDON | 315366 | 1475 | 9992 | Other | 01_612W2 | 2020-11-05 11:18 | 2020-11-06 | 3 | 0 | 3 | [10 empty] | 2020-11-13 | 2020-11-30 | 11 | 1 | 10 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | WINCHENDON | 318681 | 1475 | 9992 | Other | 01_612W1 | 2020-11-05 12:45 | 2020-11-06 | 23 | 16 | 7 | [10 empty] | 2020-12-11 | 2020-12-10 | 0 | 0 | 0 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | MENDON | 315404 | 1756 | 9992 | Other | 05_321W6 | 2020-11-05 13:11 | 2020-11-06 | 4 | 0 | 4 | [10 empty] | 2020-11-16 | 2020-12-07 | 14 | 0 | 14 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BRIDGEWATER | 322658 | 2324 | 133.2 | Solar | 07_912W73 | 2020-11-05 19:24 | 2020-11-06 | 4 | 0 | 4 | 2020-11-16 | 2021-01-06 | 35 | 15 | 20 | [20 empty] | 2021-01-14 | 2020-11-06 13:49 |  |  | EXP | [8 empty] | 2023-01-03 | Connected |  | No
National Grid | SOUTHBRIDGE | 324361 | 1550 | 17.6 | Solar | 01_413L3 | 2020-11-06 13:49 | 2020-11-09 | 28 | 27 | 1 | 2020-12-21 | 2021-01-15 | 17 | 0 | 17 | [20 empty] | 2021-01-15 |  | 2021-12-17 | Yes | EXP |  | 2021-05-20 | 2021-06-25 | 36 | 0 | 36 |  |  | 2021-06-29 | Connected |  | No
National Grid | GILBERTVILLE | 318585 | 1031 | 4950 | Other | 09_501L2 | 2020-11-06 14:25 | 2020-11-09 | 24 | 17 | 7 | [26 empty] | 2020-11-06 14:31 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | ATTLEBORO | 319753 | 2703 | 2.4 | Solar | 05_9L1 | 2020-11-06 14:31 | 2020-11-09 | 2 | 0 | 2 | 2020-11-13 | 2020-12-09 | 17 | 0 | 17 | [20 empty] | 2020-12-21 | 2020-11-06 14:42 | 2022-05-07 | Yes | EXP |  | 2021-09-17 | 2021-10-15 | 29 | 0 | 29 |  |  | 2022-05-06 | Connected |  | No
National Grid | SEEKONK | 321328 | 2771 | 7.6 | Solar | 05_7L4 | 2020-11-06 14:42 | 2020-11-09 | 2 | 0 | 2 | 2020-11-13 | 2020-12-09 | 17 | 0 | 17 | [20 empty] | 2020-12-21 |  | 2022-12-22 | Yes | EXP |  | 2022-03-03 | 2022-03-22 | 20 | 0 | 20 |  |  | 2022-05-31 | Connected |  | Yes
National Grid | GARDNER | 320803 | 1440 | 3.8 | Solar | 01_607W5 | 2020-11-06 15:58 | 2020-11-09 | 2 | 0 | 2 | 2020-11-13 | 2020-12-09 | 17 | 0 | 17 | [20 empty] | 2020-12-21 | 2020-11-06 18:59 | 2022-05-26 |  | EXP | [8 empty] | 2021-12-13 | Connected |  | Yes
National Grid | WEST NEWBURY | 320289 | 1985 | 9.8 | Solar | 14_47L1 | 2020-11-06 18:59 | 2020-11-09 | 2 | 0 | 2 | 2020-11-13 | 2020-12-09 | 17 | 0 | 17 | [20 empty] | 2020-12-21 |  | 2022-02-23 | Yes | EXP |  | 2021-05-26 | 2021-06-30 | 35 | 0 | 35 |  |  | 2021-09-24 | Connected |  | No
National Grid | SUTTON | 324458 | 1590 | 17.6 | Solar | 01_304W5 | 2020-11-07 13:34 | 2020-11-09 | 1 | 0 | 1 | 2020-11-12 | 2020-12-01 | 12 | 0 | 12 | [20 empty] | 2020-12-04 |  | 2022-02-25 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SOUTHBOROUGH | 324464 | 1772 | 16 | Solar | 05_317W3 | 2020-11-07 19:29 | 2020-11-09 | 1 | 0 | 1 | 2020-11-12 | 2020-12-02 | 13 | 0 | 13 | [20 empty] | 2020-12-04 |  | 2021-11-10 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SWANSEA | 320884 | 2777 | 10.56 | Solar | 05_11W83 | 2020-11-09 08:27 | 2020-11-10 | 1 | 0 | 1 | 2020-11-13 | 2020-12-09 | 17 | 0 | 17 | [20 empty] | 2020-12-21 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LOWELL | 324108 | 1851 | 10 | Solar | 14_2L2 | 2020-11-09 11:31 | 2020-11-10 | 17 | 14 | 3 | 2020-12-08 | 2021-01-06 | 19 | 0 | 19 | [20 empty] | 2021-01-06 |  | 2022-01-21 |  | EXP | [8 empty] | 2021-11-23 | Connected |  | No
National Grid | NEWBURY | 324647 | 1951 | 15.2 | Solar | 14_36L2 | 2020-11-09 13:00 | 2020-11-10 | 1 | 0 | 1 | 2020-11-13 | 2020-12-07 | 15 | 0 | 15 | [20 empty] | 2020-12-14 | 2020-11-09 17:28 |  |  | EXP | [8 empty] | 2021-01-29 | Connected |  | No
National Grid | LAWRENCE | 321550 | 1843 | 3.6 | Solar | 14_61L3 | 2020-11-09 17:28 | 2020-11-10 | 1 | 0 | 1 | 2020-11-13 | 2020-12-07 | 15 | 0 | 15 | [20 empty] | 2020-12-14 | 2020-11-10 09:17 | 2021-12-21 | Yes | EXP |  | 2021-08-06 | 2021-10-11 | 60 | 3 | 57 |  |  | 2021-10-21 | Connected |  | No
National Grid | MALDEN | 310897 | 2148 | 10 | Solar | 12_16W6 | 2020-11-10 09:17 | 2020-11-12 | 3 | 0 | 3 | 2020-11-18 | 2020-12-09 | 14 | 0 | 14 | [20 empty] | 2020-12-14 |  | 2022-01-04 | Yes | EXP | [8 empty] | 2021-10-15 | Connected |  | No
National Grid | FRANKLIN | 324729 | 2038 | 15.36 | Solar | 05_348W5 | 2020-11-10 11:42 | 2020-11-12 | 6 | 3 | 3 | 2020-11-20 | 2020-12-15 | 16 | 2 | 14 | [20 empty] | 2020-12-21 |  | 2021-11-19 |  | EXP | [8 empty] | 2021-03-20 | Connected |  | No
National Grid | NANTUCKET | 324332 | 2554 | 19 | Solar | 04_101L7 | 2020-11-10 11:54 | 2020-11-12 | 3 | 0 | 3 | 2020-11-18 | 2020-12-10 | 15 | 0 | 15 | [20 empty] | 2021-01-05 |  |  |  | EXP | [8 empty] | 2021-04-26 | Connected |  | No
National Grid | MARLBOROUGH | 324974 | 1752 | 115.2 | Solar | 05_311W5 | 2020-11-10 14:59 | 2020-11-12 | 14 | 9 | 5 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WRENTHAM | 319784 | 2093 | 15 | Solar | 05_3422W2 | 2020-11-10 17:47 | 2020-11-12 | 4 | 2 | 2 | 2020-11-18 | 2020-12-09 | 14 | 0 | 14 | [20 empty] | 2020-12-10 | 2020-11-11 08:02 | 2021-11-10 |  | EXP | [8 empty] | 2021-04-16 | Connected |  | No
National Grid | TYNGSBORO | 316773 | 1879 | 7.6 | Solar | 14_211L1 | 2020-11-11 08:02 | 2020-11-12 | 3 | 0 | 3 | 2020-11-18 | 2020-12-09 | 14 | 0 | 14 | [20 empty] | 2020-12-14 |  | 2022-03-13 | Yes | EXP |  | 2021-05-19 | 2021-11-08 | 174 | 7 | 167 |  |  | 2022-01-11 | Connected |  | No
National Grid | MONSON | 325183 | 1057 | 7.6 | Solar | 09_503L2 | 2020-11-11 10:17 | 2020-11-12 | 3 | 0 | 3 | 2020-11-18 | 2020-12-10 | 15 | 0 | 15 | [20 empty] | 2020-12-10 | 2020-11-11 18:09 | 2021-11-11 |  | EXP | [8 empty] | 2021-04-27 | Connected |  | No
National Grid | BROCKTON | 319559 | 2302 | 7.6 | Solar | 07_911W56 | 2020-11-11 18:09 | 2020-11-12 | 3 | 0 | 3 | 2020-11-18 | 2020-12-22 | 17 | 0 | 17 | [20 empty] | 2020-12-22 |  |  | Yes | EXP |  | 2021-02-16 | 2021-03-12 | 24 | 0 | 24 |  |  | 2021-05-06 | Connected |  | No
National Grid | SHEFFIELD | 321529 | 1257 | 17.98 | Solar | 09_1109W1 | 2020-11-12 08:50 | 2020-11-13 | 3 | 1 | 2 | 2020-11-19 | 2020-12-21 | 22 | 2 | 20 | [20 empty] | 2021-01-07 | 2020-11-12 09:56 |  |  | EXP | [8 empty] | 2021-03-13 | Connected |  | No
National Grid | MONSON | 322211 | 1057 | 9.8 | Solar | 09_507L1 | 2020-11-12 09:56 | 2020-11-13 | 2 | 0 | 2 | 2020-11-18 | 2020-12-10 | 15 | 0 | 15 | [20 empty] | 2020-12-18 | 2020-11-12 10:39 |  | Yes | EXP | [8 empty] | 2021-07-26 | Connected |  | No
National Grid | BRADFORD | 322749 | 1835 | 7.6 | Solar | 14_43L3 | 2020-11-12 10:39 | 2020-11-13 | 2 | 0 | 2 | 2020-11-18 | 2020-12-10 | 15 | 0 | 15 | [20 empty] | 2020-12-18 | 2020-11-12 11:06 |  | Yes | EXP |  | 2021-04-14 | 2021-04-26 | 12 | 0 | 12 |  |  | 2021-06-29 | Connected |  | No
National Grid | NORTH GRAFTON | 322909 | 1536 | 3.8 | Solar | 01_304W4 | 2020-11-12 11:06 | 2020-11-13 | 5 | 2 | 3 | 2020-11-23 | 2020-12-16 | 16 | 0 | 16 | [20 empty] | 2020-12-21 | 2020-11-12 12:01 | 2021-11-19 | Yes | EXP | [8 empty] | 2021-08-11 | Connected |  | No
National Grid | METHUEN | 319285 | 1844 | 8.12 | Solar | 14_53J4 | 2020-11-12 12:01 | 2020-11-13 | 2 | 0 | 2 | 2020-11-18 | 2020-12-09 | 15 | 1 | 14 | [20 empty] | 2020-12-13 |  | 2021-11-12 | Yes | EXP |  | 2021-04-14 | 2021-05-20 | 36 | 0 | 36 |  |  | 2021-05-21 | Connected |  | No
National Grid | LYNN | 324111 | 1902 | 66.6 | Solar | 12_22W2 | 2020-11-12 15:45 | 2020-11-13 | 16 | 12 | 4 | 2020-12-09 | 2021-01-20 | 28 | 0 | 28 | [20 empty] | 2021-02-19 |  | 2023-10-03 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | ATTLEBORO | 324117 | 2703 | 133.2 | Solar | 05_9L1 | 2020-11-12 15:49 | 2020-11-13 | 16 | 12 | 4 | 2020-12-09 | 2021-01-08 | 20 | 0 | 20 | [20 empty] | 2021-01-13 |  | 2022-11-19 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | GLOUCESTER | 325646 | 1930 | 10 | Solar | 12_24J11 | 2020-11-12 19:06 | 2020-11-13 | 49 | 47 | 2 | 2021-01-28 | 2021-02-24 | 18 | 0 | 18 | [20 empty] | 2021-02-24 |  | 2022-01-27 |  | EXP | [8 empty] | 2021-04-14 | Connected |  | No
National Grid | WEBSTER | 325654 | 1570 | 10 | Solar | 01_412L2 | 2020-11-12 19:59 | 2020-11-13 | 50 | 48 | 2 | 2021-01-26 | 2021-02-16 | 14 | 0 | 14 | [20 empty] | 2021-02-17 | 2020-11-13 12:14 | 2022-01-24 |  | EXP | [8 empty] | 2021-04-08 | Connected |  | No
National Grid | BEVERLY | 322713 | 1915 | 14.805 | Solar | 12_51L1 | 2020-11-13 12:14 | 2020-11-16 | 1 | 0 | 1 | 2020-11-18 | 2020-12-21 | 17 | 0 | 17 | [20 empty] | 2020-12-22 |  |  | Yes | EXP | [8 empty] | 2021-08-21 | Connected |  | No
National Grid | REHOBOTH | 325845 | 2769 | 15.2 | Solar | 05_7L4 | 2020-11-13 13:36 | 2020-11-16 | 2 | 0 | 2 | 2020-11-19 | 2020-12-11 | 15 | 0 | 15 | [20 empty] | 2020-12-21 | 2020-11-13 14:43 | 2021-11-15 |  | EXP | [8 empty] | 2021-04-05 | Connected |  | No
National Grid | FLORENCE | 325868 | 1062 | 15.2 | Solar | 09_909W4 | 2020-11-13 14:43 | 2020-11-16 | 1 | 0 | 1 | 2020-11-18 | 2020-12-21 | 17 | 0 | 17 | [20 empty] | 2020-12-21 |  | 2022-12-12 | Yes | EXP |  | 2021-03-06 | 2021-04-06 | 31 | 0 | 31 |  |  | 2022-03-08 | Connected |  | No
National Grid | BLACKSTONE | 325072 | 1504 | 17.6 | Solar | 05_108W60 | 2020-11-13 17:44 | 2020-11-16 | 20 | 17 | 3 | 2020-12-16 | 2021-03-24 | 67 | 46 | 21 | [20 empty] | 2021-03-25 | 2020-11-16 14:19 | 2022-04-05 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | ROCKLAND | 317863 | 2370 | 162.5 | Solar | 07_96W40 | 2020-11-16 14:19 | 2020-11-17 | 11 | 6 | 5 | 2020-12-03 | 2020-12-31 | 19 | 0 | 19 | [20 empty] | 2021-03-29 |  | 2022-09-05 |  | EXP |  | 2021-10-23 | 2022-01-25 | 95 | 0 | 95 |  |  | 2022-07-27 | Connected |  | No
National Grid | NORTH EASTON | 324369 | 2356 | 17.6 | Solar | 07_92W78 | 2020-11-16 15:03 | 2020-11-17 | 1 | 0 | 1 | 2020-11-19 | 2021-01-04 | 29 | 10 | 19 | [20 empty] | 2021-01-04 |  | 2022-06-05 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | ANDOVER | 326283 | 1810 | 11.4 | Solar | 14_54L3 | 2020-11-16 17:42 | 2020-11-17 | 1 | 0 | 1 | 2020-11-19 | 2020-12-11 | 15 | 0 | 15 | [20 empty] | 2020-12-21 |  | 2022-02-19 |  | EXP | [8 empty] | 2021-09-14 | Connected |  | No
National Grid | BRIDGEWATER | 322230 | 2324 | 500 | Solar | 07_912W73 | 2020-11-17 09:45 | 2020-11-18 | 277 | 269 | 8 | [29 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | HUBBARDSTON | 326400 | 1452 | 84 | Solar | 01_602W2 | 2020-11-17 10:08 | 2020-11-18 | 62 | 54 | 8 | [10 empty] | 2021-02-19 | 2021-02-23 | 2 | 0 | 2 | [14 empty] | STD | [9 empty] | Group Study |  | Yes
National Grid | WEYMOUTH | 319549 | 2190 | 7.6 | Solar | 07_99W32 | 2020-11-17 11:49 | 2020-11-18 | 3 | 0 | 3 | 2020-11-24 | 2020-12-17 | 16 | 0 | 16 | [20 empty] | 2020-12-21 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ANDOVER | 326510 | 1810 | 10 | Solar | 14_50L1 | 2020-11-17 14:41 | 2020-11-18 | 10 | 8 | 2 | 2020-12-04 | 2021-01-04 | 19 | 0 | 19 | [20 empty] | 2021-01-07 | 2020-11-17 16:35 |  |  | EXP | [8 empty] | 2021-08-18 | Connected |  | No
National Grid | NORTHBOROUGH | 326590 | 1532 | 11.4 | Solar | 05_313W4 | 2020-11-17 16:35 | 2020-11-18 | 2 | 0 | 2 | 2020-11-23 | 2020-12-21 | 19 | 0 | 19 | [20 empty] | 2020-12-22 | 2020-11-17 17:18 | 2022-09-09 | Yes | EXP |  | 2021-06-12 | 2021-08-31 | 80 | 3 | 77 |  |  | 2021-09-13 | Connected |  | No
National Grid | AYER | 326607 | 1432 | 8 | Solar | 01_201W1 | 2020-11-17 17:18 | 2020-11-18 | 2 | 0 | 2 | 2020-11-23 | 2020-12-16 | 16 | 0 | 16 | [20 empty] | 2020-12-21 |  | 2022-05-03 | Yes | EXP |  | 2021-03-12 | 2021-04-12 | 31 | 0 | 31 |  |  | 2021-09-14 | Connected |  | No
National Grid | REHOBOTH | 297893 | 2769 | 4500 | Other | 05_7L5 | 2020-11-18 00:53 | 2020-11-19 | 44 | 37 | 7 | [10 empty] | 2021-01-26 | 2021-02-23 | 20 | 0 | 20 | [10 empty] | 2022-07-28 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BEVERLY | 326457 | 1915 | 9.86 | Solar | 12_51L1 | 2020-11-18 09:45 | 2020-11-19 | 2 | 0 | 2 | 2020-11-24 | 2020-12-17 | 16 | 0 | 16 | [20 empty] | 2020-12-22 |  | 2021-11-19 |  | EXP | [8 empty] | 2021-03-19 | Connected |  | No
National Grid | ANDOVER | 326749 | 1810 | 10 | Solar | 14_54L3 | 2020-11-18 11:36 | 2020-11-19 | 2 | 0 | 2 | 2020-11-24 | 2020-12-17 | 16 | 0 | 16 | [20 empty] | 2020-12-21 |  |  |  | EXP | [8 empty] | 2021-05-21 | Connected |  | No
National Grid | WESTFORD | 326885 | 1886 | 10 | Solar | 14_57L2 | 2020-11-18 16:40 | 2020-11-19 | 2 | 0 | 2 | 2020-11-24 | 2020-12-17 | 16 | 0 | 16 | [20 empty] | 2020-12-21 | 2020-11-18 19:06 |  |  | EXP | [8 empty] | 2021-06-09 | Connected |  | No
National Grid | REHOBOTH | 326927 | 2769 | 7.6 | Solar | 05_7L4 | 2020-11-18 19:06 | 2020-11-19 | 0 | 0 | 0 | 2020-11-20 | 2020-12-16 | 17 | 0 | 17 | [20 empty] | 2020-12-17 |  | 2022-08-13 | Yes | EXP |  | 2021-04-08 | 2021-04-23 | 15 | 0 | 15 |  |  |  | Withdrawn |  | Yes
National Grid | BEVERLY | 325853 | 1915 | 33.3 | Solar | 12_12L4 | 2020-11-19 09:54 | 2020-11-20 | 10 | 8 | 2 | 2020-12-07 | 2020-12-31 | 17 | 0 | 17 | [20 empty] | 2021-01-12 |  |  |  | EXP | [8 empty] | 2021-05-27 | Connected |  | No
National Grid | LEOMINSTER | 326200 | 1453 | 11.4 | Solar | 01_207W6 | 2020-11-19 10:10 | 2020-11-20 | 4 | 2 | 2 | 2020-11-27 | 2020-12-20 | 16 | 0 | 16 | [20 empty] | 2020-12-22 |  | 2021-11-24 |  | EXP | [8 empty] | 2021-08-10 | Connected |  | No
National Grid | GRAFTON | 324435 | 1519 | 7.6 | Solar | 01_304W2 | 2020-11-19 12:55 | 2020-11-20 | 2 | 0 | 2 | 2020-11-25 | 2020-12-21 | 17 | 0 | 17 | [20 empty] | 2020-12-30 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SAUGUS | 324075 | 1906 | 1.92 | Solar | 12_23W3 | 2020-11-19 14:52 | 2020-11-20 | 2 | 0 | 2 | 2020-11-25 | 2020-12-21 | 17 | 0 | 17 | [20 empty] | 2020-12-30 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BARRE | 319065 | 1005 | 4999 | Solar | 09_604W4 | 2020-11-19 15:07 | 2020-11-20 | 18 | 12 | 6 | [10 empty] | 2020-12-18 | 2021-01-14 | 17 | 0 | 17 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | EAST LONGMEADOW | 327143 | 1028 | 11.4 | Solar | 09_139L5 | 2020-11-19 15:14 | 2020-11-20 | 5 | 1 | 4 | 2020-12-01 | 2020-12-23 | 16 | 0 | 16 | [20 empty] | 2020-12-23 | 2020-11-19 17:10 | 2022-02-07 |  | EXP | [8 empty] | 2022-01-12 | Connected |  | No
National Grid | BEVERLY | 327199 | 1915 | 10 | Solar | 12_51T1 | 2020-11-19 17:10 | 2020-11-20 | 3 | 0 | 3 | 2020-11-27 | 2020-12-22 | 17 | 0 | 17 | [20 empty] | 2020-12-22 |  | 2022-04-26 | Yes | EXP |  | 2021-04-09 | 2021-04-20 | 11 | 0 | 11 |  |  |  | Withdrawn |  | Yes
National Grid | GRANBY | 322287 | 1033 | 5 | Solar | 09_527L1 | 2020-11-19 19:10 | 2020-11-20 | 2 | 0 | 2 | 2020-11-25 | 2020-12-21 | 17 | 0 | 17 | [20 empty] | 2020-12-30 |  |  |  | EXP | [8 empty] | 2021-06-04 | Connected |  | No
National Grid | BARRE | 319066 | 1005 | 4999 | Solar | 09_604W4 | 2020-11-20 09:30 | 2020-11-23 | 26 | 20 | 6 | [10 empty] | 2021-02-08 | 2021-02-10 | 2 | 0 | 2 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 321061 | 1603 | 75 | Natural Gas | 01_HT41 | 2020-11-20 14:04 | 2020-11-23 | 9 | 0 | 9 | [10 empty] | 2020-12-08 | 2021-01-20 | 29 | 4 | 25 | [10 empty] | 2022-01-04 |  | 2023-04-27 |  | STD | [8 empty] | 2023-04-04 | Connected |  | No
National Grid | WORCESTER | 321058 | 1610 | 75 | Natural Gas | 01_4J324 | 2020-11-20 14:06 | 2020-11-23 | 9 | 0 | 9 | [10 empty] | 2020-12-08 | 2021-01-20 | 29 | 4 | 25 | [10 empty] | 2022-01-04 |  | 2023-04-27 |  | STD | [8 empty] | 2023-04-04 | Connected |  | No
National Grid | WORCESTER | 320344 | 1609 | 75 | Natural Gas | 01_HT20 | 2020-11-20 14:07 | 2020-11-23 | 9 | 0 | 9 | [10 empty] | 2020-12-08 | 2021-01-20 | 29 | 0 | 29 | [10 empty] | 2022-01-04 |  | 2023-04-27 |  | STD | [8 empty] | 2023-04-04 | Connected |  | No
National Grid | BELCHERTOWN | 326990 | 1007 | 17 | Solar | 09_523L2 | 2020-11-20 15:50 | 2020-11-23 | 10 | 8 | 2 | 2020-12-09 | 2021-01-06 | 18 | 0 | 18 | [20 empty] | 2021-01-06 |  | 2021-12-06 |  | EXP | [8 empty] | 2021-02-22 | Connected |  | No
National Grid | STOUGHTON | 327515 | 2072 | 7.68 | Solar | 07_913W67 | 2020-11-20 18:42 | 2020-11-23 | 15 | 12 | 3 | 2020-12-16 | 2021-01-07 | 14 | 0 | 14 | [20 empty] | 2021-01-08 | 2020-11-22 13:31 | 2021-12-10 |  | EXP | [8 empty] | 2021-05-13 | Connected |  | No
National Grid | RANDOLPH | 319113 | 2368 | 5 | Solar | 07_97W2 | 2020-11-22 13:31 | 2020-11-23 | 1 | 0 | 1 | 2020-11-25 | 2020-12-21 | 17 | 0 | 17 | [20 empty] | 2020-12-30 | 2020-11-23 16:32 |  | Yes | EXP |  | 2021-04-27 | 2021-05-21 | 24 | 0 | 24 |  |  | 2021-06-22 | Connected |  | No
National Grid | AUBURN | 320744 | 1501 | 10 | Solar | 01_406L2 | 2020-11-23 16:32 | 2020-11-24 | 1 | 0 | 1 | 2020-11-27 | 2020-12-21 | 16 | 0 | 16 | [20 empty] | 2020-12-30 | 2020-11-23 16:33 | 2022-10-10 | Yes | EXP |  | 2022-01-18 | 2022-03-04 | 46 | 0 | 46 |  |  | 2022-03-30 | Connected |  | Yes
National Grid | MALDEN | 323866 | 2148 | 6 | Solar | 12_16W5 | 2020-11-23 16:33 | 2020-11-24 | 1 | 0 | 1 | 2020-11-27 | 2020-12-31 | 23 | 0 | 23 | [20 empty] | 2021-01-11 |  | 2022-06-16 | Yes | EXP |  | 2021-10-15 | 2021-12-07 | 54 | 4 | 50 |  |  | 2021-12-13 | Connected |  | Yes
National Grid | GREAT BARRINGTON | 327873 | 1230 | 7.6 | Solar | 09_1109W3 | 2020-11-23 16:34 | 2020-11-24 | 10 | 9 | 1 | 2020-12-10 | 2021-01-07 | 18 | 0 | 18 | [20 empty] | 2021-01-07 | 2020-11-23 16:41 | 2021-12-09 |  | EXP | [8 empty] | 2021-04-27 | Connected |  | No
National Grid | MELROSE | 327874 | 2176 | 7.6 | Solar | 12_25W2 | 2020-11-23 16:41 | 2020-11-24 | 1 | 0 | 1 | 2020-11-27 | 2020-12-31 | 23 | 0 | 23 | [20 empty] | 2021-01-08 |  | 2022-09-10 | Yes | EXP |  | 2021-04-22 | 2021-08-10 | 110 | 0 | 110 |  |  | 2021-09-24 | Connected |  | No
National Grid | HOLBROOK | 318700 | 2343 | 6 | Solar | 07_97W3 | 2020-11-23 19:47 | 2020-11-24 | 11 | 9 | 2 | 2020-12-11 | 2021-01-07 | 17 | 0 | 17 | [20 empty] | 2021-01-08 |  | 2021-12-10 |  | EXP | [8 empty] | 2021-03-05 | Connected |  | No
National Grid | NORTH ANDOVER | 327991 | 1845 | 7.6 | Solar | 14_56L2 | 2020-11-24 09:57 | 2020-11-25 | 4 | 0 | 4 | 2020-12-03 | 2021-01-04 | 20 | 0 | 20 | [20 empty] | 2021-01-04 |  | 2021-11-26 |  | EXP | [8 empty] | 2021-04-01 | Connected |  | No
National Grid | QUINCY | 328052 | 2169 | 13.8 | Solar | 07_1W4 | 2020-11-24 12:27 | 2020-11-25 | 2 | 0 | 2 | 2020-12-01 | 2020-12-31 | 21 | 0 | 21 | [20 empty] | 2021-01-12 |  |  |  | EXP | [8 empty] | 2021-07-02 | Connected |  | No
National Grid | WRENTHAM | 328096 | 2093 | 7.6 | Solar | 05_348W1 | 2020-11-24 13:36 | 2020-11-25 | 13 | 9 | 4 | 2020-12-15 | 2021-01-07 | 15 | 0 | 15 | [20 empty] | 2021-01-08 | 2020-11-24 14:05 | 2022-03-02 |  | EXP | [8 empty] | 2021-10-08 | Connected |  | No
National Grid | RANDOLPH | 323027 | 2368 | 9.8 | Solar | 07_97W1 | 2020-11-24 14:05 | 2020-11-25 | 2 | 0 | 2 | 2020-12-01 | 2020-12-23 | 16 | 0 | 16 | [20 empty] | 2020-12-30 |  | 2022-11-23 | Yes | EXP |  | 2021-08-18 | 2021-10-12 | 54 | 3 | 51 |  |  | 2021-12-22 | Connected |  | No
National Grid | MEDFORD | 322458 | 2155 | 7.6 | Solar | 12_17J3 | 2020-11-24 14:29 | 2020-11-25 | 2 | 0 | 2 | 2020-12-01 | 2020-12-31 | 21 | 0 | 21 | [20 empty] | 2021-01-11 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 323842 | 1844 | 9.8 | Solar | 14_74L1 | 2020-11-24 15:34 | 2020-11-25 | 2 | 0 | 2 | 2020-12-01 | 2020-12-31 | 21 | 0 | 21 | [20 empty] | 2021-01-12 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOUTH GRAFTON | 328163 | 1560 | 7.6 | Solar | 05_320W3 | 2020-11-24 15:56 | 2020-11-25 | 4 | 0 | 4 | 2020-12-03 | 2021-01-20 | 32 | 15 | 17 | [20 empty] | 2021-03-09 |  | 2022-05-27 |  | EXP | [8 empty] | 2022-04-22 | Connected |  | No
National Grid | MARLBOROUGH | 328171 | 1752 | 15.2 | Solar | 05_311W2 | 2020-11-24 16:37 | 2020-11-25 | 2 | 0 | 2 | 2020-12-01 | 2020-12-23 | 16 | 0 | 16 | [20 empty] | 2020-12-30 |  | 2022-08-03 |  | EXP | [8 empty] | 2022-02-04 | Connected |  | No
National Grid | SOMERSET | 324590 | 2726 | 7.6 | Solar | 05_18J5 | 2020-11-25 08:25 | 2020-11-27 | 1 | 0 | 1 | 2020-12-01 | 2020-12-31 | 21 | 0 | 21 | [20 empty] | 2021-01-12 | 2020-11-25 08:30 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 324110 | 2302 | 7.6 | Solar | 07_712J1 | 2020-11-25 08:30 | 2020-11-27 | 3 | 0 | 3 | 2020-12-03 | 2020-12-31 | 19 | 0 | 19 | [20 empty] | 2021-01-11 |  | 2022-01-25 | Yes | EXP |  | 2021-08-12 | 2021-09-22 | 36 | 3 | 33 |  |  | 2021-10-06 | Connected |  | No
National Grid | MELROSE | 327303 | 2176 | 43.2 | Solar | 12_67J3 | 2020-11-25 09:01 | 2020-11-27 | 3 | 0 | 3 | 2020-12-03 | 2020-12-31 | 19 | 0 | 19 | [20 empty] | 2021-01-12 |  | 2022-03-25 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WRENTHAM | 328332 | 2093 | 15.2 | Solar | 05_348W1 | 2020-11-25 11:31 | 2020-11-27 | 3 | 0 | 3 | 2020-12-03 | 2021-01-05 | 21 | 0 | 21 | [20 empty] | 2021-01-12 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 322315 | 1605 | 10 | Solar | 01_24W2 | 2020-11-25 14:03 | 2020-11-27 | 3 | 0 | 3 | 2020-12-03 | 2021-01-04 | 20 | 0 | 20 | [20 empty] | 2021-01-07 | 2020-11-25 15:21 |  |  | EXP | [8 empty] | 2021-05-04 | Connected |  | No
National Grid | MALDEN | 326220 | 2148 | 7.6 | Solar | 12_16W5 | 2020-11-25 15:21 | 2020-11-27 | 2 | 0 | 2 | 2020-12-02 | 2020-12-31 | 20 | 0 | 20 | [20 empty] | 2021-01-12 |  | 2022-09-13 | Yes | EXP | [8 empty] | 2021-09-15 | Connected |  | No
National Grid | DUNCAN | 328441 | 1752 | 10 | Solar | 05_311W3 | 2020-11-25 17:30 | 2020-11-27 | 3 | 0 | 3 | 2020-12-03 | 2021-01-05 | 21 | 0 | 21 | [20 empty] | 2021-01-05 |  | 2021-11-29 |  | EXP | [8 empty] | 2021-03-05 | Connected |  | No
National Grid | ANDOVER | 328453 | 1810 | 17.6 | Solar | 14_62L2 | 2020-11-25 19:10 | 2020-11-27 | 39 | 38 | 1 | 2021-01-27 | 2021-02-17 | 14 | 0 | 14 | [20 empty] | 2021-02-18 |  | 2022-06-23 |  | EXP | [8 empty] | 2022-04-28 | Connected |  | No
National Grid | WORCESTER | 324658 | 1603 | 3.8 | Solar | 01_6W2 | 2020-11-27 09:59 | 2020-11-30 | 2 | 0 | 2 | 2020-12-03 | 2021-02-03 | 41 | 18 | 23 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTBOROUGH | 328513 | 1581 | 17.2 | Solar | 05_312W1 | 2020-11-27 13:18 | 2020-11-30 | 3 | 0 | 3 | 2020-12-04 | 2021-01-04 | 19 | 0 | 19 | [20 empty] | 2021-01-04 |  | 2022-08-26 |  | EXP | [8 empty] | 2022-07-19 | Connected |  | No
National Grid | ROYALSTON | 318176 | 1368 | 5000 | Solar | 09_701J1 | 2020-11-30 08:28 | 2020-12-01 | 23 | 21 | 2 | [10 empty] | 2021-01-06 | 2021-01-26 | 12 | 0 | 12 | [11 empty] | 2020-11-30 10:14 |  |  | STD | [9 empty] | Group Study |  | No
National Grid | METHUEN | 320041 | 1844 | 9.8 | Solar | 14_5J42 | 2020-11-30 10:14 | 2020-12-01 | 2 | 0 | 2 | 2020-12-04 | 2021-01-05 | 20 | 0 | 20 | [20 empty] | 2021-01-11 | 2020-11-30 12:10 | 2022-09-03 | Yes | EXP |  | 2021-08-19 | 2021-10-12 | 40 | 3 | 37 |  |  | 2022-06-02 | Connected |  | No
National Grid | HOPEDALE | 324127 | 1747 | 10 | Solar | 05_335W4 | 2020-11-30 12:10 | 2020-12-01 | 1 | 0 | 1 | 2020-12-03 | 2020-12-31 | 19 | 0 | 19 | [20 empty] | 2021-01-13 |  |  |  | EXP |  | 2021-05-14 | 2021-05-13 | 0 | 0 | 0 |  |  | 2021-07-16 | Connected |  | No
National Grid | MEDFORD | 328772 | 2155 | 7.6 | Solar | 12_17J6 | 2020-11-30 16:45 | 2020-12-01 | 5 | 0 | 5 | 2020-12-09 | 2021-01-06 | 18 | 0 | 18 | [20 empty] | 2021-01-07 |  | 2021-11-30 |  | EXP | [8 empty] | 2021-03-17 | Connected |  | No
National Grid | STOUGHTON | 322406 | 2072 | 7.6 | Solar | 07_913W69 | 2020-11-30 17:27 | 2020-12-01 | 2 | 0 | 2 | 2020-12-04 | 2021-01-05 | 20 | 0 | 20 | [20 empty] | 2021-01-07 | 2020-11-30 17:46 | 2022-06-16 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RANDOLPH | 324428 | 2368 | 7.6 | Solar | 07_97W1 | 2020-11-30 17:46 | 2020-12-01 | 2 | 0 | 2 | 2020-12-04 | 2021-01-05 | 20 | 0 | 20 | [20 empty] | 2021-01-07 |  | 2022-04-30 | Yes | EXP |  | 2021-10-07 | 2021-10-12 | 5 | 0 | 5 |  |  | 2022-03-04 | Connected |  | No
National Grid | NORTH EASTON | 328800 | 2356 | 15.2 | Solar | 07_92W78 | 2020-11-30 18:38 | 2020-12-01 | 5 | 0 | 5 | 2020-12-09 | 2021-01-06 | 18 | 0 | 18 | [20 empty] | 2021-01-07 | 2020-11-30 18:42 | 2021-11-30 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HOLBROOK | 324728 | 2343 | 7.6 | Solar | 07_2W1 | 2020-11-30 18:42 | 2020-12-01 | 2 | 0 | 2 | 2020-12-04 | 2021-01-05 | 20 | 0 | 20 | [20 empty] | 2021-01-07 |  | 2021-07-30 | Yes | EXP |  | 2021-04-27 | 2021-05-19 | 22 | 0 | 22 |  |  | 2021-07-15 | Connected |  | No
National Grid | LEOMINSTER | 325515 | 1453 | 7.6 | Solar | 01_207W6 | 2020-11-30 18:55 | 2020-12-01 | 5 | 0 | 5 | 2020-12-09 | 2021-01-07 | 19 | 0 | 19 | [20 empty] | 2021-01-08 |  | 2021-11-30 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SALEM | 328907 | 1970 | 8.64 | Solar | 12_2W1 | 2020-12-01 13:07 | 2020-12-02 | 4 | 0 | 4 | 2020-12-09 | 2021-01-06 | 18 | 0 | 18 | [20 empty] | 2021-01-07 |  | 2021-12-01 |  | EXP | [8 empty] | 2021-04-05 | Connected |  | No
National Grid | STOUGHTON | 328974 | 2072 | 7.6 | Solar | 07_913W43 | 2020-12-01 15:34 | 2020-12-02 | 1 | 0 | 1 | 2020-12-04 | 2021-01-04 | 19 | 0 | 19 | [20 empty] | 2021-01-07 |  | 2022-07-17 |  | EXP | [8 empty] | 2022-03-03 | Connected |  | No
National Grid | WARE | 328673 | 1082 | 12.49 | Solar | 09_501L1 | 2020-12-01 16:05 | 2020-12-02 | 4 | 0 | 4 | 2020-12-09 | 2021-01-06 | 18 | 0 | 18 | [20 empty] | 2021-01-07 | 2020-12-01 16:18 | 2022-01-12 |  | EXP | [8 empty] | 2021-12-20 | Connected |  | No
National Grid | WEBSTER | 312153 | 1570 | 5.76 | Solar | 01_412L1 | 2020-12-01 16:18 | 2020-12-02 | 1 | 0 | 1 | 2020-12-04 | 2021-01-25 | 33 | 13 | 20 | [20 empty] | 2021-01-27 |  |  | Yes | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HARDWICK | 327466 | 1037 | 6.24 | Solar | 09_501L2 | 2020-12-01 23:04 | 2020-12-02 | 22 | 18 | 4 | 2021-01-06 | 2021-01-25 | 12 | 0 | 12 | [20 empty] | 2021-01-26 | 2020-12-02 12:22 | 2022-01-04 |  | EXP | [8 empty] | 2021-02-08 | Connected |  | No
National Grid | ATTLEBORO | 265289 | 2703 | 600 | Natural Gas | 05_9L4 | 2020-12-02 12:22 | 2020-12-03 | 22 | 15 | 7 | [10 empty] | 2021-01-06 | 2021-02-24 | 34 | 13 | 21 | [10 empty] | 2023-08-15 |  | 2025-05-03 | Yes | STD | [9 empty] | Construction |  | No
National Grid | GLOUCESTER | 325210 | 1930 | 18 | Solar | 12_51T1 | 2020-12-02 14:19 | 2020-12-03 | 21 | 18 | 3 | 2021-01-05 | 2021-01-20 | 10 | 0 | 10 | [20 empty] | 2021-01-21 |  | 2022-03-21 |  | EXP | [8 empty] | 2021-10-26 | Connected |  | No
National Grid | EAST LONGMEADOW | 329328 | 1028 | 10 | Solar | 09_508L4 | 2020-12-02 20:08 | 2020-12-03 | 3 | 0 | 3 | 2020-12-09 | 2021-01-06 | 18 | 0 | 18 | [20 empty] | 2021-01-12 |  |  |  | EXP | [8 empty] | 2021-09-04 | Connected |  | No
National Grid | WESTBOROUGH | 326856 | 1581 | 8.4 | Solar | 05_313W2 | 2020-12-03 12:58 | 2020-12-04 | 2 | 0 | 2 | 2020-12-09 | 2021-01-06 | 18 | 0 | 18 | [20 empty] | 2021-01-06 |  | 2021-12-03 |  | EXP | [8 empty] | 2021-03-26 | Connected |  | No
National Grid | WESTFORD | 329231 | 1886 | 7.6 | Solar | 14_57L3 | 2020-12-03 15:39 | 2020-12-04 | 35 | 26 | 9 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | STOCKBRIDGE | 326152 | 1262 | 3 | Solar | 09_1102W1 | 2020-12-03 15:59 | 2020-12-04 | 2 | 0 | 2 | 2020-12-09 | 2021-01-07 | 19 | 0 | 19 | [20 empty] | 2021-01-12 |  |  |  | EXP | [8 empty] | 2021-05-18 | Connected |  | No
National Grid | BROCKTON | 321262 | 2302 | 9.8 | Solar | 07_91W43 | 2020-12-03 18:01 | 2020-12-04 | 2 | 0 | 2 | 2020-12-09 | 2021-01-06 | 18 | 0 | 18 | [20 empty] | 2021-01-12 | 2020-12-04 10:25 | 2022-03-23 |  | EXP | [8 empty] | 2022-04-12 | Connected |  | No
National Grid | COHASSET | 329626 | 2025 | 22.8 | Solar | 07_915W37 | 2020-12-04 10:25 | 2020-12-07 | 3 | 0 | 3 | 2020-12-11 | 2021-01-07 | 17 | 0 | 17 | [20 empty] | 2021-01-08 |  | 2021-12-06 | Yes | EXP |  | 2021-02-11 | 2021-03-17 | 34 | 0 | 34 |  |  | 2021-05-19 | Connected |  | No
National Grid | EAST LONGMEADOW | 329634 | 1028 | 15.2 | Solar | 09_508L4 | 2020-12-04 10:52 | 2020-12-07 | 3 | 0 | 3 | 2020-12-11 | 2021-01-07 | 16 | 0 | 16 | [20 empty] | 2021-01-08 | 2020-12-04 12:02 | 2022-03-25 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 314982 | 1841 | 9.765 | Solar | 14_63L1 | 2020-12-04 12:02 | 2020-12-07 | 0 | 0 | 0 | 2020-12-08 | 2021-01-06 | 19 | 0 | 19 | [20 empty] | 2021-01-12 |  | 2022-11-22 | Yes | EXP |  | 2021-08-06 | 2021-12-07 | 123 | 63 | 60 |  |  | 2021-12-09 | Connected |  | No
National Grid | RUTLAND | 318655 | 1543 | 9992 | Other | 01_55W1 | 2020-12-04 14:11 | 2020-12-07 | 20 | 16 | 4 | [10 empty] | 2021-01-06 | 2021-02-09 | 22 | 5 | 17 | [11 empty] | 2020-12-04 14:34 |  |  | STD | [9 empty] | Group Study |  | No
National Grid | SOUTHBRIDGE | 325163 | 1550 | 9992 | Other | 01_413L8 | 2020-12-04 14:34 | 2020-12-07 | 20 | 13 | 7 | [10 empty] | 2021-01-06 | 2021-02-08 | 23 | 3 | 20 | [12 empty] | 2025-04-09 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | PALMER | 329775 | 1069 | 15.2 | Solar | 09_503L1 | 2020-12-04 16:53 | 2020-12-07 | 1 | 0 | 1 | 2020-12-09 | 2021-01-06 | 18 | 0 | 18 | [20 empty] | 2021-01-12 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEOMINSTER | 327211 | 1453 | 7.6 | Solar | 01_225W4 | 2020-12-04 18:04 | 2020-12-07 | 3 | 0 | 3 | 2020-12-11 | 2021-01-07 | 17 | 0 | 17 | [20 empty] | 2021-01-08 |  | 2021-12-06 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MILFORD | 324890 | 1757 | 3.8 | Solar | 05_335W4 | 2020-12-04 18:09 | 2020-12-07 | 1 | 0 | 1 | 2020-12-09 | 2021-01-26 | 31 | 13 | 18 | [20 empty] | 2021-02-04 |  |  |  | EXP | [8 empty] | 2021-06-09 | Connected |  | No
National Grid | FRANKLIN | 329798 | 2038 | 15.2 | Solar | 05_344W5 | 2020-12-04 19:12 | 2020-12-07 | 1 | 0 | 1 | 2020-12-09 | 2021-01-06 | 18 | 0 | 18 | [20 empty] | 2021-01-12 |  |  |  | EXP | [8 empty] | 2021-06-25 | Connected |  | No
National Grid | DUDLEY | 329818 | 1571 | 15.2 | Solar | 01_412L5 | 2020-12-05 09:44 | 2020-12-07 | 1 | 0 | 1 | 2020-12-09 | 2021-01-06 | 18 | 0 | 18 | [20 empty] | 2021-01-12 |  | 2022-04-08 |  | EXP | [8 empty] | 2022-03-12 | Connected |  | No
National Grid | WRENTHAM | 329828 | 2093 | 15.2 | Solar | 05_3451W3 | 2020-12-05 12:10 | 2020-12-07 | 1 | 0 | 1 | 2020-12-09 | 2021-01-06 | 18 | 0 | 18 | [20 empty] | 2021-01-07 | 2020-12-07 09:40 | 2022-03-31 |  | EXP | [8 empty] | 2022-02-23 | Connected |  | Yes
National Grid | RANDOLPH | 325702 | 2368 | 7.6 | Solar | 07_97W1 | 2020-12-07 09:40 | 2020-12-08 | 4 | 0 | 4 | 2020-12-14 | 2021-01-07 | 16 | 0 | 16 | [20 empty] | 2021-01-12 |  | 2023-08-08 | Yes | EXP |  | 2022-03-31 | 2022-04-25 | 26 | 0 | 26 |  |  | 2023-04-10 | Connected |  | No
National Grid | WEYMOUTH | 329977 | 2190 | 10 | Solar | 07_99W32 | 2020-12-07 10:37 | 2020-12-08 | 2 | 0 | 2 | 2020-12-11 | 2021-01-07 | 16 | 0 | 16 | [20 empty] | 2021-01-08 |  | 2021-12-07 |  | EXP | [8 empty] | 2021-05-28 | Connected |  | No
National Grid | RANDOLPH | 330177 | 2368 | 12 | Solar | 07_97W1 | 2020-12-07 19:28 | 2020-12-08 | 82 | 79 | 3 | 2021-04-02 | 2021-04-23 | 12 | 0 | 12 | [20 empty] | 2021-04-26 |  | 2022-06-08 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BEVERLY | 330235 | 1915 | 7.6 | Solar | 12_12L2 | 2020-12-07 22:54 | 2020-12-08 | 40 | 38 | 2 | 2021-02-08 | 2021-03-02 | 15 | 0 | 15 | [20 empty] | 2021-03-02 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 304482 | 2302 | 10 | Solar | 07_911W56 | 2020-12-08 12:00 | 2020-12-09 | 3 | 0 | 3 | 2020-12-14 | 2021-01-28 | 30 | 9 | 21 | [20 empty] | 2021-02-02 |  |  |  | EXP | [8 empty] | 2021-05-08 | Connected |  | No
National Grid | WINTHROP | 330348 | 2152 | 7.6 | Solar | 12_96W1 | 2020-12-08 12:10 | 2020-12-09 | 13 | 8 | 5 | 2020-12-30 | 2021-01-19 | 12 | 0 | 12 | [20 empty] | 2021-01-20 |  | 2021-12-28 |  | EXP | [8 empty] | 2021-04-12 | Connected |  | No
National Grid | BROCKTON | 325302 | 2301 | 7.6 | Solar | 07_98W46 | 2020-12-08 16:04 | 2020-12-09 | 3 | 0 | 3 | 2020-12-14 | 2021-01-13 | 20 | 0 | 20 | [20 empty] | 2021-01-20 |  | 2022-05-23 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FRANKLIN | 330469 | 2038 | 10 | Solar | 05_344W1 | 2020-12-08 16:21 | 2020-12-09 | 5 | 0 | 5 | 2020-12-17 | 2021-01-07 | 13 | 0 | 13 | [20 empty] | 2021-01-08 | 2020-12-08 17:36 | 2021-12-09 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 327655 | 1844 | 7.6 | Solar | 14_74L2 | 2020-12-08 17:36 | 2020-12-09 | 0 | 0 | 0 | 2020-12-10 | 2021-01-07 | 18 | 0 | 18 | [20 empty] | 2021-01-07 | 2020-12-08 19:36 |  | Yes | EXP |  | 2021-05-05 | 2021-06-18 | 44 | 0 | 44 |  |  | 2021-08-24 | Connected |  | No
National Grid | WINCHENDON | 330507 | 1475 | 15.2 | Solar | 01_612W1 | 2020-12-08 19:36 | 2020-12-09 | 3 | 0 | 3 | 2020-12-14 | 2021-01-07 | 16 | 0 | 16 | [20 empty] | 2021-01-12 |  | 2023-02-08 | Yes | EXP |  | 2021-09-04 | 2021-10-21 | 48 | 0 | 48 |  |  | 2022-03-28 | Connected |  | No
National Grid | BRADFORD | 330625 | 1835 | 15.2 | Solar | 14_65L3 | 2020-12-09 12:46 | 2020-12-10 | 6 | 0 | 6 | 2020-12-21 | 2021-01-15 | 17 | 0 | 17 | [20 empty] | 2021-01-22 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EAST BRIDGEWATER | 330658 | 2333 | 10 | Solar | 07_797W23 | 2020-12-09 14:02 | 2020-12-10 | 19 | 14 | 5 | 2021-01-08 | 2021-02-02 | 16 | 0 | 16 | [20 empty] | 2021-02-04 |  | 2022-01-06 |  | EXP | [8 empty] | 2021-08-08 | Connected |  | No
National Grid | REVERE | 327499 | 2151 | 7.6 | Solar | 12_16W7 | 2020-12-09 14:21 | 2020-12-10 | 2 | 0 | 2 | 2020-12-14 | 2021-01-07 | 16 | 0 | 16 | [20 empty] | 2021-01-12 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SPENCER | 330669 | 1562 | 9.8 | Solar | 01_552L1 | 2020-12-09 14:48 | 2020-12-10 | 5 | 0 | 5 | 2020-12-18 | 2021-01-15 | 18 | 0 | 18 | [20 empty] | 2021-01-15 |  | 2022-03-02 |  | EXP | [8 empty] | 2021-10-14 | Connected |  | No
National Grid | WESTFORD | 330673 | 1886 | 15.2 | Solar | 14_57L1 | 2020-12-09 15:05 | 2020-12-10 | 6 | 0 | 6 | 2020-12-21 | 2021-01-15 | 17 | 0 | 17 | [20 empty] | 2021-01-27 |  | 2022-11-03 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SPENCER | 301406 | 1562 | 400 | Natural Gas | 01_552L3 | 2020-12-09 15:15 | 2020-12-10 | 7 | 0 | 7 | [10 empty] | 2020-12-22 | 2021-01-21 | 19 | 0 | 19 | [11 empty] | 2020-12-09 15:32 |  |  | STD | [9 empty] | Group Study |  | Yes
National Grid | BOXFORD | 327460 | 1921 | 10 | Solar | 14_43L7 | 2020-12-09 15:32 | 2020-12-10 | 5 | 3 | 2 | 2020-12-18 | 2021-01-13 | 16 | 0 | 16 | [20 empty] | 2021-01-19 |  |  |  | EXP |  | 2021-04-14 | 2021-04-26 | 12 | 0 | 12 |  |  | 2021-05-07 | Connected |  | No
National Grid | EAST BRIDGEWATER | 326952 | 2333 | 9.36 | Solar | 07_797W24 | 2020-12-09 15:39 | 2020-12-10 | 20 | 15 | 5 | 2021-01-11 | 2021-02-02 | 15 | 0 | 15 | [20 empty] | 2021-02-04 |  | 2022-01-07 |  | EXP | [8 empty] | 2021-03-18 | Connected |  | No
National Grid | FLORENCE | 330696 | 1062 | 7.6 | Solar | 09_909W4 | 2020-12-09 16:05 | 2020-12-10 | 5 | 0 | 5 | 2020-12-18 | 2021-01-15 | 18 | 0 | 18 | [20 empty] | 2021-01-15 |  | 2022-03-06 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH GRAFTON | 330733 | 1536 | 10 | Solar | 01_328W3 | 2020-12-09 18:52 | 2020-12-10 | 5 | 0 | 5 | 2020-12-18 | 2021-01-15 | 18 | 0 | 18 | [20 empty] | 2021-01-15 | 2020-12-09 18:59 | 2021-12-10 |  | EXP | [8 empty] | 2021-04-23 | Connected |  | No
National Grid | RANDOLPH | 327921 | 2368 | 9.8 | Solar | 07_5W3 | 2020-12-09 18:59 | 2020-12-10 | 6 | 0 | 6 | 2020-12-21 | 2021-01-18 | 17 | 0 | 17 | [20 empty] | 2021-01-27 |  | 2022-02-08 | Yes | EXP |  | 2021-09-29 | 2021-10-22 | 24 | 0 | 24 |  |  | 2022-02-04 | Connected |  | No
National Grid | AYER | 329550 | 1432 | 10 | Solar | 01_201W2 | 2020-12-10 08:54 | 2020-12-11 | 1 | 0 | 1 | 2020-12-15 | 2021-01-13 | 19 | 0 | 19 | [20 empty] | 2021-03-11 |  |  |  | EXP | [8 empty] | 2021-08-16 | Connected |  | No
National Grid | WRENTHAM | 330825 | 2093 | 11.52 | Solar | 05_3422W1 | 2020-12-10 10:18 | 2020-12-11 | 31 | 26 | 5 | 2021-01-29 | 2021-02-24 | 17 | 0 | 17 | [20 empty] | 2021-02-25 | 2020-12-10 11:33 | 2022-01-28 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WARE | 322772 | 1082 | 10 | Solar | 09_523L4 | 2020-12-10 11:33 | 2020-12-11 | 5 | 0 | 5 | 2020-12-21 | 2021-01-18 | 18 | 1 | 17 | [20 empty] | 2021-01-27 | 2020-12-10 12:49 | 2022-03-20 | Yes | EXP |  | 2021-07-02 | 2021-09-10 | 68 | 3 | 65 |  |  | 2021-10-15 | Connected |  | Yes
National Grid | BROCKTON | 330887 | 2302 | 15.2 | Solar | 07_712J1 | 2020-12-10 12:49 | 2020-12-11 | 5 | 0 | 5 | 2020-12-21 | 2021-01-19 | 18 | 0 | 18 | [20 empty] | 2021-01-20 | 2020-12-10 14:16 | 2022-12-04 | Yes | EXP |  | 2021-09-03 | 2021-10-08 | 36 | 0 | 36 |  |  | 2022-12-02 | Connected |  | No
National Grid | ESSEX | 330933 | 1929 | 5 | Solar | 12_51T2 | 2020-12-10 14:16 | 2020-12-11 | 5 | 0 | 5 | 2020-12-21 | 2021-01-19 | 18 | 0 | 18 | [20 empty] | 2021-01-20 |  | 2021-12-13 | Yes | EXP | [8 empty] | 2021-04-02 | Connected |  | No
National Grid | BELCHERTOWN | 330957 | 1007 | 17.6 | Solar | 09_509L1 | 2020-12-10 15:39 | 2020-12-11 | 15 | 11 | 4 | 2021-01-05 | 2021-01-24 | 13 | 0 | 13 | [20 empty] | 2021-01-26 |  | 2022-01-03 |  | EXP | [8 empty] | 2021-05-14 | Connected |  | No
National Grid | STOUGHTON | 326056 | 2072 | 7.6 | Solar | 07_913W47 | 2020-12-10 17:41 | 2020-12-11 | 5 | 0 | 5 | 2020-12-21 | 2021-01-18 | 17 | 0 | 17 | [20 empty] | 2021-01-27 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LEOMINSTER | 330998 | 1453 | 10 | Solar | 01_207W3 | 2020-12-10 19:45 | 2020-12-11 | 1 | 0 | 1 | 2020-12-15 | 2021-01-13 | 19 | 0 | 19 | [20 empty] | 2021-01-19 | 2020-12-10 21:10 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SALEM | 318458 | 1970 | 9.36 | Solar | 12_2W1 | 2020-12-10 21:10 | 2020-12-11 | 5 | 0 | 5 | 2020-12-21 | 2021-01-25 | 22 | 3 | 19 | [20 empty] | 2021-01-27 | 2020-12-11 11:56 | 2022-07-08 | Yes | EXP | [8 empty] | 2022-03-10 | Connected |  | No
National Grid | ATTLEBORO | 325226 | 2703 | 10 | Solar | 05_9L4 | 2020-12-11 11:56 | 2020-12-14 | 4 | 0 | 4 | 2020-12-21 | 2021-01-20 | 19 | 1 | 18 | [20 empty] | 2021-01-27 | 2020-12-11 13:33 |  | Yes | EXP | [8 empty] | 2021-05-08 | Connected |  | No
National Grid | ANDOVER | 331152 | 1810 | 25 | Solar | 14_62L2 | 2020-12-11 13:33 | 2020-12-14 | 4 | 0 | 4 | 2020-12-21 | 2021-01-18 | 17 | 0 | 17 | [20 empty] | 2021-01-25 |  | 2023-09-05 |  | EXP |  | 2021-08-15 | 2021-09-16 | 32 | 3 | 29 |  |  |  | Withdrawn |  | No
National Grid | LOWELL | 325076 | 1852 | 7.6 | Solar | 14_75L2 | 2020-12-11 14:43 | 2020-12-14 | 4 | 0 | 4 | 2020-12-21 | 2021-01-15 | 17 | 0 | 17 | [20 empty] | 2021-01-22 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEYMOUTH | 306140 | 2189 | 120 | Solar | 07_12W1 | 2020-12-11 17:12 | 2020-12-14 | 5 | 0 | 5 | 2020-12-22 | 2021-04-05 | 71 | 47 | 24 | 2021-05-13 | 2021-07-08 | 22 | 2 | 20 | [5 empty] | 2021-05-13 | 2021-07-08 | 22 | 2 | 20 | [5 empty] | 2021-06-25 | 2020-12-11 20:41 | 2024-07-01 |  | EXP |  | 2021-07-30 |  | 990 | 718 | 272 |  |  |  | Construction |  | No
National Grid | STOUGHTON | 331261 | 2072 | 8.88 | Solar | 07_913W43 | 2020-12-11 20:41 | 2020-12-14 | 18 | 14 | 4 | 2021-01-11 | 2021-02-02 | 15 | 0 | 15 | [20 empty] | 2021-02-04 | 2020-12-14 08:49 | 2023-05-15 | Yes | EXP |  | 2021-11-25 | 2022-02-12 | 80 | 0 | 80 |  |  | 2023-04-05 | Connected |  | No
National Grid | METHUEN | 327152 | 1844 | 7.6 | Solar | 14_63L1 | 2020-12-14 08:49 | 2020-12-15 | 3 | 0 | 3 | 2020-12-21 | 2021-01-15 | 17 | 0 | 17 | [20 empty] | 2021-01-22 | 2020-12-14 10:55 | 2022-03-02 | Yes | EXP |  | 2021-09-24 | 2021-10-12 | 18 | 0 | 18 |  |  | 2021-12-09 | Connected |  | No
National Grid | GRAFTON | 322960 | 1519 | 5.584 | Solar | 01_304W1 | 2020-12-14 10:55 | 2020-12-15 | 10 | 6 | 4 | 2020-12-31 | 2021-01-19 | 11 | 0 | 11 | [20 empty] | 2021-01-22 |  | 2022-02-03 | Yes | EXP |  | 2021-09-04 | 2021-11-08 | 66 | 4 | 62 |  |  | 2022-01-12 | Connected |  | No
National Grid | NORTH EASTON | 331116 | 2356 | 187.5 | Solar | 07_92W43 | 2020-12-14 11:36 | 2020-12-15 | 4 | 0 | 4 | 2020-12-22 | 2021-06-01 | 109 | 91 | 18 | [20 empty] | 2021-06-02 | 2020-12-14 14:22 | 2022-08-01 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MARLBOROUGH | 329523 | 1752 | 100.8 | Solar | 05_311W5 | 2020-12-14 14:22 | 2020-12-15 | 4 | 0 | 4 | 2020-12-22 | 2021-02-03 | 29 | 9 | 20 | [20 empty] | 2021-03-02 | 2020-12-14 15:24 |  | Yes | EXP |  | 2021-04-07 | 2021-12-20 | 257 | 7 | 250 |  |  |  | Withdrawn |  | Yes
National Grid | LOWELL | 330115 | 1850 | 5.76 | Solar | 14_75L1 | 2020-12-14 15:24 | 2020-12-15 | 41 | 38 | 3 | 2021-02-16 | 2021-04-09 | 38 | 17 | 21 | [20 empty] | 2021-04-12 |  | 2022-09-02 | Yes | EXP |  | 2021-05-28 | 2021-09-01 | 95 | 3 | 92 |  |  |  | Withdrawn |  | Yes
National Grid | WILBRAHAM | 331603 | 1095 | 8.88 | Solar | 09_523L1 | 2020-12-14 20:38 | 2020-12-15 | 14 | 11 | 3 | 2021-01-06 | 2021-01-25 | 12 | 0 | 12 | [20 empty] | 2021-01-26 | 2020-12-15 08:42 | 2022-01-04 |  | EXP | [8 empty] | 2021-04-10 | Connected |  | No
National Grid | MEDFORD | 331642 | 2155 | 10 | Solar | 12_37W4 | 2020-12-15 08:42 | 2020-12-16 | 3 | 0 | 3 | 2020-12-22 | 2021-01-15 | 16 | 0 | 16 | [20 empty] | 2021-01-19 | 2020-12-15 10:36 | 2021-12-16 | Yes | EXP |  | 2021-04-16 | 2021-05-04 | 18 | 0 | 18 |  |  | 2021-06-28 | Connected |  | No
National Grid | WARE | 329493 | 1082 | 25 | Battery Add-On | 09_501L2 | 2020-12-15 10:36 | 2020-12-16 | 17 | 13 | 4 | 2021-01-12 | 2021-02-09 | 19 | 0 | 19 | [20 empty] | 2021-02-09 | 2020-12-15 12:57 | 2022-05-23 | Yes | EXP |  | 2021-05-07 | 2021-05-18 | 11 | 0 | 11 |  |  | 2021-11-03 | Connected |  | No
National Grid | REVERE | 328785 | 2151 | 10 | Solar | 12_16W7 | 2020-12-15 12:57 | 2020-12-16 | 2 | 0 | 2 | 2020-12-21 | 2021-01-19 | 18 | 1 | 17 | [20 empty] | 2021-01-22 |  | 2022-05-19 | Yes | EXP |  | 2021-04-21 | 2021-05-11 | 20 | 0 | 20 |  |  | 2021-09-20 | Connected |  | Yes
National Grid | SEEKONK | 331769 | 2771 | 9.36 | Solar | 05_7L3 | 2020-12-15 13:59 | 2020-12-16 | 14 | 10 | 4 | 2021-01-07 | 2021-02-01 | 16 | 0 | 16 | [20 empty] | 2021-02-03 | 2020-12-15 16:57 | 2022-01-05 |  | EXP | [8 empty] | 2021-05-10 | Connected |  | No
National Grid | WILBRAHAM | 320388 | 1095 | 3.8 | Solar | 09_507L2 | 2020-12-15 16:57 | 2020-12-16 | 2 | 0 | 2 | 2020-12-21 | 2021-01-27 | 24 | 7 | 17 | [20 empty] | 2021-02-02 |  | 2022-10-06 | Yes | EXP |  | 2021-07-29 | 2021-09-10 | 42 | 3 | 39 |  |  | 2021-09-28 | Connected |  | No
National Grid | AVON | 331898 | 2322 | 15.2 | Solar | 07_75W5 | 2020-12-15 19:26 | 2020-12-16 | 0 | 0 | 0 | 2020-12-17 | 2021-01-13 | 17 | 0 | 17 | [20 empty] | 2021-01-19 |  |  |  | EXP | [8 empty] | 2021-03-18 | Connected |  | No
National Grid | MEDFORD | 331978 | 2155 | 7.6 | Solar | 12_67J1 | 2020-12-16 10:22 | 2020-12-17 | 15 | 12 | 3 | 2021-01-11 | 2021-02-03 | 16 | 0 | 16 | [20 empty] | 2021-02-05 | 2020-12-16 14:41 | 2022-01-07 |  | EXP | [8 empty] | 2021-03-04 | Connected |  | No
National Grid | WEST STOCKBRIDGE | 331061 | 1266 | 106.4 | Solar | 09_1109W3 | 2020-12-16 14:41 | 2020-12-17 | 20 | 12 | 8 | [10 empty] | 2021-01-19 | 2021-02-16 | 19 | 0 | 19 | [10 empty] | 2021-09-23 |  | 2023-06-23 | Yes | STD | [8 empty] | 2023-06-23 | Connected |  | No
National Grid | NORTH CHELMSFORD | 332924 | 1863 | 10 | Solar | 14_2L1 | 2020-12-18 09:16 | 2020-12-21 | 1 | 0 | 1 | 2020-12-23 | 2021-01-04 | 6 | 0 | 6 | [22 empty] | 2021-12-20 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SUTTON | 332953 | 1590 | 7.6 | Solar | 01_304W2 | 2020-12-18 10:37 | 2020-12-21 | 12 | 11 | 1 | 2021-01-08 | 2021-02-02 | 16 | 0 | 16 | [20 empty] | 2021-02-04 |  | 2022-07-13 |  | EXP | [8 empty] | 2022-01-21 | Connected |  | No
National Grid | AYER | 317230 | 1432 | 10 | Solar | 01_201W4 | 2020-12-18 10:48 | 2020-12-21 | 6 | 0 | 6 | 2020-12-31 | 2021-01-20 | 12 | 0 | 12 | [20 empty] | 2021-01-22 | 2020-12-18 12:01 | 2022-08-03 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTFORD | 332968 | 1886 | 20 | Solar | 14_57L2 | 2020-12-18 12:01 | 2020-12-21 | 9 | 8 | 1 | 2021-01-05 | 2021-01-21 | 11 | 0 | 11 | [20 empty] | 2021-01-22 | 2020-12-18 13:07 | 2022-01-03 | Yes | EXP | [8 empty] | 2021-03-23 | Connected |  | No
National Grid | REVERE | 316112 | 2151 | 10 | Solar | 12_16W7 | 2020-12-18 13:07 | 2020-12-21 | 6 | 0 | 6 | 2020-12-31 | 2021-01-20 | 12 | 0 | 12 | [20 empty] | 2021-01-27 |  | 2022-06-15 | Yes | EXP |  | 2021-08-02 | 2021-08-27 | 23 | 1 | 22 |  |  | 2021-09-13 | Connected |  | No
National Grid | LOWELL | 333029 | 1854 | 7.6 | Solar | 14_77L3 | 2020-12-18 13:44 | 2020-12-21 | 0 | 0 | 0 | 2020-12-22 | 2021-01-18 | 16 | 0 | 16 | [20 empty] | 2021-01-25 | 2020-12-21 14:43 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BEVERLY | 324809 | 1915 | 8.64 | Solar | 12_12L2 | 2020-12-21 14:43 | 2020-12-22 | 10 | 10 | 0 | 2021-01-07 | 2021-02-02 | 17 | 0 | 17 | [20 empty] | 2021-02-04 | 2020-12-21 15:20 | 2022-01-05 | Yes | EXP |  | 2021-07-09 | 2021-07-15 | 7 | 0 | 7 |  |  | 2021-08-05 | Connected |  | No
National Grid | BROCKTON | 330313 | 2302 | 7.6 | Solar | 07_91W46 | 2020-12-21 15:20 | 2020-12-22 | 0 | 0 | 0 | 2020-12-23 | 2021-01-19 | 16 | 0 | 16 | [20 empty] | 2021-01-25 |  |  | Yes | EXP |  | 2021-04-20 | 2021-04-19 | 0 | 0 | 0 |  |  | 2021-09-03 | Connected |  | No
National Grid | AMESBURY | 333336 | 1913 | 5.04 | Solar | 14_275L4 | 2020-12-21 15:32 | 2020-12-22 | 0 | 0 | 0 | 2020-12-23 | 2021-01-15 | 15 | 0 | 15 | [20 empty] | 2021-01-15 | 2020-12-21 16:04 | 2021-12-21 |  | EXP | [8 empty] | 2021-05-24 | Connected |  | No
National Grid | SALISBURY | 329558 | 1952 | 7.6 | Solar | 14_7L4 | 2020-12-21 16:04 | 2020-12-22 | 5 | 0 | 5 | 2020-12-31 | 2021-01-26 | 16 | 0 | 16 | [20 empty] | 2021-02-03 |  | 2022-09-14 | Yes | EXP |  | 2021-07-20 | 2021-09-10 | 52 | 3 | 49 |  |  | 2021-09-27 | Connected |  | No
National Grid | METHUEN | 326918 | 1844 | 9.8 | Solar | 14_63L1 | 2020-12-21 16:48 | 2020-12-22 | 5 | 0 | 5 | 2020-12-31 | 2021-01-21 | 13 | 0 | 13 | [20 empty] | 2021-01-27 | 2020-12-21 17:10 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LOWELL | 330497 | 1854 | 3.8 | Solar | 14_21L3 | 2020-12-21 17:10 | 2020-12-22 | 5 | 0 | 5 | 2020-12-31 | 2021-01-26 | 16 | 0 | 16 | [20 empty] | 2021-02-04 | 2020-12-22 15:10 | 2022-09-26 | Yes | EXP |  | 2021-08-25 | 2021-10-05 | 36 | 0 | 36 |  |  | 2022-06-15 | Connected |  | No
National Grid | WRENTHAM | 326235 | 2093 | 9.8 | Solar | 05_3422W1 | 2020-12-22 15:10 | 2020-12-23 | 4 | 0 | 4 | 2020-12-31 | 2021-01-26 | 16 | 0 | 16 | [20 empty] | 2021-02-04 | 2020-12-22 15:50 | 2022-03-08 | Yes | EXP |  | 2021-09-04 | 2021-10-12 | 13 | 0 | 13 |  |  | 2022-02-03 | Connected |  | No
National Grid | SWANSEA | 328690 | 2777 | 8.19 | Solar | 05_19W73 | 2020-12-22 15:50 | 2020-12-23 | 2 | 2 | 0 | 2020-12-29 | 2021-01-19 | 13 | 0 | 13 | [20 empty] | 2021-01-20 | 2020-12-22 16:01 | 2022-05-30 | Yes | EXP |  | 2021-03-25 | 2021-04-30 | 36 | 0 | 36 |  |  | 2021-12-13 | Connected |  | No
National Grid | LAWRENCE | 322575 | 1841 | 10 | Solar | 14_8L2 | 2020-12-22 16:01 | 2020-12-23 | 4 | 0 | 4 | 2020-12-31 | 2021-01-21 | 13 | 0 | 13 | [20 empty] | 2021-01-27 | 2020-12-22 16:57 |  | Yes | EXP |  | 2021-04-14 | 2021-04-26 | 12 | 0 | 12 |  |  | 2021-05-29 | Connected |  | No
National Grid | LAWRENCE | 322607 | 1841 | 5 | Solar | 14_53J4 | 2020-12-22 16:57 | 2020-12-23 | 4 | 0 | 4 | 2020-12-31 | 2021-01-26 | 16 | 0 | 16 | [20 empty] | 2021-02-04 |  | 2022-04-03 | Yes | EXP |  | 2021-08-15 | 2021-09-24 | 40 | 3 | 37 |  |  | 2021-11-09 | Connected |  | No
National Grid | RANDOLPH | 320043 | 2368 | 9.8 | Solar | 07_5W4 | 2020-12-23 14:58 | 2020-12-24 | 3 | 0 | 3 | 2020-12-31 | 2021-01-20 | 12 | 0 | 12 | [20 empty] | 2021-01-27 | 2020-12-23 18:09 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MONSON | 333791 | 1057 | 15.2 | Solar | 09_139L1 | 2020-12-23 18:09 | 2020-12-24 | 3 | 2 | 1 | 2020-12-30 | 2021-01-20 | 13 | 0 | 13 | [20 empty] | 2021-01-22 |  | 2022-06-08 | Yes | EXP |  | 2021-04-14 | 2021-05-12 | 28 | 0 | 28 |  |  | 2021-12-14 | Connected |  | No
National Grid | CHARLTON | 327784 | 1507 | 9.8 | Solar | 01_415L2 | 2020-12-28 09:37 | 2020-12-29 | 2 | 0 | 2 | 2021-01-04 | 2021-01-26 | 15 | 0 | 15 | [20 empty] | 2021-02-04 |  | 2022-02-13 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTBOROUGH | 334005 | 1581 | 7.6 | Solar | 05_312W4 | 2020-12-28 13:40 | 2020-12-29 | 7 | 7 | 0 | 2021-01-08 | 2021-02-03 | 17 | 0 | 17 | [20 empty] | 2021-02-05 | 2020-12-28 13:50 | 2022-05-16 |  | EXP | [8 empty] | 2021-10-06 | Connected |  | No
National Grid | RANDOLPH | 325552 | 2368 | 7.68 | Solar | 07_97W2 | 2020-12-28 13:50 | 2020-12-29 | 9 | 9 | 0 | 2021-01-13 | 2021-02-10 | 19 | 0 | 19 | [20 empty] | 2021-02-10 |  | 2022-05-25 | Yes | EXP |  | 2021-04-27 | 2021-05-19 | 22 | 0 | 22 |  |  | 2021-10-04 | Connected |  | No
National Grid | MELROSE | 334088 | 2176 | 10 | Solar | 12_25W5 | 2020-12-28 16:35 | 2020-12-29 | 7 | 7 | 0 | 2021-01-08 | 2021-02-03 | 17 | 0 | 17 | [20 empty] | 2021-02-05 | 2020-12-29 13:46 | 2022-01-06 |  | EXP | [8 empty] | 2021-08-26 | Connected |  | No
National Grid | METHUEN | 329444 | 1844 | 7.6 | Solar | 14_63L1 | 2020-12-29 13:46 | 2020-12-30 | 1 | 0 | 1 | 2021-01-04 | 2021-01-21 | 12 | 0 | 12 | [20 empty] | 2021-01-27 |  | 2022-12-22 | Yes | EXP |  | 2021-08-06 | 2021-10-12 | 61 | 3 | 58 |  |  | 2021-12-01 | Connected |  | Yes
National Grid | MILLBURY | 330585 | 1527 | 3.12 | Solar | 01_304W3 | 2020-12-29 16:29 | 2020-12-30 | 1 | 0 | 1 | 2021-01-04 | 2021-01-21 | 12 | 0 | 12 | [20 empty] | 2021-01-27 |  |  |  | EXP | [8 empty] | 2022-11-09 | Withdrawn |  | No
National Grid | WEST BROOKFIELD | 330996 | 1585 | 9.8 | Solar | 01_525L2 | 2020-12-30 11:27 | 2020-12-31 | 1 | 0 | 1 | 2021-01-05 | 2021-01-26 | 14 | 0 | 14 | [20 empty] | 2021-02-03 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MONTEREY | 333580 | 1245 | 20 | Solar | 09_1109W1 | 2020-12-30 11:41 | 2020-12-31 | 0 | 0 | 0 | 2021-01-04 | 2021-01-20 | 11 | 0 | 11 | [20 empty] | 2021-01-21 |  | 2022-06-05 |  | EXP | [8 empty] | 2022-05-24 | Connected |  | No
National Grid | NORTHBOROUGH | 334003 | 1532 | 10 | Solar | 05_313W2 | 2020-12-30 14:38 | 2020-12-31 | 2 | 0 | 2 | 2021-01-06 | 2021-01-29 | 16 | 0 | 16 | [20 empty] | 2021-02-04 |  |  |  | EXP | [8 empty] | 2021-07-08 | Connected |  | No
National Grid | REVERE | 330995 | 2151 | 10 | Solar | 12_7J6 | 2020-12-30 16:41 | 2020-12-31 | 2 | 0 | 2 | 2021-01-06 | 2021-01-29 | 16 | 0 | 16 | [20 empty] | 2021-02-04 |  | 2022-04-06 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WINCHENDON | 325150 | 1475 | 9992 | Other | 01_612W1 | 2020-12-31 11:07 | 2021-01-04 | 3 | 0 | 3 | [10 empty] | 2021-01-07 | 2021-01-29 | 15 | 0 | 15 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | MENDON | 297954 | 1756 | 4990 | Other | 05_321W6 | 2021-01-02 10:20 | 2021-01-04 | 17 | 12 | 5 | [10 empty] | 2021-01-29 | 2021-02-26 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | CHARLTON | 315126 | 1507 | 4990 | Other | 01_415L1 | 2021-01-02 10:20 | 2021-01-04 | 22 | 16 | 6 | [10 empty] | 2021-02-05 | 2021-03-08 | 20 | 0 | 20 | [11 empty] | 2021-01-04 14:00 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MILLBURY | 331259 | 1527 | 7.6 | Solar | 01_304W3 | 2021-01-04 14:00 | 2021-01-05 | 12 | 11 | 1 | 2021-01-22 | 2021-02-17 | 17 | 0 | 17 | [20 empty] | 2021-02-17 | 2021-01-04 15:29 | 2023-06-24 | Yes | EXP |  | 2022-03-25 | 2022-06-17 | 85 | 0 | 85 |  |  | 2022-08-30 | Connected |  | No
National Grid | SOMERSET | 331847 | 2726 | 8.75 | Solar | 05_19W72 | 2021-01-04 15:29 | 2021-01-05 | 2 | 0 | 2 | 2021-01-08 | 2021-02-03 | 17 | 0 | 17 | [20 empty] | 2021-02-09 | 2021-01-04 15:49 |  | Yes | EXP |  | 2021-08-03 | 2021-08-17 | 15 | 0 | 15 |  |  | 2021-08-26 | Connected |  | No
National Grid | METHUEN | 330332 | 1844 | 9.8 | Solar | 14_63L1 | 2021-01-04 15:49 | 2021-01-05 | 2 | 0 | 2 | 2021-01-08 | 2021-02-02 | 16 | 0 | 16 | [20 empty] | 2021-02-04 |  | 2022-03-07 | Yes | EXP |  | 2021-09-14 | 2021-10-14 | 31 | 0 | 31 |  |  | 2021-12-13 | Connected |  | Yes
National Grid | GRANBY | 293669 | 1033 | 5000 | Other | 09_527L1 | 2021-01-05 10:32 | 2021-01-06 | 50 | 42 | 8 | [26 empty] | 2021-01-05 13:11 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SOMERSET | 330085 | 2726 | 6 | Solar | 05_19W72 | 2021-01-05 13:11 | 2021-01-06 | 1 | 0 | 1 | 2021-01-08 | 2021-02-09 | 20 | 2 | 18 | [20 empty] | 2021-02-16 | 2021-01-05 13:29 |  | Yes | EXP |  | 2021-05-27 | 2021-07-08 | 42 | 0 | 42 |  |  | 2021-08-06 | Connected |  | No
National Grid | UPTON | 334895 | 1568 | 3.8 | Solar | 05_335W3 | 2021-01-05 13:29 | 2021-01-06 | 1 | 1 | 0 | 2021-01-07 | 2021-02-03 | 18 | 0 | 18 | [20 empty] | 2021-02-05 |  | 2022-01-05 | Yes | EXP |  | 2021-04-21 | 2021-06-02 | 42 | 0 | 42 |  |  | 2021-06-16 | Connected |  | No
National Grid | BROCKTON | 330724 | 2302 | 3.8 | Solar | 07_911W77 | 2021-01-06 08:52 | 2021-01-07 | 2 | 0 | 2 | 2021-01-12 | 2021-02-07 | 18 | 0 | 18 | [20 empty] | 2021-02-09 |  |  |  | EXP | [8 empty] | 2021-08-04 | Connected |  | No
National Grid | BELCHERTOWN | 335189 | 1007 | 17 | Solar | 09_509L2 | 2021-01-06 09:42 | 2021-01-07 | 0 | 0 | 0 | 2021-01-08 | 2021-02-12 | 24 | 8 | 16 | [20 empty] | 2021-02-12 |  | 2022-01-06 |  | EXP | [8 empty] | 2021-04-22 | Connected |  | No
National Grid | NORTH ANDOVER | 332646 | 1845 | 7.6 | Solar | 14_7J4 | 2021-01-06 12:05 | 2021-01-07 | 2 | 0 | 2 | 2021-01-12 | 2021-02-09 | 18 | 0 | 18 | [20 empty] | 2021-02-16 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LOWELL | 325147 | 1852 | 7.68 | Solar | 14_70L1 | 2021-01-06 12:22 | 2021-01-07 | 28 | 28 | 0 | 2021-02-18 | 2021-03-22 | 22 | 0 | 22 | [20 empty] | 2021-03-22 | 2021-01-06 14:05 | 2022-02-17 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH ANDOVER | 335404 | 1845 | 9.36 | Solar | 14_56L2 | 2021-01-06 14:05 | 2021-01-07 | 12 | 12 | 0 | 2021-01-26 | 2021-02-17 | 15 | 0 | 15 | [20 empty] | 2021-02-17 |  | 2022-01-24 | Yes | EXP |  | 2021-05-12 | 2021-06-02 | 21 | 0 | 21 |  |  | 2021-07-23 | Connected |  | No
National Grid | FRANKLIN | 320921 | 2038 | 499.9 | Solar | 05_348W7 | 2021-01-06 20:15 | 2021-01-07 | 30 | 23 | 7 | [10 empty] | 2021-02-22 | 2021-03-19 | 20 | 0 | 20 | [10 empty] | 2022-06-06 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | FRANKLIN | 320922 | 2038 | 499.9 | Solar | 05_348W7 | 2021-01-06 20:21 | 2021-01-07 | 30 | 23 | 7 | [10 empty] | 2021-02-22 | 2021-03-19 | 20 | 0 | 20 | [10 empty] | 2022-06-06 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MILL RIVER | 335591 | 1244 | 7.6 | Solar | 09_1109W1 | 2021-01-07 10:31 | 2021-01-08 | 11 | 11 | 0 | 2021-01-26 | 2021-02-17 | 15 | 0 | 15 | [20 empty] | 2021-02-17 |  | 2022-06-07 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ATTLEBORO | 331536 | 2703 | 7.6 | Solar | 05_9L4 | 2021-01-07 14:23 | 2021-01-08 | 2 | 0 | 2 | 2021-01-13 | 2021-02-10 | 19 | 0 | 19 | [20 empty] | 2021-02-17 | 2021-01-07 14:38 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 328433 | 2302 | 9.8 | Solar | 07_91W41 | 2021-01-07 14:38 | 2021-01-08 | 1 | 0 | 1 | 2021-01-12 | 2021-02-09 | 18 | 0 | 18 | [20 empty] | 2021-02-16 |  | 2022-06-25 | Yes | EXP |  | 2021-06-18 | 2021-06-28 | 11 | 0 | 11 |  |  | 2022-03-29 | Connected |  | Yes
National Grid | RANDOLPH | 332457 | 2368 | 3.8 | Solar | 07_97W2 | 2021-01-07 14:54 | 2021-01-08 | 6 | 6 | 0 | 2021-01-19 | 2021-02-10 | 16 | 0 | 16 | [20 empty] | 2021-02-10 |  | 2022-01-14 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FOXBOROUGH | 328991 | 2035 | 7.6 | Solar | 05_3424W5 | 2021-01-08 10:19 | 2021-01-11 | 4 | 4 | 0 | 2021-01-15 | 2021-02-11 | 18 | 0 | 18 | [20 empty] | 2021-02-11 | 2021-01-08 10:27 | 2022-01-14 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 326326 | 1844 | 7.6 | Solar | 14_43L4 | 2021-01-08 10:27 | 2021-01-11 | 0 | 0 | 0 | 2021-01-12 | 2021-02-03 | 15 | 0 | 15 | [20 empty] | 2021-02-11 | 2021-01-08 11:03 |  | Yes | EXP |  | 2021-05-25 | 2021-06-18 | 24 | 0 | 24 |  |  | 2021-08-27 | Connected |  | No
National Grid | EVERETT | 329274 | 2149 | 5 | Solar | 12_37W6 | 2021-01-08 11:03 | 2021-01-11 | 1 | 0 | 1 | 2021-01-13 | 2021-02-10 | 19 | 0 | 19 | [20 empty] | 2021-02-17 |  | 2022-08-03 | Yes | EXP |  | 2021-06-02 | 2021-12-09 | 191 | 7 | 184 |  |  | 2021-12-22 | Connected |  | No
National Grid | CLINTON | 321965 | 1510 | 5315 | Solar | 01_216W1 | 2021-01-08 11:28 | 2021-01-11 | 77 | 68 | 9 | [10 empty] | 2021-05-04 | 2021-06-02 | 20 | 0 | 20 | [11 empty] | 2021-01-08 12:26 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | EAST BRIDGEWATER | 328155 | 2333 | 10 | Solar | 07_797W29 | 2021-01-08 12:26 | 2021-01-11 | 1 | 0 | 1 | 2021-01-13 | 2021-02-10 | 19 | 0 | 19 | [20 empty] | 2021-02-17 |  |  | Yes | EXP |  | 2021-07-20 | 2021-08-17 | 25 | 0 | 25 |  |  | 2021-09-02 | Connected |  | No
National Grid | NORTHBRIDGE | 335875 | 1534 | 9.6 | Solar | 05_320W1 | 2021-01-08 12:34 | 2021-01-11 | 6 | 5 | 1 | 2021-01-21 | 2021-02-17 | 18 | 0 | 18 | [20 empty] | 2021-02-18 | 2021-01-08 12:37 | 2022-01-18 |  | EXP | [8 empty] | 2021-05-11 | Connected |  | No
National Grid | MEDFORD | 331636 | 2155 | 10 | Solar | 12_67J1 | 2021-01-08 12:37 | 2021-01-11 | 2 | 2 | 0 | 2021-01-13 | 2021-02-10 | 19 | 0 | 19 | [20 empty] | 2021-02-10 |  | 2022-01-11 | Yes | EXP |  | 2021-03-25 | 2021-06-24 | 91 | 0 | 91 |  |  | 2021-06-30 | Connected |  | No
National Grid | SOUTH HAMILTON | 335872 | 1982 | 100 | Solar | 12_18L2 | 2021-01-08 13:14 | 2021-01-11 | 9 | 0 | 9 | 2021-01-26 | 2021-02-22 | 18 | 0 | 18 | [20 empty] | 2021-03-10 | 2021-01-11 11:21 | 2022-12-16 |  | EXP | [8 empty] | 2022-12-12 | Connected |  | No
National Grid | WILLIAMSBURG | 332573 | 1096 | 3.48 | Solar | 09_909W3 | 2021-01-11 11:21 | 2021-01-12 | 3 | 0 | 3 | 2021-01-19 | 2021-02-16 | 19 | 0 | 19 | [20 empty] | 2021-02-17 |  |  | Yes | EXP | [8 empty] | 2021-07-07 | Connected |  | No
National Grid | WOLLASTON | 336065 | 2170 | 7.6 | Solar | 07_11W4 | 2021-01-11 11:34 | 2022-12-21 | 8 | 6 | 2 | 2023-01-04 | 2023-02-01 | 20 | 0 | 20 | [20 empty] | 2021-01-13 |  | 2024-02-15 |  | EXP | [8 empty] | 2023-02-17 | Connected |  | No
National Grid | HARVARD | 336027 | 1451 | 200 | Solar | 01_216W6 | 2021-01-11 12:00 | 2021-01-12 | 9 | 1 | 8 | 2021-02-03 | 2021-05-19 | 74 | 51 | 23 | [20 empty] | 2021-05-20 |  | 2022-07-25 |  | EXP | [8 empty] | 2022-02-16 | Connected |  | No
National Grid | WESTFORD | 335891 | 1886 | 100 | Solar | 14_57L2 | 2021-01-11 14:29 | 2021-01-12 | 8 | 0 | 8 | 2021-01-26 | 2021-02-22 | 18 | 0 | 18 | [20 empty] | 2021-03-10 |  | 2022-03-20 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RANDOLPH | 310071 | 2368 | 5 | Solar | 07_97W2 | 2021-01-11 15:22 | 2021-01-12 | 3 | 0 | 3 | 2021-01-19 | 2021-02-10 | 16 | 0 | 16 | [20 empty] | 2021-02-17 | 2021-01-11 15:51 | 2022-04-26 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WILBRAHAM | 335397 | 1095 | 7.6 | Solar | 09_507L3 | 2021-01-11 15:51 | 2021-01-12 | 3 | 0 | 3 | 2021-01-19 | 2021-02-10 | 16 | 0 | 16 | [20 empty] | 2021-02-17 |  |  | Yes | EXP |  | 2021-06-25 | 2021-08-06 | 41 | 0 | 41 |  |  | 2021-09-09 | Connected |  | No
National Grid | MEDFORD | 323871 | 2155 | 7.6 | Solar | 12_37W4 | 2021-01-11 17:20 | 2021-01-12 | 7 | 7 | 0 | 2021-01-25 | 2021-02-17 | 16 | 0 | 16 | [20 empty] | 2021-02-18 | 2021-01-11 17:42 | 2022-01-21 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WILBRAHAM | 330777 | 1095 | 7.6 | Solar | 09_507L1 | 2021-01-11 17:42 | 2021-01-12 | 4 | 4 | 0 | 2021-01-20 | 2021-02-11 | 16 | 0 | 16 | [20 empty] | 2021-02-11 |  | 2022-01-18 | Yes | EXP |  | 2021-06-02 | 2021-06-15 | 13 | 0 | 13 |  |  | 2021-07-03 | Connected |  | No
National Grid | WHITMAN | 334165 | 2382 | 9.8 | Solar | 07_91W47 | 2021-01-11 17:52 | 2021-01-12 | 6 | 6 | 0 | [26 empty] | 2021-01-12 12:22 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEBSTER | 332213 | 1570 | 7.6 | Solar | 01_412L5 | 2021-01-12 12:22 | 2021-01-13 | 2 | 0 | 2 | 2021-01-19 | 2021-02-10 | 16 | 0 | 16 | [20 empty] | 2021-02-17 | 2021-01-12 14:16 | 2022-03-08 | Yes | EXP |  | 2021-09-23 | 2022-01-19 | 119 | 4 | 115 |  |  | 2022-02-05 | Connected |  | No
National Grid | ROCKPORT | 336432 | 1966 | 7.44 | Solar | 12_40J2 | 2021-01-12 14:16 | 2021-01-13 | 0 | 0 | 0 | 2021-01-14 | 2021-02-10 | 18 | 0 | 18 | [20 empty] | 2021-02-10 |  | 2022-01-12 | Yes | EXP |  | 2021-04-21 | 2021-04-20 | 0 | 0 | 0 |  |  | 2021-05-25 | Connected |  | No
National Grid | RANDOLPH | 336483 | 2368 | 10 | Solar | 07_97W3 | 2021-01-12 17:14 | 2021-01-13 | 2 | 0 | 2 | 2021-01-19 | 2021-02-16 | 19 | 0 | 19 | [20 empty] | 2021-02-17 | 2021-01-13 13:57 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 334306 | 1844 | 7.6 | Solar | 14_74L1 | 2021-01-13 13:57 | 2021-01-14 | 11 | 11 | 0 | 2021-02-01 | 2021-03-02 | 20 | 0 | 20 | [20 empty] | 2021-03-03 | 2021-01-13 17:18 | 2022-09-29 | Yes | EXP |  | 2021-09-11 | 2021-09-24 | 14 | 0 | 14 |  |  | 2022-03-03 | Connected |  | No
National Grid | METHUEN | 334597 | 1844 | 7.6 | Solar | 14_74L6 | 2021-01-13 17:18 | 2021-01-14 | 16 | 16 | 0 | 2021-02-08 | 2021-03-02 | 15 | 0 | 15 | [20 empty] | 2021-03-02 |  | 2022-09-02 | Yes | EXP |  | 2021-08-15 | 2021-09-01 | 16 | 3 | 13 |  |  | 2022-02-02 | Connected |  | No
National Grid | DOUGLAS | 288134 | 1516 | 4990 | Other | 05_321W4 | 2021-01-14 13:16 | 2021-01-15 | 22 | 17 | 5 | [10 empty] | 2021-03-19 | 2021-04-14 | 18 | 18 | 0 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | ABINGTON | 336885 | 2351 | 8.7 | Solar | 07_60J1 | 2021-01-14 13:55 | 2021-01-15 | 0 | 0 | 0 | 2021-01-19 | 2021-02-16 | 19 | 0 | 19 | [20 empty] | 2021-02-16 |  | 2022-01-14 |  | EXP | [8 empty] | 2021-04-16 | Connected |  | No
National Grid | LEICESTER | 289979 | 1524 | 4990 | Other | 01_21W1 | 2021-01-14 13:57 | 2021-01-15 | 27 | 18 | 9 | [10 empty] | 2021-02-26 | 2021-03-23 | 17 | 0 | 17 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | ABINGTON | 336920 | 2351 | 8.7 | Solar | 07_60J1 | 2021-01-14 15:43 | 2021-01-15 | 0 | 0 | 0 | 2021-01-19 | 2021-02-10 | 16 | 0 | 16 | [20 empty] | 2021-02-10 | 2021-01-15 07:35 | 2022-01-14 |  | EXP | [8 empty] | 2021-04-16 | Connected |  | No
National Grid | EVERETT | 336201 | 2149 | 7.6 | Solar | 12_16W7 | 2021-01-15 07:35 | 2021-01-19 | 4 | 0 | 4 | 2021-01-26 | 2021-02-17 | 15 | 0 | 15 | [20 empty] | 2021-03-23 |  | 2022-04-09 | Yes | EXP |  | 2021-08-06 | 2021-12-21 | 137 | 7 | 130 |  |  | 2022-02-26 | Connected |  | No
National Grid | LAWRENCE | 335011 | 1841 | 166.6 | Solar | 14_6J2 | 2021-01-15 08:08 | 2021-01-19 | 5 | 0 | 5 | 2021-01-27 | 2021-02-24 | 19 | 0 | 19 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 336430 | 1604 | 6 | Solar | 01_27W1 | 2021-01-15 08:47 | 2021-01-19 | 4 | 0 | 4 | 2021-01-26 | 2021-02-22 | 18 | 0 | 18 | [20 empty] | 2021-03-02 |  |  |  | EXP | [8 empty] | 2021-05-06 | Connected |  | No
National Grid | NANTUCKET | 331118 | 2554 | 19.72 | Solar | 04_101L7 | 2021-01-15 12:06 | 2021-01-19 | 4 | 0 | 4 | 2021-01-26 | 2021-03-16 | 34 | 17 | 17 | [20 empty] | 2021-03-18 | 2021-01-15 12:38 |  |  | EXP | [8 empty] | 2021-07-16 | Connected |  | No
National Grid | BRIDGEWATER | 331425 | 2324 | 3286 | Solar | 07_797W1 | 2021-01-15 12:38 | 2021-01-19 | 20 | 12 | 8 | [10 empty] | 2021-02-17 | 2021-08-03 | 117 | 93 | 24 | [10 empty] | 2022-06-30 |  | 2024-11-07 | Yes | STD | [9 empty] | Design |  | No
National Grid | NORTHBRIDGE | 293617 | 1534 | 4990 | Other | 05_321W5 | 2021-01-15 13:43 | 2021-01-19 | 26 | 17 | 9 | [10 empty] | 2021-02-26 | 2021-05-27 | 63 | 45 | 18 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTFORD | 335256 | 1886 | 250 | Solar | 14_57L3 | 2021-01-15 14:46 | 2021-01-19 | 5 | 0 | 5 | 2021-01-27 | 2021-02-25 | 20 | 0 | 20 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | COHASSET | 336653 | 2025 | 233.2 | Solar | 07_96W41 | 2021-01-15 14:58 | 2021-01-19 | 5 | 0 | 5 | 2021-01-27 | 2021-02-25 | 20 | 0 | 20 | [20 empty] | 2021-05-07 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | COHASSET | 336658 | 2025 | 66.6 | Solar | 07_96W41 | 2021-01-15 15:02 | 2021-01-19 | 5 | 0 | 5 | 2021-01-27 | 2021-02-24 | 19 | 0 | 19 | [20 empty] | 2021-03-11 | 2021-01-15 16:15 | 2022-03-19 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SUTTON | 337127 | 1590 | 9.86 | Solar | 01_304W2 | 2021-01-15 16:15 | 2021-01-19 | 3 | 0 | 3 | 2021-01-25 | 2021-03-17 | 36 | 16 | 20 | [20 empty] | 2021-03-17 | 2021-01-18 08:15 | 2022-01-21 | Yes | EXP |  | 2021-05-04 | 2021-05-21 | 17 | 0 | 17 |  |  | 2021-08-05 | Connected |  | No
National Grid | PETERSHAM | 330336 | 1366 | 7.6 | Solar | 09_604W1 | 2021-01-18 08:15 | 2021-01-19 | 8 | 5 | 3 | 2021-01-29 | 2021-03-02 | 21 | 0 | 21 | [20 empty] | 2021-03-02 |  | 2022-01-27 | Yes | EXP |  | 2021-04-21 | 2021-05-12 | 21 | 0 | 21 |  |  | 2021-05-13 | Connected |  | No
National Grid | WHITINSVILLE | 329362 | 1588 | 10 | Solar | 05_320W5 | 2021-01-18 12:08 | 2021-01-19 | 19 | 16 | 3 | 2021-02-16 | 2021-02-26 | 8 | 0 | 8 | [21 empty] | 2021-01-18 13:24 | 2022-02-11 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BELLINGHAM | 335851 | 2019 | 6.96 | Solar | 05_335W1 | 2021-01-18 13:24 | 2021-01-19 | 5 | 1 | 4 | 2021-01-27 | 2021-02-23 | 18 | 0 | 18 | [20 empty] | 2021-03-02 | 2021-01-18 13:47 | 2022-05-20 | Yes | EXP |  | 2021-08-21 | 2021-09-29 | 34 | 3 | 31 |  |  | 2021-12-18 | Connected |  | No
National Grid | FALL RIVER | 335842 | 2720 | 5.52 | Solar | 05_28W51 | 2021-01-18 13:47 | 2021-01-19 | 4 | 0 | 4 | 2021-01-26 | 2021-04-28 | 64 | 40 | 24 | [20 empty] | 2021-05-06 |  | 2022-09-16 | Yes | EXP |  | 2022-03-31 | 2022-04-12 | 13 | 0 | 13 |  |  | 2022-06-04 | Connected |  | No
National Grid | BEVERLY | 335860 | 1915 | 5.52 | Solar | 12_51L1 | 2021-01-18 14:05 | 2021-01-19 | 4 | 0 | 4 | 2021-04-13 | 2021-06-09 | 40 | 16 | 24 | [20 empty] | 2021-06-09 | 2021-01-18 16:48 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RANDOLPH | 329783 | 2368 | 3.8 | Solar | 07_97W1 | 2021-01-18 16:48 | 2021-01-19 | 7 | 4 | 3 | 2021-01-28 | 2021-02-24 | 18 | 0 | 18 | [20 empty] | 2021-02-24 |  | 2022-01-27 | Yes | EXP |  | 2021-04-27 | 2021-05-21 | 24 | 0 | 24 |  |  | 2021-09-01 | Connected |  | No
National Grid | AUBURN | 337541 | 1501 | 9.8 | Solar | 01_26W3 | 2021-01-19 15:16 | 2021-01-20 | 3 | 0 | 3 | 2021-01-26 | 2021-02-23 | 19 | 1 | 18 | [20 empty] | 2021-03-02 | 2021-01-19 17:04 | 2022-03-16 |  | EXP | [8 empty] | 2021-11-13 | Connected |  | No
National Grid | EAST LONGMEADOW | 335442 | 1028 | 7.875 | Solar | 09_139L5 | 2021-01-19 17:04 | 2021-01-20 | 3 | 1 | 2 | 2021-01-26 | 2021-02-17 | 15 | 0 | 15 | [20 empty] | 2021-02-17 | 2021-01-20 07:49 | 2022-01-24 | Yes | EXP |  | 2021-05-08 | 2021-05-25 | 17 | 0 | 17 |  |  | 2021-07-13 | Connected |  | No
National Grid | WESTFORD | 311522 | 1886 | 11.4 | Solar | 14_57L1 | 2021-01-20 07:49 | 2021-01-21 | 2 | 0 | 2 | 2021-01-26 | 2021-02-17 | 15 | 0 | 15 | [20 empty] | 2021-03-01 | 2021-01-20 09:35 | 2022-04-05 | Yes | EXP |  | 2021-08-06 | 2021-12-29 | 146 | 7 | 139 |  |  | 2022-02-09 | Connected |  | No
National Grid | BELCHERTOWN | 335107 | 1007 | 10 | Solar | 09_509L2 | 2021-01-20 09:35 | 2021-01-21 | 3 | 2 | 1 | 2021-01-27 | 2021-02-22 | 17 | 0 | 17 | [20 empty] | 2021-02-23 | 2021-01-20 15:32 | 2022-01-25 | Yes | EXP | [8 empty] | 2021-04-14 | Connected |  | No
National Grid | BEVERLY | 335686 | 1915 | 7.68 | Solar | 12_51L1 | 2021-01-20 15:32 | 2021-01-21 | 15 | 14 | 1 | 2021-02-11 | 2021-03-08 | 16 | 0 | 16 | [20 empty] | 2021-03-08 |  | 2022-02-10 | Yes | EXP |  | 2021-05-15 | 2021-05-14 | 0 | 0 | 0 |  |  | 2021-05-18 | Connected |  | No
National Grid | SCITUATE | 337902 | 2066 | 7.6 | Solar | 07_915W36 | 2021-01-21 10:49 | 2021-01-22 | 13 | 12 | 1 | 2021-02-10 | 2021-03-02 | 13 | 0 | 13 | [20 empty] | 2021-03-02 |  | 2022-11-26 |  | EXP | [8 empty] | 2022-10-28 | Connected |  | Yes
National Grid | CHELMSFORD | 337957 | 1824 | 7.6 | Solar | 14_16L4 | 2021-01-21 11:37 | 2021-01-22 | 18 | 17 | 1 | 2021-02-18 | 2021-03-11 | 15 | 0 | 15 | [20 empty] | 2021-03-11 |  | 2022-02-17 |  | EXP | [8 empty] | 2021-05-04 | Connected |  | No
National Grid | NORTHAMPTON | 337254 | 1060 | 17 | Solar | 09_905W1 | 2021-01-21 14:40 | 2021-01-22 | 2 | 1 | 1 | 2021-01-27 | 2021-02-23 | 18 | 0 | 18 | [20 empty] | 2021-02-23 | 2021-01-21 16:40 | 2022-01-25 |  | EXP | [8 empty] | 2021-04-07 | Connected |  | No
National Grid | WESTBOROUGH | 338021 | 1581 | 80 | Solar | 05_312W1 | 2021-01-21 16:40 | 2021-01-22 | 2 | 0 | 2 | 2021-01-27 | 2021-03-25 | 41 | 18 | 23 | [20 empty] | 2021-04-30 | 2021-01-21 17:41 | 2024-05-05 | Yes | EXP | [9 empty] | Construction |  | No
National Grid | SOUTH HAMILTON | 330460 | 1982 | 9.8 | Solar | 12_51T2 | 2021-01-21 17:41 | 2021-01-22 | 1 | 0 | 1 | 2021-01-26 | 2021-02-17 | 15 | 0 | 15 | [20 empty] | 2021-03-01 | 2021-01-21 19:18 | 2023-04-09 | Yes | EXP |  | 2021-07-31 | 2021-08-26 | 26 | 1 | 25 |  |  | 2022-07-20 | Connected |  | No
National Grid | STOUGHTON | 331347 | 2072 | 10 | Solar | 07_913W43 | 2021-01-21 19:18 | 2021-01-22 | 3 | 2 | 1 | 2021-01-28 | 2021-02-24 | 18 | 0 | 18 | [20 empty] | 2021-03-02 |  | 2022-10-16 | Yes | EXP | [8 empty] | 2021-12-17 | Connected |  | No
National Grid | SEEKONK | 336489 | 2771 | 6 | Solar | 05_7L1 | 2021-01-21 21:05 | 2021-01-25 | 1 | 1 | 0 | 2021-01-27 | 2021-02-17 | 14 | 0 | 14 | [20 empty] | 2021-02-17 |  | 2022-01-25 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BRIMFIELD | 306870 | 1010 | 17.6 | Solar | 09_503L4 | 2021-01-22 08:42 | 2021-01-25 | 3 | 2 | 1 | 2021-01-28 | 2021-02-22 | 16 | 0 | 16 | [20 empty] | 2021-02-23 | 2021-01-22 12:06 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EAST LONGMEADOW | 338188 | 1028 | 7.6 | Solar | 09_139L1 | 2021-01-22 12:06 | 2021-01-25 | 2 | 0 | 2 | 2021-01-28 | 2021-02-24 | 18 | 0 | 18 | [20 empty] | 2021-03-02 |  | 2022-09-14 | Yes | EXP |  | 2021-09-10 | 2021-10-12 | 22 | 0 | 22 |  |  | 2021-12-15 | Connected |  | Yes
National Grid | NORTH CHELMSFORD | 337901 | 1863 | 66.6 | Solar | 14_2L1 | 2021-01-22 12:39 | 2021-01-25 | 7 | 0 | 7 | 2021-02-04 | 2021-03-09 | 22 | 0 | 22 | [20 empty] | 2021-03-26 |  | 2022-04-03 |  | EXP | [8 empty] | 2022-03-22 | Connected |  | No
National Grid | NORTH ANDOVER | 338222 | 1845 | 11.52 | Solar | 14_54L3 | 2021-01-22 13:48 | 2021-01-25 | 4 | 4 | 0 | 2021-01-29 | 2021-02-24 | 17 | 0 | 17 | [20 empty] | 2021-02-24 |  | 2022-01-28 |  | EXP | [8 empty] | 2021-07-13 | Connected |  | No
National Grid | METHUEN | 335650 | 1844 | 7.6 | Solar | 14_63L1 | 2021-01-22 16:24 | 2021-01-25 | 31 | 31 | 0 | [26 empty] | 2021-01-22 17:04 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEICESTER | 336469 | 1524 | 10 | Solar | 01_21W2 | 2021-01-22 17:04 | 2021-01-25 | 2 | 0 | 2 | 2021-01-28 | 2021-02-24 | 18 | 0 | 18 | [20 empty] | 2021-03-02 |  | 2023-05-13 | Yes | EXP |  | 2022-02-22 | 2022-04-11 | 48 | 0 | 48 |  |  | 2022-05-20 | Connected |  | No
National Grid | FLORENCE | 338313 | 1062 | 7.6 | Solar | 09_909W1 | 2021-01-22 20:59 | 2021-01-25 | 0 | 0 | 0 | 2021-01-26 | 2021-02-17 | 15 | 0 | 15 | [20 empty] | 2021-02-18 | 2021-01-23 17:49 | 2022-03-17 |  | EXP | [8 empty] | 2021-09-27 | Connected |  | No
National Grid | RANDOLPH | 333373 | 2368 | 9.36 | Solar | 07_97W3 | 2021-01-23 17:49 | 2021-01-25 | 2 | 0 | 2 | 2021-01-28 | 2021-02-24 | 18 | 0 | 18 | [20 empty] | 2021-03-02 | 2021-01-25 17:44 | 2022-04-20 | Yes | EXP |  | 2022-03-03 | 2022-03-07 | 5 | 0 | 5 |  |  | 2022-03-15 | Connected |  | No
National Grid | WORCESTER | 336649 | 1603 | 7.6 | Solar | 01_6W2 | 2021-01-25 17:44 | 2021-01-26 | 1 | 0 | 1 | 2021-01-28 | 2021-02-25 | 19 | 0 | 19 | [20 empty] | 2021-02-26 | 2021-01-26 10:58 | 2022-01-26 |  | EXP |  | 2021-05-27 | 2021-05-28 | 1 | 0 | 1 |  |  | 2021-08-11 | Connected |  | No
National Grid | WEST BRIDGEWATER | 337504 | 2379 | 150 | Solar | 07_797W20 | 2021-01-26 10:58 | 2021-01-27 | 5 | 0 | 5 | 2021-02-04 | 2021-03-09 | 22 | 0 | 22 | 2021-04-12 | 2021-07-13 | 48 | 0 | 48 | [5 empty] | 2021-04-12 | 2021-07-13 | 48 | 0 | 48 | [5 empty] | 2021-07-06 |  | 2022-11-25 | Yes | EXP |  | 2022-02-05 | 2022-07-11 | 158 | 119 | 39 |  |  | 2022-12-06 | Connected |  | No
National Grid | LANCASTER | 338749 | 1523 | 7.6 | Solar | 01_225W1 | 2021-01-26 14:01 | 2021-01-27 | 2 | 0 | 2 | 2021-02-01 | 2021-02-24 | 16 | 0 | 16 | [20 empty] | 2021-02-25 |  | 2022-01-28 |  | EXP | [8 empty] | 2021-07-28 | Connected |  | No
National Grid | WINTHROP | 317386 | 2152 | 10 | Solar | 12_96W1 | 2021-01-27 10:54 | 2021-01-28 | 3 | 0 | 3 | 2021-02-03 | 2021-03-03 | 19 | 0 | 19 | [20 empty] | 2021-03-09 | 2021-01-27 12:19 | 2022-03-29 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EAST LONGMEADOW | 338971 | 1028 | 10 | Solar | 09_508L4 | 2021-01-27 12:19 | 2021-01-28 | 13 | 13 | 0 | 2021-02-18 | 2021-03-15 | 17 | 0 | 17 | [20 empty] | 2021-03-16 |  | 2022-11-24 | Yes | EXP |  | 2021-09-14 | 2021-11-22 | 70 | 4 | 66 |  |  | 2022-01-26 | Connected |  | No
National Grid | FRANKLIN | 339026 | 2038 | 9.8 | Solar | 05_344W1 | 2021-01-27 14:16 | 2021-01-28 | 4 | 3 | 1 | 2021-02-04 | 2021-02-26 | 15 | 0 | 15 | [20 empty] | 2021-02-26 |  | 2022-02-02 |  | EXP | [8 empty] | 2021-09-03 | Connected |  | No
National Grid | WILLIAMSTOWN | 339003 | 1267 | 10 | Solar | 09_1001W1 | 2021-01-27 14:23 | 2021-01-28 | 1 | 0 | 1 | 2021-02-01 | 2021-03-24 | 37 | 13 | 24 | [20 empty] | 2021-03-24 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 332855 | 2301 | 7.6 | Solar | 07_911W13 | 2021-01-27 16:23 | 2021-01-28 | 101 | 26 | 75 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GRAFTON | 339077 | 1519 | 7.6 | Solar | 01_304W1 | 2021-01-27 16:29 | 2021-01-28 | 0 | 0 | 0 | 2021-01-29 | 2021-02-24 | 17 | 0 | 17 | [20 empty] | 2021-02-24 |  | 2022-01-28 |  | EXP | [8 empty] | 2021-06-30 | Connected |  | No
National Grid | SOUTH HAMILTON | 333234 | 1982 | 7.6 | Solar | 12_51T2 | 2021-01-27 16:53 | 2021-01-28 | 3 | 0 | 3 | 2021-02-03 | 2021-03-02 | 18 | 0 | 18 | [20 empty] | 2021-03-09 |  | 2023-04-11 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GRAFTON | 339113 | 1519 | 9.8 | Solar | 01_304W1 | 2021-01-27 17:47 | 2021-01-28 | 0 | 0 | 0 | 2021-01-29 | 2021-02-24 | 17 | 0 | 17 | [20 empty] | 2021-02-25 |  |  |  | EXP | [8 empty] | 2021-06-12 | Connected |  | No
National Grid | UXBRIDGE | 313859 | 1569 | 800 | Solar | 05_321W1 | 2021-01-27 18:41 | 2021-01-28 | 16 | 11 | 5 | [10 empty] | 2021-02-22 | 2021-05-19 | 61 | 45 | 16 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | FOXBOROUGH | 337152 | 2035 | 250 | Solar | 05_3431W1 | 2021-01-28 12:35 | 2021-01-29 | 3 | 0 | 3 | [10 empty] | 2021-02-04 | 2021-03-11 | 24 | 0 | 24 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | COHASSET | 336643 | 2025 | 250 | Solar | 07_96W41 | 2021-01-28 12:37 | 2021-01-29 | 3 | 0 | 3 | 2021-02-04 | 2021-04-05 | 42 | 20 | 22 | [20 empty] | 2021-05-07 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | PEPPERELL | 334209 | 1463 | 17.6 | Solar | 01_226L2 | 2021-01-29 09:52 | 2021-02-01 | 12 | 12 | 0 | 2021-02-18 | 2021-03-15 | 17 | 0 | 17 | [20 empty] | 2021-03-15 |  | 2022-02-16 |  | EXP | [8 empty] | 2021-04-09 | Connected |  | No
National Grid | NORTH ANDOVER | 339459 | 1845 | 25 | Battery Add-On | 14_56L1 | 2021-01-29 11:24 | 2021-02-01 | 0 | 0 | 0 | 2021-02-02 | 2021-03-04 | 21 | 0 | 21 | [20 empty] | 2021-03-04 | 2021-01-29 11:56 | 2022-03-27 |  | EXP | [8 empty] | 2022-01-21 | Connected |  | No
National Grid | SUTTON | 339473 | 1590 | 3.8 | Solar | 01_304W5 | 2021-01-29 11:56 | 2021-02-01 | 38 | 37 | 1 | 2021-03-31 | 2021-04-20 | 13 | 0 | 13 | [20 empty] | 2021-04-26 |  | 2022-07-23 | Yes | EXP |  | 2021-06-12 | 2021-07-06 | 19 | 0 | 19 |  |  | 2022-07-08 | Connected |  | No
National Grid | WORCESTER | 325927 | 1603 | 7.68 | Solar | 01_6W2 | 2021-01-29 14:17 | 2021-02-01 | 5 | 5 | 0 | 2021-02-09 | 2021-03-15 | 24 | 5 | 19 | [20 empty] | 2021-03-15 |  | 2022-02-07 |  | EXP | [8 empty] | 2021-06-30 | Connected |  | No
National Grid | WRENTHAM | 339532 | 2093 | 7.6 | Solar | 05_348W5 | 2021-01-29 14:59 | 2021-02-01 | 1 | 0 | 1 | 2021-02-03 | 2021-02-26 | 16 | 0 | 16 | [20 empty] | 2021-03-09 |  |  |  | EXP | [8 empty] | 2021-09-03 | Connected |  | No
National Grid | SOUTH HAMILTON | 339578 | 1982 | 7.6 | Solar | 12_51L3 | 2021-01-29 17:34 | 2021-02-01 | 1 | 0 | 1 | 2021-02-03 | 2021-02-26 | 16 | 0 | 16 | [20 empty] | 2021-03-09 |  | 2022-11-23 |  | EXP | [8 empty] | 2021-12-29 | Connected |  | No
National Grid | DRACUT | 339584 | 1826 | 7.6 | Solar | 14_78L1 | 2021-01-29 18:18 | 2021-02-01 | 1 | 0 | 1 | 2021-02-03 | 2021-02-26 | 16 | 0 | 16 | [20 empty] | 2021-03-01 |  |  |  | EXP | [8 empty] | 2021-08-27 | Connected |  | No
National Grid | SEEKONK | 324466 | 2771 | 10 | Solar | 05_3J3 | 2021-01-31 16:23 | 2021-02-01 | 1 | 0 | 1 | 2021-02-03 | 2021-03-04 | 20 | 0 | 20 | [20 empty] | 2021-03-09 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BILLERICA | 339771 | 1821 | 11.4 | Solar | 14_70L5 | 2021-02-01 12:55 | 2021-02-02 | 85 | 80 | 5 | 2021-06-04 | 2021-07-08 | 24 | 0 | 24 | [20 empty] | 2021-07-28 |  | 2022-08-10 |  | EXP | [8 empty] | 2022-07-22 | Connected |  | Yes
National Grid | FRANKLIN | 339784 | 2038 | 10 | Solar | 05_344W1 | 2021-02-01 13:47 | 2021-02-02 | 2 | 0 | 2 | 2021-02-05 | 2021-03-09 | 21 | 0 | 21 | [20 empty] | 2021-03-24 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BILLERICA | 339861 | 1821 | 15.2 | Solar | 14_92L1 | 2021-02-01 16:06 | 2021-02-02 | 3 | 2 | 1 | 2021-02-05 | 2021-03-02 | 16 | 0 | 16 | [20 empty] | 2021-03-02 |  | 2022-04-04 |  | EXP | [8 empty] | 2021-09-13 | Connected |  | No
National Grid | AMESBURY | 339860 | 1913 | 10 | Solar | 14_275L4 | 2021-02-01 16:07 | 2021-02-02 | 1 | 0 | 1 | 2021-02-04 | 2021-03-02 | 17 | 0 | 17 | [20 empty] | 2021-03-03 | 2021-02-01 20:36 | 2022-02-02 |  | EXP | [8 empty] | 2021-04-15 | Connected |  | No
National Grid | BEVERLY | 337612 | 1915 | 8.4 | Solar | 12_51L2 | 2021-02-01 20:36 | 2021-02-02 | 2 | 0 | 2 | 2021-02-05 | 2021-04-09 | 44 | 26 | 18 | [20 empty] | 2021-04-15 | 2021-02-02 10:57 | 2022-09-14 | Yes | EXP |  | 2021-09-16 | 2021-10-12 | 16 | 0 | 16 |  |  | 2021-12-17 | Connected |  | No
National Grid | MILLBURY | 338606 | 1527 | 8.725 | Solar | 01_304W1 | 2021-02-02 10:57 | 2021-02-03 | 8 | 8 | 0 | 2021-02-16 | 2021-03-16 | 20 | 0 | 20 | [20 empty] | 2021-03-16 |  | 2022-07-19 | Yes | EXP |  | 2021-06-25 | 2021-07-15 | 21 | 0 | 21 |  |  | 2021-09-16 | Connected |  | No
National Grid | BROCKTON | 331606 | 2382 | 200 | Solar | 07_91W46 | 2021-02-02 11:29 | 2021-02-03 | 9 | 0 | 9 | [10 empty] | 2021-02-18 | 2021-03-24 | 24 | 0 | 24 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | GRAFTON | 322290 | 1519 | 7.6 | Solar | 01_304W2 | 2021-02-03 08:45 | 2021-02-04 | 35 | 34 | 1 | 2021-03-29 | 2021-04-21 | 16 | 0 | 16 | [20 empty] | 2021-05-04 | 2021-02-03 10:25 | 2022-03-25 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 301209 | 1843 | 10 | Solar | 14_1J9 | 2021-02-03 10:25 | 2021-02-04 | 2 | 0 | 2 | 2021-02-09 | 2021-03-10 | 20 | 0 | 20 | [20 empty] | 2021-03-18 | 2021-02-03 12:15 | 2022-03-29 | Yes | EXP |  | 2021-09-02 | 2022-01-27 | 148 | 4 | 144 |  |  | 2022-01-31 | Connected |  | Yes
National Grid | BILLERICA | 306207 | 1862 | 246.6 | Solar | 14_70L4 | 2021-02-03 12:15 | 2021-02-04 | 8 | 0 | 8 | [10 empty] | 2021-02-18 | 2021-03-23 | 23 | 0 | 23 | [10 empty] | 2024-02-13 | 2021-02-03 14:12 | 2025-07-16 | Yes | STD | [9 empty] | Construction |  | No
National Grid | BROCKTON | 306208 | 2301 | 166.6 | Solar | 07_911W25 | 2021-02-03 14:12 | 2021-02-04 | 8 | 0 | 8 | 2021-02-18 | 2021-03-23 | 23 | 0 | 23 | 2021-04-22 | 2021-05-10 | 12 | 0 | 12 | [5 empty] | 2021-04-22 | 2021-05-10 | 12 | 0 | 12 | [5 empty] | 2021-05-24 | 2021-02-03 14:13 | 2022-08-24 | Yes | EXP |  | 2021-10-22 | 2022-09-02 | 315 | 203 | 112 |  |  |  | Withdrawn |  | No
National Grid | ROYALSTON | 339524 | 1368 | 16 | Solar | 09_702W2 | 2021-02-03 14:13 | 2021-02-04 | 4 | 3 | 1 | 2021-02-11 | 2021-03-09 | 17 | 1 | 16 | [20 empty] | 2021-03-09 | 2021-02-03 15:16 | 2022-04-18 | Yes | EXP |  | 2021-04-07 | 2021-04-13 | 6 | 0 | 6 |  |  | 2022-02-23 | Connected |  | No
National Grid | SALEM | 326340 | 1970 | 8.7 | Solar | 12_2W1 | 2021-02-03 15:16 | 2021-02-04 | 2 | 0 | 2 | 2021-02-09 | 2021-03-04 | 16 | 0 | 16 | [20 empty] | 2021-03-09 |  | 2023-01-11 | Yes | EXP | [8 empty] | 2021-12-06 | Connected |  | No
National Grid | EVERETT | 340353 | 2149 | 7.6 | Solar | 12_16W2 | 2021-02-03 16:12 | 2021-02-04 | 5 | 3 | 2 | 2021-02-12 | 2021-03-11 | 18 | 0 | 18 | [20 empty] | 2021-03-26 |  | 2023-03-23 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | TEWKSBURY | 340366 | 1876 | 15.2 | Solar | 14_75L2 | 2021-02-03 17:00 | 2021-02-04 | 12 | 11 | 1 | 2021-02-23 | 2021-03-25 | 22 | 0 | 22 | [20 empty] | 2021-04-07 |  |  |  | EXP | [8 empty] | 2021-08-26 | Connected |  | No
National Grid | HAMPDEN | 340383 | 1036 | 15.36 | Solar | 09_139L1 | 2021-02-03 18:12 | 2021-02-04 | 1 | 0 | 1 | 2021-02-08 | 2021-03-08 | 19 | 0 | 19 | [20 empty] | 2021-03-08 |  | 2022-02-04 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | AMESBURY | 299817 | 1913 | 7.6 | Solar | 14_5J15 | 2021-02-04 08:56 | 2021-02-05 | 1 | 0 | 1 | 2021-02-09 | 2021-03-15 | 23 | 0 | 23 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTFORD | 340473 | 1886 | 7.6 | Solar | 14_57L3 | 2021-02-04 10:22 | 2021-02-05 | 0 | 0 | 0 | 2021-02-08 | 2021-03-02 | 15 | 0 | 15 | [20 empty] | 2021-03-02 | 2021-02-04 14:24 | 2022-06-16 |  | EXP | [8 empty] | 2021-10-08 | Connected |  | No
National Grid | SHIRLEY | 336841 | 1464 | 6 | Solar | 01_227W1 | 2021-02-04 14:24 | 2021-02-05 | 4 | 1 | 3 | 2021-02-12 | 2021-03-25 | 29 | 6 | 23 | [20 empty] | 2021-04-07 |  | 2022-05-01 | Yes | EXP |  | 2021-07-09 | 2021-10-05 | 74 | 3 | 71 |  |  |  | Withdrawn |  | Yes
National Grid | BRIDGEWATER | 340182 | 2324 | 260 | Solar | 07_797W1 | 2021-02-04 15:02 | 2021-02-05 | 7 | 0 | 7 | 2021-02-18 | 2021-03-23 | 23 | 0 | 23 | [20 empty] | 2021-04-06 |  | 2024-08-21 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | UXBRIDGE | 340617 | 1569 | 10 | Solar | 05_321W2 | 2021-02-04 17:13 | 2021-02-05 | 35 | 34 | 1 | 2021-03-29 | 2021-04-21 | 16 | 0 | 16 | [20 empty] | 2021-04-26 |  | 2022-03-25 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTFORD | 340624 | 1886 | 9.6 | Solar | 14_2L1 | 2021-02-04 18:12 | 2021-02-05 | 0 | 0 | 0 | 2021-02-08 | 2021-03-10 | 21 | 0 | 21 | [20 empty] | 2021-03-10 |  | 2022-02-04 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RANDOLPH | 337718 | 2368 | 4.08 | Solar | 07_97W2 | 2021-02-05 11:22 | 2021-02-08 | 54 | 53 | 1 | 2021-04-27 | 2021-05-27 | 22 | 0 | 22 | [20 empty] | 2021-05-28 |  | 2022-04-25 |  | EXP | [8 empty] | 2021-07-27 | Connected |  | No
National Grid | WARE | 339048 | 1082 | 5 | Solar | 09_501L2 | 2021-02-05 11:26 | 2021-02-08 | 48 | 48 | 0 | 2021-04-15 | 2021-05-19 | 23 | 0 | 23 | [20 empty] | 2021-05-21 | 2021-02-05 13:29 | 2022-04-14 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RANDOLPH | 336662 | 2368 | 10 | Solar | 07_97W1 | 2021-02-05 13:29 | 2021-02-08 | 5 | 5 | 0 | 2021-02-16 | 2021-03-11 | 17 | 0 | 17 | [20 empty] | 2021-03-11 |  | 2022-02-11 | Yes | EXP |  | 2021-04-17 | 2021-05-10 | 23 | 0 | 23 |  |  | 2021-05-12 | Connected |  | No
National Grid | STOUGHTON | 340789 | 2072 | 15.2 | Solar | 07_913W43 | 2021-02-05 13:54 | 2021-02-08 | 3 | 0 | 3 | 2021-02-12 | 2021-03-11 | 18 | 0 | 18 | [20 empty] | 2021-03-26 | 2021-02-05 16:02 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHERRY VALLEY | 340849 | 1611 | 15.2 | Solar | 01_7J386 | 2021-02-05 16:02 | 2021-02-08 | 3 | 0 | 3 | 2021-02-12 | 2021-03-11 | 18 | 0 | 18 | [20 empty] | 2021-05-10 | 2021-02-05 17:24 | 2023-01-20 | Yes | EXP |  | 2022-10-05 | 2022-11-14 | 41 | 0 | 41 |  |  | 2022-12-21 | Connected |  | No
National Grid | EAST BRIDGEWATER | 340873 | 2333 | 15.2 | Solar | 07_797W23 | 2021-02-05 17:24 | 2021-02-08 | 3 | 0 | 3 | 2021-02-12 | 2021-03-11 | 18 | 0 | 18 | [20 empty] | 2021-09-24 |  | 2023-08-09 | Yes | EXP |  | 2022-06-03 | 2022-06-28 | 25 | 0 | 25 |  |  | 2022-09-30 | Connected |  | No
National Grid | SEEKONK | 330889 | 2771 | 4946 | Solar | 05_7L5 | 2021-02-05 17:25 | 2021-02-08 | 26 | 21 | 5 | [10 empty] | 2021-03-17 | 2021-04-13 | 20 | 0 | 20 | [10 empty] | 2023-09-25 |  |  |  | STD | [9 empty] | Conditional Approval |  | No
National Grid | AUBURN | 339198 | 1501 | 9.8 | Solar | 01_26W2 | 2021-02-05 20:03 | 2021-02-08 | 3 | 0 | 3 | 2021-02-12 | 2021-03-11 | 18 | 0 | 18 | [20 empty] | 2021-03-26 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 332871 | 1843 | 7.6 | Solar | 14_8L1 | 2021-02-05 21:30 | 2021-02-08 | 3 | 0 | 3 | 2021-02-12 | 2021-03-11 | 18 | 0 | 18 | [20 empty] | 2021-03-26 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | UXBRIDGE | 340928 | 1569 | 9.36 | Solar | 05_321W6 | 2021-02-06 18:24 | 2021-02-08 | 33 | 32 | 1 | 2021-03-29 | 2021-04-16 | 13 | 0 | 13 | [20 empty] | 2021-04-16 |  | 2022-05-21 |  | EXP | [8 empty] | 2022-05-20 | Connected |  | No
National Grid | SOMERSET | 322573 | 2725 | 22.05 | Solar | 05_11W84 | 2021-02-08 14:46 | 2021-02-09 | 11 | 8 | 3 | 2021-02-26 | 2021-06-01 | 66 | 41 | 25 | [20 empty] | 2021-06-15 |  | 2022-09-03 |  | EXP | [8 empty] | 2021-12-13 | Connected |  | Yes
National Grid | COHASSET | 338336 | 2025 | 466.6 | Solar | 07_915W37 | 2021-02-08 17:32 | 2021-02-09 | 5 | 0 | 5 | 2021-02-18 | 2021-03-22 | 23 | 1 | 22 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BELLINGHAM | 299593 | 2019 | 3000 | Solar | 05_335W1 | 2021-02-08 20:57 | 2021-02-09 | 26 | 19 | 7 | [10 empty] | 2021-03-18 | 2021-04-13 | 18 | 0 | 18 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | WRENTHAM | 341243 | 2093 | 30 | Solar | 05_3422W2 | 2021-02-09 10:29 | 2021-02-10 | 0 | 0 | 0 | 2021-02-11 | 2021-03-12 | 20 | 0 | 20 | [20 empty] | 2021-03-12 |  | 2022-07-13 |  | EXP | [8 empty] | 2022-06-27 | Connected |  | No
National Grid | LEOMINSTER | 340774 | 1453 | 25.52 | Solar | 01_219W1 | 2021-02-09 12:26 | 2021-02-10 | 47 | 46 | 1 | 2021-04-20 | 2021-05-24 | 24 | 0 | 24 | [20 empty] | 2021-05-25 |  |  |  | EXP | [8 empty] | 2021-08-09 | Connected |  | No
National Grid | SPENCER | 341311 | 1562 | 13.8 | Solar | 01_21W1 | 2021-02-09 13:31 | 2021-02-10 | 17 | 14 | 3 | 2021-03-09 | 2021-04-08 | 22 | 0 | 22 | [20 empty] | 2021-04-22 |  | 2023-09-20 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEYMOUTH | 341344 | 2190 | 15.2 | Solar | 07_12W5 | 2021-02-09 14:38 | 2021-02-10 | 0 | 0 | 0 | 2021-02-11 | 2021-03-08 | 16 | 0 | 16 | [20 empty] | 2021-03-08 | 2021-02-09 14:43 | 2022-02-09 |  | EXP | [8 empty] | 2021-05-10 | Connected |  | No
National Grid | STOUGHTON | 337225 | 2072 | 250 | Solar | 07_913W69 | 2021-02-09 14:43 | 2021-02-10 | 4 | 0 | 4 | 2021-02-18 | 2021-03-23 | 23 | 0 | 23 | 2021-04-06 | 2021-09-21 | 117 | 82 | 35 | [5 empty] | 2021-04-06 | 2021-09-21 | 117 | 82 | 35 | [5 empty] | 2021-10-06 |  | 2024-02-22 | Yes | EXP |  | 2022-02-17 | 2023-08-03 | 533 | 493 | 40 |  |  | 2023-09-05 | Connected |  | No
National Grid | BROCKTON | 341380 | 2302 | 7.6 | Solar | 07_911W56 | 2021-02-09 16:17 | 2021-02-10 | 1 | 0 | 1 | 2021-02-12 | 2021-03-12 | 19 | 0 | 19 | [20 empty] | 2021-03-18 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTFORD | 341508 | 1886 | 9.6 | Solar | 14_57L2 | 2021-02-10 10:54 | 2021-02-11 | 2 | 0 | 2 | 2021-02-17 | 2021-03-11 | 16 | 0 | 16 | [20 empty] | 2021-03-26 |  | 2022-12-07 |  | EXP | [8 empty] | 2022-03-25 | Connected |  | No
National Grid | AYER | 341611 | 1432 | 7.6 | Solar | 01_201W2 | 2021-02-10 17:27 | 2021-02-11 | 0 | 0 | 0 | 2021-02-12 | 2021-03-08 | 15 | 0 | 15 | [20 empty] | 2021-03-08 |  | 2022-02-10 |  | EXP | [8 empty] | 2021-05-04 | Connected |  | No
National Grid | COHASSET | 341800 | 2025 | 11.4 | Solar | 07_96W41 | 2021-02-11 14:24 | 2021-02-12 | 2 | 0 | 2 | 2021-02-18 | 2021-03-17 | 19 | 0 | 19 | [20 empty] | 2021-03-29 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SCITUATE | 341765 | 2066 | 15.2 | Solar | 07_915W82 | 2021-02-11 16:03 | 2021-02-12 | 14 | 13 | 1 | 2021-03-08 | 2021-03-29 | 15 | 0 | 15 | [20 empty] | 2021-03-30 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEYMOUTH | 341855 | 2190 | 7.6 | Solar | 07_99W32 | 2021-02-11 16:30 | 2021-02-12 | 2 | 0 | 2 | 2021-02-18 | 2021-03-17 | 19 | 0 | 19 | [20 empty] | 2021-03-29 |  | 2022-12-08 |  | EXP | [8 empty] | 2021-12-24 | Connected |  | No
National Grid | REHOBOTH | 339999 | 2769 | 15.2 | Solar | 05_7L4 | 2021-02-11 17:26 | 2021-02-12 | 7 | 7 | 0 | 2021-02-24 | 2021-03-16 | 14 | 0 | 14 | [20 empty] | 2021-03-16 | 2021-02-11 17:31 | 2022-02-23 |  | EXP | [8 empty] | 2021-07-21 | Connected |  | No
National Grid | CHERRY VALLEY | 341888 | 1611 | 7.6 | Solar | 01_7J386 | 2021-02-11 17:31 | 2021-02-12 | 0 | 0 | 0 | 2021-02-16 | 2021-03-11 | 17 | 0 | 17 | [20 empty] | 2021-03-11 |  | 2023-07-21 | Yes | EXP |  | 2021-09-23 | 2022-01-17 | 117 | 4 | 113 |  |  | 2022-10-12 | Connected |  | No
National Grid | ESSEX | 341902 | 1929 | 15.2 | Solar | 12_51T2 | 2021-02-11 18:36 | 2021-02-12 | 0 | 0 | 0 | 2021-02-16 | 2021-03-15 | 19 | 0 | 19 | [20 empty] | 2021-03-16 | 2021-02-12 11:18 | 2022-11-29 |  | EXP | [8 empty] | 2021-12-29 | Connected |  | No
National Grid | CHELMSFORD | 341277 | 1824 | 180 | Solar | 14_24L3 | 2021-02-12 11:18 | 2021-02-16 | 13 | 2 | 11 | [10 empty] | 2021-03-05 | 2021-07-19 | 94 | 78 | 16 | [10 empty] | 2022-01-13 | 2021-02-12 11:22 | 2023-06-10 | Yes | STD | [8 empty] | 2023-05-31 | Connected |  | No
National Grid | CHELMSFORD | 341278 | 1824 | 166.6 | Solar | 14_24L3 | 2021-02-12 11:22 | 2021-02-16 | 13 | 2 | 11 | [10 empty] | 2021-03-05 | 2021-07-19 | 94 | 78 | 16 | [10 empty] | 2022-01-13 | 2021-02-12 12:21 | 2023-06-14 | Yes | STD | [8 empty] | 2023-05-31 | Connected |  | No
National Grid | REVERE | 341284 | 2151 | 5 | Solar | 12_16W4 | 2021-02-12 12:21 | 2021-02-16 | 1 | 0 | 1 | 2021-02-18 | 2021-03-23 | 23 | 1 | 22 | [20 empty] | 2021-03-31 |  | 2022-05-03 | Yes | EXP |  | 2021-06-16 | 2021-07-26 | 41 | 0 | 41 |  |  | 2022-01-13 | Connected |  | No
National Grid | REHOBOTH | 342021 | 2769 | 18 | Solar | 05_7L4 | 2021-02-12 13:49 | 2021-02-16 | 7 | 3 | 4 | 2021-02-26 | 2021-04-19 | 36 | 18 | 18 | [20 empty] | 2021-04-26 |  |  |  | EXP | [8 empty] | 2021-08-10 | Connected |  | No
National Grid | WILLIAMSTOWN | 268691 | 1267 | 10 | Battery Add-On | 09_1003W2 | 2021-02-12 13:55 | 2021-02-16 | 0 | 0 | 0 | 2021-02-16 | 2021-04-13 | 40 | 25 | 15 | [20 empty] | 2019-12-19 |  | 2022-08-01 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | AMESBURY | 339779 | 1913 | 133.2 | Solar | 14_5J14 | 2021-02-12 15:07 | 2021-02-16 | 12 | 3 | 9 | 2021-03-05 | 2021-04-08 | 24 | 0 | 24 | [21 empty] | 2021-02-12 15:50 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHELMSFORD | 341279 | 1824 | 133.2 | Solar | 14_24L3 | 2021-02-12 15:50 | 2021-02-16 | 13 | 2 | 11 | [10 empty] | 2021-03-05 | 2021-07-19 | 94 | 78 | 16 | [10 empty] | 2022-01-13 |  | 2023-07-31 | Yes | STD | [8 empty] | 2023-07-10 | Connected |  | No
National Grid | HAVERHILL | 340844 | 1830 | 1264 | Solar | 14_47L1 | 2021-02-12 16:09 | 2021-02-16 | 16 | 8 | 8 | [10 empty] | 2021-03-10 | 2021-03-29 | 14 | 4 | 10 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SOUTHBOROUGH | 342097 | 1772 | 3.84 | Solar | 05_314W2 | 2021-02-12 18:32 | 2021-02-16 | 0 | 0 | 0 | 2021-02-17 | 2021-03-11 | 16 | 0 | 16 | [20 empty] | 2021-03-11 |  | 2022-02-15 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEOMINSTER | 331470 | 1453 | 3.36 | Solar | 01_207W2 | 2021-02-13 13:52 | 2021-02-16 | 0 | 0 | 0 | 2021-02-17 | 2021-03-11 | 16 | 0 | 16 | [20 empty] | 2021-03-11 |  | 2022-02-15 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEST STOCKBRIDGE | 342184 | 1266 | 6.96 | Solar | 09_1109W3 | 2021-02-15 17:08 | 2021-02-16 | 0 | 0 | 0 | 2021-02-17 | 2021-03-11 | 16 | 0 | 16 | [20 empty] | 2021-03-11 | 2021-02-16 11:31 | 2022-02-15 |  | EXP | [8 empty] | 2021-06-03 | Connected |  | No
National Grid | NORWELL | 342336 | 2061 | 7.6 | Solar | 07_96W43 | 2021-02-16 11:31 | 2021-02-17 | 0 | 0 | 0 | 2021-02-18 | 2021-03-15 | 17 | 0 | 17 | [20 empty] | 2021-03-16 |  | 2023-01-09 | Yes | EXP |  | 2021-09-14 | 2021-10-11 | 28 | 0 | 28 |  |  | 2022-12-05 | Connected |  | No
National Grid | MENDON | 342414 | 1756 | 9.6 | Solar | 05_332W1 | 2021-02-16 15:09 | 2021-02-17 | 0 | 0 | 0 | 2021-02-18 | 2021-03-17 | 19 | 0 | 19 | [20 empty] | 2021-03-26 |  | 2022-04-04 |  | EXP | [8 empty] | 2021-12-13 | Connected |  | No
National Grid | WESTMINSTER | 342428 | 1473 | 9.6 | Solar | 01_602W2 | 2021-02-16 16:03 | 2021-02-17 | 0 | 0 | 0 | 2021-02-18 | 2021-03-11 | 15 | 0 | 15 | [20 empty] | 2021-03-11 |  | 2022-02-16 |  | EXP | [8 empty] | 2021-04-28 | Connected |  | No
National Grid | LEOMINSTER | 331301 | 1453 | 9.8 | Solar | 01_225W4 | 2021-02-16 19:58 | 2021-02-17 | 0 | 0 | 0 | 2021-02-18 | 2021-04-08 | 35 | 20 | 15 | [20 empty] | 2021-04-22 |  | 2022-05-04 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HARVARD | 342501 | 1451 | 48.72 | Battery Add-On | 01_225W1 | 2021-02-17 08:50 | 2021-02-18 | 32 | 26 | 6 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | MILFORD | 337021 | 1757 | 7.6 | Solar | 05_335W3 | 2021-02-17 11:16 | 2021-02-18 | 52 | 47 | 5 | 2021-05-05 | 2021-06-09 | 24 | 0 | 24 | [20 empty] | 2021-07-13 |  | 2022-10-03 |  | EXP | [8 empty] | 2021-12-06 | Connected |  | Yes
National Grid | BEVERLY | 342563 | 1915 | 7.68 | Solar | 12_51L3 | 2021-02-17 11:36 | 2021-02-18 | 4 | 4 | 0 | 2021-02-24 | 2021-03-16 | 14 | 0 | 14 | [20 empty] | 2021-03-16 |  | 2022-02-23 |  | EXP | [8 empty] | 2021-04-30 | Connected |  | No
National Grid | BROCKTON | 340045 | 2302 | 7.6 | Solar | 07_911W56 | 2021-02-17 17:34 | 2021-02-18 | 5 | 0 | 5 | 2021-02-26 | 2021-03-23 | 17 | 0 | 17 | [20 empty] | 2021-03-31 | 2021-02-17 18:59 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEOMINSTER | 335169 | 1453 | 5.76 | Solar | 01_225W4 | 2021-02-17 18:59 | 2021-02-18 | 24 | 24 | 0 | 2021-03-25 | 2021-04-13 | 13 | 0 | 13 | [20 empty] | 2021-04-13 |  | 2022-03-24 | Yes | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | REHOBOTH | 342835 | 2769 | 11.4 | Solar | 05_7L4 | 2021-02-18 13:20 | 2021-02-19 | 4 | 0 | 4 | 2021-02-26 | 2021-03-23 | 17 | 0 | 17 | [20 empty] | 2021-03-31 |  | 2022-11-10 |  | EXP | [8 empty] | 2021-12-13 | Connected |  | No
National Grid | MARLBOROUGH | 342922 | 1752 | 203.3 | Solar | 05_310W5 | 2021-02-18 17:44 | 2021-02-19 | 9 | 0 | 9 | [10 empty] | 2021-03-05 | 2021-04-26 | 36 | 11 | 25 | [10 empty] | 2022-01-31 | 2021-02-18 18:43 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MARLBOROUGH | 342944 | 1752 | 191.6 | Solar | 05_310W5 | 2021-02-18 18:43 | 2021-02-19 | 9 | 0 | 9 | [10 empty] | 2021-03-05 | 2021-04-26 | 35 | 11 | 24 | [10 empty] | 2021-12-22 |  | 2025-04-07 | Yes | STD | [9 empty] | Construction |  | No
National Grid | DIGHTON | 342952 | 2715 | 11.4 | Solar | 05_19W73 | 2021-02-18 20:00 | 2021-02-19 | 4 | 0 | 4 | 2021-02-26 | 2021-03-23 | 17 | 0 | 17 | [20 empty] | 2021-03-31 | 2021-02-18 21:11 |  |  | EXP | [8 empty] | 2021-08-06 | Connected |  | No
National Grid | ANDOVER | 342956 | 1810 | 11.4 | Solar | 14_61L3 | 2021-02-18 21:11 | 2021-02-19 | 0 | 0 | 0 | 2021-02-22 | 2021-03-16 | 16 | 0 | 16 | [20 empty] | 2021-03-16 |  | 2022-02-18 | Yes | EXP |  | 2021-05-26 | 2021-07-08 | 43 | 0 | 43 |  |  | 2021-08-13 | Connected |  | No
National Grid | NORTHAMPTON | 302123 | 1060 | 2000 | Solar | 09_901W1 | 2021-02-19 07:06 | 2021-02-22 | 27 | 18 | 9 | [10 empty] | 2021-03-31 | 2021-05-13 | 22 | 3 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | PEPPERELL | 342970 | 1463 | 11.4 | Solar | 01_210L1 | 2021-02-19 08:22 | 2021-02-22 | 12 | 12 | 0 | 2021-03-11 | 2021-04-08 | 20 | 0 | 20 | [20 empty] | 2021-04-20 | 2021-02-19 08:35 | 2023-01-10 |  | EXP | [8 empty] | 2022-02-08 | Connected |  | No
National Grid | STOUGHTON | 336550 | 2072 | 7.6 | Solar | 07_913W67 | 2021-02-19 08:35 | 2021-02-22 | 3 | 0 | 3 | 2021-02-26 | 2021-03-23 | 17 | 0 | 17 | [20 empty] | 2021-03-31 | 2021-02-19 10:06 | 2023-02-09 | Yes | EXP |  | 2021-11-25 | 2022-01-10 | 47 | 0 | 47 |  |  | 2022-04-14 | Connected |  | No
National Grid | MARLBOROUGH | 343005 | 1752 | 208.2 | Solar | 05_310W5 | 2021-02-19 10:06 | 2021-02-22 | 9 | 0 | 9 | [10 empty] | 2021-03-08 | 2021-04-26 | 34 | 11 | 23 | [10 empty] | 2022-01-31 |  | 2025-05-12 | Yes | STD | [9 empty] | Construction |  | No
National Grid | WORCESTER | 274538 | 1602 | 48 | Natural Gas | 01_6W2 | 2021-02-19 15:14 | 2021-02-22 | 9 | 0 | 9 | 2021-03-08 | 2021-04-12 | 25 | 1 | 24 | [20 empty] | 2021-04-15 |  | 2022-06-29 |  | EXP | [8 empty] | 2021-12-29 | Connected |  | No
National Grid | MILFORD | 340729 | 1757 | 466.6 | Solar | 05_336W4 | 2021-02-19 15:35 | 2021-02-22 | 9 | 0 | 9 | [10 empty] | 2021-03-08 | 2021-07-15 | 93 | 68 | 25 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | MILFORD | 340727 | 1757 | 466.6 | Solar | 05_336W4 | 2021-02-19 15:38 | 2021-02-22 | 9 | 0 | 9 | [10 empty] | 2021-03-08 | 2021-07-19 | 93 | 70 | 23 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | MILFORD | 343062 | 1757 | 233.2 | Solar | 05_336W4 | 2021-02-19 15:40 | 2021-02-22 | 9 | 0 | 9 | [10 empty] | 2021-03-08 | 2021-07-19 | 92 | 69 | 23 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | NORTHBOROUGH | 343155 | 1532 | 16.5 | Solar | 05_314W4 | 2021-02-19 18:35 | 2021-02-22 | 3 | 2 | 1 | 2021-02-25 | 2021-03-23 | 18 | 0 | 18 | [20 empty] | 2021-03-24 |  | 2022-02-24 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | STOCKBRIDGE | 343180 | 1262 | 7.6 | Solar | 09_1102W1 | 2021-02-21 10:17 | 2021-02-22 | 3 | 0 | 3 | 2021-02-26 | 2021-03-23 | 17 | 0 | 17 | [20 empty] | 2021-03-31 |  | 2022-09-01 |  | EXP | [8 empty] | 2022-02-09 | Connected |  | No
National Grid | CHELMSFORD | 343183 | 1824 | 9.6 | Solar | 14_24L2 | 2021-02-21 13:41 | 2021-02-22 | 0 | 0 | 0 | 2021-02-23 | 2021-03-16 | 15 | 0 | 15 | [20 empty] | 2021-03-16 |  | 2022-02-21 |  | EXP | [8 empty] | 2021-07-27 | Connected |  | No
National Grid | NORTHBOROUGH | 343188 | 1532 | 11.4 | Solar | 05_313W1 | 2021-02-21 17:32 | 2021-02-22 | 0 | 0 | 0 | 2021-02-23 | 2021-08-11 | 121 | 73 | 48 | [22 empty] | 2022-02-21 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | PEPPERELL | 343268 | 1463 | 10 | Solar | 01_226L2 | 2021-02-22 12:27 | 2021-02-23 | 5 | 0 | 5 | 2021-03-03 | 2021-03-31 | 20 | 0 | 20 | [20 empty] | 2021-04-08 |  | 2022-03-02 |  | EXP | [8 empty] | 2021-05-08 | Connected |  | No
National Grid | FALL RIVER | 337864 | 2723 | 7.6 | Solar | 05_106W82 | 2021-02-22 13:23 | 2021-02-23 | 5 | 0 | 5 | 2021-03-03 | 2021-04-08 | 26 | 7 | 19 | [20 empty] | 2021-04-30 |  |  |  | EXP | [8 empty] | 2021-08-28 | Connected |  | No
National Grid | SWANSEA | 315459 | 2777 | 998 | Solar | 05_11W81 | 2021-02-22 15:02 | 2021-02-23 | 48 | 39 | 9 | [10 empty] | 2021-05-17 | 2021-06-15 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | LEOMINSTER | 341966 | 1453 | 3.8 | Solar | 01_219W2 | 2021-02-22 15:29 | 2021-02-23 | 0 | 0 | 0 | 2021-02-24 | 2021-03-22 | 18 | 0 | 18 | [20 empty] | 2021-03-23 |  | 2022-02-22 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTHBOROUGH | 323644 | 1532 | 7.6 | Solar | 05_313W2 | 2021-02-23 17:09 | 2021-02-24 | 0 | 0 | 0 | 2021-02-25 | 2021-03-23 | 18 | 0 | 18 | [20 empty] | 2021-03-24 | 2021-02-24 11:51 | 2022-02-23 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 342738 | 1844 | 7.6 | Solar | 14_63L1 | 2021-02-24 11:51 | 2021-02-25 | 14 | 14 | 0 | 2021-03-17 | 2021-04-07 | 15 | 0 | 15 | [20 empty] | 2021-04-08 |  | 2022-09-17 | Yes | EXP |  | 2021-08-15 | 2021-09-01 | 16 | 3 | 13 |  |  | 2022-02-02 | Connected |  | No
National Grid | RANDOLPH | 342575 | 2368 | 7.6 | Solar | 07_97W1 | 2021-02-24 16:21 | 2021-02-25 | 3 | 0 | 3 | 2021-03-03 | 2021-03-31 | 20 | 0 | 20 | [20 empty] | 2021-04-13 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTBOROUGH | 343902 | 1581 | 7.6 | Solar | 05_312W1 | 2021-02-25 11:12 | 2021-02-26 | 0 | 0 | 0 | 2021-03-01 | 2021-03-23 | 16 | 0 | 16 | [20 empty] | 2021-03-24 | 2021-02-25 11:44 | 2023-02-03 |  | EXP | [8 empty] | 2022-05-20 | Connected |  | No
National Grid | WRENTHAM | 330982 | 2093 | 2738 | Solar | 05_3424W3 | 2021-02-25 11:44 | 2021-02-26 | 6 | 0 | 6 | [10 empty] | 2021-03-09 | 2021-04-06 | 20 | 0 | 20 | [10 empty] | 2022-01-07 |  | 2024-11-04 | Yes | STD | [9 empty] | Design |  | No
National Grid | BILLERICA | 343928 | 1821 | 19 | Solar | 14_70L6 | 2021-02-25 13:27 | 2021-02-26 | 35 | 26 | 9 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTMINSTER | 343989 | 1473 | 7.6 | Solar | 01_609W1 | 2021-02-25 16:17 | 2021-02-26 | 1 | 0 | 1 | 2021-03-02 | 2021-03-29 | 19 | 0 | 19 | [20 empty] | 2021-03-30 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BRIDGEWATER | 343875 | 2324 | 10 | Solar | 07_912W21 | 2021-02-25 16:47 | 2021-02-26 | 6 | 3 | 3 | 2021-03-09 | 2021-04-08 | 22 | 0 | 22 | [20 empty] | 2021-04-22 |  | 2022-02-25 |  | EXP | [8 empty] | 2021-06-17 | Connected |  | No
National Grid | MARLBOROUGH | 343536 | 1752 | 100 | Solar | 05_317W8 | 2021-02-26 10:27 | 2021-03-01 | 10 | 0 | 10 | 2021-03-16 | 2021-04-19 | 24 | 0 | 24 | [20 empty] | 2021-06-21 |  | 2022-07-25 |  | EXP | [8 empty] | 2022-05-18 | Connected |  | No
National Grid | BELLINGHAM | 343803 | 2019 | 18.6 | Solar | 05_344W4 | 2021-02-26 11:36 | 2021-03-01 | 1 | 1 | 0 | 2021-03-02 | 2021-03-25 | 17 | 0 | 17 | [20 empty] | 2021-03-25 |  | 2022-07-01 |  | EXP | [8 empty] | 2022-04-29 | Connected |  | No
National Grid | UXBRIDGE | 342437 | 1569 | 17.5 | Solar | 05_321W2 | 2021-02-26 11:37 | 2021-03-01 | 1 | 1 | 0 | 2021-03-02 | 2021-03-25 | 17 | 0 | 17 | [20 empty] | 2021-03-25 |  | 2022-05-08 |  | EXP | [8 empty] | 2022-04-01 | Connected |  | No
National Grid | WINTHROP | 329452 | 2152 | 7.6 | Solar | 12_96W1 | 2021-02-26 14:19 | 2021-03-01 | 5 | 0 | 5 | 2021-03-09 | 2021-04-08 | 22 | 0 | 22 | [20 empty] | 2021-04-22 | 2021-02-26 15:01 | 2022-05-04 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BRIDGEWATER | 342566 | 2324 | 9.8 | Solar | 07_912W74 | 2021-02-26 15:01 | 2021-03-01 | 5 | 0 | 5 | 2021-03-09 | 2021-03-29 | 14 | 0 | 14 | [20 empty] | 2021-04-06 |  | 2022-12-29 | Yes | EXP |  | 2022-03-09 | 2022-05-02 | 55 | 0 | 55 |  |  | 2022-11-17 | Connected |  | No
National Grid | EAST LONGMEADOW | 344217 | 1028 | 11.4 | Solar | 09_508L4 | 2021-02-26 16:41 | 2021-03-01 | 8 | 8 | 0 | 2021-03-12 | 2021-03-29 | 11 | 0 | 11 | [20 empty] | 2021-03-30 |  | 2022-07-17 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MARLBOROUGH | 333500 | 1752 | 52.2 | Solar | 05_310W5 | 2021-03-01 12:49 | 2021-03-02 | 9 | 0 | 9 | 2021-03-16 | 2021-04-16 | 23 | 0 | 23 | [20 empty] | 2021-05-18 |  | 2023-10-09 |  | EXP |  | 2021-08-19 | 2021-09-15 | 26 | 3 | 23 |  |  | 2023-08-24 | Connected |  | No
National Grid | ORANGE | 344387 | 1364 | 9.6 | Solar | 09_705W2 | 2021-03-01 15:36 | 2021-03-02 | 4 | 4 | 0 | 2021-03-09 | 2021-03-29 | 14 | 0 | 14 | [20 empty] | 2021-03-30 |  | 2022-10-28 |  | EXP | [8 empty] | 2022-10-26 | Connected |  | No
National Grid | GARDNER | 342936 | 1440 | 7.68 | Solar | 01_602W2 | 2021-03-02 09:48 | 2021-03-03 | 4 | 4 | 0 | 2021-03-09 | 2021-03-29 | 14 | 0 | 14 | [20 empty] | 2021-03-29 |  | 2022-04-03 |  | EXP | [8 empty] | 2021-09-15 | Connected |  | Yes
National Grid | LYNN | 342995 | 1905 | 7.6 | Solar | 12_6J2 | 2021-03-02 16:00 | 2021-03-03 | 61 | 47 | 14 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SCITUATE | 344708 | 2066 | 7.68 | Solar | 07_915W82 | 2021-03-02 16:43 | 2021-03-03 | 3 | 0 | 3 | 2021-03-09 | 2021-04-08 | 22 | 0 | 22 | [20 empty] | 2021-04-22 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HANOVER | 344715 | 2339 | 9.6 | Solar | 07_95W5 | 2021-03-02 17:04 | 2021-03-03 | 3 | 0 | 3 | 2021-03-09 | 2021-03-29 | 14 | 0 | 14 | [20 empty] | 2021-04-06 |  | 2022-08-03 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHELMSFORD | 344721 | 1824 | 11.4 | Solar | 14_24L2 | 2021-03-02 18:51 | 2021-03-03 | 0 | 0 | 0 | 2021-03-04 | 2021-03-26 | 16 | 0 | 16 | [20 empty] | 2021-03-26 |  | 2022-03-02 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTFORD | 344742 | 1886 | 15.2 | Solar | 14_58L1 | 2021-03-02 21:22 | 2021-03-03 | 0 | 0 | 0 | 2021-03-04 | 2021-03-26 | 16 | 0 | 16 | [20 empty] | 2021-03-26 |  | 2022-03-02 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORWELL | 344801 | 2061 | 15.2 | Solar | 07_96W43 | 2021-03-03 09:33 | 2021-03-04 | 3 | 0 | 3 | 2021-03-10 | 2021-03-29 | 13 | 0 | 13 | [20 empty] | 2021-04-06 |  |  |  | EXP | [8 empty] | 2021-06-11 | Connected |  | No
National Grid | WESTBOROUGH | 299813 | 1581 | 10 | Solar | 05_312W1 | 2021-03-03 11:08 | 2021-03-04 | 0 | 0 | 0 | 2021-03-04 | 2021-03-03 | 0 | 0 | 0 | [20 empty] | 2020-07-08 |  | 2021-07-08 |  | EXP | [8 empty] | 2021-03-10 | Connected |  | No
National Grid | NEWBURY | 344862 | 1951 | 7.6 | Solar | 14_60L1 | 2021-03-03 11:59 | 2021-03-04 | 0 | 0 | 0 | 2021-03-05 | 2021-03-29 | 16 | 0 | 16 | [20 empty] | 2021-03-29 | 2021-03-04 08:52 | 2022-12-07 |  | EXP | [8 empty] | 2022-07-29 | Connected |  | No
National Grid | BRADFORD | 342609 | 1835 | 5 | Solar | 14_43L3 | 2021-03-04 08:52 | 2021-03-05 | 2 | 0 | 2 | 2021-03-10 | 2021-03-29 | 13 | 0 | 13 | [20 empty] | 2021-04-06 | 2021-03-04 09:15 | 2022-10-05 | Yes | EXP |  | 2021-09-11 | 2021-09-21 | 6 | 0 | 6 |  |  | 2021-09-29 | Connected |  | No
National Grid | SOMERSET | 341066 | 2726 | 10 | Solar | 05_19W72 | 2021-03-04 09:15 | 2021-03-05 | 4 | 1 | 3 | 2021-03-11 | 2021-04-13 | 23 | 6 | 17 | [20 empty] | 2021-04-26 |  |  |  | EXP |  | 2021-06-04 | 2021-06-03 | 0 | 0 | 0 |  |  | 2021-07-28 | Connected |  | No
National Grid | NORTH EGREMONT | 344660 | 1252 | 10 | Solar | 09_1109W3 | 2021-03-04 13:28 | 2021-03-05 | 12 | 12 | 0 | 2021-03-23 | 2021-04-14 | 16 | 0 | 16 | [20 empty] | 2021-04-14 | 2021-03-04 21:10 | 2022-06-22 |  | EXP | [8 empty] | 2022-05-11 | Connected |  | No
National Grid | UPTON | 345013 | 1568 | 15.12 | Solar | 05_335W3 | 2021-03-04 21:10 | 2021-03-08 | 1 | 1 | 0 | 2021-03-09 | 2021-04-06 | 20 | 6 | 14 | [20 empty] | 2021-04-06 |  | 2022-03-08 | Yes | EXP |  | 2021-04-22 | 2021-05-26 | 34 | 0 | 34 |  |  | 2021-05-28 | Connected |  | Yes
National Grid | NORTH ADAMS | 339952 | 1247 | 7.6 | Solar | 09_1015W2 | 2021-03-05 12:04 | 2021-03-08 | 2 | 0 | 2 | 2021-03-11 | 2021-04-06 | 18 | 0 | 18 | [20 empty] | 2021-04-14 | 2021-03-05 13:04 | 2022-04-23 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HARVARD | 338763 | 1451 | 7.6 | Solar | 01_225W1 | 2021-03-05 13:04 | 2021-03-08 | 0 | 0 | 0 | 2021-03-09 | 2021-03-29 | 14 | 0 | 14 | [20 empty] | 2021-03-30 | 2021-03-05 14:18 | 2022-03-07 | Yes | EXP |  | 2021-06-17 | 2021-08-17 | 61 | 0 | 61 |  |  | 2021-08-25 | Connected |  | No
National Grid | BROOKFIELD | 343332 | 1506 | 9.8 | Solar | 01_525L2 | 2021-03-05 14:18 | 2021-03-08 | 6 | 4 | 2 | 2021-03-17 | 2021-04-14 | 20 | 0 | 20 | [20 empty] | 2021-06-15 |  | 2022-06-20 | Yes | EXP |  | 2021-08-10 | 2021-09-03 | 23 | 3 | 20 |  |  | 2021-11-05 | Connected |  | No
National Grid | REHOBOTH | 342714 | 2769 | 7.6 | Solar | 05_7L5 | 2021-03-08 09:51 | 2021-03-09 | 27 | 27 | 0 | 2021-04-15 | 2021-05-19 | 23 | 0 | 23 | [20 empty] | 2021-05-21 |  | 2022-05-29 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTHAMPTON | 343658 | 1060 | 7.6 | Solar | 09_905W1 | 2021-03-08 10:35 | 2021-03-09 | 31 | 26 | 5 | 2021-04-23 | 2021-04-22 | 0 | 0 | 0 | [22 empty] | 2022-04-22 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | ABINGTON | 345576 | 2351 | 9.6 | Solar | 07_99W62 | 2021-03-08 10:45 | 2021-03-09 | 1 | 0 | 1 | 2021-03-11 | 2021-03-22 | 7 | 0 | 7 | [20 empty] | 2021-03-23 |  | 2022-11-09 |  | EXP | [8 empty] | 2021-09-14 | Connected |  | No
National Grid | WILLIAMSBURG | 345682 | 1039 | 49.08 | Solar | 09_909W3 | 2021-03-08 14:07 | 2021-03-09 | 4 | 0 | 4 | [10 empty] | 2021-03-16 | 2021-04-19 | 24 | 0 | 24 | [10 empty] | 2022-01-14 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | REVERE | 333059 | 2151 | 7.6 | Solar | 12_7J6 | 2021-03-08 16:31 | 2021-03-09 | 1 | 0 | 1 | 2021-03-11 | 2021-04-08 | 20 | 0 | 20 | [20 empty] | 2021-04-22 |  | 2022-09-05 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 342713 | 2302 | 7.6 | Solar | 07_911W56 | 2021-03-09 14:43 | 2021-03-10 | 4 | 0 | 4 | 2021-03-17 | 2021-04-14 | 20 | 0 | 20 | [20 empty] | 2021-04-28 | 2021-03-09 17:08 | 2022-05-10 |  | EXP | [8 empty] | 2021-11-24 | Connected |  | No
National Grid | WILBRAHAM | 345735 | 1095 | 180 | Solar | 09_523L1 | 2021-03-09 17:08 | 2021-03-10 | 10 | 0 | 10 | [10 empty] | 2021-03-24 | 2021-06-15 | 58 | 32 | 26 | [10 empty] | 2022-05-02 | 2021-03-09 17:11 |  | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | WILBRAHAM | 345736 | 1095 | 233.3 | Solar | 09_523L1 | 2021-03-09 17:11 | 2021-03-10 | 10 | 0 | 10 | [10 empty] | 2021-03-24 | 2021-06-15 | 58 | 32 | 26 | [10 empty] | 2022-05-02 | 2021-03-09 17:13 |  | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | WILBRAHAM | 345769 | 1095 | 103.3 | Solar | 09_523L1 | 2021-03-09 17:13 | 2021-03-10 | 10 | 0 | 10 | [10 empty] | 2021-03-24 | 2021-06-15 | 58 | 32 | 26 | [10 empty] | 2022-05-02 | 2021-03-09 17:14 |  | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | WILBRAHAM | 345775 | 1095 | 150 | Solar | 09_523L1 | 2021-03-09 17:14 | 2021-03-10 | 10 | 0 | 10 | [10 empty] | 2021-03-24 | 2021-06-15 | 58 | 32 | 26 | [10 empty] | 2022-05-02 | 2021-03-09 17:16 |  | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | WILBRAHAM | 345778 | 1095 | 130 | Solar | 09_523L1 | 2021-03-09 17:16 | 2021-03-10 | 10 | 0 | 10 | [10 empty] | 2021-03-24 | 2021-06-15 | 58 | 32 | 26 | [10 empty] | 2022-04-29 |  |  | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | WILBRAHAM | 345779 | 1095 | 140 | Solar | 09_507L3 | 2021-03-09 17:17 | 2021-03-10 | 9 | 0 | 9 | 2021-03-24 | 2021-06-08 | 53 | 28 | 25 | [20 empty] | 2021-06-21 |  | 2023-09-22 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | EAST LONGMEADOW | 345986 | 1028 | 7.68 | Solar | 09_508L5 | 2021-03-09 19:23 | 2021-03-10 | 7 | 7 | 0 | 2021-03-19 | 2021-04-13 | 17 | 4 | 13 | [20 empty] | 2021-04-13 |  | 2022-03-18 |  | EXP | [8 empty] | 2021-07-08 | Connected |  | No
National Grid | SPENCER | 346050 | 1562 | 11.4 | Solar | 01_552L1 | 2021-03-10 09:16 | 2021-03-11 | 3 | 0 | 3 | 2021-03-17 | 2021-04-07 | 15 | 0 | 15 | [20 empty] | 2021-04-14 |  | 2022-07-07 |  | EXP | [8 empty] | 2021-11-03 | Connected |  | No
National Grid | GREAT BARRINGTON | 346175 | 1230 | 9.6 | Solar | 09_1109W2 | 2021-03-10 14:38 | 2021-03-11 | 2 | 2 | 0 | 2021-03-16 | 2021-04-05 | 14 | 0 | 14 | [20 empty] | 2021-04-06 |  | 2022-03-15 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SAUGUS | 346151 | 1906 | 19.893 | Solar | 12_16W1 | 2021-03-10 14:46 | 2021-03-11 | 4 | 4 | 0 | 2021-03-18 | 2021-04-07 | 14 | 0 | 14 | [20 empty] | 2021-04-08 | 2021-03-11 10:48 | 2022-03-16 |  | EXP | [8 empty] | 2021-08-17 | Connected |  | No
National Grid | FRANKLIN | 346314 | 2038 | 240 | Solar | 05_344W3 | 2021-03-11 10:48 | 2021-03-12 | 9 | 0 | 9 | 2021-03-26 | 2021-04-30 | 25 | 0 | 25 | [20 empty] | 2021-05-12 | 2021-03-11 11:18 | 2024-01-12 | Yes | EXP |  | 2023-08-26 | 2023-12-15 | 112 | 22 | 90 |  |  | 2023-12-29 | Connected |  | No
National Grid | HARVARD | 340547 | 1451 | 10 | Solar | 01_225W1 | 2021-03-11 11:18 | 2021-03-12 | 13 | 11 | 2 | 2021-04-01 | 2021-04-22 | 14 | 0 | 14 | [20 empty] | 2021-04-29 |  | 2022-12-08 | Yes | EXP |  | 2021-08-10 | 2021-10-08 | 57 | 3 | 54 |  |  | 2021-12-01 | Connected |  | No
National Grid | HANSON | 346398 | 2341 | 17.76 | Solar | 07_95W2 | 2021-03-11 13:45 | 2021-03-12 | 18 | 18 | 0 | 2021-04-08 | 2021-05-12 | 23 | 0 | 23 | [20 empty] | 2021-05-14 | 2021-03-12 11:12 | 2022-04-06 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | AUBURN | 338558 | 1501 | 7.6 | Solar | 01_26W1 | 2021-03-12 11:12 | 2021-03-15 | 0 | 0 | 0 | 2021-03-16 | 2021-04-06 | 15 | 0 | 15 | [20 empty] | 2021-04-06 | 2021-03-12 12:10 | 2023-01-20 | Yes | EXP |  | 2021-12-15 | 2022-01-19 | 36 | 0 | 36 |  |  | 2022-01-25 | Connected |  | No
National Grid | TYNGSBOROUGH | 343831 | 1879 | 25 | Solar | 14_211L1 | 2021-03-12 12:10 | 2021-03-15 | 0 | 0 | 0 | 2021-03-16 | 2021-04-14 | 21 | 0 | 21 | [20 empty] | 2021-06-10 |  | 2022-09-01 | Yes | EXP |  | 2021-08-04 | 2021-08-31 | 26 | 3 | 23 |  |  | 2022-03-14 | Connected |  | No
National Grid | LEOMINSTER | 337622 | 1453 | 9.57 | Solar | 01_225W3 | 2021-03-12 17:53 | 2021-03-15 | 3 | 0 | 3 | 2021-03-19 | 2021-04-19 | 21 | 0 | 21 | [20 empty] | 2021-04-30 |  | 2022-09-27 |  | EXP | [8 empty] | 2021-12-06 | Connected |  | No
National Grid | NORTH CHELMSFORD | 346687 | 1863 | 11.31 | Solar | 14_2L1 | 2021-03-12 21:53 | 2021-03-15 | 27 | 25 | 2 | 2021-04-23 | 2021-05-27 | 25 | 0 | 25 | [20 empty] | 2021-06-01 | 2021-03-16 12:51 | 2022-04-21 |  | EXP | [8 empty] | 2021-07-07 | Connected |  | No
National Grid | OXFORD | 343654 | 1540 | 7.6 | Solar | 01_406L3 | 2021-03-16 12:51 | 2021-03-17 | 0 | 0 | 0 | 2021-03-18 | 2021-04-07 | 14 | 0 | 14 | [20 empty] | 2021-04-08 |  | 2022-12-08 | Yes | EXP |  | 2021-07-24 | 2021-12-08 | 138 | 7 | 131 |  |  | 2022-01-04 | Connected |  | No
National Grid | SEEKONK | 327570 | 2771 | 11.4 | Solar | 05_3J3 | 2021-03-16 12:54 | 2021-03-17 | 21 | 21 | 0 | 2021-04-15 | 2021-05-19 | 23 | 0 | 23 | [20 empty] | 2021-05-19 |  | 2022-10-28 |  | EXP | [8 empty] | 2022-09-26 | Connected |  | No
National Grid | MALDEN | 343246 | 2148 | 10 | Solar | 12_16W6 | 2021-03-16 14:58 | 2021-03-17 | 11 | 6 | 5 | 2021-04-02 | 2021-04-23 | 14 | 0 | 14 | [20 empty] | 2021-04-29 |  |  |  | EXP | [8 empty] | 2021-06-22 | Connected |  | No
National Grid | WORCESTER | 336435 | 1603 | 10 | Solar | 01_6W2 | 2021-03-17 09:40 | 2021-03-18 | 4 | 0 | 4 | 2021-03-25 | 2021-04-21 | 18 | 0 | 18 | [20 empty] | 2021-05-03 | 2021-03-17 12:16 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH ANDOVER | 347328 | 1845 | 20 | Solar | 14_56L2 | 2021-03-17 12:16 | 2021-03-18 | 0 | 0 | 0 | 2021-03-19 | 2021-04-07 | 13 | 0 | 13 | [20 empty] | 2021-04-08 | 2021-03-18 12:16 | 2022-03-17 |  | EXP |  | 2021-05-26 | 2021-07-13 | 48 | 0 | 48 |  |  | 2021-07-30 | Connected |  | No
National Grid | HUBBARDSTON | 346682 | 1452 | 22.8 | Solar | 01_602W2 | 2021-03-18 12:16 | 2021-03-19 | 10 | 10 | 0 | 2021-04-02 | 2021-04-22 | 13 | 0 | 13 | [20 empty] | 2021-04-26 | 2021-03-19 08:22 | 2022-04-01 | Yes | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 333806 | 2302 | 6.72 | Solar | 07_911W56 | 2021-03-19 08:22 | 2021-03-22 | 0 | 0 | 0 | 2021-03-23 | 2021-04-19 | 19 | 0 | 19 | [20 empty] | 2021-04-26 |  | 2023-01-23 |  | EXP |  | 2021-06-10 | 2021-06-12 | 3 | 0 | 3 |  |  | 2022-07-08 | Connected |  | No
National Grid | PALMER | 342869 | 1069 | 10 | Solar | 09_503L1 | 2021-03-19 08:35 | 2021-03-22 | 4 | 1 | 3 | 2021-03-29 | 2021-04-22 | 17 | 0 | 17 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BEVERLY | 333031 | 1915 | 100 | Solar | 12_51L1 | 2021-03-19 09:42 | 2021-03-22 | 11 | 0 | 11 | 2021-04-06 | 2021-10-08 | 129 | 106 | 23 | [20 empty] | 2021-11-09 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MARLBOROUGH | 347804 | 1752 | 216 | Solar | 05_317W6 | 2021-03-19 13:17 | 2021-03-22 | 9 | 0 | 9 | 2021-04-06 | 2021-05-11 | 24 | 0 | 24 | [20 empty] | 2021-05-24 |  | 2022-06-22 |  | EXP | [8 empty] | 2021-12-30 | Connected |  | No
National Grid | MILFORD | 341876 | 1757 | 7.6 | Solar | 05_335W5 | 2021-03-19 13:23 | 2021-03-22 | 2 | 0 | 2 | 2021-03-25 | 2021-04-21 | 18 | 0 | 18 | [20 empty] | 2021-05-04 | 2021-03-19 13:40 | 2021-06-30 |  | EXP | [8 empty] | 2021-06-17 | Connected |  | No
National Grid | EVERETT | 345364 | 2149 | 3.8 | Solar | 12_16W7 | 2021-03-19 13:40 | 2021-03-22 | 6 | 6 | 0 | 2021-03-30 | 2021-04-21 | 15 | 0 | 15 | [20 empty] | 2021-04-26 |  | 2022-07-30 | Yes | EXP |  | 2021-06-05 | 2021-06-18 | 14 | 0 | 14 |  |  | 2021-09-16 | Connected |  | No
National Grid | DUDLEY | 346007 | 1571 | 7.6 | Solar | 01_412L5 | 2021-03-19 14:13 | 2021-03-22 | 0 | 0 | 0 | 2021-03-23 | 2021-03-24 | 1 | 0 | 1 | [22 empty] | 2022-03-21 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SALEM | 345717 | 1970 | 32.4 | Solar | 12_1J7 | 2021-03-22 11:48 | 2021-03-23 | 9 | 0 | 9 | 2021-04-06 | 2021-05-11 | 24 | 0 | 24 | [20 empty] | 2021-05-24 |  | 2022-06-01 |  | EXP | [8 empty] | 2021-10-18 | Connected |  | No
National Grid | MARLBOROUGH | 333111 | 1752 | 5.76 | Solar | 05_311W3 | 2021-03-22 13:41 | 2021-03-23 | 1 | 1 | 0 | 2021-03-25 | 2021-04-14 | 14 | 0 | 14 | [20 empty] | 2021-04-15 |  | 2022-04-19 |  | EXP | [8 empty] | 2021-09-15 | Connected |  | No
National Grid | NORTH ANDOVER | 348152 | 1845 | 7.25 | Solar | 14_55L2 | 2021-03-22 16:50 | 2021-03-23 | 3 | 3 | 0 | 2021-03-26 | 2021-04-15 | 14 | 0 | 14 | [20 empty] | 2021-04-16 |  | 2022-03-24 |  | EXP | [8 empty] | 2021-07-14 | Connected |  | No
National Grid | WEYMOUTH | 348213 | 2190 | 17.68 | Battery Add-On | 07_2W2 | 2021-03-22 21:37 | 2021-03-23 | 1 | 0 | 1 | 2021-03-25 | 2021-04-21 | 18 | 0 | 18 | [20 empty] | 2021-05-04 |  | 2023-06-21 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | DIGHTON | 342591 | 2715 | 499 | Solar | 05_19W73 | 2021-03-22 23:26 | 2021-03-23 | 22 | 12 | 10 | [10 empty] | 2021-04-23 | 2021-06-23 | 43 | 19 | 24 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BRIDGEWATER | 348228 | 2324 | 15.2 | Solar | 07_912W55 | 2021-03-23 07:51 | 2021-03-24 | 0 | 0 | 0 | 2021-03-25 | 2021-04-15 | 15 | 0 | 15 | [20 empty] | 2021-04-15 | 2021-03-23 16:19 | 2022-08-05 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BELCHERTOWN | 348410 | 1007 | 9.6 | Solar | 09_509L1 | 2021-03-23 16:19 | 2021-03-24 | 0 | 0 | 0 | 2021-03-25 | 2021-04-19 | 17 | 0 | 17 | [20 empty] | 2021-04-26 |  | 2022-03-23 | Yes | EXP |  | 2021-07-17 | 2021-08-06 | 21 | 0 | 21 |  |  | 2021-08-10 | Connected |  | No
National Grid | HANSON | 348533 | 2341 | 157.52 | Solar | 07_95W2 | 2021-03-24 10:43 | 2021-03-25 | 70 | 60 | 10 | 2021-07-06 | 2021-08-02 | 20 | 0 | 20 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | BLACKSTONE | 344703 | 1504 | 6.72 | Solar | 05_108W60 | 2021-03-24 13:12 | 2021-03-25 | 6 | 6 | 0 | 2021-04-05 | 2021-05-09 | 23 | 0 | 23 | [20 empty] | 2021-05-10 |  | 2022-04-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTBOROUGH | 348940 | 1581 | 100 | Solar | 05_314W1 | 2021-03-25 16:48 | 2021-03-26 | 25 | 16 | 9 | 2021-05-11 | 2021-07-07 | 40 | 15 | 25 | [20 empty] | 2021-07-14 |  | 2022-07-19 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTBOROUGH | 348897 | 1581 | 150 | Solar | 05_314W1 | 2021-03-25 16:49 | 2021-03-26 | 25 | 16 | 9 | 2021-05-03 | 2021-07-07 | 46 | 8 | 38 | 2021-07-21 | 2022-01-11 | 120 | 7 | 113 | [5 empty] | 2021-07-21 | 2022-01-11 | 120 | 7 | 113 | [5 empty] | 2022-01-12 | 2021-03-26 07:13 | 2023-03-14 |  | EXP |  | 2023-01-10 | 2023-01-10 | 1 | 0 | 1 |  |  | 2023-04-05 | Connected |  | No
National Grid | WESTFORD | 349109 | 1886 | 150 | Solar | 14_12J1 | 2021-03-26 07:13 | 2021-03-29 | 11 | 2 | 9 | 2021-06-16 | 2021-11-19 | 109 | 84 | 25 | [20 empty] | 2021-12-13 |  | 2022-07-12 | Yes | EXP |  | 2022-03-13 | 2022-04-07 | 26 | 0 | 26 |  |  | 2022-05-26 | Connected |  | No
National Grid | HARVARD | 348883 | 1451 | 7.68 | Solar | 01_201W2 | 2021-03-26 08:56 | 2021-03-29 | 0 | 0 | 0 | 2021-03-30 | 2021-04-22 | 16 | 0 | 16 | [20 empty] | 2021-05-04 |  |  |  | EXP | [8 empty] | 2021-06-24 | Connected |  | No
National Grid | MARLBOROUGH | 348992 | 1752 | 100 | Solar | 05_317W6 | 2021-03-26 09:32 | 2021-03-29 | 24 | 15 | 9 | 2021-05-04 | 2021-06-08 | 24 | 0 | 24 | [20 empty] | 2021-06-21 |  | 2022-06-26 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 340566 | 1844 | 6 | Solar | 14_74L1 | 2021-03-26 12:04 | 2021-03-29 | 2 | 0 | 2 | 2021-04-01 | 2021-04-22 | 14 | 0 | 14 | [20 empty] | 2021-04-29 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ATHOL | 348650 | 1331 | 7.68 | Solar | 09_702W3 | 2021-03-26 12:05 | 2021-03-29 | 4 | 3 | 1 | 2021-04-05 | 2021-05-09 | 24 | 0 | 24 | [20 empty] | 2021-05-10 |  | 2022-04-01 |  | EXP | [8 empty] | 2021-07-16 | Connected |  | No
National Grid | NANTUCKET | 349242 | 2554 | 19.72 | Solar | 04_101L2 | 2021-03-26 12:49 | 2021-03-29 | 14 | 14 | 0 | 2021-04-20 | 2021-05-24 | 24 | 0 | 24 | [20 empty] | 2021-06-07 | 2021-03-26 13:24 |  |  | EXP | [8 empty] | 2021-08-31 | Connected |  | No
National Grid | BOXFORD | 347094 | 1921 | 9.966 | Solar | 14_56L3 | 2021-03-26 13:24 | 2021-03-29 | 10 | 10 | 0 | 2021-04-12 | 2021-05-17 | 24 | 0 | 24 | [20 empty] | 2021-05-19 | 2021-03-26 16:12 | 2022-08-17 |  | EXP |  | 2021-08-04 | 2021-08-12 | 9 | 0 | 9 |  |  | 2021-11-03 | Connected |  | No
National Grid | METHUEN | 346362 | 1844 | 7.6 | Solar | 14_74L1 | 2021-03-26 16:12 | 2021-03-29 | 2 | 0 | 2 | 2021-04-01 | 2021-04-22 | 14 | 0 | 14 | [20 empty] | 2021-04-29 |  | 2022-10-19 | Yes | EXP |  | 2021-09-29 | 2021-10-29 | 31 | 4 | 27 |  |  | 2021-11-30 | Connected |  | Yes
National Grid | EAST LONGMEADOW | 344559 | 1028 | 6.93 | Solar | 09_139L5 | 2021-03-26 16:17 | 2021-03-29 | 7 | 7 | 0 | 2021-04-07 | 2021-05-12 | 24 | 0 | 24 | [20 empty] | 2021-05-12 |  | 2022-04-05 |  | EXP | [8 empty] | 2021-08-13 | Connected |  | No
National Grid | SAUGUS | 340811 | 1906 | 9.8 | Solar | 12_13J2 | 2021-03-26 18:34 | 2021-03-29 | 2 | 0 | 2 | 2021-04-01 | 2021-04-22 | 14 | 0 | 14 | [20 empty] | 2021-04-29 |  | 2022-05-10 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 339133 | 1841 | 7.92 | Solar | 14_63L1 | 2021-03-26 22:18 | 2021-03-29 | 6 | 0 | 6 | 2021-04-07 | 2021-05-12 | 24 | 0 | 24 | [20 empty] | 2021-05-25 |  | 2022-06-06 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTHAMPTON | 349680 | 1060 | 15.12 | Solar | 09_901W3 | 2021-03-29 15:52 | 2021-03-30 | 2 | 2 | 0 | 2021-04-01 | 2021-04-22 | 14 | 0 | 14 | [20 empty] | 2021-04-26 |  | 2022-03-30 |  | EXP | [8 empty] | 2021-07-01 | Connected |  | No
National Grid | SALEM | 342002 | 1970 | 40 | Solar | 12_49W6 | 2021-03-30 05:49 | 2021-03-31 | 14 | 9 | 5 | 2021-04-23 | 2021-05-11 | 12 | 0 | 12 | [20 empty] | 2021-05-11 | 2021-03-30 11:57 | 2022-07-29 |  | EXP | [8 empty] | 2021-10-05 | Connected |  | No
National Grid | MONSON | 340846 | 1057 | 9.8 | Solar | 09_503L2 | 2021-03-30 11:57 | 2021-03-31 | 4 | 0 | 4 | 2021-04-07 | 2021-05-12 | 24 | 0 | 24 | [20 empty] | 2021-05-25 |  | 2023-06-07 | Yes | EXP |  | 2021-09-11 | 2021-11-16 | 67 | 4 | 63 |  |  | 2023-06-08 | Connected |  | Yes
National Grid | HANSON | 339190 | 2341 | 57.2 | Solar | 07_797W24 | 2021-03-30 12:44 | 2021-03-31 | 34 | 24 | 10 | 2021-06-03 | 2021-07-09 | 26 | 2 | 24 | [20 empty] | 2021-07-16 |  | 2022-08-25 |  | EXP | [8 empty] | 2022-01-21 | Connected |  | No
National Grid | REVERE | 346961 | 2151 | 7.6 | Solar | 12_16W4 | 2021-03-30 13:15 | 2021-03-31 | 0 | 0 | 0 | 2021-04-01 | 2021-04-22 | 14 | 0 | 14 | [20 empty] | 2021-04-26 |  | 2022-05-09 |  | EXP | [8 empty] | 2022-03-16 | Connected |  | No
National Grid | LEOMINSTER | 340616 | 1453 | 57.6 | Solar | 01_207W2 | 2021-03-30 17:39 | 2021-03-31 | 9 | 0 | 9 | 2021-04-15 | 2021-05-20 | 24 | 0 | 24 | [20 empty] | 2021-06-03 | 2021-03-31 13:35 | 2022-06-23 |  | EXP | [8 empty] | 2021-12-27 | Connected |  | No
National Grid | BRIMFIELD | 350119 | 1010 | 5.8 | Solar | 09_516L1 | 2021-03-31 13:35 | 2021-04-01 | 0 | 0 | 0 | 2021-04-02 | 2021-04-22 | 13 | 0 | 13 | [20 empty] | 2021-04-26 |  | 2022-09-24 | Yes | EXP |  | 2021-07-14 | 2021-09-22 | 70 | 3 | 67 |  |  | 2021-12-08 | Connected |  | Yes
National Grid | LYNN | 346631 | 1902 | 7.6 | Solar | 12_21J30 | 2021-03-31 17:30 | 2021-04-01 | 3 | 0 | 3 | 2021-04-07 | 2021-05-12 | 24 | 0 | 24 | [20 empty] | 2021-05-26 |  | 2022-06-06 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EVERETT | 343326 | 2149 | 6 | Solar | 12_16W7 | 2021-03-31 17:50 | 2021-04-01 | 4 | 0 | 4 | 2021-04-08 | 2021-05-12 | 23 | 0 | 23 | [20 empty] | 2021-05-14 |  | 2022-05-19 |  | EXP | [8 empty] | 2021-11-01 | Connected |  | No
National Grid | LAWRENCE | 342617 | 1843 | 7.6 | Solar | 14_8L1 | 2021-04-02 13:57 | 2021-04-05 | 8 | 0 | 8 | 2021-04-16 | 2021-05-20 | 23 | 0 | 23 | [20 empty] | 2021-06-03 |  |  |  | EXP | [8 empty] | 2021-07-15 | Connected |  | No
National Grid | SALEM | 343901 | 1970 | 7.6 | Solar | 12_29W6 | 2021-04-02 14:37 | 2021-04-05 | 1 | 0 | 1 | 2021-04-07 | 2021-05-12 | 24 | 0 | 24 | [20 empty] | 2021-05-25 |  |  |  | EXP | [8 empty] | 2021-08-10 | Connected |  | No
National Grid | LEOMINSTER | 350603 | 1453 | 9.86 | Solar | 01_207W2 | 2021-04-02 15:48 | 2021-04-05 | 13 | 13 | 0 | 2021-04-23 | 2021-05-27 | 25 | 0 | 25 | [20 empty] | 2021-05-28 |  | 2022-04-22 |  | EXP | [8 empty] | 2021-08-25 | Connected |  | No
National Grid | EAST LONGMEADOW | 350599 | 1028 | 6 | Solar | 09_508L5 | 2021-04-02 16:18 | 2021-04-05 | 1 | 1 | 0 | 2021-04-07 | 2021-05-12 | 25 | 0 | 25 | [20 empty] | 2021-05-13 |  | 2022-07-15 |  | EXP | [8 empty] | 2021-09-29 | Connected |  | No
National Grid | STOCKBRIDGE | 344288 | 1262 | 23.1 | Solar | 09_1103W1 | 2021-04-02 17:55 | 2021-04-05 | 1 | 1 | 0 | 2021-04-06 | 2021-05-09 | 23 | 0 | 23 | [20 empty] | 2021-05-10 |  | 2022-11-03 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NANTUCKET | 350253 | 2554 | 7.6 | Solar | 04_101L6 | 2021-04-05 14:30 | 2021-04-06 | 1 | 1 | 0 | 2021-04-07 | 2021-05-12 | 24 | 0 | 24 | [20 empty] | 2021-05-14 |  | 2022-04-05 |  | EXP | [8 empty] | 2021-08-30 | Connected |  | No
National Grid | SWANSEA | 349385 | 2777 | 7.6 | Solar | 05_11W81 | 2021-04-05 16:27 | 2021-04-06 | 6 | 0 | 6 | 2021-04-15 | 2021-05-20 | 24 | 0 | 24 | [20 empty] | 2021-06-03 | 2021-04-05 17:21 |  |  | EXP | [8 empty] | 2021-08-14 | Connected |  | No
National Grid | MEDFORD | 350691 | 2155 | 57.6 | Solar | 12_11J4 | 2021-04-05 17:21 | 2021-04-06 | 6 | 0 | 6 | 2021-04-15 | 2021-05-20 | 24 | 0 | 24 | [20 empty] | 2021-06-09 |  | 2023-01-02 | Yes | EXP |  | 2021-08-06 | 2021-09-20 | 24 | 3 | 21 |  |  | 2022-01-27 | Connected |  | No
National Grid | SUTTON | 348697 | 1590 | 9.28 | Solar | 01_304W6 | 2021-04-06 11:00 | 2021-04-07 | 0 | 0 | 0 | 2021-04-08 | 2021-05-12 | 23 | 0 | 23 | [20 empty] | 2021-05-14 |  | 2022-07-04 |  | EXP | [8 empty] | 2022-01-19 | Connected |  | No
National Grid | WESTMINSTER | 318674 | 1473 | 4948 | Other | 01_602W3 | 2021-04-06 12:21 | 2021-04-07 | 17 | 8 | 9 | [10 empty] | 2021-05-03 | 2021-06-01 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | NEW BRAINTREE | 336793 | 1531 | 9992 | Solar | 09_604W3 | 2021-04-06 12:26 | 2021-04-07 | 17 | 7 | 10 | [10 empty] | 2021-05-03 | 2021-06-02 | 21 | 1 | 20 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | PALMER | 327663 | 1069 | 9992 | Other | 09_503L1 | 2021-04-06 12:30 | 2021-04-07 | 17 | 7 | 10 | [10 empty] | 2021-05-03 | 2021-06-01 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | LAWRENCE | 347908 | 1843 | 7.6 | Solar | 14_1J9 | 2021-04-06 12:30 | 2021-04-07 | 5 | 0 | 5 | 2021-04-15 | 2021-05-20 | 24 | 0 | 24 | [20 empty] | 2021-06-03 |  |  |  | EXP | [8 empty] | 2021-09-09 | Connected |  | No
National Grid | PALMER | 327667 | 1069 | 9992 | Other | 09_503L1 | 2021-04-06 12:35 | 2021-04-07 | 17 | 7 | 10 | [10 empty] | 2021-05-03 | 2021-06-01 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | BARRE | 334194 | 1005 | 9992 | Other | 09_604W4 | 2021-04-06 12:46 | 2021-04-07 | 17 | 7 | 10 | [10 empty] | 2021-05-03 | 2021-06-01 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | EAST LONGMEADOW | 349187 | 1028 | 240 | Solar | 09_508L1 | 2021-04-06 23:29 | 2021-04-07 | 8 | 0 | 8 | 2021-04-20 | 2021-05-27 | 28 | 4 | 24 | 2021-07-20 | 2021-11-12 | 81 | 7 | 74 | [5 empty] | 2021-07-20 | 2021-11-12 | 81 | 7 | 74 | [5 empty] | 2021-12-02 | 2021-04-07 08:25 | 2023-11-01 |  | EXP |  | 2023-01-10 | 2023-08-03 | 206 | 0 | 206 |  |  | 2023-10-31 | Connected |  | No
National Grid | PEMBROKE | 349785 | 2359 | 200 | Solar | 07_910W51 | 2021-04-07 08:25 | 2021-04-08 | 13 | 3 | 10 | 2021-04-28 | 2021-05-28 | 22 | 0 | 22 | [20 empty] | 2021-06-16 |  | 2025-05-15 | Yes | EXP |  | 2022-02-18 |  | 787 | 737 | 50 |  |  |  | Construction |  | No
National Grid | SOUTHBRIDGE | 339091 | 1550 | 4999 | Solar | 01_413L4 | 2021-04-07 10:00 | 2021-04-08 | 14 | 4 | 10 | [10 empty] | 2021-04-29 | 2021-05-28 | 22 | 1 | 21 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | SOUTHBRIDGE | 335828 | 1550 | 9992 | Other | 01_413L3 | 2021-04-07 11:04 | 2021-04-08 | 16 | 6 | 10 | [10 empty] | 2021-05-03 | 2021-06-01 | 21 | 0 | 21 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | SOUTHBRIDGE | 335832 | 1550 | 9992 | Other | 01_413L3 | 2021-04-07 11:06 | 2021-04-08 | 16 | 6 | 10 | [10 empty] | 2021-05-03 | 2021-06-01 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SHIRLEY | 345461 | 1464 | 800 | Solar | 01_227W3 | 2021-04-07 11:33 | 2021-04-29 | 127 | 122 | 5 | [10 empty] | 2021-11-16 | 2022-04-08 | 101 | 64 | 37 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | WESTMINSTER | 345465 | 1473 | 500 | Solar | 01_602W3 | 2021-04-07 11:33 | 2021-04-08 | 314 | 158 | 156 | [29 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SALISBURY | 345471 | 1952 | 500 | Solar | 14_7L2 | 2021-04-07 11:33 | 2021-04-08 | 9 | 0 | 9 | [10 empty] | 2021-04-26 | 2021-12-26 | 169 | 33 | 136 | [11 empty] | 2021-04-07 11:34 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | FOXBOROUGH | 345466 | 2035 | 500 | Solar | 05_3424W1 | 2021-04-07 11:34 | 2021-04-08 | 59 | 50 | 9 | [10 empty] | 2021-07-02 | 2021-10-06 | 67 | 27 | 40 | [10 empty] | 2022-04-27 |  | 2024-05-16 | Yes | STD |  | 2023-02-28 | 2023-11-15 | 261 | 190 | 71 |  |  |  | Completion Documents |  | No
National Grid | EAST BRIDGEWATER | 345490 | 2333 | 500 | Solar | 07_797W29 | 2021-04-07 11:45 | 2021-04-08 | 11 | 0 | 11 | [10 empty] | 2021-07-14 | 2021-12-15 | 107 | 82 | 25 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SUTTON | 337942 | 1590 | 4948 | Other | 05_320W5 | 2021-04-07 11:55 | 2021-04-08 | 16 | 6 | 10 | [10 empty] | 2021-05-03 | 2021-06-02 | 21 | 1 | 20 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | BROCKTON | 345964 | 2301 | 500 | Solar | 07_797W19 | 2021-04-07 11:58 | 2021-04-08 | 9 | 0 | 9 | [10 empty] | 2021-07-14 | 2022-03-24 | 174 | 126 | 48 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | MARLBOROUGH | 346371 | 1752 | 250 | Solar | 05_313W4 | 2021-04-07 12:13 | 2021-04-08 | 9 | 0 | 9 | 2021-04-30 | 2021-06-08 | 26 | 2 | 24 | [20 empty] | 2021-07-14 |  | 2022-07-19 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LOWELL | 346400 | 1852 | 250 | Solar | 14_16L7 | 2021-04-07 12:31 | 2021-04-08 | 9 | 0 | 9 | [10 empty] | 2021-05-10 | 2021-11-18 | 134 | 109 | 25 | [11 empty] | 2021-04-07 12:42 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BERLIN | 346401 | 1503 | 250 | Solar | 05_318W3 | 2021-04-07 12:42 | 2021-04-08 | 11 | 0 | 11 | [10 empty] | 2021-04-26 | 2021-12-28 | 171 | 98 | 73 | [10 empty] | 2022-08-09 |  | 2024-06-21 | Yes | STD |  | 2023-08-16 | 2023-10-27 | 73 | 0 | 73 |  |  |  | Completion Documents |  | No
National Grid | SHIRLEY | 346659 | 1464 | 250 | Solar | 01_227W3 | 2021-04-07 12:51 | 2021-04-08 | 9 | 0 | 9 | 2021-04-26 | 2021-09-03 | 92 | 29 | 63 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | SHIRLEY | 346662 | 1464 | 500 | Solar | 01_227W3 | 2021-04-07 12:56 | 2021-04-08 | 10 | 0 | 10 | [10 empty] | 2021-04-26 | 2022-04-08 | 240 | 218 | 22 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SALISBURY | 346665 | 1952 | 250 | Solar | 14_7L2 | 2021-04-07 13:02 | 2021-04-08 | 9 | 0 | 9 | 2021-04-26 | 2022-01-31 | 193 | 192 | 1 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTHAMPTON | 341230 | 1060 | 14.88 | Solar | 09_909W2 | 2021-04-07 13:12 | 2021-04-08 | 2 | 1 | 1 | 2021-04-12 | 2021-05-17 | 24 | 0 | 24 | [20 empty] | 2021-06-28 |  | 2022-07-30 |  | EXP | [8 empty] | 2021-11-01 | Connected |  | No
National Grid | SOUTH EASTON | 351232 | 2375 | 8.7 | Solar | 07_92W54 | 2021-04-07 14:43 | 2021-04-08 | 9 | 7 | 2 | 2021-04-23 | 2021-05-27 | 25 | 0 | 25 | [20 empty] | 2021-05-28 |  | 2022-04-22 |  | EXP | [8 empty] | 2021-08-04 | Connected |  | No
National Grid | BROCKTON | 324131 | 2302 | 5.76 | Solar | 07_712J1 | 2021-04-07 14:46 | 2021-04-08 | 1 | 0 | 1 | 2021-04-12 | 2021-05-17 | 24 | 0 | 24 | [20 empty] | 2021-05-19 |  | 2022-04-08 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NAHANT | 351267 | 1908 | 100 | Solar | 12_79J1 | 2021-04-07 15:09 | 2021-04-08 | 16 | 6 | 10 | [10 empty] | 2021-05-11 | 2021-06-25 | 34 | 9 | 25 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | MEDFORD | 347803 | 2155 | 4.64 | Solar | 12_37W4 | 2021-04-07 18:53 | 2021-04-08 | 4 | 0 | 4 | 2021-04-15 | 2021-05-20 | 24 | 0 | 24 | [20 empty] | 2021-06-03 |  | 2023-01-06 |  | EXP | [8 empty] | 2022-02-15 | Connected |  | No
National Grid | AMESBURY | 348110 | 1913 | 9.8 | Solar | 14_275L2 | 2021-04-08 10:54 | 2021-04-09 | 1 | 0 | 1 | 2021-04-13 | 2021-05-18 | 24 | 0 | 24 | [20 empty] | 2021-05-19 |  | 2022-04-12 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NEWBURY | 349237 | 1951 | 17.6 | Solar | 14_60L1 | 2021-04-08 14:51 | 2021-04-09 | 12 | 12 | 0 | 2021-04-28 | 2021-06-02 | 25 | 0 | 25 | [20 empty] | 2021-06-08 |  | 2022-08-24 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTFORD | 351803 | 1886 | 10 | Solar | 14_58L1 | 2021-04-09 14:00 | 2021-04-12 | 0 | 0 | 0 | 2021-04-15 | 2021-06-04 | 35 | 12 | 23 | [20 empty] | 2021-06-10 |  | 2022-07-17 |  | EXP | [8 empty] | 2022-02-01 | Connected |  | No
National Grid | BROCKTON | 345930 | 2302 | 7.6 | Solar | 07_911W56 | 2021-04-10 11:01 | 2021-04-12 | 0 | 0 | 0 | 2021-04-13 | 2021-05-18 | 24 | 0 | 24 | [20 empty] | 2021-05-27 | 2021-04-12 09:44 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HUBBARDSTON | 303281 | 1452 | 15.2 | Solar | 09_604W4 | 2021-04-12 09:44 | 2021-04-13 | 4 | 0 | 4 | 2021-04-20 | 2021-05-24 | 24 | 0 | 24 | [20 empty] | 2021-06-07 |  | 2022-08-15 | Yes | EXP |  | 2022-10-21 | 2023-01-06 | 78 | 0 | 78 |  |  | 2024-01-19 | Connected |  | Yes
National Grid | CHARLTON | 321753 | 1507 | 4948 | Other | 01_415L2 | 2021-04-13 16:13 | 2021-04-14 | 12 | 2 | 10 | [10 empty] | 2021-05-03 | 2021-06-01 | 21 | 0 | 21 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | UXBRIDGE | 329621 | 1569 | 4948 | Other | 05_320W4 | 2021-04-13 16:16 | 2021-04-14 | 11 | 1 | 10 | [10 empty] | 2021-04-30 | 2021-05-27 | 19 | 0 | 19 | [11 empty] | 2021-04-14 08:57 |  |  | STD | [9 empty] | Group Study |  | No
National Grid | TOPSFIELD | 348454 | 1983 | 10 | Solar | 14_33L2 | 2021-04-14 08:57 | 2021-04-15 | 0 | 0 | 0 | 2021-04-15 | 2021-05-21 | 25 | 0 | 25 | [20 empty] | 2021-05-21 | 2021-04-14 09:13 | 2022-04-14 | Yes | EXP |  | 2021-07-14 | 2021-07-13 | 0 | 0 | 0 |  |  | 2021-09-02 | Connected |  | No
National Grid | ADAMS | 347980 | 1220 | 7.6 | Solar | 09_1021W2 | 2021-04-14 09:13 | 2021-04-15 | 2 | 0 | 2 | 2021-04-20 | 2021-05-24 | 24 | 0 | 24 | [20 empty] | 2021-06-07 |  | 2022-07-11 | Yes | EXP |  | 2022-01-04 | 2022-01-14 | 11 | 0 | 11 |  |  | 2022-02-05 | Connected |  | No
National Grid | SUTTON | 352535 | 1590 | 7.54 | Solar | 01_304W5 | 2021-04-14 11:02 | 2021-04-15 | 0 | 0 | 0 | 2021-04-16 | 2021-05-20 | 23 | 0 | 23 | [20 empty] | 2021-05-21 |  | 2022-04-14 |  | EXP | [8 empty] | 2021-07-30 | Connected |  | No
National Grid | QUINCY | 350545 | 2169 | 9.86 | Solar | 07_1W5 | 2021-04-14 21:25 | 2021-04-15 | 1 | 1 | 0 | 2021-04-16 | 2021-05-20 | 23 | 0 | 23 | [20 empty] | 2021-05-21 |  | 2022-04-14 |  | EXP | [8 empty] | 2021-07-02 | Connected |  | No
National Grid | LOWELL | 349177 | 1850 | 7.6 | Solar | 14_75L5 | 2021-04-15 11:49 | 2021-04-16 | 5 | 0 | 5 | 2021-04-27 | 2021-06-01 | 24 | 0 | 24 | [20 empty] | 2021-06-14 |  | 2022-06-20 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ATTLEBORO | 335835 | 2703 | 9.12 | Solar | 05_9L3 | 2021-04-15 12:30 | 2021-04-16 | 20 | 20 | 0 | 2021-05-17 | 2021-06-21 | 24 | 0 | 24 | [20 empty] | 2021-06-25 |  | 2022-05-13 |  | EXP | [8 empty] | 2021-08-06 | Connected |  | No
National Grid | MALDEN | 349034 | 2148 | 9.8 | Solar | 12_67J4 | 2021-04-15 13:57 | 2021-04-16 | 1 | 0 | 1 | 2021-04-20 | 2021-06-07 | 33 | 13 | 20 | [20 empty] | 2021-06-16 |  | 2022-11-10 |  | EXP | [8 empty] | 2021-12-09 | Connected |  | No
National Grid | SOUTH HAMILTON | 347745 | 1982 | 10 | Solar | 12_51T2 | 2021-04-15 15:53 | 2021-04-16 | 13 | 12 | 1 | 2021-05-06 | 2021-06-10 | 24 | 0 | 24 | [20 empty] | 2021-06-23 |  | 2022-07-03 |  | EXP | [8 empty] | 2021-10-08 | Connected |  | No
National Grid | METHUEN | 347618 | 1844 | 6.09 | Solar | 14_43L4 | 2021-04-15 16:40 | 2021-04-16 | 3 | 1 | 2 | 2021-04-23 | 2021-05-27 | 25 | 0 | 25 | [20 empty] | 2021-06-01 |  | 2022-04-22 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 349178 | 1841 | 9.8 | Solar | 14_8L2 | 2021-04-16 11:30 | 2021-04-20 | 4 | 0 | 4 | 2021-04-27 | 2021-06-01 | 25 | 0 | 25 | [20 empty] | 2021-06-15 |  | 2022-06-21 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | TEWKSBURY | 349329 | 1876 | 3.8 | Solar | 14_59L3 | 2021-04-16 12:37 | 2021-04-20 | 4 | 0 | 4 | 2021-04-27 | 2021-06-01 | 24 | 0 | 24 | [20 empty] | 2021-06-15 |  |  |  | EXP | [8 empty] | 2021-08-09 | Connected |  | No
National Grid | SCITUATE | 353056 | 2066 | 19.86 | Solar | 07_15J1 | 2021-04-16 13:04 | 2021-04-20 | 2 | 0 | 2 | 2021-04-23 | 2021-05-27 | 24 | 0 | 24 | [20 empty] | 2021-05-28 |  | 2023-05-16 |  | EXP | [8 empty] | 2023-04-05 | Connected |  | No
National Grid | WESTFORD | 353145 | 1886 | 5.8 | Solar | 14_58L3 | 2021-04-16 16:36 | 2021-04-20 | 15 | 13 | 2 | 2021-05-11 | 2021-06-14 | 23 | 0 | 23 | [20 empty] | 2021-06-16 |  | 2022-05-09 |  | EXP | [8 empty] | 2021-07-16 | Connected |  | No
National Grid | BYFIELD | 347069 | 1922 | 8.7 | Solar | 14_60L2 | 2021-04-19 11:40 | 2021-04-20 | 2 | 0 | 2 | 2021-04-23 | 2021-05-27 | 25 | 0 | 25 | [20 empty] | 2021-06-01 |  | 2022-07-06 |  | EXP | [8 empty] | 2021-10-20 | Connected |  | No
National Grid | FLORIDA | 347442 | 1247 | 2125 | Solar | 09_1015W1 | 2021-04-20 13:51 | 2021-04-21 | 25 | 16 | 9 | [10 empty] | 2021-05-26 | 2021-09-01 | 68 | 48 | 20 | [11 empty] | 2021-04-20 13:54 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | STOUGHTON | 347865 | 2072 | 9.8 | Solar | 07_913W67 | 2021-04-20 13:54 | 2021-04-21 | 3 | 0 | 3 | 2021-04-27 | 2021-06-01 | 24 | 0 | 24 | [20 empty] | 2021-06-15 |  | 2023-02-01 | Yes | EXP |  | 2022-04-15 | 2022-10-04 | 172 | 0 | 172 |  |  | 2022-11-21 | Connected |  | Yes
National Grid | BELCHERTOWN | 352557 | 1007 | 20 | Solar | 09_509L2 | 2021-04-20 16:25 | 2021-04-21 | 1 | 0 | 1 | 2021-04-23 | 2021-05-27 | 24 | 0 | 24 | [20 empty] | 2021-06-03 |  | 2022-06-15 |  | EXP | [8 empty] | 2021-12-02 | Connected |  | No
National Grid | SWANSEA | 348833 | 2777 | 499 | Solar | 05_11W83 | 2021-04-20 16:37 | 2021-04-21 | 9 | 0 | 9 | [10 empty] | 2021-05-05 | 2021-06-28 | 38 | 14 | 24 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 348431 | 2301 | 7.6 | Solar | 07_911W25 | 2021-04-20 17:54 | 2021-04-21 | 3 | 0 | 3 | 2021-04-27 | 2021-06-01 | 25 | 0 | 25 | [20 empty] | 2021-06-15 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GARDNER | 347438 | 1440 | 7.6 | Solar | 01_607W5 | 2021-04-20 18:17 | 2021-04-21 | 1 | 0 | 1 | 2021-04-23 | 2021-05-27 | 25 | 0 | 25 | [20 empty] | 2021-05-28 |  | 2022-04-22 |  | EXP | [8 empty] | 2021-08-27 | Connected |  | No
National Grid | NEWBURYPORT | 349427 | 1950 | 9.8 | Solar | 14_60L3 | 2021-04-21 08:18 | 2021-04-22 | 2 | 0 | 2 | 2021-04-27 | 2021-06-01 | 24 | 0 | 24 | [20 empty] | 2021-06-15 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | COHASSET | 352066 | 2025 | 7.6 | Solar | 07_96W41 | 2021-04-21 08:42 | 2021-04-22 | 0 | 0 | 0 | 2021-04-23 | 2021-05-27 | 24 | 0 | 24 | [20 empty] | 2021-05-28 |  | 2022-04-22 |  | EXP | [8 empty] | 2021-07-18 | Connected |  | No
National Grid | LAWRENCE | 278404 | 1843 | 5.76 | Solar | 14_61L3 | 2021-04-21 13:34 | 2021-04-22 | 4 | 0 | 4 | 2021-04-29 | 2021-06-03 | 24 | 0 | 24 | [20 empty] | 2021-06-16 |  | 2022-12-25 |  | EXP | [8 empty] | 2022-05-05 | Connected |  | No
National Grid | BROCKTON | 348390 | 2301 | 7.6 | Solar | 07_91W43 | 2021-04-22 09:08 | 2021-04-23 | 3 | 0 | 3 | 2021-04-29 | 2021-06-29 | 24 | 0 | 24 | [20 empty] | 2021-07-08 |  | 2022-08-03 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LYNN | 347227 | 1902 | 5.76 | Solar | 12_21J21 | 2021-04-22 10:18 | 2021-04-23 | 5 | 3 | 2 | 2021-05-03 | 2021-06-07 | 24 | 0 | 24 | [20 empty] | 2021-06-10 |  | 2022-07-31 |  | EXP | [8 empty] | 2021-09-27 | Connected |  | No
National Grid | WEYMOUTH | 351129 | 2188 | 7.6 | Solar | 07_12W2 | 2021-04-22 10:58 | 2021-04-23 | 2 | 0 | 2 | 2021-04-28 | 2021-06-02 | 25 | 0 | 25 | [20 empty] | 2021-06-07 | 2021-04-22 15:12 | 2022-04-27 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | STOUGHTON | 347679 | 2072 | 812.5 | Solar | 07_75W1 | 2021-04-22 15:12 | 2021-04-23 | 98 | 87 | 11 | [10 empty] | 2021-09-13 | 2021-10-07 | 19 | 0 | 19 | [10 empty] | 2022-06-13 |  | 2024-11-18 | Yes | STD | [9 empty] | Construction |  | No
National Grid | EVERETT | 354177 | 2149 | 16.82 | Solar | 12_16W2 | 2021-04-22 17:00 | 2021-04-23 | 0 | 0 | 0 | 2021-04-26 | 2021-05-27 | 23 | 0 | 23 | [20 empty] | 2021-06-03 | 2021-04-23 09:09 |  |  | EXP | [8 empty] | 2021-09-16 | Connected |  | Yes
National Grid | RANDOLPH | 351290 | 2368 | 10 | Solar | 07_97W4 | 2021-04-23 09:09 | 2021-04-26 | 2 | 0 | 2 | 2021-04-29 | 2021-06-03 | 24 | 0 | 24 | [20 empty] | 2021-06-16 |  | 2022-11-09 | Yes | EXP |  | 2021-10-19 | 2021-10-19 | 1 | 0 | 1 |  |  | 2021-12-15 | Connected |  | Yes
National Grid | LAWRENCE | 349605 | 1843 | 6 | Solar | 14_8L1 | 2021-04-23 11:36 | 2021-04-26 | 2 | 0 | 2 | 2021-04-29 | 2021-06-03 | 24 | 0 | 24 | [20 empty] | 2021-06-16 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHELMSFORD | 354303 | 1824 | 7.6 | Solar | 14_73L1 | 2021-04-23 11:41 | 2021-04-26 | 2 | 1 | 1 | 2021-04-28 | 2021-06-02 | 25 | 0 | 25 | [20 empty] | 2021-06-08 |  | 2022-09-04 |  | EXP | [8 empty] | 2021-11-02 | Connected |  | No
National Grid | NORTHAMPTON | 354333 | 1062 | 10 | Solar | 09_909W4 | 2021-04-23 12:25 | 2021-04-26 | 0 | 0 | 0 | 2021-04-27 | 2021-05-28 | 22 | 0 | 22 | [20 empty] | 2021-06-01 |  |  |  | EXP | [8 empty] | 2021-08-14 | Connected |  | No
National Grid | PALMER | 348867 | 1069 | 9992 | Other | 09_523L4 | 2021-04-23 14:57 | 2021-04-26 | 9 | 0 | 9 | [10 empty] | 2021-05-10 | 2021-06-08 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | CHESHIRE | 354411 | 1225 | 9.8 | Solar | 09_1021W2 | 2021-04-23 15:20 | 2021-04-26 | 1 | 0 | 1 | 2021-04-28 | 2021-06-02 | 25 | 0 | 25 | [20 empty] | 2021-06-08 |  | 2022-06-19 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | PALMER | 348872 | 1069 | 7998 | Other | 09_523L4 | 2021-04-23 15:21 | 2021-04-26 | 9 | 0 | 9 | [10 empty] | 2021-05-10 | 2021-06-08 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | PALMER | 348875 | 1069 | 7998 | Other | 09_523L3 | 2021-04-23 15:43 | 2021-04-26 | 10 | 0 | 10 | [10 empty] | 2021-05-10 | 2021-06-08 | 20 | 0 | 20 | [11 empty] | 2021-04-23 17:34 |  |  | STD | [9 empty] | Group Study |  | No
National Grid | DRACUT | 352979 | 1826 | 9.8 | Solar | 14_78L9 | 2021-04-23 17:34 | 2021-11-05 |  |  |  | 2021-05-19 | 2021-06-23 | 24 | 0 | 24 | [20 empty] | 2021-06-25 |  | 2022-12-06 | Yes | EXP |  | 2021-11-05 | 2021-12-03 | 29 | 0 | 29 |  |  |  | Connected |  | Yes
National Grid | PALMER | 348877 | 1069 | 4948 | Other | 09_523L3 | 2021-04-26 09:50 | 2021-04-27 | 8 | 0 | 8 | [10 empty] | 2021-05-10 | 2021-06-08 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | BILLERICA | 354556 | 1821 | 10 | Solar | 14_92L6 | 2021-04-26 15:13 | 2021-04-27 | 5 | 5 | 0 | 2021-05-05 | 2021-06-09 | 24 | 0 | 24 | [20 empty] | 2021-06-10 |  | 2022-06-19 |  | EXP | [8 empty] | 2021-09-10 | Connected |  | No
National Grid | SOUTH HAMILTON | 354859 | 1982 | 6.38 | Solar | 12_51L3 | 2021-04-27 13:28 | 2021-04-28 | 1 | 1 | 0 | 2021-04-29 | 2021-06-07 | 25 | 0 | 25 | [20 empty] | 2021-06-07 | 2021-04-28 11:53 | 2022-04-27 |  | EXP | [8 empty] | 2021-08-10 | Connected |  | No
National Grid | PEPPERELL | 355070 | 1463 | 20 | Solar | 01_226L1 | 2021-04-28 11:53 | 2021-04-29 | 0 | 0 | 0 | 2021-05-04 | 2021-06-04 | 24 | 0 | 24 | [20 empty] | 2021-06-16 |  | 2022-12-02 | Yes | EXP |  | 2021-11-16 | 2021-11-23 | 8 | 0 | 8 |  |  | 2021-12-21 | Connected |  | No
National Grid | DUNSTABLE | 354941 | 1827 | 9.6 | Solar | 01_210L1 | 2021-04-28 13:02 | 2021-04-29 | 1 | 1 | 0 | 2021-05-04 | 2021-06-04 | 24 | 0 | 24 | [20 empty] | 2021-06-10 |  | 2022-04-28 |  | EXP | [8 empty] | 2021-07-24 | Connected |  | No
National Grid | LYNN | 349185 | 1902 | 7.6 | Solar | 12_3J903 | 2021-04-28 15:38 | 2021-04-29 | 2 | 0 | 2 | 2021-05-04 | 2021-06-08 | 24 | 0 | 24 | [20 empty] | 2021-06-16 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 352007 | 2301 | 10 | Solar | 07_98W46 | 2021-04-29 08:58 | 2021-04-30 | 4 | 0 | 4 | 2021-05-07 | 2021-06-11 | 24 | 0 | 24 | [20 empty] | 2021-06-23 |  | 2023-01-26 |  | EXP | [8 empty] | 2021-10-04 | Connected |  | No
National Grid | LEOMINSTER | 351150 | 1453 | 7.6 | Solar | 01_225W4 | 2021-04-29 12:37 | 2021-04-30 | 4 | 0 | 4 | 2021-05-07 | 2021-06-11 | 24 | 0 | 24 | [20 empty] | 2021-06-23 |  | 2022-07-04 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GARDNER | 312828 | 1440 | 762 | Solar | 01_607W3 | 2021-04-29 12:45 | 2021-04-30 | 108 | 99 | 9 | [10 empty] | 2021-10-04 | 2021-12-04 | 42 | 22 | 20 | [11 empty] | 2021-04-29 15:14 |  |  | STD | [9 empty] | Study |  | No
National Grid | ATHOL | 352917 | 1366 | 10 | Solar | 09_702W1 | 2021-04-29 15:14 | 2021-04-30 | 1 | 1 | 0 | 2021-05-03 | 2021-06-07 | 24 | 0 | 24 | [20 empty] | 2021-06-10 |  | 2022-10-04 | Yes | EXP |  | 2021-08-11 | 2021-10-04 | 53 | 3 | 50 |  |  | 2021-10-05 | Connected |  | No
National Grid | WRENTHAM | 347002 | 2093 | 999 | Solar | 05_3422W3 | 2021-04-29 16:45 | 2021-04-30 | 11 | 3 | 8 | [10 empty] | 2021-05-17 | 2021-06-15 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BOLTON | 355955 | 1740 | 7.83 | Solar | 05_318W3 | 2021-05-03 15:55 | 2021-05-04 | 3 | 1 | 2 | 2021-05-07 | 2021-06-11 | 24 | 0 | 24 | [20 empty] | 2021-06-23 |  |  |  | EXP | [8 empty] | 2021-08-03 | Connected |  | No
National Grid | WESTMINSTER | 356001 | 1473 | 7.68 | Solar | 01_609W2 | 2021-05-03 20:22 | 2021-05-04 | 0 | 0 | 0 | 2021-05-05 | 2021-06-09 | 24 | 0 | 24 | [20 empty] | 2021-06-10 | 2021-05-04 11:13 | 2022-05-03 |  | EXP | [8 empty] | 2021-07-28 | Connected |  | No
National Grid | METHUEN | 348029 | 1844 | 7.6 | Solar | 14_74L2 | 2021-05-04 11:13 | 2021-05-05 | 0 | 0 | 0 | 2021-05-06 | 2021-06-10 | 24 | 0 | 24 | [20 empty] | 2021-06-15 |  | 2023-02-28 | Yes | EXP |  | 2021-11-25 | 2022-01-24 | 61 | 0 | 61 |  |  | 2022-03-09 | Connected |  | No
National Grid | CHARLTON | 349183 | 1507 | 7.6 | Solar | 01_415L2 | 2021-05-04 14:27 | 2021-05-05 | 2 | 0 | 2 | 2021-05-10 | 2021-06-14 | 24 | 0 | 24 | [20 empty] | 2021-06-23 | 2021-05-04 14:47 | 2022-10-11 |  | EXP | [8 empty] | 2022-01-28 | Connected |  | Yes
National Grid | RANDOLPH | 342233 | 2368 | 10 | Solar | 07_97W4 | 2021-05-04 14:47 | 2021-05-05 | 0 | 0 | 0 | 2021-05-06 | 2021-06-10 | 24 | 0 | 24 | [20 empty] | 2021-06-23 |  | 2022-09-25 | Yes | EXP |  | 2021-08-11 | 2021-09-23 | 43 | 3 | 40 |  |  | 2022-05-05 | Connected |  | No
National Grid | LEOMINSTER | 352779 | 1453 | 5.76 | Solar | 01_219W2 | 2021-05-04 21:53 | 2021-05-05 | 0 | 0 | 0 | 2021-05-06 | 2021-06-10 | 24 | 0 | 24 | [20 empty] | 2021-06-15 |  | 2022-06-19 |  | EXP | [8 empty] | 2021-10-07 | Connected |  | No
National Grid | BOLTON | 356319 | 1740 | 9.28 | Solar | 01_216W6 | 2021-05-05 09:49 | 2021-05-06 | 4 | 4 | 0 | 2021-05-12 | 2021-06-15 | 23 | 0 | 23 | [20 empty] | 2021-06-16 |  | 2022-05-11 |  | EXP | [8 empty] | 2021-07-07 | Connected |  | No
National Grid | REHOBOTH | 335356 | 2769 | 24.36 | Solar | 05_7L4 | 2021-05-05 12:08 | 2021-05-06 | 1 | 0 | 1 | 2021-05-10 | 2021-06-14 | 24 | 0 | 24 | [20 empty] | 2021-09-28 |  | 2022-11-09 |  | EXP | [8 empty] | 2021-12-23 | Connected |  | No
National Grid | CHARLTON | 356489 | 1507 | 21.36 | Solar | 01_415L2 | 2021-05-05 14:38 | 2021-05-06 | 4 | 2 | 2 | 2021-05-13 | 2021-06-16 | 23 | 0 | 23 | [20 empty] | 2021-06-22 | 2021-05-05 15:40 | 2023-01-01 |  | EXP | [8 empty] | 2022-02-25 | Connected |  | No
National Grid | CHARLTON | 350779 | 1507 | 24 | Solar | 01_406L1 | 2021-05-05 15:40 | 2021-05-06 | 0 | 0 | 0 | 2021-05-07 | 2021-06-11 | 24 | 0 | 24 | [20 empty] | 2021-07-30 | 2021-05-05 18:58 | 2023-03-09 | Yes | EXP |  | 2022-01-14 | 2022-01-14 | 1 | 0 | 1 |  |  | 2022-04-05 | Connected |  | No
National Grid | STOUGHTON | 356589 | 2072 | 9.8 | Solar | 07_913W67 | 2021-05-05 18:58 | 2021-06-10 | 1 | 0 | 1 | 2021-06-11 | 2021-07-16 | 25 | 0 | 25 | [20 empty] | 2021-07-19 |  | 2022-12-23 | Yes | EXP |  | 2021-11-02 | 2021-12-23 | 52 | 0 | 52 |  |  | 2022-03-25 | Connected |  | No
National Grid | BROCKTON | 333382 | 2301 | 9.6 | Solar | 07_98W46 | 2021-05-06 07:39 | 2021-05-07 | 0 | 0 | 0 | 2021-05-07 | 2021-06-11 | 24 | 0 | 24 | [20 empty] | 2021-06-14 |  | 2022-07-23 |  | EXP | [8 empty] | 2022-05-04 | Connected |  | No
National Grid | WESTBOROUGH | 356524 | 1581 | 9.86 | Solar | 05_312W1 | 2021-05-06 09:23 | 2021-05-07 | 1 | 1 | 0 | 2021-05-10 | 2021-06-14 | 24 | 0 | 24 | [20 empty] | 2021-06-16 |  | 2022-05-06 |  | EXP | [8 empty] | 2021-08-24 | Connected |  | No
National Grid | WORCESTER | 351365 | 1605 | 7.6 | Solar | 01_24W2 | 2021-05-06 17:18 | 2021-05-07 | 3 | 0 | 3 | 2021-05-13 | 2021-06-17 | 24 | 0 | 24 | [20 empty] | 2021-06-25 |  | 2022-10-09 |  | EXP | [8 empty] | 2021-12-13 | Connected |  | No
National Grid | DRACUT | 353172 | 1826 | 3.8 | Solar | 14_78L9 | 2021-05-06 18:02 | 2021-05-07 | 3 | 0 | 3 | 2021-05-13 | 2021-06-17 | 24 | 0 | 24 | [20 empty] | 2021-06-25 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BEVERLY | 354200 | 1915 | 250 | Solar | 12_51T1 | 2021-05-07 14:11 | 2021-05-10 | 13 | 8 | 5 | 2021-05-27 | 2021-07-20 | 37 | 12 | 25 | [20 empty] | 2021-07-21 |  | 2022-10-29 |  | EXP | [8 empty] | 2022-06-17 | Connected |  | No
National Grid | WARE | 357047 | 1082 | 10 | Solar | 09_523L4 | 2021-05-07 16:23 | 2021-05-10 | 7 | 7 | 0 | 2021-05-20 | 2021-06-25 | 25 | 0 | 25 | [20 empty] | 2021-06-29 |  | 2022-07-19 |  | EXP | [8 empty] | 2021-10-04 | Connected |  | No
National Grid | LAWRENCE | 356820 | 1843 | 150 | Solar | 14_8T2 | 2021-05-10 09:19 | 2021-05-11 | 18 | 10 | 8 | 2021-06-08 | 2021-09-01 | 60 | 36 | 24 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GARDNER | 351897 | 1440 | 3.8 | Solar | 01_602W2 | 2021-05-10 16:52 | 2021-05-11 | 3 | 0 | 3 | 2021-05-17 | 2021-05-18 | 1 | 0 | 1 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WARREN | 347568 | 1083 | 7.6 | Solar | 09_516L3 | 2021-05-11 10:00 | 2021-05-10 | 1 | 0 | 1 | 2021-05-12 | 2021-06-15 | 23 | 0 | 23 | [20 empty] | 2021-06-16 |  | 2022-06-29 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTHAMPTON | 357554 | 1060 | 8.99 | Solar | 09_909W3 | 2021-05-11 14:22 | 2021-05-12 | 4 | 4 | 0 | 2021-05-18 | 2021-06-21 | 23 | 0 | 23 | [20 empty] | 2021-06-25 |  | 2022-05-17 |  | EXP | [8 empty] | 2021-09-10 | Connected |  | No
National Grid | PEPPERELL | 357623 | 1463 | 9.8 | Solar | 01_226L2 | 2021-05-12 12:12 | 2021-05-13 | 1 | 1 | 0 | 2021-05-14 | 2021-06-18 | 24 | 0 | 24 | [20 empty] | 2021-06-25 | 2021-05-13 11:20 | 2022-05-12 |  | EXP | [8 empty] | 2021-08-26 | Connected |  | No
National Grid | GRAFTON | 358023 | 1519 | 20 | Solar | 01_304W1 | 2021-05-13 11:20 | 2021-05-14 | 0 | 0 | 0 | 2021-05-17 | 2021-06-21 | 24 | 0 | 24 | [20 empty] | 2021-07-12 |  | 2023-04-24 | Yes | EXP | [9 empty] | Withdrawn |  | No
National Grid | LAWRENCE | 349417 | 1841 | 9.8 | Solar | 14_43L4 | 2021-05-13 18:24 | 2021-05-14 | 5 | 0 | 5 | 2021-05-24 | 2021-07-01 | 28 | 3 | 25 | [20 empty] | 2021-07-07 |  |  |  | EXP | [8 empty] | 2021-08-10 | Connected |  | No
National Grid | COHASSET | 343627 | 2025 | 500 | Solar | 07_915W37 | 2021-05-13 18:32 | 2021-05-14 | 31 | 20 | 11 | [10 empty] | 2021-06-29 | 2021-08-18 | 36 | 11 | 25 | [10 empty] | 2022-06-08 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | COHASSET | 343630 | 2025 | 499 | Solar | 07_915W37 | 2021-05-13 18:33 | 2021-05-14 | 31 | 20 | 11 | [10 empty] | 2021-06-29 | 2021-08-18 | 36 | 11 | 25 | [10 empty] | 2022-06-08 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | GARDNER | 357820 | 1440 | 240 | Solar | 01_602W2 | 2021-05-14 08:42 | 2021-05-18 | 10 | 0 | 10 | [10 empty] | 2021-06-03 | 2021-08-17 | 53 | 28 | 25 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | EAST BRIDGEWATER | 358173 | 2333 | 9.6 | Solar | 07_797W42 | 2021-05-14 10:01 | 2021-05-17 | 3 | 3 | 0 | 2021-05-20 | 2021-06-25 | 25 | 0 | 25 | [20 empty] | 2021-06-29 |  | 2023-01-11 |  | EXP | [8 empty] | 2023-01-19 | Connected |  | No
National Grid | LEICESTER | 337144 | 1524 | 1100 | Solar | 01_21W1 | 2021-05-14 12:08 | 2021-05-17 | 27 | 17 | 10 | [10 empty] | 2021-08-23 | 2022-10-14 | 288 | 171 | 117 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | SEEKONK | 337135 | 2771 | 499.5 | Solar | 05_7L3 | 2021-05-14 12:09 | 2021-05-17 | 124 | 115 | 9 | [10 empty] | 2021-11-12 | 2021-12-16 | 24 | 0 | 24 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | FALL RIVER | 337141 | 2721 | 497.5 | Solar | 05_115W43 | 2021-05-14 12:10 | 2021-05-17 | 123 | 110 | 13 | [10 empty] | 2021-11-10 | 2022-01-21 | 50 | 27 | 23 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | SAUGUS | 357487 | 1906 | 240 | Solar | 12_25W3 | 2021-05-14 13:38 | 2021-05-18 | 26 | 16 | 10 | 2021-06-24 | 2022-11-03 | 343 | 319 | 24 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | SEEKONK | 348306 | 2771 | 499.9 | Solar | 05_7L2 | 2021-05-14 15:45 | 2021-05-17 | 53 | 40 | 13 | [10 empty] | 2021-08-02 | 2021-09-11 | 29 | 3 | 26 | [10 empty] | 2022-06-29 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ROCKLAND | 348314 | 2370 | 366.6 | Solar | 07_95W4 | 2021-05-14 17:13 | 2021-05-17 | 53 | 40 | 13 | [10 empty] | 2021-08-02 | 2021-09-11 | 29 | 3 | 26 | [10 empty] | 2022-08-05 |  |  |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | SALEM | 348179 | 1970 | 499.9 | Solar | 12_29W6 | 2021-05-14 19:27 | 2021-05-18 | 373 | 363 | 10 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEOMINSTER | 348269 | 1453 | 400 | Solar | 01_207W3 | 2021-05-14 19:27 | 2021-05-18 | 373 | 363 | 10 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 338817 | 1844 | 937.5 | Solar | 14_74L1 | 2021-05-17 09:39 | 2021-05-18 | 55 | 45 | 10 | [10 empty] | 2021-08-05 | 2021-09-08 | 24 | 3 | 21 | [10 empty] | 2022-08-18 | 2021-05-17 13:48 |  |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | MEDFORD | 357707 | 2155 | 66.6 | Solar | 12_64J4 | 2021-05-17 13:48 | 2021-05-18 | 248 | 244 | 4 | [25 empty] | 2022-08-05 |  | 2024-07-11 |  | EXP | [8 empty] | 2024-04-12 | Connected |  | No
National Grid | CHELMSFORD | 202052 | 1824 | 4975 | Solar | 14_2L4 | 2021-05-18 09:13 | 2021-05-19 | 61 | 41 | 20 | [29 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SCITUATE | 358914 | 2066 | 9.8 | Solar | 07_915W82 | 2021-05-18 12:36 | 2021-05-19 | 1 | 1 | 0 | 2021-05-21 | 2021-06-28 | 25 | 0 | 25 | [20 empty] | 2021-06-29 |  | 2022-05-20 |  | EXP | [8 empty] | 2021-08-16 | Connected |  | No
National Grid | BEVERLY | 358932 | 1915 | 10 | Solar | 12_12L2 | 2021-05-18 14:14 | 2021-05-19 | 3 | 3 | 0 | 2021-05-25 | 2021-06-29 | 24 | 0 | 24 | [20 empty] | 2021-07-01 |  | 2022-07-20 |  | EXP | [8 empty] | 2021-09-14 | Connected |  | No
National Grid | SEEKONK | 358947 | 2771 | 9.54 | Solar | 05_3J3 | 2021-05-18 16:49 | 2021-05-19 | 7 | 4 | 3 | 2021-06-01 | 2021-07-06 | 24 | 0 | 24 | [20 empty] | 2021-07-15 |  | 2022-07-23 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MANCHESTER | 359131 | 1944 | 5.22 | Solar | 12_28L2 | 2021-05-19 10:47 | 2021-05-20 | 12 | 11 | 1 | 2021-06-08 | 2021-07-08 | 22 | 0 | 22 | [20 empty] | 2021-07-09 |  | 2022-06-06 |  | EXP | [8 empty] | 2021-08-05 | Connected |  | No
National Grid | HOUSATONIC | 359175 | 1236 | 9.6 | Solar | 09_1109W3 | 2021-05-19 13:21 | 2021-05-20 | 14 | 13 | 1 | 2021-06-10 | 2021-07-14 | 24 | 0 | 24 | [20 empty] | 2021-07-15 | 2021-05-19 14:09 | 2022-07-18 |  | EXP | [8 empty] | 2021-10-21 | Connected |  | No
National Grid | BROCKTON | 350043 | 2302 | 7.6 | Solar | 07_911W56 | 2021-05-19 14:09 | 2021-05-20 | 1 | 0 | 1 | 2021-05-24 | 2021-06-28 | 25 | 0 | 25 | [20 empty] | 2021-07-08 |  | 2022-08-26 |  | EXP |  | 2022-04-08 | 2022-04-22 | 15 | 0 | 15 |  |  | 2022-06-01 | Connected |  | No
National Grid | WEST NEWBURY | 356972 | 1985 | 7.6 | Solar | 14_47L1 | 2021-05-20 11:38 | 2021-05-21 | 0 | 0 | 0 | 2021-05-24 | 2021-06-29 | 25 | 0 | 25 | [20 empty] | 2021-07-01 |  | 2022-05-20 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 357858 | 1602 | 2.88 | Solar | 01_6W2 | 2021-05-20 11:49 | 2021-05-21 | 2 | 0 | 2 | 2021-05-26 | 2021-06-29 | 23 | 0 | 23 | [20 empty] | 2021-07-07 | 2021-05-20 16:10 | 2023-11-07 |  | EXP | [8 empty] | 2023-03-08 | Connected |  | No
National Grid | WESTBOROUGH | 351004 | 1581 | 220 | Solar | 05_312W2 | 2021-05-20 16:10 | 2021-05-21 | 43 | 33 | 10 | [10 empty] | 2021-07-23 | 2021-08-27 | 26 | 3 | 23 | [10 empty] | 2022-06-01 |  | 2023-11-21 | Yes | STD |  | 2023-03-30 | 2023-04-15 | 16 | 0 | 16 |  |  | 2023-11-29 | Connected |  | No
National Grid | DRACUT | 359517 | 1826 | 15.12 | Solar | 14_78L1 | 2021-05-20 16:12 | 2021-05-21 | 42 | 35 | 7 | 2021-07-23 | 2021-08-24 | 23 | 2 | 21 | [20 empty] | 2021-08-25 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MARLBOROUGH | 355075 | 1752 | 166.6 | Solar | 05_311W5 | 2021-05-21 13:32 | 2021-05-24 | 9 | 0 | 9 | [10 empty] | 2021-06-07 | 2021-08-17 | 41 | 16 | 25 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | AUBURN | 359795 | 1501 | 9.6 | Solar | 01_406L2 | 2021-05-21 19:03 | 2021-05-24 | 0 | 0 | 0 | 2021-05-25 | 2021-06-29 | 24 | 0 | 24 | [20 empty] | 2021-07-01 |  | 2022-07-19 |  | EXP | [8 empty] | 2021-11-10 | Connected |  | No
National Grid | BILLERICA | 357954 | 1821 | 20 | Solar | 14_70L5 | 2021-05-24 10:12 | 2021-05-25 | 0 | 0 | 0 | 2021-05-26 | 2021-06-30 | 25 | 0 | 25 | [20 empty] | 2021-07-02 | 2021-05-24 15:37 | 2022-05-24 |  | EXP | [8 empty] | 2021-07-09 | Connected |  | No
National Grid | LONGMEADOW | 324797 | 1028 | 3000 | Solar | 09_508L2 | 2021-05-24 15:37 | 2021-05-25 | 37 | 27 | 10 | [10 empty] | 2021-07-19 | 2021-10-20 | 66 | 46 | 20 | [10 empty] | 2023-07-27 |  |  | Yes | STD | [9 empty] | Design |  | No
National Grid | EAST LONGMEADOW | 324800 | 1028 | 432 | Solar | 09_522L2 | 2021-05-24 15:39 | 2021-05-25 | 21 | 10 | 11 | [10 empty] | 2021-06-24 | 2021-07-30 | 26 | 3 | 23 | [10 empty] | 2022-05-13 |  |  |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | ATHOL | 360037 | 1331 | 11.4 | Solar | 09_702W1 | 2021-05-24 16:48 | 2021-05-25 | 6 | 6 | 0 | 2021-06-03 | 2021-07-08 | 24 | 0 | 24 | [20 empty] | 2021-07-16 | 2021-05-25 04:23 | 2022-07-23 |  | EXP | [8 empty] | 2022-01-26 | Connected |  | No
National Grid | SOUTH ATTLEBORO | 355741 | 2703 | 10 | Solar | 05_9L6 | 2021-05-25 04:23 | 2021-05-25 | 46 | 36 | 10 | 2021-05-28 | 2021-07-02 | 25 | 0 | 25 | [20 empty] | 2021-07-15 |  | 2022-11-03 | Yes | EXP |  | 2021-08-19 | 2021-10-12 | 23 | 3 | 20 |  |  | 2021-11-22 | Connected |  | No
National Grid | METHUEN | 357875 | 1844 | 9.8 | Solar | 14_74L5 | 2021-05-25 16:54 | 2021-05-26 | 0 | 0 | 0 | 2021-05-27 | 2021-07-01 | 25 | 0 | 25 | [20 empty] | 2021-07-06 | 2021-05-25 17:34 | 2022-08-08 |  | EXP | [8 empty] | 2022-04-11 | Connected |  | No
National Grid | REHOBOTH | 355588 | 2769 | 8.7 | Solar | 05_7L4 | 2021-05-25 17:34 | 2021-05-26 | 5 | 2 | 3 | 2021-06-04 | 2021-07-08 | 24 | 0 | 24 | [20 empty] | 2021-07-28 |  | 2023-03-01 | Yes | EXP |  | 2021-12-24 | 2022-02-24 | 63 | 0 | 63 |  |  | 2022-03-05 | Connected |  | No
National Grid | WORCESTER | 357062 | 1605 | 7.6 | Solar | 01_27W4 | 2021-05-26 09:27 | 2021-05-27 | 4 | 0 | 4 | 2021-06-04 | 2021-07-08 | 24 | 0 | 24 | [20 empty] | 2021-07-15 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | ANDOVER | 359718 | 1810 | 54.6 | Solar | 14_54L3 | 2021-05-26 12:29 | 2021-05-27 | 7 | 1 | 6 | 2021-06-09 | 2021-07-12 | 23 | 0 | 23 | [20 empty] | 2021-07-16 |  | 2022-08-16 |  | EXP | [8 empty] | 2022-02-09 | Connected |  | No
National Grid | NEWBURYPORT | 354525 | 1950 | 100 | Solar | 14_36L2 | 2021-05-27 10:07 | 2021-05-28 | 24 | 14 | 10 | 2021-07-06 | 2021-08-03 | 21 | 0 | 21 | [20 empty] | 2021-08-04 | 2021-05-27 10:30 | 2023-04-09 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | RANDOLPH | 354572 | 2368 | 3.8 | Solar | 07_97W3 | 2021-05-27 10:30 | 2021-05-28 | 1 | 0 | 1 | 2021-06-02 | 2021-07-06 | 23 | 0 | 23 | [20 empty] | 2021-07-14 |  | 2022-12-11 | Yes | EXP |  | 2021-12-07 | 2021-12-09 | 3 | 0 | 3 |  |  | 2022-03-17 | Connected |  | No
National Grid | NANTUCKET | 360480 | 2554 | 7.6 | Solar | 04_101L6 | 2021-05-27 15:05 | 2021-05-28 | 1 | 0 | 1 | 2021-06-02 | 2021-07-06 | 23 | 0 | 23 | [20 empty] | 2021-07-08 |  | 2022-07-13 |  | EXP | [8 empty] | 2021-10-20 | Connected |  | No
National Grid | BROCKTON | 342718 | 2301 | 10 | Solar | 07_98W46 | 2021-05-27 19:05 | 2021-05-28 | 3 | 0 | 3 | 2021-06-04 | 2021-07-08 | 24 | 0 | 24 | [20 empty] | 2021-07-28 | 2021-05-28 12:58 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SALEM | 357389 | 1970 | 200 | Solar | 12_49W2 | 2021-05-28 12:58 | 2021-06-01 | 202 | 186 | 16 | 2022-03-21 | 2022-05-09 | 35 | 14 | 21 | [20 empty] | 2022-05-20 | 2021-05-28 14:25 | 2023-11-25 | Yes | EXP | [8 empty] | 2023-12-01 | Connected |  | No
National Grid | HAMPDEN | 354101 | 1036 | 4992 | Solar | 09_507L1 | 2021-05-28 14:25 | 2021-06-01 | 28 | 16 | 12 | [10 empty] | 2021-07-12 | 2021-08-04 | 18 | 0 | 18 | [10 empty] | 2022-10-25 | 2021-06-01 12:09 | 2025-05-26 | Yes | STD | [9 empty] | Design |  | No
National Grid | WARE | 361080 | 1082 | 9.8 | Solar | 09_501L1 | 2021-06-01 12:09 | 2021-06-02 | 0 | 0 | 0 | 2021-06-03 | 2021-07-08 | 24 | 0 | 24 | [20 empty] | 2021-07-09 | 2021-06-01 14:59 | 2022-12-17 | Yes | EXP |  | 2021-09-11 | 2021-10-01 | 21 | 0 | 21 |  |  | 2022-08-08 | Connected |  | No
National Grid | FRANKLIN | 346755 | 2038 | 299 | Solar | 05_344W2 | 2021-06-01 14:59 | 2021-06-02 | 40 | 32 | 8 | [10 empty] | 2021-07-29 | 2021-09-02 | 26 | 3 | 23 | [10 empty] | 2022-05-03 | 2021-06-01 15:00 | 2025-01-24 | Yes | STD | [9 empty] | Construction |  | No
National Grid | FRANKLIN | 346796 | 2038 | 250 | Solar | 05_344W2 | 2021-06-01 15:00 | 2021-06-02 | 40 | 32 | 8 | [10 empty] | 2021-07-29 | 2021-09-02 | 26 | 3 | 23 | [10 empty] | 2022-05-03 | 2021-06-01 15:06 | 2024-07-24 | Yes | STD | [9 empty] | Construction |  | No
National Grid | FRANKLIN | 346790 | 2038 | 299 | Solar | 05_344W2 | 2021-06-01 15:06 | 2021-06-02 | 40 | 32 | 8 | [10 empty] | 2021-07-29 | 2021-09-02 | 25 | 3 | 22 | [10 empty] | 2022-05-03 |  | 2025-01-25 | Yes | STD | [9 empty] | Construction |  | No
National Grid | LANCASTER | 361381 | 1523 | 7.6 | Solar | 01_225W1 | 2021-06-01 15:23 | 2021-06-02 | 48 | 46 | 2 | 2021-08-11 | 2021-09-07 | 18 | 3 | 15 | [20 empty] | 2021-09-08 | 2021-06-01 16:39 | 2022-09-14 |  | EXP | [8 empty] | 2022-06-03 | Connected |  | No
National Grid | STOUGHTON | 355909 | 2072 | 480 | Solar | 07_913W69 | 2021-06-01 16:39 | 2021-06-02 | 17 | 9 | 8 | 2021-06-25 | 2021-08-10 | 33 | 10 | 23 | [20 empty] | 2021-09-29 | 2021-06-03 09:18 | 2024-12-08 |  | EXP |  | 2022-02-01 |  | 804 | 720 | 84 |  |  |  | Construction |  | No
National Grid | DRACUT | 356821 | 1826 | 7.6 | Solar | 14_78L1 | 2021-06-03 09:18 | 2021-06-30 | 2 | 0 | 2 | 2021-07-01 | 2021-07-28 | 19 | 0 | 19 | [20 empty] | 2021-08-03 |  | 2023-03-08 | Yes | EXP |  | 2022-01-26 | 2022-03-07 | 41 | 0 | 41 |  |  | 2022-08-11 | Connected |  | Yes
National Grid | SHIRLEY | 361884 | 1464 | 9.8 | Solar | 01_227W3 | 2021-06-03 16:25 | 2021-06-04 | 3 | 2 | 1 | 2021-06-09 | 2021-07-12 | 23 | 0 | 23 | [20 empty] | 2021-07-13 |  | 2022-08-07 |  | EXP | [8 empty] | 2022-01-27 | Connected |  | No
National Grid | GARDNER | 355755 | 1440 | 10 | Solar | 01_607W1 | 2021-06-07 09:06 | 2021-06-08 | 6 | 0 | 6 | 2021-06-16 | 2021-07-16 | 22 | 0 | 22 | [20 empty] | 2021-07-27 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WINCHENDON | 361142 | 1475 | 17.6 | Solar | 01_612W1 | 2021-06-07 12:02 | 2021-06-08 | 51 | 50 | 1 | 2021-08-18 | 2022-04-01 | 155 | 127 | 28 | [22 empty] | 2022-08-17 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WILBRAHAM | 353082 | 1095 | 433.3 | Solar | 09_507L3 | 2021-06-08 14:50 | 2021-06-09 | 40 | 30 | 10 | [10 empty] | 2021-08-05 | 2021-09-15 | 29 | 3 | 26 | [10 empty] | 2022-09-27 | 2021-06-09 10:49 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ANDOVER | 360062 | 1810 | 130 | Natural Gas | 14_59L6 | 2021-06-09 10:49 | 2021-06-10 | 28 | 18 | 10 | [10 empty] | 2021-07-21 | 2021-10-05 | 54 | 29 | 25 | [10 empty] | 2022-06-03 | 2021-06-09 12:24 | 2023-08-20 |  | STD | [8 empty] | 2022-11-21 | Connected |  | No
National Grid | LYNN | 362370 | 1904 | 10 | Solar | 12_24W2 | 2021-06-09 12:24 | 2021-06-10 | 4 | 3 | 1 | 2021-06-16 | 2021-07-22 | 26 | 3 | 23 | [20 empty] | 2021-07-23 |  | 2022-10-12 | Yes | EXP |  | 2021-09-16 | 2021-10-12 | 24 | 0 | 24 |  |  | 2021-10-18 | Connected |  | No
National Grid | SOMERSET | 348299 | 2725 | 433.3 | Solar | 05_11W84 | 2021-06-09 13:21 | 2021-06-10 | 44 | 35 | 9 | [10 empty] | 2021-08-12 | 2021-09-22 | 29 | 3 | 26 | [10 empty] | 2022-07-28 |  |  |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | SEEKONK | 363042 | 2771 | 15.2 | Solar | 05_7L1 | 2021-06-09 19:37 | 2021-06-10 | 15 | 13 | 2 | 2021-07-01 | 2021-07-28 | 19 | 0 | 19 | [20 empty] | 2021-07-30 |  | 2023-01-01 |  | EXP | [8 empty] | 2023-01-03 | Connected |  | No
National Grid | FRANKLIN | 362971 | 2038 | 11.4 | Solar | 05_344W5 | 2021-06-09 19:57 | 2021-06-10 | 44 | 41 | 3 | 2021-08-20 | 2021-09-29 | 28 | 3 | 25 | [20 empty] | 2021-10-01 | 2021-06-09 23:33 | 2022-08-18 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | QUINCY | 342873 | 2171 | 2575 | Solar | 07_1102 | 2021-06-09 23:33 | 2021-06-10 | 26 | 16 | 10 | [10 empty] | 2021-07-19 | 2021-08-20 | 25 | 0 | 25 | [10 empty] | 2022-04-21 |  | 2023-10-23 | Yes | STD |  | 2023-06-14 | 2023-06-13 | 0 | 0 | 0 |  |  | 2023-10-26 | Connected |  | No
National Grid | QUINCY | 348184 | 2169 | 499.9 | Solar | 07_3W1 | 2021-06-10 14:02 | 2021-06-11 | 33 | 24 | 9 | [10 empty] | 2021-07-29 | 2021-09-02 | 26 | 3 | 23 | [10 empty] | 2022-06-29 |  |  |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 348265 | 1844 | 499.9 | Solar | 14_74L2 | 2021-06-10 14:07 | 2021-06-11 | 315 | 315 | 0 | [26 empty] | 2021-06-10 14:08 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BELCHERTOWN | 356005 | 1007 | 9.8 | Solar | 09_509L1 | 2021-06-10 14:08 | 2021-06-11 | 3 | 0 | 3 | 2021-06-16 | 2021-07-16 | 21 | 0 | 21 | [20 empty] | 2021-07-27 |  | 2023-04-21 | Yes | EXP |  | 2022-03-08 | 2022-04-21 | 45 | 0 | 45 |  |  | 2022-06-07 | Connected |  | No
National Grid | PEMBROKE | 358406 | 2359 | 9.8 | Solar | 07_910W52 | 2021-06-10 14:16 | 2021-06-11 | 3 | 0 | 3 | 2021-06-16 | 2021-07-16 | 22 | 0 | 22 | [20 empty] | 2021-07-27 |  | 2022-08-03 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NANTUCKET | 362967 | 2554 | 19.99 | Solar | 04_101L2 | 2021-06-10 14:34 | 2021-06-11 | 16 | 13 | 3 | 2021-07-02 | 2021-07-28 | 18 | 0 | 18 | [20 empty] | 2021-08-04 |  | 2022-08-20 |  | EXP | [8 empty] | 2021-10-07 | Connected |  | No
National Grid | LAWRENCE | 336498 | 1843 | 10 | Solar | 14_61L1 | 2021-06-10 14:54 | 2021-06-11 | 56 | 55 | 1 | 2021-08-31 | 2021-10-04 | 24 | 0 | 24 | [20 empty] | 2021-10-06 |  | 2022-08-29 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SEEKONK | 347852 | 2771 | 995 | Solar | 05_7L3 | 2021-06-10 15:19 | 2021-06-11 | 24 | 14 | 10 | [10 empty] | 2021-07-15 | 2021-08-11 | 26 | 0 | 26 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WENHAM | 363282 | 1984 | 7.6 | Solar | 12_18L2 | 2021-06-10 19:30 | 2021-06-11 | 1 | 0 | 1 | 2021-06-14 | 2021-07-12 | 20 | 0 | 20 | [20 empty] | 2021-07-13 |  | 2022-08-27 |  | EXP | [8 empty] | 2022-01-27 | Connected |  | No
National Grid | BEVERLY | 361035 | 1915 | 3.8 | Solar | 12_12L2 | 2021-06-11 13:48 | 2021-06-14 | 3 | 0 | 3 | 2021-06-17 | 2021-07-16 | 21 | 0 | 21 | [20 empty] | 2021-07-27 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 355333 | 2302 | 480 | Natural Gas | 07_91W43 | 2021-06-14 09:45 | 2021-06-15 | 64 | 52 | 12 | [10 empty] | 2021-09-15 | 2021-10-20 | 25 | 0 | 25 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | LANCASTER | 362751 | 1523 | 10 | Solar | 01_225W1 | 2021-06-15 08:39 | 2021-06-16 | 1 | 0 | 1 | 2021-06-17 | 2021-07-22 | 25 | 0 | 25 | [20 empty] | 2021-07-23 |  | 2022-07-29 |  | EXP | [8 empty] | 2021-09-27 | Connected |  | Yes
National Grid | NORTH ANDOVER | 363866 | 1845 | 9.8 | Solar | 14_56L2 | 2021-06-15 12:00 | 2021-06-16 | 2 | 0 | 2 | 2021-06-18 | 2021-07-16 | 20 | 0 | 20 | [20 empty] | 2021-07-27 |  | 2022-08-26 |  | EXP | [8 empty] | 2022-04-15 | Connected |  | No
National Grid | PALMER | 358673 | 1069 | 10 | Solar | 09_523L4 | 2021-06-15 12:12 | 2021-06-15 | 12 | 4 | 8 | 2021-07-02 | 2021-07-28 | 18 | 0 | 18 | [20 empty] | 2021-08-02 |  | 2022-09-30 |  | EXP |  | 2021-09-17 | 2021-09-29 | 13 | 0 | 13 |  |  | 2022-01-19 | Connected |  | Yes
National Grid | MONTEREY | 364015 | 1245 | 16 | Solar | 09_1109W1 | 2021-06-15 13:01 | 2021-06-16 | 15 | 12 | 3 | 2021-07-07 | 2021-08-02 | 19 | 0 | 19 | [20 empty] | 2021-08-05 |  | 2022-09-20 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | GRANBY | 364394 | 1033 | 19 | Solar | 09_527L1 | 2021-06-16 15:02 | 2021-06-17 | 2 | 1 | 1 | 2021-06-18 | 2021-07-16 | 20 | 0 | 20 | [20 empty] | 2021-07-16 |  | 2022-08-14 |  | EXP | [8 empty] | 2021-09-21 | Connected |  | No
National Grid | WORCESTER | 360536 | 1607 | 7.6 | Solar | 01_8W1 | 2021-06-17 16:33 | 2021-06-18 | 2 | 0 | 2 | 2021-06-22 | 2021-07-27 | 25 | 0 | 25 | [20 empty] | 2021-08-03 |  | 2022-08-13 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 364216 | 2301 | 199.8 | Solar | 07_92W44 | 2021-06-18 09:01 | 2021-06-21 | 13 | 3 | 10 | 2021-07-08 | 2021-08-03 | 19 | 0 | 19 | [20 empty] | 2021-08-04 |  | 2022-12-10 |  | EXP | [8 empty] | 2022-11-28 | Connected |  | No
National Grid | RANDOLPH | 352832 | 2368 | 5.76 | Solar | 07_5W3 | 2021-06-18 14:22 | 2021-06-21 | 5 | 0 | 5 | 2021-06-28 | 2021-07-21 | 17 | 0 | 17 | [20 empty] | 2021-07-29 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MILFORD | 359562 | 1757 | 480 | Solar | 05_335W2 | 2021-06-18 17:35 | 2021-06-21 | 13 | 3 | 10 | [10 empty] | 2021-07-08 | 2021-07-30 | 17 | 0 | 17 | [11 empty] | 2021-06-21 16:03 |  |  | STD | [9 empty] | Group Study |  | Yes
National Grid | WEBSTER | 365160 | 1570 | 15.6 | Solar | 01_412L1 | 2021-06-21 16:03 | 2021-06-22 | 2 | 0 | 2 | 2021-06-24 | 2021-07-16 | 16 | 0 | 16 | [20 empty] | 2021-07-26 |  | 2023-11-05 | Yes | EXP |  | 2022-07-15 | 2022-08-26 | 43 | 0 | 43 |  |  | 2022-12-07 | Connected |  | No
National Grid | MILFORD | 361359 | 1757 | 7.6 | Solar | 05_336W3 | 2021-06-22 12:16 | 2021-06-23 | 4 | 0 | 4 | 2021-06-29 | 2021-07-21 | 16 | 0 | 16 | [20 empty] | 2021-07-23 | 2021-06-22 16:05 | 2022-06-22 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTHAMPTON | 359928 | 1060 | 8.12 | Solar | 09_909W2 | 2021-06-22 16:05 | 2021-06-23 | 3 | 0 | 3 | 2021-06-28 | 2021-07-08 | 8 | 0 | 8 | [20 empty] | 2021-07-08 |  | 2023-01-14 | Yes | EXP |  | 2021-11-16 | 2021-11-15 | 0 | 0 | 0 |  |  | 2022-03-03 | Connected |  | No
National Grid | MILLVILLE | 365368 | 1529 | 7.6 | Solar | 05_321W9 | 2021-06-23 11:59 | 2021-06-24 | 3 | 0 | 3 | 2021-06-29 | 2021-07-21 | 16 | 0 | 16 | [20 empty] | 2021-07-23 |  | 2022-10-03 |  | EXP | [8 empty] | 2022-08-31 | Connected |  | No
National Grid | MANCHESTER | 365294 | 1944 | 9.86 | Solar | 12_51T1 | 2021-06-23 12:14 | 2021-06-24 | 17 | 14 | 3 | 2021-07-19 | 2021-08-20 | 25 | 0 | 25 | [20 empty] | 2021-08-23 |  | 2022-09-17 |  | EXP | [8 empty] | 2021-12-01 | Connected |  | No
National Grid | CHARLTON | 365577 | 1507 | 7.6 | Solar | 01_415L1 | 2021-06-23 13:47 | 2021-06-24 | 18 | 14 | 4 | 2021-07-21 | 2021-08-23 | 24 | 0 | 24 | [20 empty] | 2021-08-24 |  | 2022-09-22 |  | EXP | [8 empty] | 2021-11-01 | Connected |  | Yes
National Grid | WORCESTER | 310622 | 1609 | 11.4 | Solar | 01_23W2 | 2021-06-23 16:34 | 2021-06-24 | 2 | 0 | 2 | 2021-06-28 | 2021-07-21 | 17 | 0 | 17 | [20 empty] | 2021-07-29 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | PALMER | 365209 | 1069 | 15.2 | Solar | 09_523L1 | 2021-06-23 17:37 | 2021-06-24 | 2 | 0 | 2 | 2021-06-28 | 2021-07-21 | 17 | 0 | 17 | [20 empty] | 2021-07-29 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | EAST BRIDGEWATER | 353508 | 2333 | 498 | Solar | 07_797W42 | 2021-06-23 18:26 | 2021-06-24 | 53 | 44 | 9 | [10 empty] | 2021-09-09 | 2021-12-06 | 60 | 17 | 43 | [10 empty] | 2022-06-07 | 2021-06-24 10:33 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | HAVERHILL | 357413 | 1832 | 290 | Solar | 14_48L1 | 2021-06-24 10:33 | 2021-06-25 | 109 | 99 | 10 | [10 empty] | 2021-12-02 | 2022-05-24 | 121 | 96 | 25 | [10 empty] | 2022-12-30 | 2021-06-24 11:06 | 2024-05-11 | Yes | STD | [9 empty] | Construction |  | No
National Grid | ATHOL | 363344 | 1331 | 10 | Solar | 09_702W1 | 2021-06-24 11:06 | 2021-06-25 | 3 | 0 | 3 | 2021-06-30 | 2021-07-23 | 17 | 0 | 17 | [20 empty] | 2021-07-23 |  | 2022-11-09 | Yes | EXP |  | 2021-09-24 | 2021-11-04 | 42 | 4 | 38 |  |  | 2021-11-10 | Connected |  | No
National Grid | PEMBROKE | 365824 | 2359 | 7.6 | Solar | 07_910W25 | 2021-06-24 12:36 | 2021-06-25 | 2 | 0 | 2 | 2021-06-29 | 2021-07-21 | 16 | 0 | 16 | [20 empty] | 2021-07-28 |  | 2023-07-05 |  | EXP | [8 empty] | 2022-07-13 | Connected |  | No
National Grid | BRIDGEWATER | 365913 | 2324 | 15.12 | Solar | 07_912W21 | 2021-06-24 15:03 | 2021-06-25 | 4 | 0 | 4 | 2021-07-01 | 2021-07-28 | 19 | 0 | 19 | [20 empty] | 2021-08-05 |  | 2023-10-12 |  | EXP | [8 empty] | 2022-11-14 | Connected |  | No
National Grid | BOXFORD | 365918 | 1921 | 15.36 | Solar | 14_56L3 | 2021-06-24 15:22 | 2021-06-25 | 4 | 0 | 4 | 2021-07-01 | 2021-07-28 | 19 | 0 | 19 | [20 empty] | 2021-08-05 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RANDOLPH | 366170 | 2368 | 6 | Solar | 07_97W1 | 2021-06-25 15:34 | 2021-06-28 | 4 | 2 | 2 | 2021-07-01 | 2021-07-28 | 19 | 0 | 19 | [20 empty] | 2021-07-30 |  | 2022-08-10 |  | EXP | [8 empty] | 2021-12-20 | Connected |  | No
National Grid | NEW BRAINTREE | 363219 | 1531 | 6 | Solar | 09_604W2 | 2021-06-25 18:39 | 2021-06-28 | 4 | 2 | 2 | 2021-07-01 | 2021-07-28 | 19 | 0 | 19 | [20 empty] | 2021-07-30 | 2021-06-28 08:13 | 2022-09-11 |  | EXP | [8 empty] | 2022-07-05 | Connected |  | No
National Grid | SALEM | 364600 | 1970 | 6 | Solar | 12_29W6 | 2021-06-28 08:13 | 2021-06-29 | 48 | 47 | 1 | 2021-09-03 | 2021-10-07 | 24 | 0 | 24 | [20 empty] | 2021-10-07 |  | 2023-05-13 | Yes | EXP |  | 2022-03-24 | 2022-04-21 | 29 | 0 | 29 |  |  | 2022-05-16 | Connected |  | No
National Grid | NORWELL | 364705 | 2061 | 72 | Solar | 07_96W44 | 2021-06-28 10:49 | 2021-06-29 | 17 | 9 | 8 | 2021-07-23 | 2021-08-12 | 15 | 0 | 15 | [20 empty] | 2021-08-13 | 2021-06-28 11:00 | 2023-04-09 |  | EXP | [8 empty] | 2023-04-07 | Connected |  | No
National Grid | HAVERHILL | 364023 | 1832 | 9.8 | Solar | 14_43L2 | 2021-06-28 11:00 | 2021-06-29 | 1 | 0 | 1 | 2021-06-30 | 2021-07-26 | 18 | 0 | 18 | [20 empty] | 2021-07-29 |  | 2023-12-26 | Yes | EXP |  | 2022-01-18 | 2022-07-26 | 189 | 0 | 189 |  |  | 2023-08-03 | Connected |  | No
National Grid | ROCKPORT | 366436 | 1966 | 6.96 | Solar | 12_40L1 | 2021-06-28 15:02 | 2021-06-29 | 2 | 0 | 2 | 2021-07-01 | 2021-07-02 | 2 | 0 | 2 | [21 empty] | 2021-06-29 15:55 | 2022-06-28 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOUTHBOROUGH | 366728 | 1772 | 7.6 | Solar | 05_314W2 | 2021-06-29 15:55 | 2021-06-30 | 41 | 38 | 3 | 2021-08-27 | 2021-10-01 | 25 | 0 | 25 | [20 empty] | 2021-10-01 |  | 2023-12-02 | Yes | EXP |  | 2022-01-06 | 2022-10-31 | 299 | 0 | 299 |  |  | 2023-01-25 | Connected |  | No
National Grid | BOLTON | 366741 | 1740 | 7.6 | Solar | 01_216W6 | 2021-06-29 17:47 | 2021-06-30 | 1 | 0 | 1 | 2021-07-01 | 2021-07-28 | 19 | 0 | 19 | [20 empty] | 2021-08-19 | 2021-06-30 08:35 | 2022-10-27 |  | EXP | [8 empty] | 2022-02-17 | Connected |  | No
National Grid | ALFORD | 360945 | 1230 | 10 | Solar | 09_1109W3 | 2021-06-30 08:35 | 2021-07-01 | 4 | 0 | 4 | 2021-07-08 | 2021-08-02 | 18 | 0 | 18 | [20 empty] | 2021-08-09 | 2021-06-30 13:30 | 2023-01-11 | Yes | EXP |  | 2021-12-23 | 2022-01-10 | 19 | 0 | 19 |  |  | 2022-01-24 | Connected |  | Yes
National Grid | BRIDGEWATER | 366888 | 2324 | 15.2 | Solar | 07_912W55 | 2021-06-30 13:30 | 2021-07-01 | 23 | 21 | 2 | 2021-08-03 | 2021-08-25 | 16 | 2 | 14 | [20 empty] | 2021-08-25 |  | 2022-12-21 | Yes | EXP |  | 2021-10-23 | 2021-12-17 | 56 | 4 | 52 |  |  | 2023-01-10 | Connected |  | No
National Grid | BILLERICA | 367044 | 1821 | 19 | Solar | 14_70L6 | 2021-06-30 17:36 | 2021-07-01 | 1 | 0 | 1 | 2021-07-02 | 2021-07-28 | 18 | 0 | 18 | [20 empty] | 2021-08-02 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LYNN | 360157 | 1902 | 7.6 | Solar | 12_1J901 | 2021-07-01 10:06 | 2021-07-02 | 6 | 0 | 6 | 2021-07-14 | 2021-08-05 | 17 | 0 | 17 | [20 empty] | 2021-08-11 | 2021-07-01 10:25 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LYNN | 362142 | 1905 | 7.6 | Solar | 12_29W1 | 2021-07-01 10:25 | 2021-07-02 | 6 | 0 | 6 | 2021-07-14 | 2021-08-05 | 17 | 0 | 17 | [20 empty] | 2021-08-11 |  | 2024-08-21 | Yes | EXP |  | 2022-03-22 | 2023-08-18 | 515 | 0 | 515 |  |  | 2023-09-08 | Connected |  | No
National Grid | NEWBURY | 367210 | 1951 | 7.6 | Solar | 14_60L1 | 2021-07-01 12:27 | 2021-07-02 | 84 | 63 | 21 | 2021-11-02 | 2021-12-03 | 22 | 0 | 22 | [20 empty] | 2021-12-06 |  | 2022-10-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HARVARD | 367483 | 1451 | 20 | Solar | 01_216W6 | 2021-07-02 11:52 | 2021-07-06 | 1 | 0 | 1 | 2021-07-07 | 2021-08-02 | 19 | 0 | 19 | [20 empty] | 2021-08-05 |  | 2022-09-14 |  | EXP | [8 empty] | 2022-09-12 | Connected |  | No
National Grid | UXBRIDGE | 366925 | 1569 | 9992 | Other | 05_321W6 | 2021-07-02 13:20 | 2021-07-06 | 13 | 7 | 6 | [10 empty] | 2021-07-23 | 2021-07-30 | 6 | 0 | 6 | [11 empty] | 2021-07-04 05:31 |  |  | STD | [9 empty] | Group Study |  | No
National Grid | NORTHAMPTON | 362762 | 1060 | 7.6 | Solar | 09_901W3 | 2021-07-04 05:31 | 2021-07-06 | 1 | 0 | 1 | 2021-07-08 | 2021-08-02 | 18 | 0 | 18 | [20 empty] | 2021-08-09 | 2021-07-04 05:33 | 2023-03-02 | Yes | EXP |  | 2022-02-25 | 2022-03-01 | 5 | 0 | 5 |  |  | 2022-03-29 | Connected |  | Yes
National Grid | METHUEN | 361148 | 1844 | 7.6 | Solar | 14_74L2 | 2021-07-04 05:33 | 2021-07-02 | 2 | 0 | 2 | 2021-07-08 | 2021-08-02 | 18 | 0 | 18 | [20 empty] | 2021-08-09 |  | 2023-03-10 | Yes | EXP | [8 empty] | 2022-04-04 | Connected |  | Yes
National Grid | MARLBOROUGH | 365643 | 1752 | 7.54 | Solar | 05_311W5 | 2021-07-07 12:17 | 2021-07-08 | 1 | 0 | 1 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | TYNGSBORO | 368249 | 1879 | 7.6 | Solar | 14_21L1 | 2021-07-07 15:42 | 2021-07-08 | 17 | 16 | 1 | 2021-07-30 | 2021-08-18 | 14 | 0 | 14 | [20 empty] | 2021-08-19 |  | 2022-09-02 |  | EXP | [8 empty] | 2022-02-09 | Connected |  | No
National Grid | HAVERHILL | 368286 | 1830 | 15.2 | Solar | 14_76L3 | 2021-07-07 16:41 | 2021-07-08 | 31 | 30 | 1 | 2021-08-19 | 2021-09-28 | 27 | 3 | 24 | [20 empty] | 2021-09-28 |  | 2022-10-10 |  | EXP | [8 empty] | 2021-11-20 | Connected |  | No
National Grid | MILLBURY | 366738 | 1527 | 7.44 | Solar | 01_328W2 | 2021-07-07 17:05 | 2021-07-08 | 19 | 18 | 1 | 2021-08-03 | 2021-10-21 | 56 | 31 | 25 | [20 empty] | 2021-10-22 |  | 2022-11-17 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BEVERLY | 368295 | 1915 | 53.3 | Solar | 12_18L1 | 2021-07-07 17:36 | 2021-07-08 | 18 | 9 | 9 | 2021-08-02 | 2021-09-20 | 34 | 10 | 24 | [20 empty] | 2021-09-30 |  | 2022-10-06 |  | EXP | [8 empty] | 2021-12-27 | Connected |  | No
National Grid | SPENCER | 367365 | 1562 | 3.8 | Solar | 01_21W1 | 2021-07-08 13:22 | 2021-07-09 | 3 | 0 | 3 | 2021-07-14 | 2021-08-05 | 17 | 0 | 17 | [20 empty] | 2021-09-17 |  | 2022-11-07 |  | EXP | [8 empty] | 2022-03-02 | Connected |  | No
National Grid | ABINGTON | 368498 | 2351 | 7.6 | Solar | 07_60J1 | 2021-07-08 13:45 | 2021-07-09 | 32 | 31 | 1 | 2021-08-25 | 2021-09-30 | 26 | 1 | 25 | [20 empty] | 2021-10-01 | 2021-07-09 11:01 | 2023-01-08 |  | EXP | [8 empty] | 2022-10-19 | Connected |  | No
National Grid | LYNN | 367457 | 1904 | 7.6 | Solar | 12_24W2 | 2021-07-09 11:01 | 2021-07-12 | 1 | 0 | 1 | 2021-07-13 | 2021-08-09 | 20 | 0 | 20 | [20 empty] | 2021-08-09 | 2021-07-09 11:09 | 2022-08-16 | Yes | EXP |  | 2022-01-13 | 2022-03-31 | 78 | 0 | 78 |  |  | 2022-04-11 | Connected |  | No
National Grid | FOXBOROUGH | 367906 | 2035 | 57.6 | Solar | 05_3432W2 | 2021-07-09 11:09 | 2021-07-12 | 16 | 8 | 8 | 2021-08-03 | 2021-09-10 | 27 | 3 | 24 | 2021-12-01 | 2021-12-21 | 15 | 0 | 15 | [5 empty] | 2021-12-01 | 2021-12-21 | 15 | 0 | 15 | [5 empty] | 2022-03-18 |  | 2025-01-18 | Yes | EXP | [9 empty] | Construction |  | No
National Grid | TEWKSBURY | 362871 | 1876 | 7.83 | Solar | 14_70L8 | 2021-07-09 14:56 | 2021-07-12 | 2 | 0 | 2 | 2021-07-14 | 2021-08-05 | 17 | 0 | 17 | [20 empty] | 2021-08-11 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | TYNGSBORO | 368575 | 1879 | 80 | Solar | 01_210L1 | 2021-07-09 17:43 | 2021-07-12 | 9 | 3 | 6 | 2021-07-26 | 2021-08-26 | 24 | 0 | 24 | [20 empty] | 2021-08-30 |  | 2022-10-05 |  | EXP |  | 2022-05-10 | 2022-05-09 | 0 | 0 | 0 |  |  | 2022-08-17 | Connected |  | No
National Grid | LAWRENCE | 359565 | 1843 | 466.6 | Solar | 14_8T2 | 2021-07-09 19:42 | 2021-07-12 | 9 | 3 | 6 | 2021-07-26 | 2021-09-01 | 27 | 3 | 24 | [20 empty] | 2021-09-02 |  | 2023-03-11 |  | EXP | [8 empty] | 2022-08-12 | Connected |  | No
National Grid | WHITMAN | 351890 | 2382 | 7.6 | Solar | 07_93W43 | 2021-07-12 11:38 | 2021-07-13 | 22 | 21 | 1 | 2021-08-11 | 2021-09-17 | 26 | 3 | 23 | [20 empty] | 2021-09-17 | 2021-07-12 12:55 | 2023-01-04 |  | EXP | [8 empty] | 2022-04-15 | Connected |  | No
National Grid | FALL RIVER | 364046 | 2720 | 6.24 | Solar | 05_106W81 | 2021-07-12 12:55 | 2021-07-13 | 2 | 1 | 1 | 2021-07-14 | 2021-08-05 | 17 | 0 | 17 | [20 empty] | 2021-08-06 |  | 2023-02-08 | Yes | EXP |  | 2021-12-03 | 2022-02-08 | 68 | 0 | 68 |  |  | 2022-02-10 | Connected |  | No
National Grid | TYNGSBORO | 368610 | 1879 | 6 | Solar | 14_211L2 | 2021-07-12 13:52 | 2021-07-13 | 1 | 0 | 1 | 2021-07-14 | 2021-08-05 | 17 | 0 | 17 | [20 empty] | 2021-08-11 | 2021-07-12 14:16 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SALEM | 368795 | 1970 | 151.2 | Solar | 12_3J1 | 2021-07-12 14:16 | 2021-07-13 | 16 | 9 | 7 | [10 empty] | 2021-08-04 | 2021-11-16 | 72 | 46 | 26 | [10 empty] | 2022-06-16 |  | 2024-05-13 |  | STD |  | 2024-01-30 | 2024-01-29 | 0 | 0 | 0 |  |  |  | Completion Documents |  | Yes
National Grid | WESTFORD | 369368 | 1886 | 7.6 | Solar | 14_58L3 | 2021-07-13 12:12 | 2021-07-14 | 30 | 26 | 4 | 2021-08-25 | 2021-09-30 | 26 | 1 | 25 | [20 empty] | 2021-10-01 | 2021-07-13 13:16 | 2022-12-08 |  | EXP | [8 empty] | 2022-04-12 | Connected |  | No
National Grid | EASTON | 346959 | 2356 | 499 | Solar | 07_92W54 | 2021-07-13 13:16 | 2021-07-14 | 16 | 13 | 3 | [10 empty] | 2021-08-05 | 2021-11-19 | 74 | 37 | 37 | [10 empty] | 2022-06-08 | 2021-07-13 15:17 |  | Yes | STD | [9 empty] | Study |  | No
National Grid | LEOMINSTER | 367884 | 1453 | 10 | Solar | 01_219W2 | 2021-07-13 15:17 | 2021-07-14 | 3 | 0 | 3 | 2021-07-19 | 2021-08-11 | 18 | 0 | 18 | [20 empty] | 2021-08-18 | 2021-07-13 18:34 | 2023-08-08 | Yes | EXP |  | 2022-05-03 | 2022-05-17 | 15 | 0 | 15 |  |  | 2022-08-17 | Connected |  | Yes
National Grid | METHUEN | 365469 | 1844 | 7.6 | Solar | 14_74L2 | 2021-07-13 18:34 | 2021-07-14 | 3 | 0 | 3 | 2021-07-19 | 2021-08-06 | 15 | 0 | 15 | [20 empty] | 2021-10-19 | 2021-07-14 07:47 | 2024-08-16 | Yes | EXP |  | 2022-01-18 | 2022-02-22 | 36 | 0 | 36 |  |  |  | Withdrawn |  | No
National Grid | EASTON | 346957 | 2356 | 499 | Solar | 07_92W54 | 2021-07-14 07:47 | 2021-07-15 | 16 | 9 | 7 | [10 empty] | 2021-08-06 | 2021-11-19 | 73 | 37 | 36 | [10 empty] | 2022-06-08 |  |  | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | EASTON | 346956 | 2375 | 499 | Solar | 07_92W79 | 2021-07-14 07:51 | 2021-07-15 | 28 | 19 | 9 | [10 empty] | 2021-08-24 | 2021-11-16 | 58 | 32 | 26 | [10 empty] | 2022-06-08 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | EASTON | 346955 | 2375 | 499 | Solar | 07_92W79 | 2021-07-14 07:54 | 2021-07-15 | 15 | 6 | 9 | [10 empty] | 2021-08-05 | 2021-11-16 | 71 | 45 | 26 | [10 empty] | 2022-06-08 | 2021-07-14 07:57 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | AMESBURY | 343628 | 1913 | 499 | Solar | 14_275L4 | 2021-07-14 07:57 | 2021-07-15 | 28 | 19 | 9 | [10 empty] | 2021-08-24 | 2021-10-01 | 28 | 2 | 26 | [10 empty] | 2022-07-06 | 2021-07-14 07:57 |  | Yes | STD | [9 empty] | Study |  | No
National Grid | AMESBURY | 343629 | 1913 | 499 | Solar | 14_275L4 | 2021-07-14 07:57 | 2021-07-15 | 28 | 19 | 9 | [10 empty] | 2021-08-24 | 2021-10-01 | 28 | 2 | 26 | [10 empty] | 2022-07-06 | 2021-12-29 13:47 | 2023-12-09 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 363819 | 1610 | 100 | Solar | 01_6J319 | 2021-12-29 13:47 | 2021-12-30 | 202 | 202 | 0 | [10 empty] | 2022-11-15 | 2022-12-08 | 17 | 0 | 17 | [10 empty] | 2023-10-31 |  | 2025-04-09 | Yes | STD | [9 empty] | Design |  | No
National Grid | HAMILTON | 364985 | 1982 | 43.2 | Solar | 12_18L2 | 2021-07-14 12:38 | 2021-07-15 | 37 | 27 | 10 | 2021-09-03 | 2022-02-17 | 118 | 101 | 17 | [20 empty] | 2022-02-18 |  | 2023-03-05 |  | EXP | [8 empty] | 2022-08-31 | Connected |  | No
National Grid | SALEM | 364264 | 1970 | 2490 | Solar | 12_29W6 | 2021-07-14 13:00 | 2021-07-15 | 11 | 1 | 10 | [10 empty] | 2021-07-30 | 2021-09-01 | 23 | 3 | 20 | [11 empty] | 2021-07-14 17:54 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ATTLEBORO | 356770 | 2703 | 300 | Solar | 05_9L3 | 2021-07-14 17:54 | 2021-07-15 | 19 | 9 | 10 | [10 empty] | 2021-08-11 | 2021-10-19 | 48 | 20 | 28 | [10 empty] | 2022-07-18 | 2021-07-14 18:47 | 2023-10-19 | Yes | STD | [9 empty] | Withdrawn |  | Yes
National Grid | ATTLEBORO | 356799 | 2703 | 375 | Solar | 05_9L1 | 2021-07-14 18:47 | 2021-07-15 | 21 | 11 | 10 | [10 empty] | 2021-08-13 | 2021-09-23 | 29 | 3 | 26 | [10 empty] | 2022-12-05 |  | 2024-01-10 | Yes | STD | [9 empty] | Withdrawn |  | Yes
National Grid | ATTLEBORO | 357632 | 2703 | 283.2 | Solar | 05_9L4 | 2021-07-14 18:58 | 2021-07-15 | 56 | 46 | 10 | [10 empty] | 2021-10-04 | 2021-11-18 | 32 | 4 | 28 | [10 empty] | 2023-08-29 | 2021-07-14 19:25 |  |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | ATTLEBORO | 357772 | 2703 | 133.2 | Solar | 05_1J3 | 2021-07-14 19:25 | 2021-07-15 | 19 | 10 | 9 | [10 empty] | 2021-08-11 | 2021-11-16 | 67 | 7 | 60 | [10 empty] | 2022-10-25 | 2021-07-14 19:36 | 2024-03-23 |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | ATTLEBORO | 357405 | 2703 | 487.5 | Solar | 05_5J2 | 2021-07-14 19:36 | 2021-07-15 | 20 | 10 | 10 | [10 empty] | 2021-08-12 | 2021-09-22 | 29 | 3 | 26 | [10 empty] | 2023-01-27 |  | 2024-06-18 | Yes | STD | [9 empty] | Withdrawn |  | No
National Grid | ATTLEBORO | 357619 | 2703 | 466.6 | Solar | 05_9L4 | 2021-07-14 19:45 | 2021-07-15 | 20 | 10 | 10 | [10 empty] | 2021-08-12 | 2021-09-22 | 29 | 3 | 26 | [10 empty] | 2022-12-12 | 2021-07-14 19:52 |  |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | ATTLEBORO | 357402 | 2703 | 300 | Solar | 05_9L4 | 2021-07-14 19:52 | 2021-07-15 | 20 | 10 | 10 | [10 empty] | 2021-08-12 | 2021-09-22 | 29 | 3 | 26 | [10 empty] | 2023-01-31 |  | 2024-01-06 | Yes | STD | [9 empty] | Withdrawn |  | Yes
National Grid | ATTLEBORO | 353933 | 2703 | 200 | Solar | 05_9L1 | 2021-07-14 19:59 | 2021-07-15 | 19 | 10 | 9 | 2021-08-11 | 2021-09-20 | 27 | 3 | 24 | 2021-12-09 | 2023-09-15 | 443 | 40 | 403 | [5 empty] | 2021-12-09 | 2023-09-15 | 443 | 40 | 403 | [9 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | MILFORD | 361006 | 1757 | 7.6 | Solar | 05_336W3 | 2021-07-15 04:36 | 2021-07-16 | 0 | 0 | 0 | 2021-07-16 | 2021-08-10 | 18 | 0 | 18 | [20 empty] | 2021-08-11 |  | 2022-08-15 |  | EXP | [8 empty] | 2021-09-20 | Connected |  | No
National Grid | BROCKTON | 357829 | 2301 | 9.8 | Solar | 07_98W49 | 2021-07-15 04:49 | 2021-07-16 | 1 | 1 | 0 | 2021-07-19 | 2021-08-20 | 25 | 0 | 25 | [20 empty] | 2021-05-19 |  | 2022-07-15 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 369971 | 1604 | 7.6 | Solar | 01_27W5 | 2021-07-15 11:23 | 2021-07-16 | 0 | 0 | 0 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | STOUGHTON | 367269 | 2072 | 7.6 | Solar | 07_75W7 | 2021-07-15 11:24 | 2021-07-16 | 12 | 11 | 1 | 2021-08-02 | 2021-09-03 | 24 | 3 | 21 | [20 empty] | 2021-09-03 |  | 2022-10-28 |  | EXP | [8 empty] | 2022-01-03 | Connected |  | No
National Grid | BROCKTON | 369999 | 2302 | 7.6 | Solar | 07_69J1 | 2021-07-15 12:31 | 2021-07-16 | 0 | 0 | 0 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ANDOVER | 370322 | 1810 | 7.6 | Solar | 14_62L2 | 2021-07-16 15:29 | 2021-07-19 | 13 | 12 | 1 | [26 empty] | 2021-07-16 16:31 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTMINSTER | 370345 | 1473 | 11.4 | Solar | 01_610W3 | 2021-07-16 16:31 | 2021-07-19 | 24 | 23 | 1 | 2021-08-20 | 2021-09-29 | 28 | 3 | 25 | [20 empty] | 2021-10-01 | 2021-07-19 09:57 | 2023-07-15 | Yes | EXP |  | 2022-02-17 | 2022-02-28 | 12 | 0 | 12 |  |  |  | Withdrawn |  | Yes
National Grid | SAUGUS | 362215 | 1906 | 7.6 | Solar | 12_16W1 | 2021-07-19 09:57 | 2021-07-20 | 1 | 0 | 1 | 2021-07-21 | 2021-08-18 | 21 | 0 | 21 | [20 empty] | 2021-08-19 |  | 2023-01-28 | Yes | EXP |  | 2022-01-29 | 2022-01-28 | 0 | 0 | 0 |  |  | 2022-03-16 | Connected |  | No
National Grid | BRIDGEWATER | 363047 | 2324 | 30 | Solar | 07_797W1 | 2021-07-19 10:04 | 2021-07-20 | 12 | 6 | 6 | 2021-08-05 | 2021-10-15 | 50 | 25 | 25 | [20 empty] | 2021-10-20 | 2021-07-19 10:18 | 2022-11-16 |  | EXP | [8 empty] | 2022-08-19 | Connected |  | Yes
National Grid | BROCKTON | 368085 | 2301 | 7.6 | Solar | 07_98W10 | 2021-07-19 10:18 | 2021-07-20 | 3 | 0 | 3 | 2021-07-23 | 2021-08-23 | 22 | 0 | 22 | [20 empty] | 2021-08-31 | 2021-07-19 10:45 | 2024-10-30 | Yes | EXP |  | 2022-03-01 | 2022-03-02 | 2 | 0 | 2 |  |  | 2023-11-15 | Connected |  | No
National Grid | METHUEN | 367847 | 1844 | 7.6 | Solar | 14_63L2 | 2021-07-19 10:45 | 2021-07-20 | 3 | 0 | 3 | 2021-07-23 | 2021-08-23 | 22 | 0 | 22 | [20 empty] | 2021-08-31 | 2021-07-19 18:57 |  | Yes | EXP |  | 2022-01-21 | 2022-01-24 | 4 | 0 | 4 |  |  | 2022-04-04 | Connected |  | No
National Grid | BARRE | 370720 | 1005 | 7.68 | Solar | 09_604W1 | 2021-07-19 18:57 | 2021-07-20 | 3 | 2 | 1 | 2021-07-22 | 2021-08-12 | 16 | 0 | 16 | [20 empty] | 2021-08-12 | 2021-07-20 01:06 | 2023-05-07 | Yes | EXP |  | 2021-12-02 | 2022-04-29 | 149 | 0 | 149 |  |  | 2022-05-16 | Connected |  | No
National Grid | BILLERICA | 367329 | 1821 | 7.6 | Solar | 14_92L6 | 2021-07-20 01:06 | 2021-07-22 | 0 | 0 | 0 | 2021-07-22 | 2021-08-12 | 16 | 0 | 16 | [20 empty] | 2021-08-12 |  | 2023-05-20 | Yes | EXP |  | 2022-01-18 | 2022-05-20 | 123 | 0 | 123 |  |  | 2022-06-08 | Connected |  | No
National Grid | WARE | 361060 | 1082 | 11.52 | Solar | 09_501L1 | 2021-07-21 10:33 | 2021-07-22 | 1 | 0 | 1 | 2021-07-23 | 2021-08-13 | 16 | 0 | 16 | [20 empty] | 2021-08-18 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SALISBURY | 371237 | 1952 | 10 | Solar | 14_7L4 | 2021-07-21 12:36 | 2021-07-22 | 48 | 38 | 10 | 2021-09-29 | 2021-11-08 | 28 | 6 | 22 | [20 empty] | 2021-11-09 | 2021-07-21 12:39 | 2022-09-27 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOUTHBOROUGH | 369538 | 1772 | 220 | Solar | 05_310W6 | 2021-07-21 12:39 | 2021-07-22 | 8 | 0 | 8 | [10 empty] | 2021-08-02 | 2021-09-14 | 31 | 3 | 28 | [10 empty] | 2022-04-18 | 2021-07-21 16:01 | 2024-07-09 | Yes | STD |  | 2024-03-23 | 2024-03-27 | 0 | 0 | 0 |  |  |  | Meter Installation |  | Yes
National Grid | SALEM | 371169 | 1970 | 100 | Solar | 12_49W2 | 2021-07-21 16:01 | 2021-07-22 | 8 | 0 | 8 | [10 empty] | 2021-08-02 | 2021-09-03 | 25 | 3 | 22 | [10 empty] | 2022-02-11 |  | 2022-12-28 |  | STD | [8 empty] | 2022-12-30 | Connected |  | No
National Grid | WORCESTER | 371327 | 1609 | 19 | Solar | 01_23W2 | 2021-07-21 16:11 | 2021-07-22 | 19 | 18 | 1 | 2021-08-18 | 2021-09-24 | 26 | 3 | 23 | [20 empty] | 2021-09-24 | 2021-07-21 20:14 | 2022-09-30 |  | EXP | [8 empty] | 2022-01-12 | Connected |  | No
National Grid | WORCESTER | 321984 | 1603 | 250 | Solar | 01_6W1 | 2021-07-21 20:14 | 2021-07-22 | 10 | 0 | 10 | 2021-08-05 | 2021-10-06 | 44 | 19 | 25 | [20 empty] | 2021-10-27 |  | 2023-02-02 | Yes | EXP | [8 empty] | 2022-12-08 | Connected |  | No
National Grid | FALL RIVER | 369869 | 2720 | 66.6 | Solar | 05_28W42 | 2021-07-22 11:44 | 2021-07-23 | 7 | 0 | 7 | 2021-08-02 | 2021-09-10 | 28 | 3 | 25 | [20 empty] | 2021-09-15 |  | 2022-10-31 |  | EXP | [8 empty] | 2022-03-24 | Connected |  | No
National Grid | METHUEN | 364103 | 1844 | 4.08 | Solar | 14_74L1 | 2021-07-22 13:11 | 2021-07-23 | 3 | 0 | 3 | 2021-07-28 | 2021-08-17 | 15 | 0 | 15 | [20 empty] | 2021-08-26 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SPENCER | 367879 | 1562 | 7.6 | Solar | 01_552L1 | 2021-07-22 16:39 | 2021-07-23 | 6 | 5 | 1 | 2021-07-30 | 2021-08-18 | 14 | 0 | 14 | [20 empty] | 2021-08-18 |  | 2022-08-23 |  | EXP | [8 empty] | 2021-12-21 | Connected |  | No
National Grid | LYNN | 370923 | 1902 | 3.8 | Solar | 12_29W5 | 2021-07-22 18:08 | 2021-07-23 | 3 | 0 | 3 | 2021-07-28 | 2021-08-17 | 15 | 0 | 15 | [20 empty] | 2021-08-26 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEBSTER | 371739 | 1570 | 15.2 | Solar | 01_412L1 | 2021-07-23 10:35 | 2021-07-26 | 2 | 1 | 1 | 2021-07-27 | 2021-08-16 | 15 | 0 | 15 | [20 empty] | 2021-08-16 | 2021-07-23 10:36 | 2022-09-25 |  | EXP | [8 empty] | 2022-01-24 | Connected |  | No
National Grid | BROCKTON | 368593 | 2302 | 10 | Solar | 07_911W77 | 2021-07-23 10:36 | 2021-07-26 | 2 | 0 | 2 | 2021-07-28 | 2021-08-17 | 15 | 0 | 15 | [20 empty] | 2021-08-26 |  | 2023-05-20 | Yes | EXP |  | 2022-03-09 | 2022-04-25 | 48 | 0 | 48 |  |  | 2022-05-28 | Connected |  | No
National Grid | WORCESTER | 371778 | 1609 | 11.4 | Solar | 01_23W2 | 2021-07-23 13:02 | 2021-07-26 | 1 | 0 | 1 | 2021-07-27 | 2021-08-24 | 23 | 3 | 20 | [20 empty] | 2021-08-25 |  | 2023-03-24 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FRANKLIN | 371812 | 2038 | 7.6 | Solar | 05_348W5 | 2021-07-23 14:55 | 2021-07-26 | 4 | 3 | 1 | 2021-07-29 | 2021-08-18 | 15 | 0 | 15 | [20 empty] | 2021-08-18 | 2021-07-23 16:23 | 2022-10-06 |  | EXP | [8 empty] | 2022-02-18 | Connected |  | No
National Grid | ESSEX | 368281 | 1929 | 7.6 | Solar | 12_51T2 | 2021-07-23 16:23 | 2021-07-26 | 2 | 0 | 2 | 2021-07-28 | 2021-08-17 | 15 | 0 | 15 | [20 empty] | 2021-08-26 |  | 2023-01-10 | Yes | EXP | [8 empty] | 2022-12-22 | Connected |  | No
National Grid | WESTMINSTER | 371839 | 1473 | 15.2 | Solar | 01_609W2 | 2021-07-23 16:35 | 2021-07-26 | 4 | 3 | 1 | 2021-07-29 | 2021-08-18 | 15 | 0 | 15 | [20 empty] | 2021-08-18 |  | 2022-08-31 |  | EXP | [8 empty] | 2022-06-02 | Connected |  | No
National Grid | WORCESTER | 367448 | 1602 | 7.6 | Solar | 01_3J371 | 2021-07-23 16:37 | 2021-07-26 | 2 | 0 | 2 | 2021-07-28 | 2021-08-25 | 20 | 2 | 18 | [20 empty] | 2021-09-03 | 2021-07-23 21:33 | 2022-09-25 |  | EXP | [8 empty] | 2022-04-08 | Connected |  | No
National Grid | MEDFORD | 355956 | 2155 | 240 | Solar | 12_2344 | 2021-07-23 21:33 | 2021-07-26 | 201 | 191 | 10 | [25 empty] | 2022-08-05 |  | 2025-05-31 | Yes | EXP | [9 empty] | Construction |  | No
National Grid | RUTLAND | 367324 | 1543 | 11.025 | Solar | 01_55W1 | 2021-07-25 10:08 | 2021-07-26 | 30 | 30 | 0 | 2021-09-07 | 2021-10-27 | 36 | 14 | 22 | [20 empty] | 2021-11-01 | 2021-07-26 10:59 | 2022-12-30 |  | EXP | [8 empty] | 2022-01-12 | Connected |  | No
National Grid | NANTUCKET | 371953 | 2554 | 100 | Solar | 04_101L7 | 2021-07-26 10:59 | 2021-07-27 | 16 | 6 | 10 | 2021-08-18 | 2021-09-27 | 27 | 3 | 24 | [20 empty] | 2021-09-28 |  | 2023-07-14 | Yes | EXP | [8 empty] | 2023-07-21 | Connected |  | No
National Grid | ATTLEBORO | 358156 | 2703 | 875 | Solar | 05_9L4 | 2021-07-26 11:14 | 2021-07-27 | 71 | 61 | 10 | [10 empty] | 2021-11-05 | 2022-01-17 | 61 | 38 | 23 | [11 empty] | 2021-07-26 14:00 |  |  | STD | [9 empty] | Conditional Approval |  | No
National Grid | TYNGSBOROUGH | 372068 | 1879 | 15.2 | Solar | 14_21L1 | 2021-07-26 14:00 | 2021-07-27 | 3 | 2 | 1 | 2021-07-29 | 2021-10-28 | 64 | 43 | 21 | [20 empty] | 2021-11-01 |  | 2023-09-05 | Yes | EXP |  | 2022-01-18 | 2022-09-02 | 227 | 0 | 227 |  |  |  | Withdrawn |  | No
National Grid | BELCHERTOWN | 369533 | 1007 | 7.68 | Solar | 09_527L2 | 2021-07-27 11:33 | 2021-07-28 | 5 | 0 | 5 | 2021-08-04 | 2021-08-26 | 16 | 2 | 14 | [20 empty] | 2021-08-31 | 2021-07-27 14:51 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 360395 | 1844 | 8.99 | Solar | 14_63L2 | 2021-07-27 14:51 | 2021-07-28 | 10 | 8 | 2 | 2021-08-11 | 2021-09-16 | 25 | 3 | 22 | [20 empty] | 2021-09-27 |  |  | Yes | EXP |  | 2022-03-08 | 2022-03-30 | 23 | 0 | 23 |  |  | 2022-04-07 | Connected |  | No
National Grid | GREAT BARRINGTON | 372263 | 1230 | 72 | Solar | 09_1109W2 | 2021-07-27 17:45 | 2022-03-15 | 12 | 2 | 10 | [10 empty] | 2022-03-30 | 2022-05-04 | 25 | 0 | 25 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BEVERLY | 372473 | 1915 | 6.96 | Solar | 12_51T2 | 2021-07-28 08:24 | 2021-07-29 | 1 | 0 | 1 | 2021-07-30 | 2021-08-18 | 14 | 0 | 14 | [20 empty] | 2021-08-19 |  | 2022-08-23 |  | EXP | [8 empty] | 2021-12-16 | Connected |  | No
National Grid | AMESBURY | 366611 | 1913 | 10 | Solar | 14_275L4 | 2021-07-28 11:19 | 2021-07-29 | 14 | 13 | 1 | 2021-08-18 | 2021-09-27 | 27 | 3 | 24 | [20 empty] | 2021-09-28 |  | 2023-04-11 |  | EXP | [8 empty] | 2022-04-28 | Connected |  | No
National Grid | MILLBURY | 344165 | 1527 | 2000 | Solar | 01_26W2 | 2021-07-28 12:11 | 2021-07-29 | 18 | 10 | 8 | [10 empty] | 2021-08-24 | 2021-11-23 | 79 | 59 | 20 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 372126 | 1609 | 100 | Solar | 01_HT46 | 2021-07-28 15:14 | 2021-07-29 | 71 | 62 | 9 | [10 empty] | 2021-11-09 | 2021-12-15 | 25 | 0 | 25 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | REHOBOTH | 372768 | 2769 | 15.2 | Solar | 05_7L4 | 2021-07-29 11:05 | 2021-07-30 | 45 | 37 | 8 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MENDON | 372950 | 1756 | 3.8 | Solar | 05_321W6 | 2021-07-29 18:46 | 2021-07-30 | 6 | 3 | 3 | 2021-08-06 | 2021-09-03 | 20 | 3 | 17 | [20 empty] | 2021-09-03 |  | 2022-08-04 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTH BROOKFIELD | 366176 | 1535 | 10 | Solar | 01_552L3 | 2021-07-30 09:31 | 2021-08-02 | 5 | 2 | 3 | 2021-08-06 | 2021-09-07 | 21 | 3 | 18 | [20 empty] | 2021-09-14 |  | 2022-10-15 |  | EXP | [8 empty] | 2021-12-15 | Connected |  | No
National Grid | ATTLEBORO | 357046 | 2703 | 283.3 | Solar | 05_9L1 | 2021-07-30 10:06 | 2021-08-02 | 123 | 113 | 10 | [10 empty] | 2022-01-28 | 2022-07-26 | 123 | 99 | 24 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | ATTLEBORO | 357809 | 2703 | 499.5 | Solar | 05_9L4 | 2021-07-30 10:08 | 2021-08-02 | 71 | 60 | 11 | [10 empty] | 2021-11-12 | 2021-12-16 | 24 | 0 | 24 | [10 empty] | 2022-11-16 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | CHELMSFORD | 373166 | 1824 | 15.2 | Solar | 14_58L1 | 2021-07-30 17:52 | 2021-08-02 | 27 | 25 | 2 | 2021-09-09 | 2022-01-10 | 85 | 60 | 25 | [20 empty] | 2022-01-10 |  | 2023-01-22 |  | EXP | [8 empty] | 2022-01-26 | Connected |  | No
National Grid | SEEKONK | 366959 | 2771 | 9.8 | Solar | 05_7L5 | 2021-07-30 18:20 | 2021-08-02 | 3 | 0 | 3 | 2021-08-05 | 2021-09-07 | 22 | 3 | 19 | [20 empty] | 2021-09-14 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | DUNSTABLE | 373203 | 1827 | 15.4 | Solar | 01_210L1 | 2021-07-31 16:15 | 2021-08-02 | 1 | 0 | 1 | 2021-08-03 | 2021-08-25 | 16 | 2 | 14 | [20 empty] | 2021-08-25 |  | 2022-08-30 |  | EXP | [8 empty] | 2021-09-28 | Connected |  | Yes
National Grid | SOUTHBOROUGH | 373284 | 1772 | 10 | Solar | 05_310W3 | 2021-08-02 10:59 | 2021-08-03 | 3 | 2 | 1 | 2021-08-06 | 2021-09-03 | 20 | 3 | 17 | [20 empty] | 2021-09-03 | 2021-08-02 14:48 | 2022-09-08 |  | EXP | [8 empty] | 2022-02-01 | Connected |  | No
National Grid | FOXBOROUGH | 367911 | 2035 | 266.6 | Solar | 05_3432W2 | 2021-08-02 14:48 | 2021-08-03 | 12 | 3 | 9 | 2021-08-18 | 2021-09-10 | 15 | 3 | 12 | 2021-12-01 | 2021-12-21 | 15 | 0 | 15 | [5 empty] | 2021-12-01 | 2021-12-21 | 15 | 0 | 15 | [5 empty] | 2022-03-18 |  | 2024-10-28 | Yes | EXP | [9 empty] | Construction |  | No
National Grid | SAUGUS | 371674 | 1906 | 7.6 | Solar | 12_23W2 | 2021-08-02 19:29 | 2021-08-03 | 2 | 0 | 2 | 2021-08-05 | 2021-09-07 | 22 | 3 | 19 | [20 empty] | 2021-09-14 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ROCKPORT | 371202 | 1966 | 7.6 | Solar | 12_52L1 | 2021-08-03 13:44 | 2021-08-04 | 12 | 11 | 1 | 2021-08-19 | 2021-09-27 | 26 | 3 | 23 | [20 empty] | 2021-09-28 |  | 2022-09-30 |  | EXP | [8 empty] | 2021-11-04 | Connected |  | No
National Grid | GARDNER | 371045 | 1440 | 7.6 | Solar | 01_607W4 | 2021-08-03 14:46 | 2021-08-04 | 1 | 0 | 1 | 2021-08-05 | 2021-10-21 | 53 | 29 | 24 | [20 empty] | 2021-10-22 | 2021-08-03 21:47 | 2022-11-03 |  | EXP | [8 empty] | 2022-02-04 | Connected |  | No
National Grid | HOLBROOK | 369186 | 2343 | 249 | Solar | 07_911W77 | 2021-08-03 21:47 | 2021-08-04 | 64 | 55 | 9 | 2021-11-04 | 2022-01-04 | 41 | 0 | 41 | [20 empty] | 2022-01-19 |  | 2023-12-16 | Yes | EXP | [9 empty] | Withdrawn |  | No
National Grid | UXBRIDGE | 371560 | 1569 | 116.6 | Solar | 05_321W6 | 2021-08-04 10:17 | 2021-08-05 | 63 | 53 | 10 | [10 empty] | 2021-11-04 | 2022-01-07 | 44 | 0 | 44 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | MANCHESTER | 373988 | 1944 | 9.86 | Solar | 12_28L2 | 2021-08-04 16:41 | 2021-08-05 | 4 | 2 | 2 | 2021-08-10 | 2021-09-07 | 19 | 3 | 16 | [20 empty] | 2021-09-08 | 2021-08-04 20:35 | 2022-09-13 |  | EXP | [8 empty] | 2021-10-14 | Connected |  | No
National Grid | GARDNER | 372586 | 1440 | 9.8 | Solar | 01_607W1 | 2021-08-04 20:35 | 2021-08-05 | 1 | 0 | 1 | 2021-08-06 | 2021-09-07 | 21 | 3 | 18 | [20 empty] | 2021-09-08 |  | 2022-11-24 | Yes | EXP |  | 2021-10-15 | 2021-11-23 | 40 | 4 | 36 |  |  | 2021-12-01 | Connected |  | Yes
National Grid | SEEKONK | 372331 | 2771 | 11.02 | Solar | 05_9L5 | 2021-08-04 20:49 | 2021-08-05 | 10 | 6 | 4 | 2021-08-19 | 2021-09-28 | 28 | 3 | 25 | [20 empty] | 2021-10-07 |  | 2022-10-13 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTMINSTER | 373050 | 1473 | 7.68 | Solar | 01_609W2 | 2021-08-05 10:14 | 2021-08-06 | 17 | 16 | 1 | 2021-08-30 | 2021-10-04 | 25 | 0 | 25 | [20 empty] | 2021-10-06 | 2021-08-05 10:29 | 2023-01-13 |  | EXP | [8 empty] | 2022-05-17 | Connected |  | No
National Grid | WENHAM | 374102 | 1984 | 18.99 | Solar | 12_18L2 | 2021-08-05 10:29 | 2021-08-06 | 1 | 0 | 1 | 2021-08-09 | 2021-09-07 | 21 | 8 | 13 | [20 empty] | 2021-09-08 |  | 2023-02-09 | Yes | EXP |  | 2022-01-06 | 2022-02-09 | 35 | 0 | 35 |  |  | 2022-07-12 | Connected |  | No
National Grid | BILLERICA | 372447 | 1821 | 9.8 | Solar | 14_92L4 | 2021-08-05 14:17 | 2021-08-06 | 2 | 1 | 1 | 2021-08-09 | 2021-09-07 | 20 | 3 | 17 | [20 empty] | 2021-09-08 | 2021-08-05 16:55 | 2022-09-11 |  | EXP | [8 empty] | 2022-02-23 | Connected |  | No
National Grid | OXFORD | 373487 | 1540 | 9.8 | Solar | 01_406L4 | 2021-08-05 16:55 | 2021-08-06 | 2 | 0 | 2 | 2021-08-10 | 2021-09-07 | 19 | 3 | 16 | [20 empty] | 2021-09-14 |  | 2023-11-05 | Yes | EXP |  | 2022-03-29 | 2022-06-22 | 86 | 0 | 86 |  |  | 2023-02-03 | Connected |  | No
National Grid | ATTLEBORO | 374279 | 2703 | 7.6 | Solar | 05_9L4 | 2021-08-05 18:04 | 2021-08-06 | 9 | 8 | 1 | 2021-08-18 | 2021-09-27 | 27 | 3 | 24 | [20 empty] | 2021-09-28 |  | 2022-08-17 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NANTUCKET | 374111 | 2554 | 20 | Solar | 04_101L8 | 2021-08-06 09:15 | 2021-08-09 | 1 | 0 | 1 | 2021-08-10 | 2021-09-07 | 19 | 3 | 16 | [20 empty] | 2021-09-08 |  | 2022-09-18 |  | EXP | [8 empty] | 2022-02-23 | Connected |  | No
National Grid | MELROSE | 369366 | 2176 | 12.98 | Solar | 12_16W6 | 2021-08-06 10:19 | 2021-08-09 | 18 | 16 | 2 | 2021-09-01 | 2021-10-06 | 25 | 0 | 25 | [20 empty] | 2021-10-15 | 2021-08-06 13:14 | 2022-10-30 |  | EXP | [8 empty] | 2022-01-11 | Connected |  | Yes
National Grid | SALEM | 370832 | 1970 | 250 | Solar | 12_49W6 | 2021-08-06 13:14 | 2021-08-09 | 10 | 0 | 10 | [10 empty] | 2021-08-23 | 2021-10-04 | 30 | 3 | 27 | [10 empty] | 2022-02-22 |  | 2023-08-01 |  | STD | [8 empty] | 2023-08-04 | Connected |  | No
National Grid | GRAFTON | 374481 | 1519 | 7.6 | Solar | 01_304W2 | 2021-08-06 14:13 | 2021-08-09 | 23 | 13 | 10 | 2021-09-10 | 2022-03-31 | 139 | 115 | 24 | [20 empty] | 2022-04-01 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BELLINGHAM | 373157 | 2019 | 3.8 | Solar | 05_108W60 | 2021-08-06 15:00 | 2021-08-09 | 2 | 0 | 2 | 2021-08-11 | 2021-09-16 | 25 | 3 | 22 | [20 empty] | 2021-09-27 |  | 2023-04-30 |  | EXP | [8 empty] | 2023-03-03 | Connected |  | No
National Grid | QUINCY | 374495 | 2169 | 7.6 | Solar | 07_3W2 | 2021-08-06 15:20 | 2021-08-09 | 34 | 33 | 1 | [26 empty] | 2021-08-06 15:29 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BILLERICA | 372933 | 1821 | 7.6 | Solar | 14_18L2 | 2021-08-06 15:29 | 2021-08-09 | 2 | 1 | 1 | 2021-08-10 | 2021-09-07 | 19 | 3 | 16 | [20 empty] | 2021-09-08 | 2021-08-06 17:48 | 2023-03-29 | Yes | EXP |  | 2022-01-19 | 2022-02-11 | 24 | 0 | 24 |  |  | 2022-12-17 | Connected |  | No
National Grid | WINTHROP | 366061 | 2152 | 6 | Solar | 12_96W1 | 2021-08-06 17:48 | 2021-08-09 | 18 | 16 | 2 | 2021-09-01 | 2021-10-06 | 25 | 0 | 25 | [20 empty] | 2021-10-15 |  | 2023-06-08 | Yes | EXP |  | 2022-02-11 | 2022-03-29 | 47 | 0 | 47 |  |  | 2022-08-16 | Connected |  | Yes
National Grid | NORTH EASTON | 374531 | 2356 | 11.4 | Solar | 07_92W78 | 2021-08-09 10:46 | 2021-08-10 | 13 | 12 | 1 | 2021-08-26 | 2021-10-06 | 29 | 5 | 24 | [20 empty] | 2021-10-06 |  | 2022-10-13 |  | EXP | [8 empty] | 2022-04-13 | Connected |  | No
National Grid | ATTLEBORO | 374717 | 2703 | 11.4 | Solar | 05_9L4 | 2021-08-09 14:29 | 2021-08-10 | 33 | 26 | 7 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEOMINSTER | 369937 | 1453 | 28.8 | Solar | 01_207W2 | 2021-08-09 15:23 | 2021-08-10 | 1 | 0 | 1 | 2021-08-11 | 2021-09-08 | 19 | 3 | 16 | [20 empty] | 2021-09-09 |  | 2022-09-30 |  | EXP | [8 empty] | 2022-02-02 | Connected |  | No
National Grid | MENDON | 374830 | 1756 | 15.2 | Solar | 05_321W6 | 2021-08-09 18:09 | 2021-08-10 | 20 | 19 | 1 | 2021-09-08 | 2021-11-18 | 50 | 25 | 25 | [20 empty] | 2021-11-18 |  | 2022-11-22 |  | EXP | [8 empty] | 2022-03-10 | Connected |  | No
National Grid | GARDNER | 373636 | 1440 | 3 | Solar | 01_607W5 | 2021-08-09 19:20 | 2021-08-10 | 3 | 0 | 3 | 2021-08-13 | 2021-09-16 | 23 | 3 | 20 | [20 empty] | 2021-09-27 |  | 2022-09-30 |  | EXP | [8 empty] | 2021-12-13 | Connected |  | Yes
National Grid | WORCESTER | 373959 | 1603 | 3.8 | Solar | 01_6W1 | 2021-08-09 20:08 | 2021-08-10 | 3 | 0 | 3 | 2021-08-13 | 2021-09-23 | 28 | 3 | 25 | [20 empty] | 2021-09-30 |  | 2022-10-07 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTH BILLERICA | 372170 | 1862 | 7.6 | Solar | 14_70L1 | 2021-08-09 20:36 | 2021-08-10 | 1 | 0 | 1 | 2021-08-11 | 2021-09-17 | 26 | 3 | 23 | [20 empty] | 2021-09-17 |  | 2022-09-18 |  | EXP | [8 empty] | 2022-06-17 | Connected |  | No
National Grid | RUTLAND | 368515 | 1543 | 4300 | Solar | 01_55W1 | 2021-08-10 11:42 | 2021-08-11 | 20 | 11 | 9 | [10 empty] | 2021-09-08 | 2021-10-05 | 20 | 0 | 20 | [11 empty] | 2021-08-10 11:54 |  |  | STD | [9 empty] | Study |  | No
National Grid | MENDON | 370890 | 1756 | 10 | Solar | 05_321W6 | 2021-08-10 11:54 | 2021-08-11 | 17 | 15 | 2 | 2021-09-03 | 2021-10-08 | 25 | 0 | 25 | [20 empty] | 2021-10-19 |  | 2023-07-10 | Yes | EXP |  | 2022-03-02 | 2022-06-28 | 119 | 0 | 119 |  |  | 2022-07-18 | Connected |  | No
National Grid | BOLTON | 374977 | 1740 | 11.4 | Solar | 01_216W6 | 2021-08-10 12:07 | 2021-08-11 | 19 | 18 | 1 | 2021-09-08 | 2021-10-12 | 24 | 0 | 24 | [20 empty] | 2021-10-13 | 2021-08-10 14:48 | 2022-12-17 |  | EXP | [8 empty] | 2022-01-20 | Connected |  | No
National Grid | STURBRIDGE | 365963 | 1566 | 7.6 | Solar | 01_413L7 | 2021-08-10 14:48 | 2021-08-11 | 2 | 0 | 2 | 2021-08-13 | 2021-09-16 | 23 | 3 | 20 | [20 empty] | 2021-09-27 |  | 2023-06-03 | Yes | EXP |  | 2022-03-01 | 2022-03-28 | 28 | 0 | 28 |  |  | 2022-06-15 | Connected |  | No
National Grid | NORTHAMPTON | 375139 | 1060 | 11.4 | Solar | 09_909W2 | 2021-08-10 19:14 | 2021-08-11 | 22 | 21 | 1 | 2021-09-10 | 2021-10-15 | 25 | 0 | 25 | [20 empty] | 2021-10-15 | 2021-08-11 10:32 | 2022-11-04 |  | EXP | [8 empty] | 2022-09-23 | Connected |  | No
National Grid | MARLBOROUGH | 374486 | 1752 | 9.6 | Solar | 05_310W4 | 2021-08-11 10:32 | 2021-08-12 | 5 | 1 | 4 | 2021-08-19 | 2021-09-27 | 26 | 3 | 23 | [20 empty] | 2021-10-07 | 2021-08-11 11:30 | 2023-12-22 | Yes | EXP |  | 2022-04-07 | 2022-12-21 | 259 | 0 | 259 |  |  | 2023-01-26 | Connected |  | No
National Grid | ROCKPORT | 375231 | 1966 | 11.4 | Solar | 12_52L1 | 2021-08-11 11:30 | 2021-08-12 | 14 | 13 | 1 | 2021-09-01 | 2021-10-05 | 24 | 0 | 24 | [20 empty] | 2021-10-05 |  | 2023-02-14 | Yes | EXP |  | 2022-01-06 | 2022-02-14 | 40 | 0 | 40 |  |  | 2022-04-19 | Connected |  | Yes
National Grid | SOUTHBOROUGH | 375292 | 1772 | 15.2 | Solar | 05_314W2 | 2021-08-11 14:03 | 2021-08-12 | 12 | 8 | 4 | 2021-08-30 | 2021-10-14 | 32 | 7 | 25 | [20 empty] | 2021-11-10 |  | 2023-01-05 |  | EXP | [8 empty] | 2022-04-06 | Connected |  | No
National Grid | SCITUATE | 375299 | 2066 | 21.17 | Solar | 07_915W82 | 2021-08-11 14:27 | 2021-08-12 | 3 | 2 | 1 | 2021-08-16 | 2021-09-07 | 15 | 3 | 12 | [20 empty] | 2021-09-08 |  | 2022-09-21 |  | EXP | [8 empty] | 2021-11-23 | Connected |  | No
National Grid | STOUGHTON | 375475 | 2072 | 15.2 | Solar | 07_913W43 | 2021-08-12 09:49 | 2021-08-13 | 4 | 0 | 4 | 2021-08-19 | 2021-09-28 | 28 | 3 | 25 | [20 empty] | 2021-10-07 |  | 2023-09-30 |  | EXP | [8 empty] | 2022-10-31 | Connected |  | No
National Grid | SOUTHBOROUGH | 375524 | 1772 | 7.6 | Solar | 05_314W2 | 2021-08-12 12:19 | 2021-08-13 | 16 | 15 | 1 | 2021-09-03 | 2021-10-08 | 25 | 0 | 25 | [20 empty] | 2021-10-12 | 2021-08-12 12:24 | 2022-11-07 |  | EXP | [8 empty] | 2022-02-09 | Connected |  | No
National Grid | STOUGHTON | 370680 | 2072 | 675 | Solar | 07_75W1 | 2021-08-12 12:24 | 2021-08-13 | 20 | 13 | 7 | [10 empty] | 2021-09-13 | 2021-10-07 | 19 | 0 | 19 | [10 empty] | 2022-06-13 |  | 2024-11-27 | Yes | STD | [9 empty] | Construction |  | Yes
National Grid | ATHOL | 374024 | 1331 | 20 | Solar | 09_702W2 | 2021-08-12 14:05 | 2021-08-13 | 22 | 21 | 1 | 2021-09-14 | 2022-01-25 | 92 | 66 | 26 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | MT WASHINGTON | 375639 | 1258 | 7.6 | Solar | 09_1109W2 | 2021-08-12 16:28 | 2021-08-13 | 30 | 29 | 1 | 2021-09-27 | 2021-10-26 | 21 | 0 | 21 | [20 empty] | 2021-11-02 |  | 2022-09-23 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HAVERHILL | 375768 | 1832 | 7.6 | Solar | 14_43L6 | 2021-08-13 11:58 | 2021-08-16 | 12 | 11 | 1 | 2021-08-31 | 2021-10-04 | 24 | 0 | 24 | [20 empty] | 2021-10-06 |  | 2022-08-29 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WARREN | 375844 | 1083 | 7.6 | Solar | 09_516L3 | 2021-08-13 15:52 | 2021-08-16 | 31 | 26 | 5 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HANOVER | 375893 | 2339 | 7.6 | Solar | 07_95W3 | 2021-08-13 18:05 | 2021-08-16 | 21 | 21 | 0 | 2021-09-15 | 2021-10-20 | 25 | 0 | 25 | [20 empty] | 2021-10-20 | 2021-08-13 18:52 | 2022-12-27 |  | EXP | [8 empty] | 2022-06-14 | Connected |  | No
National Grid | SOUTHBOROUGH | 375895 | 1772 | 9.6 | Solar | 05_314W2 | 2021-08-13 18:52 | 2021-08-16 | 22 | 21 | 1 | 2021-09-16 | 2021-10-21 | 25 | 0 | 25 | [20 empty] | 2021-12-06 | 2021-08-13 18:55 | 2023-05-07 | Yes | EXP |  | 2022-04-07 | 2022-04-27 | 21 | 0 | 21 |  |  | 2022-05-27 | Connected |  | No
National Grid | BROCKTON | 371375 | 2302 | 7.6 | Solar | 07_91W42 | 2021-08-13 18:55 | 2021-08-16 | 3 | 0 | 3 | 2021-08-19 | 2021-10-08 | 36 | 11 | 25 | [20 empty] | 2021-10-18 |  | 2023-09-25 | Yes | EXP |  | 2022-02-15 | 2022-04-25 | 70 | 0 | 70 |  |  | 2022-11-03 | Connected |  | No
National Grid | EAST LONGMEADOW | 375923 | 1028 | 13.44 | Solar | 09_508L4 | 2021-08-14 16:00 | 2021-08-16 | 3 | 0 | 3 | 2021-08-19 | 2021-09-27 | 26 | 3 | 23 | [20 empty] | 2021-09-28 |  | 2022-10-08 |  | EXP | [8 empty] | 2021-12-09 | Connected |  | No
National Grid | WESTFORD | 374358 | 1886 | 9.86 | Solar | 14_57L3 | 2021-08-16 09:08 | 2021-08-17 | 1 | 0 | 1 | 2021-08-18 | 2021-09-27 | 27 | 3 | 24 | [20 empty] | 2021-09-28 |  | 2022-10-04 |  | EXP | [8 empty] | 2022-01-25 | Connected |  | No
National Grid | LOWELL | 370918 | 1852 | 100 | Solar | 14_3L5 | 2021-08-16 10:52 | 2021-08-17 | 18 | 8 | 10 | 2021-09-13 | 2021-12-16 | 66 | 13 | 53 | 2021-12-30 | 2022-01-27 | 19 | 0 | 19 | [5 empty] | 2021-12-30 | 2022-01-27 | 19 | 0 | 19 | [5 empty] | 2022-02-03 |  | 2023-06-20 |  | EXP | [8 empty] | 2022-07-26 | Connected |  | No
National Grid | MENDON | 376022 | 1756 | 15.2 | Solar | 05_332W1 | 2021-08-16 12:00 | 2021-08-17 | 8 | 7 | 1 | 2021-08-27 | 2021-10-01 | 25 | 0 | 25 | [20 empty] | 2021-10-04 |  | 2022-11-20 |  | EXP | [8 empty] | 2022-11-05 | Connected |  | No
National Grid | NORWELL | 376126 | 2061 | 19 | Solar | 07_96W43 | 2021-08-16 14:55 | 2021-08-17 | 2 | 0 | 2 | 2021-08-19 | 2021-09-27 | 26 | 3 | 23 | [20 empty] | 2021-10-04 | 2021-08-16 17:36 | 2023-01-26 |  | EXP | [8 empty] | 2022-04-28 | Connected |  | No
National Grid | HAVERHILL | 376194 | 1832 | 7.6 | Solar | 14_48L2 | 2021-08-16 17:36 | 2021-09-20 | 19 | 18 | 1 | 2021-10-18 | 2021-12-09 | 37 | 15 | 22 | [20 empty] | 2021-12-09 |  | 2023-04-16 | Yes | EXP |  | 2022-01-12 | 2022-02-09 | 29 | 0 | 29 |  |  | 2022-04-22 | Connected |  | No
National Grid | BEVERLY | 369753 | 1915 | 8.376 | Solar | 12_51T2 | 2021-08-17 09:23 | 2021-08-18 | 9 | 8 | 1 | 2021-08-30 | 2021-09-09 | 8 | 0 | 8 | [20 empty] | 2021-09-10 |  | 2022-11-06 |  | EXP | [8 empty] | 2022-05-13 | Connected |  | No
National Grid | NORTH ANDOVER | 375312 | 1845 | 8.376 | Solar | 14_55L1 | 2021-08-17 16:07 | 2021-08-18 | 2 | 0 | 2 | 2021-08-20 | 2021-09-29 | 28 | 3 | 25 | [20 empty] | 2021-10-07 |  | 2022-10-23 |  | EXP | [8 empty] | 2022-01-14 | Connected |  | No
National Grid | NEW BRAINTREE | 309808 | 1531 | 1000 | Solar | 09_604W3 | 2021-08-17 17:57 | 2021-08-18 | 104 | 96 | 8 | [10 empty] | 2022-01-19 | 2022-11-21 | 212 | 205 | 7 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | BELLINGHAM | 376456 | 2019 | 7.6 | Solar | 05_344W4 | 2021-08-17 19:04 | 2021-08-18 | 23 | 23 | 0 | 2021-09-21 | 2021-10-25 | 24 | 0 | 24 | [20 empty] | 2021-11-01 |  | 2022-09-19 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BLACKSTONE | 376465 | 1504 | 15.2 | Solar | 05_108W60 | 2021-08-17 20:35 | 2021-08-18 | 23 | 22 | 1 | 2021-09-21 | 2022-06-02 | 176 | 153 | 23 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEOMINSTER | 373151 | 1453 | 7.6 | Solar | 01_219W5 | 2021-08-18 09:45 | 2021-08-19 | 8 | 3 | 5 | 2021-09-01 | 2021-10-06 | 25 | 0 | 25 | [20 empty] | 2021-10-15 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 376505 | 1602 | 43.2 | Solar | 01_2J328 | 2021-08-18 10:14 | 2021-08-19 | 16 | 6 | 10 | [10 empty] | 2021-09-13 | 2022-06-29 | 200 | 172 | 28 | [10 empty] | 2023-05-22 |  | 2023-11-20 |  | STD | [8 empty] | 2023-11-17 | Connected |  | No
National Grid | NORTON | 375342 | 2766 | 36 | Solar | 05_4L1 | 2021-08-18 11:55 | 2021-08-19 | 16 | 6 | 10 | 2021-09-13 | 2021-10-19 | 25 | 0 | 25 | [20 empty] | 2021-10-21 | 2021-08-18 12:03 | 2023-04-07 |  | EXP | [8 empty] | 2023-04-19 | Connected |  | No
National Grid | NORTON | 375559 | 2766 | 100 | Solar | 05_8L3 | 2021-08-18 12:03 | 2021-08-19 | 14 | 3 | 11 | [10 empty] | 2021-09-09 | 2021-12-05 | 59 | 28 | 31 | [10 empty] | 2022-05-26 | 2021-08-18 12:10 | 2023-03-23 | Yes | STD |  | 2023-01-25 | 2023-04-20 | 85 | 59 | 26 |  |  | 2023-05-12 | Connected |  | No
National Grid | NORTON | 375663 | 2766 | 240 | Solar | 05_8L2 | 2021-08-18 12:10 | 2021-08-19 | 14 | 3 | 11 | [10 empty] | 2021-09-09 | 2021-12-05 | 59 | 5 | 54 | [10 empty] | 2022-06-08 |  | 2024-02-23 | Yes | STD |  | 2023-04-14 | 2023-04-20 | 7 | 0 | 7 |  |  | 2023-05-10 | Connected |  | No
National Grid | DUNSTABLE | 376595 | 1827 | 7.6 | Solar | 01_210L1 | 2021-08-18 12:15 | 2021-08-19 | 4 | 4 | 0 | 2021-08-25 | 2021-09-27 | 23 | 0 | 23 | [20 empty] | 2021-09-27 |  | 2022-08-23 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTON | 375655 | 2766 | 50 | Solar | 05_4J1 | 2021-08-18 12:19 | 2021-08-19 | 16 | 6 | 10 | 2021-09-13 | 2022-11-03 | 288 | 262 | 26 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTHBOROUGH | 375628 | 1581 | 43.2 | Solar | 05_313W2 | 2021-08-18 12:26 | 2021-08-19 | 65 | 57 | 8 | 2021-11-22 | 2022-02-25 | 22 | 0 | 22 | 2022-08-05 | 2022-10-19 | 52 | 0 | 52 | [5 empty] | 2022-08-05 | 2022-10-19 | 52 | 0 | 52 | [5 empty] | 2023-01-05 | 2021-08-18 12:30 | 2024-10-07 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | NORTON | 375661 | 2766 | 100 | Solar | 05_4J1 | 2021-08-18 12:30 | 2021-08-19 | 14 | 3 | 11 | [10 empty] | 2021-09-09 | 2022-01-03 | 80 | 47 | 33 | [10 empty] | 2022-06-08 |  | 2023-09-28 | Yes | STD |  | 2023-04-25 | 2023-07-28 | 95 | 75 | 20 |  |  | 2023-09-13 | Connected |  | No
National Grid | PEMBROKE | 366907 | 2359 | 7.6 | Solar | 07_910W52 | 2021-08-18 16:14 | 2021-08-19 | 31 | 26 | 5 | [26 empty] | 2021-08-18 19:48 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEST BROOKFIELD | 353809 | 1585 | 15.2 | Solar | 01_525L2 | 2021-08-18 19:48 | 2021-08-19 | 23 | 22 | 1 | 2021-09-21 | 2021-10-21 | 22 | 0 | 22 | [20 empty] | 2021-10-22 |  | 2023-07-15 | Yes | EXP |  | 2022-02-09 | 2022-03-23 | 43 | 0 | 43 |  |  |  | Withdrawn |  | Yes
National Grid | PHILLIPSTON | 375005 | 1331 | 17.28 | Solar | 09_702W1 | 2021-08-19 06:33 | 2021-08-20 | 15 | 13 | 2 | 2021-09-13 | 2021-10-19 | 25 | 0 | 25 | [20 empty] | 2021-11-01 | 2021-08-19 11:33 | 2022-11-30 |  | EXP | [8 empty] | 2022-05-28 | Connected |  | No
National Grid | BELCHERTOWN | 367563 | 1007 | 7.6 | Solar | 09_509L2 | 2021-08-19 11:33 | 2021-08-20 | 4 | 2 | 2 | 2021-08-27 | 2021-09-30 | 23 | 0 | 23 | [20 empty] | 2021-10-07 |  | 2023-06-30 | Yes | EXP |  | 2022-04-22 | 2022-05-23 | 32 | 0 | 32 |  |  | 2022-07-06 | Connected |  | No
National Grid | WORCESTER | 368621 | 1606 | 6 | Solar | 01_24W3 | 2021-08-19 12:05 | 2021-08-20 | 4 | 2 | 2 | 2021-08-27 | 2021-10-01 | 25 | 0 | 25 | [20 empty] | 2021-10-07 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WRENTHAM | 376877 | 2093 | 15.2 | Solar | 05_348W1 | 2021-08-19 12:11 | 2021-08-20 | 3 | 3 | 0 | 2021-08-25 | 2021-09-28 | 24 | 0 | 24 | [20 empty] | 2021-09-28 | 2021-08-19 12:59 | 2022-08-23 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ATTLEBORO | 376662 | 2703 | 7.6 | Solar | 05_8L3 | 2021-08-19 12:59 | 2021-08-20 | 6 | 5 | 1 | 2021-08-27 | 2021-08-26 | 0 | 0 | 0 | [20 empty] | 2021-08-26 |  | 2022-10-01 |  | EXP |  | 2021-09-14 | 2021-09-30 | 17 | 0 | 17 |  |  | 2021-10-07 | Connected |  | No
National Grid | ORANGE | 372949 | 1364 | 14.07 | Solar | 09_702W2 | 2021-08-19 16:43 | 2021-08-20 | 133 | 124 | 9 | 2022-03-03 | 2022-05-23 | 59 | 42 | 17 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | TYNGSBORO | 375882 | 1879 | 9.86 | Solar | 01_210L1 | 2021-08-19 19:55 | 2021-08-20 | 3 | 3 | 0 | 2021-08-25 | 2021-09-27 | 24 | 3 | 21 | [20 empty] | 2021-09-27 |  | 2022-10-27 |  | EXP | [8 empty] | 2021-12-01 | Connected |  | No
National Grid | BEVERLY | 376945 | 1915 | 6.96 | Solar | 12_51T1 | 2021-08-19 20:50 | 2021-08-20 | 2 | 0 | 2 | 2021-08-24 | 2021-09-30 | 26 | 2 | 24 | [20 empty] | 2021-10-01 |  | 2022-10-07 |  | EXP | [8 empty] | 2022-01-07 | Connected |  | Yes
National Grid | FLORENCE | 375735 | 1062 | 8.505 | Solar | 09_901W3 | 2021-08-23 09:31 | 2021-08-24 | 20 | 17 | 3 | 2021-09-22 | 2021-10-26 | 24 | 0 | 24 | [20 empty] | 2021-11-30 |  | 2023-01-03 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | GRAFTON | 374462 | 1519 | 10 | Solar | 01_328W3 | 2021-08-23 09:56 | 2021-08-24 | 5 | 2 | 3 | 2021-09-01 | 2021-10-06 | 25 | 0 | 25 | [20 empty] | 2021-11-15 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BRIDGEWATER | 377527 | 2324 | 15.2 | Solar | 07_912W73 | 2021-08-23 18:15 | 2021-08-24 | 4 | 2 | 2 | 2021-09-02 | 2021-11-22 | 55 | 25 | 30 | [22 empty] | 2022-08-29 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MEDFORD | 359749 | 2155 | 15 | Solar | 12_37W4 | 2021-08-24 09:26 | 2021-08-25 | 168 | 159 | 9 | 2022-04-29 | 2022-05-26 | 20 | 0 | 20 | [20 empty] | 2022-05-27 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SALEM | 368844 | 1970 | 100.8 | Solar | 12_3J1 | 2021-08-24 16:41 | 2021-08-25 | 15 | 6 | 9 | [10 empty] | 2021-09-16 | 2021-11-16 | 42 | 12 | 30 | [10 empty] | 2022-06-16 |  |  |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | WALES | 375386 | 1081 | 10 | Solar | 09_516L1 | 2021-08-24 19:29 | 2021-08-25 | 2 | 1 | 1 | 2021-08-26 | 2021-09-30 | 25 | 0 | 25 | [20 empty] | 2021-10-01 | 2021-08-25 10:19 | 2022-10-03 |  | EXP | [8 empty] | 2021-11-20 | Connected |  | No
National Grid | FALL RIVER | 376028 | 2724 | 3.8 | Solar | 05_115W42 | 2021-08-25 10:19 | 2021-08-26 | 2 | 0 | 2 | 2021-08-30 | 2021-10-04 | 25 | 0 | 25 | [20 empty] | 2021-10-12 |  | 2023-01-24 | Yes | EXP |  | 2021-12-02 | 2022-01-12 | 42 | 0 | 42 |  |  | 2022-02-07 | Connected |  | Yes
National Grid | BOLTON | 377961 | 1740 | 7.6 | Solar | 01_225W1 | 2021-08-25 13:22 | 2021-08-26 | 29 | 28 | 1 | 2021-10-07 | 2022-01-19 | 70 | 47 | 23 | [20 empty] | 2022-01-20 |  | 2022-10-05 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH GRAFTON | 377991 | 1536 | 19 | Solar | 01_328W3 | 2021-08-25 14:52 | 2021-08-26 | 27 | 26 | 1 | 2021-10-05 | 2021-11-10 | 26 | 4 | 22 | [20 empty] | 2021-11-16 |  | 2023-05-15 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | GRANBY | 369951 | 1033 | 996 | Solar | 09_527L1 | 2021-08-25 16:51 | 2021-08-26 | 53 | 30 | 23 | [29 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BEVERLY | 378053 | 1915 | 15.2 | Solar | 12_12L2 | 2021-08-25 17:43 | 2021-08-26 | 1 | 0 | 1 | 2021-08-27 | 2021-10-01 | 25 | 0 | 25 | [20 empty] | 2021-10-04 | 2021-08-26 09:50 | 2022-12-17 |  | EXP | [8 empty] | 2022-01-10 | Connected |  | No
National Grid | BROCKTON | 377483 | 2301 | 10 | Solar | 07_91W49 | 2021-08-26 09:50 | 2021-08-27 | 4 | 1 | 3 | 2021-09-01 | 2021-10-06 | 25 | 0 | 25 | [20 empty] | 2021-10-15 |  | 2023-05-05 | Yes | EXP |  | 2022-03-09 | 2022-03-31 | 23 | 0 | 23 |  |  | 2022-11-22 | Connected |  | Yes
National Grid | HAVERHILL | 375924 | 1832 | 9.8 | Solar | 14_74L5 | 2021-08-26 11:48 | 2021-08-27 | 3 | 0 | 3 | 2021-09-01 | 2021-10-05 | 24 | 0 | 24 | [20 empty] | 2021-11-29 |  | 2022-12-07 |  | EXP | [8 empty] | 2022-06-01 | Connected |  | No
National Grid | HOPEDALE | 378195 | 1747 | 11.4 | Solar | 05_335W9 | 2021-08-26 11:52 | 2021-08-27 | 16 | 15 | 1 | 2021-09-21 | 2021-10-25 | 24 | 0 | 24 | [20 empty] | 2021-11-01 |  | 2022-11-29 |  | EXP | [8 empty] | 2022-02-07 | Connected |  | No
National Grid | BOXFORD | 378271 | 1921 | 25 | Solar | 14_56L3 | 2021-08-26 14:26 | 2021-08-27 | 13 | 10 | 3 | 2021-09-15 | 2021-10-20 | 25 | 0 | 25 | [20 empty] | 2021-10-20 |  | 2022-10-22 |  | EXP | [8 empty] | 2022-03-17 | Connected |  | No
National Grid | NORTHBRIDGE | 377003 | 1534 | 20.8 | Solar | 05_320W5 | 2021-08-26 16:52 | 2021-08-27 | 186 | 167 | 19 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NEWBURY | 378339 | 1922 | 11.4 | Solar | 14_60L2 | 2021-08-26 19:07 | 2021-08-27 | 17 | 16 | 1 | 2021-09-22 | 2021-12-21 | 62 | 39 | 23 | [20 empty] | 2021-12-22 |  | 2023-01-12 |  | EXP | [8 empty] | 2022-01-13 | Connected |  | No
National Grid | BRIDGEWATER | 378348 | 2324 | 17.6 | Solar | 07_797W20 | 2021-08-26 19:49 | 2021-08-27 | 1 | 0 | 1 | 2021-08-30 | 2021-10-04 | 25 | 0 | 25 | [20 empty] | 2021-10-06 |  | 2023-03-06 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BEVERLY | 378451 | 1915 | 11.4 | Solar | 12_12L2 | 2021-08-27 11:54 | 2021-08-30 | 2 | 0 | 2 | 2021-09-01 | 2021-10-05 | 24 | 0 | 24 | [20 empty] | 2021-10-12 | 2021-08-29 10:09 | 2023-03-08 |  | EXP | [8 empty] | 2022-04-06 | Connected |  | No
National Grid | PEMBROKE | 378618 | 2359 | 15.2 | Solar | 07_95W2 | 2021-08-29 10:09 | 2021-08-30 | 1 | 0 | 1 | 2021-08-31 | 2021-10-04 | 24 | 0 | 24 | [20 empty] | 2021-10-06 |  | 2023-08-23 | Yes | EXP |  | 2021-12-28 | 2022-02-01 | 36 | 0 | 36 |  |  | 2022-10-13 | Connected |  | No
National Grid | EASTON | 378621 | 2356 | 7.6 | Solar | 07_92W78 | 2021-08-29 13:37 | 2021-08-30 | 20 | 19 | 1 | 2021-09-27 | 2021-11-03 | 27 | 4 | 23 | [20 empty] | 2021-11-09 |  | 2022-09-23 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 377474 | 1844 | 237.5 | Solar | 14_75L3 | 2021-08-30 09:19 | 2021-08-31 | 28 | 18 | 10 | 2021-10-08 | 2021-11-17 | 27 | 4 | 23 | [20 empty] | 2022-01-03 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTH ANDOVER | 378880 | 1845 | 15.2 | Solar | 14_56L1 | 2021-08-30 17:23 | 2021-08-31 | 1 | 0 | 1 | 2021-09-01 | 2021-10-06 | 26 | 2 | 24 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHELMSFORD | 378906 | 1824 | 11.4 | Solar | 14_58L2 | 2021-08-30 19:43 | 2021-08-31 | 27 | 26 | 1 | 2021-10-08 | 2022-02-03 | 81 | 58 | 23 | [20 empty] | 2022-02-08 |  | 2023-05-05 |  | EXP | [8 empty] | 2022-08-24 | Connected |  | No
National Grid | BEVERLY | 378580 | 1915 | 9.8 | Solar | 12_12L2 | 2021-08-30 20:25 | 2021-08-31 | 9 | 8 | 1 | 2021-09-13 | 2021-10-19 | 25 | 0 | 25 | [20 empty] | 2021-10-19 |  | 2022-11-21 |  | EXP | [8 empty] | 2022-07-21 | Connected |  | No
National Grid | WORCESTER | 376655 | 1605 | 9.8 | Solar | 01_24W2 | 2021-08-31 09:30 | 2021-09-01 | 50 | 45 | 5 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 379039 | 1609 | 15.2 | Solar | 01_23W2 | 2021-08-31 11:43 | 2021-09-01 | 13 | 13 | 0 | 2021-09-21 | 2021-10-21 | 22 | 0 | 22 | [20 empty] | 2021-10-22 |  | 2023-07-27 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BOLTON | 372931 | 1740 | 7.6 | Solar | 05_318W3 | 2021-08-31 13:22 | 2021-09-01 | 4 | 4 | 0 | 2021-09-09 | 2021-10-14 | 25 | 0 | 25 | [20 empty] | 2021-10-15 |  | 2023-05-14 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | QUINCY | 379106 | 2169 | 11.4 | Solar | 07_3W2 | 2021-08-31 14:24 | 2021-09-01 | 23 | 21 | 2 | 2021-10-05 | 2021-11-10 | 26 | 4 | 22 | [20 empty] | 2021-11-18 |  | 2022-11-24 |  | EXP | [8 empty] | 2022-07-06 | Connected |  | No
National Grid | BOLTON | 379354 | 1740 | 15.36 | Solar | 01_216W6 | 2021-09-01 13:11 | 2021-09-02 | 7 | 7 | 0 | 2021-09-14 | 2021-10-19 | 25 | 0 | 25 | [20 empty] | 2021-10-19 |  | 2022-10-22 |  | EXP | [8 empty] | 2021-11-22 | Connected |  | No
National Grid | WESTBOROUGH | 376567 | 1581 | 15.2 | Solar | 05_312W4 | 2021-09-01 13:23 | 2021-09-02 | 98 | 92 | 6 | [25 empty] | 2022-02-09 |  |  |  | EXP | [8 empty] | 2022-05-26 | Connected |  | No
National Grid | ADAMS | 379398 | 1220 | 15.2 | Solar | 09_1021W1 | 2021-09-01 14:17 | 2021-09-02 | 25 | 24 | 1 | 2021-10-08 | 2021-11-16 | 26 | 4 | 22 | [20 empty] | 2021-11-18 |  | 2022-10-06 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTFORD | 378620 | 1886 | 7.6 | Solar | 14_73L2 | 2021-09-01 18:44 | 2021-09-02 | 1 | 0 | 1 | 2021-09-03 | 2021-10-07 | 24 | 0 | 24 | [20 empty] | 2021-10-07 |  | 2023-05-19 |  | EXP | [8 empty] | 2022-05-25 | Connected |  | No
National Grid | GRAFTON | 375886 | 1536 | 15.2 | Solar | 01_304W1 | 2021-09-01 19:18 | 2021-09-02 | 5 | 3 | 2 | 2021-09-10 | 2021-10-15 | 25 | 0 | 25 | [20 empty] | 2021-10-20 | 2021-09-02 05:56 | 2022-11-29 |  | EXP | [8 empty] | 2022-04-22 | Connected |  | Yes
National Grid | ROCKPORT | 376072 | 1966 | 10 | Solar | 12_40J2 | 2021-09-02 05:56 | 2021-08-19 | 12 | 10 | 2 | 2021-09-03 | 2021-10-07 | 24 | 0 | 24 | [20 empty] | 2021-10-08 |  | 2023-01-28 | Yes | EXP |  | 2021-12-10 | 2022-01-27 | 49 | 0 | 49 |  |  | 2022-01-31 | Connected |  | No
National Grid | NORTH ANDOVER | 379389 | 1845 | 9.57 | Solar | 14_55L1 | 2021-09-02 08:43 | 2021-09-03 | 23 | 23 | 0 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SALEM | 379550 | 1970 | 16 | Solar | 12_2W1 | 2021-09-02 10:05 | 2021-09-03 | 2 | 0 | 2 | 2021-09-08 | 2021-10-12 | 24 | 0 | 24 | [20 empty] | 2021-11-02 |  | 2022-11-09 |  | EXP | [8 empty] | 2022-02-16 | Connected |  | No
National Grid | NORTHAMPTON | 379683 | 1062 | 25 | Other | 09_909W4 | 2021-09-02 16:16 | 2021-09-03 | 32 | 25 | 7 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | STURBRIDGE | 379733 | 1518 | 15.2 | Solar | 01_408L2 | 2021-09-02 18:46 | 2021-09-03 | 1 | 0 | 1 | 2021-09-07 | 2021-12-14 | 68 | 26 | 42 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MILLBURY | 358733 | 1527 | 133.2 | Solar | 01_26W2 | 2021-09-03 11:24 | 2021-09-07 | 172 | 162 | 10 | [10 empty] | 2022-05-13 | 2022-06-14 | 22 | 0 | 22 | [11 empty] | 2021-09-03 12:47 |  |  | STD | [9 empty] | Study |  | No
National Grid | NORTH ANDOVER | 378789 | 1845 | 100 | Solar | 14_71L3 | 2021-09-03 12:47 | 2021-09-07 | 22 | 12 | 10 | [10 empty] | 2021-10-07 | 2021-11-29 | 35 | 4 | 31 | [10 empty] | 2022-04-21 |  | 2023-07-09 |  | STD | [8 empty] | 2022-09-07 | Connected |  | No
National Grid | SWAMPSCOTT | 380086 | 1907 | 15.2 | Solar | 12_9J2 | 2021-09-05 14:01 | 2021-09-07 | 15 | 14 | 1 | 2021-09-28 | 2021-12-07 | 48 | 29 | 19 | [20 empty] | 2021-12-08 | 2021-09-05 18:58 | 2023-01-31 |  | EXP | [8 empty] | 2022-07-15 | Connected |  | No
National Grid | WORCESTER | 380094 | 1602 | 7.6 | Solar | 01_23W4 | 2021-09-05 18:58 | 2021-09-07 | 1 | 0 | 1 | 2021-09-08 | 2021-10-13 | 25 | 0 | 25 | [20 empty] | 2021-10-13 |  | 2023-02-15 | Yes | EXP |  | 2022-01-19 | 2022-02-14 | 27 | 0 | 27 |  |  | 2022-05-27 | Connected |  | No
National Grid | BRIDGEWATER | 380096 | 2324 | 15.2 | Solar | 07_912W21 | 2021-09-05 19:37 | 2021-09-07 | 1 | 0 | 1 | 2021-09-08 | 2021-10-13 | 25 | 0 | 25 | [20 empty] | 2021-10-13 |  | 2022-09-06 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MELROSE | 376077 | 2176 | 15.2 | Solar | 12_25W5 | 2021-09-06 10:42 | 2021-09-07 | 1 | 0 | 1 | 2021-09-08 | 2021-10-11 | 24 | 0 | 24 | [20 empty] | 2021-10-12 |  | 2022-09-13 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MILLBURY | 380180 | 1527 | 15.2 | Solar | 01_328W2 | 2021-09-06 14:36 | 2021-09-07 | 19 | 18 | 1 | 2021-10-01 | 2021-11-08 | 26 | 4 | 22 | [20 empty] | 2021-11-15 |  | 2022-09-29 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ANDOVER | 380185 | 1810 | 7.6 | Solar | 14_62L2 | 2021-09-06 16:16 | 2021-09-07 | 75 | 69 | 6 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | UXBRIDGE | 370747 | 1569 | 455 | Solar | 05_321W5 | 2021-09-07 09:15 | 2021-09-08 | 198 | 189 | 9 | [10 empty] | 2022-06-23 | 2022-11-21 | 104 | 85 | 19 | [11 empty] | 2021-09-07 09:17 |  |  | STD | [9 empty] | Study |  | No
National Grid | MILFORD | 373774 | 1757 | 9.6 | Solar | 05_336W3 | 2021-09-07 09:17 | 2021-09-08 | 4 | 0 | 4 | 2021-09-14 | 2021-10-19 | 25 | 0 | 25 | [20 empty] | 2021-11-01 | 2021-09-07 16:33 | 2023-06-02 | Yes | EXP |  | 2022-02-01 | 2022-04-22 | 81 | 0 | 81 |  |  | 2022-06-07 | Connected |  | No
National Grid | BOLTON | 366496 | 1740 | 8.7 | Solar | 05_318W3 | 2021-09-07 16:33 | 2021-09-08 | 4 | 0 | 4 | 2021-09-14 | 2021-10-19 | 25 | 0 | 25 | [20 empty] | 2021-11-01 | 2021-09-08 11:03 | 2023-12-21 | Yes | EXP |  | 2022-04-13 | 2022-12-21 | 253 | 0 | 253 |  |  |  | Withdrawn |  | Yes
National Grid | NORTH ANDOVER | 367917 | 1845 | 900 | Solar | 14_43L7 | 2021-09-08 11:03 | 2021-09-09 | 20 | 10 | 10 | [10 empty] | 2021-10-07 | 2021-12-14 | 46 | 21 | 25 | [10 empty] | 2022-07-11 |  | 2024-06-27 | Yes | STD |  | 2023-07-12 | 2024-04-10 | 272 | 184 | 88 |  |  |  | Witness Test |  | No
National Grid | AVON | 378486 | 2322 | 5.76 | Solar | 07_75W3 | 2021-09-08 12:39 | 2021-09-09 | 3 | 0 | 3 | 2021-09-14 | 2021-10-21 | 23 | 0 | 23 | [20 empty] | 2021-11-22 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LYNN | 378521 | 1905 | 5.76 | Solar | 12_29W3 | 2021-09-08 13:17 | 2021-09-09 | 3 | 0 | 3 | 2021-09-14 | 2021-10-22 | 25 | 0 | 25 | [20 empty] | 2021-11-08 |  | 2022-11-17 |  | EXP | [8 empty] | 2022-01-21 | Connected |  | No
National Grid | PEMBROKE | 373135 | 2359 | 498 | Solar | 07_910W25 | 2021-09-08 17:08 | 2021-09-09 | 24 | 16 | 8 | [10 empty] | 2021-10-14 | 2021-10-15 | 5 | 4 | 1 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | WESTFORD | 373288 | 1886 | 15.2 | Solar | 14_57L2 | 2021-09-08 18:58 | 2021-09-09 | 11 | 10 | 1 | 2021-09-23 | 2021-10-22 | 21 | 0 | 21 | [20 empty] | 2021-10-22 |  | 2023-02-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SEEKONK | 380801 | 2771 | 11.4 | Solar | 05_7L1 | 2021-09-08 20:41 | 2021-09-09 | 4 | 3 | 1 | 2021-09-14 | 2021-10-19 | 25 | 0 | 25 | [20 empty] | 2021-10-19 | 2021-09-09 08:40 | 2023-05-15 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BEVERLY | 380771 | 1915 | 360 | Solar | 12_12L4 | 2021-09-09 08:40 | 2021-09-10 | 21 | 14 | 7 | [10 empty] | 2021-10-12 | 2021-12-15 | 45 | 5 | 40 | [10 empty] | 2022-10-03 |  | 2024-06-25 | Yes | STD | [9 empty] | Construction |  | Yes
National Grid | FLORENCE | 378064 | 1062 | 3.8 | Solar | 09_909W4 | 2021-09-09 13:45 | 2021-09-10 | 3 | 0 | 3 | 2021-09-15 | 2021-10-20 | 25 | 0 | 25 | [20 empty] | 2021-11-01 | 2021-09-09 15:11 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | FRANKLIN | 381025 | 2038 | 240 | Solar | 05_348W6 | 2021-09-09 15:11 | 2021-09-10 | 24 | 17 | 7 | 2021-10-15 | 2021-12-07 | 36 | 11 | 25 | 2021-12-29 | 2022-03-03 | 45 | 0 | 45 | [5 empty] | 2021-12-29 | 2022-03-03 | 45 | 0 | 45 | [5 empty] | 2022-04-20 | 2021-09-09 15:53 | 2024-09-15 | Yes | EXP | [9 empty] | Construction |  | No
National Grid | FALL RIVER | 379546 | 2723 | 10 | Solar | 05_106W82 | 2021-09-09 15:53 | 2021-09-24 | 4 | 3 | 1 | 2021-09-29 | 2021-11-03 | 25 | 4 | 21 | [20 empty] | 2021-11-04 | 2021-09-10 09:57 | 2023-01-03 | Yes | EXP |  | 2021-12-04 | 2022-01-03 | 31 | 0 | 31 |  |  | 2022-02-05 | Connected |  | No
National Grid | BEVERLY | 377712 | 1915 | 67 | Solar | 12_51L1 | 2021-09-10 09:57 | 2021-09-13 | 46 | 36 | 10 | 2021-11-18 | 2022-04-08 | 99 | 51 | 48 | [20 empty] | 2022-05-02 | 2021-09-10 14:00 | 2023-04-30 | Yes | EXP | [8 empty] | 2023-05-12 | Connected |  | No
National Grid | NORTON | 375359 | 2766 | 400 | Solar | 05_8L2 | 2021-09-10 14:00 | 2021-09-13 | 24 | 16 | 8 | [10 empty] | 2021-10-18 | 2022-01-03 | 54 | 21 | 33 | [10 empty] | 2022-06-08 | 2021-09-10 14:25 | 2024-05-03 | Yes | STD |  | 2023-02-24 | 2023-04-24 | 60 | 0 | 60 |  |  |  | Meter Installation |  | Yes
National Grid | METHUEN | 373213 | 1844 | 10 | Solar | 14_43L4 | 2021-09-10 14:25 | 2021-09-13 | 3 | 0 | 3 | 2021-09-16 | 2021-10-21 | 25 | 0 | 25 | [20 empty] | 2021-11-10 | 2021-09-10 17:56 | 2023-07-27 | Yes | EXP |  | 2022-06-09 | 2022-06-08 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Yes
National Grid | FALL RIVER | 377985 | 2721 | 6 | Solar | 05_115W52 | 2021-09-10 17:56 | 2021-09-13 | 3 | 0 | 3 | 2021-09-16 | 2021-10-21 | 25 | 0 | 25 | [20 empty] | 2021-11-23 |  | 2023-05-25 | Yes | EXP |  | 2022-04-12 | 2022-05-18 | 37 | 0 | 37 |  |  | 2022-06-29 | Connected |  | No
National Grid | METHUEN | 378603 | 1844 | 9.8 | Solar | 14_43L4 | 2021-09-10 18:25 | 2021-09-13 | 3 | 2 | 1 | 2021-09-15 | 2021-10-20 | 25 | 0 | 25 | [20 empty] | 2021-10-25 | 2021-09-10 20:16 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LYNN | 380798 | 1905 | 5 | Solar | 12_29W1 | 2021-09-10 20:16 | 2021-09-24 | 1 | 0 | 1 | 2021-09-27 | 2021-11-03 | 27 | 4 | 23 | [20 empty] | 2021-11-04 | 2021-09-13 11:30 | 2023-02-27 | Yes | EXP |  | 2022-01-13 | 2022-02-24 | 43 | 0 | 43 |  |  | 2022-03-03 | Connected |  | No
National Grid | DRACUT | 377505 | 1826 | 4.93 | Solar | 14_78L1 | 2021-09-13 11:30 | 2021-09-14 | 2 | 0 | 2 | 2021-09-16 | 2021-10-21 | 25 | 0 | 25 | [20 empty] | 2021-11-22 |  |  | Yes | EXP |  | 2022-02-22 | 2022-03-10 | 16 | 0 | 16 |  |  | 2022-03-29 | Connected |  | Yes
National Grid | PALMER | 373295 | 1080 | 7.6 | Solar | 09_514L1 | 2021-09-13 11:59 | 2021-09-14 | 20 | 19 | 1 | 2021-10-13 | 2021-11-18 | 26 | 4 | 22 | [20 empty] | 2021-11-29 | 2021-09-13 12:36 | 2022-10-11 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EVERETT | 378586 | 2149 | 7.6 | Solar | 12_16W7 | 2021-09-13 12:36 | 2021-09-14 | 2 | 0 | 2 | 2021-09-16 | 2021-10-21 | 25 | 0 | 25 | [20 empty] | 2021-11-15 |  | 2023-08-30 | Yes | EXP |  | 2022-02-22 | 2022-04-06 | 43 | 0 | 43 |  |  | 2022-09-03 | Connected |  | No
National Grid | WINTHROP | 375833 | 2152 | 8.7 | Solar | 12_22J1 | 2021-09-13 13:02 | 2021-09-14 | 7 | 6 | 1 | 2021-09-22 | 2021-10-27 | 25 | 2 | 23 | [20 empty] | 2021-11-01 |  | 2022-11-24 |  | EXP | [8 empty] | 2021-12-23 | Connected |  | No
National Grid | NORTHBOROUGH | 381762 | 1532 | 15.2 | Solar | 05_313W1 | 2021-09-13 19:52 | 2021-09-14 | 15 | 14 | 1 | 2021-10-05 | 2021-11-12 | 27 | 4 | 23 | [20 empty] | 2021-11-16 |  | 2023-01-17 |  | EXP | [8 empty] | 2023-01-13 | Connected |  | No
National Grid | NORTH ANDOVER | 379254 | 1845 | 200 | Solar | 14_2326 | 2021-09-14 13:42 | 2021-09-15 | 8 | 0 | 8 | [10 empty] | 2021-09-27 | 2021-11-30 | 44 | 4 | 40 | [10 empty] | 2022-09-12 |  |  |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | GRAFTON | 382030 | 1560 | 19 | Solar | 05_320W3 | 2021-09-14 16:27 | 2021-09-15 | 6 | 5 | 1 | 2021-09-22 | 2021-10-27 | 25 | 2 | 23 | [20 empty] | 2021-11-01 |  | 2022-09-20 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTFORD | 382038 | 1886 | 19.14 | Solar | 14_57L2 | 2021-09-14 16:41 | 2021-09-15 | 3 | 0 | 3 | 2021-09-20 | 2021-10-21 | 23 | 0 | 23 | [20 empty] | 2021-11-22 | 2021-09-15 08:33 | 2023-06-30 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | TEWKSBURY | 381249 | 1876 | 10 | Solar | 14_14L1 | 2021-09-15 08:33 | 2021-09-16 | 3 | 0 | 3 | 2021-09-21 | 2021-10-26 | 24 | 0 | 24 | [20 empty] | 2021-11-30 | 2021-09-15 10:57 | 2023-09-02 | Yes | EXP |  | 2022-07-01 | 2022-08-02 | 33 | 0 | 33 |  |  | 2022-10-12 | Connected |  | No
National Grid | WESTMINSTER | 382185 | 1473 | 15.2 | Solar | 01_610W3 | 2021-09-15 10:57 | 2021-09-16 | 3 | 0 | 3 | 2021-09-21 | 2021-10-26 | 24 | 0 | 24 | [20 empty] | 2021-11-30 | 2021-09-15 11:56 | 2023-11-03 | Yes | EXP |  | 2022-09-02 | 2022-10-26 | 55 | 0 | 55 |  |  | 2022-12-13 | Connected |  | No
National Grid | TEWKSBURY | 382224 | 1876 | 15.2 | Solar | 14_70L8 | 2021-09-15 11:56 | 2021-09-16 | 21 | 19 | 2 | 2021-10-15 | 2021-11-09 | 18 | 4 | 14 | [20 empty] | 2021-11-09 |  | 2023-05-02 | Yes | EXP |  | 2022-04-06 | 2022-05-02 | 27 | 0 | 27 |  |  | 2022-05-20 | Connected |  | No
National Grid | BEVERLY | 382216 | 1915 | 9.772 | Solar | 12_51T1 | 2021-09-15 12:03 | 2021-09-16 | 4 | 3 | 1 | 2021-09-21 | 2021-10-25 | 24 | 0 | 24 | [20 empty] | 2021-11-01 |  | 2022-11-22 |  | EXP | [8 empty] | 2022-01-22 | Connected |  | No
National Grid | FRANKLIN | 368511 | 2038 | 3.8 | Solar | 05_65H4 | 2021-09-15 14:02 | 2021-09-16 | 36 | 35 | 1 | 2021-11-09 | 2021-12-07 | 19 | 0 | 19 | [20 empty] | 2021-12-08 |  | 2023-01-10 |  | EXP | [8 empty] | 2022-03-31 | Connected |  | No
National Grid | LOWELL | 382184 | 1850 | 16.56 | Solar | 14_75L1 | 2021-09-15 14:17 | 2021-09-16 | 2 | 0 | 2 | 2021-09-20 | 2021-10-21 | 23 | 0 | 23 | [20 empty] | 2021-11-23 |  | 2024-03-27 |  | EXP | [8 empty] | 2023-06-14 | Connected |  | No
National Grid | SUTTON | 382260 | 1590 | 7.6 | Solar | 01_304W6 | 2021-09-15 14:33 | 2021-09-16 | 2 | 1 | 1 | 2021-09-20 | 2021-10-25 | 24 | 0 | 24 | [20 empty] | 2021-11-01 |  | 2023-03-17 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 378903 | 2301 | 9.8 | Solar | 07_98W46 | 2021-09-15 19:31 | 2021-09-16 | 1 | 0 | 1 | 2021-09-17 | 2021-11-03 | 33 | 10 | 23 | [20 empty] | 2021-11-04 | 2021-09-15 19:38 | 2022-09-16 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEBSTER | 379708 | 1570 | 9.8 | Solar | 01_412L1 | 2021-09-15 19:38 | 2021-09-16 | 3 | 0 | 3 | 2021-09-21 | 2021-10-26 | 24 | 0 | 24 | [20 empty] | 2021-11-30 |  | 2023-04-26 | Yes | EXP |  | 2022-03-31 | 2022-04-26 | 27 | 0 | 27 |  |  | 2022-05-24 | Connected |  | No
National Grid | METHUEN | 381715 | 1844 | 11.04 | Solar | 14_43L4 | 2021-09-16 10:59 | 2021-09-17 | 2 | 0 | 2 | 2021-09-21 | 2021-10-25 | 24 | 0 | 24 | [20 empty] | 2021-11-16 | 2021-09-16 14:16 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SWANSEA | 381880 | 2777 | 7.54 | Solar | 05_19W73 | 2021-09-16 14:16 | 2021-09-17 | 15 | 13 | 2 | 2021-10-08 | 2021-11-18 | 28 | 4 | 24 | [20 empty] | 2021-11-30 |  | 2023-01-20 | Yes | EXP |  | 2022-01-04 | 2022-01-13 | 10 | 0 | 10 |  |  | 2022-02-04 | Connected |  | No
National Grid | NEW BRAINTREE | 360612 | 1531 | 1625 | Solar | 01_525L2 | 2021-09-16 15:26 | 2021-09-17 | 60 | 50 | 10 | [10 empty] | 2021-12-14 | 2022-01-13 | 22 | 0 | 22 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | HAVERHILL | 378895 | 1832 | 6 | Solar | 14_43L2 | 2021-09-16 15:55 | 2021-09-17 | 3 | 0 | 3 | 2021-09-22 | 2021-10-26 | 24 | 0 | 24 | [20 empty] | 2021-11-30 |  | 2023-03-09 |  | EXP | [8 empty] | 2022-03-31 | Connected |  | Yes
National Grid | PEMBROKE | 363041 | 2359 | 7.6 | Solar | 07_910W52 | 2021-09-16 15:59 | 2021-09-17 | 1 | 0 | 1 | 2021-09-20 | 2021-10-21 | 23 | 0 | 23 | [20 empty] | 2021-10-22 |  | 2022-10-23 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EAST BROOKFIELD | 376647 | 1515 | 3.8 | Solar | 01_552L3 | 2021-09-16 17:45 | 2021-09-17 | 18 | 17 | 1 | 2021-10-13 | 2021-11-18 | 26 | 4 | 22 | [20 empty] | 2021-11-23 |  | 2022-10-11 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BEVERLY | 382439 | 1915 | 10 | Solar | 12_12L2 | 2021-09-17 11:20 | 2021-09-20 | 42 | 40 | 2 | 2021-11-18 | 2021-12-21 | 23 | 0 | 23 | [20 empty] | 2021-12-14 | 2021-09-17 12:26 | 2023-01-11 |  | EXP | [8 empty] | 2022-11-21 | Connected |  | No
National Grid | SAUGUS | 374128 | 1906 | 10 | Solar | 12_23W2 | 2021-09-17 12:26 | 2021-09-20 | 2 | 0 | 2 | 2021-09-22 | 2021-10-26 | 24 | 0 | 24 | [20 empty] | 2021-11-23 |  | 2023-04-07 | Yes | EXP |  | 2022-02-22 | 2022-03-22 | 28 | 0 | 28 |  |  | 2022-06-08 | Connected |  | No
National Grid | WOLLASTON | 369405 | 2170 | 9.57 | Solar | 07_1W8 | 2021-09-17 13:48 | 2021-09-20 | 2 | 0 | 2 | 2021-09-22 | 2021-10-27 | 25 | 2 | 23 | [20 empty] | 2021-10-29 |  | 2023-06-26 |  | EXP | [8 empty] | 2023-06-28 | Connected |  | No
National Grid | SAUGUS | 380188 | 1906 | 9.8 | Solar | 12_23W2 | 2021-09-18 16:25 | 2021-09-20 | 2 | 0 | 2 | 2021-09-22 | 2021-10-26 | 24 | 0 | 24 | [20 empty] | 2021-11-30 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | AYER | 382980 | 1432 | 3.8 | Solar | 01_201W3 | 2021-09-19 16:47 | 2021-09-20 | 20 | 19 | 1 | 2021-10-19 | 2021-11-22 | 24 | 4 | 20 | [20 empty] | 2021-11-29 | 2021-09-19 19:24 | 2022-10-17 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BOXFORD | 382988 | 1921 | 15.2 | Solar | 14_56L3 | 2021-09-19 19:24 | 2021-09-20 | 36 | 29 | 7 | 2021-11-10 | 2022-01-12 | 44 | 25 | 19 | [20 empty] | 2022-01-12 |  | 2023-03-17 |  | EXP |  | 2022-02-23 | 2022-03-17 | 23 | 0 | 23 |  |  | 2022-04-21 | Connected |  | No
National Grid | GREAT BARRINGTON | 376995 | 1230 | 28.8 | Solar | 09_1109W2 | 2021-09-20 10:57 | 2021-09-21 | 7 | 5 | 2 | 2021-09-30 | 2021-11-08 | 27 | 4 | 23 | [20 empty] | 2021-11-22 |  | 2022-12-08 |  | EXP | [8 empty] | 2022-05-31 | Connected |  | No
National Grid | METHUEN | 379714 | 1844 | 6 | Solar | 14_63L1 | 2021-09-20 18:53 | 2021-09-21 | 4 | 0 | 4 | 2021-09-27 | 2021-10-28 | 23 | 3 | 20 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | NEW MARLBOROUGH | 383151 | 1230 | 19.57 | Solar | 09_1109W1 | 2021-09-21 10:09 | 2021-09-22 | 5 | 4 | 1 | 2021-09-28 | 2021-10-11 | 10 | 0 | 10 | [20 empty] | 2021-10-11 |  | 2022-10-15 |  | EXP | [8 empty] | 2021-10-19 | Connected |  | No
National Grid | LAWRENCE | 348813 | 1841 | 750 | Solar | 14_2355 | 2021-09-21 12:17 | 2021-09-22 | 563 | 554 | 9 | [10 empty] | 2022-01-21 | 2022-03-03 | 29 | 0 | 29 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 376329 | 1609 | 7.6 | Solar | 01_11J351 | 2021-09-21 14:33 | 2021-09-22 | 51 | 50 | 1 | 2021-12-07 | 2022-01-06 | 22 | 0 | 22 | 2022-04-05 | 2023-12-14 | 422 | 0 | 422 | [5 empty] | 2022-04-05 | 2023-12-14 | 422 | 0 | 422 | [5 empty] | 2022-03-30 |  | 2024-08-20 |  | EXP |  | 2023-09-09 | 2023-12-14 | 97 | 0 | 97 |  |  |  | Withdrawn |  | Yes
National Grid | CHELMSFORD | 379424 | 1824 | 7.6 | Solar | 14_24L2 | 2021-09-21 15:41 | 2021-09-22 | 3 | 0 | 3 | 2021-09-27 | 2021-10-28 | 23 | 3 | 20 | [20 empty] | 2021-12-09 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SEEKONK | 383572 | 2771 | 15.2 | Solar | 05_7L5 | 2021-09-21 19:08 | 2021-09-22 | 3 | 0 | 3 | 2021-09-27 | 2021-10-28 | 23 | 3 | 20 | [20 empty] | 2021-12-09 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | PLAINVILLE | 380603 | 2762 | 9.6 | Solar | 05_3422W3 | 2021-09-22 16:18 | 2021-09-23 | 2 | 1 | 1 | 2021-09-24 | 2021-10-27 | 23 | 2 | 21 | [20 empty] | 2021-11-02 |  | 2022-11-06 |  | EXP | [8 empty] | 2021-12-16 | Connected |  | No
National Grid | ROCKLAND | 383891 | 2370 | 8.7 | Solar | 07_93W40 | 2021-09-22 23:43 | 2021-09-23 | 2 | 0 | 2 | 2021-09-27 | 2021-10-28 | 23 | 3 | 20 | [20 empty] | 2021-12-09 |  | 2023-02-07 |  | EXP | [8 empty] | 2022-07-01 | Connected |  | No
National Grid | NORTHAMPTON | 383931 | 1060 | 20.59 | Solar | 09_901W1 | 2021-09-23 09:48 | 2021-09-24 | 2 | 0 | 2 | 2021-09-28 | 2021-11-03 | 26 | 4 | 22 | [20 empty] | 2021-11-09 |  | 2023-07-21 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LYNN | 379716 | 1904 | 9.8 | Solar | 12_29W1 | 2021-09-23 14:46 | 2021-09-24 | 4 | 0 | 4 | 2021-09-30 | 2021-11-08 | 27 | 4 | 23 | [20 empty] | 2021-12-14 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | STOUGHTON | 362507 | 2072 | 900 | Solar | 07_75W7 | 2021-09-23 16:24 | 2021-09-24 | 88 | 78 | 10 | [10 empty] | 2022-02-01 | 2022-02-25 | 17 | 1 | 16 | [11 empty] | 2021-09-23 16:49 |  |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 381732 | 1841 | 6 | Solar | 14_53J5 | 2021-09-23 16:49 | 2021-09-24 | 4 | 0 | 4 | 2021-09-30 | 2021-11-08 | 27 | 4 | 23 | [20 empty] | 2021-12-09 | 2021-09-23 17:25 | 2023-05-28 | Yes | EXP |  | 2022-04-14 | 2022-05-21 | 36 | 0 | 36 |  |  | 2022-06-30 | Connected |  | Yes
National Grid | BROCKTON | 381609 | 2301 | 9.8 | Solar | 07_98W46 | 2021-09-23 17:25 | 2021-09-24 | 4 | 0 | 4 | 2021-09-30 | 2021-11-08 | 27 | 4 | 23 | [20 empty] | 2021-12-09 |  |  | Yes | EXP |  | 2022-04-23 | 2022-04-25 | 3 | 0 | 3 |  |  |  | Withdrawn |  | Yes
National Grid | SOUTH EGREMONT | 383564 | 1258 | 25 | Solar | 09_1109W2 | 2021-09-23 17:49 | 2021-09-24 | 2 | 0 | 2 | 2021-09-28 | 2021-12-07 | 49 | 27 | 22 | [20 empty] | 2021-12-08 |  | 2022-12-11 |  | EXP | [8 empty] | 2022-03-01 | Connected |  | Yes
National Grid | CLINTON | 287338 | 1510 | 3200 | Hydro | 01_216W1 | 2021-09-24 08:01 | 2021-09-27 | 137 | 127 | 10 | [10 empty] | 2022-04-28 | 2022-05-23 | 18 | 0 | 18 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | DUNSTABLE | 384470 | 1827 | 7.6 | Solar | 01_210L1 | 2021-09-26 10:16 | 2021-09-27 | 34 | 26 | 8 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BOLTON | 384559 | 1740 | 7.6 | Solar | 05_318W3 | 2021-09-27 11:35 | 2021-09-28 | 1 | 0 | 1 | 2021-09-29 | 2021-11-03 | 25 | 4 | 21 | [20 empty] | 2021-11-09 |  | 2023-05-02 |  | EXP | [8 empty] | 2022-05-16 | Connected |  | No
National Grid | NORTHBOROUGH | 380928 | 1532 | 17.92 | Solar | 05_313W2 | 2021-09-27 14:11 | 2021-09-28 | 2 | 0 | 2 | 2021-09-30 | 2021-11-08 | 27 | 4 | 23 | [20 empty] | 2021-12-07 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | DIGHTON | 383763 | 2715 | 233.3 | Solar | 05_19W74 | 2021-09-27 15:24 | 2021-09-28 | 10 | 2 | 8 | [10 empty] | 2021-10-13 | 2021-12-03 | 36 | 4 | 32 | [10 empty] | 2023-04-18 |  | 2024-05-19 |  | STD | [9 empty] | Completion Documents |  | Yes
National Grid | SCITUATE | 384763 | 2066 | 15.2 | Solar | 07_15J1 | 2021-09-27 18:47 | 2021-09-28 | 58 | 49 | 9 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | REHOBOTH | 384910 | 2769 | 9.86 | Solar | 05_7L4 | 2021-09-28 11:47 | 2021-09-29 | 9 | 7 | 2 | 2021-10-12 | 2021-11-18 | 27 | 4 | 23 | [20 empty] | 2021-12-15 |  | 2022-12-17 |  | EXP | [8 empty] | 2022-07-08 | Connected |  | No
National Grid | DUDLEY | 375104 | 1571 | 9.8 | Solar | 01_412L4 | 2021-09-28 18:22 | 2021-09-29 | 4 | 0 | 4 | 2021-10-05 | 2021-11-10 | 26 | 4 | 22 | [20 empty] | 2021-12-14 |  | 2022-12-16 |  | EXP | [8 empty] | 2022-06-16 | Connected |  | No
National Grid | WESTFORD | 385131 | 1886 | 7.6 | Solar | 14_73L2 | 2021-09-28 19:48 | 2021-09-29 | 4 | 3 | 1 | 2021-10-04 | 2021-11-08 | 25 | 4 | 21 | [20 empty] | 2021-11-15 |  | 2022-09-30 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH ANDOVER | 385253 | 1845 | 9.8 | Solar | 14_56L2 | 2021-09-29 12:36 | 2021-09-30 | 4 | 3 | 1 | 2021-10-05 | 2021-11-10 | 26 | 4 | 22 | [20 empty] | 2021-11-16 |  | 2022-11-29 |  | EXP | [8 empty] | 2022-03-24 | Connected |  | No
National Grid | SPENCER | 382477 | 1562 | 15.2 | Solar | 01_21W1 | 2021-09-29 14:56 | 2021-09-30 | 22 | 19 | 3 | 2021-11-02 | 2021-12-02 | 21 | 0 | 21 | [20 empty] | 2021-12-14 |  | 2022-12-29 |  | EXP | [8 empty] | 2022-04-13 | Connected |  | No
National Grid | MILFORD | 384000 | 1757 | 6 | Solar | 05_335W5 | 2021-09-29 16:56 | 2021-09-30 | 3 | 0 | 3 | 2021-10-05 | 2021-11-10 | 26 | 4 | 22 | [20 empty] | 2021-12-14 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | UXBRIDGE | 369766 | 1569 | 5 | Solar | 05_320W4 | 2021-09-30 15:04 | 2021-10-01 | 2 | 0 | 2 | 2021-10-05 | 2021-11-10 | 26 | 4 | 22 | [20 empty] | 2021-12-13 |  | 2023-04-08 |  | EXP | [8 empty] | 2022-08-05 | Connected |  | Yes
National Grid | WRENTHAM | 385688 | 2093 | 15.2 | Solar | 05_3422W4 | 2021-09-30 20:09 | 2021-10-01 | 1 | 0 | 1 | 2021-10-04 | 2021-11-10 | 29 | 4 | 25 | [20 empty] | 2021-11-16 |  | 2022-11-22 |  | EXP | [8 empty] | 2022-06-04 | Connected |  | No
National Grid | GREAT BARRINGTON | 377006 | 1230 | 51.9 | Solar | 09_1109W2 | 2021-10-01 15:22 | 2021-10-04 | 23 | 13 | 10 | 2021-11-05 | 2021-12-08 | 22 | 0 | 22 | [20 empty] | 2021-12-13 |  | 2022-12-15 |  | EXP | [8 empty] | 2022-06-13 | Connected |  | No
National Grid | NORTHAMPTON | 378526 | 1060 | 6 | Solar | 09_901W3 | 2021-10-01 15:37 | 2021-10-04 | 4 | 0 | 4 | 2021-10-08 | 2021-11-18 | 28 | 4 | 24 | [20 empty] | 2021-12-14 | 2021-10-01 15:47 | 2023-04-16 |  | EXP | [8 empty] | 2022-11-21 | Connected |  | No
National Grid | FLORENCE | 382307 | 1062 | 7.6 | Solar | 09_909W4 | 2021-10-01 15:47 | 2021-10-04 | 1 | 0 | 1 | 2021-10-05 | 2021-11-10 | 26 | 4 | 22 | [20 empty] | 2021-11-16 | 2021-10-04 11:17 | 2023-01-20 | Yes | EXP |  | 2022-01-05 | 2022-01-04 | 0 | 0 | 0 |  |  | 2022-01-27 | Connected |  | No
National Grid | BROCKTON | 381633 | 2302 | 5 | Solar | 07_91W43 | 2021-10-04 11:17 | 2021-10-05 | 26 | 16 | 10 | 2021-11-04 | 2021-12-06 | 21 | 0 | 21 | [20 empty] | 2021-12-15 |  | 2023-04-14 | Yes | EXP |  | 2022-02-22 | 2022-04-14 | 51 | 0 | 51 |  |  | 2022-05-13 | Connected |  | No
National Grid | SHUTESBURY | 382341 | 1072 | 10 | Solar | 09_704W1 | 2021-10-04 14:17 | 2021-10-05 | 5 | 3 | 2 | 2021-10-12 | 2021-11-18 | 27 | 4 | 23 | [20 empty] | 2021-12-01 |  | 2022-12-19 |  | EXP | [8 empty] | 2022-02-18 | Connected |  | Yes
National Grid | OXFORD | 386256 | 1540 | 7.6 | Solar | 01_406L4 | 2021-10-04 17:19 | 2021-10-05 | 31 | 26 | 5 | [26 empty] | 2021-10-04 17:52 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WILBRAHAM | 386258 | 1095 | 7.6 | Solar | 09_507L3 | 2021-10-04 17:52 | 2021-10-05 | 25 | 18 | 7 | 2021-11-10 | 2021-12-08 | 19 | 0 | 19 | [20 empty] | 2021-12-08 |  | 2023-06-05 | Yes | EXP |  | 2022-04-15 | 2022-04-19 | 5 | 0 | 5 |  |  | 2022-06-29 | Connected |  | No
National Grid | STOUGHTON | 386450 | 2072 | 15.2 | Solar | 07_94W43 | 2021-10-05 22:40 | 2021-10-06 | 63 | 56 | 7 | 2022-01-06 | 2022-01-28 | 16 | 0 | 16 | [20 empty] | 2022-02-08 | 2021-10-06 14:11 | 2023-02-09 |  | EXP | [8 empty] | 2022-03-02 | Connected |  | No
National Grid | ANDOVER | 384672 | 1810 | 144 | Solar | 14_71L1 | 2021-10-06 14:11 | 2021-10-07 | 38 | 29 | 9 | 2021-12-03 | 2022-02-10 | 48 | 24 | 24 | [20 empty] | 2022-02-18 |  | 2024-08-01 |  | EXP | [8 empty] | 2023-09-12 | Connected |  | No
National Grid | NORTH ANDOVER | 387061 | 1845 | 9.57 | Solar | 14_55L1 | 2021-10-07 13:22 | 2021-10-08 | 4 | 4 | 0 | 2021-10-15 | 2021-11-23 | 27 | 4 | 23 | [20 empty] | 2021-11-23 |  | 2022-11-23 |  | EXP | [8 empty] | 2022-03-22 | Connected |  | No
National Grid | BRIDGEWATER | 385119 | 2324 | 34.6 | Solar | 07_912W73 | 2021-10-07 17:16 | 2021-10-08 | 5 | 2 | 3 | 2021-10-18 | 2021-11-22 | 25 | 4 | 21 | [20 empty] | 2021-12-21 |  | 2023-01-06 |  | EXP | [8 empty] | 2022-05-03 | Connected |  | No
National Grid | LOWELL | 379349 | 1851 | 5 | Solar | 14_16L3 | 2021-10-08 08:55 | 2021-10-12 | 2 | 0 | 2 | 2021-10-14 | 2021-11-22 | 26 | 4 | 22 | [20 empty] | 2021-12-14 |  | 2023-02-19 |  | EXP | [8 empty] | 2022-02-25 | Connected |  | No
National Grid | DRACUT | 381009 | 1826 | 7.6 | Solar | 14_78L3 | 2021-10-08 09:11 | 2021-10-12 | 0 | 0 | 0 | 2021-10-12 | 2021-11-18 | 27 | 4 | 23 | [20 empty] | 2021-11-29 |  | 2023-05-02 |  | EXP | [8 empty] | 2022-05-06 | Connected |  | No
National Grid | MALDEN | 387541 | 2148 | 7.6 | Solar | 12_37W8 | 2021-10-10 17:07 | 2021-10-12 | 147 | 137 | 10 | [26 empty] | 2021-10-11 11:11 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RUTLAND | 378372 | 1543 | 5.52 | Solar | 01_55W1 | 2021-10-11 11:11 | 2021-10-12 | 6 | 6 | 0 | 2021-10-20 | 2021-11-26 | 27 | 4 | 23 | [20 empty] | 2021-12-07 |  | 2023-10-21 | Yes | EXP |  | 2022-02-01 | 2022-02-14 | 14 | 0 | 14 |  |  | 2023-08-23 | Connected |  | No
National Grid | NAHANT | 387711 | 1908 | 15.2 | Solar | 12_79J1 | 2021-10-11 13:36 | 2021-10-12 | 2 | 0 | 2 | 2021-10-14 | 2021-11-18 | 25 | 4 | 21 | [20 empty] | 2021-12-06 |  | 2023-02-11 |  | EXP | [8 empty] | 2022-07-08 | Connected |  | No
National Grid | LOWELL | 381753 | 1851 | 10 | Solar | 14_2L3 | 2021-10-11 20:29 | 2021-10-12 | 3 | 1 | 2 | 2021-10-18 | 2021-11-22 | 25 | 4 | 21 | [20 empty] | 2021-12-07 |  | 2023-08-03 |  | EXP | [8 empty] | 2022-09-19 | Connected |  | Yes
National Grid | LOWELL | 387537 | 1852 | 18.148 | Solar | 14_3L4 | 2021-10-12 18:51 | 2021-10-13 | 6 | 0 | 6 | 2021-10-21 | 2021-11-29 | 25 | 4 | 21 | [20 empty] | 2021-12-15 |  | 2023-01-12 |  | EXP | [8 empty] | 2022-04-11 | Connected |  | No
National Grid | OXFORD | 384307 | 1540 | 75 | Solar | 01_406L4 | 2021-10-13 07:26 | 2021-10-14 | 24 | 14 | 10 | [10 empty] | 2021-11-18 | 2021-12-28 | 28 | 0 | 28 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | LYNN | 383844 | 1901 | 75 | Solar | 12_21J22 | 2021-10-13 07:27 | 2021-10-14 | 24 | 14 | 10 | [10 empty] | 2021-11-18 | 2021-12-28 | 28 | 0 | 28 | [10 empty] | 2022-10-24 |  |  |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | LOWELL | 383082 | 1850 | 6 | Solar | 14_75L5 | 2021-10-13 12:44 | 2021-10-14 | 4 | 0 | 4 | 2021-10-20 | 2021-11-29 | 26 | 4 | 22 | [20 empty] | 2021-12-15 | 2021-10-13 13:26 | 2023-04-24 |  | EXP | [8 empty] | 2022-05-28 | Connected |  | No
National Grid | WORCESTER | 340607 | 1602 | 726.6 | Solar | 01_2J335 | 2021-10-13 13:26 | 2021-10-14 | 94 | 86 | 8 | [10 empty] | 2022-03-01 | 2022-03-01 | 1 | 0 | 1 | [10 empty] | 2023-05-30 |  | 2024-06-30 | Yes | STD | [9 empty] | Design |  | No
National Grid | FALL RIVER | 388401 | 2720 | 15.2 | Solar | 05_28W40 | 2021-10-13 16:37 | 2021-10-14 | 5 | 5 | 0 | 2021-10-21 | 2021-11-30 | 27 | 4 | 23 | [20 empty] | 2021-11-30 |  | 2023-03-17 |  | EXP | [8 empty] | 2022-09-01 | Connected |  | Yes
National Grid | DRACUT | 383819 | 1826 | 9.8 | Solar | 14_75L1 | 2021-10-14 12:45 | 2021-10-15 | 4 | 0 | 4 | 2021-10-21 | 2021-11-29 | 25 | 4 | 21 | [20 empty] | 2021-12-15 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BERLIN | 388680 | 1503 | 9.86 | Solar | 05_318W3 | 2021-10-14 15:24 | 2021-10-15 | 3 | 3 | 0 | 2021-10-20 | 2021-11-26 | 27 | 4 | 23 | [20 empty] | 2021-12-06 |  | 2023-01-08 |  | EXP | [8 empty] | 2022-06-17 | Connected |  | No
National Grid | ATTLEBORO | 384112 | 2703 | 10 | Solar | 05_9L4 | 2021-10-14 17:53 | 2021-10-15 | 4 | 2 | 2 | 2021-10-21 | 2021-11-29 | 26 | 4 | 22 | [20 empty] | 2021-12-06 | 2021-10-15 09:06 | 2023-01-30 |  | EXP | [8 empty] | 2022-03-24 | Connected |  | No
National Grid | SOMERSET | 387698 | 2726 | 10 | Solar | 05_19W72 | 2021-10-15 09:06 | 2021-10-18 | 3 | 0 | 3 | 2021-10-21 | 2021-11-29 | 25 | 4 | 21 | [20 empty] | 2021-12-15 |  | 2023-08-18 | Yes | EXP |  | 2022-05-14 | 2022-07-13 | 61 | 0 | 61 |  |  | 2022-09-23 | Connected |  | No
National Grid | SPENCER | 371682 | 1562 | 1000 | Solar | 01_21W1 | 2021-10-15 18:20 | 2021-10-18 | 53 | 44 | 9 | [10 empty] | 2022-01-04 | 2023-08-02 | 394 | 379 | 15 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | DOUGLAS | 371684 | 1516 | 1000 | Solar | 05_320W2 | 2021-10-15 18:22 | 2021-10-18 | 55 | 46 | 9 | [10 empty] | 2022-01-05 | 2022-11-22 | 220 | 211 | 9 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | GRAFTON | 388111 | 1519 | 15.2 | Solar | 01_304W1 | 2021-10-17 18:40 | 2021-10-18 | 42 | 40 | 2 | 2021-12-17 | 2022-01-10 | 16 | 0 | 16 | [20 empty] | 2022-01-10 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LYNN | 382866 | 1902 | 3.8 | Solar | 12_1J901 | 2021-10-19 10:25 | 2021-10-20 | 15 | 6 | 9 | 2021-11-10 | 2021-12-07 | 18 | 0 | 18 | [20 empty] | 2021-12-17 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WRENTHAM | 374918 | 2093 | 468 | Solar | 05_3422W4 | 2021-10-19 15:22 | 2021-10-20 | 25 | 15 | 10 | 2021-11-25 | 2022-02-15 | 57 | 0 | 57 | [20 empty] | 2022-03-17 | 2021-10-21 09:08 |  |  | EXP | [8 empty] | 2023-03-30 | Connected |  | No
National Grid | FALL RIVER | 387941 | 2724 | 3 | Solar | 05_115W42 | 2021-10-21 09:08 | 2021-10-22 | 9 | 4 | 5 | 2021-11-04 | 2021-12-06 | 21 | 0 | 21 | [20 empty] | 2021-12-15 | 2021-10-21 10:24 | 2024-05-25 | Yes | EXP |  | 2023-01-26 | 2023-05-15 | 110 | 0 | 110 |  |  | 2023-07-11 | Connected |  | No
National Grid | WILLIAMSTOWN | 378678 | 1267 | 3.8 | Solar | 09_1001W1 | 2021-10-21 10:24 | 2021-10-22 | 7 | 4 | 3 | 2021-11-02 | 2021-12-02 | 21 | 0 | 21 | [20 empty] | 2021-12-15 |  |  | Yes | EXP |  | 2022-03-01 | 2022-03-11 | 11 | 0 | 11 |  |  | 2022-04-07 | Connected |  | No
National Grid | QUINCY | 379796 | 2169 | 129.6 | Solar | 07_1W9 | 2021-10-21 15:47 | 2021-10-22 | 39 | 30 | 9 | 2021-12-20 | 2022-02-24 | 46 | 22 | 24 | [21 empty] | 2021-10-25 14:30 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SAUGUS | 389679 | 1906 | 8.027 | Solar | 12_16W1 | 2021-10-25 14:30 | 2021-10-26 | 3 | 3 | 0 | 2021-10-27 | 2021-12-01 | 24 | 3 | 21 | [20 empty] | 2021-12-07 |  | 2022-12-29 | Yes | EXP |  | 2022-01-13 | 2022-01-26 | 14 | 0 | 14 |  |  | 2022-08-23 | Connected |  | No
National Grid | FALL RIVER | 387395 | 2723 | 4999.2 | Other | 05_115W44 | 2021-10-25 17:25 | 2021-10-26 | 49 | 40 | 9 | [10 empty] | 2022-01-05 | 2022-01-26 | 15 | 0 | 15 | [11 empty] | 2021-10-26 10:26 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | GARDNER | 389904 | 1440 | 9.57 | Solar | 01_607W1 | 2021-10-26 10:26 | 2021-10-27 | 2 | 2 | 0 | 2021-10-29 | 2021-12-01 | 22 | 0 | 22 | [20 empty] | 2021-12-07 |  | 2023-05-26 | Yes | EXP |  | 2022-04-27 | 2022-05-04 | 8 | 0 | 8 |  |  | 2022-06-29 | Connected |  | No
National Grid | BARRE | 385046 | 1005 | 2660 | Solar | 09_604W3 | 2021-10-26 10:55 | 2021-10-27 | 53 | 44 | 9 | [10 empty] | 2022-01-12 | 2022-11-21 | 216 | 211 | 5 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | BRIDGEWATER | 390299 | 2324 | 43.2 | Solar | 07_797W1 | 2021-10-26 12:09 | 2021-10-27 | 18 | 13 | 5 | 2021-11-23 | 2021-12-21 | 20 | 0 | 20 | [20 empty] | 2021-12-20 | 2021-10-26 16:10 | 2023-06-28 |  | EXP | [8 empty] | 2023-06-27 | Connected |  | No
National Grid | METHUEN | 390053 | 1844 | 7.6 | Solar | 14_43L4 | 2021-10-26 16:10 | 2021-10-27 | 5 | 0 | 5 | 2021-11-03 | 2021-12-02 | 20 | 0 | 20 | [20 empty] | 2021-12-08 |  | 2023-02-07 | Yes | EXP |  | 2022-01-19 | 2022-02-07 | 20 | 0 | 20 |  |  | 2022-02-15 | Connected |  | No
National Grid | SAUGUS | 384858 | 1906 | 5 | Solar | 12_19W1 | 2021-10-26 16:37 | 2021-10-27 | 11 | 6 | 5 | 2021-11-10 | 2021-12-07 | 18 | 0 | 18 | [20 empty] | 2021-12-17 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 388182 | 2302 | 6 | Solar | 07_911W56 | 2021-10-26 20:29 | 2021-10-27 | 31 | 25 | 6 | 2021-12-10 | 2022-01-03 | 17 | 0 | 17 | [20 empty] | 2022-01-06 | 2021-10-27 02:19 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BELLINGHAM | 388023 | 2019 | 9.8 | Solar | 05_335W1 | 2021-10-27 02:19 | 2021-10-28 | 4 | 0 | 4 | 2021-11-03 | 2021-12-02 | 20 | 0 | 20 | [20 empty] | 2021-12-08 | 2021-10-27 02:26 | 2023-05-18 | Yes | EXP |  | 2022-02-16 | 2022-05-18 | 92 | 0 | 92 |  |  | 2022-06-07 | Connected |  | No
National Grid | SALEM | 387155 | 1970 | 7.6 | Solar | 12_2W1 | 2021-10-27 02:26 | 2021-10-28 | 9 | 5 | 4 | 2021-11-09 | 2021-12-07 | 19 | 0 | 19 | [20 empty] | 2021-12-14 |  | 2023-06-03 | Yes | EXP |  | 2022-04-22 | 2022-05-26 | 35 | 0 | 35 |  |  | 2022-06-29 | Connected |  | No
National Grid | WRENTHAM | 387717 | 2093 | 2000 | Solar | 05_3422W1 | 2021-10-27 11:00 | 2021-10-28 | 35 | 25 | 10 | [10 empty] | 2021-12-17 | 2022-01-16 | 20 | 0 | 20 | [11 empty] | 2021-10-29 10:47 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | DIGHTON | 390978 | 2715 | 150 | Solar | 05_19W74 | 2021-10-29 10:47 | 2021-11-01 | 8 | 0 | 8 | [10 empty] | 2021-11-12 | 2022-01-14 | 45 | 0 | 45 | [10 empty] | 2023-04-18 |  | 2024-04-20 | Yes | STD |  | 2023-11-30 | 2024-01-22 | 54 | 0 | 54 |  |  |  | Completion Documents |  | No
National Grid | FRANKLIN | 380647 | 2038 | 360 | Solar | 05_344W5 | 2021-10-29 11:39 | 2021-11-01 | 30 | 20 | 10 | [10 empty] | 2021-12-15 | 2022-01-16 | 23 | 0 | 23 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH BROOKFIELD | 385041 | 1535 | 2000 | Solar | 01_525L1 | 2021-10-29 12:46 | 2021-11-01 | 22 | 12 | 10 | [10 empty] | 2021-12-03 | 2022-01-05 | 23 | 0 | 23 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | FALL RIVER | 380699 | 2723 | 480 | Solar | 05_115W52 | 2021-10-29 12:57 | 2021-11-01 | 30 | 20 | 10 | [10 empty] | 2021-12-16 | 2022-01-16 | 22 | 0 | 22 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 392129 | 1844 | 7.6 | Solar | 14_74L2 | 2021-10-29 13:51 | 2021-11-03 | 5 | 5 | 0 | 2021-11-10 | 2021-12-07 | 18 | 0 | 18 | [20 empty] | 2021-12-14 |  | 2023-03-17 |  | EXP | [8 empty] | 2023-02-09 | Connected |  | No
National Grid | WESTMINSTER | 385049 | 1473 | 5000 | Solar | 01_609W1 | 2021-10-29 16:46 | 2021-11-01 | 44 | 34 | 10 | [10 empty] | 2021-12-03 | 2022-01-05 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | ROCKLAND | 386079 | 2370 | 100 | Solar | 07_99W63 | 2021-11-01 08:10 | 2021-11-02 | 26 | 17 | 9 | 2021-12-10 | 2022-06-10 | 127 | 105 | 22 | [21 empty] | 2021-11-01 09:04 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 387839 | 1844 | 57.6 | Solar | 14_75L3 | 2021-11-01 09:04 | 2021-11-02 | 31 | 23 | 8 | 2021-12-17 | 2022-03-29 | 65 | 50 | 15 | [20 empty] | 2022-04-19 |  | 2025-02-17 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | MEDFORD | 387786 | 2155 | 9.28 | Solar | 12_17J3 | 2021-11-01 11:28 | 2021-11-02 | 7 | 4 | 3 | 2021-11-12 | 2022-01-17 | 42 | 24 | 18 | [20 empty] | 2022-01-21 |  | 2023-08-01 |  | EXP | [8 empty] | 2022-08-16 | Connected |  | Yes
National Grid | NORTON | 391863 | 2766 | 15.2 | Solar | 05_8L4 | 2021-11-01 11:42 | 2021-11-02 | 6 | 5 | 1 | 2021-11-10 | 2021-12-07 | 18 | 0 | 18 | [20 empty] | 2021-12-14 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 379113 | 1844 | 7.6 | Solar | 14_75L4 | 2021-11-01 12:14 | 2021-11-02 | 52 | 50 | 2 | 2022-01-18 | 2022-02-08 | 16 | 0 | 16 | [20 empty] | 2022-02-08 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | PALMER | 390310 | 1069 | 15.2 | Solar | 09_503L1 | 2021-11-01 12:21 | 2021-11-02 | 2 | 0 | 2 | 2021-11-04 | 2021-12-06 | 21 | 0 | 21 | [20 empty] | 2021-12-14 | 2021-11-02 13:44 | 2022-11-02 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | PEMBROKE | 391653 | 2359 | 7.6 | Solar | 07_910W25 | 2021-11-02 13:44 | 2021-11-03 | 6 | 0 | 6 | 2021-11-09 | 2021-12-07 | 19 | 0 | 19 | [20 empty] | 2021-12-17 |  | 2023-04-07 | Yes | EXP |  | 2022-03-16 | 2022-04-04 | 20 | 0 | 20 |  |  | 2022-04-29 | Connected |  | No
National Grid | AYER | 392812 | 1432 | 15.2 | Solar | 01_201W4 | 2021-11-02 14:27 | 2021-11-03 | 34 | 25 | 9 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ATTLEBORO | 385414 | 2703 | 9.8 | Solar | 05_8L4 | 2021-11-02 17:01 | 2021-11-03 | 1 | 0 | 1 | 2021-11-04 | 2021-12-06 | 21 | 0 | 21 | [20 empty] | 2021-12-08 | 2021-11-02 17:10 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | TYNGSBOROUGH | 392140 | 1879 | 240 | Solar | 01_210L1 | 2021-11-02 17:10 | 2021-11-03 | 10 | 0 | 10 | [10 empty] | 2021-11-18 | 2021-12-22 | 24 | 0 | 24 | [10 empty] | 2022-06-10 | 2021-11-03 13:32 | 2023-05-15 | Yes | STD | [8 empty] | 2023-06-02 | Connected |  | No
National Grid | BELLINGHAM | 379282 | 2019 | 9.6 | Solar | 05_108W60 | 2021-11-03 13:32 | 2021-11-04 | 5 | 0 | 5 | 2021-11-09 | 2021-12-07 | 19 | 0 | 19 | [20 empty] | 2021-12-13 | 2021-11-03 16:05 | 2023-07-28 | Yes | EXP | [8 empty] | 2022-08-15 | Connected |  | Yes
National Grid | FALL RIVER | 391147 | 2721 | 10 | Solar | 05_115W53 | 2021-11-03 16:05 | 2021-11-04 | 5 | 0 | 5 | 2021-11-09 | 2021-12-07 | 19 | 0 | 19 | [20 empty] | 2021-12-17 |  | 2023-05-03 | Yes | EXP |  | 2022-03-11 | 2022-04-29 | 50 | 0 | 50 |  |  | 2022-07-09 | Connected |  | No
National Grid | TOPSFIELD | 393102 | 1983 | 11.4 | Solar | 12_26L1 | 2021-11-03 16:30 | 2021-11-04 | 1 | 0 | 1 | 2021-11-05 | 2021-12-06 | 20 | 0 | 20 | [20 empty] | 2021-12-14 |  | 2023-03-05 |  | EXP | [8 empty] | 2022-09-02 | Connected |  | No
National Grid | WEST BROOKFIELD | 389963 | 1585 | 6 | Solar | 01_525L2 | 2021-11-03 18:05 | 2021-11-04 | 5 | 1 | 4 | 2021-11-10 | 2021-12-07 | 18 | 0 | 18 | [20 empty] | 2022-01-06 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BOLTON | 376566 | 1740 | 7.6 | Solar | 01_216W6 | 2021-11-04 10:04 | 2021-11-05 | 21 | 18 | 3 | 2021-12-07 | 2021-12-28 | 16 | 0 | 16 | [20 empty] | 2022-01-03 |  | 2023-01-10 |  | EXP | [8 empty] | 2022-06-07 | Connected |  | No
National Grid | CHELMSFORD | 393377 | 1824 | 9.772 | Solar | 14_16L1 | 2021-11-04 14:27 | 2021-11-05 | 8 | 5 | 3 | 2021-11-17 | 2021-12-09 | 16 | 0 | 16 | [20 empty] | 2021-12-14 |  | 2022-12-16 |  | EXP | [8 empty] | 2022-01-28 | Connected |  | Yes
National Grid | PEMBROKE | 393258 | 2359 | 15.2 | Solar | 07_910W25 | 2021-11-05 07:00 | 2021-11-08 | 32 | 26 | 6 | 2022-01-06 | 2022-01-28 | 16 | 0 | 16 | [20 empty] | 2022-02-11 | 2021-11-05 12:48 | 2023-03-05 |  | EXP | [8 empty] | 2022-10-27 | Connected |  | No
National Grid | METHUEN | 393677 | 1844 | 7.25 | Solar | 14_63L1 | 2021-11-05 12:48 | 2021-12-08 | 4 | 2 | 2 | 2021-12-14 | 2022-01-04 | 15 | 0 | 15 | [20 empty] | 2022-01-05 |  | 2023-07-28 | Yes | EXP |  | 2022-05-13 | 2022-06-07 | 26 | 0 | 26 |  |  |  | Withdrawn |  | Yes
National Grid | FRANKLIN | 393614 | 2038 | 15.2 | Solar | 05_341W2 | 2021-11-05 13:03 | 2021-11-08 | 2 | 0 | 2 | 2021-11-10 | 2021-12-08 | 19 | 0 | 19 | [20 empty] | 2021-12-08 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ROCKLAND | 392758 | 2370 | 100 | Solar | 07_99W61 | 2021-11-05 14:13 | 2021-11-08 | 17 | 9 | 8 | 2021-12-03 | 2022-01-06 | 25 | 2 | 23 | [20 empty] | 2022-01-24 |  | 2024-06-27 |  | EXP | [8 empty] | 2024-04-09 | Connected |  | Yes
National Grid | SAUGUS | 374165 | 1906 | 9.98 | Solar | 12_25W1 | 2021-11-05 14:50 | 2021-11-08 | 57 | 26 | 31 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SEEKONK | 393693 | 2771 | 18 | Solar | 05_7L1 | 2021-11-05 15:57 | 2021-11-08 | 4 | 2 | 2 | 2021-11-12 | 2021-12-13 | 21 | 0 | 21 | [20 empty] | 2021-12-14 |  | 2023-01-18 |  | EXP | [8 empty] | 2023-01-03 | Connected |  | No
National Grid | WESTBOROUGH | 393761 | 1581 | 15.2 | Solar | 05_312W4 | 2021-11-05 16:13 | 2021-11-08 | 2 | 0 | 2 | 2021-11-10 | 2022-02-04 | 60 | 26 | 34 | [21 empty] | 2021-11-05 18:49 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTFORD | 388451 | 1886 | 9.8 | Solar | 14_57L3 | 2021-11-05 18:49 | 2021-11-08 | 4 | 2 | 2 | 2021-11-12 | 2021-12-08 | 18 | 0 | 18 | [20 empty] | 2021-12-13 |  | 2023-07-07 | Yes | EXP |  | 2022-06-14 | 2022-07-06 | 22 | 0 | 22 |  |  | 2022-09-09 | Connected |  | No
National Grid | CLINTON | 393819 | 1510 | 8.7 | Solar | 01_216W1 | 2021-11-06 16:16 | 2021-11-08 | 4 | 2 | 2 | 2021-11-12 | 2021-12-08 | 18 | 0 | 18 | [20 empty] | 2021-12-17 | 2021-11-08 11:30 | 2023-02-18 |  | EXP | [8 empty] | 2023-01-05 | Connected |  | No
National Grid | RUTLAND | 390938 | 1543 | 10 | Solar | 01_55W1 | 2021-11-08 11:30 | 2021-11-09 | 3 | 1 | 2 | 2021-11-12 | 2022-01-17 | 42 | 27 | 15 | [20 empty] | 2022-01-21 | 2021-11-09 09:50 |  | Yes | EXP |  | 2022-03-08 | 2022-04-11 | 35 | 0 | 35 |  |  | 2022-04-19 | Connected |  | No
National Grid | BROCKTON | 386414 | 2302 | 10 | Solar | 07_911W56 | 2021-11-09 09:50 | 2021-11-10 | 1 | 1 | 0 | 2021-11-12 | 2021-12-10 | 20 | 0 | 20 | [20 empty] | 2021-12-13 | 2021-11-09 13:29 | 2023-04-14 | Yes | EXP |  | 2022-03-19 | 2022-04-11 | 24 | 0 | 24 |  |  | 2022-04-22 | Connected |  | No
National Grid | WORCESTER | 385653 | 1609 | 3.8 | Solar | 01_23W1 | 2021-11-09 13:29 | 2021-11-10 | 1 | 0 | 1 | 2021-11-12 | 2021-12-09 | 19 | 0 | 19 | [20 empty] | 2021-12-13 | 2021-11-09 13:36 | 2023-05-07 | Yes | EXP |  | 2022-04-13 | 2022-04-12 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Yes
National Grid | LEOMINSTER | 390483 | 1453 | 4.8 | Solar | 01_207W2 | 2021-11-09 13:36 | 2021-11-10 | 4 | 2 | 2 | 2021-11-17 | 2022-01-19 | 41 | 26 | 15 | [20 empty] | 2022-01-21 |  | 2023-09-21 | Yes | EXP | [8 empty] | 2023-01-18 | Connected |  | No
National Grid | WINTHROP | 383495 | 2152 | 9.8 | Solar | 12_96W1 | 2021-11-09 13:57 | 2021-11-10 | 1 | 0 | 1 | 2021-11-12 | 2021-12-08 | 18 | 0 | 18 | [20 empty] | 2021-12-13 |  | 2022-12-20 |  | EXP | [8 empty] | 2022-03-14 | Connected |  | Yes
National Grid | UPTON | 391814 | 1568 | 1.74 | Solar | 05_335W3 | 2021-11-09 15:16 | 2021-11-10 | 5 | 4 | 1 | 2021-11-18 | 2021-12-21 | 23 | 0 | 23 | [20 empty] | 2021-12-14 |  | 2023-05-13 |  | EXP | [8 empty] | 2022-06-14 | Connected |  | No
National Grid | SEEKONK | 389716 | 2771 | 4999 | Other | 05_7L2 | 2021-11-09 17:00 | 2021-11-10 | 52 | 43 | 9 | [10 empty] | 2022-01-27 | 2022-02-25 | 20 | 0 | 20 | [11 empty] | 2021-11-09 20:04 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | MILFORD | 389597 | 1757 | 9.8 | Solar | 05_335W5 | 2021-11-09 20:04 | 2021-11-10 | 1 | 0 | 1 | 2021-11-12 | 2022-01-14 | 41 | 25 | 16 | [20 empty] | 2022-01-21 |  | 2023-12-22 | Yes | EXP |  | 2022-04-09 | 2022-12-21 | 257 | 0 | 257 |  |  | 2023-02-24 | Connected |  | No
National Grid | BROCKTON | 389731 | 2301 | 4800 | Other | 07_98W10 | 2021-11-10 09:46 | 2021-11-12 | 36 | 26 | 10 | [10 empty] | 2022-01-05 | 2022-01-26 | 15 | 0 | 15 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 389732 | 2301 | 4999 | Other | 07_797W19 | 2021-11-10 09:50 | 2021-11-12 | 51 | 42 | 9 | [10 empty] | 2022-01-27 | 2022-02-02 | 5 | 0 | 5 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | EASTON | 389734 | 2375 | 4999.2 | Other | 07_92W44 | 2021-11-10 09:52 | 2021-11-12 | 36 | 27 | 9 | [10 empty] | 2022-01-05 | 2022-01-26 | 15 | 0 | 15 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WEST BRIDGEWATER | 389735 | 2379 | 3000 | Other | 07_98W44 | 2021-11-10 09:54 | 2021-11-12 | 36 | 27 | 9 | [10 empty] | 2022-01-05 | 2022-01-26 | 15 | 0 | 15 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | WEST BRIDGEWATER | 389737 | 2379 | 4999.2 | Other | 07_797W20 | 2021-11-10 09:56 | 2021-11-12 | 36 | 27 | 9 | [10 empty] | 2022-01-05 | 2022-01-26 | 15 | 0 | 15 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | MARLBOROUGH | 389739 | 1752 | 4999.2 | Other | 05_311W1 | 2021-11-10 09:57 | 2021-11-12 | 37 | 28 | 9 | [10 empty] | 2022-01-06 | 2022-01-26 | 14 | 0 | 14 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | EASTON | 389740 | 2375 | 4200 | Other | 07_92W44 | 2021-11-10 09:59 | 2021-11-12 | 36 | 28 | 8 | [10 empty] | 2022-01-05 | 2022-01-27 | 16 | 0 | 16 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | EASTON | 389742 | 2375 | 4999 | Other | 07_98W48 | 2021-11-10 10:01 | 2021-11-12 | 36 | 26 | 10 | [10 empty] | 2022-01-05 | 2022-01-26 | 15 | 0 | 15 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | MENDON | 386848 | 1756 | 4990 | Solar | 05_332W1 | 2021-11-10 17:45 | 2021-11-12 | 32 | 24 | 8 | [10 empty] | 2021-12-28 | 2023-02-23 | 288 | 274 | 14 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | MILFORD | 387138 | 1757 | 11980 | Other | 05_335W3 | 2021-11-10 17:46 | 2021-11-12 | 32 | 24 | 8 | [10 empty] | 2022-01-06 | 2022-11-21 | 219 | 211 | 8 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | RANDOLPH | 388130 | 2368 | 3.84 | Solar | 07_5W2 | 2021-11-10 18:37 | 2021-11-12 | 3 | 0 | 3 | 2021-11-17 | 2022-01-20 | 42 | 22 | 20 | [20 empty] | 2022-02-03 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 382577 | 2302 | 240 | Solar | 07_712J1 | 2021-11-11 10:46 | 2021-11-12 | 21 | 15 | 6 | [10 empty] | 2021-12-14 | 2022-02-08 | 40 | 2 | 38 | [10 empty] | 2023-03-22 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WRENTHAM | 383113 | 2093 | 13800 | Other | 05_3422W2 | 2021-11-11 11:39 | 2021-11-12 | 34 | 25 | 9 | [10 empty] | 2021-12-31 | 2022-01-19 | 12 | 0 | 12 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | ANDOVER | 394876 | 1810 | 7.6 | Solar | 14_62L2 | 2021-11-11 13:26 | 2021-11-12 | 27 | 24 | 3 | 2021-12-21 | 2022-01-14 | 18 | 0 | 18 | [20 empty] | 2022-01-14 | 2021-11-11 14:50 | 2023-08-02 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 390140 | 1603 | 9.8 | Solar | 01_6W2 | 2021-11-11 14:50 | 2021-11-12 | 3 | 0 | 3 | 2021-11-17 | 2021-12-10 | 17 | 0 | 17 | [20 empty] | 2021-12-15 |  | 2023-06-08 | Yes | EXP |  | 2022-03-31 | 2022-06-03 | 65 | 0 | 65 |  |  | 2022-07-08 | Connected |  | Yes
National Grid | HANOVER | 391839 | 2339 | 4999.2 | Other | 07_910W26 | 2021-11-11 14:59 | 2021-11-12 | 37 | 28 | 9 | [10 empty] | 2022-01-06 | 2022-03-02 | 38 | 4 | 34 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 391841 | 2301 | 2000 | Other | 07_911W13 | 2021-11-11 15:02 | 2021-11-12 | 37 | 24 | 13 | [10 empty] | 2022-01-06 | 2022-01-26 | 14 | 0 | 14 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | EASTON | 391844 | 2375 | 4200 | Other | 07_98W48 | 2021-11-11 15:04 | 2021-11-12 | 36 | 26 | 10 | [10 empty] | 2022-01-05 | 2022-01-26 | 15 | 0 | 15 | [11 empty] | 2021-11-11 15:55 |  |  | STD | [9 empty] | Group Study |  | No
National Grid | DUDLEY | 391345 | 1571 | 7.6 | Solar | 01_412L4 | 2021-11-11 15:55 | 2021-11-12 | 3 | 0 | 3 | 2021-11-17 | 2022-01-20 | 42 | 22 | 20 | [20 empty] | 2022-02-03 | 2021-11-11 16:00 | 2023-08-26 | Yes | EXP | [8 empty] | 2022-11-04 | Connected |  | Yes
National Grid | STOUGHTON | 382329 | 2072 | 240 | Solar | 07_94W43 | 2021-11-11 16:00 | 2021-11-12 | 22 | 15 | 7 | 2021-12-14 | 2022-01-18 | 25 | 2 | 23 | 2022-03-01 | 2022-10-11 | 131 | 0 | 131 | [5 empty] | 2022-03-01 | 2022-10-11 | 131 | 0 | 131 | [5 empty] | 2022-09-20 |  |  | Yes | EXP | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 382570 | 1607 | 350 | Solar | 01_8W2 | 2021-11-11 16:08 | 2021-11-12 | 24 | 15 | 9 | [10 empty] | 2021-12-17 | 2022-01-16 | 21 | 0 | 21 | [11 empty] | 2021-11-11 16:12 |  |  | STD | [9 empty] | Group Study |  | Yes
National Grid | MILFORD | 390062 | 1757 | 9.8 | Solar | 05_336W1 | 2021-11-11 16:12 | 2021-11-12 | 56 | 53 | 3 | 2022-02-03 | 2022-02-22 | 13 | 0 | 13 | [20 empty] | 2022-02-28 | 2021-11-12 09:03 | 2024-01-02 | Yes | EXP |  | 2022-05-25 | 2022-12-21 | 211 | 0 | 211 |  |  | 2023-01-13 | Connected |  | No
National Grid | UPTON | 390487 | 1568 | 9.765 | Solar | 05_320W1 | 2021-11-12 09:03 | 2021-11-15 | 2 | 0 | 2 | 2021-11-16 | 2021-12-08 | 16 | 0 | 16 | [20 empty] | 2021-12-13 |  | 2023-04-03 | Yes | EXP |  | 2022-02-08 | 2022-03-31 | 52 | 0 | 52 |  |  | 2022-05-11 | Connected |  | No
National Grid | GARDNER | 370269 | 1440 | 2000 | Solar | 01_602W2 | 2021-11-12 12:01 | 2021-11-15 | 47 | 37 | 10 | [10 empty] | 2022-01-24 | 2022-11-21 | 209 | 201 | 8 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | BROCKTON | 391846 | 2302 | 2000 | Other | 07_911W57 | 2021-11-13 06:26 | 2021-11-15 | 36 | 27 | 9 | [10 empty] | 2022-01-06 | 2022-01-26 | 14 | 0 | 14 | [11 empty] | 2021-11-15 12:40 |  |  | STD | [9 empty] | Group Study |  | No
National Grid | SCITUATE | 392732 | 2066 | 5.76 | Solar | 07_915W82 | 2021-11-15 12:40 | 2021-11-16 | 25 | 20 | 5 | 2021-11-19 | 2021-12-21 | 22 | 0 | 22 | [20 empty] | 2021-12-21 | 2021-11-15 12:45 | 2023-05-24 | Yes | EXP |  | 2022-04-01 | 2022-05-20 | 50 | 0 | 50 |  |  | 2022-06-30 | Connected |  | Yes
National Grid | SOMERSET | 394593 | 2726 | 78.8 | Solar | 05_11W84 | 2021-11-15 12:45 | 2021-11-16 | 10 | 2 | 8 | 2021-12-01 | 2022-01-04 | 24 | 0 | 24 | [20 empty] | 2022-01-19 |  | 2023-04-10 | Yes | EXP | [8 empty] | 2023-02-16 | Connected |  | No
National Grid | NORWELL | 391836 | 2061 | 4999.2 | Other | 07_96W44 | 2021-11-15 15:17 | 2021-11-16 | 34 | 25 | 9 | [10 empty] | 2022-01-05 | 2022-01-26 | 11 | 0 | 11 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | NORWELL | 391838 | 2061 | 4999.2 | Other | 07_96W40 | 2021-11-15 15:21 | 2021-11-16 | 34 | 25 | 9 | [10 empty] | 2022-01-05 | 2022-01-26 | 11 | 0 | 11 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | NORTH EASTON | 394644 | 2356 | 9.86 | Solar | 07_92W43 | 2021-11-15 17:30 | 2021-11-16 | 1 | 0 | 1 | 2021-11-17 | 2021-12-09 | 16 | 0 | 16 | [20 empty] | 2021-12-14 | 2021-11-16 15:57 | 2022-12-20 |  | EXP | [8 empty] | 2022-03-08 | Connected |  | No
National Grid | ATTLEBORO | 370328 | 2703 | 499 | Solar | 05_9L4 | 2021-11-16 15:57 | 2021-11-17 | 19 | 11 | 8 | [10 empty] | 2021-12-15 | 2022-01-19 | 25 | 0 | 25 | [10 empty] | 2022-09-09 |  | 2024-04-19 | Yes | STD |  | 2023-09-08 |  | 221 | 125 | 96 |  |  |  | Construction |  | No
National Grid | GLOUCESTER | 380590 | 1930 | 7.6 | Solar | 12_52L1 | 2021-11-16 17:07 | 2021-11-17 | 23 | 22 | 1 | 2021-12-21 | 2022-01-14 | 18 | 0 | 18 | [20 empty] | 2022-01-14 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HOLBROOK | 389949 | 2343 | 6 | Solar | 07_10W1 | 2021-11-16 19:07 | 2021-11-17 | 20 | 15 | 5 | 2021-11-19 | 2021-12-21 | 22 | 0 | 22 | [20 empty] | 2021-12-21 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GARDNER | 395576 | 1440 | 20.355 | Solar | 01_607W1 | 2021-11-17 12:33 | 2021-11-18 | 2 | 0 | 2 | 2021-11-19 | 2021-12-21 | 22 | 0 | 22 | [20 empty] | 2021-12-21 |  | 2023-02-07 |  | EXP | [8 empty] | 2022-07-14 | Connected |  | No
National Grid | BOLTON | 396398 | 1740 | 25 | Solar | 01_225W1 | 2021-11-18 14:23 | 2021-11-19 | 4 | 2 | 2 | 2021-11-24 | 2021-12-21 | 19 | 0 | 19 | [20 empty] | 2021-12-21 |  | 2022-12-30 |  | EXP | [8 empty] | 2022-09-14 | Connected |  | No
National Grid | WESTFORD | 396438 | 1886 | 7.6 | Solar | 14_57L3 | 2021-11-18 18:04 | 2021-11-19 | 22 | 19 | 3 | 2021-12-21 | 2022-01-14 | 18 | 0 | 18 | [20 empty] | 2022-01-18 | 2021-11-18 19:01 | 2023-03-06 |  | EXP | [8 empty] | 2022-06-03 | Connected |  | No
National Grid | METHUEN | 395186 | 1844 | 6 | Solar | 14_43L4 | 2021-11-18 19:01 | 2021-11-19 | 2 | 0 | 2 | 2021-11-23 | 2021-12-21 | 20 | 0 | 20 | [20 empty] | 2021-12-21 | 2021-11-18 19:04 | 2023-06-16 | Yes | EXP | [8 empty] | 2022-07-13 | Connected |  | Yes
National Grid | RANDOLPH | 392185 | 2368 | 6 | Solar | 07_97W1 | 2021-11-18 19:04 | 2021-11-19 | 3 | 0 | 3 | 2021-11-23 | 2021-12-21 | 20 | 0 | 20 | [20 empty] | 2021-12-21 |  | 2023-02-09 | Yes | EXP |  | 2022-01-19 | 2022-02-08 | 21 | 0 | 21 |  |  | 2022-02-12 | Connected |  | No
National Grid | NORTH EASTON | 394878 | 2356 | 9.28 | Solar | 07_92W54 | 2021-11-19 10:43 | 2021-11-22 | 22 | 19 | 3 | 2021-12-22 | 2022-01-17 | 18 | 0 | 18 | [20 empty] | 2022-01-21 |  | 2023-02-01 |  | EXP | [8 empty] | 2022-04-07 | Connected |  | Yes
National Grid | FOXBOROUGH | 396690 | 2035 | 15.2 | Solar | 05_3422W3 | 2021-11-19 16:15 | 2021-11-22 | 1 | 0 | 1 | 2021-11-24 | 2021-12-17 | 17 | 0 | 17 | [20 empty] | 2021-12-20 |  | 2023-01-13 |  | EXP | [8 empty] | 2022-04-07 | Connected |  | No
National Grid | BEVERLY | 393606 | 1915 | 10 | Solar | 12_51T1 | 2021-11-19 16:35 | 2021-11-22 | 3 | 1 | 2 | 2021-11-24 | 2021-12-21 | 19 | 0 | 19 | [20 empty] | 2021-12-21 |  | 2022-12-23 |  | EXP | [8 empty] | 2022-03-24 | Connected |  | No
National Grid | WORCESTER | 396408 | 1604 | 9.772 | Solar | 01_27W1 | 2021-11-22 10:11 | 2021-11-23 | 6 | 3 | 3 | 2021-12-02 | 2021-12-21 | 14 | 0 | 14 | [20 empty] | 2021-12-22 | 2021-11-22 11:57 | 2023-05-31 |  | EXP | [8 empty] | 2023-06-06 | Connected |  | No
National Grid | LEOMINSTER | 388913 | 1453 | 10 | Solar | 01_225W4 | 2021-11-22 11:57 | 2021-11-23 | 5 | 0 | 5 | 2021-12-01 | 2021-12-21 | 15 | 0 | 15 | [20 empty] | 2021-12-29 |  | 2023-10-26 | Yes | EXP |  | 2022-04-13 | 2022-10-26 | 197 | 0 | 197 |  |  | 2022-11-14 | Connected |  | No
National Grid | AYER | 396935 | 1432 | 7.6 | Solar | 01_201W3 | 2021-11-22 12:23 | 2021-11-23 | 31 | 23 | 8 | 2022-01-07 | 2022-01-28 | 15 | 0 | 15 | [20 empty] | 2022-02-01 | 2021-11-22 14:38 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NAHANT | 392553 | 1908 | 13.96 | Solar | 12_79J2 | 2021-11-22 14:38 | 2021-11-23 | 10 | 6 | 4 | 2021-12-08 | 2021-12-28 | 15 | 0 | 15 | [20 empty] | 2022-01-04 | 2021-11-22 19:35 | 2023-07-27 | Yes | EXP |  | 2022-04-28 | 2022-06-02 | 36 | 0 | 36 |  |  | 2022-08-09 | Connected |  | No
National Grid | AUBURN | 395838 | 1501 | 9.8 | Solar | 01_406L2 | 2021-11-22 19:35 | 2021-11-23 | 1 | 0 | 1 | 2021-11-24 | 2021-12-21 | 19 | 0 | 19 | [20 empty] | 2021-12-21 | 2021-11-22 20:30 | 2023-06-07 | Yes | EXP |  | 2022-04-23 | 2022-06-07 | 46 | 0 | 46 |  |  | 2022-06-09 | Connected |  | No
National Grid | WILBRAHAM | 386581 | 1095 | 10 | Solar | 09_507L3 | 2021-11-22 20:30 | 2021-11-23 | 1 | 0 | 1 | 2021-11-24 | 2021-12-21 | 19 | 0 | 19 | [20 empty] | 2021-12-21 |  | 2023-10-03 | Yes | EXP |  | 2022-07-01 | 2022-09-15 | 77 | 0 | 77 |  |  | 2022-12-22 | Connected |  | No
National Grid | BELLINGHAM | 392259 | 2019 | 6 | Solar | 05_335W1 | 2021-11-23 14:32 | 2021-11-24 | 4 | 0 | 4 | 2021-12-01 | 2021-12-22 | 16 | 0 | 16 | [20 empty] | 2021-12-29 |  | 2023-04-09 |  | EXP | [8 empty] | 2022-06-30 | Connected |  | Yes
National Grid | BROCKTON | 392439 | 2302 | 7.6 | Solar | 07_91W40 | 2021-11-23 14:41 | 2021-11-24 | 9 | 3 | 6 | 2021-12-08 | 2021-12-28 | 15 | 0 | 15 | [20 empty] | 2022-01-03 |  | 2023-06-15 |  | EXP | [8 empty] | 2022-07-11 | Connected |  | No
National Grid | WRENTHAM | 397405 | 2093 | 5.76 | Solar | 05_3422W4 | 2021-11-23 14:51 | 2021-12-09 | 5 | 4 | 1 | 2021-12-16 | 2022-01-06 | 15 | 0 | 15 | [20 empty] | 2022-01-06 |  | 2023-07-23 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | DRACUT | 396830 | 1826 | 16 | Solar | 14_75L3 | 2021-11-24 11:43 | 2021-11-26 | 36 | 28 | 8 | 2021-11-30 | 2022-01-19 | 36 | 18 | 18 | [20 empty] | 2022-01-20 |  | 2023-01-21 |  | EXP | [8 empty] | 2022-06-14 | Connected |  | No
National Grid | DIGHTON | 392747 | 2715 | 9.8 | Solar | 05_19W73 | 2021-11-24 13:27 | 2021-11-26 | 3 | 0 | 3 | 2021-12-01 | 2021-12-21 | 15 | 0 | 15 | [20 empty] | 2021-12-27 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LOWELL | 397015 | 1852 | 200 | Solar | 14_13J6 | 2021-11-24 13:34 | 2021-11-26 | 7 | 0 | 7 | [10 empty] | 2021-12-07 | 2022-01-06 | 23 | 0 | 23 | [10 empty] | 2022-07-28 | 2021-11-24 15:12 | 2023-06-02 |  | STD | [8 empty] | 2023-05-24 | Connected |  | No
National Grid | SALEM | 391442 | 1970 | 3.8 | Solar | 12_29W4 | 2021-11-24 15:12 | 2021-11-26 | 13 | 9 | 4 | 2021-12-01 | 2021-12-21 | 15 | 0 | 15 | [20 empty] | 2021-12-17 |  | 2023-08-02 | Yes | EXP | [8 empty] | 2022-08-22 | Connected |  | Yes
National Grid | LOWELL | 394090 | 1851 | 6 | Solar | 14_2L2 | 2021-11-29 10:21 | 2021-11-30 | 11 | 10 | 1 | 2021-12-15 | 2022-01-07 | 17 | 0 | 17 | [20 empty] | 2022-01-07 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SWANSEA | 383131 | 2777 | 7000 | Other | 05_11W84 | 2021-11-29 10:26 | 2021-11-30 | 80 | 70 | 10 | [10 empty] | 2022-03-25 | 2022-03-27 | 2 | 0 | 2 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | ROCKPORT | 398018 | 1966 | 5.52 | Solar | 12_40J2 | 2021-11-29 11:56 | 2021-11-30 | 1 | 1 | 0 | 2021-12-01 | 2021-12-21 | 15 | 0 | 15 | [20 empty] | 2021-12-22 |  | 2022-12-22 |  | EXP | [8 empty] | 2022-02-24 | Connected |  | No
National Grid | NORTHBOROUGH | 387185 | 1532 | 8.12 | Solar | 05_313W3 | 2021-11-29 13:20 | 2021-11-30 | 11 | 4 | 7 | 2021-12-15 | 2022-01-07 | 17 | 0 | 17 | [20 empty] | 2022-01-12 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 392062 | 1844 | 8.7 | Solar | 14_63L2 | 2021-11-29 14:53 | 2021-11-30 | 48 | 44 | 4 | 2022-02-08 | 2022-02-24 | 12 | 0 | 12 | [20 empty] | 2022-03-01 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NAHANT | 398056 | 1908 | 15.2 | Solar | 12_79J2 | 2021-11-29 15:44 | 2021-11-30 | 7 | 6 | 1 | 2021-12-09 | 2022-01-04 | 18 | 0 | 18 | [20 empty] | 2022-01-05 |  | 2023-05-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WALES | 397572 | 1081 | 9.45 | Solar | 09_503L2 | 2021-11-30 14:00 | 2021-12-01 | 10 | 9 | 1 | 2021-12-15 | 2022-01-03 | 14 | 0 | 14 | [20 empty] | 2022-01-05 |  | 2023-02-06 |  | EXP | [8 empty] | 2022-05-19 | Connected |  | Yes
National Grid | NANTUCKET | 398235 | 2554 | 20 | Solar | 04_101L6 | 2021-11-30 15:05 | 2021-12-01 | 7 | 6 | 1 | 2021-12-10 | 2022-01-04 | 17 | 0 | 17 | [20 empty] | 2022-01-04 | 2021-11-30 15:55 | 2024-03-10 |  | EXP | [8 empty] | 2024-04-12 | Connected |  | No
National Grid | CHELMSFORD | 398325 | 1824 | 9.772 | Solar | 14_16L4 | 2021-11-30 15:55 | 2021-12-01 | 14 | 13 | 1 | 2021-12-21 | 2022-01-14 | 18 | 0 | 18 | [20 empty] | 2022-01-14 | 2021-11-30 17:05 | 2023-04-15 | Yes | EXP |  | 2022-04-12 | 2022-04-13 | 2 | 0 | 2 |  |  | 2022-05-20 | Connected |  | No
National Grid | BROCKTON | 397489 | 2302 | 6 | Solar | 07_911W77 | 2021-11-30 17:05 | 2021-12-01 | 5 | 0 | 5 | 2021-12-08 | 2022-01-26 | 35 | 15 | 20 | [20 empty] | 2022-01-27 |  |  | Yes | EXP |  | 2022-03-09 | 2022-03-31 | 23 | 0 | 23 |  |  | 2022-04-12 | Connected |  | No
National Grid | HANSON | 396601 | 2341 | 17.76 | Solar | 07_95W2 | 2021-12-01 11:28 | 2021-12-02 | 7 | 3 | 4 | 2021-12-10 | 2022-01-04 | 17 | 0 | 17 | [20 empty] | 2022-01-07 |  | 2023-03-13 |  | EXP | [8 empty] | 2022-04-25 | Connected |  | Yes
National Grid | GRANBY | 398685 | 1033 | 9.84 | Solar | 09_527L1 | 2021-12-01 15:07 | 2021-12-02 | 1 | 0 | 1 | 2021-12-03 | 2021-12-21 | 13 | 0 | 13 | [20 empty] | 2021-12-22 |  | 2022-12-24 |  | EXP | [8 empty] | 2022-02-23 | Connected |  | No
National Grid | BOXFORD | 398752 | 1921 | 15.2 | Solar | 14_56L3 | 2021-12-01 19:30 | 2021-12-02 | 1 | 0 | 1 | 2021-12-03 | 2021-12-21 | 13 | 0 | 13 | [20 empty] | 2021-12-22 | 2021-12-02 13:06 | 2023-04-23 |  | EXP | [8 empty] | 2022-07-30 | Connected |  | No
National Grid | WESTFORD | 283707 | 1886 | 600 | Natural Gas | 14_57L1 | 2021-12-02 13:06 | 2021-12-03 | 30 | 24 | 6 | [10 empty] | 2022-01-14 | 2022-03-14 | 40 | 19 | 21 | [10 empty] | 2023-07-27 |  | 2024-05-28 | Yes | STD |  | 2024-04-04 |  | 12 | 0 | 12 |  |  |  | Construction |  | No
National Grid | ATTLEBORO | 398708 | 2703 | 7.6 | Solar | 05_9L3 | 2021-12-02 14:49 | 2021-12-03 | 3 | 0 | 3 | 2021-12-08 | 2021-12-28 | 15 | 0 | 15 | [20 empty] | 2022-01-03 |  | 2023-02-22 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | TYNGSBOROUGH | 398399 | 1879 | 43.2 | Solar | 14_211L1 | 2021-12-02 15:53 | 2021-12-03 | 19 | 12 | 7 | 2021-12-29 | 2022-02-17 | 36 | 23 | 13 | [20 empty] | 2022-02-22 |  | 2023-02-23 |  | EXP | [8 empty] | 2022-06-10 | Connected |  | Yes
National Grid | BLACKSTONE | 397085 | 1504 | 10 | Solar | 05_321W9 | 2021-12-02 20:11 | 2021-12-03 | 8 | 5 | 3 | 2021-12-15 | 2022-01-07 | 17 | 0 | 17 | [20 empty] | 2022-01-12 | 2021-12-03 09:41 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BRIDGEWATER | 385956 | 2324 | 265.35 | Solar | 07_912W74 | 2021-12-03 09:41 | 2021-12-06 | 58 | 49 | 9 | [10 empty] | 2022-02-28 | 2022-04-01 | 25 | 0 | 25 | [10 empty] | 2023-08-28 |  | 2024-09-07 | Yes | STD |  | 2024-02-17 |  | 59 | 0 | 59 |  |  |  | Construction |  | Yes
National Grid | EAST DOUGLAS | 398313 | 1516 | 9.772 | Solar | 05_320W2 | 2021-12-03 11:21 | 2021-12-06 | 3 | 1 | 2 | 2021-12-08 | 2021-12-28 | 15 | 0 | 15 | [20 empty] | 2022-01-03 |  | 2023-01-05 |  | EXP | [8 empty] | 2022-07-18 | Connected |  | No
National Grid | NORTH DIGHTON | 393641 | 2764 | 10 | Solar | 05_19W74 | 2021-12-06 10:19 | 2021-12-07 | 1 | 0 | 1 | 2021-12-08 | 2022-01-06 | 22 | 8 | 14 | [20 empty] | 2022-01-07 |  | 2023-01-19 |  | EXP | [8 empty] | 2022-04-07 | Connected |  | No
National Grid | SEEKONK | 397991 | 2771 | 10 | Solar | 05_7L1 | 2021-12-06 11:01 | 2021-12-07 | 2 | 1 | 1 | 2021-12-08 | 2021-12-28 | 15 | 0 | 15 | [20 empty] | 2022-01-03 | 2021-12-06 12:47 | 2023-01-09 |  | EXP | [8 empty] | 2022-06-06 | Connected |  | No
National Grid | METHUEN | 395653 | 1844 | 6 | Solar | 14_74L1 | 2021-12-06 12:47 | 2021-12-07 | 1 | 0 | 1 | 2021-12-08 | 2021-12-28 | 15 | 0 | 15 | [20 empty] | 2022-01-04 |  | 2023-06-28 | Yes | EXP |  | 2022-05-24 | 2022-06-28 | 36 | 0 | 36 |  |  |  | Withdrawn |  | Yes
National Grid | SWANSEA | 398023 | 2777 | 13300 | Other | 05_11W85 | 2021-12-06 15:27 | 2021-12-07 | 42 | 34 | 8 | [10 empty] | 2022-02-07 | 2022-02-09 | 3 | 0 | 3 | [11 empty] | 2021-12-07 12:09 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | FOXBOROUGH | 399116 | 2035 | 234.6 | Solar | 05_3431W2 | 2021-12-07 12:09 | 2021-12-08 | 56 | 50 | 6 | [10 empty] | 2022-02-28 | 2022-04-05 | 27 | 3 | 24 | [10 empty] | 2023-08-28 | 2021-12-07 13:53 | 2024-10-04 | Yes | STD | [9 empty] | Design |  | No
National Grid | ROCKLAND | 396029 | 2370 | 6 | Solar | 07_99W61 | 2021-12-07 13:53 | 2021-12-08 | 22 | 20 | 2 | 2022-01-10 | 2022-01-31 | 15 | 0 | 15 | [20 empty] | 2022-02-04 |  | 2023-11-20 | Yes | EXP |  | 2022-06-15 | 2022-10-11 | 118 | 0 | 118 |  |  | 2023-06-01 | Connected |  | No
National Grid | MANCHESTER BY THE SEA | 400010 | 1944 | 8.027 | Solar | 12_51T1 | 2021-12-08 11:01 | 2021-12-09 | 19 | 17 | 2 | 2022-01-06 | 2022-01-28 | 16 | 0 | 16 | [20 empty] | 2022-02-15 |  | 2023-02-23 |  | EXP | [8 empty] | 2022-03-09 | Connected |  | No
National Grid | LAWRENCE | 396873 | 1843 | 7.6 | Solar | 14_8L1 | 2021-12-08 13:54 | 2021-12-09 | 5 | 4 | 1 | 2021-12-15 | 2022-01-19 | 24 | 0 | 24 | [20 empty] | 2022-01-20 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 397300 | 2302 | 3.84 | Solar | 07_911W77 | 2021-12-08 14:04 | 2021-12-09 | 4 | 0 | 4 | 2021-12-15 | 2022-01-07 | 17 | 0 | 17 | [20 empty] | 2022-01-12 | 2021-12-09 08:47 | 2023-01-20 |  | EXP | [8 empty] | 2022-05-12 | Connected |  | No
National Grid | SEEKONK | 392829 | 2771 | 10 | Solar | 05_9L5 | 2021-12-09 08:47 | 2021-12-10 | 5 | 1 | 4 | 2021-12-17 | 2022-01-11 | 17 | 0 | 17 | [20 empty] | 2022-01-13 |  | 2023-05-09 | Yes | EXP |  | 2022-05-03 | 2022-05-06 | 4 | 0 | 4 |  |  | 2022-06-08 | Connected |  | No
National Grid | CHARLTON | 398624 | 1507 | 19 | Solar | 01_415L2 | 2021-12-09 09:17 | 2021-12-10 | 3 | 0 | 3 | 2021-12-15 | 2022-01-07 | 17 | 0 | 17 | [20 empty] | 2022-01-12 |  | 2023-02-09 |  | EXP | [8 empty] | 2022-04-05 | Connected |  | Yes
National Grid | SWAMPSCOTT | 399139 | 1907 | 5.8 | Solar | 12_22W1 | 2021-12-09 10:23 | 2021-12-10 | 2 | 0 | 2 | 2021-12-14 | 2022-01-04 | 15 | 0 | 15 | [20 empty] | 2022-01-05 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GLOUCESTER | 397029 | 1930 | 20 | Solar | 12_28L2 | 2021-12-09 15:27 | 2021-12-10 | 8 | 6 | 2 | 2021-12-21 | 2022-01-14 | 18 | 0 | 18 | [20 empty] | 2022-01-18 |  | 2023-01-25 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LENOX | 394117 | 1240 | 9.765 | Solar | 09_1103W1 | 2021-12-10 08:07 | 2021-12-13 | 17 | 16 | 1 | 2022-01-05 | 2022-01-21 | 12 | 0 | 12 | [20 empty] | 2022-01-21 |  | 2023-01-31 |  | EXP | [8 empty] | 2022-03-28 | Connected |  | No
National Grid | HUBBARDSTON | 400502 | 1452 | 10 | Solar | 09_604W4 | 2021-12-10 08:40 | 2021-12-13 | 2 | 0 | 2 | 2021-12-15 | 2022-02-04 | 37 | 19 | 18 | [20 empty] | 2022-02-04 | 2021-12-13 11:44 | 2023-02-07 |  | EXP | [8 empty] | 2022-06-15 | Connected |  | No
National Grid | TYNGSBOROUGH | 399903 | 1879 | 17.54 | Solar | 01_210L1 | 2021-12-13 11:44 | 2021-12-14 | 6 | 4 | 2 | 2021-12-21 | 2022-01-14 | 18 | 0 | 18 | [20 empty] | 2022-01-14 | 2021-12-13 12:56 | 2023-06-08 | Yes | EXP |  | 2022-05-26 | 2022-06-08 | 14 | 0 | 14 |  |  | 2022-07-21 | Connected |  | No
National Grid | SAUGUS | 393404 | 1906 | 7.25 | Solar | 12_23W2 | 2021-12-13 12:56 | 2021-12-14 | 6 | 3 | 3 | 2021-12-21 | 2022-01-14 | 18 | 0 | 18 | [20 empty] | 2022-01-21 | 2021-12-14 13:22 | 2023-08-02 | Yes | EXP |  | 2022-05-06 | 2022-06-03 | 29 | 0 | 29 |  |  | 2022-08-11 | Connected |  | No
National Grid | WEYMOUTH | 399003 | 2188 | 499.5 | Solar | 07_12W1 | 2021-12-14 13:22 | 2021-12-15 | 24 | 16 | 8 | [10 empty] | 2022-01-19 | 2022-02-16 | 21 | 0 | 21 | [10 empty] | 2022-07-12 |  | 2023-12-15 | Yes | STD | [8 empty] | 2023-12-12 | Connected |  | No
National Grid | BOLTON | 395135 | 1740 | 250 | Solar | 01_216W6 | 2021-12-14 15:43 | 2021-12-15 | 14 | 8 | 6 | [10 empty] | 2022-01-04 | 2022-03-02 | 40 | 15 | 25 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | GARDNER | 389245 | 1440 | 3.84 | Solar | 01_607W1 | 2021-12-15 11:02 | 2021-12-16 | 2 | 0 | 2 | 2021-12-20 | 2022-01-11 | 16 | 0 | 16 | [20 empty] | 2022-01-19 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HANOVER | 401688 | 2339 | 9.57 | Solar | 07_910W51 | 2021-12-15 18:48 | 2021-12-16 | 26 | 25 | 1 | 2022-01-25 | 2022-02-16 | 17 | 0 | 17 | [20 empty] | 2022-02-16 |  | 2023-03-03 |  | EXP | [8 empty] | 2022-05-05 | Connected |  | No
National Grid | SUTTON | 394432 | 1590 | 15.36 | Solar | 05_320W5 | 2021-12-16 12:04 | 2021-12-17 | 1 | 0 | 1 | 2021-12-20 | 2022-01-11 | 16 | 0 | 16 | [20 empty] | 2022-01-19 | 2021-12-16 13:18 | 2023-05-27 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BRIDGEWATER | 399833 | 2324 | 131.66 | Solar | 07_912W74 | 2021-12-16 13:18 | 2021-12-17 | 30 | 23 | 7 | [10 empty] | 2022-01-31 | 2022-04-01 | 44 | 20 | 24 | [10 empty] | 2023-08-28 | 2021-12-16 14:12 | 2024-09-07 | Yes | STD | [9 empty] | Construction |  | Yes
National Grid | EAST PEPPERELL | 399819 | 1463 | 7.6 | Solar | 01_226L2 | 2021-12-16 14:12 | 2021-12-17 | 2 | 0 | 2 | 2021-12-21 | 2022-01-14 | 18 | 0 | 18 | [20 empty] | 2022-01-14 |  | 2023-06-08 | Yes | EXP |  | 2022-05-11 | 2022-06-07 | 28 | 0 | 28 |  |  | 2022-06-16 | Connected |  | No
National Grid | WESTFORD | 391848 | 1886 | 2499.6 | Other | 14_57L1 | 2021-12-16 15:52 | 2021-12-17 | 13 | 4 | 9 | [10 empty] | 2022-01-06 | 2022-02-03 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | MILFORD | 391850 | 1757 | 4999.2 | Other | 05_336W4 | 2021-12-16 16:17 | 2021-12-17 | 13 | 4 | 9 | [10 empty] | 2022-01-06 | 2022-11-22 | 221 | 213 | 8 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | MEDFORD | 394755 | 2155 | 15.22 | Solar | 12_64J5 | 2021-12-16 20:03 | 2021-12-17 | 13 | 10 | 3 | 2022-01-06 | 2022-01-28 | 16 | 0 | 16 | [20 empty] | 2022-02-07 |  | 2023-03-04 |  | EXP | [8 empty] | 2022-04-08 | Connected |  | No
National Grid | NORTH ANDOVER | 393293 | 1845 | 6.38 | Solar | 14_55L1 | 2021-12-17 09:31 | 2021-12-20 | 13 | 12 | 1 | 2022-01-07 | 2022-01-28 | 15 | 0 | 15 | [20 empty] | 2022-03-23 |  | 2023-03-26 |  | EXP | [8 empty] | 2022-05-04 | Connected |  | No
National Grid | BILLERICA | 330833 | 1821 | 4125 | Solar | 14_18L3 | 2021-12-17 09:46 | 2021-12-20 | 27 | 19 | 8 | [10 empty] | 2022-01-27 | 2022-03-02 | 24 | 15 | 9 | [14 empty] | STD | [9 empty] | Pending Withdraw |  | No
National Grid | HOPEDALE | 393123 | 1747 | 12000 | Other | 05_335W3 | 2021-12-17 09:57 | 2021-12-20 | 26 | 17 | 9 | [10 empty] | 2022-01-26 | 2022-11-22 | 208 | 201 | 7 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | FOXBOROUGH | 401844 | 2035 | 15.2 | Solar | 05_3432W1 | 2021-12-17 10:33 | 2021-12-20 | 6 | 3 | 3 | 2021-12-28 | 2022-01-19 | 15 | 0 | 15 | [20 empty] | 2022-01-20 |  | 2023-11-26 |  | EXP | [8 empty] | 2023-10-26 | Connected |  | No
National Grid | WESTFORD | 401888 | 1886 | 15.2 | Solar | 14_58L3 | 2021-12-17 11:29 | 2021-12-20 | 5 | 3 | 2 | 2021-12-24 | 2022-01-17 | 16 | 0 | 16 | [20 empty] | 2022-01-18 |  | 2023-03-10 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 398037 | 1604 | 3.8 | Solar | 01_27W5 | 2021-12-17 12:03 | 2021-12-20 | 2 | 0 | 2 | 2021-12-22 | 2022-01-19 | 19 | 0 | 19 | [20 empty] | 2022-01-21 |  | 2023-05-15 |  | EXP | [8 empty] | 2022-08-23 | Connected |  | No
National Grid | MANCHESTER BY THE SEA | 394507 | 1944 | 360 | Solar | 12_51T1 | 2021-12-17 13:25 | 2021-12-20 | 32 | 24 | 8 | [10 empty] | 2022-02-03 | 2022-03-07 | 22 | 0 | 22 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | WRENTHAM | 401972 | 2093 | 187.5 | Solar | 05_3337W1 | 2021-12-17 13:59 | 2021-12-20 | 13 | 6 | 7 | [10 empty] | 2022-01-07 | 2022-02-10 | 24 | 0 | 24 | [11 empty] | 2021-12-20 08:02 |  |  | STD | [9 empty] | Study |  | Yes
National Grid | WESTFORD | 402235 | 1886 | 24.57 | Solar | 14_58L3 | 2021-12-20 08:02 | 2021-12-21 | 1 | 0 | 1 | 2021-12-22 | 2022-01-18 | 19 | 5 | 14 | [20 empty] | 2022-01-18 |  | 2023-04-11 | Yes | EXP |  | 2022-03-09 | 2022-04-11 | 34 | 0 | 34 |  |  | 2022-05-12 | Connected |  | No
National Grid | CHELMSFORD | 402022 | 1824 | 187.5 | Solar | 14_16L4 | 2021-12-20 08:43 | 2021-12-21 | 13 | 5 | 8 | [10 empty] | 2022-01-07 | 2022-02-15 | 27 | 0 | 27 | [10 empty] | 2023-07-11 |  | 2025-04-14 |  | STD | [9 empty] | Completion Documents |  | Yes
National Grid | DRACUT | 402327 | 1826 | 15.2 | Solar | 14_78L1 | 2021-12-20 12:10 | 2021-12-21 | 3 | 2 | 1 | 2021-12-24 | 2022-01-17 | 16 | 0 | 16 | [20 empty] | 2022-01-19 | 2021-12-20 12:38 | 2023-02-17 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | STOUGHTON | 398831 | 2072 | 9.8 | Solar | 07_913W67 | 2021-12-20 12:38 | 2021-12-21 | 1 | 0 | 1 | 2021-12-22 | 2022-01-26 | 25 | 8 | 17 | [20 empty] | 2022-02-02 |  | 2024-02-24 | Yes | EXP |  | 2022-06-30 | 2023-02-22 | 238 | 0 | 238 |  |  | 2023-04-19 | Connected |  | No
National Grid | METHUEN | 348816 | 1844 | 499 | Solar | 14_2355 | 2021-12-21 14:10 | 2021-12-22 | 30 | 24 | 6 | [29 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | HUBBARDSTON | 402697 | 1452 | 16 | Solar | 01_609W1 | 2021-12-21 14:51 | 2021-12-22 | 13 | 12 | 1 | 2022-01-11 | 2022-01-31 | 14 | 0 | 14 | [20 empty] | 2022-01-31 |  | 2023-03-01 |  | EXP | [8 empty] | 2022-06-02 | Connected |  | No
National Grid | UXBRIDGE | 402695 | 1569 | 20 | Solar | 05_321W2 | 2021-12-21 22:47 | 2021-12-22 | 16 | 15 | 1 | 2022-01-13 | 2022-01-31 | 12 | 0 | 12 | [20 empty] | 2022-01-31 | 2021-12-21 23:01 | 2023-02-02 |  | EXP | [8 empty] | 2022-10-13 | Connected |  | No
National Grid | RANDOLPH | 399692 | 2368 | 9.8 | Solar | 07_97W2 | 2021-12-21 23:01 | 2021-12-22 | 1 | 0 | 1 | 2021-12-23 | 2022-01-14 | 16 | 0 | 16 | [20 empty] | 2022-01-17 | 2021-12-23 11:15 | 2023-08-02 | Yes | EXP |  | 2022-07-12 | 2022-08-01 | 21 | 0 | 21 |  |  | 2022-08-25 | Connected |  | Yes
National Grid | BROCKTON | 402370 | 2301 | 9.8 | Solar | 07_98W46 | 2021-12-23 11:15 | 2021-12-24 | 4 | 0 | 4 | 2021-12-30 | 2022-01-19 | 13 | 0 | 13 | [20 empty] | 2022-01-21 |  | 2023-04-12 | Yes | EXP |  | 2022-03-19 | 2022-04-11 | 24 | 0 | 24 |  |  | 2022-08-09 | Connected |  | Yes
National Grid | ROCHDALE | 396703 | 1542 | 250 | Solar | 01_21W2 | 2021-12-27 10:11 | 2021-12-28 | 215 | 208 | 7 | [26 empty] | 2021-12-28 10:38 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | OXFORD | 403041 | 1540 | 5.51 | Solar | 01_406L4 | 2021-12-28 10:38 | 2021-12-29 | 4 | 0 | 4 | 2022-01-04 | 2022-01-21 | 13 | 0 | 13 | [20 empty] | 2022-02-03 |  | 2023-09-06 | Yes | EXP |  | 2022-06-16 | 2022-07-18 | 33 | 0 | 33 |  |  | 2022-10-27 | Connected |  | No
National Grid | ORANGE | 403557 | 1364 | 43.2 | Solar | 09_705W3 | 2021-12-28 14:40 | 2021-12-29 | 1 | 0 | 1 | 2021-12-30 | 2022-01-19 | 13 | 0 | 13 | [20 empty] | 2022-01-20 |  | 2023-02-12 |  | EXP | [8 empty] | 2022-06-23 | Connected |  | No
National Grid | DRACUT | 403697 | 1826 | 16.67 | Solar | 14_75L3 | 2021-12-28 16:05 | 2021-12-29 | 6 | 2 | 4 | 2022-01-06 | 2022-01-28 | 16 | 0 | 16 | [20 empty] | 2022-02-15 |  | 2023-02-25 |  | EXP | [8 empty] | 2022-07-19 | Connected |  | No
National Grid | SCITUATE | 403664 | 2066 | 20 | Solar | 07_915W82 | 2021-12-29 08:14 | 2021-12-30 | 12 | 9 | 3 | 2022-01-19 | 2022-02-10 | 16 | 0 | 16 | [20 empty] | 2022-02-11 |  |  |  | EXP | [8 empty] | 2022-04-13 | Connected |  | No
National Grid | PEPPERELL | 401910 | 1463 | 20 | Battery Add-On | 01_226L2 | 2021-12-29 14:06 | 2021-12-30 | 3 | 0 | 3 | 2022-01-05 | 2022-01-21 | 13 | 1 | 12 | [20 empty] | 2022-01-21 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BOLTON | 404028 | 1740 | 15.2 | Solar | 01_216W6 | 2021-12-29 18:03 | 2021-12-30 | 3 | 0 | 3 | 2022-01-04 | 2022-01-21 | 13 | 0 | 13 | [20 empty] | 2022-01-24 |  | 2023-01-31 |  | EXP | [8 empty] | 2022-03-18 | Connected |  | No
National Grid | STURBRIDGE | 404096 | 1566 | 7.6 | Solar | 01_413L7 | 2021-12-30 14:12 | 2021-12-31 | 17 | 15 | 2 | 2022-01-27 | 2022-02-16 | 15 | 0 | 15 | [20 empty] | 2022-02-17 |  | 2023-08-02 |  | EXP | [8 empty] | 2023-07-10 | Connected |  | No
National Grid | NANTUCKET | 404158 | 2554 | 60 | Solar | 04_101L7 | 2021-12-30 15:29 | 2021-12-31 | 25 | 18 | 7 | 2022-02-07 | 2022-04-13 | 48 | 26 | 22 | [20 empty] | 2022-04-28 |  | 2023-09-16 |  | EXP | [8 empty] | 2022-10-21 | Connected |  | No
National Grid | TYNGSBOROUGH | 402600 | 1879 | 15 | Solar | 14_57L3 | 2021-12-31 17:47 | 2022-01-04 | 10 | 6 | 4 | 2022-01-19 | 2022-02-10 | 16 | 0 | 16 | [20 empty] | 2022-02-15 |  | 2023-07-08 |  | EXP | [8 empty] | 2022-07-14 | Connected |  | No
National Grid | ANDOVER | 404321 | 1810 | 7.6 | Solar | 14_62L2 | 2022-01-02 11:28 | 2022-01-04 | 1 | 0 | 1 | 2022-01-05 | 2022-01-21 | 12 | 0 | 12 | [20 empty] | 2022-01-21 |  | 2023-06-27 |  | EXP | [8 empty] | 2022-12-12 | Connected |  | No
National Grid | BELCHERTOWN | 396973 | 1007 | 15.2 | Solar | 09_509L2 | 2022-01-03 10:52 | 2022-01-04 | 1 | 0 | 1 | 2022-01-05 | 2022-02-17 | 31 | 15 | 16 | [20 empty] | 2022-02-22 |  | 2023-03-18 |  | EXP | [8 empty] | 2022-05-26 | Connected |  | Yes
National Grid | STOUGHTON | 404516 | 2072 | 16.08 | Solar | 07_94W44 | 2022-01-03 17:05 | 2022-01-04 | 4 | 2 | 2 | 2022-01-10 | 2022-01-31 | 15 | 0 | 15 | [20 empty] | 2022-02-04 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ANDOVER | 398978 | 1810 | 11.4 | Solar | 14_59L6 | 2022-01-04 09:04 | 2022-01-05 | 3 | 0 | 3 | 2022-01-10 | 2022-01-30 | 15 | 0 | 15 | [20 empty] | 2022-02-02 |  | 2023-03-29 |  | EXP | [8 empty] | 2022-07-08 | Connected |  | No
National Grid | METHUEN | 401100 | 1844 | 4999.2 | Other | 14_74L3 | 2022-01-04 10:19 | 2022-01-05 | 8 | 0 | 8 | [10 empty] | 2022-01-18 | 2022-02-02 | 12 | 0 | 12 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | DUNSTABLE | 397552 | 1827 | 15.2 | Solar | 01_210L1 | 2022-01-04 11:15 | 2022-01-05 | 1 | 0 | 1 | 2022-01-06 | 2022-01-28 | 16 | 0 | 16 | [20 empty] | 2022-02-11 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FALL RIVER | 396688 | 2720 | 4999.2 | Other | 05_106W46 | 2022-01-04 11:27 | 2022-01-05 | 7 | 0 | 7 | [10 empty] | 2022-01-14 | 2022-01-27 | 9 | 0 | 9 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BELLINGHAM | 391859 | 2019 | 999 | Other | 05_344W4 | 2022-01-04 11:31 | 2022-01-05 | 11 | 3 | 8 | [10 empty] | 2022-01-21 | 2022-01-27 | 5 | 0 | 5 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | METHUEN | 396668 | 1844 | 4999.2 | Other | 14_43L2 | 2022-01-04 11:34 | 2022-01-05 | 9 | 2 | 7 | [10 empty] | 2022-01-18 | 2022-03-02 | 31 | 15 | 16 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | NORTH ANDOVER | 396669 | 1845 | 4999.2 | Other | 14_56L2 | 2022-01-04 11:40 | 2022-01-05 | 8 | 0 | 8 | [10 empty] | 2022-01-18 | 2022-03-02 | 31 | 23 | 8 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | NEWBURYPORT | 396682 | 1950 | 4999.2 | Other | 14_60L3 | 2022-01-04 11:42 | 2022-01-05 | 8 | 0 | 8 | [10 empty] | 2022-01-18 | 2022-03-03 | 32 | 0 | 32 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | EAST LONGMEADOW | 401107 | 1028 | 4999.2 | Other | 09_508L4 | 2022-01-04 13:09 | 2022-01-05 | 7 | 0 | 7 | [10 empty] | 2022-01-14 | 2022-02-28 | 30 | 8 | 22 | [10 empty] | 2023-12-05 |  |  |  | STD | [9 empty] | Pending Withdraw |  | Yes
National Grid | WHITMAN | 404665 | 2382 | 17.6 | Solar | 07_91W41 | 2022-01-04 13:33 | 2022-01-05 | 4 | 2 | 2 | 2022-01-11 | 2022-01-31 | 14 | 0 | 14 | [20 empty] | 2022-01-31 |  | 2023-01-31 |  | EXP | [8 empty] | 2022-04-06 | Connected |  | No
National Grid | MANCHESTER | 392637 | 1944 | 4999.2 | Other | 12_51T1 | 2022-01-04 13:50 | 2022-01-05 | 17 | 9 | 8 | [10 empty] | 2022-01-31 | 2022-03-02 | 22 | 15 | 7 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | FALL RIVER | 401103 | 2720 | 4999.2 | Other | 05_28W51 | 2022-01-04 14:56 | 2022-01-05 | 17 | 9 | 8 | [10 empty] | 2022-01-28 | 2022-02-02 | 4 | 0 | 4 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | FALL RIVER | 401104 | 2721 | 4999.2 | Other | 05_106W43 | 2022-01-04 14:58 | 2022-01-05 | 8 | 0 | 8 | [10 empty] | 2022-01-18 | 2022-01-27 | 8 | 0 | 8 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | ABINGTON | 401109 | 2351 | 4999.2 | Other | 07_93W42 | 2022-01-04 15:00 | 2022-01-05 | 8 | 0 | 8 | [10 empty] | 2022-01-18 | 2022-03-02 | 31 | 3 | 28 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | HAVERHILL | 401112 | 1832 | 4999.2 | Other | 14_74L5 | 2022-01-04 15:02 | 2022-01-05 | 8 | 0 | 8 | [10 empty] | 2022-01-18 | 2022-02-02 | 12 | 0 | 12 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | ANDOVER | 391856 | 1810 | 18000 | Other | 14_8T1 | 2022-01-04 15:03 | 2022-01-05 | 16 | 9 | 7 | [10 empty] | 2022-01-27 | 2022-03-02 | 24 | 15 | 9 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | GLOUCESTER | 396042 | 1930 | 4999.2 | Other | 12_51T3 | 2022-01-04 16:22 | 2022-01-05 | 22 | 14 | 8 | [10 empty] | 2022-02-07 | 2022-03-02 | 17 | 15 | 2 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | GLOUCESTER | 396049 | 1930 | 4999.2 | Other | 12_24J2 | 2022-01-04 16:23 | 2022-01-05 | 10 | 2 | 8 | [10 empty] | 2022-01-20 | 2022-03-01 | 28 | 14 | 14 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | ESSEX | 396471 | 1929 | 4999.2 | Other | 12_51T2 | 2022-01-04 16:26 | 2022-01-05 | 17 | 9 | 8 | [10 empty] | 2022-01-31 | 2022-03-02 | 22 | 15 | 7 | [11 empty] | 2022-01-04 16:33 |  |  | STD | [9 empty] | Group Study |  | No
National Grid | BROCKTON | 400248 | 2302 | 3.84 | Solar | 07_911W56 | 2022-01-04 16:33 | 2022-01-05 | 3 | 0 | 3 | 2022-01-10 | 2022-01-31 | 15 | 0 | 15 | [20 empty] | 2022-02-04 |  | 2023-05-06 | Yes | EXP |  | 2022-04-07 | 2022-05-02 | 26 | 0 | 26 |  |  |  | Withdrawn |  | Yes
National Grid | MILFORD | 401110 | 1757 | 4999.2 | Other | 05_336W4 | 2022-01-05 08:29 | 2022-01-06 | 21 | 13 | 8 | [10 empty] | 2022-02-07 | 2022-11-22 | 199 | 199 | 0 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | DIGHTON | 402596 | 2715 | 2.03 | Solar | 05_19W74 | 2022-01-05 09:26 | 2022-01-06 | 1 | 0 | 1 | 2022-01-07 | 2022-01-28 | 15 | 0 | 15 | [20 empty] | 2022-02-15 | 2022-01-05 16:30 | 2023-05-24 |  | EXP | [8 empty] | 2022-07-20 | Connected |  | No
National Grid | NAHANT | 404987 | 1908 | 15.356 | Solar | 12_79J2 | 2022-01-05 16:30 | 2022-01-06 | 1 | 0 | 1 | 2022-01-07 | 2022-01-28 | 15 | 0 | 15 | [20 empty] | 2022-02-01 |  | 2023-06-09 | Yes | EXP |  | 2022-04-28 | 2022-06-08 | 42 | 0 | 42 |  |  | 2022-06-15 | Connected |  | No
National Grid | PLAINVILLE | 405128 | 2762 | 100 | Solar | 05_3422W3 | 2022-01-06 13:42 | 2022-01-07 | 207 | 200 | 7 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FRANKLIN | 401360 | 2038 | 4999.2 | Other | 05_344W5 | 2022-01-06 15:18 | 2022-01-07 | 7 | 0 | 7 | [10 empty] | 2022-01-19 | 2022-01-26 | 6 | 0 | 6 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | FALL RIVER | 401114 | 2724 | 16000 | Other | 05_115W45 | 2022-01-06 15:19 | 2022-01-07 | 16 | 9 | 7 | [10 empty] | 2022-02-01 | 2022-02-02 | 2 | 0 | 2 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 401101 | 1844 | 4999.2 | Other | 14_43L4 | 2022-01-06 15:21 | 2022-01-07 | 8 | 0 | 8 | [10 empty] | 2022-01-20 | 2022-03-02 | 29 | 15 | 14 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | BEVERLY | 396672 | 1915 | 4999.2 | Other | 12_18L1 | 2022-01-06 15:23 | 2022-01-07 | 8 | 0 | 8 | [10 empty] | 2022-01-20 | 2022-03-01 | 28 | 14 | 14 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | WESTFORD | 401105 | 1886 | 4999.2 | Other | 14_58L3 | 2022-01-06 15:24 | 2022-01-07 | 8 | 0 | 8 | [10 empty] | 2022-01-20 | 2022-02-10 | 16 | 0 | 16 | [11 empty] | 2022-01-06 19:53 |  |  | STD | [9 empty] | Group Study |  | No
National Grid | SEEKONK | 404929 | 2771 | 6 | Solar | 05_7L1 | 2022-01-06 19:53 | 2022-01-07 | 62 | 61 | 1 | 2022-04-08 | 2022-04-15 | 6 | 0 | 6 | [20 empty] | 2022-04-15 |  | 2023-07-30 | Yes | EXP |  | 2022-06-11 | 2022-07-18 | 38 | 0 | 38 |  |  | 2022-08-12 | Connected |  | Yes
National Grid | ATTLEBORO | 404485 | 2703 | 16.08 | Solar | 05_8L3 | 2022-01-08 14:39 | 2022-01-10 | 6 | 2 | 4 | 2022-01-19 | 2022-02-10 | 16 | 0 | 16 | [20 empty] | 2022-02-15 |  | 2023-03-31 |  | EXP | [8 empty] | 2022-11-04 | Connected |  | No
National Grid | SWAMPSCOTT | 405582 | 1907 | 21.52 | Solar | 12_9J2 | 2022-01-09 19:46 | 2022-01-10 | 1 | 0 | 1 | 2022-01-11 | 2022-01-31 | 14 | 0 | 14 | [20 empty] | 2022-01-31 |  | 2023-05-15 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | AYER | 397143 | 1432 | 17.54 | Solar | 01_201W2 | 2022-01-10 10:29 | 2022-01-11 | 3 | 2 | 1 | 2022-01-14 | 2022-02-08 | 17 | 0 | 17 | [20 empty] | 2022-02-17 |  | 2023-05-26 |  | EXP | [8 empty] | 2023-04-14 | Connected |  | No
National Grid | WILLIAMSTOWN | 386281 | 1267 | 16.02 | Solar | 09_1003W2 | 2022-01-11 11:11 | 2022-01-12 | 14 | 13 | 1 | 2022-02-01 | 2022-02-17 | 13 | 0 | 13 | [20 empty] | 2022-02-22 | 2022-01-11 15:35 | 2023-11-20 |  | EXP | [8 empty] | 2022-11-23 | Connected |  | No
National Grid | DRACUT | 403830 | 1826 | 50 | Solar | 14_21L1 | 2022-01-11 15:35 | 2022-01-12 | 16 | 10 | 6 | 2022-02-03 | 2022-03-09 | 24 | 0 | 24 | [20 empty] | 2022-03-15 | 2022-01-12 01:34 | 2023-10-09 |  | EXP | [8 empty] | 2022-11-04 | Connected |  | No
National Grid | LOWELL | 374425 | 1854 | 7.68 | Solar | 14_77L1 | 2022-01-12 01:34 | 2022-01-13 | 3 | 0 | 3 | 2022-01-19 | 2022-02-10 | 16 | 0 | 16 | [20 empty] | 2022-02-15 | 2022-01-12 11:27 | 2024-01-14 | Yes | EXP |  | 2022-05-26 | 2023-01-13 | 232 | 0 | 232 |  |  | 2023-01-25 | Connected |  | No
National Grid | FALL RIVER | 388520 | 2720 | 400 | Solar | 05_28W41 | 2022-01-12 11:27 | 2022-01-13 | 63 | 51 | 12 | [10 empty] | 2022-04-14 | 2022-05-12 | 20 | 0 | 20 | [10 empty] | 2023-07-18 | 2022-01-12 12:46 | 2024-06-20 | Yes | STD | [9 empty] | Completion Documents |  | No
National Grid | WESTFORD | 406249 | 1886 | 8.7 | Solar | 14_58L1 | 2022-01-12 12:46 | 2022-01-13 | 1 | 0 | 1 | 2022-01-14 | 2022-02-03 | 14 | 0 | 14 | [20 empty] | 2022-02-04 |  | 2023-05-21 | Yes | EXP |  | 2022-04-22 | 2022-05-20 | 29 | 0 | 29 |  |  | 2022-08-24 | Connected |  | No
National Grid | REVERE | 394618 | 2151 | 28.8 | Solar | 12_7W1 | 2022-01-13 11:27 | 2022-01-14 | 9 | 7 | 2 | 2022-01-27 | 2022-03-30 | 44 | 26 | 18 | [20 empty] | 2022-03-30 |  | 2024-03-18 |  | EXP | [8 empty] | 2024-03-01 | Connected |  | No
National Grid | WILLIAMSTOWN | 406530 | 1267 | 10 | Solar | 09_1003W2 | 2022-01-13 14:22 | 2022-01-14 | 7 | 6 | 1 | 2022-01-25 | 2022-02-16 | 17 | 0 | 17 | [20 empty] | 2022-02-16 |  | 2023-02-23 |  | EXP | [8 empty] | 2022-06-01 | Connected |  | No
National Grid | BROCKTON | 406522 | 2302 | 120 | Solar | 07_911W57 | 2022-01-13 14:59 | 2022-01-14 | 16 | 10 | 6 | [10 empty] | 2022-02-07 | 2022-03-10 | 23 | 0 | 23 | [11 empty] | 2022-01-13 16:37 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | AUBURN | 404298 | 1501 | 6 | Solar | 01_26W3 | 2022-01-13 16:37 | 2022-01-14 | 2 | 0 | 2 | 2022-01-19 | 2022-02-10 | 16 | 0 | 16 | [20 empty] | 2022-02-15 |  | 2023-07-13 | Yes | EXP |  | 2022-05-27 | 2022-06-13 | 18 | 0 | 18 |  |  | 2022-07-26 | Connected |  | Yes
National Grid | ABINGTON | 396664 | 2351 | 4999.2 | Other | 07_93W42 | 2022-01-14 09:43 | 2022-01-18 | 9 | 1 | 8 | [10 empty] | 2022-01-31 | 2022-03-02 | 22 | 1 | 21 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | NEWBURYPORT | 396685 | 1951 | 4999.2 | Other | 14_2405 | 2022-01-14 09:44 | 2022-01-18 | 9 | 1 | 8 | [10 empty] | 2022-01-31 | 2022-03-04 | 24 | 0 | 24 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | SALEM | 406678 | 1970 | 15.2 | Solar | 12_2W1 | 2022-01-14 10:23 | 2022-01-18 | 1 | 0 | 1 | 2022-01-19 | 2022-02-10 | 16 | 0 | 16 | [20 empty] | 2022-02-15 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | STURBRIDGE | 406202 | 1566 | 249 | Solar | 01_413L2 | 2022-01-14 15:57 | 2022-01-18 | 32 | 24 | 8 | [10 empty] | 2022-03-04 | 2022-04-07 | 25 | 0 | 25 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | SHIRLEY | 394134 | 1464 | 700 | Solar | 01_227W3 | 2022-01-17 17:10 | 2022-01-18 | 87 | 77 | 10 | [10 empty] | 2022-05-25 | 2022-06-27 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Group Study |  | Yes
National Grid | AVON | 391865 | 2322 | 4999.2 | Other | 07_75W3 | 2022-01-18 11:50 | 2022-01-19 | 8 | 1 | 7 | [10 empty] | 2022-01-31 | 2022-02-25 | 19 | 0 | 19 | [11 empty] | 2022-01-19 09:19 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SOUTH ATTLEBORO | 403290 | 2703 | 250 | Solar | 05_9L5 | 2022-01-19 09:19 | 2022-01-20 | 7 | 1 | 6 | 2022-01-31 | 2022-03-03 | 23 | 0 | 23 | [20 empty] | 2022-03-17 |  | 2024-05-06 | Yes | EXP | [9 empty] | Construction |  | No
National Grid | EAST LONGMEADOW | 382245 | 1028 | 366.6 | Solar | 09_522L2 | 2022-01-19 13:48 | 2022-01-20 | 16 | 12 | 4 | [10 empty] | 2022-02-10 | 2022-03-17 | 25 | 0 | 25 | [10 empty] | 2023-01-06 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LOWELL | 406690 | 1854 | 43.2 | Solar | 14_21L3 | 2022-01-19 18:28 | 2022-01-20 | 3 | 1 | 2 | 2022-01-24 | 2022-02-25 | 25 | 0 | 25 | [20 empty] | 2022-03-01 |  | 2023-03-08 |  | EXP | [8 empty] | 2022-10-10 | Connected |  | No
National Grid | GRAFTON | 382046 | 1519 | 7.6 | Solar | 01_304W2 | 2022-01-20 09:24 | 2022-01-21 | 17 | 13 | 4 | 2022-02-15 | 2022-03-08 | 15 | 0 | 15 | [20 empty] | 2022-03-18 | 2022-01-20 15:25 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BOLTON | 407694 | 1740 | 10 | Solar | 01_216W6 | 2022-01-20 15:25 | 2022-01-21 | 3 | 1 | 2 | 2022-01-25 | 2022-03-10 | 32 | 16 | 16 | [20 empty] | 2022-03-10 |  | 2023-08-31 | Yes | EXP |  | 2022-05-07 | 2022-08-25 | 108 | 0 | 108 |  |  | 2022-09-01 | Connected |  | No
National Grid | LEOMINSTER | 377022 | 1453 | 250 | Solar | 01_207W4 | 2022-01-21 14:03 | 2022-01-24 | 7 | 1 | 6 | [10 empty] | 2022-02-02 | 2022-03-15 | 30 | 7 | 23 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WRENTHAM | 405839 | 2093 | 9000 | Battery Add-On | 05_3422W1 | 2022-01-23 22:02 | 2022-01-24 | 6 | 0 | 6 | [10 empty] | 2022-02-01 | 2022-02-04 | 4 | 0 | 4 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | TEWKSBURY | 405741 | 1876 | 4999.2 | Battery Add-On | 14_59L5 | 2022-01-23 22:14 | 2022-01-24 | 6 | 0 | 6 | [10 empty] | 2022-02-01 | 2022-03-02 | 21 | 15 | 6 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | ANDOVER | 405190 | 1810 | 4999.2 | Battery Add-On | 14_59L6 | 2022-01-24 05:51 | 2022-01-25 | 8 | 0 | 8 | [10 empty] | 2022-02-04 | 2022-03-02 | 18 | 15 | 3 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | WORCESTER | 401106 | 1604 | 4999.2 | Other | 01_10J366 | 2022-01-24 06:51 | 2022-01-24 | 6 | 0 | 6 | [10 empty] | 2022-02-01 | 2022-03-01 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | GILBERTVILLE | 368904 | 1031 | 4999 | Other | 09_501L2 | 2022-01-24 08:41 | 2022-01-25 | 68 | 59 | 9 | [10 empty] | 2022-05-03 | 2022-07-11 | 47 | 28 | 19 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | WRENTHAM | 405822 | 2035 | 4999.2 | Battery Add-On | 05_3431W1 | 2022-01-24 09:30 | 2022-01-24 | 6 | 0 | 6 | [10 empty] | 2022-02-01 | 2022-02-04 | 4 | 0 | 4 | [11 empty] | 2022-01-24 15:54 |  |  | STD | [9 empty] | Group Study |  | No
National Grid | LAWRENCE | 378285 | 1840 | 60 | Solar | 14_1324 | 2022-01-24 15:54 | 2022-01-25 | 45 | 36 | 9 | 2022-03-30 | 2022-05-04 | 25 | 0 | 25 | [20 empty] | 2022-05-18 |  | 2025-02-14 |  | EXP | [9 empty] | Meter Installation |  | Yes
National Grid | UXBRIDGE | 408286 | 1569 | 15.2 | Solar | 05_320W4 | 2022-01-24 17:05 | 2022-01-25 | 3 | 2 | 1 | 2022-01-27 | 2022-02-16 | 15 | 0 | 15 | [20 empty] | 2022-02-22 | 2022-01-24 17:21 | 2023-03-16 |  | EXP | [8 empty] | 2022-06-03 | Connected |  | No
National Grid | CHARLTON | 396888 | 1507 | 7.68 | Solar | 01_415L2 | 2022-01-24 17:21 | 2022-01-25 | 1 | 0 | 1 | 2022-01-26 | 2022-02-15 | 15 | 0 | 15 | [20 empty] | 2022-02-16 | 2022-01-24 17:47 | 2023-07-27 | Yes | EXP |  | 2022-06-30 | 2022-07-26 | 27 | 0 | 27 |  |  | 2022-09-07 | Connected |  | No
National Grid | AUBURN | 402308 | 1501 | 9.8 | Solar | 01_406L2 | 2022-01-24 17:47 | 2022-01-25 | 6 | 0 | 6 | 2022-02-02 | 2022-02-17 | 12 | 0 | 12 | [20 empty] | 2022-02-23 |  | 2023-08-17 | Yes | EXP |  | 2022-07-15 | 2022-08-16 | 33 | 0 | 33 |  |  | 2022-09-01 | Connected |  | Yes
National Grid | BROCKTON | 402619 | 2302 | 3.84 | Solar | 07_91W42 | 2022-01-24 17:51 | 2022-01-25 | 7 | 0 | 7 | 2022-02-03 | 2022-02-23 | 14 | 0 | 14 | [20 empty] | 2022-02-28 |  | 2023-03-20 |  | EXP | [8 empty] | 2022-08-02 | Connected |  | No
National Grid | WRENTHAM | 405831 | 2093 | 4999.2 | Battery Add-On | 05_3422W2 | 2022-01-24 19:57 | 2022-01-25 | 8 | 0 | 8 | [10 empty] | 2022-02-04 | 2022-02-04 | 1 | 0 | 1 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | ANDOVER | 405836 | 1810 | 4999.2 | Battery Add-On | 14_54L3 | 2022-01-24 22:34 | 2022-01-25 | 8 | 0 | 8 | [10 empty] | 2022-02-04 | 2022-03-02 | 18 | 15 | 3 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | TYNGSBORO | 405845 | 1879 | 4999.2 | Battery Add-On | 14_2399 | 2022-01-25 07:41 | 2022-01-25 | 8 | 0 | 8 | [10 empty] | 2022-02-04 | 2022-03-02 | 18 | 0 | 18 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | UXBRIDGE | 408025 | 1569 | 7.6 | Solar | 05_321W2 | 2022-01-25 09:18 | 2022-01-26 | 4 | 4 | 0 | 2022-02-02 | 2022-02-17 | 12 | 0 | 12 | [20 empty] | 2022-02-23 |  | 2023-03-09 |  | EXP | [8 empty] | 2022-05-03 | Connected |  | No
National Grid | MARLBOROUGH | 396057 | 1752 | 14800 | Other | 05_310W5 | 2022-01-25 10:15 | 2022-01-26 | 9 | 4 | 5 | [29 empty] | CMPX | [9 empty] | Withdrawn |  | No
National Grid | GRAFTON | 381612 | 1519 | 20.3 | Solar | 01_304W1 | 2022-01-25 12:39 | 2022-01-26 | 27 | 26 | 1 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEOMINSTER | 401899 | 1453 | 6 | Solar | 01_207W6 | 2022-01-26 02:48 | 2022-01-27 | 0 | 0 | 0 | 2022-01-28 | 2022-02-16 | 14 | 0 | 14 | [20 empty] | 2022-02-22 |  | 2023-04-06 |  | EXP | [8 empty] | 2022-10-21 | Connected |  | No
National Grid | NEWBURYPORT | 408613 | 1950 | 15.2 | Solar | 14_47L2 | 2022-01-26 09:29 | 2022-01-27 | 7 | 6 | 1 | 2022-02-04 | 2022-02-23 | 13 | 0 | 13 | [20 empty] | 2022-02-23 | 2022-01-26 11:36 | 2023-07-15 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | RANDOLPH | 404526 | 2368 | 10 | Solar | 07_5W3 | 2022-01-26 11:36 | 2022-01-27 | 17 | 16 | 1 | 2022-02-22 | 2022-03-10 | 13 | 0 | 13 | [20 empty] | 2022-03-21 | 2022-01-26 15:42 | 2023-06-30 | Yes | EXP |  | 2022-06-16 | 2022-06-28 | 13 | 0 | 13 |  |  | 2022-07-06 | Connected |  | No
National Grid | REVERE | 397076 | 2151 | 6 | Solar | 12_16W7 | 2022-01-26 15:42 | 2022-01-27 | 5 | 0 | 5 | 2022-02-03 | 2022-02-22 | 13 | 0 | 13 | [20 empty] | 2022-02-28 |  | 2024-05-26 | Yes | EXP |  | 2022-10-05 | 2023-01-30 | 118 | 0 | 118 |  |  | 2023-09-18 | Connected |  | No
National Grid | BLACKSTONE | 408655 | 1504 | 20 | Solar | 05_321W9 | 2022-01-27 09:17 | 2022-01-28 | 2 | 0 | 2 | 2022-02-01 | 2022-02-16 | 12 | 0 | 12 | [20 empty] | 2022-02-22 | 2022-01-27 09:28 | 2023-05-15 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WEYMOUTH | 408117 | 2188 | 80 | Solar | 07_12W5 | 2022-01-27 09:28 | 2022-01-28 | 14 | 10 | 4 | 2022-02-16 | 2022-03-23 | 25 | 0 | 25 | [20 empty] | 2022-04-06 |  | 2022-10-31 | Yes | EXP | [8 empty] | 2022-10-24 | Connected |  | No
National Grid | MONSON | 409183 | 1057 | 19 | Solar | 09_503L2 | 2022-01-28 09:26 | 2022-01-31 | 20 | 19 | 1 | 2022-02-28 | 2022-03-15 | 12 | 0 | 12 | [20 empty] | 2022-03-16 | 2022-01-28 09:28 | 2023-04-04 |  | EXP | [8 empty] | 2022-11-01 | Connected |  | No
National Grid | MILFORD | 397308 | 1757 | 5.51 | Solar | 05_335W5 | 2022-01-28 09:28 | 2022-01-31 | 1 | 0 | 1 | 2022-02-01 | 2022-02-17 | 13 | 0 | 13 | [20 empty] | 2022-02-18 |  | 2023-11-24 | Yes | EXP |  | 2022-08-03 | 2022-11-08 | 98 | 0 | 98 |  |  | 2023-01-09 | Connected |  | No
National Grid | BELLINGHAM | 402732 | 2019 | 3.48 | Solar | 05_108W51 | 2022-01-28 16:23 | 2022-01-31 | 6 | 3 | 3 | 2022-02-08 | 2022-02-24 | 12 | 0 | 12 | [20 empty] | 2022-03-01 | 2022-01-28 19:00 | 2023-09-02 |  | EXP | [8 empty] | 2022-11-30 | Connected |  | No
National Grid | HAVERHILL | 406366 | 1832 | 470 | Solar | 14_43L2 | 2022-01-28 19:00 | 2022-01-31 | 64 | 54 | 10 | [10 empty] | 2022-05-03 | 2022-06-02 | 22 | 0 | 22 | [10 empty] | 2023-04-19 |  | 2024-07-04 | Yes | STD | [9 empty] | Completion Documents |  | Yes
National Grid | FRANKLIN | 396718 | 2038 | 996 | Solar | 05_348W7 | 2022-01-29 11:50 | 2022-01-31 | 26 | 17 | 9 | [10 empty] | 2022-03-09 | 2022-03-09 | 1 | 0 | 1 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | EAST BRIDGEWATER | 394890 | 2333 | 996 | Solar | 07_797W29 | 2022-01-29 11:51 | 2022-01-31 | 22 | 15 | 7 | [10 empty] | 2022-03-02 | 2022-03-02 | 1 | 0 | 1 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | MT WASHINGTON | 409466 | 1258 | 7.6 | Solar | 09_1109W2 | 2022-01-31 09:51 | 2022-02-01 | 1 | 0 | 1 | 2022-02-02 | 2022-02-17 | 12 | 0 | 12 | [20 empty] | 2022-02-23 |  | 2023-03-18 |  | EXP | [8 empty] | 2022-09-01 | Connected |  | No
National Grid | BROCKTON | 408727 | 2301 | 57.6 | Solar | 07_20W7 | 2022-01-31 10:45 | 2022-02-01 | 13 | 8 | 5 | [10 empty] | 2022-02-18 | 2022-03-24 | 24 | 0 | 24 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | NEW SALEM | 397106 | 1355 | 3600 | Solar | 09_702W3 | 2022-01-31 13:02 | 2022-02-01 | 52 | 40 | 12 | [29 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | MILFORD | 402412 | 1747 | 4999.2 | Battery Add-On | 05_335W4 | 2022-02-01 08:23 | 2022-02-02 | 6 | 0 | 6 | [10 empty] | 2022-02-10 | 2022-11-22 | 196 | 194 | 2 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | MALDEN | 405846 | 2148 | 4999.2 | Battery Add-On | 12_16W3 | 2022-02-01 08:25 | 2022-02-02 | 6 | 0 | 6 | [10 empty] | 2022-02-10 | 2022-03-04 | 16 | 0 | 16 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | DRACUT | 405981 | 1826 | 4999.2 | Battery Add-On | 14_78L3 | 2022-02-01 08:28 | 2022-02-02 | 6 | 0 | 6 | [10 empty] | 2022-02-10 | 2022-03-04 | 16 | 0 | 16 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | METHUEN | 405990 | 1844 | 4999.2 | Battery Add-On | 14_74L2 | 2022-02-01 08:29 | 2022-02-02 | 4 | 0 | 4 | [10 empty] | 2022-02-08 | 2022-02-14 | 5 | 0 | 5 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | AYER | 405997 | 1432 | 4999.2 | Battery Add-On | 01_201W3 | 2022-02-01 08:32 | 2022-02-02 | 4 | 0 | 4 | [10 empty] | 2022-02-08 | 2023-05-10 | 313 | 304 | 9 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | LOWELL | 406001 | 1851 | 4999.2 | Battery Add-On | 14_2L3 | 2022-02-01 08:34 | 2022-02-02 | 4 | 0 | 4 | [10 empty] | 2022-02-08 | 2022-02-25 | 13 | 0 | 13 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | FRANKLIN | 406053 | 2038 | 4999.2 | Battery Add-On | 05_348W6 | 2022-02-01 08:36 | 2022-02-02 | 6 | 0 | 6 | [10 empty] | 2022-02-10 | 2022-03-02 | 14 | 0 | 14 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | SOUTH HAMILTON | 406056 | 1982 | 4999.2 | Battery Add-On | 12_51L3 | 2022-02-01 08:40 | 2022-02-02 | 6 | 0 | 6 | [10 empty] | 2022-02-10 | 2022-02-14 | 3 | 0 | 3 | [11 empty] | 2022-02-01 14:42 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LYNN | 409848 | 1905 | 8.376 | Solar | 12_19W1 | 2022-02-01 14:42 | 2022-02-02 | 16 | 15 | 1 | 2022-02-24 | 2022-03-08 | 9 | 9 | 0 | [20 empty] | 2022-03-08 |  | 2023-06-27 | Yes | EXP |  | 2022-04-28 | 2022-06-15 | 49 | 0 | 49 |  |  | 2022-08-24 | Connected |  | No
National Grid | METHUEN | 400900 | 1844 | 16.53 | Solar | 14_43L2 | 2022-02-01 16:26 | 2022-02-02 | 2 | 0 | 2 | 2022-02-04 | 2022-02-23 | 13 | 0 | 13 | [20 empty] | 2022-02-23 |  | 2024-06-11 |  | EXP | [8 empty] | 2023-12-28 | Connected |  | No
National Grid | HANSON | 409784 | 2341 | 7.6 | Solar | 07_93W43 | 2022-02-02 14:04 | 2022-03-18 | 8 | 0 | 8 | 2022-03-31 | 2022-04-06 | 5 | 0 | 5 | [20 empty] | 2022-02-17 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HAMILTON | 401039 | 1982 | 15.2 | Solar | 12_51T2 | 2022-02-03 09:03 | 2022-02-04 | 1 | 0 | 1 | 2022-02-07 | 2022-03-17 | 29 | 18 | 11 | [20 empty] | 2022-03-18 | 2022-02-03 10:15 | 2023-07-15 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | AUBURN | 398501 | 1501 | 9.8 | Solar | 01_8W1 | 2022-02-03 10:15 | 2022-05-11 | 3 | 3 | 0 | 2022-05-16 | 2022-06-01 | 12 | 0 | 12 | [20 empty] | 2022-06-02 |  | 2023-08-12 | Yes | EXP |  | 2022-07-15 | 2022-08-11 | 28 | 0 | 28 |  |  | 2022-09-06 | Connected |  | Yes
National Grid | LYNN | 404787 | 1905 | 9.8 | Solar | 12_19W1 | 2022-02-03 10:41 | 2022-02-04 | 2 | 0 | 2 | 2022-02-08 | 2022-02-24 | 12 | 0 | 12 | [20 empty] | 2022-03-01 | 2022-02-03 10:45 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SPENCER | 405685 | 1562 | 9.8 | Solar | 01_552L1 | 2022-02-03 10:45 | 2022-02-04 | 2 | 0 | 2 | 2022-02-08 | 2022-02-24 | 12 | 0 | 12 | [20 empty] | 2022-03-01 |  | 2023-05-30 | Yes | EXP | [8 empty] | 2022-07-14 | Connected |  | No
National Grid | WEYMOUTH | 410224 | 2191 | 15.2 | Solar | 07_6W2 | 2022-02-03 12:35 | 2022-02-04 | 43 | 25 | 18 | 2022-04-06 | 2022-04-13 | 6 | 0 | 6 | [20 empty] | 2022-04-13 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | AYER | 410227 | 1432 | 3.8 | Solar | 01_201W3 | 2022-02-03 12:51 | 2022-02-04 | 4 | 3 | 1 | 2022-02-09 | 2022-03-01 | 14 | 0 | 14 | [20 empty] | 2022-03-08 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MELROSE | 410315 | 2176 | 8.99 | Solar | 12_25W5 | 2022-02-03 19:56 | 2022-02-04 | 1 | 0 | 1 | 2022-02-07 | 2022-02-23 | 12 | 0 | 12 | [20 empty] | 2022-02-23 | 2022-02-04 06:09 |  |  | EXP | [8 empty] | 2022-04-06 | Connected |  | No
National Grid | LYNN | 407813 | 1902 | 3.84 | Solar | 12_1J901 | 2022-02-04 06:09 | 2022-02-07 | 2 | 0 | 2 | 2022-02-09 | 2022-03-01 | 14 | 0 | 14 | [20 empty] | 2022-03-09 | 2022-02-04 06:15 | 2023-07-26 | Yes | EXP | [8 empty] | 2022-09-09 | Connected |  | No
National Grid | GARDNER | 407933 | 1440 | 6 | Solar | 01_607W4 | 2022-02-04 06:15 | 2022-02-07 | 3 | 0 | 3 | 2022-02-10 | 2022-03-01 | 13 | 0 | 13 | [20 empty] | 2022-03-09 |  | 2024-04-24 | Yes | EXP | [8 empty] | 2023-05-01 | Connected |  | No
National Grid | BILLERICA | 406289 | 1862 | 4999.2 | Battery Add-On | 14_70L2 | 2022-02-04 09:17 | 2022-02-07 | 3 | 0 | 3 | [10 empty] | 2022-02-10 | 2022-03-02 | 14 | 0 | 14 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | WILLIAMSTOWN | 401601 | 1267 | 16.95 | Solar | 09_1003W2 | 2022-02-04 09:19 | 2022-02-07 | 39 | 38 | 1 | 2022-04-04 | 2022-04-07 | 4 | 0 | 4 | [20 empty] | 2022-04-07 | 2022-02-04 11:18 | 2023-04-14 |  | EXP | [8 empty] | 2022-09-07 | Connected |  | No
National Grid | WESTBOROUGH | 409851 | 1581 | 86.4 | Solar | 05_312W3 | 2022-02-04 11:18 | 2022-02-07 | 3 | 0 | 3 | 2022-02-10 | 2022-03-17 | 25 | 0 | 25 | [20 empty] | 2022-07-01 |  | 2023-01-11 | Yes | EXP |  | 2022-12-01 | 2022-12-06 | 6 | 6 | 0 |  |  | 2023-01-19 | Connected |  | No
National Grid | BROCKTON | 393066 | 2301 | 420 | Solar | 07_94W40 | 2022-02-04 11:24 | 2022-02-07 | 10 | 4 | 6 | [10 empty] | 2022-02-22 | 2022-03-24 | 23 | 0 | 23 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | MELROSE | 410526 | 2176 | 16.405 | Solar | 12_25W1 | 2022-02-04 19:30 | 2022-02-07 | 2 | 1 | 1 | 2022-02-09 | 2022-03-01 | 14 | 0 | 14 | [20 empty] | 2022-03-03 |  |  |  | EXP | [8 empty] | 2022-04-14 | Connected |  | No
National Grid | CHELMSFORD | 378752 | 1824 | 2999 | Solar | 14_2L4 | 2022-02-05 10:08 | 2022-02-07 | 26 | 17 | 9 | [10 empty] | 2022-03-16 | 2022-03-16 | 1 | 0 | 1 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | WORCESTER | 410649 | 1605 | 6 | Solar | 01_24W2 | 2022-02-07 11:25 | 2022-02-22 | 2 | 0 | 2 | 2022-02-24 | 2022-05-11 | 54 | 39 | 15 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | FLORENCE | 410687 | 1062 | 25 | Solar | 09_909W4 | 2022-02-07 12:11 | 2022-02-08 | 12 | 11 | 1 | 2022-02-24 | 2022-03-08 | 9 | 0 | 9 | [20 empty] | 2022-03-08 |  | 2023-04-26 |  | EXP | [8 empty] | 2023-03-07 | Connected |  | No
National Grid | WESTFORD | 385677 | 1886 | 3.8 | Solar | 14_57L4 | 2022-02-07 14:48 | 2022-02-08 | 17 | 16 | 1 | 2022-03-03 | 2022-03-23 | 15 | 0 | 15 | [20 empty] | 2022-03-25 |  | 2023-04-26 |  | EXP | [8 empty] | 2022-09-19 | Connected |  | No
National Grid | BOXFORD | 410771 | 1921 | 10 | Solar | 14_56L3 | 2022-02-07 15:45 | 2022-02-08 | 3 | 1 | 2 | 2022-02-10 | 2022-03-01 | 13 | 0 | 13 | [20 empty] | 2022-03-03 |  | 2023-06-30 |  | EXP | [8 empty] | 2022-06-24 | Connected |  | No
National Grid | COHASSET | 409713 | 2025 | 7.6 | Solar | 07_96W41 | 2022-02-08 09:36 | 2022-02-09 | 4 | 3 | 1 | 2022-02-14 | 2022-03-03 | 13 | 0 | 13 | [20 empty] | 2022-03-10 |  | 2023-03-23 |  | EXP | [8 empty] | 2022-06-10 | Connected |  | No
National Grid | GRAFTON | 411110 | 1560 | 19 | Solar | 05_320W3 | 2022-02-09 11:04 | 2022-02-10 | 1 | 0 | 1 | 2022-02-11 | 2022-03-01 | 12 | 0 | 12 | [20 empty] | 2022-03-03 |  | 2023-08-02 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MENDON | 411225 | 1756 | 3.8 | Solar | 05_321W6 | 2022-02-09 12:05 | 2022-02-10 | 5 | 4 | 1 | 2022-02-16 | 2022-03-08 | 14 | 0 | 14 | [20 empty] | 2022-03-09 | 2022-02-09 13:55 | 2023-03-29 |  | EXP | [8 empty] | 2022-07-15 | Connected |  | No
National Grid | NORTH BROOKFIELD | 406582 | 1535 | 6 | Solar | 01_525L1 | 2022-02-09 13:55 | 2022-02-10 | 3 | 0 | 3 | 2022-02-15 | 2022-03-08 | 15 | 0 | 15 | [20 empty] | 2022-03-18 |  | 2023-05-26 | Yes | EXP |  | 2022-04-29 | 2022-05-19 | 21 | 0 | 21 |  |  | 2022-06-02 | Connected |  | Yes
National Grid | SCITUATE | 411314 | 2066 | 15.2 | Solar | 07_15J1 | 2022-02-09 15:26 | 2022-02-10 | 1 | 0 | 1 | 2022-02-11 | 2022-03-01 | 12 | 0 | 12 | [20 empty] | 2022-03-03 |  | 2023-03-21 |  | EXP | [8 empty] | 2022-08-08 | Connected |  | No
National Grid | NANTUCKET | 411210 | 2554 | 20 | Solar | 04_101L2 | 2022-02-10 08:59 | 2022-02-11 | 1 | 0 | 1 | 2022-02-14 | 2022-03-03 | 13 | 0 | 13 | [20 empty] | 2022-03-09 |  | 2023-03-12 |  | EXP | [8 empty] | 2022-06-22 | Connected |  | No
National Grid | MILFORD | 411189 | 1757 | 5 | Solar | 05_335W3 | 2022-02-10 14:41 | 2022-02-11 | 7 | 4 | 3 | 2022-02-23 | 2022-03-15 | 15 | 0 | 15 | [20 empty] | 2022-03-21 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WILBRAHAM | 411592 | 1095 | 15.2 | Solar | 09_507L3 | 2022-02-10 15:26 | 2022-02-11 | 2 | 0 | 2 | 2022-02-15 | 2022-03-08 | 15 | 0 | 15 | [20 empty] | 2022-03-18 | 2022-02-10 15:55 | 2023-07-15 |  | EXP | [8 empty] | 2022-10-03 | Connected |  | No
National Grid | BELLINGHAM | 409458 | 2019 | 3.8 | Solar | 05_335W1 | 2022-02-10 15:55 | 2022-02-11 | 2 | 0 | 2 | 2022-02-15 | 2022-03-08 | 15 | 0 | 15 | [20 empty] | 2022-03-18 |  | 2023-11-17 | Yes | EXP |  | 2022-08-18 | 2022-10-28 | 72 | 0 | 72 |  |  | 2022-12-05 | Connected |  | No
National Grid | WILLIAMSTOWN | 399989 | 1267 | 20 | Solar | 09_1003W1 | 2022-02-10 18:33 | 2022-02-11 | 1 | 0 | 1 | 2022-02-14 | 2022-03-03 | 13 | 0 | 13 | [20 empty] | 2022-03-17 | 2022-02-11 11:55 | 2023-04-18 |  | EXP | [8 empty] | 2022-06-24 | Connected |  | No
National Grid | GARDNER | 410542 | 1440 | 7.6 | Solar | 01_607W5 | 2022-02-11 11:55 | 2022-02-14 | 3 | 0 | 3 | 2022-02-17 | 2022-03-08 | 13 | 0 | 13 | [20 empty] | 2022-03-18 |  | 2023-06-07 | Yes | EXP |  | 2022-05-18 | 2022-05-24 | 7 | 0 | 7 |  |  | 2022-07-08 | Connected |  | No
National Grid | BROCKTON | 409189 | 2302 | 4.8 | Solar | 07_91W43 | 2022-02-11 12:14 | 2022-02-14 | 6 | 0 | 6 | 2022-02-23 | 2022-03-15 | 15 | 0 | 15 | [20 empty] | 2022-03-21 |  | 2023-03-24 |  | EXP | [8 empty] | 2022-08-03 | Connected |  | No
National Grid | ANDOVER | 408840 | 1810 | 4999.2 | Battery Add-On | 14_59L1 | 2022-02-11 15:03 | 2022-02-14 | 5 | 0 | 5 | [10 empty] | 2022-02-22 | 2022-03-02 | 7 | 0 | 7 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 408866 | 1604 | 4999.2 | Battery Add-On | 01_8W1 | 2022-02-11 16:11 | 2022-02-14 | 5 | 0 | 5 | [10 empty] | 2022-02-22 | 2022-09-02 | 135 | 129 | 6 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | MILFORD | 408868 | 1757 | 4999.2 | Battery Add-On | 05_336W1 | 2022-02-11 16:13 | 2022-02-15 | [13 empty] | 2022-02-15 | 2022-11-22 | 193 | 192 | 1 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | MILFORD | 408869 | 1757 | 4999.2 | Battery Add-On | 05_336W1 | 2022-02-11 16:16 | 2022-02-14 | 5 | 0 | 5 | [10 empty] | 2022-02-22 | 2022-11-22 | 190 | 183 | 7 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | REVERE | 408870 | 2151 | 4999.2 | Battery Add-On | 12_16W4 | 2022-02-11 16:19 | 2022-02-14 | 5 | 0 | 5 | [10 empty] | 2022-02-22 | 2022-03-04 | 9 | 0 | 9 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | ROCKLAND | 408872 | 2370 | 4999.2 | Battery Add-On | 07_99W63 | 2022-02-11 16:21 | 2022-02-14 | 5 | 0 | 5 | [10 empty] | 2022-02-22 | 2022-03-02 | 7 | 0 | 7 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTBOROUGH | 394972 | 1581 | 7.6 | Solar | 05_312W4 | 2022-02-11 16:22 | 2022-02-14 | 1 | 0 | 1 | 2022-02-15 | 2022-07-13 | 102 | 90 | 12 | [20 empty] | 2022-07-14 |  | 2023-08-31 |  | EXP | [8 empty] | 2023-07-31 | Connected |  | No
National Grid | NORTHAMPTON | 411322 | 1062 | 10 | Solar | 09_901W3 | 2022-02-15 10:09 | 2022-02-16 | 4 | 0 | 4 | 2022-02-23 | 2022-03-15 | 15 | 0 | 15 | [20 empty] | 2022-03-21 | 2022-02-15 12:32 | 2023-04-05 |  | EXP | [8 empty] | 2022-10-26 | Connected |  | No
National Grid | LYNN | 407981 | 1904 | 7.6 | Solar | 12_29W1 | 2022-02-15 12:32 | 2022-02-16 | 1 | 0 | 1 | 2022-02-17 | 2022-03-08 | 13 | 0 | 13 | [20 empty] | 2022-03-09 |  | 2023-11-02 | Yes | EXP |  | 2022-06-03 | 2022-06-10 | 8 | 0 | 8 |  |  | 2022-11-09 | Connected |  | No
National Grid | NORTH EGREMONT | 368959 | 1252 | 20 | Solar | 09_1109W3 | 2022-02-16 07:26 | 2022-02-17 | 2 | 0 | 2 | 2022-02-22 | 2022-03-10 | 13 | 0 | 13 | [20 empty] | 2022-03-18 | 2022-02-16 10:21 | 2023-04-14 |  | EXP | [8 empty] | 2022-04-22 | Connected |  | No
National Grid | LOWELL | 405329 | 1851 | 150 | Solar | 14_16L3 | 2022-02-16 10:21 | 2022-02-17 | 32 | 23 | 9 | [10 empty] | 2022-04-05 | 2022-04-04 | 0 | 0 | 0 | [10 empty] | 2023-07-18 |  | 2025-03-10 | Yes | STD | [9 empty] | Design |  | No
National Grid | PLAINVILLE | 400659 | 2762 | 19.72 | Solar | 05_3422W3 | 2022-02-16 11:43 | 2022-02-17 | 14 | 13 | 1 | 2022-03-10 | 2022-03-14 | 3 | 0 | 3 | [20 empty] | 2022-03-14 | 2022-02-16 16:44 | 2023-04-11 |  | EXP | [8 empty] | 2022-10-05 | Connected |  | No
National Grid | STOUGHTON | 412720 | 2072 | 243.3 | Solar | 07_913W17 | 2022-02-16 16:44 | 2022-02-17 | 30 | 21 | 9 | [10 empty] | 2022-04-01 | 2022-05-06 | 25 | 0 | 25 | [10 empty] | 2023-09-29 |  |  | Yes | STD | [9 empty] | Design |  | Yes
National Grid | HEATH | 412843 | 1346 | 7.6 | Solar | 09_1019W1 | 2022-02-17 11:02 | 2022-02-18 | 43 | 41 | 2 | 2022-04-22 | 2022-05-17 | 18 | 0 | 18 | [20 empty] | 2022-05-17 |  | 2023-05-18 |  | EXP | [8 empty] | 2022-12-19 | Connected |  | No
National Grid | REVERE | 395249 | 2151 | 34.6 | Solar | 12_7W3 | 2022-02-17 11:49 | 2022-02-18 | 22 | 20 | 2 | 2022-03-23 | 2022-05-31 | 48 | 29 | 19 | [20 empty] | 2022-06-01 |  | 2024-03-31 |  | EXP | [8 empty] | 2024-03-25 | Connected |  | No
National Grid | ANDOVER | 396310 | 1876 | 4999 | Other | 14_59L3 | 2022-02-17 12:23 | 2022-02-18 | 32 | 23 | 9 | [10 empty] | 2022-04-05 | 2022-04-05 | 1 | 0 | 1 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | WRENTHAM | 412928 | 2093 | 11.4 | Solar | 05_3451W3 | 2022-02-17 13:17 | 2022-02-18 | 3 | 0 | 3 | 2022-02-24 | 2022-03-08 | 9 | 0 | 9 | [20 empty] | 2022-03-08 |  | 2023-07-02 |  | EXP | [8 empty] | 2023-01-17 | Connected |  | No
National Grid | BELLINGHAM | 412984 | 2019 | 3.8 | Solar | 05_108W60 | 2022-02-17 15:50 | 2022-02-18 | 3 | 0 | 3 | 2022-02-24 | 2022-03-08 | 9 | 0 | 9 | [20 empty] | 2022-03-08 |  | 2023-04-08 |  | EXP | [8 empty] | 2022-06-28 | Connected |  | No
National Grid | WHITMAN | 392417 | 2382 | 6 | Solar | 07_91W47 | 2022-02-17 16:16 | 2022-02-18 | 3 | 0 | 3 | 2022-02-24 | 2022-03-08 | 9 | 0 | 9 | [20 empty] | 2022-03-09 | 2022-02-18 08:21 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 410011 | 1844 | 4.8 | Solar | 14_63L1 | 2022-02-18 08:21 | 2022-02-22 | 2 | 0 | 2 | 2022-02-24 | 2022-03-15 | 14 | 0 | 14 | [20 empty] | 2022-03-21 |  | 2024-02-07 | Yes | EXP |  | 2022-05-24 | 2022-06-21 | 29 | 0 | 29 |  |  |  | Withdrawn |  | Yes
National Grid | BILLERICA | 413120 | 1821 | 15.2 | Solar | 14_18L2 | 2022-02-18 11:26 | 2022-02-22 | 4 | 2 | 2 | 2022-02-25 | 2022-03-08 | 8 | 0 | 8 | [20 empty] | 2022-03-09 | 2022-02-21 10:03 | 2023-03-25 |  | EXP | [8 empty] | 2022-10-04 | Connected |  | No
National Grid | CHELMSFORD | 410741 | 1824 | 6 | Solar | 14_58L2 | 2022-02-21 10:03 | 2022-02-22 | 2 | 0 | 2 | 2022-02-24 | 2022-03-15 | 14 | 0 | 14 | [20 empty] | 2022-03-21 |  | 2024-02-15 | Yes | EXP |  | 2023-01-28 | 2023-02-14 | 18 | 0 | 18 |  |  | 2023-03-10 | Connected |  | No
National Grid | BILLERICA | 413213 | 1821 | 9.57 | Solar | 14_18L3 | 2022-02-21 10:11 | 2022-02-22 | 2 | 0 | 2 | 2022-02-24 | 2022-03-08 | 8 | 0 | 8 | [20 empty] | 2022-03-08 | 2022-02-21 10:58 | 2023-04-05 |  | EXP | [8 empty] | 2022-05-26 | Connected |  | No
National Grid | SUTTON | 406978 | 1590 | 10 | Solar | 05_320W5 | 2022-02-21 10:58 | 2022-02-22 | 2 | 0 | 2 | 2022-02-24 | 2022-03-15 | 14 | 0 | 14 | [20 empty] | 2022-03-21 |  | 2023-08-03 | Yes | EXP |  | 2022-06-23 | 2022-07-15 | 23 | 0 | 23 |  |  | 2022-08-13 | Connected |  | No
National Grid | REVERE | 407783 | 2151 | 3.84 | Solar | 12_7J3 | 2022-02-21 11:59 | 2022-02-22 | 1 | 0 | 1 | 2022-02-23 | 2022-03-15 | 15 | 0 | 15 | [20 empty] | 2022-03-18 | 2022-02-22 15:25 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEBSTER | 311549 | 1570 | 250 | Hydro | 01_412L6 | 2022-02-22 15:25 | 2022-02-23 | 67 | 59 | 8 | [10 empty] | 2022-05-31 | 2022-06-21 | 15 | 0 | 15 | [10 empty] | 2023-12-06 |  | 2024-10-20 | Yes | STD | [9 empty] | Design |  | No
National Grid | CLINTON | 402759 | 1510 | 980 | Solar | 01_216W1 | 2022-02-22 16:34 | 2022-02-23 | 34 | 24 | 10 | [10 empty] | 2022-04-12 | 2022-04-14 | 3 | 0 | 3 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | SEEKONK | 413667 | 2771 | 15.2 | Solar | 05_7L1 | 2022-02-22 17:03 | 2022-02-23 | 3 | 2 | 1 | 2022-02-25 | 2022-03-08 | 8 | 0 | 8 | [20 empty] | 2022-03-08 |  | 2023-05-10 |  | EXP | [8 empty] | 2022-11-16 | Connected |  | No
National Grid | LEOMINSTER | 405711 | 1453 | 11450 | Other | 01_207W4 | 2022-02-23 09:38 | 2022-02-24 | 26 | 17 | 9 | [10 empty] | 2022-04-04 | 2022-04-05 | 2 | 0 | 2 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | HANOVER | 411091 | 2339 | 250 | Solar | 07_95W2 | 2022-02-23 11:46 | 2022-02-24 | 11 | 2 | 9 | [10 empty] | 2022-03-10 | 2022-03-09 | 0 | 0 | 0 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | GLOUCESTER | 412422 | 1930 | 15.2 | Solar | 12_52L1 | 2022-02-23 11:50 | 2022-02-24 | 2 | 1 | 1 | 2022-02-25 | 2022-03-08 | 8 | 0 | 8 | [20 empty] | 2022-03-09 | 2022-02-23 17:48 | 2023-03-16 |  | EXP | [8 empty] | 2022-08-17 | Connected |  | No
National Grid | DUNSTABLE | 410230 | 1827 | 8.64 | Solar | 01_210L1 | 2022-02-23 17:48 | 2022-02-24 | 3 | 0 | 3 | 2022-03-01 | 2022-03-18 | 14 | 0 | 14 | [20 empty] | 2022-03-21 |  | 2023-07-28 | Yes | EXP |  | 2022-06-04 | 2022-06-28 | 24 | 0 | 24 |  |  | 2023-01-14 | Connected |  | No
National Grid | BROOKFIELD | 414012 | 1506 | 15.2 | Solar | 01_525L2 | 2022-02-24 08:08 | 2022-02-25 | 4 | 3 | 1 | 2022-03-02 | 2022-05-25 | 60 | 40 | 20 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTHBOROUGH | 414064 | 1532 | 15.2 | Solar | 05_313W1 | 2022-02-24 10:24 | 2022-02-25 | 3 | 2 | 1 | 2022-03-01 | 2022-03-09 | 7 | 0 | 7 | [20 empty] | 2022-03-10 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | QUINCY | 414118 | 2170 | 7.6 | Solar | 07_1W8 | 2022-02-24 11:56 | 2022-02-25 | 2 | 0 | 2 | 2022-03-01 | 2022-05-24 | 60 | 44 | 16 | [20 empty] | 2022-05-26 | 2022-02-24 13:31 | 2023-06-06 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTH ANDOVER | 412304 | 1845 | 7.6 | Solar | 14_56L3 | 2022-02-24 13:31 | 2022-02-25 | 2 | 0 | 2 | 2022-03-01 | 2022-03-18 | 14 | 0 | 14 | [20 empty] | 2022-03-21 |  | 2023-06-13 | Yes | EXP | [8 empty] | 2022-07-09 | Connected |  | No
National Grid | CHARLTON | 414142 | 1507 | 15.18 | Solar | 01_415L1 | 2022-02-24 13:47 | 2022-02-25 | 36 | 35 | 1 | 2022-04-19 | 2022-04-21 | 3 | 0 | 3 | [20 empty] | 2022-04-21 |  | 2024-07-15 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | HAVERHILL | 413354 | 1830 | 3.8 | Solar | 14_48L3 | 2022-02-25 10:46 | 2022-02-28 | 2 | 0 | 2 | 2022-03-02 | 2022-03-21 | 14 | 0 | 14 | [20 empty] | 2022-03-24 |  | 2023-03-28 |  | EXP | [8 empty] | 2022-04-27 | Connected |  | No
National Grid | WEST BROOKFIELD | 414330 | 1585 | 7.6 | Solar | 01_525L2 | 2022-02-25 11:29 | 2022-02-28 | 1 | 0 | 1 | 2022-03-01 | 2022-03-09 | 7 | 0 | 7 | [20 empty] | 2022-03-09 |  | 2023-06-20 |  | EXP | [8 empty] | 2022-12-10 | Connected |  | No
National Grid | GRAFTON | 414386 | 1519 | 15.2 | Solar | 01_304W1 | 2022-02-25 14:59 | 2022-02-28 | 1 | 0 | 1 | 2022-03-01 | 2022-03-09 | 7 | 0 | 7 | [20 empty] | 2022-03-09 | 2022-02-25 15:46 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 413113 | 2301 | 6 | Solar | 07_98W49 | 2022-02-25 15:46 | 2022-02-28 | 2 | 0 | 2 | 2022-03-02 | 2022-03-22 | 15 | 0 | 15 | [20 empty] | 2022-03-28 |  | 2023-05-03 |  | EXP |  | 2022-04-07 | 2022-05-02 | 26 | 0 | 26 |  |  | 2022-05-06 | Connected |  | No
National Grid | SEEKONK | 414377 | 2771 | 7.6 | Solar | 05_6J1 | 2022-02-28 07:54 | 2022-03-01 | 3 | 2 | 1 | 2022-03-03 | 2022-03-10 | 6 | 0 | 6 | [20 empty] | 2022-03-10 |  | 2023-04-11 |  | EXP | [8 empty] | 2022-10-13 | Connected |  | No
National Grid | GRAFTON | 414504 | 1519 | 15.2 | Solar | 01_304W1 | 2022-02-28 08:47 | 2022-09-09 | 2 | 0 | 2 | 2022-09-13 | 2022-09-29 | 13 | 0 | 13 | [20 empty] | 2022-03-02 | 2022-02-28 16:58 | 2023-10-10 |  | EXP | [8 empty] | 2022-10-19 | Connected |  | Yes
National Grid | AUBURN | 414703 | 1501 | 9.86 | Solar | 01_406L2 | 2022-02-28 16:58 | 2022-03-01 | 9 | 8 | 1 | 2022-03-14 | 2022-03-16 | 3 | 0 | 3 | [20 empty] | 2022-03-16 | 2022-03-01 09:52 | 2023-08-27 | Yes | EXP |  | 2022-07-16 | 2022-08-26 | 42 | 0 | 42 |  |  | 2023-03-09 | Connected |  | No
National Grid | BILLERICA | 412558 | 1821 | 9.8 | Solar | 14_70L6 | 2022-03-01 09:52 | 2022-03-02 | 1 | 0 | 1 | 2022-03-03 | 2022-03-23 | 15 | 0 | 15 | [20 empty] | 2022-03-28 |  | 2023-09-20 | Yes | EXP |  | 2022-08-18 | 2022-09-15 | 29 | 0 | 29 |  |  | 2023-01-04 | Connected |  | No
National Grid | ANDOVER | 414820 | 1810 | 7.6 | Solar | 14_59L6 | 2022-03-01 11:55 | 2022-03-02 | 1 | 0 | 1 | 2022-03-03 | 2022-03-10 | 6 | 0 | 6 | [20 empty] | 2022-03-10 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BILLERICA | 414875 | 1862 | 15.2 | Solar | 14_70L1 | 2022-03-01 14:30 | 2022-03-02 | 1 | 0 | 1 | 2022-03-03 | 2022-03-23 | 15 | 0 | 15 | [20 empty] | 2022-03-25 | 2022-03-01 16:54 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 405449 | 1844 | 7.54 | Solar | 14_75L3 | 2022-03-01 16:54 | 2022-03-02 | 47 | 45 | 2 | 2022-05-06 | 2022-05-26 | 15 | 0 | 15 | [20 empty] | 2022-05-31 |  | 2023-10-01 | Yes | EXP |  | 2022-09-20 | 2022-09-28 | 9 | 0 | 9 |  |  | 2023-01-17 | Connected |  | No
National Grid | QUINCY | 405421 | 2169 | 4.64 | Solar | 07_1W2 | 2022-03-01 17:21 | 2022-03-02 | 1 | 0 | 1 | 2022-03-03 | 2022-05-11 | 49 | 26 | 23 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ABINGTON | 414943 | 2351 | 22.6 | Solar | 07_93W43 | 2022-03-01 19:23 | 2022-03-02 | 6 | 5 | 1 | 2022-03-09 | 2022-03-11 | 3 | 0 | 3 | [20 empty] | 2022-03-14 |  | 2023-05-15 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | DRACUT | 414979 | 1826 | 15.2 | Solar | 14_21L1 | 2022-03-02 08:08 | 2022-03-03 | 16 | 15 | 1 | 2022-03-24 | 2022-03-29 | 4 | 0 | 4 | [20 empty] | 2022-03-30 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTHBOROUGH | 415123 | 1532 | 15.2 | Solar | 05_314W4 | 2022-03-02 15:16 | 2022-03-03 | 1 | 0 | 1 | 2022-03-04 | 2022-03-10 | 5 | 0 | 5 | [20 empty] | 2022-03-10 | 2022-03-02 16:50 | 2023-08-02 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEST BRIDGEWATER | 401391 | 2379 | 9.8 | Solar | 07_98W44 | 2022-03-02 16:50 | 2022-03-03 | 4 | 2 | 2 | 2022-03-09 | 2022-03-24 | 12 | 0 | 12 | [20 empty] | 2022-03-28 |  | 2023-07-27 | Yes | EXP |  | 2022-07-13 | 2022-07-21 | 9 | 0 | 9 |  |  | 2023-01-31 | Connected |  | No
National Grid | NORTHBOROUGH | 415225 | 1532 | 15.2 | Solar | 05_313W3 | 2022-03-03 08:36 | 2022-03-04 | 36 | 26 | 10 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHELMSFORD | 415288 | 1824 | 11.4 | Solar | 14_24L1 | 2022-03-03 11:37 | 2022-03-04 | 1 | 0 | 1 | 2022-03-07 | 2022-03-11 | 5 | 0 | 5 | [20 empty] | 2022-03-11 |  | 2023-04-10 |  | EXP | [8 empty] | 2022-09-08 | Connected |  | No
National Grid | GRAFTON | 415260 | 1519 | 20.3 | Solar | 01_304W1 | 2022-03-03 11:51 | 2022-03-04 | 1 | 0 | 1 | 2022-03-07 | 2022-03-25 | 16 | 3 | 13 | [20 empty] | 2022-03-31 |  | 2023-07-06 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | QUINCY | 398156 | 2169 | 500 | Solar | 07_1W1 | 2022-03-03 12:24 | 2022-03-04 | 24 | 15 | 9 | [10 empty] | 2022-04-07 | 2022-05-05 | 20 | 0 | 20 | [10 empty] | 2023-02-06 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LENOX | 415312 | 1240 | 15.2 | Solar | 09_1103W1 | 2022-03-03 12:33 | 2022-03-04 | 1 | 0 | 1 | 2022-03-07 | 2022-03-10 | 4 | 0 | 4 | [20 empty] | 2022-03-11 |  | 2023-04-07 |  | EXP | [8 empty] | 2022-07-21 | Connected |  | No
National Grid | WHITINSVILLE | 415301 | 1588 | 30 | Solar | 05_320W1 | 2022-03-03 13:44 | 2022-03-04 | 1 | 0 | 1 | 2022-03-07 | 2022-03-23 | 13 | 0 | 13 | [20 empty] | 2022-03-25 |  |  |  | EXP | [8 empty] | 2022-07-11 | Connected |  | No
National Grid | METHUEN | 408867 | 1844 | 4999.2 | Battery Add-On | 14_63L2 | 2022-03-04 15:57 | 2022-03-07 | 10 | 0 | 10 | [10 empty] | 2022-03-21 | 2022-04-05 | 12 | 0 | 12 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | BILLERICA | 408871 | 1821 | 4999.2 | Battery Add-On | 14_18L1 | 2022-03-04 15:59 | 2022-03-07 | 10 | 0 | 10 | [10 empty] | 2022-03-21 | 2022-04-06 | 13 | 0 | 13 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | FOXBOROUGH | 410297 | 2035 | 4999.2 | Battery Add-On | 05_3432W2 | 2022-03-04 16:01 | 2022-03-07 | 10 | 0 | 10 | [10 empty] | 2022-03-21 | 2022-04-14 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | MILFORD | 412214 | 1757 | 4999.2 | Battery Add-On | 05_336W2 | 2022-03-04 16:03 | 2022-03-07 | 10 | 0 | 10 | [10 empty] | 2022-03-21 | 2022-04-08 | 15 | 1 | 14 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | ANDOVER | 412219 | 1810 | 4999.2 | Battery Add-On | 14_59L1 | 2022-03-04 16:05 | 2022-03-07 | 10 | 0 | 10 | [10 empty] | 2022-03-21 | 2022-04-14 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | ROCKLAND | 412222 | 2370 | 4999.2 | Battery Add-On | 07_93W40 | 2022-03-04 16:10 | 2022-03-07 | 10 | 0 | 10 | [10 empty] | 2022-03-21 | 2022-04-14 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | FOXBOROUGH | 412230 | 2035 | 4999.2 | Battery Add-On | 05_3424W1 | 2022-03-04 16:12 | 2022-03-07 | 10 | 0 | 10 | [10 empty] | 2022-03-21 | 2022-04-25 | 25 | 7 | 18 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | ABINGTON | 412225 | 2351 | 4999.2 | Battery Add-On | 07_99W62 | 2022-03-04 16:14 | 2022-03-07 | 10 | 0 | 10 | [10 empty] | 2022-03-21 | 2022-04-14 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WEST BRIDGEWATER | 412220 | 2379 | 4999.2 | Battery Add-On | 07_797W19 | 2022-03-04 16:17 | 2022-03-07 | 38 | 29 | 9 | [10 empty] | 2022-04-29 | 2022-05-25 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | WRENTHAM | 412221 | 2093 | 4999.2 | Battery Add-On | 05_3337W1 | 2022-03-04 16:18 | 2022-03-07 | 10 | 0 | 10 | [10 empty] | 2022-03-21 | 2022-04-14 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | WILBRAHAM | 415891 | 1095 | 15.2 | Solar | 09_507L2 | 2022-03-07 10:36 | 2022-03-08 | 1 | 0 | 1 | 2022-03-09 | 2022-03-11 | 3 | 0 | 3 | [20 empty] | 2022-03-11 | 2022-03-07 13:57 | 2023-04-14 |  | EXP | [8 empty] | 2022-06-12 | Connected |  | No
National Grid | NORTHAMPTON | 395501 | 1062 | 10 | Solar | 09_909W4 | 2022-03-07 13:57 | 2022-03-08 | 2 | 1 | 1 | 2022-03-09 | 2022-03-11 | 3 | 0 | 3 | [20 empty] | 2022-03-15 |  | 2023-06-13 | Yes | EXP |  | 2022-05-19 | 2022-05-31 | 13 | 0 | 13 |  |  | 2022-08-12 | Connected |  | No
National Grid | WEYMOUTH | 416071 | 2190 | 15.2 | Solar | 07_99W32 | 2022-03-07 14:41 | 2022-03-08 | 1 | 0 | 1 | 2022-03-09 | 2022-03-11 | 3 | 0 | 3 | [20 empty] | 2022-03-11 | 2022-03-08 09:29 | 2023-05-21 |  | EXP | [8 empty] | 2023-01-18 | Connected |  | No
National Grid | LAWRENCE | 413386 | 1841 | 6 | Solar | 14_8L2 | 2022-03-08 09:29 | 2022-03-09 | 1 | 0 | 1 | 2022-03-10 | 2022-03-15 | 4 | 0 | 4 | [20 empty] | 2022-03-18 |  | 2024-07-12 | Yes | EXP |  | 2023-05-09 | 2023-06-08 | 31 | 0 | 31 |  |  | 2023-08-25 | Connected |  | No
National Grid | FRANKLIN | 401364 | 2038 | 4999.2 | Battery Add-On | 05_344W2 | 2022-03-08 09:46 | 2022-03-09 | 10 | 0 | 10 | [10 empty] | 2022-03-23 | 2022-03-25 | 3 | 0 | 3 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BOLTON | 416510 | 1740 | 32.6 | Solar | 01_225W1 | 2022-03-09 08:47 | 2022-03-10 | 1 | 0 | 1 | 2022-03-11 | 2022-03-15 | 3 | 0 | 3 | [20 empty] | 2022-03-16 |  | 2023-04-07 |  | EXP | [8 empty] | 2022-11-28 | Connected |  | No
National Grid | WHITMAN | 416681 | 2382 | 15.2 | Solar | 07_93W43 | 2022-03-09 14:11 | 2022-03-10 | 1 | 0 | 1 | 2022-03-11 | 2022-03-15 | 3 | 0 | 3 | [20 empty] | 2022-03-15 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ADAMS | 416760 | 1220 | 15.2 | Solar | 09_1021W1 | 2022-03-09 18:02 | 2022-03-10 | 32 | 26 | 6 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | REHOBOTH | 416885 | 2769 | 15.2 | Solar | 05_7L4 | 2022-03-10 11:42 | 2022-03-11 | 1 | 0 | 1 | 2022-03-14 | 2022-03-15 | 2 | 0 | 2 | [20 empty] | 2022-03-16 |  | 2023-03-30 |  | EXP | [8 empty] | 2022-07-28 | Connected |  | No
National Grid | FALL RIVER | 410239 | 2720 | 500 | Solar | 05_106W46 | 2022-03-10 13:17 | 2022-03-11 | 19 | 9 | 10 | [10 empty] | 2022-04-07 | 2022-04-20 | 9 | 0 | 9 | [10 empty] | 2024-02-28 |  |  |  | STD | [9 empty] | Pending Withdraw |  | Yes
National Grid | METHUEN | 415153 | 1844 | 9.28 | Solar | 14_63L1 | 2022-03-10 14:40 | 2022-03-11 | 2 | 0 | 2 | 2022-03-15 | 2022-03-28 | 10 | 0 | 10 | [20 empty] | 2022-03-31 |  | 2023-04-24 |  | EXP | [8 empty] | 2022-08-01 | Connected |  | No
National Grid | LEOMINSTER | 377934 | 1453 | 700 | Natural Gas | 01_219W4 | 2022-03-10 15:21 | 2022-03-11 | 54 | 45 | 9 | [10 empty] | 2022-05-27 | 2022-11-18 | 120 | 101 | 19 | [11 empty] | 2022-03-10 15:22 |  |  | STD | [9 empty] | Group Study |  | Yes
National Grid | MARLBOROUGH | 416970 | 1752 | 19 | Solar | 05_311W3 | 2022-03-10 15:22 | 2022-03-11 | 2 | 0 | 2 | 2022-03-15 | 2022-04-27 | 30 | 25 | 5 | [20 empty] | 2022-04-27 |  | 2023-06-03 | Yes | EXP | [8 empty] | 2022-09-02 | Connected |  | No
National Grid | STOUGHTON | 417002 | 2072 | 9.84 | Solar | 07_913W67 | 2022-03-10 17:13 | 2022-03-11 | 1 | 0 | 1 | 2022-03-14 | 2022-03-15 | 2 | 0 | 2 | [20 empty] | 2022-03-16 |  | 2023-05-04 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEOMINSTER | 416915 | 1453 | 9.772 | Solar | 01_225W3 | 2022-03-11 10:20 | 2022-03-14 | 13 | 12 | 1 | 2022-03-30 | 2022-03-31 | 2 | 0 | 2 | [20 empty] | 2022-03-31 | 2022-03-11 10:22 | 2023-05-02 |  | EXP | [8 empty] | 2023-01-19 | Connected |  | No
National Grid | LEOMINSTER | 416852 | 1453 | 15.66 | Solar | 01_207W6 | 2022-03-11 10:22 | 2022-03-14 | 16 | 13 | 3 | 2022-04-05 | 2022-04-13 | 8 | 2 | 6 | [20 empty] | 2022-04-14 |  | 2023-07-26 |  | EXP |  | 2022-06-30 | 2022-07-20 | 21 | 0 | 21 |  |  | 2022-08-24 | Connected |  | Yes
National Grid | EAST BRIDGEWATER | 383230 | 2333 | 3000 | Solar | 07_797W1 | 2022-03-11 14:39 | 2022-03-14 | 10 | 0 | 10 | [10 empty] | 2022-03-28 | 2022-05-20 | 39 | 20 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | ORANGE | 416537 | 1364 | 200 | Solar | 09_702W3 | 2022-03-11 14:41 | 2022-03-14 | 10 | 0 | 10 | [10 empty] | 2022-03-28 | 2022-04-27 | 22 | 0 | 22 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | NANTUCKET | 404153 | 2554 | 28.71 | Solar | 04_101L2 | 2022-03-11 16:30 | 2022-03-14 | 1 | 0 | 1 | 2022-03-15 | 2022-04-08 | 19 | 8 | 11 | [20 empty] | 2022-04-11 |  | 2023-04-23 |  | EXP | [8 empty] | 2022-07-05 | Connected |  | No
National Grid | SCITUATE | 415760 | 2066 | 20.52 | Solar | 07_915W82 | 2022-03-12 12:37 | 2022-03-14 | 2 | 1 | 1 | 2022-03-15 | 2022-03-16 | 2 | 0 | 2 | [20 empty] | 2022-03-16 |  | 2023-05-15 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 407000 | 1606 | 15.37 | Solar | 01_14J368 | 2022-03-13 12:51 | 2022-03-14 | 2 | 0 | 2 | 2022-03-16 | 2022-03-18 | 3 | 0 | 3 | [20 empty] | 2022-03-21 |  | 2023-03-29 |  | EXP | [8 empty] | 2022-07-22 | Connected |  | No
National Grid | STOUGHTON | 417294 | 2072 | 15.2 | Solar | 07_94W43 | 2022-03-14 07:53 | 2022-03-15 | 1 | 0 | 1 | 2022-03-16 | 2022-03-18 | 3 | 0 | 3 | [20 empty] | 2022-03-18 |  | 2023-05-29 |  | EXP | [8 empty] | 2022-10-13 | Connected |  | No
National Grid | BEVERLY | 411748 | 1915 | 180 | Battery Add-On | 12_12L4 | 2022-03-14 09:43 | 2022-03-15 | 10 | 0 | 10 | 2022-03-29 | 2022-05-23 | 39 | 19 | 20 | [20 empty] | 2022-06-22 |  | 2023-11-02 |  | EXP | [8 empty] | 2023-07-26 | Connected |  | No
National Grid | FALL RIVER | 397056 | 2720 | 625 | Solar | 05_28W51 | 2022-03-14 09:48 | 2022-03-15 | 166 | 157 | 9 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | FALL RIVER | 397063 | 2720 | 1750 | Solar | 05_28W42 | 2022-03-14 10:02 | 2022-03-15 | 162 | 153 | 9 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | LANCASTER | 396879 | 1523 | 1500 | Solar | 01_225W3 | 2022-03-14 10:23 | 2022-03-15 | 166 | 157 | 9 | [26 empty] | 2022-03-14 11:50 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | RANDOLPH | 413313 | 2368 | 150 | Solar | 07_97W4 | 2022-03-14 11:50 | 2022-03-15 | 96 | 87 | 9 | 2022-08-02 | 2022-10-12 | 50 | 28 | 22 | [20 empty] | 2023-04-25 | 2022-03-14 12:38 | 2024-08-05 | Yes | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | EVERETT | 415927 | 2149 | 3.8 | Solar | 12_16W2 | 2022-03-14 12:38 | 2022-03-15 | 1 | 0 | 1 | 2022-03-16 | 2022-03-22 | 5 | 0 | 5 | [20 empty] | 2022-03-28 | 2022-03-14 12:43 | 2024-04-14 | Yes | EXP | [8 empty] | 2023-05-03 | Connected |  | No
National Grid | SOUTHBRIDGE | 416620 | 1550 | 10 | Solar | 01_413L4 | 2022-03-14 12:43 | 2022-03-15 | 1 | 0 | 1 | 2022-03-16 | 2022-03-21 | 4 | 0 | 4 | [20 empty] | 2022-03-24 |  | 2024-01-18 | Yes | EXP | [8 empty] | 2023-02-08 | Connected |  | Yes
National Grid | SALEM | 415655 | 1970 | 10 | Solar | 12_2W1 | 2022-03-14 13:03 | 2022-03-15 | 7 | 3 | 4 | 2022-03-24 | 2022-06-09 | 54 | 26 | 28 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WARREN | 397233 | 1010 | 2000 | Solar | 09_516L4 | 2022-03-14 17:34 | 2022-03-15 | 166 | 157 | 9 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | WARREN | 397235 | 1010 | 2125 | Solar | 09_516L4 | 2022-03-14 17:48 | 2022-03-15 | 162 | 153 | 9 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | WARREN | 397228 | 1585 | 2125 | Solar | 09_516L4 | 2022-03-15 09:59 | 2022-03-16 | 166 | 158 | 8 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | TEWKSBURY | 397084 | 1876 | 1375 | Solar | 14_59L1 | 2022-03-15 10:08 | 2022-03-16 | 57 | 48 | 9 | [10 empty] | 2022-06-08 | 2022-06-30 | 16 | 0 | 16 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | MILLBURY | 397095 | 1527 | 1500 | Solar | 01_304W5 | 2022-03-15 10:14 | 2022-03-16 | 161 | 153 | 8 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | UXBRIDGE | 397070 | 1569 | 2500 | Solar | 05_320W4 | 2022-03-15 10:45 | 2022-03-16 | 165 | 157 | 8 | [26 empty] | 2022-03-15 10:46 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | HOPEDALE | 416720 | 1747 | 7.6 | Solar | 05_335W3 | 2022-03-15 10:46 | 2022-03-16 | 2 | 0 | 2 | 2022-03-18 | 2022-03-22 | 3 | 0 | 3 | [20 empty] | 2022-03-28 |  |  | Yes | EXP |  | 2023-01-07 | 2023-02-25 | 50 | 0 | 50 |  |  | 2023-03-08 | Connected |  | No
National Grid | SOUTHBRIDGE | 399464 | 1550 | 2625 | Solar | 01_413L3 | 2022-03-15 10:49 | 2022-03-16 | 161 | 153 | 8 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | WRENTHAM | 397258 | 2093 | 1500 | Solar | 05_2284 | 2022-03-15 12:39 | 2022-03-16 | 166 | 158 | 8 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | FRANKLIN | 397260 | 2038 | 2250 | Solar | 05_2284 | 2022-03-15 12:43 | 2022-03-16 | 165 | 157 | 8 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | DOUGLAS | 397254 | 1516 | 1500 | Solar | 05_320W4 | 2022-03-15 12:49 | 2022-03-16 | 165 | 157 | 8 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | MEDFORD | 409266 | 2155 | 17.11 | Solar | 12_9C3 | 2022-03-15 13:16 | 2022-03-16 | 7 | 2 | 5 | 2022-03-25 | 2022-04-04 | 7 | 0 | 7 | [20 empty] | 2022-04-05 |  | 2023-06-22 |  | EXP | [8 empty] | 2022-08-17 | Connected |  | No
National Grid | OXFORD | 418004 | 1540 | 15.2 | Solar | 01_406L3 | 2022-03-16 10:29 | 2022-03-17 | 1 | 0 | 1 | 2022-03-18 | 2022-03-21 | 2 | 0 | 2 | [20 empty] | 2022-03-22 |  | 2023-03-28 |  | EXP | [8 empty] | 2022-07-27 | Connected |  | No
National Grid | LOWELL | 416317 | 1854 | 7.68 | Solar | 14_77L2 | 2022-03-16 10:49 | 2022-03-17 | 5 | 0 | 5 | 2022-03-24 | 2022-03-29 | 4 | 0 | 4 | [20 empty] | 2022-03-30 | 2022-03-16 10:52 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SPENCER | 412613 | 1562 | 10 | Solar | 01_552L1 | 2022-03-16 10:52 | 2022-03-17 | 6 | 1 | 5 | 2022-03-25 | 2022-04-04 | 7 | 0 | 7 | [20 empty] | 2022-04-05 |  | 2023-06-15 | Yes | EXP |  | 2022-05-17 | 2022-06-14 | 29 | 0 | 29 |  |  | 2022-08-11 | Connected |  | No
National Grid | BERLIN | 418047 | 1503 | 15.2 | Solar | 05_318W3 | 2022-03-16 11:46 | 2022-03-17 | 3 | 2 | 1 | 2022-03-21 | 2022-03-22 | 2 | 0 | 2 | [20 empty] | 2022-03-22 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | STURBRIDGE | 418074 | 1566 | 15.2 | Solar | 01_413L2 | 2022-03-16 12:54 | 2022-03-17 | 3 | 2 | 1 | 2022-03-21 | 2022-03-22 | 2 | 0 | 2 | [20 empty] | 2022-03-22 |  | 2023-04-06 |  | EXP | [8 empty] | 2022-07-15 | Connected |  | No
National Grid | WESTFORD | 402422 | 1886 | 7.6 | Solar | 14_73L2 | 2022-03-17 15:00 | 2022-03-18 | 1 | 0 | 1 | 2022-03-21 | 2022-03-28 | 6 | 0 | 6 | [20 empty] | 2022-03-29 | 2022-03-17 16:25 | 2023-05-01 |  | EXP | [8 empty] | 2022-05-06 | Connected |  | No
National Grid | HAVERHILL | 418150 | 1832 | 149.9 | Solar | 14_43L6 | 2022-03-17 16:25 | 2022-03-18 | 7 | 0 | 7 | [10 empty] | 2022-03-29 | 2022-06-03 | 47 | 23 | 24 | [10 empty] | 2022-11-17 | 2022-03-17 16:50 | 2023-12-12 | Yes | STD | [8 empty] | 2023-12-29 | Connected |  | No
National Grid | HAVERHILL | 418169 | 1832 | 133.2 | Solar | 14_43L6 | 2022-03-17 16:50 | 2022-03-18 | 17 | 11 | 6 | [10 empty] | 2022-04-12 | 2022-06-03 | 37 | 12 | 25 | [10 empty] | 2022-11-17 | 2022-03-17 17:07 | 2023-12-12 | Yes | STD | [8 empty] | 2023-12-29 | Connected |  | No
National Grid | HAVERHILL | 418171 | 1832 | 149.9 | Solar | 14_43L6 | 2022-03-17 17:07 | 2022-03-18 | 7 | 0 | 7 | [10 empty] | 2022-03-29 | 2022-06-03 | 47 | 23 | 24 | [10 empty] | 2022-11-17 |  | 2023-12-08 | Yes | STD | [8 empty] | 2023-12-08 | Connected |  | No
National Grid | BROCKTON | 418384 | 2302 | 16.24 | Solar | 07_91W43 | 2022-03-18 12:26 | 2022-03-21 | 6 | 5 | 1 | 2022-03-29 | 2022-03-30 | 2 | 0 | 2 | [20 empty] | 2022-03-31 |  | 2023-11-24 |  | EXP | [8 empty] | 2022-12-12 | Connected |  | Yes
National Grid | NORTHAMPTON | 418652 | 1062 | 15.2 | Solar | 09_909W4 | 2022-03-18 13:23 | 2022-03-21 | 5 | 4 | 1 | 2022-03-25 | 2022-03-29 | 3 | 0 | 3 | [20 empty] | 2022-03-29 |  | 2023-04-05 |  | EXP | [8 empty] | 2022-09-16 | Connected |  | No
National Grid | LAWRENCE | 418695 | 1840 | 64.4 | Solar | 14_2J8 | 2022-03-18 15:42 | 2022-03-21 | 29 | 19 | 10 | 2022-05-02 | 2022-06-02 | 23 | 0 | 23 | [20 empty] | 2022-06-17 |  | 2024-07-15 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | ATTLEBORO | 418617 | 2703 | 20 | Battery Add-On | 05_9L3 | 2022-03-21 08:37 | 2022-03-22 | 11 | 10 | 1 | 2022-04-06 | 2022-04-13 | 6 | 0 | 6 | [20 empty] | 2022-04-13 | 2022-03-21 09:36 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | TEWKSBURY | 411194 | 1876 | 9.57 | Solar | 14_75L2 | 2022-03-21 09:36 | 2022-03-22 | 36 | 35 | 1 | 2022-05-11 | 2022-05-30 | 14 | 0 | 14 | [20 empty] | 2022-06-02 |  | 2023-08-26 | Yes | EXP |  | 2022-08-09 | 2022-08-25 | 17 | 0 | 17 |  |  | 2022-09-15 | Connected |  | No
National Grid | EASTON | 418873 | 2356 | 15.2 | Solar | 07_94W43 | 2022-03-21 10:36 | 2022-03-22 | 1 | 0 | 1 | 2022-03-23 | 2022-03-23 | 1 | 0 | 1 | [20 empty] | 2022-03-23 | 2022-03-21 12:03 | 2023-06-30 |  | EXP | [8 empty] | 2023-07-06 | Connected |  | No
National Grid | METHUEN | 418542 | 1844 | 7.6 | Solar | 14_5J41 | 2022-03-21 12:03 | 2022-03-22 | 4 | 0 | 4 | 2022-03-28 | 2022-04-05 | 7 | 0 | 7 | [20 empty] | 2022-04-05 |  | 2023-05-27 | Yes | EXP | [8 empty] | 2022-06-10 | Connected |  | No
National Grid | FALL RIVER | 418915 | 2721 | 15.2 | Solar | 05_115W54 | 2022-03-21 12:04 | 2022-03-22 | 4 | 3 | 1 | 2022-03-28 | 2022-03-29 | 2 | 0 | 2 | [20 empty] | 2022-03-30 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FALL RIVER | 409703 | 2720 | 4999.2 | Battery Add-On | 05_28W51 | 2022-03-22 05:09 | 2022-03-23 | 8 | 0 | 8 | [10 empty] | 2022-04-04 | 2022-04-05 | 2 | 0 | 2 | [11 empty] | 2022-03-22 14:21 |  |  | STD | [9 empty] | Group Study |  | No
National Grid | WRENTHAM | 408895 | 2093 | 9.6 | Solar | 05_3422W2 | 2022-03-22 14:21 | 2022-03-23 | 4 | 0 | 4 | 2022-03-29 | 2022-04-05 | 6 | 0 | 6 | [20 empty] | 2022-04-07 |  | 2023-09-14 | Yes | EXP |  | 2022-08-25 | 2022-09-08 | 15 | 0 | 15 |  |  | 2023-01-06 | Connected |  | No
National Grid | METHUEN | 414167 | 1844 | 10 | Solar | 14_74L2 | 2022-03-22 22:15 | 2022-03-23 | 328 | 156 | 172 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOUTHBRIDGE | 419438 | 1550 | 7.6 | Solar | 01_413L1 | 2022-03-23 09:55 | 2022-03-24 | 31 | 30 | 1 | 2022-05-06 | 2022-05-26 | 15 | 0 | 15 | [20 empty] | 2022-05-27 |  | 2023-08-10 |  | EXP | [8 empty] | 2022-09-01 | Connected |  | No
National Grid | MONSON | 419511 | 1057 | 15.2 | Solar | 09_503L2 | 2022-03-23 12:16 | 2022-03-24 | 5 | 4 | 1 | 2022-03-30 | 2022-04-05 | 5 | 0 | 5 | [20 empty] | 2022-04-05 |  | 2023-05-11 |  | EXP | [8 empty] | 2023-02-15 | Connected |  | No
National Grid | BRIMFIELD | 419691 | 1010 | 25 | Solar | 09_516L1 | 2022-03-24 09:34 | 2022-03-25 | 17 | 16 | 1 | 2022-04-19 | 2022-04-21 | 3 | 0 | 3 | [20 empty] | 2022-04-22 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | RANDOLPH | 412389 | 2368 | 3 | Solar | 07_97W2 | 2022-03-24 12:53 | 2022-03-25 | 2 | 0 | 2 | 2022-03-29 | 2022-03-31 | 3 | 0 | 3 | [20 empty] | 2022-04-04 | 2022-03-24 12:57 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 407121 | 1843 | 7.54 | Solar | 14_61L1 | 2022-03-24 12:57 | 2022-03-25 | 9 | 7 | 2 | 2022-04-06 | 2022-04-19 | 9 | 0 | 9 | [20 empty] | 2022-04-21 |  | 2023-08-20 | Yes | EXP |  | 2022-06-08 | 2022-07-14 | 37 | 0 | 37 |  |  | 2022-09-01 | Connected |  | No
National Grid | LAWRENCE | 407034 | 1843 | 9.57 | Solar | 14_61L1 | 2022-03-24 13:26 | 2022-03-25 | 2 | 1 | 1 | 2022-03-29 | 2022-04-05 | 6 | 0 | 6 | [20 empty] | 2022-04-06 | 2022-03-24 13:54 | 2023-07-13 |  | EXP |  | 2022-06-08 | 2022-07-12 | 35 | 0 | 35 |  |  | 2022-07-23 | Connected |  | No
National Grid | METHUEN | 409865 | 1844 | 6.67 | Solar | 14_74L1 | 2022-03-24 13:54 | 2022-03-25 | 10 | 9 | 1 | 2022-04-07 | 2022-04-14 | 6 | 0 | 6 | [20 empty] | 2022-04-14 |  | 2023-07-08 | Yes | EXP |  | 2022-06-08 | 2022-06-28 | 21 | 0 | 21 |  |  | 2022-08-01 | Connected |  | No
National Grid | BROCKTON | 413365 | 2301 | 23.4 | Solar | 07_20W10 | 2022-03-24 14:35 | 2022-04-19 | 10 | 1 | 9 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | DRACUT | 417105 | 1826 | 362.5 | Solar | 14_78L3 | 2022-03-25 18:28 | 2022-03-28 | 56 | 47 | 9 | [10 empty] | 2022-06-16 | 2022-07-15 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | ROCKPORT | 420293 | 1966 | 10 | Solar | 12_40J2 | 2022-03-28 11:37 | 2022-03-29 | 1 | 0 | 1 | 2022-03-30 | 2022-04-07 | 7 | 0 | 7 | [20 empty] | 2022-04-07 |  | 2023-04-14 |  | EXP | [8 empty] | 2022-08-16 | Connected |  | No
National Grid | SOUTHBOROUGH | 417351 | 1772 | 11.4 | Solar | 05_310W3 | 2022-03-28 11:53 | 2022-03-29 | 1 | 0 | 1 | 2022-03-30 | 2022-05-20 | 40 | 26 | 14 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | QUINCY | 365947 | 2171 | 700 | Solar | 07_11W3 | 2022-03-28 14:15 | 2022-03-29 | 65 | 57 | 8 | [10 empty] | 2022-07-01 | 2022-07-29 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | GREAT BARRINGTON | 420606 | 1230 | 15.2 | Solar | 09_1109W3 | 2022-03-29 12:59 | 2022-03-30 | 4 | 3 | 1 | 2022-04-05 | 2022-04-11 | 5 | 0 | 5 | [20 empty] | 2022-04-12 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | STOUGHTON | 420687 | 2072 | 15.2 | Solar | 07_94W43 | 2022-03-29 16:16 | 2022-03-30 | 1 | 0 | 1 | 2022-03-31 | 2022-03-31 | 1 | 0 | 1 | [20 empty] | 2022-04-01 |  | 2023-04-06 |  | EXP | [8 empty] | 2022-10-08 | Connected |  | No
National Grid | NORTHBOROUGH | 420767 | 1532 | 15.2 | Solar | 05_313W3 | 2022-03-30 08:03 | 2022-03-31 | 1 | 0 | 1 | 2022-04-01 | 2022-04-06 | 4 | 0 | 4 | [20 empty] | 2022-04-06 |  | 2023-05-07 |  | EXP | [8 empty] | 2022-08-15 | Connected |  | No
National Grid | SWANSEA | 412047 | 2777 | 12500 | Other | 05_11W82 | 2022-03-30 15:03 | 2022-03-31 | 16 | 8 | 8 | [10 empty] | 2022-04-22 | 2022-04-21 | 0 | 0 | 0 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | FRANKLIN | 411046 | 2038 | 10000 | Other | 05_348W7 | 2022-03-30 15:59 | 2022-03-31 | 10 | 4 | 6 | [10 empty] | 2022-04-14 | 2022-05-12 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | LEICESTER | 384247 | 1524 | 10000 | Other | 01_21W2 | 2022-03-30 16:25 | 2022-03-31 | 19 | 10 | 9 | [10 empty] | 2022-04-28 | 2022-06-01 | 25 | 6 | 19 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | BROCKTON | 384235 | 2301 | 10000 | Other | 07_94W40 | 2022-03-30 16:49 | 2022-03-31 | 10 | 4 | 6 | [10 empty] | 2022-04-14 | 2022-04-27 | 9 | 0 | 9 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | GRANBY | 421045 | 1033 | 10 | Solar | 09_527L2 | 2022-03-31 08:28 | 2022-04-01 | 6 | 5 | 1 | 2022-04-08 | 2022-04-14 | 5 | 0 | 5 | [20 empty] | 2022-04-14 |  | 2023-06-15 |  | EXP | [8 empty] | 2022-11-22 | Connected |  | No
National Grid | WESTFORD | 420189 | 1886 | 24.43 | Solar | 14_58L1 | 2022-03-31 08:45 | 2022-04-01 | 5 | 3 | 2 | 2022-04-07 | 2022-04-13 | 5 | 0 | 5 | [20 empty] | 2022-04-14 |  | 2023-04-21 |  | EXP | [8 empty] | 2022-06-08 | Connected |  | No
National Grid | NEWBURY | 421113 | 1951 | 18 | Solar | 14_60L1 | 2022-03-31 11:06 | 2022-04-01 | 2 | 0 | 2 | 2022-04-05 | 2022-04-11 | 5 | 0 | 5 | [20 empty] | 2022-04-12 |  | 2023-04-18 |  | EXP | [8 empty] | 2022-11-28 | Connected |  | No
National Grid | FOXBOROUGH | 421144 | 2035 | 18.3 | Solar | 05_3424W5 | 2022-03-31 11:53 | 2022-04-01 | 2 | 0 | 2 | 2022-04-05 | 2022-04-12 | 6 | 0 | 6 | [20 empty] | 2022-04-12 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 347070 | 1604 | 26 | Solar | 01_27W1 | 2022-03-31 13:07 | 2022-04-01 | 7 | 0 | 7 | 2022-04-12 | 2022-05-16 | 24 | 0 | 24 | [24 empty] | EXP | [9 empty] | Completion Documents |  | No
National Grid | LEOMINSTER | 421215 | 1453 | 17.6 | Solar | 01_225W4 | 2022-03-31 14:25 | 2022-04-01 | 2 | 0 | 2 | 2022-04-05 | 2022-04-11 | 5 | 0 | 5 | [20 empty] | 2022-04-11 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 414713 | 2302 | 10 | Solar | 07_911W56 | 2022-03-31 15:13 | 2022-04-01 | 2 | 0 | 2 | 2022-04-05 | 2022-04-12 | 6 | 0 | 6 | [20 empty] | 2022-04-13 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LYNN | 420646 | 1905 | 10 | Solar | 12_29W1 | 2022-03-31 17:26 | 2022-04-01 | 16 | 13 | 3 | 2022-04-26 | 2022-06-24 | 43 | 19 | 24 | [20 empty] | 2022-06-24 |  | 2023-08-03 |  | EXP | [8 empty] | 2022-10-10 | Connected |  | No
National Grid | WESTFORD | 421328 | 1886 | 17.6 | Solar | 14_57L3 | 2022-04-01 08:16 | 2022-04-04 | 1 | 0 | 1 | 2022-04-05 | 2022-04-11 | 5 | 0 | 5 | [20 empty] | 2022-04-12 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | ESSEX | 421351 | 1929 | 25 | Solar | 12_51T2 | 2022-04-01 09:25 | 2022-04-04 | 1 | 0 | 1 | 2022-04-05 | 2022-04-11 | 5 | 0 | 5 | [20 empty] | 2022-04-11 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MEDFORD | 421359 | 2155 | 27 | Solar | 12_17J6 | 2022-04-01 10:11 | 2022-04-04 | 1 | 0 | 1 | 2022-04-05 | 2022-04-08 | 4 | 0 | 4 | [20 empty] | 2022-04-08 |  | 2023-05-04 |  | EXP | [8 empty] | 2022-11-22 | Connected |  | No
National Grid | BELCHERTOWN | 421394 | 1007 | 17.6 | Solar | 09_509L2 | 2022-04-01 11:23 | 2022-04-04 | 1 | 0 | 1 | 2022-04-05 | 2022-04-07 | 3 | 0 | 3 | [20 empty] | 2022-04-11 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTH EASTON | 421426 | 2356 | 15.2 | Solar | 07_92W78 | 2022-04-01 12:45 | 2022-04-04 | 44 | 41 | 3 | 2022-06-07 | 2022-06-24 | 13 | 0 | 13 | [20 empty] | 2022-06-27 | 2022-04-01 15:41 | 2023-07-27 |  | EXP | [8 empty] | 2022-10-19 | Connected |  | Yes
National Grid | METHUEN | 414323 | 1844 | 499 | Solar | 14_63L2 | 2022-04-01 15:41 | 2022-04-04 | 37 | 31 | 6 | [10 empty] | 2022-05-26 | 2022-06-28 | 22 | 0 | 22 | [10 empty] | 2023-06-28 | 2022-04-04 09:11 | 2024-07-28 | Yes | STD | [9 empty] | Construction |  | No
National Grid | SOMERSET | 416604 | 2726 | 250 | Solar | 05_11W82 | 2022-04-04 09:11 | 2022-04-05 | 5 | 0 | 5 | [10 empty] | 2022-04-12 | 2022-05-16 | 24 | 0 | 24 | [10 empty] | 2023-06-28 |  | 2025-03-25 | Yes | STD | [9 empty] | Meter Installation |  | Yes
National Grid | ROCKPORT | 418962 | 1966 | 19.57 | Solar | 12_40J2 | 2022-04-04 09:11 | 2022-04-05 | 1 | 0 | 1 | 2022-04-06 | 2022-04-13 | 6 | 0 | 6 | [20 empty] | 2022-04-13 | 2022-04-04 11:58 | 2023-04-13 |  | EXP | [8 empty] | 2022-08-25 | Connected |  | No
National Grid | BELLINGHAM | 420677 | 2019 | 6 | Solar | 05_344W4 | 2022-04-04 11:58 | 2022-04-05 | 1 | 0 | 1 | 2022-04-06 | 2022-04-13 | 6 | 0 | 6 | [20 empty] | 2022-04-13 | 2022-04-04 15:30 | 2024-01-27 | Yes | EXP |  | 2022-06-11 | 2023-01-26 | 230 | 0 | 230 |  |  | 2023-02-14 | Connected |  | Yes
National Grid | WRENTHAM | 421254 | 2093 | 11.6 | Solar | 05_348W5 | 2022-04-04 15:30 | 2022-04-05 | 1 | 0 | 1 | 2022-04-06 | 2022-04-12 | 5 | 0 | 5 | [20 empty] | 2022-04-13 |  | 2023-05-19 | Yes | EXP | [8 empty] | 2022-12-06 | Connected |  | No
National Grid | BROCKTON | 386273 | 2301 | 15.2 | Solar | 07_98W46 | 2022-04-05 12:36 | 2022-04-06 | 11 | 10 | 1 | 2022-04-21 | 2022-04-22 | 2 | 0 | 2 | [20 empty] | 2022-04-22 |  | 2023-05-24 |  | EXP | [8 empty] | 2022-12-17 | Connected |  | No
National Grid | LEOMINSTER | 420950 | 1453 | 8.99 | Solar | 01_219W2 | 2022-04-06 13:56 | 2022-04-07 | 11 | 10 | 1 | 2022-04-22 | 2022-05-16 | 17 | 0 | 17 | [20 empty] | 2022-06-02 | 2022-04-06 14:05 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MILLBURY | 417754 | 1527 | 7.6 | Solar | 01_328W2 | 2022-04-06 14:05 | 2022-04-07 | 20 | 17 | 3 | 2022-05-06 | 2022-06-07 | 22 | 0 | 22 | [20 empty] | 2022-06-10 | 2022-04-06 19:07 | 2023-09-21 | Yes | EXP | [8 empty] | 2022-09-28 | Connected |  | No
National Grid | MELROSE | 418205 | 2176 | 7.68 | Solar | 12_16W6 | 2022-04-06 19:07 | 2022-04-07 | 8 | 7 | 1 | 2022-04-19 | 2022-04-22 | 4 | 0 | 4 | [20 empty] | 2022-04-25 |  | 2024-04-29 | Yes | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | BOXFORD | 422534 | 1921 | 3.8 | Solar | 14_43L7 | 2022-04-07 08:31 | 2022-04-08 | 1 | 0 | 1 | 2022-04-11 | 2022-04-18 | 6 | 0 | 6 | [20 empty] | 2022-04-18 |  | 2023-04-30 |  | EXP | [8 empty] | 2022-06-30 | Connected |  | No
National Grid | HAVERHILL | 416686 | 1830 | 100 | Solar | 14_31J1 | 2022-04-07 10:20 | 2022-04-08 | 23 | 14 | 9 | 2022-05-11 | 2022-11-03 | 122 | 100 | 22 | [21 empty] | 2022-04-07 11:57 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RANDOLPH | 416744 | 2368 | 5.51 | Solar | 07_97W2 | 2022-04-07 11:57 | 2022-04-08 | 2 | 0 | 2 | 2022-04-12 | 2022-05-06 | 18 | 0 | 18 | [20 empty] | 2022-05-16 | 2022-04-07 14:34 | 2023-12-13 | Yes | EXP |  | 2022-11-04 | 2022-12-12 | 39 | 0 | 39 |  |  | 2023-01-07 | Connected |  | No
National Grid | NAHANT | 422671 | 1908 | 15.2 | Solar | 12_79J2 | 2022-04-07 14:34 | 2022-04-08 | 1 | 0 | 1 | 2022-04-11 | 2022-04-18 | 6 | 0 | 6 | [20 empty] | 2022-04-20 |  | 2024-06-06 | Yes | EXP |  | 2023-05-18 | 2023-06-07 | 21 | 0 | 21 |  |  | 2023-07-10 | Connected |  | No
National Grid | FALL RIVER | 422789 | 2724 | 3.8 | Solar | 05_115W42 | 2022-04-07 17:52 | 2022-08-03 | 2 | 0 | 2 | 2022-08-05 | 2022-09-02 | 21 | 0 | 21 | [20 empty] | 2022-09-09 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | PEMBROKE | 421190 | 2359 | 7.6 | Solar | 07_910W52 | 2022-04-08 09:29 | 2022-04-11 | 44 | 43 | 1 | 2022-06-13 | 2022-07-08 | 17 | 0 | 17 | [20 empty] | 2022-07-08 |  | 2023-08-02 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MONSON | 422881 | 1057 | 20 | Solar | 09_139L1 | 2022-04-08 11:21 | 2022-04-11 | 1 | 0 | 1 | 2022-04-12 | 2022-05-06 | 18 | 0 | 18 | [20 empty] | 2022-05-24 |  | 2023-05-27 |  | EXP | [8 empty] | 2022-10-13 | Connected |  | No
National Grid | MANCHESTER BY THE SEA | 422580 | 1944 | 22.32 | Solar | 12_28L2 | 2022-04-08 11:38 | 2022-04-11 | 9 | 8 | 1 | 2022-04-22 | 2022-05-16 | 17 | 0 | 17 | [20 empty] | 2022-05-16 |  | 2023-05-18 |  | EXP | [8 empty] | 2022-06-17 | Connected |  | No
National Grid | QUINCY | 422902 | 2169 | 19.57 | Solar | 07_1W2 | 2022-04-08 12:09 | 2022-04-11 | 1 | 0 | 1 | 2022-04-12 | 2022-05-13 | 23 | 0 | 23 | [20 empty] | 2022-05-16 | 2022-04-08 16:19 | 2023-06-02 |  | EXP | [8 empty] | 2023-02-28 | Connected |  | No
National Grid | SOUTHBOROUGH | 422790 | 1772 | 17.6 | Solar | 05_317W3 | 2022-04-08 16:19 | 2022-04-11 | 19 | 17 | 2 | 2022-05-06 | 2022-05-24 | 13 | 1 | 12 | [20 empty] | 2022-05-25 | 2022-04-08 17:40 | 2024-03-08 | Yes | EXP |  | 2022-08-11 | 2023-01-11 | 154 | 0 | 154 |  |  | 2023-08-23 | Connected |  | No
National Grid | CHELMSFORD | 418467 | 1824 | 6 | Solar | 14_16L4 | 2022-04-08 17:40 | 2022-04-11 | 1 | 0 | 1 | 2022-04-12 | 2022-04-19 | 5 | 0 | 5 | [20 empty] | 2022-04-21 |  | 2023-09-11 | Yes | EXP |  | 2022-08-09 | 2022-08-29 | 21 | 0 | 21 |  |  | 2022-12-09 | Connected |  | No
National Grid | WESTFORD | 423112 | 1886 | 7.6 | Solar | 14_73L2 | 2022-04-11 08:29 | 2022-04-12 | 1 | 0 | 1 | 2022-04-13 | 2022-04-19 | 4 | 0 | 4 | [20 empty] | 2022-04-21 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FRANKLIN | 423130 | 2038 | 7.6 | Solar | 05_341W2 | 2022-04-11 09:13 | 2022-04-12 | 34 | 33 | 1 | 2022-05-31 | 2022-06-28 | 20 | 0 | 20 | [20 empty] | 2022-07-01 | 2022-04-11 13:51 | 2023-07-08 |  | EXP | [8 empty] | 2022-11-29 | Connected |  | No
National Grid | LAWRENCE | 423252 | 1840 | 160 | Solar | 14_1325 | 2022-04-11 13:51 | 2022-04-12 | 18 | 8 | 10 | 2022-05-09 | 2022-06-28 | 35 | 11 | 24 | [20 empty] | 2022-09-13 |  | 2024-11-05 | Yes | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | WORCESTER | 378510 | 1602 | 3000 | Natural Gas | 01_27W3 | 2022-04-12 00:25 | 2022-04-13 | 23 | 15 | 8 | [10 empty] | 2022-05-17 | 2022-06-15 | 21 | 2 | 19 | [10 empty] | 2024-04-04 | 2022-04-12 11:21 |  |  | STD | [9 empty] | Conditional Approval |  | No
National Grid | WILBRAHAM | 418321 | 1095 | 7.6 | Solar | 09_507L3 | 2022-04-12 11:21 | 2022-04-13 | 2 | 1 | 1 | 2022-04-14 | 2022-04-20 | 4 | 0 | 4 | [20 empty] | 2022-04-21 |  | 2023-08-28 | Yes | EXP |  | 2022-07-29 | 2022-08-04 | 7 | 0 | 7 |  |  | 2022-09-01 | Connected |  | No
National Grid | WESTBOROUGH | 423473 | 1581 | 15.2 | Solar | 05_312W4 | 2022-04-12 11:29 | 2022-04-13 | 1 | 0 | 1 | 2022-04-14 | 2022-04-19 | 3 | 0 | 3 | [20 empty] | 2022-04-21 |  | 2023-05-27 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LOWELL | 409499 | 1854 | 6 | Solar | 14_21L3 | 2022-04-12 12:13 | 2022-04-13 | 63 | 27 | 36 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | GRANBY | 392878 | 1033 | 999 | Solar | 09_527L2 | 2022-04-12 14:14 | 2022-04-13 | 36 | 27 | 9 | [10 empty] | 2022-06-03 | 2022-07-07 | 22 | 4 | 18 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | PEMBROKE | 419321 | 2359 | 499 | Solar | 07_910W51 | 2022-04-13 10:56 | 2022-04-14 | 89 | 26 | 63 | [26 empty] | 2022-04-13 13:49 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTHAMPTON | 419834 | 1060 | 10 | Solar | 09_905W1 | 2022-04-13 13:49 | 2022-04-14 | 1 | 0 | 1 | 2022-04-15 | 2022-04-20 | 3 | 0 | 3 | [20 empty] | 2022-04-21 | 2022-04-13 14:41 | 2023-08-17 | Yes | EXP | [8 empty] | 2022-09-07 | Connected |  | No
National Grid | EVERETT | 419637 | 2149 | 85 | Solar | 12_16W5 | 2022-04-13 14:41 | 2022-04-14 | 70 | 62 | 8 | 2022-07-27 | 2022-08-29 | 24 | 0 | 24 | [20 empty] | 2022-09-13 |  | 2023-01-18 |  | EXP | [8 empty] | 2023-02-10 | Connected |  | No
National Grid | DRACUT | 423047 | 1826 | 150 | Solar | 14_75L3 | 2022-04-14 05:15 | 2022-04-15 | 27 | 19 | 8 | 2022-05-25 | 2022-08-05 | 50 | 27 | 23 | [20 empty] | 2022-10-20 | 2022-04-14 10:36 | 2023-11-27 |  | EXP | [8 empty] | 2023-10-18 | Connected |  | No
National Grid | WESTFORD | 424028 | 1886 | 15.2 | Solar | 14_57L2 | 2022-04-14 10:36 | 2022-04-15 | 1 | 0 | 1 | 2022-04-19 | 2022-04-20 | 2 | 0 | 2 | [20 empty] | 2022-04-21 |  | 2024-11-19 | Yes | EXP |  | 2023-06-09 | 2024-03-11 | 277 | 3 | 274 |  |  |  | Completion Documents |  | Yes
National Grid | LANCASTER | 422557 | 1523 | 15.2 | Solar | 01_225W1 | 2022-04-14 13:16 | 2022-04-15 | 4 | 3 | 1 | 2022-04-21 | 2022-04-22 | 2 | 0 | 2 | [20 empty] | 2022-04-22 | 2022-04-14 13:41 | 2023-05-01 |  | EXP | [8 empty] | 2022-07-07 | Connected |  | No
National Grid | NANTUCKET | 422444 | 2554 | 49.68 | Solar | 04_101L2 | 2022-04-14 13:41 | 2022-04-15 | 101 | 91 | 10 | [10 empty] | 2022-09-12 | 2022-10-05 | 18 | 0 | 18 | [10 empty] | 2023-03-07 |  | 2024-01-11 | Yes | STD |  | 2023-07-21 | 2023-09-21 | 63 | 0 | 63 |  |  | 2023-11-17 | Connected |  | No
National Grid | WILLIAMSBURG | 418955 | 1039 | 3900 | Solar | 09_909W3 | 2022-04-14 13:43 | 2022-04-15 | 34 | 25 | 9 | [10 empty] | 2022-06-03 | 2022-07-01 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | SALISBURY | 409895 | 1952 | 7.6 | Solar | 14_7L1 | 2022-04-14 15:20 | 2022-04-15 | 5 | 4 | 1 | 2022-04-22 | 2022-05-05 | 10 | 0 | 10 | [20 empty] | 2022-05-05 | 2022-04-14 16:36 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 418368 | 1605 | 9.8 | Solar | 01_24W2 | 2022-04-14 16:36 | 2022-04-15 | 1 | 0 | 1 | 2022-04-19 | 2022-05-06 | 14 | 0 | 14 | [20 empty] | 2022-06-07 |  | 2023-09-05 | Yes | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 424339 | 1602 | 40 | Solar |  | 2022-04-15 11:21 | 2022-04-19 | 3 | 0 | 3 | [26 empty] | 2022-04-15 13:25 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 424314 | 1602 | 3.8 | Solar | 01_23W3 | 2022-04-15 13:25 | 2022-05-27 | 1 | 0 | 1 | 2022-05-31 | 2022-06-21 | 15 | 0 | 15 | [20 empty] | 2022-06-22 | 2022-04-19 09:03 | 2023-09-09 | Yes | EXP |  | 2022-08-25 | 2022-09-07 | 14 | 0 | 14 |  |  | 2022-09-12 | Connected |  | No
National Grid | BILLERICA | 406505 | 1821 | 8.027 | Solar | 14_18L3 | 2022-04-19 09:03 | 2022-04-20 | 6 | 6 | 0 | 2022-04-28 | 2022-05-18 | 15 | 0 | 15 | [20 empty] | 2022-05-20 |  | 2023-11-19 | Yes | EXP | [8 empty] | 2022-12-12 | Connected |  | No
National Grid | REHOBOTH | 424932 | 2769 | 7.6 | Solar | 05_8L4 | 2022-04-19 12:37 | 2022-04-20 | 86 | 69 | 17 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | HANOVER | 424728 | 2339 | 15.2 | Solar | 07_95W5 | 2022-04-19 14:19 | 2022-04-20 | 6 | 4 | 2 | 2022-04-27 | 2022-05-17 | 15 | 0 | 15 | [20 empty] | 2022-05-25 |  | 2023-06-02 |  | EXP | [8 empty] | 2022-10-13 | Connected |  | No
National Grid | PEPPERELL | 417558 | 1463 | 4999 | Solar | 01_226L1 | 2022-04-20 11:41 | 2022-04-21 | 43 | 34 | 9 | [10 empty] | 2022-06-22 | 2022-07-20 | 20 | 0 | 20 | [11 empty] | 2022-04-20 12:16 |  |  | STD | [9 empty] | Conditional Approval |  | No
National Grid | SAUGUS | 422479 | 1906 | 9.57 | Solar | 12_16W1 | 2022-04-20 12:16 | 2022-04-21 | 1 | 0 | 1 | 2022-04-22 | 2022-04-27 | 4 | 0 | 4 | [20 empty] | 2022-04-29 | 2022-04-20 16:24 | 2023-10-20 | Yes | EXP |  | 2022-09-14 | 2022-10-14 | 31 | 0 | 31 |  |  | 2023-02-15 | Connected |  | No
National Grid | STURBRIDGE | 418661 | 1566 | 8.12 | Solar | 01_415L1 | 2022-04-20 16:24 | 2022-04-21 | 1 | 0 | 1 | 2022-04-22 | 2022-05-16 | 17 | 0 | 17 | [20 empty] | 2022-05-31 |  | 2024-04-12 | Yes | EXP |  | 2023-04-06 | 2023-04-12 | 7 | 0 | 7 |  |  | 2023-05-15 | Connected |  | No
National Grid | MANCHESTER | 425303 | 1944 | 15.2 | Solar | 12_51T1 | 2022-04-20 16:30 | 2022-04-21 | 15 | 14 | 1 | 2022-05-12 | 2022-05-27 | 12 | 0 | 12 | [20 empty] | 2022-05-27 |  | 2023-06-30 |  | EXP | [8 empty] | 2023-06-02 | Connected |  | No
National Grid | AMESBURY | 425281 | 1913 | 133.2 | Solar | 14_5J14 | 2022-04-20 16:47 | 2022-04-21 | 10 | 0 | 10 | [10 empty] | 2022-05-05 | 2022-06-03 | 21 | 3 | 18 | [10 empty] | 2022-11-17 | 2022-04-20 17:32 |  |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 423774 | 1604 | 67.3 | Solar | 01_24W2 | 2022-04-20 17:32 | 2022-04-21 | 10 | 1 | 9 | 2022-05-05 | 2022-06-08 | 24 | 0 | 24 | [20 empty] | 2022-07-22 | 2022-04-21 08:50 | 2023-11-08 | Yes | EXP | [8 empty] | 2023-10-20 | Connected |  | No
National Grid | RANDOLPH | 424661 | 2368 | 11.4 | Solar | 07_5W3 | 2022-04-21 08:50 | 2022-05-17 | 4 | 1 | 3 | 2022-05-23 | 2022-07-05 | 28 | 8 | 20 | [20 empty] | 2022-07-19 | 2022-04-21 09:10 | 2024-08-16 | Yes | EXP |  | 2023-06-09 | 2023-08-11 | 64 | 0 | 64 |  |  | 2023-09-05 | Connected |  | No
National Grid | GRAFTON | 425276 | 1519 | 20 | Solar | 05_320W3 | 2022-04-21 09:10 | 2022-04-22 | 7 | 6 | 1 | 2022-05-02 | 2022-06-22 | 36 | 22 | 14 | [20 empty] | 2022-06-28 |  | 2024-01-11 | Yes | EXP |  | 2023-12-29 | 2024-01-05 | 8 | 0 | 8 |  |  | 2024-01-05 | Connected |  | No
National Grid | BROCKTON | 425308 | 2302 | 5.76 | Solar | 07_911W77 | 2022-04-21 09:12 | 2022-05-12 | 3 | 0 | 3 | 2022-05-17 | 2022-06-07 | 15 | 0 | 15 | [20 empty] | 2022-06-09 | 2022-04-21 12:13 | 2023-06-14 |  | EXP | [8 empty] | 2022-12-16 | Connected |  | No
National Grid | UXBRIDGE | 425379 | 1569 | 10 | Solar | 05_321W2 | 2022-04-21 12:13 | 2022-05-26 | 3 | 0 | 3 | 2022-06-01 | 2022-06-21 | 14 | 0 | 14 | [20 empty] | 2022-06-22 | 2022-04-21 12:20 | 2023-11-02 | Yes | EXP |  | 2022-09-27 | 2022-10-27 | 31 | 0 | 31 |  |  | 2022-11-30 | Connected |  | No
National Grid | FALL RIVER | 424613 | 2720 | 10 | Solar | 05_28W51 | 2022-04-21 12:20 | 2022-04-22 | 4 | 0 | 4 | 2022-04-28 | 2022-05-10 | 9 | 0 | 9 | [20 empty] | 2022-05-16 |  | 2023-09-20 | Yes | EXP |  | 2022-08-19 | 2022-09-19 | 32 | 0 | 32 |  |  | 2022-09-27 | Connected |  | Yes
National Grid | SHARON | 420576 | 2067 | 15.2 | Solar | 07_913W43 | 2022-04-21 13:34 | 2022-04-22 | 1 | 0 | 1 | 2022-04-25 | 2022-04-28 | 4 | 0 | 4 | [20 empty] | 2022-05-02 |  | 2024-06-01 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | STOUGHTON | 414774 | 2072 | 15.2 | Solar | 07_913W43 | 2022-04-22 04:06 | 2022-04-25 | 3 | 1 | 2 | 2022-04-27 | 2022-06-07 | 29 | 13 | 16 | [20 empty] | 2022-06-08 |  | 2024-08-10 |  | EXP | [8 empty] | 2024-03-05 | Connected |  | No
National Grid | MARLBOROUGH | 424366 | 1752 | 25.2 | Solar | 05_311W2 | 2022-04-22 04:10 | 2022-04-25 | 2 | 1 | 1 | 2022-04-26 | 2022-05-03 | 6 | 0 | 6 | [20 empty] | 2022-05-04 |  | 2023-08-02 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BROOKFIELD | 424701 | 1506 | 3.8 | Solar | 01_525L2 | 2022-04-22 13:20 | 2022-04-25 | 5 | 3 | 2 | 2022-05-02 | 2022-05-19 | 14 | 0 | 14 | [20 empty] | 2022-05-24 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LANCASTER | 425604 | 1523 | 15.2 | Solar | 01_216W3 | 2022-04-22 15:46 | 2022-04-25 | 3 | 2 | 1 | 2022-04-27 | 2022-05-17 | 15 | 0 | 15 | [20 empty] | 2022-05-17 |  | 2023-06-16 |  | EXP | [8 empty] | 2022-08-09 | Connected |  | No
National Grid | BROCKTON | 414097 | 2302 | 7.68 | Solar | 07_911W77 | 2022-04-22 17:21 | 2022-04-25 | 1 | 0 | 1 | 2022-04-26 | 2022-05-25 | 22 | 0 | 22 | [20 empty] | 2022-05-26 | 2022-04-24 22:20 | 2023-06-06 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ANDOVER | 424059 | 1810 | 9.772 | Solar | 14_50L1 | 2022-04-24 22:20 | 2022-04-25 | 10 | 9 | 1 | 2022-05-06 | 2022-06-07 | 22 | 10 | 12 | [20 empty] | 2022-06-07 |  | 2023-08-11 | Yes | EXP |  | 2022-07-07 | 2022-08-11 | 36 | 0 | 36 |  |  | 2022-10-21 | Connected |  | No
National Grid | BEVERLY | 426053 | 1915 | 22.272 | Solar | 12_51T1 | 2022-04-25 09:01 | 2022-04-26 | 30 | 26 | 4 | 2022-06-08 | 2022-07-22 | 31 | 11 | 20 | [20 empty] | 2022-07-26 |  | 2023-08-11 |  | EXP | [8 empty] | 2022-09-01 | Connected |  | No
National Grid | MALDEN | 426175 | 2148 | 7.6 | Solar | 12_16J1 | 2022-04-25 11:48 | 2022-04-26 | 0 | 0 | 0 | 2022-04-26 | 2022-08-04 | 70 | 52 | 18 | [21 empty] | 2022-04-25 14:44 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTFORD | 392677 | 1886 | 7.6 | Solar | 14_73L2 | 2022-04-25 14:44 | 2022-04-26 | 36 | 35 | 1 | 2022-06-16 | 2022-07-22 | 25 | 0 | 25 | [20 empty] | 2022-07-22 | 2022-04-25 16:23 | 2023-08-20 | Yes | EXP |  | 2022-12-22 | 2023-02-17 | 58 | 0 | 58 |  |  | 2023-05-11 | Connected |  | No
National Grid | ADAMS | 426295 | 1220 | 15.2 | Solar | 09_1021W1 | 2022-04-25 16:23 | 2022-04-26 | 1 | 0 | 1 | 2022-04-27 | 2022-05-23 | 19 | 0 | 19 | [20 empty] | 2022-05-24 |  | 2023-09-21 | Yes | EXP |  | 2022-08-31 | 2022-09-21 | 22 | 0 | 22 |  |  | 2022-10-12 | Connected |  | No
National Grid | CHARLTON | 377511 | 1507 | 999 | Solar | 01_415L1 | 2022-04-26 09:56 | 2022-04-27 | 16 | 7 | 9 | [10 empty] | 2022-05-19 | 2022-06-15 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | ANDOVER | 412234 | 1810 | 1125 | Battery Add-On | 14_8T1 | 2022-04-26 10:12 | 2022-04-27 | 24 | 14 | 10 | [10 empty] | 2022-05-31 | 2022-06-24 | 18 | 0 | 18 | [11 empty] | 2022-04-26 12:01 |  |  | STD | [9 empty] | Group Study |  | No
National Grid | LEOMINSTER | 426071 | 1453 | 15.2 | Solar | 01_207W3 | 2022-04-26 12:01 | 2022-04-27 | 1 | 0 | 1 | 2022-04-28 | 2022-05-18 | 15 | 0 | 15 | [20 empty] | 2022-05-25 |  | 2023-10-20 | Yes | EXP |  | 2022-09-30 | 2022-10-18 | 19 | 0 | 19 |  |  | 2023-05-04 | Connected |  | Yes
National Grid | BEVERLY | 396930 | 1915 | 1000 | Solar | 12_2365 | 2022-04-27 09:08 | 2022-04-28 | 144 | 136 | 8 | [29 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | PEPPERELL | 426686 | 1463 | 20 | Solar | 01_226L2 | 2022-04-27 10:22 | 2022-04-28 | 58 | 49 | 9 | 2022-07-22 | 2022-08-17 | 19 | 0 | 19 | [20 empty] | 2022-08-24 |  | 2023-09-25 |  | EXP | [8 empty] | 2022-10-05 | Connected |  | No
National Grid | WORCESTER | 426710 | 1605 | 15.2 | Solar | 01_24W2 | 2022-04-27 10:54 | 2022-04-28 | 2 | 0 | 2 | 2022-05-02 | 2022-05-20 | 15 | 0 | 15 | [20 empty] | 2022-06-02 |  | 2023-08-12 |  | EXP | [8 empty] | 2022-12-15 | Connected |  | No
National Grid | WORCESTER | 396684 | 1606 | 4990 | Other | 01_24W5 | 2022-04-28 09:34 | 2022-04-29 | 16 | 7 | 9 | [10 empty] | 2022-05-20 | 2022-06-16 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 423224 | 1507 | 13.12 | Solar | 01_415L2 | 2022-04-28 11:33 | 2022-04-29 | 2 | 1 | 1 | 2022-05-03 | 2022-05-19 | 13 | 0 | 13 | [20 empty] | 2022-05-20 | 2022-04-28 13:24 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTFORD | 427118 | 1886 | 15.2 | Solar | 14_58L3 | 2022-04-28 13:24 | 2022-04-29 | 29 | 29 | 0 | 2022-06-10 | 2022-06-28 | 12 | 0 | 12 | [20 empty] | 2022-06-28 |  | 2024-01-30 | Yes | EXP |  | 2023-01-07 | 2023-01-30 | 24 | 0 | 24 |  |  | 2023-04-27 | Connected |  | No
National Grid | OXFORD | 419196 | 1540 | 9.28 | Solar | 01_406L1 | 2022-04-28 14:13 | 2022-04-29 | 303 | 21 | 282 | [26 empty] | 2022-04-28 15:24 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEEDS | 426237 | 1053 | 7.6 | Solar | 09_909W3 | 2022-04-28 15:24 | 2022-04-29 | 1 | 0 | 1 | 2022-05-02 | 2022-05-24 | 16 | 0 | 16 | [20 empty] | 2022-05-27 | 2022-04-28 15:44 | 2023-08-11 | Yes | EXP | [8 empty] | 2022-08-30 | Connected |  | Yes
National Grid | LAWRENCE | 426133 | 1843 | 4.06 | Solar | 14_61L2 | 2022-04-28 15:44 | 2022-04-29 | 5 | 2 | 3 | 2022-05-06 | 2022-06-03 | 20 | 0 | 20 | [20 empty] | 2022-06-08 |  | 2024-01-03 | Yes | EXP |  | 2022-12-22 | 2023-01-03 | 13 | 0 | 13 |  |  | 2023-01-07 | Connected |  | No
National Grid | SEEKONK | 418863 | 2771 | 10 | Solar | 05_7L1 | 2022-04-28 18:52 | 2022-04-29 | 1 | 0 | 1 | 2022-05-02 | 2022-07-12 | 49 | 25 | 24 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RUTLAND | 417891 | 1543 | 6.528 | Solar | 01_55W1 | 2022-04-29 09:03 | 2022-05-02 | 0 | 0 | 0 | 2022-05-02 | 2022-05-18 | 13 | 0 | 13 | [20 empty] | 2022-05-18 |  | 2023-05-19 |  | EXP | [8 empty] | 2022-12-28 | Connected |  | No
National Grid | WHITMAN | 427434 | 2382 | 20 | Solar | 07_93W43 | 2022-04-29 14:38 | 2022-05-02 | 54 | 51 | 3 | 2022-07-20 | 2022-08-09 | 15 | 0 | 15 | [20 empty] | 2022-08-09 |  | 2023-08-17 |  | EXP | [8 empty] | 2022-09-13 | Connected |  | No
National Grid | UPTON | 427132 | 1568 | 5.376 | Solar | 05_335W3 | 2022-04-29 19:25 | 2022-05-02 | 5 | 2 | 3 | 2022-05-06 | 2022-05-26 | 15 | 0 | 15 | [20 empty] | 2022-06-02 |  | 2023-06-07 |  | EXP | [8 empty] | 2023-02-16 | Connected |  | No
National Grid | RANDOLPH | 427346 | 2368 | 6 | Solar | 07_5W3 | 2022-05-02 11:20 | 2022-05-17 | 1 | 0 | 1 | 2022-05-18 | 2022-06-09 | 16 | 0 | 16 | [20 empty] | 2022-06-10 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HANOVER | 413057 | 2339 | 51.9 | Solar | 07_95W1 | 2022-05-02 11:57 | 2022-05-03 | 26 | 19 | 7 | [10 empty] | 2022-06-09 | 2022-08-10 | 42 | 24 | 18 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | BLACKSTONE | 424141 | 1504 | 9.984 | Solar | 05_332W1 | 2022-05-02 16:21 | 2022-05-03 | 8 | 7 | 1 | 2022-05-12 | 2022-06-10 | 21 | 0 | 21 | [20 empty] | 2022-06-10 |  | 2023-07-28 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 427946 | 1603 | 11.4 | Solar | 01_7J387 | 2022-05-03 08:01 | 2022-05-04 | 0 | 0 | 0 | 2022-05-04 | 2022-06-07 | 24 | 0 | 24 | [20 empty] | 2022-06-08 |  | 2023-07-15 |  | EXP | [8 empty] | 2022-10-17 | Connected |  | No
National Grid | FRANKLIN | 427984 | 2038 | 15.2 | Solar | 05_344W5 | 2022-05-03 09:57 | 2022-05-04 | 1 | 1 | 0 | 2022-05-05 | 2022-05-19 | 11 | 0 | 11 | [20 empty] | 2022-05-20 |  | 2023-09-01 |  | EXP | [8 empty] | 2022-12-01 | Connected |  | No
National Grid | LEOMINSTER | 427452 | 1453 | 19 | Solar | 01_207W6 | 2022-05-03 14:23 | 2022-05-04 | 38 | 35 | 3 | 2022-06-29 | 2023-11-13 | 343 | 325 | 18 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EAST LONGMEADOW | 428276 | 1028 | 7.6 | Solar | 09_508L1 | 2022-05-04 08:38 | 2022-05-05 | 1 | 0 | 1 | 2022-05-06 | 2022-05-23 | 12 | 0 | 12 | [20 empty] | 2022-05-24 |  | 2023-05-25 |  | EXP | [8 empty] | 2022-12-28 | Connected |  | No
National Grid | LYNN | 424060 | 1902 | 4.06 | Solar | 12_21J21 | 2022-05-04 09:02 | 2022-05-05 | 3 | 2 | 1 | 2022-05-10 | 2022-05-27 | 14 | 0 | 14 | [20 empty] | 2022-05-31 | 2022-05-04 09:14 | 2023-06-26 |  | EXP | [8 empty] | 2022-08-11 | Connected |  | No
National Grid | SOUTHBRIDGE | 424618 | 1550 | 7.54 | Solar | 01_413L3 | 2022-05-04 09:14 | 2022-05-05 | 4 | 1 | 3 | 2022-05-10 | 2022-06-07 | 20 | 0 | 20 | [20 empty] | 2022-06-10 |  | 2024-01-10 | Yes | EXP |  | 2022-12-28 | 2023-01-10 | 14 | 0 | 14 |  |  | 2023-01-13 | Connected |  | No
National Grid | LYNN | 423857 | 1902 | 3 | Solar | 12_12J903 | 2022-05-04 09:48 | 2022-05-23 | 24 | 22 | 2 | 2022-06-27 | 2022-07-28 | 23 | 0 | 23 | [20 empty] | 2022-09-22 | 2022-05-04 09:52 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | OXFORD | 428180 | 1540 | 10 | Solar | 01_406L3 | 2022-05-04 09:52 | 2022-05-23 | 15 | 13 | 2 | 2022-06-13 | 2022-07-22 | 27 | 5 | 22 | [20 empty] | 2022-07-26 | 2022-05-04 10:38 | 2024-04-03 | Yes | EXP |  | 2023-03-09 | 2023-04-03 | 26 | 0 | 26 |  |  | 2023-04-12 | Connected |  | Yes
National Grid | WESTFORD | 421774 | 1886 | 15.2 | Solar | 14_58L1 | 2022-05-04 10:38 | 2022-05-05 | 0 | 0 | 0 | 2022-05-05 | 2022-06-24 | 36 | 25 | 11 | [20 empty] | 2022-06-28 |  | 2023-10-09 | Yes | EXP |  | 2022-08-30 | 2022-09-24 | 26 | 0 | 26 |  |  | 2022-11-24 | Connected |  | No
National Grid | PALMER | 428299 | 1069 | 15.2 | Solar | 09_523L4 | 2022-05-04 10:59 | 2022-05-05 | 6 | 6 | 0 | 2022-05-13 | 2022-06-07 | 17 | 0 | 17 | [20 empty] | 2022-06-09 |  | 2023-06-29 |  | EXP | [8 empty] | 2023-01-17 | Connected |  | No
National Grid | NORTH ANDOVER | 421208 | 1845 | 15.2 | Solar | 14_56L2 | 2022-05-04 12:20 | 2022-05-05 | 4 | 0 | 4 | 2022-05-11 | 2022-05-26 | 12 | 0 | 12 | [20 empty] | 2022-05-31 | 2022-05-04 12:51 | 2023-06-16 |  | EXP | [8 empty] | 2023-01-10 | Connected |  | Yes
National Grid | HARVARD | 428357 | 1451 | 9.28 | Solar | 01_225W1 | 2022-05-04 12:51 | 2022-05-05 | 1 | 1 | 0 | 2022-05-06 | 2022-05-27 | 16 | 4 | 12 | [20 empty] | 2022-05-27 | 2022-05-04 13:01 | 2023-11-10 | Yes | EXP |  | 2022-09-30 | 2022-11-09 | 41 | 0 | 41 |  |  | 2023-06-14 | Connected |  | No
National Grid | ANDOVER | 406250 | 1810 | 10 | Solar | 14_50L3 | 2022-05-04 13:01 | 2022-05-05 | 22 | 19 | 3 | 2022-06-07 | 2022-06-30 | 17 | 0 | 17 | [20 empty] | 2022-07-25 | 2022-05-04 15:22 | 2024-05-01 | Yes | EXP | [8 empty] | 2023-06-05 | Connected |  | Yes
National Grid | BILLERICA | 425627 | 1821 | 9.8 | Solar | 14_70L5 | 2022-05-04 15:22 | 2022-05-05 | 3 | 1 | 2 | 2022-05-10 | 2022-06-10 | 22 | 0 | 22 | [20 empty] | 2022-06-13 |  | 2024-01-06 | Yes | EXP | [8 empty] | 2023-01-27 | Connected |  | Yes
National Grid | SOUTHBOROUGH | 428460 | 1772 | 7.6 | Solar | 05_317W4 | 2022-05-04 15:56 | 2022-05-05 | 7 | 6 | 1 | 2022-05-13 | 2022-06-07 | 17 | 0 | 17 | [20 empty] | 2022-06-09 |  | 2023-08-12 |  | EXP | [8 empty] | 2022-10-04 | Connected |  | No
National Grid | AYER | 424633 | 1432 | 15.2 | Solar | 01_201W3 | 2022-05-04 17:34 | 2022-05-05 | 6 | 5 | 1 | 2022-05-13 | 2022-05-27 | 11 | 0 | 11 | [20 empty] | 2022-05-31 |  | 2023-06-25 |  | EXP | [8 empty] | 2023-03-21 | Connected |  | No
National Grid | ROCKLAND | 421780 | 2370 | 9.45 | Solar | 07_93W40 | 2022-05-05 09:51 | 2022-05-06 | 1 | 1 | 0 | 2022-05-10 | 2022-05-23 | 10 | 0 | 10 | [20 empty] | 2022-05-23 |  | 2023-07-17 |  | EXP | [8 empty] | 2023-05-18 | Connected |  | No
National Grid | WEYMOUTH | 428516 | 2190 | 7.6 | Solar | 07_8W1 | 2022-05-05 09:52 | 2022-05-09 | 15 | 14 | 1 | 2022-05-27 | 2022-06-21 | 16 | 0 | 16 | [20 empty] | 2022-06-23 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 425866 | 1602 | 9.074 | Solar | 01_23W1 | 2022-05-05 10:39 | 2022-05-06 | 2 | 0 | 2 | 2022-05-10 | 2022-05-30 | 15 | 0 | 15 | [20 empty] | 2022-06-02 |  | 2023-06-06 |  | EXP | [8 empty] | 2023-03-09 | Connected |  | No
National Grid | WESTFORD | 424042 | 1886 | 10 | Solar | 14_73L2 | 2022-05-05 12:27 | 2022-05-06 | 14 | 14 | 0 | 2022-05-26 | 2022-06-24 | 20 | 0 | 20 | [20 empty] | 2022-06-28 |  | 2023-07-06 |  | EXP | [8 empty] | 2022-09-29 | Connected |  | No
National Grid | WEST STOCKBRIDGE | 428708 | 1266 | 11.4 | Solar | 09_1109W3 | 2022-05-05 13:49 | 2022-05-06 | 2 | 0 | 2 | 2022-05-10 | 2022-05-30 | 14 | 0 | 14 | [20 empty] | 2022-06-01 |  | 2023-07-12 |  | EXP | [8 empty] | 2022-07-27 | Connected |  | No
National Grid | WEYMOUTH | 426693 | 2189 | 15.2 | Solar | 07_12W6 | 2022-05-05 14:28 | 2022-05-06 | 1 | 0 | 1 | 2022-05-09 | 2022-06-07 | 21 | 0 | 21 | [20 empty] | 2022-06-09 | 2022-05-05 20:29 | 2023-08-21 |  | EXP | [8 empty] | 2023-03-23 | Connected |  | No
National Grid | ATTLEBORO | 427776 | 2703 | 8.064 | Solar | 05_9L4 | 2022-05-05 20:29 | 2022-05-06 | 8 | 7 | 1 | 2022-05-17 | 2022-06-16 | 22 | 0 | 22 | [20 empty] | 2022-06-16 | 2022-05-09 10:21 | 2023-09-06 | Yes | EXP |  | 2022-08-06 | 2022-09-03 | 29 | 0 | 29 |  |  | 2023-01-10 | Connected |  | No
National Grid | DRACUT | 425044 | 1826 | 10 | Solar | 14_78L1 | 2022-05-09 10:21 | 2022-05-10 | 0 | 0 | 0 | 2022-05-10 | 2022-06-06 | 19 | 0 | 19 | [20 empty] | 2022-06-08 | 2022-05-09 12:57 | 2023-07-20 | Yes | EXP |  | 2022-07-16 | 2022-07-18 | 3 | 0 | 3 |  |  | 2023-05-01 | Connected |  | Yes
National Grid | AMESBURY | 427409 | 1913 | 60 | Solar | 14_7L4 | 2022-05-09 12:57 | 2022-05-10 | 8 | 0 | 8 | 2022-05-20 | 2022-07-12 | 35 | 17 | 18 | [20 empty] | 2022-07-21 |  | 2023-09-22 | Yes | EXP | [8 empty] | 2022-11-30 | Connected |  | No
National Grid | NORTON | 414390 | 2766 | 14270 | Other | 05_8L2 | 2022-05-09 13:55 | 2022-05-10 | 30 | 22 | 8 | [10 empty] | 2022-06-22 | 2022-07-20 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | RANDOLPH | 429334 | 2368 | 15.2 | Solar | 07_97W2 | 2022-05-09 14:45 | 2022-05-10 | 3 | 3 | 0 | 2022-05-16 | 2022-06-13 | 20 | 0 | 20 | [20 empty] | 2022-06-13 |  | 2023-06-28 |  | EXP | [8 empty] | 2022-11-15 | Connected |  | No
National Grid | DRACUT | 428394 | 1826 | 5.8 | Solar | 14_78L1 | 2022-05-09 17:24 | 2022-05-10 | 2 | 0 | 2 | 2022-05-12 | 2022-05-30 | 13 | 0 | 13 | [20 empty] | 2022-06-03 |  | 2023-07-10 |  | EXP | [8 empty] | 2022-08-30 | Connected |  | No
National Grid | MARLBOROUGH | 421735 | 1752 | 12 | Solar | 05_311W2 | 2022-05-10 09:04 | 2022-05-11 | 3 | 2 | 1 | 2022-05-13 | 2022-07-08 | 38 | 18 | 20 | [20 empty] | 2022-07-11 |  | 2023-07-19 |  | EXP | [8 empty] | 2022-10-20 | Connected |  | No
National Grid | TYNGSBORO | 407710 | 1879 | 7.678 | Solar | 01_210L1 | 2022-05-10 11:17 | 2022-05-11 | 28 | 25 | 3 | 2022-06-22 | 2022-07-21 | 21 | 0 | 21 | [20 empty] | 2022-08-03 |  | 2023-08-10 |  | EXP | [8 empty] | 2022-09-29 | Connected |  | No
National Grid | PEMBROKE | 429786 | 2359 | 7.6 | Solar | 07_910W51 | 2022-05-10 18:31 | 2022-05-11 | 1 | 0 | 1 | 2022-05-12 | 2022-05-30 | 13 | 0 | 13 | [20 empty] | 2022-06-02 |  | 2023-06-21 |  | EXP | [8 empty] | 2023-01-13 | Connected |  | No
National Grid | LEOMINSTER | 429601 | 1453 | 15.2 | Solar | 01_219W4 | 2022-05-11 08:07 | 2022-05-12 | 4 | 3 | 1 | 2022-05-17 | 2022-06-09 | 17 | 0 | 17 | [20 empty] | 2022-06-16 |  | 2023-07-07 |  | EXP | [8 empty] | 2022-09-02 | Connected |  | No
National Grid | BERLIN | 429894 | 1503 | 15.2 | Solar | 05_318W3 | 2022-05-11 09:56 | 2022-05-12 | 1 | 0 | 1 | 2022-05-13 | 2022-06-07 | 17 | 0 | 17 | [20 empty] | 2022-06-09 |  | 2023-08-29 |  | EXP | [8 empty] | 2022-09-27 | Connected |  | No
National Grid | BOLTON | 424363 | 1740 | 7.6 | Solar | 01_225W1 | 2022-05-11 09:59 | 2022-05-12 | 6 | 5 | 1 | 2022-05-19 | 2022-06-16 | 20 | 0 | 20 | [20 empty] | 2022-06-16 |  | 2023-08-30 |  | EXP | [8 empty] | 2022-10-27 | Connected |  | No
National Grid | STURBRIDGE | 429910 | 1566 | 15.2 | Solar | 01_415L1 | 2022-05-11 10:40 | 2022-05-12 | 5 | 4 | 1 | 2022-05-18 | 2022-06-15 | 20 | 0 | 20 | [20 empty] | 2022-06-16 |  | 2023-06-28 |  | EXP | [8 empty] | 2022-08-10 | Connected |  | No
National Grid | METHUEN | 426328 | 1844 | 5.51 | Solar | 14_5J44 | 2022-05-11 13:45 | 2022-05-12 | 10 | 7 | 3 | 2022-05-25 | 2022-06-24 | 21 | 0 | 21 | [20 empty] | 2022-06-28 | 2022-05-11 14:15 | 2023-07-16 |  | EXP | [8 empty] | 2022-10-08 | Connected |  | No
National Grid | WEST NEWBURY | 418217 | 1985 | 9.772 | Solar | 14_34M1 | 2022-05-11 14:15 | 2022-05-12 | 1 | 0 | 1 | 2022-05-13 | 2022-06-13 | 21 | 0 | 21 | [20 empty] | 2022-06-14 |  | 2023-08-23 | Yes | EXP |  | 2022-10-06 | 2022-11-03 | 29 | 0 | 29 |  |  | 2022-11-10 | Connected |  | No
National Grid | TEWKSBURY | 401363 | 1876 | 4999.2 | Battery Add-On | 14_70L1 | 2022-05-11 15:43 | 2022-05-12 | 26 | 17 | 9 | [10 empty] | 2022-06-21 | 2022-07-20 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | WRENTHAM | 422055 | 2093 | 4999.2 | Battery Add-On | 05_3337W1 | 2022-05-11 15:47 | 2022-05-12 | 18 | 10 | 8 | [10 empty] | 2022-06-07 | 2022-07-06 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | ATTLEBORO | 411356 | 2703 | 4999.2 | Battery Add-On | 05_9L5 | 2022-05-11 15:49 | 2022-05-12 | 38 | 29 | 9 | [10 empty] | 2022-07-08 | 2022-08-04 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 424441 | 1602 | 7.6 | Solar | 01_1J363 | 2022-05-11 15:51 | 2022-05-12 | 3 | 0 | 3 | 2022-05-17 | 2022-06-09 | 17 | 0 | 17 | [20 empty] | 2022-07-15 |  | 2023-12-23 |  | EXP | [8 empty] | 2023-11-22 | Connected |  | No
National Grid | WORCESTER | 396605 | 1606 | 4000 | Other | 01_24W4 | 2022-05-11 20:26 | 2022-05-12 | 13 | 5 | 8 | [10 empty] | 2022-05-31 | 2022-06-22 | 16 | 0 | 16 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | LEOMINSTER | 409760 | 1453 | 12 | Solar | 01_207W6 | 2022-05-12 10:40 | 2022-05-13 | 3 | 1 | 2 | 2022-05-18 | 2022-06-09 | 16 | 0 | 16 | [20 empty] | 2022-07-08 | 2022-05-13 09:07 | 2023-10-03 |  | EXP | [8 empty] | 2022-11-04 | Connected |  | No
National Grid | LAWRENCE | 426525 | 1843 | 10 | Solar | 14_61L3 | 2022-05-13 09:07 | 2022-05-16 | 2 | 0 | 2 | 2022-05-18 | 2022-06-09 | 16 | 0 | 16 | [20 empty] | 2022-06-17 | 2022-05-13 10:13 | 2023-10-19 | Yes | EXP |  | 2022-08-16 | 2022-10-19 | 65 | 0 | 65 |  |  | 2022-11-02 | Connected |  | No
National Grid | TEWKSBURY | 424685 | 1876 | 6.09 | Solar | 14_3L2 | 2022-05-13 10:13 | 2022-05-16 | 1 | 0 | 1 | 2022-05-17 | 2022-06-02 | 12 | 0 | 12 | [20 empty] | 2022-06-03 |  | 2024-08-19 | Yes | EXP |  | 2023-04-16 | 2023-05-03 | 18 | 0 | 18 |  |  | 2023-10-12 | Connected |  | No
National Grid | WINCHENDON | 427507 | 1475 | 13 | Solar | 01_612W1 | 2022-05-13 13:00 | 2022-05-16 | 0 | 0 | 0 | 2022-05-16 | 2022-08-29 | 74 | 55 | 19 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GLOUCESTER | 430870 | 1930 | 15.2 | Solar | 12_28L2 | 2022-05-16 11:45 | 2022-05-17 | 1 | 0 | 1 | 2022-07-12 | 2022-08-04 | 18 | 0 | 18 | [20 empty] | 2022-08-05 | 2022-05-16 13:27 | 2023-12-11 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTHBOROUGH | 430956 | 1532 | 15.2 | Solar | 05_313W1 | 2022-05-16 13:27 | 2022-05-17 | 2 | 0 | 2 | 2022-05-19 | 2022-10-28 | 111 | 92 | 19 | [20 empty] | 2022-10-28 |  | 2024-07-27 | Yes | EXP |  | 2023-02-07 | 2023-07-25 | 169 | 0 | 169 |  |  |  | Completion Documents |  | Yes
National Grid | BILLERICA | 430494 | 1821 | 15.2 | Solar | 14_70L6 | 2022-05-16 14:33 | 2022-05-17 | 1 | 0 | 1 | 2022-05-18 | 2022-06-15 | 20 | 0 | 20 | [20 empty] | 2022-06-16 |  | 2023-06-22 |  | EXP | [8 empty] | 2022-08-19 | Connected |  | No
National Grid | PEMBROKE | 417115 | 2359 | 262.5 | Natural Gas | 07_910W51 | 2022-05-16 22:47 | 2022-05-17 | 6 | 0 | 6 | [10 empty] | 2022-05-25 | 2022-08-16 | 56 | 33 | 23 | [14 empty] | STD | [9 empty] | Pending Withdraw |  | Yes
National Grid | HINGHAM | 422057 | 2043 | 4999.2 | Battery Add-On | 07_99W63 | 2022-05-17 10:26 | 2022-05-18 | 188 | 26 | 162 | [29 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | GOUCESTER | 431218 | 1930 | 10 | Solar | 12_51T1 | 2022-05-17 11:16 | 2022-05-18 | 1 | 0 | 1 | 2022-05-19 | 2022-06-09 | 15 | 0 | 15 | [20 empty] | 2022-06-16 | 2022-05-18 11:11 | 2023-07-01 |  | EXP | [8 empty] | 2023-02-17 | Connected |  | No
National Grid | NEWBURYPORT | 426194 | 1950 | 460 | Solar | 14_60L3 | 2022-05-18 11:11 | 2022-05-19 | 38 | 31 | 7 | [10 empty] | 2022-07-15 | 2022-08-05 | 16 | 0 | 16 | [10 empty] | 2023-03-27 |  | 2024-11-11 | Yes | STD | [9 empty] | Design |  | No
National Grid | ANDOVER | 431159 | 1810 | 15.2 | Solar | 14_50L1 | 2022-05-18 12:21 | 2022-05-19 | 1 | 0 | 1 | 2022-05-20 | 2022-06-15 | 18 | 0 | 18 | [20 empty] | 2022-06-16 | 2022-05-18 13:29 | 2023-06-23 |  | EXP | [8 empty] | 2023-01-11 | Connected |  | No
National Grid | BROCKTON | 430063 | 2302 | 7.6 | Solar | 07_911W77 | 2022-05-18 13:29 | 2022-05-19 | 2 | 0 | 2 | 2022-05-23 | 2022-06-15 | 17 | 0 | 17 | [20 empty] | 2022-06-21 |  | 2023-09-18 | Yes | EXP |  | 2022-08-18 | 2022-09-08 | 22 | 0 | 22 |  |  | 2022-12-30 | Connected |  | No
National Grid | REHOBOTH | 417356 | 2769 | 975 | Solar | 05_7L4 | 2022-05-18 13:56 | 2022-05-19 | 67 | 58 | 9 | [10 empty] | 2022-08-24 | 2022-09-01 | 7 | 0 | 7 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | COHASSET | 429558 | 2025 | 15.2 | Solar | 07_18J1 | 2022-05-18 15:05 | 2022-05-19 | 2 | 0 | 2 | 2022-05-23 | 2022-06-16 | 18 | 0 | 18 | [20 empty] | 2022-06-17 | 2022-05-18 16:52 | 2023-10-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHARLTON | 353715 | 1507 | 10 | Solar | 01_406L3 | 2022-05-18 16:52 | 2022-05-19 | 6 | 4 | 2 | 2022-05-26 | 2022-08-02 | 47 | 30 | 17 | [20 empty] | 2021-04-22 |  | 2024-06-06 | Yes | EXP | [8 empty] | 2023-06-21 | Connected |  | Yes
National Grid | ROCKPORT | 430455 | 1966 | 15.2 | Solar | 12_40L1 | 2022-05-19 08:16 | 2022-05-20 | 1 | 0 | 1 | 2022-05-23 | 2022-06-15 | 17 | 0 | 17 | [20 empty] | 2022-06-16 | 2022-05-19 09:57 | 2023-07-15 |  | EXP | [8 empty] | 2022-11-15 | Connected |  | No
National Grid | MILFORD | 431440 | 1757 | 7.54 | Solar | 05_336W3 | 2022-05-19 09:57 | 2022-05-23 | 3 | 2 | 1 | 2022-05-26 | 2022-06-21 | 17 | 0 | 17 | [20 empty] | 2022-06-23 | 2022-05-19 11:59 | 2023-12-21 | Yes | EXP |  | 2022-10-18 | 2022-12-21 | 65 | 0 | 65 |  |  | 2023-01-11 | Connected |  | No
National Grid | LAWRENCE | 428539 | 1841 | 7.6 | Solar | 14_8L2 | 2022-05-19 11:59 | 2022-05-20 | 4 | 3 | 1 | 2022-05-25 | 2022-11-21 | 122 | 105 | 17 | [20 empty] | 2022-12-08 |  | 2024-04-09 | Yes | EXP |  | 2023-03-15 | 2023-04-08 | 25 | 0 | 25 |  |  | 2023-06-12 | Connected |  | No
National Grid | BEVERLY | 422071 | 1915 | 4999.2 | Battery Add-On | 12_12L2 | 2022-05-19 18:21 | 2022-05-20 | 56 | 48 | 8 | [10 empty] | 2022-08-12 | 2022-09-09 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | FALL RIVER | 431612 | 2720 | 240 | Solar | 05_106W46 | 2022-05-20 11:25 | 2022-05-23 | 20 | 12 | 8 | 2022-06-22 | 2022-07-27 | 25 | 0 | 25 | [20 empty] | 2024-02-20 | 2022-05-20 12:35 |  |  | EXP | [9 empty] | Pending Withdraw |  | No
National Grid | BELCHERTOWN | 428143 | 1007 | 10 | Solar | 09_509L2 | 2022-05-20 12:35 | 2022-05-23 | 1 | 0 | 1 | 2022-05-24 | 2022-06-17 | 18 | 0 | 18 | [20 empty] | 2022-06-21 |  | 2023-10-12 | Yes | EXP |  | 2022-09-21 | 2022-10-10 | 20 | 0 | 20 |  |  | 2022-11-14 | Connected |  | Yes
National Grid | FALL RIVER | 431700 | 2720 | 160 | Solar | 05_106W46 | 2022-05-20 12:58 | 2022-05-23 | 20 | 12 | 8 | 2022-06-22 | 2022-07-27 | 25 | 0 | 25 | [20 empty] | 2024-02-20 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | No
National Grid | HANOVER | 424551 | 2339 | 20 | Solar | 07_95W4 | 2022-05-20 14:58 | 2022-05-23 | 21 | 20 | 1 | 2022-06-22 | 2022-07-21 | 21 | 0 | 21 | [20 empty] | 2022-08-03 |  | 2023-09-13 |  | EXP | [8 empty] | 2022-10-21 | Connected |  | No
National Grid | WORCESTER | 405854 | 1605 | 4990 | Other | 01_15J392 | 2022-05-20 15:52 | 2022-05-23 | 14 | 8 | 6 | [10 empty] | 2022-06-10 | 2022-06-21 | 7 | 0 | 7 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SALEM | 424741 | 1970 | 220 | Solar | 12_29W4 | 2022-05-23 10:48 | 2022-05-24 | 17 | 8 | 9 | 2022-06-16 | 2022-07-22 | 25 | 0 | 25 | [21 empty] | 2022-05-23 11:10 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHELMSFORD | 426459 | 1824 | 15.2 | Solar | 14_24L1 | 2022-05-23 11:10 | 2022-05-24 | 14 | 13 | 1 | 2022-06-13 | 2022-08-08 | 39 | 20 | 19 | [20 empty] | 2022-08-08 |  | 2023-11-14 | Yes | EXP |  | 2022-10-19 | 2022-11-14 | 27 | 0 | 27 |  |  | 2022-12-15 | Connected |  | No
National Grid | MONSON | 425011 | 1057 | 10 | Solar | 09_503L2 | 2022-05-23 11:52 | 2022-05-24 | 2 | 1 | 1 | 2022-05-26 | 2022-06-17 | 16 | 0 | 16 | [20 empty] | 2022-06-17 |  | 2023-07-09 |  | EXP | [8 empty] | 2023-03-23 | Connected |  | Yes
National Grid | CHELMSFORD | 432583 | 1824 | 15.2 | Solar | 14_16L1 | 2022-05-23 12:10 | 2022-05-24 | 27 | 25 | 2 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MILFORD | 430119 | 1757 | 6 | Solar | 05_336W3 | 2022-05-23 16:16 | 2022-05-24 | 1 | 0 | 1 | 2022-05-25 | 2022-06-15 | 15 | 0 | 15 | [20 empty] | 2022-08-03 |  | 2023-12-30 |  | EXP | [8 empty] | 2023-01-05 | Connected |  | No
National Grid | NORTH ADAMS | 426233 | 1247 | 5 | Solar | 09_1015W1 | 2022-05-23 19:22 | 2022-05-24 | 5 | 2 | 3 | 2022-06-01 | 2022-06-21 | 14 | 0 | 14 | [20 empty] | 2022-05-06 | 2022-05-24 17:11 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | DRACUT | 430404 | 1826 | 6 | Solar | 14_78L1 | 2022-05-24 17:11 | 2022-05-25 | 7 | 5 | 2 | 2022-06-03 | 2022-06-28 | 16 | 0 | 16 | [20 empty] | 2022-07-15 | 2022-05-25 08:53 | 2023-10-13 | Yes | EXP |  | 2022-09-28 | 2022-10-12 | 15 | 0 | 15 |  |  | 2022-10-24 | Connected |  | No
National Grid | MARLBOROUGH | 430828 | 1752 | 237.5 | Solar | 05_317W7 | 2022-05-25 08:53 | 2022-05-26 | 20 | 14 | 6 | 2022-06-27 | 2022-09-01 | 48 | 26 | 22 | [20 empty] | 2022-09-14 | 2022-05-25 13:21 | 2024-05-13 | Yes | EXP | [9 empty] | Completion Documents |  | No
National Grid | STOUGHTON | 430213 | 2072 | 3.8 | Solar | 07_75W7 | 2022-05-25 13:21 | 2022-05-26 | 1 | 0 | 1 | 2022-05-27 | 2022-06-28 | 21 | 0 | 21 | [20 empty] | 2022-07-08 |  | 2024-06-07 | Yes | EXP |  | 2022-12-01 | 2023-06-08 | 190 | 0 | 190 |  |  | 2023-06-14 | Connected |  | Yes
National Grid | CLINTON | 396737 | 1510 | 1744 | Other | 01_216W3 | 2022-05-25 17:55 | 2022-05-26 | 7 | 0 | 7 | [10 empty] | 2022-06-06 | 2022-07-11 | 24 | 5 | 19 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | ROCKLAND | 431370 | 2370 | 450 | Solar | 07_99W63 | 2022-05-26 08:31 | 2022-05-27 | 11 | 3 | 8 | [10 empty] | 2022-06-14 | 2022-07-15 | 22 | 0 | 22 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | FALL RIVER | 419356 | 2721 | 240 | Solar | 05_115W53 | 2022-05-26 09:54 | 2022-05-27 | 11 | 3 | 8 | [10 empty] | 2022-06-14 | 2022-07-15 | 22 | 0 | 22 | [10 empty] | 2023-11-28 |  |  |  | STD | [9 empty] | Completion Documents |  | No
National Grid | WHITINSVILLE | 419350 | 1588 | 240 | Solar | 05_321W5 | 2022-05-26 10:00 | 2022-05-27 | 12 | 6 | 6 | [10 empty] | 2022-06-14 | 2022-07-20 | 24 | 0 | 24 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | BROCKTON | 419315 | 2301 | 240 | Solar | 07_94W41 | 2022-05-26 10:03 | 2022-05-27 | 12 | 5 | 7 | [10 empty] | 2022-06-14 | 2022-07-20 | 24 | 0 | 24 | [11 empty] | 2022-05-26 10:10 |  |  | STD | [9 empty] | Study |  | No
National Grid | MEDFORD | 419319 | 2155 | 240 | Solar | 12_11J3 | 2022-05-26 10:10 | 2022-05-27 | 11 | 4 | 7 | [10 empty] | 2022-06-14 | 2022-07-15 | 22 | 0 | 22 | [10 empty] | 2022-11-28 |  | 2024-10-18 | Yes | STD | [9 empty] | Completion Documents |  | No
National Grid | ROCKLAND | 419309 | 2370 | 240 | Solar | 07_99W61 | 2022-05-26 10:14 | 2022-05-27 | 33 | 25 | 8 | [10 empty] | 2022-07-18 | 2022-08-05 | 15 | 0 | 15 | [11 empty] | 2022-05-26 10:23 |  |  | STD | [9 empty] | Group Study |  | No
National Grid | NORTH ADAMS | 419324 | 1247 | 495 | Solar | 09_1021W2 | 2022-05-26 10:23 | 2022-05-27 | 13 | 8 | 5 | [10 empty] | 2022-06-16 | 2022-07-18 | 21 | 0 | 21 | [10 empty] | 2022-12-14 |  |  | Yes | STD | [9 empty] | Design |  | No
National Grid | PALMER | 421650 | 1069 | 240 | Solar | 09_503L1 | 2022-05-26 10:38 | 2022-05-27 | 12 | 5 | 7 | [10 empty] | 2022-06-15 | 2022-07-18 | 21 | 0 | 21 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | STURBRIDGE | 419334 | 1566 | 240 | Solar | 01_413L2 | 2022-05-26 10:42 | 2022-05-27 | 12 | 6 | 6 | [10 empty] | 2022-06-14 | 2022-07-15 | 22 | 0 | 22 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | FOXBOROUGH | 419331 | 2035 | 500 | Solar | 05_3432W2 | 2022-05-26 10:52 | 2022-05-27 | 20 | 15 | 5 | [10 empty] | 2022-06-28 | 2022-07-26 | 20 | 0 | 20 | [11 empty] | 2022-05-26 11:25 |  |  | STD | [9 empty] | Group Study |  | No
National Grid | WESTBOROUGH | 419359 | 1581 | 499 | Solar | 05_312W2 | 2022-05-26 11:25 | 2022-05-27 | 12 | 7 | 5 | [10 empty] | 2022-06-15 | 2022-07-18 | 22 | 2 | 20 | [10 empty] | 2023-04-28 |  | 2024-06-20 | Yes | STD | [9 empty] | Design |  | No
National Grid | SAUGUS | 419316 | 1906 | 240 | Solar | 12_25W3 | 2022-05-26 13:48 | 2022-05-27 | 20 | 14 | 6 | 2022-06-28 | 2022-07-28 | 22 | 0 | 22 | [20 empty] | 2022-08-08 |  | 2025-03-05 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | LAWRENCE | 431131 | 1843 | 6 | Solar | 14_8L1 | 2022-05-26 14:58 | 2022-05-27 | 2 | 0 | 2 | 2022-06-01 | 2022-06-28 | 19 | 0 | 19 | [20 empty] | 2022-07-11 |  | 2023-07-13 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LYNN | 429973 | 1904 | 6 | Solar | 12_29W4 | 2022-05-27 06:29 | 2022-05-31 | 3 | 1 | 2 | 2022-06-03 | 2022-07-05 | 20 | 0 | 20 | [20 empty] | 2022-07-05 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOMERSET | 424766 | 2726 | 7.6 | Solar | 05_11W82 | 2022-05-27 11:34 | 2022-05-31 | 2 | 0 | 2 | 2022-06-02 | 2022-06-29 | 19 | 0 | 19 | [20 empty] | 2022-06-30 | 2022-05-27 11:54 | 2023-06-30 |  | EXP | [8 empty] | 2022-11-16 | Connected |  | Yes
National Grid | SWANSEA | 433811 | 2777 | 10 | Solar | 05_11W84 | 2022-05-27 11:54 | 2022-07-22 | 0 | 0 | 0 | 2022-07-22 | 2022-08-18 | 20 | 0 | 20 | [20 empty] | 2022-08-21 |  | 2024-01-07 | Yes | EXP | [8 empty] | 2023-02-02 | Connected |  | No
National Grid | PEPPERELL | 388303 | 1463 | 7.6 | Solar | 01_226L1 | 2022-05-27 12:12 | 2022-05-31 | 2 | 0 | 2 | 2022-06-02 | 2022-06-28 | 17 | 0 | 17 | [20 empty] | 2022-07-07 | 2022-05-27 13:34 | 2023-11-22 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOUTH EASTON | 430304 | 2375 | 100 | Solar | 07_98W48 | 2022-05-27 13:34 | 2022-05-31 | 56 | 49 | 7 | [10 empty] | 2022-08-19 | 2022-09-16 | 20 | 0 | 20 | [10 empty] | 2023-09-01 |  |  | Yes | STD | [9 empty] | Completion Documents |  | No
National Grid | CHELMSFORD | 431972 | 1824 | 11.4 | Solar | 14_70L3 | 2022-05-27 14:20 | 2022-05-31 | 2 | 0 | 2 | 2022-06-02 | 2022-06-28 | 17 | 0 | 17 | [20 empty] | 2022-07-07 |  | 2023-11-28 |  | EXP | [8 empty] | 2023-03-01 | Connected |  | No
National Grid | ANDOVER | 433986 | 1810 | 19 | Solar | 14_50L1 | 2022-05-27 18:25 | 2022-05-31 | 19 | 18 | 1 | 2022-06-27 | 2022-07-28 | 23 | 0 | 23 | [20 empty] | 2022-07-29 |  | 2023-08-03 |  | EXP | [8 empty] | 2023-06-07 | Connected |  | Yes
National Grid | HAVERHILL | 412233 | 1835 | 4999.2 | Battery Add-On | 14_43L3 | 2022-05-28 12:48 | 2022-05-31 | 48 | 38 | 10 | [10 empty] | 2022-08-10 | 2022-09-07 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | HOLBROOK | 424886 | 2343 | 100 | Solar | 07_10W1 | 2022-05-31 15:27 | 2022-06-01 | 76 | 68 | 8 | 2022-09-20 | 2022-10-19 | 21 | 3 | 18 | [20 empty] | 2022-11-02 |  | 2024-05-01 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | NEWBURY | 426844 | 1951 | 4998 | Solar | 14_60L4 | 2022-05-31 19:43 | 2022-06-01 | 38 | 28 | 10 | [29 empty] | CMPX | [9 empty] | Study |  | No
National Grid | LAWRENCE | 426466 | 1843 | 7.6 | Solar | 14_8L1 | 2022-06-01 09:20 | 2022-06-02 | 4 | 0 | 4 | 2022-06-08 | 2022-06-30 | 16 | 0 | 16 | [20 empty] | 2022-08-29 | 2022-06-01 09:55 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EAST LONGMEADOW | 431988 | 1028 | 3.8 | Solar | 09_508L4 | 2022-06-01 09:55 | 2022-06-02 | 3 | 0 | 3 | 2022-06-07 | 2022-06-24 | 13 | 0 | 13 | [20 empty] | 2022-06-28 | 2022-06-01 10:26 | 2023-12-22 | Yes | EXP |  | 2022-11-15 | 2022-12-21 | 37 | 0 | 37 |  |  | 2023-01-17 | Connected |  | No
National Grid | SOUTHBOROUGH | 426147 | 1772 | 10 | Solar | 05_310W6 | 2022-06-01 10:26 | 2022-06-02 | 20 | 18 | 2 | 2022-07-01 | 2022-08-03 | 23 | 0 | 23 | [20 empty] | 2022-08-03 |  | 2024-06-13 |  | EXP |  | 2022-10-11 | 2023-06-14 | 247 | 0 | 247 |  |  | 2023-08-07 | Connected |  | Yes
National Grid | BERLIN | 434493 | 1503 | 15.2 | Solar | 05_318W3 | 2022-06-01 10:37 | 2022-06-02 | 2 | 0 | 2 | 2022-06-06 | 2022-07-01 | 18 | 0 | 18 | [20 empty] | 2022-07-01 |  | 2023-07-13 |  | EXP | [8 empty] | 2023-01-28 | Connected |  | No
National Grid | AUBURN | 432998 | 1501 | 100 | Solar | 01_26W2 | 2022-06-01 12:00 | 2022-06-02 | 20 | 12 | 8 | [10 empty] | 2022-07-01 | 2022-08-03 | 23 | 0 | 23 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | AUBURN | 433265 | 1501 | 150 | Solar | 01_26W3 | 2022-06-01 12:02 | 2022-06-02 | 20 | 12 | 8 | [10 empty] | 2022-07-01 | 2022-08-03 | 23 | 0 | 23 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 425538 | 1606 | 250 | Solar | 01_24W2 | 2022-06-01 12:34 | 2022-06-02 | 10 | 2 | 8 | [10 empty] | 2022-06-16 | 2022-08-09 | 37 | 12 | 25 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTMINSTER | 426230 | 1473 | 7.6 | Solar | 01_609W1 | 2022-06-01 12:49 | 2022-06-02 | 4 | 2 | 2 | 2022-06-07 | 2022-06-30 | 17 | 0 | 17 | [20 empty] | 2022-07-07 |  | 2023-07-19 |  | EXP | [8 empty] | 2022-10-07 | Connected |  | No
National Grid | SOMERSET | 429706 | 2726 | 240 | Solar | 05_11W82 | 2022-06-01 16:09 | 2022-06-02 | 20 | 15 | 5 | 2022-07-01 |  | 445 | 421 | 24 | [24 empty] | EXP | [9 empty] | Screening |  | No
National Grid | SEEKONK | 432931 | 2771 | 8.12 | Solar | 05_7L1 | 2022-06-01 17:33 | 2022-06-02 | 3 | 0 | 3 | 2022-06-07 | 2022-06-30 | 17 | 0 | 17 | 2022-10-11 | 2022-10-31 | 15 | 0 | 15 | [5 empty] | 2022-10-11 | 2022-10-31 | 15 | 0 | 15 | [5 empty] | 2022-10-31 |  | 2023-11-04 |  | EXP | [8 empty] | 2022-12-12 | Connected |  | No
National Grid | FOXBOROUGH | 408090 | 2035 | 999 | Solar | 05_3432W2 | 2022-06-01 22:31 | 2022-06-02 | 27 | 19 | 8 | [10 empty] | 2022-07-14 | 2022-08-08 | 18 | 0 | 18 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | SIASCONSET | 434333 | 2564 | 20 | Solar | 04_101L8 | 2022-06-02 10:20 | 2022-06-03 | 4 | 2 | 2 | 2022-06-09 | 2022-07-05 | 16 | 0 | 16 | [20 empty] | 2022-07-05 |  | 2023-07-25 |  | EXP | [8 empty] | 2022-09-01 | Connected |  | No
National Grid | STOUGHTON | 432258 | 2072 | 10 | Solar | 07_913W69 | 2022-06-02 11:19 | 2022-06-03 | 3 | 0 | 3 | 2022-06-08 | 2022-07-05 | 18 | 0 | 18 | [20 empty] | 2022-07-08 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ABINGTON | 424099 | 2351 | 187.5 | Solar | 07_93W42 | 2022-06-02 13:57 | 2022-06-03 | 15 | 8 | 7 | [10 empty] | 2022-06-27 | 2022-07-27 | 22 | 0 | 22 | [14 empty] | STD | [9 empty] | Group Study |  | Yes
National Grid | EAST LONGMEADOW | 433831 | 1028 | 24.52 | Solar | 09_508L5 | 2022-06-02 14:34 | 2022-06-03 | 13 | 11 | 2 | 2022-06-23 | 2022-07-25 | 22 | 0 | 22 | [20 empty] | 2022-07-25 | 2022-06-02 15:00 | 2023-07-30 |  | EXP | [8 empty] | 2023-03-24 | Connected |  | No
National Grid | QUINCY | 419001 | 2169 | 10 | Solar | 07_1W5 | 2022-06-02 15:00 | 2022-06-03 | 21 | 20 | 1 | 2022-07-07 | 2022-08-04 | 21 | 0 | 21 | [20 empty] | 2022-08-04 |  | 2023-09-16 | Yes | EXP |  | 2022-08-27 | 2022-09-14 | 19 | 0 | 19 |  |  | 2023-01-19 | Connected |  | No
National Grid | BROCKTON | 433454 | 2302 | 3.8 | Solar | 07_911W56 | 2022-06-03 05:36 | 2022-06-06 | 2 | 0 | 2 | 2022-06-08 | 2022-06-30 | 15 | 0 | 15 | [20 empty] | 2022-07-28 |  | 2023-07-30 |  | EXP | [8 empty] | 2022-11-21 | Connected |  | No
National Grid | ATTLEBORO | 431477 | 2703 | 5.8 | Solar | 05_9L4 | 2022-06-03 12:09 | 2022-06-06 | 1 | 0 | 1 | 2022-06-07 | 2022-07-05 | 19 | 0 | 19 | [20 empty] | 2022-07-05 | 2022-06-03 12:24 | 2023-08-12 |  | EXP | [8 empty] | 2022-11-10 | Connected |  | No
National Grid | SOUTHBOROUGH | 430664 | 1772 | 5.04 | Solar | 05_314W2 | 2022-06-03 12:24 | 2022-06-06 | 1 | 0 | 1 | 2022-06-07 | 2022-06-24 | 13 | 0 | 13 | [20 empty] | 2022-06-28 |  | 2023-12-12 | Yes | EXP |  | 2022-12-13 | 2023-01-03 | 22 | 0 | 22 |  |  | 2023-01-05 | Connected |  | No
National Grid | EAST BRIDGEWATER | 429020 | 2333 | 499 | Solar | 07_91W41 | 2022-06-03 15:47 | 2022-06-06 | 18 | 12 | 6 | [10 empty] | 2022-07-05 | 2022-08-04 | 23 | 0 | 23 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | ROCKLAND | 424573 | 2370 | 480 | Solar | 07_99W63 | 2022-06-03 18:21 | 2022-06-06 | 25 | 16 | 9 | [10 empty] | 2022-07-14 | 2022-08-09 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Group Study |  | Yes
National Grid | GLOUCESTER | 434644 | 1930 | 240 | Solar | 12_2364 | 2022-06-06 09:23 | 2022-06-07 | 17 | 10 | 7 | [10 empty] | 2022-07-01 | 2022-08-05 | 25 | 0 | 25 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | STURBRIDGE | 431376 | 1566 | 500 | Solar | 01_413L2 | 2022-06-06 11:42 | 2022-06-07 | 11 | 3 | 8 | [10 empty] | 2022-06-23 | 2022-07-21 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | BOLTON | 435624 | 1740 | 15.2 | Solar | 01_216W6 | 2022-06-06 13:48 | 2022-06-07 | 13 | 11 | 2 | 2022-06-27 | 2022-07-28 | 23 | 0 | 23 | [20 empty] | 2022-07-29 |  | 2023-08-02 |  | EXP | [8 empty] | 2022-09-07 | Connected |  | No
National Grid | AVON | 429417 | 2322 | 480 | Solar | 07_75W1 | 2022-06-06 15:56 | 2022-06-07 | 18 | 11 | 7 | [10 empty] | 2022-07-05 | 2022-08-08 | 25 | 0 | 25 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | METHUEN | 435737 | 1844 | 15.2 | Solar | 14_43L4 | 2022-06-06 17:10 | 2022-06-07 | 9 | 8 | 1 | 2022-06-17 | 2022-07-18 | 19 | 0 | 19 | [20 empty] | 2022-07-25 | 2022-06-07 07:48 | 2023-08-05 |  | EXP | [8 empty] | 2022-12-14 | Connected |  | No
National Grid | METHUEN | 433206 | 1844 | 10 | Solar | 14_43L2 | 2022-06-07 07:48 | 2022-06-08 | 2 | 0 | 2 | 2022-06-10 | 2022-07-07 | 18 | 0 | 18 | [20 empty] | 2022-07-11 |  | 2023-10-20 | Yes | EXP |  | 2022-09-28 | 2022-10-19 | 22 | 0 | 22 |  |  | 2022-11-17 | Connected |  | No
National Grid | ESSEX | 433829 | 1929 | 5.76 | Solar | 12_51T2 | 2022-06-07 07:56 | 2022-06-08 | 6 | 5 | 1 | 2022-06-16 | 2022-09-20 | 74 | 42 | 32 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SAUGUS | 430334 | 1906 | 6 | Solar | 12_23W1 | 2022-06-07 15:35 | 2022-06-08 | 5 | 3 | 2 | 2022-06-15 | 2022-07-22 | 25 | 0 | 25 | [20 empty] | 2022-07-26 |  | 2023-12-08 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 431099 | 2302 | 9.8 | Solar | 07_911W56 | 2022-06-08 11:15 | 2022-06-09 | 1 | 0 | 1 | 2022-06-10 | 2022-07-17 | 24 | 2 | 22 | [20 empty] | 2022-08-03 |  | 2023-09-24 |  | EXP | [8 empty] | 2023-03-30 | Connected |  | Yes
National Grid | BRIDGEWATER | 436362 | 2324 | 7.6 | Solar | 07_912W21 | 2022-06-08 14:31 | 2022-06-09 | 1 | 0 | 1 | 2022-06-10 | 2022-07-05 | 16 | 0 | 16 | [20 empty] | 2022-07-06 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | PEPPERELL | 433783 | 1463 | 15.2 | Solar | 01_226L2 | 2022-06-08 18:42 | 2022-06-09 | 1 | 0 | 1 | 2022-06-10 | 2022-06-28 | 12 | 0 | 12 | [20 empty] | 2022-07-01 |  | 2023-07-07 |  | EXP | [8 empty] | 2023-01-13 | Connected |  | No
National Grid | STOUGHTON | 435270 | 2072 | 16 | Solar | 07_913W69 | 2022-06-09 07:50 | 2022-06-10 | 21 | 20 | 1 | 2022-07-12 | 2022-08-04 | 18 | 0 | 18 | [20 empty] | 2022-08-05 |  | 2023-08-06 |  | EXP | [8 empty] | 2023-05-09 | Connected |  | No
National Grid | WESTBOROUGH | 436643 | 1581 | 15.2 | Solar | 05_312W4 | 2022-06-09 11:39 | 2022-06-10 | 2 | 0 | 2 | 2022-06-14 | 2022-07-07 | 16 | 0 | 16 | [20 empty] | 2022-08-03 | 2022-06-09 12:12 | 2023-08-05 |  | EXP | [8 empty] | 2022-09-06 | Connected |  | Yes
National Grid | STOUGHTON | 432815 | 2072 | 14.8 | Solar | 07_913W67 | 2022-06-09 12:12 | 2022-06-10 | 1 | 0 | 1 | 2022-06-13 | 2022-07-07 | 17 | 0 | 17 | [20 empty] | 2022-07-08 |  | 2023-10-11 |  | EXP |  | 2022-09-15 | 2022-10-11 | 27 | 0 | 27 |  |  |  | Withdrawn |  | No
National Grid | SEEKONK | 436671 | 2771 | 27.6 | Solar | 05_7L1 | 2022-06-09 12:40 | 2022-06-10 | 1 | 0 | 1 | 2022-06-13 | 2022-07-07 | 17 | 0 | 17 | [20 empty] | 2022-07-29 | 2022-06-09 15:40 | 2023-08-01 |  | EXP | [8 empty] | 2023-03-20 | Connected |  | No
National Grid | WORCESTER | 429602 | 1605 | 8.7 | Solar | 01_24W1 | 2022-06-09 15:40 | 2022-06-10 | 8 | 6 | 2 | 2022-06-23 | 2022-07-28 | 25 | 0 | 25 | [20 empty] | 2022-08-01 |  | 2023-11-30 | Yes | EXP | [8 empty] | 2023-03-22 | Connected |  | No
National Grid | GOSHEN | 435182 | 1032 | 15.2 | Solar | 09_909W3 | 2022-06-09 16:31 | 2022-06-10 | 3 | 0 | 3 | 2022-06-15 | 2022-07-22 | 26 | 1 | 25 | [20 empty] | 2022-07-26 |  | 2023-07-30 |  | EXP | [8 empty] | 2023-01-13 | Connected |  | Yes
National Grid | STURBRIDGE | 436971 | 1566 | 10 | Solar | 01_413L7 | 2022-06-10 11:58 | 2022-06-13 | 0 | 0 | 0 | 2022-06-14 | 2022-07-07 | 16 | 0 | 16 | [20 empty] | 2022-07-29 |  | 2023-08-05 |  | EXP | [8 empty] | 2022-09-13 | Connected |  | No
National Grid | MILLBURY | 434574 | 1527 | 10 | Solar | 01_304W1 | 2022-06-13 07:23 | 2022-06-14 | 1 | 0 | 1 | 2022-06-15 | 2022-07-21 | 25 | 0 | 25 | [20 empty] | 2022-07-27 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WILBRAHAM | 434053 | 1095 | 3.8 | Solar | 09_507L3 | 2022-06-13 07:29 | 2022-06-14 | 10 | 8 | 2 | 2022-06-29 | 2022-08-01 | 23 | 0 | 23 | [20 empty] | 2022-08-03 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTBOROUGH | 384615 | 1581 | 200 | Solar | 05_312W1 | 2022-06-13 12:34 | 2022-06-14 | 36 | 28 | 8 | [10 empty] | 2022-08-05 | 2022-09-09 | 25 | 0 | 25 | [10 empty] | 2023-09-14 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTBOROUGH | 384611 | 1581 | 400 | Solar | 05_312W2 | 2022-06-13 12:35 | 2022-06-14 | 43 | 34 | 9 | [10 empty] | 2022-08-15 | 2022-09-13 | 22 | 2 | 20 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTBOROUGH | 384617 | 1581 | 400 | Solar | 05_312W1 | 2022-06-13 12:36 | 2022-06-14 | 36 | 27 | 9 | [10 empty] | 2022-08-05 | 2022-09-09 | 25 | 0 | 25 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTBOROUGH | 384619 | 1581 | 400 | Solar | 05_312W1 | 2022-06-13 12:39 | 2022-06-14 | 36 | 27 | 9 | [10 empty] | 2022-08-05 | 2022-09-09 | 25 | 0 | 25 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | GLOUCESTER | 426149 | 1930 | 7.6 | Solar | 12_51T1 | 2022-06-13 13:20 | 2022-06-14 | 0 | 0 | 0 | 2022-06-14 | 2022-07-12 | 18 | 0 | 18 | [20 empty] | 2022-07-14 |  | 2023-07-19 |  | EXP | [8 empty] | 2023-02-27 | Connected |  | No
National Grid | WARE | 435977 | 1082 | 6 | Solar | 09_501L1 | 2022-06-13 13:50 | 2022-06-14 | 1 | 0 | 1 | 2022-06-15 | 2022-07-18 | 20 | 0 | 20 | [20 empty] | 2022-08-03 |  | 2023-08-06 |  | EXP | [8 empty] | 2022-09-09 | Connected |  | No
National Grid | NORTHBOROUGH | 437383 | 1532 | 15.2 | Solar | 05_313W3 | 2022-06-13 16:41 | 2022-06-14 | 1 | 0 | 1 | 2022-06-15 | 2022-07-11 | 16 | 0 | 16 | [20 empty] | 2022-07-14 | 2022-06-14 10:49 | 2023-08-25 |  | EXP | [8 empty] | 2022-12-13 | Connected |  | No
National Grid | SALEM | 437523 | 1970 | 15.2 | Solar | 12_2W1 | 2022-06-14 10:49 | 2022-06-15 | 1 | 0 | 1 | 2022-06-16 | 2022-07-18 | 20 | 0 | 20 | [20 empty] | 2022-07-21 |  | 2024-02-29 | Yes | EXP |  | 2023-01-25 | 2023-04-17 | 83 | 0 | 83 |  |  | 2023-05-22 | Connected |  | No
National Grid | GREAT BARRINGTON | 437566 | 1230 | 15.2 | Solar | 09_1109W3 | 2022-06-14 12:03 | 2022-06-15 | 3 | 2 | 1 | 2022-06-17 | 2022-07-18 | 19 | 0 | 19 | [20 empty] | 2022-07-19 |  | 2023-12-04 |  | EXP | [8 empty] | 2023-09-02 | Connected |  | No
National Grid | BROCKTON | 436238 | 2301 | 10 | Solar | 07_98W46 | 2022-06-14 12:59 | 2022-06-15 | 2 | 1 | 1 | 2022-06-16 | 2022-07-21 | 24 | 0 | 24 | [20 empty] | 2022-07-25 | 2022-06-14 13:49 | 2023-07-29 |  | EXP | [8 empty] | 2022-10-20 | Connected |  | No
National Grid | AYER | 437610 | 1432 | 3.8 | Solar | 01_201W3 | 2022-06-14 13:49 | 2022-06-15 | 1 | 0 | 1 | 2022-06-16 | 2022-07-14 | 19 | 0 | 19 | [20 empty] | 2022-07-14 |  | 2023-08-25 | Yes | EXP |  | 2022-09-14 | 2022-09-28 | 15 | 0 | 15 |  |  | 2022-10-05 | Connected |  | No
National Grid | HAMILTON | 433980 | 1982 | 7.6 | Solar | 12_51T2 | 2022-06-14 15:09 | 2022-06-15 | 2 | 1 | 1 | 2022-06-16 | 2022-07-11 | 16 | 0 | 16 | [20 empty] | 2022-07-25 | 2022-06-14 15:44 | 2023-07-26 |  | EXP | [8 empty] | 2023-01-04 | Connected |  | No
National Grid | STURBRIDGE | 435573 | 1566 | 7.6 | Solar | 01_415L1 | 2022-06-14 15:44 | 2022-06-15 | 1 | 0 | 1 | 2022-06-16 | 2022-07-14 | 19 | 0 | 19 | [20 empty] | 2022-07-19 |  | 2024-06-22 | Yes | EXP |  | 2023-05-10 | 2023-06-22 | 44 | 0 | 44 |  |  | 2023-06-30 | Connected |  | No
National Grid | GLOUCESTER | 419846 | 1930 | 4992 | Other | 12_51T3 | 2022-06-14 16:05 | 2022-06-15 | 23 | 18 | 5 | [10 empty] | 2022-07-20 | 2022-08-08 | 14 | 0 | 14 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | NEWBURYPORT | 419852 | 1950 | 4999.2 | Other | 14_2405 | 2022-06-14 16:33 | 2022-06-15 | 31 | 24 | 7 | [10 empty] | 2022-08-02 | 2022-08-24 | 17 | 0 | 17 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | BEVERLY | 419862 | 1915 | 4992 | Other | 12_51L2 | 2022-06-14 16:35 | 2022-06-15 | 9 | 3 | 6 | [10 empty] | 2022-06-29 | 2022-07-27 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | GLOUCESTER | 409260 | 1930 | 480 | Solar | 12_2364 | 2022-06-15 09:40 | 2022-06-16 | 17 | 8 | 9 | [10 empty] | 2022-07-14 | 2022-08-09 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | TEWKSBURY | 437891 | 1876 | 15.2 | Solar | 14_14L2 | 2022-06-15 11:47 | 2022-06-16 | 5 | 3 | 2 | 2022-06-24 | 2022-07-21 | 19 | 0 | 19 | [20 empty] | 2022-08-05 |  | 2023-08-10 |  | EXP | [8 empty] | 2022-11-21 | Connected |  | Yes
National Grid | CHELMSFORD | 437921 | 1824 | 15.2 | Solar | 14_16L1 | 2022-06-15 13:23 | 2022-06-16 | 1 | 0 | 1 | 2022-06-17 | 2022-07-18 | 20 | 0 | 20 | [20 empty] | 2022-08-03 |  | 2023-08-20 |  | EXP | [8 empty] | 2022-12-12 | Connected |  | No
National Grid | CHARLTON | 433800 | 1507 | 9.984 | Solar | 01_406L1 | 2022-06-15 13:26 | 2022-06-16 | 1 | 0 | 1 | 2022-06-17 | 2022-07-22 | 23 | 0 | 23 | [20 empty] | 2022-07-22 |  | 2024-02-29 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ATTLEBORO | 421701 | 2703 | 15.2 | Solar | 05_9L4 | 2022-06-15 13:28 | 2022-06-16 | 6 | 4 | 2 | 2022-06-27 | 2022-07-27 | 22 | 0 | 22 | [20 empty] | 2022-07-27 |  | 2023-10-07 |  | EXP | [8 empty] | 2023-01-04 | Connected |  | No
National Grid | MELROSE | 437932 | 2176 | 9.984 | Solar | 12_25W5 | 2022-06-15 13:44 | 2022-06-27 | 3 | 1 | 2 | 2022-06-30 | 2022-07-12 | 8 | 0 | 8 | [20 empty] | 2022-06-24 |  | 2023-07-16 |  | EXP | [8 empty] | 2023-02-28 | Connected |  | No
National Grid | UXBRIDGE | 426220 | 1569 | 3.8 | Solar | 05_321W6 | 2022-06-15 15:32 | 2022-06-16 | 2 | 0 | 2 | 2022-06-21 | 2022-07-19 | 20 | 0 | 20 | [20 empty] | 2022-07-21 |  | 2023-08-03 |  | EXP | [8 empty] | 2023-01-20 | Connected |  | Yes
National Grid | REHOBOTH | 430893 | 2769 | 6.67 | Solar | 05_7L4 | 2022-06-16 07:46 | 2022-06-17 | 2 | 0 | 2 | 2022-06-22 | 2022-07-25 | 23 | 0 | 23 | [20 empty] | 2022-07-27 |  | 2023-07-28 |  | EXP | [8 empty] | 2022-12-12 | Connected |  | No
National Grid | NEWBURYPORT | 438236 | 1950 | 15.2 | Solar | 14_36L1 | 2022-06-16 13:14 | 2022-06-17 | 2 | 0 | 2 | 2022-06-22 | 2022-07-25 | 22 | 0 | 22 | [20 empty] | 2022-07-26 |  | 2023-08-05 |  | EXP | [8 empty] | 2022-12-21 | Connected |  | No
National Grid | ROCKPORT | 434717 | 1966 | 10 | Solar | 12_40L1 | 2022-06-16 14:15 | 2022-06-17 | 2 | 0 | 2 | 2022-06-22 | 2022-07-25 | 23 | 0 | 23 | [20 empty] | 2022-07-27 | 2022-06-16 17:59 | 2024-05-15 |  | EXP |  | 2023-01-07 | 2023-05-15 | 129 | 0 | 129 |  |  | 2023-05-24 | Connected |  | No
National Grid | BELLINGHAM | 425396 | 2019 | 10 | Solar | 05_108W60 | 2022-06-16 17:59 | 2022-06-17 | 5 | 3 | 2 | 2022-06-24 | 2022-07-27 | 23 | 0 | 23 | [20 empty] | 2022-07-29 | 2022-06-17 10:58 | 2024-02-02 | Yes | EXP |  | 2022-10-12 | 2023-01-14 | 95 | 0 | 95 |  |  | 2023-05-23 | Connected |  | Yes
National Grid | WORCESTER | 436749 | 1605 | 5.22 | Solar | 01_24W2 | 2022-06-17 10:58 | 2022-06-21 | 2 | 0 | 2 | 2022-06-23 | 2022-09-22 | 65 | 40 | 25 | [20 empty] | 2022-10-27 | 2022-06-17 11:14 | 2024-11-29 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | WESTFORD | 433175 | 1886 | 10 | Solar | 14_57L2 | 2022-06-17 11:14 | 2022-06-21 | 2 | 0 | 2 | 2022-06-23 | 2022-07-22 | 21 | 0 | 21 | [20 empty] | 2022-07-26 |  | 2024-03-19 | Yes | EXP |  | 2023-03-08 | 2023-03-20 | 13 | 0 | 13 |  |  | 2023-03-27 | Connected |  | Yes
National Grid | SOUTHBOROUGH | 420913 | 1772 | 15.2 | Solar | 05_314W2 | 2022-06-17 17:21 | 2022-06-21 | 2 | 0 | 2 | 2022-06-23 | 2022-07-25 | 22 | 0 | 22 | [20 empty] | 2022-07-27 | 2022-06-20 13:34 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 438769 | 2301 | 20 | Solar | 07_91W49 | 2022-06-20 13:34 | 2022-06-21 | 1 | 0 | 1 | 2022-06-22 | 2022-07-25 | 23 | 0 | 23 | [20 empty] | 2022-07-26 |  | 2024-05-03 | Yes | EXP |  | 2023-04-13 | 2023-05-03 | 21 | 0 | 21 |  |  | 2023-05-24 | Connected |  | No
National Grid | GREAT BARRINGTON | 438767 | 1230 | 7.6 | Solar | 09_1109W3 | 2022-06-20 13:52 | 2022-06-21 | 5 | 2 | 3 | 2022-06-27 | 2022-07-28 | 23 | 0 | 23 | [20 empty] | 2022-08-03 |  | 2023-08-27 |  | EXP | [8 empty] | 2022-09-28 | Connected |  | No
National Grid | SAUGUS | 438832 | 1906 | 15.2 | Solar | 12_23W2 | 2022-06-20 17:40 | 2022-06-21 | 2 | 0 | 2 | 2022-06-23 | 2022-07-25 | 22 | 0 | 22 | [20 empty] | 2022-07-27 |  | 2023-07-30 |  | EXP | [8 empty] | 2023-05-25 | Connected |  | Yes
National Grid | NEWBURYPORT | 432857 | 1950 | 10 | Solar | 14_36L1 | 2022-06-21 10:43 | 2022-06-22 | 1 | 0 | 1 | 2022-06-23 | 2022-07-25 | 22 | 0 | 22 | [20 empty] | 2022-07-26 | 2022-06-21 11:02 | 2023-07-29 |  | EXP | [8 empty] | 2023-02-27 | Connected |  | No
National Grid | LEOMINSTER | 438321 | 1453 | 5.22 | Solar | 01_219W5 | 2022-06-21 11:02 | 2022-06-22 | 2 | 1 | 1 | 2022-06-24 | 2022-07-27 | 23 | 0 | 23 | [20 empty] | 2022-07-29 |  | 2024-04-04 | Yes | EXP | [8 empty] | 2023-05-31 | Connected |  | Yes
National Grid | UPTON | 438977 | 1568 | 15.2 | Solar | 05_335W3 | 2022-06-21 11:45 | 2022-06-22 | 2 | 0 | 2 | 2022-06-24 | 2022-07-28 | 23 | 0 | 23 | [20 empty] | 2022-07-29 |  | 2023-08-02 |  | EXP | [8 empty] | 2022-11-10 | Connected |  | No
National Grid | LYNN | 436299 | 1902 | 6 | Solar | 12_22W2 | 2022-06-21 16:54 | 2022-06-22 | 1 | 0 | 1 | 2022-06-23 | 2022-07-27 | 24 | 0 | 24 | [20 empty] | 2022-07-29 | 2022-06-21 17:26 | 2023-08-18 |  | EXP | [8 empty] | 2022-10-10 | Connected |  | No
National Grid | LAWRENCE | 436374 | 1843 | 3.8 | Solar | 14_61L3 | 2022-06-21 17:26 | 2022-06-22 | 1 | 0 | 1 | 2022-06-23 | 2022-07-28 | 25 | 0 | 25 | [20 empty] | 2022-08-02 | 2022-06-22 10:09 | 2024-05-01 | Yes | EXP | [9 empty] | Completion Documents |  | No
National Grid | ATTLEBORO | 433514 | 2703 | 10 | Solar | 05_9L2 | 2022-06-22 10:09 | 2022-06-23 | 2 | 0 | 2 | 2022-06-27 | 2022-07-28 | 23 | 0 | 23 | [20 empty] | 2022-08-01 | 2022-06-22 17:53 | 2024-01-07 | Yes | EXP |  | 2023-01-07 | 2023-01-06 | 0 | 0 | 0 |  |  | 2023-02-03 | Connected |  | No
National Grid | ORANGE | 432618 | 1364 | 9.6 | Solar | 09_705W3 | 2022-06-22 17:53 | 2022-06-23 | 2 | 0 | 2 | 2022-06-27 | 2022-07-29 | 24 | 0 | 24 | [20 empty] | 2022-07-29 |  | 2024-01-05 | Yes | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 433662 | 1843 | 10 | Solar | 14_61L3 | 2022-06-22 18:43 | 2022-06-23 | 2 | 0 | 2 | 2022-06-27 | 2022-08-24 | 42 | 19 | 23 | [20 empty] | 2022-08-25 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHARLTON | 420713 | 1507 | 240 | Solar | 01_406L1 | 2022-06-22 21:00 | 2022-06-23 | 74 | 64 | 10 | [10 empty] | 2022-10-11 | 2024-01-26 | 322 | 298 | 24 | [11 empty] | 2022-06-23 08:03 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | ROYALSTON | 435569 | 1331 | 9.86 | Solar | 09_702W2 | 2022-06-23 08:03 | 2022-06-24 | 1 | 0 | 1 | 2022-06-27 | 2022-07-29 | 24 | 0 | 24 | [20 empty] | 2022-08-01 |  | 2023-11-13 | Yes | EXP |  | 2022-10-06 | 2022-11-10 | 36 | 0 | 36 |  |  | 2023-04-27 | Connected |  | No
National Grid | NORWELL | 438286 | 2061 | 15.2 | Solar | 07_915W35 | 2022-06-23 10:06 | 2022-06-24 | 22 | 19 | 3 | 2022-07-27 | 2022-08-17 | 16 | 0 | 16 | [20 empty] | 2022-08-23 | 2022-06-23 11:27 | 2023-11-06 |  | EXP | [8 empty] | 2022-11-21 | Connected |  | Yes
National Grid | MARLBOROUGH | 436246 | 1752 | 9.984 | Solar | 05_311W4 | 2022-06-23 11:27 | 2022-06-24 | 1 | 0 | 1 | 2022-06-27 | 2022-07-28 | 23 | 0 | 23 | [20 empty] | 2022-08-01 |  |  | Yes | EXP |  | 2022-09-15 | 2022-10-18 | 34 | 0 | 34 |  |  | 2023-05-19 | Connected |  | No
National Grid | LEOMINSTER | 439536 | 1453 | 18.56 | Solar | 01_219W4 | 2022-06-23 12:08 | 2022-06-24 | 12 | 10 | 2 | 2022-07-13 | 2022-08-09 | 20 | 0 | 20 | [20 empty] | 2022-08-10 |  | 2023-08-15 |  | EXP | [8 empty] | 2022-11-22 | Connected |  | Yes
National Grid | SOUTHBOROUGH | 439607 | 1772 | 15.2 | Solar | 05_310W3 | 2022-06-23 13:05 | 2022-06-24 | 4 | 0 | 4 | 2022-06-30 | 2022-08-01 | 22 | 0 | 22 | [20 empty] | 2022-08-02 | 2022-06-23 13:08 | 2023-08-10 |  | EXP | [8 empty] | 2023-01-25 | Connected |  | No
National Grid | BARRE | 439587 | 1005 | 15.2 | Solar | 09_604W4 | 2022-06-23 13:08 | 2022-06-24 | 9 | 5 | 4 | 2022-07-07 | 2022-08-02 | 19 | 0 | 19 | [20 empty] | 2022-08-02 | 2022-06-23 13:25 | 2023-09-19 | Yes | EXP |  | 2022-09-07 | 2022-09-19 | 13 | 0 | 13 |  |  | 2022-12-13 | Connected |  | No
National Grid | FRANKLIN | 432298 | 2038 | 10 | Solar | 05_348W5 | 2022-06-23 13:25 | 2022-06-24 | 1 | 0 | 1 | 2022-06-27 | 2022-07-28 | 23 | 0 | 23 | [20 empty] | 2022-08-01 | 2022-06-23 14:32 | 2024-08-05 | Yes | EXP |  | 2023-01-07 | 2023-08-03 | 209 | 0 | 209 |  |  | 2023-08-16 | Connected |  | No
National Grid | MANCHESTER BY THE SEA | 432837 | 1944 | 230 | Solar | 12_51T1 | 2022-06-23 14:32 | 2022-06-24 | 25 | 15 | 10 | [10 empty] | 2022-08-01 | 2022-08-31 | 23 | 4 | 19 | [10 empty] | 2023-06-28 |  | 2024-06-22 | Yes | STD | [9 empty] | Design |  | Yes
National Grid | PEMBROKE | 439708 | 2359 | 15.2 | Solar | 07_910W25 | 2022-06-23 14:38 | 2022-06-24 | 2 | 0 | 2 | 2022-06-28 | 2022-07-28 | 22 | 0 | 22 | [20 empty] | 2022-07-29 |  | 2023-08-01 |  | EXP | [8 empty] | 2022-12-22 | Connected |  | No
National Grid | CHARLTON | 439718 | 1507 | 15.2 | Solar | 01_406L1 | 2022-06-23 15:01 | 2022-06-24 | 1 | 0 | 1 | 2022-06-27 | 2022-07-28 | 23 | 0 | 23 | [20 empty] | 2022-07-29 |  | 2023-08-03 |  | EXP | [8 empty] | 2023-04-05 | Connected |  | Yes
National Grid | FALL RIVER | 439740 | 2721 | 15.2 | Solar | 05_115W54 | 2022-06-23 16:04 | 2022-06-24 | 42 | 33 | 9 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | PEPPERELL | 435399 | 1463 | 10 | Solar | 01_226L2 | 2022-06-23 16:11 | 2022-06-24 | 20 | 16 | 4 | 2022-07-22 | 2022-10-25 | 65 | 45 | 20 | [20 empty] | 2022-11-03 |  | 2023-11-22 |  | EXP | [8 empty] | 2023-03-10 | Connected |  | No
National Grid | BRIDGEWATER | 439899 | 2324 | 20 | Solar | 07_912W55 | 2022-06-24 11:53 | 2022-06-27 | 5 | 2 | 3 | 2022-07-01 | 2022-08-02 | 22 | 0 | 22 | [20 empty] | 2022-08-05 | 2022-06-24 12:22 | 2023-08-09 |  | EXP | [8 empty] | 2023-02-02 | Connected |  | No
National Grid | HALIFAX | 437722 | 2338 | 6 | Solar | 07_912W75 | 2022-06-24 12:22 | 2022-06-27 | 2 | 0 | 2 | 2022-06-29 | 2022-09-07 | 49 | 25 | 24 | [20 empty] | 2022-09-08 |  | 2023-12-21 | Yes | EXP |  | 2022-12-22 | 2022-12-21 | 0 | 0 | 0 |  |  | 2023-01-26 | Connected |  | No
National Grid | STOUGHTON | 437242 | 2072 | 6 | Solar | 07_94W44 | 2022-06-24 18:03 | 2022-06-27 | 2 | 0 | 2 | 2022-06-29 | 2022-07-28 | 21 | 0 | 21 | [20 empty] | 2022-08-03 | 2022-06-26 09:17 | 2023-09-06 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GRAFTON | 425991 | 1519 | 7.25 | Solar | 01_304W2 | 2022-06-26 09:17 | 2022-06-27 | 16 | 13 | 3 | 2022-07-19 | 2022-08-09 | 16 | 0 | 16 | [20 empty] | 2022-08-09 |  | 2024-04-03 | Yes | EXP |  | 2023-03-25 | 2023-04-04 | 11 | 0 | 11 |  |  | 2023-04-05 | Connected |  | No
National Grid | MILLBURY | 427594 | 1527 | 15.66 | Solar | 01_304W3 | 2022-06-26 12:04 | 2022-06-27 | 47 | 44 | 3 | 2022-08-31 | 2022-09-16 | 12 | 0 | 12 | [20 empty] | 2022-09-19 | 2022-06-26 13:01 | 2023-10-12 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GARDNER | 438200 | 1440 | 7.25 | Solar | 01_607W5 | 2022-06-26 13:01 | 2022-06-27 | 8 | 6 | 2 | 2022-07-07 | 2022-08-02 | 19 | 0 | 19 | [20 empty] | 2022-08-05 | 2022-06-26 13:20 | 2024-02-18 | Yes | EXP |  | 2023-02-07 | 2023-02-16 | 10 | 0 | 10 |  |  | 2023-03-06 | Connected |  | No
National Grid | LEOMINSTER | 439256 | 1453 | 4.64 | Solar | 01_207W3 | 2022-06-26 13:20 | 2022-06-27 | 18 | 17 | 1 | 2022-07-22 | 2022-08-15 | 17 | 0 | 17 | [20 empty] | 2022-08-15 |  | 2023-08-19 | Yes | EXP |  | 2022-09-21 | 2022-10-11 | 21 | 0 | 21 |  |  | 2023-05-05 | Connected |  | No
National Grid | SCITUATE | 434617 | 2066 | 9.57 | Solar | 07_96W40 | 2022-06-27 08:34 | 2022-06-28 | 2 | 0 | 2 | 2022-06-30 | 2022-07-28 | 20 | 0 | 20 | [20 empty] | 2022-08-03 | 2022-06-27 10:45 | 2023-08-04 |  | EXP | [8 empty] | 2023-07-31 | Connected |  | Yes
National Grid | NORTH DIGHTON | 425019 | 2764 | 7.68 | Solar | 05_19W74 | 2022-06-27 10:45 | 2022-06-28 | 2 | 0 | 2 | 2022-06-30 | 2023-08-28 | 290 | 270 | 20 | [20 empty] | 2023-08-30 |  | 2024-09-13 | Yes | EXP |  | 2023-11-28 | 2024-01-16 | 50 | 3 | 47 |  |  | 2024-01-20 | Connected |  | No
National Grid | WORCESTER | 438934 | 1610 | 150 | Solar | 01_HT17 | 2022-06-27 11:09 | 2022-06-28 | 9 | 0 | 9 | [10 empty] | 2022-07-12 | 2022-08-10 | 22 | 0 | 22 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 438978 | 1610 | 100 | Solar | 01_HT27 | 2022-06-27 11:11 | 2022-06-28 | 9 | 0 | 9 | [10 empty] | 2022-07-12 | 2022-08-10 | 22 | 0 | 22 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | PALMER | 440288 | 1069 | 18.85 | Solar | 09_503L1 | 2022-06-27 11:53 | 2022-06-28 | 4 | 1 | 3 | 2022-09-09 | 2022-09-28 | 14 | 14 | 0 | 2022-10-05 | 2022-11-09 | 25 | 0 | 25 | [5 empty] | 2022-10-05 | 2022-11-09 | 25 | 0 | 25 | [5 empty] | 2022-11-17 |  | 2024-03-05 |  | EXP |  | 2023-01-07 | 2023-03-06 | 59 | 0 | 59 |  |  | 2023-03-09 | Connected |  | Yes
National Grid | NORTON | 440304 | 2766 | 15.2 | Solar | 05_8L4 | 2022-06-27 12:03 | 2022-06-28 | 2 | 0 | 2 | 2022-06-30 | 2022-07-29 | 21 | 0 | 21 | [20 empty] | 2022-08-10 | 2022-06-27 13:29 | 2023-09-08 |  | EXP | [8 empty] | 2022-11-14 | Connected |  | No
National Grid | RANDOLPH | 438829 | 2368 | 6 | Solar | 07_97W2 | 2022-06-27 13:29 | 2022-06-28 | 2 | 0 | 2 | 2022-06-30 | 2022-07-28 | 20 | 0 | 20 | [20 empty] | 2022-08-01 |  | 2025-03-24 | Yes | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | NORTHAMPTON | 426180 | 1060 | 580 | Solar | 09_901W1 | 2022-06-27 15:57 | 2022-06-28 | 31 | 23 | 8 | [10 empty] | 2022-08-11 | 2022-09-08 | 20 | 0 | 20 | [10 empty] | 2023-07-12 |  |  |  | STD | [9 empty] | Design |  | No
National Grid | DUDLEY | 440471 | 1571 | 15.2 | Solar | 01_412L4 | 2022-06-27 17:17 | 2022-06-28 | 3 | 0 | 3 | 2022-07-01 | 2022-08-02 | 22 | 0 | 22 | [20 empty] | 2022-08-05 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTON | 426000 | 2766 | 11.89 | Solar | 05_8L3 | 2022-06-28 01:18 | 2022-06-29 | 15 | 14 | 1 | 2022-07-21 | 2022-08-17 | 20 | 0 | 20 | [20 empty] | 2022-08-18 |  | 2023-08-29 |  | EXP | [8 empty] | 2022-11-08 | Connected |  | No
National Grid | MANCHESTER | 429415 | 1944 | 10 | Solar | 12_23H3 | 2022-06-28 09:21 | 2022-06-29 | 2 | 0 | 2 | 2022-07-01 | 2022-08-02 | 22 | 0 | 22 | [20 empty] | 2022-08-05 |  | 2023-08-17 |  | EXP | [8 empty] | 2022-10-27 | Connected |  | Yes
National Grid | NANTUCKET | 436989 | 2554 | 17.6 | Solar | 04_101L2 | 2022-06-28 10:20 | 2022-06-29 | 5 | 3 | 2 | 2022-07-06 | 2022-08-17 | 31 | 10 | 21 | [20 empty] | 2022-08-19 |  | 2023-08-31 |  | EXP | [8 empty] | 2022-12-13 | Connected |  | No
National Grid | SEEKONK | 432969 | 2771 | 4999.2 | Battery Add-On | 05_7L2 | 2022-06-28 13:33 | 2022-06-29 | 9 | 0 | 9 | [10 empty] | 2022-07-13 | 2022-08-08 | 19 | 0 | 19 | [11 empty] | 2022-06-28 15:52 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTMINSTER | 413977 | 1473 | 13.05 | Solar | 01_609W2 | 2022-06-28 15:52 | 2022-06-29 | 3 | 0 | 3 | 2022-07-05 | 2022-08-02 | 21 | 0 | 21 | [20 empty] | 2022-08-05 |  | 2024-01-18 | Yes | EXP |  | 2023-01-07 | 2023-01-14 | 8 | 0 | 8 |  |  | 2023-06-29 | Connected |  | No
National Grid | GARDNER | 437898 | 1440 | 10 | Solar | 01_607W4 | 2022-06-28 17:28 | 2022-06-29 | 48 | 26 | 22 | [26 empty] | 2022-06-29 10:46 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SALISBURY | 440658 | 1952 | 7.6 | Solar | 14_7L1 | 2022-06-29 10:46 | 2022-06-30 | 1 | 0 | 1 | 2022-07-01 | 2022-08-03 | 23 | 0 | 23 | [20 empty] | 2022-08-03 |  | 2023-08-30 | Yes | EXP |  | 2022-11-02 | 2022-11-08 | 7 | 0 | 7 |  |  | 2022-11-10 | Connected |  | No
National Grid | SPENCER | 431528 | 1562 | 15.66 | Solar | 01_552L1 | 2022-06-29 11:04 | 2022-06-30 | 23 | 22 | 1 | 2022-08-02 | 2022-09-30 | 42 | 21 | 21 | [20 empty] | 2022-09-30 |  | 2023-10-24 |  | EXP | [8 empty] | 2022-11-10 | Connected |  | No
National Grid | NORTH BILLERICA | 419848 | 1862 | 4992 | Other | 14_70L1 | 2022-06-29 11:35 | 2022-06-30 | 9 | 2 | 7 | [10 empty] | 2022-07-13 | 2022-08-09 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | CHELMSFORD | 439488 | 1824 | 5.76 | Solar | 14_24L1 | 2022-06-29 14:52 | 2022-06-30 | 2 | 0 | 2 | 2022-07-05 | 2022-08-04 | 23 | 0 | 23 | [20 empty] | 2022-08-09 | 2022-06-29 14:54 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 439483 | 1843 | 6 | Solar | 14_61L3 | 2022-06-29 14:54 | 2022-06-30 | 2 | 0 | 2 | 2022-07-05 | 2022-08-02 | 21 | 0 | 21 | [20 empty] | 2022-08-05 | 2022-06-29 15:17 | 2024-04-13 | Yes | EXP |  | 2023-03-15 | 2023-04-12 | 29 | 0 | 29 |  |  | 2023-06-12 | Connected |  | No
National Grid | HAVERHILL | 438729 | 1832 | 6 | Solar | 14_48L4 | 2022-06-29 15:17 | 2022-06-30 | 3 | 0 | 3 | 2022-07-06 | 2022-08-10 | 26 | 4 | 22 | [20 empty] | 2022-08-11 |  | 2023-08-25 | Yes | EXP |  | 2022-10-13 | 2022-10-25 | 13 | 0 | 13 |  |  | 2022-10-31 | Connected |  | Yes
National Grid | NORTHBRIDGE | 427162 | 1534 | 9.8 | Solar | 05_320W3 | 2022-06-29 15:39 | 2022-06-30 | 1 | 0 | 1 | 2022-07-01 | 2022-08-01 | 21 | 0 | 21 | [20 empty] | 2022-08-02 |  | 2023-08-03 |  | EXP | [8 empty] | 2022-12-02 | Connected |  | No
National Grid | WARE | 434992 | 1082 | 8.99 | Solar | 09_501L2 | 2022-06-29 16:20 | 2022-06-30 | 1 | 0 | 1 | 2022-07-01 | 2022-08-02 | 22 | 0 | 22 | [20 empty] | 2022-08-02 |  | 2023-08-03 |  | EXP | [8 empty] | 2022-09-13 | Connected |  | No
National Grid | GARDNER | 439984 | 1440 | 9.86 | Solar | 01_607W3 | 2022-06-29 16:30 | 2022-06-30 | 1 | 0 | 1 | 2022-07-01 | 2022-08-02 | 22 | 0 | 22 | [20 empty] | 2022-08-02 |  | 2023-08-04 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | PEPPERELL | 440673 | 1463 | 9.28 | Solar | 01_226L2 | 2022-06-30 09:55 | 2022-07-01 | 1 | 0 | 1 | 2022-07-05 | 2022-08-04 | 23 | 0 | 23 | [20 empty] | 2022-08-09 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 406009 | 2301 | 5.52 | Solar | 07_20W13 | 2022-06-30 16:13 | 2022-07-01 | 156 | 17 | 139 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MARLBOROUGH | 441361 | 1752 | 15.2 | Solar | 05_311W2 | 2022-06-30 16:32 | 2022-07-01 | 4 | 3 | 1 | 2022-07-08 | 2022-10-28 | 79 | 51 | 28 | [21 empty] | 2022-06-30 17:41 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SALEM | 431968 | 1970 | 7.83 | Solar | 12_49W4 | 2022-06-30 17:41 | 2022-07-01 | 3 | 2 | 1 | 2022-07-06 | 2022-08-09 | 26 | 2 | 24 | [20 empty] | 2022-08-09 |  | 2024-05-22 | Yes | EXP |  | 2022-11-15 | 2023-05-19 | 186 | 0 | 186 |  |  | 2023-06-17 | Connected |  | No
National Grid | OXFORD | 440487 | 1540 | 3.8 | Solar | 01_406L3 | 2022-07-01 10:50 | 2022-07-05 | 1 | 0 | 1 | 2022-07-06 | 2022-08-02 | 20 | 0 | 20 | [20 empty] | 2022-08-03 | 2022-07-01 10:55 | 2023-09-06 |  | EXP | [8 empty] | 2023-01-26 | Connected |  | No
National Grid | PETERSHAM | 436738 | 1366 | 3.8 | Solar | 09_604W1 | 2022-07-01 10:55 | 2022-07-05 | 6 | 3 | 3 | 2022-07-13 | 2022-08-04 | 17 | 0 | 17 | [20 empty] | 2022-08-10 |  | 2024-08-08 | Yes | EXP |  | 2023-03-07 | 2023-08-02 | 149 | 0 | 149 |  |  |  | Completion Documents |  | No
National Grid | LEOMINSTER | 435106 | 1453 | 4000 | Other | 01_207W3 | 2022-07-01 18:43 | 2022-07-05 | 78 | 68 | 10 | [10 empty] | 2022-10-25 | 2022-11-17 | 17 | 0 | 17 | [14 empty] | STD | [9 empty] | Group Study |  | Yes
National Grid | WORCESTER | 441629 | 1602 | 16.82 | Solar | 01_16J1 | 2022-07-04 03:19 | 2022-07-05 | 50 | 47 | 3 | [26 empty] | 2022-07-04 18:44 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SEEKONK | 432869 | 2771 | 7.6 | Solar | 05_7L4 | 2022-07-04 18:44 | 2022-07-05 | 2 | 0 | 2 | 2022-07-07 | 2022-08-05 | 22 | 0 | 22 | [20 empty] | 2022-08-09 |  | 2024-04-17 | Yes | EXP |  | 2022-10-14 | 2022-12-21 | 69 | 0 | 69 |  |  |  | Completion Documents |  | Yes
National Grid | LEOMINSTER | 435107 | 1453 | 4000 | Other | 01_207W3 | 2022-07-05 09:48 | 2022-07-06 | 75 | 65 | 10 | [10 empty] | 2022-10-21 | 2022-11-08 | 13 | 0 | 13 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | BRIDGEWATER | 435095 | 2324 | 9000 | Other | 07_912W73 | 2022-07-05 10:40 | 2022-07-06 | 210 | 202 | 8 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | FRANKLIN | 440655 | 2038 | 22.8 | Solar | 05_344W1 | 2022-07-05 13:33 | 2022-07-06 | 4 | 3 | 1 | 2022-07-11 | 2022-08-04 | 19 | 0 | 19 | [20 empty] | 2022-08-05 |  | 2023-12-11 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MELROSE | 435099 | 2176 | 6000 | Other | 12_2335 | 2022-07-05 15:26 | 2022-07-06 | 81 | 71 | 10 | [10 empty] | 2022-10-31 | 2022-11-30 | 21 | 1 | 20 | [11 empty] | 2022-07-05 15:35 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 438914 | 2301 | 6 | Solar | 07_91W43 | 2022-07-05 15:35 | 2022-07-06 | 27 | 24 | 3 | 2022-08-12 | 2022-09-12 | 22 | 2 | 20 | [20 empty] | 2022-09-14 | 2022-07-05 19:54 | 2024-05-22 | Yes | EXP |  | 2023-05-13 | 2023-05-19 | 7 | 0 | 7 |  |  | 2023-07-24 | Connected |  | No
National Grid | HANSON | 436781 | 2341 | 7.6 | Solar | 07_93W43 | 2022-07-05 19:54 | 2022-07-06 | 1 | 0 | 1 | 2022-07-07 | 2022-08-12 | 28 | 8 | 20 | [20 empty] | 2022-08-12 |  | 2023-09-07 | Yes | EXP |  | 2022-10-12 | 2022-10-26 | 15 | 0 | 15 |  |  | 2023-01-30 | Connected |  | No
National Grid | HANSON | 439549 | 2341 | 15 | Solar | 07_797W24 | 2022-07-06 08:28 | 2022-07-07 | 3 | 2 | 1 | 2022-07-11 | 2022-09-23 | 54 | 34 | 20 | [20 empty] | 2022-09-26 |  | 2023-11-09 |  | EXP | [8 empty] | 2022-11-28 | Connected |  | No
National Grid | OXFORD | 398616 | 1540 | 11.4 | Solar | 01_406L4 | 2022-07-06 11:17 | 2022-07-07 | 3 | 2 | 1 | 2022-07-12 | 2022-08-02 | 16 | 0 | 16 | [20 empty] | 2022-08-03 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 438734 | 2302 | 10 | Solar | 07_911W56 | 2022-07-06 11:48 | 2022-07-07 | 4 | 1 | 3 | 2022-07-13 | 2022-08-08 | 19 | 0 | 19 | [20 empty] | 2022-08-09 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EVERETT | 433145 | 2149 | 3000 | Other | 12_2401 | 2022-07-06 14:06 | 2022-07-07 | 80 | 72 | 8 | [10 empty] | 2022-10-31 | 2022-11-22 | 16 | 0 | 16 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | BILLERICA | 396676 | 1862 | 4999.2 | Battery Add-On | 14_70L3 | 2022-07-06 14:20 | 2022-07-07 | 26 | 16 | 10 | [10 empty] | 2022-08-11 | 2022-09-16 | 27 | 7 | 20 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | FRANKLIN | 412237 | 2038 | 4999.2 | Battery Add-On | 05_344W3 | 2022-07-06 14:29 | 2022-07-07 | 18 | 9 | 9 | [10 empty] | 2022-08-02 | 2022-08-29 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | BROCKTON | 431649 | 2301 | 4999.2 | Battery Add-On | 07_98W10 | 2022-07-06 14:47 | 2022-07-07 | 26 | 16 | 10 | [10 empty] | 2022-08-11 | 2022-09-08 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | PEMBROKE | 431674 | 2359 | 4999.2 | Battery Add-On | 07_910W25 | 2022-07-06 15:29 | 2022-07-07 | 26 | 16 | 10 | [10 empty] | 2022-08-11 | 2022-09-08 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | FRANKLIN | 434015 | 2038 | 4999.2 | Battery Add-On | 05_344W2 | 2022-07-06 15:35 | 2022-07-07 | 18 | 9 | 9 | [10 empty] | 2022-08-02 | 2022-08-29 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | WRENTHAM | 434016 | 2093 | 4999.2 | Battery Add-On | 05_3337W1 | 2022-07-06 15:37 | 2022-07-07 | 19 | 9 | 10 | [10 empty] | 2022-08-02 | 2022-08-29 | 20 | 0 | 20 | [11 empty] | 2022-07-07 12:43 |  |  | STD | [9 empty] | Group Study |  | No
National Grid | NORTHAMPTON | 442267 | 1062 | 22.8 | Solar | 09_909W2 | 2022-07-07 12:43 | 2022-07-08 | 4 | 3 | 1 | 2022-07-13 | 2022-08-09 | 20 | 0 | 20 | [20 empty] | 2022-08-10 | 2022-07-07 13:48 | 2023-09-03 | Yes | EXP |  | 2022-10-13 | 2022-10-20 | 8 | 0 | 8 |  |  | 2022-11-08 | Connected |  | No
National Grid | BELCHERTOWN | 437714 | 1007 | 10 | Solar | 09_523L2 | 2022-07-07 13:48 | 2022-07-08 | 3 | 0 | 3 | 2022-07-13 | 2022-08-03 | 16 | 0 | 16 | [20 empty] | 2022-08-05 |  | 2024-04-06 | Yes | EXP |  | 2022-12-22 | 2023-04-05 | 105 | 0 | 105 |  |  | 2023-04-11 | Connected |  | No
National Grid | EAST LONGMEADOW | 442568 | 1028 | 15.2 | Solar | 09_508L4 | 2022-07-07 14:26 | 2022-07-08 | 1 | 0 | 1 | 2022-07-11 | 2022-08-02 | 17 | 0 | 17 | [20 empty] | 2022-08-05 |  | 2023-11-23 |  | EXP | [8 empty] | 2022-12-07 | Connected |  | No
National Grid | BELLINGHAM | 442113 | 2019 | 240 | Solar | 05_344W4 | 2022-07-08 08:37 | 2022-07-11 | 13 | 3 | 10 | [10 empty] | 2022-07-27 | 2022-08-30 | 25 | 0 | 25 | [14 empty] | STD | [9 empty] | Group Study |  | Yes
National Grid | SHEFFIELD | 438170 | 1257 | 250 | Solar | 09_1108W1 | 2022-07-08 11:26 | 2022-07-11 | 12 | 3 | 9 | [10 empty] | 2022-07-27 | 2022-08-30 | 25 | 0 | 25 | [10 empty] | 2023-02-23 |  |  |  | STD | [9 empty] | Completion Documents |  | Yes
National Grid | WESTFORD | 431905 | 1886 | 7.6 | Solar | 14_57L2 | 2022-07-08 13:40 | 2022-07-11 | 8 | 7 | 1 | 2022-07-20 | 2022-08-11 | 17 | 0 | 17 | [20 empty] | 2022-08-11 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORWELL | 443129 | 2061 | 15.2 | Solar | 07_96W42 | 2022-07-11 09:30 | 2022-07-12 | 1 | 0 | 1 | 2022-07-13 | 2022-08-10 | 21 | 0 | 21 | [20 empty] | 2022-08-10 |  | 2023-08-30 |  | EXP | [8 empty] | 2023-02-02 | Connected |  | No
National Grid | HAVERHILL | 443275 | 1832 | 15.2 | Solar | 14_43L2 | 2022-07-11 12:45 | 2022-07-12 | 2 | 0 | 2 | 2022-07-14 | 2022-08-09 | 19 | 0 | 19 | [20 empty] | 2022-08-10 |  | 2023-08-16 |  | EXP | [8 empty] | 2022-10-21 | Connected |  | No
National Grid | WORCESTER | 415781 | 1606 | 8.41 | Solar | 01_24W5 | 2022-07-11 15:03 | 2022-07-12 | 30 | 27 | 3 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SAUGUS | 434702 | 1906 | 4999 | Other | 12_16W3 | 2022-07-12 08:41 | 2022-09-30 | 67 | 58 | 9 | [10 empty] | 2023-01-12 | 2023-02-24 | 30 | 10 | 20 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | METHUEN | 402955 | 1844 | 99.9 | Solar | 14_63L2 | 2022-07-12 11:32 | 2022-07-13 | 41 | 30 | 11 | 2022-09-08 | 2022-09-30 | 17 | 0 | 17 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | PLAINVILLE | 433335 | 2762 | 300 | Solar | 05_3422W3 | 2022-07-12 11:36 | 2022-07-13 | 111 | 101 | 10 | [10 empty] | 2022-12-23 | 2023-10-25 | 209 | 185 | 24 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | LOWELL | 434017 | 1852 | 4999.2 | Battery Add-On | 14_16L1 | 2022-07-12 15:16 | 2022-07-13 | 28 | 19 | 9 | [10 empty] | 2022-08-22 | 2022-09-19 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | WORCESTER | 396738 | 1607 | 4999 | Other | 01_8W1 | 2022-07-13 14:58 | 2022-07-14 | 25 | 16 | 9 | [10 empty] | 2022-08-17 | 2022-09-13 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | LEOMINSTER | 427478 | 1453 | 3000 | Other | 01_219W1 | 2022-07-13 15:01 | 2022-07-14 | 25 | 16 | 9 | [10 empty] | 2022-08-17 | 2022-09-14 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Pending Withdraw |  | No
National Grid | LEOMINSTER | 427472 | 1453 | 4999 | Other | 01_219W4 | 2022-07-13 15:02 | 2022-07-14 | 25 | 16 | 9 | [10 empty] | 2022-08-17 | 2022-09-13 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Pending Withdraw |  | No
National Grid | LEOMINSTER | 431629 | 1453 | 11.4 | Solar | 01_227W1 | 2022-07-13 16:44 | 2022-07-14 | 2 | 0 | 2 | 2022-07-18 | 2022-10-13 | 62 | 42 | 20 | [20 empty] | 2022-10-14 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GRAFTON | 444127 | 1519 | 20 | Solar | 01_304W1 | 2022-07-14 08:37 | 2022-07-15 | 1 | 1 | 0 | 2022-07-18 | 2022-08-09 | 17 | 0 | 17 | [20 empty] | 2022-08-09 |  | 2023-08-12 |  | EXP | [8 empty] | 2023-07-03 | Connected |  | No
National Grid | LEOMINSTER | 440596 | 1453 | 10 | Solar | 01_219W2 | 2022-07-14 10:37 | 2022-07-15 | 2 | 1 | 1 | 2022-07-18 | 2022-08-08 | 16 | 0 | 16 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SWANSEA | 433519 | 2777 | 10 | Solar | 05_11W84 | 2022-07-14 11:44 | 2022-07-15 | 5 | 0 | 5 | 2022-07-22 | 2022-08-18 | 20 | 0 | 20 | [20 empty] | 2022-08-21 | 2022-07-14 11:54 | 2023-08-25 |  | EXP | [8 empty] | 2023-01-21 | Connected |  | No
National Grid | WORCESTER | 442781 | 1605 | 10 | Solar | 01_27W4 | 2022-07-14 11:54 | 2022-07-15 | 2 | 0 | 2 | 2022-07-19 | 2022-08-11 | 18 | 0 | 18 | [20 empty] | 2022-08-12 |  | 2023-08-25 | Yes | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEOMINSTER | 426808 | 1453 | 9.57 | Solar | 01_225W3 | 2022-07-14 14:10 | 2022-07-15 | 16 | 9 | 7 | 2022-08-05 | 2022-10-18 | 51 | 32 | 19 | [20 empty] | 2022-10-19 | 2022-07-14 17:24 | 2023-10-26 |  | EXP | [8 empty] | 2023-04-12 | Connected |  | No
National Grid | BOLTON | 444227 | 1740 | 7.6 | Solar | 01_225W1 | 2022-07-14 17:24 | 2022-10-31 | 3 | 0 | 3 | 2022-11-03 | 2022-11-29 | 17 | 0 | 17 | [20 empty] | 2022-07-25 |  | 2024-08-30 | Yes | EXP | [8 empty] | 2023-11-18 | Connected |  | No
National Grid | BYFIELD | 443818 | 1922 | 50 | Solar | 14_60L2 | 2022-07-15 08:45 | 2022-07-18 | 10 | 0 | 10 | 2022-08-01 | 2022-09-16 | 34 | 9 | 25 | [20 empty] | 2022-09-27 |  | 2024-02-23 |  | EXP | [8 empty] | 2024-02-21 | Connected |  | No
National Grid | AYER | 443314 | 1432 | 240 | Solar | 01_201W3 | 2022-07-15 09:49 | 2022-07-18 | 9 | 0 | 9 | [10 empty] | 2022-07-29 | 2022-08-31 | 24 | 0 | 24 | [14 empty] | STD | [9 empty] | Group Study |  | Yes
National Grid | WEBSTER | 440022 | 1570 | 3.77 | Solar | 01_412L2 | 2022-07-15 15:23 | 2022-07-18 | 21 | 20 | 1 | 2022-08-15 | 2022-11-14 | 63 | 44 | 19 | [20 empty] | 2022-11-15 | 2022-07-15 15:48 | 2023-11-21 |  | EXP | [8 empty] | 2023-07-20 | Connected |  | No
National Grid | DRACUT | 441257 | 1826 | 3.48 | Solar | 14_21L2 | 2022-07-15 15:48 | 2022-07-18 | 2 | 0 | 2 | 2022-07-20 | 2022-08-11 | 17 | 0 | 17 | [20 empty] | 2022-08-15 |  | 2024-03-01 | Yes | EXP |  | 2023-02-17 | 2023-02-28 | 12 | 0 | 12 |  |  | 2023-09-06 | Connected |  | Yes
National Grid | BOLTON | 442327 | 1740 | 15 | Solar | 01_225W1 | 2022-07-18 08:23 | 2022-07-19 | 3 | 2 | 1 | 2022-07-21 | 2022-08-11 | 16 | 0 | 16 | [20 empty] | 2022-08-12 | 2022-07-18 12:42 | 2023-09-17 |  | EXP | [8 empty] | 2022-11-03 | Connected |  | No
National Grid | LEOMINSTER | 437201 | 1453 | 5.76 | Solar | 01_219W2 | 2022-07-18 12:42 | 2022-07-19 | 1 | 0 | 1 | 2022-07-20 | 2022-08-11 | 17 | 0 | 17 | [20 empty] | 2022-08-15 | 2022-07-18 12:55 | 2024-02-01 | Yes | EXP |  | 2023-01-07 | 2023-02-01 | 26 | 0 | 26 |  |  | 2023-05-08 | Connected |  | No
National Grid | LANCASTER | 438016 | 1523 | 10 | Solar | 01_216W4 | 2022-07-18 12:55 | 2022-07-19 | 2 | 0 | 2 | 2022-07-21 | 2022-08-11 | 16 | 0 | 16 | [20 empty] | 2022-08-12 |  | 2023-08-25 | Yes | EXP |  | 2022-10-11 | 2022-12-21 | 72 | 0 | 72 |  |  | 2023-01-10 | Connected |  | No
National Grid | HANOVER | 421168 | 2339 | 999 | Solar | 07_95W2 | 2022-07-18 16:28 | 2022-07-19 | 19 | 10 | 9 | [10 empty] | 2022-08-12 | 2022-09-09 | 20 | 0 | 20 | [11 empty] | 2022-07-18 20:51 |  |  | STD | [9 empty] | Group Study |  | No
National Grid | NORTH CHELMSFORD | 445187 | 1863 | 15.08 | Solar | 14_73L2 | 2022-07-18 20:51 | 2022-07-19 | 13 | 11 | 2 | 2022-08-04 | 2022-09-08 | 25 | 1 | 24 | [20 empty] | 2022-09-09 |  | 2023-10-01 | Yes | EXP |  | 2022-10-19 | 2022-11-09 | 22 | 0 | 22 |  |  | 2022-11-29 | Connected |  | No
National Grid | GRAFTON | 445236 | 1519 | 15.2 | Solar | 01_304W1 | 2022-07-19 08:49 | 2022-07-20 | 1 | 0 | 1 | 2022-07-21 | 2022-08-17 | 20 | 0 | 20 | [20 empty] | 2022-08-25 |  | 2023-09-28 |  | EXP | [8 empty] | 2023-01-12 | Connected |  | No
National Grid | DUDLEY | 442567 | 1571 | 15.2 | Solar | 01_412L5 | 2022-07-19 11:22 | 2022-07-20 | 1 | 0 | 1 | 2022-07-21 | 2022-08-17 | 20 | 0 | 20 | [20 empty] | 2022-08-17 |  | 2023-08-19 |  | EXP | [8 empty] | 2022-10-12 | Connected |  | No
National Grid | WESTFORD | 441483 | 1886 | 7.6 | Solar | 14_57L2 | 2022-07-19 11:41 | 2022-07-20 | 1 | 0 | 1 | 2022-07-21 | 2022-08-16 | 19 | 0 | 19 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTFORD | 445349 | 1886 | 7.6 | Solar | 14_73L2 | 2022-07-19 12:37 | 2022-07-20 | 4 | 3 | 1 | 2022-07-25 | 2022-10-13 | 57 | 39 | 18 | [20 empty] | 2022-10-14 | 2022-07-19 14:18 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 443258 | 1606 | 7.6 | Solar | 01_24W3 | 2022-07-19 14:18 | 2022-07-20 | 1 | 0 | 1 | 2022-07-21 | 2022-08-15 | 18 | 0 | 18 | [20 empty] | 2022-08-17 | 2022-07-19 15:11 | 2024-02-24 | Yes | EXP | [8 empty] | 2023-05-01 | Connected |  | Yes
National Grid | AUBURN | 430569 | 1501 | 11.02 | Solar | 01_26W3 | 2022-07-19 15:11 | 2022-07-20 | 1 | 0 | 1 | 2022-07-21 | 2022-08-15 | 18 | 0 | 18 | [20 empty] | 2022-08-16 | 2022-07-19 16:23 | 2023-11-16 | Yes | EXP |  | 2022-10-12 | 2022-11-14 | 34 | 0 | 34 |  |  | 2022-12-07 | Connected |  | Yes
National Grid | LEOMINSTER | 443788 | 1453 | 11.02 | Solar | 01_225W4 | 2022-07-19 16:23 | 2022-07-20 | 4 | 2 | 2 | 2022-07-26 | 2022-08-15 | 15 | 0 | 15 | [20 empty] | 2022-08-16 | 2022-07-19 19:06 | 2024-02-02 | Yes | EXP |  | 2023-02-02 | 2023-02-01 | 0 | 0 | 0 |  |  | 2023-02-28 | Connected |  | No
National Grid | ROCKPORT | 442681 | 1966 | 5.8 | Solar | 12_40J2 | 2022-07-19 19:06 | 2022-07-20 | 1 | 0 | 1 | 2022-07-21 | 2022-08-17 | 20 | 0 | 20 | [20 empty] | 2022-08-18 |  | 2024-04-23 | Yes | EXP |  | 2022-12-22 | 2023-04-24 | 124 | 0 | 124 |  |  | 2023-04-27 | Connected |  | No
National Grid | COHASSET | 440798 | 2025 | 9.86 | Solar | 07_915W37 | 2022-07-19 21:18 | 2022-07-20 | 2 | 0 | 2 | 2022-07-22 | 2022-08-18 | 20 | 0 | 20 | [20 empty] | 2022-08-22 |  | 2023-08-26 |  | EXP | [8 empty] | 2023-03-14 | Connected |  | No
National Grid | SPENCER | 445609 | 1562 | 24 | Solar | 01_552L1 | 2022-07-20 12:00 | 2022-10-19 | 29 | 20 | 9 | 2022-12-01 | 2022-12-19 | 13 | 0 | 13 | [20 empty] | 2022-12-20 |  | 2024-01-19 |  | EXP | [8 empty] | 2023-04-03 | Connected |  | No
National Grid | FRANKLIN | 422051 | 2038 | 4999.2 | Battery Add-On | 05_348W6 | 2022-07-20 13:06 | 2022-07-21 | 8 | 0 | 8 | [10 empty] | 2022-08-02 | 2022-08-29 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | WESTFORD | 442456 | 1886 | 7.6 | Solar | 14_73L2 | 2022-07-20 16:31 | 2022-07-21 | 1 | 0 | 1 | 2022-07-22 | 2022-08-12 | 16 | 0 | 16 | [20 empty] | 2022-08-15 | 2022-07-20 17:30 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 440578 | 1606 | 8.41 | Solar | 01_24W5 | 2022-07-20 17:30 | 2022-07-21 | 11 | 8 | 3 | 2022-08-04 | 2022-09-13 | 28 | 7 | 21 | [20 empty] | 2022-09-15 |  | 2024-06-08 | Yes | EXP |  | 2023-05-24 | 2023-06-08 | 16 | 0 | 16 |  |  | 2023-06-30 | Connected |  | Yes
National Grid | TEWKSBURY | 444078 | 1876 | 9.8 | Solar | 14_70L1 | 2022-07-20 17:52 | 2022-07-21 | 38 | 26 | 12 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 445969 | 1609 | 7.6 | Solar | 01_23W1 | 2022-07-21 13:15 | 2022-07-22 | 1 | 0 | 1 | 2022-07-25 | 2022-08-18 | 19 | 0 | 19 | [20 empty] | 2022-08-18 |  | 2023-08-19 |  | EXP | [8 empty] | 2023-03-31 | Connected |  | No
National Grid | LOWELL | 424750 | 1850 | 7.6 | Solar | 14_21L2 | 2022-07-21 18:03 | 2022-07-22 | 13 | 10 | 3 | 2022-08-10 | 2022-09-29 | 36 | 16 | 20 | [20 empty] | 2022-09-30 |  | 2024-01-20 |  | EXP | [8 empty] | 2023-04-28 | Connected |  | No
National Grid | LEOMINSTER | 412235 | 1453 | 4999.2 | Battery Add-On | 01_207W1 | 2022-07-22 07:23 | 2022-07-25 | 9 | 0 | 9 | [10 empty] | 2022-08-05 | 2022-09-01 | 20 | 0 | 20 | [11 empty] | 2022-07-22 10:42 |  |  | STD | [9 empty] | Group Study |  | No
National Grid | AUBURN | 438906 | 1501 | 9.86 | Solar | 01_26W1 | 2022-07-22 10:42 | 2022-07-25 | 2 | 2 | 0 | 2022-07-27 | 2022-08-17 | 16 | 0 | 16 | [20 empty] | 2022-08-17 |  | 2023-09-01 | Yes | EXP |  | 2022-10-20 | 2023-03-08 | 140 | 0 | 140 |  |  | 2023-03-09 | Connected |  | No
National Grid | BEVERLY | 438522 | 1915 | 50 | Solar | 12_12J7 | 2022-07-22 11:31 | 2022-07-25 | 36 | 26 | 10 | [10 empty] | 2022-09-14 | 2022-10-11 | 19 | 0 | 19 | [10 empty] | 2024-02-28 |  |  |  | STD | [9 empty] | Conditional Approval |  | Yes
National Grid | NORTH ANDOVER | 446210 | 1845 | 15.2 | Solar | 14_56L2 | 2022-07-22 11:53 | 2022-07-25 | 0 | 0 | 0 | 2022-07-25 | 2022-08-16 | 17 | 0 | 17 | [20 empty] | 2022-08-17 |  | 2023-08-18 |  | EXP | [8 empty] | 2023-06-24 | Connected |  | No
National Grid | WILBRAHAM | 446236 | 1095 | 15.2 | Solar | 09_507L3 | 2022-07-22 12:32 | 2022-07-25 | 0 | 0 | 0 | 2022-07-25 | 2022-08-17 | 18 | 0 | 18 | [20 empty] | 2022-08-25 | 2022-07-22 14:33 | 2023-08-29 |  | EXP | [8 empty] | 2022-10-18 | Connected |  | No
National Grid | WINCHENDON | 441942 | 1475 | 7.54 | Solar | 01_612W1 | 2022-07-22 14:33 | 2022-07-25 | 2 | 1 | 1 | 2022-07-27 | 2022-08-26 | 23 | 4 | 19 | [20 empty] | 2022-08-26 |  | 2023-09-02 | Yes | EXP |  | 2022-09-21 | 2022-11-01 | 41 | 0 | 41 |  |  | 2023-01-20 | Connected |  | No
National Grid | BEVERLY | 446332 | 1915 | 50 | Solar | 12_12J7 | 2022-07-22 16:07 | 2022-07-25 | 39 | 29 | 10 | [10 empty] | 2022-09-19 | 2022-10-17 | 20 | 0 | 20 | [10 empty] | 2024-02-28 |  |  |  | STD | [9 empty] | Conditional Approval |  | Yes
National Grid | LAWRENCE | 446168 | 1840 | 50 | Solar | 14_1325 | 2022-07-22 17:06 | 2022-07-25 | 13 | 4 | 9 | 2022-08-11 | 2022-09-22 | 30 | 10 | 20 | [20 empty] | 2022-10-05 |  | 2024-08-04 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | FALL RIVER | 440461 | 2721 | 250 | Solar | 05_115W53 | 2022-07-25 11:27 | 2022-07-26 | 12 | 2 | 10 | 2022-08-11 | 2022-09-15 | 25 | 0 | 25 | [20 empty] | 2024-03-29 | 2022-07-25 18:57 |  |  | EXP | [9 empty] | Conditional Approval |  | No
National Grid | LYNN | 445004 | 1905 | 10 | Solar | 12_19W1 | 2022-07-25 18:57 | 2022-07-26 | 15 | 15 | 0 | 2022-08-16 | 2022-09-12 | 19 | 0 | 19 | [20 empty] | 2022-09-22 |  | 2023-09-29 | Yes | EXP |  | 2023-03-23 | 2023-04-21 | 30 | 0 | 30 |  |  | 2023-05-01 | Connected |  | No
National Grid | LEOMINSTER | 445310 | 1453 | 100 | Solar | 01_207W4 | 2022-07-26 11:31 | 2022-07-27 | 24 | 15 | 9 | [10 empty] | 2022-08-30 | 2022-10-03 | 24 | 0 | 24 | [11 empty] | 2022-07-26 19:07 |  |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | CHELMSFORD | 418712 | 1824 | 6 | Solar | 14_16L1 | 2022-07-26 19:07 | 2022-07-27 | 2 | 0 | 2 | 2022-07-29 | 2022-08-23 | 18 | 0 | 18 | [20 empty] | 2022-08-29 |  | 2024-05-10 | Yes | EXP |  | 2023-02-22 | 2023-05-10 | 78 | 0 | 78 |  |  | 2023-05-23 | Connected |  | Yes
National Grid | NORTH GRAFTON | 440801 | 1536 | 11.89 | Solar | 01_304W4 | 2022-07-27 08:45 | 2022-07-28 | 4 | 3 | 1 | 2022-08-02 | 2022-08-31 | 22 | 1 | 21 | [20 empty] | 2022-09-01 |  | 2023-09-06 |  | EXP | [8 empty] | 2022-09-07 | Connected |  | No
National Grid | PEMBROKE | 445451 | 2359 | 1500 | Solar | 07_910W51 | 2022-07-27 09:20 | 2022-07-28 | 12 | 3 | 9 | [10 empty] | 2022-08-15 | 2022-09-13 | 22 | 2 | 20 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTH EASTON | 422073 | 2356 | 4999.2 | Battery Add-On | 07_92W78 | 2022-07-27 12:47 | 2022-07-28 | 12 | 2 | 10 | [10 empty] | 2022-08-12 | 2022-09-09 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | HANOVER | 412226 | 2339 | 4999.2 | Battery Add-On | 07_95W1 | 2022-07-27 12:49 | 2022-07-28 | 10 | 0 | 10 | [10 empty] | 2022-08-11 | 2022-09-08 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | BROCKTON | 445947 | 2302 | 6 | Solar | 07_911W56 | 2022-07-27 12:50 | 2022-07-28 | 2 | 0 | 2 | 2022-08-01 | 2022-08-24 | 18 | 0 | 18 | [20 empty] | 2022-08-25 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 442032 | 1605 | 3.8 | Solar | 01_24W1 | 2022-07-27 13:00 | 2022-07-28 | 2 | 0 | 2 | 2022-08-01 | 2022-08-31 | 23 | 0 | 23 | [20 empty] | 2022-09-01 |  | 2023-09-08 |  | EXP | [8 empty] | 2022-10-17 | Connected |  | No
National Grid | FRANKLIN | 434013 | 2038 | 4999.2 | Battery Add-On | 05_348W6 | 2022-07-27 14:12 | 2022-07-28 | 10 | 0 | 10 | [10 empty] | 2022-08-11 | 2022-09-08 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | FALL RIVER | 445797 | 2724 | 6 | Solar | 05_115W42 | 2022-07-27 14:44 | 2022-07-28 | 2 | 0 | 2 | 2022-08-01 | 2022-08-31 | 23 | 0 | 23 | [20 empty] | 2022-09-06 |  | 2023-09-15 |  | EXP | [8 empty] | 2022-11-22 | Connected |  | Yes
National Grid | CLINTON | 435349 | 1510 | 4999 | Other | 01_216W3 | 2022-07-27 23:05 | 2022-07-28 | 19 | 9 | 10 | [10 empty] | 2022-08-24 | 2022-09-16 | 17 | 0 | 17 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | HOLBROOK | 434918 | 2343 | 20 | Solar | 07_10W1 | 2022-07-28 10:08 | 2022-07-29 | 4 | 3 | 1 | 2022-08-03 | 2022-09-02 | 23 | 0 | 23 | [20 empty] | 2022-09-02 |  | 2024-01-20 |  | EXP | [8 empty] | 2023-10-30 | Connected |  | No
National Grid | QUINCY | 447713 | 2169 | 50 | Solar | 07_3W1 | 2022-07-28 12:50 | 2022-07-29 | 64 | 54 | 10 | 2022-10-28 | 2022-12-14 | 33 | 8 | 25 | [20 empty] | 2023-01-13 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | QUINCY | 447739 | 2169 | 66 | Solar | 07_3W3 | 2022-07-28 13:19 | 2022-07-29 | 68 | 59 | 9 | 2022-11-04 |  | 126 | 107 | 19 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FOXBOROUGH | 412238 | 2035 | 4999.2 | Battery Add-On | 05_3424W3 | 2022-07-28 14:49 | 2022-07-29 | 10 | 0 | 10 | [10 empty] | 2022-08-12 | 2022-09-09 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | MILFORD | 422048 | 1757 | 4999.2 | Battery Add-On | 05_336W4 | 2022-07-28 16:27 | 2022-07-29 | 9 | 0 | 9 | [10 empty] | 2022-08-11 | 2022-09-08 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | RANDOLPH | 434012 | 2368 | 4999.2 | Battery Add-On | 07_5W3 | 2022-07-28 16:48 | 2022-07-29 | 10 | 0 | 10 | [10 empty] | 2022-08-12 | 2022-09-09 | 20 | 0 | 20 | [11 empty] | 2022-07-28 16:58 |  |  | STD | [9 empty] | Study |  | No
National Grid | SOUTHBOROUGH | 439477 | 1772 | 7.6 | Solar | 05_317W3 | 2022-07-28 16:58 | 2022-07-29 | 2 | 0 | 2 | 2022-08-02 | 2022-08-24 | 17 | 0 | 17 | [20 empty] | 2022-08-25 | 2022-07-28 17:42 | 2024-01-05 |  | EXP |  | 2022-10-11 | 2023-01-24 | 106 | 0 | 106 |  |  | 2023-01-14 | Connected |  | No
National Grid | CHELMSFORD | 441231 | 1824 | 6 | Solar | 14_16L4 | 2022-07-28 17:42 | 2022-07-29 | 1 | 0 | 1 | 2022-08-01 | 2022-08-23 | 17 | 0 | 17 | [20 empty] | 2022-08-29 | 2022-07-29 13:55 | 2023-12-22 | Yes | EXP | [8 empty] | 2023-02-25 | Connected |  | No
National Grid | SOUTHBOROUGH | 448026 | 1772 | 10 | Solar | 05_310W3 | 2022-07-29 13:55 | 2022-08-01 | 1 | 0 | 1 | 2022-08-02 | 2022-08-29 | 21 | 6 | 15 | [20 empty] | 2022-08-30 |  | 2023-09-06 |  | EXP |  | 2022-10-11 | 2023-03-03 | 144 | 0 | 144 |  |  | 2023-03-07 | Connected |  | No
National Grid | HAVERHILL | 448164 | 1830 | 30 | Solar | 14_76L1 | 2022-07-31 15:46 | 2022-08-01 | 1 | 0 | 1 | 2022-08-02 | 2022-09-01 | 23 | 0 | 23 | [20 empty] | 2022-09-02 |  | 2023-10-03 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ROCKLAND | 404082 | 2370 | 240 | Solar | 07_93W40 | 2022-08-01 08:58 | 2022-08-02 | 21 | 11 | 10 | [10 empty] | 2022-08-30 | 2022-10-03 | 24 | 0 | 24 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | FOXBOROUGH | 439470 | 2035 | 240 | Solar | 05_3431W1 | 2022-08-01 10:48 | 2022-08-02 | 12 | 3 | 9 | [10 empty] | 2022-08-17 | 2022-09-21 | 25 | 0 | 25 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | MILLBURY | 403477 | 1527 | 9.57 | Solar | 01_26W3 | 2022-08-01 10:54 | 2022-08-02 | 21 | 21 | 0 | 2022-08-31 | 2022-09-20 | 14 | 0 | 14 | [20 empty] | 2022-01-13 |  | 2023-10-24 |  | EXP | [8 empty] | 2023-03-02 | Connected |  | No
National Grid | EASTON | 448291 | 2334 | 15.2 | Solar | 07_92W78 | 2022-08-01 11:21 | 2022-08-02 | 1 | 0 | 1 | 2022-08-03 | 2022-08-31 | 21 | 0 | 21 | [20 empty] | 2022-09-01 | 2022-08-01 11:58 | 2023-09-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RANDOLPH | 445564 | 2368 | 10 | Solar | 07_97W1 | 2022-08-01 11:58 | 2022-08-02 | 1 | 0 | 1 | 2022-08-03 | 2022-08-24 | 16 | 0 | 16 | [20 empty] | 2022-08-25 | 2022-08-01 15:02 | 2024-03-01 | Yes | EXP |  | 2023-03-02 | 2023-03-01 | 0 | 0 | 0 |  |  | 2023-03-07 | Connected |  | No
National Grid | WRENTHAM | 446350 | 2093 | 6.96 | Solar | 05_3422W4 | 2022-08-01 15:02 | 2022-08-02 | 3 | 0 | 3 | 2022-08-05 | 2022-09-02 | 21 | 0 | 21 | [20 empty] | 2022-09-09 | 2022-08-02 09:47 | 2024-02-03 | Yes | EXP |  | 2022-10-27 | 2023-02-01 | 98 | 0 | 98 |  |  | 2023-02-14 | Connected |  | No
National Grid | ANDOVER | 442063 | 1810 | 13.6 | Solar | 14_62L2 | 2022-08-02 09:47 | 2022-08-03 | 2 | 1 | 1 | 2022-08-04 | 2022-08-24 | 15 | 0 | 15 | [20 empty] | 2022-08-24 |  | 2023-08-30 | Yes | EXP |  | 2022-09-28 | 2022-12-21 | 85 | 0 | 85 |  |  | 2023-01-05 | Connected |  | No
National Grid | DRACUT | 447195 | 1826 | 10 | Solar | 14_75L6 | 2022-08-02 17:38 | 2022-08-03 | 1 | 0 | 1 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 437699 | 2301 | 4999.2 | Battery Add-On | 07_98W10 | 2022-08-02 18:22 | 2022-08-03 | 8 | 0 | 8 | [10 empty] | 2022-08-15 | 2022-09-07 | 17 | 0 | 17 | [11 empty] | 2022-08-03 09:43 |  |  | STD | [9 empty] | Group Study |  | No
National Grid | WORCESTER | 445228 | 1602 | 9.57 | Solar | 01_6W2 | 2022-08-03 09:43 | 2022-08-04 | 4 | 0 | 4 | 2022-08-10 | 2022-09-07 | 20 | 0 | 20 | [20 empty] | 2022-09-26 |  | 2024-05-09 | Yes | EXP |  | 2023-04-20 | 2023-05-04 | 15 | 0 | 15 |  |  | 2023-05-21 | Connected |  | No
National Grid | PALMER | 448095 | 1080 | 7.6 | Solar | 09_514L1 | 2022-08-03 10:19 | 2022-08-04 | 6 | 5 | 1 | 2022-08-11 | 2022-09-08 | 20 | 0 | 20 | [20 empty] | 2022-09-09 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ATTLEBORO | 442263 | 2703 | 11.6 | Solar | 05_9L1 | 2022-08-03 10:29 | 2022-08-04 | 21 | 20 | 1 | 2022-09-01 | 2022-10-11 | 27 | 8 | 19 | [20 empty] | 2022-10-12 |  | 2023-10-28 |  | EXP | [8 empty] | 2022-11-24 | Connected |  | No
National Grid | RANDOLPH | 447515 | 2368 | 10 | Solar | 07_97W2 | 2022-08-03 13:58 | 2022-08-04 | 4 | 0 | 4 | 2022-08-10 | 2022-09-08 | 21 | 0 | 21 | [20 empty] | 2022-09-13 | 2022-08-03 14:23 | 2023-09-25 |  | EXP | [8 empty] | 2022-12-20 | Connected |  | No
National Grid | REHOBOTH | 447033 | 2769 | 7.296 | Solar | 05_7L5 | 2022-08-03 14:23 | 2022-08-04 | 3 | 2 | 1 | 2022-08-08 | 2022-09-07 | 22 | 0 | 22 | [20 empty] | 2022-09-22 | 2022-08-03 15:42 | 2024-02-02 | Yes | EXP |  | 2023-01-28 | 2023-01-27 | 0 | 0 | 0 |  |  | 2023-02-24 | Connected |  | No
National Grid | EAST CHELMSFORD | 449174 | 1824 | 15.2 | Solar | 14_70L3 | 2022-08-03 15:42 | 2022-08-04 | 13 | 12 | 1 | 2022-08-22 | 2022-09-15 | 19 | 2 | 17 | [20 empty] | 2022-09-15 |  | 2023-10-10 | Yes | EXP |  | 2022-10-19 | 2022-10-28 | 10 | 0 | 10 |  |  | 2023-08-30 | Connected |  | No
National Grid | EAST CHELMSFORD | 449194 | 1824 | 15.2 | Solar | 14_70L3 | 2022-08-03 15:58 | 2022-08-04 | 6 | 4 | 2 | 2022-08-12 | 2022-09-09 | 20 | 0 | 20 | [20 empty] | 2022-09-14 |  | 2023-11-29 |  | EXP | [8 empty] | 2023-10-24 | Connected |  | No
National Grid | GRAFTON | 449309 | 1519 | 15.2 | Solar | 01_304W1 | 2022-08-04 08:21 | 2022-08-05 | 4 | 3 | 1 | 2022-08-11 | 2022-09-08 | 20 | 0 | 20 | [20 empty] | 2022-09-08 |  | 2024-01-19 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTBOROUGH | 449344 | 1581 | 3.8 | Solar | 05_312W4 | 2022-08-04 09:39 | 2022-08-05 | 3 | 0 | 3 | 2022-08-10 | 2022-09-07 | 20 | 0 | 20 | [20 empty] | 2022-09-26 |  | 2023-09-29 |  | EXP | [8 empty] | 2023-04-14 | Connected |  | No
National Grid | REHOBOTH | 443865 | 2769 | 10 | Solar | 05_7L5 | 2022-08-04 11:38 | 2022-08-05 | 4 | 3 | 1 | 2022-08-10 | 2022-09-07 | 20 | 0 | 20 | [20 empty] | 2022-09-08 |  | 2023-10-05 |  | EXP | [8 empty] | 2022-12-27 | Connected |  | No
National Grid | FOXBOROUGH | 447463 | 2035 | 7.6 | Solar | 05_3424W5 | 2022-08-04 13:10 | 2022-08-05 | 3 | 0 | 3 | 2022-08-10 | 2022-09-08 | 21 | 0 | 21 | [20 empty] | 2022-09-13 |  | 2023-10-06 |  | EXP | [8 empty] | 2023-03-16 | Connected |  | Yes
National Grid | MILLBURY | 449447 | 1527 | 16.896 | Solar | 01_304W3 | 2022-08-04 13:49 | 2022-08-05 | 19 | 18 | 1 | 2022-09-01 | 2022-09-23 | 17 | 4 | 13 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 442804 | 1843 | 7.6 | Solar | 14_61L3 | 2022-08-04 15:00 | 2022-08-05 | 1 | 0 | 1 | 2022-08-08 | 2022-09-01 | 20 | 0 | 20 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ROCKPORT | 449533 | 1966 | 10 | Solar |  | 2022-08-04 16:13 | 2022-08-05 | 1 | 0 | 1 | 2022-08-08 | 2022-09-02 | 20 | 0 | 20 | [20 empty] | 2022-09-06 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | STURBRIDGE | 449561 | 1566 | 19 | Solar | 01_413L7 | 2022-08-04 17:29 | 2022-08-05 | 6 | 3 | 3 | 2022-08-15 | 2022-09-19 | 25 | 3 | 22 | [20 empty] | 2022-09-21 |  | 2023-09-27 |  | EXP | [8 empty] | 2023-01-05 | Connected |  | No
National Grid | BRIDGEWATER | 441068 | 2324 | 13 | Solar | 07_912W55 | 2022-08-05 14:39 | 2022-08-08 | 8 | 7 | 1 | 2022-08-17 | 2022-09-19 | 23 | 0 | 23 | [20 empty] | 2022-09-19 |  | 2023-09-23 |  | EXP | [8 empty] | 2023-02-01 | Connected |  | No
National Grid | GRAFTON | 447696 | 1519 | 9.86 | Solar | 01_304W1 | 2022-08-05 15:17 | 2022-08-08 | 2 | 0 | 2 | 2022-08-10 | 2022-10-19 | 49 | 26 | 23 | 2023-01-06 | 2023-01-11 | 4 | 0 | 4 | [5 empty] | 2023-01-06 | 2023-01-11 | 4 | 0 | 4 | [5 empty] | 2023-01-11 |  | 2024-01-13 |  | EXP |  | 2023-04-08 | 2023-04-21 | 14 | 0 | 14 |  |  | 2023-04-25 | Connected |  | No
National Grid | SOUTH HAMILTON | 445040 | 1982 | 250 | Solar | 12_51T2 | 2022-08-08 10:25 | 2022-08-09 | 17 | 7 | 10 | [10 empty] | 2022-09-01 | 2022-10-03 | 22 | 0 | 22 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | MALDEN | 448424 | 2148 | 67.3 | Solar | 12_37W7 | 2022-08-08 17:59 | 2022-08-09 | 7 | 0 | 7 | 2022-08-18 | 2022-10-03 | 32 | 7 | 25 | [20 empty] | 2022-11-23 |  | 2023-12-20 |  | EXP | [8 empty] | 2023-08-11 | Connected |  | No
National Grid | HANSON | 434010 | 2341 | 4999.2 | Battery Add-On | 07_95W3 | 2022-08-08 18:53 | 2022-08-09 | 7 | 0 | 7 | [10 empty] | 2022-08-18 | 2022-09-15 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | WESTFORD | 449761 | 1886 | 7.6 | Solar | 14_57L2 | 2022-08-09 08:42 | 2022-08-10 | 1 | 0 | 1 | 2022-08-11 | 2022-09-08 | 20 | 0 | 20 | [20 empty] | 2022-09-09 | 2022-08-09 09:30 | 2024-09-21 |  | EXP | [8 empty] | 2024-03-12 | Connected |  | No
National Grid | LAWRENCE | 449817 | 1843 | 9.45 | Solar | 14_61L3 | 2022-08-09 09:30 | 2022-08-10 | 3 | 0 | 3 | 2022-08-15 | 2022-09-12 | 20 | 0 | 20 | [20 empty] | 2022-09-27 |  | 2024-02-24 | Yes | EXP |  | 2023-01-24 | 2023-02-07 | 15 | 0 | 15 |  |  | 2023-06-08 | Connected |  | No
National Grid | RANDOLPH | 442826 | 2368 | 8.12 | Solar | 07_5W4 | 2022-08-09 14:04 | 2022-08-10 | 2 | 0 | 2 | 2022-08-12 | 2022-09-09 | 20 | 0 | 20 | [20 empty] | 2022-09-13 |  | 2023-09-16 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EVERETT | 384620 | 2149 | 1266 | Solar | 12_37W9 | 2022-08-10 09:34 | 2022-08-11 | 231 | 63 | 168 | [29 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | AUBURN | 450660 | 1501 | 19 | Solar | 01_26W3 | 2022-08-10 10:58 | 2022-08-11 | 22 | 22 | 0 | 2022-09-13 | 2022-09-29 | 13 | 0 | 13 | 2022-12-07 | 2023-03-20 | 70 | 0 | 70 | [5 empty] | 2022-12-07 | 2023-03-20 | 70 | 0 | 70 | [5 empty] | 2023-03-23 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SPENCER | 448029 | 1562 | 10 | Solar | 01_552L1 | 2022-08-10 11:02 | 2022-08-11 | 4 | 3 | 1 | 2022-08-16 | 2022-09-12 | 19 | 0 | 19 | [20 empty] | 2022-09-13 |  | 2023-10-09 |  | EXP | [8 empty] | 2022-11-01 | Connected |  | No
National Grid | TEWKSBURY | 420643 | 1752 | 4999.2 | Battery Add-On | 14_75L2 | 2022-08-10 13:25 | 2022-08-11 | 12 | 1 | 11 | [10 empty] | 2022-08-29 | 2022-09-23 | 19 | 2 | 17 | [10 empty] | 2023-12-11 | 2022-08-10 15:19 |  |  | STD | [9 empty] | Conditional Approval |  | Yes
National Grid | BROCKTON | 444881 | 2302 | 6 | Solar | 07_911W56 | 2022-08-10 15:19 | 2022-08-11 | 2 | 0 | 2 | 2022-08-15 | 2022-09-12 | 20 | 0 | 20 | [20 empty] | 2022-09-14 |  | 2024-06-22 | Yes | EXP |  | 2023-05-03 | 2023-06-13 | 42 | 0 | 42 |  |  | 2023-07-07 | Connected |  | No
National Grid | BELCHERTOWN | 448581 | 1007 | 14.37 | Solar | 09_509L2 | 2022-08-11 09:48 | 2022-08-12 | 13 | 12 | 1 | 2022-08-30 | 2022-09-27 | 20 | 0 | 20 | [20 empty] | 2022-09-28 | 2022-08-11 10:29 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTHBRIDGE | 450732 | 1534 | 19.195 | Solar | 05_320W5 | 2022-08-11 10:29 | 2022-08-12 | 6 | 4 | 2 | 2022-08-19 | 2022-09-19 | 21 | 0 | 21 | [20 empty] | 2022-09-19 |  | 2023-10-17 | Yes | EXP |  | 2022-12-16 | 2023-01-18 | 34 | 0 | 34 |  |  | 2023-01-23 | Connected |  | No
National Grid | BILLERICA | 384623 | 1821 | 400 | Solar | 14_92L2 | 2022-08-11 11:22 | 2022-08-12 | 38 | 28 | 10 | [10 empty] | 2022-10-06 | 2022-11-10 | 25 | 3 | 22 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | MEDFORD | 384625 | 2155 | 298.8 | Solar | 12_37W2 | 2022-08-11 11:23 | 2022-08-12 | 61 | 51 | 10 | [10 empty] | 2022-11-09 | 2023-09-21 | 216 | 197 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BILLERICA | 384627 | 1821 | 400 | Solar | 14_92L2 | 2022-08-11 11:23 | 2022-08-12 | 38 | 28 | 10 | [10 empty] | 2022-10-05 | 2022-10-28 | 17 | 0 | 17 | [11 empty] | 2022-08-11 12:40 |  |  | STD | [9 empty] | Study |  | No
National Grid | RANDOLPH | 449261 | 2368 | 6 | Solar | 07_5W3 | 2022-08-11 12:40 | 2022-08-12 | 3 | 1 | 2 | 2022-08-16 | 2022-09-23 | 28 | 8 | 20 | [20 empty] | 2022-09-28 |  | 2024-11-03 | Yes | EXP |  | 2023-08-11 | 2023-10-06 | 57 | 0 | 57 |  |  | 2023-11-09 | Connected |  | No
National Grid | MILLBURY | 441932 | 1527 | 8.41 | Solar | 01_304W1 | 2022-08-11 18:08 | 2022-08-12 | 15 | 13 | 2 | 2022-09-02 | 2022-09-22 | 14 | 0 | 14 | 2022-10-05 | 2022-10-19 | 10 | 0 | 10 | [5 empty] | 2022-10-05 | 2022-10-19 | 10 | 0 | 10 | [5 empty] | 2023-01-05 |  | 2024-05-16 |  | EXP |  | 2023-04-20 | 2023-05-16 | 27 | 0 | 27 |  |  | 2023-05-19 | Connected |  | No
National Grid | WESTFORD | 449402 | 1886 | 11.4 | Solar | 14_57L3 | 2022-08-12 08:24 | 2022-08-15 | 1 | 0 | 1 | 2022-08-16 | 2022-09-14 | 21 | 0 | 21 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEOMINSTER | 439851 | 1453 | 2341 | Solar | 01_207W4 | 2022-08-12 13:13 | 2022-08-15 | 64 | 54 | 10 | [10 empty] | 2022-11-17 | 2022-12-13 | 18 | 0 | 18 | [11 empty] | 2022-08-12 13:37 |  |  | STD | [9 empty] | Group Study |  | Yes
National Grid | BROCKTON | 449542 | 2302 | 6 | Solar | 07_911W56 | 2022-08-12 13:37 | 2022-08-15 | 16 | 15 | 1 | 2022-09-07 | 2022-10-26 | 34 | 14 | 20 | [20 empty] | 2022-11-02 |  | 2024-04-30 | Yes | EXP |  | 2023-04-13 | 2023-04-27 | 15 | 0 | 15 |  |  |  | Completion Documents |  | No
National Grid | MARLBOROUGH | 449265 | 1752 | 10 | Solar | 05_311W2 | 2022-08-12 15:49 | 2022-08-15 | 5 | 4 | 1 | 2022-08-22 | 2022-09-14 | 17 | 0 | 17 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NEWBURYPORT | 451338 | 1950 | 67.3 | Solar | 14_36J6 | 2022-08-12 16:22 | 2022-08-15 | 26 | 16 | 10 | 2022-09-20 | 2022-10-27 | 27 | 6 | 21 | [20 empty] | 2022-11-08 |  | 2024-10-22 |  | EXP | [8 empty] | 2023-12-01 | Connected |  | No
National Grid | NORTH ANDOVER | 451464 | 1845 | 50 | Solar | 14_56L1 | 2022-08-12 17:43 | 2022-08-15 | 26 | 16 | 10 | [10 empty] | 2022-09-20 | 2022-10-26 | 26 | 8 | 18 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | DIGHTON | 437709 | 2715 | 999 | Solar | 05_19W73 | 2022-08-15 09:36 | 2022-08-16 | 20 | 11 | 9 | [10 empty] | 2022-09-14 | 2022-10-05 | 16 | 0 | 16 | [10 empty] | 2024-01-18 |  |  |  | STD | [9 empty] | Conditional Approval |  | No
National Grid | BROCKTON | 425562 | 2302 | 770 | Solar | 07_91W41 | 2022-08-15 14:23 | 2022-08-16 | 16 | 6 | 10 | [10 empty] | 2022-09-07 | 2022-09-28 | 16 | 0 | 16 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | LAWRENCE | 450745 | 1843 | 6 | Solar | 14_61L1 | 2022-08-15 14:45 | 2022-08-16 | 12 | 10 | 2 | 2022-09-01 | 2022-09-30 | 21 | 6 | 15 | [20 empty] | 2022-11-21 |  | 2025-03-26 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | SALEM | 448048 | 1970 | 6 | Solar | 12_29W4 | 2022-08-15 15:07 | 2022-08-16 | 7 | 6 | 1 | 2022-08-24 | 2022-09-21 | 20 | 0 | 20 | [20 empty] | 2022-09-22 |  | 2023-10-22 |  | EXP | [8 empty] | 2022-11-10 | Connected |  | No
National Grid | CHARLTON | 438733 | 1507 | 1500 | Natural Gas | 01_413L4 | 2022-08-16 12:30 | 2022-08-17 | 49 | 40 | 9 | [10 empty] | 2022-10-27 | 2022-11-28 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Group Study |  | Yes
National Grid | HAMILTON | 413470 | 1982 | 15.2 | Solar | 12_51L3 | 2022-08-16 13:31 | 2022-08-17 | 2 | 0 | 2 | 2022-08-19 | 2022-09-19 | 21 | 0 | 21 | [20 empty] | 2022-02-26 |  | 2023-09-27 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BEVERLY | 448083 | 1915 | 7.6 | Solar | 12_51T2 | 2022-08-17 10:25 | 2022-08-01 | 17 | 9 | 8 | 2022-08-23 | 2022-09-21 | 21 | 0 | 21 | [20 empty] | 2022-09-22 |  | 2023-10-15 |  | EXP | [8 empty] | 2023-02-24 | Connected |  | No
National Grid | SOUTH GRAFTON | 427817 | 1560 | 7.54 | Solar | 01_304W2 | 2022-08-17 14:02 | 2022-08-18 | 0 | 0 | 0 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LYNN | 438823 | 1904 | 7.6 | Solar | 12_24W2 | 2022-08-18 10:40 | 2022-08-19 | 4 | 3 | 1 | 2022-08-24 | 2022-10-31 | 47 | 28 | 19 | [20 empty] | 2022-10-31 | 2022-08-18 11:29 | 2023-11-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BELLINGHAM | 451936 | 2019 | 9.57 | Solar | 05_348W7 | 2022-08-18 11:29 | 2022-08-19 | 2 | 0 | 2 | 2022-08-23 | 2022-09-15 | 17 | 0 | 17 | [20 empty] | 2022-09-19 |  | 2024-01-18 | Yes | EXP | [8 empty] | 2023-02-02 | Connected |  | No
National Grid | ATTLEBORO | 422661 | 2703 | 11700 | Other | 05_9L1 | 2022-08-18 11:44 | 2022-08-19 | 22 | 12 | 10 | [10 empty] | 2022-09-20 | 2022-10-18 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BARRE | 433961 | 1005 | 5900 | Other | 09_604W3 | 2022-08-18 11:45 | 2022-08-19 | 32 | 22 | 10 | [10 empty] | 2022-10-04 | 2022-10-27 | 17 | 0 | 17 | [11 empty] | 2022-08-19 11:30 |  |  | STD | [9 empty] | Study |  | No
National Grid | WESTFORD | 452930 | 1886 | 7.6 | Solar | 14_73L2 | 2022-08-19 11:30 | 2022-08-22 | 1 | 0 | 1 | 2022-08-23 | 2022-09-22 | 22 | 0 | 22 | [20 empty] | 2022-09-23 | 2022-08-19 14:36 | 2023-09-30 | Yes | EXP |  | 2022-12-06 | 2022-12-05 | 0 | 0 | 0 |  |  | 2023-03-17 | Connected |  | No
National Grid | EASTON | 428918 | 2356 | 7.6 | Solar | 07_92W78 | 2022-08-19 14:36 | 2022-08-22 | 1 | 0 | 1 | 2022-08-23 | 2022-09-21 | 22 | 5 | 17 | [20 empty] | 2022-09-21 |  | 2023-09-23 | Yes | EXP |  | 2022-10-27 | 2022-12-07 | 42 | 0 | 42 |  |  | 2023-01-18 | Connected |  | No
National Grid | SAUGUS | 447931 | 1906 | 9.6 | Solar | 12_19W2 | 2022-08-19 18:46 | 2022-08-22 | 1 | 0 | 1 | 2022-08-23 | 2022-09-21 | 21 | 0 | 21 | [20 empty] | 2022-09-26 |  | 2023-10-02 |  | EXP | [8 empty] | 2022-10-15 | Connected |  | No
National Grid | LAWRENCE | 430644 | 1843 | 1125 | Battery Add-On | 14_8T2 | 2022-08-23 08:47 | 2022-08-24 | 9 | 0 | 9 | [10 empty] | 2022-09-07 | 2022-09-30 | 18 | 0 | 18 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | EAST BROOKFIELD | 447837 | 1515 | 7.25 | Solar | 01_552L3 | 2022-08-24 12:59 | 2022-08-25 | 4 | 0 | 4 | 2022-08-31 | 2022-09-29 | 21 | 0 | 21 | [20 empty] | 2022-09-30 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NEWBURY | 422863 | 1922 | 14000 | Other | 14_2405 | 2022-08-25 11:17 | 2022-08-26 | 22 | 12 | 10 | [10 empty] | 2022-12-05 | 2023-01-03 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | MELROSE | 447514 | 2176 | 15.66 | Solar | 12_25W4 | 2022-08-25 12:34 | 2022-08-26 | 13 | 12 | 1 | 2022-09-14 | 2022-10-11 | 19 | 0 | 19 | [20 empty] | 2022-10-12 | 2022-08-25 13:05 | 2023-10-31 |  | EXP | [8 empty] | 2023-02-14 | Connected |  | No
National Grid | NORTHAMPTON | 445340 | 1060 | 7.6 | Solar | 09_909W2 | 2022-08-25 13:05 | 2022-08-26 | 3 | 0 | 3 | 2022-08-31 | 2022-09-29 | 21 | 0 | 21 | [20 empty] | 2022-09-30 |  | 2024-08-10 | Yes | EXP |  | 2023-04-25 | 2023-08-09 | 107 | 0 | 107 |  |  | 2023-08-16 | Connected |  | No
National Grid | LEOMINSTER | 451693 | 1453 | 6 | Solar | 01_219W2 | 2022-08-25 14:33 | 2022-08-26 | 3 | 0 | 3 | 2022-08-31 | 2022-12-12 | 71 | 27 | 44 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHELMSFORD | 427890 | 1824 | 750 | Solar | 14_58L2 | 2022-08-25 16:57 | 2022-08-26 | 74 | 64 | 10 | [10 empty] | 2022-12-16 | 2023-03-02 | 51 | 26 | 25 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | WESTBOROUGH | 452182 | 1581 | 999 | Solar | 05_314W1 | 2022-08-25 20:36 | 2022-08-26 | 278 | 268 | 10 | [10 empty] | 2023-10-10 | 2024-02-27 | 95 | 80 | 15 | [14 empty] | STD | [9 empty] | Pending Withdraw |  | Yes
National Grid | WESTBOROUGH | 432400 | 1581 | 999 | Solar | 05_314W1 | 2022-08-25 20:37 | 2022-08-26 | 289 | 279 | 10 | [10 empty] | 2023-10-25 | 2024-02-27 | 85 | 65 | 20 | [11 empty] | 2022-08-25 21:13 |  |  | STD | [9 empty] | Pending Withdraw |  | Yes
National Grid | WILLIAMSTOWN | 446211 | 1267 | 5.8 | Solar | 09_1003W2 | 2022-08-25 21:13 | 2022-08-26 | 2 | 0 | 2 | 2022-08-30 | 2022-09-27 | 20 | 0 | 20 | [20 empty] | 2022-09-29 | 2022-08-26 09:58 | 2024-04-03 | Yes | EXP | [9 empty] | Completion Documents |  | No
National Grid | WESTPORT | 450178 | 2790 | 10 | Solar | 05_115W45 | 2022-08-26 09:58 | 2022-08-29 | 18 | 15 | 3 | 2022-09-23 | 2022-10-19 | 18 | 0 | 18 | [20 empty] | 2022-10-20 |  | 2024-02-08 | Yes | EXP |  | 2023-01-07 | 2023-02-07 | 32 | 0 | 32 |  |  | 2023-03-23 | Connected |  | No
National Grid | BROCKTON | 451320 | 2301 | 3.8 | Solar | 07_91W48 | 2022-08-26 10:07 | 2022-08-29 | 35 | 26 | 9 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | EVERETT | 454546 | 2149 | 15.744 | Solar | 12_37W6 | 2022-08-26 11:54 | 2022-08-29 | 20 | 19 | 1 | 2022-09-26 | 2022-10-19 | 17 | 0 | 17 | [20 empty] | 2022-10-19 |  | 2023-11-22 |  | EXP | [8 empty] | 2023-06-22 | Connected |  | No
National Grid | FALL RIVER | 448988 | 2720 | 480 | Solar | 05_28W40 | 2022-08-26 16:58 | 2022-08-29 | 42 | 33 | 9 | [10 empty] | 2022-10-31 | 2023-01-10 | 47 | 27 | 20 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | EAST LONGMEADOW | 419520 | 1028 | 4250 | Natural Gas | 09_522L2 | 2022-08-26 20:49 | 2022-08-29 | 46 | 37 | 9 | [10 empty] | 2022-11-03 | 2022-12-23 | 36 | 16 | 20 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | LAWRENCE | 426199 | 1841 | 117.3 | Solar | 14_2355 | 2022-08-29 14:43 | 2022-08-30 | 62 | 54 | 8 | [10 empty] | 2022-11-30 | 2023-01-18 | 31 | 8 | 23 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | GREAT BARRINGTON | 454957 | 1230 | 9.86 | Solar | 09_1109W3 | 2022-08-29 17:30 | 2022-08-30 | 3 | 0 | 3 | 2022-09-02 | 2022-09-27 | 17 | 0 | 17 | [20 empty] | 2022-09-28 |  | 2023-11-06 |  | EXP | [8 empty] | 2023-02-17 | Connected |  | No
National Grid | BLACKSTONE | 452803 | 1504 | 6 | Solar | 05_321W9 | 2022-08-30 13:01 | 2022-08-31 | 2 | 0 | 2 | 2022-09-02 | 2022-09-22 | 14 | 0 | 14 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 446320 | 1610 | 16.24 | Solar | 01_3J372 | 2022-08-30 13:25 | 2022-08-31 | 11 | 9 | 2 | 2022-09-16 | 2023-03-31 | 134 | 117 | 17 | [20 empty] | 2023-04-05 |  | 2024-06-04 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | WORCESTER | 446313 | 1610 | 14.5 | Solar | 01_3J372 | 2022-08-30 13:36 | 2022-08-31 | 28 | 27 | 1 | 2022-10-12 | 2022-12-19 | 46 | 25 | 21 | [20 empty] | 2022-12-21 |  | 2024-06-04 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | HAVERHILL | 425587 | 1832 | 498 | Solar | 14_43L2 | 2022-08-31 09:00 | 2022-09-01 | 14 | 4 | 10 | [10 empty] | 2022-09-21 | 2022-10-19 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | FRANKLIN | 425595 | 2038 | 996 | Solar | 05_344W4 | 2022-08-31 09:03 | 2022-09-01 | 14 | 4 | 10 | [10 empty] | 2022-09-21 | 2022-10-19 | 20 | 0 | 20 | [11 empty] | 2022-08-31 10:27 |  |  | STD | [9 empty] | Group Study |  | No
National Grid | SOUTHBRIDGE | 447179 | 1550 | 7.6 | Solar | 01_413L3 | 2022-08-31 10:27 | 2022-09-01 | 30 | 30 | 0 | 2022-10-17 | 2022-11-08 | 17 | 0 | 17 | [20 empty] | 2022-11-15 | 2022-08-31 12:46 | 2024-02-15 | Yes | EXP |  | 2023-04-27 | 2023-06-08 | 43 | 0 | 43 |  |  | 2023-10-20 | Connected |  | No
National Grid | RANDOLPH | 450193 | 2368 | 7.6 | Solar | 07_5W1 | 2022-08-31 12:46 | 2022-09-01 | 2 | 0 | 2 | 2022-09-06 | 2022-09-30 | 19 | 1 | 18 | [20 empty] | 2022-09-30 | 2022-08-31 14:45 | 2024-03-07 | Yes | EXP |  | 2023-02-24 | 2023-03-08 | 13 | 0 | 13 |  |  | 2023-03-13 | Connected |  | No
National Grid | BROCKTON | 443774 | 2302 | 7.6 | Solar | 07_911W56 | 2022-08-31 14:45 | 2022-09-01 | 1 | 0 | 1 | 2022-09-02 | 2022-10-27 | 38 | 17 | 21 | [20 empty] | 2022-11-04 |  | 2024-06-07 | Yes | EXP | [8 empty] | 2023-06-15 | Connected |  | No
National Grid | BELCHERTOWN | 448872 | 1007 | 10 | Solar | 09_527L1 | 2022-08-31 15:02 | 2022-09-01 | 1 | 0 | 1 | 2022-09-02 | 2022-09-27 | 17 | 0 | 17 | [20 empty] | 2022-09-29 | 2022-09-01 08:20 | 2023-10-19 |  | EXP | [8 empty] | 2022-11-29 | Connected |  | No
National Grid | MONTEREY | 451140 | 1245 | 7.6 | Solar | 09_1109W1 | 2022-09-01 08:20 | 2022-09-02 | 5 | 3 | 2 | 2022-09-09 | 2022-09-26 | 12 | 0 | 12 | [20 empty] | 2022-09-28 |  | 2023-12-22 | Yes | EXP |  | 2022-11-15 | 2022-12-21 | 37 | 0 | 37 |  |  | 2023-02-08 | Connected |  | No
National Grid | MALDEN | 437637 | 2148 | 350 | Solar | 12_16W3 | 2022-09-01 09:05 | 2022-09-02 | 15 | 5 | 10 | [10 empty] | 2022-11-02 | 2023-01-04 | 42 | 40 | 2 | [11 empty] | 2022-09-01 15:39 |  |  | STD | [9 empty] | Conditional Approval |  | Yes
National Grid | WESTBOROUGH | 452283 | 1581 | 100 | Solar | 05_314W3 | 2022-09-01 15:39 | 2022-09-02 | 11 | 2 | 9 | 2022-09-20 | 2022-10-24 | 24 | 0 | 24 | [20 empty] | 2022-12-01 |  | 2024-04-15 | Yes | EXP |  | 2023-09-15 | 2024-02-08 | 146 | 145 | 1 |  |  | 2024-04-09 | Connected |  | Yes
National Grid | NEWBURYPORT | 454032 | 1950 | 21.75 | Solar | 14_36J2 | 2022-09-01 17:59 | 2022-09-02 | 4 | 4 | 0 | 2022-09-09 | 2022-10-03 | 17 | 0 | 17 | [20 empty] | 2022-11-30 | 2022-09-01 18:30 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SEEKONK | 451125 | 2771 | 10 | Solar | 05_7L1 | 2022-09-01 18:30 | 2022-09-02 | 3 | 1 | 2 | 2022-09-07 | 2022-10-13 | 26 | 7 | 19 | [20 empty] | 2022-10-18 | 2022-09-02 12:14 | 2024-10-24 | Yes | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | ATTLEBORO | 452367 | 2703 | 8.832 | Solar | 05_8L1 | 2022-09-02 12:14 | 2022-09-06 | 2 | 0 | 2 | 2022-09-08 | 2022-09-30 | 17 | 1 | 16 | [20 empty] | 2022-10-04 |  | 2024-01-18 | Yes | EXP | [8 empty] | 2023-04-03 | Connected |  | Yes
National Grid | FALL RIVER | 455939 | 2720 | 196.175 | Solar | 05_28W50 | 2022-09-02 13:41 | 2022-09-06 | 22 | 13 | 9 | [10 empty] | 2022-10-05 | 2022-11-08 | 24 | 7 | 17 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | ROCKLAND | 456001 | 2370 | 200 | Solar | 07_99W61 | 2022-09-02 14:18 | 2022-09-06 | 10 | 0 | 10 | [10 empty] | 2022-09-20 | 2022-10-17 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Group Study |  | Yes
National Grid | UXBRIDGE | 452462 | 1569 | 15.2 | Solar | 05_320W4 | 2022-09-02 15:04 | 2022-09-06 | 7 | 5 | 2 | 2022-09-14 | 2022-09-29 | 12 | 0 | 12 | [20 empty] | 2022-09-30 |  | 2024-01-23 |  | EXP | [8 empty] | 2023-02-15 | Connected |  | Yes
National Grid | ATTLEBORO | 456501 | 2703 | 19.14 | Solar | 05_9L2 | 2022-09-03 08:07 | 2022-09-06 | 3 | 2 | 1 | 2022-09-08 | 2022-09-30 | 17 | 0 | 17 | [20 empty] | 2022-09-30 |  | 2023-11-02 |  | EXP | [8 empty] | 2023-02-08 | Connected |  | No
National Grid | SOUTHBOROUGH | 456585 | 1772 | 10 | Solar | 05_317W3 | 2022-09-05 13:20 | 2022-09-06 | 1 | 0 | 1 | 2022-09-07 | 2022-09-26 | 15 | 3 | 12 | [20 empty] | 2022-10-19 |  | 2023-10-24 |  | EXP | [8 empty] | 2023-01-13 | Connected |  | No
National Grid | GLOUCESTER | 456681 | 1930 | 15.2 | Solar | 12_51T1 | 2022-09-06 10:23 | 2022-09-07 | 1 | 0 | 1 | 2022-09-08 | 2022-09-23 | 12 | 0 | 12 | [20 empty] | 2022-09-26 |  | 2023-09-28 |  | EXP | [8 empty] | 2023-03-29 | Connected |  | No
National Grid | NEW BRAINTREE | 454366 | 1531 | 10 | Solar | 09_604W3 | 2022-09-06 10:28 | 2022-09-07 | 4 | 1 | 3 | 2022-09-13 | 2022-09-27 | 11 | 0 | 11 | [20 empty] | 2022-09-29 | 2022-09-06 11:19 | 2023-09-30 |  | EXP | [8 empty] | 2023-02-03 | Connected |  | No
National Grid | FLORENCE | 456714 | 1060 | 17.4 | Solar | 09_901W3 | 2022-09-06 11:19 | 2022-09-07 | 3 | 1 | 2 | 2022-09-09 | 2022-11-17 | 48 | 27 | 21 | [20 empty] | 2022-11-21 | 2022-09-06 11:40 | 2024-02-07 | Yes | EXP | [8 empty] | 2023-03-13 | Connected |  | No
National Grid | HAMPDEN | 456718 | 1036 | 15.2 | Solar | 09_139L3 | 2022-09-06 11:40 | 2022-09-07 | 1 | 0 | 1 | 2022-09-08 | 2022-09-29 | 16 | 4 | 12 | [20 empty] | 2022-09-29 |  | 2023-10-10 | Yes | EXP |  | 2023-01-07 | 2023-01-14 | 8 | 0 | 8 |  |  | 2023-03-02 | Connected |  | No
National Grid | BRIDGEWATER | 456937 | 2324 | 22.8 | Solar | 07_912W21 | 2022-09-06 17:14 | 2022-09-07 | 3 | 2 | 1 | 2022-09-09 | 2022-10-03 | 17 | 0 | 17 | [20 empty] | 2022-10-04 |  | 2023-10-11 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HAMILTON | 457042 | 1982 | 15.2 | Solar | 12_51T2 | 2022-09-07 09:19 | 2022-09-08 | 1 | 0 | 1 | 2022-09-09 | 2022-09-28 | 14 | 0 | 14 | [20 empty] | 2022-09-29 |  | 2024-06-12 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | MEDFORD | 457068 | 2155 | 15.2 | Solar | 12_11J3 | 2022-09-07 10:23 | 2022-09-08 | 2 | 0 | 2 | 2022-09-12 | 2022-09-30 | 15 | 0 | 15 | [20 empty] | 2022-10-03 |  | 2023-10-05 |  | EXP | [8 empty] | 2022-12-09 | Connected |  | No
National Grid | BROCKTON | 441919 | 2301 | 999 | Solar | 07_98W19 | 2022-09-07 10:47 | 2022-09-08 | 23 | 16 | 7 | [10 empty] | 2022-10-12 | 2022-11-08 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | BROCKTON | 443641 | 2301 | 5 | Solar | 07_911W13 | 2022-09-07 11:35 | 2022-09-08 | 3 | 0 | 3 | 2022-09-13 | 2022-09-30 | 14 | 0 | 14 | [20 empty] | 2022-10-04 | 2022-09-07 12:38 | 2023-10-12 |  | EXP | [8 empty] | 2022-10-18 | Connected |  | No
National Grid | SOUTH EASTON | 454234 | 2375 | 9.984 | Solar | 07_92W44 | 2022-09-07 12:38 | 2022-09-08 | 5 | 4 | 1 | 2022-09-15 | 2022-10-18 | 23 | 3 | 20 | [20 empty] | 2022-09-06 | 2022-09-07 14:06 | 2023-12-13 | Yes | EXP |  | 2022-12-06 | 2022-12-19 | 14 | 0 | 14 |  |  | 2023-11-02 | Connected |  | No
National Grid | EAST LONGMEADOW | 455467 | 1028 | 6 | Solar | 09_508L4 | 2022-09-07 14:06 | 2022-09-08 | 3 | 0 | 3 | 2022-09-13 | 2022-09-29 | 13 | 0 | 13 | [20 empty] | 2022-09-30 |  | 2023-12-31 | Yes | EXP | [8 empty] | 2023-02-01 | Connected |  | No
National Grid | BILLERICA | 434023 | 1821 | 1100 | Other | 14_18L3 | 2022-09-07 16:08 | 2022-09-08 | 15 | 6 | 9 | [10 empty] | 2022-09-29 | 2022-10-26 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | REVERE | 457238 | 2151 | 7.6 | Solar | 12_35J2 | 2022-09-07 16:14 | 2022-09-08 | 2 | 0 | 2 | 2022-09-12 | 2022-09-30 | 15 | 0 | 15 | [20 empty] | 2022-10-03 |  | 2023-11-01 |  | EXP | [8 empty] | 2023-06-08 | Connected |  | No
National Grid | LEOMINSTER | 453761 | 1453 | 499 | Solar | 01_225W2 | 2022-09-08 10:55 | 2022-09-09 | 18 | 8 | 10 | [10 empty] | 2022-10-05 | 2022-10-31 | 18 | 0 | 18 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | NEW SALEM | 440575 | 1355 | 11.4 | Solar | 09_702W3 | 2022-09-08 15:07 | 2022-09-09 | 275 | 63 | 212 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 457672 | 1602 | 16.82 | Solar | 01_16J1 | 2022-09-09 05:41 | 2022-09-12 | 0 | 0 | 0 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ATTLEBORO | 444120 | 2703 | 9.86 | Solar | 05_9L3 | 2022-09-09 09:27 | 2022-09-12 | 2 | 0 | 2 | 2022-09-14 | 2022-09-27 | 10 | 0 | 10 | [20 empty] | 2022-09-29 |  | 2023-10-04 |  | EXP | [8 empty] | 2023-01-27 | Connected |  | No
National Grid | ANDOVER | 457561 | 1810 | 9.6 | Solar | 14_59L1 | 2022-09-09 10:33 | 2022-09-12 | 13 | 12 | 1 | 2022-09-28 | 2022-10-26 | 20 | 0 | 20 | [20 empty] | 2022-10-26 | 2022-09-09 13:32 | 2023-11-01 |  | EXP | [8 empty] | 2023-10-05 | Connected |  | Yes
National Grid | GRAFTON | 454266 | 1519 | 11.866 | Solar | 01_328W3 | 2022-09-09 13:32 | 2022-09-12 | 2 | 0 | 2 | 2022-09-14 | 2022-09-29 | 12 | 0 | 12 | [20 empty] | 2022-09-30 | 2022-09-12 09:56 | 2024-02-15 | Yes | EXP |  | 2023-02-16 | 2023-07-28 | 163 | 0 | 163 |  |  | 2023-07-20 | Connected |  | No
National Grid | ATTLEBORO | 453607 | 2703 | 5 | Solar | 05_9L1 | 2022-09-12 09:56 | 2022-09-13 | 0 | 0 | 0 | 2022-09-13 | 2022-09-29 | 13 | 0 | 13 | [20 empty] | 2022-09-29 |  | 2023-10-26 | Yes | EXP |  | 2023-01-07 | 2023-01-06 | 0 | 0 | 0 |  |  | 2023-01-10 | Connected |  | No
National Grid | WESTFORD | 458118 | 1886 | 19 | Solar | 14_57L2 | 2022-09-12 10:54 | 2022-09-13 | 0 | 0 | 0 | 2022-09-13 | 2022-09-30 | 14 | 0 | 14 | [20 empty] | 2022-09-30 |  | 2023-10-18 |  | EXP | [8 empty] | 2023-05-03 | Connected |  | No
National Grid | METHUEN | 454191 | 1844 | 3.48 | Solar | 14_75L3 | 2022-09-13 12:01 | 2022-09-14 | 2 | 0 | 2 | 2022-09-16 | 2022-09-30 | 11 | 0 | 11 | [20 empty] | 2022-10-04 | 2022-09-13 19:57 | 2024-02-29 |  | EXP | [8 empty] | 2023-11-18 | Connected |  | No
National Grid | LEOMINSTER | 455958 | 1453 | 9.6 | Solar | 01_225W4 | 2022-09-13 19:57 | 2022-09-14 | 2 | 0 | 2 | 2022-09-16 | 2022-09-30 | 11 | 0 | 11 | [20 empty] | 2022-10-03 |  | 2024-02-03 | Yes | EXP |  | 2023-02-03 | 2023-02-02 | 0 | 0 | 0 |  |  | 2023-06-05 | Connected |  | No
National Grid | WORCESTER | 458817 | 1602 | 17.6 | Solar | 01_1J363 | 2022-09-14 10:48 | 2022-09-15 | 7 | 7 | 0 | 2022-09-26 | 2023-03-27 | 124 | 37 | 87 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | ATHOL | 439057 | 1331 | 9.8 | Solar | 09_702W3 | 2022-09-14 13:39 | 2022-09-15 | 8 | 7 | 1 | 2022-09-26 | 2022-10-26 | 23 | 1 | 22 | [20 empty] | 2022-10-27 | 2022-09-14 14:40 | 2023-12-17 |  | EXP | [8 empty] | 2023-04-24 | Connected |  | No
National Grid | WEBSTER | 446153 | 1570 | 7.6 | Solar | 01_412L2 | 2022-09-14 14:40 | 2022-09-15 | 18 | 16 | 2 | 2022-10-12 | 2022-11-02 | 16 | 0 | 16 | [20 empty] | 2022-11-04 | 2022-09-14 17:32 | 2024-03-27 | Yes | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HANSON | 456914 | 2341 | 6.96 | Solar | 07_95W2 | 2022-09-14 17:32 | 2022-09-15 | 6 | 5 | 1 | 2022-09-22 | 2022-10-19 | 19 | 0 | 19 | [20 empty] | 2022-10-19 |  | 2023-10-21 | Yes | EXP |  | 2022-11-05 | 2022-12-21 | 47 | 0 | 47 |  |  | 2023-01-12 | Connected |  | No
National Grid | FISKDALE | 432891 | 1518 | 15.2 | Solar | 01_408L2 | 2022-09-15 09:10 | 2022-09-16 | 0 | 0 | 0 | 2022-09-16 | 2022-10-03 | 12 | 0 | 12 | [20 empty] | 2022-10-03 |  | 2024-05-31 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | ESSEX | 459143 | 1929 | 15.2 | Solar | 12_51T2 | 2022-09-15 09:52 | 2022-09-16 | 2 | 0 | 2 | 2022-09-20 | 2022-10-18 | 20 | 0 | 20 | [20 empty] | 2022-10-19 |  | 2023-10-31 |  | EXP | [8 empty] | 2023-01-10 | Connected |  | No
National Grid | DIGHTON | 458078 | 2715 | 13 | Solar | 05_19W74 | 2022-09-15 09:58 | 2022-09-16 | 1 | 0 | 1 | 2022-09-19 | 2022-11-02 | 32 | 13 | 19 | [20 empty] | 2023-06-23 | 2022-09-15 15:11 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 450999 | 2302 | 3.8 | Solar | 07_91W43 | 2022-09-15 15:11 | 2022-09-16 | 2 | 0 | 2 | 2022-09-20 | 2022-10-18 | 20 | 0 | 20 | [20 empty] | 2022-10-19 |  | 2024-03-31 | Yes | EXP |  | 2023-03-29 | 2023-03-31 | 3 | 0 | 3 |  |  | 2023-04-28 | Connected |  | Yes
National Grid | RANDOLPH | 457785 | 2368 | 10 | Solar | 07_5W2 | 2022-09-15 15:53 | 2022-09-16 | 1 | 0 | 1 | 2022-09-19 | 2022-09-30 | 10 | 0 | 10 | [20 empty] | 2022-09-30 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEYMOUTH | 455605 | 2190 | 15.2 | Solar | 07_12W3 | 2022-09-16 09:02 | 2022-09-19 | 4 | 4 | 0 | 2022-09-23 | 2022-10-25 | 21 | 0 | 21 | [20 empty] | 2022-11-03 |  | 2023-12-08 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RANDOLPH | 456432 | 2368 | 7.6 | Solar | 07_5W3 | 2022-09-16 09:16 | 2022-09-19 | 2 | 0 | 2 | 2022-09-21 | 2022-10-18 | 19 | 0 | 19 | [20 empty] | 2022-10-19 | 2022-09-16 09:22 | 2023-12-06 |  | EXP | [8 empty] | 2023-03-21 | Connected |  | No
National Grid | UPTON | 447435 | 1568 | 15 | Solar | 05_335W3 | 2022-09-16 09:22 | 2022-09-19 | 1 | 0 | 1 | 2022-09-20 | 2022-10-19 | 21 | 2 | 19 | [20 empty] | 2022-10-20 |  | 2023-12-22 | Yes | EXP |  | 2023-02-09 | 2023-03-08 | 28 | 0 | 28 |  |  | 2023-03-11 | Connected |  | No
National Grid | LEOMINSTER | 429394 | 1453 | 4999 | Other | 01_207W4 | 2022-09-16 11:05 | 2022-09-19 | 24 | 15 | 9 | [10 empty] | 2022-10-24 | 2022-11-09 | 13 | 0 | 13 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | BROCKTON | 457764 | 2301 | 15 | Solar | 07_98W46 | 2022-09-16 12:07 | 2022-09-19 | 0 | 0 | 0 | 2022-09-20 | 2022-10-18 | 20 | 0 | 20 | [20 empty] | 2022-10-19 | 2022-09-16 13:09 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | GREAT BARRINGTON | 458936 | 1230 | 20 | Solar | 09_1109W3 | 2022-09-16 13:09 | 2022-09-19 | 3 | 3 | 0 | 2022-09-22 | 2022-10-19 | 19 | 0 | 19 | [20 empty] | 2022-10-19 |  | 2023-11-01 |  | EXP |  | 2023-01-28 | 2023-03-04 | 36 | 0 | 36 |  |  | 2023-04-27 | Connected |  | No
National Grid | MEDFORD | 456275 | 2155 | 10 | Solar | 12_37W5 | 2022-09-16 13:39 | 2022-09-19 | 19 | 19 | 0 | 2022-10-17 | 2022-11-08 | 17 | 0 | 17 | [20 empty] | 2022-11-14 |  | 2024-02-13 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ORANGE | 457131 | 1364 | 160 | Solar | 09_705W3 | 2022-09-19 14:28 | 2022-09-20 | 10 | 0 | 10 | [10 empty] | 2022-10-04 | 2022-11-07 | 24 | 0 | 24 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | WILBRAHAM | 460064 | 1095 | 15.2 | Solar | 09_507L1 | 2022-09-19 16:11 | 2022-09-20 | 1 | 0 | 1 | 2022-09-21 |  | 203 | 25 | 178 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BILLERICA | 460075 | 1821 | 15.2 | Solar | 14_70L6 | 2022-09-19 16:32 | 2022-09-20 | 3 | 0 | 3 | 2022-09-23 | 2022-10-18 | 17 | 0 | 17 | [20 empty] | 2022-10-19 |  | 2024-03-06 |  | EXP |  | 2023-01-07 | 2023-03-03 | 56 | 0 | 56 |  |  | 2023-05-24 | Connected |  | No
National Grid | LANCASTER | 460092 | 1523 | 7.6 | Solar | 01_225W1 | 2022-09-19 17:13 | 2022-09-20 | 10 | 5 | 5 | 2022-10-04 | 2022-10-26 | 16 | 0 | 16 | [20 empty] | 2022-11-04 |  | 2023-11-08 |  | EXP | [8 empty] | 2023-05-24 | Connected |  | No
National Grid | LEOMINSTER | 437434 | 1453 | 4999 | Other | 01_207W1 | 2022-09-19 21:33 | 2022-09-20 | 22 | 12 | 10 | [10 empty] | 2022-10-21 | 2022-11-17 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | WORCESTER | 396692 | 1607 | 4999 | Other | 01_8W1 | 2022-09-19 23:32 | 2022-09-20 | 24 | 13 | 11 | [10 empty] | 2022-10-25 | 2022-11-10 | 13 | 0 | 13 | [14 empty] | STD | [9 empty] | Pending Withdraw |  | No
National Grid | LYNN | 450088 | 1902 | 6 | Solar | 12_29W5 | 2022-09-20 08:58 | 2022-09-21 | 1 | 0 | 1 | 2022-09-22 | 2022-10-19 | 19 | 0 | 19 | [20 empty] | 2022-10-20 | 2022-09-20 09:20 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | AMESBURY | 451807 | 1913 | 10 | Solar | 14_5J11 | 2022-09-20 09:20 | 2022-09-21 | 1 | 0 | 1 | 2022-09-22 | 2022-10-18 | 18 | 0 | 18 | [20 empty] | 2022-10-19 | 2022-09-20 11:15 | 2023-11-23 | Yes | EXP | [8 empty] | 2023-01-07 | Connected |  | No
National Grid | HALIFAX | 434834 | 2338 | 3.8 | Solar | 07_912W75 | 2022-09-20 11:15 | 2022-09-21 | 2 | 0 | 2 | 2022-09-23 | 2022-10-19 | 18 | 0 | 18 | [20 empty] | 2022-10-20 |  | 2024-02-10 | Yes | EXP |  | 2023-02-01 | 2023-02-08 | 8 | 0 | 8 |  |  | 2023-04-28 | Connected |  | No
National Grid | WHITMAN | 460265 | 2382 | 15.2 | Solar | 07_797W29 | 2022-09-20 11:53 | 2022-09-21 | 78 | 57 | 21 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEOMINSTER | 441594 | 1453 | 4999 | Other | 01_227W1 | 2022-09-20 18:31 | 2022-09-21 | 21 | 12 | 9 | [10 empty] | 2022-10-21 | 2022-11-09 | 14 | 0 | 14 | [11 empty] | 2022-09-21 08:50 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | RANDOLPH | 459057 | 2368 | 6 | Solar | 07_5W4 | 2022-09-21 08:50 | 2022-09-22 | 2 | 0 | 2 | 2022-09-26 | 2022-10-20 | 18 | 0 | 18 | [20 empty] | 2022-10-24 |  | 2024-10-02 | Yes | EXP |  | 2023-06-01 | 2023-09-08 | 100 | 0 | 100 |  |  | 2023-10-20 | Connected |  | No
National Grid | EASTON | 460236 | 2375 | 9.984 | Solar | 07_92W44 | 2022-09-21 09:01 | 2022-09-22 | 10 | 9 | 1 | 2022-10-05 | 2022-11-02 | 20 | 0 | 20 | [20 empty] | 2022-11-16 |  | 2023-11-18 |  | EXP | [8 empty] | 2023-07-07 | Connected |  | No
National Grid | BROCKTON | 459507 | 2302 | 6 | Solar | 07_911W77 | 2022-09-21 09:02 | 2022-09-22 | 3 | 0 | 3 | 2022-09-27 | 2022-10-25 | 19 | 0 | 19 | [20 empty] | 2022-11-07 |  | 2024-04-05 |  | EXP | [8 empty] | 2024-03-01 | Connected |  | No
National Grid | HARVARD | 456305 | 1451 | 10 | Solar | 01_201W2 | 2022-09-22 10:29 | 2022-09-23 | 7 | 5 | 2 | 2022-10-03 | 2022-10-27 | 18 | 0 | 18 | [20 empty] | 2022-11-15 |  | 2024-01-25 |  | EXP | [8 empty] | 2023-01-28 | Connected |  | No
National Grid | LEOMINSTER | 437424 | 1453 | 4999 | Other | 01_225W3 | 2022-09-22 14:09 | 2022-09-23 | 17 | 10 | 7 | [10 empty] | 2022-10-19 | 2022-11-09 | 16 | 0 | 16 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | STOCKBRIDGE | 460725 | 1262 | 20 | Battery Add-On | 09_1102W1 | 2022-09-23 09:29 | 2022-09-26 | 11 | 10 | 1 | 2022-10-11 | 2022-11-02 | 17 | 0 | 17 | [20 empty] | 2022-11-16 | 2022-09-23 13:17 | 2023-12-04 |  | EXP | [8 empty] | 2023-08-24 | Connected |  | No
National Grid | ERVING | 453993 | 1344 | 7.6 | Solar | 09_705W3 | 2022-09-23 13:17 | 2022-09-26 | 3 | 0 | 3 | 2022-09-29 | 2022-10-26 | 19 | 0 | 19 | [20 empty] | 2022-11-04 |  | 2024-01-19 | Yes | EXP | [8 empty] | 2023-02-15 | Connected |  | No
National Grid | GARDNER | 459174 | 1440 | 240 | Solar | 01_607W4 | 2022-09-23 13:54 | 2022-09-26 | 16 | 8 | 8 | [10 empty] | 2022-10-18 | 2022-11-08 | 16 | 0 | 16 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | GLOUCESTER | 434942 | 1930 | 240 | Solar | 12_2364 | 2022-09-23 14:14 | 2022-09-26 | 8 | 0 | 8 | [10 empty] | 2022-10-06 | 2022-11-03 | 20 | 0 | 20 | [11 empty] | 2022-09-23 15:43 |  |  | STD | [9 empty] | Study |  | No
National Grid | PALMER | 459446 | 1069 | 100 | Solar | 09_523L2 | 2022-09-23 15:43 | 2022-09-26 | 34 | 24 | 10 | [10 empty] | 2022-11-15 | 2022-12-09 | 18 | 0 | 18 | [10 empty] | 2023-12-08 | 2022-09-23 15:54 |  | Yes | STD | [9 empty] | Completion Documents |  | Yes
National Grid | PALMER | 459286 | 1069 | 167.3 | Solar | 09_523L2 | 2022-09-23 15:54 | 2022-09-26 | 29 | 21 | 8 | [10 empty] | 2022-11-07 | 2022-11-23 | 12 | 0 | 12 | [10 empty] | 2023-11-13 | 2022-09-23 16:02 |  | Yes | STD | [9 empty] | Construction |  | Yes
National Grid | BONDSVILLE | 459546 | 1009 | 150 | Solar | 09_523L2 | 2022-09-23 16:02 | 2022-09-26 | 28 | 17 | 11 | [10 empty] | 2022-11-04 | 2022-11-23 | 13 | 0 | 13 | [10 empty] | 2023-11-13 | 2022-09-23 16:05 |  | Yes | STD | [9 empty] | Construction |  | Yes
National Grid | BONDSVILLE | 460033 | 1009 | 34.6 | Solar | 09_523L2 | 2022-09-23 16:05 | 2022-09-26 | 28 | 17 | 11 | [10 empty] | 2022-11-04 | 2022-11-23 | 13 | 0 | 13 | [10 empty] | 2023-11-13 |  |  | Yes | STD | [9 empty] | Completion Documents |  | Yes
National Grid | METHUEN | 444190 | 1844 | 499 | Solar | 14_74L1 | 2022-09-26 09:37 | 2022-09-27 | 25 | 15 | 10 | [10 empty] | 2022-11-02 | 2022-12-01 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | BROCKTON | 437923 | 2301 | 250 | Solar | 07_94W40 | 2022-09-26 09:51 | 2022-09-27 | 17 | 7 | 10 | [10 empty] | 2022-10-20 | 2023-02-09 | 75 | 51 | 24 | [11 empty] | 2022-09-26 10:00 |  |  | STD | [9 empty] | Study |  | No
National Grid | PALMER | 459650 | 1069 | 100 | Solar | 09_523L2 | 2022-09-26 10:00 | 2022-09-27 | 29 | 20 | 9 | [10 empty] | 2022-11-08 | 2022-11-29 | 14 | 0 | 14 | [10 empty] | 2023-11-13 |  |  | Yes | STD | [9 empty] | Completion Documents |  | Yes
National Grid | MONSON | 462569 | 1057 | 19 | Solar | 09_139L1 | 2022-09-26 11:07 | 2022-09-27 | 2 | 1 | 1 | 2022-09-28 | 2022-10-20 | 16 | 0 | 16 | [20 empty] | 2022-10-21 |  | 2024-09-06 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | PRIDESOUTH XING | 456466 | 1915 | 24.57 | Solar | 12_51T1 | 2022-09-26 11:31 | 2022-09-27 | 4 | 3 | 1 | 2022-10-03 | 2022-10-26 | 17 | 0 | 17 | [20 empty] | 2022-10-26 | 2022-09-26 11:44 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SALEM | 460824 | 1970 | 6 | Solar | 12_2W1 | 2022-09-26 11:44 | 2022-09-27 | 2 | 0 | 2 | 2022-09-29 | 2022-10-26 | 19 | 0 | 19 | [20 empty] | 2022-11-04 |  | 2024-06-09 | Yes | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | LEOMINSTER | 437404 | 1453 | 4999 | Other | 01_207W4 | 2022-09-26 13:01 | 2022-09-27 | 23 | 13 | 10 | [10 empty] | 2022-10-28 | 2022-11-22 | 17 | 0 | 17 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | UXBRIDGE | 461106 | 1569 | 13.8 | Solar | 05_321W10 | 2022-09-26 14:02 | 2022-09-27 | 4 | 0 | 4 | 2022-10-03 | 2022-12-28 | 58 | 38 | 20 | [20 empty] | 2023-01-09 |  | 2024-01-19 |  | EXP | [8 empty] | 2023-07-14 | Connected |  | No
National Grid | LEOMINSTER | 437417 | 1453 | 4000 | Other | 01_207W4 | 2022-09-26 16:45 | 2022-09-27 | 22 | 12 | 10 | [10 empty] | 2022-10-27 | 2022-11-17 | 15 | 0 | 15 | [14 empty] | STD | [9 empty] | Pending Withdraw |  | No
National Grid | GLOUCESTER | 453090 | 1930 | 8.7 | Solar | 12_28L2 | 2022-09-26 20:33 | 2022-09-27 | 3 | 2 | 1 | 2022-09-30 | 2022-10-26 | 18 | 0 | 18 | [20 empty] | 2022-10-26 | 2022-09-27 09:40 | 2023-12-14 |  | EXP | [8 empty] | 2023-02-07 | Connected |  | No
National Grid | MILLVILLE | 448582 | 1529 | 6 | Solar | 05_321W9 | 2022-09-27 09:40 | 2022-09-28 | 17 | 16 | 1 | 2022-10-24 | 2022-11-15 | 16 | 0 | 16 | [20 empty] | 2022-11-17 |  | 2024-05-03 | Yes | EXP | [8 empty] | 2023-08-11 | Connected |  | No
National Grid | STOCKBRIDGE | 463551 | 1262 | 15.2 | Solar | 09_1102W1 | 2022-09-27 10:02 | 2022-09-28 | 1 | 0 | 1 | 2022-09-29 | 2023-08-04 | 217 | 37 | 180 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SEEKONK | 458562 | 2771 | 8.99 | Solar | 05_7L3 | 2022-09-27 12:23 | 2022-09-28 | 8 | 7 | 1 | 2022-10-11 | 2022-11-01 | 16 | 0 | 16 | [20 empty] | 2022-11-02 |  | 2023-11-02 |  | EXP | [8 empty] | 2023-04-27 | Connected |  | No
National Grid | FALL RIVER | 460340 | 2723 | 5.51 | Solar | 05_106W82 | 2022-09-27 12:37 | 2022-09-28 | 3 | 1 | 2 | 2022-09-30 | 2022-10-26 | 18 | 0 | 18 | [20 empty] | 2022-10-31 |  | 2023-11-03 |  | EXP | [8 empty] | 2023-04-20 | Connected |  | Yes
National Grid | DUDLEY | 445324 | 1571 | 7.6 | Solar | 01_412L4 | 2022-09-27 13:11 | 2022-09-28 | 10 | 7 | 3 | 2022-10-13 | 2022-11-07 | 18 | 0 | 18 | 2022-11-29 | 2023-04-24 | 100 | 0 | 100 | [5 empty] | 2022-11-29 | 2023-04-24 | 100 | 0 | 100 | [5 empty] | 2023-05-15 | 2022-09-27 13:46 | 2024-10-25 |  | EXP |  | 2024-04-10 |  | 6 | 0 | 6 |  |  |  | Construction |  | Yes
National Grid | LAWRENCE | 450807 | 1843 | 5 | Solar | 14_61L3 | 2022-09-27 13:46 | 2022-09-28 | 4 | 1 | 3 | 2022-10-03 | 2022-10-26 | 17 | 0 | 17 | [20 empty] | 2022-11-03 | 2022-09-27 13:57 | 2024-01-21 | Yes | EXP |  | 2023-01-21 | 2023-01-20 | 0 | 0 | 0 |  |  | 2023-04-07 | Connected |  | No
National Grid | LEICESTER | 457727 | 1524 | 5.22 | Solar | 01_21W2 | 2022-09-27 13:57 | 2022-09-28 | 3 | 0 | 3 | 2022-10-03 | 2022-11-03 | 23 | 7 | 16 | [20 empty] | 2022-11-04 |  | 2024-05-19 | Yes | EXP |  | 2023-04-21 | 2023-05-19 | 29 | 0 | 29 |  |  | 2023-06-09 | Connected |  | No
National Grid | NEWBURYPORT | 463499 | 1950 | 15.2 | Solar | 14_36L1 | 2022-09-27 15:19 | 2022-09-28 | 6 | 5 | 1 | 2022-10-05 | 2022-10-28 | 17 | 0 | 17 | [20 empty] | 2022-10-28 |  | 2024-01-10 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTHAMPTON | 460740 | 1062 | 15.2 | Solar | 09_901W3 | 2022-09-28 13:54 | 2022-09-29 | 3 | 2 | 1 | 2022-10-04 | 2022-10-27 | 17 | 0 | 17 | [20 empty] | 2022-10-27 |  | 2023-11-07 |  | EXP | [8 empty] | 2023-03-31 | Connected |  | No
National Grid | METHUEN | 461031 | 1844 | 6 | Solar | 14_74L3 | 2022-09-28 16:05 | 2022-09-29 | 6 | 3 | 3 | 2022-10-07 | 2022-10-31 | 16 | 0 | 16 | [20 empty] | 2022-11-02 |  | 2023-12-16 |  | EXP | [8 empty] | 2023-04-13 | Connected |  | No
National Grid | HAVERHILL | 461652 | 1830 | 19.6 | Solar | 14_76L1 | 2022-09-28 16:13 | 2022-09-29 | 4 | 3 | 1 | 2022-10-05 | 2022-11-01 | 19 | 0 | 19 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | ANDOVER | 464540 | 1810 | 23.32 | Solar | 14_54L3 | 2022-09-29 09:31 | 2022-09-30 | 3 | 0 | 3 | 2022-10-05 | 2022-10-31 | 18 | 0 | 18 | [20 empty] | 2023-03-17 | 2022-09-29 10:02 | 2024-03-29 |  | EXP | [8 empty] | 2023-10-13 | Connected |  | No
National Grid | METHUEN | 460980 | 1844 | 3.8 | Solar | 14_74L3 | 2022-09-29 10:02 | 2022-09-30 | 7 | 3 | 4 | 2022-10-11 | 2022-11-02 | 17 | 0 | 17 | [20 empty] | 2022-11-27 | 2022-09-29 10:11 | 2024-07-19 | Yes | EXP |  | 2023-01-24 | 2023-02-01 | 9 | 0 | 9 |  |  |  | Withdrawn |  | Yes
National Grid | WEST NEWBURY | 461606 | 1985 | 7.6 | Solar | 14_47L2 | 2022-09-29 10:11 | 2022-12-14 | 5 | 0 | 5 | 2022-12-21 | 2023-01-20 | 20 | 0 | 20 | [20 empty] | 2023-01-26 |  | 2024-06-27 | Yes | EXP |  | 2023-08-10 | 2023-08-22 | 13 | 0 | 13 |  |  | 2023-09-11 | Connected |  | No
National Grid | LOWELL | 461779 | 1851 | 17.6 | Solar | 14_2L3 | 2022-09-29 14:18 | 2022-09-30 | 1 | 0 | 1 | 2022-10-03 | 2022-10-26 | 17 | 0 | 17 | [20 empty] | 2022-10-27 |  | 2024-01-13 |  | EXP | [8 empty] | 2023-11-30 | Connected |  | No
National Grid | CHELMSFORD | 415211 | 1863 | 7.6 | Solar | 14_73L2 | 2022-09-29 14:37 | 2022-09-30 | 1 | 0 | 1 | 2022-10-03 | 2022-10-26 | 17 | 0 | 17 | [20 empty] | 2022-03-07 |  | 2023-12-11 |  | EXP | [8 empty] | 2023-02-15 | Connected |  | No
National Grid | PEMBROKE | 464697 | 2359 | 9.984 | Solar | 07_910W25 | 2022-09-30 09:07 | 2022-10-03 | 16 | 16 | 0 | 2022-10-26 | 2022-11-16 | 15 | 0 | 15 | [20 empty] | 2022-11-17 |  | 2023-11-22 |  | EXP | [8 empty] | 2023-06-30 | Connected |  | No
National Grid | HAVERHILL | 418273 | 1830 | 500 | Solar | 14_47L1 | 2022-09-30 10:14 | 2022-10-03 | 89 | 79 | 10 | [10 empty] | 2023-02-15 | 2023-03-20 | 23 | 0 | 23 | [11 empty] | 2022-09-30 10:57 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTHAMPTON | 457933 | 1060 | 6.67 | Solar | 09_901W1 | 2022-09-30 10:57 | 2022-10-03 | 6 | 2 | 4 | 2022-10-11 | 2022-11-07 | 20 | 5 | 15 | [20 empty] | 2022-11-14 |  | 2024-03-29 | Yes | EXP |  | 2023-03-29 | 2023-03-30 | 2 | 0 | 2 |  |  | 2023-05-31 | Connected |  | Yes
National Grid | WESTPORT | 465035 | 2790 | 4.06 | Solar | 05_115W45 | 2022-09-30 13:07 | 2022-10-03 | 13 | 12 | 1 | 2022-10-21 | 2022-11-14 | 16 | 0 | 16 | [20 empty] | 2022-11-17 |  | 2024-01-20 |  | EXP | [8 empty] | 2023-01-30 | Connected |  | No
National Grid | GRANBY | 442707 | 1033 | 3000 | Solar | 09_527L1 | 2022-09-30 16:53 | 2022-10-03 | 17 | 7 | 10 | [10 empty] | 2022-10-26 | 2022-11-16 | 15 | 0 | 15 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | BILLERICA | 465206 | 1821 | 15.2 | Solar | 14_92L4 | 2022-10-02 14:04 | 2022-10-03 | 4 | 3 | 1 | 2022-10-06 | 2022-10-31 | 17 | 0 | 17 | [20 empty] | 2022-11-01 | 2022-10-02 16:30 | 2023-11-08 |  | EXP | [8 empty] | 2023-02-13 | Connected |  | No
National Grid | BROCKTON | 465211 | 2301 | 15.2 | Solar | 07_98W46 | 2022-10-02 16:30 | 2022-10-03 | 6 | 3 | 3 | 2022-10-11 | 2022-11-04 | 19 | 0 | 19 | [20 empty] | 2022-11-07 |  | 2024-04-01 | Yes | EXP |  | 2023-06-09 |  | 312 | 3 | 309 |  |  |  | Construction |  | Yes
National Grid | AVON | 412236 | 2322 | 4999.2 | Battery Add-On | 07_75W3 | 2022-10-02 17:21 | 2022-10-03 | 31 | 21 | 10 | [10 empty] | 2022-11-16 | 2023-08-03 | 178 | 158 | 20 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | PALMER | 465144 | 1069 | 50 | Solar | 09_503L1 | 2022-10-03 11:06 | 2022-10-04 | 19 | 9 | 10 | [10 empty] | 2022-10-31 | 2022-12-02 | 23 | 0 | 23 | [11 empty] | 2022-10-03 12:49 |  |  | STD | [9 empty] | Study |  | No
National Grid | BEVERLY | 464712 | 1915 | 7.6 | Solar | 12_12L2 | 2022-10-03 12:49 | 2022-10-04 | 3 | 0 | 3 | 2022-10-07 | 2022-11-16 | 28 | 11 | 17 | [20 empty] | 2022-11-17 |  | 2024-05-03 | Yes | EXP | [8 empty] | 2023-05-11 | Connected |  | No
National Grid | STOUGHTON | 465450 | 2072 | 3.8 | Solar | 07_94W44 | 2022-10-03 13:12 | 2022-10-04 | 1 | 0 | 1 | 2022-10-05 | 2022-11-02 | 20 | 0 | 20 | [20 empty] | 2022-11-16 | 2022-10-04 14:28 | 2023-12-07 |  | EXP | [8 empty] | 2023-04-28 | Connected |  | No
National Grid | HUBBARDSTON | 452437 | 1452 | 8.12 | Solar | 01_602W2 | 2022-10-04 14:28 | 2022-10-05 | 18 | 14 | 4 | 2022-10-31 | 2022-11-20 | 15 | 0 | 15 | [20 empty] | 2022-12-08 |  | 2024-05-04 | Yes | EXP |  | 2023-04-20 | 2023-05-03 | 14 | 0 | 14 |  |  | 2023-05-12 | Connected |  | No
National Grid | SPENCER | 460324 | 1562 | 15.66 | Solar | 01_552L1 | 2022-10-04 15:59 | 2022-10-05 | 19 | 17 | 2 | 2022-11-01 | 2022-11-22 | 15 | 0 | 15 | [20 empty] | 2022-11-30 |  | 2023-12-29 |  | EXP | [8 empty] | 2023-01-12 | Connected |  | No
National Grid | HAMPDEN | 460717 | 1036 | 17.98 | Solar | 09_139L3 | 2022-10-04 16:28 | 2022-10-05 | 4 | 1 | 3 | 2022-10-11 | 2022-11-01 | 16 | 0 | 16 | [20 empty] | 2022-11-02 | 2022-10-05 10:49 | 2024-01-13 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTMINSTER | 461669 | 1473 | 7.68 | Solar | 01_609W2 | 2022-10-05 10:49 | 2022-10-06 | 3 | 0 | 3 | 2022-10-11 | 2022-11-02 | 17 | 0 | 17 | [20 empty] | 2022-11-27 |  |  | Yes | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SEEKONK | 428659 | 2771 | 11700 | Other | 05_7L5 | 2022-10-05 10:52 | 2022-10-06 | 59 | 49 | 10 | [10 empty] | 2023-01-05 | 2023-02-02 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | LOWELL | 422062 | 1852 | 4999.2 | Battery Add-On | 14_3L4 | 2022-10-05 13:40 | 2022-10-06 | 176 | 166 | 10 | [10 empty] | 2023-06-23 | 2023-07-18 | 17 | 0 | 17 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | MEDFORD | 463128 | 2155 | 15 | Solar | 12_37W5 | 2022-10-05 14:35 | 2022-10-06 | 5 | 3 | 2 | 2022-10-14 | 2022-11-08 | 18 | 0 | 18 | [20 empty] | 2022-11-16 |  | 2024-01-08 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 465385 | 1844 | 10 | Solar | 14_63L1 | 2022-10-06 09:23 | 2022-10-07 | 59 | 37 | 22 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | REVERE | 462753 | 2151 | 7.6 | Solar | 12_7W2 | 2022-10-06 10:48 | 2022-10-07 | 4 | 1 | 3 | 2022-10-13 | 2022-11-03 | 16 | 0 | 16 | [20 empty] | 2022-11-27 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EAST LONGMEADOW | 460692 | 1028 | 14.79 | Solar | 09_139L5 | 2022-10-06 11:32 | 2022-10-07 | 2 | 0 | 2 | 2022-10-11 | 2022-12-23 | 52 | 37 | 15 | [20 empty] | 2023-01-04 | 2022-10-06 13:21 | 2024-05-12 |  | EXP | [8 empty] | 2023-08-02 | Connected |  | No
National Grid | NORTON | 457393 | 2766 | 10 | Solar | 05_4L1 | 2022-10-06 13:21 | 2022-10-07 | 2 | 0 | 2 | 2022-10-11 | 2022-11-08 | 21 | 0 | 21 | [20 empty] | 2022-11-08 | 2022-10-06 13:37 | 2024-02-15 | Yes | EXP |  | 2023-03-25 | 2023-04-20 | 27 | 0 | 27 |  |  | 2023-04-24 | Connected |  | No
National Grid | NORTH ANDOVER | 466523 | 1845 | 6 | Solar | 14_56L2 | 2022-10-06 13:37 | 2022-10-07 | 3 | 1 | 2 | 2022-10-13 | 2022-11-07 | 19 | 2 | 17 | [20 empty] | 2022-11-08 | 2022-10-06 15:03 | 2023-11-10 | Yes | EXP |  | 2022-12-21 | 2022-12-21 | 1 | 0 | 1 |  |  | 2023-04-14 | Connected |  | No
National Grid | BERLIN | 462578 | 1503 | 60 | Solar | 05_318W3 | 2022-10-06 15:03 | 2022-10-07 | 22 | 12 | 10 | 2022-11-08 | 2022-12-05 | 18 | 0 | 18 | [20 empty] | 2023-01-25 | 2022-10-06 16:48 | 2024-06-25 | Yes | EXP | [8 empty] | 2024-03-08 | Connected |  | No
National Grid | MARLBOROUGH | 454160 | 1752 | 133.2 | Solar | 05_317W6 | 2022-10-06 16:48 | 2022-10-07 | 72 | 62 | 10 | 2023-01-25 | 2023-02-24 | 22 | 0 | 22 | [20 empty] | 2023-04-25 | 2022-10-07 07:21 | 2024-07-17 | Yes | EXP | [9 empty] | Construction |  | No
National Grid | HAVERHILL | 465137 | 1830 | 3.8 | Solar | 14_76L3 | 2022-10-07 07:21 | 2022-10-11 | 1 | 0 | 1 | 2022-10-12 | 2022-11-02 | 16 | 0 | 16 | [20 empty] | 2022-11-03 |  | 2024-04-30 | Yes | EXP |  | 2023-04-11 | 2023-04-28 | 18 | 0 | 18 |  |  | 2023-06-06 | Connected |  | No
National Grid | ATTLEBORO | 466729 | 2703 | 100 | Solar | 05_8L1 | 2022-10-07 13:59 | 2022-10-11 | 24 | 15 | 9 | [10 empty] | 2022-11-14 | 2022-12-08 | 18 | 0 | 18 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 457510 | 1844 | 100 | Solar | 14_74L1 | 2022-10-10 08:23 | 2022-10-11 | 59 | 49 | 10 | [10 empty] | 2023-01-05 | 2023-02-07 | 23 | 0 | 23 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | CHARLTON | 466862 | 1507 | 20 | Solar | 01_415L1 | 2022-10-10 15:52 | 2022-10-11 | 18 | 17 | 1 | 2022-11-04 | 2022-11-30 | 17 | 0 | 17 | [20 empty] | 2022-12-01 |  | 2024-04-30 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | HANOVER | 438749 | 2339 | 375 | Solar | 07_95W3 | 2022-10-10 16:39 | 2022-10-11 | 21 | 12 | 9 | [10 empty] | 2022-11-08 | 2022-12-07 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | WESTFORD | 462180 | 1886 | 13.63 | Solar | 14_58L1 | 2022-10-10 19:45 | 2022-10-11 | 2 | 0 | 2 | 2022-10-13 | 2022-11-02 | 15 | 0 | 15 | 2022-11-08 | 2022-12-13 | 15 | 0 | 15 | [5 empty] | 2022-11-08 | 2022-12-13 | 15 | 0 | 15 | [5 empty] | 2022-12-05 |  | 2024-01-06 |  | EXP |  | 2023-02-18 | 2023-05-05 | 77 | 0 | 77 |  |  | 2023-06-26 | Connected |  | No
National Grid | DUNSTABLE | 465180 | 1827 | 15.95 | Solar | 01_210L1 | 2022-10-10 19:47 | 2022-10-11 | 1 | 0 | 1 | 2022-10-12 | 2022-11-01 | 15 | 0 | 15 | [20 empty] | 2022-11-02 |  | 2023-11-08 |  | EXP | [8 empty] | 2023-02-15 | Connected |  | Yes
National Grid | SPENCER | 452168 | 1562 | 5 | Solar | 01_552L1 | 2022-10-11 11:25 | 2022-10-12 | 27 | 24 | 3 | 2022-11-21 | 2022-12-16 | 19 | 0 | 19 | [20 empty] | 2022-12-25 | 2022-10-11 15:31 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WILBRAHAM | 465488 | 1095 | 6.96 | Solar | 09_507L2 | 2022-10-11 15:31 | 2022-10-12 | 2 | 0 | 2 | 2022-10-14 | 2022-11-16 | 23 | 7 | 16 | [20 empty] | 2022-11-17 | 2022-10-11 17:07 | 2024-02-09 | Yes | EXP |  | 2023-02-03 | 2023-02-08 | 6 | 0 | 6 |  |  | 2023-02-14 | Connected |  | No
National Grid | GARDNER | 450860 | 1440 | 5 | Solar | 01_607W1 | 2022-10-11 17:07 | 2022-10-12 | 27 | 24 | 3 | 2022-11-21 | 2022-12-16 | 19 | 0 | 19 | [20 empty] | 2022-12-25 | 2022-10-11 17:14 | 2024-09-20 | Yes | EXP | [8 empty] | 2023-09-27 | Connected |  | No
National Grid | METHUEN | 456175 | 1844 | 5 | Solar | 14_5J41 | 2022-10-11 17:14 | 2022-10-12 | 10 | 9 | 1 | 2022-10-25 | 2022-11-16 | 16 | 0 | 16 | [20 empty] | 2022-11-17 | 2022-10-12 09:25 | 2024-01-06 | Yes | EXP |  | 2023-03-15 | 2023-03-31 | 17 | 0 | 17 |  |  | 2023-04-03 | Connected |  | No
National Grid | RANDOLPH | 466464 | 2368 | 10 | Solar | 07_97W1 | 2022-10-12 09:25 | 2022-10-13 | 1 | 0 | 1 | 2022-10-14 | 2022-11-08 | 18 | 0 | 18 | [20 empty] | 2022-11-14 |  | 2024-06-14 | Yes | EXP | [8 empty] | 2023-07-28 | Connected |  | No
National Grid | BEVERLY | 466433 | 1915 | 6 | Solar | 12_12L2 | 2022-10-12 17:12 | 2022-10-13 | 1 | 0 | 1 | 2022-10-14 | 2022-11-08 | 18 | 0 | 18 | [20 empty] | 2022-11-15 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SALISBURY | 467964 | 1952 | 15.2 | Solar | 14_7L2 | 2022-10-13 09:37 | 2022-10-14 | 40 | 39 | 1 | 2022-12-13 | 2023-01-12 | 21 | 0 | 21 | [20 empty] | 2023-01-12 |  | 2024-01-17 |  | EXP | [8 empty] | 2023-04-20 | Connected |  | No
National Grid | STOUGHTON | 466090 | 2072 | 10 | Solar | 07_913W17 | 2022-10-13 11:05 | 2022-10-14 | 3 | 0 | 3 | 2022-10-19 | 2022-11-08 | 15 | 0 | 15 | [20 empty] | 2022-11-14 |  | 2023-11-17 |  | EXP | [8 empty] | 2022-12-28 | Connected |  | No
National Grid | SHUTESBURY | 460940 | 1072 | 5.22 | Solar | 09_704W1 | 2022-10-13 11:15 | 2022-10-14 | 2 | 0 | 2 | 2022-10-18 | 2022-11-07 | 15 | 0 | 15 | [20 empty] | 2022-11-08 | 2022-10-13 13:32 | 2023-11-11 |  | EXP | [8 empty] | 2023-06-21 | Connected |  | Yes
National Grid | WEST BROOKFIELD | 457878 | 1585 | 3.77 | Solar | 01_525L2 | 2022-10-13 13:32 | 2022-10-14 | 4 | 1 | 3 | 2022-10-19 | 2022-11-09 | 16 | 2 | 14 | [20 empty] | 2022-11-17 |  | 2024-08-06 | Yes | EXP |  | 2023-07-19 | 2023-08-04 | 17 | 0 | 17 |  |  | 2023-08-24 | Connected |  | No
National Grid | SOMERSET | 467759 | 2726 | 6 | Solar | 05_18J5 | 2022-10-14 11:16 | 2022-10-17 | 6 | 5 | 1 | 2022-10-24 | 2022-10-21 | 0 | 0 | 0 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SCITUATE | 461808 | 2066 | 480 | Solar | 07_915W37 | 2022-10-14 14:13 | 2022-10-17 | 13 | 4 | 9 | [10 empty] | 2022-11-04 | 2022-11-30 | 17 | 0 | 17 | [11 empty] | 2022-10-14 15:12 |  |  | STD | [9 empty] | Study |  | Yes
National Grid | WEST NEWBURY | 464397 | 1985 | 9.86 | Solar | 14_47L2 | 2022-10-14 15:12 | 2022-10-17 | 9 | 0 | 9 | 2022-10-28 | 2022-11-28 | 20 | 0 | 20 | [20 empty] | 2022-11-29 | 2022-10-17 07:21 | 2023-12-05 | Yes | EXP |  | 2023-01-25 | 2023-02-01 | 8 | 0 | 8 |  |  | 2023-04-07 | Connected |  | No
National Grid | EAST LONGMEADOW | 457549 | 1028 | 10 | Solar | 09_508L5 | 2022-10-17 07:21 | 2022-10-18 | 2 | 0 | 2 | 2022-10-20 | 2022-11-15 | 19 | 5 | 14 | [20 empty] | 2022-11-17 |  | 2023-11-28 | Yes | EXP | [8 empty] | 2023-04-01 | Connected |  | No
National Grid | BROCKTON | 457927 | 2302 | 4999 | Other | 07_911W57 | 2022-10-17 15:38 | 2022-10-18 | 16 | 8 | 8 | [10 empty] | 2022-11-08 | 2022-11-23 | 11 | 0 | 11 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | PETERSHAM | 466768 | 1366 | 3.8 | Solar | 09_604W1 | 2022-10-17 19:16 | 2022-10-18 | 1 | 0 | 1 | 2022-10-19 | 2022-11-07 | 14 | 0 | 14 | [20 empty] | 2022-11-07 |  | 2023-11-18 |  | EXP | [8 empty] | 2022-12-03 | Connected |  | No
National Grid | FOXBOROUGH | 453555 | 2035 | 4999.2 | Battery Add-On | 05_3422W4 | 2022-10-17 19:26 | 2022-10-18 | 8 | 0 | 8 | [10 empty] | 2022-10-28 | 2022-11-21 | 16 | 0 | 16 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | NORTON | 434014 | 2766 | 4999.2 | Battery Add-On | 05_4L1 | 2022-10-18 08:26 | 2022-10-19 | 120 | 112 | 8 | [10 empty] | 2023-04-13 | 2023-05-15 | 22 | 2 | 20 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | SOMERSET | 468426 | 2726 | 10 | Solar | 05_11W82 | 2022-10-18 09:03 | 2022-10-19 | 2 | 0 | 2 | 2022-10-21 | 2022-11-14 | 16 | 0 | 16 | [20 empty] | 2022-11-27 |  | 2024-02-23 |  | EXP | [8 empty] | 2023-03-22 | Connected |  | No
National Grid | DIGHTON | 461180 | 2715 | 10 | Solar | 05_19W73 | 2022-10-18 11:58 | 2022-10-19 | 2 | 0 | 2 | 2022-10-21 | 2022-11-08 | 13 | 0 | 13 | [20 empty] | 2022-11-14 |  | 2024-02-22 |  | EXP | [8 empty] | 2023-03-27 | Connected |  | Yes
National Grid | WEST STOCKBRIDGE | 469401 | 1266 | 7.6 | Solar | 09_1109W3 | 2022-10-18 16:57 | 2022-10-19 | 2 | 0 | 2 | 2022-10-21 | 2023-08-04 | 202 | 107 | 95 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | LANCASTER | 466225 | 1523 | 13.824 | Solar | 01_225W3 | 2022-10-18 17:20 | 2022-10-19 | 10 | 8 | 2 | 2022-11-02 | 2023-01-18 | 51 | 31 | 20 | [20 empty] | 2023-01-23 |  | 2024-02-16 |  | EXP | [8 empty] | 2023-05-23 | Connected |  | No
National Grid | BRIDGEWATER | 467978 | 2324 | 28.8 | Solar | 07_797W1 | 2022-10-19 10:18 | 2022-10-20 | 2 | 1 | 1 | 2022-10-24 | 2022-11-29 | 25 | 7 | 18 | 2023-07-21 | 2023-09-18 | 41 | 0 | 41 | [5 empty] | 2023-07-21 | 2023-09-18 | 41 | 0 | 41 | [5 empty] | 2023-09-21 |  | 2024-10-22 |  | EXP | [9 empty] | Construction |  | No
National Grid | CHELMSFORD | 469528 | 1824 | 7.6 | Solar | 14_73L1 | 2022-10-19 10:36 | 2022-10-20 | 1 | 0 | 1 | 2022-10-21 | 2022-12-19 | 40 | 22 | 18 | [20 empty] | 2022-12-20 |  | 2023-12-20 |  | EXP | [8 empty] | 2023-03-17 | Connected |  | No
National Grid | MILLBURY | 460302 | 1527 | 13.92 | Solar | 01_304W3 | 2022-10-19 12:56 | 2022-10-20 | 3 | 0 | 3 | 2022-10-25 | 2022-11-16 | 16 | 0 | 16 | [20 empty] | 2022-11-17 | 2022-10-19 15:05 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOUTH ATTLEBORO | 469711 | 2703 | 16.53 | Solar | 05_9L6 | 2022-10-19 15:05 | 2022-10-20 | 53 | 51 | 2 | 2023-01-09 | 2023-02-10 | 24 | 0 | 24 | [20 empty] | 2023-02-14 |  | 2024-05-07 | Yes | EXP |  | 2023-07-20 | 2023-09-14 | 57 | 0 | 57 |  |  | 2023-09-19 | Connected |  | No
National Grid | REHOBOTH | 457493 | 2769 | 10 | Solar | 05_7L5 | 2022-10-19 15:58 | 2022-10-20 | 12 | 10 | 2 | 2022-11-07 | 2022-11-30 | 16 | 0 | 16 | [20 empty] | 2022-12-05 |  | 2023-12-08 |  | EXP | [8 empty] | 2023-04-21 | Connected |  | No
National Grid | FRANKLIN | 469770 | 2038 | 15.2 | Solar | 05_344W1 | 2022-10-19 16:34 | 2022-10-20 | 2 | 0 | 2 | 2022-10-24 | 2022-11-14 | 15 | 0 | 15 | [20 empty] | 2022-11-17 |  | 2023-12-01 |  | EXP | [8 empty] | 2023-01-24 | Connected |  | No
National Grid | SEEKONK | 422061 | 2771 | 4999.2 | Battery Add-On | 05_7L3 | 2022-10-19 19:46 | 2022-10-20 | 134 | 125 | 9 | [10 empty] | 2023-05-05 | 2023-07-12 | 44 | 24 | 20 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | GREAT BARRINGTON | 469582 | 1230 | 20.88 | Solar | 09_1109W2 | 2022-10-19 21:00 | 2022-10-20 | 4 | 2 | 2 | 2022-10-25 | 2022-10-24 | 0 | 0 | 0 | [20 empty] | 2023-09-29 |  | 2024-10-27 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | NANTUCKET | 467030 | 2554 | 7.6 | Solar | 04_101L4 | 2022-10-20 08:45 | 2022-10-21 | 16 | 15 | 1 | 2022-11-14 | 2022-12-13 | 21 | 0 | 21 | [20 empty] | 2022-12-14 |  | 2024-05-24 |  | EXP | [8 empty] | 2024-01-11 | Connected |  | No
National Grid | QUINCY | 468425 | 2169 | 9.8 | Solar | 07_1W2 | 2022-10-20 09:54 | 2022-10-21 | 2 | 0 | 2 | 2022-10-25 |  | 180 | 25 | 155 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 468024 | 1841 | 10 | Solar | 14_74L3 | 2022-10-20 10:16 | 2022-10-21 | 2 | 0 | 2 | 2022-10-25 | 2022-11-29 | 24 | 0 | 24 | [20 empty] | 2022-11-30 |  | 2023-12-02 |  | EXP | [8 empty] | 2023-05-03 | Connected |  | No
National Grid | TEWKSBURY | 469773 | 1876 | 15.2 | Solar | 14_14L1 | 2022-10-20 10:39 | 2022-10-21 | 14 | 13 | 1 | 2022-11-09 | 2022-11-30 | 14 | 0 | 14 | [20 empty] | 2022-12-01 |  | 2024-02-23 |  | EXP | [8 empty] | 2023-11-09 | Connected |  | No
National Grid | RANDOLPH | 465464 | 2368 | 6 | Solar | 07_5W2 | 2022-10-20 10:44 | 2022-10-21 | 3 | 0 | 3 | 2022-10-26 | 2023-11-13 | 261 | 247 | 14 | [21 empty] | 2022-10-20 11:04 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LYNN | 469141 | 1905 | 10 | Solar | 12_19W1 | 2022-10-20 11:04 | 2022-10-21 | 3 | 0 | 3 | 2022-10-26 | 2022-11-21 | 18 | 0 | 18 | [20 empty] | 2022-11-27 | 2022-10-20 13:40 | 2024-04-11 | Yes | EXP |  | 2023-04-11 | 2023-04-10 | 0 | 0 | 0 |  |  | 2023-04-25 | Connected |  | No
National Grid | TEWKSBURY | 465832 | 1876 | 14.5 | Solar | 14_75L2 | 2022-10-20 13:40 | 2022-10-21 | 7 | 6 | 1 | 2022-11-01 | 2022-11-22 | 15 | 0 | 15 | [20 empty] | 2022-11-28 | 2022-10-21 09:11 | 2024-01-24 | Yes | EXP |  | 2023-03-22 | 2023-04-05 | 15 | 0 | 15 |  |  | 2023-06-30 | Connected |  | No
National Grid | NORTH ANDOVER | 470177 | 1810 | 15.2 | Solar | 14_62L2 | 2022-10-21 09:11 | 2022-10-24 | 2 | 0 | 2 | 2022-10-26 | 2022-11-21 | 18 | 0 | 18 | [20 empty] | 2022-11-30 |  | 2024-01-20 | Yes | EXP | [8 empty] | 2023-04-20 | Connected |  | No
National Grid | BOXFORD | 466707 | 1921 | 22.8 | Solar | 14_56L3 | 2022-10-21 09:18 | 2022-10-24 | 2 | 0 | 2 | 2022-10-26 | 2024-02-15 | 325 | 302 | 23 | [20 empty] | 2024-02-20 | 2022-10-21 13:39 | 2025-03-20 |  | EXP | [9 empty] | Meter Installation |  | Yes
National Grid | CHERRY VALLEY | 470048 | 1611 | 20 | Solar | 01_21W2 | 2022-10-21 13:39 | 2022-10-24 | 4 | 2 | 2 | 2022-10-28 | 2022-11-28 | 20 | 0 | 20 | [20 empty] | 2022-12-02 |  | 2024-06-11 | Yes | EXP |  | 2023-05-16 | 2023-06-12 | 28 | 0 | 28 |  |  | 2023-06-21 | Connected |  | Yes
National Grid | MALDEN | 468598 | 2148 | 6 | Solar | 12_67J4 | 2022-10-21 14:05 | 2022-10-24 | 5 | 2 | 3 | 2022-10-31 | 2022-11-22 | 16 | 0 | 16 | [20 empty] | 2022-12-08 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BLACKSTONE | 469025 | 1504 | 3.8 | Solar | 05_108W60 | 2022-10-21 14:24 | 2022-10-24 | 4 | 1 | 3 | 2022-10-27 | 2022-12-13 | 33 | 20 | 13 | [20 empty] | 2022-12-19 | 2022-10-21 15:06 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SAUGUS | 468441 | 1906 | 7.6 | Solar | 12_16W1 | 2022-10-21 15:06 | 2022-10-24 | 3 | 0 | 3 | 2022-10-27 | 2022-11-17 | 15 | 0 | 15 | [20 empty] | 2022-11-17 |  | 2024-07-25 | Yes | EXP | [8 empty] | 2023-08-09 | Connected |  | No
National Grid | SOUTHBRIDGE | 466552 | 1550 | 250 | Solar | 01_413L1 | 2022-10-21 15:53 | 2022-10-24 | 12 | 6 | 6 | [10 empty] | 2022-11-08 | 2022-12-05 | 18 | 0 | 18 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | EAST LONGMEADOW | 430108 | 1028 | 9.86 | Solar | 09_139L5 | 2022-10-21 16:11 | 2022-10-24 | 2 | 0 | 2 | 2022-10-26 | 2022-11-21 | 18 | 0 | 18 | [20 empty] | 2022-05-20 |  | 2023-11-29 |  | EXP | [8 empty] | 2023-06-26 | Connected |  | No
National Grid | GREAT BARRINGTON | 465317 | 1230 | 10 | Solar | 09_1109W3 | 2022-10-24 10:18 | 2022-10-25 | 2 | 0 | 2 | 2022-10-27 | 2023-11-13 | 260 | 247 | 13 | [21 empty] | 2022-10-24 14:48 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTBOROUGH | 470820 | 1581 | 15.2 | Solar | 05_312W4 | 2022-10-24 14:48 | 2022-10-25 | 1 | 0 | 1 | 2022-10-26 | 2022-11-21 | 18 | 0 | 18 | [20 empty] | 2022-11-30 |  | 2023-12-19 | Yes | EXP |  | 2023-02-15 | 2023-04-27 | 72 | 0 | 72 |  |  | 2023-06-22 | Connected |  | No
National Grid | CLINTON | 470890 | 1510 | 15.2 | Solar | 01_216W2 | 2022-10-24 16:52 | 2022-10-25 | 2 | 0 | 2 | 2022-10-27 | 2022-11-15 | 13 | 0 | 13 | [20 empty] | 2022-11-15 |  | 2023-11-28 |  | EXP | [8 empty] | 2023-04-20 | Connected |  | No
National Grid | WEST NEWBURY | 466928 | 1985 | 20 | Solar | 14_47L1 | 2022-10-24 19:15 | 2022-10-25 | 226 | 25 | 201 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ABINGTON | 401108 | 2351 | 4999.2 | Battery Add-On | 07_911W77 | 2022-10-25 08:55 | 2022-10-26 | 141 | 131 | 10 | [10 empty] | 2023-05-23 | 2023-06-22 | 21 | 0 | 21 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | COHASSET | 470354 | 2025 | 150 | Solar | 07_96W41 | 2022-10-25 13:09 | 2022-10-26 | 97 | 87 | 10 | [10 empty] | 2023-03-20 | 2023-04-19 | 22 | 0 | 22 | [11 empty] | 2022-10-26 15:46 |  |  | STD | [9 empty] | Pending Withdraw |  | No
National Grid | EVERETT | 464132 | 2149 | 80 | Solar | 12_37W6 | 2022-10-26 15:46 | 2022-10-27 | 74 | 63 | 11 | 2023-02-15 | 2023-03-20 | 23 | 0 | 23 | [20 empty] | 2023-03-28 |  | 2025-03-25 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | COHASSET | 458657 | 2025 | 300 | Solar | 07_96W41 | 2022-10-26 16:19 | 2022-10-27 | 36 | 26 | 10 | [10 empty] | 2022-12-20 | 2023-01-30 | 28 | 5 | 23 | [14 empty] | STD | [9 empty] | Pending Withdraw |  | No
National Grid | REVERE | 471831 | 2151 | 15.2 | Solar | 12_7J6 | 2022-10-27 10:44 | 2022-10-28 | 1 | 0 | 1 | 2022-10-31 | 2022-11-22 | 16 | 0 | 16 | [20 empty] | 2022-11-23 |  | 2024-03-07 |  | EXP | [8 empty] | 2023-11-13 | Connected |  | No
National Grid | UPTON | 471899 | 1568 | 15.2 | Solar | 05_335W3 | 2022-10-27 11:37 | 2022-10-28 | 1 | 0 | 1 | 2022-10-31 | 2022-11-28 | 19 | 0 | 19 | [20 empty] | 2022-11-29 |  | 2023-12-13 |  | EXP | [8 empty] | 2023-01-26 | Connected |  | No
National Grid | ALFORD | 471659 | 1230 | 16.34 | Solar | 09_1109W3 | 2022-10-27 12:01 | 2022-10-28 | 8 | 7 | 1 | 2022-11-08 | 2022-11-30 | 15 | 0 | 15 | [20 empty] | 2022-12-01 | 2022-10-27 12:24 | 2023-12-07 |  | EXP | [8 empty] | 2023-03-01 | Connected |  | No
National Grid | UXBRIDGE | 438621 | 1569 | 10 | Solar | 05_321W10 | 2022-10-27 12:24 | 2022-10-28 | 2 | 0 | 2 | 2022-11-01 | 2022-12-19 | 33 | 18 | 15 | [20 empty] | 2022-06-30 |  | 2024-07-20 | Yes | EXP |  | 2023-06-09 | 2023-06-21 | 13 | 0 | 13 |  |  | 2023-08-02 | Connected |  | No
National Grid | METHUEN | 458326 | 1844 | 7.83 | Solar | 14_63L2 | 2022-10-27 14:28 | 2022-10-28 | 16 | 14 | 2 | 2022-11-22 | 2022-12-21 | 21 | 0 | 21 | 2023-01-17 | 2023-03-03 | 13 | 0 | 13 | [5 empty] | 2023-01-17 | 2023-03-03 | 13 | 0 | 13 | [5 empty] | 2023-02-02 | 2022-10-27 15:07 | 2024-11-30 |  | EXP |  | 2023-06-15 | 2024-01-26 | 226 | 3 | 223 |  |  | 2024-03-09 | Connected |  | No
National Grid | AYER | 472052 | 1432 | 18.816 | Solar | 01_201W2 | 2022-10-27 15:07 | 2022-10-28 | 14 | 13 | 1 | 2022-11-17 | 2022-12-27 | 27 | 15 | 12 | [20 empty] | 2022-12-27 |  | 2024-01-11 | Yes | EXP |  | 2023-06-09 | 2023-08-10 | 63 | 0 | 63 |  |  | 2023-08-11 | Connected |  | No
National Grid | AYER | 456437 | 1432 | 4.64 | Solar | 01_201W1 | 2022-10-27 16:02 | 2022-10-28 | 2 | 0 | 2 | 2022-11-22 | 2022-12-20 | 20 | 0 | 20 | [20 empty] | 2022-12-29 | 2022-10-27 16:25 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RUTLAND | 452194 | 1543 | 6.09 | Solar | 01_55W1 | 2022-10-27 16:25 | 2022-10-28 | 17 | 15 | 2 | 2022-11-23 | 2022-12-13 | 14 | 0 | 14 | [20 empty] | 2022-12-16 |  | 2024-06-14 | Yes | EXP |  | 2023-06-06 | 2023-06-14 | 9 | 0 | 9 |  |  | 2023-07-12 | Connected |  | No
National Grid | FALL RIVER | 451467 | 2720 | 5.76 | Solar | 05_106W81 | 2022-10-27 17:47 | 2022-10-28 | 11 | 9 | 2 | 2022-11-14 | 2022-12-01 | 13 | 0 | 13 | [20 empty] | 2022-12-05 |  | 2023-12-07 |  | EXP | [8 empty] | 2022-12-14 | Connected |  | Yes
National Grid | DRACUT | 472086 | 1826 | 15.2 | Solar | 14_75L2 | 2022-10-28 06:55 | 2022-10-31 | 1 | 0 | 1 | 2022-11-01 | 2022-11-28 | 18 | 0 | 18 | [20 empty] | 2022-11-29 |  | 2023-12-13 |  | EXP | [8 empty] | 2023-07-25 | Connected |  | Yes
National Grid | MENDON | 470892 | 1756 | 9.984 | Solar | 05_335W1 | 2022-10-28 09:27 | 2022-10-31 | 3 | 0 | 3 | 2022-11-03 | 2022-11-22 | 13 | 0 | 13 | [20 empty] | 2022-11-30 |  | 2023-12-28 |  | EXP | [8 empty] | 2023-08-23 | Connected |  | No
National Grid | NORTH GRAFTON | 470975 | 1536 | 20.352 | Solar | 01_328W3 | 2022-10-28 09:55 | 2022-10-31 | 5 | 4 | 1 | 2022-11-04 | 2022-11-29 | 16 | 0 | 16 | [20 empty] | 2022-11-30 | 2022-10-28 12:49 | 2024-01-02 |  | EXP | [8 empty] | 2023-04-11 | Connected |  | No
National Grid | STURBRIDGE | 409406 | 1566 | 7.6 | Solar | 01_415L1 | 2022-10-28 12:49 | 2022-10-31 | 57 | 51 | 6 | 2023-01-25 | 2023-02-21 | 20 | 1 | 19 | [20 empty] | 2023-02-22 |  | 2024-05-29 | Yes | EXP |  | 2023-04-27 | 2023-06-08 | 43 | 0 | 43 |  |  | 2023-08-24 | Connected |  | No
National Grid | WILLIAMSTOWN | 461061 | 1267 | 10 | Solar | 09_1003W2 | 2022-10-28 14:45 | 2022-10-31 | 8 | 5 | 3 | 2022-11-10 | 2022-12-13 | 22 | 0 | 22 | [20 empty] | 2022-12-14 |  | 2024-02-12 |  | EXP | [8 empty] | 2023-09-22 | Connected |  | No
National Grid | GRANBY | 458825 | 1033 | 4980 | Solar | 09_527L1 | 2022-10-28 15:26 | 2022-10-31 | 21 | 15 | 6 | [10 empty] | 2022-11-30 | 2022-11-30 | 1 | 0 | 1 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | FRANKLIN | 472534 | 2038 | 15.2 | Solar | 05_344W5 | 2022-10-31 08:42 | 2022-11-01 | 1 | 0 | 1 | 2022-11-02 | 2022-11-28 | 17 | 0 | 17 | [20 empty] | 2022-11-29 |  | 2023-12-13 |  | EXP | [8 empty] | 2023-02-08 | Connected |  | No
National Grid | ERVING | 436398 | 1344 | 3373 | Other | 09_705W1 | 2022-10-31 16:13 | 2022-11-01 | 113 | 107 | 6 | [10 empty] | 2023-04-18 | 2023-07-12 | 59 | 40 | 19 | [11 empty] | 2022-11-01 08:15 |  |  | STD | [9 empty] | Study |  | Yes
National Grid | OXFORD | 471444 | 1540 | 6.38 | Solar | 01_406L4 | 2022-11-01 08:15 | 2022-11-02 | 8 | 3 | 5 | 2022-11-15 | 2022-12-07 | 16 | 0 | 16 | [20 empty] | 2022-12-09 | 2022-11-01 11:08 | 2024-03-30 | Yes | EXP |  | 2023-02-23 | 2023-03-30 | 36 | 0 | 36 |  |  | 2023-05-01 | Connected |  | No
National Grid | BEVERLY | 468924 | 1915 | 10 | Solar | 12_72L1 | 2022-11-01 11:08 | 2022-11-02 | 1 | 0 | 1 | 2022-11-03 | 2023-02-01 | 60 | 42 | 18 | [20 empty] | 2023-02-07 |  | 2024-07-02 | Yes | EXP |  | 2023-04-22 | 2023-06-30 | 70 | 0 | 70 |  |  | 2023-08-09 | Connected |  | No
National Grid | LYNN | 471551 | 1902 | 80 | Solar | 12_22W2 | 2022-11-01 16:12 | 2022-11-02 | 7 | 0 | 7 | 2022-11-14 | 2022-12-14 | 22 | 0 | 22 | [20 empty] | 2023-01-25 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ATTLEBORO | 471193 | 2703 | 120 | Solar | 05_9L1 | 2022-11-01 16:23 | 2022-11-02 | 8 | 1 | 7 | [10 empty] | 2022-11-14 | 2022-12-08 | 18 | 0 | 18 | [11 empty] | 2022-11-01 16:48 |  |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | WESTFORD | 473412 | 1886 | 15.2 | Solar | 14_73L2 | 2022-11-01 16:48 | 2022-11-02 | 1 | 0 | 1 | 2022-11-03 | 2022-11-30 | 19 | 2 | 17 | [20 empty] | 2022-11-30 | 2022-11-02 08:47 | 2023-12-19 | Yes | EXP |  | 2023-01-28 | 2023-02-15 | 19 | 0 | 19 |  |  | 2023-06-13 | Connected |  | No
National Grid | NORTHAMPTON | 468492 | 1060 | 10 | Solar | 09_909W2 | 2022-11-02 08:47 | 2022-11-03 | 1 | 0 | 1 | 2022-11-04 | 2022-11-30 | 17 | 0 | 17 | [20 empty] | 2022-11-30 |  | 2024-01-04 | Yes | EXP | [8 empty] | 2023-06-30 | Connected |  | No
National Grid | NORTH BROOKFIELD | 459951 | 1535 | 4999 | Solar | 01_525L1 | 2022-11-02 14:28 | 2022-11-03 | 11 | 3 | 8 | [10 empty] | 2022-11-18 | 2022-12-15 | 19 | 0 | 19 | [11 empty] | 2022-11-02 16:04 |  |  | STD | [9 empty] | Study |  | No
National Grid | SPENCER | 452991 | 1562 | 10 | Solar | 01_21W1 | 2022-11-02 16:04 | 2022-11-03 | 6 | 4 | 2 | 2022-11-10 | 2022-12-14 | 23 | 0 | 23 | [20 empty] | 2022-12-19 |  | 2024-08-05 | Yes | EXP |  | 2023-06-16 | 2023-08-03 | 49 | 0 | 49 |  |  | 2023-08-29 | Connected |  | Yes
National Grid | NORTH ANDOVER | 473878 | 1845 | 22.8 | Solar | 14_56L1 | 2022-11-02 16:33 | 2022-11-03 | 1 | 0 | 1 | 2022-11-04 | 2024-02-28 | 325 | 266 | 59 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEBSTER | 458959 | 1570 | 3.8 | Solar | 01_412L2 | 2022-11-02 16:56 | 2022-11-03 | 3 | 1 | 2 | 2022-11-07 | 2022-11-30 | 16 | 0 | 16 | [20 empty] | 2022-12-08 |  | 2024-04-09 |  | EXP | [8 empty] | 2023-06-14 | Connected |  | Yes
National Grid | NANTUCKET | 472903 | 2554 | 20 | Solar | 04_101L2 | 2022-11-02 20:21 | 2022-11-03 | 5 | 4 | 1 | 2022-11-09 | 2022-12-09 | 21 | 0 | 21 | [20 empty] | 2022-12-14 |  | 2023-12-21 |  | EXP | [8 empty] | 2023-04-07 | Connected |  | No
National Grid | GARDNER | 473103 | 1440 | 14.79 | Solar | 01_602W2 | 2022-11-03 08:18 | 2022-11-04 | 171 | 72 | 99 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MARLBOROUGH | 473967 | 1752 | 15.2 | Solar | 05_310W4 | 2022-11-03 08:30 | 2022-11-04 | 2 | 0 | 2 | 2022-11-09 | 2022-12-13 | 23 | 0 | 23 | [20 empty] | 2022-12-13 |  | 2024-01-03 |  | EXP | [8 empty] | 2023-03-23 | Connected |  | No
National Grid | MILLBURY | 457862 | 1527 | 1800 | Solar | 01_304W6 | 2022-11-03 11:19 | 2022-11-04 | 10 | 2 | 8 | [10 empty] | 2022-11-18 | 2022-12-15 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Pending Withdraw |  | No
National Grid | HANSON | 463055 | 2341 | 2550 | Solar | 07_797W24 | 2022-11-03 13:36 | 2022-11-04 | 4 | 0 | 4 | [29 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | BRIDGEWATER | 473567 | 2324 | 15.925 | Solar | 07_797W1 | 2022-11-03 14:11 | 2022-11-04 | 2 | 0 | 2 | 2022-11-08 | 2022-11-30 | 15 | 0 | 15 | [20 empty] | 2022-12-08 |  | 2023-12-13 |  | EXP | [8 empty] | 2023-05-03 | Connected |  | No
National Grid | HANOVER | 468958 | 2339 | 480 | Solar | 07_95W1 | 2022-11-04 14:54 | 2022-11-07 | 7 | 0 | 7 | [10 empty] | 2022-11-17 | 2022-12-14 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Group Study |  | Yes
National Grid | BOXFORD | 475112 | 1921 | 15.2 | Solar | 14_56L3 | 2022-11-07 09:39 | 2022-11-08 | 1 | 0 | 1 | 2022-11-09 | 2022-11-30 | 14 | 0 | 14 | [20 empty] | 2022-12-01 |  | 2023-12-07 |  | EXP | [8 empty] | 2023-05-01 | Connected |  | No
National Grid | SAUGUS | 475161 | 1906 | 15.2 | Solar | 12_25W2 | 2022-11-07 10:56 | 2022-11-08 | 2 | 1 | 1 | 2022-11-09 | 2022-12-01 | 15 | 0 | 15 | [20 empty] | 2022-12-05 | 2022-11-07 11:04 | 2023-12-07 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WILLIAMSTOWN | 473079 | 1267 | 10 | Solar | 09_1003W1 | 2022-11-07 11:04 | 2022-11-08 | 3 | 0 | 3 | 2022-11-14 | 2022-12-05 | 15 | 0 | 15 | [20 empty] | 2022-12-09 |  | 2024-02-15 | Yes | EXP |  | 2023-02-02 | 2023-02-14 | 13 | 0 | 13 |  |  | 2023-06-28 | Connected |  | Yes
National Grid | NORTH QUINCY | 475207 | 2171 | 15.2 | Solar | 07_11W1 | 2022-11-07 11:35 | 2022-11-08 | 1 | 0 | 1 | 2022-11-09 | 2022-12-01 | 15 | 0 | 15 | [20 empty] | 2022-12-05 |  | 2023-12-19 |  | EXP | [8 empty] | 2023-03-03 | Connected |  | No
National Grid | WARREN | 440640 | 1083 | 1940 | Solar | 09_516L2 | 2022-11-07 16:02 | 2022-11-08 | 128 | 118 | 10 | [10 empty] | 2023-05-16 | 2023-06-12 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | BROCKTON | 421229 | 2302 | 4999.2 | Battery Add-On | 07_911W56 | 2022-11-07 21:14 | 2022-11-08 | 173 | 163 | 10 | [10 empty] | 2023-07-21 | 2023-10-17 | 60 | 40 | 20 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | SOMERSET | 475485 | 2726 | 15.08 | Solar | 05_11W82 | 2022-11-08 01:23 | 2022-11-09 | 3 | 2 | 1 | 2022-11-15 | 2022-11-23 | 7 | 0 | 7 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOMERSET | 475488 | 2726 | 15.08 | Solar | 05_11W82 | 2022-11-08 02:24 | 2022-11-09 | 3 | 2 | 1 | 2022-11-15 | 2022-11-23 | 7 | 0 | 7 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MILLBURY | 471063 | 1527 | 6 | Solar | 01_304W3 | 2022-11-08 07:59 | 2022-11-09 | 3 | 0 | 3 | 2022-11-15 | 2022-12-14 | 21 | 0 | 21 | [20 empty] | 2022-12-19 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTHBOROUGH | 471917 | 1532 | 3.8 | Solar | 05_313W4 | 2022-11-08 08:18 | 2022-11-09 | 3 | 0 | 3 | 2022-11-15 | 2022-12-14 | 21 | 0 | 21 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WILBRAHAM | 470981 | 1095 | 15.2 | Solar | 09_523L1 | 2022-11-08 08:57 | 2022-11-09 | 1 | 0 | 1 | 2022-11-10 | 2022-12-01 | 14 | 0 | 14 | [20 empty] | 2022-12-05 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EAST DOUGLAS | 475577 | 1516 | 15.2 | Solar | 05_320W2 | 2022-11-08 09:36 | 2022-11-09 | 1 | 0 | 1 | 2022-11-10 | 2022-12-04 | 16 | 0 | 16 | [20 empty] | 2022-12-05 |  | 2024-01-16 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHELMSFORD | 475619 | 1824 | 100 | Solar | 14_24L1 | 2022-11-08 13:58 | 2022-11-09 | 23 | 13 | 10 | [10 empty] | 2022-12-13 | 2023-01-18 | 25 | 0 | 25 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | FRANKLIN | 456412 | 2038 | 16.24 | Solar | 05_344W1 | 2022-11-08 14:45 | 2022-11-09 | 169 | 25 | 144 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 475993 | 1609 | 15.08 | Solar | 01_2J335 | 2022-11-09 01:42 | 2022-11-10 | 18 | 17 | 1 | 2022-12-08 | 2023-01-09 | 21 | 0 | 21 | [20 empty] | 2023-01-13 |  | 2024-02-06 |  | EXP | [8 empty] | 2023-03-20 | Connected |  | No
National Grid | WESTBOROUGH | 471366 | 1581 | 9.75 | Solar | 05_312W1 | 2022-11-09 08:35 | 2022-11-10 | 8 | 3 | 5 | 2022-11-22 | 2022-12-08 | 12 | 0 | 12 | [20 empty] | 2022-12-15 |  | 2024-01-12 |  | EXP | [8 empty] | 2023-03-31 | Connected |  | No
National Grid | SWANSEA | 443975 | 2777 | 4999 | Other | 05_11W81 | 2022-11-09 09:55 | 2022-11-10 | 50 | 40 | 10 | [10 empty] | 2023-02-01 | 2023-03-02 | 22 | 2 | 20 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WEST BRIDGEWATER | 443981 | 2379 | 4999 | Other | 07_797W19 | 2022-11-09 09:56 | 2022-11-10 | 52 | 42 | 10 | [10 empty] | 2023-02-01 | 2023-03-02 | 22 | 2 | 20 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | WEST BRIDGEWATER | 443983 | 2379 | 4999 | Other | 07_797W19 | 2022-11-09 09:57 | 2022-11-10 | 121 | 113 | 8 | [29 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | STOUGHTON | 443997 | 2072 | 4999 | Other | 07_94W41 | 2022-11-09 09:57 | 2022-11-10 | 121 | 113 | 8 | [29 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | ABINGTON | 443989 | 2351 | 4999 | Other | 07_93W42 | 2022-11-09 09:58 | 2022-11-10 | 121 | 113 | 8 | [29 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | MEDFORD | 469990 | 2155 | 20 | Solar | 12_37W4 | 2022-11-09 13:57 | 2022-11-10 | 27 | 26 | 1 | 2022-12-20 | 2023-01-20 | 21 | 0 | 21 | [20 empty] | 2023-01-20 |  | 2024-04-20 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SOUTH HAMILTON | 476277 | 1982 | 20 | Solar | 12_51T2 | 2022-11-09 14:52 | 2022-11-10 | 27 | 26 | 1 | 2022-12-20 | 2023-01-20 | 21 | 0 | 21 | [20 empty] | 2023-01-20 | 2022-11-10 10:02 | 2024-04-20 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | MONSON | 475071 | 1057 | 8.7 | Solar | 09_514L1 | 2022-11-10 10:02 | 2022-11-14 | 4 | 2 | 2 | 2022-11-18 | 2023-01-03 | 30 | 6 | 24 | [20 empty] | 2023-01-06 |  | 2024-04-17 | Yes | EXP |  | 2023-03-17 | 2023-04-17 | 32 | 0 | 32 |  |  | 2023-07-18 | Connected |  | No
National Grid | DOUGLAS | 470299 | 1516 | 8.12 | Solar | 05_320W2 | 2022-11-10 11:12 | 2022-11-14 | 1 | 0 | 1 | 2022-11-15 | 2022-12-07 | 16 | 0 | 16 | [20 empty] | 2022-12-08 |  | 2023-12-13 |  | EXP | [8 empty] | 2023-06-14 | Connected |  | No
National Grid | NORTHAMPTON | 460987 | 1062 | 5.8 | Solar | 09_909W2 | 2022-11-10 11:18 | 2022-11-14 | 4 | 0 | 4 | 2022-11-18 | 2022-12-05 | 11 | 0 | 11 | [20 empty] | 2022-12-09 |  | 2023-12-14 |  | EXP | [8 empty] | 2023-06-09 | Connected |  | No
National Grid | STOUGHTON | 467208 | 2072 | 5 | Solar | 07_913W67 | 2022-11-10 12:18 | 2022-11-14 | 1 | 0 | 1 | 2022-11-15 | 2022-12-12 | 20 | 1 | 19 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FALL RIVER | 476578 | 2720 | 180 | Solar | 05_28W42 | 2022-11-10 12:55 | 2022-11-14 | 28 | 18 | 10 | [10 empty] | 2022-12-23 | 2023-02-08 | 32 | 7 | 25 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | MELROSE | 475633 | 2176 | 50 | Solar | 12_25W4 | 2022-11-10 16:25 | 2022-11-14 | 8 | 0 | 8 | 2022-11-25 | 2023-01-27 | 44 | 24 | 20 | 2023-02-02 | 2023-03-22 | 32 | 0 | 32 | [5 empty] | 2023-02-02 | 2023-03-22 | 32 | 0 | 32 | [5 empty] | 2023-03-22 |  | 2024-11-29 |  | EXP |  | 2023-10-21 | 2023-12-05 | 46 | 0 | 46 |  |  |  | Completion Documents |  | Yes
National Grid | MELROSE | 475615 | 2176 | 67.3 | Solar | 12_16W6 | 2022-11-10 17:01 | 2022-11-14 | 8 | 0 | 8 | 2022-11-25 | 2022-12-21 | 19 | 0 | 19 | [20 empty] | 2023-01-06 | 2022-11-11 07:11 | 2024-08-21 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | NORTHBOROUGH | 472757 | 1532 | 11.31 | Solar | 05_314W4 | 2022-11-11 07:11 | 2022-11-14 | 6 | 2 | 4 | 2022-11-21 | 2022-12-07 | 12 | 0 | 12 | [20 empty] | 2022-12-09 | 2022-11-11 10:56 | 2024-04-24 | Yes | EXP |  | 2023-02-07 | 2023-04-25 | 78 | 0 | 78 |  |  | 2023-12-01 | Connected |  | No
National Grid | BROCKTON | 448503 | 2302 | 6 | Solar | 07_911W77 | 2022-11-11 10:56 | 2022-11-14 | 1 | 0 | 1 | 2022-11-15 | 2022-12-14 | 21 | 0 | 21 | [20 empty] | 2022-12-15 |  | 2024-02-09 | Yes | EXP |  | 2023-03-22 | 2023-04-03 | 13 | 0 | 13 |  |  | 2023-05-18 | Connected |  | No
National Grid | TYNGSBOROUGH | 475793 | 1879 | 3.8 | Solar | 14_211L2 | 2022-11-11 12:21 | 2022-11-14 | 1 | 0 | 1 | 2022-11-15 | 2022-12-14 | 21 | 0 | 21 | [20 empty] | 2022-12-14 | 2022-11-11 13:46 | 2023-12-19 |  | EXP | [8 empty] | 2023-04-13 | Connected |  | No
National Grid | WORCESTER | 469690 | 1604 | 9.84 | Solar | 01_27W5 | 2022-11-11 13:46 | 2022-11-14 | 1 | 0 | 1 | 2022-11-15 | 2022-12-14 | 21 | 0 | 21 | [20 empty] | 2022-12-19 | 2022-11-11 14:33 | 2024-09-13 | Yes | EXP |  | 2023-07-20 | 2023-09-14 | 57 | 0 | 57 |  |  |  | Withdrawn |  | Yes
National Grid | MALDEN | 476941 | 2148 | 9.074 | Solar | 12_37W7 | 2022-11-11 14:33 | 2022-11-14 | 1 | 0 | 1 | 2022-11-15 | 2023-01-13 | 41 | 25 | 16 | [20 empty] | 2023-01-13 | 2022-11-11 16:08 | 2024-01-23 | Yes | EXP |  | 2023-07-01 | 2023-11-03 | 126 | 0 | 126 |  |  | 2023-11-14 | Connected |  | No
National Grid | BILLERICA | 470694 | 1821 | 3.8 | Solar | 14_92L2 | 2022-11-11 16:08 | 2022-11-14 | 4 | 0 | 4 | 2022-11-18 | 2022-12-07 | 13 | 0 | 13 | [20 empty] | 2022-12-15 | 2022-11-14 14:46 | 2024-04-25 | Yes | EXP |  | 2023-04-05 | 2023-04-25 | 21 | 0 | 21 |  |  | 2023-05-02 | Connected |  | No
National Grid | MARLBOROUGH | 473323 | 1752 | 120 | Solar | 05_311W6 | 2022-11-14 14:46 | 2022-11-15 | 20 | 11 | 9 | 2022-12-14 | 2023-01-18 | 23 | 0 | 23 | [20 empty] | 2023-04-25 | 2022-11-14 20:41 | 2024-09-29 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | ROCKPORT | 471710 | 1966 | 5.22 | Solar | 12_40L1 | 2022-11-14 20:41 | 2022-11-15 | 6 | 3 | 3 | 2022-11-23 | 2022-12-20 | 19 | 0 | 19 | [20 empty] | 2022-12-29 |  | 2024-11-15 | Yes | EXP |  | 2023-05-17 | 2023-11-06 | 174 | 0 | 174 |  |  | 2023-12-06 | Connected |  | Yes
National Grid | SOUTH EASTON | 443464 | 2375 | 999 | Solar | 07_92W44 | 2022-11-15 09:45 | 2022-11-16 | 12 | 2 | 10 | [10 empty] | 2022-12-02 | 2022-12-27 | 17 | 0 | 17 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | MENDON | 477539 | 1756 | 15.2 | Solar | 05_332W1 | 2022-11-15 10:35 | 2022-11-16 | 2 | 0 | 2 | 2022-11-18 | 2022-12-14 | 18 | 0 | 18 | [20 empty] | 2022-12-15 |  | 2024-01-04 |  | EXP | [8 empty] | 2023-03-22 | Connected |  | No
National Grid | NORTH GRAFTON | 469374 | 1536 | 17.69 | Solar | 01_328W3 | 2022-11-15 12:30 | 2022-11-16 | 44 | 34 | 10 | 2023-01-24 | 2023-02-21 | 20 | 0 | 20 | [20 empty] | 2023-02-23 |  | 2024-03-19 |  | EXP | [8 empty] | 2023-08-01 | Connected |  | Yes
National Grid | NORWELL | 477628 | 2061 | 15.2 | Solar | 07_96W44 | 2022-11-15 12:36 | 2022-11-16 | 2 | 0 | 2 | 2022-11-18 | 2022-12-14 | 18 | 0 | 18 | [20 empty] | 2022-12-15 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | DRACUT | 457130 | 1826 | 4300 | Other | 14_75L6 | 2022-11-15 13:06 | 2022-11-16 | 57 | 47 | 10 | [10 empty] | 2023-02-09 | 2023-03-29 | 34 | 14 | 20 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | AVON | 467612 | 2322 | 4500 | Other | 07_75W5 | 2022-11-15 13:09 | 2022-11-16 | 46 | 36 | 10 | [10 empty] | 2023-01-24 | 2023-02-21 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | ESSEX | 477583 | 1929 | 9.57 | Solar | 12_51T2 | 2022-11-15 13:30 | 2022-11-16 | 2 | 0 | 2 | 2022-11-18 | 2022-12-15 | 19 | 0 | 19 | [20 empty] | 2022-12-19 |  | 2024-01-05 |  | EXP | [8 empty] | 2023-03-30 | Connected |  | No
National Grid | REVERE | 464788 | 2151 | 8.99 | Solar | 12_7W3 | 2022-11-15 13:51 | 2022-11-16 | 3 | 0 | 3 | 2022-11-21 | 2022-12-16 | 19 | 0 | 19 | [20 empty] | 2022-12-25 |  | 2023-12-30 |  | EXP | [8 empty] | 2023-05-30 | Connected |  | No
National Grid | WEBSTER | 455151 | 1570 | 100 | Solar | 01_412L6 | 2022-11-15 14:33 | 2022-11-16 | 237 | 229 | 8 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | AMHERST | 477733 | 1002 | 20.08 | Solar | 09_704W1 | 2022-11-15 14:38 | 2022-11-16 | 4 | 2 | 2 | 2022-11-22 | 2022-12-27 | 24 | 12 | 12 | [20 empty] | 2022-12-27 |  | 2024-01-09 |  | EXP | [8 empty] | 2023-11-17 | Connected |  | No
National Grid | DUNSTABLE | 477387 | 1827 | 7.6 | Solar | 01_210L1 | 2022-11-15 15:54 | 2022-11-16 | 3 | 0 | 3 | 2022-11-21 | 2022-12-08 | 13 | 0 | 13 | [20 empty] | 2022-12-15 | 2022-11-16 10:36 | 2024-02-29 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ATTLEBORO | 466376 | 2703 | 5.76 | Solar | 05_8L3 | 2022-11-16 10:36 | 2022-11-17 | 3 | 0 | 3 | 2022-11-22 | 2022-12-19 | 19 | 0 | 19 | [20 empty] | 2022-12-29 | 2022-11-16 10:45 | 2024-02-29 | Yes | EXP |  | 2023-02-25 | 2023-02-27 | 3 | 0 | 3 |  |  | 2023-05-23 | Connected |  | No
National Grid | BROCKTON | 474867 | 2302 | 3.8 | Solar | 07_911W56 | 2022-11-16 10:45 | 2022-11-17 | 2 | 0 | 2 | 2022-11-21 | 2022-12-19 | 20 | 0 | 20 | [20 empty] | 2022-12-25 | 2022-11-16 11:33 | 2024-05-10 | Yes | EXP | [8 empty] | 2023-06-14 | Connected |  | No
National Grid | REVERE | 471406 | 2151 | 14.976 | Solar | 12_16W8 | 2022-11-16 11:33 | 2022-11-17 | 8 | 7 | 1 | 2022-11-29 | 2023-01-18 | 35 | 11 | 24 | [20 empty] | 2023-01-20 |  | 2024-07-23 | Yes | EXP | [9 empty] | Completion Documents |  | No
National Grid | EVERETT | 478025 | 2149 | 15.2 | Solar | 12_16W7 | 2022-11-16 12:52 | 2022-11-17 | 1 | 0 | 1 | 2022-11-18 | 2022-12-15 | 19 | 0 | 19 | [20 empty] | 2022-12-15 | 2022-11-16 14:14 | 2023-12-28 |  | EXP | [8 empty] | 2023-05-03 | Connected |  | No
National Grid | WINCHENDON | 474354 | 1475 | 3.8 | Solar | 01_612W1 | 2022-11-16 14:14 | 2022-11-17 | 23 | 21 | 2 | 2022-12-21 | 2023-01-23 | 21 | 0 | 21 | [20 empty] | 2023-01-26 |  | 2024-03-08 | Yes | EXP |  | 2023-03-02 | 2023-03-09 | 8 | 0 | 8 |  |  | 2023-04-04 | Connected |  | No
National Grid | RANDOLPH | 467533 | 2368 | 7.6 | Solar | 07_97W2 | 2022-11-16 14:49 | 2022-11-17 | 2 | 0 | 2 | 2022-11-21 | 2022-12-07 | 12 | 0 | 12 | [20 empty] | 2022-12-12 | 2022-11-16 17:39 | 2024-02-15 |  | EXP | [8 empty] | 2023-04-04 | Connected |  | No
National Grid | WESTPORT | 454988 | 2790 | 6.96 | Solar | 05_115W52 | 2022-11-16 17:39 | 2022-11-17 | 29 | 25 | 4 | 2023-01-04 | 2023-02-01 | 20 | 0 | 20 | [20 empty] | 2023-02-06 |  | 2024-06-25 |  | EXP |  | 2023-03-29 | 2023-05-03 | 36 | 0 | 36 |  |  | 2023-07-20 | Connected |  | No
National Grid | DOUGLAS | 473685 | 1516 | 11.02 | Solar | 01_412L1 | 2022-11-17 11:48 | 2022-11-18 | 22 | 20 | 2 | 2022-12-21 | 2023-01-20 | 20 | 0 | 20 | [20 empty] | 2023-01-23 |  | 2024-01-26 |  | EXP | [8 empty] | 2023-06-02 | Connected |  | No
National Grid | LAWRENCE | 470911 | 1841 | 10 | Solar | 14_43L4 | 2022-11-17 13:13 | 2022-11-18 | 162 | 50 | 112 | [26 empty] | 2022-11-17 14:11 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HALIFAX | 473559 | 2338 | 10 | Solar | 07_912W75 | 2022-11-17 14:11 | 2022-11-18 | 3 | 0 | 3 | 2022-11-23 | 2022-12-14 | 15 | 0 | 15 | [20 empty] | 2022-12-19 |  | 2024-06-27 | Yes | EXP | [8 empty] | 2023-07-01 | Connected |  | No
National Grid | REHOBOTH | 478091 | 2769 | 25 | Solar | 05_3J1 | 2022-11-17 14:25 | 2022-11-18 | 16 | 13 | 3 | 2022-12-13 | 2023-01-12 | 21 | 0 | 21 | [20 empty] | 2023-01-12 |  | 2024-01-20 |  | EXP | [8 empty] | 2023-05-09 | Connected |  | No
National Grid | STOUGHTON | 477659 | 2072 | 16.53 | Solar | 07_913W43 | 2022-11-17 16:33 | 2022-11-18 | 3 | 0 | 3 | 2022-11-23 | 2022-12-20 | 19 | 0 | 19 | [20 empty] | 2022-12-22 |  | 2024-04-25 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | BOXFORD | 462041 | 1921 | 14.79 | Solar | 14_33L1 | 2022-11-17 16:36 | 2022-11-18 | 4 | 1 | 3 | 2022-11-25 | 2022-12-13 | 13 | 0 | 13 | [20 empty] | 2022-12-15 |  | 2024-01-24 |  | EXP | [8 empty] | 2023-03-13 | Connected |  | No
National Grid | LEOMINSTER | 472241 | 1453 | 6.38 | Solar | 01_219W5 | 2022-11-17 18:42 | 2022-11-18 | 47 | 46 | 1 | 2023-01-31 | 2023-02-24 | 18 | 0 | 18 | [20 empty] | 2023-03-01 | 2022-11-18 07:33 | 2024-05-27 |  | EXP | [8 empty] | 2023-09-05 | Connected |  | No
National Grid | PEPPERELL | 473320 | 1463 | 3.48 | Solar | 01_226L2 | 2022-11-18 07:33 | 2022-11-21 | 2 | 0 | 2 | 2022-11-23 | 2022-12-13 | 14 | 0 | 14 | [20 empty] | 2022-12-15 |  | 2024-04-19 | Yes | EXP |  | 2023-04-12 | 2023-04-19 | 8 | 0 | 8 |  |  | 2023-06-23 | Connected |  | No
National Grid | WINCHENDON | 467785 | 1475 | 8.7 | Solar | 01_607W5 | 2022-11-18 09:24 | 2022-11-21 | 17 | 15 | 2 | 2022-12-14 | 2023-01-18 | 23 | 0 | 23 | [20 empty] | 2023-01-19 | 2022-11-18 10:27 | 2024-04-19 |  | EXP | [8 empty] | 2023-06-01 | Connected |  | No
National Grid | MANCHESTER | 456448 | 1944 | 15.2 | Solar | 12_51T1 | 2022-11-18 10:27 | 2022-11-21 | 2 | 0 | 2 | 2022-11-23 | 2023-01-03 | 28 | 14 | 14 | [20 empty] | 2023-01-04 |  | 2024-04-07 | Yes | EXP |  | 2023-04-05 | 2023-06-12 | 69 | 0 | 69 |  |  |  | Completion Documents |  | No
National Grid | SWANSEA | 471482 | 2777 | 7.6 | Solar | 05_11W84 | 2022-11-18 11:19 | 2022-11-21 | 6 | 4 | 2 | 2022-11-29 |  | 343 | 51 | 292 | [24 empty] | EXP | [9 empty] | Screening |  | No
National Grid | FRANKLIN | 478730 | 2038 | 15.2 | Solar | 05_344W5 | 2022-11-18 12:20 | 2022-11-21 | 10 | 8 | 2 | 2022-12-06 | 2023-01-03 | 19 | 0 | 19 | [20 empty] | 2023-01-04 | 2022-11-18 13:16 | 2024-01-17 |  | EXP | [8 empty] | 2023-04-24 | Connected |  | No
National Grid | WESTMINSTER | 472538 | 1473 | 7.6 | Solar | 01_609W1 | 2022-11-18 13:16 | 2022-11-21 | 3 | 0 | 3 | 2022-11-25 | 2022-12-21 | 19 | 0 | 19 | [20 empty] | 2022-12-29 |  | 2024-03-02 | Yes | EXP |  | 2023-02-23 | 2023-03-02 | 8 | 0 | 8 |  |  | 2023-06-24 | Connected |  | No
National Grid | WESTMINSTER | 477503 | 1473 | 7.6 | Solar | 01_610W3 | 2022-11-18 13:31 | 2022-11-21 | 2 | 0 | 2 | 2022-11-23 | 2022-12-19 | 18 | 0 | 18 | [20 empty] | 2022-12-20 |  | 2023-12-31 |  | EXP | [8 empty] | 2023-09-22 | Connected |  | No
National Grid | QUINCY | 477496 | 2169 | 2.792 | Solar | 07_1W2 | 2022-11-18 14:26 | 2022-11-21 | 3 | 0 | 3 | 2022-11-25 | 2023-11-13 | 241 | 222 | 19 | [21 empty] | 2022-11-18 15:13 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RANDOLPH | 477574 | 2368 | 10 | Solar | 07_5W2 | 2022-11-18 15:13 | 2022-11-21 | 2 | 0 | 2 | 2022-11-23 | 2022-12-20 | 19 | 0 | 19 | [20 empty] | 2022-12-29 |  | 2024-12-19 | Yes | EXP |  | 2023-10-26 | 2023-11-29 | 35 | 0 | 35 |  |  | 2024-01-05 | Connected |  | No
National Grid | BERLIN | 478862 | 1503 | 16.82 | Solar | 05_318W3 | 2022-11-18 16:11 | 2022-11-21 | 3 | 0 | 3 | 2022-11-25 | 2022-12-22 | 20 | 0 | 20 | [20 empty] | 2023-01-04 |  | 2024-05-12 |  | EXP | [8 empty] | 2023-08-10 | Connected |  | No
National Grid | FOXBOROUGH | 475897 | 2035 | 240 | Solar | 05_2468W1 | 2022-11-18 16:16 | 2022-11-21 | 38 | 28 | 10 | [10 empty] | 2023-01-18 | 2023-02-09 | 17 | 0 | 17 | [11 empty] | 2022-11-18 20:17 |  |  | STD | [9 empty] | Group Study |  | No
National Grid | LAWRENCE | 459549 | 1841 | 6 | Solar | 14_8L2 | 2022-11-18 20:17 | 2022-11-21 | 5 | 0 | 5 | 2022-11-28 | 2022-12-16 | 15 | 0 | 15 | [20 empty] | 2022-12-17 |  | 2024-05-16 | Yes | EXP |  | 2023-09-12 | 2023-10-04 | 23 | 0 | 23 |  |  | 2023-10-10 | Connected |  | No
National Grid | QUINCY | 478161 | 2169 | 186 | Solar | 07_3W1 | 2022-11-19 19:48 | 2022-11-21 | 18 | 11 | 7 | 2022-12-15 |  | 99 | 78 | 21 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BRIDGEWATER | 479062 | 2324 | 15.2 | Solar | 07_912W55 | 2022-11-21 10:07 | 2022-11-22 | 4 | 2 | 2 | 2022-11-29 | 2023-01-04 | 25 | 0 | 25 | [20 empty] | 2023-01-04 | 2022-11-21 10:55 | 2024-01-26 |  | EXP | [8 empty] | 2023-05-04 | Connected |  | No
National Grid | EASTON | 471914 | 2375 | 10 | Solar | 07_92W54 | 2022-11-21 10:55 | 2022-11-22 | 8 | 6 | 2 | 2022-12-02 | 2022-12-28 | 18 | 0 | 18 | [20 empty] | 2023-01-09 |  | 2024-04-18 | Yes | EXP |  | 2023-03-29 | 2023-03-28 | 0 | 0 | 0 |  |  | 2023-08-19 | Connected |  | Yes
National Grid | MARLBOROUGH | 479117 | 1752 | 7.6 | Solar | 05_311W2 | 2022-11-21 11:41 | 2022-11-22 | 1 | 0 | 1 | 2022-11-23 | 2023-02-14 | 56 | 32 | 24 | [20 empty] | 2023-02-15 |  | 2024-02-15 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SAUGUS | 471801 | 1906 | 3.8 | Solar | 12_23W2 | 2022-11-21 12:14 | 2022-11-22 | 4 | 0 | 4 | 2022-11-28 | 2023-01-04 | 26 | 2 | 24 | [20 empty] | 2023-01-05 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOUTH EASTON | 479156 | 2375 | 7.6 | Solar | 07_92W79 | 2022-11-21 12:39 | 2022-11-22 | 4 | 0 | 4 | 2022-11-29 | 2022-12-28 | 21 | 0 | 21 | [20 empty] | 2023-01-09 |  | 2024-01-20 |  | EXP | [8 empty] | 2023-06-22 | Connected |  | No
National Grid | AMESBURY | 478526 | 1913 | 22.8 | Solar | 14_275L4 | 2022-11-21 15:09 | 2022-11-22 | 4 | 0 | 4 | 2022-11-28 | 2023-03-08 | 69 | 25 | 44 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | LEICESTER | 479173 | 1524 | 15.2 | Solar | 01_21W2 | 2022-11-21 15:43 | 2022-11-22 | 4 | 0 | 4 | 2022-11-28 | 2023-01-03 | 25 | 5 | 20 | [20 empty] | 2023-01-04 |  | 2024-05-17 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ANDOVER | 479312 | 1810 | 15.2 | Solar | 14_3J41 | 2022-11-21 17:19 | 2022-11-22 | 2 | 0 | 2 | 2022-11-25 | 2022-12-22 | 20 | 0 | 20 | [20 empty] | 2022-12-27 |  | 2024-07-31 |  | EXP | [8 empty] | 2023-08-02 | Connected |  | No
National Grid | EASTON | 479458 | 2334 | 7.6 | Solar | 07_92W78 | 2022-11-22 09:53 | 2022-11-23 | 4 | 0 | 4 | 2022-11-30 | 2023-01-04 | 24 | 0 | 24 | [20 empty] | 2023-01-11 |  | 2024-01-16 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTH ANDOVER | 472543 | 1845 | 15.2 | Solar | 14_71L3 | 2022-11-22 10:18 | 2022-11-23 | 3 | 0 | 3 | 2022-11-29 | 2022-12-28 | 21 | 0 | 21 | [20 empty] | 2023-01-03 |  | 2024-01-12 |  | EXP | [8 empty] | 2023-03-30 | Connected |  | No
National Grid | NORTH EASTON | 479467 | 2356 | 17.28 | Solar | 07_92W78 | 2022-11-22 10:20 | 2022-11-23 | 50 | 46 | 4 | 2023-02-07 | 2023-02-27 | 15 | 0 | 15 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SHIRLEY | 477515 | 1464 | 15.2 | Solar | 01_227W1 | 2022-11-22 10:59 | 2022-11-23 | 4 | 0 | 4 | 2022-11-30 | 2022-12-28 | 20 | 0 | 20 | [20 empty] | 2022-12-28 |  | 2024-04-20 |  | EXP | [8 empty] | 2023-08-30 | Connected |  | No
National Grid | NORTH ANDOVER | 479560 | 1845 | 15.2 | Solar | 14_55L1 | 2022-11-22 12:36 | 2022-11-23 | 4 | 0 | 4 | 2022-11-30 | 2023-01-04 | 24 | 0 | 24 | [20 empty] | 2023-01-10 |  | 2024-01-12 |  | EXP | [8 empty] | 2023-06-16 | Connected |  | No
National Grid | HALIFAX | 475256 | 2338 | 3.8 | Solar | 07_912W75 | 2022-11-22 13:27 | 2022-11-23 | 3 | 0 | 3 | 2022-11-29 | 2022-12-28 | 21 | 0 | 21 | [20 empty] | 2023-01-03 | 2022-11-23 05:13 | 2024-05-21 |  | EXP |  | 2023-04-26 | 2023-05-19 | 24 | 0 | 24 |  |  | 2023-06-13 | Connected |  | No
National Grid | SOUTHBRIDGE | 471147 | 1550 | 10 | Solar | 01_413L2 | 2022-11-23 05:13 | 2022-11-25 | 3 | 0 | 3 | 2022-11-30 | 2022-12-28 | 20 | 0 | 20 | [20 empty] | 2023-01-03 |  | 2024-08-29 | Yes | EXP | [8 empty] | 2023-09-02 | Connected |  | No
National Grid | BOXFORD | 479868 | 1921 | 22.8 | Solar | 14_33L1 | 2022-11-23 09:35 | 2022-11-25 | 3 | 0 | 3 | 2022-11-30 | 2023-01-04 | 24 | 0 | 24 | [20 empty] | 2023-06-26 | 2022-11-23 09:56 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTMINSTER | 473722 | 1473 | 8.99 | Solar | 01_609W2 | 2022-11-23 09:56 | 2022-11-25 | 3 | 1 | 2 | 2022-11-30 | 2022-12-28 | 20 | 0 | 20 | [20 empty] | 2023-01-03 |  | 2024-06-08 | Yes | EXP |  | 2023-04-27 | 2023-06-08 | 43 | 0 | 43 |  |  | 2023-06-16 | Connected |  | Yes
National Grid | PEPPERELL | 471136 | 1463 | 15.2 | Solar | 01_226L1 | 2022-11-23 10:13 | 2022-11-25 | 3 | 0 | 3 | 2022-11-30 | 2022-12-28 | 20 | 0 | 20 | [20 empty] | 2022-12-28 |  | 2024-01-10 |  | EXP | [8 empty] | 2023-04-26 | Connected |  | No
National Grid | SOUTHBRIDGE | 457748 | 1550 | 14470 | Other | 01_413L3 | 2022-11-23 10:55 | 2022-11-25 | 20 | 11 | 9 | [10 empty] | 2022-12-22 | 2023-01-23 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | ATTLEBORO | 480136 | 2703 | 15.2 | Solar | 05_8L1 | 2022-11-24 09:23 | 2022-11-25 | 8 | 5 | 3 | 2022-12-07 | 2023-01-06 | 21 | 0 | 21 | [20 empty] | 2023-01-09 |  | 2024-01-14 |  | EXP | [8 empty] | 2023-03-20 | Connected |  | No
National Grid | WESTMINSTER | 468590 | 1472 | 16.24 | Solar | 01_610W3 | 2022-11-26 18:55 | 2022-11-28 | 4 | 2 | 2 | 2022-12-02 | 2022-12-22 | 15 | 0 | 15 | [20 empty] | 2022-12-27 |  | 2024-01-31 |  | EXP | [8 empty] | 2023-05-11 | Connected |  | No
National Grid | MONSON | 480347 | 1057 | 7.6 | Battery Add-On | 09_514L1 | 2022-11-28 04:31 | 2022-11-29 | 9 | 8 | 1 | 2022-12-09 | 2023-01-13 | 24 | 0 | 24 | [20 empty] | 2023-01-13 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | ATHOL | 479424 | 1331 | 25 | Solar | 09_702W2 | 2022-11-28 09:56 | 2022-11-29 | 5 | 4 | 1 | 2022-12-06 | 2023-03-23 | 73 | 53 | 20 | [20 empty] | 2023-03-31 |  | 2024-04-06 |  | EXP | [8 empty] | 2023-11-06 | Connected |  | No
National Grid | NORTH BROOKFIELD | 480402 | 1535 | 7.6 | Solar | 09_604W3 | 2022-11-28 10:35 | 2022-11-29 | 6 | 5 | 1 | 2022-12-06 | 2023-02-28 | 58 | 38 | 20 | [20 empty] | 2023-03-01 | 2022-11-28 11:16 | 2024-03-01 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 472498 | 2302 | 7.6 | Solar | 07_911W56 | 2022-11-28 11:16 | 2022-11-29 | 10 | 6 | 4 | 2022-12-12 | 2023-01-12 | 22 | 0 | 22 | [20 empty] | 2023-01-13 | 2022-11-28 12:08 | 2024-11-29 | Yes | EXP |  | 2023-08-30 |  | 230 | 3 | 227 |  |  |  | Construction |  | Yes
National Grid | BROCKTON | 473250 | 2302 | 10 | Solar | 07_911W56 | 2022-11-28 12:08 | 2022-11-29 | 4 | 0 | 4 | 2022-12-05 | 2022-12-28 | 17 | 0 | 17 | [20 empty] | 2023-01-03 |  | 2024-11-29 | Yes | EXP | [9 empty] | Construction |  | No
National Grid | BLACKSTONE | 480519 | 1504 | 17.6 | Solar | 05_108W60 | 2022-11-28 12:28 | 2022-11-29 | 2 | 1 | 1 | 2022-11-30 | 2023-01-04 | 24 | 0 | 24 | [20 empty] | 2023-01-05 |  | 2024-02-10 |  | EXP | [8 empty] | 2023-10-31 | Connected |  | No
National Grid | BEVERLY | 480578 | 1915 | 24 | Solar | 12_51T1 | 2022-11-28 12:39 | 2022-11-29 | 1 | 0 | 1 | 2022-11-30 | 2023-01-04 | 24 | 0 | 24 | [20 empty] | 2023-01-05 |  | 2024-01-19 |  | EXP | [8 empty] | 2023-01-20 | Connected |  | No
National Grid | WORCESTER | 467875 | 1604 | 6 | Solar | 01_27W1 | 2022-11-28 13:29 | 2022-11-29 | 239 | 65 | 174 | [26 empty] | 2022-11-28 13:35 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ATHOL | 480601 | 1331 | 18.56 | Solar | 09_702W2 | 2022-11-28 13:35 | 2022-11-29 | 5 | 4 | 1 | 2022-12-06 | 2023-02-09 | 45 | 25 | 20 | [20 empty] | 2023-02-10 | 2022-11-28 14:46 | 2024-10-19 | Yes | EXP |  | 2023-05-02 | 2023-10-19 | 171 | 0 | 171 |  |  | 2023-10-24 | Connected |  | No
National Grid | DUNSTABLE | 480125 | 1827 | 16.9 | Solar | 01_210L1 | 2022-11-28 14:46 | 2022-11-29 | 2 | 0 | 2 | 2022-12-01 | 2022-12-28 | 19 | 0 | 19 | [20 empty] | 2023-01-03 | 2022-11-28 15:39 | 2024-03-06 | Yes | EXP |  | 2023-02-24 | 2023-03-06 | 11 | 0 | 11 |  |  |  | Withdrawn |  | Yes
National Grid | WEYMOUTH | 456387 | 2190 | 7.6 | Solar | 07_8W1 | 2022-11-28 15:39 | 2022-11-29 | 3 | 2 | 1 | 2022-12-02 | 2022-12-27 | 17 | 0 | 17 | [20 empty] | 2023-01-05 |  | 2024-06-10 | Yes | EXP |  | 2023-05-12 | 2023-06-09 | 29 | 0 | 29 |  |  | 2023-06-23 | Connected |  | No
National Grid | AUBURN | 480883 | 1501 | 20 | Solar | 01_26W1 | 2022-11-29 09:02 | 2022-11-30 | 2 | 0 | 2 | 2022-12-02 | 2022-12-22 | 15 | 0 | 15 | [20 empty] | 2022-12-27 | 2022-11-29 10:14 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTFORD | 461886 | 1886 | 7.6 | Solar | 14_57L2 | 2022-11-29 10:14 | 2022-11-30 | 2 | 0 | 2 | 2022-12-02 | 2022-12-27 | 17 | 0 | 17 | [20 empty] | 2023-01-06 |  | 2024-06-15 | Yes | EXP |  | 2023-06-09 | 2023-06-12 | 4 | 0 | 4 |  |  |  | Withdrawn |  | Yes
National Grid | BROCKTON | 473683 | 2301 | 12 | Solar | 07_94W40 | 2022-11-29 10:21 | 2022-11-30 | 23 | 18 | 5 | 2023-01-03 | 2023-02-01 | 21 | 0 | 21 | [20 empty] | 2023-02-02 | 2022-11-29 12:24 | 2024-02-23 |  | EXP | [8 empty] | 2023-09-01 | Connected |  | No
National Grid | NORTON | 481017 | 2766 | 15.2 | Solar | 07_92W79 | 2022-11-29 12:24 | 2022-11-30 | 10 | 8 | 2 | 2022-12-13 | 2023-01-24 | 28 | 5 | 23 | [20 empty] | 2023-01-31 | 2022-11-29 13:02 | 2024-06-15 | Yes | EXP |  | 2023-06-15 | 2023-06-16 | 2 | 0 | 2 |  |  | 2023-07-03 | Connected |  | No
National Grid | QUINCY | 469559 | 2169 | 22.8 | Solar | 07_1W10 | 2022-11-29 13:02 | 2022-11-30 | 2 | 0 | 2 | 2022-12-02 | 2023-01-17 | 31 | 16 | 15 | [20 empty] | 2023-01-17 |  | 2024-01-25 | Yes | EXP |  | 2023-03-09 | 2023-05-26 | 79 | 0 | 79 |  |  | 2023-06-13 | Connected |  | No
National Grid | MENDON | 481074 | 1756 | 20 | Solar | 05_332W1 | 2022-11-29 13:17 | 2022-11-30 | 2 | 0 | 2 | 2022-12-02 | 2022-12-22 | 15 | 0 | 15 | [20 empty] | 2022-12-27 | 2022-11-29 13:18 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WILLIAMSTOWN | 481070 | 1267 | 11.4 | Solar | 09_1003W2 | 2022-11-29 13:18 | 2022-11-30 | 3 | 1 | 2 | 2022-12-05 | 2023-01-04 | 21 | 0 | 21 | [20 empty] | 2023-01-11 |  | 2024-02-15 | Yes | EXP |  | 2023-02-02 | 2023-02-14 | 13 | 0 | 13 |  |  | 2023-03-01 | Connected |  | No
National Grid | CHELMSFORD | 408495 | 1824 | 16 | Solar | 14_24L2 | 2022-11-29 13:57 | 2022-11-30 | 220 | 204 | 16 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | SOUTHBRIDGE | 471227 | 1550 | 7.6 | Solar | 01_413L2 | 2022-11-29 14:14 | 2022-11-30 | 2 | 0 | 2 | 2022-12-02 |  | 155 | 21 | 134 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FALL RIVER | 480438 | 2724 | 3.8 | Solar | 05_115W42 | 2022-11-29 14:18 | 2022-11-30 | 5 | 0 | 5 | 2022-12-07 | 2023-01-04 | 19 | 0 | 19 | [20 empty] | 2023-01-05 |  | 2024-05-01 |  | EXP | [8 empty] | 2023-05-17 | Connected |  | No
National Grid | BROCKTON | 467668 | 2301 | 6 | Solar | 07_911W13 | 2022-11-29 14:30 | 2022-11-30 | 5 | 0 | 5 | 2022-12-07 | 2023-01-06 | 21 | 0 | 21 | [20 empty] | 2023-01-09 |  | 2024-08-04 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTFORD | 460840 | 1886 | 17.6 | Solar | 14_57L3 | 2022-11-29 15:52 | 2022-11-30 | 2 | 0 | 2 | 2022-12-02 | 2022-12-27 | 17 | 0 | 17 | [20 empty] | 2022-12-28 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | DOUGLAS | 475763 | 1516 | 6.96 | Solar | 05_321W2 | 2022-11-29 16:17 | 2022-11-30 | 5 | 0 | 5 | 2022-12-07 | 2023-01-06 | 21 | 0 | 21 | [20 empty] | 2023-01-09 |  | 2024-02-23 |  | EXP | [8 empty] | 2023-08-31 | Connected |  | Yes
National Grid | MILLVILLE | 481212 | 1529 | 16 | Solar | 05_321W9 | 2022-11-29 16:29 | 2022-11-30 | 4 | 2 | 2 | 2022-12-06 | 2023-01-03 | 19 | 0 | 19 | [20 empty] | 2023-01-04 |  | 2024-04-23 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | UPTON | 481179 | 1568 | 16 | Solar | 05_335W3 | 2022-11-30 09:00 | 2022-12-01 | 7 | 6 | 1 | 2022-12-09 | 2023-01-13 | 24 | 0 | 24 | [20 empty] | 2023-01-13 |  | 2024-03-21 |  | EXP | [8 empty] | 2023-04-07 | Connected |  | No
National Grid | WEYMOUTH | 481330 | 2191 | 15.2 | Solar | 07_6W2 | 2022-11-30 09:36 | 2022-12-01 | 3 | 2 | 1 | 2022-12-06 | 2023-01-04 | 20 | 0 | 20 | [20 empty] | 2023-01-05 |  | 2024-06-08 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | RANDOLPH | 480025 | 2368 | 86 | Solar | 07_75W7 | 2022-11-30 17:08 | 2022-12-01 | 20 | 10 | 10 | [10 empty] | 2022-12-30 | 2023-02-03 | 25 | 1 | 24 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | WEST NEWBURY | 413785 | 1985 | 312.5 | Solar | 14_47L1 | 2022-12-01 08:53 | 2022-12-02 | 151 | 144 | 7 | [10 empty] | 2023-07-13 | 2023-09-15 | 46 | 28 | 18 | [10 empty] | 2024-03-29 |  |  |  | STD | [9 empty] | Conditional Approval |  | No
National Grid | ATTLEBORO | 472474 | 2703 | 13.6 | Solar | 05_9L6 | 2022-12-01 15:32 | 2022-12-02 | 4 | 0 | 4 | 2022-12-08 | 2023-01-11 | 23 | 0 | 23 | [20 empty] | 2023-01-12 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HAVERHILL | 478125 | 1830 | 15.2 | Solar | 14_76L3 | 2022-12-01 21:36 | 2022-12-02 | 4 | 2 | 2 | 2022-12-08 | 2023-01-12 | 24 | 0 | 24 | [20 empty] | 2023-01-18 | 2022-12-02 10:22 | 2024-03-22 |  | EXP | [8 empty] | 2023-05-01 | Connected |  | No
National Grid | SEEKONK | 476815 | 2771 | 13 | Solar | 05_7L4 | 2022-12-02 10:22 | 2022-12-05 | 3 | 0 | 3 | 2022-12-08 | 2023-01-17 | 27 | 3 | 24 | [20 empty] | 2023-01-18 |  | 2024-08-11 | Yes | EXP | [8 empty] | 2023-08-23 | Connected |  | No
National Grid | WEBSTER | 482139 | 1570 | 16.754 | Battery Add-On | 01_412L2 | 2022-12-02 10:25 | 2022-12-05 | 2 | 0 | 2 | 2022-12-07 | 2023-03-02 | 58 | 25 | 33 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | SWAMPSCOTT | 479881 | 1907 | 16 | Solar | 12_22W2 | 2022-12-02 10:58 | 2022-12-05 | 3 | 1 | 2 | 2022-12-08 | 2023-01-12 | 24 | 0 | 24 | [20 empty] | 2023-01-13 |  | 2024-04-30 |  | EXP | [8 empty] | 2023-09-19 | Connected |  | No
National Grid | GRAFTON | 482228 | 1519 | 20 | Solar | 01_304W1 | 2022-12-02 14:18 | 2022-12-05 | 8 | 7 | 1 | 2022-12-14 | 2023-01-19 | 24 | 0 | 24 | [20 empty] | 2023-01-24 |  | 2024-01-25 |  | EXP | [8 empty] | 2023-03-17 | Connected |  | No
National Grid | MARLBOROUGH | 478391 | 1752 | 990 | Other | 05_313W2 | 2022-12-02 17:53 | 2022-12-05 | 75 | 75 | 0 | [10 empty] | 2023-04-10 | 2023-10-26 | 138 | 119 | 19 | [11 empty] | 2022-12-05 07:40 |  |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | DUDLEY | 471682 | 1571 | 3.8 | Solar | 01_413L3 | 2022-12-05 07:40 | 2022-12-06 | 3 | 0 | 3 | 2022-12-09 | 2023-01-10 | 21 | 0 | 21 | [20 empty] | 2023-01-11 | 2022-12-05 08:23 | 2024-12-09 | Yes | EXP | [9 empty] | Completion Documents |  | No
National Grid | RANDOLPH | 468022 | 2368 | 6 | Solar | 07_97W2 | 2022-12-05 08:23 | 2022-12-06 | 2 | 0 | 2 | 2022-12-08 | 2023-01-06 | 20 | 0 | 20 | [20 empty] | 2023-01-12 | 2022-12-05 08:51 | 2024-04-13 | Yes | EXP |  | 2023-04-12 | 2023-04-11 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Yes
National Grid | NORTON | 476141 | 2766 | 6 | Solar | 05_4L2 | 2022-12-05 08:51 | 2022-12-06 | 2 | 0 | 2 | 2022-12-08 | 2023-01-10 | 22 | 0 | 22 | [20 empty] | 2023-01-17 | 2022-12-05 10:26 | 2024-04-30 | Yes | EXP |  | 2023-04-27 | 2023-04-29 | 3 | 0 | 3 |  |  | 2023-06-16 | Connected |  | No
National Grid | UPTON | 469257 | 1568 | 11.4 | Solar | 05_335W3 | 2022-12-05 10:26 | 2022-12-06 | 3 | 0 | 3 | 2022-12-09 | 2023-01-10 | 21 | 0 | 21 | [20 empty] | 2023-01-11 | 2022-12-05 12:54 | 2024-01-13 | Yes | EXP |  | 2023-03-01 | 2023-04-13 | 44 | 0 | 44 |  |  | 2023-05-10 | Connected |  | No
National Grid | CHARLTON | 482703 | 1507 | 23.49 | Solar | 01_415L2 | 2022-12-05 12:54 | 2022-12-06 | 3 | 0 | 3 | 2022-12-09 | 2023-01-19 | 28 | 4 | 24 | [20 empty] | 2023-01-20 |  | 2024-01-24 | Yes | EXP |  | 2023-05-05 | 2023-06-08 | 35 | 0 | 35 |  |  | 2023-07-27 | Connected |  | No
National Grid | WORCESTER | 482717 | 1609 | 24.779 | Solar | 01_3J375 | 2022-12-05 13:40 | 2022-12-06 | 4 | 1 | 3 | 2022-12-09 | 2023-01-13 | 24 | 0 | 24 | [20 empty] | 2023-01-17 |  | 2024-03-01 |  | EXP | [8 empty] | 2023-06-08 | Connected |  | No
National Grid | FALL RIVER | 482372 | 2724 | 3 | Solar | 05_115W42 | 2022-12-05 16:47 | 2022-12-06 | 10 | 5 | 5 | 2022-12-20 | 2023-01-19 | 20 | 0 | 20 | [20 empty] | 2023-01-20 | 2022-12-06 08:54 | 2024-05-25 |  | EXP | [8 empty] | 2023-08-30 | Connected |  | Yes
National Grid | EAST WEYMOUTH | 475879 | 2189 | 7.6 | Solar | 07_9W2 | 2022-12-06 08:54 | 2022-12-07 | 3 | 0 | 3 | 2022-12-12 | 2023-01-13 | 23 | 0 | 23 | [20 empty] | 2023-01-17 | 2022-12-06 09:06 | 2024-07-25 | Yes | EXP | [8 empty] | 2023-08-08 | Connected |  | No
National Grid | GRANBY | 471040 | 1033 | 3.8 | Solar | 09_527L1 | 2022-12-06 09:06 | 2022-12-07 | 3 | 0 | 3 | 2022-12-12 | 2023-01-11 | 21 | 0 | 21 | [20 empty] | 2023-01-12 |  | 2024-04-11 | Yes | EXP |  | 2023-03-10 | 2023-04-12 | 34 | 0 | 34 |  |  | 2023-04-18 | Connected |  | Yes
National Grid | NORTH ADAMS | 475135 | 1247 | 1250 | Solar | 09_1021W2 | 2022-12-06 10:49 | 2022-12-07 | 34 | 25 | 9 | [10 empty] | 2023-01-27 | 2023-03-03 | 25 | 2 | 23 | [10 empty] | 2024-03-22 |  |  |  | STD | [9 empty] | Conditional Approval |  | No
National Grid | TYNGSBORO | 450750 | 1879 | 11.4 | Solar | 14_211L1 | 2022-12-06 13:50 | 2022-12-07 | 1 | 0 | 1 | 2022-12-08 | 2023-01-09 | 21 | 0 | 21 | [20 empty] | 2023-01-13 | 2022-12-06 17:55 | 2024-01-18 |  | EXP | [8 empty] | 2023-03-31 | Connected |  | Yes
National Grid | UXBRIDGE | 479285 | 1569 | 10 | Solar | 05_320W4 | 2022-12-06 17:55 | 2022-12-07 | 14 | 12 | 2 | 2022-12-28 | 2023-02-01 | 24 | 2 | 22 | [20 empty] | 2023-02-01 |  | 2024-02-25 | Yes | EXP |  | 2023-04-04 | 2023-04-26 | 23 | 0 | 23 |  |  | 2023-09-19 | Connected |  | No
National Grid | SUTTON | 473792 | 1590 | 9.28 | Solar | 01_304W6 | 2022-12-07 10:10 | 2022-12-08 | 6 | 5 | 1 | 2022-12-15 | 2023-01-19 | 23 | 0 | 23 | [20 empty] | 2023-01-20 |  | 2024-01-26 |  | EXP | [8 empty] | 2023-06-13 | Connected |  | No
National Grid | AUBURN | 478360 | 1505 | 13.34 | Solar | 01_26W1 | 2022-12-07 10:28 | 2022-12-08 | 5 | 2 | 3 | 2022-12-15 | 2023-01-19 | 23 | 0 | 23 | [20 empty] | 2023-01-20 |  | 2024-01-27 |  | EXP | [8 empty] | 2023-02-25 | Connected |  | No
National Grid | SOUTHBOROUGH | 421420 | 1772 | 16.46 | Solar | 05_317W1 | 2022-12-07 11:04 | 2022-12-08 | 8 | 7 | 1 | 2022-12-20 | 2023-02-28 | 46 | 25 | 21 | [20 empty] | 2023-03-01 |  | 2024-03-07 |  | EXP | [8 empty] | 2023-05-08 | Connected |  | No
National Grid | HOLBROOK | 473793 | 2343 | 11.4 | Solar | 07_10W1 | 2022-12-07 13:25 | 2022-12-08 | 6 | 4 | 2 | 2022-12-15 | 2022-12-19 | 4 | 0 | 4 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FOXBOROUGH | 476497 | 2035 | 240 | Solar | 05_2468W1 | 2022-12-07 13:55 | 2022-12-08 | 21 | 11 | 10 | [10 empty] | 2023-01-09 | 2023-02-09 | 23 | 0 | 23 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | ATHOL | 483184 | 1331 | 6 | Solar | 09_702W1 | 2022-12-07 14:29 | 2022-12-08 | 4 | 3 | 1 | 2022-12-13 | 2023-01-18 | 24 | 0 | 24 | [20 empty] | 2023-01-19 |  | 2024-08-02 |  | EXP | [8 empty] | 2023-08-24 | Connected |  | No
National Grid | LYNN | 472733 | 1902 | 10 | Solar | 12_12J903 | 2022-12-07 14:50 | 2022-12-08 | 150 | 25 | 125 | [26 empty] | 2022-12-07 15:01 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOUTHBRIDGE | 480272 | 1550 | 7.6 | Solar | 01_413L2 | 2022-12-07 15:01 | 2022-12-08 | 25 | 22 | 3 | 2023-01-13 | 2023-02-13 | 21 | 1 | 20 | [20 empty] | 2023-02-15 |  | 2024-08-09 | Yes | EXP | [8 empty] | 2023-09-22 | Connected |  | No
National Grid | LAWRENCE | 475239 | 1841 | 7.6 | Solar | 14_74L3 | 2022-12-07 16:10 | 2022-12-08 | 3 | 0 | 3 | 2022-12-12 | 2023-01-11 | 21 | 0 | 21 | [20 empty] | 2023-01-12 |  | 2024-01-17 |  | EXP | [8 empty] | 2023-04-05 | Connected |  | No
National Grid | FALL RIVER | 480673 | 2724 | 6 | Solar | 05_115W42 | 2022-12-07 16:48 | 2022-12-08 | 3 | 0 | 3 | 2022-12-12 | 2023-01-13 | 23 | 0 | 23 | [20 empty] | 2023-01-17 | 2022-12-07 17:12 | 2024-02-09 |  | EXP | [8 empty] | 2023-03-20 | Connected |  | No
National Grid | TOPSFIELD | 463152 | 1983 | 7.6 | Solar | 14_33L1 | 2022-12-07 17:12 | 2022-12-08 | 1 | 0 | 1 | 2022-12-09 | 2023-01-10 | 21 | 0 | 21 | [20 empty] | 2023-01-17 |  | 2024-05-29 | Yes | EXP |  | 2023-03-28 | 2023-05-30 | 64 | 0 | 64 |  |  | 2023-06-02 | Connected |  | No
National Grid | EAST LONGMEADOW | 481092 | 1028 | 7.6 | Solar | 09_508L5 | 2022-12-08 07:52 | 2022-12-09 | 14 | 12 | 2 | 2022-12-29 | 2023-01-23 | 16 | 0 | 16 | [20 empty] | 2023-01-26 |  | 2024-02-02 |  | EXP | [8 empty] | 2023-08-29 | Connected |  | No
National Grid | ESSEX | 483824 | 1929 | 20 | Solar | 12_51T2 | 2022-12-08 08:00 | 2022-12-09 | 6 | 4 | 2 | 2022-12-16 | 2023-01-18 | 21 | 0 | 21 | [20 empty] | 2023-01-18 |  | 2024-06-06 |  | EXP | [8 empty] | 2023-06-20 | Connected |  | No
National Grid | STOUGHTON | 483858 | 2072 | 16 | Solar | 07_913W43 | 2022-12-08 09:29 | 2022-12-09 | 2 | 0 | 2 | 2022-12-13 | 2023-01-18 | 24 | 0 | 24 | [20 empty] | 2023-01-19 | 2022-12-08 10:59 | 2024-04-09 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | BELLINGHAM | 478736 | 2019 | 10 | Solar | 05_344W4 | 2022-12-08 10:59 | 2022-12-09 | 2 | 0 | 2 | 2022-12-13 | 2023-01-12 | 21 | 0 | 21 | [20 empty] | 2023-01-19 | 2022-12-08 11:21 | 2024-07-12 | Yes | EXP | [8 empty] | 2023-07-19 | Connected |  | No
National Grid | AUBURN | 473720 | 1501 | 5.76 | Solar | 01_406L2 | 2022-12-08 11:21 | 2022-12-09 | 2 | 0 | 2 | 2022-12-13 | 2023-01-12 | 21 | 0 | 21 | [20 empty] | 2023-01-13 |  | 2024-04-25 | Yes | EXP | [8 empty] | 2023-05-10 | Connected |  | No
National Grid | CHARLTON | 473594 | 1507 | 8.41 | Solar | 01_406L3 | 2022-12-08 11:52 | 2022-12-09 | 8 | 7 | 1 | 2022-12-21 | 2023-01-20 | 20 | 0 | 20 | [20 empty] | 2023-01-23 |  | 2024-03-28 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MARLBOROUGH | 475389 | 1752 | 3200 | Other | 05_311W6 | 2022-12-08 13:48 | 2022-12-09 | 35 | 25 | 10 | [10 empty] | 2023-02-02 | 2023-03-02 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | NEW BRAINTREE | 479620 | 1531 | 10 | Solar | 09_604W3 | 2022-12-08 13:48 | 2022-12-09 | 2 | 0 | 2 | 2022-12-13 | 2023-03-15 | 63 | 38 | 25 | [20 empty] | 2023-03-21 | 2022-12-09 09:19 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH QUINCY | 463424 | 2171 | 10 | Solar | 07_11W4 | 2022-12-09 09:19 | 2022-12-12 | 1 | 0 | 1 | 2022-12-13 | 2023-01-12 | 21 | 0 | 21 | [20 empty] | 2023-01-19 |  | 2024-05-02 | Yes | EXP |  | 2023-04-06 | 2023-05-01 | 26 | 0 | 26 |  |  | 2023-05-31 | Connected |  | Yes
National Grid | BELCHERTOWN | 484294 | 1007 | 17.6 | Solar | 09_509L2 | 2022-12-09 10:59 | 2022-12-12 | 4 | 3 | 1 | 2022-12-16 | 2023-01-18 | 21 | 0 | 21 | [20 empty] | 2023-01-19 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | HARVARD | 484329 | 1451 | 25.3 | Solar | 01_225W1 | 2022-12-09 11:54 | 2022-12-12 | 42 | 35 | 7 | 2023-02-13 | 2023-03-20 | 25 | 0 | 25 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | DUDLEY | 484394 | 1571 | 7.6 | Solar | 01_412L4 | 2022-12-09 15:03 | 2022-12-12 | 3 | 1 | 2 | 2022-12-15 | 2023-01-18 | 22 | 0 | 22 | [20 empty] | 2023-01-23 |  | 2024-01-31 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MEDFORD | 484436 | 2155 | 15.2 | Solar | 12_11J3 | 2022-12-09 16:11 | 2022-12-12 | 5 | 4 | 1 | 2022-12-16 | 2023-01-18 | 21 | 0 | 21 | [20 empty] | 2023-01-19 |  | 2024-02-03 |  | EXP | [8 empty] | 2023-05-12 | Connected |  | No
National Grid | WORCESTER | 447540 | 1606 | 3.8 | Solar | 01_24W1 | 2022-12-09 16:20 | 2022-12-12 | 44 | 42 | 2 | 2023-02-15 | 2023-07-13 | 102 | 81 | 21 | [20 empty] | 2023-07-18 |  | 2024-08-08 |  | EXP | [8 empty] | 2023-09-26 | Connected |  | No
National Grid | BEVERLY | 479722 | 1915 | 6 | Solar | 12_12L2 | 2022-12-10 14:37 | 2022-12-12 | 13 | 9 | 4 | 2022-12-30 | 2023-01-31 | 21 | 0 | 21 | [20 empty] | 2023-02-01 |  | 2024-06-05 |  | EXP | [8 empty] | 2023-10-04 | Connected |  | Yes
National Grid | BRIDGEWATER | 482811 | 2324 | 10 | Solar | 07_797W1 | 2022-12-12 15:43 | 2022-12-13 | 1 | 0 | 1 | 2022-12-14 | 2023-01-12 | 20 | 0 | 20 | [20 empty] | 2023-01-12 | 2022-12-12 18:18 | 2024-04-28 |  | EXP | [8 empty] | 2023-05-09 | Connected |  | No
National Grid | RANDOLPH | 481663 | 2368 | 7.6 | Solar | 07_5W3 | 2022-12-12 18:18 | 2022-12-13 | 2 | 0 | 2 | 2022-12-15 | 2023-01-17 | 21 | 0 | 21 | [20 empty] | 2023-01-18 |  | 2024-10-06 | Yes | EXP | [8 empty] | 2024-03-26 | Connected |  | No
National Grid | BERLIN | 482613 | 1503 | 18 | Solar | 05_318W3 | 2022-12-13 09:07 | 2022-12-14 | 13 | 8 | 5 | 2023-01-04 | 2023-01-30 | 18 | 0 | 18 | [20 empty] | 2023-01-31 |  | 2025-01-20 |  | EXP | [8 empty] | 2024-02-20 | Connected |  | No
National Grid | WESTFORD | 485002 | 1886 | 15.2 | Solar | 14_58L1 | 2022-12-13 10:14 | 2022-12-14 | 2 | 0 | 2 | 2022-12-16 | 2023-01-19 | 22 | 0 | 22 | 2023-03-21 | 2023-04-27 | 28 | 0 | 28 | [5 empty] | 2023-03-21 | 2023-04-27 | 28 | 0 | 28 | [5 empty] | 2023-04-05 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BRIDGEWATER | 485014 | 2324 | 16 | Solar | 07_797W1 | 2022-12-13 10:48 | 2022-12-14 | 9 | 8 | 1 | 2022-12-28 | 2023-01-30 | 22 | 0 | 22 | [20 empty] | 2023-01-31 |  | 2024-03-27 |  | EXP | [8 empty] | 2023-03-29 | Connected |  | No
National Grid | SAUGUS | 471967 | 1906 | 3.8 | Solar | 12_16W1 | 2022-12-13 11:03 | 2022-12-14 | 5 | 0 | 5 | 2022-12-21 | 2023-01-20 | 20 | 0 | 20 | [20 empty] | 2023-01-26 |  | 2024-02-01 |  | EXP | [8 empty] | 2023-04-08 | Connected |  | No
National Grid | FRANKLIN | 475744 | 2038 | 18.846 | Solar | 05_348W1 | 2022-12-13 11:41 | 2022-12-14 | 1 | 0 | 1 | 2022-12-15 | 2023-01-19 | 23 | 0 | 23 | [20 empty] | 2023-01-20 | 2022-12-13 11:45 | 2024-01-30 |  | EXP | [8 empty] | 2023-07-21 | Connected |  | No
National Grid | LAWRENCE | 483461 | 1843 | 10 | Solar | 14_61L3 | 2022-12-13 11:45 | 2022-12-14 | 5 | 0 | 5 | 2022-12-21 | 2023-01-20 | 20 | 0 | 20 | [20 empty] | 2023-01-26 |  | 2024-05-01 | Yes | EXP | [8 empty] | 2023-05-21 | Connected |  | No
National Grid | WENHAM | 485207 | 1984 | 19 | Solar | 12_51L3 | 2022-12-13 15:23 | 2022-12-14 | 2 | 0 | 2 | 2022-12-16 | 2023-01-20 | 23 | 0 | 23 | [20 empty] | 2023-01-26 |  | 2024-02-17 |  | EXP | [8 empty] | 2023-04-04 | Connected |  | No
National Grid | SOUTHBOROUGH | 485238 | 1772 | 15.2 | Solar | 05_310W3 | 2022-12-13 16:45 | 2022-12-14 | 1 | 0 | 1 | 2022-12-15 | 2023-01-17 | 21 | 0 | 21 | [20 empty] | 2023-01-18 |  | 2024-02-22 |  | EXP | [8 empty] | 2023-04-13 | Connected |  | No
National Grid | AUBURN | 476717 | 1501 | 160 | Solar | 01_26W3 | 2022-12-13 18:03 | 2022-12-14 | 46 | 39 | 7 | [10 empty] | 2023-02-21 | 2023-03-24 | 24 | 0 | 24 | [14 empty] | STD | [9 empty] | Conditional Approval |  | Yes
National Grid | NORTHBOROUGH | 483268 | 1532 | 10 | Solar | 05_313W4 | 2022-12-14 12:21 | 2022-12-15 | 4 | 0 | 4 | 2022-12-21 | 2023-02-01 | 28 | 4 | 24 | 2023-02-06 | 2023-03-20 | 30 | 0 | 30 | [5 empty] | 2023-02-06 | 2023-03-20 | 30 | 0 | 30 | [5 empty] | 2023-03-23 |  | 2024-04-25 |  | EXP |  | 2023-04-08 | 2023-04-26 | 19 | 0 | 19 |  |  | 2023-07-20 | Connected |  | No
National Grid | SOUTH EASTON | 485460 | 2375 | 20 | Solar | 07_92W54 | 2022-12-14 13:27 | 2022-12-15 | 112 | 71 | 41 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | LEICESTER | 485085 | 1524 | 6 | Solar | 01_21W2 | 2022-12-14 14:22 | 2022-12-15 | 4 | 0 | 4 | 2022-12-21 | 2023-01-20 | 20 | 0 | 20 | [20 empty] | 2023-01-26 |  | 2024-08-01 |  | EXP | [8 empty] | 2023-11-02 | Connected |  | No
National Grid | WESTFORD | 485511 | 1886 | 20 | Solar | 14_57L3 | 2022-12-14 14:26 | 2022-12-15 | 1 | 0 | 1 | 2022-12-16 | 2023-01-20 | 23 | 0 | 23 | [20 empty] | 2023-01-20 |  | 2024-03-19 |  | EXP | [8 empty] | 2023-10-10 | Connected |  | No
National Grid | BOLTON | 483675 | 1740 | 13.92 | Solar | 01_225W1 | 2022-12-14 14:37 | 2022-12-15 | 4 | 1 | 3 | 2022-12-21 | 2023-01-20 | 20 | 0 | 20 | [20 empty] | 2023-01-26 |  | 2024-05-24 |  | EXP | [8 empty] | 2023-06-13 | Connected |  | No
National Grid | BRIMFIELD | 485570 | 1010 | 25 | Solar | 09_516L1 | 2022-12-14 16:22 | 2022-12-15 | 2 | 0 | 2 | 2022-12-19 | 2023-01-20 | 22 | 0 | 22 | [20 empty] | 2023-01-27 |  | 2024-07-01 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SOUTHBOROUGH | 485595 | 1772 | 20 | Solar | 05_310W5 | 2022-12-14 17:13 | 2022-12-15 | 3 | 2 | 1 | 2022-12-20 | 2023-01-19 | 20 | 0 | 20 | [20 empty] | 2023-01-20 |  | 2024-02-13 |  | EXP | [8 empty] | 2023-10-02 | Connected |  | No
National Grid | FALL RIVER | 484084 | 2720 | 126.3 | Solar | 05_28W51 | 2022-12-14 17:39 | 2022-12-15 | 39 | 29 | 10 | [10 empty] | 2023-02-13 | 2023-03-21 | 27 | 2 | 25 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | ROCKLAND | 478163 | 2370 | 120 | Solar | 07_95W4 | 2022-12-14 22:43 | 2022-12-15 | 72 | 62 | 10 | [10 empty] | 2023-04-03 | 2023-05-08 | 25 | 0 | 25 | [14 empty] | STD | [9 empty] | Group Study |  | Yes
National Grid | ROCKLAND | 478187 | 2370 | 120 | Solar | 07_95W4 | 2022-12-14 22:48 | 2022-12-15 | 72 | 62 | 10 | [10 empty] | 2023-04-03 | 2023-05-08 | 25 | 0 | 25 | [14 empty] | STD | [9 empty] | Group Study |  | Yes
National Grid | ESSEX | 485658 | 1929 | 7.6 | Solar | 12_51T2 | 2022-12-15 09:23 | 2022-12-16 | 2 | 0 | 2 | 2022-12-20 | 2023-03-23 | 63 | 40 | 23 | [20 empty] | 2023-03-23 |  | 2024-03-26 |  | EXP | [8 empty] | 2023-08-01 | Connected |  | Yes
National Grid | STURBRIDGE | 484990 | 1566 | 5.51 | Solar | 01_415L1 | 2022-12-15 09:29 | 2022-12-16 | 7 | 1 | 6 | 2022-12-27 | 2023-03-08 | 48 | 25 | 23 | [20 empty] | 2023-03-14 | 2022-12-15 09:38 | 2024-03-24 |  | EXP | [8 empty] | 2023-05-26 | Connected |  | No
National Grid | LEOMINSTER | 484968 | 1453 | 8.99 | Solar | 01_207W2 | 2022-12-15 09:38 | 2022-12-16 | 7 | 1 | 6 | 2022-12-27 | 2023-01-30 | 23 | 0 | 23 | [20 empty] | 2023-01-31 |  | 2024-10-25 | Yes | EXP |  | 2023-07-18 | 2023-10-20 | 95 | 0 | 95 |  |  |  | Completion Documents |  | Yes
National Grid | BROCKTON | 485684 | 2301 | 15.08 | Solar | 07_94W40 | 2022-12-15 09:55 | 2022-12-16 | 4 | 2 | 2 | 2022-12-21 | 2023-01-20 | 20 | 0 | 20 | [20 empty] | 2023-01-23 |  | 2024-01-25 |  | EXP | [8 empty] | 2023-03-31 | Connected |  | No
National Grid | WEYMOUTH | 485756 | 2190 | 17.11 | Solar | 07_12W5 | 2022-12-15 11:39 | 2022-12-16 | 4 | 1 | 3 | 2022-12-21 | 2023-01-20 | 20 | 0 | 20 | [20 empty] | 2023-01-25 |  | 2024-02-01 |  | EXP | [8 empty] | 2023-04-14 | Connected |  | No
National Grid | BOLTON | 485679 | 1740 | 15.6 | Solar | 01_225W1 | 2022-12-15 11:48 | 2022-12-16 | 37 | 36 | 1 | 2023-02-10 | 2023-03-16 | 24 | 0 | 24 | [20 empty] | 2023-03-16 |  | 2024-03-17 |  | EXP | [8 empty] | 2023-06-03 | Connected |  | No
National Grid | WEST STOCKBRIDGE | 346854 | 1266 | 4980 | Solar | 09_1109W3 | 2022-12-15 12:12 | 2022-12-16 | 101 | 93 | 8 | [10 empty] | 2023-05-15 | 2023-11-02 | 119 | 100 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | STOUGHTON | 474223 | 2072 | 5.8 | Solar | 07_913W43 | 2022-12-15 13:12 | 2022-12-16 | 11 | 7 | 4 | 2023-01-04 | 2023-03-15 | 49 | 30 | 19 | [20 empty] | 2023-03-20 |  | 2024-11-30 |  | EXP | [8 empty] | 2024-02-15 | Connected |  | No
National Grid | PEPPERELL | 478031 | 1463 | 4.64 | Solar | 01_226L2 | 2022-12-15 13:34 | 2022-12-16 | 3 | 0 | 3 | 2022-12-21 | 2023-01-23 | 21 | 0 | 21 | [20 empty] | 2023-01-31 | 2022-12-15 14:53 | 2024-03-21 |  | EXP | [8 empty] | 2023-05-02 | Connected |  | No
National Grid | LANCASTER | 481067 | 1523 | 6.38 | Solar | 01_216W4 | 2022-12-15 14:53 | 2022-12-16 | 7 | 1 | 6 | 2022-12-27 | 2023-01-23 | 18 | 0 | 18 | [20 empty] | 2023-01-26 | 2022-12-15 15:02 | 2024-05-16 | Yes | EXP | [8 empty] | 2023-06-22 | Connected |  | No
National Grid | NEWBURYPORT | 475737 | 1950 | 100 | Solar | 14_60L3 | 2022-12-15 15:02 | 2022-12-16 | 21 | 12 | 9 | 2023-01-19 | 2023-03-16 | 40 | 15 | 25 | [20 empty] | 2023-03-30 |  | 2024-10-06 | Yes | EXP | [9 empty] | Completion Documents |  | No
National Grid | ATTLEBORO | 485614 | 2703 | 15.2 | Solar | 05_9L1 | 2022-12-15 15:09 | 2022-12-16 | 7 | 4 | 3 | 2022-12-28 | 2023-01-30 | 22 | 0 | 22 | [20 empty] | 2023-01-30 | 2022-12-15 15:30 | 2024-02-01 |  | EXP | [8 empty] | 2023-04-06 | Connected |  | No
National Grid | ANDOVER | 485876 | 1810 | 17.6 | Solar | 14_54L3 | 2022-12-15 15:30 | 2022-12-16 | 2 | 0 | 2 | 2022-12-20 | 2023-01-19 | 20 | 0 | 20 | [20 empty] | 2023-01-20 |  | 2024-04-26 | Yes | EXP |  | 2023-05-09 | 2023-06-08 | 31 | 0 | 31 |  |  | 2024-01-17 | Connected |  | No
National Grid | FALL RIVER | 484096 | 2724 | 10 | Solar | 05_115W42 | 2022-12-15 19:03 | 2022-12-16 | 3 | 0 | 3 | 2022-12-21 | 2023-01-04 | 9 | 0 | 9 | [20 empty] | 2023-01-05 | 2022-12-16 12:28 | 2024-01-06 |  | EXP | [8 empty] | 2023-07-20 | Connected |  | No
National Grid | DIGHTON | 482133 | 2715 | 8.12 | Solar | 05_19W73 | 2022-12-16 12:28 | 2022-12-19 | 3 | 2 | 1 | 2022-12-21 | 2023-01-23 | 21 | 0 | 21 | [20 empty] | 2023-01-30 | 2022-12-19 08:01 | 2024-03-20 | Yes | EXP |  | 2023-02-11 | 2023-03-17 | 35 | 0 | 35 |  |  | 2023-06-16 | Connected |  | No
National Grid | SWAMPSCOTT | 451712 | 1907 | 10 | Solar | 12_29W4 | 2022-12-19 08:01 | 2022-12-20 | 1 | 0 | 1 | 2022-12-21 | 2023-01-20 | 20 | 0 | 20 | [20 empty] | 2023-01-25 |  | 2024-09-10 | Yes | EXP |  | 2023-08-09 | 2023-08-29 | 21 | 0 | 21 |  |  | 2023-09-26 | Connected |  | No
National Grid | METHUEN | 479994 | 1844 | 7.6 | Solar | 14_43L4 | 2022-12-19 09:40 | 2022-12-20 | 5 | 0 | 5 | 2022-12-27 | 2023-01-17 | 14 | 0 | 14 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EAST BRIDGEWATER | 486457 | 2333 | 7.6 | Solar | 07_797W1 | 2022-12-19 09:56 | 2022-12-20 | 9 | 7 | 2 | [10 empty] | 2023-01-04 | 2023-09-06 | 168 | 148 | 20 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | STOCKBRIDGE | 486533 | 1262 | 22.8 | Solar | 09_1102W1 | 2022-12-19 17:07 | 2022-12-20 | 1 | 0 | 1 | 2022-12-21 | 2023-01-20 | 20 | 0 | 20 | [20 empty] | 2023-01-23 |  | 2024-01-25 |  | EXP | [8 empty] | 2023-02-22 | Connected |  | No
National Grid | HAVERHILL | 416288 | 1832 | 7.6 | Solar | 14_43L6 | 2022-12-20 07:53 | 2022-12-21 | 10 | 10 | 0 | 2023-01-06 | 2023-01-30 | 16 | 0 | 16 | [20 empty] | 2023-01-31 |  | 2024-02-03 |  | EXP | [8 empty] | 2023-02-17 | Connected |  | No
National Grid | FALL RIVER | 482174 | 2724 | 3.8 | Solar | 05_115W42 | 2022-12-20 09:51 | 2022-12-21 | 4 | 0 | 4 | 2022-12-27 | 2023-01-20 | 17 | 0 | 17 | [20 empty] | 2023-01-26 | 2022-12-20 10:02 | 2024-02-01 |  | EXP | [8 empty] | 2023-02-15 | Connected |  | No
National Grid | WEYMOUTH | 477444 | 2189 | 10 | Solar | 07_6W1 | 2022-12-20 10:02 | 2022-12-21 | 4 | 0 | 4 | 2022-12-27 | 2023-01-23 | 18 | 0 | 18 | [20 empty] | 2023-01-26 | 2022-12-20 10:18 | 2024-09-25 | Yes | EXP | [8 empty] | 2023-10-17 | Connected |  | No
National Grid | METHUEN | 474114 | 1844 | 10 | Solar | 14_74L1 | 2022-12-20 10:18 | 2022-12-21 | 1 | 0 | 1 | 2022-12-22 | 2023-01-23 | 20 | 0 | 20 | [20 empty] | 2023-01-30 | 2022-12-20 10:22 | 2024-04-19 | Yes | EXP |  | 2023-03-14 | 2023-04-19 | 37 | 0 | 37 |  |  | 2023-05-15 | Connected |  | No
National Grid | LOWELL | 481185 | 1854 | 201.9 | Solar | 14_77L2 | 2022-12-20 10:22 | 2022-12-21 | 56 | 47 | 9 | 2023-03-15 | 2023-04-19 | 25 | 0 | 25 | [20 empty] | 2023-05-03 | 2022-12-20 10:30 | 2024-05-25 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | FLORENCE | 483548 | 1062 | 3.8 | Solar | 09_909W1 | 2022-12-20 10:30 | 2022-12-21 | 2 | 0 | 2 | 2022-12-23 | 2023-01-23 | 19 | 0 | 19 | [20 empty] | 2023-01-30 | 2022-12-20 14:11 | 2024-06-30 | Yes | EXP |  | 2023-05-16 | 2023-06-30 | 45 | 0 | 45 |  |  | 2023-07-25 | Connected |  | No
National Grid | WESTPORT | 473743 | 2790 | 10 | Solar | 05_115W45 | 2022-12-20 14:11 | 2022-12-21 | 4 | 2 | 2 | 2022-12-28 | 2023-03-09 | 48 | 25 | 23 | [20 empty] | 2023-03-09 |  | 2024-04-06 | Yes | EXP |  | 2023-04-22 | 2023-05-25 | 34 | 0 | 34 |  |  | 2023-06-01 | Connected |  | No
National Grid | OXFORD | 427518 | 1537 | 996 | Solar | 01_406L1 | 2022-12-20 17:32 | 2022-12-21 | 73 | 73 | 0 | [10 empty] | 2023-04-07 | 2023-05-03 | 18 | 0 | 18 | [11 empty] | 2022-12-21 07:26 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BELLINGHAM | 472217 | 2019 | 10 | Solar | 05_344W4 | 2022-12-21 07:26 | 2022-12-22 | 1 | 0 | 1 | 2022-12-23 | 2023-01-23 | 19 | 0 | 19 | [20 empty] | 2023-01-30 |  | 2024-12-24 | Yes | EXP |  | 2023-07-28 | 2024-02-13 | 200 | 3 | 197 |  |  |  | Completion Documents |  | Yes
National Grid | BELLINGHAM | 477584 | 2019 | 6 | Solar | 05_335W1 | 2022-12-21 07:38 | 2022-12-22 | 190 | 188 | 2 | 2023-09-26 | 2023-10-23 | 19 | 0 | 19 | [20 empty] | 2023-10-26 |  | 2024-11-10 |  | EXP | [8 empty] | 2024-01-27 | Connected |  | No
National Grid | WILBRAHAM | 486553 | 1095 | 15.2 | Solar | 09_507L3 | 2022-12-21 08:52 | 2022-12-22 | 1 | 0 | 1 | 2022-12-23 | 2023-01-23 | 19 | 0 | 19 | [20 empty] | 2023-01-24 |  | 2024-02-15 |  | EXP | [8 empty] | 2023-08-08 | Connected |  | No
National Grid | PEMBROKE | 482498 | 2359 | 10 | Solar | 07_910W52 | 2022-12-21 11:58 | 2022-12-22 | 3 | 0 | 3 | 2022-12-27 | 2023-01-25 | 20 | 0 | 20 | [20 empty] | 2023-01-30 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | PRIDESOUTH XING | 486700 | 1965 | 19.57 | Solar | 12_51T1 | 2022-12-21 13:04 | 2022-12-22 | 4 | 3 | 1 | 2022-12-28 | 2023-01-30 | 22 | 0 | 22 | [20 empty] | 2023-01-31 |  | 2024-01-31 |  | EXP | [8 empty] | 2023-03-01 | Connected |  | No
National Grid | WORCESTER | 485090 | 1609 | 17.45 | Solar | 01_23W2 | 2022-12-21 14:52 | 2022-12-22 | 1 | 0 | 1 | 2022-12-23 | 2023-01-23 | 19 | 0 | 19 | [20 empty] | 2023-01-23 |  | 2024-01-31 |  | EXP | [8 empty] | 2023-09-06 | Connected |  | No
National Grid | MILFORD | 475185 | 1757 | 6.96 | Solar | 05_335W3 | 2022-12-21 17:00 | 2022-12-22 | 7 | 0 | 7 | 2023-01-04 | 2023-02-01 | 20 | 0 | 20 | [20 empty] | 2023-02-07 |  | 2024-02-09 |  | EXP | [8 empty] | 2023-04-05 | Connected |  | No
National Grid | NORTHAMPTON | 484829 | 1060 | 120 | Solar | 09_905W1 | 2022-12-21 17:04 | 2022-12-22 | 49 | 38 | 11 | [10 empty] | 2023-03-07 | 2023-04-11 | 26 | 2 | 24 | [10 empty] | 2023-12-27 |  |  |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | NORTHAMPTON | 485578 | 1060 | 120 | Solar | 09_905W1 | 2022-12-21 17:08 | 2022-12-22 | 50 | 40 | 10 | [10 empty] | 2023-03-08 | 2023-04-11 | 25 | 1 | 24 | [10 empty] | 2023-12-27 |  |  |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | GRANBY | 465731 | 1033 | 14999 | Other | 09_527L1 | 2022-12-22 14:44 | 2022-12-23 | 12 | 2 | 10 | [10 empty] | 2023-01-11 | 2023-02-09 | 21 | 0 | 21 | [11 empty] | 2022-12-22 15:01 |  |  | STD | [9 empty] | Study |  | No
National Grid | CHARLEMONT | 417651 | 1339 | 16 | Solar | 09_1007G1 | 2022-12-22 15:01 | 2022-12-23 | 2 | 0 | 2 | 2022-12-28 | 2023-01-30 | 22 | 0 | 22 | [20 empty] | 2023-01-30 |  | 2024-02-03 | Yes | EXP |  | 2023-04-25 | 2023-08-24 | 122 | 0 | 122 |  |  | 2023-11-06 | Connected |  | No
National Grid | SOUTH GRAFTON | 487761 | 1560 | 15.2 | Solar | 05_320W3 | 2022-12-22 16:21 | 2022-12-23 | 2 | 0 | 2 | 2022-12-28 | 2023-04-13 | 73 | 50 | 23 | 2023-05-03 | 2023-12-14 | 154 | 25 | 129 | [5 empty] | 2023-05-03 | 2023-12-14 | 154 | 25 | 129 | [6 empty] | 2022-12-23 05:03 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | REHOBOTH | 481302 | 2769 | 5.22 | Solar | 05_3J2 | 2022-12-23 05:03 | 2022-12-27 | 4 | 2 | 2 | 2023-01-03 | 2023-03-15 | 50 | 29 | 21 | [20 empty] | 2023-03-21 |  | 2024-05-16 | Yes | EXP |  | 2023-04-29 | 2023-05-15 | 17 | 0 | 17 |  |  | 2023-08-09 | Connected |  | No
National Grid | METHUEN | 486205 | 1844 | 7.6 | Solar | 14_43L4 | 2022-12-27 09:12 | 2022-12-28 | 2 | 0 | 2 | 2022-12-30 | 2023-01-23 | 15 | 0 | 15 | [20 empty] | 2023-01-26 |  | 2024-01-31 |  | EXP | [8 empty] | 2023-05-21 | Connected |  | No
National Grid | UPTON | 485628 | 1568 | 7.6 | Solar | 05_335W3 | 2022-12-27 09:26 | 2022-12-28 | 4 | 0 | 4 | 2023-01-04 | 2023-01-24 | 14 | 0 | 14 | [20 empty] | 2023-01-31 | 2022-12-27 10:35 | 2024-02-01 |  | EXP | [8 empty] | 2023-05-08 | Connected |  | No
National Grid | WEST BRIDGEWATER | 486251 | 2379 | 10 | Solar | 07_797W20 | 2022-12-27 10:35 | 2022-12-28 | 4 | 0 | 4 | 2023-01-04 | 2023-01-25 | 15 | 0 | 15 | [20 empty] | 2023-01-31 |  | 2024-03-26 | Yes | EXP |  | 2023-03-28 | 2023-03-27 | 0 | 0 | 0 |  |  | 2023-07-24 | Connected |  | Yes
National Grid | BROCKTON | 487499 | 2301 | 15.2 | Solar | 07_91W49 | 2022-12-27 13:54 | 2022-12-28 | 4 | 2 | 2 | 2023-01-04 | 2023-01-30 | 18 | 0 | 18 | [20 empty] | 2023-01-31 |  | 2024-05-23 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | PEPPERELL | 488269 | 1463 | 20.591 | Solar | 01_226L2 | 2022-12-27 14:02 | 2022-12-28 | 42 | 41 | 1 | [26 empty] | 2022-12-27 15:00 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HOLBROOK | 485772 | 2343 | 7.6 | Solar | 07_10W1 | 2022-12-27 15:00 | 2022-12-28 | 2 | 0 | 2 | 2022-12-30 | 2023-01-23 | 15 | 0 | 15 | [20 empty] | 2023-01-26 |  | 2024-05-13 | Yes | EXP |  | 2023-09-28 | 2023-10-26 | 29 | 0 | 29 |  |  | 2023-11-27 | Connected |  | Yes
National Grid | HARVARD | 488296 | 1451 | 25 | Solar | 01_225W1 | 2022-12-27 15:07 | 2022-12-28 | 4 | 1 | 3 | 2023-01-04 | 2023-01-30 | 18 | 0 | 18 | [20 empty] | 2023-01-31 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SOUTH EASTON | 487262 | 2375 | 15.2 | Solar | 07_92W54 | 2022-12-28 12:49 | 2022-12-29 | 5 | 1 | 4 | 2023-01-05 | 2023-02-02 | 20 | 0 | 20 | [20 empty] | 2023-02-03 |  | 2024-02-03 |  | EXP | [8 empty] | 2023-04-24 | Connected |  | No
National Grid | WESTMINSTER | 485301 | 1473 | 11.4 | Solar | 01_609W2 | 2022-12-28 15:16 | 2022-12-29 | 136 | 59 | 77 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | ANDOVER | 483147 | 1810 | 15.2 | Solar | 14_62L2 | 2022-12-28 15:40 | 2022-12-29 | 14 | 13 | 1 | 2023-01-19 | 2023-02-16 | 22 | 1 | 21 | [20 empty] | 2023-02-21 | 2022-12-28 17:34 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EAST LONGMEADOW | 486713 | 1028 | 7.83 | Solar | 09_139L5 | 2022-12-28 17:34 | 2022-12-29 | 3 | 1 | 2 | 2023-01-04 | 2023-01-25 | 15 | 0 | 15 | [20 empty] | 2023-01-30 |  | 2024-07-06 | Yes | EXP | [8 empty] | 2023-11-01 | Connected |  | No
National Grid | NORTH CHELMSFORD | 488662 | 1863 | 22.272 | Solar | 14_2L2 | 2022-12-29 09:59 | 2022-12-30 | 68 | 59 | 9 | 2023-04-07 | 2023-11-13 | 150 | 133 | 17 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | EAST BRIDGEWATER | 485389 | 2333 | 7.6 | Solar | 07_797W23 | 2022-12-29 12:05 | 2022-12-30 | 2 | 0 | 2 | 2023-01-04 | 2023-02-02 | 24 | 0 | 24 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEICESTER | 449868 | 1524 | 10 | Solar | 01_21W1 | 2022-12-29 12:44 | 2022-12-30 | 3 | 0 | 3 | 2023-01-05 | 2023-01-25 | 14 | 0 | 14 | [20 empty] | 2023-01-26 | 2022-12-29 13:36 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SALEM | 488516 | 1970 | 80 | Solar | 12_49W2 | 2022-12-29 13:36 | 2022-12-30 | 15 | 6 | 9 | 2023-01-24 | 2023-03-02 | 27 | 0 | 27 | [20 empty] | 2023-03-16 | 2022-12-29 17:20 | 2024-08-19 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | WILBRAHAM | 485815 | 1095 | 9.86 | Solar | 09_507L3 | 2022-12-29 17:20 | 2022-12-30 | 2 | 0 | 2 | 2023-01-04 | 2023-01-25 | 15 | 0 | 15 | [20 empty] | 2023-01-30 | 2022-12-30 11:56 | 2024-05-15 | Yes | EXP | [8 empty] | 2023-07-26 | Connected |  | No
National Grid | BROCKTON | 484350 | 2302 | 10 | Solar | 07_911W56 | 2022-12-30 11:56 | 2023-01-03 | 2 | 0 | 2 | 2023-01-05 | 2023-01-25 | 14 | 0 | 14 | [20 empty] | 2023-01-31 |  | 2024-05-15 | Yes | EXP |  | 2023-04-07 | 2023-05-15 | 39 | 0 | 39 |  |  | 2023-07-11 | Connected |  | No
National Grid | DIGHTON | 486122 | 2764 | 10 | Solar | 05_19W73 | 2023-01-03 09:59 | 2023-01-04 | 1 | 0 | 1 | 2023-01-05 | 2023-02-02 | 20 | 0 | 20 | [20 empty] | 2023-02-08 |  | 2024-02-11 |  | EXP | [8 empty] | 2023-06-14 | Connected |  | No
National Grid | BROCKTON | 486521 | 2302 | 7.6 | Solar | 07_91W49 | 2023-01-03 11:08 | 2023-01-04 | 17 | 15 | 2 | 2023-01-30 | 2023-02-23 | 18 | 0 | 18 | [20 empty] | 2023-02-24 |  | 2024-03-07 |  | EXP | [8 empty] | 2023-06-02 | Connected |  | Yes
National Grid | DIGHTON | 484722 | 2715 | 7.6 | Solar | 05_19W72 | 2023-01-03 11:22 | 2023-01-04 | 1 | 0 | 1 | 2023-01-05 | 2023-01-25 | 14 | 0 | 14 | [20 empty] | 2023-01-31 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH GRAFTON | 486978 | 1536 | 16.82 | Solar | 01_328W3 | 2023-01-03 15:27 | 2023-01-04 | 1 | 0 | 1 | 2023-01-05 | 2023-02-03 | 20 | 0 | 20 | [20 empty] | 2023-02-03 |  | 2024-02-09 |  | EXP | [8 empty] | 2023-06-06 | Connected |  | No
National Grid | SCITUATE | 488438 | 2066 | 10 | Solar | 07_915W37 | 2023-01-03 16:05 | 2023-01-04 | 2 | 0 | 2 | 2023-01-06 | 2023-02-02 | 19 | 0 | 19 | [20 empty] | 2023-02-08 |  | 2024-04-13 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | SOUTHBRIDGE | 482280 | 1550 | 18.816 | Solar | 01_413L1 | 2023-01-03 19:51 | 2023-01-04 | 15 | 14 | 1 | 2023-01-26 | 2023-02-21 | 19 | 1 | 18 | [20 empty] | 2023-02-22 |  | 2024-03-26 |  | EXP | [8 empty] | 2023-06-22 | Connected |  | Yes
National Grid | EAST LONGMEADOW | 489544 | 1028 | 7.6 | Solar | 09_508L1 | 2023-01-04 09:58 | 2023-01-05 | 3 | 0 | 3 | 2023-01-10 | 2023-03-02 | 37 | 17 | 20 | [20 empty] | 2023-03-07 |  | 2024-04-02 |  | EXP | [8 empty] | 2023-08-22 | Connected |  | Yes
National Grid | WESTBOROUGH | 489567 | 1581 | 15.2 | Solar | 05_312W4 | 2023-01-04 11:15 | 2023-01-05 | 3 | 2 | 1 | 2023-01-09 | 2023-02-10 | 24 | 0 | 24 | [20 empty] | 2023-02-10 |  | 2024-02-14 |  | EXP | [8 empty] | 2023-05-03 | Connected |  | No
National Grid | WESTFORD | 479921 | 1886 | 7.6 | Solar | 14_57L2 | 2023-01-04 11:28 | 2023-01-05 | 3 | 0 | 3 | 2023-01-10 | 2023-02-07 | 20 | 0 | 20 | [20 empty] | 2023-02-09 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MALDEN | 485036 | 2148 | 7.6 | Solar | 12_16W7 | 2023-01-04 12:36 | 2023-01-05 | 41 | 35 | 6 | 2023-03-07 | 2023-04-17 | 30 | 13 | 17 | [20 empty] | 2023-04-20 |  | 2024-05-04 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | BERLIN | 484982 | 1503 | 7.6 | Solar | 05_318W3 | 2023-01-04 13:55 | 2023-01-05 | 1 | 0 | 1 | 2023-01-06 | 2023-01-30 | 16 | 0 | 16 | [20 empty] | 2023-01-31 |  | 2024-02-03 |  | EXP | [8 empty] | 2023-03-23 | Connected |  | Yes
National Grid | MILFORD | 489672 | 1757 | 23.12 | Solar | 05_335W3 | 2023-01-04 15:05 | 2023-01-05 | 68 | 45 | 23 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | LANCASTER | 430312 | 1523 | 4999 | Other | 01_216W4 | 2023-01-04 17:06 | 2023-01-05 | 10 | 3 | 7 | [10 empty] | 2023-01-20 | 2023-02-22 | 22 | 0 | 22 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTBOROUGH | 479590 | 1581 | 7.6 | Solar | 05_312W4 | 2023-01-05 10:32 | 2023-01-06 | 3 | 0 | 3 | 2023-01-11 | 2023-02-13 | 23 | 0 | 23 | [20 empty] | 2023-02-14 |  | 2024-04-23 |  | EXP | [8 empty] | 2023-06-21 | Connected |  | No
National Grid | WORCESTER | 459363 | 1605 | 3.8 | Solar | 01_27W4 | 2023-01-05 10:39 | 2023-01-06 | 213 | 213 | 0 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | DUDLEY | 489902 | 1571 | 15.2 | Solar | 01_412L5 | 2023-01-05 10:43 | 2023-01-06 | 1 | 0 | 1 | 2023-01-09 | 2023-02-06 | 20 | 0 | 20 | [20 empty] | 2023-02-07 |  | 2024-02-08 |  | EXP | [8 empty] | 2023-04-07 | Connected |  | No
National Grid | WEYMOUTH | 489983 | 2191 | 15.2 | Solar | 07_6W2 | 2023-01-05 13:58 | 2023-01-06 | 1 | 0 | 1 | 2023-01-09 | 2023-02-06 | 20 | 0 | 20 | [20 empty] | 2023-02-07 |  | 2024-02-09 |  | EXP | [8 empty] | 2023-06-27 | Connected |  | No
National Grid | WESTMINSTER | 487740 | 1473 | 9.86 | Solar | 01_602W2 | 2023-01-05 15:28 | 2023-01-06 | 2 | 0 | 2 | 2023-01-10 | 2023-05-15 | 86 | 25 | 61 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GLOUCESTER | 485413 | 1930 | 7.6 | Solar | 12_52L1 | 2023-01-05 16:21 | 2023-01-06 | 1 | 0 | 1 | 2023-01-09 | 2023-02-10 | 24 | 0 | 24 | [20 empty] | 2023-02-10 |  | 2024-05-08 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | HALIFAX | 490153 | 2338 | 20 | Solar | 07_797W24 | 2023-01-05 20:36 | 2023-01-06 | 1 | 0 | 1 | 2023-01-09 | 2023-02-10 | 24 | 0 | 24 | [20 empty] | 2023-02-10 |  | 2024-03-24 |  | EXP | [8 empty] | 2023-05-25 | Connected |  | No
National Grid | SHIRLEY | 489990 | 1464 | 11.31 | Solar | 01_201W1 | 2023-01-06 06:27 | 2023-01-09 | 0 | 0 | 0 | 2023-01-09 | 2023-02-08 | 23 | 3 | 20 | [20 empty] | 2023-02-10 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | DRACUT | 490227 | 1826 | 7.6 | Solar | 14_21L1 | 2023-01-06 09:57 | 2023-01-09 | 1 | 0 | 1 | 2023-01-10 | 2023-02-13 | 24 | 0 | 24 | [20 empty] | 2023-02-13 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BRIDGEWATER | 489549 | 2324 | 67.3 | Solar | 07_912W73 | 2023-01-06 10:06 | 2023-01-09 | 47 | 37 | 10 | [10 empty] | 2023-03-17 | 2023-04-13 | 27 | 7 | 20 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 487520 | 1507 | 8.7 | Solar | 01_415L2 | 2023-01-06 14:20 | 2023-01-09 | 4 | 0 | 4 | 2023-01-13 | 2023-02-14 | 22 | 0 | 22 | [20 empty] | 2023-02-16 | 2023-01-06 14:46 | 2024-09-27 |  | EXP | [8 empty] | 2023-10-04 | Connected |  | Yes
National Grid | NANTUCKET | 485414 | 2554 | 100 | Solar | 04_101L7 | 2023-01-06 14:46 | 2023-01-09 | 21 | 11 | 10 | 2023-02-07 | 2023-03-14 | 25 | 0 | 25 | 2023-04-04 | 2023-05-16 | 30 | 0 | 30 | [5 empty] | 2023-04-04 | 2023-05-16 | 30 | 0 | 30 | [5 empty] | 2023-05-30 |  | 2024-06-09 |  | EXP | [9 empty] | Design |  | No
National Grid | BRIDGEWATER | 489538 | 2324 | 80 | Solar | 07_912W73 | 2023-01-06 15:49 | 2023-01-09 | 47 | 37 | 10 | [10 empty] | 2023-03-17 | 2023-06-13 | 61 | 46 | 15 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | HANOVER | 469930 | 2339 | 11300 | Other | 07_910W51 | 2023-01-06 16:00 | 2023-01-09 | 37 | 27 | 10 | [10 empty] | 2023-03-03 | 2023-05-04 | 45 | 25 | 20 | [14 empty] | STD | [9 empty] | Pending Withdraw |  | No
National Grid | ATHOL | 490479 | 1331 | 15.08 | Solar | 09_702W1 | 2023-01-06 16:14 | 2023-01-09 | 1 | 0 | 1 | 2023-01-10 | 2023-02-10 | 23 | 0 | 23 | [20 empty] | 2023-02-27 | 2023-01-09 04:57 | 2024-03-24 |  | EXP | [8 empty] | 2023-07-31 | Connected |  | Yes
National Grid | DIGHTON | 480346 | 2715 | 5.22 | Solar | 05_19W73 | 2023-01-09 04:57 | 2023-01-10 | 13 | 10 | 3 | 2023-01-30 | 2023-02-24 | 19 | 0 | 19 | [20 empty] | 2023-03-01 |  | 2024-06-23 | Yes | EXP | [8 empty] | 2023-08-01 | Connected |  | Yes
National Grid | COHASSET | 490600 | 2025 | 20.01 | Solar | 07_96W41 | 2023-01-09 08:11 | 2023-01-10 | 8 | 7 | 1 | 2023-01-20 | 2023-02-15 | 19 | 0 | 19 | [20 empty] | 2023-02-16 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EAST BRIDGEWATER | 490718 | 2333 | 17.6 | Solar | 07_91W41 | 2023-01-09 11:34 | 2023-01-10 | 2 | 1 | 1 | 2023-01-11 | 2023-02-07 | 19 | 0 | 19 | [20 empty] | 2023-02-08 |  | 2024-02-13 |  | EXP | [8 empty] | 2023-11-13 | Connected |  | No
National Grid | ADAMS | 480218 | 1220 | 7.6 | Solar | 09_1021W1 | 2023-01-09 14:01 | 2023-01-10 | 1 | 0 | 1 | 2023-01-11 | 2023-02-15 | 25 | 0 | 25 | [20 empty] | 2023-02-17 | 2023-01-09 16:54 | 2024-10-25 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SWANSEA | 489747 | 2777 | 10 | Solar | 05_11W81 | 2023-01-09 16:54 | 2023-01-10 | 2 | 0 | 2 | 2023-01-12 | 2023-02-24 | 31 | 12 | 19 | [20 empty] | 2023-02-28 | 2023-01-10 10:03 | 2024-05-03 |  | EXP |  | 2023-04-11 | 2023-05-02 | 22 | 0 | 22 |  |  | 2023-06-21 | Connected |  | Yes
National Grid | NORTH DIGHTON | 484704 | 2764 | 8.7 | Solar | 05_19W73 | 2023-01-10 10:03 | 2023-01-11 | 1 | 0 | 1 | 2023-01-12 | 2023-02-06 | 17 | 3 | 14 | [20 empty] | 2023-02-08 | 2023-01-10 11:20 | 2024-04-14 | Yes | EXP |  | 2023-03-04 | 2023-04-13 | 41 | 0 | 41 |  |  | 2023-07-17 | Connected |  | No
National Grid | LYNN | 488328 | 1904 | 6 | Solar | 12_29W3 | 2023-01-10 11:20 | 2023-01-11 | 1 | 0 | 1 | 2023-01-12 | 2023-02-16 | 25 | 0 | 25 | [20 empty] | 2023-02-21 |  | 2024-06-13 | Yes | EXP |  | 2023-06-09 | 2023-06-09 | 1 | 0 | 1 |  |  | 2023-07-11 | Connected |  | No
National Grid | WORCESTER | 476456 | 1606 | 6 | Solar | 01_24W3 | 2023-01-10 13:41 | 2023-01-11 | 1 | 0 | 1 | 2023-01-12 | 2023-02-14 | 23 | 0 | 23 | [20 empty] | 2023-02-17 | 2023-01-10 15:17 | 2024-02-27 |  | EXP | [8 empty] | 2023-04-13 | Connected |  | No
National Grid | SOMERSET | 485618 | 2725 | 10 | Solar | 05_11W84 | 2023-01-10 15:17 | 2023-01-11 | 1 | 0 | 1 | 2023-01-12 | 2023-03-02 | 35 | 16 | 19 | [20 empty] | 2023-04-04 | 2023-01-10 20:11 | 2024-04-22 | Yes | EXP |  | 2023-07-04 | 2023-07-12 | 9 | 0 | 9 |  |  |  | Withdrawn |  | Yes
National Grid | EASTON | 489931 | 2356 | 13 | Solar | 07_92W78 | 2023-01-10 20:11 | 2023-01-11 | 5 | 4 | 1 | 2023-01-18 | 2023-03-29 | 50 | 30 | 20 | [20 empty] | 2023-03-29 |  | 2024-07-17 | Yes | EXP |  | 2023-08-10 | 2023-09-08 | 30 | 0 | 30 |  |  | 2023-09-15 | Connected |  | No
National Grid | HOPEDALE | 478522 | 1747 | 7.6 | Solar | 05_335W9 | 2023-01-11 08:28 | 2023-01-12 | 1 | 0 | 1 | 2023-01-13 | 2023-02-09 | 19 | 0 | 19 | [20 empty] | 2023-02-14 |  | 2024-08-09 |  | EXP | [8 empty] | 2023-08-17 | Connected |  | Yes
National Grid | ANDOVER | 486898 | 1810 | 16 | Solar | 14_59L6 | 2023-01-11 08:31 | 2023-01-12 | 9 | 8 | 1 | 2023-01-25 | 2023-02-21 | 19 | 0 | 19 | [20 empty] | 2023-02-21 |  | 2024-08-01 |  | EXP | [8 empty] | 2023-08-03 | Connected |  | No
National Grid | BROCKTON | 471403 | 2302 | 6.144 | Solar | 07_69J1 | 2023-01-11 09:12 | 2023-01-12 | 2 | 0 | 2 | 2023-01-17 | 2023-02-16 | 23 | 0 | 23 | [20 empty] | 2023-02-22 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MARLBOROUGH | 491445 | 1752 | 15.2 | Solar | 05_311W3 | 2023-01-11 09:51 | 2023-01-12 | 1 | 0 | 1 | 2023-01-13 | 2023-03-23 | 47 | 25 | 22 | 2023-04-25 | 2023-05-31 | 13 | 0 | 13 | [5 empty] | 2023-04-25 | 2023-05-31 | 13 | 0 | 13 | [5 empty] | 2023-05-16 |  | 2024-08-16 |  | EXP |  | 2023-07-26 | 2023-08-10 | 16 | 0 | 16 |  |  | 2023-10-16 | Connected |  | Yes
National Grid | STOUGHTON | 491489 | 2072 | 7.6 | Solar | 07_94W43 | 2023-01-11 10:59 | 2023-01-12 | 1 | 0 | 1 | 2023-01-13 | 2023-03-03 | 34 | 14 | 20 | [20 empty] | 2023-03-03 |  | 2024-05-10 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | WHITMAN | 483153 | 2382 | 13.63 | Solar | 07_93W42 | 2023-01-11 11:03 | 2023-01-12 | 1 | 0 | 1 | 2023-01-13 | 2023-02-14 | 22 | 0 | 22 | [20 empty] | 2023-02-17 |  | 2024-03-26 |  | EXP | [8 empty] | 2023-04-25 | Connected |  | No
National Grid | BOLTON | 488595 | 1740 | 15.95 | Solar | 05_318W3 | 2023-01-11 11:30 | 2023-01-12 | 12 | 11 | 1 | 2023-01-30 | 2023-02-24 | 19 | 0 | 19 | [20 empty] | 2023-02-24 |  | 2024-04-28 |  | EXP | [8 empty] | 2023-08-31 | Connected |  | No
National Grid | REVERE | 487786 | 2151 | 6 | Solar | 12_35J3 | 2023-01-11 12:01 | 2023-01-12 | 2 | 1 | 1 | 2023-01-13 | 2023-02-14 | 22 | 0 | 22 | [20 empty] | 2023-02-17 | 2023-01-11 17:38 | 2024-02-22 |  | EXP | [8 empty] | 2023-05-01 | Connected |  | No
National Grid | BLACKSTONE | 491574 | 1504 | 20 | Solar | 05_108W60 | 2023-01-11 17:38 | 2023-01-12 | 3 | 2 | 1 | 2023-01-17 | 2023-02-21 | 26 | 7 | 19 | [20 empty] | 2023-02-22 |  | 2024-03-02 | Yes | EXP |  | 2023-03-21 | 2023-04-22 | 33 | 0 | 33 |  |  | 2023-06-26 | Connected |  | No
National Grid | DUDLEY | 477663 | 1571 | 15.2 | Solar | 01_412L5 | 2023-01-12 07:45 | 2023-01-13 | 2 | 0 | 2 | 2023-01-18 | 2023-02-15 | 21 | 0 | 21 | [20 empty] | 2023-02-17 |  | 2024-03-19 |  | EXP | [8 empty] | 2023-03-24 | Connected |  | No
National Grid | BELCHERTOWN | 472374 | 1007 | 3 | Solar | 09_509L2 | 2023-01-12 10:09 | 2023-01-13 | 2 | 0 | 2 | 2023-01-18 | 2023-05-08 | 77 | 59 | 18 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | DRACUT | 483029 | 1826 | 4990 | Other | 14_78L3 | 2023-01-12 11:24 | 2023-01-13 | 23 | 13 | 10 | [10 empty] | 2023-02-16 | 2023-03-21 | 23 | 0 | 23 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SHIRLEY | 434882 | 1464 | 2400 | Solar | 01_227W3 | 2023-01-12 11:50 | 2023-01-13 | 70 | 61 | 9 | [10 empty] | 2023-04-26 | 2023-05-23 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | GLOUCESTER | 488780 | 1930 | 15.2 | Solar | 12_52L1 | 2023-01-12 12:51 | 2023-01-13 | 2 | 0 | 2 | 2023-01-18 | 2023-04-24 | 67 | 25 | 42 | [21 empty] | 2023-01-12 13:44 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ADAMS | 485106 | 1220 | 7.6 | Solar | 09_1021W2 | 2023-01-12 13:44 | 2023-01-13 | 2 | 0 | 2 | 2023-01-18 | 2023-02-15 | 22 | 3 | 19 | [20 empty] | 2023-02-17 |  | 2024-06-13 | Yes | EXP | [8 empty] | 2023-07-12 | Connected |  | No
National Grid | UXBRIDGE | 490668 | 1569 | 22.8 | Solar | 05_321W2 | 2023-01-12 13:51 | 2023-01-13 | 4 | 2 | 2 | 2023-01-20 | 2023-02-15 | 19 | 0 | 19 | [20 empty] | 2023-02-16 |  | 2024-02-17 |  | EXP | [8 empty] | 2023-05-02 | Connected |  | No
National Grid | STOUGHTON | 486030 | 2072 | 7.6 | Solar | 07_94W43 | 2023-01-12 15:05 | 2023-01-13 | 3 | 0 | 3 | 2023-01-19 | 2023-02-16 | 21 | 0 | 21 | [20 empty] | 2023-02-16 |  | 2024-02-17 |  | EXP | [8 empty] | 2023-05-12 | Connected |  | No
National Grid | SCITUATE | 491908 | 2066 | 41.17 | Solar | 07_915W82 | 2023-01-12 15:35 | 2023-01-13 | 4 | 1 | 3 | 2023-01-19 | 2023-03-21 | 43 | 23 | 20 | [21 empty] | 2023-01-13 10:21 |  |  | EXP | [9 empty] | Supplemental Review |  | No
National Grid | BROCKTON | 476015 | 2301 | 6 | Solar | 07_911W25 | 2023-01-13 10:21 | 2023-01-17 | 1 | 0 | 1 | 2023-01-18 | 2023-02-16 | 22 | 0 | 22 | [20 empty] | 2023-02-21 |  | 2024-11-17 | Yes | EXP |  | 2023-09-12 | 2023-10-11 | 30 | 0 | 30 |  |  | 2024-01-30 | Connected |  | No
National Grid | WESTFORD | 480047 | 1886 | 15.2 | Solar | 14_57L3 | 2023-01-13 13:23 | 2023-01-17 | 2 | 0 | 2 | 2023-01-19 | 2023-02-14 | 19 | 0 | 19 | [20 empty] | 2022-12-05 |  | 2024-02-21 |  | EXP | [8 empty] | 2023-06-01 | Connected |  | No
National Grid | ANDOVER | 489268 | 1810 | 22.75 | Solar | 14_62L2 | 2023-01-13 14:10 | 2023-01-17 | 3 | 1 | 2 | 2023-01-19 | 2023-02-14 | 19 | 0 | 19 | [20 empty] | 2023-02-15 |  | 2024-02-16 |  | EXP | [8 empty] | 2023-08-24 | Connected |  | No
National Grid | RANDOLPH | 479096 | 2368 | 6 | Solar | 07_5W3 | 2023-01-16 10:13 | 2023-01-17 | 1 | 0 | 1 | 2023-01-18 | 2023-02-13 | 19 | 0 | 19 | [20 empty] | 2023-02-16 |  | 2024-03-28 |  | EXP | [8 empty] | 2023-06-05 | Connected |  | No
National Grid | ANDOVER | 481649 | 1810 | 9.984 | Solar | 14_62L2 | 2023-01-16 10:56 | 2023-01-17 | 2 | 0 | 2 | 2023-01-19 | 2023-02-16 | 21 | 0 | 21 | [20 empty] | 2023-02-22 | 2023-01-16 15:21 | 2024-04-27 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | BELCHERTOWN | 483456 | 1007 | 10 | Solar | 09_509L1 | 2023-01-16 15:21 | 2023-01-17 | 1 | 0 | 1 | 2023-01-18 | 2023-03-20 | 43 | 24 | 19 | [20 empty] | 2023-03-22 |  | 2024-05-18 | Yes | EXP | [8 empty] | 2023-06-09 | Connected |  | No
National Grid | NANTUCKET | 492630 | 2554 | 21.638 | Solar | 04_101L7 | 2023-01-16 15:24 | 2023-01-17 | 2 | 0 | 2 | 2023-01-19 | 2023-02-14 | 19 | 0 | 19 | [20 empty] | 2023-02-15 | 2023-01-16 15:28 | 2024-03-04 |  | EXP | [8 empty] | 2023-06-02 | Connected |  | No
National Grid | METHUEN | 492624 | 1844 | 17.45 | Solar | 14_74L1 | 2023-01-16 15:28 | 2023-01-17 | 2 | 0 | 2 | 2023-01-19 | 2023-02-16 | 21 | 0 | 21 | [20 empty] | 2023-02-22 |  | 2024-05-15 | Yes | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | HALIFAX | 477830 | 2338 | 10 | Solar | 07_912W75 | 2023-01-16 15:53 | 2023-01-17 | 1 | 0 | 1 | 2023-01-18 | 2023-02-14 | 20 | 0 | 20 | [20 empty] | 2023-02-16 |  | 2024-04-22 |  | EXP | [8 empty] | 2023-06-07 | Connected |  | No
National Grid | EAST LONGMEADOW | 492771 | 1028 | 15.2 | Solar | 09_508L4 | 2023-01-17 09:36 | 2023-01-18 | 1 | 0 | 1 | 2023-01-19 | 2023-02-27 | 28 | 8 | 20 | [20 empty] | 2023-02-28 |  | 2024-03-06 |  | EXP | [8 empty] | 2023-07-17 | Connected |  | No
National Grid | CHELMSFORD | 482365 | 1824 | 7.6 | Solar | 14_70L3 | 2023-01-17 10:09 | 2023-01-18 | 2 | 0 | 2 | 2023-01-20 | 2023-02-17 | 21 | 0 | 21 | [20 empty] | 2023-02-23 |  | 2024-03-14 |  | EXP | [8 empty] | 2023-07-11 | Connected |  | No
National Grid | LOWELL | 480217 | 1854 | 7.6 | Solar | 14_77L1 | 2023-01-17 12:32 | 2023-01-18 | 1 | 0 | 1 | 2023-01-19 | 2023-02-15 | 21 | 2 | 19 | 2023-02-23 | 2023-03-22 | 20 | 0 | 20 | [5 empty] | 2023-02-23 | 2023-03-22 | 20 | 0 | 20 | [5 empty] | 2023-03-22 |  | 2024-03-24 |  | EXP | [8 empty] | 2023-05-31 | Connected |  | Yes
National Grid | PEPPERELL | 477267 | 1463 | 17.45 | Solar | 01_226L1 | 2023-01-17 14:59 | 2023-01-18 | 1 | 0 | 1 | 2023-01-19 | 2023-02-16 | 21 | 0 | 21 | [20 empty] | 2023-02-16 |  | 2024-02-21 |  | EXP | [8 empty] | 2023-05-30 | Connected |  | No
National Grid | WESTFORD | 437862 | 1886 | 7.6 | Solar | 14_73L2 | 2023-01-17 15:23 | 2023-01-18 | 2 | 0 | 2 | 2023-01-20 | 2023-11-13 | 204 | 184 | 20 | [21 empty] | 2023-01-17 16:29 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTMINSTER | 493004 | 1473 | 15.95 | Solar | 01_602W2 | 2023-01-17 16:29 | 2023-01-18 | 16 | 15 | 1 | 2023-02-09 | 2023-03-30 | 36 | 12 | 24 | [20 empty] | 2023-03-30 | 2023-01-17 16:33 | 2024-07-26 | Yes | EXP |  | 2023-08-15 | 2023-09-22 | 39 | 0 | 39 |  |  | 2023-10-03 | Connected |  | No
National Grid | WARREN | 486284 | 1083 | 7.6 | Solar | 09_516L2 | 2023-01-17 16:33 | 2023-01-18 | 1 | 0 | 1 | 2023-01-19 | 2023-02-16 | 21 | 0 | 21 | [20 empty] | 2023-02-22 |  | 2024-11-14 | Yes | EXP | [8 empty] | 2024-03-05 | Connected |  | No
National Grid | METHUEN | 480100 | 1844 | 3.8 | Solar | 14_63L2 | 2023-01-17 17:16 | 2023-01-18 | 2 | 0 | 2 | 2023-01-20 | 2023-06-16 | 104 | 83 | 21 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FALL RIVER | 486948 | 2724 | 3 | Solar | 05_115W42 | 2023-01-17 17:35 | 2023-01-18 | 1 | 0 | 1 | 2023-01-19 | 2023-02-16 | 21 | 0 | 21 | [20 empty] | 2023-02-21 | 2023-01-18 12:43 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTON | 478397 | 2766 | 15 | Solar | 05_8L3 | 2023-01-18 12:43 | 2023-01-19 | 2 | 0 | 2 | 2023-01-23 | 2023-02-21 | 21 | 0 | 21 | [20 empty] | 2023-02-24 |  | 2024-04-18 |  | EXP |  | 2023-03-29 | 2023-04-13 | 16 | 0 | 16 |  |  | 2023-10-07 | Connected |  | No
National Grid | ANDOVER | 492260 | 1810 | 14.79 | Solar | 14_54L3 | 2023-01-18 12:52 | 2023-01-19 | 1 | 0 | 1 | [10 empty] | 2023-01-20 | 2023-12-08 | 222 | 204 | 18 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | FOXBOROUGH | 493291 | 2035 | 19 | Solar | 05_3424W1 | 2023-01-18 14:01 | 2023-01-19 | 1 | 0 | 1 | 2023-01-20 | 2023-02-15 | 19 | 0 | 19 | [20 empty] | 2023-02-16 | 2023-01-18 15:22 | 2024-02-17 |  | EXP | [8 empty] | 2023-05-16 | Connected |  | No
National Grid | METHUEN | 488617 | 1844 | 6 | Solar | 14_63L1 | 2023-01-18 15:22 | 2023-01-19 | 1 | 0 | 1 | 2023-01-20 | 2023-02-21 | 22 | 0 | 22 | [20 empty] | 2023-02-23 |  | 2024-07-02 | Yes | EXP |  | 2023-04-18 | 2023-06-30 | 74 | 0 | 74 |  |  | 2023-07-12 | Connected |  | No
National Grid | MILLBURY | 486689 | 1527 | 4999 | Other | 01_304W5 | 2023-01-19 09:47 | 2023-01-20 | 12 | 2 | 10 | [10 empty] | 2023-02-06 | 2023-03-27 | 35 | 16 | 19 | [14 empty] | STD | [9 empty] | Pending Withdraw |  | No
National Grid | BROCKTON | 485572 | 2302 | 4999 | Other | 07_91W40 | 2023-01-19 09:48 | 2023-01-20 | 12 | 2 | 10 | [10 empty] | 2023-02-06 | 2023-08-03 | 124 | 105 | 19 | [14 empty] | STD | [9 empty] | Pending Withdraw |  | No
National Grid | WESTFORD | 491393 | 1886 | 14.592 | Solar | 14_58L1 | 2023-01-19 09:52 | 2023-01-20 | 1 | 0 | 1 | 2023-01-23 | 2024-02-28 | 274 | 112 | 162 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LOWELL | 493495 | 1852 | 16680 | Hydro | 14_2386 | 2023-01-19 11:11 | 2023-01-20 | 60 | 51 | 9 | [10 empty] | 2023-04-18 | 2023-06-05 | 34 | 15 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | LYNN | 490857 | 1905 | 6 | Solar | 12_19W1 | 2023-01-19 15:13 | 2023-01-20 | 1 | 0 | 1 | 2023-01-23 | 2023-02-16 | 19 | 0 | 19 | [20 empty] | 2023-02-22 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SEEKONK | 486773 | 2771 | 8.12 | Solar | 05_7L5 | 2023-01-19 16:32 | 2023-01-20 | 9 | 7 | 2 | 2023-02-02 | 2023-03-03 | 21 | 4 | 17 | 2023-03-09 | 2023-03-24 | 8 | 0 | 8 | [5 empty] | 2023-03-09 | 2023-03-24 | 8 | 0 | 8 | [5 empty] | 2023-03-24 |  | 2024-10-03 |  | EXP |  | 2023-08-03 | 2023-10-04 | 63 | 0 | 63 |  |  | 2023-10-10 | Connected |  | Yes
National Grid | PEPPERELL | 493769 | 1463 | 24.94 | Solar | 01_226L1 | 2023-01-20 09:33 | 2023-01-23 | 2 | 1 | 1 | 2023-01-24 | 2023-02-23 | 23 | 3 | 20 | [20 empty] | 2023-02-24 |  | 2024-03-09 |  | EXP | [8 empty] | 2023-05-03 | Connected |  | No
National Grid | BELCHERTOWN | 478367 | 1007 | 3 | Solar | 09_509L2 | 2023-01-20 10:58 | 2023-01-23 | 1 | 0 | 1 | 2023-01-24 | 2023-04-17 | 59 | 34 | 25 | 2023-05-01 | 2023-05-31 | 2 | 0 | 2 | [5 empty] | 2023-05-01 | 2023-05-31 | 2 | 0 | 2 | [5 empty] | 2023-05-08 |  | 2024-06-27 |  | EXP | [8 empty] | 2023-07-31 | Connected |  | Yes
National Grid | SOUTHBRIDGE | 478408 | 1550 | 8.7 | Solar | 01_413L2 | 2023-01-20 12:04 | 2023-01-23 | 1 | 0 | 1 | 2023-01-24 | 2023-02-23 | 23 | 3 | 20 | [20 empty] | 2023-02-28 |  | 2024-04-03 |  | EXP | [8 empty] | 2023-08-25 | Connected |  | No
National Grid | ANDOVER | 485562 | 1810 | 15.2 | Solar | 14_50L1 | 2023-01-20 13:57 | 2023-01-23 | 5 | 5 | 0 | 2023-01-30 | 2023-08-04 | 136 | 25 | 111 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MILLBURY | 462891 | 1527 | 480 | Solar | 01_27W5 | 2023-01-20 14:10 | 2023-01-23 | 55 | 45 | 10 | [10 empty] | 2023-04-11 | 2023-05-09 | 20 | 0 | 20 | [11 empty] | 2023-01-20 14:38 |  |  | STD | [9 empty] | Study |  | Yes
National Grid | METHUEN | 491242 | 1844 | 7.83 | Solar | 14_43L4 | 2023-01-20 14:38 | 2023-01-23 | 3 | 1 | 2 | 2023-01-26 | 2023-02-21 | 18 | 0 | 18 | [20 empty] | 2023-02-23 |  | 2024-08-03 | Yes | EXP | [8 empty] | 2023-08-11 | Connected |  | No
National Grid | MELROSE | 491299 | 2176 | 6.48 | Solar | 12_25W4 | 2023-01-20 15:30 | 2023-01-23 | 2 | 0 | 2 | 2023-01-25 | 2023-02-23 | 21 | 0 | 21 | 2023-03-28 | 2023-06-27 | 63 | 0 | 63 | [5 empty] | 2023-03-28 | 2023-06-27 | 63 | 0 | 63 | [5 empty] | 2023-07-24 |  | 2024-11-01 |  | EXP | [8 empty] | 2023-11-15 | Connected |  | No
National Grid | PLAINVILLE | 493141 | 2762 | 15.2 | Solar | 05_3451W2 | 2023-01-23 09:57 | 2023-01-24 | 2 | 1 | 1 | 2023-01-25 | 2023-02-23 | 21 | 0 | 21 | [20 empty] | 2023-02-23 |  | 2024-02-27 |  | EXP | [8 empty] | 2023-08-18 | Connected |  | No
National Grid | BELLINGHAM | 489055 | 2019 | 10 | Solar | 05_108W60 | 2023-01-23 10:11 | 2023-01-24 | 2 | 0 | 2 | 2023-01-26 | 2023-02-07 | 10 | 0 | 10 | [21 empty] | 2023-01-23 10:21 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BLACKSTONE | 478954 | 1504 | 10 | Solar | 05_108W60 | 2023-01-23 10:21 | 2023-01-24 | 1 | 0 | 1 | 2023-01-25 | 2023-02-21 | 19 | 0 | 19 | [20 empty] | 2023-02-24 |  | 2024-04-18 | Yes | EXP |  | 2023-03-21 | 2023-04-19 | 30 | 0 | 30 |  |  | 2023-07-17 | Connected |  | No
National Grid | FALL RIVER | 487714 | 2720 | 3.8 | Solar | 05_28W50 | 2023-01-23 10:27 | 2023-01-24 | 1 | 0 | 1 | 2023-01-25 | 2023-02-22 | 20 | 0 | 20 | [20 empty] | 2023-02-27 | 2023-01-23 10:33 | 2024-03-23 |  | EXP | [8 empty] | 2023-05-18 | Connected |  | No
National Grid | HAVERHILL | 491622 | 1830 | 6 | Solar | 14_76L3 | 2023-01-23 10:33 | 2023-01-24 | 2 | 0 | 2 | 2023-01-26 | 2023-02-21 | 18 | 0 | 18 | [20 empty] | 2023-02-23 | 2023-01-23 13:37 | 2024-09-04 | Yes | EXP |  | 2023-07-01 | 2023-09-05 | 67 | 0 | 67 |  |  | 2023-09-18 | Connected |  | Yes
National Grid | QUINCY | 493396 | 2169 | 7.6 | Solar | 07_1W2 | 2023-01-23 13:37 | 2023-01-24 | 2 | 0 | 2 | 2023-01-26 | 2023-03-22 | 39 | 15 | 24 | [20 empty] | 2023-03-23 |  | 2024-07-06 | Yes | EXP | [8 empty] | 2023-08-17 | Connected |  | Yes
National Grid | PLAINVILLE | 490027 | 2762 | 15.2 | Solar | 05_3451W3 | 2023-01-23 14:19 | 2023-01-24 | 3 | 2 | 1 | 2023-01-26 | 2023-02-21 | 18 | 0 | 18 | [20 empty] | 2023-02-22 |  | 2024-08-18 |  | EXP | [8 empty] | 2023-09-25 | Connected |  | No
National Grid | SOUTH EASTON | 494331 | 2375 | 25 | Solar | 07_92W54 | 2023-01-23 15:34 | 2023-01-24 | 1 | 0 | 1 | 2023-01-25 | 2023-02-23 | 21 | 0 | 21 | [20 empty] | 2023-02-24 |  | 2024-07-31 |  | EXP | [8 empty] | 2023-08-25 | Connected |  | No
National Grid | ANDOVER | 492109 | 1810 | 9.86 | Solar | 14_50L3 | 2023-01-24 08:38 | 2023-01-25 | 10 | 9 | 1 | 2023-02-07 | 2023-03-08 | 21 | 0 | 21 | [20 empty] | 2023-03-09 | 2023-01-24 09:37 | 2024-04-04 |  | EXP | [8 empty] | 2023-09-28 | Connected |  | No
National Grid | NORTHAMPTON | 487983 | 1062 | 10 | Solar | 09_909W4 | 2023-01-24 09:37 | 2023-01-25 | 2 | 0 | 2 | 2023-01-27 | 2023-02-21 | 17 | 0 | 17 | [20 empty] | 2023-02-24 | 2023-01-24 11:08 | 2024-08-23 | Yes | EXP |  | 2023-07-28 | 2023-07-27 | 0 | 0 | 0 |  |  | 2023-08-31 | Connected |  | No
National Grid | RANDOLPH | 490321 | 2368 | 6 | Solar | 07_97W2 | 2023-01-24 11:08 | 2023-01-25 | 3 | 0 | 3 | 2023-01-30 | 2023-02-24 | 19 | 0 | 19 | [20 empty] | 2023-03-01 | 2023-01-24 11:24 | 2024-09-07 | Yes | EXP |  | 2023-08-17 | 2023-09-01 | 16 | 0 | 16 |  |  | 2023-09-18 | Connected |  | Yes
National Grid | ATTLEBORO | 470212 | 2703 | 6 | Solar | 05_1J1 | 2023-01-24 11:24 | 2023-01-25 | 2 | 0 | 2 | 2023-01-27 | 2023-02-24 | 20 | 0 | 20 | [20 empty] | 2023-03-02 |  | 2024-06-07 | Yes | EXP |  | 2023-05-16 | 2023-06-08 | 24 | 0 | 24 |  |  | 2023-07-10 | Connected |  | No
National Grid | BROCKTON | 494553 | 2301 | 19 | Solar | 07_94W43 | 2023-01-24 11:56 | 2023-01-25 | 2 | 1 | 1 | 2023-01-26 | 2023-02-23 | 20 | 0 | 20 | [20 empty] | 2023-02-24 |  | 2024-03-07 |  | EXP | [8 empty] | 2023-06-15 | Connected |  | No
National Grid | WORCESTER | 494547 | 1602 | 18.432 | Solar | 01_23W4 | 2023-01-24 12:05 | 2023-01-25 | 85 | 81 | 4 | [10 empty] | 2023-05-26 | 2023-07-12 | 31 | 7 | 24 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH ANDOVER | 492288 | 1845 | 3.8 | Solar | 14_71L3 | 2023-01-24 15:24 | 2023-01-25 | 3 | 0 | 3 | 2023-01-30 | 2023-03-15 | 33 | 14 | 19 | 2023-04-18 | 2023-05-16 | 6 | 0 | 6 | [5 empty] | 2023-04-18 | 2023-05-16 | 6 | 0 | 6 | [5 empty] | 2023-05-01 |  | 2024-11-29 |  | EXP |  | 2023-08-09 | 2023-12-28 | 142 | 3 | 139 |  |  | 2024-01-05 | Connected |  | No
National Grid | BROCKTON | 494818 | 2301 | 19 | Solar | 07_797W19 | 2023-01-25 08:11 | 2023-01-26 | 5 | 3 | 2 | 2023-02-01 | 2023-03-06 | 23 | 0 | 23 | [20 empty] | 2023-03-07 |  | 2024-03-06 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | AYER | 477550 | 1432 | 7.83 | Solar | 01_201W4 | 2023-01-25 10:05 | 2023-01-26 | 12 | 10 | 2 | 2023-02-10 | 2023-03-15 | 23 | 0 | 23 | [20 empty] | 2023-03-16 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MARLBOROUGH | 488924 | 1752 | 6.09 | Solar | 05_311W2 | 2023-01-25 10:22 | 2023-01-26 | 5 | 3 | 2 | 2023-02-01 | 2023-02-28 | 19 | 0 | 19 | [20 empty] | 2023-03-06 |  | 2024-03-19 |  | EXP | [8 empty] | 2023-10-23 | Connected |  | No
National Grid | LAWRENCE | 477774 | 1843 | 11.89 | Solar | 14_61L3 | 2023-01-25 12:50 | 2023-01-26 | 1 | 0 | 1 | 2023-01-27 | 2023-02-24 | 20 | 0 | 20 | [20 empty] | 2023-03-01 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FALL RIVER | 456820 | 2720 | 6 | Solar | 05_106W81 | 2023-01-26 09:47 | 2023-01-27 | 65 | 65 | 0 | 2023-05-03 | 2023-06-02 | 22 | 0 | 22 | [20 empty] | 2023-06-06 |  | 2024-06-07 |  | EXP | [8 empty] | 2023-06-29 | Connected |  | No
National Grid | RANDOLPH | 492308 | 2368 | 6 | Solar | 07_97W2 | 2023-01-26 10:38 | 2023-01-27 | 1 | 0 | 1 | 2023-01-30 | 2024-02-20 | 263 | 25 | 238 | [21 empty] | 2023-01-26 10:44 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SWANSEA | 494490 | 2777 | 10 | Solar | 05_11W84 | 2023-01-26 10:44 | 2023-01-27 | 2 | 0 | 2 | 2023-01-31 | 2023-02-27 | 19 | 2 | 17 | [20 empty] | 2023-03-02 | 2023-01-26 10:56 | 2024-09-14 | Yes | EXP |  | 2023-06-24 | 2023-09-14 | 83 | 0 | 83 |  |  | 2023-09-20 | Connected |  | No
National Grid | BROCKTON | 476961 | 2301 | 10 | Solar | 07_91W48 | 2023-01-26 10:56 | 2023-01-27 | 2 | 0 | 2 | 2023-01-31 | 2023-03-07 | 25 | 0 | 25 | [20 empty] | 2023-03-08 |  | 2024-06-23 | Yes | EXP |  | 2023-06-22 | 2023-06-21 | 0 | 0 | 0 |  |  |  | Completion Documents |  | Yes
National Grid | SOUTH EASTON | 484048 | 2375 | 20 | Solar | 07_92W79 | 2023-01-26 11:17 | 2023-01-27 | 4 | 3 | 1 | 2023-02-01 | 2023-02-28 | 19 | 0 | 19 | [20 empty] | 2023-03-01 |  | 2024-03-21 |  | EXP | [8 empty] | 2023-05-10 | Connected |  | No
National Grid | FOXBOROUGH | 495226 | 2035 | 15.2 | Solar | 05_3422W3 | 2023-01-26 11:21 | 2023-01-27 | 55 | 55 | 0 | 2023-04-18 | 2023-08-09 | 78 | 57 | 21 | [20 empty] | 2023-08-09 |  | 2024-11-18 |  | EXP | [8 empty] | 2024-03-25 | Connected |  | No
National Grid | NORTHAMPTON | 494316 | 1060 | 5 | Solar | 09_901W3 | 2023-01-26 15:19 | 2023-01-27 | 1 | 0 | 1 | 2023-01-30 | 2023-02-27 | 20 | 2 | 18 | 2023-03-02 | 2023-03-23 | 13 | 0 | 13 | [5 empty] | 2023-03-02 | 2023-03-23 | 13 | 0 | 13 | [5 empty] | 2023-03-23 |  | 2024-07-24 |  | EXP |  | 2023-07-12 | 2023-07-25 | 14 | 0 | 14 |  |  | 2023-08-03 | Connected |  | Yes
National Grid | WARE | 491099 | 1082 | 11.02 | Solar | 09_501L2 | 2023-01-26 18:21 | 2023-01-27 | 21 | 20 | 1 | 2023-02-27 | 2023-06-09 | 72 | 49 | 23 | [20 empty] | 2023-06-13 |  | 2024-09-08 |  | EXP | [8 empty] | 2024-02-01 | Connected |  | No
National Grid | WESTMINSTER | 487745 | 1473 | 2000 | Solar | 01_610W3 | 2023-01-27 08:19 | 2023-01-30 | 18 | 8 | 10 | [10 empty] | 2023-02-23 | 2023-03-23 | 21 | 0 | 21 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | HOLBROOK | 487663 | 2343 | 960 | Solar | 07_10W1 | 2023-01-27 08:21 | 2023-01-30 | 17 | 8 | 9 | [10 empty] | 2023-02-23 | 2023-03-23 | 21 | 0 | 21 | [10 empty] | 2023-08-15 |  |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | TOPSFIELD | 495464 | 1983 | 16.53 | Solar | 12_26L1 | 2023-01-27 08:44 | 2023-01-30 | 5 | 2 | 3 | 2023-02-06 | 2023-03-01 | 17 | 0 | 17 | [20 empty] | 2023-03-03 | 2023-01-27 09:06 | 2024-03-08 |  | EXP | [8 empty] | 2023-04-08 | Connected |  | No
National Grid | UPTON | 417539 | 1568 | 7.6 | Solar | 05_335W3 | 2023-01-27 09:06 | 2023-01-30 | 1 | 0 | 1 | 2023-01-31 | 2023-03-07 | 25 | 0 | 25 | [20 empty] | 2023-03-14 |  | 2024-06-21 | Yes | EXP | [8 empty] | 2023-07-05 | Connected |  | Yes
National Grid | NORWELL | 495553 | 2061 | 23.808 | Solar | 07_96W44 | 2023-01-27 12:10 | 2023-01-30 | 27 | 26 | 1 | [10 empty] | 2023-03-08 | 2023-07-12 | 86 | 64 | 22 | [10 empty] | 2024-02-08 | 2023-01-27 14:17 |  |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | GREAT BARRINGTON | 490673 | 1230 | 15.2 | Solar | 09_1109W2 | 2023-01-27 14:17 | 2023-01-30 | 1 | 0 | 1 | 2023-01-31 | 2023-02-27 | 19 | 0 | 19 | [20 empty] | 2023-03-01 |  | 2024-05-22 | Yes | EXP | [8 empty] | 2023-08-10 | Connected |  | No
National Grid | BOLTON | 495716 | 1740 | 20 | Solar | 01_225W1 | 2023-01-27 17:38 | 2023-01-30 | 4 | 3 | 1 | 2023-02-02 | 2023-03-07 | 23 | 0 | 23 | [20 empty] | 2023-03-08 |  | 2024-03-14 |  | EXP | [8 empty] | 2024-02-16 | Connected |  | No
National Grid | MANCHESTER | 495086 | 1944 | 16.67 | Solar | 12_51T1 | 2023-01-27 18:13 | 2023-01-30 | 33 | 32 | 1 | 2023-03-17 | 2023-04-06 | 15 | 0 | 15 | [20 empty] | 2023-04-07 |  | 2024-06-17 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | MONSON | 494712 | 1057 | 240 | Solar | 09_139L1 | 2023-01-28 11:00 | 2023-01-30 | 0 | 0 | 0 | [10 empty] | 2023-06-05 | 2023-06-30 | 19 | 0 | 19 | [11 empty] | 2023-01-30 02:04 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTHAMPTON | 458403 | 1062 | 10 | Solar | 09_909W4 | 2023-01-30 02:04 | 2023-01-31 | 11 | 9 | 2 | 2023-02-15 | 2023-03-17 | 22 | 0 | 22 | [20 empty] | 2023-03-22 |  | 2024-10-25 | Yes | EXP |  | 2023-10-10 | 2023-10-16 | 7 | 0 | 7 |  |  | 2023-11-16 | Connected |  | Yes
National Grid | WEBSTER | 443970 | 1570 | 4999 | Other | 01_412L4 | 2023-01-30 09:48 | 2023-01-31 | 13 | 3 | 10 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | WILBRAHAM | 476868 | 1095 | 7.6 | Solar | 09_507L3 | 2023-01-30 13:21 | 2023-01-31 | 8 | 6 | 2 | 2023-02-10 | 2023-05-30 | 75 | 53 | 22 | [20 empty] | 2023-06-01 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SWANSEA | 443980 | 2777 | 4999 | Other | 05_11W85 | 2023-01-30 13:59 | 2023-01-31 | 12 | 2 | 10 | [10 empty] | 2023-02-22 | 2023-03-21 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SOMERSET | 443979 | 2726 | 4999 | Other | 05_11W82 | 2023-01-30 14:29 | 2023-01-31 | 13 | 3 | 10 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | BROOKFIELD | 496520 | 1506 | 15.2 | Solar | 01_525L2 | 2023-01-30 14:40 | 2023-01-31 | 15 | 14 | 1 | 2023-02-21 | 2023-03-23 | 23 | 0 | 23 | [20 empty] | 2023-03-23 |  | 2024-04-03 |  | EXP | [8 empty] | 2023-07-26 | Connected |  | No
National Grid | BLACKSTONE | 480715 | 1504 | 10 | Solar | 05_321W9 | 2023-01-30 16:50 | 2023-01-31 | 2 | 0 | 2 | 2023-02-02 | 2023-03-08 | 24 | 0 | 24 | [20 empty] | 2023-03-13 | 2023-01-31 08:34 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTON | 493344 | 2766 | 10 | Solar | 05_4L2 | 2023-01-31 08:34 | 2023-02-01 | 1 | 0 | 1 | 2023-02-02 | 2023-03-07 | 23 | 0 | 23 | [20 empty] | 2023-03-14 |  | 2024-09-19 | Yes | EXP |  | 2023-09-20 | 2023-11-06 | 48 | 0 | 48 |  |  | 2024-01-18 | Connected |  | No
National Grid | WEST STOCKBRIDGE | 461068 | 1266 | 30 | Solar | 09_1109W3 | 2023-01-31 08:54 | 2023-02-01 | 6 | 5 | 1 | 2023-02-09 | 2023-05-18 | 69 | 48 | 21 | [20 empty] | 2023-05-18 |  | 2024-07-11 |  | EXP | [8 empty] | 2023-07-31 | Connected |  | No
National Grid | ATTLEBORO | 484658 | 2703 | 6 | Solar | 05_2J1 | 2023-01-31 09:47 | 2023-02-01 | 1 | 0 | 1 | 2023-02-02 | 2023-02-28 | 19 | 1 | 18 | [20 empty] | 2023-03-06 | 2023-01-31 10:01 | 2024-03-18 |  | EXP | [8 empty] | 2023-08-11 | Connected |  | No
National Grid | ATTLEBORO | 484664 | 2703 | 6 | Solar | 05_2J1 | 2023-01-31 10:01 | 2023-02-01 | 1 | 0 | 1 | 2023-02-02 | 2023-04-11 | 48 | 25 | 23 | [20 empty] | 2023-04-13 |  | 2024-07-26 | Yes | EXP |  | 2023-07-01 | 2023-07-27 | 27 | 0 | 27 |  |  | 2023-08-02 | Connected |  | No
National Grid | QUINCY | 489665 | 2169 | 499.9 | Solar | 07_3W1 | 2023-01-31 14:25 | 2023-02-01 | 117 | 99 | 18 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SEEKONK | 489659 | 2771 | 499.9 | Solar | 05_7L2 | 2023-01-31 14:27 | 2023-02-01 | 116 | 70 | 46 | [29 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | HALIFAX | 493922 | 2338 | 10 | Solar | 07_912W75 | 2023-01-31 16:53 | 2023-02-01 | 2 | 0 | 2 | 2023-02-03 | 2023-03-08 | 23 | 0 | 23 | [20 empty] | 2023-03-13 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HOLBROOK | 493719 | 2343 | 10 | Solar | 07_2W1 | 2023-01-31 17:55 | 2023-02-01 | 5 | 4 | 1 | 2023-02-08 | 2023-03-15 | 25 | 0 | 25 | [20 empty] | 2023-03-15 | 2023-02-01 02:24 | 2024-03-30 |  | EXP | [8 empty] | 2023-08-02 | Connected |  | No
National Grid | CLINTON | 497623 | 1510 | 18.27 | Solar | 01_216W5 | 2023-02-01 02:24 | 2023-02-02 | 3 | 2 | 1 | 2023-02-06 | 2023-03-03 | 19 | 2 | 17 | [20 empty] | 2023-03-03 | 2023-02-01 08:12 | 2024-03-05 | Yes | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEOMINSTER | 491913 | 1453 | 3.8 | Solar | 01_225W3 | 2023-02-01 08:12 | 2023-02-02 | 1 | 0 | 1 | 2023-02-03 | 2023-03-22 | 34 | 17 | 17 | [20 empty] | 2023-03-27 |  | 2024-06-07 | Yes | EXP |  | 2023-05-02 | 2023-06-08 | 38 | 0 | 38 |  |  | 2023-08-10 | Connected |  | No
National Grid | LEOMINSTER | 490204 | 1453 | 7.68 | Solar | 01_225W4 | 2023-02-01 08:17 | 2023-02-02 | 1 | 0 | 1 | 2023-02-03 | 2023-02-28 | 17 | 0 | 17 | [20 empty] | 2023-03-06 | 2023-02-01 09:51 | 2024-03-27 |  | EXP | [8 empty] | 2023-07-12 | Connected |  | Yes
National Grid | NORTHBOROUGH | 492962 | 1532 | 14.5 | Solar | 05_313W1 | 2023-02-01 09:51 | 2023-02-02 | 1 | 0 | 1 | 2023-02-03 | 2023-03-08 | 23 | 0 | 23 | [20 empty] | 2023-03-14 |  | 2024-09-08 | Yes | EXP |  | 2023-05-11 | 2023-09-06 | 119 | 0 | 119 |  |  | 2024-01-27 | Connected |  | No
National Grid | WESTFORD | 497827 | 1886 | 15.2 | Solar | 14_57L3 | 2023-02-01 10:19 | 2023-02-02 | 1 | 0 | 1 | 2023-02-03 | 2023-03-16 | 30 | 12 | 18 | 2023-04-10 | 2023-05-15 | 6 | 0 | 6 | [5 empty] | 2023-04-10 | 2023-05-15 | 6 | 0 | 6 | [5 empty] | 2023-04-19 |  | 2024-11-29 |  | EXP |  | 2023-08-31 | 2024-02-27 | 181 | 3 | 178 |  |  | 2024-03-07 | Connected |  | No
National Grid | LYNN | 487065 | 1902 | 19 | Solar | 12_12J904 | 2023-02-01 10:45 | 2023-02-02 | 1 | 0 | 1 | 2023-02-03 | 2023-03-08 | 23 | 0 | 23 | [20 empty] | 2023-03-08 |  | 2024-04-03 |  | EXP | [8 empty] | 2023-08-16 | Connected |  | No
National Grid | BROCKTON | 471429 | 2301 | 166.6 | Solar | 07_911W25 | 2023-02-01 12:14 | 2023-02-02 | 131 | 121 | 10 | 2023-08-14 |  | 167 | 127 | 40 | [21 empty] | 2023-02-01 13:14 |  |  | EXP | [9 empty] | Screening |  | No
National Grid | EAST LONGMEADOW | 493740 | 1028 | 6 | Solar | 09_508L4 | 2023-02-01 13:14 | 2023-02-02 | 2 | 0 | 2 | 2023-02-06 | 2023-03-09 | 23 | 0 | 23 | [20 empty] | 2023-03-16 | 2023-02-01 14:20 | 2024-07-31 | Yes | EXP |  | 2023-07-19 | 2023-08-01 | 14 | 0 | 14 |  |  | 2023-08-10 | Connected |  | No
National Grid | FALL RIVER | 492560 | 2721 | 7.6 | Solar | 05_115W53 | 2023-02-01 14:20 | 2023-02-02 | 1 | 0 | 1 | 2023-02-03 | 2023-03-01 | 18 | 0 | 18 | [20 empty] | 2023-03-06 |  | 2024-07-01 | Yes | EXP |  | 2023-07-13 | 2023-09-15 | 65 | 0 | 65 |  |  | 2023-11-21 | Connected |  | No
National Grid | BROCKTON | 492594 | 2302 | 6 | Solar | 07_91W43 | 2023-02-01 14:23 | 2023-02-02 | 2 | 0 | 2 | 2023-02-06 | 2023-03-08 | 22 | 0 | 22 | [20 empty] | 2023-03-16 |  | 2024-06-24 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | HAMPDEN | 498078 | 1036 | 17.6 | Battery Add-On | 09_139L1 | 2023-02-01 14:43 | 2023-02-02 | 1 | 0 | 1 | 2023-02-03 | 2023-03-08 | 23 | 0 | 23 | [20 empty] | 2023-03-08 | 2023-02-02 08:36 | 2024-04-15 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | LEOMINSTER | 491121 | 1453 | 9.86 | Solar | 01_207W6 | 2023-02-02 08:36 | 2023-02-03 | 2 | 0 | 2 | 2023-02-07 | 2023-03-03 | 18 | 1 | 17 | [20 empty] | 2023-03-07 | 2023-02-02 11:31 | 2024-05-31 | Yes | EXP |  | 2023-06-01 | 2023-05-31 | 0 | 0 | 0 |  |  | 2023-06-14 | Connected |  | No
National Grid | WILBRAHAM | 491959 | 1095 | 8.7 | Solar | 09_507L3 | 2023-02-02 11:31 | 2023-02-03 | 1 | 0 | 1 | 2023-02-06 | 2023-03-09 | 23 | 0 | 23 | [20 empty] | 2023-03-14 |  | 2024-10-13 | Yes | EXP |  | 2024-01-31 |  | 76 | 0 | 76 |  |  |  | Construction |  | Yes
National Grid | BELCHERTOWN | 498622 | 1007 | 12.6 | Solar | 09_509L1 | 2023-02-02 12:35 | 2023-02-03 | 90 | 88 | 2 | 2023-06-13 | 2023-07-10 | 18 | 0 | 18 | [20 empty] | 2023-07-11 |  | 2024-08-11 |  | EXP | [8 empty] | 2024-03-29 | Connected |  | No
National Grid | PEPPERELL | 498726 | 1463 | 12.47 | Solar | 01_226L2 | 2023-02-02 14:36 | 2023-02-03 | 2 | 0 | 2 | 2023-02-07 | 2023-03-08 | 21 | 0 | 21 | [20 empty] | 2023-03-09 |  | 2024-07-02 |  | EXP | [8 empty] | 2023-07-19 | Connected |  | Yes
National Grid | MENDON | 498788 | 1756 | 15.2 | Solar | 05_335W1 | 2023-02-02 15:26 | 2023-02-03 | 1 | 0 | 1 | 2023-02-06 | 2023-03-02 | 18 | 0 | 18 | [20 empty] | 2023-03-03 | 2023-02-03 00:14 | 2024-03-02 |  | EXP | [8 empty] | 2023-08-02 | Connected |  | No
National Grid | OXFORD | 495957 | 1540 | 6.96 | Solar | 01_406L3 | 2023-02-03 00:14 | 2023-02-06 | 3 | 1 | 2 | 2023-02-09 | 2023-03-13 | 22 | 0 | 22 | [20 empty] | 2023-03-14 |  | 2024-07-24 | Yes | EXP | [8 empty] | 2023-10-05 | Connected |  | No
National Grid | DUDLEY | 483367 | 1571 | 7.6 | Solar | 01_412L5 | 2023-02-03 09:38 | 2023-02-06 | 2 | 0 | 2 | 2023-02-08 | 2023-06-15 | 89 | 65 | 24 | [20 empty] | 2023-06-21 |  | 2024-08-01 |  | EXP | [8 empty] | 2023-08-10 | Connected |  | Yes
National Grid | NAHANT | 490037 | 1908 | 4.06 | Solar | 12_79J1 | 2023-02-03 10:05 | 2023-02-06 | 2 | 0 | 2 | 2023-02-08 | 2023-03-10 | 22 | 0 | 22 | [20 empty] | 2023-03-14 |  | 2024-04-08 |  | EXP | [8 empty] | 2023-06-24 | Connected |  | No
National Grid | LOWELL | 493449 | 1850 | 6 | Solar | 14_21L2 | 2023-02-03 13:06 | 2023-02-06 | 2 | 0 | 2 | 2023-02-08 | 2023-03-07 | 19 | 0 | 19 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ANDOVER | 499224 | 1810 | 15.08 | Solar | 14_59L6 | 2023-02-03 13:20 | 2023-02-06 | 2 | 0 | 2 | 2023-02-08 | 2023-03-15 | 25 | 0 | 25 | [20 empty] | 2023-03-20 | 2023-02-03 14:40 | 2024-09-27 |  | EXP | [8 empty] | 2023-10-05 | Connected |  | Yes
National Grid | BROCKTON | 493283 | 2302 | 5 | Solar | 07_91W40 | 2023-02-03 14:40 | 2023-02-06 | 2 | 0 | 2 | 2023-02-08 | 2023-03-10 | 22 | 0 | 22 | [20 empty] | 2023-03-17 |  | 2024-11-07 | Yes | EXP | [8 empty] | 2023-11-29 | Connected |  | No
National Grid | HALIFAX | 499293 | 2338 | 19 | Solar | 07_797W24 | 2023-02-03 15:18 | 2023-02-06 | 2 | 0 | 2 | 2023-02-08 | 2023-03-15 | 25 | 0 | 25 | [20 empty] | 2023-03-22 |  | 2024-06-21 |  | EXP | [8 empty] | 2023-08-04 | Connected |  | No
National Grid | FLORENCE | 498813 | 1062 | 6 | Solar | 09_909W1 | 2023-02-03 16:49 | 2023-02-06 | 1 | 0 | 1 | 2023-02-07 | 2023-05-25 | 66 | 48 | 18 | [20 empty] | 2023-05-26 |  | 2024-05-31 |  | EXP | [8 empty] | 2023-06-23 | Connected |  | No
National Grid | WORCESTER | 495536 | 1605 | 11.4 | Solar | 01_27W2 | 2023-02-04 14:14 | 2023-02-06 | 26 | 25 | 1 | 2023-03-14 | 2023-04-11 | 21 | 0 | 21 | [20 empty] | 2023-04-12 | 2023-02-06 11:08 | 2024-04-30 |  | EXP | [8 empty] | 2023-05-25 | Connected |  | No
National Grid | WESTMINSTER | 494286 | 1473 | 7.6 | Solar | 01_610W3 | 2023-02-06 11:08 | 2023-02-07 | 2 | 0 | 2 | 2023-02-09 | 2023-03-13 | 22 | 0 | 22 | [20 empty] | 2023-03-14 |  | 2024-07-06 | Yes | EXP | [8 empty] | 2023-08-14 | Connected |  | Yes
National Grid | GARDNER | 482643 | 1440 | 17.4 | Solar | 01_607W2 | 2023-02-06 12:02 | 2023-02-07 | 33 | 32 | 1 | 2023-03-27 | 2023-07-10 | 72 | 52 | 20 | [20 empty] | 2023-08-22 | 2023-02-06 14:03 | 2024-10-20 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | SHUTESBURY | 491819 | 1072 | 10 | Solar | 09_704W1 | 2023-02-06 14:03 | 2023-02-07 | 3 | 2 | 1 | 2023-02-09 | 2023-03-13 | 22 | 0 | 22 | [20 empty] | 2023-03-17 | 2023-02-06 14:48 | 2024-08-01 | Yes | EXP |  | 2023-06-07 | 2023-08-28 | 83 | 0 | 83 |  |  | 2023-09-06 | Connected |  | No
National Grid | LEOMINSTER | 487948 | 1453 | 10 | Solar | 01_207W6 | 2023-02-06 14:48 | 2023-02-07 | 2 | 0 | 2 | 2023-02-09 | 2023-03-13 | 22 | 0 | 22 | [20 empty] | 2023-03-14 |  | 2024-09-19 | Yes | EXP |  | 2023-10-18 | 2023-11-14 | 28 | 0 | 28 |  |  | 2024-01-31 | Connected |  | Yes
National Grid | BEVERLY | 439647 | 1915 | 480 | Solar | 12_51L1 | 2023-02-06 15:32 | 2023-02-07 | 8 | 0 | 8 | [10 empty] | 2023-02-17 | 2023-03-21 | 22 | 0 | 22 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | HOLBROOK | 494242 | 2343 | 10 | Solar | 07_2W1 | 2023-02-07 08:40 | 2023-02-08 | 2 | 0 | 2 | 2023-02-10 | 2023-03-16 | 24 | 0 | 24 | [20 empty] | 2023-03-22 |  | 2024-03-25 |  | EXP | [8 empty] | 2023-05-22 | Connected |  | No
National Grid | FOXBOROUGH | 491954 | 2035 | 6.96 | Solar | 05_3431W2 | 2023-02-07 10:01 | 2023-02-08 | 1 | 0 | 1 | 2023-02-09 | 2023-03-08 | 19 | 0 | 19 | [20 empty] | 2023-03-14 | 2023-02-07 13:58 | 2024-07-02 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | HAVERHILL | 500093 | 1830 | 15.36 | Solar | 14_76L1 | 2023-02-07 13:58 | 2023-02-08 | 13 | 12 | 1 | 2023-02-27 | 2023-05-23 | 61 | 42 | 19 | [20 empty] | 2023-05-25 |  | 2024-06-27 | Yes | EXP |  | 2023-07-27 | 2023-10-25 | 91 | 0 | 91 |  |  | 2023-10-27 | Connected |  | No
National Grid | BOXFORD | 499234 | 1921 | 15 | Solar | 14_33L2 | 2023-02-07 16:06 | 2023-02-08 | 10 | 9 | 1 | 2023-02-22 | 2023-03-24 | 22 | 0 | 22 | [20 empty] | 2023-03-24 |  | 2024-03-26 |  | EXP | [8 empty] | 2023-07-29 | Connected |  | No
National Grid | FALL RIVER | 461538 | 2724 | 490 | Solar | 05_115W42 | 2023-02-08 10:38 | 2023-02-09 | 91 | 81 | 10 | [10 empty] | 2023-06-23 | 2024-01-08 | 135 | 114 | 21 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | WILLIAMSBURG | 485087 | 1096 | 6 | Solar | 09_909W3 | 2023-02-08 11:09 | 2023-02-09 | 1 | 0 | 1 | 2023-02-10 | 2023-03-15 | 23 | 0 | 23 | [20 empty] | 2023-03-22 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BYFIELD | 488659 | 1922 | 10.752 | Solar | 14_60L2 | 2023-02-08 12:51 | 2023-02-09 | 2 | 1 | 1 | 2023-02-10 | 2023-03-16 | 24 | 0 | 24 | [20 empty] | 2023-03-16 | 2023-02-08 13:15 | 2024-03-27 |  | EXP | [8 empty] | 2023-05-23 | Connected |  | No
National Grid | WORCESTER | 496344 | 1603 | 9.86 | Solar | 01_7J387 | 2023-02-08 13:15 | 2023-02-09 | 1 | 0 | 1 | 2023-02-10 | 2023-03-15 | 23 | 0 | 23 | [20 empty] | 2023-03-21 |  | 2024-07-24 | Yes | EXP | [8 empty] | 2023-07-28 | Connected |  | No
National Grid | WILBRAHAM | 478811 | 1095 | 10 | Solar | 09_523L1 | 2023-02-09 08:11 | 2023-02-10 | 2 | 0 | 2 | 2023-02-14 | 2023-03-17 | 23 | 0 | 23 | [20 empty] | 2023-03-20 | 2023-02-09 10:05 | 2024-03-22 |  | EXP | [8 empty] | 2023-06-22 | Connected |  | Yes
National Grid | BROCKTON | 494772 | 2301 | 7.6 | Solar | 07_911W59 | 2023-02-09 10:05 | 2023-02-10 | 2 | 0 | 2 | 2023-02-14 | 2023-03-21 | 26 | 3 | 23 | [20 empty] | 2023-03-27 |  | 2024-12-17 | Yes | EXP |  | 2023-08-09 | 2023-10-06 | 59 | 0 | 59 |  |  | 2024-04-13 | Connected |  | No
National Grid | BROCKTON | 500083 | 2301 | 15 | Solar | 07_98W46 | 2023-02-09 12:58 | 2023-02-10 | 2 | 0 | 2 | 2023-02-14 | 2023-08-11 | 124 | 102 | 22 | 2023-12-06 | 2024-01-17 | 19 | 3 | 16 | [5 empty] | 2023-12-06 | 2024-01-17 | 19 | 3 | 16 | [5 empty] | 2024-01-04 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 495450 | 2301 | 3.8 | Solar | 07_98W46 | 2023-02-09 13:24 | 2023-02-10 | 2 | 0 | 2 | 2023-02-14 | 2023-03-16 | 22 | 0 | 22 | [20 empty] | 2023-03-22 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 495040 | 1604 | 3.8 | Solar | 01_10J383 | 2023-02-09 13:34 | 2023-02-10 | 2 | 0 | 2 | 2023-02-14 | 2023-03-17 | 23 | 0 | 23 | [20 empty] | 2023-03-22 | 2023-02-09 13:39 | 2024-03-23 |  | EXP | [8 empty] | 2023-07-12 | Connected |  | No
National Grid | LAWRENCE | 494773 | 1843 | 6 | Solar | 14_61L3 | 2023-02-09 13:39 | 2023-02-10 | 2 | 0 | 2 | 2023-02-14 | 2023-03-17 | 23 | 0 | 23 | [20 empty] | 2023-03-22 |  | 2024-10-05 | Yes | EXP |  | 2023-08-12 | 2023-10-05 | 55 | 0 | 55 |  |  | 2023-10-12 | Connected |  | No
National Grid | NANTUCKET | 490698 | 2554 | 19 | Solar | 04_101L6 | 2023-02-09 14:27 | 2023-02-10 | 3 | 1 | 2 | 2023-02-14 | 2023-03-16 | 22 | 0 | 22 | [20 empty] | 2023-03-17 |  | 2024-04-07 |  | EXP | [8 empty] | 2024-02-13 | Connected |  | No
National Grid | BROCKTON | 492024 | 2302 | 6 | Solar | 07_712J1 | 2023-02-09 15:38 | 2023-02-10 | 2 | 0 | 2 | 2023-02-14 | 2023-03-17 | 23 | 0 | 23 | [20 empty] | 2023-03-22 | 2023-02-09 16:21 | 2024-03-22 |  | EXP | [8 empty] | 2023-10-26 | Connected |  | No
National Grid | WEYMOUTH | 494588 | 2191 | 9.86 | Solar | 07_6W2 | 2023-02-09 16:21 | 2023-02-10 | 2 | 0 | 2 | 2023-02-14 | 2023-03-20 | 24 | 2 | 22 | [20 empty] | 2023-03-22 |  | 2024-06-22 | Yes | EXP |  | 2023-06-09 | 2023-06-22 | 14 | 0 | 14 |  |  | 2023-07-29 | Connected |  | No
National Grid | BOXFORD | 500918 | 1921 | 22.8 | Solar | 14_33L1 | 2023-02-09 16:31 | 2023-02-10 | 2 | 0 | 2 | 2023-02-14 | 2023-03-17 | 23 | 0 | 23 | [20 empty] | 2023-03-20 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | STOUGHTON | 500931 | 2072 | 15.2 | Solar | 07_913W47 | 2023-02-09 17:14 | 2023-02-10 | 2 | 0 | 2 | 2023-02-14 | 2023-03-17 | 23 | 0 | 23 | [20 empty] | 2023-03-20 |  | 2024-03-22 |  | EXP | [8 empty] | 2023-04-25 | Connected |  | No
National Grid | METHUEN | 489999 | 1844 | 10 | Solar | 14_43L4 | 2023-02-10 09:20 | 2023-02-13 | 43 | 25 | 18 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BEVERLY | 500295 | 1915 | 15.66 | Solar | 12_18L1 | 2023-02-10 10:02 | 2023-02-13 | 3 | 2 | 1 | 2023-02-16 | 2023-03-22 | 24 | 0 | 24 | [20 empty] | 2023-03-22 |  | 2024-05-01 |  | EXP | [8 empty] | 2023-06-14 | Connected |  | No
National Grid | WEST NEWBURY | 496631 | 1985 | 10 | Solar | 14_47L1 | 2023-02-10 13:00 | 2023-02-13 | 1 | 0 | 1 | 2023-02-14 | 2023-03-17 | 23 | 0 | 23 | [20 empty] | 2023-03-22 | 2023-02-10 15:03 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 494765 | 2301 | 10 | Solar | 07_911W25 | 2023-02-10 15:03 | 2023-02-13 | 1 | 0 | 1 | 2023-02-14 | 2023-03-17 | 23 | 0 | 23 | [20 empty] | 2023-03-22 | 2023-02-10 18:37 | 2024-05-23 | Yes | EXP |  | 2023-05-12 | 2023-05-23 | 12 | 0 | 12 |  |  | 2023-06-10 | Connected |  | No
National Grid | REHOBOTH | 497589 | 2769 | 10 | Solar | 05_7L4 | 2023-02-10 18:37 | 2023-02-13 | 1 | 0 | 1 | 2023-02-14 | 2023-03-20 | 24 | 0 | 24 | [20 empty] | 2023-03-22 |  | 2024-06-08 | Yes | EXP |  | 2023-05-06 | 2023-06-08 | 34 | 0 | 34 |  |  | 2023-07-18 | Connected |  | No
National Grid | WRENTHAM | 393455 | 2093 | 10 | Solar | 05_3422W4 | 2023-02-12 18:47 | 2023-02-13 | 2 | 1 | 1 | 2023-02-14 | 2023-03-21 | 26 | 3 | 23 | 2023-04-06 | 2023-05-08 | 16 | 0 | 16 | [5 empty] | 2023-04-06 | 2023-05-08 | 16 | 0 | 16 | [5 empty] | 2022-01-14 | 2023-02-13 05:04 | 2024-08-02 |  | EXP |  | 2023-07-13 | 2023-07-26 | 14 | 0 | 14 |  |  | 2023-08-30 | Connected |  | Yes
National Grid | LEOMINSTER | 475067 | 1453 | 5.22 | Solar | 01_207W2 | 2023-02-13 05:04 | 2023-02-14 | 5 | 3 | 2 | 2023-02-21 | 2023-03-23 | 23 | 0 | 23 | [20 empty] | 2023-03-29 |  | 2024-11-15 | Yes | EXP |  | 2023-12-14 | 2023-12-22 | 9 | 3 | 6 |  |  | 2023-12-29 | Connected |  | No
National Grid | RANDOLPH | 500180 | 2368 | 120 | Solar | 07_75W7 | 2023-02-13 09:55 | 2023-02-14 | 6 | 0 | 6 | [10 empty] | 2023-02-23 | 2023-03-29 | 25 | 0 | 25 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | ANDOVER | 501458 | 1810 | 15.2 | Solar | 14_59L1 | 2023-02-13 10:58 | 2023-02-14 | 1 | 0 | 1 | 2023-02-15 | 2023-03-17 | 22 | 0 | 22 | [20 empty] | 2023-03-22 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTBOROUGH | 501473 | 1581 | 15.2 | Solar | 05_312W1 | 2023-02-13 11:13 | 2023-02-14 | 2 | 1 | 1 | 2023-02-16 | 2023-03-22 | 24 | 0 | 24 | [20 empty] | 2023-03-22 |  | 2024-03-22 |  | EXP | [8 empty] | 2023-08-30 | Connected |  | No
National Grid | MENDON | 499131 | 1756 | 13.3 | Solar | 05_321W6 | 2023-02-13 11:52 | 2023-02-14 | 1 | 0 | 1 | 2023-02-15 | 2024-04-01 | 280 | 29 | 251 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTMINSTER | 423419 | 1473 | 2.33 | Solar | 01_610W3 | 2023-02-13 15:55 | 2023-02-14 | 2 | 0 | 2 | 2023-02-16 | 2023-03-23 | 25 | 0 | 25 | [20 empty] | 2023-03-29 | 2023-02-14 10:31 | 2024-08-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EVERETT | 418839 | 2149 | 11.5 | Solar | 12_16W2 | 2023-02-14 10:31 | 2023-02-15 | 1 | 0 | 1 | 2023-02-16 | 2023-04-27 | 48 | 25 | 23 | [20 empty] | 2023-05-02 |  | 2024-07-16 | Yes | EXP | [9 empty] | Withdrawn |  | No
National Grid | HAVERHILL | 409267 | 1832 | 4900 | Other | 01_406L4 | 2023-02-14 10:58 | 2023-02-15 | 104 | 46 | 58 | [29 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | PEMBROKE | 497568 | 2359 | 17.28 | Solar | 07_95W3 | 2023-02-14 12:06 | 2023-02-15 | 12 | 10 | 2 | 2023-03-06 | 2023-03-29 | 18 | 0 | 18 | [20 empty] | 2023-03-30 |  | 2024-04-23 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BRIDGEWATER | 497556 | 2324 | 15.66 | Solar | 07_912W55 | 2023-02-14 12:07 | 2023-02-15 | 22 | 20 | 2 | 2023-03-20 | 2023-04-28 | 29 | 8 | 21 | [20 empty] | 2023-05-01 | 2023-02-14 12:48 | 2024-05-01 |  | EXP | [8 empty] | 2023-06-02 | Connected |  | No
National Grid | UPTON | 493873 | 1568 | 10 | Solar | 05_335W3 | 2023-02-14 12:48 | 2023-02-15 | 1 | 0 | 1 | 2023-02-16 | 2023-03-22 | 24 | 0 | 24 | [20 empty] | 2023-03-23 |  | 2024-10-11 | Yes | EXP | [8 empty] | 2023-10-20 | Connected |  | No
National Grid | WESTBOROUGH | 501896 | 1581 | 13.975 | Solar | 05_312W4 | 2023-02-14 12:52 | 2023-02-15 | 1 | 0 | 1 | 2023-02-16 | 2023-03-22 | 24 | 0 | 24 | [20 empty] | 2023-03-28 |  | 2024-04-27 |  | EXP | [8 empty] | 2023-08-22 | Connected |  | No
National Grid | SALEM | 435355 | 1970 | 7.6 | Solar | 12_29W4 | 2023-02-14 13:25 | 2023-02-15 | 1 | 0 | 1 | 2023-02-16 | 2024-02-06 | 242 | 216 | 26 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 501981 | 1844 | 11.02 | Solar | 14_5J40 | 2023-02-14 15:47 | 2023-02-15 | 25 | 23 | 2 | 2023-03-22 | 2023-09-25 | 129 | 109 | 20 | [20 empty] | 2023-09-29 |  | 2024-10-08 |  | EXP | [8 empty] | 2023-11-21 | Connected |  | No
National Grid | SAUGUS | 490744 | 1906 | 7.6 | Solar | 12_23W3 | 2023-02-14 18:09 | 2023-02-15 | 1 | 0 | 1 | 2023-02-16 | 2023-03-22 | 24 | 0 | 24 | [20 empty] | 2023-03-24 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WARD HILL | 487600 | 1835 | 7.54 | Solar | 14_65L3 | 2023-02-15 09:50 | 2023-02-16 | 1 | 0 | 1 | 2023-02-17 | 2023-11-13 | 184 | 162 | 22 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MARLBOROUGH | 494891 | 1752 | 24.94 | Solar | 05_317W6 | 2023-02-15 11:18 | 2023-02-16 | 23 | 22 | 1 | 2023-03-21 | 2023-05-04 | 32 | 13 | 19 | [20 empty] | 2023-05-16 |  | 2024-07-26 |  | EXP | [8 empty] | 2023-11-08 | Connected |  | No
National Grid | NORTH ANDOVER | 502282 | 1845 | 15.2 | Solar | 14_54L3 | 2023-02-15 13:28 | 2023-02-16 | 1 | 0 | 1 | 2023-02-17 | 2023-03-22 | 23 | 0 | 23 | [20 empty] | 2023-03-23 | 2023-02-15 13:34 | 2024-04-20 |  | EXP | [8 empty] | 2024-01-19 | Connected |  | No
National Grid | ATTLEBORO | 493074 | 2703 | 6 | Solar | 05_1J1 | 2023-02-15 13:34 | 2023-02-16 | 1 | 0 | 1 | 2023-02-17 | 2023-04-25 | 46 | 23 | 23 | [20 empty] | 2023-04-28 | 2023-02-15 15:54 | 2024-07-08 | Yes | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | EASTON | 502360 | 2356 | 13.3 | Solar | 07_92W78 | 2023-02-15 15:54 | 2023-02-16 | 3 | 2 | 1 | 2023-02-21 | 2023-03-24 | 24 | 0 | 24 | [20 empty] | 2023-03-24 |  | 2024-05-04 | Yes | EXP |  | 2023-07-07 | 2023-07-26 | 20 | 0 | 20 |  |  |  | Withdrawn |  | Yes
National Grid | BLACKSTONE | 502463 | 1504 | 6.96 | Solar | 05_321W9 | 2023-02-16 13:09 | 2023-02-17 | 1 | 0 | 1 | 2023-02-21 | 2023-03-29 | 27 | 5 | 22 | 2023-04-04 | 2023-05-08 | 15 | 0 | 15 | [5 empty] | 2023-04-04 | 2023-05-08 | 15 | 0 | 15 | [5 empty] | 2023-05-01 |  | 2024-08-16 |  | EXP |  | 2023-07-25 | 2023-08-17 | 24 | 0 | 24 |  |  | 2023-08-29 | Connected |  | Yes
National Grid | DRACUT | 499858 | 1826 | 10 | Solar | 14_78L1 | 2023-02-16 15:44 | 2023-02-17 | 4 | 3 | 1 | 2023-02-24 | 2023-03-23 | 20 | 0 | 20 | [20 empty] | 2023-03-24 |  | 2024-03-29 |  | EXP | [8 empty] | 2023-06-30 | Connected |  | No
National Grid | SPENCER | 418278 | 1562 | 2000 | Solar | 01_21W1 | 2023-02-17 09:03 | 2023-02-21 | 98 | 88 | 10 | [10 empty] | 2023-07-14 | 2023-08-07 | 17 | 0 | 17 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | NORWELL | 495669 | 2061 | 220 | Solar | 07_96W40 | 2023-02-17 09:46 | 2023-02-21 | 42 | 34 | 8 | [10 empty] | 2023-04-21 | 2023-05-12 | 17 | 2 | 15 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | REVERE | 499811 | 2151 | 50 | Solar | 12_35J3 | 2023-02-17 10:13 | 2023-02-21 | 56 | 48 | 8 | 2023-05-11 | 2023-06-08 | 21 | 4 | 17 | [20 empty] | 2023-06-13 |  | 2024-11-04 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | NORWELL | 500310 | 2061 | 8.7 | Solar | 07_96W43 | 2023-02-17 11:23 | 2023-02-21 | 1 | 0 | 1 | 2023-02-22 | 2023-03-24 | 22 | 0 | 22 | [20 empty] | 2023-03-29 | 2023-02-17 13:32 | 2024-08-01 |  | EXP | [8 empty] | 2023-08-25 | Connected |  | No
National Grid | BROCKTON | 473695 | 2302 | 6 | Solar | 07_797W42 | 2023-02-17 13:32 | 2023-02-21 | 1 | 0 | 1 | 2023-02-22 | 2023-04-06 | 33 | 10 | 23 | [20 empty] | 2023-04-11 |  | 2024-09-07 | Yes | EXP | [8 empty] | 2024-02-13 | Connected |  | No
National Grid | STURBRIDGE | 503087 | 1566 | 22.62 | Solar | 01_408L1 | 2023-02-17 14:32 | 2023-02-21 | 1 | 0 | 1 | 2023-02-22 | 2023-03-23 | 22 | 0 | 22 | [20 empty] | 2023-03-31 |  | 2024-04-03 |  | EXP | [8 empty] | 2023-10-02 | Connected |  | No
National Grid | SWANSEA | 465846 | 2777 | 14770 | Other | 05_11W85 | 2023-02-17 14:45 | 2023-02-21 | 51 | 43 | 8 | [10 empty] | 2023-05-04 | 2023-06-07 | 24 | 4 | 20 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | LEOMINSTER | 499837 | 1453 | 240 | Solar | 01_207W3 | 2023-02-20 10:32 | 2023-02-21 | 24 | 14 | 10 | [10 empty] | 2023-03-27 | 2023-04-28 | 24 | 0 | 24 | [11 empty] | 2023-02-20 16:22 |  |  | STD | [9 empty] | Study |  | No
National Grid | LEOMINSTER | 503390 | 1453 | 16.24 | Solar | 01_225W4 | 2023-02-20 16:22 | 2023-02-21 | 19 | 18 | 1 | 2023-03-17 | 2023-04-07 | 16 | 0 | 16 | [20 empty] | 2023-04-10 |  | 2024-04-26 | Yes | EXP |  | 2023-07-06 | 2023-08-15 | 41 | 0 | 41 |  |  | 2024-01-31 | Connected |  | No
National Grid | QUINCY | 489308 | 2169 | 4.35 | Solar | 07_1W2 | 2023-02-21 09:38 | 2023-02-09 | 8 | 0 | 8 | 2023-02-22 | 2024-02-06 | 239 | 213 | 26 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 502980 | 1609 | 15.2 | Solar | 01_23W1 | 2023-02-21 10:25 | 2023-02-22 | 1 | 0 | 1 | 2023-02-23 | 2023-03-24 | 21 | 0 | 21 | [20 empty] | 2023-03-31 |  | 2024-04-02 |  | EXP | [8 empty] | 2023-08-04 | Connected |  | No
National Grid | NORTH BILLERICA | 503539 | 1862 | 6.3 | Solar | 14_70L3 | 2023-02-21 11:48 | 2023-02-22 | 1 | 0 | 1 | 2023-02-23 | 2023-03-23 | 21 | 0 | 21 | [20 empty] | 2023-03-24 | 2023-02-21 11:50 | 2024-05-03 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | BARRE | 498809 | 1005 | 7.6 | Solar | 09_604W1 | 2023-02-21 11:50 | 2023-02-22 | 2 | 0 | 2 | 2023-02-24 | 2023-03-23 | 20 | 0 | 20 | [20 empty] | 2023-03-29 |  | 2024-07-05 | Yes | EXP |  | 2023-08-16 | 2023-11-01 | 78 | 0 | 78 |  |  | 2023-11-23 | Connected |  | No
National Grid | GLOUCESTER | 496619 | 1930 | 110 | Solar | 12_51T3 | 2023-02-21 13:51 | 2023-02-22 | 41 | 31 | 10 | [10 empty] | 2023-04-24 | 2023-06-09 | 35 | 13 | 22 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | FRANKLIN | 476346 | 2038 | 5000 | Other | 05_341W2 | 2023-02-21 15:19 | 2023-02-22 | 99 | 56 | 43 | [29 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | REVERE | 483382 | 2151 | 8.7 | Solar | 12_16W8 | 2023-02-22 08:47 | 2023-02-23 | 5 | 4 | 1 | 2023-03-02 | 2023-03-29 | 20 | 0 | 20 | [20 empty] | 2023-04-04 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BELCHERTOWN | 503874 | 1007 | 14.79 | Solar | 09_509L2 | 2023-02-22 11:01 | 2023-02-23 | 26 | 25 | 1 | 2023-03-30 | 2023-06-05 | 46 | 29 | 17 | [20 empty] | 2023-06-05 |  | 2024-06-06 |  | EXP | [8 empty] | 2023-07-19 | Connected |  | No
National Grid | ANDOVER | 503342 | 1810 | 18.85 | Solar | 14_50L1 | 2023-02-22 11:11 | 2023-02-23 | 1 | 0 | 1 | 2023-02-24 | 2023-03-23 | 20 | 0 | 20 | [20 empty] | 2023-03-24 |  | 2024-04-03 |  | EXP | [8 empty] | 2023-08-16 | Connected |  | No
National Grid | ATTLEBORO | 492352 | 2703 | 4999 | Other | 05_8L1 | 2023-02-22 11:19 | 2023-02-23 | 11 | 2 | 9 | [10 empty] | 2023-03-09 | 2023-03-28 | 14 | 0 | 14 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | BRIMFIELD | 461539 | 1010 | 10 | Solar | 09_516L1 | 2023-02-22 12:53 | 2023-02-23 | 1 | 0 | 1 | 2023-02-24 | 2023-03-23 | 20 | 0 | 20 | [20 empty] | 2023-03-23 | 2023-02-22 13:49 | 2024-04-10 |  | EXP | [8 empty] | 2023-11-21 | Connected |  | No
National Grid | STURBRIDGE | 477664 | 1566 | 9.57 | Solar | 01_413L7 | 2023-02-22 13:49 | 2023-02-23 | 1 | 0 | 1 | 2023-02-24 | 2023-03-23 | 20 | 0 | 20 | [20 empty] | 2023-03-29 |  | 2024-08-21 | Yes | EXP | [8 empty] | 2023-11-29 | Connected |  | No
National Grid | ATHOL | 504058 | 1331 | 7.6 | Solar | 09_702W3 | 2023-02-22 15:48 | 2023-02-23 | 6 | 4 | 2 | 2023-03-03 | 2023-06-23 | 78 | 56 | 22 | [20 empty] | 2023-07-12 |  | 2024-07-20 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | EVERETT | 502664 | 2149 | 6 | Solar | 12_16W2 | 2023-02-22 18:29 | 2023-02-23 | 2 | 0 | 2 | 2023-02-27 | 2023-11-13 | 179 | 160 | 19 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LANCASTER | 504134 | 1523 | 7.6 | Solar | 01_227W1 | 2023-02-23 08:11 | 2023-02-24 | 7 | 7 | 0 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | SAUGUS | 476349 | 1906 | 240 | Solar | 12_25W3 | 2023-02-23 08:13 | 2023-02-24 | 36 | 26 | 10 | 2023-08-23 |  | 160 | 93 | 67 | [21 empty] | 2023-02-23 10:52 |  |  | EXP | [9 empty] | Screening |  | No
National Grid | WORCESTER | 492821 | 1603 | 7.6 | Solar | 01_6W2 | 2023-02-23 10:52 | 2023-02-24 | 1 | 0 | 1 | 2023-02-27 | 2023-03-31 | 25 | 0 | 25 | [20 empty] | 2023-04-06 | 2023-02-23 12:11 | 2024-06-25 | Yes | EXP | [8 empty] | 2023-10-03 | Connected |  | No
National Grid | NORTH OXFORD | 483875 | 1537 | 10 | Solar | 01_406L1 | 2023-02-23 12:11 | 2023-02-24 | 1 | 0 | 1 | 2023-02-27 | 2023-03-31 | 25 | 0 | 25 | [20 empty] | 2023-04-06 | 2023-02-23 17:45 | 2024-07-01 | Yes | EXP | [8 empty] | 2023-11-20 | Connected |  | No
National Grid | RANDOLPH | 466954 | 2368 | 3.77 | Solar | 07_97W5 | 2023-02-23 17:45 | 2023-02-24 | 34 | 28 | 6 | 2023-04-13 | 2023-05-11 | 20 | 0 | 20 | [20 empty] | 2023-05-16 |  | 2024-07-23 | Yes | EXP |  | 2023-10-21 | 2023-11-07 | 18 | 0 | 18 |  |  | 2023-11-09 | Connected |  | Yes
National Grid | NORTON | 502806 | 2766 | 6 | Solar | 05_4L2 | 2023-02-23 18:46 | 2023-02-24 | 1 | 0 | 1 | 2023-02-27 | 2023-03-24 | 20 | 0 | 20 | [20 empty] | 2023-03-29 |  | 2024-04-07 |  | EXP | [8 empty] | 2023-06-05 | Connected |  | No
National Grid | LYNN | 502819 | 1905 | 3.8 | Solar | 12_19W1 | 2023-02-23 18:53 | 2023-02-24 | 2 | 0 | 2 | 2023-02-28 | 2023-03-29 | 22 | 0 | 22 | [20 empty] | 2023-04-03 | 2023-02-23 19:14 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LYNN | 503337 | 1904 | 3.8 | Solar | 12_12J904 | 2023-02-23 19:14 | 2023-02-24 | 19 | 17 | 2 | 2023-03-23 | 2023-04-27 | 25 | 0 | 25 | [20 empty] | 2023-05-02 | 2023-02-24 09:11 | 2025-01-23 | Yes | EXP |  | 2023-09-06 | 2023-12-08 | 94 | 0 | 94 |  |  | 2024-02-22 | Connected |  | No
National Grid | HAVERHILL | 488061 | 1832 | 7.6 | Solar | 14_48L4 | 2023-02-24 09:11 | 2023-02-27 | 3 | 0 | 3 | 2023-03-02 | 2023-04-02 | 23 | 0 | 23 | [20 empty] | 2023-01-01 |  | 2024-05-14 | Yes | EXP |  | 2023-08-12 | 2023-10-09 | 59 | 0 | 59 |  |  | 2023-10-18 | Connected |  | Yes
National Grid | FRANKLIN | 488486 | 2038 | 240 | Solar | 05_344W1 | 2023-02-24 10:42 | 2023-02-27 | 61 | 51 | 10 | [10 empty] | 2023-05-24 | 2023-06-22 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | SAUGUS | 488519 | 1906 | 480 | Solar | 12_25W3 | 2023-02-24 10:43 | 2023-02-27 | 84 | 74 | 10 | [10 empty] | 2023-06-29 | 2023-07-27 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Conditional Approval |  | No
National Grid | LOWELL | 488581 | 1852 | 300 | Solar | 14_3J5 | 2023-02-24 10:44 | 2023-02-27 | 283 | 204 | 79 | [29 empty] | STD | [9 empty] | Application |  | No
National Grid | LAWRENCE | 500858 | 1841 | 60 | Solar | 14_6J8 | 2023-02-24 10:45 | 2023-02-27 | 257 | 163 | 94 | [26 empty] | 2023-02-24 10:46 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LOWELL | 500890 | 1852 | 100 | Solar | 14_3L4 | 2023-02-24 10:46 | 2023-02-27 | 30 | 21 | 9 | 2023-04-10 | 2023-06-09 | 43 | 18 | 25 | [20 empty] | 2023-06-23 |  | 2024-07-17 | Yes | EXP | [9 empty] | Completion Documents |  | No
National Grid | WORCESTER | 500916 | 1605 | 100 | Solar | 01_27W2 | 2023-02-24 10:47 | 2023-02-27 | 31 | 21 | 10 | 2023-04-10 | 2023-05-19 | 29 | 5 | 24 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | FALL RIVER | 501029 | 2721 | 100 | Solar | 05_115W44 | 2023-02-24 10:55 | 2023-02-27 | 257 | 163 | 94 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | SPENCER | 492345 | 1562 | 5000 | Solar | 01_552L1 | 2023-02-24 11:09 | 2023-02-27 | 18 | 9 | 9 | [10 empty] | 2023-03-22 | 2023-05-16 | 39 | 24 | 15 | [11 empty] | 2023-02-24 13:55 |  |  | STD | [9 empty] | Study |  | No
National Grid | ANDOVER | 504001 | 1810 | 20 | Solar | 14_59L1 | 2023-02-24 13:55 | 2023-02-27 | 1 | 0 | 1 | 2023-02-28 | 2023-03-31 | 24 | 0 | 24 | [20 empty] | 2023-04-03 |  | 2024-07-27 | Yes | EXP |  | 2023-08-29 | 2023-10-04 | 37 | 0 | 37 |  |  | 2023-11-20 | Connected |  | No
National Grid | BEVERLY | 496638 | 1915 | 7.6 | Solar | 12_51L2 | 2023-02-24 15:09 | 2023-02-27 | 2 | 0 | 2 | 2023-03-01 | 2023-10-27 | 167 | 127 | 40 | [20 empty] | 2023-10-31 |  | 2024-11-07 |  | EXP | [8 empty] | 2023-12-21 | Connected |  | No
National Grid | WESTFORD | 495618 | 1886 | 7.6 | Solar | 14_57L3 | 2023-02-27 09:57 | 2023-02-28 | 6 | 5 | 1 | [10 empty] | 2023-03-07 | 2024-02-06 | 230 | 206 | 24 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | EAST LONGMEADOW | 502131 | 1028 | 22.674 | Solar | 09_139L5 | 2023-02-27 11:02 | 2023-02-28 | 3 | 2 | 1 | 2023-03-02 | 2023-03-29 | 20 | 0 | 20 | [20 empty] | 2023-03-29 |  | 2024-04-18 |  | EXP | [8 empty] | 2023-09-01 | Connected |  | No
National Grid | MARLBOROUGH | 503948 | 1752 | 10 | Solar | 05_311W3 | 2023-02-27 12:13 | 2023-02-28 | 2 | 0 | 2 | 2023-03-02 | 2023-04-02 | 23 | 0 | 23 | [20 empty] | 2023-05-04 |  | 2024-08-15 |  | EXP | [8 empty] | 2023-12-30 | Connected |  | No
National Grid | BARRE | 467839 | 1005 | 1900 | Solar | 09_604W2 | 2023-02-27 13:04 | 2023-02-28 | 49 | 39 | 10 | [10 empty] | 2023-05-10 | 2023-06-27 | 34 | 19 | 15 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | NORTHAMPTON | 479453 | 1060 | 10 | Solar | 09_901W3 | 2023-02-27 14:10 | 2023-02-28 | 2 | 0 | 2 | 2023-03-02 | 2023-04-02 | 23 | 0 | 23 | 2023-05-26 | 2023-06-28 | 12 | 0 | 12 | [5 empty] | 2023-05-26 | 2023-06-28 | 12 | 0 | 12 | [5 empty] | 2023-06-20 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEOMINSTER | 485045 | 1453 | 4990 | Other | 01_207W4 | 2023-02-27 16:13 | 2023-02-28 | 8 | 0 | 8 | [10 empty] | 2023-03-10 | 2023-03-24 | 11 | 0 | 11 | [14 empty] | STD | [9 empty] | Pending Withdraw |  | No
National Grid | CHARLTON | 437435 | 1507 | 4990 | Other | 01_415L3 | 2023-02-27 16:33 | 2023-02-28 | 14 | 4 | 10 | [10 empty] | 2023-03-17 | 2023-04-18 | 22 | 3 | 19 | [14 empty] | STD | [9 empty] | Pending Withdraw |  | No
National Grid | WENDELL | 465809 | 1379 | 8477 | Other | 09_705W1 | 2023-02-27 16:56 | 2023-02-28 | 34 | 24 | 10 | [10 empty] | 2023-04-14 | 2023-05-26 | 31 | 11 | 20 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | STURBRIDGE | 437621 | 1566 | 4482 | Solar | 01_415L3 | 2023-02-27 17:26 | 2023-02-28 | 14 | 4 | 10 | [10 empty] | 2023-03-17 | 2023-03-27 | 7 | 0 | 7 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | LAWRENCE | 501424 | 1843 | 10 | Solar | 14_61L2 | 2023-02-27 20:07 | 2023-02-28 | 2 | 0 | 2 | 2023-03-02 | 2023-03-29 | 20 | 0 | 20 | [20 empty] | 2023-04-04 | 2023-02-28 06:43 | 2024-04-12 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | BRADFORD | 498937 | 1835 | 5.04 | Solar | 14_43L3 | 2023-02-28 06:43 | 2023-03-01 | 5 | 3 | 2 | 2023-03-08 | 2023-04-06 | 22 | 0 | 22 | [20 empty] | 2023-04-11 |  | 2024-11-29 | Yes | EXP |  | 2023-06-09 | 2024-02-03 | 240 | 3 | 237 |  |  | 2024-02-06 | Connected |  | No
National Grid | BROCKTON | 487773 | 2301 | 1680 | Solar | 07_91W48 | 2023-02-28 13:40 | 2023-03-01 | 10 | 0 | 10 | [10 empty] | 2023-03-15 | 2023-04-11 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | WARE | 505468 | 1082 | 17.6 | Solar | 09_501L1 | 2023-03-01 10:17 | 2023-03-02 | 11 | 10 | 1 | 2023-03-16 | 2023-04-05 | 15 | 0 | 15 | [20 empty] | 2023-04-06 |  | 2024-04-10 |  | EXP | [8 empty] | 2023-07-07 | Connected |  | No
National Grid | WORCESTER | 504930 | 1610 | 20 | Solar | 01_6J326 | 2023-03-01 15:51 | 2023-03-02 | 14 | 4 | 10 | 2023-03-22 | 2024-03-25 | 252 | 233 | 19 | [24 empty] | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | FRANKLIN | 494444 | 2038 | 937.5 | Solar | 05_344W6 | 2023-03-01 16:44 | 2023-03-02 | 107 | 98 | 9 | [10 empty] | 2023-08-04 | 2023-08-28 | 17 | 0 | 17 | [14 empty] | STD | [9 empty] | Group Study |  | Yes
National Grid | STURBRIDGE | 505691 | 1566 | 15 | Solar | 01_413L7 | 2023-03-02 09:33 | 2023-03-03 | 34 | 25 | 9 | 2023-04-21 | 2023-06-12 | 37 | 14 | 23 | [20 empty] | 2023-06-15 |  | 2024-06-19 |  | EXP | [8 empty] | 2023-07-17 | Connected |  | No
National Grid | ATHOL | 501750 | 1331 | 7.6 | Solar | 09_702W3 | 2023-03-02 10:44 | 2023-03-03 | 3 | 0 | 3 | 2023-03-08 | 2023-03-31 | 18 | 2 | 16 | [20 empty] | 2023-04-06 |  | 2024-04-30 |  | EXP | [8 empty] | 2023-06-29 | Connected |  | No
National Grid | HANOVER | 500843 | 2339 | 1500 | Solar | 07_95W2 | 2023-03-02 11:35 | 2023-03-03 | 21 | 11 | 10 | [10 empty] | 2023-03-31 | 2023-04-28 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Group Study |  | Yes
National Grid | WESTFORD | 506132 | 1886 | 15.2 | Solar | 14_58L1 | 2023-03-02 14:59 | 2023-03-03 | 3 | 0 | 3 | 2023-03-08 | 2023-03-31 | 18 | 0 | 18 | [20 empty] | 2023-03-31 | 2023-03-03 08:21 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOUTHBOROUGH | 497172 | 1772 | 15.356 | Solar | 05_317W4 | 2023-03-03 08:21 | 2023-03-06 | 1 | 0 | 1 | 2023-03-07 | 2023-04-05 | 22 | 0 | 22 | [20 empty] | 2023-04-06 | 2023-03-03 10:41 | 2024-10-31 | Yes | EXP |  | 2023-06-14 | 2023-11-01 | 141 | 0 | 141 |  |  | 2023-11-11 | Connected |  | No
National Grid | RUTLAND | 505628 | 1543 | 7.83 | Solar | 01_55W1 | 2023-03-03 10:41 | 2023-03-06 | 2 | 0 | 2 | 2023-03-08 | 2023-03-31 | 18 | 0 | 18 | [20 empty] | 2023-04-06 | 2023-03-03 14:13 | 2024-08-01 | Yes | EXP |  | 2023-10-04 | 2023-10-16 | 13 | 0 | 13 |  |  | 2023-10-30 | Connected |  | Yes
National Grid | DRACUT | 491978 | 1826 | 7.6 | Solar | 14_78L3 | 2023-03-03 14:13 | 2023-03-06 | 1 | 0 | 1 | 2023-03-07 | 2023-03-30 | 18 | 0 | 18 | [20 empty] | 2023-04-04 |  | 2024-06-29 | Yes | EXP |  | 2023-06-13 | 2023-06-30 | 18 | 0 | 18 |  |  | 2023-07-13 | Connected |  | No
National Grid | FLORENCE | 505781 | 1062 | 10.47 | Solar | 09_909W4 | 2023-03-06 09:30 | 2023-03-07 | 2 | 0 | 2 | 2023-03-09 | 2023-03-30 | 16 | 0 | 16 | [20 empty] | 2023-04-04 |  | 2024-04-05 |  | EXP | [8 empty] | 2023-07-28 | Connected |  | No
National Grid | GRAFTON | 506760 | 1519 | 18.85 | Solar | 01_304W2 | 2023-03-06 12:10 | 2023-03-07 | 1 | 0 | 1 | 2023-03-08 | 2023-03-30 | 17 | 0 | 17 | [20 empty] | 2023-03-31 |  | 2024-04-18 |  | EXP | [8 empty] | 2023-11-01 | Connected |  | No
National Grid | WORCESTER | 502075 | 1606 | 7.68 | Solar | 01_24W3 | 2023-03-06 14:32 | 2023-03-07 | 2 | 1 | 1 | 2023-03-09 | 2023-04-12 | 25 | 0 | 25 | 2023-05-12 | 2023-06-09 | 20 | 0 | 20 | [5 empty] | 2023-05-12 | 2023-06-09 | 20 | 0 | 20 | [5 empty] | 2023-06-13 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MEDFORD | 502077 | 2155 | 15.744 | Solar | 12_67J1 | 2023-03-06 14:37 | 2023-03-07 | 6 | 5 | 1 | 2023-03-15 | 2023-04-26 | 30 | 5 | 25 | 2023-05-12 | 2023-06-14 | 23 | 0 | 23 | [5 empty] | 2023-05-12 | 2023-06-14 | 23 | 0 | 23 | [5 empty] | 2023-06-22 |  | 2024-08-03 |  | EXP | [8 empty] | 2023-08-19 | Connected |  | No
National Grid | ANDOVER | 484404 | 1810 | 14.5 | Solar | 14_50L3 | 2023-03-06 15:07 | 2023-03-07 | 14 | 12 | 2 | 2023-03-27 | 2023-06-29 | 66 | 48 | 18 | [20 empty] | 2023-07-03 |  | 2024-08-03 |  | EXP | [8 empty] | 2023-08-15 | Connected |  | No
National Grid | PALMER | 506481 | 1069 | 16.896 | Solar | 09_503L4 | 2023-03-07 10:29 | 2023-03-08 | 73 | 72 | 1 | 2023-06-23 | 2023-11-27 | 111 | 68 | 43 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 479635 | 2301 | 8.064 | Solar | 07_797W19 | 2023-03-07 10:36 | 2023-03-08 | 0 | 0 | 0 | 2023-03-08 | 2023-04-06 | 22 | 0 | 22 | [20 empty] | 2023-04-12 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BEVERLY | 495132 | 1915 | 7.6 | Solar | 12_51L1 | 2023-03-07 11:25 | 2023-03-08 | 2 | 0 | 2 | 2023-03-10 | 2023-06-12 | 65 | 50 | 15 | 2023-06-16 | 2023-08-24 | 37 | 0 | 37 | [5 empty] | 2023-06-16 | 2023-08-24 | 37 | 0 | 37 | [5 empty] | 2023-08-10 | 2023-03-07 12:25 | 2024-12-16 |  | EXP |  | 2024-01-03 | 2024-01-02 | 0 | 0 | 0 |  |  | 2024-01-24 | Connected |  | No
National Grid | LEOMINSTER | 477027 | 1453 | 6 | Solar | 01_207W1 | 2023-03-07 12:25 | 2023-03-08 | 2 | 1 | 1 | 2023-03-10 | 2023-04-10 | 22 | 0 | 22 | [20 empty] | 2023-04-12 |  | 2024-06-08 | Yes | EXP |  | 2023-06-09 | 2023-05-31 | 64 | 0 | 64 |  |  | 2023-08-07 | Connected |  | No
National Grid | OXFORD | 505438 | 1540 | 15 | Solar | 01_406L4 | 2023-03-07 13:06 | 2023-03-08 | 2 | 0 | 2 | 2023-03-10 | 2023-08-27 | 117 | 95 | 22 | [20 empty] | 2023-08-30 | 2023-03-07 13:24 | 2024-09-24 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | LAWRENCE | 506007 | 1841 | 17.6 | Solar | 14_6J2 | 2023-03-07 13:24 | 2023-03-08 | 2 | 0 | 2 | 2023-03-10 | 2023-04-19 | 29 | 13 | 16 | [20 empty] | 2023-04-21 |  | 2024-06-06 | Yes | EXP |  | 2023-08-12 | 2023-10-11 | 61 | 0 | 61 |  |  | 2023-10-14 | Connected |  | No
National Grid | ROYALSTON | 494175 | 1368 | 7.6 | Solar | 09_701J1 | 2023-03-08 09:19 | 2023-03-09 | 4 | 3 | 1 | 2023-03-14 | 2023-04-10 | 20 | 2 | 18 | [20 empty] | 2023-04-11 |  | 2024-06-13 |  | EXP | [8 empty] | 2023-06-26 | Connected |  | No
National Grid | BROCKTON | 507289 | 2301 | 12.76 | Solar | 07_911W13 | 2023-03-08 09:47 | 2023-03-09 | 29 | 27 | 2 | 2023-04-20 | 2023-05-18 | 21 | 0 | 21 | [20 empty] | 2023-05-19 |  | 2024-07-17 |  | EXP | [8 empty] | 2023-12-28 | Connected |  | No
National Grid | NEW BRAINTREE | 492334 | 1531 | 2000 | Solar | 09_604W3 | 2023-03-08 13:22 | 2023-03-09 | 10 | 1 | 9 | [10 empty] | 2023-03-23 | 2023-05-16 | 39 | 24 | 15 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | RUTLAND | 506739 | 1543 | 6.96 | Solar | 01_55W1 | 2023-03-08 17:29 | 2023-03-09 | 2 | 0 | 2 | 2023-03-13 | 2023-04-05 | 18 | 0 | 18 | [20 empty] | 2023-04-06 |  | 2024-05-31 |  | EXP | [8 empty] | 2023-06-08 | Connected |  | No
National Grid | DIGHTON | 498979 | 2715 | 7.54 | Solar | 05_19W73 | 2023-03-08 20:54 | 2023-03-09 | 2 | 0 | 2 | 2023-03-13 | 2023-04-05 | 18 | 0 | 18 | [20 empty] | 2023-04-10 | 2023-03-09 09:01 | 2024-04-20 |  | EXP | [8 empty] | 2023-08-03 | Connected |  | No
National Grid | BILLERICA | 503842 | 1821 | 10 | Solar | 14_18L3 | 2023-03-09 09:01 | 2023-03-10 | 2 | 1 | 1 | 2023-03-13 | 2023-04-11 | 22 | 0 | 22 | [20 empty] | 2023-04-11 |  | 2024-05-25 | Yes | EXP |  | 2023-09-26 | 2023-10-12 | 17 | 0 | 17 |  |  | 2023-10-16 | Connected |  | No
National Grid | METHUEN | 503150 | 1844 | 6 | Solar | 14_63L1 | 2023-03-09 09:48 | 2023-03-10 | 1 | 0 | 1 | 2023-03-13 | 2023-04-12 | 23 | 0 | 23 | 2023-04-18 | 2023-05-16 | 18 | 0 | 18 | [5 empty] | 2023-04-18 | 2023-05-16 | 18 | 0 | 18 | [5 empty] | 2023-05-18 | 2023-03-09 09:59 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FALL RIVER | 504881 | 2724 | 6 | Solar | 05_115W42 | 2023-03-09 09:59 | 2023-03-10 | 2 | 0 | 2 | 2023-03-14 | 2023-04-12 | 22 | 0 | 22 | [20 empty] | 2023-04-14 |  | 2024-07-13 | Yes | EXP |  | 2023-06-20 | 2023-07-13 | 24 | 0 | 24 |  |  | 2023-08-23 | Connected |  | No
National Grid | SOUTHBOROUGH | 507198 | 1772 | 19.72 | Solar | 05_317W3 | 2023-03-09 10:04 | 2023-03-10 | 1 | 0 | 1 | 2023-03-13 | 2023-04-05 | 18 | 0 | 18 | [20 empty] | 2023-04-05 |  | 2024-04-12 |  | EXP | [8 empty] | 2023-11-15 | Connected |  | No
National Grid | LAWRENCE | 505172 | 1841 | 6 | Solar | 14_74L3 | 2023-03-09 10:06 | 2023-03-10 | 5 | 0 | 5 | 2023-03-17 | 2023-04-19 | 23 | 0 | 23 | 2023-04-27 | 2023-05-31 | 11 | 0 | 11 | [5 empty] | 2023-04-27 | 2023-05-31 | 11 | 0 | 11 | [5 empty] | 2023-05-18 | 2023-03-09 10:11 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH GRAFTON | 505155 | 1536 | 7.6 | Solar | 01_304W4 | 2023-03-09 10:11 | 2023-03-10 | 7 | 0 | 7 | 2023-03-21 | 2023-05-02 | 31 | 10 | 21 | [20 empty] | 2023-05-05 |  | 2024-07-28 | Yes | EXP | [8 empty] | 2024-02-01 | Connected |  | No
National Grid | BELLINGHAM | 478755 | 2019 | 7.6 | Solar | 05_335W1 | 2023-03-09 10:19 | 2023-03-10 | 1 | 0 | 1 | 2023-03-13 | 2023-04-06 | 19 | 0 | 19 | [20 empty] | 2023-04-10 |  | 2024-07-05 |  | EXP |  | 2023-07-07 | 2023-07-06 | 0 | 0 | 0 |  |  | 2023-07-21 | Connected |  | No
National Grid | WARE | 504231 | 1082 | 10 | Solar | 09_509L2 | 2023-03-09 11:05 | 2023-03-10 | 1 | 0 | 1 | 2023-03-13 | 2023-09-19 | 132 | 112 | 20 | [20 empty] | 2023-09-20 |  | 2024-11-02 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SEEKONK | 477446 | 2771 | 6000 | Solar | 05_7L4 | 2023-03-09 11:41 | 2023-03-10 | 39 | 31 | 8 | [10 empty] | 2023-05-04 | 2023-06-01 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | BERLIN | 502268 | 1503 | 7.6 | Solar | 05_318W3 | 2023-03-09 12:40 | 2023-03-10 | 17 | 16 | 1 | 2023-04-03 | 2023-07-10 | 66 | 46 | 20 | [20 empty] | 2023-07-11 |  | 2024-08-09 |  | EXP | [8 empty] | 2023-10-04 | Connected |  | No
National Grid | WARE | 489441 | 1082 | 3.8 | Solar | 09_523L4 | 2023-03-09 13:42 | 2023-03-10 | 5 | 0 | 5 | 2023-03-17 | 2023-04-12 | 19 | 0 | 19 | [20 empty] | 2023-04-17 |  | 2024-04-27 |  | EXP | [8 empty] | 2023-07-22 | Connected |  | No
National Grid | FALL RIVER | 500885 | 2724 | 3.8 | Solar | 05_115W42 | 2023-03-10 12:50 | 2023-03-13 | 6 | 0 | 6 | 2023-03-21 | 2023-04-24 | 24 | 0 | 24 | [20 empty] | 2023-04-27 |  | 2024-08-29 |  | EXP | [8 empty] | 2023-10-20 | Connected |  | No
National Grid | WINCHENDON | 497546 | 1475 | 6.528 | Solar | 01_612W1 | 2023-03-10 14:59 | 2023-03-13 | 2 | 0 | 2 | 2023-03-15 | 2023-05-12 | 43 | 19 | 24 | [20 empty] | 2023-05-17 | 2023-03-14 02:38 | 2024-05-17 |  | EXP | [8 empty] | 2023-07-01 | Connected |  | No
National Grid | BELLINGHAM | 508761 | 2019 | 5.8 | Solar | 05_344W4 | 2023-03-14 02:38 | 2023-03-15 | 0 | 0 | 0 | 2023-03-15 | 2023-04-20 | 26 | 3 | 23 | [20 empty] | 2023-04-26 |  | 2024-09-10 | Yes | EXP |  | 2023-06-30 | 2023-09-08 | 71 | 0 | 71 |  |  | 2023-09-14 | Connected |  | No
National Grid | PEPPERELL | 491024 | 1463 | 10 | Solar | 01_226L1 | 2023-03-14 14:57 | 2023-03-15 | 4 | 0 | 4 | 2023-03-21 | 2023-06-07 | 55 | 39 | 16 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 444419 | 1603 | 4990 | Other | 01_6W2 | 2023-03-14 22:47 | 2023-03-15 | 84 | 74 | 10 | [10 empty] | 2023-07-17 | 2023-08-09 | 19 | 2 | 17 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | QUINCY | 444420 | 2171 | 4990 | Other | 07_1W8 | 2023-03-14 22:47 | 2023-03-15 | 84 | 74 | 10 | [10 empty] | 2023-07-17 | 2023-08-08 | 17 | 0 | 17 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | SALEM | 444421 | 1970 | 4990 | Other | 12_49W4 | 2023-03-14 22:47 | 2023-03-15 | 84 | 74 | 10 | [10 empty] | 2023-07-17 | 2023-08-08 | 17 | 0 | 17 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | HUBBARDSTON | 511164 | 1452 | 9.57 | Solar | 01_602W2 | 2023-03-15 12:04 | 2023-03-16 | 26 | 25 | 1 | 2023-04-24 | 2023-08-30 | 90 | 73 | 17 | [20 empty] | 2023-08-31 |  | 2024-09-07 |  | EXP | [8 empty] | 2024-02-21 | Connected |  | No
National Grid | ATTLEBORO | 505519 | 2703 | 7.6 | Solar | 05_2J1 | 2023-03-15 12:28 | 2023-03-16 | 5 | 4 | 1 | 2023-03-23 | 2023-04-27 | 25 | 0 | 25 | [20 empty] | 2023-04-28 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LOWELL | 505742 | 1851 | 3.8 | Solar | 14_2L3 | 2023-03-15 12:33 | 2023-03-16 | 3 | 0 | 3 | 2023-03-21 | 2023-04-20 | 22 | 1 | 21 | 2023-04-26 | 2023-05-31 | 12 | 0 | 12 | [5 empty] | 2023-04-26 | 2023-05-31 | 12 | 0 | 12 | [5 empty] | 2023-05-18 | 2023-03-15 12:38 | 2024-09-28 |  | EXP |  | 2023-07-29 | 2023-09-28 | 62 | 0 | 62 |  |  | 2023-10-13 | Connected |  | Yes
National Grid | BROCKTON | 505549 | 2302 | 7.6 | Solar | 07_69J1 | 2023-03-15 12:38 | 2023-03-16 | 3 | 0 | 3 | 2023-03-21 | 2023-06-12 | 58 | 38 | 20 | [20 empty] | 2023-06-20 |  | 2024-08-09 | Yes | EXP |  | 2024-02-02 | 2024-02-12 | 11 | 0 | 11 |  |  |  | Completion Documents |  | Yes
National Grid | GREAT BARRINGTON | 511135 | 1230 | 15.2 | Solar | 09_1109W2 | 2023-03-15 14:04 | 2023-03-16 | 2 | 1 | 1 | 2023-03-17 | 2023-04-12 | 19 | 0 | 19 | [20 empty] | 2023-04-13 | 2023-03-15 14:32 | 2024-04-20 |  | EXP | [8 empty] | 2023-06-27 | Connected |  | No
National Grid | ABINGTON | 504529 | 2351 | 10.44 | Solar | 07_93W42 | 2023-03-15 14:32 | 2023-03-16 | 4 | 1 | 3 | 2023-03-21 | 2023-04-14 | 19 | 0 | 19 | [20 empty] | 2023-04-20 |  | 2024-06-07 | Yes | EXP | [8 empty] | 2023-08-16 | Connected |  | No
National Grid | CHELMSFORD | 511233 | 1824 | 11.24 | Solar | 14_24L1 | 2023-03-15 16:19 | 2023-03-16 | 135 | 132 | 3 | 2023-09-29 | 2024-02-23 | 98 | 65 | 33 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | FOXBOROUGH | 509726 | 2035 | 240 | Solar | 05_2468W1 | 2023-03-15 17:30 | 2023-03-16 | 17 | 7 | 10 | [10 empty] | 2023-04-10 | 2023-05-15 | 25 | 0 | 25 | [11 empty] | 2023-03-15 17:49 |  |  | STD | [9 empty] | Group Study |  | No
National Grid | MEDFORD | 499173 | 2155 | 15.2 | Solar | 12_9C6 | 2023-03-15 17:49 | 2023-03-16 | 1 | 0 | 1 | 2023-03-17 | 2023-04-10 | 17 | 0 | 17 | [20 empty] | 2023-04-11 | 2023-03-16 09:37 | 2024-09-01 | Yes | EXP |  | 2023-07-28 | 2023-08-28 | 32 | 0 | 32 |  |  | 2023-09-20 | Connected |  | No
National Grid | WILBRAHAM | 506045 | 1095 | 10 | Solar | 09_139L3 | 2023-03-16 09:37 | 2023-03-17 | 5 | 2 | 3 | 2023-03-23 | 2023-04-26 | 25 | 4 | 21 | [20 empty] | 2023-04-28 | 2023-03-16 09:39 | 2024-06-04 | Yes | EXP | [8 empty] | 2023-09-07 | Connected |  | No
National Grid | SOUTHBOROUGH | 511745 | 1772 | 15.2 | Solar | 05_317W3 | 2023-03-16 09:39 | 2023-03-17 | 1 | 0 | 1 | 2023-03-20 | 2023-04-11 | 17 | 0 | 17 | [20 empty] | 2023-04-12 | 2023-03-16 10:04 | 2024-04-27 | Yes | EXP |  | 2023-05-06 | 2023-12-06 | 215 | 0 | 215 |  |  | 2023-12-14 | Connected |  | No
National Grid | BELCHERTOWN | 488737 | 1007 | 10 | Solar | 09_527L2 | 2023-03-16 10:04 | 2023-03-17 | 3 | 1 | 2 | 2023-03-22 | 2023-04-20 | 21 | 0 | 21 | [20 empty] | 2023-04-26 |  | 2024-06-25 | Yes | EXP |  | 2023-06-09 | 2023-06-23 | 15 | 0 | 15 |  |  | 2023-06-29 | Connected |  | No
National Grid | QUINCY | 504369 | 2169 | 4.64 | Solar | 07_1W2 | 2023-03-16 10:23 | 2023-03-17 | 5 | 2 | 3 | 2023-03-23 | 2023-04-24 | 22 | 0 | 22 | 2023-06-02 | 2023-07-12 | 14 | 0 | 14 | [5 empty] | 2023-06-02 | 2023-07-12 | 14 | 0 | 14 | [5 empty] | 2023-06-29 |  | 2024-09-06 |  | EXP |  | 2023-07-06 | 2023-09-01 | 58 | 0 | 58 |  |  | 2023-09-22 | Connected |  | Yes
National Grid | WILBRAHAM | 511786 | 1095 | 15.2 | Solar | 09_507L3 | 2023-03-16 10:34 | 2023-03-17 | 1 | 0 | 1 | 2023-03-20 | 2023-04-18 | 21 | 0 | 21 | [20 empty] | 2023-04-21 |  | 2024-04-27 |  | EXP | [8 empty] | 2023-10-31 | Connected |  | No
National Grid | SOUTH EGREMONT | 505807 | 1258 | 20 | Solar | 09_1109W2 | 2023-03-16 11:02 | 2023-03-17 | 3 | 0 | 3 | 2023-03-22 | 2023-04-19 | 20 | 0 | 20 | [20 empty] | 2023-04-20 |  | 2024-11-27 |  | EXP | [8 empty] | 2023-12-04 | Connected |  | No
National Grid | FRANKLIN | 507457 | 2038 | 8.448 | Solar | 05_341W2 | 2023-03-16 11:34 | 2023-03-17 | 28 | 27 | 1 | 2023-04-26 | 2023-09-25 | 105 | 82 | 23 | [20 empty] | 2023-09-25 |  | 2024-10-07 |  | EXP | [8 empty] | 2023-11-14 | Connected |  | No
National Grid | UXBRIDGE | 506986 | 1569 | 13.3 | Solar | 05_321W5 | 2023-03-16 12:51 | 2023-03-17 | 3 | 0 | 3 | 2023-03-22 | 2023-04-20 | 21 | 0 | 21 | [20 empty] | 2023-06-12 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | ANDOVER | 512029 | 1810 | 15.2 | Solar | 14_59L1 | 2023-03-16 14:13 | 2023-03-17 | 2 | 0 | 2 | 2023-03-21 | 2023-06-13 | 59 | 39 | 20 | [20 empty] | 2023-06-20 |  | 2024-07-29 |  | EXP | [8 empty] | 2024-03-13 | Connected |  | No
National Grid | BILLERICA | 511257 | 1821 | 249 | Solar | 14_92L2 | 2023-03-16 14:39 | 2023-03-17 | 16 | 6 | 10 | [10 empty] | 2023-04-10 | 2023-05-18 | 29 | 4 | 25 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | SEEKONK | 506779 | 2771 | 11.02 | Solar | 05_9L5 | 2023-03-17 08:13 | 2023-03-20 | 2 | 0 | 2 | 2023-03-22 | 2023-10-25 | 150 | 130 | 20 | [20 empty] | 2023-10-26 |  | 2024-12-01 |  | EXP | [8 empty] | 2024-04-09 | Connected |  | Yes
National Grid | HANOVER | 503019 | 2339 | 16 | Solar | 07_95W4 | 2023-03-17 13:36 | 2023-03-20 | 2 | 0 | 2 | 2023-03-22 | 2023-04-20 | 21 | 0 | 21 | [20 empty] | 2023-04-25 |  | 2024-06-01 |  | EXP | [8 empty] | 2023-09-06 | Connected |  | No
National Grid | NORWELL | 511876 | 2061 | 13.6 | Solar | 07_96W43 | 2023-03-17 13:43 | 2023-03-20 | 13 | 11 | 2 | 2023-04-05 | 2023-05-19 | 32 | 13 | 19 | [20 empty] | 2023-05-19 |  | 2024-06-07 |  | EXP | [8 empty] | 2023-06-29 | Connected |  | No
National Grid | LEOMINSTER | 492026 | 1453 | 450 | Solar | 01_219W4 | 2023-03-17 16:23 | 2023-03-20 | 246 | 236 | 10 | [29 empty] | STD | [9 empty] | Pending Withdraw |  | Yes
National Grid | REVERE | 503442 | 2151 | 10 | Solar | 12_7W2 | 2023-03-19 21:41 | 2023-03-20 | 2 | 0 | 2 | 2023-03-22 | 2023-04-26 | 25 | 0 | 25 | 2023-05-08 | 2023-06-14 | 26 | 0 | 26 | [5 empty] | 2023-05-08 | 2023-06-14 | 26 | 0 | 26 | [5 empty] | 2023-06-21 |  | 2024-07-31 |  | EXP |  | 2023-08-01 | 2023-07-31 | 0 | 0 | 0 |  |  | 2023-08-08 | Connected |  | Yes
National Grid | BOLTON | 506817 | 1740 | 13.34 | Solar | 01_225W1 | 2023-03-20 10:30 | 2023-03-21 | 3 | 0 | 3 | 2023-03-24 | 2023-04-28 | 25 | 0 | 25 | 2023-06-21 | 2023-08-09 | 35 | 0 | 35 | [5 empty] | 2023-06-21 | 2023-08-09 | 35 | 0 | 35 | [5 empty] | 2023-08-10 | 2023-03-20 12:36 | 2024-08-14 |  | EXP |  | 2023-10-05 | 2023-10-18 | 14 | 0 | 14 |  |  | 2023-10-27 | Connected |  | Yes
National Grid | COHASSET | 471856 | 2025 | 13.34 | Solar | 07_915W37 | 2023-03-20 12:36 | 2023-03-21 | 204 | 194 | 10 | 2024-01-17 | 2024-03-08 | 37 | 16 | 21 | [20 empty] | 2024-03-08 |  | 2025-03-26 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | GREAT BARRINGTON | 513251 | 1230 | 20 | Solar | 09_1109W2 | 2023-03-20 14:50 | 2023-03-21 | 25 | 23 | 2 | 2023-04-25 | 2023-05-25 | 23 | 0 | 23 | [20 empty] | 2023-05-26 |  | 2024-07-05 |  | EXP | [8 empty] | 2023-11-07 | Connected |  | No
National Grid | BLACKSTONE | 508947 | 1504 | 10 | Solar | 05_108W60 | 2023-03-20 15:11 | 2023-03-21 | 1 | 0 | 1 | 2023-03-22 | 2023-06-06 | 52 | 31 | 21 | [20 empty] | 2023-06-07 | 2023-03-21 09:28 | 2024-06-13 |  | EXP | [8 empty] | 2023-07-31 | Connected |  | No
National Grid | NORTHAMPTON | 472683 | 1060 | 10 | Solar | 09_909W2 | 2023-03-21 09:28 | 2023-03-22 | 2 | 0 | 2 | 2023-03-24 | 2023-04-28 | 25 | 0 | 25 | [20 empty] | 2023-05-01 |  | 2024-06-12 | Yes | EXP |  | 2023-08-01 | 2023-08-04 | 4 | 0 | 4 |  |  | 2023-10-10 | Connected |  | No
National Grid | HANOVER | 506126 | 2339 | 10 | Solar | 07_95W5 | 2023-03-21 11:00 | 2023-03-22 | 201 | 62 | 139 | 2024-01-11 | 2024-02-15 | 25 | 4 | 21 | [20 empty] | 2024-02-20 |  | 2025-03-25 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | EAST BRIDGEWATER | 513457 | 2333 | 17.6 | Solar | 07_712J1 | 2023-03-21 11:54 | 2023-03-22 | 144 | 128 | 16 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | LEOMINSTER | 513551 | 1453 | 13.8 | Solar | 01_219W2 | 2023-03-21 13:10 | 2023-03-22 | 1 | 0 | 1 | 2023-03-23 | 2023-06-09 | 54 | 33 | 21 | [20 empty] | 2023-06-16 | 2023-03-22 11:00 | 2025-01-09 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | SALEM | 511480 | 1970 | 15.2 | Solar | 12_49W2 | 2023-03-22 11:00 | 2023-03-23 | 1 | 0 | 1 | 2023-03-24 | 2023-04-25 | 22 | 0 | 22 | [20 empty] | 2023-04-25 |  | 2024-04-26 | Yes | EXP |  | 2023-07-28 | 2023-08-09 | 13 | 0 | 13 |  |  | 2023-08-14 | Connected |  | No
National Grid | REHOBOTH | 493282 | 2769 | 50 | Solar | 05_7L5 | 2023-03-22 11:41 | 2023-03-23 | 22 | 13 | 9 | [10 empty] | 2023-04-25 | 2023-05-26 | 24 | 0 | 24 | [11 empty] | 2023-03-22 16:07 |  |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | CHELMSFORD | 468824 | 1824 | 6.144 | Solar | 14_16L4 | 2023-03-22 16:07 | 2023-03-23 | 2 | 0 | 2 | 2023-03-27 | 2023-04-25 | 21 | 1 | 20 | [20 empty] | 2023-04-28 |  | 2024-07-13 | Yes | EXP |  | 2023-07-06 | 2023-07-13 | 8 | 0 | 8 |  |  | 2023-09-23 | Connected |  | No
National Grid | WESTFORD | 514032 | 1886 | 15.34 | Solar | 14_57L3 | 2023-03-23 08:25 | 2023-03-24 | 3 | 2 | 1 | 2023-03-28 | 2024-04-01 | 252 | 25 | 227 | [21 empty] | 2023-03-23 08:55 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | RANDOLPH | 508496 | 2368 | 6 | Solar | 07_97W1 | 2023-03-23 08:55 | 2023-03-24 | 15 | 12 | 3 | 2023-04-13 | 2023-05-11 | 20 | 0 | 20 | [20 empty] | 2023-05-16 | 2023-03-23 09:12 | 2024-10-03 | Yes | EXP |  | 2023-08-01 | 2023-10-04 | 65 | 0 | 65 |  |  | 2023-11-01 | Connected |  | No
National Grid | RANDOLPH | 507261 | 2368 | 6 | Solar | 07_5W4 | 2023-03-23 09:12 | 2023-03-24 | 3 | 0 | 3 | 2023-03-29 | 2023-04-28 | 22 | 0 | 22 | [20 empty] | 2023-05-01 |  | 2024-09-11 | Yes | EXP |  | 2023-07-20 | 2023-09-08 | 51 | 0 | 51 |  |  | 2023-09-21 | Connected |  | No
National Grid | GRAFTON | 514181 | 1519 | 10 | Solar | 01_304W2 | 2023-03-23 13:10 | 2023-03-24 | 1 | 0 | 1 | 2023-03-27 | 2024-04-01 | 253 | 25 | 228 | [21 empty] | 2023-03-23 14:56 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 512252 | 2301 | 3.84 | Solar | 07_911W13 | 2023-03-23 14:56 | 2023-03-24 | 3 | 0 | 3 | 2023-03-29 | 2023-04-28 | 22 | 0 | 22 | [20 empty] | 2023-05-01 |  | 2024-05-16 | Yes | EXP |  | 2023-07-20 | 2023-07-20 | 1 | 0 | 1 |  |  | 2023-08-03 | Connected |  | Yes
National Grid | REHOBOTH | 492065 | 2769 | 7.6 | Solar | 05_7L5 | 2023-03-23 15:59 | 2023-03-24 | 3 | 3 | 0 | 2023-03-29 | 2023-05-12 | 33 | 12 | 21 | [20 empty] | 2023-01-24 |  | 2024-05-15 |  | EXP | [8 empty] | 2023-07-10 | Connected |  | No
National Grid | STOUGHTON | 514367 | 2072 | 19.968 | Solar | 07_94W44 | 2023-03-24 09:46 | 2023-03-27 | 6 | 5 | 1 | 2023-04-03 |  | 258 | 35 | 223 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | MANCHESTER | 514443 | 1944 | 20 | Solar | 12_51T1 | 2023-03-24 12:24 | 2023-03-27 | 1 | 0 | 1 | [10 empty] | 2023-03-28 | 2023-07-11 | 72 | 54 | 18 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | WORCESTER | 513744 | 1605 | 7.6 | Solar | 01_11J354 | 2023-03-24 13:45 | 2023-03-27 | 1 | 0 | 1 | 2023-03-28 | 2023-04-27 | 22 | 0 | 22 | [20 empty] | 2023-05-02 | 2023-03-24 14:44 | 2024-05-05 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | ATHOL | 512262 | 1331 | 7.6 | Solar | 09_702W3 | 2023-03-24 14:44 | 2023-03-27 | 1 | 0 | 1 | 2023-03-28 | 2023-04-27 | 22 | 0 | 22 | [20 empty] | 2023-04-28 | 2023-03-24 15:33 | 2024-07-13 | Yes | EXP |  | 2023-07-07 | 2023-07-12 | 6 | 0 | 6 |  |  | 2023-08-23 | Connected |  | No
National Grid | LYNN | 507161 | 1902 | 4.64 | Solar | 12_22W2 | 2023-03-24 15:33 | 2023-03-27 | 1 | 0 | 1 | 2023-03-28 | 2023-04-28 | 23 | 0 | 23 | [20 empty] | 2023-05-03 |  | 2024-07-19 | Yes | EXP |  | 2023-07-21 | 2023-07-20 | 0 | 0 | 0 |  |  | 2023-07-25 | Connected |  | No
National Grid | EAST LONGMEADOW | 514196 | 1028 | 17.6 | Solar | 09_139L5 | 2023-03-27 10:03 | 2023-03-28 | 5 | 4 | 1 | 2023-04-03 | 2023-05-08 | 25 | 0 | 25 | [20 empty] | 2023-05-09 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | ORANGE | 506021 | 1364 | 10 | Solar | 09_705W3 | 2023-03-27 13:14 | 2023-03-28 | 1 | 0 | 1 | 2023-03-29 |  | 76 | 21 | 55 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOUTH GRAFTON | 515069 | 1560 | 15.2 | Solar | 05_320W3 | 2023-03-28 10:21 | 2023-03-29 | 1 | 0 | 1 | [10 empty] | 2023-03-30 | 2023-05-11 | 31 | 11 | 20 | [11 empty] | 2023-03-28 11:14 |  |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | STOUGHTON | 513459 | 2072 | 10 | Solar | 07_913W18 | 2023-03-28 11:14 | 2023-03-29 | 1 | 0 | 1 | 2023-03-30 | 2023-04-28 | 21 | 0 | 21 | [20 empty] | 2023-05-01 |  | 2024-06-06 | Yes | EXP |  | 2023-07-20 | 2023-08-11 | 23 | 0 | 23 |  |  | 2023-08-24 | Connected |  | No
National Grid | RUTLAND | 504707 | 1543 | 10 | Solar | 01_55W1 | 2023-03-28 12:12 | 2023-03-29 | 2 | 0 | 2 | 2023-03-31 | 2023-05-03 | 23 | 0 | 23 | [20 empty] | 2023-05-05 | 2023-03-28 12:59 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BELLINGHAM | 503144 | 2019 | 6 | Solar | 05_108W60 | 2023-03-28 12:59 | 2023-03-29 | 2 | 0 | 2 | 2023-03-31 | 2023-04-28 | 20 | 0 | 20 | [20 empty] | 2023-05-01 |  | 2024-05-21 | Yes | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HANSON | 494260 | 2341 | 10 | Solar | 07_797W24 | 2023-03-28 14:38 | 2023-03-29 | 2 | 0 | 2 | 2023-03-31 | 2023-05-02 | 22 | 0 | 22 | [20 empty] | 2023-05-09 |  | 2024-05-16 |  | EXP | [8 empty] | 2023-07-19 | Connected |  | No
National Grid | BROCKTON | 511260 | 2301 | 7.6 | Solar | 07_91W49 | 2023-03-28 15:18 | 2023-03-29 | 214 | 208 | 6 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NEWBURY | 508264 | 1532 | 9.57 | Solar | 14_60L1 | 2023-03-28 15:21 | 2023-03-29 | 2 | 1 | 1 | 2023-03-31 | 2023-05-02 | 22 | 0 | 22 | [20 empty] | 2023-05-02 | 2023-03-29 06:12 | 2024-05-20 |  | EXP | [8 empty] | 2023-07-31 | Connected |  | No
National Grid | WORCESTER | 503254 | 1606 | 6.09 | Solar | 01_14J367 | 2023-03-29 06:12 | 2023-03-30 | 2 | 0 | 2 | 2023-04-03 | 2023-05-02 | 22 | 2 | 20 | [20 empty] | 2023-05-08 |  | 2024-11-28 | Yes | EXP | [8 empty] | 2023-12-28 | Connected |  | No
National Grid | AMESBURY | 502722 | 1913 | 2000 | Solar | 14_275L4 | 2023-03-29 09:23 | 2023-03-30 | 103 | 93 | 10 | [10 empty] | 2023-08-28 | 2023-10-18 | 37 | 17 | 20 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | WESTBOROUGH | 479439 | 1581 | 11.4 | Solar | 05_312W4 | 2023-03-29 09:55 | 2023-03-30 | 2 | 0 | 2 | 2023-04-03 | 2023-05-03 | 22 | 0 | 22 | [20 empty] | 2022-12-07 |  | 2024-05-11 |  | EXP | [8 empty] | 2023-12-04 | Connected |  | No
National Grid | WESTFORD | 515435 | 1886 | 12.6 | Solar | 14_58L1 | 2023-03-29 11:13 | 2023-03-30 | 2 | 0 | 2 | 2023-04-03 | 2023-05-15 | 31 | 11 | 20 | [20 empty] | 2023-05-15 |  | 2024-06-10 |  | EXP | [8 empty] | 2023-08-24 | Connected |  | No
National Grid | LEE | 515529 | 1240 | 22.8 | Solar | 09_1103W1 | 2023-03-29 13:26 | 2023-03-30 | 3 | 1 | 2 | 2023-04-03 | 2023-05-01 | 20 | 0 | 20 | [20 empty] | 2023-05-02 |  | 2024-05-06 |  | EXP | [8 empty] | 2023-07-05 | Connected |  | No
National Grid | WEYMOUTH | 515717 | 2191 | 7.6 | Solar | 07_6W2 | 2023-03-30 09:26 | 2023-03-31 | 1 | 0 | 1 | 2023-04-03 | 2023-05-03 | 22 | 0 | 22 | [20 empty] | 2023-05-04 | 2023-03-30 10:19 | 2024-05-08 |  | EXP | [8 empty] | 2023-07-10 | Connected |  | No
National Grid | ESSEX | 501092 | 1929 | 5.76 | Solar | 12_51T2 | 2023-03-30 10:19 | 2023-03-31 | 2 | 0 | 2 | 2023-04-04 | 2023-05-02 | 20 | 0 | 20 | [20 empty] | 2023-05-05 |  | 2024-05-21 | Yes | EXP |  | 2023-07-20 | 2023-07-24 | 5 | 0 | 5 |  |  | 2023-08-01 | Connected |  | Yes
National Grid | WORCESTER | 514581 | 1610 | 9.6 | Solar | 01_4J336 | 2023-03-30 10:57 | 2023-03-31 | 41 | 40 | 1 | 2023-05-31 | 2023-07-19 | 35 | 13 | 22 | 2023-08-07 | 2024-03-28 | 162 | 28 | 134 | [5 empty] | 2023-08-07 | 2024-03-28 | 162 | 28 | 134 | [9 empty] | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | LYNN | 515479 | 1904 | 3.8 | Solar | 12_24W1 | 2023-03-30 11:37 | 2023-03-31 | 1 | 0 | 1 | 2023-04-03 | 2023-05-03 | 22 | 0 | 22 | [20 empty] | 2023-05-04 |  | 2024-05-07 |  | EXP | [8 empty] | 2023-07-19 | Connected |  | No
National Grid | SHUTESBURY | 515826 | 1072 | 10 | Solar | 09_705W1 | 2023-03-30 13:05 | 2023-03-31 | 20 | 18 | 2 | 2023-05-01 | 2023-05-31 | 23 | 2 | 21 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | GREAT BARRINGTON | 515132 | 1230 | 10 | Solar | 09_1109W3 | 2023-03-30 13:17 | 2023-03-31 | 2 | 0 | 2 | 2023-04-04 | 2023-05-23 | 36 | 17 | 19 | [20 empty] | 2023-05-25 |  | 2024-09-10 |  | EXP | [8 empty] | 2023-09-22 | Connected |  | No
National Grid | BROCKTON | 494808 | 2302 | 9.86 | Solar | 07_69J1 | 2023-03-31 05:28 | 2023-04-03 | 1 | 0 | 1 | 2023-04-04 | 2023-05-03 | 21 | 0 | 21 | [20 empty] | 2023-05-08 | 2023-03-31 11:10 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 504970 | 2302 | 10 | Solar | 07_911W56 | 2023-03-31 11:10 | 2023-04-03 | 2 | 0 | 2 | 2023-04-05 | 2023-05-04 | 21 | 0 | 21 | [20 empty] | 2023-05-09 |  | 2024-05-25 | Yes | EXP |  | 2023-07-21 | 2023-08-02 | 13 | 0 | 13 |  |  | 2023-10-05 | Connected |  | Yes
National Grid | BRIDGEWATER | 503065 | 2324 | 1680 | Solar | 07_912W55 | 2023-03-31 11:48 | 2023-04-03 | 10 | 0 | 10 | [10 empty] | 2023-04-18 | 2023-05-15 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | ANDOVER | 500876 | 1810 | 200 | Solar | 14_54L3 | 2023-03-31 14:55 | 2023-04-03 | 10 | 0 | 10 | [10 empty] | 2023-04-18 | 2023-05-19 | 24 | 0 | 24 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | WARE | 516139 | 1082 | 20 | Solar | 09_501L1 | 2023-03-31 15:17 | 2023-04-03 | 1 | 0 | 1 | 2023-04-04 | 2023-10-12 | 132 | 113 | 19 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH ANDOVER | 514296 | 1845 | 10 | Solar | 14_71L1 | 2023-04-03 10:11 | 2023-04-04 | 3 | 0 | 3 | 2023-04-07 | 2023-05-04 | 19 | 0 | 19 | [20 empty] | 2023-05-09 | 2023-04-03 10:32 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 515091 | 1841 | 6 | Solar | 14_63L1 | 2023-04-03 10:32 | 2023-04-04 | 2 | 0 | 2 | 2023-04-06 | 2023-05-04 | 20 | 0 | 20 | [20 empty] | 2023-05-11 |  | 2024-09-19 | Yes | EXP |  | 2023-08-12 | 2023-09-20 | 40 | 0 | 40 |  |  | 2023-09-22 | Connected |  | No
National Grid | WILBRAHAM | 513503 | 1095 | 10 | Solar | 09_507L2 | 2023-04-03 10:47 | 2023-04-04 | 135 | 119 | 16 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | STOUGHTON | 515428 | 2072 | 200 | Solar | 07_75W7 | 2023-04-03 11:42 | 2023-04-04 | 13 | 3 | 10 | [10 empty] | 2023-04-21 | 2023-05-19 | 21 | 0 | 21 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | WEST BROOKFIELD | 514350 | 1585 | 13.92 | Solar | 01_525L2 | 2023-04-04 08:20 | 2023-04-05 | 1 | 0 | 1 | 2023-04-06 | 2023-05-11 | 25 | 0 | 25 | [20 empty] | 2023-05-16 | 2023-04-04 09:08 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HAMPDEN | 511047 | 1036 | 6 | Solar | 09_507L2 | 2023-04-04 09:08 | 2023-04-05 | 5 | 1 | 4 | 2023-04-11 | 2023-05-11 | 22 | 0 | 22 | [20 empty] | 2023-05-17 |  | 2024-06-29 | Yes | EXP | [8 empty] | 2024-01-16 | Connected |  | Yes
National Grid | STURBRIDGE | 516424 | 1566 | 7.6 | Solar | 01_408L1 | 2023-04-04 09:35 | 2023-04-05 | 5 | 4 | 1 | 2023-04-11 | 2023-05-26 | 33 | 12 | 21 | [20 empty] | 2023-06-01 |  | 2024-06-14 |  | EXP | [8 empty] | 2023-07-13 | Connected |  | No
National Grid | BROCKTON | 515597 | 2302 | 10 | Solar | 07_797W42 | 2023-04-04 12:10 | 2023-04-05 | 13 | 12 | 1 | [10 empty] | 2023-04-24 | 2023-12-11 | 158 | 137 | 21 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | WESTFORD | 467561 | 1886 | 4999.2 | Battery Add-On | 14_57L1 | 2023-04-04 12:59 | 2023-04-05 | 33 | 23 | 10 | [10 empty] | 2023-05-23 | 2023-06-23 | 23 | 6 | 17 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | ADAMS | 512682 | 1220 | 6 | Solar | 09_1021W1 | 2023-04-05 13:00 | 2023-04-06 | 12 | 11 | 1 | 2023-04-25 | 2023-05-26 | 24 | 0 | 24 | [20 empty] | 2023-06-05 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WILBRAHAM | 517155 | 1095 | 15.36 | Solar | 09_507L1 | 2023-04-05 15:17 | 2023-04-06 | 20 | 18 | 2 | 2023-05-05 | 2023-06-05 | 21 | 0 | 21 | [20 empty] | 2023-06-06 |  | 2024-06-06 |  | EXP | [8 empty] | 2023-06-27 | Connected |  | No
National Grid | STURBRIDGE | 498882 | 1566 | 12.6 | Solar | 01_415L1 | 2023-04-06 09:59 | 2023-04-07 | 14 | 12 | 2 | 2023-04-27 | 2023-06-29 | 45 | 22 | 23 | [20 empty] | 2023-07-03 | 2023-04-06 12:45 | 2024-08-08 |  | EXP | [8 empty] | 2023-08-24 | Connected |  | No
National Grid | LEOMINSTER | 514450 | 1453 | 7.6 | Solar | 01_207W2 | 2023-04-06 12:45 | 2023-04-07 | 7 | 5 | 2 | 2023-04-18 | 2023-05-17 | 22 | 0 | 22 | [20 empty] | 2023-05-18 |  | 2024-07-26 | Yes | EXP | [8 empty] | 2024-01-11 | Connected |  | No
National Grid | EAST LONGMEADOW | 517452 | 1028 | 15.2 | Solar | 09_508L4 | 2023-04-06 13:30 | 2023-04-07 | 1 | 0 | 1 | 2023-04-10 | 2023-05-03 | 17 | 0 | 17 | [20 empty] | 2023-05-09 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HUBBARDSTON | 516473 | 1452 | 10 | Solar | 09_604W4 | 2023-04-06 13:36 | 2023-04-07 | 203 | 133 | 70 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | DUDLEY | 517480 | 1571 | 14.79 | Solar | 01_412L4 | 2023-04-06 14:13 | 2023-04-07 | 2 | 0 | 2 | 2023-04-11 | 2023-05-10 | 21 | 2 | 19 | [20 empty] | 2023-10-26 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BEVERLY | 517501 | 1915 | 16 | Solar | 12_51L3 | 2023-04-06 15:13 | 2023-04-07 | 39 | 38 | 1 | 2023-06-05 | 2024-02-28 | 182 | 25 | 157 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SAUGUS | 510472 | 1906 | 6 | Solar | 12_19W1 | 2023-04-06 15:37 | 2023-04-07 | 2 | 0 | 2 | 2023-04-11 | 2023-05-11 | 22 | 0 | 22 | [20 empty] | 2023-05-17 | 2023-04-06 16:55 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MARLBOROUGH | 517555 | 1752 | 15.2 | Solar | 05_311W2 | 2023-04-06 16:55 | 2023-04-07 | 1 | 0 | 1 | 2023-04-10 | 2023-05-08 | 20 | 0 | 20 | [20 empty] | 2023-05-09 |  | 2024-05-10 | Yes | EXP |  | 2023-07-04 | 2023-11-06 | 126 | 0 | 126 |  |  | 2023-11-14 | Connected |  | No
National Grid | WILBRAHAM | 517065 | 1095 | 20 | Solar | 09_507L3 | 2023-04-07 10:23 | 2023-04-10 | 1 | 0 | 1 | 2023-04-11 | 2023-05-08 | 19 | 0 | 19 | [20 empty] | 2023-05-08 |  | 2024-06-12 |  | EXP | [8 empty] | 2023-06-23 | Connected |  | No
National Grid | SALEM | 492195 | 1970 | 750 | Solar | 12_49W4 | 2023-04-07 11:35 | 2023-04-10 | 44 | 34 | 10 | [10 empty] | 2023-06-13 | 2023-07-12 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | REVERE | 514805 | 2151 | 6 | Solar | 12_35J1 | 2023-04-07 12:33 | 2023-04-10 | 1 | 0 | 1 | 2023-04-11 | 2023-05-16 | 25 | 0 | 25 | 2023-06-26 | 2023-08-23 | 42 | 0 | 42 | [5 empty] | 2023-06-26 | 2023-08-23 | 42 | 0 | 42 | [5 empty] | 2023-08-24 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 515931 | 1844 | 3.8 | Solar | 14_5J43 | 2023-04-07 13:05 | 2023-04-10 | 149 | 148 | 1 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | AUBURN | 514516 | 1501 | 14.79 | Solar | 01_26W1 | 2023-04-07 13:46 | 2023-04-10 | 8 | 7 | 1 | 2023-04-21 | 2023-06-28 | 46 | 25 | 21 | [20 empty] | 2023-07-05 |  | 2024-09-28 |  | EXP | [8 empty] | 2023-10-06 | Connected |  | No
National Grid | RANDOLPH | 516478 | 2368 | 150 | Solar | 07_75W7 | 2023-04-07 16:20 | 2023-04-10 | 9 | 0 | 9 | [10 empty] | 2023-04-24 | 2023-05-24 | 23 | 2 | 21 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | REHOBOTH | 517932 | 2769 | 13.05 | Solar | 05_7L5 | 2023-04-10 10:36 | 2023-04-11 | 3 | 2 | 1 | 2023-04-14 | 2023-06-30 | 54 | 30 | 24 | [20 empty] | 2023-07-07 |  | 2024-07-20 |  | EXP | [8 empty] | 2023-07-26 | Connected |  | No
National Grid | NORTHBOROUGH | 495314 | 1532 | 11.136 | Solar | 05_314W4 | 2023-04-10 12:55 | 2023-04-11 | 15 | 13 | 2 | 2023-05-03 | 2023-05-25 | 17 | 0 | 17 | [20 empty] | 2023-05-26 |  | 2024-07-14 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | NORTHAMPTON | 477384 | 1060 | 10 | Solar | 09_901W3 | 2023-04-10 15:27 | 2023-04-11 | 1 | 0 | 1 | 2023-04-12 | 2023-05-12 | 22 | 0 | 22 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ADAMS | 515158 | 1220 | 6 | Solar | 09_1021W1 | 2023-04-11 08:24 | 2023-04-12 | 3 | 0 | 3 | 2023-04-18 | 2023-05-18 | 23 | 0 | 23 | [20 empty] | 2023-05-22 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WARE | 518320 | 1082 | 10.73 | Solar | 09_509L2 | 2023-04-11 10:16 | 2023-04-12 | 3 | 1 | 2 | 2023-04-18 | 2023-06-01 | 32 | 10 | 22 | [20 empty] | 2023-06-06 |  | 2024-06-10 |  | EXP | [8 empty] | 2023-09-26 | Connected |  | Yes
National Grid | HOLBROOK | 512728 | 2343 | 6 | Solar | 07_2W1 | 2023-04-11 10:23 | 2023-04-12 | 3 | 0 | 3 | 2023-04-18 | 2023-05-16 | 21 | 0 | 21 | [20 empty] | 2023-05-23 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ANDOVER | 518526 | 1810 | 8.99 | Solar | 14_54L3 | 2023-04-11 17:06 | 2023-04-12 | 2 | 1 | 1 | 2023-04-13 | 2023-06-01 | 34 | 12 | 22 | [20 empty] | 2023-06-02 | 2023-04-12 13:52 | 2024-06-04 |  | EXP | [8 empty] | 2023-09-18 | Connected |  | No
National Grid | LEOMINSTER | 502848 | 1453 | 14.79 | Solar | 01_225W4 | 2023-04-12 13:52 | 2023-04-13 | 3 | 1 | 2 | 2023-04-18 | 2023-05-17 | 22 | 0 | 22 | [20 empty] | 2023-05-18 |  | 2024-05-24 | Yes | EXP | [8 empty] | 2023-07-18 | Connected |  | No
National Grid | BILLERICA | 448098 | 1821 | 280 | Solar | 14_92L2 | 2023-04-13 11:56 | 2023-04-14 | 80 | 70 | 10 | [10 empty] | 2023-08-10 | 2023-09-07 | 20 | 0 | 20 | [11 empty] | 2023-04-13 14:11 |  |  | STD | [9 empty] | Study |  | No
National Grid | LOWELL | 513162 | 1851 | 5.67 | Solar | 14_16L3 | 2023-04-13 14:11 | 2023-04-14 | 3 | 1 | 2 | 2023-04-20 | 2023-05-23 | 25 | 4 | 21 | [20 empty] | 2023-05-25 |  | 2024-06-09 | Yes | EXP | [8 empty] | 2023-10-11 | Connected |  | No
National Grid | LAWRENCE | 501293 | 1841 | 6 | Solar | 14_74L6 | 2023-04-13 16:05 | 2023-04-14 | 202 | 198 | 4 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GLOUCESTER | 516409 | 1930 | 15.007 | Solar | 12_51T1 | 2023-04-14 10:55 | 2023-04-18 | 2 | 0 | 2 | 2023-04-20 | 2023-05-18 | 21 | 0 | 21 | [20 empty] | 2023-05-23 | 2023-04-14 11:39 | 2024-08-02 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | FLORENCE | 514076 | 1062 | 9.86 | Solar | 09_909W1 | 2023-04-14 11:39 | 2023-04-18 | 2 | 0 | 2 | 2023-04-20 | 2023-05-22 | 24 | 3 | 21 | [20 empty] | 2023-05-24 |  | 2024-06-06 | Yes | EXP |  | 2023-08-01 | 2023-08-04 | 4 | 0 | 4 |  |  | 2023-08-28 | Connected |  | No
National Grid | SUTTON | 519333 | 1590 | 18 | Battery Add-On | 01_304W5 | 2023-04-14 15:21 | 2023-04-18 | 5 | 0 | 5 | 2023-04-25 | 2024-03-20 | 226 | 204 | 22 | [20 empty] | 2024-03-26 |  | 2025-03-29 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 518145 | 2723 | 14.5 | Solar | 05_106W82 | 2023-04-15 17:22 | 2023-04-18 | 2 | 0 | 2 | 2023-04-20 | 2023-05-26 | 28 | 24 | 4 | [20 empty] | 2023-10-18 |  | 2024-11-14 |  | EXP | [8 empty] | 2024-01-22 | Connected |  | No
National Grid | LEOMINSTER | 495510 | 1453 | 1600 | Solar | 01_219W5 | 2023-04-16 20:08 | 2023-04-18 | 51 | 41 | 10 | [10 empty] | 2023-06-30 | 2023-07-26 | 19 | 3 | 16 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | LAWRENCE | 518138 | 1843 | 10 | Solar | 14_61L3 | 2023-04-17 08:06 | 2023-04-18 | 2 | 0 | 2 | 2023-04-20 | 2023-06-12 | 38 | 17 | 21 | [20 empty] | 2023-06-14 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOUTHBOROUGH | 516469 | 1772 | 6 | Solar | 05_310W5 | 2023-04-17 10:27 | 2023-04-18 | 1 | 0 | 1 | 2023-04-19 | 2023-08-24 | 89 | 67 | 22 | [20 empty] | 2023-08-29 |  | 2024-08-29 |  | EXP | [8 empty] | 2023-11-08 | Connected |  | No
National Grid | HAMPDEN | 519840 | 1036 | 15.2 | Solar | 09_139L1 | 2023-04-18 09:44 | 2023-04-19 | 4 | 0 | 4 | 2023-04-25 | 2023-05-25 | 23 | 0 | 23 | [20 empty] | 2023-05-30 |  | 2024-06-01 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HAVERHILL | 519947 | 1830 | 19.6 | Solar | 14_76L1 | 2023-04-18 12:05 | 2023-04-19 | 3 | 0 | 3 | 2023-04-24 | 2024-02-27 | 211 | 192 | 19 | [20 empty] | 2024-03-04 |  | 2025-03-08 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | BELCHERTOWN | 515884 | 1007 | 15 | Solar | 09_509L2 | 2023-04-18 14:44 | 2023-04-19 | 2 | 0 | 2 | 2023-04-21 | 2023-06-21 | 41 | 25 | 16 | [20 empty] | 2023-06-26 |  | 2024-08-25 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | WILBRAHAM | 520047 | 1095 | 12.025 | Solar | 09_507L2 | 2023-04-18 17:02 | 2023-04-19 | 17 | 13 | 4 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RANDOLPH | 517154 | 2368 | 7.875 | Solar | 07_5W2 | 2023-04-19 09:42 | 2023-04-20 | 1 | 0 | 1 | 2023-04-21 | 2023-06-26 | 45 | 22 | 23 | 2023-07-18 | 2023-08-24 | 23 | 0 | 23 | [5 empty] | 2023-07-18 | 2023-08-24 | 23 | 0 | 23 | [5 empty] | 2023-08-28 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HANOVER | 520180 | 2339 | 20 | Solar | 07_95W1 | 2023-04-19 11:26 | 2023-04-20 | 3 | 0 | 3 | 2023-04-25 | 2024-03-13 | 221 | 202 | 19 | [20 empty] | 2024-03-18 | 2023-04-19 13:26 |  |  | EXP | [9 empty] | Conditional Approval |  | No
National Grid | BELLINGHAM | 516130 | 2019 | 5 | Solar | 05_344W4 | 2023-04-19 13:26 | 2023-04-20 | 5 | 2 | 3 | 2023-04-26 | 2023-07-28 | 65 | 42 | 23 | [20 empty] | 2023-08-02 |  | 2024-09-21 | Yes | EXP |  | 2024-02-29 | 2024-03-26 | 27 | 0 | 27 |  |  | 2024-03-28 | Connected |  | Yes
National Grid | LAWRENCE | 520212 | 1841 | 15.08 | Solar | 14_6J1 | 2023-04-19 13:28 | 2023-04-20 | 1 | 0 | 1 | 2023-04-21 | 2023-05-18 | 20 | 0 | 20 | [20 empty] | 2023-05-25 |  | 2024-05-26 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | ABINGTON | 471854 | 2351 | 14900 | Other | 07_93W43 | 2023-04-19 13:31 | 2023-04-20 | 21 | 11 | 10 | [10 empty] | 2023-05-19 | 2023-06-21 | 22 | 2 | 20 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | BEVERLY | 492383 | 1915 | 3.84 | Solar | 12_12L2 | 2023-04-19 14:21 | 2023-04-20 | 3 | 0 | 3 | 2023-04-25 | 2023-05-25 | 23 | 0 | 23 | [20 empty] | 2023-05-30 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | THREE RIVERS | 520289 | 1080 | 12.47 | Solar | 09_514L1 | 2023-04-19 14:32 | 2023-04-20 | 16 | 13 | 3 | 2023-05-11 | 2023-06-14 | 25 | 7 | 18 | [20 empty] | 2023-06-22 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEBSTER | 519952 | 1570 | 11.4 | Solar | 01_412L1 | 2023-04-19 14:52 | 2023-04-20 | 6 | 5 | 1 | [10 empty] | 2023-04-27 | 2023-08-07 | 70 | 51 | 19 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | ATHOL | 520344 | 1331 | 14.79 | Solar | 09_702W2 | 2023-04-19 17:02 | 2023-04-20 | 10 | 7 | 3 | 2023-05-04 | 2023-10-16 | 112 | 97 | 15 | [20 empty] | 2023-10-17 |  | 2025-01-01 |  | EXP | [8 empty] | 2024-01-18 | Connected |  | No
National Grid | BELLINGHAM | 516573 | 2019 | 6 | Solar | 05_344W4 | 2023-04-20 05:36 | 2023-04-21 | 1 | 0 | 1 | 2023-04-24 | 2023-05-19 | 20 | 0 | 20 | [20 empty] | 2023-05-22 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEBSTER | 520273 | 1570 | 14.79 | Solar | 01_412L2 | 2023-04-20 08:52 | 2023-04-21 | 3 | 2 | 1 | 2023-04-25 | 2023-06-07 | 32 | 12 | 20 | [20 empty] | 2023-06-08 |  | 2024-09-14 |  | EXP | [8 empty] | 2023-10-12 | Connected |  | No
National Grid | AUBURN | 520407 | 1501 | 15 | Solar | 01_26W3 | 2023-04-20 11:35 | 2023-04-21 | 2 | 0 | 2 | 2023-04-25 | 2023-06-26 | 43 | 23 | 20 | [20 empty] | 2023-06-30 |  | 2024-08-18 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | WEYMOUTH | 520468 | 2190 | 20 | Solar | 07_8W1 | 2023-04-20 11:48 | 2023-04-21 | 2 | 0 | 2 | 2023-04-25 | 2023-05-25 | 23 | 2 | 21 | [20 empty] | 2023-05-26 |  | 2024-08-03 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | MILLVILLE | 520207 | 1529 | 17.98 | Solar | 05_321W9 | 2023-04-20 13:55 | 2023-04-21 | 2 | 0 | 2 | 2023-04-25 | 2024-03-07 | 218 | 75 | 143 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | AUBURN | 520551 | 1501 | 16 | Solar | 01_26W3 | 2023-04-20 14:01 | 2023-04-21 | 5 | 3 | 2 | 2023-04-28 | 2024-04-01 | 231 | 210 | 21 | [20 empty] | 2024-04-04 |  |  |  | EXP | [9 empty] | Conditional Approval |  | No
National Grid | FRANKLIN | 519911 | 2038 | 15.2 | Solar | 05_344W5 | 2023-04-20 16:22 | 2023-04-21 | 38 | 37 | 1 | 2023-06-15 | 2023-07-14 | 20 | 0 | 20 | [20 empty] | 2023-07-17 |  | 2024-07-18 |  | EXP | [8 empty] | 2023-09-08 | Connected |  | No
National Grid | FALL RIVER | 519921 | 2721 | 6 | Solar | 05_115W53 | 2023-04-21 07:17 | 2023-04-24 | 1 | 0 | 1 | 2023-04-25 | 2023-05-30 | 25 | 0 | 25 | [20 empty] | 2023-06-05 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LENOX | 509170 | 1240 | 11900 | Other | 09_1103W2 | 2023-04-21 11:14 | 2023-04-24 | 14 | 4 | 10 | [10 empty] | 2023-05-12 | 2023-06-09 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | MENDON | 495154 | 1756 | 11.4 | Solar | 05_332W1 | 2023-04-21 11:33 | 2023-04-24 | 1 | 0 | 1 | 2023-04-25 | 2023-07-26 | 64 | 42 | 22 | [20 empty] | 2023-08-01 |  | 2024-08-19 |  | EXP | [8 empty] | 2023-10-31 | Connected |  | Yes
National Grid | STOUGHTON | 501289 | 2072 | 7.6 | Solar | 07_913W17 | 2023-04-21 13:03 | 2023-04-24 | 1 | 0 | 1 | 2023-04-25 | 2024-01-19 | 158 | 133 | 25 | [20 empty] | 2024-01-23 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEICESTER | 520923 | 1524 | 20 | Solar | 01_21W1 | 2023-04-21 16:02 | 2023-04-24 | 1 | 0 | 1 | 2023-04-25 |  | 243 | 196 | 47 | [21 empty] | 2023-04-24 06:06 |  |  | EXP | [9 empty] | Screening |  | No
National Grid | HOLBROOK | 519721 | 2343 | 7.6 | Solar | 07_2W1 | 2023-04-24 06:06 | 2023-04-25 | 24 | 22 | 2 | 2023-05-26 | 2023-06-23 | 19 | 0 | 19 | [20 empty] | 2023-06-28 | 2023-04-24 06:16 | 2024-07-06 | Yes | EXP | [8 empty] | 2023-09-22 | Connected |  | Yes
National Grid | RANDOLPH | 517602 | 2368 | 3.8 | Solar | 07_97W2 | 2023-04-24 06:16 | 2023-04-25 | 2 | 0 | 2 | 2023-04-27 | 2023-06-08 | 31 | 6 | 25 | [20 empty] | 2023-06-12 | 2023-04-24 10:08 | 2024-08-22 | Yes | EXP | [8 empty] | 2023-12-12 | Connected |  | No
National Grid | METHUEN | 515458 | 1844 | 12.6 | Solar | 14_74L1 | 2023-04-24 10:08 | 2023-04-25 | 2 | 0 | 2 | 2023-04-27 | 2023-05-30 | 23 | 0 | 23 | [20 empty] | 2023-06-05 |  | 2024-11-05 | Yes | EXP |  | 2023-09-12 | 2023-10-24 | 43 | 0 | 43 |  |  | 2023-11-18 | Connected |  | No
National Grid | SALISBURY | 521126 | 1952 | 16 | Solar | 14_7L4 | 2023-04-24 11:54 | 2023-04-25 | 4 | 1 | 3 | 2023-05-01 | 2023-06-01 | 23 | 0 | 23 | [20 empty] | 2023-06-02 |  | 2024-07-30 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | RANDOLPH | 518780 | 2368 | 7.54 | Solar | 07_5W4 | 2023-04-24 13:24 | 2023-04-25 | 2 | 0 | 2 | 2023-04-27 | 2023-06-01 | 25 | 0 | 25 | [20 empty] | 2023-06-05 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEYMOUTH | 520939 | 2189 | 67.3 | Solar | 07_12W6 | 2023-04-24 16:05 | 2023-04-25 | 34 | 26 | 8 | 2023-06-13 | 2023-07-19 | 25 | 0 | 25 | [20 empty] | 2023-08-02 | 2023-04-25 10:00 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 489910 | 2301 | 10 | Solar | 07_91W49 | 2023-04-25 10:00 | 2023-04-26 | 20 | 19 | 1 | 2023-05-23 | 2023-06-21 | 20 | 0 | 20 | [20 empty] | 2023-06-27 |  | 2025-02-04 | Yes | EXP |  | 2023-10-18 | 2023-11-03 | 17 | 0 | 17 |  |  |  | Completion Documents |  | No
National Grid | WESTMINSTER | 487743 | 1473 | 4999 | Other | 01_610W3 | 2023-04-26 10:40 | 2023-04-27 | 8 | 2 | 6 | [10 empty] | 2023-05-09 | 2023-05-31 | 16 | 0 | 16 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | DRACUT | 521839 | 1826 | 4.93 | Solar | 14_75L5 | 2023-04-26 12:07 | 2023-04-27 | 55 | 54 | 1 | 2023-07-18 | 2024-02-21 | 149 | 126 | 23 | [20 empty] | 2024-02-26 |  | 2025-03-19 |  | EXP | [8 empty] | 2024-03-20 | Connected |  | No
National Grid | EASTON | 521894 | 2334 | 14.97 | Solar | 07_92W78 | 2023-04-26 13:07 | 2023-04-27 | 4 | 2 | 2 | 2023-05-02 | 2023-06-30 | 42 | 23 | 19 | [20 empty] | 2023-07-03 |  | 2024-08-16 |  | EXP | [8 empty] | 2023-12-27 | Connected |  | No
National Grid | BEVERLY | 521346 | 1915 | 10 | Solar | 12_51L1 | 2023-04-26 13:30 | 2023-06-02 | 2 | 0 | 2 | 2023-06-06 | 2023-07-12 | 26 | 3 | 23 | [20 empty] | 2023-07-14 | 2023-04-26 14:19 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BEVERLY | 516020 | 1915 | 5 | Solar | 12_72L1 | 2023-04-26 14:19 | 2023-04-27 | 22 | 21 | 1 | 2023-05-30 | 2023-06-28 | 21 | 0 | 21 | [20 empty] | 2023-06-28 | 2023-04-26 14:59 | 2024-08-18 | Yes | EXP |  | 2023-10-25 | 2023-10-25 | 1 | 0 | 1 |  |  | 2023-11-17 | Connected |  | No
National Grid | LAWRENCE | 519281 | 1843 | 7.6 | Solar | 14_61L3 | 2023-04-26 14:59 | 2023-04-27 | 4 | 0 | 4 | 2023-05-03 | 2023-06-06 | 24 | 0 | 24 | [20 empty] | 2023-06-07 | 2023-04-26 15:04 | 2024-08-02 | Yes | EXP |  | 2023-09-12 | 2023-10-05 | 24 | 0 | 24 |  |  | 2023-10-16 | Connected |  | No
National Grid | SAUGUS | 519497 | 1906 | 10 | Solar | 12_19W1 | 2023-04-26 15:04 | 2023-04-27 | 10 | 6 | 4 | 2023-05-10 | 2023-06-12 | 23 | 0 | 23 | [20 empty] | 2023-06-14 |  | 2024-08-25 | Yes | EXP |  | 2024-01-12 | 2024-03-04 | 53 | 0 | 53 |  |  | 2024-03-08 | Connected |  | No
National Grid | BROCKTON | 520042 | 2301 | 7.83 | Solar | 07_98W46 | 2023-04-27 14:38 | 2023-04-28 | 12 | 9 | 3 | 2023-05-16 | 2023-06-09 | 18 | 0 | 18 | [20 empty] | 2023-06-13 |  | 2024-07-28 |  | EXP | [8 empty] | 2023-10-20 | Connected |  | No
National Grid | METHUEN | 521781 | 1844 | 11.04 | Solar | 14_43L4 | 2023-04-27 16:07 | 2023-04-28 | 136 | 135 | 1 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | DRACUT | 466563 | 1826 | 600 | Other | 14_75L3 | 2023-04-27 16:46 | 2023-04-28 | 43 | 33 | 10 | [10 empty] | 2023-06-30 | 2023-07-28 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | NORTHBRIDGE | 520350 | 1588 | 9.86 | Solar | 05_320W3 | 2023-04-27 17:06 | 2023-04-28 | 7 | 4 | 3 | 2023-05-09 | 2023-07-12 | 43 | 25 | 18 | [20 empty] | 2023-07-13 |  | 2024-08-11 |  | EXP | [8 empty] | 2023-10-04 | Connected |  | Yes
National Grid | LYNN | 520372 | 1902 | 6 | Solar | 12_29W4 | 2023-04-28 03:48 | 2023-05-01 | 3 | 1 | 2 | 2023-05-03 | 2023-06-05 | 23 | 0 | 23 | [20 empty] | 2023-06-05 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BLACKSTONE | 520510 | 1504 | 3.48 | Solar | 05_321W6 | 2023-04-28 04:03 | 2023-05-01 | 3 | 1 | 2 | 2023-05-03 | 2023-06-05 | 23 | 0 | 23 | [20 empty] | 2023-06-05 |  | 2024-06-05 |  | EXP | [8 empty] | 2023-07-07 | Connected |  | No
National Grid | EAST LONGMEADOW | 515456 | 1028 | 7.6 | Solar | 09_508L1 | 2023-04-28 04:04 | 2023-05-01 | 1 | 0 | 1 | 2023-05-02 | 2023-06-05 | 24 | 0 | 24 | [20 empty] | 2023-06-08 |  | 2024-06-13 |  | EXP | [8 empty] | 2023-08-01 | Connected |  | No
National Grid | NORTHAMPTON | 507310 | 1060 | 3.8 | Solar | 09_909W1 | 2023-04-28 04:19 | 2023-05-01 | 1 | 0 | 1 | 2023-05-02 | 2023-06-05 | 24 | 0 | 24 | [20 empty] | 2023-06-08 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WARE | 519111 | 1082 | 7.6 | Solar | 09_501L2 | 2023-04-28 05:42 | 2023-05-01 | 6 | 4 | 2 | 2023-05-09 | 2023-06-08 | 22 | 0 | 22 | [20 empty] | 2023-06-12 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CLINTON | 521794 | 1510 | 13 | Solar | 01_216W5 | 2023-04-28 12:19 | 2023-05-01 | 7 | 5 | 2 | 2023-05-09 | 2023-08-10 | 65 | 47 | 18 | [20 empty] | 2023-08-10 |  | 2024-09-14 |  | EXP | [8 empty] | 2023-12-11 | Connected |  | No
National Grid | MEDFORD | 522539 | 2155 | 15.2 | Solar | 12_37W5 | 2023-04-28 15:04 | 2023-05-01 | 27 | 26 | 1 | 2023-06-08 | 2023-07-06 | 19 | 0 | 19 | [20 empty] | 2023-07-10 |  | 2024-08-08 |  | EXP | [8 empty] | 2023-10-16 | Connected |  | No
National Grid | RANDOLPH | 516245 | 2368 | 75 | Solar | 07_75W7 | 2023-04-28 15:26 | 2023-05-01 | 171 | 161 | 10 | [10 empty] | 2024-01-08 | 2024-02-07 | 22 | 0 | 22 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | CHELMSFORD | 517633 | 1824 | 72 | Solar | 14_16L1 | 2023-04-29 18:57 | 2023-05-01 | 171 | 161 | 10 | [10 empty] | 2024-01-08 | 2024-03-28 | 56 | 35 | 21 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | CHELMSFORD | 517634 | 1824 | 100 | Solar | 14_16L4 | 2023-04-29 19:57 | 2023-05-01 | 56 | 46 | 10 | [10 empty] | 2023-07-21 | 2024-01-09 | 117 | 96 | 21 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | MILFORD | 522693 | 1757 | 100 | Solar | 05_336W4 | 2023-04-29 21:01 | 2023-05-01 | 171 | 162 | 9 | [10 empty] | 2024-01-08 | 2024-02-07 | 22 | 0 | 22 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | BROCKTON | 519664 | 2302 | 6 | Solar | 07_69J1 | 2023-05-01 07:30 | 2023-05-02 | 1 | 0 | 1 | 2023-05-03 | 2023-06-02 | 23 | 2 | 21 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EAST LONGMEADOW | 519747 | 1028 | 10 | Solar | 09_508L1 | 2023-05-01 07:44 | 2023-05-02 | 2 | 0 | 2 | 2023-05-04 | 2023-06-06 | 23 | 0 | 23 | [20 empty] | 2023-06-07 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SALEM | 522459 | 1970 | 34.6 | Solar | 12_1J7 | 2023-05-01 09:28 | 2023-05-02 | 1 | 0 | 1 | 2023-05-03 | 2023-05-25 | 17 | 0 | 17 | [20 empty] | 2023-05-31 |  | 2024-06-27 |  | EXP | [8 empty] | 2024-01-26 | Connected |  | No
National Grid | SAUGUS | 501622 | 1906 | 7.6 | Solar | 12_7J903 | 2023-05-01 11:30 | 2023-05-02 | 3 | 1 | 2 | 2023-05-05 | 2023-06-07 | 23 | 0 | 23 | 2023-06-14 | 2023-09-18 | 66 | 0 | 66 | [5 empty] | 2023-06-14 | 2023-09-18 | 66 | 0 | 66 | [5 empty] | 2023-09-29 | 2023-05-01 12:05 | 2024-10-27 |  | EXP |  | 2023-12-07 | 2023-12-06 | 0 | 0 | 0 |  |  | 2024-01-12 | Connected |  | Yes
National Grid | HOLBROOK | 513638 | 2343 | 7.6 | Solar | 07_2W1 | 2023-05-01 12:05 | 2023-05-02 | 14 | 13 | 1 | 2023-05-22 | 2023-06-23 | 23 | 0 | 23 | [20 empty] | 2023-06-27 |  | 2024-08-24 | Yes | EXP |  | 2023-09-28 | 2023-10-09 | 12 | 0 | 12 |  |  | 2023-10-24 | Connected |  | No
National Grid | EAST BRIDGEWATER | 491623 | 2333 | 7.6 | Solar | 07_797W23 | 2023-05-01 14:09 | 2023-05-02 | 1 | 0 | 1 | 2023-05-03 | 2023-06-05 | 23 | 0 | 23 | [20 empty] | 2023-06-06 |  | 2024-07-30 |  | EXP | [8 empty] | 2023-08-04 | Connected |  | Yes
National Grid | SWAMPSCOTT | 493073 | 1907 | 4999 | Other | 12_29W6 | 2023-05-01 15:15 | 2023-05-03 | 118 | 109 | 9 | [10 empty] | 2023-10-24 | 2023-12-09 | 33 | 16 | 17 | [14 empty] | STD | [9 empty] | Pending Withdraw |  | No
National Grid | WRENTHAM | 493072 | 2093 | 10000 | Other | 05_3422W3 | 2023-05-01 15:17 | 2023-05-02 | 40 | 30 | 10 | [10 empty] | 2023-06-30 | 2023-12-07 | 110 | 96 | 14 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | OXFORD | 489250 | 1540 | 7.6 | Solar | 01_406L4 | 2023-05-01 16:57 | 2023-05-02 | 53 | 25 | 28 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HANSON | 518671 | 2341 | 9.86 | Solar | 07_797W24 | 2023-05-01 17:04 | 2023-05-02 | 6 | 5 | 1 | 2023-05-10 | 2023-06-09 | 22 | 0 | 22 | [20 empty] | 2023-06-13 |  | 2024-06-15 |  | EXP | [8 empty] | 2023-08-01 | Connected |  | No
National Grid | BELLINGHAM | 521532 | 2019 | 7.6 | Solar | 05_344W4 | 2023-05-02 05:55 | 2023-05-03 | 2 | 0 | 2 | 2023-05-05 | 2023-10-03 | 104 | 76 | 28 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | DRACUT | 521189 | 1826 | 7.6 | Solar | 14_78L1 | 2023-05-02 10:24 | 2023-05-03 | 1 | 0 | 1 | 2023-05-04 | 2023-07-18 | 51 | 28 | 23 | [20 empty] | 2023-07-18 | 2023-05-02 10:39 | 2024-07-19 |  | EXP | [8 empty] | 2023-08-23 | Connected |  | No
National Grid | LAWRENCE | 507185 | 1843 | 10 | Solar | 14_8L1 | 2023-05-02 10:39 | 2023-05-03 | 28 | 25 | 3 | 2023-06-13 | 2023-07-13 | 21 | 0 | 21 | [20 empty] | 2023-07-14 | 2023-05-02 12:02 | 2024-08-11 | Yes | EXP | [9 empty] | Design |  | No
National Grid | RANDOLPH | 509035 | 2368 | 10 | Solar | 07_5W3 | 2023-05-02 12:02 | 2023-05-03 | 7 | 5 | 2 | 2023-05-12 | 2023-07-24 | 50 | 27 | 23 | [20 empty] | 2023-07-26 |  | 2025-02-15 | Yes | EXP |  | 2023-12-02 | 2023-12-02 | 1 | 0 | 1 |  |  |  | Completion Documents |  | Yes
National Grid | WEYMOUTH | 521091 | 2190 | 23 | Solar | 07_12W3 | 2023-05-02 12:44 | 2023-05-03 | 2 | 0 | 2 | 2023-05-05 | 2023-05-26 | 16 | 0 | 16 | [20 empty] | 2023-06-01 |  | 2024-06-15 |  | EXP | [8 empty] | 2024-02-09 | Connected |  | No
National Grid | ROCKPORT | 523300 | 1966 | 10 | Solar | 12_40J2 | 2023-05-02 13:56 | 2023-05-03 | 2 | 0 | 2 | 2023-05-05 | 2023-10-12 | 160 | 137 | 23 | [20 empty] | 2023-10-16 |  | 2024-11-10 |  | EXP | [8 empty] | 2024-02-03 | Connected |  | No
National Grid | FALL RIVER | 521951 | 2720 | 6 | Solar | 05_28W50 | 2023-05-03 10:02 | 2023-05-04 | 2 | 0 | 2 | 2023-05-08 | 2023-06-06 | 21 | 0 | 21 | [20 empty] | 2023-06-08 |  | 2024-07-29 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 520774 | 1604 | 6 | Solar | 01_10J383 | 2023-05-03 10:17 | 2023-05-04 | 2 | 0 | 2 | 2023-05-08 | 2023-10-11 | 108 | 25 | 83 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SAUGUS | 519264 | 1906 | 3.8 | Solar | 12_7J903 | 2023-05-03 10:38 | 2023-05-04 | 3 | 0 | 3 | 2023-05-09 | 2023-06-07 | 21 | 0 | 21 | 2023-06-14 | 2023-09-15 | 65 | 0 | 65 | [5 empty] | 2023-06-14 | 2023-09-15 | 65 | 0 | 65 | [5 empty] | 2023-09-29 |  | 2024-10-22 |  | EXP |  | 2024-01-03 | 2024-01-09 | 7 | 0 | 7 |  |  | 2024-01-13 | Connected |  | No
National Grid | MILFORD | 521118 | 1757 | 6 | Solar | 05_335W4 | 2023-05-03 10:57 | 2023-05-04 | 3 | 0 | 3 | 2023-05-09 | 2023-06-09 | 23 | 0 | 23 | [20 empty] | 2023-06-14 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RANDOLPH | 522183 | 2368 | 6 | Solar | 07_5W3 | 2023-05-03 11:23 | 2023-05-04 | 1 | 0 | 1 | 2023-05-05 | 2023-06-05 | 21 | 0 | 21 | [20 empty] | 2023-06-06 | 2023-05-03 11:47 | 2024-06-13 |  | EXP | [8 empty] | 2023-08-04 | Connected |  | No
National Grid | LEOMINSTER | 519207 | 1453 | 10 | Solar | 01_207W3 | 2023-05-03 11:47 | 2023-05-04 | 1 | 0 | 1 | 2023-05-05 | 2023-05-26 | 16 | 0 | 16 | [20 empty] | 2023-06-05 |  | 2024-06-15 | Yes | EXP |  | 2023-08-26 | 2023-10-19 | 55 | 0 | 55 |  |  | 2023-10-28 | Connected |  | No
National Grid | LEOMINSTER | 505826 | 1453 | 6 | Solar | 01_219W5 | 2023-05-03 13:12 | 2023-05-04 | 1 | 0 | 1 | 2023-05-05 | 2023-06-06 | 22 | 0 | 22 | [20 empty] | 2023-06-07 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SOUTHBRIDGE | 521609 | 1550 | 7.6 | Solar | 01_413L2 | 2023-05-03 14:51 | 2023-05-04 | 1 | 0 | 1 | 2023-05-05 | 2023-06-06 | 22 | 0 | 22 | [20 empty] | 2023-06-07 | 2023-05-04 06:38 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 521365 | 2302 | 10 | Solar | 07_911W77 | 2023-05-04 06:38 | 2023-05-05 | 2 | 0 | 2 | 2023-05-09 | 2023-06-06 | 20 | 0 | 20 | [20 empty] | 2023-06-07 |  | 2024-07-06 | Yes | EXP |  | 2023-09-06 | 2023-10-02 | 27 | 0 | 27 |  |  | 2023-10-06 | Connected |  | No
National Grid | GRANBY | 522509 | 1033 | 12.18 | Solar | 09_527L1 | 2023-05-04 13:18 | 2023-05-05 | 2 | 0 | 2 | 2023-05-09 | 2023-06-20 | 30 | 11 | 19 | [20 empty] | 2023-06-23 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GARDNER | 524121 | 1440 | 14.5 | Solar | 01_607W1 | 2023-05-04 16:21 | 2023-05-05 | 24 | 22 | 2 | 2023-06-08 | 2023-09-08 | 64 | 44 | 20 | [20 empty] | 2023-09-13 |  | 2024-09-13 |  | EXP | [8 empty] | 2023-12-13 | Connected |  | Yes
National Grid | BOLTON | 524294 | 1740 | 15.2 | Solar | 01_225W1 | 2023-05-05 09:48 | 2023-05-08 | 1 | 0 | 1 | 2023-05-09 | 2023-06-05 | 19 | 0 | 19 | [20 empty] | 2023-06-06 |  | 2024-06-06 |  | EXP | [8 empty] | 2023-07-11 | Connected |  | No
National Grid | HOLBROOK | 523316 | 2343 | 10 | Solar | 07_10W1 | 2023-05-05 11:34 | 2023-05-08 | 1 | 0 | 1 | 2023-05-09 | 2023-06-07 | 20 | 0 | 20 | [20 empty] | 2023-06-08 |  | 2024-11-16 |  | EXP | [8 empty] | 2023-11-28 | Connected |  | Yes
National Grid | WEYMOUTH | 520867 | 2191 | 10.15 | Solar | 07_6W2 | 2023-05-05 12:32 | 2023-05-08 | 1 | 0 | 1 | 2023-05-09 | 2023-06-06 | 20 | 3 | 17 | [20 empty] | 2023-06-07 |  | 2024-06-12 |  | EXP | [8 empty] | 2023-10-06 | Connected |  | No
National Grid | AUBURN | 455849 | 1501 | 299.7 | Solar | 01_26W2 | 2023-05-05 13:31 | 2023-05-08 | 120 | 112 | 8 | [29 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | GRANBY | 501268 | 1033 | 2.03 | Solar | 09_527L1 | 2023-05-05 13:45 | 2023-05-08 | 1 | 0 | 1 | 2023-05-09 | 2023-12-12 | 149 | 134 | 15 | [20 empty] | 2023-12-13 | 2023-05-05 14:46 | 2025-01-07 |  | EXP | [8 empty] | 2024-01-29 | Connected |  | No
National Grid | AUBURN | 523508 | 1501 | 3 | Solar | 01_26W1 | 2023-05-05 14:46 | 2023-05-08 | 1 | 0 | 1 | 2023-05-09 | 2023-06-06 | 20 | 0 | 20 | [20 empty] | 2023-06-12 | 2023-05-08 01:49 | 2024-06-21 | Yes | EXP |  | 2023-08-19 | 2023-09-29 | 42 | 0 | 42 |  |  | 2023-10-10 | Connected |  | No
National Grid | DUDLEY | 523805 | 1571 | 6.67 | Solar | 01_412L5 | 2023-05-08 01:49 | 2023-05-09 | 4 | 2 | 2 | 2023-05-15 | 2023-06-08 | 18 | 0 | 18 | [20 empty] | 2023-06-12 | 2023-05-08 08:16 | 2024-07-12 | Yes | EXP | [8 empty] | 2023-10-23 | Connected |  | No
National Grid | ROCKPORT | 522876 | 1966 | 10 | Solar | 12_40L1 | 2023-05-08 08:16 | 2023-05-09 | 1 | 0 | 1 | 2023-05-10 | 2023-06-06 | 19 | 0 | 19 | [20 empty] | 2023-06-07 | 2023-05-08 10:14 | 2024-06-20 | Yes | EXP |  | 2023-08-19 | 2023-10-18 | 61 | 0 | 61 |  |  | 2023-10-23 | Connected |  | No
National Grid | UPTON | 523162 | 1568 | 10 | Solar | 05_335W3 | 2023-05-08 10:14 | 2023-05-09 | 1 | 0 | 1 | 2023-05-10 | 2023-06-12 | 24 | 4 | 20 | [20 empty] | 2023-06-15 | 2023-05-08 11:19 | 2024-08-23 | Yes | EXP |  | 2023-08-02 | 2023-10-30 | 90 | 0 | 90 |  |  | 2024-01-09 | Connected |  | No
National Grid | ATHOL | 506129 | 1331 | 10 | Solar | 09_702W1 | 2023-05-08 11:19 | 2023-05-09 | 1 | 0 | 1 | 2023-05-10 | 2023-06-12 | 23 | 0 | 23 | [20 empty] | 2023-06-14 |  | 2024-07-12 | Yes | EXP |  | 2023-09-07 | 2023-10-25 | 49 | 0 | 49 |  |  | 2023-10-27 | Connected |  | No
National Grid | HAMILTON | 524266 | 1982 | 9.28 | Solar | 12_51T2 | 2023-05-08 11:44 | 2023-05-09 | 2 | 0 | 2 | 2023-05-11 | 2023-07-24 | 50 | 25 | 25 | [20 empty] | 2023-07-30 | 2023-05-08 12:13 | 2024-08-22 |  | EXP | [8 empty] | 2023-10-11 | Connected |  | No
National Grid | UPTON | 524693 | 1568 | 15.2 | Solar | 05_335W3 | 2023-05-08 12:13 | 2023-05-09 | 2 | 0 | 2 | 2023-05-11 | 2023-06-07 | 19 | 0 | 19 | [20 empty] | 2023-06-12 |  | 2024-12-07 | Yes | EXP |  | 2023-09-26 | 2023-11-17 | 53 | 0 | 53 |  |  | 2024-01-16 | Connected |  | No
National Grid | OXFORD | 524689 | 1540 | 17.6 | Solar | 01_406L3 | 2023-05-08 12:31 | 2023-05-09 | 2 | 0 | 2 | 2023-05-11 | 2024-02-28 | 199 | 180 | 19 | [20 empty] | 2024-03-05 |  | 2025-03-12 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | CLINTON | 486664 | 1510 | 4999 | Solar | 01_216W2 | 2023-05-08 16:42 | 2023-05-09 | 11 | 1 | 10 | [10 empty] | 2023-05-23 | 2023-05-23 | 1 | 0 | 1 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | SWANSEA | 524644 | 2777 | 16.48 | Solar | 05_11W83 | 2023-05-09 09:15 | 2023-05-10 | 1 | 0 | 1 | 2023-05-11 | 2024-02-26 | 197 | 176 | 21 | [20 empty] | 2024-02-29 |  | 2025-03-05 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | CLINTON | 515975 | 1510 | 7.6 | Solar | 01_216W6 | 2023-05-09 09:30 | 2023-05-10 | 68 | 66 | 2 | 2023-08-17 | 2023-09-07 | 15 | 0 | 15 | [20 empty] | 2023-09-12 | 2023-05-09 10:55 | 2024-11-23 |  | EXP | [8 empty] | 2023-12-09 | Connected |  | No
National Grid | MEDFORD | 521915 | 2155 | 10 | Solar | 12_17J6 | 2023-05-09 10:55 | 2023-05-10 | 2 | 0 | 2 | 2023-05-12 | 2023-06-12 | 22 | 1 | 21 | [20 empty] | 2023-06-15 | 2023-05-09 11:06 | 2025-01-14 | Yes | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RANDOLPH | 431236 | 2368 | 8.12 | Solar | 07_5W4 | 2023-05-09 11:06 | 2023-05-10 | 3 | 2 | 1 | 2023-05-15 | 2023-06-15 | 23 | 0 | 23 | [20 empty] | 2023-06-15 |  | 2024-06-20 | Yes | EXP |  | 2023-12-07 | 2023-12-12 | 6 | 0 | 6 |  |  | 2023-12-18 | Connected |  | No
National Grid | SOUTH EASTON | 525072 | 2375 | 10 | Solar | 07_92W54 | 2023-05-09 13:02 | 2023-05-10 | 2 | 0 | 2 | 2023-05-12 | 2023-07-21 | 49 | 27 | 22 | [20 empty] | 2023-07-25 |  | 2024-11-06 |  | EXP | [8 empty] | 2023-11-14 | Connected |  | No
National Grid | LEOMINSTER | 520020 | 1453 | 250 | Solar | 01_219W4 | 2023-05-09 13:57 | 2023-05-10 | 53 | 43 | 10 | [10 empty] | 2023-07-26 | 2023-08-22 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | MEDFORD | 506789 | 2155 | 5.04 | Solar | 12_37W5 | 2023-05-09 14:11 | 2023-05-10 | 2 | 0 | 2 | 2023-05-12 | 2023-06-13 | 22 | 0 | 22 | [20 empty] | 2023-06-21 |  | 2024-07-30 |  | EXP | [8 empty] | 2023-08-19 | Connected |  | No
National Grid | ANDOVER | 501405 | 1810 | 250 | Solar | 14_8L1 | 2023-05-10 09:40 | 2023-05-11 | 15 | 5 | 10 | [10 empty] | 2023-06-01 | 2023-07-07 | 25 | 0 | 25 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | NORTHAMPTON | 510764 | 1060 | 7.54 | Solar | 09_901W3 | 2023-05-10 10:17 | 2023-05-11 | 3 | 0 | 3 | 2023-05-16 | 2023-06-14 | 21 | 0 | 21 | [20 empty] | 2023-06-22 |  | 2024-07-30 |  | EXP | [8 empty] | 2023-09-30 | Connected |  | No
National Grid | BOXFORD | 525009 | 1921 | 13.824 | Solar | 14_56L3 | 2023-05-10 10:30 | 2023-05-11 | 6 | 4 | 2 | 2023-05-19 | 2023-07-10 | 35 | 12 | 23 | [20 empty] | 2023-07-12 | 2023-05-10 11:21 | 2024-08-01 |  | EXP | [8 empty] | 2024-02-09 | Connected |  | No
National Grid | CHESHIRE | 522477 | 1225 | 3 | Solar | 09_1021W2 | 2023-05-10 11:21 | 2023-05-11 | 1 | 0 | 1 | 2023-05-12 | 2023-06-14 | 23 | 0 | 23 | [20 empty] | 2023-06-22 |  | 2024-07-03 | Yes | EXP |  | 2023-09-08 | 2023-10-03 | 26 | 0 | 26 |  |  | 2023-10-19 | Connected |  | Yes
National Grid | LAWRENCE | 521435 | 1841 | 10.368 | Solar | 14_63L1 | 2023-05-10 12:34 | 2023-05-11 | 11 | 8 | 3 | 2023-05-26 | 2023-07-19 | 37 | 17 | 20 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 512389 | 1844 | 9.86 | Solar | 14_43L4 | 2023-05-10 12:44 | 2023-05-11 | 3 | 0 | 3 | 2023-05-16 | 2023-06-07 | 22 | 0 | 22 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | AMESBURY | 525541 | 1913 | 15 | Solar | 14_5J13 | 2023-05-10 14:35 | 2023-05-11 | 2 | 0 | 2 | 2023-05-15 | 2023-06-13 | 22 | 5 | 17 | [20 empty] | 2023-06-20 | 2023-05-10 15:43 | 2024-07-29 |  | EXP | [8 empty] | 2023-08-10 | Connected |  | Yes
National Grid | WINCHENDON | 522629 | 1475 | 10 | Solar | 01_612W1 | 2023-05-10 15:43 | 2023-05-11 | 3 | 2 | 1 | 2023-05-16 | 2023-06-16 | 23 | 0 | 23 | [20 empty] | 2023-06-16 |  | 2024-06-20 | Yes | EXP |  | 2023-07-07 | 2023-08-08 | 33 | 0 | 33 |  |  | 2023-08-25 | Connected |  | No
National Grid | BLACKSTONE | 525114 | 1504 | 20 | Solar | 05_108W60 | 2023-05-11 10:30 | 2023-05-12 | 45 | 42 | 3 | [10 empty] | 2023-07-19 | 2023-09-07 | 36 | 16 | 20 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | SEEKONK | 523179 | 2771 | 6 | Solar | 05_7L1 | 2023-05-11 11:35 | 2023-05-12 | 1 | 0 | 1 | 2023-05-15 | 2023-06-15 | 23 | 0 | 23 | [20 empty] | 2023-06-15 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ANDOVER | 495148 | 1810 | 15.2 | Solar | 14_54L3 | 2023-05-11 16:09 | 2023-05-12 | 2 | 0 | 2 | 2023-05-16 | 2023-07-24 | 47 | 25 | 22 | [21 empty] | 2023-05-12 08:49 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LEOMINSTER | 523383 | 1453 | 6 | Solar | 01_207W2 | 2023-05-12 08:49 | 2023-05-15 | 2 | 0 | 2 | 2023-05-17 | 2023-06-16 | 22 | 0 | 22 | [20 empty] | 2023-06-21 |  | 2024-07-23 | Yes | EXP |  | 2023-09-21 | 2023-10-24 | 34 | 0 | 34 |  |  | 2023-11-09 | Connected |  | No
National Grid | BROCKTON | 524386 | 2301 | 6 | Solar | 07_911W13 | 2023-05-12 09:44 | 2023-05-15 | 107 | 91 | 16 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LYNN | 526047 | 1905 | 7.6 | Solar | 12_19W1 | 2023-05-12 10:19 | 2023-05-15 | 1 | 0 | 1 | 2023-05-16 | 2023-06-07 | 16 | 0 | 16 | [20 empty] | 2023-06-08 | 2023-05-12 14:36 | 2024-07-26 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | STURBRIDGE | 520785 | 1566 | 10 | Solar | 01_413L2 | 2023-05-12 14:36 | 2023-05-15 | 2 | 0 | 2 | 2023-05-17 | 2023-06-08 | 16 | 0 | 16 | [20 empty] | 2023-06-12 |  | 2024-06-22 | Yes | EXP | [8 empty] | 2024-02-15 | Connected |  | No
National Grid | WILBRAHAM | 526173 | 1095 | 14.79 | Solar | 09_507L1 | 2023-05-12 14:42 | 2023-05-15 | 15 | 14 | 1 | 2023-06-06 | 2023-07-05 | 20 | 0 | 20 | [20 empty] | 2023-07-10 |  | 2024-07-27 |  | EXP | [8 empty] | 2023-09-13 | Connected |  | No
National Grid | GARDNER | 472560 | 1440 | 30 | Solar | 01_602W2 | 2023-05-14 21:13 | 2023-05-15 | 11 | 2 | 9 | [10 empty] | 2023-05-31 | 2023-09-01 | 66 | 41 | 25 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | SOMERSET | 510632 | 2726 | 30 | Solar | 05_11W82 | 2023-05-14 23:36 | 2023-05-15 | 11 | 2 | 9 | 2023-05-31 | 2023-09-01 | 66 | 42 | 24 | [20 empty] | 2023-11-01 |  | 2024-05-01 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | FOXBOROUGH | 513658 | 2035 | 487.5 | Solar | 05_3432W2 | 2023-05-15 10:08 | 2023-05-16 | 47 | 37 | 10 | [10 empty] | 2023-07-24 | 2023-08-18 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | LOWELL | 524377 | 1852 | 7.6 | Solar | 14_75L2 | 2023-05-15 10:31 | 2023-05-16 | 3 | 0 | 3 | 2023-05-19 | 2023-06-22 | 23 | 0 | 23 | 2023-06-26 | 2023-07-31 | 9 | 0 | 9 | [5 empty] | 2023-06-26 | 2023-07-31 | 9 | 0 | 9 | [5 empty] | 2023-07-18 |  | 2024-11-29 |  | EXP |  | 2023-11-04 | 2023-12-13 | 40 | 0 | 40 |  |  | 2023-12-28 | Connected |  | Yes
National Grid | METHUEN | 524456 | 1844 | 3.8 | Solar | 14_63L2 | 2023-05-15 10:39 | 2023-05-16 | 1 | 0 | 1 | 2023-05-17 | 2023-07-14 | 40 | 17 | 23 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTMINSTER | 523055 | 1473 | 7.6 | Solar | 01_602W2 | 2023-05-15 11:21 | 2023-05-16 | 0 | 0 | 0 | 2023-05-16 | 2024-02-28 | 195 | 34 | 161 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | TEWKSBURY | 525204 | 1876 | 4.41 | Solar | 14_59L3 | 2023-05-16 09:56 | 2023-05-17 | 1 | 0 | 1 | 2023-05-18 | 2023-07-18 | 42 | 24 | 18 | [20 empty] | 2023-07-24 |  | 2024-08-18 |  | EXP | [8 empty] | 2023-12-04 | Connected |  | Yes
National Grid | AUBURN | 524124 | 1501 | 8.41 | Solar | 01_26W2 | 2023-05-16 10:30 | 2023-05-17 | 9 | 8 | 1 | 2023-05-31 | 2023-06-28 | 20 | 0 | 20 | [20 empty] | 2023-06-29 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HARVARD | 505820 | 1451 | 12.18 | Solar | 01_201W2 | 2023-05-16 11:11 | 2023-05-17 | 3 | 2 | 1 | 2023-05-19 | 2023-10-10 | 98 | 79 | 19 | [20 empty] | 2023-10-11 |  | 2024-10-13 |  | EXP | [8 empty] | 2023-11-04 | Connected |  | No
National Grid | HAMILTON | 526797 | 1982 | 15.2 | Solar | 12_51T2 | 2023-05-16 12:07 | 2023-05-17 | 2 | 0 | 2 | 2023-05-19 | 2023-06-16 | 20 | 0 | 20 | [20 empty] | 2023-06-21 |  | 2024-08-06 |  | EXP | [8 empty] | 2023-12-28 | Connected |  | No
National Grid | PHILLIPSTON | 526873 | 1331 | 6 | Solar | 09_702W1 | 2023-05-16 14:05 | 2023-06-01 | 14 | 12 | 2 | 2023-06-22 | 2023-11-29 | 110 | 89 | 21 | [20 empty] | 2023-11-30 |  | 2024-12-16 |  | EXP | [8 empty] | 2024-04-02 | Connected |  | No
National Grid | DUDLEY | 517386 | 1570 | 3 | Solar | 01_412L2 | 2023-05-17 08:33 | 2023-05-18 | 18 | 18 | 0 | 2023-06-13 | 2023-07-12 | 20 | 0 | 20 | 2023-08-09 | 2023-09-14 | 26 | 0 | 26 | [5 empty] | 2023-08-09 | 2023-09-14 | 26 | 0 | 26 | [5 empty] | 2023-09-29 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MILFORD | 521681 | 1757 | 10 | Solar | 05_336W3 | 2023-05-17 11:29 | 2023-05-18 | 1 | 0 | 1 | 2023-05-19 | 2023-06-16 | 20 | 0 | 20 | [20 empty] | 2023-06-21 | 2023-05-17 11:53 | 2024-07-29 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SUTTON | 523641 | 1590 | 5 | Solar | 01_304W2 | 2023-05-17 11:53 | 2023-05-18 | 1 | 0 | 1 | 2023-05-19 | 2023-06-21 | 22 | 0 | 22 | [20 empty] | 2023-06-27 | 2023-05-17 12:08 | 2025-01-08 | Yes | EXP |  | 2024-01-10 | 2024-02-23 | 45 | 0 | 45 |  |  |  | Completion Documents |  | Yes
National Grid | STOUGHTON | 523764 | 2072 | 10 | Solar | 07_913W18 | 2023-05-17 12:08 | 2023-05-18 | 1 | 0 | 1 | 2023-05-19 | 2023-06-21 | 23 | 6 | 17 | [20 empty] | 2023-06-26 | 2023-05-17 12:09 | 2024-10-25 | Yes | EXP | [8 empty] | 2024-03-09 | Connected |  | No
National Grid | BROCKTON | 512233 | 2302 | 7.6 | Solar | 07_911W56 | 2023-05-17 12:09 | 2023-05-18 | 1 | 0 | 1 | 2023-05-19 | 2023-06-16 | 20 | 0 | 20 | [20 empty] | 2023-06-26 |  | 2024-09-14 | Yes | EXP |  | 2023-09-06 | 2023-09-15 | 10 | 0 | 10 |  |  | 2023-10-28 | Connected |  | No
National Grid | METHUEN | 522777 | 1844 | 3.8 | Solar | 14_53J5 | 2023-05-17 12:20 | 2023-05-18 | 2 | 2 | 0 | 2023-05-22 | 2023-06-16 | 19 | 0 | 19 | [20 empty] | 2023-06-21 |  | 2024-07-28 |  | EXP | [8 empty] | 2023-11-09 | Connected |  | No
National Grid | EAST BRIDGEWATER | 527426 | 2333 | 6.96 | Solar | 07_797W29 | 2023-05-18 10:14 | 2023-05-19 | 2 | 0 | 2 | 2023-05-23 | 2023-08-30 | 70 | 49 | 21 | [20 empty] | 2023-08-31 |  | 2024-09-30 |  | EXP | [8 empty] | 2023-10-21 | Connected |  | No
National Grid | BROCKTON | 522930 | 2301 | 6.38 | Solar | 07_91W49 | 2023-05-18 14:11 | 2023-05-19 | 18 | 17 | 1 | 2023-06-15 | 2023-07-18 | 22 | 0 | 22 | [20 empty] | 2023-07-24 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BILLERICA | 526597 | 1821 | 15.2 | Solar | 14_70L8 | 2023-05-19 10:37 | 2023-05-22 | 5 | 5 | 0 | 2023-05-30 | 2023-06-21 | 16 | 0 | 16 | [20 empty] | 2023-06-27 | 2023-05-19 13:40 | 2024-07-26 |  | EXP | [8 empty] | 2023-08-15 | Connected |  | No
National Grid | LAWRENCE | 516649 | 1841 | 10 | Solar | 14_74L3 | 2023-05-19 13:40 | 2023-05-22 | 2 | 1 | 1 | 2023-05-23 | 2023-06-23 | 22 | 1 | 21 | [20 empty] | 2023-06-28 | 2023-05-19 15:09 | 2024-08-16 | Yes | EXP |  | 2024-01-24 | 2024-01-31 | 8 | 0 | 8 |  |  | 2024-02-28 | Connected |  | No
National Grid | EAST LONGMEADOW | 525075 | 1028 | 10 | Solar | 09_508L4 | 2023-05-19 15:09 | 2023-05-22 | 5 | 0 | 5 | 2023-05-30 | 2023-07-11 | 30 | 9 | 21 | [20 empty] | 2023-07-14 |  | 2024-08-31 | Yes | EXP | [8 empty] | 2023-10-31 | Connected |  | Yes
National Grid | BROCKTON | 527992 | 2302 | 20.01 | Solar | 07_91W46 | 2023-05-20 15:11 | 2023-05-22 | 35 | 33 | 2 | 2023-07-13 | 2023-09-06 | 40 | 23 | 17 | [20 empty] | 2023-10-05 |  | 2024-10-13 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | METHUEN | 524863 | 1844 | 7.68 | Solar | 14_75L6 | 2023-05-22 08:59 | 2023-05-23 | 1 | 0 | 1 | 2023-05-24 | 2023-06-26 | 22 | 0 | 22 | [20 empty] | 2023-06-28 |  | 2024-08-11 |  | EXP | [8 empty] | 2023-10-02 | Connected |  | Yes
National Grid | LYNN | 525248 | 1902 | 3.84 | Solar | 12_1384 | 2023-05-22 09:14 | 2023-05-23 | 1 | 0 | 1 | 2023-05-24 | 2024-02-06 | 175 | 149 | 26 | [21 empty] | 2023-05-22 09:25 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | OXFORD | 526264 | 1540 | 7.6 | Solar | 01_406L3 | 2023-05-22 09:25 | 2023-05-23 | 3 | 0 | 3 | 2023-05-26 | 2023-07-07 | 29 | 8 | 21 | [20 empty] | 2023-07-10 |  | 2024-07-09 | Yes | EXP |  | 2023-08-10 | 2023-09-11 | 33 | 0 | 33 |  |  | 2023-10-04 | Connected |  | No
National Grid | BROCKTON | 525277 | 2302 | 7.6 | Solar | 07_911W56 | 2023-05-22 09:51 | 2023-05-23 | 3 | 0 | 3 | 2023-05-26 | 2023-06-21 | 17 | 0 | 17 | [20 empty] | 2023-06-27 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEST BROOKFIELD | 449501 | 1585 | 3.8 | Solar | 01_525L2 | 2023-05-22 11:52 | 2023-05-23 | 2 | 0 | 2 | 2023-05-25 | 2023-08-10 | 53 | 34 | 19 | [20 empty] | 2022-09-01 |  | 2024-12-12 |  | EXP | [8 empty] | 2023-12-18 | Connected |  | No
National Grid | WILLIAMSTOWN | 528161 | 1267 | 20 | Solar | 09_1003W1 | 2023-05-22 12:23 | 2023-05-23 | 2 | 0 | 2 | 2023-05-25 | 2023-06-21 | 18 | 0 | 18 | [20 empty] | 2023-06-27 |  | 2024-10-22 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | CHELMSFORD | 517472 | 1824 | 8.7 | Solar | 14_24L2 | 2023-05-22 13:55 | 2023-05-23 | 4 | 0 | 4 | 2023-05-30 | 2023-06-29 | 22 | 0 | 22 | [20 empty] | 2023-07-03 |  | 2024-07-04 |  | EXP | [8 empty] | 2023-08-03 | Connected |  | Yes
National Grid | WORCESTER | 526849 | 1604 | 9.57 | Solar | 01_27W5 | 2023-05-23 12:42 | 2023-05-24 | 2 | 0 | 2 | 2023-05-26 | 2023-06-22 | 18 | 0 | 18 | 2023-06-28 | 2023-08-02 | 18 | 0 | 18 | [5 empty] | 2023-06-28 | 2023-08-02 | 18 | 0 | 18 | [5 empty] | 2023-07-28 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SHEFFIELD | 528587 | 1257 | 15.2 | Solar | 09_1108W2 | 2023-05-23 14:11 | 2023-05-24 | 3 | 0 | 3 | 2023-05-30 | 2023-06-21 | 16 | 0 | 16 | [20 empty] | 2023-06-26 |  | 2024-08-20 |  | EXP | [8 empty] | 2023-12-04 | Connected |  | Yes
National Grid | NANTUCKET | 526775 | 2554 | 16.24 | Solar | 04_101L7 | 2023-05-23 15:37 | 2023-05-24 | 28 | 26 | 2 | 2023-07-05 | 2023-07-25 | 15 | 0 | 15 | [20 empty] | 2023-07-31 |  | 2024-08-31 |  | EXP | [8 empty] | 2023-10-02 | Connected |  | Yes
National Grid | ANDOVER | 528645 | 1810 | 9.86 | Solar | 14_50L1 | 2023-05-23 16:50 | 2023-05-24 | 2 | 0 | 2 | 2023-05-26 | 2023-08-29 | 65 | 45 | 20 | [20 empty] | 2023-08-31 |  | 2024-09-10 |  | EXP | [8 empty] | 2023-10-28 | Connected |  | No
National Grid | QUINCY | 528713 | 2169 | 20 | Solar | 07_1W5 | 2023-05-24 03:50 | 2023-05-25 | 1 | 0 | 1 | 2023-05-26 | 2023-06-26 | 20 | 0 | 20 | [20 empty] | 2023-06-28 |  | 2024-09-13 |  | EXP | [8 empty] | 2023-11-17 | Connected |  | No
National Grid | MENDON | 506009 | 1756 | 12.564 | Solar | 05_332W1 | 2023-05-24 08:10 | 2023-05-25 | 71 | 71 | 0 | 2023-09-08 | 2024-02-07 | 103 | 82 | 21 | [20 empty] | 2024-02-12 |  | 2025-02-22 |  | EXP | [8 empty] | 2024-02-27 | Connected |  | No
National Grid | MILLBURY | 526963 | 1527 | 7.6 | Solar | 01_304W3 | 2023-05-24 09:44 | 2023-05-25 | 13 | 12 | 1 | 2023-06-13 | 2023-08-01 | 35 | 14 | 21 | [20 empty] | 2023-08-02 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HAMILTON | 515409 | 1982 | 34.6 | Solar | 12_51T2 | 2023-05-24 12:00 | 2023-05-25 | 34 | 24 | 10 | 2023-07-17 | 2023-08-18 | 25 | 1 | 24 | [20 empty] | 2024-04-01 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | SHEFFIELD | 500745 | 1222 | 11.89 | Solar | 09_1108W2 | 2023-05-24 13:35 | 2023-05-25 | 42 | 33 | 9 | 2023-07-28 | 2023-11-15 | 77 | 59 | 18 | [20 empty] | 2023-11-20 | 2023-05-25 08:12 | 2024-12-25 |  | EXP | [8 empty] | 2024-02-12 | Connected |  | No
National Grid | LYNN | 526726 | 1902 | 6 | Solar | 12_1J901 | 2023-05-25 08:12 | 2023-05-26 | 2 | 0 | 2 | 2023-05-31 | 2023-06-30 | 22 | 0 | 22 | [20 empty] | 2023-07-06 | 2023-05-25 08:22 | 2024-11-29 | Yes | EXP |  | 2023-09-06 | 2023-12-15 | 101 | 0 | 101 |  |  | 2024-01-25 | Connected |  | No
National Grid | BROCKTON | 526606 | 2302 | 10 | Solar | 07_911W56 | 2023-05-25 08:22 | 2023-05-26 | 4 | 0 | 4 | 2023-06-02 | 2023-07-06 | 23 | 0 | 23 | [20 empty] | 2023-07-12 |  | 2024-07-30 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | LAWRENCE | 521243 | 1841 | 10 | Solar | 14_53J2 | 2023-05-25 08:43 | 2023-05-26 | 1 | 0 | 1 | 2023-05-30 | 2023-06-22 | 17 | 0 | 17 | [20 empty] | 2023-06-26 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WRENTHAM | 515278 | 2093 | 8.99 | Solar | 05_3422W1 | 2023-05-25 13:36 | 2023-05-26 | 1 | 0 | 1 | 2023-05-30 | 2023-06-28 | 21 | 0 | 21 | [20 empty] | 2023-06-29 | 2023-05-25 14:52 | 2024-09-21 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | LANCASTER | 506925 | 1523 | 8.7 | Solar | 01_216W4 | 2023-05-25 14:52 | 2023-05-26 | 6 | 4 | 2 | 2023-06-06 | 2023-07-10 | 23 | 0 | 23 | [20 empty] | 2023-07-10 |  | 2024-08-12 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | GARDNER | 522487 | 1440 | 4.06 | Solar | 01_607W5 | 2023-05-26 08:13 | 2023-05-30 | 1 | 0 | 1 | 2023-05-31 | 2023-06-28 | 20 | 0 | 20 | [20 empty] | 2023-07-05 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SALISBURY | 529466 | 1952 | 15.2 | Solar | 14_7L4 | 2023-05-26 12:58 | 2023-05-30 | 2 | 1 | 1 | 2023-05-31 | 2023-06-29 | 21 | 0 | 21 | [20 empty] | 2023-06-30 |  | 2024-07-02 |  | EXP | [8 empty] | 2023-08-16 | Connected |  | No
National Grid | WORCESTER | 514546 | 1610 | 4000 | Natural Gas | 01_HT41 | 2023-05-26 14:24 | 2023-05-30 | 21 | 11 | 10 | [10 empty] | 2023-06-29 | 2023-07-21 | 16 | 0 | 16 | [10 empty] | 2024-03-20 |  |  |  | STD | [9 empty] | Detailed Study |  | No
National Grid | NORTH GRAFTON | 529519 | 1536 | 12.6 | Solar | 01_304W4 | 2023-05-26 15:22 | 2023-05-30 | 1 | 0 | 1 | 2023-05-31 | 2023-07-20 | 35 | 13 | 22 | [20 empty] | 2023-07-25 |  | 2024-07-30 |  | EXP | [8 empty] | 2024-02-08 | Connected |  | No
National Grid | STURBRIDGE | 528584 | 1566 | 11.34 | Solar | 01_415L1 | 2023-05-26 15:38 | 2023-05-30 | 3 | 0 | 3 | 2023-06-02 | 2023-08-30 | 62 | 44 | 18 | [20 empty] | 2023-08-31 | 2023-05-26 15:50 | 2024-09-16 |  | EXP | [8 empty] | 2023-10-20 | Connected |  | No
National Grid | FLORENCE | 528675 | 1062 | 7.6 | Solar | 09_909W4 | 2023-05-26 15:50 | 2023-05-30 | 3 | 0 | 3 | 2023-06-02 | 2023-06-30 | 20 | 0 | 20 | [20 empty] | 2023-07-05 |  | 2024-07-06 | Yes | EXP |  | 2023-08-01 | 2023-08-04 | 4 | 0 | 4 |  |  | 2023-08-12 | Connected |  | No
National Grid | BRADFORD | 529552 | 1835 | 7.6 | Solar | 14_43L3 | 2023-05-26 15:51 | 2023-05-30 | 5 | 1 | 4 | 2023-06-06 |  | 214 | 25 | 189 | [24 empty] | EXP | [9 empty] | Screening |  | No
National Grid | RANDOLPH | 526253 | 2368 | 10 | Solar | 07_97W1 | 2023-05-26 16:36 | 2023-05-30 | 82 | 80 | 2 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 509862 | 2302 | 6 | Solar | 07_911W56 | 2023-05-26 18:33 | 2023-05-30 | 1 | 0 | 1 | 2023-05-31 | 2023-06-30 | 22 | 0 | 22 | [20 empty] | 2023-06-30 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BLACKSTONE | 528272 | 1504 | 10 | Solar | 05_321W9 | 2023-05-30 11:05 | 2023-05-31 | 2 | 0 | 2 | 2023-06-02 | 2023-07-07 | 24 | 0 | 24 | 2023-08-29 | 2023-10-02 | 7 | 0 | 7 | [5 empty] | 2023-08-29 | 2023-10-02 | 7 | 0 | 7 | [5 empty] | 2023-09-12 | 2023-05-30 11:15 | 2024-11-29 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 529271 | 2301 | 7.6 | Solar | 07_911W13 | 2023-05-30 11:15 | 2023-05-31 | 2 | 0 | 2 | 2023-06-02 | 2023-07-05 | 22 | 0 | 22 | [20 empty] | 2023-07-10 | 2023-05-30 11:25 | 2024-11-05 | Yes | EXP |  | 2023-10-11 | 2023-11-02 | 23 | 0 | 23 |  |  | 2024-02-02 | Connected |  | No
National Grid | BROCKTON | 528274 | 2302 | 6 | Solar | 07_712J1 | 2023-05-30 11:25 | 2023-05-31 | 3 | 2 | 1 | 2023-06-02 | 2023-07-06 | 23 | 0 | 23 | [20 empty] | 2023-07-10 | 2023-05-30 11:37 | 2024-09-28 | Yes | EXP |  | 2023-09-06 | 2023-09-27 | 22 | 0 | 22 |  |  | 2023-10-06 | Connected |  | No
National Grid | WHITMAN | 528712 | 2382 | 3.84 | Solar | 07_797W29 | 2023-05-30 11:37 | 2023-05-31 | 14 | 13 | 1 | 2023-06-20 | 2023-08-11 | 39 | 18 | 21 | [20 empty] | 2023-08-14 |  | 2024-11-29 | Yes | EXP |  | 2024-03-19 |  | 28 | 0 | 28 |  |  |  | Construction |  | Yes
National Grid | METHUEN | 516114 | 1844 | 7.6 | Solar | 14_63L1 | 2023-05-30 12:19 | 2023-05-31 | 3 | 1 | 2 | 2023-06-05 | 2023-07-10 | 24 | 0 | 24 | [20 empty] | 2023-07-11 |  | 2024-07-31 |  | EXP | [8 empty] | 2023-08-03 | Connected |  | No
National Grid | RANDOLPH | 528175 | 2368 | 7.6 | Solar | 07_5W3 | 2023-05-30 12:19 | 2023-05-31 | 2 | 0 | 2 | 2023-06-02 | 2023-07-10 | 25 | 0 | 25 | [20 empty] | 2023-07-10 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEOMINSTER | 527887 | 1453 | 6 | Solar | 01_219W2 | 2023-05-30 12:54 | 2023-05-31 | 2 | 0 | 2 | 2023-06-02 | 2023-07-09 | 25 | 0 | 25 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HANSON | 479187 | 2341 | 4990 | Solar | 07_797W29 | 2023-05-30 13:19 | 2023-05-31 | 29 | 19 | 10 | [10 empty] | 2023-07-14 | 2023-08-17 | 26 | 6 | 20 | [11 empty] | 2023-05-30 13:30 |  |  | STD | [9 empty] | Study |  | No
National Grid | CLINTON | 527951 | 1510 | 6 | Solar | 01_216W1 | 2023-05-30 13:30 | 2023-05-31 | 2 | 0 | 2 | 2023-06-02 | 2023-06-29 | 19 | 0 | 19 | [20 empty] | 2023-07-03 | 2023-05-31 14:33 | 2024-08-03 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | WORCESTER | 527877 | 1602 | 10 | Solar | 01_23W3 | 2023-05-31 14:33 | 2023-06-01 | 4 | 3 | 1 | 2023-06-06 | 2023-07-07 | 22 | 1 | 21 | [20 empty] | 2023-07-07 |  | 2024-08-03 | Yes | EXP |  | 2023-08-10 | 2023-08-28 | 19 | 0 | 19 |  |  | 2023-10-06 | Connected |  | No
National Grid | METHUEN | 491261 | 1844 | 10 | Solar | 14_63L1 | 2023-06-01 11:39 | 2023-06-02 | 3 | 2 | 1 | 2023-06-06 | 2023-09-19 | 75 | 43 | 32 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RANDOLPH | 522517 | 2368 | 10 | Solar | 07_97W1 | 2023-06-01 13:35 | 2023-06-02 | 55 | 55 | 0 | 2023-08-22 | 2023-10-18 | 40 | 7 | 33 | [21 empty] | 2023-06-01 15:19 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 525627 | 1844 | 6 | Solar | 14_63L1 | 2023-06-01 15:19 | 2023-06-02 | 2 | 1 | 1 | 2023-06-06 | 2023-08-28 | 57 | 38 | 19 | [20 empty] | 2023-08-29 |  | 2024-10-03 | Yes | EXP |  | 2023-12-09 | 2023-12-30 | 22 | 3 | 19 |  |  | 2024-01-18 | Connected |  | No
National Grid | MALDEN | 530618 | 2148 | 17.6 | Solar | 12_16J5 | 2023-06-01 15:44 | 2023-06-02 | 1 | 0 | 1 | 2023-06-05 | 2023-06-30 | 19 | 0 | 19 | [20 empty] | 2023-07-07 |  | 2024-09-08 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | WARREN | 498553 | 1083 | 5000 | Solar | 09_516L2 | 2023-06-01 15:59 | 2023-06-02 | 30 | 21 | 9 | [10 empty] | 2023-07-18 | 2023-08-15 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | BROCKTON | 528287 | 2302 | 10 | Solar | 07_911W77 | 2023-06-01 16:19 | 2023-06-02 | 1 | 0 | 1 | 2023-06-05 | 2023-07-10 | 24 | 0 | 24 | [20 empty] | 2023-07-11 | 2023-06-01 16:30 | 2024-07-26 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | HOLBROOK | 529626 | 2343 | 6 | Solar | 07_10W1 | 2023-06-01 16:30 | 2023-06-02 | 2 | 0 | 2 | 2023-06-06 | 2023-07-11 | 24 | 0 | 24 | [20 empty] | 2023-07-13 |  | 2024-07-19 | Yes | EXP |  | 2024-01-13 | 2024-03-04 | 52 | 0 | 52 |  |  | 2024-03-09 | Connected |  | No
National Grid | ORANGE | 529380 | 1364 | 7.6 | Solar | 09_705W3 | 2023-06-01 16:39 | 2023-06-02 | 2 | 0 | 2 | 2023-06-06 | 2023-07-11 | 24 | 0 | 24 | [20 empty] | 2023-07-14 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 527876 | 1844 | 3.8 | Solar | 14_63L2 | 2023-06-01 16:49 | 2023-06-02 | 2 | 0 | 2 | 2023-06-06 | 2023-07-14 | 27 | 17 | 10 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FALL RIVER | 504309 | 2721 | 7.6 | Solar | 05_115W43 | 2023-06-01 20:27 | 2023-06-02 | 11 | 10 | 1 | 2023-06-16 | 2023-11-13 | 102 | 84 | 18 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MILFORD | 526856 | 1757 | 10 | Solar | 05_335W2 | 2023-06-01 20:31 | 2023-06-02 | 2 | 0 | 2 | 2023-06-06 | 2023-07-11 | 24 | 0 | 24 | [20 empty] | 2023-07-12 | 2023-06-01 20:35 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH QUINCY | 529304 | 2171 | 6 | Solar | 07_11W4 | 2023-06-01 20:35 | 2023-06-02 | 1 | 0 | 1 | 2023-06-05 | 2023-07-10 | 24 | 0 | 24 | [20 empty] | 2023-07-11 |  | 2024-07-13 | Yes | EXP |  | 2023-08-05 | 2023-10-27 | 84 | 0 | 84 |  |  | 2023-10-30 | Connected |  | No
National Grid | METHUEN | 527661 | 1844 | 10 | Solar | 14_43L4 | 2023-06-01 20:46 | 2023-06-02 | 2 | 0 | 2 | 2023-06-06 |  | 29 | 5 | 24 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WILLIAMSBURG | 520969 | 1096 | 6 | Solar | 09_909W3 | 2023-06-02 08:47 | 2023-06-05 | 1 | 0 | 1 | 2023-06-06 | 2023-07-10 | 23 | 0 | 23 | [20 empty] | 2023-07-11 |  | 2024-07-23 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FLORENCE | 529594 | 1062 | 3.8 | Solar | 09_909W4 | 2023-06-02 11:09 | 2023-06-05 | 2 | 0 | 2 | 2023-06-07 | 2023-08-02 | 40 | 17 | 23 | [20 empty] | 2023-08-06 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NEWBURY | 520810 | 1922 | 9990 | Other | 14_60L1 | 2023-06-02 13:33 | 2023-06-05 | 13 | 3 | 10 | [10 empty] | 2023-06-23 | 2023-08-14 | 37 | 17 | 20 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WILBRAHAM | 523750 | 1095 | 4900 | Other | 09_507L3 | 2023-06-02 13:39 | 2023-06-05 | 131 | 35 | 96 | [29 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | UXBRIDGE | 474054 | 1569 | 10050 | Solar | 05_321W2 | 2023-06-02 15:57 | 2023-06-05 | 70 | 60 | 10 | [10 empty] | 2023-09-14 | 2023-10-09 | 18 | 0 | 18 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | UXBRIDGE | 474056 | 1516 | 10050 | Solar | 05_321W2 | 2023-06-02 16:01 | 2023-06-05 | 72 | 62 | 10 | [10 empty] | 2023-09-15 | 2023-10-09 | 17 | 0 | 17 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | UXBRIDGE | 474060 | 1516 | 10050 | Solar | 05_321W2 | 2023-06-02 16:03 | 2023-06-05 | 71 | 61 | 10 | [10 empty] | 2023-09-15 | 2023-10-09 | 17 | 0 | 17 | [11 empty] | 2023-06-05 07:14 |  |  | STD | [9 empty] | Study |  | No
National Grid | WESTPORT | 523454 | 2790 | 10 | Solar | 05_115W45 | 2023-06-05 07:14 | 2023-06-06 | 5 | 4 | 1 | 2023-06-13 | 2023-07-14 | 23 | 2 | 21 | [20 empty] | 2023-07-14 | 2023-06-05 09:14 | 2024-07-16 | Yes | EXP |  | 2023-08-16 | 2023-10-11 | 57 | 0 | 57 |  |  | 2023-10-16 | Connected |  | No
National Grid | BLACKSTONE | 530593 | 1504 | 7.6 | Solar | 05_321W6 | 2023-06-05 09:14 | 2023-06-06 | 2 | 0 | 2 | 2023-06-08 | 2023-07-11 | 22 | 0 | 22 | [20 empty] | 2023-07-14 |  | 2024-08-24 | Yes | EXP | [8 empty] | 2023-11-21 | Connected |  | No
National Grid | HOLBROOK | 530297 | 2343 | 18.85 | Solar | 07_2W1 | 2023-06-05 11:49 | 2023-06-06 | 17 | 16 | 1 | 2023-06-30 | 2023-07-25 | 17 | 0 | 17 | [20 empty] | 2023-07-31 |  | 2024-08-09 |  | EXP | [8 empty] | 2023-09-20 | Connected |  | No
National Grid | HANSON | 523276 | 2341 | 6.8 | Solar | 07_95W3 | 2023-06-05 11:55 | 2023-06-06 | 1 | 0 | 1 | 2023-06-07 | 2023-07-11 | 24 | 5 | 19 | 2023-11-24 | 2024-01-02 | 17 | 0 | 17 | [5 empty] | 2023-11-24 | 2024-01-02 | 17 | 0 | 17 | [5 empty] | 2023-12-14 |  | 2025-01-31 |  | EXP | [8 empty] | 2024-02-17 | Connected |  | No
National Grid | MONSON | 522193 | 1057 | 10 | Solar | 09_139L1 | 2023-06-05 12:31 | 2023-06-06 | 6 | 5 | 1 | 2023-06-13 | 2023-07-12 | 20 | 0 | 20 | 2023-08-09 | 2023-09-14 | 20 | 0 | 20 | [5 empty] | 2023-08-09 | 2023-09-14 | 20 | 0 | 20 | [5 empty] | 2023-09-11 | 2023-06-05 14:02 | 2024-11-01 |  | EXP |  | 2023-10-25 | 2023-10-30 | 6 | 0 | 6 |  |  | 2024-02-14 | Connected |  | No
National Grid | BROCKTON | 529280 | 2302 | 9.28 | Solar | 07_911W56 | 2023-06-05 14:02 | 2023-06-06 | 11 | 10 | 1 | 2023-06-21 | 2023-07-17 | 18 | 0 | 18 | [20 empty] | 2023-07-17 |  | 2024-07-20 | Yes | EXP |  | 2023-08-01 | 2023-08-11 | 11 | 0 | 11 |  |  | 2023-10-10 | Connected |  | No
National Grid | FRANKLIN | 531442 | 2038 | 14.79 | Solar | 05_344W5 | 2023-06-05 15:28 | 2023-06-06 | 10 | 9 | 1 | 2023-06-20 | 2023-08-08 | 35 | 16 | 19 | [20 empty] | 2023-08-08 |  | 2024-08-12 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | DRACUT | 531489 | 1826 | 15.2 | Solar | 14_78L1 | 2023-06-05 17:12 | 2023-06-06 | 1 | 0 | 1 | 2023-06-07 | 2023-07-06 | 20 | 0 | 20 | [20 empty] | 2023-07-12 |  | 2024-08-04 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | WILLIAMSBURG | 531637 | 1096 | 15.2 | Solar | 09_909W3 | 2023-06-06 11:04 | 2023-06-07 | 5 | 4 | 1 | 2023-06-13 | 2023-07-13 | 21 | 0 | 21 | [20 empty] | 2023-07-17 |  | 2024-08-05 |  | EXP | [8 empty] | 2023-11-01 | Connected |  | No
National Grid | LYNN | 527219 | 1902 | 19.43 | Solar | 12_22W2 | 2023-06-07 05:17 | 2023-06-08 | 13 | 13 | 0 | 2023-06-29 | 2023-07-26 | 20 | 2 | 18 | [20 empty] | 2023-07-26 |  | 2024-07-27 |  | EXP | [8 empty] | 2023-12-14 | Connected |  | No
National Grid | STOCKBRIDGE | 530128 | 1262 | 240 | Solar | 09_1103W1 | 2023-06-07 09:03 | 2023-06-08 | 51 | 40 | 11 | [10 empty] | 2023-08-22 | 2023-09-20 | 21 | 0 | 21 | [10 empty] | 2024-04-03 |  |  |  | STD | [9 empty] | Conditional Approval |  | Yes
National Grid | NORTON | 524257 | 2766 | 4500 | Other | 05_4L1 | 2023-06-07 09:35 | 2023-06-08 | 212 | 206 | 6 | [29 empty] | STD | [9 empty] | Application |  | No
National Grid | RUTLAND | 526469 | 1543 | 9.86 | Solar | 01_55W1 | 2023-06-07 10:25 | 2023-06-08 | 1 | 0 | 1 | 2023-06-09 | 2023-08-31 | 58 | 38 | 20 | 2023-09-26 |  | 137 | 41 | 96 | [5 empty] | 2023-09-26 |  | 137 | 41 | 96 | [5 empty] | 2024-01-29 |  | 2025-02-11 |  | EXP | [9 empty] | Construction |  | Yes
National Grid | HAMPDEN | 526470 | 1036 | 10 | Solar | 09_139L1 | 2023-06-07 11:47 | 2023-06-08 | 19 | 16 | 3 | 2023-07-06 | 2023-07-27 | 16 | 0 | 16 | [20 empty] | 2023-07-27 |  | 2024-08-02 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | PALMER | 531883 | 1069 | 15 | Solar | 09_503L4 | 2023-06-07 11:48 | 2023-06-08 | 1 | 0 | 1 | 2023-06-09 | 2023-07-24 | 30 | 10 | 20 | [20 empty] | 2023-07-30 |  | 2024-08-22 |  | EXP | [8 empty] | 2023-12-13 | Connected |  | Yes
National Grid | RANDOLPH | 475958 | 2368 | 3.8 | Solar | 07_97W1 | 2023-06-07 12:43 | 2023-06-08 | 108 | 106 | 2 | 2023-11-14 | 2023-12-15 | 23 | 0 | 23 | [20 empty] | 2023-12-28 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BOLTON | 532056 | 1740 | 15 | Solar | 01_225W1 | 2023-06-07 12:57 | 2023-06-08 | 13 | 12 | 1 | 2023-06-28 | 2023-07-24 | 18 | 4 | 14 | [20 empty] | 2023-10-31 |  | 2024-12-28 |  | EXP | [8 empty] | 2024-01-17 | Connected |  | No
National Grid | LYNN | 529508 | 1902 | 10 | Solar | 12_1388 | 2023-06-07 15:19 | 2023-06-08 | 46 | 35 | 11 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ORANGE | 528322 | 1364 | 15.08 | Solar | 09_705W3 | 2023-06-07 17:04 | 2023-06-08 | 1 | 0 | 1 | 2023-06-09 | 2024-02-28 | 178 | 25 | 153 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEEDS | 532258 | 1053 | 10 | Solar | 09_909W3 | 2023-06-07 17:22 | 2023-06-08 | 10 | 0 | 10 | 2023-06-23 | 2023-07-18 | 17 | 0 | 17 | [20 empty] | 2023-07-20 |  | 2024-07-26 |  | EXP | [8 empty] | 2023-09-01 | Connected |  | No
National Grid | MILFORD | 527637 | 1757 | 10.15 | Solar | 05_335W5 | 2023-06-07 18:50 | 2023-06-08 | 91 | 73 | 18 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | PHILLIPSTON | 530162 | 1331 | 10 | Solar | 09_702W1 | 2023-06-08 08:27 | 2023-06-09 | 4 | 3 | 1 | 2023-06-14 | 2023-09-19 | 67 | 48 | 19 | [20 empty] | 2023-10-03 |  | 2024-10-28 |  | EXP | [8 empty] | 2024-04-10 | Connected |  | Yes
National Grid | SUTTON | 523131 | 1590 | 9.216 | Solar | 01_304W2 | 2023-06-08 09:58 | 2023-06-09 | 2 | 0 | 2 | 2023-06-13 | 2023-07-14 | 22 | 0 | 22 | [20 empty] | 2023-07-19 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 527571 | 2301 | 6 | Solar | 07_911W25 | 2023-06-08 11:02 | 2023-06-09 | 11 | 8 | 3 | 2023-06-27 | 2023-07-19 | 16 | 0 | 16 | [20 empty] | 2023-07-19 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RANDOLPH | 531563 | 2368 | 100 | Solar | 07_5W3 | 2023-06-08 11:41 | 2023-06-09 | 72 | 62 | 10 | [10 empty] | 2023-09-22 | 2023-10-25 | 23 | 0 | 23 | [11 empty] | 2023-06-08 12:10 |  |  | STD | [9 empty] | Study |  | Yes
National Grid | FALL RIVER | 531727 | 2720 | 9.984 | Solar | 05_28W40 | 2023-06-08 12:10 | 2023-06-09 | 4 | 1 | 3 | 2023-06-15 | 2023-07-20 | 25 | 5 | 20 | [20 empty] | 2023-07-25 |  | 2024-08-17 | Yes | EXP |  | 2023-08-31 | 2023-09-02 | 3 | 0 | 3 |  |  | 2023-11-15 | Connected |  | No
National Grid | BLACKSTONE | 531948 | 1504 | 11.517 | Solar | 05_321W9 | 2023-06-08 12:26 | 2023-06-09 | 41 | 41 | 0 | 2023-08-09 | 2023-09-05 | 19 | 0 | 19 | 2023-09-14 | 2023-10-20 | 19 | 0 | 19 | [5 empty] | 2023-09-14 | 2023-10-20 | 19 | 0 | 19 | [5 empty] | 2023-10-13 |  | 2024-10-22 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LANCASTER | 532473 | 1523 | 15.2 | Solar | 01_227W1 | 2023-06-08 13:28 | 2023-06-09 | 2 | 0 | 2 | 2023-06-13 | 2023-07-17 | 23 | 7 | 16 | [20 empty] | 2023-07-19 |  | 2024-09-27 |  | EXP | [8 empty] | 2023-11-06 | Connected |  | No
National Grid | LAWRENCE | 476315 | 1841 | 8.8 | Solar | 14_8L2 | 2023-06-08 14:43 | 2023-06-09 | 46 | 45 | 1 | 2023-08-16 | 2023-09-08 | 17 | 0 | 17 | [20 empty] | 2023-09-08 |  | 2024-09-11 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | METHUEN | 524638 | 1844 | 6 | Solar | 14_43L4 | 2023-06-08 15:52 | 2023-06-09 | 2 | 0 | 2 | 2023-06-13 | 2023-07-14 | 22 | 0 | 22 | [20 empty] | 2023-07-17 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LAWRENCE | 530025 | 1843 | 5.85 | Solar | 14_61L1 | 2023-06-08 16:13 | 2023-06-09 | 14 | 12 | 2 | 2023-06-29 | 2023-07-25 | 18 | 0 | 18 | [20 empty] | 2023-07-26 |  | 2024-08-21 |  | EXP | [8 empty] | 2023-12-27 | Connected |  | No
National Grid | ANDOVER | 520199 | 1810 | 10 | Solar | 14_50L1 | 2023-06-09 10:20 | 2023-06-12 | 1 | 0 | 1 | 2023-06-13 | 2023-11-08 | 103 | 25 | 78 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MILFORD | 531921 | 1757 | 6 | Solar | 05_335W5 | 2023-06-09 11:08 | 2023-06-12 | 2 | 0 | 2 | 2023-06-14 | 2023-07-18 | 23 | 0 | 23 | [20 empty] | 2023-07-20 | 2023-06-09 11:37 | 2024-07-30 |  | EXP | [8 empty] | 2023-10-26 | Connected |  | No
National Grid | ATHOL | 517086 | 1331 | 6 | Solar | 09_702W2 | 2023-06-09 11:37 | 2023-06-12 | 5 | 4 | 1 | 2023-06-16 | 2023-07-19 | 22 | 0 | 22 | [20 empty] | 2023-07-19 | 2023-06-09 11:55 | 2024-08-20 | Yes | EXP |  | 2023-11-10 | 2024-01-12 | 64 | 3 | 61 |  |  | 2024-01-18 | Connected |  | No
National Grid | WINCHENDON | 529144 | 1475 | 5.76 | Solar | 01_612W1 | 2023-06-09 11:55 | 2023-06-12 | 2 | 0 | 2 | 2023-06-14 | 2023-07-18 | 23 | 0 | 23 | [20 empty] | 2023-07-20 |  | 2024-07-28 | Yes | EXP | [8 empty] | 2023-10-12 | Connected |  | No
National Grid | MALDEN | 530667 | 2148 | 10 | Solar | 12_16W7 | 2023-06-09 12:04 | 2023-06-12 | 2 | 0 | 2 | 2023-06-14 | 2023-07-17 | 23 | 0 | 23 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 530664 | 2302 | 6 | Solar | 07_69J1 | 2023-06-09 12:15 | 2023-06-12 | 1 | 0 | 1 | 2023-06-13 | 2023-07-11 | 19 | 0 | 19 | [20 empty] | 2023-07-12 | 2023-06-09 12:48 | 2024-08-07 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HANSON | 516332 | 2341 | 10 | Solar | 07_797W24 | 2023-06-09 12:48 | 2023-06-12 | 22 | 21 | 1 | 2023-07-13 | 2023-08-02 | 15 | 0 | 15 | [20 empty] | 2023-08-02 |  | 2024-08-16 | Yes | EXP |  | 2023-09-13 | 2023-09-13 | 1 | 0 | 1 |  |  | 2023-09-18 | Connected |  | No
National Grid | MONTEREY | 532774 | 1245 | 15.2 | Solar | 09_1109W1 | 2023-06-09 13:06 | 2023-06-12 | 1 | 0 | 1 | 2023-06-13 | 2023-07-11 | 19 | 0 | 19 | [20 empty] | 2023-07-12 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EASTON | 532740 | 2356 | 10 | Solar | 07_92W78 | 2023-06-09 13:38 | 2023-06-12 | 27 | 25 | 2 | 2023-07-21 | 2023-10-30 | 70 | 49 | 21 | [20 empty] | 2023-11-14 |  | 2025-01-17 |  | EXP | [8 empty] | 2024-02-21 | Connected |  | No
National Grid | BARRE | 532813 | 1005 | 10 | Solar | 09_604W4 | 2023-06-09 14:47 | 2023-06-12 | 2 | 1 | 1 | 2023-06-14 | 2023-08-29 | 52 | 33 | 19 | [20 empty] | 2023-09-01 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BELCHERTOWN | 531295 | 1007 | 10 | Solar | 09_509L2 | 2023-06-09 15:32 | 2023-06-12 | 1 | 0 | 1 | 2023-06-13 | 2023-07-14 | 22 | 0 | 22 | [20 empty] | 2023-07-19 |  | 2024-08-08 |  | EXP | [8 empty] | 2023-09-25 | Connected |  | Yes
National Grid | BOXFORD | 532991 | 1921 | 15 | Solar | 14_43L7 | 2023-06-12 10:01 | 2023-06-13 | 1 | 0 | 1 | 2023-06-14 | 2023-07-26 | 30 | 10 | 20 | [20 empty] | 2023-08-02 |  | 2024-08-02 |  | EXP | [8 empty] | 2023-10-20 | Connected |  | No
National Grid | SAUGUS | 531279 | 1906 | 7.6 | Solar | 12_23W3 | 2023-06-12 11:27 | 2023-06-13 | 44 | 27 | 17 | [26 empty] | 2023-06-12 12:33 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 525411 | 1844 | 6 | Solar | 14_63L1 | 2023-06-12 12:33 | 2023-06-13 | 38 | 33 | 5 | 2023-08-07 | 2023-08-29 | 17 | 0 | 17 | [20 empty] | 2023-08-31 |  | 2024-09-23 | Yes | EXP |  | 2024-01-24 | 2024-02-09 | 17 | 0 | 17 |  |  | 2024-02-21 | Connected |  | No
National Grid | NORTHBOROUGH | 521440 | 1532 | 6.175 | Solar | 05_313W4 | 2023-06-12 14:18 | 2023-06-13 | 1 | 0 | 1 | 2023-06-14 | 2023-10-04 | 78 | 57 | 21 | 2023-10-11 | 2023-10-31 | 15 | 0 | 15 | [5 empty] | 2023-10-11 | 2023-10-31 | 15 | 0 | 15 | [5 empty] | 2023-11-06 |  | 2024-11-18 |  | EXP |  | 2024-03-26 | 2024-04-11 | 17 | 0 | 17 |  |  |  | Completion Documents |  | Yes
National Grid | MONSON | 530542 | 1057 | 3.8 | Solar | 09_503L2 | 2023-06-12 16:53 | 2023-06-13 | 1 | 0 | 1 | 2023-06-14 | 2023-07-14 | 21 | 0 | 21 | [20 empty] | 2023-07-14 |  | 2024-09-03 |  | EXP | [8 empty] | 2023-10-25 | Connected |  | No
National Grid | SALEM | 530784 | 1970 | 7.6 | Solar | 12_49W4 | 2023-06-12 18:14 | 2023-06-13 | 2 | 0 | 2 | 2023-06-15 | 2023-07-17 | 21 | 0 | 21 | [20 empty] | 2023-07-20 | 2023-06-13 07:54 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EAST LONGMEADOW | 530576 | 1028 | 10 | Solar | 09_508L4 | 2023-06-13 07:54 | 2023-06-07 | 5 | 0 | 5 | 2023-06-14 | 2023-07-18 | 23 | 0 | 23 | [20 empty] | 2023-07-19 |  | 2024-09-06 | Yes | EXP |  | 2023-11-10 | 2023-11-09 | 0 | 0 | 0 |  |  | 2023-11-14 | Connected |  | No
National Grid | STURBRIDGE | 533391 | 1566 | 16.24 | Solar | 01_415L3 | 2023-06-13 09:03 | 2023-06-14 | 4 | 2 | 2 | 2023-06-21 | 2023-07-14 | 17 | 0 | 17 | [20 empty] | 2023-07-19 | 2023-06-13 11:00 | 2024-08-16 |  | EXP | [8 empty] | 2023-10-14 | Connected |  | No
National Grid | ROYALSTON | 526584 | 1368 | 3.8 | Solar | 09_702W2 | 2023-06-13 11:00 | 2023-06-14 | 1 | 0 | 1 | 2023-06-15 | 2023-07-18 | 22 | 0 | 22 | [20 empty] | 2023-07-21 |  | 2024-07-31 | Yes | EXP |  | 2023-08-24 | 2023-12-26 | 125 | 3 | 122 |  |  | 2024-01-04 | Connected |  | Yes
National Grid | GREAT BARRINGTON | 525221 | 1230 | 15.2 | Solar | 09_1109W2 | 2023-06-13 13:56 | 2023-06-14 | 1 | 0 | 1 | 2023-06-15 | 2023-07-14 | 20 | 0 | 20 | [20 empty] | 2023-07-19 |  | 2024-07-21 |  | EXP | [8 empty] | 2023-11-16 | Connected |  | No
National Grid | WESTMINSTER | 527513 | 1473 | 10 | Solar | 01_607W4 | 2023-06-13 15:02 | 2023-06-14 | 1 | 0 | 1 | 2023-06-15 | 2023-07-17 | 21 | 0 | 21 | [20 empty] | 2023-07-20 |  | 2024-07-31 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FALL RIVER | 501441 | 2721 | 14.79 | Solar | 05_115W53 | 2023-06-13 15:03 | 2023-06-14 | 13 | 9 | 4 | 2023-07-05 | 2023-09-06 | 45 | 35 | 10 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH DIGHTON | 532519 | 2764 | 11.4 | Solar | 05_19W74 | 2023-06-13 15:14 | 2023-06-14 | 8 | 5 | 3 | 2023-06-27 | 2023-07-18 | 16 | 1 | 15 | [20 empty] | 2023-07-20 | 2023-06-13 15:18 | 2024-08-30 |  | EXP | [8 empty] | 2023-11-08 | Connected |  | No
National Grid | UPTON | 532571 | 1568 | 10 | Solar | 05_332W1 | 2023-06-13 15:18 | 2023-06-14 | 8 | 5 | 3 | 2023-06-27 | 2023-07-18 | 15 | 0 | 15 | [20 empty] | 2023-07-20 |  | 2025-02-25 | Yes | EXP |  | 2024-03-26 |  | 21 | 0 | 21 |  |  |  | Construction |  | Yes
National Grid | LEOMINSTER | 532600 | 1453 | 6 | Solar | 01_207W2 | 2023-06-13 15:19 | 2023-06-14 | 1 | 0 | 1 | 2023-06-15 | 2023-07-18 | 22 | 0 | 22 | [20 empty] | 2023-07-18 |  | 2024-08-03 |  | EXP | [8 empty] | 2023-10-06 | Connected |  | No
National Grid | WORCESTER | 532272 | 1605 | 7.68 | Solar | 01_24W1 | 2023-06-14 08:15 | 2023-06-14 | 4 | 0 | 4 | 2023-06-21 | 2023-07-24 | 23 | 0 | 23 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SEEKONK | 530430 | 2771 | 50 | Solar | 05_7L3 | 2023-06-14 08:16 | 2023-06-15 | 27 | 17 | 10 | [10 empty] | 2023-07-26 | 2023-11-29 | 86 | 61 | 25 | [14 empty] | STD | [9 empty] | Group Study |  | Yes
National Grid | SEEKONK | 530749 | 2771 | 100 | Solar | 05_7L3 | 2023-06-14 08:19 | 2023-06-15 | 39 | 29 | 10 | [10 empty] | 2023-08-10 | 2023-09-06 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Group Study |  | Yes
National Grid | SEEKONK | 530753 | 2771 | 80 | Solar | 05_7L3 | 2023-06-14 08:20 | 2023-06-15 | 197 | 188 | 9 | 2024-04-01 |  | 11 | 0 | 11 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | SEEKONK | 530748 | 2771 | 100 | Solar | 05_7L3 | 2023-06-14 08:22 | 2023-06-15 | 39 | 29 | 10 | [10 empty] | 2023-08-10 | 2023-09-06 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Group Study |  | Yes
National Grid | SEEKONK | 530747 | 2771 | 100 | Solar | 05_7L3 | 2023-06-14 08:24 | 2023-06-15 | 39 | 29 | 10 | [10 empty] | 2023-08-10 | 2023-09-06 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Group Study |  | Yes
National Grid | LAWRENCE | 533130 | 1843 | 3.8 | Solar | 14_61L2 | 2023-06-14 12:12 | 2023-06-15 | 1 | 0 | 1 | 2023-06-16 | 2023-07-18 | 21 | 0 | 21 | [20 empty] | 2023-07-20 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HAVERHILL | 532437 | 1835 | 6 | Solar | 14_43L6 | 2023-06-14 14:18 | 2023-06-15 | 2 | 0 | 2 | 2023-06-20 | 2023-07-21 | 24 | 6 | 18 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | DUNSTABLE | 486759 | 1827 | 13.92 | Solar | 01_210L1 | 2023-06-14 17:51 | 2023-06-15 | 41 | 40 | 1 | 2023-08-14 | 2023-08-30 | 13 | 0 | 13 | [20 empty] | 2023-08-31 |  | 2024-10-05 |  | EXP | [8 empty] | 2024-03-29 | Connected |  | No
National Grid | GRAFTON | 533787 | 1519 | 15 | Solar | 01_304W1 | 2023-06-15 10:51 | 2023-06-16 | 4 | 2 | 2 | 2023-06-22 | 2023-08-22 | 42 | 25 | 17 | [20 empty] | 2023-08-28 |  | 2024-12-12 |  | EXP | [8 empty] | 2024-01-08 | Connected |  | Yes
National Grid | WESTFORD | 534351 | 1886 | 15.2 | Solar | 14_58L3 | 2023-06-15 16:35 | 2023-06-16 | 7 | 5 | 2 | 2023-06-28 | 2023-07-19 | 15 | 0 | 15 | [20 empty] | 2023-07-25 | 2023-06-15 16:43 | 2024-08-06 |  | EXP | [8 empty] | 2023-10-26 | Connected |  | No
National Grid | NORTHAMPTON | 529560 | 1060 | 10 | Solar | 09_901W3 | 2023-06-15 16:43 | 2023-06-16 | 4 | 2 | 2 | 2023-06-23 | 2023-07-18 | 18 | 2 | 16 | [20 empty] | 2023-07-18 | 2023-06-16 10:17 | 2024-08-28 | Yes | EXP |  | 2023-08-30 | 2023-08-29 | 0 | 0 | 0 |  |  | 2023-09-01 | Connected |  | No
National Grid | LAWRENCE | 533125 | 1841 | 10 | Solar | 14_8L2 | 2023-06-16 10:17 | 2023-06-20 | 2 | 0 | 2 | 2023-06-22 | 2023-07-21 | 21 | 0 | 21 | [20 empty] | 2023-07-25 |  | 2024-08-04 | Yes | EXP |  | 2023-12-06 | 2023-12-26 | 21 | 3 | 18 |  |  |  | Withdrawn |  | Yes
National Grid | NORTH BROOKFIELD | 534547 | 1535 | 25 | Solar | 01_525L1 | 2023-06-16 11:52 | 2023-06-20 | 5 | 3 | 2 | [10 empty] | 2023-06-26 | 2023-08-10 | 34 | 18 | 16 | [10 empty] | 2024-03-25 |  | 2025-04-09 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | WINTHROP | 533569 | 2152 | 17.6 | Solar | 12_96W1 | 2023-06-16 12:16 | 2023-06-20 | 2 | 0 | 2 | 2023-06-22 | 2023-07-14 | 16 | 0 | 16 | [20 empty] | 2023-07-21 |  | 2024-08-22 |  | EXP | [8 empty] | 2023-10-06 | Connected |  | No
National Grid | GARDNER | 533436 | 1440 | 16 | Battery Add-On | 01_607W1 | 2023-06-16 13:23 | 2023-06-20 | 2 | 0 | 2 | 2023-06-22 | 2023-10-30 | 90 | 25 | 65 | [21 empty] | 2023-06-16 14:10 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | RANDOLPH | 519279 | 2368 | 9.984 | Solar | 07_97W2 | 2023-06-16 14:10 | 2023-06-20 | 2 | 1 | 1 | 2023-06-22 | 2023-07-21 | 21 | 0 | 21 | [20 empty] | 2023-07-26 |  | 2024-12-06 | Yes | EXP |  | 2023-10-26 | 2023-12-04 | 40 | 0 | 40 |  |  | 2023-12-29 | Connected |  | No
National Grid | ANDOVER | 530104 | 1810 | 9.86 | Solar | 14_59L6 | 2023-06-17 17:18 | 2023-06-01 | 13 | 8 | 5 | 2023-06-21 | 2023-07-20 | 21 | 0 | 21 | 2023-08-09 | 2023-09-12 | 10 | 0 | 10 | [5 empty] | 2023-08-09 | 2023-09-12 | 10 | 0 | 10 | [5 empty] | 2023-08-28 |  | 2024-10-10 |  | EXP |  | 2023-10-06 | 2023-10-05 | 0 | 0 | 0 |  |  | 2023-11-29 | Connected |  | Yes
National Grid | WORCESTER | 534808 | 1606 | 15.2 | Solar | 01_24W2 | 2023-06-19 09:30 | 2023-06-20 | 30 | 26 | 4 | 2023-08-02 | 2023-08-31 | 22 | 0 | 22 | [20 empty] | 2024-03-04 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | UXBRIDGE | 534936 | 1569 | 7.6 | Solar | 05_321W2 | 2023-06-19 13:37 | 2023-06-20 | 5 | 2 | 3 | 2023-06-27 | 2023-08-07 | 30 | 15 | 15 | [20 empty] | 2023-08-16 |  | 2025-01-29 |  | EXP | [8 empty] | 2024-02-22 | Connected |  | No
National Grid | WESTFORD | 534960 | 1886 | 15.2 | Solar | 14_57L3 | 2023-06-19 14:20 | 2023-06-20 | 5 | 2 | 3 | 2023-06-27 | 2023-07-25 | 20 | 0 | 20 | [20 empty] | 2023-07-30 |  | 2024-10-12 |  | EXP | [8 empty] | 2023-10-25 | Connected |  | No
National Grid | WORCESTER | 534979 | 1603 | 14.21 | Solar | 01_2J349 | 2023-06-19 15:15 | 2023-06-20 | 2 | 0 | 2 | 2023-06-22 | 2023-08-10 | 35 | 16 | 19 | [20 empty] | 2023-08-11 |  | 2024-08-19 |  | EXP | [8 empty] | 2023-09-28 | Connected |  | Yes
National Grid | DUDLEY | 535016 | 1571 | 15.2 | Solar | 01_412L5 | 2023-06-19 18:43 | 2023-06-20 | 5 | 2 | 3 | 2023-06-27 | 2023-10-12 | 75 | 61 | 14 | [20 empty] | 2023-10-16 |  | 2025-01-08 |  | EXP | [8 empty] | 2024-02-03 | Connected |  | No
National Grid | ROCKPORT | 534135 | 1966 | 14.79 | Solar | 12_40J2 | 2023-06-20 09:38 | 2023-06-21 | 2 | 0 | 2 | 2023-06-23 | 2023-09-05 | 52 | 29 | 23 | [20 empty] | 2023-09-06 |  | 2024-09-12 |  | EXP | [8 empty] | 2023-11-09 | Connected |  | No
National Grid | LAWRENCE | 516167 | 1841 | 6 | Solar | 14_74L6 | 2023-06-20 10:31 | 2023-06-21 | 3 | 1 | 2 | 2023-06-23 | 2023-07-18 | 17 | 0 | 17 | [20 empty] | 2023-07-20 | 2023-06-20 11:10 | 2024-09-04 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | AMESBURY | 533655 | 1913 | 10 | Solar | 14_5J16 | 2023-06-20 11:10 | 2023-06-21 | 6 | 4 | 2 | 2023-06-29 | 2023-07-31 | 23 | 8 | 15 | [20 empty] | 2023-08-02 |  | 2024-09-28 | Yes | EXP |  | 2024-01-04 | 2024-01-18 | 15 | 0 | 15 |  |  | 2024-01-29 | Connected |  | No
National Grid | NORTH ANDOVER | 529680 | 1845 | 7.875 | Solar | 14_56L2 | 2023-06-20 13:04 | 2023-05-31 | 21 | 16 | 5 | 2023-06-30 | 2023-07-25 | 17 | 0 | 17 | 2023-09-29 | 2023-11-01 | 8 | 0 | 8 | [5 empty] | 2023-09-29 | 2023-11-01 | 8 | 0 | 8 | [5 empty] | 2023-10-13 | 2023-06-20 13:46 | 2024-10-22 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MILFORD | 534064 | 1757 | 7.25 | Solar | 05_335W5 | 2023-06-20 13:46 | 2023-06-21 | 9 | 7 | 2 | 2023-07-05 | 2023-07-27 | 17 | 0 | 17 | [20 empty] | 2023-08-03 |  | 2024-11-26 | Yes | EXP |  | 2023-11-28 | 2023-11-29 | 2 | 0 | 2 |  |  | 2023-12-07 | Connected |  | No
National Grid | METHUEN | 527935 | 1844 | 10 | Solar | 14_43L4 | 2023-06-20 13:48 | 2023-06-21 | 2 | 0 | 2 | 2023-06-23 | 2023-07-18 | 17 | 0 | 17 | [20 empty] | 2023-07-20 |  | 2024-07-23 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | HOLBROOK | 534192 | 2343 | 5.76 | Solar | 07_97W3 | 2023-06-20 15:09 | 2023-06-21 | 2 | 0 | 2 | 2023-06-23 | 2023-07-25 | 22 | 0 | 22 | 2023-08-29 | 2023-10-02 | 17 | 0 | 17 | [5 empty] | 2023-08-29 | 2023-10-02 | 17 | 0 | 17 | [5 empty] | 2023-10-06 | 2023-06-20 15:53 | 2024-10-22 |  | EXP |  | 2023-12-21 | 2024-02-08 | 49 | 1 | 48 |  |  | 2024-04-15 | Connected |  | Yes
National Grid | BROCKTON | 526795 | 2302 | 9.8 | Solar | 07_911W56 | 2023-06-20 15:53 | 2023-06-21 | 2 | 0 | 2 | 2023-06-23 | 2023-07-18 | 17 | 0 | 17 | [20 empty] | 2023-07-20 |  | 2024-08-04 | Yes | EXP |  | 2023-10-03 | 2023-10-20 | 18 | 0 | 18 |  |  |  | Meter Installation |  | Yes
National Grid | CHELMSFORD | 532374 | 1824 | 9.765 | Solar | 14_24L1 | 2023-06-20 17:06 | 2023-06-21 | 2 | 0 | 2 | 2023-06-23 | 2023-07-24 | 21 | 0 | 21 | 2023-08-04 | 2023-08-24 | 15 | 0 | 15 | [5 empty] | 2023-08-04 | 2023-08-24 | 15 | 0 | 15 | [5 empty] | 2023-08-29 |  | 2024-11-29 |  | EXP |  | 2024-02-02 |  | 74 | 0 | 74 |  |  |  | Construction |  | Yes
National Grid | EAST BRIDGEWATER | 531257 | 2333 | 14.4 | Solar | 07_797W29 | 2023-06-20 22:30 | 2023-06-21 | 2 | 0 | 2 | 2023-06-23 | 2023-07-17 | 16 | 0 | 16 | [20 empty] | 2023-07-21 |  | 2024-08-28 |  | EXP | [8 empty] | 2023-08-31 | Connected |  | No
National Grid | WEBSTER | 535445 | 1570 | 3 | Solar | 01_412L1 | 2023-06-21 09:01 | 2023-06-22 | 3 | 1 | 2 | 2023-06-27 |  | 200 | 25 | 175 | [24 empty] | EXP | [9 empty] | Screening |  | No
National Grid | WORCESTER | 525753 | 1605 | 6 | Solar | 01_24W1 | 2023-06-21 11:32 | 2023-06-22 | 0 | 0 | 0 | 2023-06-22 | 2023-07-25 | 23 | 0 | 23 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 529105 | 1844 | 3.8 | Solar | 14_74L2 | 2023-06-21 13:10 | 2023-06-22 | 3 | 0 | 3 | 2023-06-27 | 2023-07-25 | 20 | 0 | 20 | [20 empty] | 2023-07-30 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EAST BRIDGEWATER | 528895 | 2333 | 7.6 | Solar | 07_797W29 | 2023-06-21 13:42 | 2023-06-22 | 1 | 0 | 1 | 2023-06-23 | 2023-07-21 | 20 | 0 | 20 | [20 empty] | 2023-07-25 |  | 2024-10-03 |  | EXP | [8 empty] | 2023-10-30 | Connected |  | No
National Grid | WORCESTER | 517558 | 1604 | 10 | Solar | 01_10J383 | 2023-06-22 07:14 | 2023-06-23 | 3 | 0 | 3 | 2023-06-28 | 2023-07-26 | 20 | 0 | 20 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BEVERLY | 535949 | 1915 | 150 | Solar | 12_51T1 | 2023-06-22 13:28 | 2023-06-23 | 115 | 106 | 9 | [10 empty] | 2023-12-08 | 2024-01-19 | 28 | 3 | 25 | [11 empty] | 2023-06-22 17:41 |  |  | STD | [9 empty] | Study |  | Yes
National Grid | BROCKTON | 534904 | 2301 | 3.84 | Solar | 07_911W59 | 2023-06-22 17:41 | 2023-06-23 | 3 | 0 | 3 | 2023-06-28 | 2023-10-10 | 72 | 54 | 18 | [20 empty] | 2023-10-12 | 2023-06-22 18:04 | 2024-10-20 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | BROCKTON | 534910 | 2301 | 5.76 | Solar | 07_98W46 | 2023-06-22 18:04 | 2023-06-23 | 2 | 0 | 2 | 2023-06-27 | 2023-08-16 | 36 | 17 | 19 | [20 empty] | 2023-08-17 | 2023-06-23 10:32 | 2024-10-22 | Yes | EXP |  | 2023-10-04 | 2023-10-20 | 17 | 0 | 17 |  |  | 2023-10-26 | Connected |  | No
National Grid | CHESHIRE | 536190 | 1225 | 21.12 | Solar | 09_1021W2 | 2023-06-23 10:32 | 2023-06-26 | 2 | 0 | 2 | 2023-06-28 | 2023-07-25 | 20 | 5 | 15 | [20 empty] | 2023-08-22 |  | 2024-09-08 | Yes | EXP | [8 empty] | 2024-01-25 | Connected |  | No
National Grid | HOPEDALE | 532580 | 1747 | 16.4 | Solar | 05_335W3 | 2023-06-23 13:31 | 2023-06-26 | 1 | 0 | 1 | 2023-06-27 |  | 200 | 154 | 46 | [21 empty] | 2023-06-23 13:56 |  |  | EXP | [9 empty] | Screening |  | Yes
National Grid | BELCHERTOWN | 533647 | 1007 | 10 | Solar | 09_509L2 | 2023-06-23 13:56 | 2023-06-26 | 3 | 1 | 2 | 2023-06-28 | 2023-08-07 | 28 | 6 | 22 | [20 empty] | 2023-08-08 |  | 2024-08-16 | Yes | EXP |  | 2023-09-22 | 2023-10-11 | 20 | 0 | 20 |  |  | 2023-10-26 | Connected |  | No
National Grid | FRANKLIN | 497564 | 2038 | 480 | Solar | 05_348W7 | 2023-06-23 14:51 | 2023-06-26 | 60 | 50 | 10 | [10 empty] | 2023-09-19 | 2023-10-10 | 15 | 0 | 15 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | FRANKLIN | 498286 | 2038 | 480 | Solar | 05_348W7 | 2023-06-23 15:56 | 2023-06-26 | 60 | 50 | 10 | [10 empty] | 2023-09-19 | 2023-10-10 | 15 | 0 | 15 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | STOCKBRIDGE | 528486 | 1236 | 14.79 | Solar | 09_1109W3 | 2023-06-23 21:57 | 2023-06-26 | 10 | 6 | 4 | 2023-07-10 | 2023-07-27 | 14 | 0 | 14 | [20 empty] | 2023-08-02 |  | 2024-08-16 |  | EXP | [8 empty] | 2024-02-27 | Connected |  | No
National Grid | ANDOVER | 534892 | 1810 | 15.2 | Solar | 14_50L1 | 2023-06-26 10:55 | 2023-06-27 | 4 | 3 | 1 | 2023-06-30 | 2023-08-08 | 27 | 9 | 18 | [20 empty] | 2023-08-08 |  | 2024-08-16 |  | EXP | [8 empty] | 2023-11-11 | Connected |  | No
National Grid | REVERE | 534356 | 2151 | 3.8 | Solar | 12_16W4 | 2023-06-26 11:14 | 2023-06-27 | 2 | 0 | 2 | 2023-06-29 | 2023-07-20 | 15 | 0 | 15 | [20 empty] | 2023-07-25 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | NANTUCKET | 531486 | 2554 | 5.584 | Solar | 04_101L2 | 2023-06-26 11:49 | 2023-06-27 | 44 | 44 | 0 | 2023-08-29 | 2023-09-28 | 22 | 0 | 22 | [20 empty] | 2023-09-29 |  | 2024-10-05 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | EAST BRIDGEWATER | 536248 | 2333 | 15.2 | Solar | 07_797W42 | 2023-06-26 11:53 | 2023-06-27 | 2 | 1 | 1 | 2023-06-28 | 2023-07-25 | 19 | 0 | 19 | [20 empty] | 2023-07-25 |  | 2024-07-31 |  | EXP | [8 empty] | 2023-12-18 | Connected |  | No
National Grid | SUTTON | 533804 | 1590 | 15.36 | Solar | 05_320W5 | 2023-06-26 13:47 | 2023-06-27 | 30 | 28 | 2 | [10 empty] | 2023-08-08 | 2023-09-01 | 20 | 3 | 17 | [11 empty] | 2023-06-27 01:36 |  |  | STD | [9 empty] | Study |  | Yes
National Grid | LEICESTER | 526652 | 1524 | 14.5 | Solar | 01_21W2 | 2023-06-27 01:36 | 2023-06-28 | 1 | 1 | 0 | 2023-06-29 | 2023-07-25 | 18 | 0 | 18 | [20 empty] | 2023-07-31 |  | 2024-07-31 | Yes | EXP |  | 2023-09-14 | 2023-10-10 | 27 | 0 | 27 |  |  | 2023-10-16 | Connected |  | No
National Grid | WEYMOUTH | 525126 | 2190 | 7.6 | Solar | 07_99W32 | 2023-06-27 11:09 | 2023-06-28 | 27 | 25 | 2 | 2023-08-04 | 2023-08-28 | 17 | 0 | 17 | [20 empty] | 2023-08-28 | 2023-06-27 11:11 | 2024-09-21 |  | EXP | [8 empty] | 2023-10-09 | Connected |  | No
National Grid | BROCKTON | 536961 | 2302 | 10 | Solar | 07_91W48 | 2023-06-27 11:11 | 2023-07-07 | 2 | 0 | 2 | 2023-07-11 | 2023-10-26 | 77 | 59 | 18 | [20 empty] | 2023-10-30 |  | 2024-12-06 | Yes | EXP |  | 2024-02-02 | 2024-02-12 | 11 | 0 | 11 |  |  |  | Completion Documents |  | No
National Grid | MILLBURY | 536757 | 1527 | 10 | Solar | 01_304W3 | 2023-06-27 12:05 | 2023-06-28 | 71 | 25 | 46 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 513192 | 2302 | 6.38 | Solar | 07_911W77 | 2023-06-27 13:15 | 2023-06-28 | 22 | 20 | 2 | 2023-07-31 | 2023-08-25 | 20 | 0 | 20 | [20 empty] | 2023-04-19 |  | 2024-09-24 |  | EXP | [8 empty] | 2023-10-05 | Connected |  | Yes
National Grid | LAWRENCE | 537292 | 1843 | 20 | Solar | 14_8L1 | 2023-06-28 11:12 | 2023-06-29 | 77 | 77 | 0 | 2023-10-20 | 2024-02-06 | 71 | 27 | 44 | [21 empty] | 2023-06-28 11:23 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | RUTLAND | 536354 | 1543 | 5 | Solar | 01_55W1 | 2023-06-28 11:23 | 2023-06-29 | 3 | 1 | 2 | 2023-07-03 | 2023-07-27 | 18 | 0 | 18 | [20 empty] | 2023-07-30 |  | 2024-08-30 | Yes | EXP | [8 empty] | 2023-12-12 | Connected |  | No
National Grid | RUTLAND | 534007 | 1543 | 6 | Solar | 01_55W1 | 2023-06-28 13:44 | 2023-06-29 | 2 | 0 | 2 | 2023-07-03 | 2023-07-25 | 16 | 0 | 16 | [20 empty] | 2024-01-04 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | HOLBROOK | 534907 | 2343 | 7.6 | Solar | 07_10W1 | 2023-06-28 16:37 | 2023-06-29 | 2 | 1 | 1 | 2023-06-30 | 2023-09-13 | 52 | 25 | 27 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 534674 | 1844 | 7.6 | Solar | 14_5J40 | 2023-06-28 17:44 | 2023-06-29 | 5 | 4 | 1 | 2023-07-06 | 2023-08-01 | 19 | 0 | 19 | [20 empty] | 2023-08-04 |  | 2024-08-07 |  | EXP | [8 empty] | 2023-10-03 | Connected |  | No
National Grid | LANCASTER | 537573 | 1523 | 50 | Solar | 01_225W1 | 2023-06-28 23:39 | 2023-06-29 | 130 | 120 | 10 | 2024-01-08 | 2024-02-07 | 22 | 0 | 22 | [20 empty] | 2024-02-20 | 2023-06-29 10:37 | 2025-02-25 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | MALDEN | 532542 | 2148 | 5 | Solar | 12_16J1 | 2023-06-29 10:37 | 2023-06-30 | 5 | 4 | 1 | 2023-07-07 | 2023-07-31 | 17 | 0 | 17 | [20 empty] | 2023-08-02 |  | 2024-10-25 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | BARRE | 531613 | 1005 | 2499 | Other | 09_604W3 | 2023-06-29 11:13 | 2023-06-30 | 18 | 9 | 9 | [10 empty] | 2023-07-27 | 2023-08-29 | 24 | 6 | 18 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | SCITUATE | 534667 | 2066 | 67.3 | Solar | 07_915W82 | 2023-06-29 11:13 | 2023-06-30 | 39 | 30 | 9 | 2023-08-25 | 2023-09-25 | 21 | 0 | 21 | [20 empty] | 2024-02-16 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | HARVARD | 537240 | 1451 | 22.61 | Solar | 01_201W2 | 2023-06-29 15:08 | 2023-06-30 | 4 | 3 | 1 | 2023-07-06 | 2023-12-12 | 110 | 97 | 13 | [20 empty] | 2023-12-13 |  | 2024-12-20 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | WILLIAMSBURG | 535697 | 1039 | 151.9 | Solar | 09_909W3 | 2023-06-29 15:15 | 2023-06-30 | 10 | 0 | 10 | [10 empty] | 2023-07-17 | 2023-09-08 | 39 | 15 | 24 | [10 empty] | 2024-01-29 |  |  |  | STD | [9 empty] | Conditional Approval |  | Yes
National Grid | ADAMS | 535723 | 1220 | 100 | Solar | 09_1021W2 | 2023-06-29 16:44 | 2023-06-30 | 33 | 24 | 9 | [10 empty] | 2023-08-17 | 2023-09-13 | 19 | 0 | 19 | [10 empty] | 2024-02-21 |  |  |  | STD | [9 empty] | Conditional Approval |  | Yes
National Grid | SEEKONK | 518104 | 2771 | 9000 | Other | 05_7L1 | 2023-06-30 10:14 | 2023-07-03 | 10 | 0 | 10 | [10 empty] | 2023-07-18 | 2023-09-12 | 41 | 21 | 20 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | MENDON | 533315 | 1756 | 15.2 | Solar | 05_335W1 | 2023-06-30 10:33 | 2023-07-03 | 1 | 0 | 1 | 2023-07-05 | 2023-08-21 | 35 | 21 | 14 | [20 empty] | 2023-08-24 |  | 2024-09-08 |  | EXP | [8 empty] | 2023-10-10 | Connected |  | No
National Grid | REVERE | 537998 | 2151 | 2.32 | Solar | 12_35J3 | 2023-06-30 12:12 | 2023-07-03 | 2 | 0 | 2 | 2023-07-06 | 2023-07-25 | 14 | 0 | 14 | [20 empty] | 2023-07-31 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BOLTON | 535567 | 1740 | 15.12 | Solar | 01_225W1 | 2023-06-30 12:38 | 2023-07-03 | 2 | 0 | 2 | 2023-07-06 | 2023-07-25 | 14 | 0 | 14 | [20 empty] | 2023-07-30 |  | 2024-10-15 |  | EXP | [8 empty] | 2024-01-05 | Connected |  | No
National Grid | LENOX | 538076 | 1240 | 22.8 | Solar | 09_1103W1 | 2023-06-30 14:04 | 2023-07-03 | 2 | 1 | 1 | 2023-07-05 | 2023-07-24 | 14 | 0 | 14 | [20 empty] | 2023-07-25 |  | 2024-08-22 |  | EXP | [8 empty] | 2023-12-12 | Connected |  | No
National Grid | WESTMINSTER | 536407 | 1473 | 15.2 | Solar | 01_610W3 | 2023-06-30 18:33 | 2023-07-03 | 2 | 1 | 1 | 2023-07-06 | 2023-07-25 | 14 | 0 | 14 | [20 empty] | 2023-07-26 |  | 2024-08-07 |  | EXP | [8 empty] | 2023-11-30 | Connected |  | No
National Grid | REHOBOTH | 531460 | 2769 | 15 | Solar | 05_7L4 | 2023-07-03 09:22 | 2023-07-05 | 2 | 1 | 1 | 2023-07-06 | 2023-08-01 | 19 | 5 | 14 | [20 empty] | 2023-08-01 |  | 2024-08-16 |  | EXP | [8 empty] | 2023-11-11 | Connected |  | No
National Grid | REVERE | 538307 | 2151 | 3.8 | Solar | 12_16W8 | 2023-07-04 10:08 | 2023-07-05 | 2 | 0 | 2 | 2023-07-07 | 2023-10-04 | 63 | 42 | 21 | [20 empty] | 2023-10-09 |  | 2024-10-14 |  | EXP | [9 empty] | Conditional Approval |  | No
National Grid | LAWRENCE | 535614 | 1843 | 3 | Solar | 14_61L1 | 2023-07-04 10:42 | 2023-07-05 | 4 | 3 | 1 | 2023-07-11 | 2023-07-31 | 15 | 0 | 15 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | ANDOVER | 538685 | 1844 | 15 | Solar | 14_50L1 | 2023-07-05 13:13 | 2023-07-06 | 1 | 0 | 1 | 2023-07-07 | 2023-08-01 | 19 | 4 | 15 | [20 empty] | 2023-08-06 |  | 2024-10-18 |  | EXP | [8 empty] | 2023-12-07 | Connected |  | No
National Grid | ATTLEBORO | 494670 | 2703 | 750 | Solar | 05_8L3 | 2023-07-05 13:33 | 2023-07-06 | 80 | 71 | 9 | [10 empty] | 2023-10-31 | 2024-01-03 | 43 | 23 | 20 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | WORCESTER | 538092 | 1605 | 10 | Solar | 01_11J354 | 2023-07-05 13:39 | 2023-07-06 | 2 | 1 | 1 | 2023-07-07 | 2023-11-14 | 90 | 50 | 40 | [21 empty] | 2023-07-05 13:56 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HAMPDEN | 537341 | 1036 | 3.8 | Solar | 09_139L1 | 2023-07-05 13:56 | 2023-07-06 | 11 | 10 | 1 | 2023-07-20 | 2023-08-17 | 21 | 0 | 21 | [20 empty] | 2023-08-17 | 2023-07-05 14:37 | 2024-11-17 | Yes | EXP |  | 2024-01-20 | 2024-01-19 | 0 | 0 | 0 |  |  | 2024-01-23 | Connected |  | No
National Grid | RANDOLPH | 535946 | 2368 | 5.76 | Solar | 07_97W3 | 2023-07-05 14:37 | 2023-07-06 | 2 | 1 | 1 | 2023-07-07 | 2023-07-31 | 17 | 0 | 17 | [20 empty] | 2023-08-01 |  | 2024-08-09 | Yes | EXP |  | 2023-10-19 | 2023-10-20 | 2 | 0 | 2 |  |  | 2023-10-23 | Connected |  | No
National Grid | NORTH OXFORD | 538718 | 1537 | 20.01 | Solar | 01_406L1 | 2023-07-05 14:45 | 2023-07-06 | 4 | 3 | 1 | 2023-07-12 | 2023-12-22 | 114 | 25 | 89 | [21 empty] | 2023-07-05 15:45 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MILLBURY | 525794 | 1527 | 10 | Solar | 01_304W5 | 2023-07-05 15:45 | 2023-07-06 | 1 | 0 | 1 | 2023-07-07 | 2023-07-28 | 16 | 0 | 16 | [20 empty] | 2023-08-02 |  | 2024-10-30 | Yes | EXP | [8 empty] | 2024-03-02 | Connected |  | No
National Grid | ATTLEBORO | 538767 | 2703 | 15.2 | Solar | 05_9L4 | 2023-07-05 17:13 | 2023-07-06 | 1 | 0 | 1 | 2023-07-07 | 2023-09-21 | 54 | 26 | 28 | [21 empty] | 2023-07-06 09:12 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 534971 | 1844 | 7.6 | Solar | 14_5J42 | 2023-07-06 09:12 | 2023-07-07 | 14 | 13 | 1 | 2023-07-26 | 2023-08-23 | 21 | 0 | 21 | [20 empty] | 2023-08-23 | 2023-07-06 09:30 | 2024-09-20 | Yes | EXP |  | 2024-01-24 | 2024-02-14 | 22 | 0 | 22 |  |  |  | Withdrawn |  | Yes
National Grid | METHUEN | 533962 | 1844 | 10 | Solar | 14_5J42 | 2023-07-06 09:30 | 2023-07-07 | 6 | 5 | 1 | 2023-07-14 | 2023-08-04 | 16 | 0 | 16 | [20 empty] | 2023-08-04 |  | 2024-09-02 | Yes | EXP |  | 2024-02-17 | 2024-02-16 | 0 | 0 | 0 |  |  | 2024-02-21 | Connected |  | No
National Grid | MARLBOROUGH | 511796 | 1752 | 249 | Solar | 05_311W5 | 2023-07-06 11:32 | 2023-07-07 | 42 | 32 | 10 | [10 empty] | 2023-09-05 | 2023-10-05 | 23 | 0 | 23 | [11 empty] | 2023-07-06 12:21 |  |  | STD | [9 empty] | Study |  | No
National Grid | FALL RIVER | 529857 | 2723 | 3.8 | Solar | 05_106W82 | 2023-07-06 12:21 | 2023-07-07 | 21 | 20 | 1 | 2023-08-04 | 2023-08-27 | 17 | 0 | 17 | [20 empty] | 2023-08-30 |  | 2024-11-26 | Yes | EXP |  | 2023-10-24 | 2023-12-01 | 39 | 0 | 39 |  |  | 2023-12-04 | Connected |  | No
National Grid | LYNN | 537934 | 1905 | 3.8 | Solar | 12_19W1 | 2023-07-06 14:29 | 2023-07-07 | 1 | 0 | 1 | 2023-07-10 | 2023-07-31 | 16 | 0 | 16 | [20 empty] | 2023-08-02 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | QUINCY | 539000 | 2169 | 30 | Solar | 07_3W2 | 2023-07-06 14:29 | 2023-07-07 | 32 | 22 | 10 | 2023-08-21 | 2023-10-24 | 45 | 26 | 19 | 2023-11-01 | 2023-12-11 | 13 | 0 | 13 | [5 empty] | 2023-11-01 | 2023-12-11 | 13 | 0 | 13 | [5 empty] | 2023-11-22 |  | 2024-12-25 |  | EXP |  | 2023-12-07 | 2024-02-16 | 72 | 3 | 69 |  |  | 2024-04-12 | Connected |  | No
National Grid | LEICESTER | 523512 | 1542 | 4000 | Solar | 01_21W2 | 2023-07-06 15:32 | 2023-07-07 | 38 | 28 | 10 | [10 empty] | 2023-08-29 | 2023-10-13 | 33 | 14 | 19 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | SWANSEA | 494886 | 2777 | 2000 | Solar | 05_11W85 | 2023-07-06 16:26 | 2023-07-07 | 36 | 26 | 10 | [10 empty] | 2023-08-25 | 2023-09-18 | 16 | 0 | 16 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | NORTHBOROUGH | 482180 | 1532 | 2550 | Solar | 05_313W3 | 2023-07-06 16:52 | 2023-07-07 | 78 | 68 | 10 | [10 empty] | 2023-10-26 | 2023-11-16 | 15 | 0 | 15 | [11 empty] | 2023-07-07 08:39 |  |  | STD | [9 empty] | Study |  | No
National Grid | DRACUT | 537415 | 1826 | 8.064 | Solar | 14_78L9 | 2023-07-07 08:39 | 2023-07-10 | 51 | 50 | 1 | 2023-09-20 | 2023-10-17 | 19 | 0 | 19 | [20 empty] | 2023-10-18 |  | 2025-01-16 | Yes | EXP |  | 2024-03-14 |  | 33 | 0 | 33 |  |  |  | Construction |  | Yes
National Grid | PEPPERELL | 532028 | 1463 | 10 | Solar | 01_226L1 | 2023-07-07 11:33 | 2023-07-10 | 2 | 0 | 2 | 2023-07-12 | 2023-08-10 | 22 | 0 | 22 | 2023-10-02 | 2023-11-01 | 15 | 0 | 15 | [5 empty] | 2023-10-02 | 2023-11-01 | 15 | 0 | 15 | [5 empty] | 2023-10-30 |  | 2024-12-11 |  | EXP |  | 2023-12-22 | 2024-01-24 | 34 | 0 | 34 |  |  | 2024-02-01 | Connected |  | Yes
National Grid | BILLERICA | 507609 | 1821 | 450 | Solar | 14_70L2 | 2023-07-07 12:54 | 2023-07-10 | 13 | 3 | 10 | [10 empty] | 2023-07-26 | 2023-08-21 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | WORCESTER | 396740 | 1607 | 3486 | Other | 01_8W1 | 2023-07-07 17:55 | 2023-07-10 | 41 | 31 | 10 | [10 empty] | 2023-09-06 | 2024-01-22 | 93 | 75 | 18 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | BELCHERTOWN | 528517 | 1007 | 3.19 | Solar | 09_509L2 | 2023-07-10 10:27 | 2023-07-11 | 3 | 1 | 2 | [10 empty] | 2023-07-13 | 2023-11-16 | 88 | 72 | 16 | [11 empty] | 2023-07-10 10:37 |  |  | STD | [9 empty] | Study |  | No
National Grid | CHARLTON | 521797 | 1507 | 12.288 | Solar | 01_415L2 | 2023-07-10 10:37 | 2023-07-11 | 3 | 1 | 2 | 2023-07-13 | 2023-08-01 | 14 | 0 | 14 | [20 empty] | 2023-08-01 |  | 2024-09-07 | Yes | EXP |  | 2023-10-24 | 2023-12-13 | 51 | 0 | 51 |  |  |  | Completion Documents |  | No
National Grid | RANDOLPH | 536421 | 2368 | 3.8 | Solar | 07_5W3 | 2023-07-10 11:29 | 2023-07-11 | 1 | 0 | 1 | 2023-07-12 | 2023-07-31 | 14 | 0 | 14 | [20 empty] | 2023-07-31 |  | 2024-08-20 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RANDOLPH | 538902 | 2368 | 10 | Solar | 07_97W1 | 2023-07-10 14:04 | 2023-07-11 | 35 | 34 | 1 | 2023-09-01 | 2023-12-12 | 70 | 52 | 18 | 2024-01-31 | 2024-03-04 | 14 | 0 | 14 | [5 empty] | 2024-01-31 | 2024-03-04 | 14 | 0 | 14 | [5 empty] | 2024-02-23 |  | 2025-04-03 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | MELROSE | 536960 | 2176 | 10 | Solar | 12_25W4 | 2023-07-10 16:05 | 2023-07-11 | 1 | 0 | 1 | 2023-07-12 | 2023-08-15 | 25 | 0 | 25 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | STOUGHTON | 524728 | 2072 | 14.976 | Solar | 07_913W67 | 2023-07-11 07:35 | 2023-07-12 | 5 | 4 | 1 | 2023-07-18 | 2023-09-22 | 48 | 27 | 21 | [20 empty] | 2023-09-25 |  | 2024-10-04 |  | EXP | [8 empty] | 2023-10-11 | Connected |  | No
National Grid | METHUEN | 539231 | 1844 | 5.76 | Solar | 14_74L3 | 2023-07-11 13:15 | 2023-07-12 | 1 | 0 | 1 | 2023-07-13 | 2023-08-01 | 14 | 0 | 14 | [20 empty] | 2023-08-02 |  | 2024-11-13 |  | EXP | [9 empty] | Construction |  | Yes
National Grid | BROCKTON | 534311 | 2301 | 10 | Solar | 07_797W19 | 2023-07-11 15:09 | 2023-07-12 | 1 | 0 | 1 | 2023-07-13 | 2023-08-07 | 18 | 0 | 18 | [20 empty] | 2023-08-10 |  | 2024-09-24 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 494666 | 1844 | 360 | Solar | 14_43L4 | 2023-07-11 16:30 | 2023-07-12 | 39 | 30 | 9 | [10 empty] | 2023-09-05 | 2023-10-02 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | AUBURN | 513820 | 1501 | 4990 | Other | 01_26W2 | 2023-07-11 18:09 | 2023-07-12 | 33 | 23 | 10 | [10 empty] | 2023-08-28 | 2023-11-28 | 62 | 43 | 19 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | LEICESTER | 536765 | 1524 | 13.8 | Solar | 01_21W1 | 2023-07-11 18:51 | 2023-07-12 | 82 | 72 | 10 | 2023-11-08 | 2023-12-15 | 26 | 1 | 25 | [20 empty] | 2023-12-19 |  | 2025-01-01 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | FALL RIVER | 537794 | 2720 | 7.6 | Solar | 05_106W46 | 2023-07-12 09:24 | 2023-07-13 | 1 | 0 | 1 | 2023-07-14 | 2023-08-04 | 16 | 0 | 16 | [20 empty] | 2023-08-07 |  | 2024-08-06 |  | EXP | [8 empty] | 2023-08-30 | Connected |  | Yes
National Grid | DRACUT | 538861 | 1826 | 15 | Solar | 14_75L3 | 2023-07-12 09:50 | 2023-07-13 | 3 | 0 | 3 | 2023-07-18 | 2023-09-05 | 35 | 16 | 19 | [20 empty] | 2023-09-06 |  | 2024-09-18 |  | EXP | [8 empty] | 2023-12-05 | Connected |  | Yes
National Grid | REVERE | 530131 | 2151 | 8.12 | Solar | 12_7W2 | 2023-07-12 10:08 | 2023-07-13 | 16 | 15 | 1 | 2023-08-03 | 2023-09-08 | 27 | 9 | 18 | [20 empty] | 2023-09-08 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SWANSEA | 494888 | 2777 | 1500 | Solar | 05_11W85 | 2023-07-12 11:14 | 2023-07-13 | 13 | 3 | 10 | [10 empty] | 2023-07-31 | 2023-09-18 | 35 | 19 | 16 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | PALMER | 540050 | 1069 | 17.6 | Solar | 09_503L1 | 2023-07-13 11:09 | 2023-07-14 | 1 | 0 | 1 | 2023-07-17 | 2024-01-31 | 135 | 115 | 20 | [20 empty] | 2024-02-01 |  | 2025-02-05 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | BEVERLY | 513872 | 1915 | 4990 | Other | 12_12L4 | 2023-07-13 11:15 | 2023-07-14 | 57 | 47 | 10 | [10 empty] | 2023-10-03 | 2023-11-28 | 38 | 15 | 23 | [11 empty] | 2023-07-13 12:43 |  |  | STD | [9 empty] | Study |  | No
National Grid | OAKHAM | 539539 | 1068 | 18.99 | Battery Add-On | 09_604W2 | 2023-07-13 12:43 | 2023-07-14 | 2 | 0 | 2 | 2023-07-18 | 2024-01-22 | 129 | 104 | 25 | 2024-02-16 | 2024-02-15 | 0 | 0 | 0 | [5 empty] | 2024-02-16 | 2024-02-15 | 0 | 0 | 0 | [5 empty] | 2024-02-15 |  | 2025-03-21 | Yes | EXP | [9 empty] | Construction |  | No
National Grid | FOXBOROUGH | 538944 | 2035 | 240 | Solar | 05_3432W2 | 2023-07-14 09:12 | 2023-07-17 | 16 | 8 | 8 | [10 empty] | 2023-08-08 | 2023-12-09 | 85 | 64 | 21 | [14 empty] | STD | [9 empty] | Group Study |  | Yes
National Grid | WORCESTER | 540716 | 1606 | 20 | Solar | 01_24W2 | 2023-07-14 09:38 | 2023-07-17 | 3 | 0 | 3 | 2023-07-20 | 2023-10-03 | 54 | 30 | 24 | [20 empty] | 2023-10-09 |  | 2024-10-11 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LYNN | 536831 | 1902 | 6 | Solar | 12_22W2 | 2023-07-14 11:50 | 2023-07-17 | 1 | 0 | 1 | 2023-07-18 | 2023-09-06 | 36 | 16 | 20 | [20 empty] | 2023-09-06 |  | 2024-09-10 |  | EXP | [8 empty] | 2024-01-13 | Connected |  | No
National Grid | WORCESTER | 519419 | 1605 | 12.47 | Solar | 01_24W1 | 2023-07-14 16:15 | 2023-07-17 | 1 | 0 | 1 | 2023-07-18 | 2023-08-17 | 23 | 0 | 23 | 2023-09-20 | 2023-10-20 | 15 | 0 | 15 | [5 empty] | 2023-09-20 | 2023-10-20 | 15 | 0 | 15 | [5 empty] | 2023-10-25 |  | 2024-11-26 |  | EXP |  | 2024-01-03 | 2024-02-23 | 52 | 0 | 52 |  |  |  | Withdrawn |  | Yes
National Grid | BELLINGHAM | 541092 | 2019 | 25 | Solar | 05_344W4 | 2023-07-14 18:56 | 2023-07-17 | 14 | 13 | 1 | 2023-08-04 | 2023-09-21 | 36 | 19 | 17 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORWELL | 541172 | 2061 | 7.56 | Solar | 07_96W44 | 2023-07-17 07:21 | 2023-07-18 | 2 | 0 | 2 | 2023-07-20 | 2023-10-31 | 72 | 51 | 21 | [20 empty] | 2023-11-03 |  | 2024-11-22 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | BELCHERTOWN | 541261 | 1007 | 20 | Solar | 09_527L2 | 2023-07-17 10:46 | 2023-07-18 | 2 | 0 | 2 | [10 empty] | 2023-07-20 | 2023-12-07 | 97 | 76 | 21 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | NORWELL | 541284 | 2061 | 15.2 | Solar | 07_96W43 | 2023-07-17 11:26 | 2023-07-18 | 2 | 0 | 2 | 2023-07-20 | 2023-08-21 | 23 | 0 | 23 | [20 empty] | 2023-08-23 | 2023-07-17 12:30 | 2024-09-10 |  | EXP | [8 empty] | 2023-10-31 | Connected |  | No
National Grid | BROCKTON | 540461 | 2302 | 10 | Solar | 07_91W43 | 2023-07-17 12:30 | 2023-07-18 | 1 | 0 | 1 | 2023-07-19 | 2023-08-14 | 19 | 0 | 19 | [20 empty] | 2023-08-15 |  | 2024-09-16 | Yes | EXP |  | 2023-10-28 | 2023-11-14 | 18 | 0 | 18 |  |  | 2024-01-26 | Connected |  | No
National Grid | MILFORD | 540445 | 1757 | 6 | Solar | 05_336W3 | 2023-07-17 12:41 | 2023-07-18 | 1 | 0 | 1 | 2023-07-19 | 2023-08-10 | 17 | 0 | 17 | 2023-08-24 | 2023-09-25 | 14 | 0 | 14 | [5 empty] | 2023-08-24 | 2023-09-25 | 14 | 0 | 14 | [5 empty] | 2023-09-12 |  | 2024-10-22 |  | EXP | [8 empty] | 2023-12-04 | Connected |  | No
National Grid | SWANSEA | 515758 | 2777 | 15.2 | Solar | 05_11W84 | 2023-07-17 14:23 | 2023-07-18 | 1 | 0 | 1 | 2023-07-19 | 2023-12-11 | 100 | 78 | 22 | [20 empty] | 2023-04-07 | 2023-07-18 09:18 | 2025-01-03 |  | EXP | [8 empty] | 2024-03-21 | Connected |  | No
National Grid | SOMERSET | 522489 | 2726 | 6 | Solar | 05_18J5 | 2023-07-18 09:18 | 2023-07-19 | 18 | 15 | 3 | 2023-08-11 | 2023-08-31 | 15 | 0 | 15 | [20 empty] | 2023-09-05 |  | 2024-10-05 | Yes | EXP |  | 2023-12-07 | 2023-12-07 | 1 | 0 | 1 |  |  | 2023-12-28 | Connected |  | No
National Grid | BROCKTON | 536401 | 2301 | 100 | Solar | 07_91W49 | 2023-07-18 09:48 | 2023-07-19 | 36 | 27 | 9 | [10 empty] | 2023-09-07 | 2023-10-30 | 37 | 17 | 20 | [11 empty] | 2023-07-18 13:58 |  |  | STD | [9 empty] | Group Study |  | No
National Grid | BROCKTON | 526991 | 2302 | 14.79 | Solar | 07_69J1 | 2023-07-18 13:58 | 2023-07-19 | 16 | 15 | 1 | 2023-08-09 | 2023-08-30 | 16 | 0 | 16 | [20 empty] | 2023-08-30 | 2023-07-18 14:35 | 2024-10-09 | Yes | EXP |  | 2023-10-24 | 2023-10-23 | 0 | 0 | 0 |  |  | 2023-10-25 | Connected |  | No
National Grid | WESTFORD | 541791 | 1886 | 15.2 | Solar | 14_58L1 | 2023-07-18 14:35 | 2023-07-19 | 4 | 2 | 2 | 2023-07-25 | 2023-08-25 | 24 | 0 | 24 | [20 empty] | 2023-09-01 |  | 2025-01-24 | Yes | EXP |  | 2024-03-29 |  | 18 | 0 | 18 |  |  |  | Construction |  | Yes
National Grid | FALL RIVER | 512760 | 2720 | 6 | Solar | 05_106W81 | 2023-07-18 14:38 | 2023-07-19 | 81 | 79 | 2 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | QUINCY | 531634 | 2169 | 10 | Solar | 07_1W4 | 2023-07-18 14:49 | 2023-07-19 | 1 | 0 | 1 | 2023-07-20 | 2023-08-15 | 19 | 0 | 19 | 2023-09-06 | 2023-09-22 | 13 | 0 | 13 | [5 empty] | 2023-09-06 | 2023-09-22 | 13 | 0 | 13 | [5 empty] | 2023-09-21 |  | 2024-11-26 |  | EXP |  | 2023-11-02 | 2023-12-08 | 37 | 0 | 37 |  |  | 2023-12-18 | Connected |  | Yes
National Grid | WORCESTER | 541036 | 1606 | 3.8 | Solar | 01_24W1 | 2023-07-18 14:50 | 2023-07-19 | 1 | 0 | 1 | 2023-07-20 | 2023-08-21 | 23 | 0 | 23 | [20 empty] | 2023-08-22 | 2023-07-18 15:00 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SOMERSET | 541084 | 2726 | 10 | Solar | 05_19W74 | 2023-07-18 15:00 | 2023-07-19 | 1 | 0 | 1 | 2023-07-20 | 2023-10-12 | 58 | 37 | 21 | [20 empty] | 2023-10-12 |  | 2024-10-18 | Yes | EXP |  | 2023-10-25 | 2024-01-22 | 90 | 3 | 87 |  |  | 2024-01-25 | Connected |  | No
National Grid | STOUGHTON | 541916 | 2072 | 16 | Solar | 07_913W43 | 2023-07-19 07:52 | 2023-07-20 | 5 | 4 | 1 | 2023-07-27 | 2024-02-06 | 132 | 107 | 25 | [20 empty] | 2024-02-08 |  | 2025-03-26 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | ABINGTON | 531761 | 2351 | 247.3 | Solar | 07_93W42 | 2023-07-19 14:20 | 2023-07-20 | 34 | 24 | 10 | [10 empty] | 2023-09-06 | 2023-10-05 | 22 | 0 | 22 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | WILBRAHAM | 522940 | 1095 | 4990 | Other | 09_507L3 | 2023-07-19 15:17 | 2023-07-20 | 55 | 45 | 10 | [10 empty] | 2023-10-10 | 2023-11-03 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WEBSTER | 521145 | 1570 | 17.6 | Solar | 01_412L2 | 2023-07-19 15:26 | 2023-07-20 | 2 | 1 | 1 | 2023-07-21 | 2024-02-28 | 151 | 130 | 21 | [20 empty] | 2024-03-04 |  | 2025-03-14 |  | EXP | [8 empty] | 2024-03-18 | Connected |  | No
National Grid | FOXBOROUGH | 531270 | 2035 | 480 | Solar | 05_3431W2 | 2023-07-20 15:38 | 2023-07-21 | 11 | 1 | 10 | [10 empty] | 2023-08-07 | 2023-09-05 | 21 | 0 | 21 | [14 empty] | STD | [9 empty] | Group Study |  | Yes
National Grid | FRANKLIN | 536018 | 2038 | 150 | Solar | 05_348W5 | 2023-07-21 10:21 | 2023-07-24 | 26 | 16 | 10 | [10 empty] | 2023-08-28 | 2023-10-20 | 38 | 18 | 20 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | GARDNER | 536174 | 1440 | 275 | Solar | 01_602W2 | 2023-07-21 10:22 | 2023-07-24 | 26 | 16 | 10 | [10 empty] | 2023-08-28 | 2023-10-20 | 39 | 20 | 19 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | STOUGHTON | 536065 | 2072 | 300 | Solar | 07_913W69 | 2023-07-21 10:23 | 2023-07-24 | 26 | 16 | 10 | [10 empty] | 2023-08-28 | 2023-10-20 | 39 | 20 | 19 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | WEYMOUTH | 542638 | 2190 | 18 | Solar | 07_2W2 | 2023-07-21 10:55 | 2023-07-24 | 2 | 0 | 2 | 2023-07-26 | 2023-08-22 | 20 | 0 | 20 | [20 empty] | 2023-08-28 |  | 2024-10-11 |  | EXP | [8 empty] | 2024-02-01 | Connected |  | No
National Grid | NORTH EASTON | 542282 | 2356 | 20 | Solar | 07_92W78 | 2023-07-21 11:15 | 2023-07-24 | 1 | 0 | 1 | 2023-07-25 | 2024-01-05 | 113 | 94 | 19 | [20 empty] | 2024-01-08 |  | 2025-01-08 |  | EXP | [8 empty] | 2024-03-18 | Connected |  | No
National Grid | HANOVER | 541461 | 2339 | 22.8 | Solar | 07_910W51 | 2023-07-21 11:37 | 2023-07-24 | 98 | 61 | 37 | 2023-12-13 |  | 85 | 28 | 57 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | MARLBOROUGH | 534257 | 1752 | 20 | Solar | 05_311W2 | 2023-07-21 11:50 | 2023-07-24 | 3 | 1 | 2 | 2023-07-27 | 2023-08-24 | 21 | 0 | 21 | [20 empty] | 2023-08-29 |  | 2024-10-01 |  | EXP | [8 empty] | 2024-03-22 | Connected |  | No
National Grid | WORCESTER | 536053 | 1602 | 850 | Solar | 01_6W2 | 2023-07-21 15:12 | 2023-07-24 | 26 | 16 | 10 | [10 empty] | 2023-08-28 | 2024-03-28 | 145 | 94 | 51 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | LOWELL | 536046 | 1854 | 900 | Solar | 14_77L3 | 2023-07-21 15:13 | 2023-07-24 | 26 | 16 | 10 | [10 empty] | 2023-08-28 | 2023-12-04 | 67 | 48 | 19 | [11 empty] | 2023-07-24 10:14 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | BLACKSTONE | 540221 | 1504 | 10.15 | Solar | 05_321W9 | 2023-07-24 10:14 | 2023-07-25 | 2 | 1 | 1 | 2023-07-26 | 2023-11-06 | 72 | 52 | 20 | [20 empty] | 2023-11-09 | 2023-07-24 13:52 | 2024-11-15 | Yes | EXP |  | 2023-12-14 | 2024-01-14 | 32 | 3 | 29 |  |  |  | Completion Documents |  | Yes
National Grid | GRANBY | 540230 | 1033 | 5 | Solar | 09_527L1 | 2023-07-24 13:52 | 2023-07-25 | 2 | 0 | 2 | 2023-07-27 | 2023-08-22 | 19 | 0 | 19 | [20 empty] | 2023-08-28 | 2023-07-24 13:58 | 2024-12-02 | Yes | EXP |  | 2023-11-17 | 2023-12-14 | 28 | 0 | 28 |  |  | 2024-02-17 | Connected |  | No
National Grid | ATTLEBORO | 532360 | 2703 | 10 | Solar | 05_9L6 | 2023-07-24 13:58 | 2023-07-25 | 1 | 0 | 1 | 2023-07-26 | 2023-08-22 | 20 | 0 | 20 | [20 empty] | 2023-08-29 |  | 2024-10-25 | Yes | EXP |  | 2023-10-25 | 2023-12-14 | 51 | 0 | 51 |  |  | 2024-01-09 | Connected |  | No
National Grid | MEDFORD | 541845 | 2155 | 15.66 | Solar | 12_37W4 | 2023-07-24 14:00 | 2023-07-25 | 96 | 70 | 26 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SWANSEA | 533802 | 2777 | 2400 | Solar | 05_11W81 | 2023-07-24 15:40 | 2023-07-25 | 34 | 24 | 10 | [10 empty] | 2023-09-11 | 2023-09-18 | 6 | 0 | 6 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | WESTFORD | 540656 | 1886 | 13.92 | Solar | 14_57L2 | 2023-07-24 15:55 | 2023-07-25 | 4 | 3 | 1 | 2023-07-28 | 2023-10-27 | 64 | 45 | 19 | [20 empty] | 2023-10-31 | 2023-07-24 17:32 | 2024-11-26 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | ANDOVER | 543279 | 1810 | 14.79 | Solar | 14_54L3 | 2023-07-24 17:32 | 2023-07-25 | 2 | 0 | 2 | 2023-07-27 | 2023-09-12 | 33 | 12 | 21 | [20 empty] | 2023-09-14 |  | 2024-11-29 | Yes | EXP |  | 2023-12-04 | 2024-01-16 | 44 | 3 | 41 |  |  | 2024-01-19 | Connected |  | No
National Grid | BOLTON | 543308 | 1740 | 15 | Solar | 01_216W6 | 2023-07-24 19:16 | 2023-07-25 | 1 | 0 | 1 | 2023-07-26 | 2023-08-24 | 23 | 3 | 20 | [20 empty] | 2023-08-24 | 2023-07-25 08:55 | 2024-09-08 |  | EXP | [8 empty] | 2024-01-05 | Connected |  | No
National Grid | WOLLASTON | 531854 | 2170 | 5 | Solar | 07_1W8 | 2023-07-25 08:55 | 2023-07-26 | 58 | 52 | 6 | 2023-10-18 | 2023-11-08 | 16 | 1 | 15 | [20 empty] | 2023-11-09 |  | 2024-11-27 | Yes | EXP |  | 2024-01-10 | 2024-01-09 | 0 | 0 | 0 |  |  | 2024-01-26 | Connected |  | No
National Grid | WILBRAHAM | 543374 | 1095 | 15.2 | Solar | 09_507L3 | 2023-07-25 09:06 | 2023-07-26 | 1 | 0 | 1 | 2023-07-27 | 2023-08-24 | 21 | 0 | 21 | [20 empty] | 2023-08-29 |  | 2025-01-04 |  | EXP | [8 empty] | 2024-01-24 | Connected |  | No
National Grid | NORTH ANDOVER | 543541 | 1845 | 84.6 | Solar | 14_71L1 | 2023-07-25 15:50 | 2023-07-26 | 26 | 16 | 10 | [10 empty] | 2023-08-30 | 2023-10-04 | 25 | 0 | 25 | [11 empty] | 2023-07-25 19:54 |  |  | STD | [9 empty] | Study |  | Yes
National Grid | RANDOLPH | 542276 | 2368 | 9.57 | Solar | 07_5W3 | 2023-07-25 19:54 | 2023-07-26 | 5 | 4 | 1 | 2023-08-02 | 2023-08-24 | 17 | 1 | 16 | [20 empty] | 2023-08-25 | 2023-07-26 10:02 | 2024-08-27 | Yes | EXP |  | 2023-10-21 | 2023-10-23 | 3 | 0 | 3 |  |  | 2023-10-27 | Connected |  | No
National Grid | LYNN | 542019 | 1904 | 3.8 | Solar | 12_29W1 | 2023-07-26 10:02 | 2023-07-27 | 1 | 0 | 1 | 2023-07-28 | 2023-08-23 | 19 | 0 | 19 | [20 empty] | 2023-08-23 |  | 2024-08-24 | Yes | EXP |  | 2023-10-20 | 2023-11-03 | 15 | 0 | 15 |  |  | 2023-11-15 | Connected |  | No
National Grid | WEST NEWBURY | 543688 | 1985 | 15.2 | Solar | 14_47L1 | 2023-07-26 10:15 | 2023-07-27 | 3 | 0 | 3 | 2023-07-31 | 2023-11-03 | 69 | 45 | 24 | [20 empty] | 2023-11-09 |  | 2025-03-05 |  | EXP | [8 empty] | 2024-04-01 | Connected |  | Yes
National Grid | FRANKLIN | 526935 | 2038 | 7.6 | Solar | 05_344W5 | 2023-07-26 11:57 | 2023-07-27 | 4 | 1 | 3 | 2023-08-01 | 2023-11-17 | 78 | 26 | 52 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 540408 | 1841 | 6 | Solar | 14_53J4 | 2023-07-26 14:36 | 2023-07-27 | 20 | 19 | 1 | 2023-08-23 | 2023-09-14 | 16 | 0 | 16 | [20 empty] | 2023-09-15 |  | 2024-09-21 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | ATTLEBORO | 543889 | 2703 | 3 | Solar | 05_9L4 | 2023-07-26 16:00 | 2023-07-27 | 7 | 5 | 2 | 2023-08-07 | 2023-10-12 | 47 | 29 | 18 | [20 empty] | 2023-10-18 | 2023-07-27 09:29 | 2024-11-08 |  | EXP | [8 empty] | 2023-11-28 | Connected |  | No
National Grid | BROCKTON | 543198 | 2302 | 6 | Solar | 07_911W56 | 2023-07-27 09:29 | 2023-07-28 | 1 | 0 | 1 | 2023-07-31 | 2023-09-08 | 30 | 10 | 20 | [20 empty] | 2023-09-08 |  | 2024-09-16 | Yes | EXP |  | 2023-10-28 | 2023-11-14 | 18 | 0 | 18 |  |  |  | Completion Documents |  | Yes
National Grid | BROCKTON | 543423 | 2302 | 3.8 | Solar | 07_91W49 | 2023-07-27 10:21 | 2023-07-28 | 2 | 0 | 2 | 2023-08-01 | 2023-08-24 | 18 | 0 | 18 | [20 empty] | 2023-08-28 | 2023-07-27 10:29 | 2024-08-30 |  | EXP | [8 empty] | 2024-03-01 | Connected |  | No
National Grid | BROCKTON | 543283 | 2301 | 3.8 | Solar | 07_91W49 | 2023-07-27 10:29 | 2023-07-28 | 1 | 0 | 1 | 2023-07-31 | 2023-09-19 | 37 | 17 | 20 | [20 empty] | 2023-09-19 | 2023-07-27 11:49 | 2024-10-07 | Yes | EXP |  | 2024-03-15 |  | 32 | 0 | 32 |  |  |  | Construction |  | Yes
National Grid | METHUEN | 534617 | 1844 | 11.31 | Solar | 14_43L4 | 2023-07-27 11:49 | 2023-07-28 | 1 | 0 | 1 | 2023-07-31 | 2023-08-25 | 20 | 0 | 20 | [20 empty] | 2023-08-30 |  | 2024-10-31 | Yes | EXP |  | 2023-12-06 | 2023-12-12 | 7 | 0 | 7 |  |  | 2024-01-12 | Connected |  | No
National Grid | SCITUATE | 521120 | 2066 | 15 | Solar | 07_915W82 | 2023-07-27 12:34 | 2023-07-28 | 9 | 7 | 2 | 2023-08-10 | 2023-10-11 | 43 | 23 | 20 | [20 empty] | 2023-10-16 |  | 2024-12-03 |  | EXP | [8 empty] | 2024-02-02 | Connected |  | No
National Grid | ATHOL | 544256 | 1331 | 10 | Solar | 09_702W1 | 2023-07-28 07:10 | 2023-07-31 | 1 | 0 | 1 | 2023-08-01 | 2023-09-06 | 26 | 8 | 18 | [20 empty] | 2023-10-04 |  | 2024-10-11 |  | EXP | [8 empty] | 2024-03-05 | Connected |  | No
National Grid | NORTHAMPTON | 543487 | 1060 | 3 | Solar | 09_909W2 | 2023-07-28 10:03 | 2023-07-31 | 2 | 0 | 2 | 2023-08-02 | 2023-08-23 | 16 | 0 | 16 | [20 empty] | 2023-08-28 |  | 2024-09-26 |  | EXP | [8 empty] | 2023-10-06 | Connected |  | No
National Grid | NORTH DIGHTON | 543936 | 2764 | 7.68 | Solar | 05_19W74 | 2023-07-28 11:07 | 2023-07-31 | 3 | 1 | 2 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 543499 | 1843 | 6 | Solar | 14_61L3 | 2023-07-28 11:17 | 2023-07-31 | 1 | 0 | 1 | 2023-08-01 | 2023-08-28 | 20 | 0 | 20 | [20 empty] | 2023-09-05 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 543562 | 2301 | 10 | Solar | 07_91W49 | 2023-07-28 11:27 | 2023-07-31 | 2 | 0 | 2 | 2023-08-02 | 2023-08-25 | 18 | 0 | 18 | [20 empty] | 2023-08-28 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ERVING | 538142 | 1344 | 4999 | Other | 09_705W3 | 2023-07-28 16:14 | 2023-08-02 | 46 | 36 | 10 | [10 empty] | 2023-10-06 | 2023-11-03 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | CHELMSFORD | 544628 | 1824 | 12.6 | Solar | 14_70L3 | 2023-07-31 10:08 | 2023-08-01 | 1 | 0 | 1 | 2023-08-02 | 2023-09-05 | 25 | 8 | 17 | [20 empty] | 2023-09-05 |  | 2024-09-15 |  | EXP | [8 empty] | 2024-02-22 | Connected |  | No
National Grid | LOWELL | 543762 | 1850 | 220 | Solar | 14_75L1 | 2023-07-31 10:15 | 2023-08-01 | 14 | 4 | 10 | [10 empty] | 2023-08-18 | 2023-09-06 | 13 | 0 | 13 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | HANOVER | 544647 | 2339 | 16 | Solar | 07_95W4 | 2023-07-31 10:27 | 2023-08-01 | 5 | 3 | 2 | 2023-08-08 | 2024-02-06 | 124 | 54 | 70 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EAST BRIDGEWATER | 544773 | 2333 | 15.2 | Solar | 07_91W41 | 2023-07-31 13:00 | 2023-08-01 | 3 | 0 | 3 | 2023-08-04 | 2023-08-24 | 15 | 0 | 15 | [20 empty] | 2023-08-29 |  | 2024-09-17 |  | EXP | [8 empty] | 2024-03-18 | Connected |  | No
National Grid | EGREMONT | 544313 | 1230 | 22.8 | Solar | 09_1109W3 | 2023-07-31 14:21 | 2023-08-01 | 1 | 0 | 1 | 2023-08-02 | 2023-08-23 | 16 | 0 | 16 | [20 empty] | 2023-08-28 |  | 2024-08-30 |  | EXP | [8 empty] | 2023-12-16 | Connected |  | No
National Grid | METHUEN | 539516 | 1844 | 10 | Solar | 14_74L1 | 2023-08-01 09:02 | 2023-08-02 | 1 | 0 | 1 | 2023-08-03 | 2023-08-25 | 17 | 0 | 17 | [20 empty] | 2023-08-31 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTHBOROUGH | 544895 | 1532 | 15.2 | Solar | 05_314W4 | 2023-08-01 09:15 | 2023-08-02 | 4 | 0 | 4 | 2023-08-08 | 2023-08-31 | 18 | 0 | 18 | [20 empty] | 2023-09-05 |  | 2024-10-12 |  | EXP | [8 empty] | 2023-11-13 | Connected |  | No
National Grid | UXBRIDGE | 540266 | 1569 | 5 | Solar | 05_321W2 | 2023-08-01 09:27 | 2023-08-02 | 1 | 0 | 1 | 2023-08-03 | 2023-09-05 | 23 | 0 | 23 | 2023-10-17 | 2023-10-31 | 11 | 0 | 11 | [5 empty] | 2023-10-17 | 2023-10-31 | 11 | 0 | 11 | [5 empty] | 2023-11-06 | 2023-08-01 09:29 | 2024-12-09 |  | EXP | [8 empty] | 2024-03-23 | Connected |  | No
National Grid | SAUGUS | 537105 | 1906 | 10 | Solar | 12_25W1 | 2023-08-01 09:29 | 2023-08-02 | 4 | 0 | 4 | 2023-08-08 | 2023-09-05 | 20 | 1 | 19 | [20 empty] | 2023-09-06 |  | 2024-11-18 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | NEWBURYPORT | 510521 | 1950 | 480 | Solar | 14_60L3 | 2023-08-01 10:28 | 2023-08-02 | 27 | 19 | 8 | [10 empty] | 2023-09-11 | 2023-12-11 | 63 | 45 | 18 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | LEOMINSTER | 543114 | 1453 | 7.6 | Solar | 01_207W3 | 2023-08-01 14:46 | 2023-08-02 | 1 | 0 | 1 | 2023-08-03 | 2023-08-24 | 16 | 0 | 16 | [20 empty] | 2023-08-25 |  | 2024-09-06 |  | EXP | [8 empty] | 2023-10-28 | Connected |  | No
National Grid | MENDON | 543188 | 1756 | 7.6 | Solar | 05_332W1 | 2023-08-01 15:06 | 2023-08-02 | 1 | 0 | 1 | 2023-08-03 | 2023-08-28 | 18 | 2 | 16 | [20 empty] | 2023-08-29 |  | 2024-09-07 |  | EXP | [8 empty] | 2024-03-12 | Connected |  | No
National Grid | ABINGTON | 545216 | 2351 | 15.2 | Solar | 07_67J1 | 2023-08-01 15:25 | 2023-08-02 | 1 | 0 | 1 | 2023-08-03 | 2024-02-22 | 138 | 109 | 29 | [20 empty] | 2024-03-13 |  | 2025-04-05 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | LOWELL | 543272 | 1850 | 160 | Solar | 14_75L1 | 2023-08-01 16:34 | 2023-08-02 | 13 | 3 | 10 | [10 empty] | 2023-08-22 | 2023-09-19 | 20 | 0 | 20 | [11 empty] | 2023-08-01 16:35 |  |  | STD | [9 empty] | Study |  | Yes
National Grid | LOWELL | 543280 | 1854 | 240 | Solar | 14_77L1 | 2023-08-01 16:35 | 2023-08-02 | 11 | 0 | 11 | 2023-08-17 | 2023-09-08 | 16 | 0 | 16 | [20 empty] | 2023-10-13 | 2023-08-02 08:42 | 2024-09-27 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | RANDOLPH | 545250 | 2368 | 7.6 | Solar | 07_5W3 | 2023-08-02 08:42 | 2023-08-03 | 3 | 0 | 3 | 2023-08-08 | 2023-08-30 | 17 | 0 | 17 | [20 empty] | 2023-08-31 | 2023-08-02 11:44 | 2024-09-10 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | REHOBOTH | 544824 | 2769 | 7.6 | Solar | 05_7L4 | 2023-08-02 11:44 | 2023-08-03 | 3 | 0 | 3 | 2023-08-08 | 2023-09-01 | 19 | 0 | 19 | [20 empty] | 2023-09-05 | 2023-08-02 15:56 | 2024-10-09 | Yes | EXP |  | 2023-11-10 | 2024-01-05 | 57 | 3 | 54 |  |  | 2024-02-03 | Connected |  | No
National Grid | SOUTHBRIDGE | 545544 | 1550 | 15.2 | Solar | 01_413L2 | 2023-08-02 15:56 | 2023-08-03 | 6 | 5 | 1 | 2023-08-10 | 2023-10-04 | 39 | 21 | 18 | [20 empty] | 2024-01-24 |  | 2025-01-23 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | REVERE | 544704 | 2151 | 100 | Solar | 12_35J1 | 2023-08-02 16:28 | 2023-08-03 | 57 | 48 | 9 | 2023-10-25 | 2023-12-11 | 32 | 8 | 24 | [20 empty] | 2023-12-21 |  | 2024-06-20 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | PLAINVILLE | 544286 | 2762 | 14.625 | Solar | 05_3451W2 | 2023-08-03 13:30 | 2023-08-04 | 1 | 0 | 1 | 2023-08-07 | 2023-09-08 | 25 | 7 | 18 | [20 empty] | 2023-09-13 | 2023-08-03 14:07 | 2024-09-13 |  | EXP | [8 empty] | 2023-10-25 | Connected |  | No
National Grid | BROCKTON | 527500 | 2302 | 10 | Solar | 07_69J1 | 2023-08-03 14:07 | 2023-08-04 | 1 | 0 | 1 | 2023-08-07 | 2023-08-27 | 16 | 0 | 16 | [20 empty] | 2023-08-28 | 2023-08-04 08:49 | 2024-09-07 | Yes | EXP |  | 2023-09-26 | 2023-09-25 | 0 | 0 | 0 |  |  | 2023-12-04 | Connected |  | No
National Grid | BROCKTON | 535460 | 2302 | 6.615 | Solar | 07_911W57 | 2023-08-04 08:49 | 2023-08-07 | 3 | 2 | 1 | 2023-08-09 | 2023-08-30 | 16 | 0 | 16 | [20 empty] | 2023-08-30 |  | 2024-08-31 | Yes | EXP |  | 2023-10-18 | 2023-11-06 | 20 | 0 | 20 |  |  | 2023-11-09 | Connected |  | No
National Grid | LEOMINSTER | 546090 | 1453 | 26 | Solar | 01_207W2 | 2023-08-04 13:39 | 2023-08-07 | 2 | 0 | 2 | 2023-08-09 |  | 171 | 29 | 142 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | FALL RIVER | 544185 | 2721 | 18.85 | Solar | 05_115W44 | 2023-08-04 17:19 | 2023-08-07 | 2 | 0 | 2 | 2023-08-09 | 2024-04-01 | 161 | 28 | 133 | [21 empty] | 2023-08-05 13:16 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 542169 | 1603 | 7.6 | Solar | 01_6W2 | 2023-08-05 13:16 | 2023-08-07 | 1 | 0 | 1 | 2023-08-08 | 2023-08-30 | 17 | 0 | 17 | [20 empty] | 2023-09-05 |  | 2024-10-25 | Yes | EXP |  | 2024-02-16 | 2024-04-11 | 56 | 0 | 56 |  |  |  | Completion Documents |  | Yes
National Grid | BEVERLY | 546247 | 1915 | 9.86 | Solar | 12_51L2 | 2023-08-06 09:14 | 2023-08-07 | 1 | 0 | 1 | 2023-08-08 | 2023-10-02 | 39 | 21 | 18 | [20 empty] | 2023-10-04 |  | 2024-10-08 |  | EXP | [8 empty] | 2023-12-01 | Connected |  | No
National Grid | LAWRENCE | 546077 | 1843 | 3.8 | Solar | 14_61L3 | 2023-08-07 08:52 | 2023-08-08 | 1 | 0 | 1 | 2023-08-09 | 2023-09-05 | 20 | 1 | 19 | 2023-09-15 | 2023-10-10 | 17 | 0 | 17 | [5 empty] | 2023-09-15 | 2023-10-10 | 17 | 0 | 17 | [5 empty] | 2023-10-06 |  | 2024-11-29 |  | EXP |  | 2024-01-20 | 2024-01-19 | 0 | 0 | 0 |  |  |  | Completion Documents |  | Yes
National Grid | LOWELL | 537411 | 1854 | 10 | Solar | 14_21L3 | 2023-08-07 10:19 | 2023-08-08 | 1 | 0 | 1 | 2023-08-09 | 2023-08-11 | 5 | 0 | 5 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WHITMAN | 541611 | 2382 | 90 | Solar | 07_91W47 | 2023-08-07 10:40 | 2023-08-08 | 43 | 33 | 10 | [10 empty] | 2023-10-06 | 2023-12-05 | 41 | 18 | 23 | [11 empty] | 2023-08-07 12:52 |  |  | STD | [9 empty] | Pending Withdraw |  | Yes
National Grid | BELLINGHAM | 540635 | 2019 | 10.44 | Solar | 05_348W7 | 2023-08-07 12:52 | 2023-08-08 | 18 | 17 | 1 | 2023-08-31 | 2023-10-03 | 23 | 0 | 23 | [20 empty] | 2023-10-06 |  | 2024-10-11 | Yes | EXP |  | 2023-11-02 | 2023-11-29 | 28 | 0 | 28 |  |  |  | Completion Documents |  | Yes
National Grid | WESTBOROUGH | 546560 | 1581 | 20 | Solar | 05_312W4 | 2023-08-07 15:43 | 2023-08-08 | 1 | 0 | 1 | 2023-08-09 | 2023-09-05 | 19 | 0 | 19 | [20 empty] | 2023-09-06 |  | 2024-12-23 |  | EXP | [8 empty] | 2024-02-01 | Connected |  | No
National Grid | REVERE | 516902 | 2151 | 6.38 | Solar | 12_7W2 | 2023-08-07 16:13 | 2023-08-08 | 84 | 26 | 58 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BOXFORD | 546601 | 1921 | 15.08 | Solar | 14_56L3 | 2023-08-07 18:25 | 2023-08-08 | 50 | 26 | 24 | [26 empty] | 2023-08-08 10:52 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | AUBURN | 544706 | 1501 | 10 | Solar | 01_26W3 | 2023-08-08 10:52 | 2023-08-09 | 2 | 0 | 2 | 2023-08-11 | 2023-09-25 | 31 | 11 | 20 | [20 empty] | 2023-09-28 |  | 2024-10-10 | Yes | EXP |  | 2024-03-05 | 2024-03-04 | 0 | 0 | 0 |  |  | 2024-03-26 | Connected |  | No
National Grid | LEOMINSTER | 546565 | 1453 | 7.6 | Solar | 01_219W5 | 2023-08-08 11:16 | 2023-08-09 | 119 | 93 | 26 | [26 empty] | 2023-08-08 12:24 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WEBSTER | 545472 | 1570 | 5.8 | Solar | 01_412L2 | 2023-08-08 12:24 | 2023-08-09 | 15 | 14 | 1 | 2023-08-29 | 2023-10-02 | 24 | 0 | 24 | [20 empty] | 2023-10-05 |  | 2024-10-11 | Yes | EXP |  | 2024-01-16 | 2024-02-08 | 24 | 0 | 24 |  |  | 2024-02-22 | Connected |  | No
National Grid | MELROSE | 545446 | 2176 | 6 | Solar | 12_25W5 | 2023-08-08 14:54 | 2023-08-09 | 3 | 0 | 3 | 2023-08-14 | 2023-09-07 | 18 | 0 | 18 | [20 empty] | 2023-09-12 |  | 2024-09-19 |  | EXP | [8 empty] | 2023-10-07 | Connected |  | No
National Grid | ORANGE | 545906 | 1364 | 10 | Solar | 09_705W2 | 2023-08-08 17:20 | 2023-08-09 | 6 | 3 | 3 | 2023-08-17 | 2023-09-11 | 17 | 2 | 15 | [20 empty] | 2023-09-12 | 2023-08-09 01:52 | 2024-09-19 |  | EXP | [8 empty] | 2023-11-04 | Connected |  | No
National Grid | SPENCER | 546629 | 1562 | 4.64 | Solar | 01_552L1 | 2023-08-09 01:52 | 2023-08-10 | 9 | 9 | 0 | 2023-08-23 | 2023-10-04 | 31 | 10 | 21 | [20 empty] | 2023-10-06 |  | 2024-10-10 | Yes | EXP |  | 2023-10-28 | 2024-01-29 | 94 | 3 | 91 |  |  | 2024-02-01 | Connected |  | No
National Grid | SOUTH EGREMONT | 541112 | 1258 | 20 | Solar | 09_1109W2 | 2023-08-09 05:40 | 2023-08-10 | 18 | 18 | 0 | 2023-09-07 | 2023-10-10 | 23 | 0 | 23 | [20 empty] | 2023-10-11 | 2023-08-09 09:50 | 2024-10-28 |  | EXP | [8 empty] | 2023-11-22 | Connected |  | No
National Grid | LEEDS | 546867 | 1053 | 9.86 | Solar | 09_909W3 | 2023-08-09 09:50 | 2023-08-10 | 1 | 0 | 1 | 2023-08-11 | 2023-08-30 | 14 | 0 | 14 | [20 empty] | 2023-09-06 | 2023-08-09 11:58 | 2024-09-30 | Yes | EXP |  | 2023-10-19 | 2023-10-24 | 6 | 0 | 6 |  |  | 2024-03-20 | Connected |  | No
National Grid | NORTHAMPTON | 545579 | 1060 | 4.06 | Solar | 09_905W1 | 2023-08-09 11:58 | 2023-08-10 | 1 | 0 | 1 | 2023-08-11 | 2023-09-11 | 21 | 0 | 21 | [20 empty] | 2023-09-11 |  | 2024-09-13 | Yes | EXP |  | 2023-10-10 | 2023-10-09 | 0 | 0 | 0 |  |  | 2023-10-26 | Connected |  | No
National Grid | NORTHAMPTON | 547130 | 1062 | 15.2 | Solar | 09_909W4 | 2023-08-09 14:17 | 2023-08-10 | 4 | 0 | 4 | 2023-08-16 | 2023-09-07 | 16 | 0 | 16 | [20 empty] | 2023-09-12 |  | 2024-10-19 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | BEVERLY | 537790 | 1915 | 60 | Solar | 12_18L1 | 2023-08-10 09:59 | 2023-08-11 | 17 | 7 | 10 | [10 empty] | 2023-09-05 | 2023-10-05 | 23 | 1 | 22 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | GREAT BARRINGTON | 547421 | 1230 | 5 | Solar | 09_1109W3 | 2023-08-10 12:51 | 2023-08-11 | 4 | 3 | 1 | 2023-08-16 | 2023-09-11 | 18 | 0 | 18 | [20 empty] | 2023-09-12 |  | 2024-10-15 |  | EXP | [8 empty] | 2023-11-27 | Connected |  | No
National Grid | LYNN | 535794 | 1902 | 8.8 | Solar | 12_1388 | 2023-08-10 23:24 | 2023-08-11 | 5 | 2 | 3 | 2023-08-17 | 2024-01-22 | 106 | 43 | 63 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FLORENCE | 540910 | 1062 | 6 | Solar | 09_909W1 | 2023-08-11 10:19 | 2023-08-14 | 5 | 2 | 3 | 2023-08-18 | 2023-09-13 | 18 | 0 | 18 | [20 empty] | 2023-09-19 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WINTHROP | 547388 | 2152 | 130 | Solar | 12_22W5 | 2023-08-11 11:22 | 2023-08-14 | 72 | 61 | 11 | 2023-11-28 | 2024-01-08 | 28 | 3 | 25 | [20 empty] | 2024-01-23 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | WINTHROP | 547547 | 2152 | 60 | Solar | 12_22J2 | 2023-08-11 12:21 | 2023-08-14 | 72 | 61 | 11 | 2023-11-28 | 2024-01-10 | 30 | 6 | 24 | [20 empty] | 2024-01-25 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | NEWBURY | 521128 | 1922 | 9990 | Other | 14_60L3 | 2023-08-11 13:34 | 2023-08-14 | 12 | 2 | 10 | [10 empty] | 2023-08-29 | 2024-02-09 | 112 | 93 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | OXFORD | 543392 | 1540 | 6 | Solar | 01_406L4 | 2023-08-11 15:41 | 2023-08-14 | 1 | 0 | 1 | 2023-08-15 | 2023-09-11 | 19 | 0 | 19 | [20 empty] | 2023-09-11 |  | 2024-10-19 |  | EXP | [8 empty] | 2023-12-26 | Connected |  | No
National Grid | ROCKLAND | 547930 | 2370 | 18.048 | Solar | 07_93W40 | 2023-08-14 09:05 | 2023-08-15 | 4 | 2 | 2 | 2023-08-18 | 2023-10-18 | 42 | 19 | 23 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 521575 | 2301 | 2.61 | Solar | 07_911W13 | 2023-08-14 10:20 | 2023-08-15 | 3 | 0 | 3 | 2023-08-18 | 2023-09-11 | 16 | 0 | 16 | [20 empty] | 2023-09-12 | 2023-08-14 10:49 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 541415 | 1843 | 11.31 | Solar | 14_61L1 | 2023-08-14 10:49 | 2023-08-15 | 11 | 10 | 1 | 2023-08-29 | 2023-10-02 | 24 | 0 | 24 | [20 empty] | 2023-10-05 |  | 2024-10-18 | Yes | EXP |  | 2024-01-24 | 2024-02-02 | 10 | 0 | 10 |  |  | 2024-02-06 | Connected |  | No
National Grid | CLINTON | 546329 | 1510 | 15.2 | Solar | 01_216W1 | 2023-08-14 10:52 | 2023-08-15 | 1 | 0 | 1 | 2023-08-16 | 2023-09-07 | 16 | 0 | 16 | [20 empty] | 2023-09-12 |  | 2025-04-13 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | WESTFORD | 547989 | 1886 | 15.2 | Solar | 14_58L1 | 2023-08-14 11:33 | 2023-08-15 | 2 | 1 | 1 | 2023-08-16 | 2023-10-03 | 35 | 17 | 18 | [20 empty] | 2023-10-12 |  | 2024-11-21 |  | EXP | [8 empty] | 2024-01-31 | Connected |  | No
National Grid | RANDOLPH | 547826 | 2368 | 3 | Solar | 07_5W4 | 2023-08-15 10:23 | 2023-08-16 | 6 | 5 | 1 | 2023-08-23 | 2023-09-22 | 22 | 0 | 22 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SWANSEA | 532784 | 2777 | 14900 | Other | 05_11W84 | 2023-08-15 13:52 | 2023-08-16 | 37 | 27 | 10 | [10 empty] | 2023-10-06 | 2023-12-06 | 42 | 23 | 19 | [11 empty] | 2023-08-16 10:39 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | LAWRENCE | 547080 | 1841 | 6 | Solar | 14_74L3 | 2023-08-16 10:39 | 2023-08-17 | 1 | 0 | 1 | 2023-08-18 | 2023-09-12 | 17 | 0 | 17 | [20 empty] | 2023-09-18 | 2023-08-16 11:04 | 2024-11-14 | Yes | EXP |  | 2024-01-24 | 2024-01-31 | 8 | 0 | 8 |  |  | 2024-03-18 | Connected |  | No
National Grid | METHUEN | 544833 | 1844 | 9.8 | Solar | 14_74L3 | 2023-08-16 11:04 | 2023-08-17 | 3 | 0 | 3 | 2023-08-22 | 2023-09-14 | 17 | 0 | 17 | [20 empty] | 2023-09-18 |  | 2024-09-24 | Yes | EXP |  | 2024-03-26 |  | 21 | 0 | 21 |  |  |  | Construction |  | Yes
National Grid | RANDOLPH | 546614 | 2368 | 3.8 | Solar | 07_97W1 | 2023-08-16 11:30 | 2023-08-17 | 1 | 0 | 1 | 2023-08-18 | 2023-09-11 | 16 | 0 | 16 | [20 empty] | 2023-09-12 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | WEBSTER | 516396 | 1570 | 12.76 | Solar | 01_412L2 | 2023-08-17 11:29 | 2023-08-18 | 15 | 14 | 1 | 2023-09-08 | 2023-10-12 | 24 | 0 | 24 | 2023-11-22 | 2024-01-17 | 37 | 3 | 34 | [5 empty] | 2023-11-22 | 2024-01-17 | 37 | 3 | 34 | [5 empty] | 2024-01-22 |  | 2025-02-19 |  | EXP |  | 2024-04-13 |  | 3 | 0 | 3 |  |  |  | Construction |  | Yes
National Grid | WESTFORD | 549217 | 1886 | 7.6 | Solar | 14_58L1 | 2023-08-17 15:08 | 2023-08-18 | 2 | 1 | 1 | 2023-08-22 | 2023-12-11 | 76 | 60 | 16 | [20 empty] | 2023-12-12 |  | 2025-01-21 |  | EXP | [8 empty] | 2024-03-07 | Connected |  | No
National Grid | FALL RIVER | 518149 | 2720 | 250 | Natural Gas | 05_17J1 | 2023-08-17 22:37 | 2023-08-18 | 115 | 109 | 6 | [29 empty] | STD | [9 empty] | Application |  | Yes
National Grid | BROCKTON | 515523 | 2301 | 400 | Natural Gas | 07_20W9 | 2023-08-17 23:20 | 2023-08-18 | 151 | 83 | 68 | [26 empty] | 2023-08-18 09:53 |  |  | STD | [9 empty] | Withdrawn |  | Yes
National Grid | SOUTHBRIDGE | 548793 | 1550 | 15 | Solar | 01_413L4 | 2023-08-18 09:53 | 2023-08-21 | 1 | 0 | 1 | 2023-08-22 | 2023-10-09 | 34 | 16 | 18 | [20 empty] | 2023-10-10 |  | 2024-10-22 | Yes | EXP |  | 2023-12-08 | 2024-01-24 | 48 | 3 | 45 |  |  | 2024-02-03 | Connected |  | No
National Grid | SCITUATE | 546343 | 2066 | 10.64 | Solar | 07_915W82 | 2023-08-18 12:06 | 2023-08-21 | 7 | 6 | 1 | 2023-08-29 | 2023-12-04 | 66 | 45 | 21 | [20 empty] | 2023-12-12 |  | 2024-12-20 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | WARE | 544083 | 1082 | 7.6 | Solar | 09_501L2 | 2023-08-18 16:32 | 2023-08-21 | 2 | 0 | 2 | 2023-08-23 | 2023-09-25 | 23 | 0 | 23 | [20 empty] | 2023-09-29 | 2023-08-18 17:09 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EAST LONGMEADOW | 549132 | 1028 | 3.8 | Solar | 09_508L1 | 2023-08-18 17:09 | 2023-08-21 | 3 | 2 | 1 | 2023-08-23 | 2023-09-25 | 23 | 0 | 23 | [20 empty] | 2023-09-28 |  | 2024-10-28 | Yes | EXP |  | 2024-02-15 | 2024-03-07 | 22 | 0 | 22 |  |  | 2024-04-08 | Connected |  | No
National Grid | WHITMAN | 546743 | 2382 | 10 | Solar | 07_797W29 | 2023-08-21 10:53 | 2023-08-22 | 1 | 0 | 1 | 2023-08-23 | 2023-09-21 | 21 | 0 | 21 | [20 empty] | 2023-09-22 |  | 2024-10-28 |  | EXP | [8 empty] | 2023-11-22 | Connected |  | No
National Grid | WESTBOROUGH | 544251 | 1581 | 14.805 | Solar | 05_312W4 | 2023-08-21 12:38 | 2023-08-22 | 17 | 13 | 4 | 2023-09-15 | 2023-10-20 | 26 | 4 | 22 | [20 empty] | 2023-10-24 |  | 2024-10-24 |  | EXP | [8 empty] | 2023-11-30 | Connected |  | No
National Grid | LYNN | 536037 | 1904 | 3.8 | Solar | 12_29W4 | 2023-08-21 15:01 | 2023-08-22 | 7 | 5 | 2 | 2023-08-30 | 2023-10-02 | 23 | 0 | 23 | [20 empty] | 2023-10-05 |  | 2024-11-18 |  | EXP | [8 empty] | 2024-02-23 | Connected |  | No
National Grid | DRACUT | 542582 | 1826 | 6.67 | Solar | 14_75L3 | 2023-08-21 15:23 | 2023-08-22 | 21 | 19 | 2 | 2023-09-20 | 2023-10-17 | 19 | 0 | 19 | [20 empty] | 2023-10-23 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FALL RIVER | 537229 | 2720 | 4.93 | Solar | 05_28W50 | 2023-08-21 15:40 | 2023-08-22 | 7 | 6 | 1 | 2023-08-30 | 2023-10-03 | 24 | 0 | 24 | [21 empty] | 2023-08-21 16:19 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WHITINSVILLE | 545580 | 1588 | 7.6 | Solar | 05_320W5 | 2023-08-21 16:19 | 2023-08-22 | 10 | 9 | 1 | 2023-09-05 | 2023-10-09 | 25 | 0 | 25 | [20 empty] | 2023-10-09 |  | 2024-11-15 | Yes | EXP |  | 2024-01-19 | 2024-04-03 | 76 | 0 | 76 |  |  | 2024-04-05 | Connected |  | No
National Grid | WORCESTER | 547657 | 1602 | 3.8 | Solar | 01_1J363 | 2023-08-21 17:05 | 2023-08-22 | 1 | 0 | 1 | 2023-08-23 | 2023-09-14 | 16 | 0 | 16 | [20 empty] | 2023-09-15 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SPRINGFIELD | 550020 | 1095 | 15.2 | Solar | 09_507L3 | 2023-08-22 08:01 | 2023-08-23 | 2 | 0 | 2 | 2023-08-25 | 2023-09-14 | 14 | 0 | 14 | [20 empty] | 2023-09-19 |  | 2024-10-04 |  | EXP | [8 empty] | 2023-12-21 | Connected |  | No
National Grid | NORTHBOROUGH | 548633 | 1532 | 5.985 | Solar | 05_314W4 | 2023-08-22 08:45 | 2023-08-23 | 3 | 1 | 2 | 2023-08-28 | 2023-09-29 | 24 | 0 | 24 | [20 empty] | 2023-10-04 |  | 2024-11-10 |  | EXP | [8 empty] | 2024-03-16 | Connected |  | No
National Grid | NORTON | 546735 | 2766 | 3 | Solar | 05_4L2 | 2023-08-22 09:06 | 2023-08-23 | 4 | 3 | 1 | 2023-08-28 | 2023-09-29 | 24 | 0 | 24 | [20 empty] | 2023-10-02 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FOXBOROUGH | 544841 | 2035 | 6 | Solar | 05_3432W1 | 2023-08-22 09:09 | 2023-08-23 | 4 | 2 | 2 | 2023-08-28 | 2024-01-23 | 100 | 75 | 25 | [20 empty] | 2024-01-26 |  | 2025-02-22 |  | EXP | [8 empty] | 2024-02-27 | Connected |  | No
National Grid | WORCESTER | 550048 | 1602 | 9.5 | Solar | 01_23W4 | 2023-08-22 09:58 | 2023-08-23 | 1 | 0 | 1 | 2023-08-24 | 2024-02-26 | 125 | 106 | 19 | [20 empty] | 2024-02-27 | 2023-08-22 11:14 |  |  | EXP | [9 empty] | Pending Withdraw |  | No
National Grid | DUDLEY | 517520 | 1571 | 10 | Solar | 01_412L5 | 2023-08-22 11:14 | 2023-08-23 | 5 | 4 | 1 | 2023-08-29 | 2023-10-02 | 24 | 0 | 24 | [20 empty] | 2023-04-15 |  | 2024-10-23 | Yes | EXP |  | 2024-03-13 | 2024-03-22 | 10 | 0 | 10 |  |  | 2024-03-25 | Connected |  | No
National Grid | GRANBY | 528884 | 1033 | 10 | Solar | 09_527L1 | 2023-08-22 12:51 | 2023-08-24 |  |  |  | 2023-08-24 | 2023-10-23 | 42 | 17 | 25 | [20 empty] | 2023-08-01 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | STOUGHTON | 540995 | 2072 | 6 | Solar | 07_913W43 | 2023-08-22 13:38 | 2023-08-23 | 19 | 16 | 3 | 2023-09-20 | 2023-10-10 | 14 | 0 | 14 | [20 empty] | 2023-10-12 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BELLINGHAM | 544470 | 2019 | 10 | Solar | 05_344W4 | 2023-08-22 14:21 | 2023-08-23 | 1 | 0 | 1 | 2023-08-24 | 2023-09-29 | 26 | 5 | 21 | [20 empty] | 2023-11-14 |  | 2024-11-17 |  | EXP | [8 empty] | 2023-12-28 | Connected |  | Yes
National Grid | FRANKLIN | 548490 | 2038 | 462.5 | Solar | 05_344W6 | 2023-08-23 07:12 | 2023-08-24 | 38 | 28 | 10 | [10 empty] | 2023-10-19 | 2024-03-08 | 96 | 79 | 17 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | LYNN | 550054 | 1902 | 6 | Solar | 12_29W5 | 2023-08-23 09:22 | 2023-08-24 | 3 | 2 | 1 | 2023-08-29 | 2023-10-03 | 25 | 0 | 25 | 2023-10-18 | 2023-12-04 | 32 | 0 | 32 | [5 empty] | 2023-10-18 | 2023-12-04 | 32 | 0 | 32 | [5 empty] | 2023-12-27 |  | 2025-01-01 |  | EXP |  | 2024-03-14 |  | 33 | 0 | 33 |  |  |  | Construction |  | Yes
National Grid | FLORENCE | 548485 | 1062 | 6 | Solar | 09_909W4 | 2023-08-23 11:39 | 2023-08-24 | 4 | 0 | 4 | 2023-08-30 | 2023-09-29 | 22 | 0 | 22 | [20 empty] | 2023-10-05 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | OXFORD | 550427 | 1540 | 6 | Solar | 01_406L1 | 2023-08-23 12:29 | 2023-08-24 | 3 | 1 | 2 | 2023-08-28 | 2023-11-22 | 60 | 26 | 34 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RANDOLPH | 548604 | 2368 | 10 | Solar | 07_97W1 | 2023-08-23 13:24 | 2023-08-24 | 4 | 0 | 4 | 2023-08-30 | 2024-01-10 | 90 | 66 | 24 | [20 empty] | 2024-01-17 |  | 2025-02-01 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | LAWRENCE | 546449 | 1843 | 6 | Solar | 14_1J1 | 2023-08-23 13:42 | 2023-08-24 | 10 | 9 | 1 | 2023-09-07 | 2023-10-11 | 24 | 0 | 24 | [20 empty] | 2023-10-11 |  | 2024-10-14 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | DUDLEY | 548244 | 1571 | 6 | Solar | 01_412L5 | 2023-08-23 14:05 | 2023-08-24 | 1 | 0 | 1 | 2023-08-25 | 2023-09-28 | 24 | 0 | 24 | [20 empty] | 2023-09-29 |  | 2024-12-15 |  | EXP | [8 empty] | 2024-04-02 | Connected |  | No
National Grid | DUDLEY | 547469 | 1571 | 6 | Solar | 01_412L4 | 2023-08-23 16:00 | 2023-08-24 | 3 | 1 | 2 | 2023-08-29 | 2023-11-14 | 53 | 26 | 27 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOMERSET | 549535 | 2725 | 17.6 | Solar | 05_11W84 | 2023-08-23 16:31 | 2023-08-24 | 6 | 4 | 2 | 2023-08-31 | 2023-10-03 | 23 | 0 | 23 | [20 empty] | 2023-10-06 |  | 2025-03-05 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | BELCHERTOWN | 500677 | 1007 | 999 | Solar | 09_509L2 | 2023-08-23 16:45 | 2023-08-24 | 74 | 64 | 10 | [10 empty] | 2023-12-12 | 2024-01-23 | 28 | 10 | 18 | [11 empty] | 2023-08-24 11:46 |  |  | STD | [9 empty] | Study |  | No
National Grid | PEPPERELL | 550348 | 1463 | 16 | Solar | 01_226L2 | 2023-08-24 11:46 | 2023-08-25 | 1 | 0 | 1 | 2023-08-28 | 2023-09-25 | 20 | 0 | 20 | [20 empty] | 2023-09-29 |  | 2024-11-10 | Yes | EXP | [9 empty] | Design |  | No
National Grid | RANDOLPH | 550147 | 2368 | 5 | Solar | 07_5W4 | 2023-08-24 14:50 | 2023-08-25 | 3 | 1 | 2 | 2023-08-29 | 2023-10-05 | 27 | 3 | 24 | [20 empty] | 2023-10-12 | 2023-08-24 15:41 | 2024-10-14 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | ATTLEBORO | 549717 | 2703 | 11.4 | Solar | 05_9L4 | 2023-08-24 15:41 | 2023-08-25 | 14 | 13 | 1 | 2023-09-14 | 2023-10-16 | 22 | 0 | 22 | [20 empty] | 2023-10-17 | 2023-08-25 07:47 | 2024-11-15 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | BROCKTON | 548794 | 2302 | 6 | Solar | 07_91W40 | 2023-08-25 07:47 | 2023-08-28 | 1 | 0 | 1 | 2023-08-29 | 2023-10-03 | 25 | 0 | 25 | [20 empty] | 2023-10-06 | 2023-08-25 08:25 | 2024-11-24 | Yes | EXP |  | 2024-01-30 | 2024-02-06 | 8 | 0 | 8 |  |  |  | Completion Documents |  | Yes
National Grid | LOWELL | 543771 | 1850 | 9.6 | Solar | 14_75L5 | 2023-08-25 08:25 | 2023-08-28 | 2 | 0 | 2 | 2023-08-30 | 2023-10-03 | 24 | 0 | 24 | [20 empty] | 2023-10-09 | 2023-08-25 10:33 | 2024-10-17 | Yes | EXP | [8 empty] | 2024-04-10 | Connected |  | No
National Grid | CHARLTON | 548536 | 1507 | 7.6 | Solar | 01_415L2 | 2023-08-25 10:33 | 2023-08-28 | 3 | 2 | 1 | 2023-08-30 | 2023-09-29 | 22 | 0 | 22 | [20 empty] | 2023-10-03 | 2023-08-25 12:00 | 2024-11-09 | Yes | EXP |  | 2024-03-09 | 2024-04-10 | 33 | 0 | 33 |  |  |  | Completion Documents |  | Yes
National Grid | FALL RIVER | 550284 | 2724 | 10 | Solar | 05_115W55 | 2023-08-25 12:00 | 2023-08-28 | 2 | 0 | 2 | 2023-08-30 | 2023-09-29 | 22 | 0 | 22 | [20 empty] | 2023-10-04 |  | 2024-11-29 | Yes | EXP |  | 2024-01-10 | 2024-02-28 | 50 | 0 | 50 |  |  |  | Completion Documents |  | Yes
National Grid | ATHOL | 550490 | 1331 | 25 | Solar | 09_702W2 | 2023-08-25 12:08 | 2023-08-28 | 11 | 9 | 2 | 2023-09-13 | 2024-04-03 | 139 | 122 | 17 | [20 empty] | 2024-04-10 | 2023-08-25 12:40 |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LAWRENCE | 550449 | 1840 | 50 | Solar | 14_2J3 | 2023-08-25 12:40 | 2023-08-28 | 18 | 10 | 8 | 2023-09-22 | 2023-10-13 | 15 | 0 | 15 | [20 empty] | 2023-11-06 |  | 2024-08-10 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | LAWRENCE | 550550 | 1841 | 200 | Solar | 14_6J8 | 2023-08-25 13:10 | 2023-08-28 | 10 | 1 | 9 | [10 empty] | 2023-09-11 | 2023-10-16 | 25 | 0 | 25 | [10 empty] | 2024-03-27 |  |  |  | STD | [9 empty] | Conditional Approval |  | Yes
National Grid | BROCKTON | 550852 | 2301 | 8.99 | Solar | 07_91W48 | 2023-08-25 16:38 | 2023-08-28 | 2 | 0 | 2 | 2023-08-30 | 2023-10-26 | 41 | 17 | 24 | [20 empty] | 2023-10-30 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | UPTON | 526206 | 1568 | 15.2 | Solar | 05_320W1 | 2023-08-27 17:09 | 2023-08-28 | 1 | 0 | 1 | 2023-08-29 | 2023-10-05 | 28 | 3 | 25 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GRANBY | 547979 | 1033 | 10 | Solar | 09_527L1 | 2023-08-28 11:43 | 2023-08-29 | 2 | 1 | 1 | 2023-08-30 | 2023-10-04 | 26 | 1 | 25 | 2023-11-02 | 2023-12-11 | 18 | 0 | 18 | [5 empty] | 2023-11-02 | 2023-12-11 | 18 | 0 | 18 | [5 empty] | 2023-11-29 |  | 2024-12-21 |  | EXP |  | 2024-01-18 | 2024-01-31 | 14 | 0 | 14 |  |  | 2024-02-22 | Connected |  | No
National Grid | HOLBROOK | 546998 | 2343 | 11.34 | Solar | 07_97W3 | 2023-08-28 12:32 | 2023-08-29 | 6 | 5 | 1 | 2023-09-06 | 2023-10-09 | 24 | 0 | 24 | 2023-11-21 | 2024-01-05 | 31 | 3 | 28 | [5 empty] | 2023-11-21 | 2024-01-05 | 31 | 3 | 28 | [5 empty] | 2024-01-10 |  | 2025-02-11 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | REVERE | 550822 | 2151 | 3.8 | Solar | 12_16W4 | 2023-08-28 13:00 | 2023-08-29 | 4 | 2 | 2 | 2023-09-05 | 2023-10-05 | 23 | 0 | 23 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 551311 | 1604 | 4.93 | Solar | 01_10J383 | 2023-08-28 13:31 | 2023-08-29 | 3 | 2 | 1 | 2023-08-31 | 2023-10-30 | 42 | 20 | 22 | 2023-11-07 | 2024-01-05 | 40 | 3 | 37 | [5 empty] | 2023-11-07 | 2024-01-05 | 40 | 3 | 37 | [5 empty] | 2024-01-16 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | CHARLTON | 536279 | 1507 | 7.6 | Solar | 01_415L1 | 2023-08-28 15:35 | 2023-08-29 | 2 | 0 | 2 | 2023-08-31 | 2023-09-29 | 21 | 0 | 21 | [20 empty] | 2023-10-05 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTMINSTER | 542295 | 1473 | 9900 | Other | 01_609W1 | 2023-08-28 16:30 | 2023-08-29 | 10 | 2 | 8 | [10 empty] | 2023-09-13 | 2023-10-11 | 20 | 0 | 20 | [11 empty] | 2023-08-28 17:17 |  |  | STD | [9 empty] | Study |  | No
National Grid | AYER | 548714 | 1432 | 7.6 | Solar | 01_201W4 | 2023-08-28 17:17 | 2023-08-29 | 2 | 0 | 2 | 2023-08-31 | 2023-09-29 | 21 | 0 | 21 | [20 empty] | 2023-10-05 | 2023-08-29 09:08 | 2024-11-03 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | RANDOLPH | 550162 | 2368 | 10 | Solar | 07_97W2 | 2023-08-29 09:08 | 2023-08-30 | 1 | 0 | 1 | 2023-08-31 | 2023-10-27 | 41 | 16 | 25 | [20 empty] | 2023-10-30 |  | 2024-11-23 | Yes | EXP |  | 2023-12-07 | 2024-02-17 | 73 | 3 | 70 |  |  | 2024-03-18 | Connected |  | No
National Grid | WEST BRIDGEWATER | 544370 | 2379 | 4999 | Solar | 07_98W19 | 2023-08-29 09:28 | 2023-08-30 | 89 | 83 | 6 | [10 empty] | 2024-01-10 | 2024-02-06 | 19 | 0 | 19 | [11 empty] | 2023-08-29 09:29 |  |  | STD | [9 empty] | Group Study |  | No
National Grid | MENDON | 550748 | 1756 | 3.8 | Solar | 05_335W1 | 2023-08-29 09:29 | 2023-08-30 | 1 | 0 | 1 | 2023-08-31 | 2023-10-27 | 41 | 16 | 25 | [20 empty] | 2023-10-31 |  | 2025-01-11 | Yes | EXP |  | 2024-02-06 | 2024-02-09 | 4 | 0 | 4 |  |  |  | Completion Documents |  | Yes
National Grid | METHUEN | 551686 | 1844 | 6.38 | Solar | 14_74L1 | 2023-08-29 09:47 | 2023-08-30 | 2 | 0 | 2 | 2023-09-01 | 2023-10-06 | 25 | 0 | 25 | 2023-10-13 | 2023-10-31 | 13 | 0 | 13 | [5 empty] | 2023-10-13 | 2023-10-31 | 13 | 0 | 13 | [5 empty] | 2023-11-06 |  | 2024-11-18 |  | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | THREE RIVERS | 550086 | 1080 | 7.6 | Solar | 09_523L1 | 2023-08-29 10:14 | 2023-08-30 | 5 | 3 | 2 | 2023-09-07 | 2023-10-11 | 24 | 0 | 24 | [20 empty] | 2023-10-16 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | DUNSTABLE | 551822 | 1827 | 15.2 | Solar | 01_210L1 | 2023-08-29 11:52 | 2023-08-30 | 8 | 6 | 2 | 2023-09-11 | 2023-10-05 | 19 | 0 | 19 | [20 empty] | 2023-10-09 | 2023-08-29 11:56 | 2024-10-20 |  | EXP | [8 empty] | 2023-11-23 | Connected |  | No
National Grid | DUDLEY | 516711 | 1571 | 9.28 | Solar | 01_412L4 | 2023-08-29 11:56 | 2023-08-30 | 1 | 0 | 1 | 2023-08-31 | 2023-09-29 | 21 | 0 | 21 | [20 empty] | 2023-10-04 |  | 2024-12-07 | Yes | EXP |  | 2024-03-01 | 2024-03-05 | 5 | 0 | 5 |  |  |  | Construction |  | Yes
National Grid | NANTUCKET | 551854 | 2554 | 19 | Solar | 04_101L7 | 2023-08-29 14:03 | 2023-08-30 | 12 | 11 | 1 | 2023-09-15 | 2023-10-09 | 17 | 0 | 17 | [20 empty] | 2023-10-10 | 2023-08-29 18:51 | 2024-11-04 |  | EXP | [8 empty] | 2024-04-12 | Connected |  | No
National Grid | MENDON | 543563 | 1756 | 8.7 | Solar | 05_321W6 | 2023-08-29 18:51 | 2023-08-30 | 11 | 9 | 2 | 2023-09-14 | 2023-10-16 | 22 | 0 | 22 | [20 empty] | 2023-10-23 |  | 2024-11-20 | Yes | EXP |  | 2023-12-13 | 2024-04-01 | 111 | 3 | 108 |  |  | 2024-04-06 | Connected |  | No
National Grid | METHUEN | 546709 | 1844 | 10 | Solar | 14_63L1 | 2023-08-30 04:55 | 2023-08-31 | 70 | 54 | 16 | [26 empty] | 2023-08-30 10:09 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 550755 | 2302 | 10 | Solar | 07_911W77 | 2023-08-30 10:09 | 2023-08-31 | 29 | 25 | 4 | 2023-10-13 | 2023-11-07 | 18 | 0 | 18 | [20 empty] | 2023-11-13 |  | 2024-11-26 | Yes | EXP |  | 2024-01-25 | 2024-02-06 | 13 | 0 | 13 |  |  |  | Completion Documents |  | Yes
National Grid | BROCKTON | 550779 | 2302 | 6 | Solar | 07_911W56 | 2023-08-30 10:14 | 2023-08-31 | 101 | 84 | 17 | 2024-01-30 | 2024-03-29 | 43 | 29 | 14 | [20 empty] | 2024-04-03 | 2023-08-30 10:49 |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | RANDOLPH | 548813 | 2368 | 10 | Solar | 07_97W3 | 2023-08-30 10:49 | 2023-08-31 | 9 | 8 | 1 | 2023-09-13 | 2023-10-16 | 23 | 0 | 23 | [20 empty] | 2023-10-17 | 2023-08-30 11:21 | 2024-11-05 | Yes | EXP |  | 2024-01-04 | 2024-02-08 | 36 | 0 | 36 |  |  | 2024-02-29 | Connected |  | Yes
National Grid | SOUTH ATTLEBORO | 549181 | 2703 | 7.6 | Solar | 05_5J2 | 2023-08-30 11:21 | 2023-08-31 | 1 | 0 | 1 | 2023-09-01 | 2023-10-03 | 22 | 0 | 22 | [20 empty] | 2023-10-09 | 2023-08-30 13:14 | 2024-11-24 |  | EXP |  | 2024-01-06 | 2024-01-30 | 25 | 0 | 25 |  |  |  | Completion Documents |  | Yes
National Grid | LEOMINSTER | 551656 | 1453 | 3.8 | Solar | 01_207W2 | 2023-08-30 13:14 | 2023-08-31 | 2 | 0 | 2 | 2023-09-05 | 2023-10-03 | 21 | 0 | 21 | [20 empty] | 2023-10-04 |  | 2024-11-10 | Yes | EXP |  | 2024-02-22 | 2024-03-13 | 21 | 0 | 21 |  |  |  | Completion Documents |  | Yes
National Grid | NEW SALEM | 548337 | 1355 | 7.6 | Solar | 09_702W3 | 2023-08-30 14:06 | 2023-08-31 | 103 | 75 | 28 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEYMOUTH | 552140 | 2190 | 20 | Solar | 07_99W32 | 2023-08-30 14:06 | 2023-08-31 | 24 | 23 | 1 | 2023-10-04 | 2023-12-07 | 45 | 22 | 23 | [20 empty] | 2024-03-08 | 2023-08-30 14:49 | 2025-03-15 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | LAWRENCE | 543146 | 1843 | 9.6 | Solar | 14_61L3 | 2023-08-30 14:49 | 2023-08-31 | 6 | 5 | 1 | 2023-09-11 | 2023-10-16 | 25 | 0 | 25 | [20 empty] | 2023-10-18 |  | 2024-11-09 | Yes | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | METHUEN | 552256 | 1844 | 20 | Solar | 14_74L1 | 2023-08-30 15:29 | 2023-08-31 | 6 | 4 | 2 | 2023-09-11 | 2024-02-08 | 104 | 82 | 22 | [20 empty] | 2024-02-13 |  | 2025-02-13 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | WEST BRIDGEWATER | 552189 | 2379 | 4.095 | Solar | 07_98W44 | 2023-08-31 08:59 | 2023-09-01 | 2 | 0 | 2 | 2023-09-06 | 2023-10-10 | 24 | 0 | 24 | [20 empty] | 2023-10-12 |  | 2024-11-07 |  | EXP | [8 empty] | 2023-12-07 | Connected |  | Yes
National Grid | GRANBY | 550526 | 1033 | 17.6 | Solar | 09_527L2 | 2023-08-31 11:21 | 2023-09-01 | 8 | 6 | 2 | 2023-09-13 | 2023-12-06 | 59 | 40 | 19 | [20 empty] | 2023-12-13 |  | 2024-12-31 |  | EXP | [9 empty] | Meter Installation |  | No
National Grid | MILFORD | 552467 | 1757 | 10 | Solar | 05_336W3 | 2023-08-31 11:40 | 2023-09-01 | 2 | 0 | 2 | 2023-09-06 | 2023-10-05 | 22 | 3 | 19 | [20 empty] | 2023-10-09 | 2023-08-31 13:51 | 2024-11-06 |  | EXP | [8 empty] | 2024-03-02 | Connected |  | No
National Grid | LEOMINSTER | 540185 | 1453 | 4.35 | Solar | 01_219W5 | 2023-08-31 13:51 | 2023-09-01 | 1 | 0 | 1 | 2023-09-05 | 2023-10-09 | 25 | 0 | 25 | [20 empty] | 2023-10-09 |  | 2024-10-13 | Yes | EXP |  | 2024-01-18 | 2024-02-07 | 21 | 0 | 21 |  |  | 2024-02-07 | Connected |  | No
National Grid | LAWRENCE | 552093 | 1840 | 200 | Solar | 14_2J8 | 2023-08-31 16:57 | 2023-09-01 | 20 | 10 | 10 | [10 empty] | 2023-09-29 | 2023-10-30 | 21 | 0 | 21 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | EAST LONGMEADOW | 545092 | 1028 | 10 | Solar | 09_508L4 | 2023-08-31 17:42 | 2023-09-01 | 3 | 1 | 2 | 2023-09-06 | 2023-10-09 | 24 | 0 | 24 | [20 empty] | 2023-10-12 | 2023-09-01 10:37 | 2024-11-06 |  | EXP | [8 empty] | 2023-11-10 | Connected |  | No
National Grid | DUDLEY | 552358 | 1571 | 6 | Solar | 01_412L4 | 2023-09-01 10:37 | 2023-09-05 | 1 | 0 | 1 | 2023-09-06 | 2023-10-11 | 25 | 0 | 25 | [20 empty] | 2023-10-16 |  | 2024-10-27 | Yes | EXP |  | 2024-01-27 | 2024-04-03 | 68 | 0 | 68 |  |  |  | Meter Installation |  | Yes
National Grid | HUBBARDSTON | 552766 | 1452 | 17.6 | Solar | 01_609W1 | 2023-09-01 11:26 | 2023-09-05 | 1 | 0 | 1 | [10 empty] | 2023-09-06 | 2023-10-26 | 37 | 18 | 19 | [10 empty] | 2024-02-16 | 2023-09-01 11:42 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | SAUGUS | 551251 | 1906 | 3.8 | Solar | 12_16W1 | 2023-09-01 11:42 | 2023-09-05 | 1 | 0 | 1 | 2023-09-06 | 2023-10-09 | 24 | 0 | 24 | [20 empty] | 2023-10-10 | 2023-09-01 13:19 | 2024-10-19 | Yes | EXP |  | 2024-02-09 | 2024-02-26 | 18 | 0 | 18 |  |  | 2024-03-04 | Connected |  | No
National Grid | LAWRENCE | 552329 | 1843 | 7.6 | Solar | 14_61L2 | 2023-09-01 13:19 | 2023-09-05 | 5 | 2 | 3 | 2023-09-11 | 2023-11-06 | 41 | 18 | 23 | [20 empty] | 2023-11-09 |  | 2024-12-02 | Yes | EXP |  | 2024-03-26 |  | 21 | 0 | 21 |  |  |  | Construction |  | Yes
National Grid | LAWRENCE | 552102 | 1841 | 150 | Solar | 14_6J1 | 2023-09-01 13:33 | 2023-09-05 | 15 | 6 | 9 | [10 empty] | 2023-09-25 | 2023-10-31 | 27 | 2 | 25 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 549692 | 1840 | 480 | Solar | 14_61L1 | 2023-09-01 14:15 | 2023-09-05 | 28 | 18 | 10 | [10 empty] | 2023-10-13 | 2023-11-08 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | WEYMOUTH | 552899 | 2190 | 7.6 | Solar | 07_99W32 | 2023-09-01 19:37 | 2023-09-05 | 3 | 0 | 3 | 2023-09-08 | 2023-12-21 | 72 | 25 | 47 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | BELLINGHAM | 552896 | 2019 | 7.6 | Solar | 05_344W4 | 2023-09-01 20:14 | 2023-09-14 | 1 | 0 | 1 | 2023-09-15 | 2023-10-16 | 21 | 0 | 21 | [20 empty] | 2023-10-18 |  | 2024-10-22 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | DUDLEY | 551716 | 1571 | 15.2 | Solar | 01_412L5 | 2023-09-05 10:13 | 2023-09-06 | 3 | 1 | 2 | 2023-09-08 | 2023-10-05 | 20 | 0 | 20 | [20 empty] | 2023-10-09 | 2023-09-05 10:25 | 2024-11-01 |  | EXP | [8 empty] | 2023-12-02 | Connected |  | No
National Grid | METHUEN | 551612 | 1844 | 6.09 | Solar | 14_74L3 | 2023-09-05 10:25 | 2023-09-06 | 15 | 14 | 1 | 2023-09-26 | 2023-11-15 | 35 | 15 | 20 | [20 empty] | 2023-11-16 | 2023-09-05 11:09 | 2024-12-14 | Yes | EXP |  | 2024-01-31 | 2024-03-22 | 52 | 0 | 52 |  |  |  | Completion Documents |  | Yes
National Grid | MILLVILLE | 550614 | 1529 | 3.8 | Solar | 05_321W9 | 2023-09-05 11:09 | 2023-09-06 | 1 | 0 | 1 | 2023-09-07 | 2023-10-04 | 20 | 0 | 20 | [20 empty] | 2023-10-09 |  | 2024-10-18 | Yes | EXP |  | 2024-02-14 |  | 62 | 0 | 62 |  |  |  | Construction |  | No
National Grid | METHUEN | 551550 | 1844 | 12 | Solar | 14_74L1 | 2023-09-05 11:11 | 2023-09-06 | 110 | 53 | 57 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 544120 | 1844 | 5.04 | Solar | 14_74L3 | 2023-09-05 11:25 | 2023-09-06 | 1 | 0 | 1 | 2023-09-07 | 2023-10-11 | 24 | 0 | 24 | 2023-10-24 | 2023-11-27 | 12 | 0 | 12 | [5 empty] | 2023-10-24 | 2023-11-27 | 12 | 0 | 12 | [5 empty] | 2023-11-17 |  | 2024-11-26 |  | EXP |  | 2024-02-01 |  | 75 | 0 | 75 |  |  |  | Construction |  | Yes
National Grid | GARDNER | 551596 | 1440 | 4.93 | Solar | 01_607W5 | 2023-09-05 11:51 | 2023-09-06 | 56 | 56 | 0 | 2023-11-28 | 2024-04-01 | 86 | 29 | 57 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 538670 | 1841 | 12.76 | Solar | 14_53J2 | 2023-09-05 13:40 | 2023-09-06 | 105 | 95 | 10 | 2024-02-08 | 2024-02-21 | 9 | 0 | 9 | 2024-02-27 |  | 35 | 0 | 35 | [5 empty] | 2024-02-27 |  | 35 | 0 | 35 | [9 empty] | EXP | [9 empty] | Supplemental Review |  | Yes
National Grid | WEBSTER | 549203 | 1570 | 12 | Solar | 01_412L2 | 2023-09-05 15:28 | 2023-09-06 | 49 | 46 | 3 | 2023-11-15 | 2024-02-23 | 68 | 36 | 32 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | FALL RIVER | 546881 | 2721 | 10 | Solar | 05_115W53 | 2023-09-05 16:48 | 2023-09-06 | 4 | 0 | 4 | 2023-09-12 | 2023-10-11 | 21 | 0 | 21 | [20 empty] | 2023-08-15 |  | 2024-10-19 |  | EXP | [8 empty] | 2024-02-22 | Connected |  | No
National Grid | BROCKTON | 553044 | 2302 | 6 | Solar | 07_911W56 | 2023-09-05 17:15 | 2023-09-06 | 1 | 0 | 1 | 2023-09-07 | 2023-10-11 | 24 | 0 | 24 | [20 empty] | 2023-10-16 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 553080 | 1605 | 11.5 | Solar | 01_24W1 | 2023-09-06 07:12 | 2023-09-07 | 1 | 0 | 1 | 2023-09-08 | 2023-10-11 | 23 | 0 | 23 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 549133 | 1841 | 6 | Solar | 14_6J2 | 2023-09-06 08:48 | 2023-09-07 | 4 | 3 | 1 | 2023-09-12 | 2023-11-15 | 46 | 22 | 24 | 2023-11-28 | 2024-01-23 | 37 | 3 | 34 | [5 empty] | 2023-11-28 | 2024-01-23 | 37 | 3 | 34 | [5 empty] | 2024-01-23 |  | 2025-03-06 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LYNN | 550854 | 1902 | 6 | Solar | 12_22W2 | 2023-09-06 10:28 | 2023-09-07 | 14 | 13 | 1 | 2023-09-26 | 2023-10-27 | 23 | 0 | 23 | [20 empty] | 2023-10-31 |  | 2024-11-29 |  | EXP | [8 empty] | 2024-01-05 | Connected |  | No
National Grid | BROCKTON | 550946 | 2301 | 3.8 | Solar | 07_911W13 | 2023-09-06 10:52 | 2023-09-07 | 2 | 1 | 1 | 2023-09-11 | 2023-10-11 | 22 | 0 | 22 | [20 empty] | 2023-10-12 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BILLERICA | 529445 | 1821 | 6 | Solar | 14_70L8 | 2023-09-06 15:21 | 2023-09-07 | 3 | 2 | 1 | 2023-09-12 | 2024-02-28 | 115 | 91 | 24 | [20 empty] | 2024-03-05 |  | 2025-04-08 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | FOXBOROUGH | 529749 | 2035 | 6 | Solar | 05_3431W2 | 2023-09-06 16:30 | 2023-09-07 | 1 | 0 | 1 | 2023-09-08 | 2024-01-11 | 85 | 63 | 22 | [20 empty] | 2023-06-04 |  | 2025-01-21 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | WORCESTER | 553055 | 1604 | 10 | Solar | 01_10J383 | 2023-09-07 06:05 | 2023-09-08 | 9 | 7 | 2 | 2023-09-21 | 2023-11-08 | 35 | 16 | 19 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SPENCER | 547266 | 1562 | 10 | Solar | 01_552L3 | 2023-09-07 06:31 | 2023-09-08 | 21 | 20 | 1 | 2023-10-10 | 2023-10-17 | 6 | 0 | 6 | 2023-10-27 | 2023-12-11 | 9 | 0 | 9 | [5 empty] | 2023-10-27 | 2023-12-11 | 9 | 0 | 9 | [5 empty] | 2023-11-15 |  | 2024-12-15 |  | EXP |  | 2024-01-18 |  | 90 | 19 | 71 |  |  |  | Completion Documents |  | No
National Grid | SPENCER | 547263 | 1562 | 10 | Solar | 01_552L3 | 2023-09-07 07:14 | 2023-09-08 | 23 | 22 | 1 | 2023-10-11 | 2023-10-17 | 5 | 0 | 5 | 2023-10-27 | 2023-12-11 | 9 | 0 | 9 | [5 empty] | 2023-10-27 | 2023-12-11 | 9 | 0 | 9 | [5 empty] | 2023-11-15 |  | 2024-12-15 |  | EXP |  | 2024-01-18 |  | 90 | 19 | 71 |  |  |  | Completion Documents |  | No
National Grid | SPENCER | 547258 | 1562 | 10 | Solar | 01_552L3 | 2023-09-07 07:21 | 2023-09-08 | 4 | 3 | 1 | 2023-09-14 | 2023-10-17 | 23 | 0 | 23 | 2023-10-27 | 2023-12-11 | 9 | 0 | 9 | [5 empty] | 2023-10-27 | 2023-12-11 | 9 | 0 | 9 | [5 empty] | 2023-11-15 |  | 2024-11-19 |  | EXP |  | 2024-01-18 | 2024-03-07 | 50 | 0 | 50 |  |  | 2024-04-01 | Connected |  | Yes
National Grid | LOWELL | 553845 | 1851 | 7.54 | Solar | 14_2L3 | 2023-09-07 13:28 | 2023-09-08 | 63 | 46 | 17 | 2023-12-08 | 2024-01-30 | 36 | 13 | 23 | [20 empty] | 2024-02-02 |  | 2025-03-12 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | HUBBARDSTON | 543236 | 1452 | 4999 | Other | 01_602W2 | 2023-09-07 13:32 | 2023-09-08 | 16 | 6 | 10 | [10 empty] | 2023-10-03 | 2023-11-07 | 26 | 6 | 20 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | CLINTON | 546068 | 1510 | 750 | Solar | 01_216W5 | 2023-09-07 14:29 | 2023-09-08 | 24 | 14 | 10 | [10 empty] | 2023-10-13 | 2023-11-03 | 16 | 0 | 16 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | BROCKTON | 553165 | 2301 | 10 | Solar | 07_94W43 | 2023-09-08 12:12 | 2023-09-11 | 44 | 43 | 1 | 2023-11-14 | 2023-12-19 | 25 | 5 | 20 | [20 empty] | 2023-12-21 | 2023-09-08 15:26 | 2024-12-21 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | SOUTHBOROUGH | 554254 | 1772 | 25 | Solar | 05_317W3 | 2023-09-08 15:26 | 2023-09-11 | 2 | 0 | 2 | 2023-09-13 | 2023-10-24 | 29 | 7 | 22 | [20 empty] | 2023-10-26 |  | 2024-12-07 | Yes | EXP |  | 2023-11-21 | 2023-11-21 | 1 | 0 | 1 |  |  | 2024-02-12 | Connected |  | No
National Grid | BELLINGHAM | 550304 | 2019 | 7.6 | Solar | 05_344W4 | 2023-09-08 16:35 | 2023-09-11 | 145 | 52 | 93 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEOMINSTER | 554393 | 1453 | 12.285 | Solar | 01_219W5 | 2023-09-11 07:31 | 2023-09-12 | 2 | 0 | 2 | 2023-09-14 | 2023-11-02 | 36 | 16 | 20 | [20 empty] | 2023-11-08 |  | 2024-11-14 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | WINCHENDON | 553455 | 1475 | 120 | Solar | 01_612W1 | 2023-09-11 09:44 | 2023-09-12 | 15 | 5 | 10 | [10 empty] | 2023-10-02 | 2023-10-30 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | BROCKTON | 552507 | 2301 | 5.985 | Solar | 07_91W49 | 2023-09-11 09:45 | 2023-09-12 | 2 | 1 | 1 | 2023-09-13 | 2023-10-11 | 20 | 0 | 20 | [20 empty] | 2023-10-13 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NAHANT | 538674 | 1908 | 15.2 | Solar | 12_79J2 | 2023-09-11 13:09 | 2023-09-12 | 2 | 0 | 2 | 2023-09-14 | 2023-10-13 | 21 | 0 | 21 | [20 empty] | 2023-10-16 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 550688 | 2301 | 5 | Solar | 07_911W13 | 2023-09-11 13:24 | 2023-09-12 | 5 | 0 | 5 | 2023-09-19 | 2023-10-17 | 21 | 0 | 21 | [21 empty] | 2023-09-11 13:40 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MALDEN | 553658 | 2148 | 10 | Solar | 12_11J2 | 2023-09-11 13:40 | 2023-09-12 | 1 | 0 | 1 | 2023-09-13 | 2023-10-16 | 23 | 0 | 23 | [20 empty] | 2023-10-17 | 2023-09-11 13:54 | 2024-10-26 | Yes | EXP |  | 2024-02-09 |  | 67 | 0 | 67 |  |  |  | Construction |  | Yes
National Grid | BELLINGHAM | 551974 | 2019 | 10 | Solar | 05_108W51 | 2023-09-11 13:54 | 2023-09-12 | 5 | 0 | 5 | 2023-09-19 | 2023-10-19 | 22 | 0 | 22 | [20 empty] | 2023-10-23 |  | 2024-10-28 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | ANDOVER | 554641 | 1810 | 15 | Solar | 14_59L6 | 2023-09-11 13:59 | 2023-09-12 | 2 | 0 | 2 | 2023-09-14 | 2023-10-12 | 20 | 3 | 17 | [20 empty] | 2023-11-09 | 2023-09-11 16:14 | 2024-11-15 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | NORTHBOROUGH | 553637 | 1532 | 160 | Solar | 05_313W1 | 2023-09-11 16:14 | 2023-09-12 | 9 | 0 | 9 | 2023-09-25 | 2023-10-26 | 23 | 0 | 23 | [20 empty] | 2023-11-09 |  | 2024-12-05 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | NORTH ANDOVER | 553486 | 1845 | 15.2 | Solar | 14_55L2 | 2023-09-11 16:45 | 2023-09-12 | 2 | 0 | 2 | 2023-09-14 | 2023-10-12 | 20 | 0 | 20 | [20 empty] | 2023-10-16 |  | 2024-12-20 |  | EXP | [8 empty] | 2024-01-22 | Connected |  | Yes
National Grid | REHOBOTH | 554638 | 2769 | 20 | Solar | 05_7L4 | 2023-09-11 17:24 | 2023-09-12 | 2 | 0 | 2 | 2023-09-14 | 2024-02-28 | 113 | 96 | 17 | [20 empty] | 2024-03-05 | 2023-09-11 17:33 | 2025-03-21 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | NORTHBOROUGH | 553642 | 1532 | 120 | Solar | 05_314W4 | 2023-09-11 17:33 | 2023-09-12 | 14 | 5 | 9 | 2023-10-02 | 2023-11-01 | 22 | 2 | 20 | [20 empty] | 2023-11-15 | 2023-09-11 17:43 | 2024-10-07 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | NORTHBOROUGH | 553649 | 1532 | 160 | Solar | 05_313W3 | 2023-09-11 17:43 | 2023-09-12 | 14 | 5 | 9 | 2023-10-02 | 2023-10-31 | 21 | 0 | 21 | [20 empty] | 2023-11-14 |  | 2024-10-07 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | BROCKTON | 554323 | 2301 | 3.8 | Solar | 07_911W13 | 2023-09-12 07:30 | 2023-09-13 | 28 | 25 | 3 | 2023-10-24 | 2023-11-07 | 11 | 0 | 11 | [20 empty] | 2023-11-13 |  | 2024-11-24 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | WORCESTER | 554530 | 1606 | 3.8 | Solar | 01_24W5 | 2023-09-12 07:42 | 2023-09-13 | 4 | 0 | 4 | 2023-09-19 | 2023-10-16 | 19 | 0 | 19 | [20 empty] | 2023-10-18 |  | 2024-10-24 |  | EXP | [8 empty] | 2023-12-28 | Connected |  | Yes
National Grid | SOUTHBOROUGH | 553692 | 1772 | 10 | Solar | 05_310W5 | 2023-09-12 07:56 | 2023-09-13 | 4 | 2 | 2 | 2023-09-19 | 2023-10-09 | 15 | 0 | 15 | [20 empty] | 2023-10-12 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BEVERLY | 554842 | 1915 | 10 | Solar | 12_51T1 | 2023-09-12 10:39 | 2023-09-13 | 2 | 0 | 2 | 2023-09-15 | 2024-04-01 | 134 | 51 | 83 | [21 empty] | 2023-09-12 13:28 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MONSON | 554489 | 1057 | 3.8 | Solar | 09_503L2 | 2023-09-12 13:28 | 2023-09-13 | 1 | 0 | 1 | 2023-09-14 | 2023-10-13 | 21 | 0 | 21 | [20 empty] | 2023-10-16 | 2023-09-12 13:36 | 2024-11-11 | Yes | EXP |  | 2023-12-27 | 2024-01-18 | 23 | 0 | 23 |  |  | 2024-03-08 | Connected |  | No
National Grid | FLORENCE | 549354 | 1062 | 2.61 | Solar | 09_909W1 | 2023-09-12 13:36 | 2023-09-13 | 13 | 8 | 5 | 2023-10-02 | 2023-11-01 | 22 | 0 | 22 | [20 empty] | 2023-11-02 |  | 2024-12-07 | Yes | EXP |  | 2024-03-07 | 2024-03-06 | 0 | 0 | 0 |  |  | 2024-04-03 | Connected |  | No
National Grid | FALL RIVER | 549206 | 2724 | 25 | Solar | 05_115W55 | 2023-09-12 15:51 | 2023-09-13 | 4 | 2 | 2 | 2023-09-18 | 2023-11-02 | 34 | 18 | 16 | [20 empty] | 2023-11-06 |  | 2024-11-16 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | FLORENCE | 553933 | 1062 | 22.8 | Solar | 09_909W4 | 2023-09-12 17:08 | 2023-09-13 | 4 | 0 | 4 | 2023-09-19 | 2023-10-16 | 19 | 0 | 19 | [20 empty] | 2023-10-23 |  | 2024-11-03 |  | EXP | [8 empty] | 2024-01-27 | Connected |  | No
National Grid | DUDLEY | 552482 | 1571 | 10 | Solar | 01_412L4 | 2023-09-13 10:25 | 2023-09-14 | 4 | 2 | 2 | 2023-09-20 | 2023-10-27 | 27 | 6 | 21 | [20 empty] | 2023-10-30 |  | 2025-03-03 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | LAWRENCE | 504462 | 1843 | 4999 | Other | 14_1J2 | 2023-09-13 11:35 | 2023-09-14 | 38 | 28 | 10 | [10 empty] | 2023-11-08 | 2023-12-09 | 21 | 2 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | WEBSTER | 547164 | 1570 | 3.8 | Solar | 01_412L2 | 2023-09-13 14:32 | 2023-09-14 | 5 | 2 | 3 | 2023-09-21 | 2023-10-23 | 22 | 0 | 22 | [20 empty] | 2023-10-26 | 2023-09-13 14:53 | 2024-11-23 |  | EXP | [8 empty] | 2024-01-05 | Connected |  | No
National Grid | BLACKSTONE | 553505 | 1504 | 10 | Solar | 05_332W1 | 2023-09-13 14:53 | 2023-09-14 | 5 | 3 | 2 | 2023-09-21 | 2023-10-12 | 15 | 0 | 15 | [20 empty] | 2023-10-13 |  | 2024-12-26 | Yes | EXP |  | 2024-01-30 | 2024-02-27 | 29 | 0 | 29 |  |  | 2024-03-25 | Connected |  | No
National Grid | MALDEN | 551574 | 2148 | 10 | Solar | 12_16W7 | 2023-09-13 15:09 | 2023-09-14 | 14 | 12 | 2 | 2023-10-03 | 2023-11-02 | 22 | 0 | 22 | 2023-11-16 | 2024-03-26 | 89 | 3 | 86 | [5 empty] | 2023-11-16 | 2024-03-26 | 89 | 3 | 86 | [5 empty] | 2024-02-26 |  | 2025-04-11 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | MALDEN | 532886 | 2148 | 6 | Solar | 12_37W10 | 2023-09-13 18:15 | 2023-09-14 | 5 | 2 | 3 | 2023-09-20 | 2023-10-23 | 23 | 0 | 23 | [20 empty] | 2023-10-25 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NEWBURYPORT | 555470 | 1950 | 7.54 | Solar | 14_36L1 | 2023-09-14 08:12 | 2023-09-15 | 3 | 1 | 2 | 2023-09-19 | 2023-10-20 | 23 | 3 | 20 | [20 empty] | 2023-10-26 |  | 2024-10-31 |  | EXP | [8 empty] | 2024-02-07 | Connected |  | No
National Grid | GLOUCESTER | 555498 | 1930 | 23.8 | Solar | 12_28L2 | 2023-09-14 09:57 | 2023-09-15 | 28 | 23 | 5 | 2023-10-26 | 2024-01-07 | 49 | 30 | 19 | [20 empty] | 2024-01-10 |  | 2025-01-21 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | MENDON | 555534 | 1756 | 25.2 | Solar | 05_321W6 | 2023-09-14 11:11 | 2023-09-15 | 2 | 0 | 2 | 2023-09-19 | 2024-03-08 | 117 | 28 | 89 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | WORCESTER | 523999 | 1602 | 6.09 | Solar | 01_2J335 | 2023-09-14 11:15 | 2023-09-15 | 1 | 0 | 1 | 2023-09-18 | 2023-12-12 | 59 | 25 | 34 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NEWBURY | 555669 | 1951 | 20 | Solar | 14_60L1 | 2023-09-14 15:33 | 2023-09-15 | 4 | 3 | 1 | 2023-09-20 | 2023-10-10 | 14 | 0 | 14 | [20 empty] | 2023-10-11 |  | 2024-10-14 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | STOCKBRIDGE | 545516 | 1262 | 20 | Solar | 09_1102W1 | 2023-09-14 17:07 | 2023-09-15 | 3 | 0 | 3 | 2023-09-20 | 2023-10-10 | 14 | 0 | 14 | [20 empty] | 2023-10-12 |  | 2025-01-13 |  | EXP | [9 empty] | Meter Installation |  | Yes
National Grid | BROCKTON | 528106 | 2302 | 5.8 | Solar | 07_911W77 | 2023-09-14 17:49 | 2023-09-15 | 93 | 76 | 17 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 519443 | 1843 | 11.375 | Solar | 14_8L1 | 2023-09-14 19:00 | 2023-09-15 | 11 | 10 | 1 | 2023-10-02 | 2023-10-26 | 18 | 0 | 18 | [20 empty] | 2023-10-30 | 2023-09-15 09:26 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MEDFORD | 555081 | 2155 | 10 | Solar | 12_67J1 | 2023-09-15 09:26 | 2023-09-18 | 3 | 2 | 1 | 2023-09-20 | 2023-10-20 | 22 | 0 | 22 | [20 empty] | 2023-10-20 |  | 2024-10-26 | Yes | EXP |  | 2024-02-16 |  | 60 | 0 | 60 |  |  |  | Construction |  | Yes
National Grid | NORTON | 524705 | 2766 | 6 | Solar | 05_4L2 | 2023-09-15 10:12 | 2023-09-18 | 16 | 15 | 1 | 2023-10-10 | 2023-11-03 | 19 | 0 | 19 | [20 empty] | 2023-11-06 | 2023-09-15 13:12 | 2024-11-28 |  | EXP | [8 empty] | 2024-02-03 | Connected |  | No
National Grid | SOUTHBOROUGH | 555478 | 1772 | 240 | Solar | 05_310W3 | 2023-09-15 13:12 | 2023-09-18 | 10 | 1 | 9 | 2023-10-02 | 2023-10-31 | 21 | 0 | 21 | [20 empty] | 2023-11-14 |  | 2024-12-05 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | RANDOLPH | 555021 | 2368 | 10 | Solar | 07_97W2 | 2023-09-15 14:51 | 2023-09-18 | 1 | 0 | 1 | 2023-09-19 | 2023-10-19 | 22 | 0 | 22 | [20 empty] | 2023-10-20 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 554912 | 2301 | 5 | Solar | 07_98W46 | 2023-09-15 14:54 | 2023-09-18 | 42 | 26 | 16 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | LAWRENCE | 553269 | 1841 | 6 | Solar | 14_43L4 | 2023-09-15 15:14 | 2023-09-18 | 9 | 7 | 2 | 2023-09-29 | 2023-10-30 | 21 | 6 | 15 | [21 empty] | 2023-09-15 15:19 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTHBOROUGH | 555486 | 1532 | 240 | Solar | 05_313W1 | 2023-09-15 15:19 | 2023-09-18 | 19 | 10 | 9 | 2023-10-16 | 2023-11-08 | 18 | 0 | 18 | [20 empty] | 2023-11-21 |  | 2024-10-31 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | EAST LONGMEADOW | 547682 | 1028 | 5 | Solar | 09_508L1 | 2023-09-15 15:40 | 2023-09-18 | 2 | 0 | 2 | 2023-09-20 | 2023-10-11 | 15 | 0 | 15 | [20 empty] | 2023-10-16 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTHAMPTON | 555710 | 1060 | 5 | Solar | 09_909W1 | 2023-09-15 15:56 | 2023-09-18 | 2 | 0 | 2 | 2023-09-20 | 2023-10-18 | 20 | 0 | 20 | 2023-10-24 | 2023-12-06 | 30 | 0 | 30 | [5 empty] | 2023-10-24 | 2023-12-06 | 30 | 0 | 30 | [5 empty] | 2023-12-11 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | STOUGHTON | 556059 | 2072 | 22 | Solar | 07_913W69 | 2023-09-15 16:23 | 2023-09-18 | 2 | 0 | 2 | [10 empty] | 2023-09-20 | 2023-10-17 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | BOLTON | 556180 | 1740 | 37.8 | Battery Add-On | 01_225W1 | 2023-09-18 08:12 | 2023-09-19 | 17 | 16 | 1 | 2023-10-12 |  | 127 | 28 | 99 | [24 empty] | EXP | [9 empty] | Screening |  | No
National Grid | LOWELL | 556253 | 1851 | 16 | Battery Add-On | 14_16L3 | 2023-09-18 10:37 | 2023-09-19 | 15 | 14 | 1 | 2023-10-10 | 2024-02-13 | 86 | 69 | 17 | [20 empty] | 2024-02-15 |  | 2025-02-15 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | WEBSTER | 555700 | 1570 | 10 | Solar | 01_412L1 | 2023-09-18 11:26 | 2023-09-19 | 1 | 0 | 1 | 2023-09-20 | 2023-10-20 | 22 | 0 | 22 | [20 empty] | 2023-10-23 |  | 2025-02-20 |  | EXP | [8 empty] | 2024-03-06 | Connected |  | No
National Grid | ANDOVER | 556272 | 1810 | 34 | Battery Add-On | 14_50L1 | 2023-09-18 11:39 | 2023-09-19 | 15 | 14 | 1 | 2023-10-11 |  | 128 | 28 | 100 | [24 empty] | EXP | [9 empty] | Screening |  | No
National Grid | NORTHBOROUGH | 540566 | 1532 | 480 | Solar | 05_313W4 | 2023-09-18 13:34 | 2023-09-19 | 54 | 46 | 8 | [10 empty] | 2023-12-07 | 2024-02-21 | 51 | 32 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | No
National Grid | NORTHBOROUGH | 551451 | 1532 | 250 | Solar | 05_313W4 | 2023-09-18 14:13 | 2023-10-03 | 57 | 57 | 0 | 2023-12-27 | 2024-02-21 | 38 | 17 | 21 | [24 empty] | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LYNN | 553302 | 1904 | 5 | Solar | 12_29W4 | 2023-09-18 17:10 | 2023-09-19 | 10 | 8 | 2 | 2023-10-03 | 2023-11-01 | 21 | 0 | 21 | [20 empty] | 2023-11-02 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LAWRENCE | 555821 | 1841 | 6 | Solar | 14_8L2 | 2023-09-19 11:40 | 2023-09-20 | 4 | 3 | 1 | 2023-09-25 | 2023-11-15 | 37 | 13 | 24 | [20 empty] | 2023-11-21 |  | 2024-12-12 |  | EXP | [8 empty] | 2023-12-15 | Connected |  | No
National Grid | WEBSTER | 551576 | 1570 | 4.64 | Solar | 01_412L2 | 2023-09-19 11:53 | 2023-09-20 | 3 | 0 | 3 | 2023-09-25 | 2023-10-23 | 20 | 0 | 20 | 2023-11-13 | 2024-03-15 | 58 | 41 | 17 | [5 empty] | 2023-11-13 | 2024-03-15 | 58 | 41 | 17 | [5 empty] | 2024-02-13 |  | 2025-02-13 |  | EXP |  | 2024-04-13 |  | 3 | 0 | 3 |  |  |  | Construction |  | No
National Grid | NORTH CHELMSFORD | 553547 | 1863 | 3.8 | Solar | 14_2L3 | 2023-09-19 13:30 | 2023-09-20 | 1 | 0 | 1 | 2023-09-21 | 2023-10-12 | 15 | 0 | 15 | [20 empty] | 2023-10-13 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 553654 | 1602 | 3.8 | Solar | 01_23W1 | 2023-09-19 15:06 | 2023-09-20 | 1 | 0 | 1 | 2023-09-21 | 2024-02-28 | 108 | 28 | 80 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 551871 | 2301 | 6 | Solar | 07_91W49 | 2023-09-19 15:28 | 2023-09-20 | 11 | 8 | 3 | 2023-10-04 | 2023-11-02 | 21 | 0 | 21 | [20 empty] | 2023-11-06 |  | 2025-02-22 |  | EXP | [8 empty] | 2024-03-13 | Connected |  | No
National Grid | SOUTHBOROUGH | 556943 | 1772 | 25 | Solar | 05_310W3 | 2023-09-20 07:19 | 2023-09-21 | 12 | 11 | 1 | 2023-10-06 | 2023-12-11 | 45 | 22 | 23 | [20 empty] | 2023-12-12 |  | 2025-03-07 |  | EXP | [8 empty] | 2024-03-08 | Connected |  | No
National Grid | LYNN | 552539 | 1904 | 3.8 | Solar | 12_29W1 | 2023-09-20 11:08 | 2023-09-21 | 3 | 2 | 1 | 2023-09-25 | 2023-10-17 | 16 | 0 | 16 | [20 empty] | 2023-10-18 |  | 2024-12-01 |  | EXP | [8 empty] | 2024-01-04 | Connected |  | No
National Grid | ORANGE | 556896 | 1364 | 8.99 | Solar | 09_702W2 | 2023-11-15 14:49 | 2023-11-16 | 3 | 1 | 2 | 2023-11-20 | 2023-11-28 | 6 | 0 | 6 | [20 empty] | 2023-11-30 |  | 2024-12-06 |  | EXP | [8 empty] | 2024-02-28 | Connected |  | No
National Grid | LYNN | 533852 | 1905 | 2.925 | Solar | 12_21J37 | 2023-09-20 16:52 | 2023-09-21 | 39 | 36 | 3 | 2023-11-17 | 2024-03-04 | 72 | 58 | 14 | [20 empty] | 2024-03-05 |  | 2025-04-01 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | AUBURN | 557228 | 1501 | 12.18 | Solar | 01_26W2 | 2023-09-21 04:08 | 2023-09-22 | 0 | 0 | 0 | 2023-09-22 | 2023-11-07 | 32 | 17 | 15 | [20 empty] | 2023-11-09 |  | 2024-11-17 |  | EXP | [8 empty] | 2024-01-12 | Connected |  | No
National Grid | WESTMINSTER | 557260 | 1473 | 15.28 | Solar | 01_609W2 | 2023-09-21 08:18 | 2023-09-22 | 11 | 10 | 1 | 2023-10-10 | 2023-12-27 | 54 | 31 | 23 | [20 empty] | 2024-01-02 |  | 2025-02-15 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | LOWELL | 553986 | 1850 | 10 | Solar | 14_75L1 | 2023-09-21 10:36 | 2023-09-22 | 22 | 20 | 2 | 2023-10-24 | 2024-03-05 | 90 | 75 | 15 | [20 empty] | 2024-03-08 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | ANDOVER | 555740 | 1810 | 10 | Solar | 14_59L6 | 2023-09-21 10:46 | 2023-09-22 | 1 | 0 | 1 | 2023-09-25 | 2023-10-24 | 21 | 0 | 21 | 2024-01-31 | 2024-03-04 | 14 | 0 | 14 | [5 empty] | 2024-01-31 | 2024-03-04 | 14 | 0 | 14 | [5 empty] | 2024-02-26 |  | 2025-03-18 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | MILFORD | 529971 | 1757 | 480 | Solar | 05_336W2 | 2023-09-21 10:48 | 2023-09-22 | 118 | 108 | 10 | [10 empty] | 2024-03-15 |  | 22 | 17 | 5 | [14 empty] | STD | [9 empty] | Screening |  | Yes
National Grid | DRACUT | 557324 | 1826 | 3.8 | Solar | 14_75L3 | 2023-09-21 12:01 | 2023-09-22 | 1 | 0 | 1 | 2023-09-25 | 2024-01-19 | 79 | 24 | 55 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | MILLBURY | 556313 | 1527 | 15 | Solar | 01_304W5 | 2023-09-21 14:29 | 2023-09-22 | 7 | 6 | 1 | 2023-10-03 | 2023-10-27 | 18 | 0 | 18 | [20 empty] | 2023-11-08 |  | 2024-11-30 |  | EXP | [8 empty] | 2024-03-15 | Connected |  | No
National Grid | LOWELL | 551159 | 1852 | 6 | Solar | 14_20L2 | 2023-09-21 14:38 | 2023-09-22 | 1 | 0 | 1 | 2023-09-25 | 2023-10-30 | 25 | 0 | 25 | [20 empty] | 2024-02-14 |  | 2025-03-11 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | NORTON | 555397 | 2766 | 7.6 | Solar | 05_4L2 | 2023-09-21 14:45 | 2023-09-22 | 2 | 0 | 2 | 2023-09-26 | 2023-12-05 | 49 | 26 | 23 | [20 empty] | 2023-12-11 |  | 2025-02-22 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | ORANGE | 553560 | 1364 | 13.8 | Solar | 09_705W2 | 2023-09-21 14:50 | 2023-09-22 | 2 | 0 | 2 | 2023-09-26 | 2024-02-23 | 102 | 50 | 52 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTHBOROUGH | 548448 | 1532 | 10 | Solar | 05_313W2 | 2023-09-21 16:06 | 2023-09-22 | 1 | 0 | 1 | 2023-09-25 | 2023-10-16 | 15 | 0 | 15 | [20 empty] | 2023-10-17 |  | 2024-10-23 |  | EXP | [8 empty] | 2023-11-30 | Connected |  | No
National Grid | LOWELL | 556991 | 1851 | 80 | Solar | 14_16L3 | 2023-09-21 17:00 | 2023-09-22 | 14 | 3 | 11 | [10 empty] | 2023-10-13 | 2024-02-27 | 92 | 71 | 21 | [11 empty] | 2023-09-21 17:01 |  |  | STD | [9 empty] | Study |  | Yes
National Grid | LOWELL | 557014 | 1852 | 200 | Solar | 14_3L2 | 2023-09-21 17:01 | 2023-09-22 | 11 | 2 | 9 | 2023-10-10 | 2023-11-06 | 20 | 0 | 20 | [20 empty] | 2023-11-21 |  | 2025-03-23 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | LYNN | 557391 | 1902 | 3.36 | Solar | 12_1J901 | 2023-09-22 08:30 | 2023-09-25 | 30 | 27 | 3 | 2023-11-07 | 2023-12-06 | 20 | 0 | 20 | [20 empty] | 2023-12-11 | 2023-09-22 09:00 | 2024-12-20 |  | EXP | [8 empty] | 2024-03-06 | Connected |  | No
National Grid | HUBBARDSTON | 553543 | 1452 | 6 | Solar | 01_602W2 | 2023-09-22 09:00 | 2023-09-25 | 2 | 0 | 2 | 2023-09-27 | 2023-10-26 | 21 | 0 | 21 | [20 empty] | 2023-10-30 | 2023-09-22 09:26 | 2024-12-02 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | WHITMAN | 545337 | 2382 | 7.56 | Solar | 07_91W47 | 2023-09-22 09:26 | 2023-09-25 | 2 | 1 | 1 | 2023-09-26 | 2023-10-27 | 23 | 0 | 23 | [20 empty] | 2023-10-30 |  | 2024-11-02 | Yes | EXP |  | 2023-12-02 | 2024-01-19 | 49 | 3 | 46 |  |  | 2024-01-25 | Connected |  | No
National Grid | NORTHBOROUGH | 557386 | 1532 | 17.4 | Solar | 05_313W1 | 2023-09-22 10:22 | 2023-09-25 | 12 | 9 | 3 | 2023-10-12 | 2023-11-07 | 19 | 0 | 19 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BERLIN | 554413 | 1503 | 26.4 | Battery Add-On | 05_318W3 | 2023-09-22 11:24 | 2023-09-25 | 2 | 0 | 2 | 2023-09-27 | 2024-01-25 | 81 | 60 | 21 | [20 empty] | 2024-01-30 | 2023-09-22 11:29 | 2025-04-04 |  | EXP | [8 empty] | 2024-04-12 | Connected |  | No
National Grid | MILFORD | 556107 | 1757 | 3.84 | Solar | 05_335W2 | 2023-09-22 11:29 | 2023-09-25 | 1 | 0 | 1 | 2023-09-26 | 2023-10-24 | 20 | 0 | 20 | [20 empty] | 2023-10-25 |  | 2024-11-21 | Yes | EXP |  | 2024-03-05 |  | 42 | 0 | 42 |  |  |  | Construction |  | No
National Grid | DRACUT | 557592 | 1826 | 7.6 | Solar | 14_78L9 | 2023-09-22 11:40 | 2023-09-25 | 1 | 0 | 1 | 2023-09-26 | 2023-10-25 | 21 | 0 | 21 | [20 empty] | 2023-10-26 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | TYNGSBOROUGH | 555818 | 1879 | 6 | Solar | 14_211L1 | 2023-09-22 11:47 | 2023-09-25 | 1 | 0 | 1 | 2023-09-26 | 2024-02-23 | 102 | 25 | 77 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 557158 | 2302 | 7.6 | Solar | 07_911W56 | 2023-09-22 12:05 | 2023-09-25 | 1 | 0 | 1 | 2023-09-26 | 2023-11-15 | 36 | 13 | 23 | [20 empty] | 2023-11-21 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ATTLEBORO | 552428 | 2703 | 6 | Solar | 05_9L4 | 2023-09-22 12:39 | 2023-09-25 | 2 | 1 | 1 | 2023-09-26 | 2023-11-28 | 43 | 18 | 25 | [20 empty] | 2023-11-29 | 2023-09-22 14:12 | 2025-01-10 |  | EXP | [8 empty] | 2024-01-03 | Connected |  | No
National Grid | BROCKTON | 556280 | 2301 | 10 | Solar | 07_94W40 | 2023-09-22 14:12 | 2023-09-25 | 1 | 0 | 1 | 2023-09-26 | 2023-10-30 | 24 | 0 | 24 | [20 empty] | 2023-10-31 |  | 2024-11-15 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | TYNGSBOROUGH | 547517 | 1879 | 360 | Solar | 14_211L1 | 2023-09-22 14:30 | 2023-09-25 | 16 | 6 | 10 | [10 empty] | 2023-10-17 | 2023-11-13 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | WORCESTER | 542998 | 1609 | 22.8 | Solar | 01_23W2 | 2023-09-22 16:15 | 2023-09-25 | 9 | 8 | 1 | 2023-10-06 | 2024-02-05 | 81 | 34 | 47 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | BOXFORD | 557784 | 1921 | 13.8 | Solar | 14_56L3 | 2023-09-22 16:33 | 2023-09-25 | 1 | 0 | 1 | 2023-09-26 | 2023-11-28 | 42 | 20 | 22 | [20 empty] | 2023-11-30 |  | 2024-12-06 |  | EXP | [8 empty] | 2024-01-13 | Connected |  | No
National Grid | AUBURN | 518028 | 1501 | 6 | Solar | 01_26W1 | 2023-09-22 18:11 | 2023-09-25 | 2 | 1 | 1 | 2023-09-26 | 2023-10-30 | 24 | 0 | 24 | [20 empty] | 2023-10-31 | 2023-09-22 20:10 | 2024-11-08 |  | EXP | [8 empty] | 2024-02-22 | Connected |  | No
National Grid | ANDOVER | 541519 | 1810 | 9.57 | Solar | 14_59L1 | 2023-09-22 20:10 | 2023-09-25 | 2 | 0 | 2 | 2023-09-27 | 2023-10-26 | 21 | 0 | 21 | [20 empty] | 2023-10-30 |  | 2024-11-22 | Yes | EXP |  | 2024-03-26 |  | 21 | 0 | 21 |  |  |  | Construction |  | Yes
National Grid | WESTFORD | 555011 | 1886 | 9.57 | Solar | 14_58L1 | 2023-09-25 10:07 | 2023-09-26 | 4 | 1 | 3 | 2023-09-29 | 2023-10-31 | 23 | 3 | 20 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SPENCER | 557789 | 1562 | 10 | Solar | 01_552L2 | 2023-09-25 10:36 | 2023-09-26 | 8 | 4 | 4 | 2023-10-05 | 2024-02-22 | 94 | 76 | 18 | [20 empty] | 2024-02-28 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BELCHERTOWN | 557758 | 1007 | 10 | Solar | 09_509L2 | 2023-09-25 10:59 | 2023-09-26 | 23 | 20 | 3 | 2023-10-27 | 2024-02-02 | 67 | 46 | 21 | [20 empty] | 2024-03-15 | 2023-09-25 12:34 | 2025-03-18 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | AUBURN | 553735 | 1501 | 6.912 | Solar | 01_26W3 | 2023-09-25 12:34 | 2023-09-26 | 12 | 5 | 7 | 2023-10-13 | 2023-11-06 | 17 | 0 | 17 | [20 empty] | 2023-11-06 | 2023-09-25 12:55 | 2025-02-15 | Yes | EXP |  | 2024-04-13 |  | 3 | 0 | 3 |  |  |  | Construction |  | Yes
National Grid | ATHOL | 550568 | 1331 | 15 | Solar | 09_702W2 | 2023-09-25 12:55 | 2023-09-26 | 5 | 1 | 4 | 2023-10-03 | 2023-12-05 | 43 | 18 | 25 | [20 empty] | 2023-12-06 |  | 2024-12-20 | Yes | EXP |  | 2024-01-30 | 2024-03-18 | 49 | 0 | 49 |  |  | 2024-03-20 | Connected |  | No
National Grid | GRANBY | 528945 | 1033 | 15.08 | Solar | 09_527L2 | 2023-09-25 13:12 | 2023-09-26 | 5 | 2 | 3 | 2023-10-03 | 2023-10-03 | 1 | 0 | 1 | [20 empty] | 2023-06-02 | 2023-09-25 13:16 |  |  | EXP | [8 empty] | 2023-10-10 | Connected |  | No
National Grid | DUDLEY | 556681 | 1571 | 10 | Solar | 01_412L4 | 2023-09-25 13:16 | 2023-09-26 | 6 | 0 | 6 | 2023-10-04 | 2023-12-07 | 44 | 25 | 19 | [20 empty] | 2023-12-12 | 2023-09-25 13:52 | 2024-12-20 | Yes | EXP |  | 2024-03-06 |  | 41 | 0 | 41 |  |  |  | Construction |  | No
National Grid | BROCKTON | 554168 | 2302 | 10 | Solar | 07_91W40 | 2023-09-25 13:52 | 2023-09-26 | 4 | 0 | 4 | 2023-10-02 | 2023-11-01 | 22 | 0 | 22 | [20 empty] | 2023-11-02 | 2023-09-25 14:09 | 2024-11-22 | Yes | EXP |  | 2024-01-30 | 2024-01-31 | 2 | 0 | 2 |  |  |  | Withdrawn |  | Yes
National Grid | LYNN | 554746 | 1905 | 10 | Solar | 12_29W1 | 2023-09-25 14:09 | 2023-09-26 | 4 | 0 | 4 | 2023-10-02 | 2023-11-01 | 22 | 0 | 22 | [20 empty] | 2023-11-02 |  | 2024-12-06 | Yes | EXP |  | 2024-02-09 |  | 67 | 0 | 67 |  |  |  | Construction |  | Yes
National Grid | GLOUCESTER | 558123 | 1930 | 3.8 | Solar | 12_28L2 | 2023-09-25 15:16 | 2023-09-26 | 6 | 0 | 6 | 2023-10-04 | 2023-12-19 | 52 | 30 | 22 | [20 empty] | 2023-12-21 | 2023-09-25 17:08 | 2025-01-01 |  | EXP | [8 empty] | 2024-04-03 | Connected |  | No
National Grid | BELCHERTOWN | 551035 | 1007 | 7.6 | Solar | 09_509L1 | 2023-09-25 17:08 | 2023-09-26 | 10 | 4 | 6 | 2023-10-10 | 2023-11-13 | 25 | 5 | 20 | [20 empty] | 2023-11-17 |  | 2024-12-09 | Yes | EXP |  | 2024-04-04 | 2024-04-12 | 9 | 0 | 9 |  |  |  | Construction |  | Yes
National Grid | MARLBOROUGH | 549586 | 1752 | 200 | Solar | 05_317W2 | 2023-09-25 20:30 | 2023-09-26 | 111 | 102 | 9 | 2024-03-08 | 2024-03-19 | 8 | 1 | 7 | [20 empty] | 2024-04-02 | 2023-09-26 09:25 |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | BROCKTON | 554224 | 2301 | 6 | Solar | 07_91W48 | 2023-09-26 09:25 | 2023-09-27 | 5 | 0 | 5 | 2023-10-04 | 2023-11-01 | 20 | 0 | 20 | [20 empty] | 2023-11-07 |  | 2024-11-18 | Yes | EXP |  | 2024-02-27 | 2024-03-18 | 21 | 0 | 21 |  |  |  | Completion Documents |  | Yes
National Grid | CHELMSFORD | 555930 | 1824 | 10 | Solar | 14_16L4 | 2023-09-26 09:33 | 2023-09-27 | 2 | 0 | 2 | 2023-09-29 | 2023-10-30 | 21 | 0 | 21 | 2023-12-05 | 2024-01-17 | 22 | 3 | 19 | [5 empty] | 2023-12-05 | 2024-01-17 | 22 | 3 | 19 | [5 empty] | 2024-01-10 | 2023-09-26 09:45 |  |  | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | GARDNER | 555974 | 1440 | 10 | Solar | 01_607W1 | 2023-09-26 09:45 | 2023-09-27 | 2 | 0 | 2 | 2023-09-29 | 2023-10-30 | 21 | 0 | 21 | [20 empty] | 2023-11-01 |  | 2024-11-18 | Yes | EXP |  | 2024-01-18 | 2024-01-23 | 6 | 0 | 6 |  |  | 2024-02-26 | Connected |  | No
National Grid | MILFORD | 556931 | 1757 | 10 | Solar | 05_336W3 | 2023-09-27 14:20 | 2023-09-28 | 1 | 0 | 1 | 2023-09-29 | 2023-10-24 | 17 | 0 | 17 | [20 empty] | 2023-10-25 | 2023-09-27 15:47 | 2024-11-16 |  | EXP | [8 empty] | 2023-12-01 | Connected |  | No
National Grid | METHUEN | 554723 | 1844 | 7.6 | Solar | 14_63L1 | 2023-09-27 15:47 | 2023-09-28 | 1 | 0 | 1 | 2023-09-29 | 2023-10-24 | 17 | 0 | 17 | [20 empty] | 2023-10-30 |  | 2024-12-05 | Yes | EXP |  | 2024-01-24 | 2024-02-09 | 17 | 0 | 17 |  |  | 2024-03-05 | Connected |  | No
National Grid | LAWRENCE | 555249 | 1841 | 5.76 | Solar | 14_8L2 | 2023-09-27 18:08 | 2023-09-28 | 34 | 30 | 4 | 2023-11-16 | 2023-12-19 | 23 | 1 | 22 | [20 empty] | 2023-12-21 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LYNN | 554220 | 1902 | 10 | Solar | 12_21J34 | 2023-09-28 10:03 | 2023-09-29 | 5 | 2 | 3 | 2023-10-06 | 2024-02-15 | 89 | 25 | 64 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEYMOUTH | 559009 | 2190 | 15.2 | Solar | 07_99W32 | 2023-09-28 12:02 | 2023-09-29 | 3 | 0 | 3 | 2023-10-04 | 2023-11-01 | 20 | 0 | 20 | [20 empty] | 2023-11-03 | 2023-09-28 12:03 | 2025-03-08 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | BROCKTON | 557901 | 2302 | 9.216 | Solar | 07_911W56 | 2023-09-28 12:03 | 2023-09-29 | 6 | 3 | 3 | 2023-10-06 | 2023-11-03 | 20 | 0 | 20 | [20 empty] | 2023-11-07 |  | 2024-12-13 | Yes | EXP |  | 2024-01-08 | 2024-02-06 | 30 | 0 | 30 |  |  |  | Completion Documents |  | Yes
National Grid | ORANGE | 556457 | 1364 | 25 | Solar | 09_702W2 | 2023-09-28 13:25 | 2023-09-29 | 2 | 0 | 2 | 2023-10-03 | 2024-01-04 | 63 | 42 | 21 | [20 empty] | 2024-01-08 |  | 2025-01-16 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | ATTLEBORO | 559140 | 2703 | 19 | Battery Add-On | 05_9L4 | 2023-09-28 15:03 | 2023-09-29 | 2 | 0 | 2 | 2023-10-03 |  | 132 | 84 | 48 | [20 empty] | 2024-03-07 |  |  |  | EXP | [9 empty] | Conditional Approval |  | No
National Grid | LYNN | 551927 | 1902 | 7.54 | Solar | 12_29W5 | 2023-09-28 16:06 | 2023-09-29 | 32 | 29 | 3 | 2023-11-16 |  | 103 | 40 | 63 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | BEVERLY | 518913 | 1915 | 10 | Solar | 12_51L1 | 2023-09-29 08:40 | 2023-10-02 | 6 | 3 | 3 | [10 empty] | 2023-10-10 | 2023-12-12 | 45 | 25 | 20 | [10 empty] | 2024-03-29 | 2023-09-29 10:07 |  |  | STD | [9 empty] | Conditional Approval |  | Yes
National Grid | LOWELL | 558618 | 1854 | 240 | Solar | 14_77L2 | 2023-09-29 10:07 | 2023-10-02 | 15 | 6 | 9 | 2023-10-24 | 2023-11-15 | 16 | 0 | 16 | [20 empty] | 2023-11-30 |  | 2025-03-23 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | LOWELL | 558936 | 1852 | 240 | Solar | 14_13J6 | 2023-09-29 10:41 | 2023-10-02 | 16 | 6 | 10 | [10 empty] | 2023-10-24 | 2023-11-15 | 16 | 0 | 16 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | LOWELL | 558959 | 1851 | 240 | Solar | 14_16L3 | 2023-09-29 10:56 | 2023-10-02 | 15 | 5 | 10 | [10 empty] | 2023-10-24 | 2023-11-15 | 16 | 0 | 16 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | MARLBOROUGH | 528910 | 1752 | 360 | Solar | 05_311W3 | 2023-09-29 11:40 | 2023-10-02 | 19 | 9 | 10 | [10 empty] | 2023-10-31 | 2023-12-01 | 22 | 0 | 22 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | PEPPERELL | 559025 | 1463 | 9.57 | Solar | 01_226L2 | 2023-09-29 12:22 | 2023-10-02 | 9 | 8 | 1 | 2023-10-13 | 2024-02-02 | 75 | 52 | 23 | [20 empty] | 2024-02-06 |  | 2025-02-07 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | PEPPERELL | 559004 | 1463 | 30 | Solar | 01_226L2 | 2023-09-29 12:29 | 2023-10-02 | 5 | 4 | 1 | 2023-10-10 | 2024-03-19 | 110 | 91 | 19 | [20 empty] | 2024-04-04 |  | 2025-04-09 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | BELLINGHAM | 558058 | 2019 | 6 | Solar | 05_344W4 | 2023-09-29 15:18 | 2023-10-02 | 4 | 0 | 4 | 2023-10-06 | 2023-10-31 | 17 | 0 | 17 | [20 empty] | 2023-11-03 |  | 2024-11-20 |  | EXP | [8 empty] | 2024-04-03 | Connected |  | No
National Grid | BROCKTON | 554975 | 2301 | 6 | Solar | 07_911W13 | 2023-09-29 15:32 | 2023-10-02 | 2 | 0 | 2 | 2023-10-04 | 2023-11-01 | 20 | 0 | 20 | [20 empty] | 2023-11-02 |  | 2024-11-10 |  | EXP | [8 empty] | 2024-03-12 | Connected |  | No
National Grid | NORWELL | 542075 | 2061 | 2000 | Solar | 07_915W35 | 2023-09-29 15:59 | 2023-10-02 | 33 | 23 | 10 | [10 empty] | 2023-11-17 | 2024-01-05 | 34 | 14 | 20 | [11 empty] | 2023-09-29 16:06 |  |  | STD | [9 empty] | Study |  | No
National Grid | BROCKTON | 557710 | 2302 | 3.84 | Solar | 07_91W40 | 2023-09-29 16:06 | 2023-10-02 | 1 | 0 | 1 | 2023-10-03 | 2023-11-02 | 22 | 0 | 22 | [20 empty] | 2023-11-06 | 2023-09-29 16:08 | 2024-12-08 | Yes | EXP | [9 empty] | Construction |  | No
National Grid | BELLINGHAM | 557516 | 2019 | 10 | Solar | 05_344W4 | 2023-09-29 16:08 | 2023-10-02 | 8 | 6 | 2 | 2023-10-13 | 2023-11-09 | 20 | 0 | 20 | [20 empty] | 2023-11-14 |  | 2024-11-17 | Yes | EXP |  | 2024-01-30 |  | 77 | 0 | 77 |  |  |  | Construction |  | Yes
National Grid | BROCKTON | 558405 | 2301 | 3.8 | Solar | 07_911W13 | 2023-09-29 16:45 | 2023-10-02 | 3 | 1 | 2 | 2023-10-04 | 2023-11-02 | 21 | 0 | 21 | [20 empty] | 2023-11-07 | 2023-09-29 17:02 | 2024-11-18 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | WORCESTER | 558041 | 1602 | 7.6 | Solar | 01_6W2 | 2023-09-29 17:02 | 2023-10-02 | 4 | 0 | 4 | 2023-10-06 | 2023-11-02 | 19 | 0 | 19 | [20 empty] | 2023-11-06 |  | 2024-11-19 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | BROCKTON | 535779 | 2302 | 8.12 | Solar | 07_69J1 | 2023-09-29 21:56 | 2023-10-02 | 18 | 16 | 2 | 2023-10-27 | 2024-02-28 | 82 | 28 | 54 | [21 empty] | 2023-10-02 08:11 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SWANSEA | 559394 | 2777 | 5 | Solar | 05_11W83 | 2023-10-02 08:11 | 2023-10-03 | 10 | 7 | 3 | 2023-10-17 | 2023-11-06 | 15 | 0 | 15 | [20 empty] | 2023-11-06 |  | 2024-11-10 | Yes | EXP |  | 2024-01-12 | 2024-02-21 | 41 | 0 | 41 |  |  |  | Completion Documents |  | Yes
National Grid | DUDLEY | 558380 | 1571 | 15.2 | Solar | 01_412L4 | 2023-10-02 12:05 | 2023-10-03 | 15 | 14 | 1 | 2023-10-24 | 2024-01-11 | 55 | 39 | 16 | [20 empty] | 2024-01-16 |  | 2025-01-18 |  | EXP | [8 empty] | 2024-02-07 | Connected |  | No
National Grid | TEWKSBURY | 558173 | 1876 | 240 | Solar | 14_20L2 | 2023-10-02 16:02 | 2023-10-03 | 94 | 86 | 8 | [10 empty] | 2024-02-22 | 2024-03-01 | 7 | 0 | 7 | [11 empty] | 2023-10-02 17:45 |  |  | STD | [9 empty] | Study |  | Yes
National Grid | PEMBROKE | 553060 | 2359 | 10 | Solar | 07_910W25 | 2023-10-02 17:45 | 2023-10-03 | 3 | 0 | 3 | 2023-10-06 | 2024-02-20 | 91 | 74 | 17 | [20 empty] | 2024-02-26 | 2023-10-03 09:10 | 2025-02-26 | Yes | EXP |  | 2024-03-14 |  | 33 | 0 | 33 |  |  |  | Construction |  | Yes
National Grid | LOWELL | 558692 | 1854 | 7.6 | Solar | 14_77L3 | 2023-10-03 09:10 | 2023-10-04 | 2 | 0 | 2 | 2023-10-06 | 2023-11-01 | 18 | 0 | 18 | [20 empty] | 2023-11-03 |  | 2024-11-16 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | BILLERICA | 559528 | 1821 | 13.34 | Solar | 14_18L3 | 2023-10-03 12:01 | 2023-10-04 | 6 | 4 | 2 | 2023-10-13 | 2023-11-29 | 32 | 9 | 23 | [20 empty] | 2023-11-30 |  | 2024-12-02 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | BROCKTON | 548907 | 2302 | 600 | Natural Gas | 07_91W40 | 2023-10-03 13:23 | 2023-10-04 | 82 | 73 | 9 | [10 empty] | 2024-02-06 | 2024-02-20 | 10 | 0 | 10 | [14 empty] | STD | [9 empty] | Group Study |  | Yes
National Grid | WORCESTER | 559088 | 1607 | 10 | Solar | 01_8W1 | 2023-10-03 14:44 | 2023-10-04 | 3 | 0 | 3 | 2023-10-10 | 2024-03-13 | 106 | 28 | 78 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 558668 | 2301 | 2.61 | Solar | 07_911W13 | 2023-10-04 10:29 | 2023-10-05 | 6 | 3 | 3 | 2023-10-13 | 2023-11-05 | 17 | 0 | 17 | [20 empty] | 2023-11-06 |  | 2025-02-11 |  | EXP | [8 empty] | 2024-02-15 | Connected |  | No
National Grid | MELROSE | 560633 | 2176 | 9.57 | Solar | 12_25W5 | 2023-10-04 15:36 | 2023-10-05 | 2 | 1 | 1 | 2023-10-06 | 2023-11-03 | 20 | 0 | 20 | [20 empty] | 2023-11-09 |  | 2024-12-20 |  | EXP | [8 empty] | 2024-03-19 | Connected |  | No
National Grid | NANTUCKET | 560671 | 2554 | 20.88 | Solar | 04_101L5 | 2023-10-04 15:47 | 2023-10-05 | 6 | 4 | 2 | 2023-10-13 | 2023-11-16 | 25 | 6 | 19 | [20 empty] | 2023-11-20 | 2023-10-04 16:17 | 2024-11-23 |  | EXP | [8 empty] | 2024-02-13 | Connected |  | No
National Grid | LAWRENCE | 558017 | 1841 | 7.6 | Solar | 14_74L6 | 2023-10-04 16:17 | 2023-10-05 | 3 | 0 | 3 | 2023-10-10 | 2023-11-06 | 20 | 0 | 20 | [20 empty] | 2023-11-09 |  | 2024-11-29 | Yes | EXP | [8 empty] | 2024-03-11 | Connected |  | No
National Grid | BROCKTON | 554752 | 2301 | 6 | Solar | 07_91W48 | 2023-10-04 18:41 | 2023-10-05 | 3 | 0 | 3 | 2023-10-11 | 2023-11-01 | 16 | 0 | 16 | [20 empty] | 2023-11-06 |  | 2024-11-28 |  | EXP | [8 empty] | 2024-02-12 | Connected |  | No
National Grid | NORTHAMPTON | 552016 | 1062 | 12.6 | Solar | 09_909W4 | 2023-10-05 07:22 | 2023-10-06 | 2 | 0 | 2 | 2023-10-10 | 2024-02-23 | 93 | 50 | 43 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTPORT | 560606 | 2790 | 15.08 | Solar | 05_115W45 | 2023-10-05 10:01 | 2023-10-06 | 2 | 0 | 2 | 2023-10-10 | 2024-01-10 | 63 | 41 | 22 | [20 empty] | 2024-01-16 |  | 2025-01-23 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | MANCHESTER | 560873 | 1944 | 23 | Solar | 12_28L2 | 2023-10-05 11:51 | 2023-10-06 | 1 | 0 | 1 | 2023-10-10 | 2024-03-21 | 112 | 91 | 21 | [20 empty] | 2024-03-26 |  | 2025-03-27 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | LOWELL | 558659 | 1851 | 200 | Solar | 14_16L3 | 2023-10-05 14:45 | 2023-10-06 | 12 | 2 | 10 | [10 empty] | 2023-10-24 | 2023-12-05 | 29 | 11 | 18 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | LOWELL | 558966 | 1854 | 200 | Solar | 14_77L2 | 2023-10-05 14:47 | 2023-10-06 | 11 | 2 | 9 | 2023-10-24 | 2023-12-05 | 29 | 11 | 18 | [20 empty] | 2023-12-19 |  | 2024-08-08 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | MILFORD | 500304 | 1757 | 3000 | Solar | 05_335W2 | 2023-10-05 16:46 | 2023-10-06 | 129 | 120 | 9 | [29 empty] | STD | [9 empty] | Application |  | Yes
National Grid | GRAFTON | 561102 | 1536 | 15.2 | Solar | 01_328W2 | 2023-10-06 07:36 | 2023-10-10 | 0 | 0 | 0 | 2023-10-10 | 2023-11-03 | 19 | 0 | 19 | [20 empty] | 2023-11-07 | 2023-10-06 09:03 | 2025-01-29 |  | EXP | [8 empty] | 2024-02-10 | Connected |  | No
National Grid | RANDOLPH | 560567 | 2368 | 6.144 | Solar | 07_97W2 | 2023-10-06 09:03 | 2023-10-10 | 10 | 6 | 4 | 2023-10-24 | 2023-11-15 | 16 | 0 | 16 | [20 empty] | 2023-11-27 |  | 2024-12-28 | Yes | EXP | [9 empty] | Meter Installation |  | Yes
National Grid | HAVERHILL | 554496 | 1830 | 480 | Solar | 14_76L3 | 2023-10-06 11:30 | 2023-10-10 | 11 | 1 | 10 | [10 empty] | 2023-10-24 |  | 118 | 53 | 65 | [14 empty] | STD | [9 empty] | Screening |  | Yes
National Grid | MELROSE | 530600 | 2176 | 15.8 | Solar | 12_25W5 | 2023-10-09 09:09 | 2023-10-10 | 5 | 4 | 1 | 2023-10-17 | 2023-11-09 | 18 | 0 | 18 | [20 empty] | 2023-06-13 | 2023-10-09 12:20 | 2024-11-22 |  | EXP | [8 empty] | 2024-03-01 | Connected |  | No
National Grid | ADAMS | 558595 | 1220 | 3.8 | Solar | 09_1021W2 | 2023-10-09 12:20 | 2023-10-10 | 3 | 0 | 3 | 2023-10-13 | 2023-11-09 | 20 | 0 | 20 | [20 empty] | 2023-11-14 |  | 2024-12-26 | Yes | EXP |  | 2024-01-18 | 2024-02-06 | 20 | 0 | 20 |  |  | 2024-03-05 | Connected |  | No
National Grid | STOUGHTON | 560318 | 2072 | 7.6 | Solar | 07_94W44 | 2023-10-09 12:24 | 2023-10-10 | 3 | 0 | 3 | 2023-10-13 | 2023-11-15 | 23 | 6 | 17 | 2023-11-22 | 2024-02-23 | 63 | 3 | 60 | [5 empty] | 2023-11-22 | 2024-02-23 | 63 | 3 | 60 | [5 empty] | 2024-03-19 |  | 2025-03-26 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | MARLBOROUGH | 538691 | 1752 | 11.05 | Solar | 05_311W2 | 2023-10-09 12:38 | 2023-10-10 | 1 | 0 | 1 | 2023-10-11 | 2023-11-03 | 18 | 0 | 18 | [20 empty] | 2023-11-09 | 2023-10-09 12:38 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 559181 | 1607 | 10 | Solar | 01_8W1 | 2023-10-09 12:38 | 2023-10-10 | 5 | 4 | 1 | 2023-10-16 | 2023-11-07 | 17 | 0 | 17 | [20 empty] | 2023-11-13 | 2023-10-09 13:08 | 2024-12-23 | Yes | EXP |  | 2024-01-12 | 2024-01-18 | 7 | 0 | 7 |  |  | 2024-03-06 | Connected |  | No
National Grid | BROCKTON | 558206 | 2301 | 6 | Solar | 07_911W13 | 2023-10-09 13:08 | 2023-10-10 | 3 | 0 | 3 | 2023-10-13 | 2023-11-02 | 15 | 0 | 15 | [20 empty] | 2023-11-06 |  | 2024-11-29 | Yes | EXP |  | 2024-03-14 | 2024-03-21 | 8 | 0 | 8 |  |  |  | Completion Documents |  | Yes
National Grid | SOUTHBRIDGE | 555308 | 1550 | 5 | Solar | 01_413L4 | 2023-10-10 09:45 | 2023-10-11 | 1 | 0 | 1 | 2023-10-12 | 2024-02-27 | 93 | 70 | 23 | [20 empty] | 2024-03-04 |  | 2025-03-04 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | LAWRENCE | 561606 | 1843 | 3.8 | Solar | 14_61L3 | 2023-10-10 11:56 | 2023-10-11 | 5 | 3 | 2 | 2023-10-17 | 2023-12-04 | 34 | 16 | 18 | 2023-12-11 | 2024-01-17 | 21 | 3 | 18 | [5 empty] | 2023-12-11 | 2024-01-17 | 21 | 3 | 18 | [5 empty] | 2024-01-05 |  | 2025-01-24 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | WILLIAMSTOWN | 559874 | 1267 | 225 | Solar | 09_1001W1 | 2023-10-10 12:05 | 2023-10-11 | 35 | 26 | 9 | 2023-12-01 | 2024-04-01 | 83 | 59 | 24 | [24 empty] | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | WESTMINSTER | 556865 | 1473 | 4998 | Solar |  | 2023-10-10 12:09 | 2023-10-11 | 123 | 3 | 120 | [29 empty] | STD | [9 empty] | Pending Withdraw |  | No
National Grid | SPENCER | 561832 | 1562 | 10 | Solar | 01_552L3 | 2023-10-10 13:45 | 2023-10-11 | 1 | 0 | 1 | 2023-10-12 | 2024-01-03 | 56 | 33 | 23 | [20 empty] | 2024-01-08 |  | 2025-01-10 |  | EXP | [8 empty] | 2024-04-10 | Connected |  | No
National Grid | BROCKTON | 561903 | 2301 | 15.2 | Solar | 07_91W49 | 2023-10-10 14:10 | 2023-10-11 | 8 | 6 | 2 | 2023-10-23 | 2023-11-30 | 28 | 16 | 12 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 555644 | 2301 | 5 | Solar | 07_91W49 | 2023-10-11 10:01 | 2023-10-12 | 3 | 0 | 3 | 2023-10-17 | 2023-11-06 | 15 | 0 | 15 | [20 empty] | 2023-11-07 | 2023-10-19 11:26 | 2024-12-16 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | DRACUT | 559958 | 1826 | 10 | Solar | 14_75L3 | 2023-10-19 11:26 | 2023-10-20 | 5 | 4 | 1 | 2023-10-27 | 2024-01-02 | 44 | 19 | 25 | [20 empty] | 2024-01-02 |  | 2025-01-07 | Yes | EXP |  | 2024-03-06 | 2024-03-26 | 21 | 0 | 21 |  |  |  | Completion Documents |  | Yes
National Grid | METHUEN | 559163 | 1844 | 250 | Solar | 14_75L3 | 2023-11-03 16:32 | 2023-11-06 | 10 | 0 | 10 | [10 empty] | 2023-11-20 | 2024-01-03 | 30 | 11 | 19 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | LYNN | 565880 | 1904 | 10 | Solar | 12_24W1 | 2023-11-03 16:37 | 2023-11-06 | 2 | 0 | 2 | 2023-11-08 | 2024-03-11 | 83 | 65 | 18 | [20 empty] | 2024-03-15 |  | 2025-04-12 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LYNN | 560141 | 1904 | 6 | Solar | 12_24W1 | 2023-10-19 11:43 | 2023-10-20 | 17 | 15 | 2 | 2023-11-14 | 2023-12-14 | 23 | 7 | 16 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HAVERHILL | 562970 | 1832 | 10 | Solar | 14_43L2 | 2023-11-01 17:57 | 2023-11-02 | 3 | 2 | 1 | 2023-11-07 | 2023-12-27 | 34 | 12 | 22 | 2024-02-13 | 2024-03-11 | 19 | 0 | 19 | [5 empty] | 2024-02-13 | 2024-03-11 | 19 | 0 | 19 | [5 empty] | 2024-03-13 | 2023-10-11 14:47 | 2025-03-25 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LYNN | 552287 | 1904 | 10 | Solar | 12_24W2 | 2023-10-11 14:47 | 2023-10-12 | 1 | 0 | 1 | 2023-10-13 | 2023-11-06 | 17 | 0 | 17 | [20 empty] | 2023-12-13 |  | 2025-02-14 | Yes | EXP |  | 2024-04-11 |  | 5 | 0 | 5 |  |  |  | Construction |  | Yes
National Grid | WESTMINSTER | 566961 | 1473 | 5 | Solar | 01_609W1 | 2023-11-08 15:52 | 2023-11-09 | 1 | 0 | 1 | 2023-11-13 | 2024-01-08 | 38 | 14 | 24 | 2024-03-01 | 2024-03-29 | 10 | 0 | 10 | [5 empty] | 2024-03-01 | 2024-03-29 | 10 | 0 | 10 | [5 empty] | 2024-03-19 | 2023-11-07 09:52 |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | WESTMINSTER | 560920 | 1473 | 5.235 | Solar | 01_609W1 | 2023-11-07 09:52 | 2023-11-08 | 4 | 3 | 1 | 2023-11-15 | 2023-12-15 | 22 | 0 | 22 | [20 empty] | 2023-12-19 |  | 2025-01-29 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | LAWRENCE | 564231 | 1844 | 7.6 | Solar | 14_43L4 | 2023-11-08 13:32 | 2023-11-09 | 6 | 3 | 3 | 2023-11-20 | 2023-12-22 | 23 | 3 | 20 | [20 empty] | 2023-12-27 |  | 2025-01-24 |  | EXP | [8 empty] | 2024-02-09 | Connected |  | No
National Grid | BRADFORD | 550928 | 1835 | 7.6 | Solar | 14_43L6 | 2023-10-11 16:39 | 2023-10-12 | 1 | 0 | 1 | 2023-10-13 | 2023-11-07 | 18 | 0 | 18 | 2023-12-12 | 2024-01-25 | 30 | 3 | 27 | [5 empty] | 2023-12-12 | 2024-01-25 | 30 | 3 | 27 | [5 empty] | 2024-01-30 | 2023-10-24 08:11 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | AUBURN | 564813 | 1501 | 7.6 | Solar | 01_406L2 | 2023-10-24 08:11 | 2023-10-25 | 11 | 10 | 1 | 2023-11-08 | 2023-12-15 | 26 | 5 | 21 | [20 empty] | 2023-12-28 |  | 2025-01-08 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | WEST NEWBURY | 563377 | 1985 | 22.6 | Solar | 14_47L1 | 2023-10-16 22:00 | 2023-10-17 | 1 | 0 | 1 | 2023-10-18 | 2023-11-13 | 18 | 0 | 18 | [20 empty] | 2023-11-17 |  | 2025-01-09 |  | EXP | [8 empty] | 2024-01-30 | Connected |  | No
National Grid | LYNN | 563069 | 1905 | 2.9 | Solar | 12_29W1 | 2023-11-08 14:22 | 2023-11-09 | 2 | 0 | 2 | 2023-11-14 | 2024-03-06 | 77 | 61 | 16 | [20 empty] | 2024-03-13 |  | 2025-04-01 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | LYNN | 566137 | 1904 | 6 | Solar | 12_29W1 | 2023-11-06 14:14 | 2023-11-07 | 11 | 9 | 2 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | OXFORD | 568197 | 1540 | 24.8 | Battery Add-On | 01_406L3 | 2023-11-02 07:55 | 2023-11-03 | 27 | 24 | 3 | 2023-12-14 |  | 83 | 60 | 23 | [21 empty] | 2023-11-08 09:49 |  |  | EXP | [9 empty] | Screening |  | No
National Grid | OXFORD | 568942 | 1540 | 14.79 | Solar | 01_406L3 | 2023-11-08 09:49 | 2023-11-09 | 2 | 1 | 1 | 2023-11-14 | 2023-12-13 | 21 | 0 | 21 | [20 empty] | 2023-12-18 |  | 2024-12-20 | Yes | EXP |  | 2024-02-16 | 2024-02-16 | 1 | 0 | 1 |  |  | 2024-04-03 | Connected |  | No
National Grid | SWAMPSCOTT | 560742 | 1902 | 10 | Solar | 12_29W4 | 2023-10-11 14:05 | 2023-10-12 | 3 | 2 | 1 | 2023-10-16 | 2023-11-05 | 16 | 0 | 16 | [20 empty] | 2023-11-08 |  | 2025-01-11 |  | EXP | [8 empty] | 2024-03-01 | Connected |  | No
National Grid | SALISBURY | 566104 | 1952 | 70 | Solar | 14_7L4 | 2023-11-06 15:52 | 2023-11-07 | 10 | 0 | 10 | 2023-11-22 | 2024-01-02 | 27 | 3 | 24 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | ANDOVER | 569243 | 1810 | 25.2 | Solar | 14_50L1 | 2023-11-06 16:34 | 2023-11-07 | 2 | 0 | 2 | 2023-11-09 | 2024-02-06 | 59 | 35 | 24 | [20 empty] | 2024-02-07 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | No
National Grid | ANDOVER | 566383 | 1810 | 25 | Solar | 14_50L1 | 2023-10-26 09:24 | 2023-10-27 | 1 | 0 | 1 | 2023-10-30 | 2024-02-15 | 74 | 52 | 22 | [20 empty] | 2024-02-20 | 2023-11-01 10:53 |  |  | EXP | [9 empty] | Pending Withdraw |  | No
National Grid | ANDOVER | 566189 | 1810 | 5 | Solar | 14_8L1 | 2023-11-01 10:53 | 2023-11-02 | 3 | 0 | 3 | 2023-11-07 | 2023-12-28 | 35 | 16 | 19 | [20 empty] | 2024-01-04 |  | 2025-03-13 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | ANDOVER | 569398 | 1810 | 7.6 | Solar | 14_54L3 | 2023-11-07 10:13 | 2023-11-08 | 65 | 63 | 2 | 2024-02-14 | 2024-03-08 | 18 | 11 | 7 | [20 empty] | 2024-03-13 |  | 2025-04-03 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | SALEM | 557503 | 1970 | 7.6 | Solar | 12_2W1 | 2023-10-18 12:16 | 2023-10-19 | 3 | 0 | 3 | 2023-10-24 | 2023-12-06 | 31 | 20 | 11 | [20 empty] | 2023-12-11 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | DOUGLAS | 562803 | 1516 | 23 | Solar | 01_412L1 | 2023-10-13 10:27 | 2023-10-16 | 12 | 11 | 1 | 2023-10-31 | 2024-01-09 | 47 | 26 | 21 | [20 empty] | 2024-01-10 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | DUDLEY | 527634 | 1571 | 6 | Solar | 01_412L4 | 2023-10-24 14:05 | 2023-10-25 | 11 | 10 | 1 | 2023-11-08 | 2024-02-16 | 65 | 42 | 23 | [20 empty] | 2024-02-21 | 2023-11-07 12:46 | 2025-02-21 |  | EXP | [8 empty] | 2024-03-05 | Connected |  | No
National Grid | MEDFORD | 563912 | 2155 | 7.6 | Solar | 12_37W5 | 2023-11-07 12:46 | 2023-11-08 | 2 | 0 | 2 | 2023-11-13 | 2023-12-18 | 24 | 4 | 20 | [20 empty] | 2023-12-28 |  | 2025-01-08 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | EVERETT | 566763 | 2149 | 7.6 | Solar | 12_37W6 | 2023-11-02 14:01 | 2023-11-03 | 4 | 2 | 2 | 2023-11-09 | 2023-12-08 | 20 | 0 | 20 | [20 empty] | 2023-12-12 | 2023-11-01 11:20 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WEBSTER | 565284 | 1570 | 6 | Solar | 01_412L5 | 2023-11-01 11:20 | 2023-11-02 | 3 | 2 | 1 | 2023-11-07 | 2023-12-15 | 27 | 5 | 22 | [20 empty] | 2023-12-19 |  | 2025-01-01 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | BOLTON | 568830 | 1740 | 15.435 | Solar | 01_216W6 | 2023-11-06 16:39 | 2023-11-07 | 2 | 0 | 2 | [10 empty] | 2023-11-09 | 2024-01-03 | 36 | 14 | 22 | [11 empty] | 2023-11-01 11:31 |  |  | STD | [9 empty] | Study |  | Yes
National Grid | ROCKPORT | 562901 | 1966 | 9.86 | Solar | 12_40J2 | 2023-11-01 11:31 | 2023-11-02 | 5 | 2 | 3 | 2023-11-08 | 2023-12-13 | 25 | 4 | 21 | [20 empty] | 2023-12-20 | 2023-10-27 13:41 | 2024-12-28 | Yes | EXP |  | 2024-03-21 | 2024-04-03 | 14 | 0 | 14 |  |  |  | Completion Documents |  | Yes
National Grid | ROCKPORT | 556928 | 1966 | 6 | Solar | 12_40J4 | 2023-10-27 13:41 | 2023-10-30 | 1 | 0 | 1 | 2023-10-31 | 2023-11-16 | 12 | 0 | 12 | [20 empty] | 2023-11-21 |  | 2024-12-07 | Yes | EXP |  | 2024-03-30 |  | 17 | 0 | 17 |  |  |  | Construction |  | Yes
National Grid | ROCKPORT | 559826 | 1966 | 16.96 | Solar | 12_40L1 | 2023-10-18 13:10 | 2023-10-19 | 3 | 1 | 2 | 2023-10-23 | 2023-12-01 | 28 | 9 | 19 | [20 empty] | 2023-12-06 |  | 2024-12-11 |  | EXP | [8 empty] | 2024-01-16 | Connected |  | No
National Grid | SALEM | 559364 | 1970 | 5 | Solar | 12_49W2 | 2023-10-17 15:42 | 2023-10-18 | 2 | 0 | 2 | 2023-10-20 | 2024-01-09 | 54 | 38 | 16 | [20 empty] | 2024-01-10 |  | 2025-01-21 |  | EXP | [8 empty] | 2024-02-14 | Connected |  | No
National Grid | BLACKSTONE | 563891 | 1504 | 3.8 | Solar | 05_108W60 | 2023-10-30 14:48 | 2023-10-31 | 42 | 37 | 5 | 2024-01-02 | 2024-02-05 | 24 | 0 | 24 | [20 empty] | 2024-02-08 |  | 2025-02-19 |  | EXP | [8 empty] | 2024-03-08 | Connected |  | No
National Grid | FALL RIVER | 529991 | 2724 | 3.8 | Solar | 05_115W42 | 2023-10-20 18:03 | 2023-10-23 | 2 | 0 | 2 | 2023-10-25 | 2023-11-07 | 10 | 0 | 10 | [20 empty] | 2023-11-09 |  | 2024-12-09 |  | EXP | [8 empty] | 2024-02-06 | Connected |  | No
National Grid | SOUTH HAMILTON | 484468 | 1982 | 18.376 | Solar | 12_51L3 | 2023-11-01 14:45 | 2023-11-02 | 1 | 0 | 1 | 2023-11-03 | 2024-02-27 | 76 | 25 | 51 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTFORD | 554429 | 1886 | 11 | Battery Add-On | 14_58L3 | 2023-10-20 07:12 | 2023-10-23 | 1 | 0 | 1 | 2023-10-24 | 2024-02-01 | 69 | 48 | 21 | [20 empty] | 2024-02-05 | 2023-11-01 07:39 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SOUTHBRIDGE | 560222 | 1550 | 7.749 | Solar | 01_413L4 | 2023-11-01 07:39 | 2023-11-02 | 5 | 2 | 3 | 2023-11-08 | 2023-12-07 | 20 | 0 | 20 | [20 empty] | 2023-12-12 |  | 2025-02-01 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | FALL RIVER | 565509 | 2721 | 5 | Solar | 05_115W45 | 2023-11-08 17:12 | 2023-11-09 | 13 | 10 | 3 | 2023-11-30 | 2024-01-04 | 24 | 3 | 21 | [20 empty] | 2024-01-08 | 2023-10-20 13:31 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ANDOVER | 564915 | 1810 | 20 | Solar | 14_59L1 | 2023-10-20 13:31 | 2023-10-23 | 1 | 0 | 1 | 2023-10-24 | 2024-03-06 | 90 | 78 | 12 | [20 empty] | 2024-03-11 |  | 2025-03-20 | Yes | EXP | [9 empty] | Construction |  | No
National Grid | ANDOVER | 568051 | 1810 | 26.4 | Solar | 14_59L6 | 2023-11-01 15:30 | 2023-11-02 | 1 | 0 | 1 | 2023-11-03 | 2023-12-20 | 32 | 11 | 21 | [20 empty] | 2023-12-21 |  | 2025-01-02 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | HAMILTON | 562855 | 1982 | 16.065 | Solar | 12_51T2 | 2023-10-17 16:12 | 2023-10-18 | 10 | 7 | 3 | 2023-11-01 | 2023-12-04 | 22 | 0 | 22 | [20 empty] | 2023-12-06 |  | 2024-12-14 |  | EXP | [8 empty] | 2024-01-04 | Connected |  | No
National Grid | ESSEX | 566169 | 1929 | 16.82 | Solar | 12_51T2 | 2023-10-25 14:30 | 2023-10-26 | 6 | 3 | 3 | 2023-11-03 | 2023-11-22 | 13 | 0 | 13 | [20 empty] | 2023-11-29 |  | 2024-12-07 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | SWANSEA | 562469 | 2777 | 5 | Solar | 05_11W81 | 2023-11-06 11:18 | 2023-11-07 | 14 | 12 | 2 | 2023-11-29 | 2024-01-12 | 31 | 7 | 24 | [20 empty] | 2024-01-16 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SWANSEA | 569149 | 2777 | 15 | Solar | 05_11W81 | 2023-11-06 14:02 | 2023-11-07 | 9 | 6 | 3 | 2023-11-20 | 2023-12-26 | 25 | 5 | 20 | [20 empty] | 2024-01-02 | 2023-11-03 15:34 | 2025-01-25 |  | EXP | [8 empty] | 2024-02-26 | Connected |  | No
National Grid | SWANSEA | 564941 | 2777 | 10 | Solar | 05_11W81 | 2023-11-03 15:34 | 2023-11-06 | 26 | 23 | 3 | 2023-12-13 | 2024-02-21 | 48 | 25 | 23 | [20 empty] | 2024-02-23 |  | 2025-03-05 |  | EXP | [9 empty] | Design |  | Yes
National Grid | METHUEN | 558417 | 1844 | 10 | Solar | 14_5J42 | 2023-10-11 15:14 | 2023-10-12 | 1 | 0 | 1 | 2023-10-13 | 2023-11-04 | 17 | 0 | 17 | [20 empty] | 2023-11-09 | 2023-11-08 14:59 | 2024-11-17 |  | EXP | [8 empty] | 2024-03-09 | Connected |  | No
National Grid | LEOMINSTER | 564107 | 1453 | 10 | Solar | 01_225W3 | 2023-11-08 14:59 | 2023-11-09 | 2 | 0 | 2 | 2023-11-14 | 2023-12-14 | 22 | 0 | 22 | [20 empty] | 2023-12-20 |  | 2025-01-02 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | GLOUCESTER | 570135 | 1930 | 15.2 | Solar | 12_52L1 | 2023-11-09 10:24 | 2023-11-13 | 11 | 9 | 2 | 2023-11-28 | 2024-01-02 | 24 | 3 | 21 | [20 empty] | 2024-01-03 |  | 2025-01-18 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | SWANSEA | 565023 | 2777 | 5 | Solar | 05_11W84 | 2023-10-25 13:31 | 2023-10-26 | 4 | 2 | 2 | 2023-10-31 | 2023-12-15 | 32 | 10 | 22 | [20 empty] | 2023-12-21 |  | 2025-01-01 |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BEVERLY | 565683 | 1915 | 3.8 | Solar | 12_72L1 | 2023-10-24 10:11 | 2023-11-09 | 3 | 1 | 2 | 2023-11-15 | 2024-01-12 | 40 | 18 | 22 | [20 empty] | 2024-01-16 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LAWRENCE | 562630 | 1843 | 10 | Solar | 14_61L3 | 2023-10-12 17:57 | 2023-10-13 | 15 | 12 | 3 | 2023-11-03 | 2024-03-12 | 87 | 66 | 21 | [20 empty] | 2024-03-18 |  | 2025-03-21 |  | EXP | [9 empty] | Conditional Approval |  | No
National Grid | PEPPERELL | 541794 | 1463 | 999 | Solar | 01_226L1 | 2023-10-13 09:35 | 2023-10-16 | 45 | 35 | 10 | [10 empty] | 2023-12-19 | 2024-01-26 | 27 | 8 | 19 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | REVERE | 562600 | 2151 | 6 | Solar | 12_7J6 | 2023-10-16 08:28 | 2023-11-02 | 3 | 2 | 1 | 2023-11-07 | 2024-03-13 | 86 | 26 | 60 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SAUGUS | 562325 | 1906 | 3.8 | Solar | 12_7J903 | 2023-10-24 08:42 | 2023-10-25 | 1 | 0 | 1 | 2023-10-26 | 2023-11-16 | 15 | 0 | 15 | [20 empty] | 2023-11-20 | 2023-10-16 09:42 | 2024-11-29 |  | EXP | [8 empty] | 2024-02-06 | Connected |  | No
National Grid | SPENCER | 562432 | 1562 | 9.074 | Solar | 01_552L1 | 2023-10-16 09:42 | 2023-10-17 | 4 | 2 | 2 | 2023-10-20 | 2023-11-08 | 14 | 0 | 14 | [20 empty] | 2023-11-15 |  | 2024-11-19 | Yes | EXP |  | 2023-12-14 | 2024-02-07 | 56 | 3 | 53 |  |  | 2024-02-08 | Connected |  | No
National Grid | SPENCER | 568209 | 1562 | 13.05 | Solar | 01_552L1 | 2023-11-06 06:44 | 2023-11-07 | 4 | 2 | 2 | 2023-11-14 | 2024-01-04 | 35 | 18 | 17 | [20 empty] | 2024-01-08 |  | 2025-01-14 |  | EXP | [8 empty] | 2024-02-23 | Connected |  | No
National Grid | REVERE | 565408 | 2151 | 25 | Solar | 12_7W3 | 2023-11-03 12:57 | 2023-11-06 | 59 | 55 | 4 | 2024-02-01 |  | 52 | 40 | 12 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | WINTHROP | 562542 | 2152 | 10 | Solar | 12_96W1 | 2023-10-17 16:20 | 2023-10-18 | 4 | 1 | 3 | 2023-10-23 | 2024-01-10 | 55 | 31 | 24 | [20 empty] | 2024-01-16 |  | 2025-01-16 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | SPENCER | 562496 | 1562 | 5 | Solar | 01_552L3 | 2023-10-20 23:06 | 2023-10-23 | 14 | 11 | 3 | 2023-11-13 | 2023-12-12 | 21 | 0 | 21 | 2023-12-21 |  | 78 | 1 | 77 | [5 empty] | 2023-12-21 |  | 78 | 1 | 77 | [9 empty] | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | DIGHTON | 565988 | 2715 | 10 | Solar | 05_19W74 | 2023-11-01 10:00 | 2023-11-02 | 3 | 2 | 1 | 2023-11-07 | 2024-01-31 | 57 | 26 | 31 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RUTLAND | 561632 | 1543 | 7.6 | Solar | 01_55W1 | 2023-10-13 10:40 | 2023-10-16 | 1 | 0 | 1 | 2023-10-17 | 2024-01-26 | 68 | 45 | 23 | [20 empty] | 2024-01-29 | 2023-10-25 13:57 | 2025-04-04 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | WORCESTER | 552074 | 1606 | 5.985 | Solar | 01_24W5 | 2023-10-25 13:57 | 2023-10-26 | 30 | 25 | 5 | 2023-12-11 | 2024-01-22 | 28 | 4 | 24 | [20 empty] | 2024-01-23 |  | 2025-02-14 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | TYNGSBOROUGH | 564846 | 1879 | 200 | Solar | 14_211L2 | 2023-10-24 13:17 | 2023-10-25 | 10 | 0 | 10 | [10 empty] | 2023-11-08 | 2023-12-05 | 18 | 0 | 18 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | HUBBARDSTON | 566632 | 1452 | 2000 | Solar | 01_602W2 | 2023-11-01 18:29 | 2023-11-02 | 95 | 55 | 40 | [26 empty] | 2023-11-07 14:27 |  |  | STD | [9 empty] | Withdrawn |  | No
National Grid | WESTMINSTER | 565997 | 1473 | 10 | Solar | 01_602W2 | 2023-11-07 14:27 | 2023-11-08 | 2 | 0 | 2 | 2023-11-13 | 2023-12-27 | 30 | 7 | 23 | [20 empty] | 2024-01-02 |  | 2025-01-10 | Yes | EXP |  | 2024-03-23 |  | 24 | 0 | 24 |  |  |  | Construction |  | Yes
National Grid | HUBBARDSTON | 569809 | 1452 | 20 | Solar | 01_602W2 | 2023-11-08 11:01 | 2023-11-09 | 2 | 1 | 1 | 2023-11-14 | 2024-01-26 | 50 | 28 | 22 | [20 empty] | 2024-02-02 |  |  |  | EXP | [9 empty] | Conditional Approval |  | No
National Grid | BILLERICA | 569114 | 1821 | 17.6 | Solar | 14_70L8 | 2023-11-06 13:07 | 2023-11-07 | 17 | 15 | 2 | 2023-12-01 | 2024-02-20 | 54 | 31 | 23 | [20 empty] | 2024-02-23 |  | 2025-03-05 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | MARLBOROUGH | 562727 | 1752 | 17.6 | Battery Add-On | 05_311W2 | 2023-10-13 07:47 | 2023-10-16 | 1 | 0 | 1 | 2023-10-17 | 2023-11-09 | 18 | 0 | 18 | [20 empty] | 2023-12-06 | 2023-10-31 13:52 | 2025-04-15 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | CHELMSFORD | 566273 | 1824 | 4.095 | Solar | 14_24L2 | 2023-10-31 13:52 | 2023-11-01 | 2 | 0 | 2 | 2023-11-03 | 2023-12-07 | 24 | 3 | 21 | [20 empty] | 2023-12-12 |  | 2024-12-26 | Yes | EXP | [8 empty] | 2024-04-04 | Connected |  | No
National Grid | GARDNER | 564080 | 1440 | 20 | Battery Add-On | 01_607W1 | 2023-10-19 11:15 | 2023-10-20 | 121 | 120 | 1 | [29 empty] | EXP | [9 empty] | Application |  | No
National Grid | METHUEN | 559191 | 1844 | 240 | Solar | 14_74L1 | 2023-11-03 16:16 | 2023-11-06 | 10 | 0 | 10 | [10 empty] | 2023-11-21 | 2023-12-27 | 25 | 3 | 22 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | MARLBOROUGH | 559734 | 1752 | 400 | Solar | 05_311W3 | 2023-10-12 07:18 | 2023-10-13 | 39 | 29 | 10 | [10 empty] | 2023-12-11 | 2024-01-26 | 32 | 12 | 20 | [11 empty] | 2023-10-24 14:26 |  |  | STD | [9 empty] | Pending Withdraw |  | No
National Grid | WORCESTER | 562649 | 1604 | 7.6 | Solar | 01_27W5 | 2023-10-24 14:26 | 2023-10-25 | 1 | 0 | 1 | 2023-10-26 | 2023-11-08 | 10 | 0 | 10 | [20 empty] | 2023-11-15 |  | 2024-11-29 | Yes | EXP |  | 2024-02-23 | 2024-03-26 | 33 | 0 | 33 |  |  | 2024-04-12 | Connected |  | No
National Grid | LOWELL | 566878 | 1851 | 7.6 | Solar | 14_2L2 | 2023-11-03 12:59 | 2023-11-06 | 15 | 8 | 7 | 2023-11-28 | 2024-01-12 | 33 | 12 | 21 | [20 empty] | 2024-01-19 |  | 2025-02-19 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | METHUEN | 569971 | 1844 | 16.53 | Solar | 14_74L5 | 2023-11-08 15:34 | 2023-11-09 | 8 | 5 | 3 | 2023-11-22 | 2024-03-04 | 69 | 45 | 24 | [20 empty] | 2024-03-06 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | LAWRENCE | 552870 | 1841 | 10 | Solar | 14_74L6 | 2023-11-06 15:42 | 2023-11-07 | 6 | 4 | 2 | 2023-11-16 | 2024-02-16 | 48 | 41 | 7 | [20 empty] | 2024-02-23 | 2023-11-01 18:01 |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LAWRENCE | 562808 | 1841 | 6 | Solar | 14_74L6 | 2023-11-01 18:01 | 2023-11-02 | 3 | 2 | 1 | 2023-11-07 | 2023-12-07 | 22 | 4 | 18 | [20 empty] | 2023-12-08 |  | 2024-12-20 | Yes | EXP | [8 empty] | 2024-04-04 | Connected |  | No
National Grid | NEWBURYPORT | 549712 | 1950 | 4998 | Other | 14_36L2 | 2023-10-25 13:26 | 2023-10-26 | 15 | 5 | 10 | [10 empty] | 2023-11-17 | 2024-02-16 | 62 | 43 | 19 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | BROCKTON | 562350 | 2302 | 10 | Solar | 07_911W56 | 2023-10-16 06:41 | 2023-10-17 | 1 | 0 | 1 | 2023-10-18 | 2023-11-07 | 15 | 0 | 15 | [20 empty] | 2023-11-09 |  | 2024-11-16 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | BROCKTON | 563942 | 2302 | 6 | Solar | 07_911W56 | 2023-10-30 14:38 | 2023-10-31 | 2 | 1 | 1 | 2023-11-02 | 2023-11-29 | 18 | 0 | 18 | [20 empty] | 2023-12-04 |  | 2024-12-07 |  | EXP | [8 empty] | 2024-03-15 | Connected |  | No
National Grid | BROCKTON | 568574 | 2302 | 6 | Solar | 07_911W56 | 2023-11-08 13:33 | 2023-11-09 | 2 | 0 | 2 | 2023-11-14 | 2023-12-07 | 17 | 0 | 17 | [20 empty] | 2023-12-12 | 2023-10-18 12:39 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 559201 | 2302 | 7.6 | Solar | 07_911W56 | 2023-10-18 12:39 | 2023-10-19 | 1 | 0 | 1 | 2023-10-20 | 2023-11-07 | 13 | 0 | 13 | [20 empty] | 2023-11-13 |  | 2024-12-06 | Yes | EXP |  | 2024-01-25 | 2024-02-16 | 23 | 0 | 23 |  |  | 2024-02-21 | Connected |  | No
National Grid | NORTH ADAMS | 562359 | 1247 | 27.3 | Solar | 09_1015W2 | 2023-10-19 10:06 | 2023-10-20 | 1 | 0 | 1 | 2023-10-23 | 2023-11-15 | 17 | 0 | 17 | [20 empty] | 2023-11-20 |  | 2024-11-23 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | BARRE | 565348 | 1005 | 1999.2 | Solar | 09_604W1 | 2023-10-30 23:25 | 2023-10-31 | 61 | 53 | 8 | [10 empty] | 2024-01-31 | 2024-02-20 | 14 | 0 | 14 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | BROCKTON | 562462 | 2302 | 11.4 | Solar | 07_911W57 | 2023-10-20 18:23 | 2023-10-23 | 51 | 50 | 1 | 2024-01-05 | 2024-04-09 | 67 | 46 | 21 | [20 empty] | 2024-04-15 |  |  |  | EXP | [9 empty] | Conditional Approval |  | No
National Grid | BROCKTON | 563390 | 2302 | 3.8 | Solar | 07_911W77 | 2023-10-26 16:52 | 2023-10-27 | 2 | 0 | 2 | 2023-10-31 | 2023-11-22 | 17 | 2 | 15 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | WESTBOROUGH | 567577 | 1581 | 240 | Solar | 05_314W4 | 2023-10-31 12:42 | 2023-11-01 | 97 | 27 | 70 | [26 empty] | 2023-11-07 13:32 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BRIDGEWATER | 564081 | 2324 | 10 | Solar | 07_912W55 | 2023-11-07 13:32 | 2023-11-08 | 2 | 0 | 2 | 2023-11-13 | 2024-01-12 | 42 | 17 | 25 | [20 empty] | 2024-01-19 |  | 2025-02-12 | Yes | EXP | [9 empty] | Design |  | No
National Grid | BOLTON | 566220 | 1740 | 7.6 | Solar | 05_318W3 | 2023-10-25 15:25 | 2023-10-26 | 1 | 0 | 1 | 2023-10-27 | 2023-11-06 | 7 | 0 | 7 | [20 empty] | 2023-11-06 |  | 2024-11-12 |  | EXP | [8 empty] | 2023-11-21 | Connected |  | No
National Grid | ATHOL | 557213 | 1331 | 10 | Solar | 09_702W1 | 2023-10-25 14:57 | 2023-10-26 | 14 | 13 | 1 | 2023-11-15 | 2023-12-15 | 22 | 0 | 22 | [20 empty] | 2023-12-28 | 2023-10-12 12:30 | 2025-01-03 |  | EXP | [8 empty] | 2024-02-13 | Connected |  | No
National Grid | GREAT BARRINGTON | 558449 | 1230 | 6 | Solar | 09_1109W2 | 2023-10-12 12:30 | 2023-10-13 | 1 | 0 | 1 | 2023-10-16 | 2023-11-30 | 32 | 13 | 19 | [20 empty] | 2023-12-05 |  | 2024-12-09 | Yes | EXP |  | 2024-01-19 | 2024-01-18 | 0 | 0 | 0 |  |  |  | Completion Documents |  | Yes
National Grid | DOUGLAS | 568589 | 1516 | 46 | Solar | 05_320W2 | 2023-11-03 09:53 | 2023-11-06 | 7 | 5 | 2 | 2023-11-15 |  | 103 | 86 | 17 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | ATTLEBORO | 564312 | 2703 | 15.2 | Solar | 05_9L4 | 2023-10-18 17:09 | 2023-10-19 | 2 | 0 | 2 | 2023-10-23 | 2024-02-16 | 80 | 64 | 16 | [20 empty] | 2024-02-21 |  | 2025-03-18 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | HAMPDEN | 564573 | 1036 | 20 | Solar | 09_139L1 | 2023-10-19 13:37 | 2023-10-20 | 6 | 5 | 1 | 2023-10-27 | 2024-01-19 | 56 | 43 | 13 | [20 empty] | 2024-01-22 | 2023-10-27 14:32 | 2025-02-15 |  | EXP | [8 empty] | 2024-03-14 | Connected |  | No
National Grid | BROCKTON | 559477 | 2302 | 7.56 | Solar | 07_91W41 | 2023-10-27 14:32 | 2023-10-30 | 1 | 0 | 1 | 2023-10-31 | 2023-12-11 | 29 | 14 | 15 | [20 empty] | 2023-12-15 |  | 2025-01-28 | Yes | EXP |  | 2024-02-27 |  | 49 | 0 | 49 |  |  |  | Construction |  | Yes
National Grid | MILLVILLE | 561628 | 1529 | 19.845 | Solar | 05_321W2 | 2023-10-13 13:18 | 2023-10-16 | 1 | 0 | 1 | 2023-10-17 | 2024-01-26 | 69 | 49 | 20 | [20 empty] | 2024-02-01 |  | 2025-02-15 |  | EXP | [9 empty] | Meter Installation |  | Yes
National Grid | ORANGE | 561338 | 1364 | 2.9 | Solar | 09_705W2 | 2023-10-13 11:14 | 2023-10-16 | 2 | 0 | 2 | 2023-10-18 | 2023-11-14 | 19 | 3 | 16 | [20 empty] | 2023-11-17 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | ORANGE | 562198 | 1364 | 100 | Solar | 09_705W2 | 2023-10-19 16:41 | 2023-10-20 | 19 | 9 | 10 | [10 empty] | 2023-11-20 | 2023-12-20 | 22 | 2 | 20 | [11 empty] | 2023-11-07 03:33 |  |  | STD | [9 empty] | Study |  | Yes
National Grid | ORANGE | 569310 | 1364 | 22.995 | Solar | 09_705W2 | 2023-11-07 03:33 | 2023-11-08 | 8 | 5 | 3 | 2023-11-21 | 2024-01-08 | 33 | 11 | 22 | [20 empty] | 2024-01-09 |  | 2025-01-10 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | BROCKTON | 562243 | 2301 | 6 | Solar | 07_91W43 | 2023-10-25 10:24 | 2023-10-26 | 81 | 25 | 56 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EAST LONGMEADOW | 567007 | 1028 | 10 | Solar | 09_139L5 | 2023-11-08 10:42 | 2023-11-09 | 5 | 5 | 0 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WHITMAN | 566719 | 2382 | 7.6 | Solar | 07_91W47 | 2023-11-09 11:06 | 2023-11-13 | 4 | 1 | 3 | 2023-11-17 | 2023-12-22 | 24 | 4 | 20 | [20 empty] | 2023-12-26 | 2023-10-24 07:58 | 2025-01-01 |  | EXP | [8 empty] | 2024-02-07 | Connected |  | No
National Grid | BROCKTON | 562420 | 2301 | 3.8 | Solar | 07_91W48 | 2023-10-24 07:58 | 2023-10-25 | 2 | 1 | 1 | 2023-10-27 | 2023-11-13 | 11 | 0 | 11 | [20 empty] | 2023-11-14 |  | 2024-12-07 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | BROCKTON | 475340 | 2301 | 250 | Solar | 07_91W48 | 2023-10-31 08:09 | 2023-11-01 | 92 | 27 | 65 | [29 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | UXBRIDGE | 561181 | 1569 | 3.8 | Solar | 05_321W6 | 2023-10-13 11:01 | 2023-10-16 | 2 | 0 | 2 | 2023-10-18 | 2023-11-16 | 21 | 3 | 18 | 2023-12-05 | 2024-01-17 | 22 | 3 | 19 | [5 empty] | 2023-12-05 | 2024-01-17 | 22 | 3 | 19 | [5 empty] | 2024-01-10 |  | 2025-02-14 |  | EXP |  | 2024-03-13 | 2024-03-28 | 16 | 0 | 16 |  |  |  | Completion Documents |  | Yes
National Grid | WEYMOUTH | 549988 | 2188 | 4999 | Other | 07_12W2 | 2023-11-08 15:03 | 2023-11-09 | 29 | 22 | 7 | [10 empty] | 2023-12-22 | 2024-04-01 | 68 | 49 | 19 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | BROCKTON | 559160 | 2301 | 7.875 | Solar | 07_91W49 | 2023-10-12 09:48 | 2023-10-13 | 3 | 1 | 2 | 2023-10-17 | 2023-11-06 | 15 | 0 | 15 | [20 empty] | 2023-11-09 |  | 2024-12-05 |  | EXP | [8 empty] | 2024-01-23 | Connected |  | No
National Grid | QUINCY | 559804 | 2169 | 3.8 | Solar | 07_1W2 | 2023-10-26 10:08 | 2023-10-27 | 15 | 13 | 2 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | QUINCY | 564935 | 2169 | 6 | Solar | 07_1W3 | 2023-10-24 09:29 | 2023-10-25 | 2 | 1 | 1 | 2023-10-27 | 2023-12-14 | 34 | 21 | 13 | 2024-01-18 | 2024-02-21 | 4 | 0 | 4 | [5 empty] | 2024-01-18 | 2024-02-21 | 4 | 0 | 4 | [5 empty] | 2024-01-24 | 2023-10-23 14:15 | 2025-02-07 |  | EXP |  | 2024-02-15 | 2024-03-11 | 26 | 0 | 26 |  |  | 2024-04-01 | Connected |  | Yes
National Grid | PALMER | 555915 | 1069 | 10 | Solar | 09_503L1 | 2023-10-23 14:15 | 2023-10-24 | 1 | 0 | 1 | 2023-10-25 | 2023-11-13 | 13 | 0 | 13 | [20 empty] | 2023-11-17 | 2023-10-25 10:35 | 2025-01-08 | Yes | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | MENDON | 527237 | 1756 | 14.79 | Solar | 05_332W1 | 2023-10-25 10:35 | 2023-10-26 | 3 | 2 | 1 | 2023-10-31 | 2024-02-07 | 67 | 51 | 16 | [20 empty] | 2023-05-28 |  | 2025-02-19 | Yes | EXP |  | 2024-03-08 | 2024-03-07 | 0 | 0 | 0 |  |  | 2024-04-08 | Connected |  | Yes
National Grid | ROCKLAND | 563028 | 2370 | 7.25 | Solar | 07_93W40 | 2023-10-17 12:25 | 2023-10-18 | 4 | 1 | 3 | 2023-10-23 | 2023-11-07 | 12 | 0 | 12 | [20 empty] | 2023-11-08 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MILFORD | 563998 | 1757 | 6.912 | Solar | 05_335W2 | 2023-11-06 10:45 | 2023-11-07 | 4 | 2 | 2 | 2023-11-14 |  | 104 | 66 | 38 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | UPTON | 565699 | 1568 | 6 | Solar | 05_335W3 | 2023-11-07 12:56 | 2023-11-08 | 6 | 4 | 2 | 2023-11-17 | 2023-12-27 | 27 | 6 | 21 | 2024-01-31 | 2024-03-04 | 8 | 0 | 8 | [5 empty] | 2024-01-31 | 2024-03-04 | 8 | 0 | 8 | [5 empty] | 2024-02-16 |  | 2025-02-21 |  | EXP | [9 empty] | Construction |  | Yes
National Grid | RANDOLPH | 566616 | 2368 | 16.5 | Solar | 07_5W3 | 2023-10-26 16:48 | 2023-10-27 | 1 | 0 | 1 | 2023-10-30 | 2023-12-21 | 38 | 15 | 23 | [21 empty] | 2023-11-01 12:26 |  |  | EXP | [9 empty] | Study |  | No
National Grid | RANDOLPH | 561990 | 2368 | 10 | Solar | 07_5W3 | 2023-11-01 12:26 | 2023-11-02 | 1 | 0 | 1 | 2023-11-03 | 2023-12-18 | 30 | 6 | 24 | [20 empty] | 2023-12-21 | 2023-10-23 11:50 | 2025-01-09 | Yes | EXP |  | 2024-03-14 | 2024-03-16 | 3 | 0 | 3 |  |  |  | Completion Documents |  | Yes
National Grid | STOUGHTON | 560639 | 2072 | 6 | Solar | 07_94W43 | 2023-10-23 11:50 | 2023-10-24 | 2 | 0 | 2 | 2023-10-26 | 2023-12-20 | 38 | 14 | 24 | [20 empty] | 2023-12-21 |  | 2025-01-01 | Yes | EXP |  | 2024-03-05 | 2024-03-26 | 22 | 0 | 22 |  |  |  | Meter Installation |  | No
National Grid | MILFORD | 544198 | 1757 | 10 | Solar | 05_335W9 | 2023-10-17 11:21 | 2023-10-18 | 3 | 2 | 1 | 2023-10-23 | 2023-11-21 | 22 | 5 | 17 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EAST LONGMEADOW | 565680 | 1028 | 35 | Solar | 09_508L4 | 2023-10-24 10:25 | 2023-10-25 | 2 | 0 | 2 | 2023-10-27 | 2023-12-15 | 34 | 11 | 23 | [20 empty] | 2023-12-20 |  | 2025-04-08 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | HANOVER | 542074 | 2339 | 15.2 | Solar | 07_95W5 | 2023-10-18 10:57 | 2023-10-19 | 3 | 2 | 1 | 2023-10-23 | 2023-11-08 | 13 | 0 | 13 | [20 empty] | 2023-11-15 |  | 2025-01-18 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | BROCKTON | 559691 | 2302 | 8.19 | Solar | 07_712J1 | 2023-10-24 08:37 | 2023-10-25 | 3 | 1 | 2 | 2023-10-27 | 2023-11-13 | 11 | 0 | 11 | [20 empty] | 2023-11-15 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MALDEN | 546706 | 2148 | 25 | Solar | 12_16J4 | 2023-11-07 08:10 | 2023-11-08 | 2 | 0 | 2 | 2023-11-10 | 2023-12-05 | 16 | 0 | 16 | [20 empty] | 2023-12-06 |  | 2024-12-16 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | MALDEN | 546731 | 2148 | 25 | Solar | 12_16J4 | 2023-10-27 16:09 | 2023-10-30 | 8 | 5 | 3 | 2023-11-08 | 2023-12-05 | 18 | 0 | 18 | [20 empty] | 2023-12-06 |  | 2024-12-16 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | MALDEN | 546570 | 2148 | 25 | Solar | 12_16J4 | 2023-10-27 16:22 | 2023-10-30 | 1 | 0 | 1 | 2023-10-31 | 2023-11-30 | 21 | 2 | 19 | [20 empty] | 2023-12-05 |  | 2024-12-16 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | FRANKLIN | 568963 | 2038 | 17.6 | Battery Add-On | 05_341W2 | 2023-11-06 08:23 | 2023-11-07 | 21 | 19 | 2 | 2023-12-08 | 2024-02-20 | 28 | 28 | 0 | [24 empty] | EXP | [9 empty] | Conditional Approval |  | No
National Grid | SAUGUS | 555760 | 1906 | 2.9 | Solar | 12_16W1 | 2023-10-11 12:24 | 2023-10-12 | 8 | 4 | 4 | 2023-10-24 | 2023-11-29 | 25 | 2 | 23 | [20 empty] | 2023-12-05 |  | 2025-02-09 |  | EXP | [8 empty] | 2024-02-27 | Connected |  | No
National Grid | NORWELL | 562218 | 2061 | 17.45 | Solar | 07_96W43 | 2023-10-12 10:08 | 2023-10-13 | 17 | 15 | 2 | 2023-11-07 | 2024-01-08 | 41 | 24 | 17 | [20 empty] | 2024-01-12 |  | 2025-01-24 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | BROCKTON | 564779 | 2301 | 6 | Solar | 07_797W19 | 2023-11-01 09:44 | 2023-11-02 | 3 | 0 | 3 | 2023-11-07 | 2023-12-06 | 20 | 0 | 20 | [20 empty] | 2023-12-11 |  | 2024-12-28 |  | EXP | [8 empty] | 2024-03-20 | Connected |  | No
National Grid | BROCKTON | 561847 | 2301 | 7.6 | Solar | 07_797W19 | 2023-10-24 11:33 | 2023-10-25 | 3 | 1 | 2 | 2023-10-30 | 2023-12-06 | 27 | 14 | 13 | [20 empty] | 2023-12-07 |  | 2024-12-09 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | WEST BRIDGEWATER | 521068 | 2379 | 700 | Solar | 07_797W20 | 2023-11-02 10:24 | 2023-11-03 | 52 | 42 | 10 | [10 empty] | 2024-01-22 | 2024-02-15 | 19 | 0 | 19 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | WRENTHAM | 566683 | 2093 | 46 | Solar | 05_3422W4 | 2023-10-27 07:51 | 2023-10-30 | 10 | 8 | 2 | 2023-11-14 | 2024-04-01 | 95 | 79 | 16 | [20 empty] | 2024-04-05 | 2023-10-25 11:59 | 2025-04-15 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | RANDOLPH | 559566 | 2368 | 6 | Solar | 07_97W2 | 2023-10-25 11:59 | 2023-10-26 | 1 | 0 | 1 | 2023-10-27 | 2023-11-15 | 13 | 0 | 13 | [20 empty] | 2023-11-17 |  | 2025-01-03 | Yes | EXP |  | 2024-03-14 |  | 33 | 0 | 33 |  |  |  | Construction |  | Yes
National Grid | EAST BRIDGEWATER | 517489 | 2333 | 5.22 | Solar | 07_797W29 | 2023-11-01 13:55 | 2023-11-02 | 20 | 19 | 1 | 2023-12-01 | 2024-03-19 | 74 | 51 | 23 | [20 empty] | 2024-03-25 |  | 2025-04-05 |  | EXP | [8 empty] | 2024-04-09 | Connected |  | Yes
National Grid | MEDFORD | 561621 | 2155 | 16.05 | Solar | 12_17J5 | 2023-10-12 10:11 | 2023-10-13 | 6 | 4 | 2 | 2023-10-20 | 2023-11-13 | 16 | 0 | 16 | [20 empty] | 2023-11-16 | 2023-10-11 14:39 | 2024-11-19 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | HOLBROOK | 551665 | 2343 | 7.6 | Solar | 07_97W3 | 2023-10-11 14:39 | 2023-10-12 | 3 | 0 | 3 | 2023-10-17 | 2023-12-27 | 49 | 28 | 21 | [20 empty] | 2024-01-04 |  | 2025-01-29 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | LYNN | 559420 | 1905 | 3.8 | Solar | 12_19W1 | 2023-10-13 10:48 | 2023-10-16 | 1 | 0 | 1 | 2023-10-17 | 2023-11-07 | 16 | 0 | 16 | [20 empty] | 2023-11-13 | 2023-10-18 15:09 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BELLINGHAM | 558155 | 2019 | 7.6 | Solar | 05_344W4 | 2023-10-18 15:09 | 2023-10-19 | 4 | 1 | 3 | 2023-10-24 | 2023-11-13 | 14 | 0 | 14 | [20 empty] | 2023-11-17 | 2023-11-01 11:05 | 2024-12-08 | Yes | EXP |  | 2024-02-06 |  | 70 | 0 | 70 |  |  |  | Construction |  | Yes
National Grid | BELLINGHAM | 565970 | 2019 | 10 | Solar | 05_344W4 | 2023-11-01 11:05 | 2023-11-02 | 5 | 2 | 3 | 2023-11-08 | 2023-12-07 | 20 | 0 | 20 | [20 empty] | 2023-12-12 | 2023-10-12 10:30 | 2025-01-10 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | WILBRAHAM | 548426 | 1095 | 11.6 | Solar | 09_523L1 | 2023-10-12 10:30 | 2023-10-13 | 2 | 0 | 2 | 2023-10-17 | 2023-11-06 | 15 | 0 | 15 | [20 empty] | 2023-11-09 | 2023-10-16 14:24 | 2024-11-29 | Yes | EXP | [8 empty] | 2024-02-08 | Connected |  | Yes
National Grid | LYNN | 561827 | 1902 | 5 | Solar | 12_1J901 | 2023-10-16 14:24 | 2023-10-17 | 7 | 6 | 1 | 2023-10-26 | 2023-11-08 | 10 | 0 | 10 | [20 empty] | 2023-11-09 |  | 2024-11-15 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | LYNN | 552910 | 1902 | 14.04 | Solar | 12_22W2 | 2023-10-25 12:39 | 2023-10-26 | 4 | 1 | 3 | 2023-11-01 | 2024-01-23 | 56 | 32 | 24 | [20 empty] | 2024-01-24 | 2023-11-07 13:25 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 563286 | 2301 | 7.6 | Solar | 07_911W13 | 2023-11-07 13:25 | 2023-11-08 | 2 | 0 | 2 | 2023-11-13 | 2023-12-27 | 31 | 8 | 23 | [20 empty] | 2024-01-04 |  | 2025-01-29 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | GRANBY | 563791 | 1033 | 6 | Solar | 09_527L1 | 2023-10-24 07:39 | 2023-10-25 | 2 | 1 | 1 | 2023-10-27 | 2023-12-05 | 26 | 2 | 24 | [20 empty] | 2023-12-06 |  | 2025-01-02 |  | EXP | [8 empty] | 2024-01-16 | Connected |  | No
National Grid | SAUGUS | 527299 | 1906 | 16 | Solar | 12_23W2 | 2023-11-01 11:41 | 2023-11-02 | 1 | 0 | 1 | 2023-11-03 | 2023-12-04 | 20 | 1 | 19 | [20 empty] | 2023-12-06 |  | 2024-12-10 |  | EXP | [8 empty] | 2023-12-13 | Connected |  | No
National Grid | WEYMOUTH | 568632 | 2190 | 7.6 | Solar | 07_99W32 | 2023-11-03 11:02 | 2023-11-06 | 59 | 55 | 4 | 2024-02-02 | 2024-03-04 | 21 | 10 | 11 | [20 empty] | 2024-03-07 |  | 2025-03-12 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | NANTUCKET | 568300 | 2554 | 15.95 | Solar | 04_101L3 | 2023-11-02 12:21 | 2023-11-03 | 5 | 3 | 2 | 2023-11-13 | 2024-01-02 | 34 | 10 | 24 | [20 empty] | 2024-01-05 | 2023-11-05 09:52 | 2025-01-30 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | WEYMOUTH | 540130 | 2189 | 7.6 | Solar | 07_9W2 | 2023-11-05 09:52 | 2023-11-06 | 1 | 0 | 1 | 2023-11-07 | 2023-12-18 | 29 | 4 | 25 | [20 empty] | 2023-12-19 |  | 2025-03-11 | Yes | EXP |  | 2024-03-28 | 2024-04-03 | 7 | 0 | 7 |  |  |  | Meter Installation |  | Yes
National Grid | WILLIAMSTOWN | 562368 | 1267 | 100 | Solar | 09_1003W1 | 2023-10-13 10:52 | 2023-10-16 | 10 | 0 | 10 | [10 empty] | 2023-10-30 | 2023-12-04 | 23 | 0 | 23 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | WORCESTER | 560507 | 1605 | 3.8 | Solar | 01_11J354 | 2023-10-18 16:57 | 2023-10-19 | 3 | 2 | 1 | 2023-10-23 | 2024-02-06 | 72 | 25 | 47 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 564727 | 1605 | 8.12 | Solar | 01_11J354 | 2023-10-25 03:27 | 2023-10-26 | 17 | 15 | 2 | 2023-11-21 |  | 100 | 29 | 71 | [24 empty] | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | AYER | 562170 | 1432 | 24.8 | Battery Add-On | 01_201W1 | 2023-10-11 12:01 | 2023-10-12 | 1 | 0 | 1 | 2023-10-13 | 2024-02-28 | 93 | 75 | 18 | [20 empty] | 2024-03-05 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | No
National Grid | HARVARD | 567774 | 1451 | 23 | Solar | 01_201W2 | 2023-11-01 07:12 | 2023-11-02 | 112 | 109 | 3 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | HARVARD | 564591 | 1451 | 44.6 | Solar | 01_201W2 | 2023-10-24 12:46 | 2023-10-25 | 1 | 0 | 1 | 2023-10-26 | 2023-11-16 | 15 | 0 | 15 | [20 empty] | 2024-04-02 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | AYER | 565211 | 1432 | 17.6 | Solar | 01_201W4 | 2023-10-23 10:22 | 2023-10-24 | 1 | 0 | 1 | 2023-10-25 | 2024-01-05 | 50 | 29 | 21 | [20 empty] | 2024-01-08 |  | 2025-02-07 |  | EXP | [8 empty] | 2024-04-04 | Connected |  | No
National Grid | LEOMINSTER | 565145 | 1453 | 6.3 | Solar | 01_207W2 | 2023-10-27 02:10 | 2023-10-30 | 1 | 0 | 1 | 2023-10-31 | 2023-12-11 | 29 | 6 | 23 | [20 empty] | 2023-12-12 |  | 2024-12-15 |  | EXP | [8 empty] | 2024-02-06 | Connected |  | No
National Grid | LEOMINSTER | 556880 | 1453 | 9.86 | Solar | 01_207W6 | 2023-10-18 13:48 | 2023-10-19 | 16 | 14 | 2 | 2023-11-09 | 2023-12-27 | 33 | 9 | 24 | [20 empty] | 2024-01-02 |  | 2025-01-08 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | MILLBURY | 562326 | 1527 | 10 | Solar | 01_304W1 | 2023-11-01 15:44 | 2023-11-02 | 1 | 0 | 1 | 2023-11-03 | 2024-01-22 | 52 | 28 | 24 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BOXFORD | 567193 | 1921 | 25 | Battery Add-On | 14_43L7 | 2023-11-02 14:49 | 2023-11-03 | 8 | 5 | 3 | 2023-11-16 | 2024-01-23 | 46 | 24 | 22 | [20 empty] | 2024-01-24 |  | 2025-01-29 |  | EXP | [8 empty] | 2024-03-20 | Connected |  | No
National Grid | BOXFORD | 565734 | 1921 | 14.3 | Solar | 14_43L7 | 2023-11-01 12:01 | 2023-11-02 | 11 | 8 | 3 | 2023-11-20 | 2024-02-02 | 52 | 38 | 14 | [20 empty] | 2024-02-05 |  | 2025-02-05 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | GRAFTON | 570827 | 1536 | 23 | Solar | 01_304W4 | 2023-11-13 12:11 | 2023-11-14 | 2 | 0 | 2 | 2023-11-16 | 2024-03-05 | 74 | 50 | 24 | [20 empty] | 2024-03-08 |  | 2025-04-12 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | DRACUT | 569134 | 1826 | 6 | Solar | 14_75L2 | 2023-11-10 04:42 | 2023-11-13 | 10 | 4 | 6 | 2023-11-28 | 2024-01-25 | 40 | 17 | 23 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | DRACUT | 569622 | 1826 | 6 | Solar | 14_75L2 | 2023-11-20 11:51 | 2023-11-21 | 8 | 4 | 4 | 2023-12-01 | 2024-01-10 | 27 | 3 | 24 | [20 empty] | 2024-01-17 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LOWELL | 556411 | 1852 | 250 | Solar | 14_3L4 | 2023-12-01 16:29 | 2023-12-04 | 16 | 8 | 8 | [10 empty] | 2023-12-27 | 2024-01-23 | 18 | 0 | 18 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | MILLBURY | 566450 | 1527 | 10 | Solar | 01_304W5 | 2023-12-08 11:10 | 2023-12-11 | 2 | 0 | 2 | 2023-12-13 | 2024-01-24 | 28 | 5 | 23 | 2024-01-31 | 2024-04-10 | 51 | 25 | 26 | [5 empty] | 2024-01-31 | 2024-04-10 | 51 | 25 | 26 | [9 empty] | EXP | [9 empty] | Supplemental Review |  | Yes
National Grid | DRACUT | 574265 | 1826 | 6 | Solar | 14_75L3 | 2023-12-04 12:55 | 2023-12-05 | 2 | 0 | 2 | 2023-12-07 | 2024-01-17 | 27 | 3 | 24 | [20 empty] | 2024-01-23 | 2023-11-16 09:19 | 2025-03-05 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | SUTTON | 570231 | 1590 | 10 | Solar | 01_304W6 | 2023-11-16 09:19 | 2023-11-17 | 3 | 1 | 2 | 2023-11-22 | 2024-01-23 | 41 | 17 | 24 | [20 empty] | 2024-01-26 |  | 2025-01-31 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | LOWELL | 576217 | 1850 | 15.2 | Solar | 14_75L5 | 2023-12-06 14:30 | 2023-12-07 | 13 | 10 | 3 | 2023-12-28 | 2024-01-26 | 20 | 0 | 20 | [20 empty] | 2024-01-29 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 558735 | 1844 | 350 | Solar | 14_75L6 | 2023-12-04 15:54 | 2023-12-05 | 21 | 11 | 10 | [10 empty] | 2024-01-05 | 2024-01-31 | 18 | 0 | 18 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | HAVERHILL | 547085 | 1832 | 50 | Solar | 14_43L6 | 2023-11-14 10:14 | 2023-11-15 | 57 | 47 | 10 | [10 empty] | 2024-02-08 | 2024-02-21 | 9 | 0 | 9 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | WESTMINSTER | 569500 | 1473 | 7.6 | Solar | 01_609W1 | 2023-11-27 15:46 | 2023-11-28 | 3 | 2 | 1 | 2023-11-30 | 2024-01-04 | 24 | 3 | 21 | [20 empty] | 2024-01-08 | 2023-11-10 05:03 | 2025-01-21 |  | EXP | [8 empty] | 2024-03-08 | Connected |  | No
National Grid | HAVERHILL | 566963 | 1830 | 7.6 | Solar | 14_76L3 | 2023-11-10 05:03 | 2023-11-13 | 4 | 1 | 3 | 2023-11-17 | 2023-12-22 | 24 | 4 | 20 | [20 empty] | 2023-12-26 |  | 2025-01-01 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | HAVERHILL | 559445 | 1830 | 11.05 | Solar | 14_76L3 | 2023-11-21 12:42 | 2023-11-22 | 1 | 0 | 1 | 2023-11-24 | 2024-03-26 | 84 | 29 | 55 | [21 empty] | 2023-12-07 10:05 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LYNN | 572266 | 1905 | 7.6 | Solar | 12_29W1 | 2023-12-07 10:05 | 2023-12-08 | 3 | 0 | 3 | 2023-12-13 | 2024-01-30 | 33 | 20 | 13 | [20 empty] | 2024-01-31 |  | 2025-01-31 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | LYNN | 572647 | 1905 | 5.8 | Solar | 12_29W1 | 2023-11-27 09:50 | 2023-11-28 | 3 | 2 | 1 | 2023-12-01 | 2024-01-24 | 37 | 16 | 21 | [20 empty] | 2024-01-29 | 2023-11-14 02:09 | 2025-01-31 |  | EXP | [8 empty] | 2024-02-15 | Connected |  | No
National Grid | DRACUT | 569358 | 1826 | 6.09 | Solar | 14_78L1 | 2023-11-14 02:09 | 2023-11-15 | 4 | 1 | 3 | 2023-11-21 | 2023-12-27 | 25 | 3 | 22 | [20 empty] | 2023-12-27 |  | 2025-01-01 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | NEWBURYPORT | 566203 | 1950 | 86.4 | Solar | 14_47L2 | 2023-12-05 14:46 | 2023-12-06 | 51 | 41 | 10 | 2024-02-21 | 2024-03-01 | 8 | 0 | 8 | [20 empty] | 2024-03-14 | 2023-11-13 14:10 |  |  | EXP | [9 empty] | Conditional Approval |  | No
National Grid | DRACUT | 559780 | 1826 | 8.505 | Solar | 14_78L1 | 2023-11-13 14:10 | 2023-11-14 | 10 | 6 | 4 | 2023-11-29 | 2024-01-07 | 27 | 8 | 19 | [20 empty] | 2024-01-11 | 2023-12-01 10:05 | 2025-01-28 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | LYNN | 572629 | 1902 | 10 | Solar | 12_29W4 | 2023-12-01 10:05 | 2023-12-04 | 1 | 0 | 1 | 2023-12-05 | 2024-01-12 | 27 | 3 | 24 | [20 empty] | 2024-01-17 |  | 2025-01-25 | Yes | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | LYNN | 544488 | 1902 | 7.83 | Solar | 12_29W5 | 2023-11-20 16:57 | 2023-11-21 | 46 | 25 | 21 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | ANDOVER | 560942 | 1810 | 10 | Solar | 14_50L1 | 2023-11-20 17:00 | 2023-11-21 | 4 | 2 | 2 | 2023-11-28 | 2024-03-04 | 67 | 44 | 23 | [20 empty] | 2024-03-07 |  | 2025-03-11 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | SALEM | 573931 | 1970 | 10.47 | Solar | 12_29W6 | 2023-11-28 06:59 | 2023-11-29 | 16 | 16 | 0 | 2023-12-21 | 2024-01-26 | 23 | 1 | 22 | [20 empty] | 2024-01-29 |  | 2025-01-29 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | SALEM | 569404 | 1970 | 7.6 | Solar | 12_2W1 | 2023-11-27 09:35 | 2023-11-28 | 1 | 0 | 1 | 2023-11-29 | 2024-01-13 | 32 | 10 | 22 | [20 empty] | 2024-01-19 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | NORTH ANDOVER | 572292 | 1845 | 480 | Solar | 14_55L1 | 2023-12-07 16:26 | 2023-12-08 | 37 | 28 | 9 | [10 empty] | 2024-02-02 | 2024-02-20 | 12 | 0 | 12 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | NORTH ANDOVER | 575743 | 1845 | 240 | Solar | 14_55L1 | 2023-12-08 12:50 | 2023-12-11 | 36 | 25 | 11 | [10 empty] | 2024-02-02 | 2024-02-20 | 12 | 0 | 12 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | METHUEN | 573304 | 1844 | 10.036 | Solar | 14_8L2 | 2023-11-24 11:35 | 2023-11-27 | 3 | 0 | 3 | 2023-11-30 | 2024-01-09 | 27 | 3 | 24 | [24 empty] | EXP | [9 empty] | Supplemental Review |  | Yes
National Grid | LAWRENCE | 537941 | 1841 | 8.7 | Solar | 14_8L2 | 2023-12-04 13:32 | 2023-12-05 | 42 | 30 | 12 | [26 empty] | 2023-11-15 13:46 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MEDFORD | 563473 | 2155 | 10 | Solar | 12_37W1 | 2023-11-15 13:46 | 2023-11-16 | 1 | 0 | 1 | 2023-11-17 | 2023-12-27 | 26 | 4 | 22 | [20 empty] | 2024-01-03 |  | 2025-01-03 | Yes | EXP |  | 2024-03-14 |  | 33 | 0 | 33 |  |  |  | Construction |  | Yes
National Grid | WORCESTER | 567253 | 1603 | 6 | Solar | 01_7J386 | 2023-11-15 10:25 | 2023-11-16 | 2 | 0 | 2 | 2023-11-20 | 2023-12-08 | 14 | 0 | 14 | [20 empty] | 2023-12-11 |  | 2024-12-17 |  | EXP | [8 empty] | 2024-02-16 | Connected |  | No
National Grid | NORTH ANDOVER | 572842 | 1845 | 250 | Solar | 14_56L2 | 2023-12-07 16:30 | 2023-12-08 | 38 | 29 | 9 | [10 empty] | 2024-02-05 | 2024-02-20 | 11 | 0 | 11 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | WORCESTER | 571635 | 1604 | 6 | Solar | 01_8W1 | 2023-12-04 09:34 | 2023-12-05 | 1 | 0 | 1 | 2023-12-06 | 2024-02-08 | 45 | 21 | 24 | [20 empty] | 2024-02-14 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | WORCESTER | 568724 | 1607 | 7.6 | Solar | 01_8W1 | 2023-11-10 04:22 | 2023-11-13 | 3 | 1 | 2 | 2023-11-16 | 2023-12-07 | 15 | 0 | 15 | [20 empty] | 2023-12-08 | 2023-12-01 02:30 | 2025-03-25 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | DUDLEY | 573922 | 1571 | 10 | Solar | 01_412L4 | 2023-12-01 02:30 | 2023-12-04 | 3 | 0 | 3 | 2023-12-07 | 2024-01-18 | 28 | 3 | 25 | [20 empty] | 2024-01-23 |  | 2025-02-25 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | ROCKPORT | 551438 | 1966 | 10 | Solar | 12_40J2 | 2023-11-16 13:23 | 2023-11-17 | 2 | 0 | 2 | 2023-11-21 | 2024-01-02 | 27 | 3 | 24 | [20 empty] | 2024-01-05 |  | 2025-01-09 |  | EXP | [8 empty] | 2024-02-18 | Connected |  | No
National Grid | WORCESTER | 552028 | 1604 | 5.8 | Solar | 01_9J321 | 2023-11-16 13:42 | 2023-11-17 | 3 | 1 | 2 | 2023-11-21 | 2024-01-02 | 29 | 4 | 25 | [20 empty] | 2024-01-05 |  | 2025-01-10 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | MALDEN | 563209 | 2148 | 10 | Solar | 12_5C3 | 2023-12-06 10:27 | 2023-12-07 | 52 | 50 | 2 | 2024-03-08 |  | 27 | 21 | 6 | [21 empty] | 2023-11-10 12:31 |  |  | EXP | [9 empty] | Screening |  | Yes
National Grid | WESTFORD | 570545 | 1886 | 23.6 | Battery Add-On | 14_57L2 | 2023-11-10 12:31 | 2023-11-13 | 14 | 12 | 2 | 2023-12-01 | 2024-01-09 | 26 | 3 | 23 | [20 empty] | 2024-02-21 |  | 2025-02-21 | Yes | EXP | [9 empty] | Construction |  | No
National Grid | WORCESTER | 535525 | 1610 | 990 | Solar | 01_HT26 | 2023-11-21 14:59 | 2023-11-22 | 83 | 75 | 8 | [29 empty] | STD | [9 empty] | Pending Withdraw |  | Yes
National Grid | BOLTON | 574056 | 1740 | 17.6 | Battery Add-On | 01_216W6 | 2023-11-28 10:52 | 2023-11-29 | 23 | 17 | 6 | 2024-01-03 | 2024-02-16 | 33 | 13 | 20 | [20 empty] | 2024-02-21 |  |  |  | EXP | [9 empty] | Conditional Approval |  | No
National Grid | DUDLEY | 564963 | 1571 | 6 | Solar | 01_412L5 | 2023-11-15 14:27 | 2023-11-16 | 3 | 1 | 2 | 2023-11-21 | 2024-01-29 | 46 | 21 | 25 | 2024-04-01 |  | 11 | 0 | 11 | [5 empty] | 2024-04-01 |  | 11 | 0 | 11 | [9 empty] | EXP | [9 empty] | Supplemental Review |  | Yes
National Grid | LEOMINSTER | 571393 | 1453 | 10 | Solar | 01_219W2 | 2023-11-24 13:29 | 2023-11-27 | 12 | 11 | 1 | 2023-12-12 | 2024-01-17 | 24 | 3 | 21 | [20 empty] | 2024-01-22 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FALL RIVER | 569078 | 2723 | 3.8 | Solar | 05_106W82 | 2023-11-30 13:54 | 2023-12-01 | 34 | 32 | 2 | [26 empty] | 2023-11-10 11:29 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BELLINGHAM | 564861 | 2019 | 10 | Solar | 05_108W51 | 2023-11-10 11:29 | 2023-11-13 | 2 | 0 | 2 | 2023-11-15 | 2023-12-15 | 22 | 0 | 22 | [20 empty] | 2023-12-21 |  | 2024-12-28 | Yes | EXP |  | 2024-03-07 |  | 40 | 0 | 40 |  |  |  | Construction |  | Yes
National Grid | ESSEX | 567996 | 1929 | 10 | Solar | 12_51T1 | 2023-11-15 16:38 | 2023-11-16 | 7 | 0 | 7 | 2023-11-28 | 2024-01-03 | 26 | 7 | 19 | [20 empty] | 2024-01-10 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GLOUCESTER | 575964 | 1930 | 8.99 | Solar | 12_51T1 | 2023-12-05 16:22 | 2023-12-06 | 4 | 3 | 1 | 2023-12-12 | 2024-02-12 | 43 | 20 | 23 | [20 empty] | 2024-02-12 |  | 2025-02-15 |  | EXP | [8 empty] | 2024-04-12 | Connected |  | No
National Grid | FALL RIVER | 570860 | 2721 | 6 | Solar | 05_115W45 | 2023-11-20 09:04 | 2023-11-21 | 11 | 7 | 4 | 2023-12-06 | 2024-02-22 | 52 | 42 | 10 | [20 empty] | 2024-02-28 | 2023-11-14 13:54 | 2025-04-01 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | BOLTON | 569141 | 1740 | 7.6 | Solar | 01_225W1 | 2023-11-14 13:54 | 2023-11-24 | 2 | 0 | 2 | 2023-11-28 | 2024-01-08 | 28 | 6 | 22 | [20 empty] | 2024-01-09 |  | 2025-01-11 | Yes | EXP |  | 2024-02-17 | 2024-03-19 | 32 | 0 | 32 |  |  |  | Meter Installation |  | Yes
National Grid | BOLTON | 574015 | 1740 | 30 | Battery Add-On | 01_225W1 | 2023-11-28 09:55 | 2023-11-29 | 6 | 5 | 1 | 2023-12-06 | 2024-03-27 | 78 | 62 | 16 | [20 empty] | 2024-04-02 |  | 2025-04-11 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | GLOUCESTER | 574937 | 1930 | 23 | Solar | 12_52L1 | 2023-11-30 17:43 | 2023-12-01 | 2 | 0 | 2 | 2023-12-05 |  | 91 | 28 | 63 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | SWANSEA | 562342 | 2777 | 4990 | Solar | 05_11W81 | 2023-12-05 15:43 | 2023-12-06 | 31 | 21 | 10 | [10 empty] | 2024-01-22 | 2024-03-28 | 48 | 30 | 18 | [14 empty] | STD | [9 empty] | Screening |  | No
National Grid | LAWRENCE | 568004 | 1843 | 7.6 | Solar | 14_61L2 | 2023-11-30 12:26 | 2023-12-01 | 3 | 0 | 3 | 2023-12-06 | 2024-02-12 | 47 | 23 | 24 | [24 empty] | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | REVERE | 553820 | 2151 | 8.725 | Solar | 12_7J2 | 2023-11-22 09:58 | 2023-11-24 | 25 | 20 | 5 | 2024-01-02 |  | 73 | 25 | 48 | [21 empty] | 2023-11-15 17:53 |  |  | EXP | [9 empty] | Screening |  | Yes
National Grid | LAWRENCE | 566020 | 1843 | 7.6 | Solar | 14_61L3 | 2023-11-15 17:53 | 2023-11-16 | 13 | 8 | 5 | 2023-12-06 | 2024-01-12 | 26 | 3 | 23 | [20 empty] | 2024-01-19 |  | 2025-02-01 | Yes | EXP | [9 empty] | Construction |  | No
National Grid | REVERE | 567022 | 2151 | 6.96 | Solar | 12_7J6 | 2023-11-15 02:50 | 2023-11-16 | 3 | 1 | 2 | 2023-11-21 | 2023-12-22 | 23 | 3 | 20 | [20 empty] | 2023-12-27 |  | 2025-01-02 |  | EXP | [8 empty] | 2024-03-07 | Connected |  | No
National Grid | ANDOVER | 571929 | 1810 | 30 | Solar | 14_62L2 | 2023-11-16 11:26 | 2023-11-17 | 6 | 0 | 6 | 2023-11-28 | 2024-03-11 | 71 | 51 | 20 | [20 empty] | 2024-03-15 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | No
National Grid | ANDOVER | 572719 | 1810 | 22.8 | Solar | 14_62L2 | 2023-11-20 15:02 | 2023-11-21 | 14 | 13 | 1 | 2023-12-12 | 2024-01-29 | 32 | 12 | 20 | 2024-01-31 | 2024-02-21 | 15 | 0 | 15 | [5 empty] | 2024-01-31 | 2024-02-21 | 15 | 0 | 15 | [5 empty] | 2024-02-27 | 2023-11-21 09:39 | 2025-03-05 |  | EXP | [9 empty] | Construction |  | Yes
National Grid | WEST BROOKFIELD | 572056 | 1585 | 5.22 | Solar | 01_525L2 | 2023-11-21 09:39 | 2023-11-22 | 4 | 0 | 4 | 2023-11-29 | 2024-01-12 | 32 | 8 | 24 | [20 empty] | 2024-01-16 |  | 2025-01-18 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | WEST BROOKFIELD | 574688 | 1585 | 34.5 | Battery Add-On | 01_525L2 | 2023-11-30 10:42 | 2023-12-01 | 2 | 0 | 2 | 2023-12-05 |  | 90 | 25 | 65 | [24 empty] | EXP | [9 empty] | Screening |  | No
National Grid | METHUEN | 572865 | 1844 | 3.8 | Solar | 14_63L1 | 2023-11-29 11:52 | 2023-11-30 | 4 | 0 | 4 | 2023-12-06 | 2024-02-09 | 46 | 23 | 23 | [20 empty] | 2024-02-14 | 2023-11-22 18:34 | 2025-02-20 |  | EXP | [8 empty] | 2022-09-01 | Connected |  | No
National Grid | METHUEN | 570739 | 1844 | 9.28 | Solar | 14_63L1 | 2023-11-22 18:34 | 2023-11-24 | 5 | 2 | 3 | 2023-11-30 | 2024-01-11 | 30 | 7 | 23 | [20 empty] | 2024-01-16 | 2023-12-01 08:51 | 2025-01-21 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | MEDFORD | 562890 | 2155 | 6.96 | Solar | 12_9C6 | 2023-12-01 08:51 | 2023-12-04 | 4 | 2 | 2 | 2023-12-07 | 2024-01-11 | 24 | 3 | 21 | [20 empty] | 2024-01-16 |  | 2025-01-18 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | SWAMPSCOTT | 566018 | 1907 | 200 | Solar | 12_9J1 | 2023-11-15 11:06 | 2023-11-16 | 16 | 6 | 10 | 2023-12-11 | 2023-12-08 | 0 | 0 | 0 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | LOWELL | 556428 | 1852 | 480 | Solar | 14_13L1 | 2023-11-22 12:29 | 2023-11-24 | 18 | 10 | 8 | [10 empty] | 2023-12-19 | 2024-02-14 | 40 | 21 | 19 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | LOWELL | 566922 | 1852 | 250 | Solar | 14_13L1 | 2023-12-01 16:32 | 2023-12-04 | 17 | 9 | 8 | [10 empty] | 2023-12-27 | 2024-01-26 | 22 | 2 | 20 | [11 empty] | 2023-11-15 14:38 |  |  | STD | [9 empty] | Study |  | Yes
National Grid | SOMERSET | 565151 | 2726 | 13.262 | Solar | 05_19W72 | 2023-11-15 14:38 | 2023-11-16 | 15 | 13 | 2 | 2023-12-07 | 2024-01-18 | 28 | 4 | 24 | [20 empty] | 2024-01-24 |  | 2025-01-31 | Yes | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | SHIRLEY | 562155 | 1464 | 10 | Solar | 01_227W3 | 2023-11-29 14:11 | 2023-11-30 | 14 | 10 | 4 | 2023-12-20 | 2024-02-21 | 42 | 19 | 23 | [20 empty] | 2024-02-26 |  | 2025-04-01 |  | EXP | [9 empty] | Conditional Approval |  | No
National Grid | METHUEN | 568866 | 1844 | 10 | Solar | 14_63L2 | 2023-12-07 10:17 | 2023-12-08 | 3 | 0 | 3 | 2023-12-13 | 2024-02-02 | 36 | 12 | 24 | 2024-04-01 |  | 11 | 0 | 11 | [5 empty] | 2024-04-01 |  | 11 | 0 | 11 | [9 empty] | EXP | [9 empty] | Supplemental Review |  | Yes
National Grid | SWANSEA | 557478 | 2777 | 2500 | Solar | 05_19W73 | 2023-12-07 15:19 | 2023-12-08 | 28 | 18 | 10 | [10 empty] | 2024-01-19 |  | 60 | 41 | 19 | [14 empty] | STD | [9 empty] | Screening |  | No
National Grid | WORCESTER | 575450 | 1609 | 7.6 | Solar | 01_23W2 | 2023-12-04 11:29 | 2023-12-05 | 25 | 24 | 1 | 2024-01-10 | 2024-02-27 | 34 | 17 | 17 | [20 empty] | 2024-03-04 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | No
National Grid | WORCESTER | 568633 | 1605 | 7.6 | Solar | 01_24W1 | 2023-11-21 08:15 | 2023-11-22 | 6 | 2 | 4 | 2023-12-01 | 2024-04-04 | 86 | 66 | 20 | [24 empty] | EXP | [9 empty] | Supplemental Review |  | Yes
National Grid | RUTLAND | 569867 | 1543 | 10 | Solar | 01_55W1 | 2023-12-05 14:30 | 2023-12-06 | 3 | 2 | 1 | 2023-12-08 | 2024-02-15 | 48 | 24 | 24 | [20 empty] | 2024-02-20 |  | 2025-02-20 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | WORCESTER | 575704 | 1606 | 14.4 | Solar | 01_24W2 | 2023-12-07 12:19 | 2023-12-08 | 1 | 0 | 1 | 2023-12-11 | 2024-01-22 | 28 | 3 | 25 | 2024-02-07 |  | 48 | 0 | 48 | [5 empty] | 2024-02-07 |  | 48 | 0 | 48 | [5 empty] | 2024-03-22 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | TYNGSBORO | 576580 | 1879 | 19 | Battery Add-On | 14_211L2 | 2023-12-07 16:46 | 2023-12-08 | 43 | 39 | 4 | 2024-02-09 | 2024-04-03 | 38 | 28 | 10 | [20 empty] | 2024-04-09 |  |  |  | EXP | [9 empty] | Conditional Approval |  | No
National Grid | AUBURN | 568871 | 1501 | 10 | Solar | 01_26W1 | 2023-11-14 12:00 | 2023-11-15 | 2 | 0 | 2 | 2023-11-17 | 2023-12-27 | 27 | 4 | 23 | [20 empty] | 2024-01-03 | 2023-11-20 16:48 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | AUBURN | 569888 | 1501 | 10 | Solar | 01_26W1 | 2023-11-20 16:48 | 2023-11-21 | 1 | 0 | 1 | 2023-11-22 | 2024-01-16 | 37 | 12 | 25 | [20 empty] | 2024-01-19 | 2023-11-15 12:12 | 2025-01-25 | Yes | EXP |  | 2024-03-16 |  | 31 | 0 | 31 |  |  |  | Construction |  | Yes
National Grid | TEWKSBURY | 570311 | 1876 | 7.6 | Solar | 14_70L8 | 2023-11-15 12:12 | 2023-11-16 | 15 | 13 | 2 | 2023-12-08 | 2024-01-24 | 30 | 8 | 22 | [20 empty] | 2024-01-25 |  | 2025-02-20 | Yes | EXP |  | 2024-03-19 | 2024-03-18 | 0 | 0 | 0 |  |  |  | Completion Documents |  | Yes
National Grid | ANDOVER | 573060 | 1810 | 20 | Solar | 14_71L1 | 2023-12-04 15:30 | 2023-12-05 | 6 | 4 | 2 | 2023-12-13 | 2024-01-29 | 31 | 6 | 25 | [20 empty] | 2024-01-29 |  | 2025-01-29 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | NORTH ANDOVER | 575824 | 1845 | 100 | Solar | 14_71L1 | 2023-12-08 07:13 | 2023-12-11 | 10 | 3 | 7 | [10 empty] | 2023-12-26 | 2024-01-26 | 22 | 0 | 22 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | HUBBARDSTON | 561273 | 1452 | 6.38 | Solar | 01_602W2 | 2023-11-14 11:27 | 2023-11-15 | 39 | 31 | 8 | 2024-01-11 | 2024-02-09 | 21 | 1 | 20 | [20 empty] | 2024-02-16 |  |  |  | EXP | [9 empty] | Conditional Approval |  | No
National Grid | AUBURN | 522113 | 1501 | 15.08 | Solar | 01_26W2 | 2023-11-29 10:12 | 2023-11-30 | 7 | 6 | 1 | 2023-12-08 | 2024-01-10 | 22 | 3 | 19 | [20 empty] | 2024-01-11 |  | 2025-01-10 |  | EXP | [8 empty] | 2024-01-16 | Connected |  | No
National Grid | WESTMINSTER | 570427 | 1473 | 10 | Solar | 01_602W2 | 2023-11-21 08:09 | 2023-11-22 | 7 | 4 | 3 | 2023-12-01 | 2024-01-10 | 27 | 3 | 24 | [20 empty] | 2024-01-17 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | AUBURN | 569868 | 1501 | 10 | Solar | 01_26W2 | 2023-12-06 07:58 | 2023-12-07 | 6 | 3 | 3 | 2023-12-15 | 2024-02-13 | 41 | 19 | 22 | [20 empty] | 2024-02-15 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | SOUTHBOROUGH | 574904 | 1772 | 28.6 | Battery Add-On | 05_310W5 | 2023-11-30 15:21 | 2023-12-01 | 22 | 13 | 9 | 2024-01-04 | 2024-02-02 | 21 | 0 | 21 | [20 empty] | 2024-02-05 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | SOUTHBOROUGH | 574084 | 1772 | 22.8 | Battery Add-On | 05_310W5 | 2023-11-28 11:19 | 2023-11-29 | 1 | 0 | 1 | 2023-11-30 | 2024-01-08 | 26 | 3 | 23 | [20 empty] | 2024-01-12 | 2023-12-04 13:50 | 2025-03-29 |  | EXP | [8 empty] | 2024-04-04 | Connected |  | No
National Grid | AUBURN | 570140 | 1501 | 14.3 | Solar | 01_26W3 | 2023-12-04 13:50 | 2023-12-05 | 3 | 0 | 3 | 2023-12-08 | 2024-01-10 | 22 | 3 | 19 | [20 empty] | 2024-01-17 |  | 2025-03-08 | Yes | EXP |  | 2024-04-16 |  | 0 | 0 | 0 |  |  |  | Construction |  | Yes
National Grid | METHUEN | 558385 | 1844 | 990 | Solar | 14_74L1 | 2023-12-04 16:05 | 2023-12-05 | 91 | 26 | 65 | [29 empty] | STD | [9 empty] | Application |  | Yes
National Grid | METHUEN | 571764 | 1844 | 240 | Solar | 14_74L1 | 2023-11-17 13:17 | 2023-11-20 | 13 | 3 | 10 | [10 empty] | 2023-12-07 | 2024-01-19 | 30 | 5 | 25 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | METHUEN | 559307 | 1844 | 250 | Solar | 14_74L1 | 2023-11-17 10:30 | 2023-11-20 | 14 | 4 | 10 | [10 empty] | 2023-12-11 | 2024-01-18 | 26 | 6 | 20 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | MARLBOROUGH | 570780 | 1752 | 10 | Solar | 05_311W3 | 2023-11-20 16:57 | 2023-11-21 | 1 | 0 | 1 | 2023-11-22 | 2024-02-26 | 64 | 41 | 23 | [20 empty] | 2024-03-01 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | MARLBOROUGH | 569808 | 1752 | 6 | Solar | 05_311W3 | 2023-11-20 12:12 | 2023-11-21 | 8 | 4 | 4 | 2023-12-01 | 2024-01-10 | 27 | 3 | 24 | [20 empty] | 2024-01-17 |  | 2025-02-04 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | METHUEN | 571180 | 1844 | 10 | Solar | 14_74L2 | 2023-12-08 09:58 | 2023-12-11 | 3 | 1 | 2 | 2023-12-14 | 2024-02-26 | 50 | 28 | 22 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BELLINGHAM | 573961 | 2019 | 10 | Solar | 05_344W4 | 2023-12-06 09:38 | 2023-12-07 | 1 | 0 | 1 | 2023-12-08 | 2024-03-01 | 57 | 36 | 21 | [20 empty] | 2024-03-05 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | WESTBOROUGH | 573957 | 1581 | 20 | Battery Add-On | 05_312W1 | 2023-11-28 08:19 | 2023-11-29 | 21 | 20 | 1 | 2023-12-29 | 2024-01-26 | 19 | 0 | 19 | [20 empty] | 2024-02-01 |  | 2025-03-13 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | NORTHBOROUGH | 552640 | 1532 | 333 | Solar | 05_312W3 | 2023-11-21 16:15 | 2023-11-22 | 98 | 42 | 56 | [29 empty] | STD | [9 empty] | Application |  | Yes
National Grid | FRANKLIN | 567611 | 2038 | 7.6 | Solar | 05_344W5 | 2023-12-05 10:21 | 2023-12-06 | 5 | 2 | 3 | 2023-12-12 | 2024-02-23 | 51 | 28 | 23 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WESTBOROUGH | 573934 | 1581 | 15.2 | Solar | 05_312W4 | 2023-11-28 07:09 | 2023-11-29 | 11 | 8 | 3 | 2023-12-14 | 2024-01-25 | 28 | 6 | 22 | [20 empty] | 2024-01-30 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | FRANKLIN | 570717 | 2038 | 20 | Solar | 05_348W5 | 2023-11-13 09:27 | 2023-11-14 | 6 | 2 | 4 | 2023-12-06 | 2024-02-07 | 43 | 22 | 21 | [20 empty] | 2024-02-14 | 2023-11-14 16:27 | 2025-02-19 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | WEYMOUTH | 567935 | 2189 | 10 | Solar | 07_9W2 | 2023-11-14 16:27 | 2023-11-15 | 2 | 0 | 2 | 2023-11-17 |  | 101 | 17 | 84 | [20 empty] | 2024-01-19 |  | 2025-02-01 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | BROCKTON | 571870 | 2301 | 6 | Solar | 07_911W13 | 2023-11-29 09:13 | 2023-11-30 | 4 | 3 | 1 | 2023-12-06 | 2024-01-16 | 28 | 4 | 24 | [20 empty] | 2024-01-17 |  | 2025-04-08 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | BROCKTON | 566755 | 2301 | 7.6 | Solar | 07_911W13 | 2023-11-10 05:26 | 2023-11-13 | 7 | 4 | 3 | 2023-11-21 | 2023-12-27 | 25 | 3 | 22 | [20 empty] | 2024-01-04 | 2023-12-07 10:53 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | REHOBOTH | 572571 | 2769 | 3.19 | Solar | 05_3J2 | 2023-12-07 10:53 | 2023-12-08 | 1 | 0 | 1 | 2023-12-11 | 2024-01-10 | 21 | 3 | 18 | [20 empty] | 2024-01-11 |  | 2025-01-21 | Yes | EXP |  | 2024-03-05 | 2024-03-25 | 21 | 0 | 21 |  |  | 2024-03-30 | Connected |  | No
National Grid | GRANBY | 570155 | 1033 | 10 | Solar | 09_527L1 | 2023-11-27 08:13 | 2023-11-28 | 1 | 0 | 1 | 2023-11-29 | 2024-01-09 | 29 | 9 | 20 | 2024-01-22 | 2024-01-24 | 3 | 0 | 3 | [5 empty] | 2024-01-22 | 2024-01-24 | 3 | 0 | 3 | [5 empty] | 2024-02-07 |  | 2025-02-19 |  | EXP |  | 2024-02-28 | 2024-04-03 | 36 | 0 | 36 |  |  | 2024-04-09 | Connected |  | No
National Grid | WESTBOROUGH | 571722 | 1581 | 7.6 | Solar | 05_313W2 | 2023-11-21 11:25 | 2023-11-22 | 14 | 11 | 3 | 2023-12-12 | 2024-01-17 | 24 | 3 | 21 | [20 empty] | 2024-01-23 |  | 2025-02-25 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | NORTHBOROUGH | 574880 | 1532 | 29.87 | Solar | 05_313W2 | 2023-11-30 14:59 | 2023-12-01 | 9 | 6 | 3 | 2023-12-13 | 2024-01-24 | 28 | 3 | 25 | [20 empty] | 2024-01-25 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 570751 | 2302 | 7.6 | Solar | 07_911W56 | 2023-11-16 10:59 | 2023-11-17 | 2 | 0 | 2 | 2023-11-21 | 2024-01-02 | 28 | 3 | 25 | [20 empty] | 2024-01-02 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | BROCKTON | 561771 | 2302 | 5.8 | Solar | 07_911W77 | 2023-11-13 07:35 | 2023-11-14 | 2 | 0 | 2 | 2023-11-16 | 2023-12-22 | 27 | 9 | 18 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHESHIRE | 570337 | 1225 | 7.6 | Solar | 09_1021W1 | 2023-11-20 14:59 | 2023-11-21 | 7 | 2 | 5 | 2023-11-30 | 2024-02-01 | 44 | 22 | 22 | [20 empty] | 2024-02-05 | 2023-11-28 11:25 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | REHOBOTH | 572861 | 2769 | 15.2 | Solar | 05_7L5 | 2023-11-28 11:25 | 2023-11-29 | 2 | 1 | 1 | 2023-11-30 | 2024-01-30 | 42 | 17 | 25 | [20 empty] | 2024-02-01 | 2023-12-07 10:28 | 2025-02-11 | Yes | EXP |  | 2024-03-05 |  | 42 | 0 | 42 |  |  |  | Construction |  | Yes
National Grid | REHOBOTH | 571548 | 2769 | 3.77 | Solar | 05_7L5 | 2023-12-07 10:28 | 2023-12-08 | 1 | 0 | 1 | 2023-12-11 | 2024-01-10 | 21 | 3 | 18 | [20 empty] | 2024-01-11 |  | 2025-01-21 | Yes | EXP | [8 empty] | 2024-03-30 | Connected |  | No
National Grid | REHOBOTH | 570949 | 2769 | 25 | Solar | 05_7L5 | 2023-11-13 16:08 | 2023-11-14 | 4 | 3 | 1 | 2023-11-20 | 2024-01-25 | 45 | 18 | 27 | [20 empty] | 2024-01-29 |  | 2025-01-29 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | BARRE | 570272 | 1005 | 1500 | Solar | 09_604W3 | 2023-12-05 15:16 | 2023-12-06 | 56 | 48 | 8 | [10 empty] | 2024-02-29 | 2024-02-29 | 1 | 0 | 1 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | BRIDGEWATER | 554874 | 2324 | 7.54 | Solar | 07_912W74 | 2023-11-15 17:06 | 2023-11-16 | 19 | 17 | 2 | 2023-12-13 | 2024-02-02 | 35 | 13 | 22 | [20 empty] | 2024-02-06 | 2023-12-05 15:45 | 2025-02-12 |  | EXP | [8 empty] | 2024-04-09 | Connected |  | No
National Grid | ATTLEBORO | 571237 | 2703 | 5 | Solar | 05_8L1 | 2023-12-05 15:45 | 2023-12-06 | 47 | 37 | 10 | 2024-02-13 | 2024-02-28 | 12 | 5 | 7 | [20 empty] | 2024-03-04 |  | 2025-03-04 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | ATTLEBORO | 562760 | 2703 | 9.984 | Solar | 05_8L4 | 2023-11-27 13:30 | 2023-11-28 | 18 | 16 | 2 | 2023-12-22 | 2024-01-30 | 25 | 1 | 24 | [20 empty] | 2024-02-05 |  | 2025-02-14 |  | EXP | [8 empty] | 2024-03-28 | Connected |  | No
National Grid | GREAT BARRINGTON | 573964 | 1230 | 10 | Solar | 09_1109W1 | 2023-11-29 14:16 | 2023-11-30 | 2 | 1 | 1 | 2023-12-01 | 2024-01-09 | 26 | 3 | 23 | [20 empty] | 2024-01-12 |  | 2025-01-18 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | SOUTH GRAFTON | 559289 | 1560 | 7.25 | Solar | 05_320W3 | 2023-11-09 18:09 | 2023-11-13 | 4 | 1 | 3 | 2023-11-17 | 2024-02-28 | 69 | 48 | 21 | [20 empty] | 2024-03-04 | 2023-11-30 16:18 | 2025-03-11 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | ATHOL | 567606 | 1331 | 10 | Solar | 09_702W2 | 2023-11-30 16:18 | 2023-12-01 | 13 | 11 | 2 | 2023-12-20 | 2024-02-05 | 31 | 6 | 25 | [20 empty] | 2024-02-06 | 2023-11-10 20:41 | 2025-03-04 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | WEST STOCKBRIDGE | 559483 | 1266 | 10 | Solar | 09_1109W3 | 2023-11-10 20:41 | 2023-11-13 | 19 | 18 | 1 | 2023-12-11 | 2024-01-17 | 25 | 3 | 22 | [20 empty] | 2024-01-19 | 2023-11-27 10:54 | 2025-03-25 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | BROCKTON | 565340 | 2302 | 10 | Solar | 07_91W42 | 2023-11-27 10:54 | 2023-11-28 | 3 | 0 | 3 | 2023-12-01 | 2024-01-13 | 30 | 6 | 24 | [20 empty] | 2024-01-19 |  | 2025-02-19 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | BROCKTON | 571413 | 2301 | 75 | Solar | 07_91W43 | 2023-11-22 16:42 | 2023-11-24 | 98 | 26 | 72 | [29 empty] | EXP | [9 empty] | Pending Withdraw |  | No
National Grid | HAMPDEN | 575689 | 1036 | 11.4 | Solar | 09_139L1 | 2023-12-05 07:23 | 2023-12-06 | 1 | 0 | 1 | 2023-12-07 | 2024-04-02 | 80 | 56 | 24 | [20 empty] | 2024-04-08 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | BROCKTON | 568122 | 2301 | 22.8 | Solar | 07_91W43 | 2023-11-22 16:19 | 2023-11-24 | 17 | 14 | 3 | 2023-12-19 |  | 81 | 28 | 53 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | MENDON | 572760 | 1756 | 6.08 | Solar | 05_321W6 | 2023-11-21 09:49 | 2023-11-22 | 5 | 0 | 5 | 2023-11-30 | 2024-03-05 | 65 | 45 | 20 | [20 empty] | 2024-03-08 |  | 2025-04-10 |  | EXP | [9 empty] | Conditional Approval |  | No
National Grid | BROCKTON | 568459 | 2301 | 15.2 | Solar | 07_91W49 | 2023-11-22 16:32 | 2023-11-24 | 17 | 14 | 3 | 2023-12-19 |  | 81 | 28 | 53 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | BROCKTON | 568062 | 2301 | 6 | Solar | 07_91W49 | 2023-11-16 12:29 | 2023-11-17 | 73 | 27 | 46 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | BROCKTON | 566403 | 2301 | 6 | Solar | 07_91W49 | 2023-11-16 12:00 | 2023-11-17 | 6 | 0 | 6 | 2023-11-28 | 2024-04-04 | 89 | 68 | 21 | [24 empty] | EXP | [9 empty] | Supplemental Review |  | Yes
National Grid | BROCKTON | 570456 | 2301 | 20 | Solar | 07_91W49 | 2023-11-10 08:43 | 2023-11-13 | 5 | 3 | 2 | 2023-11-17 |  | 102 | 25 | 77 | [24 empty] | EXP | [9 empty] | Screening |  | No
National Grid | QUINCY | 571106 | 2169 | 3.8 | Solar | 07_1W2 | 2023-12-01 10:10 | 2023-12-04 | 58 | 26 | 32 | 2024-02-28 | 2024-04-04 | 28 | 25 | 3 | [24 empty] | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | NORTHAMPTON | 566378 | 1060 | 3.78 | Solar | 09_901W1 | 2023-11-13 10:03 | 2023-11-14 | 1 | 0 | 1 | 2023-11-15 | 2024-02-06 | 56 | 26 | 30 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | QUINCY | 576061 | 2169 | 8.41 | Solar | 07_1W5 | 2023-12-06 08:09 | 2023-12-07 | 26 | 24 | 2 | 2024-01-17 | 2024-03-19 | 45 | 25 | 20 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | NORTHAMPTON | 567873 | 1060 | 22.8 | Solar | 09_901W3 | 2023-11-21 16:23 | 2023-11-22 | 1 | 0 | 1 | 2023-11-24 | 2024-01-03 | 27 | 3 | 24 | [20 empty] | 2024-01-04 |  | 2025-01-23 |  | EXP | [8 empty] | 2024-04-11 | Connected |  | No
National Grid | MENDON | 573727 | 1756 | 15.2 | Solar | 05_335W1 | 2023-11-28 14:41 | 2023-11-29 | 10 | 9 | 1 | 2023-12-13 | 2024-02-07 | 38 | 16 | 22 | [20 empty] | 2024-02-09 | 2023-11-28 13:31 | 2025-02-15 |  | EXP | [8 empty] | 2024-03-27 | Connected |  | No
National Grid | FLORENCE | 571152 | 1062 | 10 | Solar | 09_909W1 | 2023-11-28 13:31 | 2023-11-29 | 11 | 8 | 3 | 2023-12-13 | 2024-01-24 | 28 | 5 | 23 | [20 empty] | 2024-01-29 |  | 2025-02-04 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | QUINCY | 566869 | 2169 | 3.8 | Solar | 07_3W2 | 2023-11-16 16:01 | 2023-11-17 | 1 | 0 | 1 | 2023-11-20 | 2024-02-06 | 52 | 31 | 21 | [20 empty] | 2024-02-06 | 2023-12-04 15:56 | 2025-02-07 |  | EXP | [8 empty] | 2024-03-19 | Connected |  | No
National Grid | RANDOLPH | 572680 | 2368 | 5 | Solar | 07_5W2 | 2023-12-04 15:56 | 2023-12-05 | 1 | 0 | 1 | 2023-12-06 | 2024-01-08 | 22 | 3 | 19 | [20 empty] | 2024-01-08 |  | 2025-02-04 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | MILFORD | 566642 | 1757 | 7.6 | Solar | 05_335W4 | 2023-11-15 17:35 | 2023-11-16 | 7 | 0 | 7 | 2023-11-28 | 2024-02-26 | 59 | 40 | 19 | [20 empty] | 2024-03-04 | 2023-11-22 09:42 | 2025-03-08 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | FLORENCE | 564752 | 1062 | 5 | Solar | 09_909W4 | 2023-11-22 09:42 | 2023-11-24 | 11 | 9 | 2 | 2023-12-08 | 2024-01-11 | 23 | 4 | 19 | [20 empty] | 2024-01-16 |  | 2025-03-06 | Yes | EXP |  | 2024-03-30 | 2024-04-09 | 11 | 0 | 11 |  |  | 2024-04-11 | Connected |  | No
National Grid | STOUGHTON | 572141 | 2072 | 6 | Solar | 07_94W43 | 2023-12-07 10:00 | 2023-12-08 | 3 | 0 | 3 | 2023-12-13 | 2024-01-23 | 27 | 3 | 24 | [20 empty] | 2024-01-24 |  | 2025-01-28 |  | EXP | [8 empty] | 2024-02-09 | Connected |  | No
National Grid | BROCKTON | 567965 | 2302 | 6 | Solar | 07_69J1 | 2023-11-10 10:42 | 2023-11-13 | 10 | 4 | 6 | 2023-11-28 | 2024-01-03 | 25 | 3 | 22 | [20 empty] | 2024-01-10 | 2023-12-06 13:27 | 2025-02-25 |  | EXP | [9 empty] | Meter Installation |  | Yes
National Grid | BROCKTON | 570864 | 2302 | 7.6 | Solar | 07_69J1 | 2023-12-06 13:27 | 2023-12-07 | 4 | 2 | 2 | 2023-12-13 | 2024-01-26 | 31 | 7 | 24 | [20 empty] | 2024-01-29 |  | 2025-02-28 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | MILFORD | 571863 | 1757 | 9.86 | Solar | 05_336W1 | 2023-12-07 11:07 | 2023-12-08 | 3 | 0 | 3 | 2023-12-13 | 2024-01-23 | 28 | 5 | 23 | [20 empty] | 2024-01-25 |  | 2025-03-08 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | BROCKTON | 571401 | 2302 | 7.6 | Solar | 07_712J1 | 2023-12-05 09:07 | 2023-12-06 | 3 | 0 | 3 | 2023-12-11 | 2024-01-19 | 27 | 4 | 23 | [20 empty] | 2024-01-25 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HANOVER | 573570 | 2339 | 10 | Solar | 07_95W5 | 2023-11-27 01:56 | 2023-11-28 | 5 | 3 | 2 | 2023-12-05 | 2024-01-30 | 38 | 19 | 19 | [20 empty] | 2024-02-05 |  | 2025-02-05 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | EAST LONGMEADOW | 556511 | 1028 | 499.5 | Solar | 09_508L5 | 2023-11-21 16:01 | 2023-11-22 | 98 | 42 | 56 | [29 empty] | STD | [9 empty] | Application |  | Yes
National Grid | BELCHERTOWN | 572116 | 1007 | 10 | Solar | 09_509L2 | 2023-11-17 04:09 | 2023-11-20 | 3 | 2 | 1 | 2023-11-22 | 2024-01-29 | 46 | 22 | 24 | [20 empty] | 2024-01-29 | 2023-12-07 10:24 | 2025-01-30 |  | EXP | [8 empty] | 2024-04-02 | Connected |  | No
National Grid | RANDOLPH | 572609 | 2368 | 6 | Solar | 07_97W1 | 2023-12-07 10:24 | 2023-12-08 | 3 | 0 | 3 | 2023-12-13 | 2024-01-24 | 28 | 5 | 23 | [20 empty] | 2024-01-26 |  | 2025-02-25 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | RANDOLPH | 569520 | 2368 | 7.6 | Solar | 07_97W1 | 2023-11-21 07:51 | 2023-11-22 | 15 | 14 | 1 | 2023-12-13 | 2024-01-26 | 31 | 7 | 24 | [20 empty] | 2024-01-29 |  | 2025-01-31 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | MALDEN | 576689 | 2148 | 12.6 | Battery Add-On | 12_16W3 | 2023-12-08 11:31 | 2023-12-11 | 7 | 6 | 1 | 2023-12-20 | 2024-01-30 | 27 | 7 | 20 | [20 empty] | 2024-02-05 | 2023-12-04 10:44 | 2025-03-19 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | RANDOLPH | 562983 | 2368 | 9.765 | Solar | 07_97W2 | 2023-12-04 10:44 | 2023-12-05 | 16 | 13 | 3 | 2023-12-28 | 2024-01-25 | 20 | 2 | 18 | [20 empty] | 2024-01-29 | 2023-12-01 09:50 | 2025-02-04 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | RANDOLPH | 570882 | 2368 | 10 | Solar | 07_97W2 | 2023-12-01 09:50 | 2023-12-04 | 3 | 0 | 3 | 2023-12-07 | 2024-01-16 | 26 | 3 | 23 | [20 empty] | 2024-01-19 |  | 2025-01-29 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | EVERETT | 569775 | 2149 | 6 | Solar | 12_16W7 | 2023-11-22 18:21 | 2023-11-24 | 8 | 4 | 4 | 2023-12-06 | 2024-02-05 | 42 | 18 | 24 | [20 empty] | 2024-02-08 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | FRANKLIN | 576378 | 2038 | 25 | Battery Add-On | 05_344W1 | 2023-12-07 10:04 | 2023-12-08 | 4 | 3 | 1 | 2023-12-13 | 2024-03-04 | 55 | 31 | 24 | [20 empty] | 2024-03-07 |  | 2025-04-10 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | MALDEN | 570139 | 2148 | 6 | Solar | 12_16W7 | 2023-11-20 11:59 | 2023-11-21 | 7 | 2 | 5 | 2023-12-01 | 2024-01-09 | 27 | 4 | 23 | [21 empty] | 2023-11-16 12:15 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 567311 | 2302 | 10 | Solar | 07_797W42 | 2023-11-16 12:15 | 2023-11-17 | 1 | 0 | 1 | 2023-11-20 | 2024-01-02 | 29 | 6 | 23 | [20 empty] | 2024-01-03 | 2023-11-27 14:06 | 2025-01-18 | Yes | EXP |  | 2024-03-29 |  | 18 | 0 | 18 |  |  |  | Construction |  | Yes
National Grid | RANDOLPH | 572536 | 2368 | 9.6 | Solar | 07_97W5 | 2023-11-27 14:06 | 2023-11-28 | 10 | 7 | 3 | 2023-12-12 | 2024-01-19 | 26 | 3 | 23 | 2024-02-15 | 2024-03-15 | 4 | 0 | 4 | [5 empty] | 2024-02-15 | 2024-03-15 | 4 | 0 | 4 | [5 empty] | 2024-02-27 |  | 2025-03-04 | Yes | EXP |  | 2024-03-16 |  | 31 | 0 | 31 |  |  |  | Construction |  | Yes
National Grid | REVERE | 572705 | 2151 | 7.83 | Solar | 12_16W8 | 2023-11-28 14:55 | 2023-11-29 | 18 | 16 | 2 | 2023-12-22 |  | 78 | 25 | 53 | [21 empty] | 2023-11-14 16:59 |  |  | EXP | [9 empty] | Screening |  | Yes
National Grid | BROCKTON | 571236 | 2301 | 9.984 | Solar | 07_98W19 | 2023-11-14 16:59 | 2023-11-15 | 4 | 3 | 1 | 2023-11-21 | 2024-01-12 | 37 | 12 | 25 | [20 empty] | 2024-01-16 | 2023-12-04 12:33 | 2025-03-01 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | WINTHROP | 574519 | 2152 | 7.6 | Solar | 12_22J7 | 2023-12-04 12:33 | 2023-12-05 | 32 | 25 | 7 | 2024-01-23 | 2024-02-13 | 16 | 0 | 16 | [20 empty] | 2024-02-15 |  | 2025-03-15 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | BONDSVILLE | 561289 | 1009 | 10 | Solar | 09_523L2 | 2023-12-05 12:05 | 2023-12-06 | 1 | 0 | 1 | 2023-12-07 | 2024-01-16 | 26 | 3 | 23 | [20 empty] | 2024-01-16 | 2023-11-22 13:20 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SAUGUS | 570482 | 1906 | 6 | Solar | 12_23W2 | 2023-11-22 13:20 | 2023-11-24 | 3 | 1 | 2 | 2023-11-29 | 2024-01-07 | 27 | 6 | 21 | [20 empty] | 2024-01-08 |  | 2025-01-10 | Yes | EXP |  | 2024-04-03 | 2024-04-03 | 1 | 0 | 1 |  |  | 2024-04-10 | Connected |  | No
National Grid | SAUGUS | 561352 | 1906 | 6.175 | Solar | 12_23W3 | 2023-11-21 11:01 | 2023-11-22 | 1 | 0 | 1 | 2023-11-24 | 2024-02-27 | 64 | 41 | 23 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NANTUCKET | 572025 | 2554 | 22.8 | Solar | 04_101L6 | 2023-11-17 14:00 | 2023-11-20 | 1 | 0 | 1 | 2023-11-21 | 2023-12-27 | 25 | 3 | 22 | [20 empty] | 2024-01-05 |  | 2025-02-01 |  | EXP | [8 empty] | 2024-04-11 | Connected |  | No
National Grid | WORCESTER | 569102 | 1604 | 10 | Solar | 01_10J383 | 2023-11-14 11:41 | 2023-11-15 | 2 | 0 | 2 | 2023-11-17 | 2024-01-04 | 32 | 7 | 25 | [21 empty] | 2023-12-07 10:41 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WORCESTER | 571562 | 1602 | 10 | Solar | 01_1J369 | 2023-12-07 10:41 | 2023-12-08 | 4 | 1 | 3 | 2023-12-13 | 2024-01-24 | 28 | 3 | 25 | [20 empty] | 2024-01-30 |  | 2025-02-14 | Yes | EXP |  | 2024-04-16 |  | 0 | 0 | 0 |  |  |  | Construction |  | Yes
National Grid | LEOMINSTER | 576114 | 1453 | 34.5 | Solar | 01_207W2 | 2023-12-06 10:14 | 2023-12-07 | 38 | 26 | 12 | 2024-02-02 |  | 51 | 25 | 26 | [21 empty] | 2023-11-15 07:57 |  |  | EXP | [9 empty] | Screening |  | Yes
National Grid | LEOMINSTER | 568532 | 1453 | 6.96 | Solar | 01_207W3 | 2023-11-15 07:57 | 2023-11-16 | 5 | 3 | 2 | 2023-11-22 | 2023-12-27 | 24 | 3 | 21 | [20 empty] | 2024-01-02 | 2023-11-20 15:13 | 2025-01-01 | Yes | EXP |  | 2024-01-30 | 2024-02-16 | 18 | 0 | 18 |  |  |  | Completion Documents |  | Yes
National Grid | LEOMINSTER | 471046 | 1453 | 6 | Solar | 01_207W6 | 2023-11-20 15:13 | 2023-11-21 | 1 | 0 | 1 | 2023-11-22 | 2024-01-23 | 40 | 19 | 21 | [20 empty] | 2022-11-01 | 2023-11-27 13:00 | 2025-01-30 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | LEOMINSTER | 571006 | 1453 | 7.6 | Solar | 01_207W6 | 2023-11-27 13:00 | 2023-11-28 | 3 | 2 | 1 | 2023-11-30 | 2024-01-07 | 26 | 5 | 21 | [20 empty] | 2024-01-08 |  | 2025-01-08 | Yes | EXP |  | 2024-02-17 | 2024-02-16 | 0 | 0 | 0 |  |  |  | Completion Documents |  | Yes
National Grid | LEOMINSTER | 573946 | 1453 | 16.3 | Battery Add-On | 01_207W6 | 2023-11-28 07:51 | 2023-11-29 | 2 | 0 | 2 | 2023-12-01 | 2024-03-07 | 66 | 49 | 17 | [20 empty] | 2024-03-14 |  | 2025-04-04 |  | EXP | [8 empty] | 2024-04-05 | Connected |  | No
National Grid | LOWELL | 556404 | 1852 | 250 | Solar | 14_306 | 2023-11-22 12:21 | 2023-11-24 | 8 | 0 | 8 | [10 empty] | 2023-12-06 | 2024-01-11 | 26 | 5 | 21 | [11 empty] | 2023-11-15 12:18 |  |  | STD | [9 empty] | Study |  | Yes
National Grid | WINCHENDON | 567040 | 1475 | 10 | Solar | 01_607W5 | 2023-11-15 12:18 | 2023-11-16 | 2 | 0 | 2 | 2023-11-20 | 2023-12-27 | 26 | 3 | 23 | [20 empty] | 2024-01-04 |  | 2025-01-28 | Yes | EXP |  | 2024-03-08 | 2024-03-07 | 0 | 0 | 0 |  |  | 2024-03-30 | Connected |  | No
National Grid | GARDNER | 570537 | 1440 | 21.4 | Solar | 01_607W5 | 2023-11-10 16:12 | 2023-11-13 | 86 | 52 | 34 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | GARDNER | 570460 | 1440 | 20 | Solar | 01_607W5 | 2023-11-10 08:30 | 2023-11-13 | 14 | 12 | 2 | 2023-12-01 | 2024-01-19 | 33 | 10 | 23 | [20 empty] | 2024-01-22 |  | 2025-01-29 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | NORTH GRAFTON | 567264 | 1536 | 11.6 | Solar | 01_328W2 | 2023-11-20 08:51 | 2023-11-21 | 3 | 2 | 1 | 2023-11-24 | 2024-03-07 | 71 | 38 | 33 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FALL RIVER | 576257 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-08 | [28 empty] | 2021-04-23 |  | 2024-05-06 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 566803 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-10-28 | [28 empty] | 2021-04-23 |  | 2024-04-08 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 576553 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-08 | [28 empty] | 2021-04-23 |  | 2025-02-24 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 576270 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-08 | [28 empty] | 2021-04-23 |  | 2024-05-06 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 566738 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-10-28 | [28 empty] | 2021-04-23 |  | 2024-05-05 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 566786 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-10-28 | [28 empty] | 2021-04-23 | 2024-01-05 10:31 | 2024-05-06 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | METHUEN | 565286 | 1844 | 11.97 | Solar | 14_74L5 | 2024-01-05 10:31 | 2024-01-08 | 1 | 0 | 1 | 2024-01-09 | 2024-02-12 | 24 | 0 | 24 | [20 empty] | 2024-02-13 |  | 2025-02-14 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | LYNN | 573665 | 1904 | 7.6 | Solar | 12_24W1 | 2023-12-11 09:53 | 2023-12-12 | 1 | 0 | 1 | 2023-12-13 | 2024-03-15 | 64 | 40 | 24 | [21 empty] | 2023-12-27 09:23 |  |  | EXP | [9 empty] | Supplemental Review |  | Yes
National Grid | NEWBURYPORT | 578652 | 1950 | 11.4 | Solar | 14_36L1 | 2023-12-27 09:23 | 2023-12-28 | 4 | 0 | 4 | 2024-01-04 | 2024-02-05 | 22 | 0 | 22 | [20 empty] | 2024-02-06 |  | 2025-02-27 | Yes | EXP |  | 2024-03-16 | 2024-04-10 | 26 | 0 | 26 |  |  |  | Meter Installation |  | Yes
National Grid | LAWRENCE | 578472 | 1841 | 2.03 | Solar | 14_74L6 | 2024-01-02 12:25 | 2024-01-03 | 3 | 0 | 3 | 2024-01-08 | 2024-02-06 | 21 | 0 | 21 | [20 empty] | 2024-02-07 |  | 2025-02-11 |  | EXP | [8 empty] | 2024-02-21 | Connected |  | No
National Grid | SAUGUS | 578612 | 1906 | 8.7 | Solar | 12_25W1 | 2024-01-08 08:17 | 2024-01-09 | 3 | 0 | 3 | 2024-01-12 | 2024-02-15 | 24 | 0 | 24 | [24 empty] | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | ANDOVER | 577657 | 1810 | 23 | Solar | 14_3J44 | 2023-12-13 11:20 | 2023-12-14 | 3 | 2 | 1 | 2023-12-19 |  | 81 | 28 | 53 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | GARDNER | 558965 | 1440 | 11.5 | Solar | 01_607W1 | 2024-01-11 14:13 | 2024-01-12 | 35 | 31 | 4 | 2024-03-05 | 2024-04-04 | 24 | 22 | 2 | [20 empty] | 2024-04-08 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | WESTBOROUGH | 571788 | 1581 | 3000 | Other | 05_312W1 | 2024-01-11 10:45 | 2024-01-12 | 64 | 51 | 13 | [29 empty] | STD | [9 empty] | Application |  | Yes
National Grid | WORCESTER | 570742 | 1609 | 10 | Solar | 01_3J374 | 2023-12-19 21:00 | 2023-12-20 | 79 | 75 | 4 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | LOWELL | 576639 | 1854 | 9.984 | Solar | 14_77L1 | 2023-12-14 08:40 | 2023-12-15 | 24 | 23 | 1 | 2024-01-23 | 2024-03-21 | 43 | 25 | 18 | [21 empty] | 2023-12-20 10:52 |  |  | EXP | [9 empty] | Screening |  | Yes
National Grid | LYNN | 573455 | 1904 | 9.86 | Solar | 12_29W3 | 2023-12-20 10:52 | 2023-12-21 | 6 | 1 | 5 | 2024-01-03 | 2024-01-31 | 20 | 0 | 20 | [20 empty] | 2024-02-06 |  | 2025-02-25 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | WESTMINSTER | 578023 | 1473 | 9.86 | Solar | 01_609W1 | 2024-01-03 12:56 | 2024-01-04 | 32 | 25 | 7 | 2024-02-21 |  | 39 | 33 | 6 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | SALEM | 576101 | 1970 | 6 | Solar | 12_29W4 | 2023-12-19 15:56 | 2023-12-20 | 37 | 25 | 12 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | CHARLTON | 579001 | 1507 | 140 | Solar | 01_406L3 | 2023-12-21 16:52 | 2023-12-22 | 10 | 0 | 10 | [10 empty] | 2024-01-08 | 2024-02-08 | 23 | 0 | 23 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | CHARLTON | 574156 | 1507 | 480 | Solar | 01_406L3 | 2023-12-22 08:30 | 2023-12-26 | 9 | 0 | 9 | [10 empty] | 2024-01-09 | 2024-02-06 | 20 | 0 | 20 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | OXFORD | 578775 | 1540 | 6.09 | Solar | 01_406L3 | 2024-01-08 10:51 | 2024-01-09 | 4 | 0 | 4 | 2024-01-16 | 2024-02-07 | 17 | 0 | 17 | [20 empty] | 2024-02-14 |  | 2025-03-09 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | ANDOVER | 576984 | 1810 | 17.6 | Solar | 14_54L3 | 2023-12-11 11:08 | 2023-12-12 | 2 | 0 | 2 | 2023-12-14 | 2024-02-28 | 52 | 28 | 24 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | ANDOVER | 581109 | 1810 | 25 | Battery Add-On | 14_8L1 | 2024-01-03 09:32 | 2024-01-04 | 2 | 0 | 2 | 2024-01-08 | 2024-03-07 | 43 | 25 | 18 | [20 empty] | 2024-03-13 |  | 2025-03-25 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | MEDFORD | 578954 | 2155 | 200 | Solar | 12_37W1 | 2024-01-03 15:46 | 2024-01-04 | 6 | 0 | 6 | 2024-01-12 | 2024-02-12 | 21 | 0 | 21 | [20 empty] | 2024-02-21 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LAWRENCE | 579143 | 1841 | 10 | Solar | 14_8L2 | 2024-01-10 16:27 | 2024-01-11 | 14 | 12 | 2 | 2024-01-31 | 2024-03-06 | 25 | 12 | 13 | [20 empty] | 2024-03-11 |  | 2025-03-25 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | MEDFORD | 578165 | 2155 | 10 | Solar | 12_37W4 | 2023-12-20 16:26 | 2023-12-21 | 8 | 8 | 0 | 2024-01-05 | 2024-02-01 | 19 | 0 | 19 | 2024-02-05 | 2024-03-12 | 19 | 0 | 19 | [5 empty] | 2024-02-05 | 2024-03-12 | 19 | 0 | 19 | [5 empty] | 2024-02-23 |  | 2025-02-25 |  | EXP |  | 2024-03-16 |  | 31 | 0 | 31 |  |  |  | Construction |  | Yes
National Grid | MEDFORD | 580959 | 2155 | 23 | Solar | 12_37W4 | 2024-01-02 14:01 | 2024-01-03 | 44 | 43 | 1 | 2024-03-15 |  | 22 | 19 | 3 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | AUBURN | 557102 | 1501 | 6 | Solar | 01_6W1 | 2024-01-03 15:29 | 2024-03-01 |  |  |  | 2024-02-16 | 2024-02-23 | 5 | 0 | 5 | [20 empty] | 2023-09-29 |  | 2025-02-28 |  | EXP | [9 empty] | Connected |  | No
National Grid | NORTH ANDOVER | 581516 | 1845 | 7.6 | Solar | 14_56L2 | 2024-01-04 14:36 | 2024-01-05 | 12 | 7 | 5 | 2024-01-24 | 2024-02-16 | 18 | 0 | 18 | [20 empty] | 2024-02-23 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | MEDFORD | 581300 | 2155 | 17.6 | Battery Add-On | 12_37W5 | 2024-01-03 17:15 | 2024-01-04 | 2 | 0 | 2 | 2024-01-08 | 2024-04-08 | 64 | 47 | 17 | [20 empty] | 2024-04-12 |  |  |  | EXP | [9 empty] | Conditional Approval |  | No
National Grid | MEDFORD | 575277 | 2155 | 25 | Solar | 12_37W5 | 2024-01-08 04:25 | 2024-01-09 | 9 | 6 | 3 | 2024-01-23 |  | 59 | 41 | 18 | [24 empty] | EXP | [9 empty] | Screening |  | No
National Grid | WESTBOROUGH | 580711 | 1581 | 150 | Solar | 05_314W1 | 2024-01-07 18:29 | 2024-01-08 | 21 | 11 | 10 | [10 empty] | 2024-02-08 | 2024-02-21 | 9 | 0 | 9 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | DUDLEY | 572497 | 1571 | 7.25 | Solar | 01_412L4 | 2023-12-11 09:39 | 2023-12-12 | 3 | 0 | 3 | 2023-12-15 | 2024-01-31 | 31 | 6 | 25 | 2024-02-09 | 2024-03-12 | 10 | 0 | 10 | [5 empty] | 2024-02-09 | 2024-03-12 | 10 | 0 | 10 | [5 empty] | 2024-02-29 |  | 2025-03-07 |  | EXP |  | 2024-03-08 |  | 39 | 0 | 39 |  |  |  | Construction |  | Yes
National Grid | DUDLEY | 578997 | 1571 | 140 | Solar | 01_412L4 | 2023-12-22 08:45 | 2023-12-26 | 9 | 0 | 9 | [10 empty] | 2024-01-09 | 2024-02-08 | 22 | 0 | 22 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | DUDLEY | 578994 | 1571 | 240 | Solar | 01_412L4 | 2023-12-22 08:55 | 2023-12-26 | 10 | 0 | 10 | [10 empty] | 2024-01-10 | 2024-02-08 | 21 | 0 | 21 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | BEVERLY | 578751 | 1915 | 17.6 | Solar | 12_51L1 | 2023-12-19 08:24 | 2023-12-20 | 2 | 2 | 0 | 2023-12-26 | 2024-02-16 | 38 | 16 | 22 | [20 empty] | 2024-02-21 |  | 2025-02-26 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | BOLTON | 582430 | 1740 | 15.2 | Solar | 01_216W6 | 2024-01-09 13:58 | 2024-01-10 | 2 | 0 | 2 | 2024-01-12 | 2024-03-13 | 43 | 23 | 20 | [20 empty] | 2024-03-18 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | DUDLEY | 577506 | 1571 | 7.6 | Solar | 01_412L5 | 2023-12-21 08:37 | 2023-12-22 | 1 | 0 | 1 | 2023-12-26 | 2024-02-02 | 27 | 2 | 25 | [20 empty] | 2024-02-06 |  | 2025-02-26 |  | EXP | [8 empty] | 2024-04-09 | Connected |  | No
National Grid | CHELMSFORD | 576775 | 1824 | 23 | Solar | 14_58L2 | 2023-12-08 15:22 | 2023-12-11 | 2 | 0 | 2 | 2023-12-13 | 2024-02-28 | 53 | 28 | 25 | [20 empty] | 2024-03-06 |  | 2025-03-26 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | SOUTHBRIDGE | 579815 | 1550 | 7.25 | Solar | 01_413L1 | 2024-01-05 13:31 | 2024-01-08 | 5 | 3 | 2 | 2024-01-16 |  | 64 | 25 | 39 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | NORTHBRIDGE | 573240 | 1534 | 50 | Solar | 05_320W1 | 2023-12-18 15:38 | 2023-12-19 | 47 | 38 | 9 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOUTHBRIDGE | 573990 | 1550 | 6 | Solar | 01_413L1 | 2023-12-13 09:16 | 2023-12-14 | 2 | 1 | 1 | 2023-12-15 | 2024-01-05 | 14 | 3 | 11 | [21 empty] | 2024-01-08 10:25 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | SOUTHBRIDGE | 568896 | 1550 | 6 | Solar | 01_413L2 | 2024-01-08 10:25 | 2024-01-09 | 11 | 9 | 2 | 2024-01-24 | 2024-03-15 | 38 | 20 | 18 | [20 empty] | 2024-03-19 |  | 2025-03-25 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | ANDOVER | 551107 | 1810 | 300 | Solar | 14_59L1 | 2024-01-05 15:32 | 2024-01-08 | 21 | 11 | 10 | [10 empty] | 2024-02-08 | 2024-02-23 | 11 | 0 | 11 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | HAMILTON | 574209 | 1982 | 490 | Solar | 12_51T2 | 2023-12-15 16:59 | 2023-12-18 | 14 | 5 | 9 | [10 empty] | 2024-01-10 | 2024-03-11 | 43 | 25 | 18 | [14 empty] | STD | [9 empty] | Pending Withdraw |  | Yes
National Grid | LEICESTER | 575102 | 1524 | 9.86 | Solar | 01_21W2 | 2023-12-19 16:22 | 2023-12-20 | 1 | 1 | 0 | 2023-12-21 | 2024-01-24 | 21 | 1 | 20 | [20 empty] | 2024-01-29 |  | 2025-01-31 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | CHERRY VALLEY | 566580 | 1611 | 17.6 | Solar | 01_21W2 | 2023-12-14 11:16 | 2023-12-15 | 8 | 4 | 4 | 2023-12-28 |  | 75 | 25 | 50 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | SUTTON | 542382 | 1590 | 1000 | Solar | 05_320W5 | 2024-01-10 15:18 | 2024-01-11 | 65 | 57 | 8 | [29 empty] | STD | [9 empty] | Application |  | Yes
National Grid | HARVARD | 582536 | 1451 | 24.375 | Solar | 01_225W1 | 2024-01-12 15:07 | 2024-01-16 | 3 | 1 | 2 | 2024-01-18 | 2024-02-14 | 20 | 0 | 20 | [20 empty] | 2024-02-20 |  | 2025-02-22 |  | EXP | [8 empty] | 2024-03-15 | Connected |  | No
National Grid | DOUGLAS | 574593 | 1516 | 6 | Solar | 05_321W2 | 2023-12-27 16:48 | 2023-12-28 | 22 | 19 | 3 | 2024-01-30 | 2024-03-07 | 28 | 15 | 13 | [20 empty] | 2024-03-11 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | GLOUCESTER | 581847 | 1930 | 24.86 | Solar | 12_52L1 | 2024-01-08 10:41 | 2024-01-09 | 22 | 19 | 3 | 2024-02-08 | 2024-02-22 | 10 | 0 | 10 | [20 empty] | 2024-02-28 | 2023-12-28 12:03 |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 575137 | 1507 | 6 | Solar | 01_415L1 | 2023-12-28 12:03 | 2023-12-29 | 2 | 0 | 2 | 2024-01-03 | 2024-01-29 | 18 | 0 | 18 | [20 empty] | 2024-01-31 |  | 2025-01-31 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | MEDFORD | 562644 | 2155 | 2.52 | Solar | 12_64J1 | 2023-12-13 10:05 | 2023-12-14 | 5 | 3 | 2 | 2023-12-21 | 2024-02-08 | 33 | 12 | 21 | [20 empty] | 2024-02-09 |  | 2025-02-12 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | MEDFORD | 561812 | 2155 | 6.3 | Solar | 12_64J1 | 2023-12-13 14:12 | 2023-12-14 | 2 | 1 | 1 | 2023-12-15 | 2024-01-24 | 26 | 3 | 23 | [20 empty] | 2024-01-26 | 2023-12-18 10:44 | 2025-02-06 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | FALL RIVER | 577963 | 2721 | 10 | Solar | 05_115W53 | 2023-12-18 10:44 | 2023-12-19 | 8 | 6 | 2 | 2024-01-03 | 2024-02-02 | 22 | 0 | 22 | [20 empty] | 2024-02-06 |  | 2025-02-06 | Yes | EXP |  | 2024-03-26 | 2024-03-25 | 0 | 0 | 0 |  |  |  | Completion Documents |  | No
National Grid | FALL RIVER | 575780 | 2721 | 9.765 | Solar | 05_115W53 | 2023-12-11 12:33 | 2023-12-12 | 3 | 0 | 3 | 2023-12-15 | 2024-02-07 | 37 | 14 | 23 | [20 empty] | 2024-02-14 |  | 2025-02-25 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LAWRENCE | 581506 | 1843 | 7.6 | Solar | 14_61L3 | 2024-01-04 13:57 | 2024-01-05 | 30 | 25 | 5 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | CHARLTON | 557025 | 1507 | 16 | Solar | 01_415L2 | 2023-12-22 13:07 | 2023-12-26 | 5 | 2 | 3 | 2024-01-03 | 2024-02-26 | 38 | 18 | 20 | [20 empty] | 2024-03-01 |  | 2025-03-05 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | LAWRENCE | 573321 | 1843 | 3.8 | Solar | 14_61L3 | 2024-01-12 13:43 | 2024-01-16 | 11 | 8 | 3 | 2024-01-31 | 2024-03-18 | 34 | 21 | 13 | [20 empty] | 2024-03-19 |  | 2025-04-10 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LEOMINSTER | 578035 | 1453 | 8.7 | Solar | 01_225W4 | 2024-01-08 06:52 | 2024-01-09 | 4 | 0 | 4 | 2024-01-16 | 2024-02-15 | 23 | 0 | 23 | 2024-04-05 |  | 7 | 0 | 7 | [5 empty] | 2024-04-05 |  | 7 | 0 | 7 | [6 empty] | 2024-01-03 08:04 |  |  | EXP | [9 empty] | Supplemental Review |  | Yes
National Grid | BLACKSTONE | 579135 | 1504 | 8.775 | Solar | 05_321W9 | 2024-01-03 08:04 | 2024-01-04 | 6 | 3 | 3 | 2024-01-12 | 2024-02-15 | 24 | 0 | 24 | [20 empty] | 2024-02-20 |  | 2025-03-07 | Yes | EXP |  | 2024-04-09 |  | 7 | 0 | 7 |  |  |  | Construction |  | Yes
National Grid | UXBRIDGE | 573979 | 1569 | 10 | Solar | 05_321W9 | 2023-12-11 10:12 | 2023-12-12 | 2 | 1 | 1 | 2023-12-13 | 2024-01-23 | 27 | 3 | 24 | 2024-02-27 | 2024-03-27 | 10 | 0 | 10 | [5 empty] | 2024-02-27 | 2024-03-27 | 10 | 0 | 10 | [5 empty] | 2024-03-19 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | PEPPERELL | 577018 | 1463 | 6.67 | Solar | 01_226L1 | 2023-12-27 14:04 | 2023-12-28 | 4 | 0 | 4 | 2024-01-04 | 2024-02-06 | 23 | 0 | 23 | [20 empty] | 2024-02-13 | 2023-12-29 10:44 | 2025-02-14 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | NORTH BROOKFIELD | 571567 | 1535 | 10 | Solar | 01_525L1 | 2023-12-29 10:44 | 2024-01-02 | 27 | 26 | 1 | 2024-02-08 | 2024-02-21 | 9 | 0 | 9 | [20 empty] | 2024-02-27 |  | 2025-02-28 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | METHUEN | 579133 | 1844 | 9.57 | Solar | 14_63L1 | 2023-12-21 10:40 | 2023-12-22 | 1 | 0 | 1 | 2023-12-26 | 2024-01-30 | 24 | 0 | 24 | [20 empty] | 2024-01-30 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | SWANSEA | 575399 | 2777 | 6 | Solar | 05_11W84 | 2023-12-12 09:54 | 2023-12-13 | 5 | 2 | 3 | 2023-12-20 | 2024-01-26 | 26 | 6 | 20 | 2024-02-13 | 2024-03-07 | 17 | 0 | 17 | [5 empty] | 2024-02-13 | 2024-03-07 | 17 | 0 | 17 | [5 empty] | 2024-02-29 | 2024-01-12 12:46 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | METHUEN | 580403 | 1844 | 10 | Solar | 14_63L1 | 2024-01-12 12:46 | 2024-01-16 | 27 | 25 | 2 | 2024-03-05 | 2024-03-15 | 10 | 8 | 2 | [20 empty] | 2024-03-20 |  | 2025-03-22 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | MENDON | 580306 | 1756 | 7.6 | Solar | 05_332W1 | 2024-01-05 11:43 | 2024-01-08 | 6 | 1 | 5 | 2024-01-17 | 2024-04-11 | 39 | 25 | 14 | [24 empty] | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | UPTON | 568463 | 1568 | 4750 | Solar | 05_332W1 | 2024-01-10 14:47 | 2024-01-11 | 66 | 56 | 10 | [29 empty] | STD | [9 empty] | Application |  | No
National Grid | UPTON | 582910 | 1568 | 19.6 | Battery Add-On | 05_332W1 | 2024-01-11 10:33 | 2024-01-12 | 59 | 54 | 5 | 2024-04-08 |  | 6 | 2 | 4 | [21 empty] | 2023-12-18 15:51 |  |  | EXP | [9 empty] | Screening |  | No
National Grid | PEPPERELL | 570251 | 1463 | 6 | Solar | 01_226L2 | 2023-12-18 15:51 | 2023-12-19 | 9 | 3 | 6 | 2024-01-03 | 2024-02-05 | 23 | 0 | 23 | [20 empty] | 2024-02-08 |  | 2025-02-12 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | WEST BROOKFIELD | 572189 | 1585 | 9.28 | Solar | 01_525L2 | 2024-01-10 09:42 | 2024-01-11 | 41 | 37 | 4 | 2024-03-12 |  | 25 | 20 | 5 | [24 empty] | EXP | [9 empty] | Screening |  | No
National Grid | SPENCER | 571014 | 1562 | 10 | Solar | 01_552L1 | 2023-12-21 09:27 | 2023-12-22 | 5 | 0 | 5 | 2024-01-02 | 2024-03-07 | 47 | 27 | 20 | [20 empty] | 2024-03-14 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | WORCESTER | 581452 | 1605 | 7.6 | Solar | 01_23W2 | 2024-01-04 16:13 | 2024-01-05 | 9 | 7 | 2 | 2024-01-18 | 2024-03-11 | 38 | 19 | 19 | [20 empty] | 2024-03-18 |  | 2025-03-19 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | WORCESTER | 575782 | 1602 | 7.83 | Solar | 01_23W3 | 2023-12-27 15:42 | 2023-12-28 | 1 | 0 | 1 | 2023-12-29 | 2024-01-31 | 22 | 0 | 22 | 2024-02-27 | 2024-03-27 | 15 | 0 | 15 | [5 empty] | 2024-02-27 | 2024-03-27 | 15 | 0 | 15 | [5 empty] | 2024-03-22 | 2023-12-18 12:21 |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | EAST BROOKFIELD | 570255 | 1515 | 10 | Solar | 01_552L3 | 2023-12-18 12:21 | 2023-12-19 | 9 | 7 | 2 | 2024-01-03 | 2024-02-05 | 23 | 0 | 23 | [20 empty] | 2024-02-07 |  | 2025-02-07 | Yes | EXP |  | 2024-03-08 |  | 39 | 0 | 39 |  |  |  | Construction |  | Yes
National Grid | NORTH BROOKFIELD | 575455 | 1535 | 10 | Solar | 01_552L3 | 2023-12-13 08:28 | 2023-12-14 | 15 | 8 | 7 | 2024-01-05 | 2024-02-12 | 26 | 7 | 19 | [20 empty] | 2024-02-15 |  | 2025-03-04 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LAWRENCE | 579731 | 1841 | 7.6 | Solar | 14_6J8 | 2023-12-29 13:45 | 2024-01-02 | 11 | 8 | 3 | 2024-01-17 | 2024-03-01 | 33 | 12 | 21 | [24 empty] | EXP | [9 empty] | Supplemental Review |  | Yes
National Grid | NORTH DIGHTON | 578440 | 2764 | 10 | Solar | 05_19W73 | 2023-12-20 15:43 | 2023-12-21 | 7 | 3 | 4 | 2024-01-04 | 2024-01-30 | 18 | 0 | 18 | [20 empty] | 2024-01-30 |  | 2025-02-06 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | WORCESTER | 577496 | 1602 | 6 | Solar | 01_23W4 | 2023-12-27 15:24 | 2023-12-28 | 4 | 0 | 4 | 2024-01-04 | 2024-01-31 | 19 | 0 | 19 | [20 empty] | 2024-02-06 |  | 2025-02-12 |  | EXP | [8 empty] | 2024-02-27 | Connected |  | No
National Grid | TEWKSBURY | 547089 | 1876 | 240 | Solar | 14_70L1 | 2023-12-12 12:40 | 2023-12-13 | 37 | 27 | 10 | [10 empty] | 2024-02-06 | 2024-02-20 | 10 | 0 | 10 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | MILFORD | 575857 | 1757 | 3.77 | Solar | 05_335W4 | 2023-12-20 10:32 | 2023-12-21 | 3 | 1 | 2 | 2023-12-28 | 2024-02-05 | 26 | 3 | 23 | [20 empty] | 2024-02-06 |  | 2025-02-07 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | WORCESTER | 576161 | 1606 | 10 | Solar | 01_24W2 | 2024-01-03 09:53 | 2024-01-04 | 2 | 0 | 2 | 2024-01-08 | 2024-03-08 | 44 | 19 | 25 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | RUTLAND | 578149 | 1543 | 2.32 | Solar | 01_55W1 | 2024-01-08 07:50 | 2024-01-09 | 1 | 1 | 0 | 2024-01-11 | 2024-02-07 | 19 | 0 | 19 | [20 empty] | 2024-02-08 | 2024-01-03 10:03 | 2025-02-12 |  | EXP | [8 empty] | 2024-03-05 | Connected |  | No
National Grid | WORCESTER | 576736 | 1606 | 6 | Solar | 01_24W3 | 2024-01-03 10:03 | 2024-01-04 | 3 | 1 | 2 | 2024-01-09 | 2024-02-12 | 24 | 0 | 24 | [20 empty] | 2024-02-15 |  | 2025-03-04 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | DRACUT | 574472 | 1826 | 10 | Solar | 14_21L2 | 2023-12-08 17:44 | 2023-12-11 | 2 | 0 | 2 | 2023-12-13 | 2024-01-22 | 26 | 3 | 23 | [20 empty] | 2024-01-25 |  | 2025-02-20 |  | EXP | [8 empty] | 2024-03-01 | Connected |  | No
National Grid | BILLERICA | 579214 | 1821 | 34.5 | Solar | 14_70L6 | 2023-12-20 14:18 | 2023-12-21 | 40 | 26 | 14 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH ANDOVER | 578504 | 1845 | 400 | Solar | 14_71L3 | 2024-01-12 14:30 | 2024-01-16 | 19 | 9 | 10 | [10 empty] | 2024-02-09 | 2024-02-23 | 10 | 0 | 10 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | NORTH ANDOVER | 578593 | 1845 | 480 | Solar | 14_71L3 | 2024-01-12 14:33 | 2024-01-16 | 19 | 9 | 10 | [10 empty] | 2024-02-09 | 2024-02-23 | 10 | 0 | 10 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | FALL RIVER | 582560 | 2720 | 10 | Battery Add-On | 05_28W50 | 2024-01-10 10:14 | 2024-01-11 | 7 | 4 | 3 | 2024-01-23 | 2024-04-05 | 53 | 34 | 19 | [24 empty] | EXP | [9 empty] | Conditional Approval |  | No
National Grid | AUBURN | 572356 | 1501 | 7.6 | Solar | 01_26W2 | 2024-01-09 10:03 | 2024-01-10 | 11 | 7 | 4 | 2024-01-25 | 2024-02-16 | 17 | 0 | 17 | [20 empty] | 2024-02-23 | 2024-01-12 14:21 |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | AMESBURY | 574491 | 1913 | 11.4 | Solar | 14_275L2 | 2024-01-12 14:21 | 2024-01-16 | 5 | 4 | 1 | 2024-01-23 | 2024-02-13 | 17 | 1 | 16 | [20 empty] | 2024-02-15 |  | 2025-02-14 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | WORCESTER | 573451 | 1604 | 5.51 | Solar | 01_27W1 | 2023-12-12 09:53 | 2023-12-13 | 2 | 1 | 1 | 2023-12-15 | 2024-01-24 | 26 | 3 | 23 | [20 empty] | 2024-01-29 |  | 2025-02-25 |  | EXP | [8 empty] | 2024-03-15 | Connected |  | No
National Grid | LOWELL | 561313 | 1851 | 7.25 | Solar | 14_2L2 | 2024-01-03 12:23 | 2024-01-04 | 32 | 25 | 7 | 2024-02-21 | 2024-03-29 | 29 | 25 | 4 | [24 empty] | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | WORCESTER | 582263 | 1605 | 10.44 | Solar | 01_27W4 | 2024-01-09 15:28 | 2024-01-10 | 3 | 1 | 2 | 2024-01-12 | 2024-02-15 | 25 | 4 | 21 | [20 empty] | 2024-02-20 |  | 2025-03-21 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | LAWRENCE | 580225 | 1841 | 5.8 | Solar | 14_74L3 | 2024-01-11 16:33 | 2024-01-12 | 7 | 6 | 1 | 2024-01-23 |  | 59 | 30 | 29 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | WEYMOUTH | 579417 | 2190 | 16 | Solar | 07_8W1 | 2023-12-26 11:49 | 2023-12-27 | 2 | 0 | 2 | 2023-12-29 | 2024-03-08 | 49 | 25 | 24 | [21 empty] | 2023-12-14 13:07 |  |  | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | REVERE | 575019 | 2151 | 9.86 | Solar | 12_16W8 | 2023-12-14 13:07 | 2023-12-15 | 3 | 1 | 2 | 2023-12-20 | 2024-02-28 | 47 | 23 | 24 | [20 empty] | 2024-03-04 |  | 2025-03-05 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | RANDOLPH | 576970 | 2368 | 3.8 | Solar | 07_97W4 | 2023-12-27 15:59 | 2023-12-28 | 3 | 0 | 3 | 2024-01-03 | 2024-02-12 | 28 | 10 | 18 | [20 empty] | 2024-02-20 |  | 2025-02-20 |  | EXP | [9 empty] | Conditional Approval |  | No
National Grid | RANDOLPH | 579463 | 2368 | 10 | Solar | 07_97W5 | 2024-01-10 12:28 | 2024-01-11 | 3 | 0 | 3 | 2024-01-17 | 2024-02-15 | 22 | 6 | 16 | [20 empty] | 2024-02-21 |  | 2025-03-06 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | HOLLAND | 576582 | 1521 | 10 | Solar | 09_516L1 | 2024-01-03 17:36 | 2024-01-04 | 4 | 2 | 2 | 2024-01-09 | 2024-02-06 | 20 | 2 | 18 | [20 empty] | 2024-02-08 | 2024-01-05 12:12 | 2025-02-09 |  | EXP | [8 empty] | 2024-02-14 | Connected |  | No
National Grid | BELLINGHAM | 556593 | 2019 | 6 | Solar | 05_344W4 | 2024-01-05 12:12 | 2024-01-08 | 6 | 5 | 1 | 2024-01-17 | 2024-02-07 | 16 | 0 | 16 | [20 empty] | 2024-02-12 |  | 2025-02-14 | Yes | EXP | [9 empty] | Construction |  | No
National Grid | BELLINGHAM | 570649 | 2019 | 5.51 | Solar | 05_344W4 | 2023-12-27 03:31 | 2023-12-28 | 6 | 2 | 4 | 2024-01-08 | 2024-03-12 | 46 | 25 | 21 | [24 empty] | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | BEVERLY | 568254 | 1915 | 480 | Solar | 12_18L1 | 2023-12-19 15:32 | 2023-12-20 | 11 | 2 | 9 | [10 empty] | 2024-01-09 | 2024-02-06 | 21 | 1 | 20 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | SAUGUS | 575819 | 1906 | 6 | Solar | 12_19W1 | 2023-12-11 14:54 | 2023-12-12 | 2 | 1 | 1 | 2023-12-13 | 2024-02-16 | 46 | 21 | 25 | [20 empty] | 2024-02-20 |  | 2025-02-28 |  | EXP | [9 empty] | Conditional Approval |  | No
National Grid | LYNN | 575591 | 1905 | 3.8 | Solar | 12_19W1 | 2023-12-13 14:53 | 2023-12-14 | 2 | 1 | 1 | 2023-12-15 | 2024-01-31 | 31 | 6 | 25 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HANOVER | 577710 | 2339 | 4999.2 | Other | 07_910W52 | 2024-01-04 05:19 | 2024-01-05 | 32 | 25 | 7 | [10 empty] | 2024-02-22 | 2024-02-26 | 3 | 0 | 3 | [14 empty] | STD | [9 empty] | Group Study |  | Yes
National Grid | BROCKTON | 576593 | 2301 | 2.32 | Solar | 07_911W25 | 2023-12-19 16:12 | 2023-12-20 | 4 | 2 | 2 | 2023-12-28 | 2024-01-30 | 22 | 0 | 22 | [20 empty] | 2024-02-01 |  | 2025-02-01 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | LYNN | 579935 | 1902 | 7.6 | Solar | 12_22W2 | 2023-12-29 12:56 | 2024-01-02 | 9 | 7 | 2 | 2024-01-16 | 2024-03-21 | 48 | 28 | 20 | [20 empty] | 2024-03-26 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | BROCKTON | 574093 | 2302 | 9.6 | Solar | 07_911W56 | 2023-12-19 16:59 | 2023-12-20 | 1 | 1 | 0 | 2023-12-21 | 2024-02-21 | 41 | 18 | 23 | [20 empty] | 2024-02-22 | 2023-12-15 11:42 |  |  | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | SAUGUS | 575934 | 1906 | 9.86 | Solar | 12_23W2 | 2023-12-15 11:42 | 2023-12-18 | 3 | 2 | 1 | 2023-12-21 | 2024-01-24 | 21 | 1 | 20 | [20 empty] | 2024-01-25 | 2024-01-04 12:54 | 2025-01-31 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | NORTON | 579176 | 2766 | 9.45 | Solar | 05_4L2 | 2024-01-04 12:54 | 2024-01-05 | 17 | 13 | 4 | 2024-01-31 | 2024-02-16 | 13 | 0 | 13 | [20 empty] | 2024-02-20 |  | 2025-03-25 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | NORTON | 579332 | 2766 | 10 | Solar | 05_4L2 | 2024-01-08 09:22 | 2024-01-09 | 4 | 0 | 4 | 2024-01-16 | 2024-02-12 | 20 | 0 | 20 | [20 empty] | 2024-02-15 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | SEEKONK | 575382 | 2771 | 2.9 | Solar | 05_7L1 | 2023-12-26 11:12 | 2023-12-27 | 6 | 1 | 5 | 2024-01-04 | 2024-04-09 | 67 | 46 | 21 | [20 empty] | 2024-04-11 |  |  |  | EXP | [9 empty] | Conditional Approval |  | No
National Grid | BROCKTON | 582509 | 2302 | 6 | Solar | 07_911W77 | 2024-01-12 13:24 | 2024-01-16 | 64 | 61 | 3 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | WORCESTER | 578609 | 1604 | 6.96 | Solar | 01_10J323 | 2024-01-08 15:49 | 2024-01-09 | 2 | 0 | 2 | 2024-01-11 |  | 66 | 25 | 41 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | SEEKONK | 578325 | 2771 | 10 | Solar | 05_7L4 | 2023-12-15 16:52 | 2023-12-18 | 4 | 3 | 1 | 2023-12-22 | 2024-01-24 | 21 | 0 | 21 | [20 empty] | 2024-01-29 |  | 2025-01-29 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | REHOBOTH | 579230 | 2769 | 19.215 | Solar | 05_7L5 | 2024-01-12 07:54 | 2024-01-16 | 3 | 0 | 3 | 2024-01-19 | 2024-02-14 | 19 | 0 | 19 | [20 empty] | 2024-02-15 |  | 2025-02-25 |  | EXP | [8 empty] | 2024-03-20 | Connected |  | No
National Grid | AYER | 581647 | 1432 | 7.83 | Solar | 01_201W2 | 2024-01-09 08:11 | 2024-01-10 | 5 | 1 | 4 | 2024-01-17 | 2024-02-20 | 24 | 3 | 21 | [20 empty] | 2024-02-23 | 2024-01-03 12:13 | 2025-03-06 |  | EXP | [8 empty] | 2024-04-12 | Connected |  | No
National Grid | HALIFAX | 577395 | 2338 | 6.144 | Solar | 07_912W75 | 2024-01-03 12:13 | 2024-01-04 | 4 | 2 | 2 | 2024-01-09 | 2024-02-12 | 24 | 1 | 23 | [20 empty] | 2024-02-14 | 2023-12-12 12:39 | 2025-02-25 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | LEOMINSTER | 573630 | 1453 | 10 | Solar | 01_207W2 | 2023-12-12 12:39 | 2023-12-13 | 5 | 1 | 4 | 2023-12-20 | 2024-01-24 | 23 | 2 | 21 | [20 empty] | 2024-01-30 |  | 2025-02-12 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | ATTLEBORO | 581408 | 2703 | 25 | Solar | 05_8L3 | 2024-01-04 10:46 | 2024-01-05 | 13 | 12 | 1 | 2024-01-24 | 2024-02-16 | 18 | 0 | 18 | [20 empty] | 2024-02-23 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | No
National Grid | NORTON | 581441 | 2766 | 24.8 | Solar | 05_8L3 | 2024-01-04 11:30 | 2024-01-05 | 1 | 0 | 1 | 2024-01-08 | 2024-02-20 | 31 | 13 | 18 | [20 empty] | 2024-02-23 |  | 2025-04-01 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | ATTLEBORO | 556357 | 2703 | 199.8 | Solar | 05_9L1 | 2024-01-08 16:22 | 2024-01-09 | 36 | 35 | 1 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | BROCKTON | 576220 | 2302 | 2.32 | Solar | 07_91W43 | 2023-12-20 10:31 | 2023-12-21 | 1 | 1 | 0 | 2023-12-26 | 2024-01-31 | 25 | 0 | 25 | [21 empty] | 2023-12-26 11:34 |  |  | EXP | [9 empty] | Pending Withdraw |  | No
National Grid | SEEKONK | 579428 | 2771 | 6.09 | Solar | 05_9L5 | 2023-12-26 11:34 | 2023-12-27 | 4 | 0 | 4 | 2024-01-03 | 2024-02-21 | 35 | 15 | 20 | [20 empty] | 2024-02-22 |  | 2025-02-25 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | CLINTON | 577614 | 1510 | 7.6 | Solar | 01_216W1 | 2023-12-28 11:34 | 2023-12-29 | 4 | 0 | 4 | 2024-01-05 | 2024-02-06 | 22 | 0 | 22 | [20 empty] | 2024-02-13 |  | 2025-02-19 |  | EXP | [9 empty] | Meter Installation |  | Yes
National Grid | BROCKTON | 577152 | 2301 | 8.7 | Solar | 07_91W49 | 2023-12-27 16:32 | 2023-12-28 | 4 | 0 | 4 | 2024-01-04 | 2024-02-16 | 32 | 12 | 20 | [20 empty] | 2024-02-21 |  | 2025-03-08 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | NORTH QUINCY | 574216 | 2171 | 7.6 | Solar | 07_11W4 | 2024-01-03 11:04 | 2024-01-04 | 2 | 0 | 2 | 2024-01-08 | 2024-02-20 | 31 | 13 | 18 | [20 empty] | 2024-02-23 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | NORTH EASTON | 580004 | 2356 | 220 | Solar | 07_92W43 | 2023-12-29 15:02 | 2024-01-02 | 13 | 7 | 6 | [10 empty] | 2024-01-19 | 2024-02-13 | 18 | 0 | 18 | [14 empty] | STD | [9 empty] | Group Study |  | Yes
National Grid | EASTON | 574910 | 2356 | 90 | Solar | 07_92W44 | 2024-01-09 07:51 | 2024-01-10 | 65 | 56 | 9 | 2024-04-12 |  | 2 | 0 | 2 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | ROCKLAND | 577762 | 2370 | 4999.2 | Other | 07_93W40 | 2023-12-21 15:53 | 2023-12-22 | 39 | 30 | 9 | [10 empty] | 2024-02-22 | 2024-02-27 | 4 | 0 | 4 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | ABINGTON | 577755 | 2351 | 4999.2 | Other | 07_93W42 | 2023-12-21 15:44 | 2023-12-22 | 39 | 30 | 9 | [10 empty] | 2024-02-22 | 2024-02-27 | 4 | 0 | 4 | [14 empty] | STD | [9 empty] | Group Study |  | Yes
National Grid | WHITMAN | 580263 | 2382 | 9.984 | Solar | 07_93W43 | 2024-01-11 09:48 | 2024-01-12 | 26 | 25 | 1 | 2024-02-20 | 2024-02-27 | 6 | 1 | 5 | [20 empty] | 2024-03-04 |  | 2025-03-14 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | BROCKTON | 572349 | 2301 | 3.8 | Solar | 07_94W40 | 2023-12-11 13:10 | 2023-12-12 | 4 | 3 | 1 | 2023-12-15 | 2024-03-01 | 53 | 30 | 23 | [24 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | RANDOLPH | 574106 | 2368 | 4.35 | Solar | 07_5W3 | 2023-12-13 09:07 | 2023-12-14 | 4 | 1 | 3 | 2023-12-20 | 2024-01-24 | 23 | 2 | 21 | [20 empty] | 2024-01-30 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | ABINGTON | 577766 | 2351 | 4999.2 | Other | 07_99W32 | 2023-12-21 15:55 | 2023-12-22 | 41 | 32 | 9 | [10 empty] | 2024-02-22 | 2024-02-28 | 5 | 0 | 5 | [14 empty] | STD | [9 empty] | Group Study |  | No
National Grid | BROCKTON | 575267 | 2302 | 3.8 | Solar | 07_69J1 | 2023-12-15 11:31 | 2023-12-18 | 2 | 1 | 1 | 2023-12-20 | 2024-01-31 | 28 | 3 | 25 | [21 empty] | 2024-01-12 14:08 |  |  | EXP | [9 empty] | Pending Withdraw |  | No
National Grid | COHASSET | 583288 | 2025 | 21.2 | Battery Add-On | 07_96W41 | 2024-01-12 14:08 | 2024-01-16 | 13 | 10 | 3 | 2024-02-02 | 2024-03-05 | 21 | 11 | 10 | [20 empty] | 2024-03-11 | 2023-12-20 10:04 | 2025-03-29 | Yes | EXP | [9 empty] | Design |  | No
National Grid | RANDOLPH | 575266 | 2368 | 3.19 | Solar | 07_97W1 | 2023-12-20 10:04 | 2023-12-21 | 6 | 1 | 5 | 2024-01-03 | 2024-01-30 | 19 | 0 | 19 | [20 empty] | 2024-02-05 |  | 2025-02-14 | Yes | EXP | [9 empty] | Design |  | No
National Grid | GARDNER | 575195 | 1440 | 5 | Solar | 01_607W5 | 2023-12-14 12:47 | 2023-12-15 | 4 | 2 | 2 | 2023-12-21 | 2024-03-26 | 65 | 41 | 24 | [24 empty] | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | RANDOLPH | 576442 | 2368 | 10 | Solar | 07_97W2 | 2023-12-08 18:05 | 2023-12-11 | 15 | 12 | 3 | 2024-01-02 | 2024-02-22 | 36 | 14 | 22 | [20 empty] | 2024-02-28 |  | 2025-04-04 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | EAST BRIDGEWATER | 581189 | 2333 | 240 | Solar | 07_797W20 | 2024-01-09 11:33 | 2024-01-10 | 4 | 0 | 4 | [10 empty] | 2024-01-17 | 2024-02-13 | 20 | 0 | 20 | [11 empty] | 2023-12-27 16:16 |  |  | STD | [9 empty] | Study |  | Yes
National Grid | UXBRIDGE | 576750 | 1569 | 10 | Solar | 05_320W4 | 2023-12-27 16:16 | 2023-12-28 | 4 | 0 | 4 | 2024-01-04 | 2024-02-06 | 23 | 0 | 23 | [20 empty] | 2024-02-07 |  | 2025-02-26 | Yes | EXP |  | 2024-03-14 | 2024-04-03 | 21 | 0 | 21 |  |  |  | Completion Documents |  | Yes
National Grid | ORANGE | 577357 | 1364 | 19.86 | Battery Add-On | 09_702W2 | 2023-12-12 14:35 | 2023-12-13 | 13 | 11 | 2 | 2024-01-03 | 2024-03-06 | 45 | 25 | 20 | [20 empty] | 2024-04-09 |  | 2025-04-10 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | ORANGE | 577961 | 1364 | 240 | Solar | 09_705W2 | 2023-12-15 16:54 | 2023-12-18 | 13 | 3 | 10 | [10 empty] | 2024-01-05 | 2024-02-08 | 24 | 0 | 24 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | NORTHAMPTON | 581268 | 1060 | 11.5 | Solar | 09_909W2 | 2024-01-11 10:23 | 2024-01-12 | 2 | 0 | 2 | 2024-01-17 | 2024-03-21 | 47 | 25 | 22 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | SAUGUS | 578271 | 1906 | 11.4 | Solar | 12_16W1 | 2023-12-21 12:25 | 2023-12-22 | 5 | 0 | 5 | 2024-01-02 | 2024-01-30 | 20 | 0 | 20 | 2024-04-11 |  | 3 | 0 | 3 | [5 empty] | 2024-04-11 |  | 3 | 0 | 3 | [9 empty] | EXP | [9 empty] | Supplemental Review |  | Yes
National Grid | EVERETT | 580198 | 2149 | 7.25 | Solar | 12_16W2 | 2024-01-09 07:57 | 2024-01-10 | 40 | 40 | 0 | [29 empty] | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | REVERE | 535671 | 2151 | 5 | Solar | 12_16W4 | 2024-01-02 10:44 | 2024-01-03 | 28 | 25 | 3 | [29 empty] | EXP | [9 empty] | Withdrawn |  | No
National Grid | MELROSE | 582518 | 2176 | 10 | Solar | 12_16W6 | 2024-01-12 13:55 | 2024-01-16 | 17 | 14 | 3 | 2024-02-08 | 2024-03-12 | 23 | 14 | 9 | 2024-03-29 |  | 12 | 0 | 12 | [5 empty] | 2024-03-29 |  | 12 | 0 | 12 | [9 empty] | EXP | [9 empty] | Supplemental Review |  | Yes
National Grid | ABINGTON | 577753 | 2351 | 4999.2 | Other | 07_99W62 | 2024-01-04 09:29 | 2024-01-05 | 32 | 25 | 7 | [10 empty] | 2024-02-22 | 2024-02-28 | 5 | 0 | 5 | [14 empty] | STD | [9 empty] | Group Study |  | Yes
National Grid | ROCKLAND | 577761 | 2370 | 4999.2 | Other | 07_99W63 | 2024-01-04 09:26 | 2024-01-05 | 31 | 28 | 3 | [10 empty] | 2024-02-22 | 2024-02-28 | 5 | 0 | 5 | [11 empty] | 2024-01-09 11:04 |  |  | STD | [9 empty] | Group Study |  | No
National Grid | WILLIAMSTOWN | 577992 | 1267 | 7.6 | Solar | 09_1001W1 | 2024-01-09 11:04 | 2024-01-10 | 7 | 4 | 3 | 2024-01-22 | 2024-02-16 | 20 | 1 | 19 | [20 empty] | 2024-02-20 |  | 2025-02-20 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | WILLIAMSTOWN | 578098 | 1267 | 9.57 | Solar | 09_1001W1 | 2024-01-03 10:04 | 2024-01-04 | 5 | 0 | 5 | 2024-01-11 | 2024-04-02 | 58 | 35 | 23 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | GREAT BARRINGTON | 577919 | 1230 | 10 | Solar | 09_1109W2 | 2023-12-15 14:09 | 2023-12-18 | 27 | 22 | 5 | 2024-01-26 | 2024-02-16 | 16 | 0 | 16 | [20 empty] | 2024-02-21 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | EAST LONGMEADOW | 582369 | 1028 | 15.2 | Solar | 09_139L5 | 2024-01-09 11:53 | 2024-01-10 | 14 | 12 | 2 | 2024-01-30 | 2024-02-16 | 14 | 0 | 14 | [20 empty] | 2024-02-22 |  | 2025-03-29 |  | EXP | [8 empty] | 2024-04-03 | Connected |  | No
National Grid | WARE | 573208 | 1082 | 7.6 | Solar | 09_501L2 | 2023-12-12 08:24 | 2023-12-13 | 1 | 0 | 1 | 2023-12-14 | 2024-01-24 | 27 | 3 | 24 | [20 empty] | 2024-02-09 |  | 2025-03-08 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | WARE | 576642 | 1082 | 7.6 | Solar | 09_501L2 | 2024-01-08 08:49 | 2024-01-09 | 6 | 3 | 3 | 2024-01-17 | 2024-02-13 | 20 | 0 | 20 | [20 empty] | 2024-02-15 |  | 2025-03-01 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | PALMER | 573402 | 1069 | 9.765 | Solar | 09_503L4 | 2023-12-27 04:23 | 2023-12-28 | 6 | 5 | 1 | 2024-01-05 | 2024-03-25 | 56 | 35 | 21 | [21 empty] | 2023-12-11 12:32 |  |  | EXP | [9 empty] | Screening |  | Yes
National Grid | WILBRAHAM | 572302 | 1095 | 6.67 | Solar | 09_507L3 | 2023-12-11 12:32 | 2023-12-12 | 3 | 2 | 1 | 2023-12-15 | 2024-01-31 | 31 | 9 | 22 | [20 empty] | 2024-02-05 |  | 2025-03-04 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | EAST LONGMEADOW | 567652 | 1028 | 10 | Solar | 09_508L1 | 2023-12-27 09:09 | 2023-12-28 | 6 | 2 | 4 | 2024-01-08 | 2024-02-15 | 28 | 3 | 25 | [20 empty] | 2024-02-20 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | EAST LONGMEADOW | 577364 | 1028 | 8.832 | Solar | 09_508L2 | 2023-12-13 09:58 | 2023-12-14 | 26 | 24 | 2 | 2024-01-24 | 2024-03-11 | 34 | 16 | 18 | [20 empty] | 2024-03-15 |  | 2025-04-05 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | BELCHERTOWN | 580279 | 1007 | 5.04 | Solar | 09_509L2 | 2023-12-28 11:30 | 2023-12-29 | 35 | 33 | 2 | 2024-02-21 | 2024-04-01 | 30 | 25 | 5 | [24 empty] | EXP | [9 empty] | Screening |  | No
National Grid | FALL RIVER | 580271 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-29 | [28 empty] | 2021-04-23 |  | 2024-05-02 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 580274 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-30 | [28 empty] | 2021-04-23 |  | 2024-05-03 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 580282 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-29 | [28 empty] | 2021-04-23 |  | 2024-05-01 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 580288 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-29 | [28 empty] | 2021-04-23 |  | 2024-05-06 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 580253 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-29 | [28 empty] | 2021-04-23 |  | 2024-05-03 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 580387 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-29 | [28 empty] | 2021-04-23 |  | 2024-05-01 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 580430 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-29 | [28 empty] | 2021-04-23 |  | 2024-03-15 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 580284 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-29 | [28 empty] | 2021-04-23 |  | 2024-05-02 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 580320 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-29 | [28 empty] | 2021-04-23 |  | 2024-05-03 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 580326 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-29 | [28 empty] | 2021-04-23 |  | 2024-05-03 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 580393 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-29 | [28 empty] | 2021-04-23 |  | 2024-05-01 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 580262 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-29 | [28 empty] | 2021-04-23 |  | 2024-04-25 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 580242 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-29 | [28 empty] | 2021-04-23 |  | 2024-04-25 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 580402 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-29 | [28 empty] | 2021-04-23 |  | 2024-05-01 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 580229 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-29 | [28 empty] | 2021-04-23 |  | 2024-05-02 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 580361 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-29 | [28 empty] | 2021-04-23 |  | 2024-05-01 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 580349 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-30 | [28 empty] | 2021-04-23 |  | 2025-03-14 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 580341 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-29 | [28 empty] | 2021-04-23 |  | 2024-05-02 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 580264 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-29 | [28 empty] | 2021-04-23 |  | 2024-05-01 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 580432 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-29 | [28 empty] | 2021-04-23 |  | 2024-05-01 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 580359 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-29 | [28 empty] | 2021-04-23 |  | 2024-05-01 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 580358 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-29 | [28 empty] | 2021-04-23 |  | 2025-01-25 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 580410 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-29 | [28 empty] | 2021-04-23 |  | 2024-05-01 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 580298 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-29 | [28 empty] | 2021-04-23 |  | 2024-05-06 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 580245 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-29 | [28 empty] | 2021-04-23 |  | 2024-05-03 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 580235 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-29 | [28 empty] | 2021-04-23 |  | 2024-05-21 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 580347 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-29 | [28 empty] | 2021-04-23 |  | 2024-05-01 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 580426 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-29 | [28 empty] | 2021-04-23 |  | 2024-05-01 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 580300 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-29 | [28 empty] | 2021-04-23 |  | 2024-05-03 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 580408 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-29 | [28 empty] | 2021-04-23 |  | 2025-01-25 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 580423 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-29 | [28 empty] | 2021-04-23 |  | 2025-03-13 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 580435 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-29 | [28 empty] | 2021-04-23 |  | 2025-01-25 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | FALL RIVER | 580366 | 2720 | 25 | Solar | 05_28W51 | 2020-05-18 07:59 | 2023-12-29 | [28 empty] | 2021-04-23 |  | 2024-05-01 |  | STD | [9 empty] | Completion Documents |  | No
National Grid | WORCESTER | 581603 | 1604 | 10 | Solar | 01_27W5 | 2024-01-19 13:20 | 2024-01-22 | 2 | 0 | 2 | 2024-01-24 | 2024-02-16 | 19 | 2 | 17 | [20 empty] | 2024-02-21 |  | 2025-04-01 |  | EXP | [8 empty] | 2024-04-15 | Connected |  | Yes
National Grid | FALL RIVER | 581883 | 2720 | 100 | Solar | 05_28W51 | 2024-01-19 21:08 | 2024-01-22 | 13 | 3 | 10 | [10 empty] | 2024-02-09 | 2024-02-21 | 8 | 0 | 8 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | LOWELL | 583375 | 1852 | 10 | Solar | 14_20L3 | 2024-01-26 12:18 | 2024-01-29 | 2 | 0 | 2 | 2024-01-31 | 2024-04-05 | 48 | 35 | 13 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | LOWELL | 580543 | 1852 | 300 | Solar | 14_20L3 | 2024-01-16 09:56 | 2024-01-17 | 23 | 13 | 10 | [10 empty] | 2024-02-20 | 2024-03-25 | 26 | 22 | 4 | [11 empty] | 2024-01-26 13:00 |  |  | STD | [9 empty] | Study |  | No
National Grid | DRACUT | 585135 | 1826 | 10 | Solar | 14_75L2 | 2024-01-26 13:00 | 2024-01-29 | 12 | 11 | 1 | 2024-02-14 | 2024-02-22 | 7 | 1 | 6 | [20 empty] | 2024-02-27 |  | 2025-03-01 |  | EXP | [9 empty] | Design |  | Yes
National Grid | WEST MARLBOROUGH | 586186 | 1752 | 150 | Solar | 05_311W1 | 2024-02-01 12:52 | 2024-02-02 | 37 | 28 | 9 | 2024-03-26 | 2024-04-08 | 10 | 0 | 10 | [21 empty] | 2024-01-23 14:54 |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | MARLBOROUGH | 581937 | 1752 | 5.376 | Solar | 05_311W2 | 2024-01-23 14:54 | 2024-01-24 | 11 | 10 | 1 | 2024-02-07 | 2024-02-20 | 9 | 0 | 9 | [20 empty] | 2024-02-23 |  | 2025-03-14 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | MILLBURY | 575814 | 1527 | 4948 | Solar | 01_304W5 | 2024-01-23 12:59 | 2024-01-24 | 35 | 25 | 10 | [10 empty] | 2024-03-15 | 2024-04-11 | 21 | 16 | 5 | [14 empty] | STD | [9 empty] | Study |  | No
National Grid | MARLBOROUGH | 584824 | 1752 | 7.6 | Solar | 05_311W3 | 2024-01-22 14:58 | 2024-01-23 | 3 | 0 | 3 | 2024-01-26 | 2024-02-16 | 16 | 0 | 16 | [20 empty] | 2024-02-22 | 2024-01-19 12:44 |  |  | EXP | [9 empty] | Pending Withdraw |  | No
National Grid | SALEM | 583402 | 1970 | 10 | Solar | 12_29W2 | 2024-01-19 12:44 | 2024-01-22 | 18 | 16 | 2 | 2024-02-14 | 2024-02-22 | 6 | 0 | 6 | [20 empty] | 2024-02-27 |  | 2025-03-01 |  | EXP | [9 empty] | Design |  | Yes
National Grid | LYNN | 585391 | 1905 | 2.03 | Solar | 12_29W3 | 2024-01-29 15:00 | 2024-01-30 | 1 | 0 | 1 | 2024-01-31 | 2024-03-01 | 23 | 10 | 13 | [20 empty] | 2024-03-04 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | LOWELL | 579700 | 1854 | 6 | Solar | 14_77L1 | 2024-01-24 17:52 | 2024-01-25 | 4 | 0 | 4 | 2024-01-31 | 2024-02-16 | 13 | 0 | 13 | [20 empty] | 2024-02-21 |  | 2025-03-04 |  | EXP | [9 empty] | Meter Installation |  | Yes
National Grid | WEST NEWBURY | 550096 | 1985 | 9.984 | Solar | 14_47L2 | 2024-01-10 07:50 | 2024-01-23 | 0 | 0 | 0 | 2024-01-23 | 2024-02-15 | 19 | 1 | 18 | [20 empty] | 2024-02-21 |  | 2025-02-21 |  | EXP | [8 empty] | 2024-02-28 | Connected |  | No
National Grid | LOWELL | 583929 | 1854 | 5.22 | Solar | 14_77L3 | 2024-02-01 11:05 | 2024-02-02 | 3 | 0 | 3 | 2024-02-07 | 2024-02-23 | 12 | 0 | 12 | 2024-03-29 |  | 12 | 0 | 12 | [5 empty] | 2024-03-29 |  | 12 | 0 | 12 | [5 empty] | 2024-04-11 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LOWELL | 576999 | 1854 | 5.51 | Solar | 14_77L3 | 2024-01-16 11:27 | 2024-01-17 | 2 | 0 | 2 | 2024-01-19 | 2024-02-15 | 20 | 0 | 20 | 2024-03-22 |  | 17 | 0 | 17 | [5 empty] | 2024-03-22 |  | 17 | 0 | 17 | [5 empty] | 2024-04-11 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | HAVERHILL | 586282 | 1830 | 15.2 | Solar | 14_48L2 | 2024-01-31 12:26 | 2024-02-01 | 13 | 10 | 3 | 2024-02-21 | 2024-02-27 | 5 | 0 | 5 | [20 empty] | 2024-03-04 |  | 2025-04-04 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | ANDOVER | 582479 | 1810 | 6 | Solar | 14_50L1 | 2024-02-01 11:59 | 2024-02-02 | 3 | 0 | 3 | 2024-02-07 | 2024-02-21 | 10 | 0 | 10 | [20 empty] | 2024-02-26 |  | 2025-04-12 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | WESTBOROUGH | 582654 | 1851 | 17.32 | Solar | 05_312W3 | 2024-02-02 13:48 | 2024-02-05 | 34 | 32 | 2 | 2024-03-22 |  | 17 | 15 | 2 | [24 empty] | EXP | [9 empty] | Screening |  | No
National Grid | NORTHBOROUGH | 584740 | 1532 | 9.28 | Solar | 05_313W1 | 2024-01-23 09:56 | 2024-01-24 | 6 | 5 | 1 | 2024-01-31 | 2024-02-16 | 13 | 0 | 13 | [20 empty] | 2024-02-23 |  | 2025-03-08 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | ANDOVER | 584528 | 1810 | 11.4 | Solar | 14_8L1 | 2024-02-01 17:09 | 2024-02-02 | 8 | 6 | 2 | 2024-02-13 | 2024-02-22 | 7 | 0 | 7 | [20 empty] | 2024-02-28 |  | 2025-03-25 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | WINCHENDON | 581103 | 1475 | 7.6 | Solar | 01_612W3 | 2024-01-25 14:44 | 2024-01-26 | 3 | 1 | 2 | 2024-01-30 | 2024-02-21 | 16 | 2 | 14 | [20 empty] | 2024-02-23 |  | 2025-03-01 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | OXFORD | 579324 | 1540 | 1.45 | Solar | 01_406L4 | 2024-02-01 17:52 | 2024-02-02 | 27 | 25 | 2 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | OXFORD | 585919 | 1540 | 23.4 | Solar | 01_406L4 | 2024-01-31 12:39 | 2024-02-01 | 16 | 14 | 2 | 2024-02-26 | 2024-04-09 | 32 | 29 | 3 | [20 empty] | 2024-04-15 | 2024-02-01 11:31 |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LAWRENCE | 582651 | 1841 | 5.22 | Solar | 14_8L2 | 2024-02-01 11:31 | 2024-02-02 | 3 | 0 | 3 | 2024-02-07 | 2024-02-22 | 11 | 0 | 11 | [20 empty] | 2024-02-28 |  | 2025-03-08 | Yes | EXP |  | 2024-04-16 |  | 0 | 0 | 0 |  |  |  | Construction |  | Yes
National Grid | LYNN | 584871 | 1902 | 7.6 | Solar | 12_3J903 | 2024-02-01 17:20 | 2024-02-02 | 12 | 10 | 2 | 2024-02-20 | 2024-02-22 | 3 | 0 | 3 | [20 empty] | 2024-02-27 |  | 2025-03-08 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | WORCESTER | 581993 | 1603 | 9.86 | Solar | 01_6W2 | 2024-01-22 16:12 | 2024-01-23 | 1 | 0 | 1 | 2024-01-24 | 2024-02-15 | 17 | 0 | 17 | [20 empty] | 2024-02-15 | 2024-01-22 11:43 |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | WEBSTER | 576129 | 1570 | 11.4 | Solar | 01_412L1 | 2024-01-22 11:43 | 2024-01-23 | 21 | 19 | 2 | 2024-02-22 | 2024-02-26 | 3 | 0 | 3 | [20 empty] | 2024-02-29 |  | 2025-03-29 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | WORCESTER | 578629 | 1604 | 299 | Solar | 01_9J303 | 2024-01-29 10:47 | 2024-01-30 | 54 | 25 | 29 | [29 empty] | STD | [9 empty] | Application |  | No
National Grid | DUDLEY | 574933 | 1571 | 499 | Solar | 01_412L4 | 2024-01-19 17:17 | 2024-01-22 | 34 | 25 | 9 | [29 empty] | STD | [9 empty] | Pending Withdraw |  | Yes
National Grid | BOLTON | 570119 | 1740 | 9.45 | Solar | 01_216W6 | 2024-01-31 18:05 | 2024-02-01 | 4 | 1 | 3 | 2024-02-07 | 2024-02-29 | 16 | 7 | 9 | [20 empty] | 2024-03-05 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | BOLTON | 582976 | 1740 | 8.775 | Solar | 01_216W6 | 2024-01-29 12:24 | 2024-01-30 | 9 | 8 | 1 | 2024-02-09 | 2024-02-21 | 8 | 0 | 8 | [20 empty] | 2024-02-23 | 2024-01-18 13:46 | 2025-03-05 |  | EXP | [8 empty] | 2024-04-02 | Connected |  | No
National Grid | CHELMSFORD | 579860 | 1824 | 7.875 | Solar | 14_58L2 | 2024-01-18 13:46 | 2024-01-19 | 11 | 9 | 2 | 2024-02-02 | 2024-02-21 | 13 | 0 | 13 | [20 empty] | 2024-02-27 |  | 2025-02-26 | Yes | EXP |  | 2024-03-20 | 2024-04-09 | 21 | 0 | 21 |  |  | 2024-04-12 | Connected |  | Yes
National Grid | FALL RIVER | 580036 | 2723 | 6 | Solar | 05_106W82 | 2024-02-02 11:16 | 2024-02-05 | 2 | 0 | 2 | 2024-02-07 | 2024-02-21 | 10 | 0 | 10 | [20 empty] | 2024-02-26 |  | 2025-03-04 |  | EXP | [9 empty] | Conditional Approval |  | No
National Grid | TEWKSBURY | 585728 | 1876 | 17.6 | Solar | 14_59L3 | 2024-01-26 07:40 | 2024-01-29 | 5 | 3 | 2 | 2024-02-02 | 2024-02-20 | 12 | 0 | 12 | [20 empty] | 2024-02-26 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | No
National Grid | ANDOVER | 586370 | 1810 | 2890 | Battery Add-On | 14_59L5 | 2024-02-01 15:09 | 2024-02-02 | 51 | 25 | 26 | [29 empty] | STD | [9 empty] | Application |  | Yes
National Grid | ANDOVER | 587585 | 1810 | 23 | Solar | 14_59L5 | 2024-02-02 14:43 | 2024-02-05 | 27 | 25 | 2 | [29 empty] | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | METHUEN | 574631 | 1844 | 6.38 | Solar | 14_5J40 | 2024-01-23 09:06 | 2024-01-24 | 4 | 0 | 4 | 2024-01-30 | 2024-03-22 | 39 | 25 | 14 | [21 empty] | 2024-01-29 13:51 |  |  | EXP | [9 empty] | Screening |  | Yes
National Grid | REVERE | 583707 | 2151 | 7.6 | Solar | 12_7J2 | 2024-01-29 13:51 | 2024-01-30 | 5 | 4 | 1 | 2024-02-05 | 2024-02-20 | 11 | 0 | 11 | [20 empty] | 2024-02-23 |  | 2025-03-08 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | LAWRENCE | 579602 | 1843 | 8.7 | Solar | 14_61L2 | 2024-01-23 11:51 | 2024-01-24 | 2 | 0 | 2 | 2024-01-26 | 2024-02-20 | 18 | 3 | 15 | [20 empty] | 2024-02-26 | 2024-01-22 14:36 | 2025-03-13 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LAWRENCE | 583839 | 1843 | 4.06 | Solar | 14_61L2 | 2024-01-22 14:36 | 2024-01-23 | 3 | 0 | 3 | 2024-01-26 | 2024-02-16 | 16 | 0 | 16 | [20 empty] | 2024-02-21 |  | 2025-03-27 | Yes | EXP |  | 2024-04-16 |  | 0 | 0 | 0 |  |  |  | Construction |  | Yes
National Grid | LANCASTER | 587327 | 1523 | 19 | Solar | 01_225W3 | 2024-02-01 16:07 | 2024-02-02 | 3 | 1 | 2 | 2024-02-07 | 2024-02-21 | 10 | 0 | 10 | [20 empty] | 2024-02-26 |  | 2025-02-25 |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FALL RIVER | 582671 | 2724 | 1.74 | Solar | 05_115W55 | 2024-01-26 09:39 | 2024-01-29 | 2 | 0 | 2 | 2024-01-31 | 2024-03-18 | 34 | 21 | 13 | [20 empty] | 2024-03-19 |  | 2025-04-09 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | LOWELL | 580139 | 1852 | 200 | Solar | 14_13L1 | 2024-01-15 14:16 | 2024-01-16 | 64 | 25 | 39 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | MENDON | 581970 | 1756 | 7.6 | Solar | 05_332W1 | 2024-01-24 17:16 | 2024-01-25 | 4 | 3 | 1 | 2024-01-30 | 2024-03-15 | 33 | 20 | 13 | [20 empty] | 2024-03-18 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | BRADFORD | 586417 | 1835 | 17.08 | Battery Add-On | 14_65L3 | 2024-01-30 11:23 | 2024-01-31 | 12 | 9 | 3 | 2024-02-16 | 2024-03-07 | 14 | 9 | 5 | [20 empty] | 2024-03-14 |  | 2025-03-21 |  | EXP | [9 empty] | Conditional Approval |  | No
National Grid | LAWRENCE | 582362 | 1841 | 2.9 | Solar | 14_6J2 | 2024-01-17 11:30 | 2024-01-18 | 2 | 0 | 2 | 2024-01-22 |  | 60 | 41 | 19 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | TYNGSBOROUGH | 583467 | 1879 | 10 | Solar | 14_211L1 | 2024-01-15 10:24 | 2024-01-16 | 37 | 28 | 9 | 2024-03-08 | 2024-03-15 | 6 | 3 | 3 | [20 empty] | 2024-03-21 |  | 2025-03-21 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | NORTH BILLERICA | 578847 | 1862 | 10 | Solar | 14_70L1 | 2024-01-22 09:31 | 2024-01-23 | 2 | 0 | 2 | 2024-01-25 | 2024-02-16 | 17 | 0 | 17 | [20 empty] | 2024-02-22 | 2024-01-16 11:50 | 2025-03-12 |  | EXP | [8 empty] | 2024-04-02 | Connected |  | No
National Grid | DIGHTON | 580411 | 2715 | 3.8 | Solar | 05_19W73 | 2024-01-16 11:50 | 2024-01-17 | 3 | 0 | 3 | 2024-01-22 | 2024-02-14 | 19 | 2 | 17 | [20 empty] | 2024-02-15 |  | 2025-02-20 | Yes | EXP | [9 empty] | Construction |  | No
National Grid | MILFORD | 579839 | 1757 | 1.74 | Solar | 05_335W5 | 2024-01-17 18:01 | 2024-01-18 | 4 | 0 | 4 | 2024-01-24 | 2024-03-01 | 28 | 13 | 15 | [20 empty] | 2024-03-05 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | No
National Grid | MILFORD | 586068 | 1757 | 25.2 | Battery Add-On | 05_335W5 | 2024-01-29 10:21 | 2024-01-30 | 6 | 3 | 3 | 2024-02-06 | 2024-02-20 | 10 | 0 | 10 | [20 empty] | 2024-02-26 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | No
National Grid | RUTLAND | 584251 | 1543 | 3.8 | Solar | 01_55W1 | 2024-02-01 12:26 | 2024-02-02 | 2 | 0 | 2 | 2024-02-06 | 2024-02-21 | 11 | 0 | 11 | [20 empty] | 2024-02-26 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | MILFORD | 529975 | 1757 | 1000 | Solar | 05_336W2 | 2024-01-29 10:40 | 2024-01-30 | 53 | 44 | 9 | [29 empty] | STD | [9 empty] | Application |  | Yes
National Grid | MILFORD | 581882 | 1757 | 240 | Solar | 05_336W2 | 2024-01-19 20:11 | 2024-01-22 | 13 | 3 | 10 | [10 empty] | 2024-02-09 | 2024-02-21 | 8 | 0 | 8 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | AUBURN | 581921 | 1501 | 6.38 | Solar | 01_26W1 | 2024-01-23 12:40 | 2024-01-24 | 4 | 0 | 4 | 2024-01-30 | 2024-02-21 | 16 | 0 | 16 | [20 empty] | 2024-02-26 |  | 2025-03-06 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | CHELMSFORD | 580798 | 1824 | 9.765 | Solar | 14_73L1 | 2024-01-23 14:32 | 2024-01-24 | 4 | 1 | 3 | 2024-01-29 | 2024-02-16 | 15 | 0 | 15 | [20 empty] | 2024-02-22 |  | 2025-03-24 |  | EXP | [8 empty] | 2024-04-15 | Connected |  | Yes
National Grid | BRIDGEWATER | 578968 | 2324 | 10 | Solar | 07_797W1 | 2024-01-18 15:41 | 2024-01-19 | 3 | 0 | 3 | 2024-01-24 | 2024-04-03 | 50 | 33 | 17 | [20 empty] | 2024-04-10 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | NORWELL | 586854 | 2061 | 25 | Battery Add-On | 07_96W44 | 2024-01-31 13:37 | 2024-02-01 | 13 | 11 | 2 | 2024-02-21 | 2024-02-29 | 7 | 0 | 7 | [20 empty] | 2024-03-05 |  | 2025-03-06 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | NORTH CHELMSFORD | 582189 | 1863 | 100 | Solar | 14_2L4 | 2024-01-19 22:50 | 2024-01-22 | 14 | 4 | 10 | 2024-02-12 | 2024-02-22 | 8 | 0 | 8 | [24 empty] | EXP | [9 empty] | Study |  | Yes
National Grid | EAST BRIDGEWATER | 572096 | 2333 | 13.05 | Solar | 07_797W23 | 2024-01-22 14:25 | 2024-01-23 | 6 | 4 | 2 | 2024-01-30 | 2024-02-16 | 14 | 0 | 14 | [20 empty] | 2024-02-23 |  | 2025-03-01 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | EAST BRIDGEWATER | 586841 | 2333 | 15.2 | Solar | 07_797W23 | 2024-01-31 12:58 | 2024-02-01 | 17 | 15 | 2 | 2024-02-27 | 2024-03-04 | 5 | 0 | 5 | [20 empty] | 2024-03-06 |  | 2025-03-11 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | RANDOLPH | 580555 | 2368 | 4.64 | Solar | 07_97W2 | 2024-01-12 17:06 | 2024-01-16 | 3 | 0 | 3 | 2024-01-19 | 2024-02-15 | 20 | 0 | 20 | [20 empty] | 2024-02-21 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | RANDOLPH | 581836 | 2368 | 5.51 | Solar | 07_97W2 | 2024-01-19 17:04 | 2024-01-22 | 1 | 0 | 1 | 2024-01-23 | 2024-02-16 | 19 | 0 | 19 | [20 empty] | 2024-02-20 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | FOXBOROUGH | 583853 | 2035 | 11.5 | Solar | 05_3424W1 | 2024-02-01 11:10 | 2024-02-02 | 5 | 3 | 2 | 2024-02-09 | 2024-02-23 | 10 | 0 | 10 | [20 empty] | 2024-02-29 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | REVERE | 581875 | 2151 | 100 | Solar | 12_16W4 | 2024-01-19 21:47 | 2024-01-22 | 13 | 3 | 10 | [10 empty] | 2024-02-09 | 2024-02-21 | 8 | 0 | 8 | [14 empty] | STD | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 582426 | 2301 | 10 | Solar | 07_911W13 | 2024-02-01 15:03 | 2024-02-02 | 25 | 24 | 1 | 2024-03-08 |  | 27 | 21 | 6 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | BROCKTON | 582938 | 2301 | 5.8 | Solar | 07_911W25 | 2024-02-01 11:12 | 2024-02-02 | 3 | 0 | 3 | 2024-02-07 | 2024-02-21 | 10 | 0 | 10 | [20 empty] | 2024-02-26 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | FRANKLIN | 582192 | 2038 | 75 | Solar | 05_348W6 | 2024-01-23 12:53 | 2024-01-24 | 13 | 3 | 10 | [10 empty] | 2024-02-12 | 2024-02-22 | 8 | 0 | 8 | [11 empty] | 2024-01-19 16:51 |  |  | STD | [9 empty] | Group Study |  | Yes
National Grid | BROCKTON | 583692 | 2302 | 7.6 | Solar | 07_911W56 | 2024-01-19 16:51 | 2024-01-22 | 10 | 8 | 2 | 2024-02-05 | 2024-02-20 | 11 | 0 | 11 | [20 empty] | 2024-02-23 |  | 2025-03-15 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | BROCKTON | 582602 | 2302 | 13.44 | Solar | 07_911W56 | 2024-01-18 13:27 | 2024-01-19 | 6 | 3 | 3 | 2024-01-26 | 2024-02-16 | 16 | 0 | 16 | [20 empty] | 2024-02-20 | 2024-01-15 07:52 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | LEOMINSTER | 575385 | 1453 | 2.32 | Solar | 01_207W6 | 2024-01-15 07:52 | 2024-01-16 | 8 | 5 | 3 | 2024-01-25 | 2024-02-14 | 15 | 0 | 15 | [20 empty] | 2024-02-21 | 2024-01-24 13:29 | 2025-03-06 | Yes | EXP | [9 empty] | Design |  | No
National Grid | BROCKTON | 564420 | 2302 | 9.765 | Solar | 07_91W43 | 2024-01-24 13:29 | 2024-01-25 | 2 | 1 | 1 | 2024-01-26 | 2024-02-16 | 16 | 0 | 16 | [20 empty] | 2024-02-21 |  | 2025-03-08 | Yes | EXP |  | 2024-04-10 |  | 6 | 0 | 6 |  |  |  | Construction |  | Yes
National Grid | BROCKTON | 578958 | 2301 | 7.6 | Solar | 07_91W43 | 2024-01-31 14:48 | 2024-02-01 | 1 | 0 | 1 | 2024-02-02 | 2024-02-20 | 12 | 0 | 12 | [20 empty] | 2024-02-21 | 2024-01-23 14:18 | 2025-02-22 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | BROCKTON | 580600 | 2302 | 9.765 | Solar | 07_91W43 | 2024-01-23 14:18 | 2024-01-24 | 1 | 0 | 1 | 2024-01-25 | 2024-02-16 | 18 | 2 | 16 | [20 empty] | 2024-02-20 |  | 2025-03-04 | Yes | EXP |  | 2024-03-26 |  | 21 | 0 | 21 |  |  |  | Construction |  | Yes
National Grid | BROCKTON | 584131 | 2301 | 10 | Solar | 07_91W49 | 2024-01-24 14:14 | 2024-01-25 | 28 | 26 | 2 | 2024-03-06 | 2024-03-22 | 14 | 12 | 2 | [20 empty] | 2024-04-01 |  | 2025-04-15 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | GRAFTON | 586889 | 1519 | 15.2 | Solar | 01_304W1 | 2024-02-02 12:49 | 2024-02-05 | 11 | 10 | 1 | 2024-02-20 | 2024-02-26 | 5 | 0 | 5 | [20 empty] | 2024-02-29 |  | 2025-03-11 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | SOUTH EASTON | 585541 | 2375 | 19.35 | Solar | 07_92W79 | 2024-01-31 01:55 | 2024-02-01 | 12 | 10 | 2 | 2024-02-20 |  | 40 | 35 | 5 | [21 empty] | 2024-01-24 14:00 |  |  | EXP | [9 empty] | Screening |  | No
National Grid | HOLBROOK | 585200 | 2343 | 6.09 | Solar | 07_2W1 | 2024-01-24 14:00 | 2024-01-25 | 4 | 0 | 4 | 2024-01-31 | 2024-02-23 | 17 | 4 | 13 | [20 empty] | 2024-02-28 |  | 2025-03-08 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | HOLBROOK | 585093 | 2343 | 22 | Solar | 07_2W1 | 2024-01-23 14:50 | 2024-01-24 | 1 | 0 | 1 | 2024-01-25 | 2024-02-14 | 15 | 0 | 15 | [20 empty] | 2024-02-15 |  |  |  | EXP | [9 empty] | Conditional Approval |  | No
National Grid | WHITMAN | 577969 | 2382 | 9.5 | Solar | 07_93W43 | 2024-01-24 12:47 | 2024-01-25 | 2 | 0 | 2 | 2024-01-29 | 2024-03-26 | 42 | 27 | 15 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | STOUGHTON | 556459 | 2072 | 7086 | Solar | 07_94W44 | 2024-01-30 16:03 | 2024-01-31 | 52 | 43 | 9 | [29 empty] | STD | [9 empty] | Application |  | No
National Grid | RANDOLPH | 581941 | 2368 | 8.12 | Solar | 07_5W4 | 2024-02-01 16:20 | 2024-02-02 | 26 | 25 | 1 | 2024-03-15 | 2024-03-20 | 4 | 0 | 4 | [20 empty] | 2024-03-21 |  | 2025-03-22 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | BROCKTON | 584083 | 2302 | 10.15 | Solar | 07_69J1 | 2024-01-19 12:51 | 2024-01-22 | 27 | 18 | 9 | 2024-02-29 | 2024-03-07 | 7 | 4 | 3 | [20 empty] | 2024-03-12 |  | 2025-03-19 |  | EXP | [9 empty] | Conditional Approval |  | No
National Grid | AVON | 579567 | 2322 | 4.35 | Solar | 07_75W3 | 2024-01-18 11:53 | 2024-01-19 | 1 | 0 | 1 | 2024-01-22 | 2024-02-12 | 16 | 0 | 16 | [20 empty] | 2024-02-15 |  | 2025-02-20 |  | EXP | [8 empty] | 2024-03-09 | Connected |  | No
National Grid | NORWELL | 583818 | 2061 | 21.735 | Solar | 07_96W43 | 2024-01-19 12:50 | 2024-01-22 | 18 | 16 | 2 | 2024-02-14 | 2024-02-21 | 5 | 0 | 5 | [20 empty] | 2024-02-26 |  | 2025-02-28 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | THREE RIVERS | 584933 | 1080 | 7.6 | Solar | 09_523L1 | 2024-01-30 12:48 | 2024-01-31 | 27 | 25 | 2 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | BELCHERTOWN | 583851 | 1007 | 15.66 | Solar | 09_527L1 | 2024-01-16 17:10 | 2024-01-17 | 2 | 0 | 2 | 2024-01-19 | 2024-02-14 | 19 | 0 | 19 | [20 empty] | 2024-02-21 |  | 2025-02-25 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | ATHOL | 577497 | 1331 | 7.6 | Solar | 09_702W1 | 2024-01-31 17:39 | 2024-02-01 | 5 | 3 | 2 | 2024-02-08 | 2024-02-21 | 9 | 0 | 9 | [20 empty] | 2024-02-23 |  | 2025-03-04 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | SHUTESBURY | 582306 | 1072 | 10 | Solar | 09_704W1 | 2024-01-22 16:09 | 2024-01-23 | 3 | 0 | 3 | 2024-01-26 | 2024-02-15 | 15 | 0 | 15 | [20 empty] | 2024-02-21 |  | 2025-03-04 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LEEDS | 585251 | 1053 | 7.6 | Solar | 09_909W3 | 2024-02-02 10:01 | 2024-02-05 | 10 | 9 | 1 | 2024-02-20 | 2024-02-27 | 7 | 3 | 4 | [24 empty] | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | WILLIAMSBURG | 587581 | 1096 | 15.2 | Solar | 09_909W3 | 2024-02-02 14:34 | 2024-02-05 | 2 | 1 | 1 | 2024-02-07 | 2024-02-21 | 10 | 0 | 10 | [20 empty] | 2024-02-23 |  | 2025-03-01 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | BEVERLY | 586184 | 1915 | 25 | Solar | 12_12J5 | 2024-01-30 09:29 | 2024-01-31 | 7 | 5 | 2 | 2024-02-08 | 2024-02-22 | 10 | 0 | 10 | 2024-02-27 | 2024-04-03 | 26 | 0 | 26 | [5 empty] | 2024-02-27 | 2024-04-03 | 26 | 0 | 26 | [5 empty] | 2024-04-03 |  | 2025-04-03 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | BROCKTON | 447289 | 2301 | 6 | Solar | 07_98W19 | 2024-01-29 12:28 | 2024-01-30 | 8 | 4 | 4 | 2024-02-09 | 2024-02-22 | 9 | 0 | 9 | [20 empty] | 2022-08-16 | 2024-01-26 12:40 |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | WARE | 585404 | 1082 | 11.4 | Solar | 09_501L2 | 2024-01-26 12:40 | 2024-01-29 | 42 | 41 | 1 | 2024-03-28 | 2024-03-29 | 2 | 0 | 2 | [20 empty] | 2024-04-02 |  | 2025-04-04 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | PALMER | 579915 | 1069 | 7.6 | Solar | 09_503L1 | 2024-01-18 13:44 | 2024-01-19 | 3 | 0 | 3 | 2024-01-24 | 2024-03-20 | 41 | 25 | 16 | [21 empty] | 2024-01-24 12:05 |  |  | EXP | [9 empty] | Screening |  | Yes
National Grid | EAST LONGMEADOW | 581722 | 1028 | 3.8 | Solar | 09_508L1 | 2024-01-24 12:05 | 2024-01-25 | 4 | 0 | 4 | 2024-01-31 | 2024-02-21 | 15 | 0 | 15 | [20 empty] | 2024-02-22 |  | 2025-02-28 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | BELCHERTOWN | 581714 | 1007 | 10 | Solar | 09_509L1 | 2024-01-17 08:36 | 2024-01-18 | 5 | 3 | 2 | 2024-01-25 | 2024-02-26 | 22 | 6 | 16 | [20 empty] | 2024-03-01 |  | 2025-03-06 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | LYNN | 592974 | 1904 | 10.73 | Solar | 12_24W1 | 2024-03-06 15:22 | 2024-03-07 | 12 | 8 | 4 | 2024-03-22 | 2024-03-27 | 4 | 0 | 4 | [20 empty] | 2024-03-29 |  | 2025-04-04 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | LYNN | 586866 | 1904 | 7.6 | Solar | 12_24W1 | 2024-03-08 13:47 | 2024-03-11 | 1 | 0 | 1 | 2024-03-12 | 2024-03-15 | 4 | 0 | 4 | [24 empty] | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | AUBURN | 587625 | 1501 | 200 | Solar | 01_26W2 | 2024-03-14 08:19 | 2024-03-15 | 22 | 15 | 7 | [29 empty] | EXP | [9 empty] | Application |  | No
National Grid | AUBURN | 587534 | 1501 | 200 | Solar | 01_26W2 | 2024-03-14 08:03 | 2024-03-15 | 22 | 15 | 7 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | LYNN | 567702 | 1904 | 6 | Solar | 12_24W2 | 2024-02-26 10:17 | 2024-02-27 | 11 | 6 | 5 | 2024-03-13 |  | 24 | 22 | 2 | [21 empty] | 2024-02-12 10:35 |  |  | EXP | [9 empty] | Screening |  | Yes
National Grid | LYNN | 588113 | 1904 | 10 | Solar | 12_24W2 | 2024-02-12 10:35 | 2024-02-13 | 7 | 4 | 3 | 2024-02-23 | 2024-02-29 | 5 | 0 | 5 | [20 empty] | 2024-03-04 |  | 2025-04-04 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | TOPSFIELD | 590429 | 1983 | 23 | Solar | 14_33L1 | 2024-02-15 14:48 | 2024-02-16 | 4 | 0 | 4 | 2024-02-23 | 2024-02-27 | 3 | 0 | 3 | [20 empty] | 2024-03-04 | 2024-02-02 15:40 |  |  | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | LAWRENCE | 586831 | 1841 | 7.83 | Solar | 14_74L3 | 2024-02-02 15:40 | 2024-02-05 | 2 | 0 | 2 | 2024-02-07 | 2024-02-21 | 10 | 0 | 10 | [20 empty] | 2024-02-26 |  | 2025-03-06 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | BOXFORD | 566735 | 1921 | 34.2 | Solar | 14_33L2 | 2024-02-28 16:46 | 2024-02-29 | 28 | 25 | 3 | [26 empty] | 2024-02-23 15:03 |  |  | EXP | [9 empty] | Application |  | Yes
National Grid | AUBURN | 588492 | 1501 | 9.135 | Solar | 01_26W3 | 2024-02-23 15:03 | 2024-02-26 | 5 | 1 | 4 | 2024-03-04 | 2024-03-05 | 2 | 0 | 2 | [20 empty] | 2024-03-11 | 2024-02-27 10:15 | 2025-03-12 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | RUTLAND | 591901 | 1543 | 6 | Solar | 01_55W1 | 2024-02-27 10:15 | 2024-02-28 | 3 | 1 | 2 | 2024-03-01 | 2024-03-04 | 2 | 0 | 2 | [20 empty] | 2024-03-06 |  | 2025-03-20 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | WORCESTER | 556062 | 1604 | 7.6 | Solar | 01_27W1 | 2024-03-15 11:19 | 2024-03-18 | 1 | 0 | 1 | 2024-03-19 | 2024-03-21 | 3 | 0 | 3 | [20 empty] | 2024-03-22 |  | 2025-03-27 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | LAWRENCE | 556519 | 1841 | 333 | Natural Gas | 14_74L4 | 2024-02-20 09:36 | 2024-02-21 | 39 | 25 | 14 | [29 empty] | STD | [9 empty] | Application |  | Yes
National Grid | METHUEN | 590983 | 1844 | 10 | Solar | 14_74L4 | 2024-03-11 17:07 | 2024-03-12 | 2 | 0 | 2 | 2024-03-14 |  | 23 | 21 | 2 | [21 empty] | 2024-03-13 12:14 |  |  | EXP | [9 empty] | Screening |  | Yes
National Grid | LOWELL | 595183 | 1852 | 3.8 | Solar | 14_3L4 | 2024-03-13 12:14 | 2024-03-14 | 1 | 0 | 1 | 2024-03-15 | 2024-03-19 | 3 | 0 | 3 | [20 empty] | 2024-03-19 |  | 2025-04-01 |  | EXP | [9 empty] | Design |  | Yes
National Grid | LAWRENCE | 590405 | 1840 | 25 | Solar | 14_74L6 | 2024-02-15 14:34 | 2024-02-16 | 41 | 39 | 2 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | LAWRENCE | 580061 | 1841 | 10 | Solar | 14_74L6 | 2024-02-28 13:19 | 2024-02-29 | 3 | 0 | 3 | 2024-03-05 | 2024-03-19 | 12 | 5 | 7 | [20 empty] | 2024-03-21 | 2024-02-05 12:21 | 2025-03-22 |  | EXP | [8 empty] | 2024-04-04 | Connected |  | No
National Grid | MAGNOLIA | 586229 | 1930 | 6 | Solar | 12_28L2 | 2024-02-05 12:21 | 2024-02-06 | 2 | 0 | 2 | 2024-02-08 | 2024-02-21 | 9 | 0 | 9 | [20 empty] | 2024-02-27 |  | 2025-03-04 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | DRACUT | 592767 | 1826 | 10 | Solar | 14_75L1 | 2024-03-13 12:53 | 2024-03-14 | 4 | 0 | 4 | 2024-03-20 | 2024-03-22 | 3 | 0 | 3 | [20 empty] | 2024-03-26 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | METHUEN | 585644 | 1844 | 9.28 | Solar | 14_43L4 | 2024-02-02 16:17 | 2024-02-05 | 2 | 0 | 2 | 2024-02-07 | 2024-02-21 | 11 | 1 | 10 | [20 empty] | 2024-02-26 | 2024-03-13 12:26 | 2025-03-06 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LAWRENCE | 595579 | 1841 | 7.6 | Solar | 14_43L4 | 2024-03-13 12:26 | 2024-03-14 | 4 | 0 | 4 | 2024-03-20 | 2024-03-25 | 4 | 0 | 4 | [20 empty] | 2024-03-29 |  | 2025-04-04 | Yes | EXP |  | 2024-04-16 |  | 0 | 0 | 0 |  |  |  | Construction |  | Yes
National Grid | GRAFTON | 591813 | 1519 | 3.8 | Solar | 01_304W2 | 2024-02-26 15:43 | 2024-02-27 | 8 | 3 | 5 | 2024-03-08 | 2024-04-01 | 18 | 17 | 1 | [20 empty] | 2024-04-05 | 2024-02-23 10:48 |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | METHUEN | 591270 | 1844 | 6 | Solar | 14_43L4 | 2024-02-23 10:48 | 2024-02-26 | 1 | 0 | 1 | 2024-02-27 | 2024-03-21 | 19 | 15 | 4 | [20 empty] | 2024-03-25 |  | 2025-03-27 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | LYNN | 583921 | 1904 | 5.22 | Solar | 12_29W1 | 2024-02-12 03:54 | 2024-02-13 | 5 | 2 | 3 | 2024-02-21 | 2024-03-01 | 8 | 3 | 5 | [20 empty] | 2024-03-05 |  | 2025-04-12 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | METHUEN | 589208 | 1844 | 7.6 | Solar | 14_43L4 | 2024-02-23 12:01 | 2024-02-26 | 6 | 0 | 6 | 2024-03-05 | 2024-03-07 | 3 | 0 | 3 | [20 empty] | 2024-03-14 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | LYNN | 587528 | 1904 | 7.6 | Solar | 12_29W1 | 2024-02-09 12:34 | 2024-02-12 | 3 | 0 | 3 | 2024-02-15 | 2024-02-21 | 4 | 0 | 4 | [20 empty] | 2024-02-23 |  | 2025-03-01 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | LYNN | 588428 | 1904 | 3.8 | Solar | 12_29W1 | 2024-02-21 18:52 | 2024-02-22 | 28 | 25 | 3 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | LYNN | 590460 | 1904 | 6 | Solar | 12_29W1 | 2024-03-01 14:01 | 2024-03-04 | 31 | 25 | 6 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | GARDNER | 438280 | 1440 | 15.2 | Solar | 01_602W2 | 2024-03-12 09:36 | 2024-03-13 | 15 | 13 | 2 | 2024-04-02 | 2024-04-10 | 7 | 0 | 7 | [21 empty] | 2024-02-26 08:59 |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | HUBBARDSTON | 579357 | 1452 | 5.22 | Solar | 01_602W2 | 2024-02-26 08:59 | 2024-02-27 | 1 | 0 | 1 | 2024-02-28 | 2024-03-01 | 3 | 0 | 3 | [20 empty] | 2024-03-04 |  | 2025-03-12 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | DRACUT | 592634 | 1826 | 50 | Solar | 14_75L3 | 2024-02-26 13:30 | 2024-02-27 | 28 | 18 | 10 | 2024-04-04 |  | 8 | 0 | 8 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | MILLBURY | 593460 | 1527 | 7.6 | Solar | 01_304W3 | 2024-03-05 16:27 | 2024-03-06 | 3 | 0 | 3 | 2024-03-11 | 2024-03-08 | 0 | 0 | 0 | [20 empty] | 2024-03-15 |  | 2025-03-22 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LYNN | 588850 | 1905 | 5 | Solar | 12_29W3 | 2024-02-23 10:48 | 2024-02-26 | 9 | 8 | 1 | 2024-03-07 | 2024-03-07 | 1 | 0 | 1 | [20 empty] | 2024-03-11 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LOWELL | 584135 | 1850 | 7.6 | Solar | 14_75L5 | 2024-02-06 14:04 | 2024-02-07 | 1 | 0 | 1 | 2024-02-08 | 2024-03-04 | 17 | 9 | 8 | [20 empty] | 2024-03-05 |  | 2025-03-12 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | LYNN | 592433 | 1902 | 6 | Solar | 12_29W5 | 2024-02-27 19:49 | 2024-02-28 | 4 | 0 | 4 | 2024-03-05 |  | 30 | 25 | 5 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | LYNN | 591596 | 1902 | 6 | Solar | 12_29W5 | 2024-03-07 17:24 | 2024-03-08 | 2 | 0 | 2 | 2024-03-12 | 2024-03-15 | 5 | 3 | 2 | [20 empty] | 2024-03-19 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | MILLBURY | 590002 | 1527 | 7.6 | Solar | 01_304W5 | 2024-02-22 12:19 | 2024-02-23 | 2 | 0 | 2 | 2024-02-27 | 2024-03-04 | 5 | 0 | 5 | [20 empty] | 2024-03-05 |  | 2025-03-22 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | GARDNER | 593301 | 1440 | 7.6 | Solar | 01_607W1 | 2024-03-06 12:42 | 2024-03-07 | 2 | 0 | 2 | 2024-03-11 | 2024-03-12 | 2 | 0 | 2 | [20 empty] | 2024-03-18 |  | 2025-04-01 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | HAVERHILL | 591663 | 1830 | 22.92 | Battery Add-On | 14_76L3 | 2024-03-06 14:10 | 2024-03-07 | 11 | 9 | 2 | 2024-03-21 | 2024-03-22 | 2 | 0 | 2 | [20 empty] | 2024-03-28 |  | 2025-04-01 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | HAVERHILL | 595357 | 1830 | 9.57 | Solar | 14_48L1 | 2024-03-13 12:02 | 2024-03-14 | 4 | 0 | 4 | 2024-03-20 | 2024-03-22 | 3 | 0 | 3 | [20 empty] | 2024-03-28 | 2024-02-05 05:56 | 2025-04-09 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | HAVERHILL | 571517 | 1830 | 3.8 | Solar | 14_48L2 | 2024-02-05 05:56 | 2024-02-06 | 0 | 0 | 0 | 2024-02-06 | 2024-02-20 | 10 | 0 | 10 | [20 empty] | 2024-02-21 | 2024-02-07 17:18 | 2025-02-28 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | HAVERHILL | 586272 | 1832 | 3.19 | Solar | 14_48L4 | 2024-02-07 17:18 | 2024-02-08 | 3 | 0 | 3 | 2024-02-13 | 2024-02-27 | 10 | 0 | 10 | [20 empty] | 2024-02-29 | 2024-02-27 12:09 | 2025-03-15 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | MARLBOROUGH | 592139 | 1752 | 6 | Solar | 05_311W5 | 2024-02-27 12:09 | 2024-02-28 | 5 | 0 | 5 | 2024-03-06 | 2024-03-07 | 2 | 0 | 2 | [20 empty] | 2024-03-14 |  | 2025-03-22 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | WORCESTER | 575082 | 1609 | 9.6 | Solar | 01_3J375 | 2024-03-05 15:49 | 2024-03-06 | 4 | 1 | 3 | 2024-03-12 | 2024-03-15 | 4 | 0 | 4 | 2024-03-29 |  | 12 | 0 | 12 | [5 empty] | 2024-03-29 |  | 12 | 0 | 12 | [9 empty] | EXP | [9 empty] | Supplemental Review |  | Yes
National Grid | NORTH OXFORD | 586275 | 1537 | 20.01 | Solar | 01_406L1 | 2024-02-19 11:51 | 2024-02-20 | 40 | 38 | 2 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | MARLBOROUGH | 588582 | 1752 | 5 | Solar | 05_311W6 | 2024-03-11 14:44 | 2024-03-12 | 1 | 0 | 1 | 2024-03-13 | 2024-03-20 | 6 | 0 | 6 | [20 empty] | 2024-03-25 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | HUBBARDSTON | 593641 | 1452 | 17.6 | Battery Add-On | 01_609W1 | 2024-03-08 14:38 | 2024-03-11 | 4 | 0 | 4 | 2024-03-15 | 2024-03-19 | 3 | 0 | 3 | [20 empty] | 2024-03-25 |  | 2025-04-01 |  | EXP | [9 empty] | Conditional Approval |  | No
National Grid | LAWRENCE | 586777 | 1840 | 7.6 | Solar | 14_53J1 | 2024-02-26 14:19 | 2024-02-27 | 35 | 32 | 3 | [26 empty] | 2024-02-23 12:57 |  |  | EXP | [9 empty] | Application |  | Yes
National Grid | WESTBOROUGH | 557462 | 1581 | 7.6 | Solar | 05_312W1 | 2024-02-23 12:57 | 2024-02-26 | 7 | 5 | 2 | 2024-03-06 | 2024-03-06 | 1 | 0 | 1 | [20 empty] | 2024-03-11 | 2024-02-23 11:14 | 2025-03-14 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | METHUEN | 590580 | 1844 | 10 | Solar | 14_53J4 | 2024-02-23 11:14 | 2024-02-26 | 2 | 0 | 2 | 2024-02-28 | 2024-03-01 | 3 | 0 | 3 | [20 empty] | 2024-03-06 |  | 2025-03-08 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | WESTBOROUGH | 573242 | 1581 | 500 | Solar | 05_312W1 | 2024-02-08 12:37 | 2024-02-09 | 46 | 37 | 9 | [26 empty] | 2024-02-22 13:18 |  |  | STD | [9 empty] | Application |  | No
National Grid | METHUEN | 589338 | 1844 | 10 | Solar | 14_53J4 | 2024-02-22 13:18 | 2024-02-23 | 2 | 0 | 2 | 2024-02-27 | 2024-02-29 | 3 | 0 | 3 | [20 empty] | 2024-03-05 |  | 2025-03-08 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | WESTBOROUGH | 573239 | 1581 | 500 | Solar | 05_312W1 | 2024-02-08 12:35 | 2024-02-09 | 46 | 37 | 9 | [29 empty] | STD | [9 empty] | Application |  | No
National Grid | WESTBOROUGH | 596048 | 1581 | 15.2 | Solar | 05_312W1 | 2024-03-12 07:52 | 2024-03-13 | 4 | 0 | 4 | 2024-03-19 | 2024-03-21 | 3 | 0 | 3 | [20 empty] | 2024-03-28 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | WESTBOROUGH | 591712 | 1581 | 9.1 | Solar | 05_312W1 | 2024-02-27 14:08 | 2024-02-28 | 3 | 1 | 2 | 2024-03-04 | 2024-03-05 | 2 | 0 | 2 | [20 empty] | 2024-03-11 |  | 2025-03-13 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | AUBURN | 590501 | 1501 | 5.8 | Solar | 01_406L2 | 2024-02-22 15:12 | 2024-02-23 | 2 | 0 | 2 | 2024-02-27 | 2024-03-01 | 4 | 0 | 4 | [20 empty] | 2024-03-07 | 2024-03-04 09:58 | 2025-03-13 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | EVERETT | 592425 | 2149 | 6 | Solar | 12_37W9 | 2024-03-04 09:58 | 2024-03-05 | 1 | 0 | 1 | 2024-03-06 | 2024-03-07 | 2 | 0 | 2 | [20 empty] | 2024-03-11 |  | 2025-03-12 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | LYNN | 584595 | 1902 | 5 | Solar | 12_3J903 | 2024-02-09 18:56 | 2024-02-12 | 2 | 1 | 1 | 2024-02-13 | 2024-03-18 | 25 | 19 | 6 | [20 empty] | 2024-03-19 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LYNN | 592529 | 1902 | 3.8 | Solar | 12_3J903 | 2024-02-27 19:27 | 2024-02-28 | 5 | 0 | 5 | 2024-03-06 |  | 29 | 25 | 4 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | OXFORD | 594064 | 1540 | 7.6 | Solar | 01_406L3 | 2024-03-06 12:32 | 2024-03-07 | 4 | 0 | 4 | 2024-03-13 | 2024-03-19 | 5 | 0 | 5 | [20 empty] | 2024-03-20 |  | 2025-03-25 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | OXFORD | 594844 | 1540 | 11.4 | Solar | 01_406L3 | 2024-03-06 11:45 | 2024-03-07 | 15 | 12 | 3 | 2024-03-27 |  | 14 | 12 | 2 | [24 empty] | EXP | [9 empty] | Screening |  | No
National Grid | BOXFORD | 587700 | 1921 | 21.735 | Solar | 14_56L3 | 2024-02-06 10:48 | 2024-02-07 | 16 | 14 | 2 | 2024-03-01 | 2024-03-05 | 3 | 0 | 3 | [20 empty] | 2024-03-08 |  | 2025-03-20 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | BOXFORD | 593058 | 1921 | 15.2 | Solar | 14_56L3 | 2024-02-27 15:23 | 2024-02-28 | 26 | 25 | 1 | 2024-04-10 |  | 4 | 0 | 4 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | LAWRENCE | 592133 | 1841 | 10 | Solar | 14_8L2 | 2024-03-11 17:42 | 2024-03-12 | 3 | 0 | 3 | 2024-03-15 | 2024-03-21 | 5 | 0 | 5 | [20 empty] | 2024-03-28 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LYNN | 591000 | 1902 | 10 | Solar | 12_4J2 | 2024-03-06 13:25 | 2024-03-07 | 2 | 0 | 2 | 2024-03-11 | 2024-03-18 | 6 | 0 | 6 | [20 empty] | 2024-03-22 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | BEVERLY | 575451 | 1915 | 5.376 | Solar | 12_51L1 | 2024-02-08 16:23 | 2024-02-09 | 4 | 0 | 4 | 2024-02-15 |  | 42 | 25 | 17 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | WESTFORD | 588461 | 1886 | 23 | Solar | 14_57L2 | 2024-02-07 11:14 | 2024-02-08 | 6 | 4 | 2 | 2024-02-15 | 2024-04-09 | 38 | 25 | 13 | [20 empty] | 2024-04-11 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | BEVERLY | 592675 | 1915 | 34.5 | Solar | 12_51L3 | 2024-02-26 14:25 | 2024-02-27 | 1 | 0 | 1 | 2024-02-28 | 2024-04-03 | 26 | 22 | 4 | [20 empty] | 2024-04-10 |  | 2025-04-11 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | WORCESTER | 583917 | 1602 | 4.93 | Solar | 01_6W2 | 2024-02-09 11:04 | 2024-02-12 | 3 | 0 | 3 | 2024-02-15 | 2024-02-21 | 4 | 0 | 4 | [20 empty] | 2024-02-26 |  | 2025-03-08 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | STURBRIDGE | 586660 | 1518 | 10 | Solar | 01_408L2 | 2024-02-08 14:19 | 2024-02-09 | 1 | 0 | 1 | 2024-02-12 | 2024-03-19 | 27 | 19 | 8 | [20 empty] | 2024-03-25 |  | 2025-04-02 |  | EXP | [9 empty] | Meter Installation |  | Yes
National Grid | CHERRY VALLEY | 592273 | 1611 | 7.6 | Solar | 01_6W2 | 2024-03-08 17:43 | 2024-03-11 | 16 | 13 | 3 | 2024-04-01 |  | 11 | 5 | 6 | [21 empty] | 2024-03-01 15:18 |  |  | EXP | [9 empty] | Screening |  | Yes
National Grid | ESSEX | 590822 | 1929 | 8.7 | Solar | 12_51T1 | 2024-03-01 15:18 | 2024-03-04 | 5 | 3 | 2 | 2024-03-11 | 2024-03-15 | 5 | 3 | 2 | [20 empty] | 2024-03-20 |  | 2025-03-27 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | WORCESTER | 578624 | 1604 | 200 | Solar | 01_HT56B | 2024-02-06 09:29 | 2024-02-07 | 34 | 25 | 9 | [26 empty] | 2024-02-14 07:10 |  |  | EXP | [9 empty] | Pending Withdraw |  | No
National Grid | WORCESTER | 586363 | 1603 | 5 | Solar | 01_7J387 | 2024-02-14 07:10 | 2024-02-15 | 4 | 2 | 2 | 2024-02-22 | 2024-02-29 | 7 | 3 | 4 | [20 empty] | 2024-03-04 |  | 2025-03-25 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | BOLTON | 588321 | 1740 | 6.282 | Solar | 01_216W6 | 2024-03-05 16:22 | 2024-03-06 | 17 | 16 | 1 | 2024-03-28 | 2024-03-29 | 2 | 0 | 2 | [20 empty] | 2024-04-02 |  | 2025-04-05 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | WORCESTER | 594220 | 1607 | 7.6 | Solar | 01_8J365 | 2024-03-05 14:31 | 2024-03-06 | 3 | 0 | 3 | 2024-03-11 | 2024-03-15 | 5 | 0 | 5 | [20 empty] | 2024-03-20 |  | 2025-03-27 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | WORCESTER | 584498 | 1607 | 10 | Solar | 01_8J389 | 2024-02-14 15:15 | 2024-02-15 | 2 | 0 | 2 | 2024-02-20 | 2024-02-22 | 3 | 0 | 3 | [20 empty] | 2024-02-27 |  | 2025-03-01 |  | EXP | [8 empty] | 2024-04-03 | Connected |  | No
National Grid | NORTHBOROUGH | 593596 | 1532 | 6.282 | Solar | 05_314W4 | 2024-03-08 11:33 | 2024-03-11 | 3 | 0 | 3 | 2024-03-14 | 2024-03-14 | 1 | 0 | 1 | [20 empty] | 2024-03-18 |  | 2025-03-27 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | DUDLEY | 587291 | 1571 | 4.93 | Solar | 01_412L4 | 2024-02-13 14:23 | 2024-02-14 | 2 | 0 | 2 | 2024-02-16 | 2024-03-26 | 28 | 25 | 3 | [24 empty] | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | DUDLEY | 585721 | 1571 | 8.12 | Solar | 01_412L5 | 2024-02-19 12:00 | 2024-02-20 | 40 | 37 | 3 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | WORCESTER | 592110 | 1605 | 60 | Solar | 01_12J377 | 2024-03-11 15:07 | 2024-03-12 | 8 | 2 | 6 | 2024-03-21 |  | 18 | 12 | 6 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | FALL RIVER | 581461 | 2724 | 6 | Solar | 05_106W42 | 2024-02-08 13:30 | 2024-02-09 | 8 | 5 | 3 | 2024-02-22 | 2024-03-08 | 13 | 7 | 6 | [20 empty] | 2024-03-13 |  | 2025-03-15 |  | EXP | [9 empty] | Meter Installation |  | No
National Grid | ANDOVER | 594025 | 1810 | 10 | Solar | 14_59L6 | 2024-03-11 11:40 | 2024-03-12 | 3 | 0 | 3 | 2024-03-15 |  | 22 | 19 | 3 | [21 empty] | 2024-02-12 17:22 |  |  | EXP | [9 empty] | Screening |  | Yes
National Grid | GLOUCESTER | 572797 | 1930 | 7.6 | Solar | 12_51T3 | 2024-02-12 17:22 | 2024-02-13 | 3 | 0 | 3 | 2024-02-16 | 2024-02-23 | 5 | 0 | 5 | [20 empty] | 2024-02-26 |  | 2025-02-28 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | SOUTHBRIDGE | 585346 | 1550 | 8.12 | Solar | 01_413L1 | 2024-03-15 13:14 | 2024-03-18 | 3 | 0 | 3 | 2024-03-21 | 2024-04-11 | 17 | 14 | 3 | [24 empty] | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | UPTON | 586651 | 1568 | 10 | Solar | 05_320W1 | 2024-02-16 17:12 | 2024-02-20 | 21 | 17 | 4 | 2024-03-19 | 2024-04-09 | 17 | 14 | 3 | [20 empty] | 2024-04-15 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | FALL RIVER | 591268 | 2723 | 6 | Solar | 05_106W82 | 2024-03-06 14:48 | 2024-03-07 | 2 | 0 | 2 | 2024-03-11 | 2024-03-12 | 2 | 0 | 2 | [20 empty] | 2024-03-18 |  | 2025-04-01 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | MALDEN | 587973 | 2148 | 550 | Natural Gas | 12_5J9 | 2024-02-28 10:49 | 2024-02-29 | 33 | 23 | 10 | [29 empty] | STD | [9 empty] | Application |  | Yes
National Grid | METHUEN | 592556 | 1844 | 3.8 | Solar | 14_5J41 | 2024-03-01 19:29 | 2024-03-04 | 31 | 25 | 6 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | BELLINGHAM | 585799 | 2019 | 6 | Solar | 05_108W60 | 2024-02-07 16:56 | 2024-02-08 | 5 | 0 | 5 | 2024-02-15 | 2024-02-22 | 5 | 0 | 5 | [20 empty] | 2024-02-28 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | BLACKSTONE | 580770 | 1504 | 6.528 | Solar | 05_108W60 | 2024-02-23 13:09 | 2024-02-26 | 6 | 2 | 4 | 2024-03-04 | 2024-03-27 | 19 | 18 | 1 | [20 empty] | 2024-04-02 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | BELLINGHAM | 587903 | 2019 | 7.83 | Solar | 05_108W60 | 2024-02-16 09:58 | 2024-02-20 | 2 | 0 | 2 | 2024-02-22 | 2024-02-29 | 6 | 0 | 6 | [20 empty] | 2024-03-04 |  | 2025-03-19 |  | EXP | [8 empty] | 2024-04-11 | Connected |  | No
National Grid | SOUTHBRIDGE | 585545 | 1550 | 498 | Solar | 01_413L3 | 2024-02-14 16:14 | 2024-02-15 | 42 | 33 | 9 | [29 empty] | STD | [9 empty] | Pending Withdraw |  | No
National Grid | SAUGUS | 587947 | 1906 | 3.8 | Solar | 12_7J903 | 2024-02-10 12:19 | 2024-02-12 | 1 | 0 | 1 | 2024-02-13 | 2024-02-26 | 9 | 0 | 9 | [20 empty] | 2024-02-27 |  | 2025-02-28 |  | EXP | [8 empty] | 2024-04-09 | Connected |  | Yes
National Grid | DESOUZA | 592756 | 1550 | 7.6 | Solar | 01_413L4 | 2024-02-28 17:11 | 2024-02-29 | 33 | 25 | 8 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | SOUTHBRIDGE | 591210 | 1550 | 6 | Solar | 01_413L4 | 2024-03-08 11:45 | 2024-03-11 | 4 | 0 | 4 | 2024-03-15 | 2024-04-02 | 13 | 10 | 3 | [20 empty] | 2024-04-09 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | REVERE | 591484 | 2151 | 3.8 | Solar | 12_7W2 | 2024-02-27 19:39 | 2024-02-28 | 30 | 25 | 5 | 2024-04-12 |  | 2 | 0 | 2 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | LAWRENCE | 587226 | 1843 | 6 | Solar | 14_61L1 | 2024-02-21 12:05 | 2024-02-22 | 3 | 0 | 3 | 2024-02-27 | 2024-02-28 | 2 | 0 | 2 | [20 empty] | 2024-03-04 |  |  |  | EXP | [9 empty] | Withdrawn |  | No
National Grid | LAWRENCE | 582729 | 1843 | 9.86 | Solar | 14_61L3 | 2024-02-21 20:33 | 2024-02-22 | 34 | 25 | 9 | 2024-04-10 |  | 4 | 0 | 4 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | REVERE | 587779 | 2151 | 7.6 | Solar | 12_7W3 | 2024-02-05 10:51 | 2024-02-06 | 6 | 0 | 6 | 2024-02-14 | 2024-02-23 | 7 | 0 | 7 | [20 empty] | 2024-02-28 | 2024-02-29 13:04 | 2025-03-11 |  | EXP | [9 empty] | Meter Installation |  | Yes
National Grid | LAWRENCE | 590957 | 1843 | 3.8 | Solar | 14_61L3 | 2024-02-29 13:04 | 2024-03-01 | 5 | 2 | 3 | 2024-03-07 | 2024-03-12 | 4 | 0 | 4 | [20 empty] | 2024-03-18 |  | 2025-03-20 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | STURBRIDGE | 595438 | 1566 | 46 | Solar | 01_413L7 | 2024-03-08 10:52 | 2024-03-11 | 2 | 0 | 2 | 2024-03-13 | 2024-03-19 | 5 | 0 | 5 | [20 empty] | 2024-03-25 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LEOMINSTER | 595356 | 1453 | 7.6 | Solar | 01_225W3 | 2024-03-15 13:56 | 2024-03-18 | 2 | 0 | 2 | 2024-03-20 | 2024-03-22 | 4 | 2 | 2 | [20 empty] | 2024-03-26 |  | 2025-04-04 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LANCASTER | 582926 | 1523 | 4948 | Solar | 01_225W3 | 2024-02-06 13:14 | 2024-02-07 | 45 | 35 | 10 | [10 empty] | 2024-04-11 |  | 3 | 0 | 3 | [14 empty] | STD | [9 empty] | Screening |  | No
National Grid | MILLVILLE | 594814 | 1529 | 6 | Solar | 05_321W2 | 2024-03-12 11:17 | 2024-03-13 | 1 | 0 | 1 | 2024-03-14 | 2024-03-21 | 6 | 0 | 6 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | FALL RIVER | 583847 | 2723 | 480 | Solar | 05_115W52 | 2024-02-22 13:03 | 2024-02-23 | 37 | 27 | 10 | [29 empty] | STD | [9 empty] | Application |  | Yes
National Grid | METHUEN | 580779 | 1844 | 5.8 | Solar | 14_63L1 | 2024-02-08 15:37 | 2024-02-09 | 9 | 5 | 4 | 2024-02-22 | 2024-03-04 | 9 | 6 | 3 | 2024-03-29 |  | 12 | 0 | 12 | [5 empty] | 2024-03-29 |  | 12 | 0 | 12 | [9 empty] | EXP | [9 empty] | Supplemental Review |  | Yes
National Grid | LAWRENCE | 590846 | 1841 | 5 | Solar | 14_63L1 | 2024-03-07 17:55 | 2024-03-08 | 3 | 0 | 3 | 2024-03-13 | 2024-03-15 | 3 | 0 | 3 | [20 empty] | 2024-03-18 | 2024-02-09 11:31 |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | PEPPERELL | 586042 | 1463 | 8.41 | Solar | 01_226L1 | 2024-02-09 11:31 | 2024-02-12 | 2 | 0 | 2 | 2024-02-14 | 2024-02-22 | 6 | 0 | 6 | [20 empty] | 2024-02-28 |  | 2025-03-01 | Yes | EXP |  | 2024-04-16 |  | 0 | 0 | 0 |  |  |  | Construction |  | Yes
National Grid | LOWELL | 592199 | 1851 | 7.6 | Solar | 14_16L3 | 2024-02-27 11:52 | 2024-02-28 | 5 | 0 | 5 | 2024-03-06 | 2024-03-08 | 4 | 2 | 2 | 2024-03-29 |  | 12 | 0 | 12 | [5 empty] | 2024-03-29 |  | 12 | 0 | 12 | [9 empty] | EXP | [9 empty] | Supplemental Review |  | Yes
National Grid | CHARLTON | 493328 | 1507 | 2000 | Solar | 01_415L2 | 2024-02-21 12:42 | 2024-02-22 | 35 | 25 | 10 | [29 empty] | STD | [9 empty] | Pending Withdraw |  | No
National Grid | BLACKSTONE | 586359 | 1504 | 11.4 | Solar | 05_321W6 | 2024-02-20 16:21 | 2024-02-21 | 28 | 25 | 3 | [29 empty] | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | CHELMSFORD | 589144 | 1824 | 3.8 | Solar | 14_16L4 | 2024-02-22 15:07 | 2024-02-23 | 3 | 1 | 2 | 2024-02-27 | 2024-03-04 | 5 | 0 | 5 | [20 empty] | 2024-03-05 | 2024-02-12 13:35 |  |  | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | NORTH BILLERICA | 587504 | 1862 | 7.25 | Solar | 14_18L3 | 2024-02-12 13:35 | 2024-02-13 | 3 | 0 | 3 | 2024-02-16 | 2024-02-26 | 6 | 0 | 6 | [20 empty] | 2024-02-27 |  | 2025-02-28 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | LANCASTER | 582916 | 1523 | 4948 | Solar | 01_227W1 | 2024-02-06 13:24 | 2024-02-07 | 45 | 35 | 10 | [10 empty] | 2024-04-11 |  | 3 | 0 | 3 | [14 empty] | STD | [9 empty] | Screening |  | No
National Grid | SHIRLEY | 591793 | 1464 | 15.2 | Solar | 01_227W1 | 2024-02-21 17:46 | 2024-02-22 | 16 | 11 | 5 | 2024-03-15 | 2024-03-18 | 2 | 0 | 2 | [20 empty] | 2024-03-22 |  |  |  | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | TYNGSBORO | 590700 | 1879 | 7.6 | Solar | 14_211L1 | 2024-03-04 12:56 | 2024-03-05 | 5 | 1 | 4 | 2024-03-12 | 2024-03-18 | 5 | 0 | 5 | [20 empty] | 2024-03-21 |  | 2025-03-26 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | SWANSEA | 562551 | 2777 | 5334 | Solar | 05_11W84 | 2024-02-20 10:45 | 2024-02-21 | 38 | 30 | 8 | [29 empty] | STD | [9 empty] | Pending Withdraw |  | No
National Grid | LAWRENCE | 594507 | 1841 | 3.8 | Solar | 14_6J8 | 2024-03-07 19:35 | 2024-03-08 | 3 | 0 | 3 | 2024-03-13 | 2024-03-15 | 3 | 0 | 3 | [20 empty] | 2024-03-18 |  | 2025-03-20 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | BELLINGHAM | 579748 | 2019 | 10 | Solar | 05_335W1 | 2024-02-15 09:29 | 2024-02-16 | 2 | 0 | 2 | 2024-02-21 | 2024-02-29 | 7 | 0 | 7 | [20 empty] | 2024-03-05 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | SPENCER | 588485 | 1562 | 7.6 | Solar | 01_552L1 | 2024-02-12 13:27 | 2024-02-13 | 4 | 2 | 2 | 2024-02-16 | 2024-03-12 | 18 | 13 | 5 | [20 empty] | 2024-03-29 | 2024-02-28 16:50 | 2025-04-04 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | BELLINGHAM | 592697 | 2019 | 6 | Solar | 05_335W1 | 2024-02-28 16:50 | 2024-02-29 | 3 | 0 | 3 | 2024-03-05 | 2024-03-08 | 4 | 0 | 4 | [20 empty] | 2024-03-11 |  | 2025-03-12 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | BELLINGHAM | 590034 | 2019 | 10 | Solar | 05_335W1 | 2024-02-22 12:45 | 2024-02-23 | 2 | 0 | 2 | 2024-02-27 | 2024-03-01 | 4 | 0 | 4 | [20 empty] | 2024-03-04 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | BELLINGHAM | 589409 | 2019 | 6 | Solar | 05_335W1 | 2024-02-27 11:16 | 2024-02-28 | 4 | 0 | 4 | 2024-03-05 | 2024-03-07 | 3 | 0 | 3 | [20 empty] | 2024-03-11 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LOWELL | 588627 | 1854 | 20 | Solar | 14_21L3 | 2024-02-12 15:30 | 2024-02-13 | 17 | 15 | 2 | 2024-03-07 | 2024-03-21 | 11 | 8 | 3 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | WORCESTER | 582505 | 1605 | 10 | Solar | 01_24W1 | 2024-02-16 15:35 | 2024-02-20 | 4 | 0 | 4 | 2024-02-26 | 2024-03-01 | 5 | 0 | 5 | [21 empty] | 2024-02-22 12:59 |  |  | EXP | [9 empty] | Screening |  | Yes
National Grid | SOMERSET | 590736 | 2726 | 3.8 | Solar | 05_19W72 | 2024-02-22 12:59 | 2024-02-23 | 2 | 0 | 2 | 2024-02-27 | 2024-03-29 | 25 | 22 | 3 | [20 empty] | 2024-04-02 |  | 2025-04-04 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | BILLERICA | 590690 | 1821 | 10 | Solar | 14_70L5 | 2024-02-22 15:36 | 2024-02-23 | 2 | 0 | 2 | 2024-02-27 | 2024-03-11 | 11 | 7 | 4 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BILLERICA | 588066 | 1821 | 14.49 | Solar | 14_70L6 | 2024-02-12 12:09 | 2024-02-13 | 7 | 5 | 2 | 2024-02-22 | 2024-03-01 | 7 | 0 | 7 | [20 empty] | 2024-03-05 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | RANDOLPH | 583670 | 2368 | 7.6 | Solar | 07_5W3 | 2024-02-09 08:07 | 2024-02-12 | 1 | 0 | 1 | 2024-02-13 | 2024-03-08 | 18 | 11 | 7 | [20 empty] | 2024-03-14 | 2024-02-08 05:35 | 2025-03-18 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | RANDOLPH | 587703 | 2368 | 8.7 | Solar | 07_5W3 | 2024-02-08 05:35 | 2024-02-09 | 7 | 5 | 2 | 2024-02-20 | 2024-02-22 | 3 | 0 | 3 | [20 empty] | 2024-02-27 |  | 2025-03-27 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | WORCESTER | 591330 | 1606 | 3.8 | Solar | 01_24W3 | 2024-02-26 10:28 | 2024-02-27 | 6 | 0 | 6 | 2024-03-06 | 2024-03-07 | 2 | 0 | 2 | [20 empty] | 2024-03-14 |  | 2025-04-04 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | AMESBURY | 586162 | 1913 | 1375 | Solar | 14_275L4 | 2024-02-05 12:16 | 2024-02-06 | 13 | 4 | 9 | [10 empty] | 2024-02-23 | 2024-02-29 | 5 | 0 | 5 | [14 empty] | STD | [9 empty] | Pending Withdraw |  | No
National Grid | NORTH ANDOVER | 583602 | 1845 | 6.38 | Solar | 14_71L3 | 2024-02-14 17:22 | 2024-02-15 | 1 | 0 | 1 | 2024-02-16 | 2024-02-23 | 5 | 0 | 5 | [20 empty] | 2024-03-01 | 2024-02-03 12:51 |  |  | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | WORCESTER | 587312 | 1606 | 7.6 | Solar | 01_24W5 | 2024-02-03 12:51 | 2024-02-05 | 1 | 0 | 1 | 2024-02-06 | 2024-02-20 | 10 | 0 | 10 | [20 empty] | 2024-02-21 |  | 2025-02-22 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | LAWRENCE | 587976 | 1840 | 625 | Natural Gas | 14_2J4 | 2024-03-07 10:52 | 2024-03-08 | 27 | 17 | 10 | [29 empty] | STD | [9 empty] | Application |  | Yes
National Grid | MILFORD | 588787 | 1757 | 3.8 | Solar | 05_335W5 | 2024-02-22 11:39 | 2024-02-23 | 2 | 0 | 2 | 2024-02-27 | 2024-03-04 | 5 | 0 | 5 | [20 empty] | 2024-03-05 |  | 2025-03-14 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | RANDOLPH | 589709 | 2368 | 6.96 | Solar | 07_5W4 | 2024-02-21 13:38 | 2024-02-22 | 3 | 0 | 3 | 2024-02-27 | 2024-04-03 | 28 | 25 | 3 | [24 empty] | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | LOWELL | 588923 | 1851 | 7.6 | Solar | 14_2L2 | 2024-02-28 15:29 | 2024-02-29 | 4 | 0 | 4 | 2024-03-06 | 2024-03-06 | 1 | 0 | 1 | [20 empty] | 2024-03-13 |  | 2025-03-21 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | MILFORD | 591098 | 1757 | 7.6 | Solar | 05_335W9 | 2024-03-04 09:48 | 2024-03-05 | 3 | 0 | 3 | 2024-03-08 | 2024-03-13 | 5 | 4 | 1 | [20 empty] | 2024-03-18 |  | 2025-04-11 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | STOUGHTON | 592215 | 2072 | 8.832 | Solar | 07_94W43 | 2024-02-28 07:25 | 2024-02-29 | 17 | 15 | 2 | 2024-03-25 | 2024-04-03 | 8 | 5 | 3 | [20 empty] | 2024-04-10 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | EASTON | 476653 | 2356 | 20 | Solar | 07_94W43 | 2024-02-23 13:44 | 2024-02-26 | 36 | 34 | 2 | [29 empty] | EXP | [9 empty] | Application |  | No
National Grid | NORTHAMPTON | 584005 | 1060 | 4.095 | Solar | 09_909W2 | 2024-02-27 15:02 | 2024-02-28 | 5 | 1 | 4 | 2024-03-06 | 2024-03-08 | 3 | 0 | 3 | [20 empty] | 2024-03-13 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | BROCKTON | 591557 | 2302 | 3.8 | Solar | 07_69J1 | 2024-02-22 14:51 | 2024-02-23 | 2 | 0 | 2 | 2024-02-27 | 2024-03-04 | 5 | 0 | 5 | [20 empty] | 2024-03-06 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | STOUGHTON | 550589 | 2072 | 18.29 | Solar | 07_94W44 | 2024-03-07 10:13 | 2024-03-08 | 7 | 5 | 2 | 2024-03-18 | 2024-03-21 | 4 | 0 | 4 | [24 empty] | EXP | [9 empty] | Supplemental Review |  | Yes
National Grid | METHUEN | 593838 | 1844 | 15.2 | Solar | 14_74L1 | 2024-03-01 11:04 | 2024-03-04 | 28 | 25 | 3 | 2024-04-16 |  | 0 | 0 | 0 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | MILFORD | 592714 | 1757 | 13.92 | Solar | 05_336W3 | 2024-03-08 16:00 | 2024-03-11 | 4 | 1 | 3 | 2024-03-15 | 2024-04-02 | 14 | 11 | 3 | [20 empty] | 2024-04-08 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | HANOVER | 592315 | 2339 | 150 | Solar | 07_95W2 | 2024-02-26 09:48 | 2024-02-27 | 35 | 25 | 10 | [29 empty] | EXP | [9 empty] | Pending Withdraw |  | No
National Grid | WILBRAHAM | 587628 | 1095 | 8.19 | Solar | 09_507L2 | 2024-02-13 16:39 | 2024-02-14 | 3 | 1 | 2 | 2024-02-20 | 2024-02-22 | 3 | 0 | 3 | [20 empty] | 2024-02-28 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | EAST LONGMEADOW | 594830 | 1028 | 10 | Solar | 09_508L4 | 2024-03-12 11:23 | 2024-03-13 | 21 | 17 | 4 | 2024-04-10 |  | 4 | 0 | 4 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | RANDOLPH | 591148 | 2368 | 6 | Solar | 07_97W1 | 2024-03-11 17:29 | 2024-03-12 | 3 | 0 | 3 | 2024-03-15 | 2024-03-20 | 3 | 1 | 2 | [20 empty] | 2024-03-28 |  | 2025-04-15 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | FOXBOROUGH | 593998 | 2035 | 6 | Solar | 05_3432W1 | 2024-03-11 12:05 | 2024-03-12 | 1 | 0 | 1 | 2024-03-13 | 2024-03-20 | 6 | 0 | 6 | [20 empty] | 2024-03-21 | 2024-02-07 15:18 | 2025-04-04 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | RANDOLPH | 586650 | 2368 | 8.7 | Solar | 07_97W2 | 2024-02-07 15:18 | 2024-02-08 | 2 | 0 | 2 | 2024-02-12 | 2024-02-22 | 8 | 0 | 8 | [20 empty] | 2024-02-28 | 2024-02-07 17:33 | 2025-03-01 | Yes | EXP |  | 2024-03-30 |  | 17 | 0 | 17 |  |  |  | Construction |  | Yes
National Grid | RANDOLPH | 586576 | 2368 | 7.25 | Solar | 07_97W2 | 2024-02-07 17:33 | 2024-02-08 | 5 | 0 | 5 | 2024-02-15 | 2024-02-23 | 6 | 0 | 6 | [20 empty] | 2024-02-28 |  | 2025-03-15 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | RANDOLPH | 595756 | 2368 | 9.8 | Solar | 07_97W2 | 2024-03-14 12:00 | 2024-03-15 | 1 | 0 | 1 | 2024-03-18 | 2024-03-19 | 2 | 0 | 2 | [20 empty] | 2024-03-20 |  | 2025-03-25 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | RANDOLPH | 589671 | 2368 | 9.57 | Solar | 07_97W2 | 2024-02-27 18:41 | 2024-02-28 | 1 | 0 | 1 | 2024-02-29 |  | 33 | 25 | 8 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | RANDOLPH | 587494 | 2368 | 7.6 | Solar | 07_97W2 | 2024-02-12 11:04 | 2024-02-13 | 3 | 0 | 3 | 2024-02-16 | 2024-02-23 | 5 | 0 | 5 | 2024-03-22 |  | 17 | 0 | 17 | [5 empty] | 2024-03-22 |  | 17 | 0 | 17 | [9 empty] | EXP | [9 empty] | Supplemental Review |  | Yes
National Grid | RANDOLPH | 591319 | 2368 | 7.6 | Solar | 07_97W2 | 2024-03-06 14:57 | 2024-03-07 | 27 | 25 | 2 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | RANDOLPH | 590155 | 2368 | 7.6 | Solar | 07_97W2 | 2024-02-23 11:29 | 2024-02-26 | 34 | 25 | 9 | 2024-04-12 |  | 2 | 0 | 2 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | BELLINGHAM | 589418 | 2019 | 18.99 | Solar | 05_344W4 | 2024-02-12 16:16 | 2024-02-13 | 20 | 18 | 2 | 2024-03-12 | 2024-03-18 | 5 | 0 | 5 | [20 empty] | 2024-03-25 |  | 2025-04-11 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | RANDOLPH | 587439 | 2368 | 7.25 | Solar | 07_97W3 | 2024-02-09 11:46 | 2024-02-12 | 19 | 16 | 3 | 2024-03-08 | 2024-03-14 | 5 | 0 | 5 | [21 empty] | 2024-03-14 14:02 |  |  | EXP | [9 empty] | Supplemental Review |  | Yes
National Grid | BRIMFIELD | 596959 | 1010 | 23 | Solar | 09_516L1 | 2024-03-14 14:02 | 2024-03-15 | 2 | 0 | 2 | 2024-03-19 | 2024-03-20 | 2 | 0 | 2 | [20 empty] | 2024-03-27 |  | 2025-04-08 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | BROCKTON | 587841 | 2301 | 15 | Solar | 07_98W46 | 2024-02-14 14:18 | 2024-02-15 | 12 | 10 | 2 | 2024-03-04 | 2024-03-06 | 4 | 2 | 2 | [20 empty] | 2024-03-26 |  | 2025-04-07 |  | EXP | [8 empty] | 2024-04-09 | Connected |  | No
National Grid | FRANKLIN | 574094 | 2038 | 3935 | Solar | 05_348W1 | 2024-02-27 01:03 | 2024-02-28 | 34 | 25 | 9 | [29 empty] | STD | [9 empty] | Application |  | No
National Grid | WEST BROOKFIELD | 578928 | 1585 | 996 | Solar | 09_516L2 | 2024-02-29 15:57 | 2024-03-01 | 32 | 22 | 10 | [29 empty] | STD | [9 empty] | Application |  | No
National Grid | FRANKLIN | 579418 | 2038 | 9.984 | Solar | 05_348W5 | 2024-02-05 14:35 | 2024-02-06 | 2 | 1 | 1 | 2024-02-07 | 2024-02-20 | 9 | 0 | 9 | [20 empty] | 2024-02-23 |  | 2025-03-07 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | FOXBOROUGH | 587835 | 2035 | 100 | Solar | 05_349W1 | 2024-02-29 09:32 | 2024-03-01 | 32 | 22 | 10 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | WILBRAHAM | 594318 | 1095 | 10 | Solar | 09_523L1 | 2024-03-04 15:44 | 2024-03-05 | 30 | 25 | 5 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | ROCKLAND | 581885 | 2370 | 100 | Solar | 07_99W63 | 2024-02-22 14:15 | 2024-02-23 | 9 | 0 | 9 | [10 empty] | 2024-03-07 | 2024-03-11 | 3 | 0 | 3 | [14 empty] | STD | [9 empty] | Study |  | Yes
National Grid | REHOBOTH | 594903 | 2769 | 34.5 | Solar | 05_7L4 | 2024-03-06 15:40 | 2024-03-07 | 2 | 0 | 2 | 2024-03-11 |  | 26 | 24 | 2 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | NORTH ADAMS | 585259 | 1247 | 25 | Solar | 09_1015W1 | 2024-02-22 10:56 | 2024-02-23 | 20 | 15 | 5 | 2024-03-22 | 2024-03-26 | 3 | 0 | 3 | [20 empty] | 2024-04-01 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | NORTH ADAMS | 592033 | 1247 | 22.8 | Solar | 09_1015W1 | 2024-02-22 13:51 | 2024-02-23 | 20 | 15 | 5 | 2024-03-22 | 2024-03-27 | 4 | 0 | 4 | [20 empty] | 2024-04-01 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | NORTH ADAMS | 592018 | 1247 | 22.8 | Solar | 09_1015W1 | 2024-02-22 13:28 | 2024-02-23 | 20 | 15 | 5 | 2024-03-22 | 2024-03-27 | 4 | 0 | 4 | [20 empty] | 2024-04-01 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | NORTH ADAMS | 590175 | 1247 | 20 | Solar | 09_1015W1 | 2024-02-22 11:03 | 2024-02-23 | 20 | 15 | 5 | 2024-03-22 | 2024-03-26 | 3 | 0 | 3 | [20 empty] | 2024-04-02 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | NORTH ADAMS | 592001 | 1247 | 25 | Solar | 09_1015W1 | 2024-02-22 13:03 | 2024-02-23 | 20 | 15 | 5 | 2024-03-22 | 2024-03-27 | 4 | 0 | 4 | [20 empty] | 2024-04-01 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | NORTH ADAMS | 592039 | 1247 | 22.8 | Solar | 09_1015W1 | 2024-02-22 13:59 | 2024-02-23 | 20 | 15 | 5 | 2024-03-22 | 2024-03-27 | 4 | 0 | 4 | [20 empty] | 2024-04-01 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | NORTH ADAMS | 590327 | 1247 | 20 | Solar | 09_1015W1 | 2024-02-22 11:33 | 2024-02-23 | 20 | 15 | 5 | 2024-03-22 | 2024-03-27 | 4 | 0 | 4 | [20 empty] | 2024-04-01 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | NORTH ADAMS | 592026 | 1247 | 22.8 | Solar | 09_1015W1 | 2024-02-22 13:40 | 2024-02-23 | 20 | 15 | 5 | 2024-03-22 | 2024-03-27 | 4 | 0 | 4 | [20 empty] | 2024-04-01 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | NORTH ADAMS | 590179 | 1247 | 22.8 | Solar | 09_1015W1 | 2024-02-22 11:13 | 2024-02-23 | 20 | 15 | 5 | 2024-03-22 | 2024-03-27 | 4 | 0 | 4 | [20 empty] | 2024-04-01 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | NORTH ADAMS | 590284 | 1247 | 20 | Solar | 09_1015W1 | 2024-02-22 11:28 | 2024-02-23 | 20 | 15 | 5 | 2024-03-22 | 2024-03-27 | 4 | 0 | 4 | [20 empty] | 2024-04-01 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | NORTH ADAMS | 592011 | 1247 | 25 | Solar | 09_1015W1 | 2024-02-22 13:15 | 2024-02-23 | 20 | 15 | 5 | 2024-03-22 | 2024-03-27 | 4 | 0 | 4 | [24 empty] | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | NORTH ADAMS | 591983 | 1247 | 20 | Solar | 09_1015W1 | 2024-02-22 11:58 | 2024-02-23 | 4 | 0 | 4 | 2024-02-29 | 2024-03-25 | 17 | 14 | 3 | [20 empty] | 2024-04-01 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | NORTH ADAMS | 592046 | 1247 | 25 | Solar | 09_1015W1 | 2024-02-22 14:07 | 2024-02-23 | 4 | 0 | 4 | 2024-02-29 | 2024-03-27 | 19 | 17 | 2 | [20 empty] | 2024-04-04 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | NORTH ADAMS | 591947 | 1247 | 20 | Solar | 09_1015W1 | 2024-02-22 10:43 | 2024-02-23 | 4 | 0 | 4 | 2024-02-29 | 2024-03-25 | 17 | 14 | 3 | [20 empty] | 2024-04-01 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LENOX | 593413 | 1240 | 100 | Solar | 09_1103W2 | 2024-03-04 12:16 | 2024-03-05 | 9 | 0 | 9 | 2024-03-18 | 2024-04-08 | 17 | 13 | 4 | [24 empty] | EXP | [9 empty] | Conditional Approval |  | No
National Grid | NEW MARLBOROUGH | 588172 | 1230 | 15.2 | Solar | 09_1109W1 | 2024-02-06 12:25 | 2024-02-07 | 2 | 0 | 2 | 2024-02-09 | 2024-02-21 | 8 | 0 | 8 | [20 empty] | 2024-02-26 |  | 2025-03-04 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | ATTLEBORO | 583657 | 2703 | 8.12 | Solar | 05_9L4 | 2024-02-06 14:37 | 2024-02-07 | 10 | 7 | 3 | 2024-02-21 | 2024-03-01 | 8 | 0 | 8 | [20 empty] | 2024-04-04 |  | 2025-04-11 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | WEST STOCKBRIDGE | 583485 | 1266 | 3.8 | Solar | 09_1109W3 | 2024-03-14 14:24 | 2024-03-15 | 3 | 0 | 3 | 2024-03-20 | 2024-03-21 | 2 | 0 | 2 | 2024-04-03 |  | 9 | 0 | 9 | [5 empty] | 2024-04-03 |  | 9 | 0 | 9 | [9 empty] | EXP | [9 empty] | Supplemental Review |  | Yes
National Grid | GREAT BARRINGTON | 589495 | 1230 | 15.66 | Solar | 09_1109W3 | 2024-02-12 17:35 | 2024-02-13 | 19 | 16 | 3 | 2024-03-11 | 2024-03-14 | 4 | 0 | 4 | [20 empty] | 2024-03-18 |  | 2025-03-19 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | ATHOL | 594763 | 1331 | 4.64 | Solar | 09_702W2 | 2024-03-12 11:06 | 2024-03-13 | 1 | 0 | 1 | 2024-03-14 | 2024-04-03 | 16 | 15 | 1 | [20 empty] | 2024-04-03 |  | 2025-04-05 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | QUINCY | 586029 | 2189 | 3.19 | Solar | 07_1W2 | 2024-02-06 03:21 | 2024-02-07 | 3 | 0 | 3 | 2024-02-12 |  | 45 | 36 | 9 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | SHUTESBURY | 593171 | 1072 | 16 | Solar | 09_704W1 | 2024-02-28 07:18 | 2024-02-29 | 12 | 9 | 3 | 2024-03-18 | 2024-03-21 | 4 | 0 | 4 | [20 empty] | 2024-03-26 |  | 2025-04-12 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | QUINCY | 590352 | 2169 | 7.6 | Solar | 07_1W5 | 2024-02-15 12:36 | 2024-02-16 | 2 | 0 | 2 | 2024-02-21 | 2024-03-06 | 11 | 7 | 4 | [20 empty] | 2024-03-13 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | No
National Grid | QUINCY | 587954 | 2169 | 325 | Natural Gas | 07_1W5 | 2024-02-26 09:10 | 2024-02-27 | 35 | 26 | 9 | [29 empty] | STD | [9 empty] | Application |  | Yes
National Grid | QUINCY | 552146 | 2169 | 360 | Solar | 07_1W6 | 2024-02-16 11:04 | 2024-02-20 | 40 | 31 | 9 | [29 empty] | STD | [9 empty] | Application |  | No
National Grid | QUINCY | 584110 | 2171 | 4950 | Other | 07_1W8 | 2024-02-28 12:01 | 2024-02-29 | 33 | 23 | 10 | [29 empty] | STD | [9 empty] | Application |  | No
National Grid | ORANGE | 588507 | 1364 | 10 | Solar | 09_705W2 | 2024-02-19 11:10 | 2024-02-20 | 2 | 0 | 2 | 2024-02-22 | 2024-03-06 | 10 | 6 | 4 | [20 empty] | 2024-03-12 |  | 2025-03-12 |  | EXP | [8 empty] | 2024-03-22 | Connected |  | No
National Grid | BROCKTON | 591013 | 2301 | 34.6 | Solar | 07_20W10 | 2024-02-19 12:47 | 2024-02-20 | 12 | 9 | 3 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | HOLBROOK | 586498 | 2343 | 10 | Solar | 07_2W1 | 2024-02-06 14:09 | 2024-02-07 | 10 | 7 | 3 | 2024-02-21 |  | 39 | 30 | 9 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | WARE | 595171 | 1082 | 7.6 | Solar | 09_501L2 | 2024-03-13 12:38 | 2024-03-14 | 16 | 12 | 4 | 2024-04-04 | 2024-04-10 | 5 | 0 | 5 | [20 empty] | 2024-04-12 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | ORANGE | 546846 | 1364 | 1494 | Solar | 09_705W3 | 2024-03-08 09:40 | 2024-03-11 | 26 | 18 | 8 | [29 empty] | STD | [9 empty] | Application |  | No
National Grid | RANDOLPH | 586990 | 2368 | 7.6 | Solar | 07_5W1 | 2024-02-19 10:12 | 2024-02-20 | 31 | 28 | 3 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | NORTHAMPTON | 590297 | 1060 | 60 | Solar | 09_901W2 | 2024-02-20 13:02 | 2024-02-21 | 39 | 30 | 9 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | STOUGHTON | 591631 | 2072 | 7.6 | Solar | 07_75W1 | 2024-02-23 15:01 | 2024-02-26 | 6 | 0 | 6 | 2024-03-05 | 2024-03-08 | 4 | 0 | 4 | [20 empty] | 2024-03-15 |  | 2025-04-01 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | FLORENCE | 585752 | 1062 | 5 | Solar | 09_909W1 | 2024-02-23 09:18 | 2024-02-26 | 7 | 5 | 2 | 2024-03-05 | 2024-03-26 | 16 | 14 | 2 | [20 empty] | 2024-03-29 |  | 2025-04-03 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | NORTHAMPTON | 596291 | 1062 | 20 | Solar | 09_909W4 | 2024-03-12 16:07 | 2024-03-13 | 3 | 1 | 2 | 2024-03-18 |  | 20 | 20 | 0 | [21 empty] | 2024-02-27 12:59 |  |  | EXP | [9 empty] | Screening |  | No
National Grid | BRIDGEWATER | 592007 | 2324 | 8.99 | Solar | 07_797W1 | 2024-02-27 12:59 | 2024-02-28 | 5 | 3 | 2 | 2024-03-06 | 2024-03-07 | 2 | 0 | 2 | [20 empty] | 2024-03-11 |  | 2025-03-15 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | WEST BRIDGEWATER | 591477 | 2379 | 15.2 | Solar | 07_797W20 | 2024-02-20 18:29 | 2024-02-21 | 2 | 0 | 2 | 2024-02-23 | 2024-02-29 | 5 | 0 | 5 | [20 empty] | 2024-03-06 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | EAST BRIDGEWATER | 563367 | 2333 | 4980 | Solar | 07_797W23 | 2024-02-28 10:40 | 2024-02-29 | 32 | 22 | 10 | [10 empty] | 2024-04-12 |  | 2 | 0 | 2 | [11 empty] | 2024-03-07 15:15 |  |  | STD | [9 empty] | Screening |  | No
National Grid | BROCKTON | 468616 | 2301 | 4.35 | Solar | 07_911W13 | 2024-03-07 15:15 | 2024-03-08 | 13 | 10 | 3 | 2024-03-26 | 2024-03-25 | 0 | 0 | 0 | [20 empty] | 2024-03-26 |  | 2025-03-27 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | BROCKTON | 595605 | 2301 | 10 | Solar | 07_911W56 | 2024-03-13 11:28 | 2024-03-14 | 4 | 0 | 4 | 2024-03-20 | 2024-03-21 | 2 | 0 | 2 | [20 empty] | 2024-03-26 |  | 2025-04-01 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | BROCKTON | 590773 | 2302 | 6 | Solar | 07_911W56 | 2024-02-27 11:36 | 2024-02-28 | 4 | 0 | 4 | 2024-03-05 | 2024-03-06 | 2 | 0 | 2 | [20 empty] | 2024-03-11 |  | 2025-03-12 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | BRIDGEWATER | 524421 | 2324 | 1180 | Solar | 07_912W21 | 2024-02-15 11:45 | 2024-02-16 | 41 | 25 | 16 | [29 empty] | STD | [9 empty] | Application |  | Yes
National Grid | STOUGHTON | 588598 | 2072 | 20 | Solar | 07_913W17 | 2024-02-07 16:37 | 2024-02-08 | 15 | 13 | 2 | 2024-03-01 | 2024-03-07 | 5 | 0 | 5 | [20 empty] | 2024-03-12 | 2024-02-07 16:36 |  |  | EXP | [9 empty] | Pending Withdraw |  | No
National Grid | STOUGHTON | 574370 | 2072 | 8.448 | Solar | 07_913W47 | 2024-02-07 16:36 | 2024-02-08 | 3 | 1 | 2 | 2024-02-13 | 2024-02-22 | 7 | 0 | 7 | [20 empty] | 2024-02-26 |  | 2025-03-01 | Yes | EXP |  | 2024-04-16 |  | 0 | 0 | 0 |  |  |  | Construction |  | Yes
National Grid | SCITUATE | 594641 | 2066 | 23 | Solar | 07_915W82 | 2024-03-05 14:37 | 2024-03-06 | 2 | 0 | 2 | 2024-03-08 |  | 27 | 23 | 4 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | BROCKTON | 583557 | 2302 | 4.35 | Solar | 07_91W40 | 2024-02-08 15:24 | 2024-02-09 | 2 | 0 | 2 | 2024-02-13 | 2024-02-22 | 7 | 0 | 7 | [20 empty] | 2024-02-26 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | No
National Grid | BROCKTON | 589554 | 2302 | 9.8 | Solar | 07_91W42 | 2024-02-21 18:42 | 2024-02-22 | 27 | 24 | 3 | 2024-04-01 |  | 11 | 9 | 2 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | BROCKTON | 590937 | 2301 | 10 | Solar | 07_91W43 | 2024-02-22 14:27 | 2024-02-23 | 2 | 0 | 2 | 2024-02-27 | 2024-03-04 | 5 | 0 | 5 | [20 empty] | 2024-03-04 |  | 2025-03-13 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | BROCKTON | 591245 | 2301 | 3.78 | Solar | 07_91W43 | 2024-03-06 12:24 | 2024-03-07 | 3 | 0 | 3 | 2024-03-12 | 2024-03-15 | 4 | 1 | 3 | 2024-04-08 |  | 6 | 0 | 6 | [5 empty] | 2024-04-08 |  | 6 | 0 | 6 | [9 empty] | EXP | [9 empty] | Supplemental Review |  | Yes
National Grid | BROCKTON | 586610 | 2301 | 7.6 | Solar | 07_91W49 | 2024-02-09 14:05 | 2024-02-12 | 16 | 13 | 3 | 2024-03-06 | 2024-03-28 | 17 | 14 | 3 | [20 empty] | 2024-04-05 |  | 2025-04-11 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | BROCKTON | 578264 | 2301 | 10 | Solar | 07_91W49 | 2024-02-14 14:45 | 2024-02-15 | 2 | 0 | 2 | 2024-02-20 | 2024-02-22 | 3 | 0 | 3 | [20 empty] | 2024-02-27 |  | 2025-03-01 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | BROCKTON | 588823 | 2301 | 6 | Solar | 07_91W49 | 2024-02-14 19:06 | 2024-02-15 | 3 | 0 | 3 | 2024-02-21 | 2024-03-07 | 12 | 6 | 6 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | BROCKTON | 588333 | 2301 | 6.96 | Solar | 07_91W49 | 2024-02-14 10:55 | 2024-02-15 | 3 | 0 | 3 | 2024-02-21 | 2024-02-20 | 0 | 0 | 0 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | NORTH EASTON | 590129 | 2356 | 10 | Solar | 07_92W54 | 2024-02-15 10:46 | 2024-02-16 | 2 | 0 | 2 | 2024-02-21 | 2024-02-26 | 4 | 0 | 4 | [20 empty] | 2024-03-04 |  | 2025-03-08 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | ROCKLAND | 581852 | 2370 | 3.8 | Solar | 07_93W40 | 2024-02-12 16:17 | 2024-02-13 | 4 | 1 | 3 | 2024-02-16 | 2024-02-26 | 6 | 0 | 6 | [20 empty] | 2024-03-04 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | BEVERLY | 590972 | 1915 | 75 | Solar | 12_12L4 | 2024-02-19 10:27 | 2024-02-20 | 40 | 25 | 15 | [29 empty] | EXP | [9 empty] | Application |  | No
National Grid | LYNN | 593565 | 1902 | 67.3 | Solar | 12_1381 | 2024-02-29 10:25 | 2024-03-01 | 23 | 13 | 10 | 2024-04-02 |  | 10 | 0 | 10 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | MARLBOROUGH | 587963 | 1752 | 325 | Natural Gas | 12_1383 | 2024-02-23 18:27 | 2024-02-26 | 36 | 25 | 11 | [29 empty] | STD | [9 empty] | Application |  | Yes
National Grid | LYNN | 587964 | 1901 | 250 | Natural Gas | 12_1383 | 2024-03-07 10:39 | 2024-03-08 | 27 | 17 | 10 | [29 empty] | STD | [9 empty] | Application |  | Yes
National Grid | SAUGUS | 594652 | 1906 | 7.6 | Solar | 12_16W1 | 2024-03-08 15:55 | 2024-03-11 | 2 | 0 | 2 | 2024-03-13 | 2024-03-21 | 7 | 0 | 7 | 2024-04-08 |  | 6 | 0 | 6 | [5 empty] | 2024-04-08 |  | 6 | 0 | 6 | [6 empty] | 2024-02-16 13:02 |  |  | EXP | [9 empty] | Supplemental Review |  | Yes
National Grid | REVERE | 537674 | 2151 | 7.6 | Solar | 12_16W1 | 2024-02-16 13:02 | 2024-02-20 | 4 | 0 | 4 | 2024-02-26 | 2024-02-27 | 2 | 0 | 2 | [20 empty] | 2024-03-07 |  | 2025-03-13 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | EVERETT | 586800 | 2149 | 6.38 | Solar | 12_16W2 | 2024-02-19 10:48 | 2024-02-20 | 2 | 0 | 2 | 2024-02-22 | 2024-03-29 | 28 | 25 | 3 | [24 empty] | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | MELROSE | 587105 | 2176 | 7.68 | Solar | 12_16W6 | 2024-02-23 14:58 | 2024-02-26 | 13 | 9 | 4 | 2024-03-14 | 2024-03-20 | 5 | 1 | 4 | [20 empty] | 2024-03-27 | 2024-03-04 15:36 | 2025-04-09 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | MELROSE | 588827 | 2176 | 6 | Solar | 12_16W6 | 2024-03-04 15:36 | 2024-03-05 | 3 | 0 | 3 | 2024-03-08 | 2024-03-14 | 5 | 0 | 5 | [20 empty] | 2024-03-20 |  | 2025-04-12 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | EVERETT | 591953 | 2149 | 15.2 | Solar | 12_16W7 | 2024-02-22 11:04 | 2024-02-23 | 37 | 25 | 12 | [26 empty] | 2024-02-29 14:33 |  |  | EXP | [9 empty] | Application |  | Yes
National Grid | EVERETT | 589342 | 2149 | 6 | Solar | 12_16W7 | 2024-02-29 14:33 | 2024-03-01 | 2 | 0 | 2 | 2024-03-05 | 2024-03-06 | 2 | 0 | 2 | [20 empty] | 2024-03-11 |  | 2025-03-12 | Yes | EXP |  | 2024-03-20 |  | 27 | 0 | 27 |  |  |  | Construction |  | Yes
National Grid | MALDEN | 590680 | 2148 | 6 | Solar | 12_16W7 | 2024-02-20 11:17 | 2024-02-21 | 19 | 18 | 1 | 2024-03-18 | 2024-03-21 | 4 | 0 | 4 | [20 empty] | 2024-03-25 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | REVERE | 587620 | 2151 | 11 | Solar | 12_16W8 | 2024-02-09 19:03 | 2024-02-12 | 13 | 11 | 2 | 2024-02-29 | 2024-03-22 | 18 | 15 | 3 | [20 empty] | 2024-03-29 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | BEVERLY | 591448 | 1915 | 20 | Solar | 12_18L1 | 2024-02-20 16:41 | 2024-02-21 | 26 | 23 | 3 | 2024-03-28 | 2024-04-03 | 6 | 4 | 2 | [20 empty] | 2024-04-04 |  | 2025-04-08 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LYNN | 594697 | 1902 | 6 | Solar | 12_22W2 | 2024-03-07 19:53 | 2024-03-08 | 5 | 0 | 5 | 2024-03-15 | 2024-03-21 | 5 | 0 | 5 | [24 empty] | EXP | [9 empty] | Supplemental Review |  | Yes
National Grid | LYNN | 589445 | 1902 | 8.99 | Solar | 12_22W2 | 2024-02-21 19:28 | 2024-02-22 | 3 | 0 | 3 | 2024-02-27 | 2024-03-07 | 8 | 0 | 8 | [24 empty] | EXP | [9 empty] | Supplemental Review |  | No
National Grid | LYNN | 589414 | 1902 | 7.6 | Solar | 12_22W2 | 2024-02-21 19:04 | 2024-02-22 | 3 | 0 | 3 | 2024-02-27 |  | 35 | 25 | 10 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | SAUGUS | 594738 | 1906 | 2.4 | Solar | 12_23W2 | 2024-03-15 00:05 | 2024-03-18 | 12 | 10 | 2 | 2024-04-02 | 2024-04-10 | 7 | 0 | 7 | [24 empty] | EXP | [9 empty] | Conditional Approval |  | No
National Grid | SAUGUS | 588883 | 1906 | 7.6 | Solar | 12_23W3 | 2024-02-29 13:27 | 2024-03-01 | 27 | 25 | 2 | 2024-04-10 |  | 4 | 0 | 4 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | NANTUCKET | 585339 | 2554 | 7.6 | Solar | 04_101L5 | 2024-02-06 11:40 | 2024-02-07 | 3 | 0 | 3 | 2024-02-12 | 2024-02-21 | 7 | 0 | 7 | [20 empty] | 2024-02-26 |  | 2025-03-08 |  | EXP | [9 empty] | Conditional Approval |  | No
National Grid | NANTUCKET | 590905 | 2554 | 25 | Other | 04_101L7 | 2024-03-14 05:11 | 2024-03-15 | 9 | 7 | 2 | 2024-03-28 |  | 13 | 3 | 10 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | WORCESTER | 587958 | 1609 | 825 | Natural Gas | 01_11J331 | 2024-03-07 11:38 | 2024-03-08 | 27 | 17 | 10 | [29 empty] | STD | [9 empty] | Application |  | Yes
National Grid | WORCESTER | 590880 | 1605 | 1.74 | Solar | 01_11J354 | 2024-02-23 15:19 | 2024-02-26 | 1 | 0 | 1 | 2024-02-27 | 2024-03-04 | 5 | 0 | 5 | [20 empty] | 2024-03-04 | 2024-03-01 09:16 | 2025-03-11 |  | EXP | [8 empty] | 2024-03-29 | Connected |  | No
National Grid | WORCESTER | 589307 | 1606 | 7.6 | Solar | 01_14J367 | 2024-03-01 09:16 | 2024-03-04 | 2 | 0 | 2 | 2024-03-06 | 2024-03-07 | 2 | 0 | 2 | [20 empty] | 2024-03-11 |  | 2025-03-22 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | WORCESTER | 593407 | 1609 | 17.6 | Solar | 01_16J2 | 2024-02-29 15:23 | 2024-03-01 | 8 | 5 | 3 | 2024-03-13 | 2024-03-25 | 10 | 7 | 3 | 2024-04-01 |  | 11 | 0 | 11 | [5 empty] | 2024-04-01 |  | 11 | 0 | 11 | [9 empty] | EXP | [9 empty] | Supplemental Review |  | Yes
National Grid | WORCESTER | 539352 | 1602 | 6 | Solar | 01_1J369 | 2024-02-12 12:18 | 2024-02-13 | 9 | 9 | 0 | 2024-02-27 | 2024-03-04 | 5 | 0 | 5 | [20 empty] | 2024-03-05 |  | 2025-04-03 |  | EXP | [8 empty] | 2024-04-09 | Connected |  | Yes
National Grid | HARVARD | 593191 | 1451 | 15.2 | Solar | 01_201W2 | 2024-02-29 11:48 | 2024-03-01 | 4 | 0 | 4 | 2024-03-07 | 2024-03-07 | 1 | 0 | 1 | [20 empty] | 2024-03-14 |  |  |  | EXP | [9 empty] | Pending Withdraw |  | Yes
National Grid | LEOMINSTER | 593162 | 1453 | 3.77 | Solar | 01_207W2 | 2024-03-03 17:56 | 2024-03-04 | 3 | 0 | 3 | 2024-03-07 | 2024-04-02 | 19 | 18 | 1 | [20 empty] | 2024-04-09 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LEOMINSTER | 592388 | 1453 | 7.6 | Solar | 01_207W2 | 2024-03-11 12:53 | 2024-03-12 | 3 | 0 | 3 | 2024-03-15 | 2024-03-20 | 4 | 0 | 4 | [20 empty] | 2024-03-28 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LEOMINSTER | 579807 | 1453 | 6.38 | Solar | 01_207W4 | 2024-02-13 08:42 | 2024-02-14 | 30 | 27 | 3 | 2024-03-28 | 2024-04-04 | 7 | 1 | 6 | [20 empty] | 2024-04-08 |  | 2025-04-09 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | LEOMINSTER | 587583 | 1453 | 7.25 | Solar | 01_207W4 | 2024-02-13 17:44 | 2024-02-14 | 15 | 12 | 3 | 2024-03-07 | 2024-03-19 | 10 | 9 | 1 | [20 empty] | 2024-03-22 | 2024-02-22 14:01 | 2025-04-04 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LEOMINSTER | 590751 | 1453 | 10 | Solar | 01_207W4 | 2024-02-22 14:01 | 2024-02-23 | 2 | 0 | 2 | 2024-02-27 | 2024-03-01 | 4 | 0 | 4 | [20 empty] | 2024-03-06 |  | 2025-03-08 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | DUNSTABLE | 585368 | 1827 | 10 | Solar | 01_210L1 | 2024-02-15 10:59 | 2024-02-16 | 8 | 4 | 4 | 2024-02-29 | 2024-03-04 | 3 | 0 | 3 | [20 empty] | 2024-03-06 |  | 2025-03-20 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | DUNSTABLE | 594891 | 1827 | 20 | Solar | 01_210L1 | 2024-03-06 13:23 | 2024-03-07 | 4 | 1 | 3 | 2024-03-13 | 2024-03-15 | 3 | 0 | 3 | [20 empty] | 2024-03-18 | 2024-03-11 12:23 | 2025-03-26 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | DUNSTABLE | 588595 | 1827 | 9.86 | Solar | 01_210L1 | 2024-03-11 12:23 | 2024-03-12 | 2 | 0 | 2 | 2024-03-14 | 2024-03-18 | 3 | 0 | 3 | [20 empty] | 2024-03-21 | 2024-02-23 11:50 | 2025-03-29 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | CLINTON | 589386 | 1510 | 7.6 | Solar | 01_216W2 | 2024-02-23 11:50 | 2024-02-26 | 6 | 0 | 6 | 2024-03-05 | 2024-03-08 | 4 | 0 | 4 | [20 empty] | 2024-03-15 | 2024-02-28 13:40 | 2025-03-21 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | CLINTON | 588934 | 1510 | 6 | Solar | 01_216W3 | 2024-02-28 13:40 | 2024-02-29 | 3 | 0 | 3 | 2024-03-05 | 2024-03-07 | 3 | 0 | 3 | [20 empty] | 2024-03-11 |  | 2025-03-12 | Yes | EXP | [9 empty] | Construction |  | Yes
National Grid | GRAFTON | 594840 | 1519 | 15.2 | Solar | 01_304W1 | 2024-03-06 11:48 | 2024-03-07 | 3 | 0 | 3 | 2024-03-12 |  | 25 | 21 | 4 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | LOWELL | 587969 | 1852 | 325 | Natural Gas | 14_306 | 2024-02-26 11:40 | 2024-02-27 | 35 | 26 | 9 | [29 empty] | STD | [9 empty] | Application |  | Yes
National Grid | NORTH ANDOVER | 524407 | 1845 | 2000 | Solar | 14_43L7 | 2024-02-15 11:50 | 2024-02-16 | 31 | 25 | 6 | [29 empty] | STD | [9 empty] | Pending Withdraw |  | Yes
National Grid | PLAINVILLE | 588469 | 2762 | 6 | Solar | 05_3451W3 | 2024-02-15 09:24 | 2024-02-16 | 1 | 0 | 1 | 2024-02-20 | 2024-02-27 | 6 | 0 | 6 | [20 empty] | 2024-02-29 |  | 2025-03-11 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | NORTH GRAFTON | 586964 | 1536 | 4000 | Other | 01_328W2 | 2024-02-05 15:48 | 2024-02-06 | 32 | 25 | 7 | [29 empty] | STD | [9 empty] | Pending Withdraw |  | No
National Grid | TEWKSBURY | 594235 | 1876 | 23 | Solar | 14_20L2 | 2024-03-04 12:36 | 2024-03-05 | 2 | 0 | 2 | 2024-03-07 | 2024-03-07 | 1 | 0 | 1 | [20 empty] | 2024-03-12 |  | 2025-03-15 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | WORCESTER | 595137 | 1605 | 8.7 | Solar | 01_24W2 | 2024-03-29 09:42 | 2024-04-01 | 4 | 0 | 4 | 2024-04-05 | 2024-04-12 | 6 | 0 | 6 | [24 empty] | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | WORCESTER | 598070 | 1606 | 7.6 | Solar | 01_24W2 | 2024-03-21 18:57 | 2024-03-22 | 2 | 0 | 2 | 2024-03-26 | 2024-03-28 | 3 | 0 | 3 | [20 empty] | 2024-04-04 |  | 2025-04-11 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LOWELL | 583609 | 1851 | 6.67 | Solar | 14_2L2 | 2024-04-09 13:19 | 2024-04-10 | 1 | 0 | 1 | 2024-04-11 |  | 3 | 0 | 3 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | LYNN | 599918 | 1904 | 6 | Solar | 12_24W2 | 2024-04-09 11:30 | 2024-04-10 | 4 | 0 | 4 | [29 empty] | EXP | [9 empty] | Application |  | No
National Grid | LYNN | 599697 | 1904 | 10 | Solar | 12_24W2 | 2024-04-12 11:28 | 2024-04-16 | 0 | 0 | 0 | 2024-04-16 |  | 0 | 0 | 0 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | METHUEN | 596597 | 1844 | 6 | Solar | 14_74L1 | 2024-03-18 13:24 | 2024-03-19 | 1 | 0 | 1 | 2024-03-20 | 2024-03-22 | 3 | 0 | 3 | [20 empty] | 2024-03-26 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | METHUEN | 597545 | 1844 | 7.6 | Solar | 14_74L1 | 2024-03-21 11:56 | 2024-03-22 | 17 | 14 | 3 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | METHUEN | 600465 | 1844 | 10 | Solar | 14_74L1 | 2024-04-04 12:20 | 2024-04-05 | 7 | 6 | 1 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | WORCESTER | 601631 | 1606 | 3.8 | Solar | 01_24W4 | 2024-04-10 12:42 | 2024-04-11 | 1 | 0 | 1 | 2024-04-12 |  | 2 | 0 | 2 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | LAWRENCE | 567261 | 1841 | 5 | Solar | 14_74L3 | 2024-03-28 11:30 | 2024-03-29 | 12 | 9 | 3 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | METHUEN | 597076 | 1844 | 8.12 | Solar | 14_74L3 | 2024-03-22 10:47 | 2024-03-25 | 3 | 0 | 3 | 2024-03-28 |  | 13 | 12 | 1 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | LOWELL | 601232 | 1852 | 6 | Solar | 14_3L4 | 2024-04-08 17:47 | 2024-04-09 | 2 | 0 | 2 | 2024-04-11 |  | 3 | 0 | 3 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | LYNN | 596319 | 1905 | 3.8 | Solar | 12_29W1 | 2024-03-20 13:11 | 2024-03-21 | 3 | 0 | 3 | 2024-03-26 | 2024-03-28 | 3 | 0 | 3 | [20 empty] | 2024-04-03 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | METHUEN | 593130 | 1844 | 10 | Solar | 14_74L4 | 2024-04-03 14:13 | 2024-04-04 | 2 | 0 | 2 | 2024-04-08 |  | 6 | 0 | 6 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | LYNN | 600626 | 1905 | 3.8 | Solar | 12_29W1 | 2024-04-10 11:45 | 2024-04-11 | 3 | 0 | 3 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | METHUEN | 595995 | 1844 | 7.6 | Solar | 14_43L4 | 2024-04-05 14:18 | 2024-04-08 | 6 | 2 | 4 | 2024-04-16 |  | 0 | 0 | 0 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | WORCESTER | 596342 | 1604 | 8.8 | Solar | 01_27W1 | 2024-03-28 11:20 | 2024-03-29 | 7 | 3 | 4 | 2024-04-09 |  | 5 | 0 | 5 | [24 empty] | EXP | [9 empty] | Screening |  | No
National Grid | LAWRENCE | 597079 | 1841 | 2.32 | Solar | 14_43L4 | 2024-03-22 04:34 | 2024-03-25 | 5 | 2 | 3 | 2024-04-01 |  | 11 | 5 | 6 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | WORCESTER | 600630 | 1604 | 6 | Solar | 01_27W1 | 2024-04-04 12:07 | 2024-04-05 | 2 | 0 | 2 | 2024-04-09 |  | 5 | 0 | 5 | [24 empty] | EXP | [9 empty] | Screening |  | No
National Grid | WORCESTER | 600309 | 1604 | 5 | Solar | 01_27W1 | 2024-04-03 17:56 | 2024-04-04 | 2 | 0 | 2 | 2024-04-08 |  | 6 | 1 | 5 | [24 empty] | EXP | [9 empty] | Screening |  | No
National Grid | LAWRENCE | 597509 | 1841 | 13.325 | Solar | 14_43L4 | 2024-04-03 10:53 | 2024-04-04 | 8 | 6 | 2 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | LYNN | 602833 | 1904 | 3.8 | Solar | 12_29W3 | 2024-04-10 13:12 | 2024-04-11 | 1 | 0 | 1 | 2024-04-12 |  | 2 | 0 | 2 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | LYNN | 595104 | 1905 | 3.8 | Solar | 12_29W3 | 2024-04-09 15:21 | 2024-04-10 | 1 | 0 | 1 | 2024-04-11 |  | 3 | 0 | 3 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | HAVERHILL | 593129 | 1832 | 7.6 | Solar | 14_43L6 | 2024-03-16 09:18 | 2024-03-18 | 1 | 0 | 1 | 2024-03-19 | 2024-03-26 | 6 | 1 | 5 | 2024-04-16 |  | 0 | 0 | 0 | [5 empty] | 2024-04-16 |  | 0 | 0 | 0 | [6 empty] | 2024-03-25 13:27 |  |  | EXP | [9 empty] | Supplemental Review |  | Yes
National Grid | LYNN | 599284 | 1902 | 10 | Battery Add-On | 12_29W4 | 2024-03-25 13:27 | 2024-03-26 | 3 | 1 | 2 | 2024-03-29 | 2024-04-01 | 2 | 0 | 2 | [20 empty] | 2024-04-08 |  | 2025-04-09 | Yes | EXP | [9 empty] | Design |  | No
National Grid | FALL RIVER | 599193 | 2720 | 10 | Solar | 05_28W40 | 2024-04-03 19:08 | 2024-04-04 | 2 | 0 | 2 | 2024-04-08 |  | 6 | 1 | 5 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | LYNN | 601269 | 1902 | 11.4 | Solar | 12_29W5 | 2024-04-09 15:48 | 2024-04-10 | 4 | 0 | 4 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | WESTMINSTER | 599345 | 1473 | 18.7 | Battery Add-On | 01_602W2 | 2024-03-26 14:53 | 2024-03-27 | 14 | 12 | 2 | [29 empty] | EXP | [9 empty] | Application |  | No
National Grid | NEWBURYPORT | 602560 | 1950 | 15.2 | Solar | 14_47L2 | 2024-04-08 17:01 | 2024-04-09 | 5 | 3 | 2 | [29 empty] | EXP | [9 empty] | Application |  | No
National Grid | WEST NEWBURY | 600694 | 1985 | 15.2 | Solar | 14_47L2 | 2024-04-05 12:18 | 2024-04-08 | 2 | 0 | 2 | 2024-04-10 | 2024-04-15 | 4 | 0 | 4 | [24 empty] | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | SALEM | 597666 | 1970 | 3.8 | Solar | 12_2W1 | 2024-03-26 16:57 | 2024-03-27 | 4 | 0 | 4 | 2024-04-02 | 2024-04-04 | 3 | 0 | 3 | [20 empty] | 2024-04-10 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | METHUEN | 597814 | 1844 | 14.3 | Solar | 14_75L6 | 2024-03-28 11:19 | 2024-03-29 | 4 | 2 | 2 | 2024-04-03 |  | 9 | 2 | 7 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | REVERE | 601237 | 2151 | 5 | Solar | 12_35J3 | 2024-04-09 14:05 | 2024-04-10 | 4 | 0 | 4 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | LOWELL | 598862 | 1854 | 7.6 | Solar | 14_77L1 | 2024-04-05 15:06 | 2024-04-08 | 5 | 0 | 5 | 2024-04-16 |  | 0 | 0 | 0 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | ANDOVER | 597748 | 1810 | 1.45 | Solar | 14_50L1 | 2024-04-02 23:00 | 2024-04-03 | 9 | 8 | 1 | [29 empty] | EXP | [9 empty] | Application |  | No
National Grid | ANDOVER | 600002 | 1810 | 23 | Solar | 14_50L1 | 2024-03-27 17:09 | 2024-03-28 | 2 | 0 | 2 | 2024-04-01 | 2024-04-12 | 11 | 6 | 5 | [24 empty] | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | GARDNER | 593486 | 1440 | 7.6 | Solar | 01_607W1 | 2024-03-18 13:12 | 2024-03-19 | 3 | 0 | 3 | 2024-03-22 | 2024-03-28 | 5 | 0 | 5 | [20 empty] | 2024-04-04 |  | 2025-04-11 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | TYNGSBORO | 599934 | 1879 | 15.2 | Solar | 14_77L3 | 2024-03-27 15:10 | 2024-03-28 | 3 | 0 | 3 | 2024-04-02 |  | 10 | 1 | 9 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | METHUEN | 598618 | 1844 | 9.56 | Solar | 14_53J4 | 2024-03-27 18:00 | 2024-03-28 | 5 | 2 | 3 | 2024-04-04 |  | 8 | 4 | 4 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | EVERETT | 596442 | 2149 | 7.6 | Solar | 12_37W6 | 2024-03-21 16:57 | 2024-03-22 | 4 | 0 | 4 | 2024-03-28 |  | 13 | 7 | 6 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | EVERETT | 591336 | 2149 | 10 | Solar | 12_37W6 | 2024-03-27 17:11 | 2024-03-28 | 3 | 0 | 3 | 2024-04-02 | 2024-04-03 | 2 | 0 | 2 | [20 empty] | 2024-04-04 |  |  |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | GARDNER | 600531 | 1440 | 7.6 | Solar | 01_607W4 | 2024-04-04 13:05 | 2024-04-05 | 4 | 0 | 4 | 2024-04-11 |  | 3 | 0 | 3 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | GARDNER | 601448 | 1440 | 3.8 | Solar | 01_607W4 | 2024-04-10 11:09 | 2024-04-11 | 3 | 0 | 3 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | DRACUT | 602555 | 1826 | 12 | Battery Add-On | 14_78L3 | 2024-04-10 16:58 | 2024-04-11 | 3 | 0 | 3 | [29 empty] | EXP | [9 empty] | Application |  | No
National Grid | LYNN | 599564 | 1902 | 3.8 | Solar | 12_3J903 | 2024-04-04 12:43 | 2024-04-05 | 2 | 0 | 2 | 2024-04-09 |  | 5 | 0 | 5 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | WESTMINSTER | 598052 | 1473 | 15.2 | Solar | 01_609W1 | 2024-03-23 10:39 | 2024-03-25 | 5 | 2 | 3 | 2024-04-01 | 2024-04-02 | 2 | 0 | 2 | [20 empty] | 2024-04-04 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | NORTH ANDOVER | 598369 | 1845 | 14.208 | Solar | 14_55L2 | 2024-04-15 14:03 | 2024-04-16 | 0 | 0 | 0 | [29 empty] | EXP | [9 empty] | Application |  | No
National Grid | NORTH ANDOVER | 600029 | 1845 | 25.2 | Battery Add-On | 14_56L2 | 2024-03-27 18:52 | 2024-03-28 | 2 | 0 | 2 | 2024-04-01 | 2024-04-05 | 5 | 0 | 5 | [20 empty] | 2024-04-11 |  |  |  | EXP | [9 empty] | Conditional Approval |  | No
National Grid | SALISBURY | 574923 | 1952 | 10 | Solar | 14_7L4 | 2024-04-03 10:04 | 2024-04-04 | 5 | 3 | 2 | 2024-04-10 |  | 4 | 0 | 4 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | LAWRENCE | 593454 | 1843 | 6 | Solar | 14_8L1 | 2024-03-25 14:39 | 2024-03-26 | 2 | 0 | 2 | 2024-03-28 | 2024-03-29 | 2 | 0 | 2 | [20 empty] | 2024-04-02 |  | 2025-04-04 |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LAWRENCE | 595986 | 1841 | 6 | Solar | 14_8L2 | 2024-03-25 15:54 | 2024-03-26 | 2 | 0 | 2 | 2024-03-28 | 2024-04-08 | 8 | 1 | 7 | [20 empty] | 2024-04-15 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LAWRENCE | 595649 | 1841 | 10 | Solar | 14_8L2 | 2024-03-26 12:40 | 2024-03-27 | 4 | 0 | 4 | 2024-04-02 | 2024-04-04 | 4 | 1 | 3 | [20 empty] | 2024-04-10 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LAWRENCE | 595888 | 1841 | 7.6 | Solar | 14_8L2 | 2024-03-29 18:08 | 2024-04-01 | 3 | 0 | 3 | 2024-04-04 | 2024-04-10 | 5 | 0 | 5 | [20 empty] | 2024-04-14 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LAWRENCE | 599574 | 1841 | 5.85 | Solar | 14_8L2 | 2024-04-01 11:21 | 2024-04-02 | 3 | 1 | 2 | 2024-04-04 | 2024-04-12 | 7 | 0 | 7 | [24 empty] | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | WESTBOROUGH | 599975 | 1581 | 11.6 | Solar | 05_312W4 | 2024-04-04 16:01 | 2024-04-05 | 7 | 3 | 4 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | OXFORD | 602577 | 1540 | 10 | Solar | 01_406L4 | 2024-04-12 17:35 | 2024-04-16 | 0 | 0 | 0 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | BILLERICA | 599440 | 1821 | 15.744 | Solar | 14_92L1 | 2024-03-27 16:38 | 2024-03-28 | 3 | 0 | 3 | 2024-04-02 | 2024-04-12 | 9 | 0 | 9 | [24 empty] | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | WORCESTER | 599616 | 1603 | 7.6 | Solar | 01_6J316 | 2024-04-04 13:23 | 2024-04-05 | 2 | 0 | 2 | 2024-04-09 |  | 5 | 1 | 4 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | WORCESTER | 595595 | 1603 | 10 | Solar | 01_6W1 | 2024-03-28 17:20 | 2024-03-29 | 2 | 0 | 2 | 2024-04-02 | 2024-04-03 | 3 | 2 | 1 | [20 empty] | 2024-04-05 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | BOLTON | 598176 | 1740 | 11.5 | Solar | 01_216W6 | 2024-03-20 10:55 | 2024-03-21 | 16 | 13 | 3 | 2024-04-12 |  | 2 | 0 | 2 | [24 empty] | EXP | [9 empty] | Screening |  | No
National Grid | WORCESTER | 600333 | 1607 | 10 | Solar | 01_8J365 | 2024-03-29 16:30 | 2024-04-01 | 2 | 0 | 2 | 2024-04-03 |  | 9 | 3 | 6 | [21 empty] | 2019-11-04 13:24 |  |  | EXP | [9 empty] | Screening |  | Yes
National Grid | BOLTON | 263665 | 1740 | 12.6 | Solar | 01_216W6 | 2019-11-04 13:24 | 2019-11-05 | 3 | 0 | 3 | 2019-11-12 | 2019-11-13 | 1 | 0 | 1 | [20 empty] | 2019-11-19 |  | 2020-11-04 | Yes | EXP | [8 empty] | 2020-08-20 | Connected |  | No
National Grid | DUDLEY | 595397 | 1571 | 7.296 | Solar | 01_412L4 | 2024-04-01 11:19 | 2024-04-02 | 2 | 0 | 2 | 2024-04-04 | 2024-04-11 | 6 | 0 | 6 | [24 empty] | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | WESTBOROUGH | 597594 | 1581 | 120 | Solar | 05_314W4 | 2024-03-18 18:54 | 2024-03-19 | 20 | 15 | 5 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | GLOUCESTER | 593568 | 1930 | 24.86 | Solar | 12_52L1 | 2024-03-18 15:15 | 2024-03-19 | 1 | 0 | 1 | 2024-03-20 | 2024-03-19 | 0 | 0 | 0 | [20 empty] | 2024-03-25 |  | 2025-03-26 |  | EXP | [9 empty] | Completion Documents |  | No
National Grid | WORCESTER | 602571 | 1604 | 6 | Solar | 01_9J303 | 2024-04-10 12:18 | 2024-04-11 | 3 | 0 | 3 | 2024-04-16 |  | 0 | 0 | 0 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | WORCESTER | 595193 | 1604 | 7.6 | Solar | 01_9J303 | 2024-03-27 17:48 | 2024-03-28 | 2 | 0 | 2 | 2024-04-01 | 2024-04-10 | 8 | 0 | 8 | [24 empty] | EXP | [9 empty] | Supplemental Review |  | Yes
National Grid | WORCESTER | 595739 | 1604 | 10 | Solar | 01_9J307 | 2024-03-15 17:11 | 2024-03-18 | 21 | 18 | 3 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | WORCESTER | 601301 | 1604 | 3.8 | Solar | 01_9J337 | 2024-04-10 11:28 | 2024-04-11 | 3 | 2 | 1 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | DUDLEY | 592892 | 1571 | 6 | Solar | 01_412L5 | 2024-03-21 15:16 | 2024-03-22 | 2 | 0 | 2 | 2024-03-26 | 2024-04-04 | 8 | 0 | 8 | [20 empty] | 2024-04-10 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | BEVERLY | 596850 | 1915 | 3.77 | Solar | 12_72L1 | 2024-03-19 10:51 | 2024-03-20 | 2 | 1 | 1 | 2024-03-22 | 2024-04-01 | 8 | 6 | 2 | [20 empty] | 2024-04-05 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | METHUEN | 534198 | 1844 | 6.912 | Solar | 14_5J40 | 2024-03-20 09:07 | 2024-03-21 | 18 | 15 | 3 | 2024-04-16 |  | 0 | 0 | 0 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | METHUEN | 596274 | 1844 | 5 | Solar | 14_5J40 | 2024-04-01 15:25 | 2024-04-02 | 10 | 8 | 2 | [26 empty] | 2024-03-19 10:44 |  |  | EXP | [9 empty] | Application |  | Yes
National Grid | METHUEN | 596892 | 1844 | 5 | Solar | 14_5J42 | 2024-03-19 10:44 | 2024-03-20 | 4 | 0 | 4 | 2024-03-26 | 2024-03-28 | 3 | 0 | 3 | [20 empty] | 2024-04-04 |  | 2025-04-12 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | MARLBOROUGH | 597028 | 1752 | 57 | Solar | 05_317W6 | 2024-03-22 10:49 | 2024-04-11 | 2 | 0 | 2 | [29 empty] | EXP | [9 empty] | Application |  | No
National Grid | METHUEN | 588136 | 1844 | 7.6 | Solar | 14_5J43 | 2024-04-05 12:25 | 2024-04-08 | 6 | 3 | 3 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | NEWBURYPORT | 603110 | 1950 | 46 | Solar | 14_60L1 | 2024-04-10 16:29 | 2024-04-11 | 3 | 1 | 2 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | STURBRIDGE | 602467 | 1566 | 9.765 | Solar | 01_413L2 | 2024-04-12 17:23 | 2024-04-16 | 0 | 0 | 0 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | SOUTHBRIDGE | 601302 | 1550 | 10 | Solar | 01_413L2 | 2024-04-04 15:32 | 2024-04-05 | 4 | 0 | 4 | 2024-04-11 |  | 3 | 0 | 3 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | REVERE | 600033 | 2151 | 10 | Solar | 12_7W2 | 2024-03-29 13:32 | 2024-04-01 | 11 | 8 | 3 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | BLACKSTONE | 587149 | 1504 | 7.6 | Solar | 05_108W60 | 2024-03-26 19:58 | 2024-03-27 | 14 | 13 | 1 | [25 empty] | 2024-02-06 |  |  |  | EXP | [9 empty] | Application |  | Yes
National Grid | LAWRENCE | 597488 | 1843 | 10.075 | Solar | 14_61L1 | 2024-03-19 16:37 | 2024-03-20 | 7 | 5 | 2 | 2024-03-29 | 2024-04-12 | 11 | 2 | 9 | [24 empty] | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | BELLINGHAM | 599414 | 2019 | 7.6 | Solar | 05_108W60 | 2024-03-27 19:33 | 2024-03-28 | 3 | 0 | 3 | 2024-04-02 |  | 10 | 1 | 9 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | REVERE | 596446 | 2151 | 6 | Solar | 12_7W4 | 2024-04-01 12:52 | 2024-04-02 | 2 | 0 | 2 | 2024-04-04 | 2024-04-09 | 4 | 0 | 4 | [20 empty] | 2024-04-12 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | HARVARD | 601438 | 1451 | 25 | Solar | 01_225W1 | 2024-04-03 11:35 | 2024-04-04 | 8 | 6 | 2 | [29 empty] | EXP | [9 empty] | Application |  | No
National Grid | LAWRENCE | 595150 | 1843 | 7.6 | Solar | 14_61L3 | 2024-03-29 11:50 | 2024-04-01 | 11 | 7 | 4 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | LAWRENCE | 600825 | 1843 | 7.6 | Solar | 14_61L3 | 2024-04-04 11:28 | 2024-04-05 | 7 | 3 | 4 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | WHITINSVILLE | 600585 | 1588 | 10 | Solar | 05_320W3 | 2024-04-04 13:37 | 2024-04-05 | 4 | 0 | 4 | 2024-04-11 |  | 3 | 0 | 3 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | FALL RIVER | 594405 | 2724 | 5 | Solar | 05_115W42 | 2024-03-19 12:15 | 2024-03-20 | 4 | 0 | 4 | 2024-03-26 | 2024-04-04 | 8 | 0 | 8 | [20 empty] | 2024-04-10 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LOWELL | 599266 | 1852 | 6 | Solar | 14_16L2 | 2024-03-26 18:20 | 2024-03-27 | 4 | 0 | 4 | 2024-04-02 |  | 10 | 0 | 10 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | STURBRIDGE | 594094 | 1566 | 9.86 | Solar | 01_413L7 | 2024-03-19 11:27 | 2024-03-20 | 19 | 16 | 3 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | LOWELL | 598212 | 1851 | 3.8 | Solar | 14_16L3 | 2024-03-21 19:24 | 2024-03-22 | 3 | 0 | 3 | 2024-03-27 | 2024-04-01 | 4 | 0 | 4 | [20 empty] | 2024-04-05 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LOWELL | 598082 | 1851 | 3.8 | Solar | 14_16L3 | 2024-03-21 17:31 | 2024-03-22 | 3 | 0 | 3 | 2024-03-27 | 2024-04-01 | 4 | 0 | 4 | [20 empty] | 2024-04-05 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | WESTPORT | 601783 | 2790 | 24.8 | Solar | 05_115W45 | 2024-04-04 12:39 | 2024-04-05 | 2 | 0 | 2 | 2024-04-09 |  | 5 | 0 | 5 | [24 empty] | EXP | [9 empty] | Screening |  | No
National Grid | FALL RIVER | 598026 | 2721 | 2.9 | Solar | 05_115W52 | 2024-04-11 12:02 | 2024-04-12 | 2 | 0 | 2 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | METHUEN | 599558 | 1844 | 10.075 | Solar | 14_63L2 | 2024-04-05 09:07 | 2024-04-08 | 3 | 1 | 2 | 2024-04-10 | 2024-04-15 | 4 | 0 | 4 | [20 empty] | 2024-04-15 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | PEPPERELL | 599998 | 1463 | 6 | Solar | 01_226L2 | 2024-04-01 17:15 | 2024-04-02 | 2 | 0 | 2 | 2024-04-04 |  | 8 | 3 | 5 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | SHIRLEY | 589295 | 1464 | 14.21 | Solar | 01_227W1 | 2024-03-22 12:28 | 2024-03-25 | 3 | 0 | 3 | 2024-03-28 | 2024-03-29 | 2 | 0 | 2 | [20 empty] | 2024-04-05 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LANCASTER | 598492 | 1523 | 20 | Solar | 01_227W1 | 2024-03-21 12:58 | 2024-03-22 | 8 | 6 | 2 | 2024-04-03 |  | 9 | 2 | 7 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | LOWELL | 600344 | 1854 | 3 | Solar | 14_21L3 | 2024-04-05 13:44 | 2024-04-08 | 3 | 1 | 2 | 2024-04-10 |  | 4 | 0 | 4 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | LOWELL | 601226 | 1854 | 5 | Solar | 14_21L3 | 2024-04-09 15:43 | 2024-04-10 | 4 | 0 | 4 | 2024-04-16 |  | 0 | 0 | 0 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | LAWRENCE | 600180 | 1841 | 6 | Solar | 14_6J6 | 2024-04-06 10:29 | 2024-04-08 | 2 | 0 | 2 | 2024-04-10 |  | 4 | 0 | 4 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | BROCKTON | 595125 | 2301 | 7.6 | Solar | 07_91W49 | 2024-04-10 17:00 | 2024-04-11 | 3 | 0 | 3 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | WORCESTER | 599599 | 1602 | 7.6 | Solar | 01_23W3 | 2024-03-28 17:56 | 2024-03-29 | 2 | 0 | 2 | 2024-04-02 | 2024-04-12 | 9 | 0 | 9 | [20 empty] | 2024-04-15 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | QUINCY | 573913 | 2169 | 7.25 | Solar | 07_1W5 | 2024-03-21 19:36 | 2024-03-22 | 2 | 0 | 2 | 2024-03-26 | 2024-04-04 | 8 | 5 | 3 | [24 empty] | EXP | [9 empty] | Supplemental Review |  | Yes
National Grid | WORCESTER | 595776 | 1605 | 3.8 | Solar | 01_24W1 | 2024-03-15 16:51 | 2024-03-18 | 1 | 0 | 1 | 2024-03-19 | 2024-03-21 | 3 | 0 | 3 | [20 empty] | 2024-03-22 |  | 2025-03-25 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | AMESBURY | 603133 | 1913 | 20 | Solar | 14_275L4 | 2024-04-10 17:48 | 2024-04-11 | 3 | 0 | 3 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | BILLERICA | 597903 | 1821 | 16.4 | Solar | 14_70L8 | 2024-03-19 18:29 | 2024-03-20 | 2 | 0 | 2 | 2024-03-22 | 2024-03-27 | 4 | 0 | 4 | [20 empty] | 2024-04-03 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | MILFORD | 601386 | 1757 | 14.175 | Solar | 05_335W2 | 2024-04-15 08:28 | 2024-04-16 | 0 | 0 | 0 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | EAST LONGMEADOW | 601540 | 1028 | 7.6 | Solar | 09_139L5 | 2024-04-05 10:08 | 2024-04-08 | 2 | 0 | 2 | 2024-04-10 |  | 4 | 0 | 4 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | RANDOLPH | 599536 | 2368 | 6 | Solar | 07_5W3 | 2024-03-26 18:30 | 2024-03-27 | 1 | 0 | 1 | 2024-03-28 |  | 13 | 5 | 8 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | ABINGTON | 596183 | 2351 | 7.6 | Solar | 07_93W42 | 2024-04-03 15:30 | 2024-04-04 | 1 | 0 | 1 | 2024-04-05 |  | 7 | 2 | 5 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | WHEELWRIGHT | 602802 | 1094 | 6 | Solar | 09_501L2 | 2024-04-13 09:18 | 2024-04-16 | 0 | 0 | 0 | 2024-04-16 |  | 0 | 0 | 0 | [24 empty] | EXP | [9 empty] | Screening |  | No
National Grid | WARE | 588156 | 1082 | 6972 | Solar | 09_501L2 | 2024-04-12 13:27 | 2024-04-16 | 0 | 0 | 0 | [29 empty] | STD | [9 empty] | Application |  | No
National Grid | BROCKTON | 600250 | 2301 | 6.67 | Solar | 07_94W40 | 2024-03-29 16:48 | 2024-04-01 | 4 | 2 | 2 | 2024-04-04 |  | 8 | 0 | 8 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | BROCKTON | 589714 | 2301 | 980 | Solar | 07_94W41 | 2024-03-20 15:12 | 2024-03-21 | 18 | 12 | 6 | [29 empty] | STD | [9 empty] | Application |  | No
National Grid | BROCKTON | 592814 | 2302 | 9.984 | Solar | 07_69J1 | 2024-03-18 12:51 | 2024-03-19 | 3 | 1 | 2 | 2024-03-21 | 2024-03-21 | 1 | 0 | 1 | [20 empty] | 2024-03-26 |  | 2025-03-28 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | BROCKTON | 601320 | 2302 | 7.6 | Solar | 07_69J1 | 2024-04-10 13:00 | 2024-04-11 | 3 | 0 | 3 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | STOUGHTON | 599024 | 2072 | 7.6 | Solar | 07_94W43 | 2024-04-01 16:53 | 2024-04-02 | 2 | 0 | 2 | 2024-04-04 |  | 8 | 3 | 5 | [21 empty] | 2024-03-18 07:26 |  |  | EXP | [9 empty] | Screening |  | Yes
National Grid | PALMER | 588858 | 1069 | 7.6 | Solar | 09_503L1 | 2024-03-18 07:26 | 2024-03-19 | 1 | 0 | 1 | 2024-03-20 | 2024-03-28 | 7 | 3 | 4 | [20 empty] | 2024-04-03 |  | 2025-04-05 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | STOUGHTON | 600322 | 2072 | 15.2 | Solar | 07_94W44 | 2024-03-29 12:34 | 2024-04-01 | 11 | 10 | 1 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | STOUGHTON | 592939 | 2072 | 12 | Solar | 07_75W1 | 2024-03-26 15:06 | 2024-03-27 | 7 | 3 | 4 | 2024-04-04 |  | 8 | 3 | 5 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | HANSON | 597316 | 2341 | 6 | Solar | 07_95W3 | 2024-04-04 11:24 | 2024-04-05 | 7 | 6 | 1 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | HAMPDEN | 600823 | 1036 | 6.96 | Solar | 09_507L2 | 2024-04-05 12:02 | 2024-04-08 | 6 | 4 | 2 | 2024-04-16 |  | 0 | 0 | 0 | [24 empty] | EXP | [9 empty] | Screening |  | No
National Grid | EAST BRIDGEWATER | 600324 | 2333 | 12 | Solar | 07_797W1 | 2024-04-03 08:51 | 2024-04-04 | 2 | 0 | 2 | 2024-04-08 |  | 6 | 0 | 6 | [24 empty] | EXP | [9 empty] | Screening |  | No
National Grid | WEST BRIDGEWATER | 546935 | 2379 | 4000 | Other | 07_797W19 | 2024-03-21 15:04 | 2024-03-22 | 17 | 13 | 4 | [29 empty] | STD | [9 empty] | Application |  | No
National Grid | BRIDGEWATER | 594128 | 2333 | 12.915 | Solar | 07_797W23 | 2024-03-21 09:01 | 2024-03-22 | 4 | 2 | 2 | 2024-03-28 | 2024-04-02 | 4 | 0 | 4 | [20 empty] | 2024-04-05 |  | 2025-04-11 |  | EXP | [9 empty] | Meter Installation |  | Yes
National Grid | EAST BRIDGEWATER | 597731 | 2333 | 10.44 | Solar | 07_797W23 | 2024-03-21 15:35 | 2024-03-22 | 2 | 0 | 2 | 2024-03-26 | 2024-04-04 | 8 | 0 | 8 | [20 empty] | 2024-04-08 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | EAST BRIDGEWATER | 598158 | 2333 | 10 | Solar | 07_797W23 | 2024-03-26 17:11 | 2024-03-27 | 4 | 0 | 4 | 2024-04-02 | 2024-04-11 | 8 | 0 | 8 | [21 empty] | 2024-03-16 10:51 |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | RANDOLPH | 594854 | 2368 | 5 | Solar | 07_97W1 | 2024-03-16 10:51 | 2024-03-18 | 2 | 0 | 2 | 2024-03-20 | 2024-03-20 | 1 | 0 | 1 | [20 empty] | 2024-03-21 |  | 2025-04-08 | Yes | EXP | [9 empty] | Design |  | No
National Grid | RANDOLPH | 598614 | 2368 | 7.6 | Solar | 07_97W1 | 2024-03-26 17:42 | 2024-03-27 | 1 | 0 | 1 | 2024-03-28 | 2024-04-05 | 7 | 0 | 7 | [20 empty] | 2024-04-09 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | HANSON | 601957 | 2341 | 10 | Solar | 07_797W24 | 2024-04-11 12:45 | 2024-04-12 | 1 | 0 | 1 | 2024-04-16 |  | 0 | 0 | 0 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | EAST BRIDGEWATER | 598236 | 2333 | 10 | Solar | 07_797W42 | 2024-04-15 09:54 | 2024-04-16 | 0 | 0 | 0 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | BROCKTON | 600629 | 2302 | 11.4 | Solar | 07_797W42 | 2024-04-12 15:31 | 2024-04-16 | 0 | 0 | 0 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | BELCHERTOWN | 597730 | 1007 | 13.8 | Solar | 09_509L2 | 2024-03-18 18:00 | 2024-03-19 | 2 | 0 | 2 | 2024-03-21 | 2024-04-11 | 16 | 9 | 7 | [24 empty] | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | BROCKTON | 597159 | 2301 | 5 | Solar | 07_98W10 | 2024-04-05 17:38 | 2024-04-08 | 6 | 3 | 3 | [29 empty] | EXP | [9 empty] | Application |  | No
National Grid | PEMBROKE | 601823 | 2359 | 6 | Solar | 07_910W52 | 2024-04-15 12:25 | 2024-04-16 | 0 | 0 | 0 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | BROCKTON | 587972 | 2301 | 6.67 | Solar | 07_98W46 | 2024-03-19 11:24 | 2024-03-20 | 4 | 0 | 4 | 2024-03-26 |  | 15 | 11 | 4 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | BROCKTON | 602397 | 2301 | 6 | Solar | 07_911W13 | 2024-04-10 11:33 | 2024-04-11 | 3 | 0 | 3 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | BROCKTON | 598320 | 2301 | 10 | Solar | 07_911W25 | 2024-03-26 17:33 | 2024-03-27 | 4 | 0 | 4 | 2024-04-02 |  | 10 | 8 | 2 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | EASTON | 598992 | 2375 | 30 | Solar | 07_98W48 | 2024-03-22 17:54 | 2024-03-25 | 12 | 9 | 3 | 2024-04-10 |  | 4 | 0 | 4 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | BROCKTON | 597382 | 2301 | 6 | Solar | 07_98W49 | 2024-03-29 14:38 | 2024-04-01 | 3 | 0 | 3 | 2024-04-04 |  | 8 | 0 | 8 | [24 empty] | EXP | [9 empty] | Screening |  | No
National Grid | BROCKTON | 596006 | 2302 | 13.05 | Solar | 07_911W56 | 2024-03-21 17:39 | 2024-03-22 | 2 | 0 | 2 | 2024-03-26 | 2024-03-29 | 4 | 0 | 4 | [20 empty] | 2024-04-05 |  | 2025-04-11 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | BROCKTON | 596891 | 2302 | 9.8 | Solar | 07_911W56 | 2024-03-21 17:52 | 2024-03-22 | 16 | 12 | 4 | 2024-04-16 |  | 0 | 0 | 0 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | BROCKTON | 600594 | 2302 | 15.2 | Solar | 07_911W56 | 2024-03-29 16:05 | 2024-04-01 | 11 | 9 | 2 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | ABINGTON | 553916 | 2351 | 10 | Solar | 07_99W62 | 2024-04-03 17:42 | 2024-04-04 | 3 | 0 | 3 | 2024-04-09 |  | 5 | 0 | 5 | [20 empty] | 2023-09-15 |  |  |  | EXP | [9 empty] | Screening |  | Yes
National Grid | WILLIAMSTOWN | 602572 | 1267 | 17.6 | Solar | 09_1003W1 | 2024-04-08 17:24 | 2024-04-09 | 5 | 1 | 4 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | BROCKTON | 594316 | 2301 | 5 | Solar | 07_911W59 | 2024-04-01 17:49 | 2024-04-02 | 10 | 7 | 3 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | BROCKTON | 598335 | 2301 | 3.8 | Solar | 07_911W59 | 2024-04-04 11:43 | 2024-04-05 | 2 | 0 | 2 | 2024-04-09 |  | 5 | 0 | 5 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | BROCKTON | 590208 | 2302 | 10 | Solar | 07_911W77 | 2024-04-11 17:51 | 2024-04-12 | 2 | 0 | 2 | 2024-04-16 |  | 0 | 0 | 0 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | BROCKTON | 599815 | 2302 | 10 | Solar | 07_911W77 | 2024-03-29 11:12 | 2024-04-01 | 4 | 0 | 4 | 2024-04-05 |  | 7 | 0 | 7 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | GRANBY | 602089 | 1033 | 6 | Solar | 09_527L1 | 2024-04-11 14:43 | 2024-04-12 | 2 | 0 | 2 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | GRANBY | 595501 | 1033 | 10 | Solar | 09_527L1 | 2024-03-27 10:13 | 2024-03-28 | 3 | 0 | 3 | 2024-04-02 |  | 10 | 2 | 8 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | GRANBY | 598591 | 1033 | 10 | Solar | 09_527L1 | 2024-03-27 08:20 | 2024-03-28 | 13 | 10 | 3 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | STOUGHTON | 595908 | 2072 | 10 | Solar | 07_913W67 | 2024-03-18 13:38 | 2024-03-19 | 1 | 0 | 1 | 2024-03-20 | 2024-03-22 | 3 | 0 | 3 | [20 empty] | 2024-03-25 |  | 2025-03-27 |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | STOUGHTON | 593534 | 2072 | 9.765 | Solar | 07_913W69 | 2024-03-18 13:53 | 2024-03-19 | 20 | 17 | 3 | [29 empty] | EXP | [9 empty] | Application |  | No
National Grid | STOUGHTON | 598040 | 2072 | 7.6 | Solar | 07_913W69 | 2024-03-22 09:32 | 2024-03-25 | 2 | 0 | 2 | 2024-03-27 | 2024-03-28 | 2 | 0 | 2 | [20 empty] | 2024-04-01 |  |  |  | EXP | [9 empty] | Completion Documents |  | Yes
National Grid | SCITUATE | 600721 | 2066 | 27.6 | Solar | 07_915W36 | 2024-03-31 15:17 | 2024-04-01 | 2 | 0 | 2 | 2024-04-03 | 2024-04-05 | 3 | 0 | 3 | [20 empty] | 2024-04-12 |  |  |  | EXP | [9 empty] | Conditional Approval |  | No
National Grid | SCITUATE | 601761 | 2066 | 30 | Solar | 07_915W82 | 2024-04-04 11:28 | 2024-04-05 | 2 | 0 | 2 | 2024-04-09 |  | 5 | 0 | 5 | [24 empty] | EXP | [9 empty] | Screening |  | No
National Grid | GREAT BARRINGTON | 597196 | 1230 | 6 | Solar | 09_1109W1 | 2024-03-20 08:57 | 2024-03-21 | 1 | 0 | 1 | 2024-03-22 | 2024-03-27 | 4 | 0 | 4 | [20 empty] | 2024-03-28 | 2024-03-22 11:06 |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | BARRE | 596912 | 1005 | 7.6 | Solar | 09_604W4 | 2024-03-22 11:06 | 2024-03-25 | 3 | 0 | 3 | 2024-03-28 | 2024-04-01 | 3 | 0 | 3 | [20 empty] | 2024-04-04 | 2024-03-19 21:25 | 2025-04-09 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | SOUTH EGREMONT | 597071 | 1258 | 10 | Solar | 09_1109W2 | 2024-03-19 21:25 | 2024-03-20 | 4 | 3 | 1 | 2024-03-26 | 2024-04-01 | 6 | 4 | 2 | [20 empty] | 2024-04-04 |  | 2025-04-05 | Yes | EXP | [9 empty] | Design |  | Yes
National Grid | GREAT BARRINGTON | 599630 | 1230 | 8.41 | Solar | 09_1109W2 | 2024-04-05 09:05 | 2024-04-08 | 5 | 0 | 5 | 2024-04-16 |  | 0 | 0 | 0 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | SHEFFIELD | 599473 | 1257 | 11.4 | Solar | 09_1109W2 | 2024-03-26 13:20 | 2024-03-27 | 12 | 10 | 2 | 2024-04-12 |  | 2 | 0 | 2 | [24 empty] | EXP | [9 empty] | Screening |  | No
National Grid | ALFORD | 603142 | 1230 | 20 | Solar | 09_1109W3 | 2024-04-10 19:20 | 2024-04-11 | 3 | 1 | 2 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | MILFORD | 600151 | 1757 | 5.76 | Solar | 05_335W4 | 2024-04-01 17:34 | 2024-04-02 | 2 | 0 | 2 | 2024-04-04 | 2024-04-10 | 5 | 0 | 5 | [20 empty] | 2024-04-11 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | FOXBOROUGH | 601533 | 2035 | 7.6 | Solar | 05_3422W3 | 2024-04-04 14:49 | 2024-04-05 | 7 | 3 | 4 | [29 empty] | EXP | [9 empty] | Application |  | No
National Grid | REHOBOTH | 600188 | 2769 | 10 | Solar | 05_3J3 | 2024-03-29 12:25 | 2024-04-01 | 3 | 2 | 1 | 2024-04-03 | 2024-04-12 | 9 | 4 | 5 | [24 empty] | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | NORTON | 586858 | 2766 | 6 | Solar | 05_4L2 | 2024-04-05 18:08 | 2024-04-08 | 3 | 0 | 3 | 2024-04-11 | 2024-04-15 | 3 | 0 | 3 | [20 empty] | 2024-04-15 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | SEEKONK | 596128 | 2771 | 7.6 | Solar | 05_7L1 | 2024-03-18 13:51 | 2024-03-19 | 1 | 0 | 1 | 2024-03-20 | 2024-03-25 | 5 | 2 | 3 | [24 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | REHOBOTH | 597739 | 2769 | 10 | Solar | 05_7L4 | 2024-03-20 12:07 | 2024-03-21 | 18 | 16 | 2 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | ATTLEBORO | 598260 | 2703 | 10 | Solar | 05_9L2 | 2024-03-29 14:56 | 2024-04-01 | 11 | 9 | 2 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | SEEKONK | 603824 | 2771 | 15.2 | Solar | 05_9L5 | 2024-04-15 05:16 | 2024-04-16 | 0 | 0 | 0 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | FLORENCE | 600071 | 1062 | 5 | Solar | 09_909W4 | 2024-04-02 10:08 | 2024-04-03 | 1 | 0 | 1 | 2024-04-04 | 2024-04-11 | 6 | 0 | 6 | [20 empty] | 2024-04-12 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LYNN | 591993 | 1902 | 7.6 | Solar | 12_12J903 | 2024-03-26 12:55 | 2024-03-27 | 1 | 0 | 1 | 2024-03-28 | 2024-04-01 | 3 | 0 | 3 | [24 empty] | EXP | [9 empty] | Supplemental Review |  | Yes
National Grid | MALDEN | 595219 | 2148 | 5 | Solar | 12_16W1 | 2024-03-26 11:27 | 2024-03-27 | 2 | 0 | 2 | 2024-03-29 |  | 12 | 9 | 3 | [24 empty] | EXP | [9 empty] | Screening |  | No
National Grid | REVERE | 600326 | 2151 | 6 | Solar | 12_16W4 | 2024-04-05 14:07 | 2024-04-08 | 5 | 2 | 3 | [29 empty] | EXP | [9 empty] | Withdrawn |  | Yes
National Grid | MELROSE | 600609 | 2176 | 6 | Solar | 12_16W6 | 2024-04-04 11:52 | 2024-04-05 | 4 | 0 | 4 | 2024-04-11 |  | 3 | 0 | 3 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | MALDEN | 596663 | 2148 | 5 | Solar | 12_16W7 | 2024-04-12 10:41 | 2024-04-16 | 0 | 0 | 0 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | REVERE | 588803 | 2151 | 6 | Solar | 12_16W8 | 2024-04-09 15:55 | 2024-04-10 | 4 | 0 | 4 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | MEDFORD | 598869 | 2155 | 6.08 | Solar | 12_17J4 | 2024-03-29 10:35 | 2024-04-01 | 11 | 9 | 2 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | SAUGUS | 600347 | 1906 | 7.6 | Solar | 12_19W1 | 2024-04-12 11:33 | 2024-04-16 | 0 | 0 | 0 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | SAUGUS | 597865 | 1906 | 10 | Solar | 12_19W1 | 2024-03-21 19:15 | 2024-03-22 | 2 | 0 | 2 | 2024-03-26 | 2024-04-04 | 8 | 0 | 8 | [20 empty] | 2024-04-10 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | SAUGUS | 598390 | 1906 | 6 | Solar | 12_19W1 | 2024-03-28 16:58 | 2024-03-29 | 2 | 0 | 2 | 2024-04-02 |  | 10 | 0 | 10 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | LYNN | 595928 | 1902 | 3.8 | Solar | 12_21J33 | 2024-03-25 15:27 | 2024-03-26 | 2 | 1 | 1 | 2024-03-28 | 2024-03-29 | 2 | 0 | 2 | [20 empty] | 2024-04-01 |  | 2025-04-04 |  | EXP | [9 empty] | Meter Installation |  | Yes
National Grid | LYNN | 597743 | 1905 | 7.6 | Solar | 12_21J37 | 2024-04-01 12:32 | 2024-04-02 | 2 | 0 | 2 | 2024-04-04 | 2024-04-12 | 7 | 0 | 7 | [24 empty] | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LYNN | 602059 | 1902 | 11.6 | Solar | 12_22W2 | 2024-04-09 13:00 | 2024-04-10 | 1 | 0 | 1 | 2024-04-11 |  | 3 | 0 | 3 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | SAUGUS | 592548 | 1906 | 6 | Solar | 12_23W3 | 2024-04-03 15:14 | 2024-04-04 | 1 | 0 | 1 | 2024-04-05 | 2024-04-11 | 5 | 0 | 5 | [20 empty] | 2024-04-12 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | HARVARD | 597435 | 1451 | 23 | Solar | 01_201W2 | 2024-03-18 07:09 | 2024-03-19 | 8 | 6 | 2 | 2024-03-28 | 2024-03-29 | 2 | 0 | 2 | [20 empty] | 2024-04-05 |  |  |  | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | LEOMINSTER | 598939 | 1453 | 5 | Solar | 01_207W4 | 2024-03-28 16:44 | 2024-03-29 | 2 | 0 | 2 | 2024-04-02 |  | 9 | 1 | 8 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | CLINTON | 598936 | 1510 | 7.6 | Solar | 01_216W1 | 2024-04-11 15:01 | 2024-04-12 | 2 | 0 | 2 | 2024-04-16 |  | 0 | 0 | 0 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | CLINTON | 601702 | 1510 | 7.6 | Solar | 01_216W2 | 2024-04-10 12:27 | 2024-04-11 | 3 | 0 | 3 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | STOUGHTON | 597061 | 2072 | 7.6 | Solar | 07_913W43 | 2024-03-21 16:43 | 2024-03-22 | 13 | 11 | 2 | 2024-04-09 |  | 5 | 0 | 5 | [24 empty] | EXP | [9 empty] | Screening |  | Yes
National Grid | FALL RIVER | 593434 | 2721 | 7.6 | Solar | 05_115W43 | 2024-03-29 14:01 | 2024-04-01 | 4 | 0 | 4 | 2024-04-05 | 2024-04-12 | 6 | 0 | 6 | [24 empty] | EXP | [9 empty] | Conditional Approval |  | Yes
National Grid | GARDNER | 597945 | 1440 | 20 | Solar | 01_607W5 | 2024-04-11 17:11 | 2024-04-12 | 2 | 0 | 2 | [29 empty] | EXP | [9 empty] | Application |  | Yes
National Grid | STURBRIDGE | 567984 | 1518 | 6972 | Solar |  | 2024-04-15 11:03 | 2024-04-16 | 0 | 0 | 0 | [29 empty] | STD | [9 empty] | Application |  | No