## Sheet1
Tasks | 2015-12-15 | 2015-01-16 | 2015-02-16 | 2015-03-16 | 2015-04-16 | 2015-05-16 | 2015-06-15 | 2015-07-16 | 2015-08-16 | 2015-09-16 | 2015-10-16 | 2015-11-16 | 2015-12-16
State Plan | Governor's review internal QC & edits | Finalize. Steering Committee review. Field review. Set up Public R & C process. Post for public R & C (1/15/2016) | Public R & C ends 2/12/16. R & C organized. & posted. Corresponding edits to State Plan. | March 3 submission. |  |  | Plan feedback from USDOL. | Plan in effect. Revisions per DOL?
State MOU | Internal QC & edits | Finalize draft MOU. Post within State Plan for public R & C. Publish for process. SC approval? MWB approval? | Public R & C as part of SP process. Corresponding edits. | State MOU submitted within State Plan. | State MOU finalized. | State MOU fully executed.
Local MOU |  | Local review of State MOU template. Develop local MOU template. | Local MOU Policy draft and field R & C. | MOU Template issued as policy. Local partners convene/discuss/agree. | Negotiate shared costs and infrastructure contributions. | Finlaize local MOUs. | Local MOUs fully executed.
Regional Assignment | Policy draft - internal R & C. Posted for local R & C. | Regional consultations. | Regions/Policy finalized. | MA regions included in State Plan. |  | Convene regional planning team meetings.
Regional Planning |  |  |  | Establish regional relationships. | Local regional convening & strategizing begins. | Local regional activities continue. | Local regional activities continue. | Local regional activities continue. | Local regional activities continue. | Local regional activities continue. | State posts regional planning policy guidance. | Local regions begin work on regional planning. | Regional Plans will be effective July 2017.
Local Annual Plans |  | Develop Local Plan Policy guidance incl. local submission content. | Field R & C. Corresponding edits. Policy guidance posted. | Field prep Local Plan package. DCS & Partners develop review tool & process; recruit reviewers. | Local Plans due:______ State review begins. Narrative. Fiscal Performance | Review teams, read, compile questions. Local response, clarification. | Review finalized. Local Plans approved. | Local Plans in effect.
One-Stop Certification Standards | Workgroup finalizes OSCC Cert. standards. | OSCC Cert. Policy developed. . | Field R & C. Corresponding edits. Policy guidance posted. | Field prep for application of standards, review of OSCC submissions.
One-Stop Competitive Selection | Workgroup finalizes OSCC competitive selection standards. | Competitive selection policy guidance developed. State site visits for guidance on area-specific issues. | Policy guidance posted. DCS provides Q & A/TA. Local RFPs issued. | Local RFPs issued, due dates will vary. | RFP in process. | RFP in process. | RFP in process. | OSCC operator bids due. Local selection committees, including Partners, convene. Review process finalized. | OSCC Operator proposal review begins. | Selection committee proposal review and site visits. | Selection committee proposal review and site visits. | OSCC Operator Selection finalized. | Where applicable, OSCC Operator transitions begin. DCS TA.
Workforce Board Certification | Workgroup finalizes Local Board Cert. standards. | Local Board Cert. Policy developed. . | Field R & C. Corresponding edits. | Local Board Certification Policy guidance posted. | Local Boards prep cert. packages. Revise Board/CEO agreements. Revise By-Laws. | Local Boards prep cert. packages. | LBs prep cert. packages. | Local Board Certification packages due:___ | DCS & Partner review of Local Board packages - Q & A. | Finalize DCS & Partner review of Board Packages. Approvals finalized. Approval letters generated. | New Workforce Board Biennial Certification period begins.
Performance | Workgroup finalizes state goals. | Partner proposed performance goals for federal measures. Proposed state perf. Goals for Plan. | Begin discussion on common intake process and I.D. of shared customers. | Required performance data submitted in State Plan. | Performance discussions continue re: system impacts. | Performance discussions continue re: system impacts. | Performance discussions continue re: system impacts. | FY17 WIOA performance begins. |  |  |  | First WIOA Quarterly Report with new measures.
RED FONT INDICATES DECISION REQUIRED