## Sheet1
FY 2023 BoS CoC NOFO Response Timeline |  |  |  | 08.02.23
Item | Dates in bold are required by the NOFO | Who Responsible | Done | Comments
Complete
In progress
NOFO Release | 08.01.22 | HUD | X
Applications available in e-snaps; instructions available at HUD website | 07.28.23 | HUD |  | CoC Program Competition ¦ HUD.gov / U.S. Department of Housing and Urban Development (HUD)
Review NOFO-relevant webinars as they become available | TBD | Interested parties |  | CoC Program Competition ¦ HUD.gov / U.S. Department of Housing and Urban Development (HUD)
Applications in e-snaps ready for subrecipients | TBD | Joanna
Renewal Application Excerpts and Instructions sent to Subrecipients | 07.11.23 | Karen
Meeting to review NOFO changes from previous years, what is new, CoC-required tasks, discuss reallocations proposed (if any), new projects, DV projects and the Ranking and Review Tool. | 07.12.23 | Full membership |  | This is part of the monthly CoC meeting.
NOFO Kickoff meeting | 07.14.23 | HLC Team
Renewal Applications assigned to HLC Team | 07.14.23 | Karen
Project Evaluation Committee Ranking Tool Development | 07.25.23 | Committee, HLC Team |  | Ongoing meetings with intent to have final tool by 07.31
Collaborative Application assignments made | 07.31.23 | Karen
Renewal and Expansion Guidance Meeting | 08.02.23 | Karen |  | This took the place of the regular Planning Meeting
Web Posting of Competition Deadline | 08.11.23 | Karen |  | HUD requires 30 days before the competition submission deadline
Survey sent to all CoC members | 08.04.23 | Karen and Troy
Collaborative Application input due to Karen | 08.18.23 | HLC Team
Project Applications due in esnaps | 08.16.23 | Project applicants |  | These will be reviewed by HLC staff
Review applications | Ongoing as applications are submitted through final project application | HLC Team
Ranking and Review Groups created | 08.18.23 | Karen and Joanna
Final project applications and all attachments due in esnaps | 08.24.23 | Project applicants
All Applications received by CoC | 08.25.23 | Project applicants and HLC team |  | HUD requires 30 days before submission which falls on a weekend this year
Training for Ranking and Review Groups | 08.23.23 and 08.25.23 | Karen and Kelly
Ranking and Review Groups review applications | 08.28.23 - 09.06.23 | Groups
Project Evaluation Committee Meets to decide on ranking reccomendations to present to the Advisory Board | 09.07.23 | Committee, HLC Team
Advisory Board meets to review priority list options and vote on final priority listing | 09.08.23 | Advisory Board |  | Votes on all projects accepted, rejected, or reduced.
All applications accepted or rejected by CoC | 09.12.23 | Advisory Board |  | HUD requires 15 days before submission deadline
Notification of acceptance, rejection or reduction of project applications, and ranking position in the Priority Listing in writing | 09.12.23 | Karen |  | HUD requires 15 days before submission deadline
Collaborative Application draft ready for last review before Adam | 09.13.23 | Team
Final Review of Consolidated Application | 09.20.23 | Adam |  | Will be sent to Adam by 09.15.23
Full NOFA response available on CoC webpage and partner websites for public review | 09.22.23 | BoS CoC website, member websites |  | HUD requires 2 days before submission deadline
Final Consolidated Application, Priority Listings and Project Applications with additional comments from public | 09.26.23 | Karen
NOFO submitted | 09.26.23 | Karen
NOFO responses due | 09.28.23