## Slide 1
New Public Assistance Delivery Process & Grants Portal
Presented By:
MEMA Disaster Recovery Department

## Slide 2
Agenda
FEMA Public Assistance (PA) Program Refresher
Key Benefits of the New PA Delivery Process
Grants Portal
New PA Delivery Process
Project Documentation Reviews & Closeouts
Grants Portal Account

## Slide 3
The FEMA Public Assistance (PA) Program provides grant funding to eligible sub-recipients (applicants) for eligible disaster recovery related activities such as:
  Debris Removal
  Emergency Protective Measures
  Permanent Repairs or Replacement of applicant owned infrastructure
Eligible applicants typically include municipalities, state agencies, certain private non-profits, municipal light corporations, quasi-public agencies, and tribal organizations
Grant funding is awarded in the form of reimbursement as an obligated Project Worksheet (PW)
FEMA Public Assistance Program

## Slide 4
New FEMA Public Assistance Delivery Process
WHAT HASN’T CHANGED
Law
Policy
Regulations
Eligibility Criteria
WHAT HAS CHANGED
Process
Roles/Responsibilities
Tools/Templates
Takes effect for all disasters declared on or after 9/13/17

## Slide 5
Benefits
Notes: 1.) New Delivery Process has many benefits, which fall into 3 general categories
2.) Throughout presentation, these words will be displayed to show how the new process increases transparency, accountability, and consistency over the old process

## Slide 6
Web-based tool through which all FEMA project documentation and determinations will flow
Track all projects, documentation, and information through portal - live site, 24/7
Upload documentation even without disaster declaration, such as:
  Union pay policy, Insurance policy, Procurement policy, Equipment inventory list
Each applicant can have one or more registered users
  Registered users may have different roles and rights
Grants Portal
*Use with Firefox – Free Download!
Notes: 1.) Required to use grants portal for PA reimbursement
2.) Must be invited by grantee (recipient) to portal (which we will do after today’s session)

## Slide 7: Phase I – Operational Planning Objective - Identify applicant’s disaster impacts and recovery priorities
EVENT
Preliminary Damage Assessment (PDA)
DEVELOP
INITIAL
OPERATING
PROFILE
APPLICANT
BRIEFINGS
REQUEST FOR PUBLIC ASSISTANCE
(RPA)
Program Delivery Manager (PDMG)
ASSIGNED
EXPLORATORY
CALL (EC)
RECOVERY SCOPING MEETING (RSM)
CONTACT SPECIAL CONSIDERATION SPECIALISTS
AS NECESSARY
WITHIN 7 DAYS
WITHIN 21 DAYS
ESSENTIAL ELEMENTS OF
INFORMATION REQUEST (EEI)
Incomplete RSM
Complete RSM
Declaration
Initial Damage Assessment (IDA)
JFO
WITHIN 30 DAYS
Notes: 1.) Operational Planning and Initial Operating Profile: FEMA reviews the IDA/PDA information and pulls together staff. Considerations include number of staff and experience of staff for different types of projects. (Click to circle this box)
2.) JFO still opened and FEMA staff work out of JFO
3.) Special Consideration specialists determined throughout early stages of operational planning. They will be available to all applicants who need assistance and will be inserted as part of the new model process during the very beginning stages. (click to circle this box)
4.) RPA is first look into grants portal/New PADM process (click to circle this box)

## Slide 8
Request for Public Assistance (RPA)
RPA is formal acknowledgement of applicant’s intent to request reimbursement from the FEMA PA program
RPA’s must be completed and submitted electronically in Grants Portal within 30 days of declaration

## Slide 9
The Program Delivery Manager (PDMG)
PDMG is primary FEMA POC for applicant
Works closely with state program coordinators
Each PDMG assigned 5-7 applicants*
Assigned after RPA is approved by FEMA
Works at Joint Field Office (JFO)
Key PDMG responsibilities:
  Conduct Meetings
  Assist with documentation upload into portal
  Grants Portal troubleshooting
  Coordinate between FEMA staff, state staff, and applicant
  Request site inspections
  Identify and troubleshoot any/all questions or concerns
Notes: 1.) State Program Coordinator works closely with PDMG
2.) 5-7 applicants dependent on size and scope of disaster

## Slide 10
FEMA developed roles, responsibilities, and performance expectations for FEMA PDMG’s
FEMA’s Position Assists
Notes: 1.) FEMA Position Assist packet breaks down employee roles, responsibilities, and requirements.
2) Built-in performance expectations to each position, through TFL and grants manager
(Click twice to reveal “consistency” and “accountability” pics)

## Slide 11
Exploratory Call (EC)
PDMG conducts Exploratory Call within 7 days of applicant assignment and it is designed to:
  Introduce the PDMG to the applicant
  Discuss damages at a high level
  Schedule date/time for Recovery Scoping Meeting
Notes: 1.) Consistent questions/dialogue across all PDMG’s
(click once for accountability photo to display)

## Slide 12
Recovery Scoping Meeting (RSM)
PDMG conducts RSM within 21 days of applicant assignment
RSM similar to ‘old model’s’ kickoff meeting
The RSM is designed to:
  Be the first formal, in person meeting between PDMG, applicant, and state
  Review and discuss all disaster related damages
  Determine need for site inspections
  Identify all potential or actual Environmental/Historic Preservation, Mitigation, and Insurance questions or concerns
  Introduce the Damage Inventory spreadsheet
  Determine Essential Elements of Information
    Comprehensive list of required documentation for each type of damage/work
  Assist with documentation upload into the Grants Portal
  Develop correspondence schedule
Notes: Many clicks to reveal all words, last click will reveal “consistency”

## Slide 13
Damage Inventory (DI)
An excel spreadsheet to log all damages
Must be submitted within 60 days of RSM (no change from previous model)
DI can be updated any time within 60 day window
DI is submitted through the Grants Portal
  The system knows when it was submitted!
    If you try to upload after the 60 day deadline, it will not work!
Notes: 1.) No more ambiguity on what damages were submitted to FEMA
2.) Permanent record of damages
3.) 60-day clock in grants portal

## Slide 14
Essential Elements of Information (EEI)
Lives in Grants Portal
Reference for required documentation
Notes: 1.) R = Requested, S = Submitted
(click once for accountability photo to display)

## Slide 15
Essential Elements of Information (EEI)
Notes: 1.) R = Requested, S = Submitted

## Slide 16: Phase II – Intake Damage and Eligibility Analysis Objective - Capture and document all the incident-related damage
SEND SITE INSPECTION WORK ORDER – WORK TO BE COMPLETED
100% WORK COMPLETED:
Routed To Consolidated Resource Center (CRC)
SEND SITE INSPECTION WORK ORDER – WORK TO BE COMPLETED
SPECIALIZED
LANE:
STANDARD
LANE:
VALIDATE AND DEVELOP DDD, SOW AND COSTS
PROGRAM COMPLIANCE REVIEW
PDMG THEN RECIPIENT REVIEWS DDD, SOW AND COSTS
SITE INSPECTION – applicant signs off in field
PDMG REVIEWS SITE INSPECTION REPORT (SIR) & DDD
SITE INSPECTION – applicant signs off in field
PDMG REVIEWS SITE INSPECTION REPORT (SIR) & DDD
DETERMINATION MEMO
DETERMINATION MEMO
NO
NO
YES
YES
APPLICANT REVIEWS & SIGNS PROJECT
APPLICANT REVIEWS & SIGNS
DDD
CONTACT SPECIAL CONSIDERATION SPECIALISTS AS NECESSARY
100% WORK COMPLETED LANE:
DDD = Damage Description and Dimensions SOW = Scope of Work
ELIGIBLE?
ELIGIBLE?

## Slide 17
COMPLETED WORK
STANDARD
CRC Lanes
WORK 100% COMPLETE
All documentation submitted
Projects move quickly through this lane
WORK TO BE COMPLETED
Site inspections
Projects written based on estimate by CRC
FEMA no longer treating all projects as equal
3 Lanes allow for efficient approach to project formulation and review
SPECIALIZED
WORK TO BE COMPLETED
Complex Projects/Technical Expertise
Site inspections
Projects written based on estimate by CRC
Notes: 1.) FEMA estimates based on applicant’s estimates (from backup) or FEMA cost estimating tools

## Slide 18
Site Inspections (SI)
PDMG will schedule site inspections for all work incomplete at time of RSM
  State Program Coordinator may attend SI
A site inspector will be dispatched to meet with applicant and view incomplete work
  SI records detailed information
    Latitude/Longitude
    Photos
    Dimensions of damage
Report of all damage will be created from each site inspection
Report must be reviewed and approved in Grants Portal by PDMG and applicant

## Slide 19: Consolidated Resource Center (CRC)
CRC’s employ full time project writing staff
Projects formulated from Damage Inventory sheet Damages logically grouped
For WORK 100% COMPLETE, CRC’s will write Damage, Description, and Dimensions (DDD) and Scope of Work (SOW) based upon information in Grants Portal
For WORK TO BE COMPLETED, Site Inspector will write DDD; CRC writes SOW
FEMA reviews will be conducted at CRC
Applicant signs off (approve) project(s) after development and validation at CRC
Notes: 1.) Damages logically grouped into projects by geographic location, department, complete versus incomplete work, type of work
2.) Applicant approval should be final step before project obligation

## Slide 20: Phase III – Scoping and Costing Objective - Validate WORK TO BE COMPLETED projects
CONTACT SPECIAL CONSIDERATIONS AS NECESSARY
FEMA
APPLICANT
APPLICANT
FEMA DEVELOPS SOW/COSTS
APPLICANT DEVELOPED SOW/COSTS
APPLICANT DEVELOPED SOW/COSTS
STANDARD
LANE
SPECIALIZED
LANE
FEMA VALIDATES APPLICANT SOW / COSTS
FEMA VALIDATES APPLICANT SOW / COSTS
FEMA PROGRAM COMPLIANCE REVIEW
FEMA PROGRAM COMPLIANCE REVIEW
PDMG THEN RECIPIENT REVIEWS SOW AND COSTS
PDMG THEN RECIPIENT REVIEWS SOW AND COSTS
ELIGIBLE?
YES
NO
DETERMINATION MEMO
COMPLETED
LANE
APPLICANT SIGNED PW PROCEEDS TO END OF PHASE III
APPLICANT REVIEWS & SIGNS PROJECT
WORK TO BE COMPLETED
FEMA OR APPLICANT DEVELOPS SCOPE OF WORK AND COSTS?
PROJECT ENTERED INTO EMMIE BY CONSOLIDATED RESOURCE CENTER DOCUMENT INTEGRITY UNIT

## Slide 21: Phase IV – Reviews Objective - Prepare eligible projects for obligation
FEMA FINAL
REVIEW
RECIPIENT (MEMA)
REVIEW
ELIGIBILITY REVIEWS AT CRC
INITIAL
REVIEW
INSURANCE
REVIEW
MITIGATION
REVIEW
EHP
REVIEW
NO
DETERMINATION MEMO
ELIGIBLE?
YES
OBLIGATION
APPLICANT
REVIEW
PDMG
REVIEW
Approvals

## Slide 22
Determination Memo (DM)
Determination Memo – A detailed explanation of ineligible costs/activities
DM’s outline ineligible costs from what was requested by applicant
DM’s include:
  Overview of eligibility concern
  Explanation of law, policy, regulation
  Application of law, policy, regulation to specific eligibility concern(s)
  Decision
Request for Information (RFI)
RFI’s drafted by CRC if missing information/documentation
Sent to PDMG with time limit to obtain information
PDMG requests information from applicant

## Slide 23
Large Project Closeouts
Large, long term projects will be closed out by FEMA Region 1, (thru MEMA)
Recovery Transition Meeting
Applicant documentation will still be uploaded into Grants Portal
FEMA Regional staff will award final project funding

## Slide 24
Initial Applicant Account Creation
Invitation e-mails will be sent after the completion of the trainings
All e-mails come from support@pagrants.fema.gov; please check your junk/spam folder if you do not receive an invite in your inbox
Grants Portal runs best on Firefox, free download available

## Slide 25: You will receive an e-mail from support@pagrants.fema.gov inviting you to join Grants Portal:
Your E-mail
Your Name
Subject:
1.

## Slide 26: Use the “click here” link provided in the email to fill in your info and hit “submit” in the lower left of screen 5 to register your organization:
2.
Your Organization’s Name
Only boxes with * are required

## Slide 27: You will receive an email from support@pagrants.fema.gov notification that your request was initiated:
3.
Subject:
Your E-mail
Your Name

## Slide 28: Once approved, you will receive an email from support@pagrants.fema.gov with your Username (email) and a Temporary Password generated by the system:
4.
Subject:
Your E-mail
Your Name
Your E-mail
System Generated

## Slide 29: Use the “click here” link in the email to sign in with your Username and Temporary Password provided. Once in the portal, you will be prompted to change your password, create a security question, and finalize your account:
5.
Your E-mail
Create your own password

## Slide 30
Adding Additional Applicant User Accounts Within Your Organization

## Slide 35
FEMA’s New Public Assistance Delivery Process & Grants Portal
Thank you!
Questions?
FEMA Help Desk:
866-337-8448
Disaster.recovery@state.ma.us